## Sheet1
ID* | Name* | Location | C55 | Project Status | Alectra Status | Alectra Sub-status | Priority | Impact | Year | Design Supervisor | Responsible Manager | Job Pkg Rec'd Date | Planned Units Number | Actual Units Number | Planned Total Cost | Actual Total Cost | Original Budget | Current Budget | Project Owner | Contractor | Anticipated Finish | Scheduled Finish | Anticipated Start | Construction Actual Start Date | Construction Actual Finish Date | Start Delay? | Finish Delay? | RFC Design Approval Date | RFC Amount
9000 | 9000 Templates | [9 empty] | Templates |  |  |  | 0 | 0 |  | 0
Alectra - SW | Alectra Template - SouthWest | 840 - Southgate |  | Template | 10 | ACTIVE |  |  | 2021 |  | Templates |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 02-Jan-20
Project - Alectra Template | Alectra Template - Alectra | 815 - Addiscott |  | Template | 10 | ACTIVE |  |  | 2023 |  | Templates |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Jan-20
Alectra | Alectra Utilities | [9 empty] | Alectra Utilities |  | 3,631.00 | 2,229.00 | 873662067.55 | 693132398.7 | 302196031 | 302196031 | [5 empty] | 16-Nov-15 | 30-Oct-23
P6JDE | P6JDE Integration Template | 800 - Mavis |  | What If | 10 | ACTIVE |  |  | 2023 |  | P6JDE Interface Admin |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
WEST | West Region (Horizon) | [9 empty] | West |  | 813 | 429 | 181314738.44 | 158923492.68 | 52660297 | 52660297 | [5 empty] | 16-Nov-15 | 20-Jul-23
636451 | FOOTHILLS OF WINONA - SERVICE ADDITIONS/RE-LOCATIONS | 820 - Nebo | 151653 | Active | 95 | COMPLETE |  |  | 2022 | Gamboa, Henry | Morris, Mark | 02-Mar-21 |  |  | 58541.53 | 51813.95 | 58541.53 | 58541.53 | Roy Owen |  | 23-Apr-21 | 26-Jul-23 | 19-Apr-21 | 08-Oct-21 | 21-Jan-22 | Customer | Customer |  | 0
636686 | 2023 - SPOT POLE REPLACEMENTS #2 - 5 POLES | 830 - St. Catharines | 150335 | Active | 93 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 30-Mar-23 | 5 | 5 | 94806.67 | 43463.28 | 94806.67 | 94806.67 | Macdougall, Stephen |  | 03-Jul-23 | 26-Jul-23 | 01-Jun-23 | 25-May-23 | 16-May-23 |  |  |  | 0
635328 | NEWTON 282X - PART 2 | 820 - Nebo | 151452 | Active | HL | RELEASED |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 27-Aug-20 |  |  | 110343.36 | 75496.03 | 110343.36 | 110343.36 | Tony Ierace |  | 04-Dec-20 | 26-Jul-23 | 23-Nov-20 |  |  | Materials | Materials |  | 0
635012 | CABLE INJECT - RYMAL/MUD/CENTENNIAL | 820 - Nebo | 151302 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 1186.09 |  | 0 | Brad Carr |  |  | 26-Jul-23
636549 | 179 LOUTH ST, ST.CATHARINES | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE | High | Res-ICI | 2021 | Paesano, Andrew | Laus, Tomislav | 25-Sep-20 |  |  | 94217.28 | 65723.87 | 94217.28 | 94217.28 | Frank Giancola | Wiens | 16-Nov-20 | 26-Jul-23 | 02-Nov-20 | 16-Oct-20 | 08-Apr-21 | Customer | Customer |  | 0
452008 | 690 Rennie St | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2021 | Paesano, Andrew | Dragojevic, Igor | 25-May-20 |  |  | 60683.38 | 72232.38 | 54032.43 | 60683.38 | Macdougall, Stephen |  | 07-Jul-20 | 26-Jul-23 | 29-Jun-20 | 31-Aug-21 | 13-Dec-21 | Customer | Customer |  | 6,650.95
451653 | MARSDALE DR. REARLOT REBUILD | 830 - St. Catharines | 150496 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 29559.53 |  | 0 | Weaver, Thomas |  |  | 26-Jul-23
636315 | 535 UPPER KENILWORTH AVE - BERNIE ARBOUR STADIUM | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Patel, Ketan | 02-Feb-21 |  |  | 20720.76 | 21980.17 | 20720.76 | 20720.76 | Roy Owen |  | 11-Mar-21 | 30-Jan-23 | 08-Mar-21 | 19-Jan-21 | 25-May-21 |  | Customer |  | 0
451477 | SILVERWOOD HOMES PHASE 1C - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 01-Jun-21 |  |  | 9008.43 | 12193.23 | 9008.43 | 9008.43 | Roy Owen |  | 08-Mar-22 | 27-Jan-23 | 07-Mar-22 | 29-Apr-22 | 17-May-22 | Customer | Customer |  | 0
451279 | 281/283 St Paul St | 830 - St. Catharines | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Dragojevic, Igor | 15-Jun-17 |  |  | 50238.2 | 49397.06 | 41287.71 | 50238.2 | Brad Carr |  | 01-Feb-22 | 26-Sep-22 | 01-Feb-22 | 25-Sep-17 | 01-Nov-22 | Customer | Customer |  | 8,950.49
452169 | Lakeport Rd , St. Catharines | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Aug-22
452182 | Hastings St, St. Catharines | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Aug-22
635601 | REBUILD: W 31ST, BTWN ANGELA AVE & LESLIE AVE (HAMILTON) - 9 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-20 | 9 | 9 | 117533.97 | 150356.25 | 87517.09 | 117533.97 | Koeppe, Jeffrey |  | 23-Dec-21 | 22-Aug-22 | 22-Nov-21 | 02-Dec-21 | 01-Feb-22 | Locates | Locates |  | 30,016.88
636624 | ELMA ST - 2021 CABLE REPLACEMENT | 830 - St. Catharines | 151287 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 30-Nov-20 |  |  | 932034.5 | 962765.1 | 906775.12 | 932034.5 | Dan Despres | B&M | 19-Aug-21 | 08-Jun-22 | 12-Apr-21 | 12-Apr-21 | 08-Nov-21 |  | Contractor |  | 25,259.38
635938 | WATERDOWN - 3RD FEEDER SUBDIVISION WORK | 820 - Nebo | 150390 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Anderson, Dean | 20-Jul-20 |  |  | 501879.07 | 509573.07 | 501879.07 | 501879.07 | Brad Carr | Transpw | 23-Oct-20 | 04-Oct-21 | 05-Oct-20 | 22-Mar-21 | 19-Apr-21 | Contractor | Contractor |  | 0
451906 | 396 Acadia Dr, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 1566.12 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 15-Jul-21 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
635627 | POLE RESIDUAL 2021 PH1 - 11 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 01-May-20 | 11 |  | 157373.91 | 156595.29 | 157373.91 | 157373.91 | Dan Despres |  | 12-Apr-21 | 05-Jul-21 | 01-Mar-21 | 08-Jan-21 | 08-Feb-21 |  |  |  | 0
451854 | 2018 NRBN Permit Review | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 13-Mar-19 |  |  | 0 | 2021.28 |  | 0 | Weaver, Thomas |  | 13-Mar-19 | 19-Apr-21 | 13-Mar-19 | 13-Mar-19 | 13-Mar-19
451343 | Stroud Lane 4 Conversion (2018) | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Wardell, Paul | 04-Sep-18 |  |  | 124400.98 | 145666.4 | 124400.98 | 124400.98 | Andrew Mehlenbacher |  | 07-Dec-18 | 31-Dec-20 | 09-Oct-18 | 10-Apr-19 | 15-Aug-19 | MC/PUCC Permit | Lines |  | 0
633210 | 224 - 228 GLENDALE AVE | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 05-Sep-19 |  |  | 93157.83 | 70861.81 | 93157.83 | 93157.83 | Frank Giancola | Wiens | 17-Oct-19 | 23-Nov-20 | 07-Oct-19 | 06-Sep-19 | 11-Sep-19 |  | Customer |  | 0
451102 | 30 Milton Ave Large Load Move | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Johnson, William | 28-May-19 |  |  | 0 | 3920.26 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 19-Nov-20 | 28-May-19 | 28-May-19 | 28-May-19
632838 | 51 Sulphur Springs Rd | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Sabbah, Amir | 03-Sep-19 |  |  | 5310.16 | 3690.21 | 5310.16 | 5310.16 | Koeppe, Jeffrey |  | 30-Sep-19 | 24-Aug-20 | 30-Sep-19 | 17-Sep-19 | 17-Sep-19 |  |  |  | 0
451754 | 34 Malton Dr, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 2581.07 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 24-Aug-20 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
636668 | LAKESHORE STANLEY PARNELL - CABLE REPLACEMENT | 830 - St. Catharines | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636002 | 11-15 CANNON ST W - UG | 820 - Nebo | 150449 | Active | 40 | ACTIVE | VerHigh | Res-ICI | 2023 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636065 | EMERGING OH INSULATOR REPLACEMENT 2022 - HORNING M11 | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
632677 | OTTAWA AND CAMPBELL ALLEY | 820 - Nebo | 150496 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 30-Jul-19
451543 | 7 Everton Crt | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Oct-17
451407 | 488 Rymal Rd E, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 11-Jul-17
451209 | 461 King St. E - Service Relocation | 820 - Nebo | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Koeppe, Jeffrey |  |  | 16-Nov-15
636338 | 57 CARLISLE ST, ST.CATHARINES - PHASE 1 | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2021 | Frigotto, Rodrigo | Laus, Tomislav | 22-Jul-21 |  |  | 87887.75 | 63014.25 | 87887.75 | 87887.75 | Frank Giancola |  | 01-Sep-21 | 26-Jul-23 | 23-Aug-21 | 06-Aug-21 | 30-Aug-21 |  |  |  | 0
635013 | CABLE INJECT - MILLEN/BARTON/FRUITLAND | 820 - Nebo | 151300 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 31-Dec-19 |  |  | 245280.09 | 849268.67 | 245280.09 | 245280.09 | Brad Carr | Nvinium | 17-Dec-21 | 26-Jul-23 | 03-Sep-21 | 04-Oct-21 | 26-Jul-22 | Contractor | Contractor |  | 0
636685 | EMERGING OH INSULATOR REPLACEMENT 2022 - LAKE M81 | 820 - Nebo | 150496 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 30-Jun-22 |  |  | 34623.2 | 42552.62 | 34623.2 | 34623.2 | Macdougall, Stephen |  | 26-Oct-22 | 30-May-23 | 17-Oct-22 | 24-Aug-22 | 02-Dec-22 |  | Filler |  | 0
635715 | MH2163 SEWERING | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Biggs, Scott | Jolie, Chris | 29-Jul-21 |  |  | 66450.31 | 56242.99 | 106297.41 | 66450.31 | Brad Carr | B&M | 24-Sep-21 | 22-Sep-22 | 20-Sep-21 | 24-Aug-21 | 26-Aug-21 |  |  |  | -39,847.10
636625 | WEIDEN CABLE REPLACEMENT | 830 - St. Catharines | 151282 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 10-Nov-20 |  |  | 269116.17 | 307927.71 | 238779.31 | 269116.17 | Dan Despres | Wiens | 21-Jun-21 | 22-Sep-22 | 26-Apr-21 | 12-Apr-21 | 16-Nov-21 |  | Contractor |  | 30,336.86
633200 | 446 DUNDAS ST.E - TEMP | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Oosterlinck, David | 04-Nov-19 |  |  | 70605.73 | 52274.02 | 70605.73 | 70605.73 | Macdougall, Stephen | Fairway | 01-Feb-22 | 22-Sep-22 | 01-Feb-22 | 09-Dec-19 | 11-Mar-22 | Locates | Customer |  | 0
636688 | 121 KING ST E - GORE PARK LOFTS | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2022 | Kappheim, Adam | Sabbah, Amir | 22-Jun-21 |  |  | 44461.24 | 0 | 44461.24 | 44461.24 | Roy Owen |  | 23-Aug-21 | 22-Sep-22 | 20-Aug-21 | 20-Oct-21 | 14-Nov-22 | Customer | Customer |  | 0
635932 | RYMAL RD WIDENING - CITY OF HAMILTON - PHASE 2 | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE | High | Infrast | 2022 | Jakubowski, Mark | Celic, Dusan | 10-Nov-20 |  |  | 880044.16 | 885834.81 | 925685.1 | 880044.16 | Koeppe, Jeffrey | K-Line | 18-Aug-21 | 14-Sep-22 | 23-Dec-20 | 07-Dec-20 | 18-May-22 |  | N/A |  | -45,640.94
635534 | JOINT USE PERMIT HW2020-002 - CROCKETT, E24, QUEENSDALE E - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jul-20 |  |  | 20856.28 | 54238.85 | 20856.28 | 20856.28 | Macdougall, Stephen |  | 30-Nov-20 | 22-Aug-22 | 02-Nov-20 | 08-Feb-21 | 19-Apr-21 | Filler | Filler |  | 0
451600 | Mountain URD - Phase 2 - (South) | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 19-Nov-18 |  |  | 516979.71 | 671204.05 | 532011.16 | 516979.71 | Andrew Mehlenbacher | B&M | 29-Nov-19 | 21-Apr-22 | 04-Mar-19 | 12-Aug-19 | 26-Apr-21 | MC/PUCC Permit | Control/SCADA |  | -15,031.45
636230 | VICTORY RIDGE - PHASE 4 | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 23-Sep-20 |  |  | 115956.91 | 98461.7 | 115956.91 | 115956.91 | Brad Carr | Transpw | 27-Nov-20 | 30-Mar-22 | 16-Nov-20 | 21-Jun-21 | 15-Sep-21 | Customer | Customer |  | 0
635602 | REBUILD: LESLIE & W 32ND, N OF BENDAMERE (HAMILTON) -18 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 10-Nov-20 | 18 |  | 136045.92 | 228320.81 | 124584.75 | 136045.92 | Koeppe, Jeffrey |  | 16-Apr-21 | 14-Feb-22 | 01-Mar-21 | 22-Feb-21 | 16-Apr-21 |  |  |  | 11,461.17
632672 | 27 CLAREMONT DRIVE | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Wardell, Paul | 06-Jul-20 |  |  | 13376.76 | 19553.51 | 13376.76 | 13376.76 | Macdougall, Stephen | Fairway | 11-Sep-20 | 14-Feb-22 | 09-Sep-20 | 07-Sep-20 | 28-May-21 |  | Lines |  | 0
452007 | 40 Louth St | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 26-Aug-19 |  |  | 20175.79 | 19196.3 | 20175.79 | 20175.79 | Frank Giancola |  | 02-Oct-19 | 17-Jan-22 | 30-Sep-19 | 27-Sep-19 | 18-Oct-19 |  | Customer |  | 0
451853 | 23 Clayburn Ave | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 16-Nov-18 |  |  | 29394.95 | 25859.52 | 29394.95 | 29394.95 | Frank Giancola | Wiens | 28-Dec-18 | 17-Jan-22 | 17-Dec-18 | 06-Dec-18 | 23-Sep-19 |  | Customer |  | 0
635378 | JOINT USE PERMIT HW2019-151 - MITCHELL AND BERRYMAN - ST CATH | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jun-20 |  |  | 5895.82 | 4018.68 | 5895.82 | 5895.82 | Hewitson, Trevor |  | 30-Nov-20 | 05-Jan-22 | 02-Nov-20 | 03-Jan-21 | 03-Jan-21 | Filler | Filler |  | 0
634207 | GLOVER, BARTON, AND MCNEILLY, HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jun-20 |  |  | 17095.67 | 14463.22 | 17095.67 | 17095.67 | Hewitson, Trevor |  | 31-Dec-20 | 05-Oct-21 | 19-Oct-20 | 22-Feb-21 | 22-Feb-21 | Filler | Filler |  | 0
634492 | KAREN CRES REBUILD (HAMILTON) - 7 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 16-Dec-19 | 7 |  | 115827.63 | 99391.61 | 115827.63 | 115827.63 | Koeppe, Jeffrey |  | 08-Mar-21 | 16-Sep-21 | 01-Feb-21 | 30-Dec-20 | 26-Feb-21 |  |  |  | 0
634827 | HAMILTON 2020 POLE RESIDUALS PHASE 6 - 8 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 16-Dec-19 | 8 |  | 161821.39 | 155133.87 | 116206.58 | 161821.39 | Macdougall, Stephen |  | 30-Oct-21 | 16-Sep-21 | 06-Apr-21 | 12-Feb-21 | 28-May-21 | COVID19 | Filler |  | 45,614.81
636730 | 133 HANNOVER DR, ST.CATHARINES | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Paesano, Andrew | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 19-Jul-21
635822 | DUNDAS ST E & HAMILTON ST PMH AUTOMATION - Deep dive | 820 - Nebo | 150390 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Anderson, Dean | 15-Jul-20 |  |  | 324895.11 | 326093.87 | 324895.11 | 324895.11 | Brad Carr | K-Line | 18-Dec-20 | 15-Jul-21 | 10-Aug-20 | 18-Sep-20 | 10-Feb-21 | MC/PUCC Permit | MC/PUCC Permit |  | 0
636003 | GLENDALE TS - POLE RELOCATION | 820 - Nebo | 150570 | Inactive | 99 | COMPLETE |  |  | 2021 | Braletic, Bob | Lustrinelli, Mark | 22-Feb-21 |  |  | 65670.74 | 0 | 65670.74 | 65670.74 | Frank Giancola |  | 20-Apr-21 | 27-May-21 | 29-Mar-21 | 31-Mar-21 | 16-Apr-21 | Locates |  |  | 0
632837 | 1527 UPPER JAMES ST MAIN SERVICE REMOVAL | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Sabbah, Amir | 30-Sep-19 |  |  | 6233.1 | 3343.11 | 6233.1 | 6233.1 | Roy Owen |  | 30-Oct-19 | 25-Mar-21 | 29-Oct-19 | 30-Oct-19 | 30-Oct-19 |  |  |  | 0
451342 | 101 Shoreview Place, Stoney Creek | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 15-Nov-17 |  |  | 121554.13 | 128657.73 | 121554.13 | 121554.13 | Andrew Mehlenbacher |  | 22-Dec-17 | 22-Mar-21 | 13-Dec-17 | 21-Dec-17 | 02-May-19 |  | Customer |  | 0
451101 | Buchanan St. Pole Replacements | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | McAlpine, Robert | Webb-Murre, Paige | 08-Oct-18 |  |  | 61354.16 | 45502.46 | 61354.16 | 61354.16 | Scott Borer |  | 03-May-19 | 08-Mar-21 | 15-Apr-19 | 04-Apr-19 | 17-Jun-19 |  | Customer |  | 0
451476 | Moffat Street Reconstruction | 830 - St. Catharines | 150653 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Johnson, William | 03-Jan-18 |  |  | 644160.28 | 709733.04 | 613941.86 | 644160.28 | Dan Despres | Fairway | 17-Aug-18 | 08-Feb-21 | 19-Feb-18 | 20-Feb-18 | 31-Oct-19 | Customer | Customer |  | 30,218.42
635329 | NEWTON 282X - PART 3 | 820 - Nebo | 151452 | Active | 10 | ACTIVE |  |  | 2023 | Billone, Justin | Beaudrie, Scott |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
634918 | 285 GENEVA ST, ST.CATHARINES | 830 - St. Catharines | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636626 | BERKLEY CABLE REPLACEMENT 2022 | 830 - St. Catharines | 151295 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 24-Nov-21 |  |  | 1210731.5 | 1324393.97 | 1075687.09 | 1210731.5 | Brad Carr | B&M | 29-Jul-22 | 26-Jul-23 | 01-Mar-22 | 31-Jan-22 | 20-Jul-22 |  |  |  | 135,044.41
635174 | HAMILTON HEALTH SCIENCES - ST. PETER'S HOSPITAL. | 820 - Nebo | 150449 | Active | 91 | ACTIVE | VerHigh | Health | 2023 | Kappheim, Adam | Sabbah, Amir | 18-Oct-21 |  |  | 123767.02 | 113971.96 | 117013.54 | 123767.02 | Macdougall, Stephen | Fairway | 30-Dec-21 | 08-Aug-23 | 29-Nov-21 | 10-May-22 |  | Customer | Customer |  | 6,753.48
451852 | 869 Barton St | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 26-Apr-19 |  |  | 85638.12 | 89589.28 | 85638.12 | 85638.12 | Koeppe, Jeffrey | Fairway | 12-Jun-19 | 26-Jul-23 | 03-Jun-19 | 31-May-19 | 12-Jul-19 |  | Customer |  | 0
635639 | 223 EAST AVE N | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2022 | Kappheim, Adam | Bennett, Aaron | 26-Oct-21 |  |  | 81484.79 | 79915.16 | 81484.79 | 81484.79 | Macdougall, Stephen | Fairway | 10-Jan-22 | 22-Sep-22 | 29-Dec-21 | 24-Jan-22 | 12-Mar-22 | Customer | Customer |  | 0
635603 | REBUILD: W 31ST, N OF BENDAMERE (HAMILTON) - 7 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 10-Nov-20 | 7 |  | 127427.67 | 150279.73 | 86017.09 | 127427.67 | Koeppe, Jeffrey |  | 11-Jun-21 | 22-Aug-22 | 10-May-21 | 19-Apr-21 | 04-Jun-21 |  |  |  | 41,410.58
633562 | REBUILD: W 34TH & W 33RD STREET, N OF LESLIE AVE (HAMILTON) - 16 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 27-Nov-20 | 16 |  | 341580.3 | 320776.97 | 347796.56 | 341580.3 | Brad Carr | B&M | 21-May-21 | 22-Aug-22 | 19-Apr-21 | 19-Apr-21 | 17-Jun-21 |  | Contractor |  | -6,216.26
452006 | 304 Read Rd | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 27-May-19 |  |  | 4009.54 | 1220.83 | 4009.54 | 4009.54 | Frank Giancola |  | 08-Jul-19 | 17-Aug-22 | 08-Jul-19 | 09-Jul-19 | 09-Jul-19 | Locates | Locates |  | 0
451341 | 525 Welland Ave, st catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-Jun-22
634528 | JOINT USE PERMIT HW2019-087 - CENTRAL, HOLMESDALE, LUCERNE, SUMMERHILL, ETC - HA | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 18-Feb-21 |  |  | 20301.69 | 10320.95 | 20301.69 | 20301.69 | Hewitson, Trevor | K-Line | 30-Apr-21 | 21-Apr-22 | 22-Mar-21 | 24-Mar-21 | 24-Mar-21 | Filler |  |  | 0
635826 | COGECO BONDS - 2020 ANCASTER | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 10-Jun-20 |  |  | 3614.82 | 2418.81 | 3614.82 | 3614.82 | Hewitson, Trevor | N/A | 28-Aug-20 | 13-Jan-22 | 04-Aug-20 | 22-Feb-21 | 22-Feb-21 | Filler | Filler |  | 0
632836 | BELL MAKE READY - MANSFIELD DR | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 06-Jul-20 |  |  | 8002.9 | 4791.81 | 8002.9 | 8002.9 | Hewitson, Trevor | K-Line | 30-Oct-20 | 11-Jan-22 | 01-Oct-20 | 01-Mar-21 | 01-Mar-21 | Filler | Filler |  | 0
635945 | HAMILTON - URGENT POLE # 55818 REPLACEMENT - 1 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 28-Feb-20 | 1 |  | 40403.8 | 39947.62 | 40403.8 | 40403.8 | Brian Robinson |  | 16-Mar-20 | 21-Sep-21 | 09-Mar-20 | 08-May-21 | 09-May-21 | COVID19 | Lines |  | 0
634490 | DANBURY ST REBUILD (HAMILTON) - 4 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 16-Dec-19 | 4 |  | 51423.32 | 32267.03 | 51423.32 | 51423.32 | Koeppe, Jeffrey |  | 20-Jan-21 | 16-Sep-21 | 04-Jan-21 | 04-Jan-21 | 15-Jan-21 |  |  |  | 0
451802 | 50 Colquhoun Cres | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 27-May-19 |  |  | 8272.97 | 11370.51 | 8272.97 | 8272.97 | Scott Borer |  | 27-Jun-19 | 15-Sep-21 | 26-Jun-19 | 05-Jul-19 | 23-Jul-19 | Locates | Locates |  | 0
633198 | ROGERS MAKE READY - CONCESSION ST | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 25-Sep-19 |  |  | 6250.32 | 1328.65 | 6250.32 | 6250.32 | Hewitson, Trevor |  | 07-Nov-19 | 21-Jan-21 | 07-Nov-19 | 29-Oct-19 | 29-Oct-19 |  |  |  | 0
451100 | York to 290 Barton St W Large Move | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Johnson, William | 28-May-19 |  |  | 5408.36 | 6298.12 | 5408.36 | 5408.36 | Jakubowski, Mark |  | 28-May-19 | 14-Dec-20 | 28-May-19 | 28-May-19 | 28-May-19 |  |  |  | 0
636005 | 1 JARVIS ST | 820 - Nebo | 150449 | Active | 10 | ACTIVE | VerHigh | Res-ICI | 2023 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
451702 | 724 Queenston Rd, Stoney Creek | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Laus, Tomislav | 14-Dec-18 |  |  | 30897.29 | 36444.6 | 30897.29 | 30897.29 | Koeppe, Jeffrey |  | 21-Jan-19 | 24-Aug-20 | 14-Jan-19 | 27-Dec-18 | 10-Feb-19 |  | Customer |  | 0
636094 | 1 REDFERN AVENUE | 820 - Nebo | 150449 | Active | 50 | ACTIVE | VerHigh | Res-ICI | 2023 | Frigotto, Rodrigo | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636563 | OVERLOADED O/H TX. # 12219 AT 203 MAIN ST. PORT DALHOUSIE. ST. CATHERINES | 830 - St. Catharines | 151064 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Rolfe, Eric |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
634876 | DAKOTA PHASE 2 - TIE-IN | 820 - Nebo | 150588 | Active | 40 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
634922 | 95 HOWARD STREET SERVICE UPGRADE | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Kappheim, Adam | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
635014 | CABLE INJECT - STONE CHURCH/GARTH/LINC | 820 - Nebo | 151304 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
452180 | CNR BRIDGE CONSTRUCTION - ST. PAUL ST, ST. CATHARINES | 830 - St. Catharines | 150653 | Active | 50 | ACTIVE | High | Infrast | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas | K-Line |  | 24-Jun-19
636409 | CCRA - 191 KING STREET WEST - NEW SERVICE | 820 - Nebo | 150449 | Active | 84 | ACTIVE | VerHigh | Res-ICI | 2023 | Frigotto, Rodrigo | Sabbah, Amir | 23-Nov-22 |  |  | 257972.81 | 238143.81 | 257972.81 | 257972.81 | Macdougall, Stephen | Fairway | 24-Jan-23 | 03-Aug-23 | 12-Dec-22 | 22-Jun-23 |  | Customer | Customer |  | 0
635604 | REBUILD: W 33RD, N OF SANATORIUM (HAMILTON) - 7 | 820 - Nebo | 150335 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-20 | 7 | 7 | 132815.54 | 153475.93 | 111642.54 | 132815.54 | Koeppe, Jeffrey |  | 26-Sep-22 | 26-Jul-23 | 29-Aug-22 | 22-Sep-22 | 28-Oct-22 | Locates | Locates |  | 21,173.00
635366 | 324 PARKDALE AVE NORTH - HYUNDAI DEALERSHIP | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2021 | Paesano, Andrew | Bharosi, Mohindra | 04-Sep-20 |  |  | 120153.02 | 105931.12 | 120153.02 | 120153.02 | Macdougall, Stephen | Fairway | 22-Oct-20 | 26-Jul-23 | 28-Sep-20 | 16-Oct-20 | 01-Apr-21 | Customer | Customer |  | 0
635658 | Fruitland Rd & Lakeview Dr - DESANTIS ROSE JOINT VENTURE INC. - TEMP | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Paesano, Andrew | Bharosi, Mohindra | 13-Aug-20 |  |  | 106779.85 | 89911.44 | 106779.85 | 106779.85 | Macdougall, Stephen | Fairway | 07-Oct-20 | 09-Aug-23 | 21-Sep-20 | 04-Sep-20 | 22-Nov-22 |  | Customer |  | 0
635385 | CENTRAL CONVERSION - CE-10 & CE-2 REMOVALS | 820 - Nebo | 150352 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Wardell, Paul | 26-Feb-21 |  |  | 44122.8 | 19100.81 | 44122.8 | 44122.8 | Tony Ierace |  | 21-Sep-21 | 22-Sep-22 | 13-Sep-21 | 27-Sep-21 | 14-Jan-22 | Lines | Lines |  | 0
635015 | CABLE INJECT - BOLGER/ELMA/DOROTHY | 820 - Nebo | 151289 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 09-Mar-21 |  |  | 143796.48 | 35858.57 | 143796.48 | 143796.48 | Brad Carr | Nvinium | 24-Jun-22 | 22-Sep-22 | 30-May-22 | 10-May-22 | 30-Jun-22 | Contractor | Contractor |  | 0
636628 | 76 BUNTING RD, ST. CATHARINES - GUY-WIRE & ANCHOR RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 31-Aug-22
636495 | 10 AINTREE CRT - GUY REMOVAL | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 18-Nov-20 |  |  | 907.12 | 0 | 907.12 | 907.12 | Brad Carr | K-Line | 30-Apr-21 | 31-Aug-22 | 01-Apr-21 | 08-Jun-21 | 08-Jun-21 | Filler | Filler |  | 0
452005 | 1 Dunn St | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 06-May-19 |  |  | 8295.54 | 7474.33 | 8295.54 | 8295.54 | Frank Giancola |  | 13-Jun-19 | 17-Aug-22 | 12-Jun-19 | 24-Jul-19 | 24-Jul-19 | Customer | Customer |  | 0
452179 | 57 Lakeport Rd | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 04-Sep-19 |  |  | 20374.28 | 19431.94 | 20374.28 | 20374.28 | Frank Giancola |  | 11-Oct-19 | 01-Dec-21 | 10-Oct-19 | 18-Sep-19 | 23-Sep-19 |  | Customer |  | 0
635181 | VSM82 - AUTOMATION - 2 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 11-Aug-20 |  |  | 324838.43 | 345721.32 | 324838.43 | 324838.43 | Brad Carr | B&M | 16-Oct-20 | 04-Oct-21 | 07-Sep-20 | 05-Oct-20 | 04-Mar-21 | Contractor | Control/SCADA |  | 0
451540 | 155 Ontario St | 820 - Nebo | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | McAlpine, Robert | Morris, Mark |  |  |  | 0 | 752.24 |  | 0 | Weaver, Thomas |  |  | 15-Jul-21
635951 | POLE RESIDUAL 2021 PH 2 - BARTON ST - 8 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 13-Apr-20 | 8 |  | 118802.33 | 90287.86 | 118802.33 | 118802.33 | Dan Despres |  | 20-May-21 | 05-Jul-21 | 19-Apr-21 | 08-Feb-21 | 12-Mar-21 |  |  |  | 0
452057 | SCH 2019 Pole Residuals Phase 7 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 01-May-19 |  |  | 96776.06 | 116346.84 | 96776.06 | 96776.06 | Dan Despres |  | 31-Dec-19 | 08-Mar-21 | 06-Aug-19 | 07-Oct-19 | 13-Dec-19 | Filler | Filler |  | 0
451201 | Pole Residual – 2017 Replacement | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 20-Jun-18 |  |  | 90767.74 | 77233.2 | 90767.74 | 90767.74 | XPopiel, Joseph |  | 30-May-19 | 22-Oct-20 | 23-Jul-18 | 06-Sep-18 | 24-May-19 |  | Filler |  | 0
635592 | DELTA TRANSFORMER - VISUAL INSPECTION | 820 - Nebo | 150336 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
635386 | CENTRAL CONVERSION - NEW 5221X FEEDER | 820 - Nebo | 150352 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 18-Nov-22 |  |  | 191605.3 | 218899.84 | 191605.3 | 191605.3 | Tony Ierace | Fairway | 08-May-23 | 31-Oct-23 | 17-Apr-23 | 03-Apr-23 |  |  | Contractor |  | 0
451539 | 52 Ottawa St N, Hamilton - Temp | 820 - Nebo | 150449 | Active | 98 | COMPLETE | Medium | Infrast | 2022 | Paesano, Andrew | Laus, Tomislav | 16-Apr-19 |  |  | 118948.7 | 113919.95 | 80400.97 | 118948.7 | Macdougall, Stephen | Clrway | 01-Feb-22 | 03-Aug-23 | 01-Feb-22 | 06-Jun-19 | 29-Dec-22 | Customer | Customer |  | 38,547.73
451700 | 60/68 Centennial Pkwy S, Stny Crk | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 25-Jun-19 |  |  | 62699.64 | 64586.48 | 62699.64 | 62699.64 | Roy Owen |  | 08-Aug-19 | 26-Jul-23 | 29-Jul-19 | 29-Jul-19 | 17-Sep-19 |  | Customer |  | 0
635593 | JOINT USE PERMIT HW2020-003 - DUNKIRK, ROSEDALE, MONTROSE, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 13-Sep-21 |  |  | 22943.29 | 27781.01 | 22943.29 | 22943.29 | K-Line Construction | K-Line | 07-Mar-22 | 30-Jan-23 | 07-Mar-22 | 24-Jan-22 | 24-Jan-22 | Filler | Filler |  | 0
634503 | ST. PETERS HOSPITAL UPGRADE - CUMBERLAND AVE | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE | VerHigh | Health | 2021 | Jakubowski, Mark | Jolie, Chris | 28-Jan-21 |  |  | 759207.45 | 722719.01 | 736547.02 | 759207.45 | Brad Carr | K-Line | 22-Apr-21 | 22-Sep-22 | 08-Feb-21 | 16-Feb-21 | 10-Jun-21 | Contractor | N/A |  | 22,660.43
632381 | 291 LODOR ST - SERVICE UPGRADE | 820 - Nebo | 150456 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Sabbah, Amir | 23-Jul-21 |  |  | 52498.39 | 43282.45 | 52498.39 | 52498.39 | Macdougall, Stephen |  | 01-Sep-21 | 22-Sep-22 | 23-Aug-21 | 08-Oct-21 | 28-Mar-22 | Locates | Customer |  | 0
633504 | 350 SCOTT STREET | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Bharosi, Mohindra | 18-Oct-19 |  |  | 33830.92 | 0 | 33830.92 | 33830.92 | Frank Giancola | Wiens | 16-Dec-19 | 22-Sep-22 | 09-Dec-19 | 05-Dec-19 | 10-Dec-19 |  | Customer |  | 0
635605 | REBUILD: W 31ST, N OF SANATORIUM (HAMILTON) - 6 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-20 | 6 |  | 155333.54 | 188794.06 | 121064.6 | 155333.54 | Koeppe, Jeffrey |  | 14-Sep-21 | 22-Sep-22 | 26-Jul-21 | 26-Jul-21 | 17-Sep-21 |  | Lines |  | 34,268.94
635016 | CABLE INJECT - LAKESHORE/STANLEY/PARNELL | 830 - St. Catharines | 151294 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 09-Mar-21 |  |  | 75066.64 | 76883.35 | 75066.64 | 75066.64 | Brad Carr | Nvinium | 24-Jun-22 | 18-Aug-22 | 31-May-22 | 02-May-22 | 31-May-22 | Contractor | Contractor |  | 0
452112 | 133 Hannover Dr, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 23-Jun-22
634043 | JOINT USE PERMIT HW2019-121 - COURT AND CENTRE, ST CATH | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jul-20 |  |  | 7005.08 | 2369.58 | 7005.08 | 7005.08 | Hewitson, Trevor |  | 31-Dec-20 | 27-Jan-22 | 19-Oct-20 | 24-Mar-21 | 24-Mar-21 | Filler | Filler |  | 0
451270 | Trenergy Boiler Large Load Move | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Johnson, William | 28-May-19 |  |  | 0 | 16076.96 |  | 0 | Weaver, Thomas |  | 28-May-19 | 03-Aug-21 | 28-May-19 | 28-May-19 | 28-May-19
451649 | 2018 Cogeco Permit Review | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 22-Feb-19 |  |  | 0 | 9963.7 |  | 0 | Weaver, Thomas |  | 22-Feb-19 | 15-Apr-21 | 22-Feb-19 | 22-Feb-19 | 22-Feb-19
452178 | Bell Make Ready - Lovers Lane | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 19-Sep-19 |  |  | 5521.78 | 4367.6 | 5521.78 | 5521.78 | Brian Robinson |  | 21-Oct-19 | 04-May-20 | 21-Oct-19 | 29-Oct-19 | 29-Oct-19 |  |  |  | 0
636423 | POLE RESIDUAL 2020 - REAR YARD | 830 - St. Catharines | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Rolfe, Eric |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636017 | 3 WIRE ISSUE - HILLYARD STREET | 820 - Nebo | 150336 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
635182 | NEWTON 282X - SW GEAR | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
451902 | 179-187 James St N, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2023 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Jan-19
451403 | 470 Upper Sherman Ave, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 12-Jun-17
451339 | 1070 Main St W - Padmount Tx | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 31-Oct-16
635606 | REBUILD: LESLIE, W28TH TO W27TH (HAMILTON) - 5 | 820 - Nebo | 150335 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-20 | 5 | 5 | 30067.68 | 31756.58 | 30067.68 | 30067.68 | Koeppe, Jeffrey |  | 20-Oct-22 | 01-Aug-23 | 10-Oct-22 | 04-Nov-22 | 09-Nov-22 | Locates | Locates |  | 0
633500 | ST. MARY'S CHURCH - PARK ST & SHEAFFE ST | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 22-Sep-22
635017 | CABLE INJECT - MILLWARD/JEANETTE/TREVOR | 830 - St. Catharines | 151280 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 09-Mar-21 |  |  | 54925.46 | 79573.37 | 54925.46 | 54925.46 | Brad Carr | Nvinium | 27-Aug-21 | 24-May-22 | 03-Aug-21 | 12-Sep-21 | 24-Feb-22 | Contractor | Contractor |  | 0
635727 | JOINT USE PERMIT HW2020-011 - HIGHLAND AND UPR MT ALBION - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jun-20 |  |  | 7443.22 | 6716.98 | 7443.22 | 7443.22 | Hewitson, Trevor |  | 31-Dec-20 | 05-Jan-22 | 19-Oct-20 | 22-Feb-21 | 22-Feb-21 | Filler | Filler |  | 0
452177 | 43 Scott Street-Pole Residual | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 03-Oct-19 |  |  | 52889.03 | 62618.1 | 52889.03 | 52889.03 | Dan Despres |  | 15-Nov-19 | 08-Mar-21 | 04-Nov-19 | 04-Oct-19 | 16-Oct-19 |  |  |  | 0
635695 | STELCO- M20 FEEDER | 820 - Nebo | 150449 | Active | 10 | ACTIVE | Medium | Indust | 2023 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
452002 | 16 Lombardy Ave | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 12-Apr-19 |  |  | 24999.32 | 20680.1 | 24999.32 | 24999.32 | Frank Giancola |  | 21-May-19 | 24-Aug-20 | 13-May-19 | 07-May-19 | 17-May-19 |  | Customer |  | 0
451749 | Cross of Lorraine, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 2927.56 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 24-Aug-20 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
451093 | 27 Bold St, Hamilton | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Laus, Tomislav | 23-Nov-17 |  |  | 52766.58 | 62354.9 | 47088.66 | 52766.58 | Koeppe, Jeffrey |  | 16-Jan-18 | 24-Aug-20 | 08-Jan-18 | 05-Jan-18 | 08-Mar-19 |  | Customer |  | 5,677.92
635000 | 198 WELLINGTON ST.S - NEW CONDO BUILDING | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
634169 | BIOLYSE PHARMA - 500KW NETMETERING | 820 - Nebo | 151513 | Active | 10 | ACTIVE |  |  | 2023 | Braletic, Bob | Lustrinelli, Mark |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 04-Nov-19
633455 | KING/QUEEN CUSTOMER EXPANSION | 820 - Nebo | 152381 | Active | 93 | ANALYZE | High | Hotel | 2023 | Jakubowski, Mark | Karan, Andjelo | 28-Nov-22 |  |  | 418387.37 | 382268.96 | 418387.37 | 418387.37 | Brad Carr | B&M | 31-Jan-23 | 26-Jul-23 | 19-Dec-22 | 12-Dec-22 | 06-Mar-23 | Customer | Customer |  | 0
631915 | OTTAWA 3 - #6 REPLACEMENT PROGRAM | 820 - Nebo | 150496 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 776023.8 | 21569.8 | 776023.8 | 776023.8 | Dre Danieli |  |  | 26-Jul-23 | [6 empty] | 0
452001 | 50 Secord Dr | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2021 | Paesano, Andrew | Dragojevic, Igor | 06-Nov-19 |  |  | 89231.17 | 97992.88 | 98400.46 | 89231.17 | Macdougall, Stephen | B&M | 06-Apr-20 | 26-Jul-23 | 23-Mar-20 | 06-Apr-20 | 13-Aug-21 | COVID19 | COVID19 |  | -9,169.29
451337 | 212 KING WILLIAM ST, HAMILTON | 820 - Nebo | 150449 | Active | 95 | COMPLETE | VerHigh | Res-ICI | 2021 | Kappheim, Adam | Bennett, Aaron | 06-Oct-21 |  |  | 21546.59 | 26504.15 | 21546.59 | 21546.59 | Roy Owen |  | 01-Nov-21 | 26-Jul-23 | 25-Oct-21 | 25-Oct-21 | 05-Nov-21 |  | Customer |  | 0
452176 | 2 CUSHMAN RD. | 830 - St. Catharines | 150496 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 21-Dec-22 |  |  | 155460.16 | 25204.7 | 155460.16 | 155460.16 | Weaver, Thomas |  | 21-Dec-22 | 08-Mar-23 | 21-Dec-22 | 21-Dec-22 | 21-Dec-22 |  |  |  | 0
451647 | Celtic Dr - 8 kV Conv. - Phase 2 | 820 - Nebo | 150320 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 28-Nov-19 |  |  | 1632511.31 | 1831021.15 | 1461920.31 | 1632511.31 | Brad Carr | B&M | 26-Feb-21 | 22-Sep-22 | 31-Aug-20 | 12-Oct-20 | 17-Jun-21 | Contractor | Contractor |  | 170,591.00
451595 | 690 SOUTH SERVICE RD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Frigotto, Rodrigo | Dragojevic, Igor | 29-Jul-21 |  |  | 172120.45 | 175442.28 | 172120.45 | 172120.45 | Macdougall, Stephen |  | 21-Sep-21 | 22-Sep-22 | 30-Aug-21 | 24-Sep-21 | 21-Oct-21 | Locates | Locates |  | 0
635739 | 212 KING WILLIAM ST - TEMP SERVICE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2021 | Kappheim, Adam | Bennett, Aaron | 29-Jun-20 |  |  | 38901.77 | 44684.78 | 38901.77 | 38901.77 | Roy Owen |  | 07-Aug-20 | 22-Sep-22 | 05-Aug-20 | 03-Jul-20 | 24-Nov-21 |  | Customer |  | 0
635607 | REBUILD: ELMWOOD & W 25TH (HAMILTON) - 2 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-20 | 2 |  | 20140.35 | 21173.22 | 17703.42 | 20140.35 | Koeppe, Jeffrey |  | 05-Jul-21 | 22-Aug-22 | 28-Jun-21 | 07-Jun-21 | 14-Jun-21 |  |  |  | 2,436.93
632821 | BELL POLE RELOCATE - TRANSFER PRIMARY - NEW INTERSECTION INSTALL | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 11-Sep-19 |  |  | 0 | 39579.05 |  | 0 | Scott Borer |  | 11-Sep-19 | 09-Aug-22 | 11-Sep-19 | 11-Sep-19 | 11-Sep-19
452162 | 2513 Fifth St. St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Lustrinelli, Mark | 25-Jun-19 |  |  | 25315.99 | 24935.73 | 25315.99 | 25315.99 | Frank Giancola |  | 08-Aug-19 | 17-Jan-22 | 01-Aug-19 | 23-Jul-19 | 03-Sep-19 |  | Customer |  | 0
451951 | 331X_Part 1 | 820 - Nebo | 151250 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Billone, Justin | 07-Feb-19 |  |  | 592399.49 | 694339.2 | 624858.88 | 592399.49 | Andrew Mehlenbacher | B&M | 15-Aug-19 | 20-Sep-21 | 08-Apr-19 | 14-Mar-19 | 09-Dec-19 |  | Control/SCADA |  | -32,459.39
451401 | 18 West Ave S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 18-Mar-19 |  |  | 28426.09 | 26964.81 | 28426.09 | 28426.09 | Koeppe, Jeffrey | Fairway | 02-May-19 | 15-Jul-21 | 29-Apr-19 | 10-Apr-19 | 25-Oct-19 |  | Customer |  | 0
451087 | 6 & 10 Dalhousie Ave, St. Kitts | 830 - St. Catharines | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 28-Jun-16 |  |  | 95614.15 | 106716.13 | 80341.03 | 95614.15 | Frank Giancola |  | 01-Dec-16 | 10-Dec-20 | 15-Aug-16 | 26-Jul-16 | 13-Feb-19 |  | Customer |  | 15,273.12
451198 | Beach TS Pole Brace | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 13735.87 |  | 0 | Brian Robinson |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451646 | ROAD AUTHORITY - POLE RELOCATION - REGION OF PEEL - DIXIE RD - LOCATION 1 | 820 - Nebo | 151807 | Inactive | 99 | CANCELLED |  |  | 2021 | Pelleja, Emily | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Sep-22
635608 | REBUILD: DENLOW & GARTH (HAMILTON) - 3 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-20 | 3 |  | 52975.38 | 67249.29 | 40688.2 | 52975.38 | Koeppe, Jeffrey |  | 22-Jul-21 | 22-Aug-22 | 07-Jul-21 | 02-Jul-21 | 22-Jul-21 |  |  |  | 12,287.18
451899 | Supercrawl, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 07-Aug-19 |  |  | 32539.17 | 36617.3 | 32539.17 | 32539.17 | Koeppe, Jeffrey |  | 16-Sep-19 | 15-Jul-21 | 09-Sep-19 | 09-Sep-19 | 22-Nov-19 |  | Locates |  | 0
451950 | 12 Colton Ave, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 15-Nov-18 |  |  | 1094.89 | 1096.26 | 1094.89 | 1094.89 | Carr, Brad |  | 20-Dec-18 | 15-Jul-21 | 20-Dec-18 | 30-Apr-19 | 30-Apr-19 | Customer | Customer |  | 0
634277 | UPGRADE SC1355 TO A PMH11 WITH SCADA - 1 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 08-Jun-20 |  |  | 127139.08 | 156056.13 | 127139.08 | 127139.08 | Roy Owen |  | 23-Oct-20 | 15-Jul-21 | 21-Oct-20 | 06-Jan-21 | 06-Jan-21 | Lines | Lines |  | 0
633453 | 476 BEACH ROAD | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2019 | Paesano, Andrew | Bharosi, Mohindra |  |  |  | 0 | 0 |  | 0 | Koeppe, Jeffrey |  | 21-Nov-19 | 29-Mar-21 | 21-Nov-19 | 21-Nov-19 | 21-Nov-19
451336 | 30 Hamilton St S, Waterdown | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 14-Dec-18 |  |  | 63228.04 | 74817.77 | 58186.04 | 63228.04 | Roy Owen | Fairway | 12-Feb-19 | 10-Dec-20 | 04-Feb-19 | 19-Feb-19 | 28-Jun-19 |  | Customer |  | 5,042.00
451747 | 408 Cumberland Ave, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 03-Jul-18 |  |  | 85610.63 | 90449.59 | 85610.63 | 85610.63 | Koeppe, Jeffrey |  | 31-Aug-18 | 10-Dec-20 | 13-Aug-18 | 16-Jul-18 | 07-Jan-19 |  | Customer |  | 0
451594 | Parkdale Data Center | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2019 | Vande Kuyt, Greg | Jolie, Chris | 28-May-19 |  |  | 0 | 145241.33 |  | 0 | Weaver, Thomas |  | 07-May-19 | 16-Nov-20 | 07-May-19 | 07-May-19 | 07-May-19
451797 | 399 Kenora Ave | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 23-Apr-19 |  |  | 10242.77 | 13158.36 | 10242.77 | 10242.77 | Koeppe, Jeffrey |  | 24-May-19 | 16-Nov-20 | 22-May-19 | 07-Jun-19 | 12-Jun-19 |  | Customer |  | 0
632820 | POLE RELOCATION - FEEDER UPGRADE - CHARLTON AVE | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 11-Sep-19 |  |  | 0 | 36614.16 |  | 0 | XPopiel, Joseph |  | 11-Sep-19 | 24-Aug-20 | 11-Sep-19 | 11-Sep-19 | 11-Sep-19
451196 | Lynden Rd Large Load Move | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 692.84 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
452108 | Pole Relocation - 41 Oak Ave | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 01-May-19 |  |  | 14980.28 | 12387.21 | 14980.28 | 14980.28 | XPopiel, Joseph |  | 14-Jun-19 | 30-Mar-20 | 12-Jun-19 | 17-Jun-19 | 28-Jun-19 |  | Locates |  | 0
636032 | 3 STUDEBAKER PLACE | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
451086 | 2016 Pole Residual Melody Crt | 820 - Nebo | 150335 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 18450.13 | 0 | 18450.31 | 18450.31 | Koeppe, Jeffrey |  |  | 20-Aug-14 | [6 empty] | 0
631913 | OTTAWA # 5 - #6 REPLACEMENT | 820 - Nebo | 150333 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 942185.88 | 11353.38 | 942185.88 | 942185.88 | Dre Danieli |  |  | 26-Jul-23 | [6 empty] | 0
451084 | James St | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Destefano, Nick |  |  | 22-Sep-22
635744 | HAMILTON KICKER TX REPLACEMENT - TX # 6592 - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 28-Feb-20 |  |  | 58787.47 | 44830.5 | 58787.47 | 58787.47 | Koeppe, Jeffrey |  | 18-Dec-20 | 23-Sep-22 | 08-Dec-20 | 01-Feb-21 | 31-Dec-21 | COVID19 | COVID19 |  | 0
635609 | REBUILD: AUCHMAR & GARTH (HAMILTON) - 3 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-20 | 3 |  | 80157.63 | 64364.55 | 80157.63 | 80157.63 | Brad Carr | K-Line | 11-Aug-21 | 22-Aug-22 | 26-Jul-21 | 08-Nov-21 | 18-Nov-21 | Locates | Locates |  | 0
451746 | Project Estimating 2018 | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 21-Apr-22
451469 | Elgin TS Rebuild Phase 2 | 820 - Nebo | 151090 | Inactive | 99 | COMPLETE |  |  | 2021 | Vande Kuyt, Greg | Lustrinelli, Mark | 05-Mar-19 |  |  | 1327490.81 | 1548300.4 | 1327490.81 | 1327490.81 | Andrew Mehlenbacher |  | 30-Oct-20 | 27-Jan-22 | 01-May-19 | 22-Apr-19 | 18-Oct-21 | N/A | N/A |  | 0
635455 | JOINT USE PERMIT HW2020-001 - BONAVENTURE DR - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 19-Feb-21 |  |  | 9739.28 | 11050.32 | 9739.28 | 9739.28 | Brad Carr | K-Line | 30-Apr-21 | 24-Jan-22 | 01-Mar-21 | 08-Jun-21 | 08-Jun-21 | Filler | Filler |  | 0
451949 | 1 Abbott St, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 18-Mar-19 |  |  | 28401.13 | 27264.95 | 28401.13 | 28401.13 | Frank Giancola | Wiens | 29-Apr-19 | 15-Jul-21 | 23-Apr-19 | 04-Apr-19 | 25-Jul-19 |  | Customer |  | 0
451898 | 171 Appleford Crt, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 02-Apr-19 |  |  | 17509.56 | 23062.46 | 17509.56 | 17509.56 | Roy Owen | Fairway | 22-May-19 | 15-Jul-21 | 21-May-19 | 03-Jun-19 | 14-Jun-19 |  | Customer |  | 0
451593 | Martindale Road Duct Work | 830 - St. Catharines | 150336 | Inactive | 99 | CANCELLED |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 05-Jul-21
452174 | 128 Grantham Ave | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 04-Oct-19 |  |  | 50240.38 | 28460.32 | 50240.38 | 50240.38 | Dan Despres |  | 26-Nov-19 | 02-Jul-21 | 18-Nov-19 | 11-Nov-19 | 15-Jan-21 | Customer | Customer |  | 0
451796 | 57 Lakeport, (St.Cath) | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 15-Apr-19 |  |  | 21091.22 | 8974.68 | 21091.22 | 21091.22 | Frank Giancola |  | 29-May-19 | 02-Jun-21 | 21-May-19 | 15-Apr-19 | 23-Apr-19 |  | Customer |  | 0
452052 | 27 Scott St W, St Cath | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 03-May-19 |  |  | 4089.34 | 3481.83 | 4089.34 | 4089.34 | Dan Despres |  | 06-Jun-19 | 10-Dec-20 | 06-Jun-19 | 21-May-19 | 04-Jun-19 |  | Customer |  | 0
451645 | Upp. Sherman Ave-Bell Pole Relocate | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 25-Jul-18 |  |  | 125661.29 | 331868.94 | 122854.97 | 125661.29 | Carr, Brad | K-Line | 05-Oct-18 | 30-Nov-20 | 17-Sep-18 | 17-Sep-18 | 29-Mar-19 |  |  |  | 2,806.32
451999 | 459 Welland Ave. Leaking Pad Mount | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 02-Apr-19 |  |  | 24922.44 | 16210.62 | 24922.44 | 24922.44 | Frank Giancola |  | 22-Jul-19 | 23-Nov-20 | 17-Jun-19 | 07-May-19 | 18-Jul-19 |  | Filler |  | 0
452107 | 154 Main St E Structure Upgrade | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Vande Kuyt, Greg | Jolie, Chris | 19-Apr-19 |  |  | 465589.07 | 456303.74 | 464351.04 | 465589.07 | Carr, Brad | B&M | 28-Jun-19 | 24-Aug-20 | 29-Apr-19 | 14-May-19 | 07-Nov-19 | Customer | Customer |  | 1,238.03
451533 | 2120 Rymal Rd E | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 01-Aug-18 |  |  | 89224.85 | 91231.38 | 89224.85 | 89224.85 | Andrew Mehlenbacher |  | 13-Sep-18 | 24-Aug-20 | 04-Sep-18 | 17-Sep-18 | 07-Jan-19 |  | Customer |  | 0
634249 | DEERHURST CONVERSION PART 2 - HENLEY AND ELLINGTON URD | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 04-Nov-19
632801 | TO BE RE-USED. | 820 - Nebo | 150496 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 3614.38 | 0 | 3614.38 | 3614.38 | Dre Danieli |  |  | 30-Jul-19 | [6 empty] | 0
452160 | 110 Bellagio Ave, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Jul-19
451998 | Ridgewood and Highland Expansion | 830 - St. Catharines | 150665 | Active | 98 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Oosterlinck, David | 30-Apr-19 |  |  | 54177.31 | 49504.11 | 54177.31 | 54177.31 | Dan Despres |  | 26-Jun-19 | 26-Jul-23 | 10-Jun-19 | 11-Jun-19 | 03-Jul-19 | MC/PUCC Permit | MC/PUCC Permit |  | 0
451532 | LANTANA CIR & WILLCHER DR URD | 820 - Nebo | 151452 | Active | 93 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 19-Oct-22 |  |  | 301244.33 | 353641.99 | 301244.33 | 301244.33 | Dan Despres | B&M | 28-Apr-23 | 26-Jul-23 | 26-Dec-22 | 19-Dec-22 | 13-Mar-23 |  |  |  | 0
451592 | 473-475 Carlton Street Development | 830 - St. Catharines | 150588 | Inactive | 99 | CANCELLED |  |  | 2022 | Velickovski, Goran | Paesano, Andrew |  |  |  | 0 | 0 | 0 | 0 | Weaver, Thomas |  |  | 31-Aug-22 | [6 empty] | 0
632760 | CABLE INJECTION INVESTIGATION | 820 - Nebo | 151300 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 11-Sep-19 |  |  | 390385.43 | 262048 | 379952 | 390385.43 | Brad Carr | K-Line | 13-Dec-19 | 10-Aug-22 | 15-Oct-19 | 23-Sep-19 | 10-Dec-21 |  | Contractor |  | 10,433.43
636038 | 282 CENTENNIAL PARKWAY NORTH - IMAGE HONDA (ON HOLD - EXTERNAL) | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra |  |  |  | 98594.53 | 10293.69 | 98594.53 | 98594.53 | Calvin Arsenault |  |  | 03-May-22 | [6 empty] | 0
451695 | 693 Beach Blvd. Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 29-Jan-19 |  |  | 23983.84 | 29175.69 | 23983.84 | 23983.84 | Koeppe, Jeffrey | Clrway | 27-Feb-19 | 17-Jan-22 | 25-Feb-19 | 05-Feb-19 | 13-Sep-19 |  | Customer |  | 0
633160 | 80 AUBREY AVE, HAMILTON - NEW 200A U/G SERVICE | 820 - Nebo | 150456 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Bharosi, Mohindra | 23-Sep-19 |  |  | 30597.25 | 25977.95 | 30597.25 | 30597.25 | Koeppe, Jeffrey | Fairway | 25-Oct-19 | 15-Jul-21 | 22-Oct-19 | 27-Sep-19 | 11-Nov-19 |  | Customer |  | 0
452051 | 9 West Hampton Rd. | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 27-May-19 |  |  | 25957.51 | 26748.38 | 25957.51 | 25957.51 | Dan Despres | Wiens | 24-Jul-19 | 08-Mar-21 | 15-Jul-19 | 16-Jul-19 | 18-Sep-19 | Locates | Lines |  | 0
452106 | 690 Lake St - TX Replacement | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 07-Jun-19 |  |  | 84448.55 | 75439.03 | 84448.55 | 84448.55 | Dan Despres | Wiens | 29-Jul-19 | 23-Nov-20 | 22-Jul-19 | 15-Jul-19 | 23-Jul-19 |  |  |  | 0
451795 | 966 Beach Blvd | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 10-May-19 |  |  | 35159.72 | 20071.47 | 15712.97 | 35159.72 | Carr, Brad | GUCI | 10-Jun-19 | 22-Oct-20 | 10-Jun-19 | 03-Jul-19 | 28-Oct-19 |  | Customer |  | 19,446.75
634245 | DEERHURST CONVERSION PART 2 - KING ST & GREEN RD OH | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 04-Nov-19
451844 | 1041 West 5th St. HAM | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2021 | Kappheim, Adam | Sabbah, Amir | 26-Jun-20 |  |  | 80859.66 | 77894.01 | 80859.66 | 80859.66 | Roy Owen | Fairway | 17-Aug-20 | 26-Jul-23 | 10-Aug-20 | 04-Aug-20 | 07-May-21 |  | Customer |  | 0
635835 | ROAD AUTHORITY - PARKIDE DR ROAD WIDENING - WATERDOWN | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE | Medium | Infrast | 2022 | Jakubowski, Mark | Celic, Dusan | 10-Nov-21 |  |  | 2271588.88 | 2234118.46 | 2222139.53 | 2271588.88 | Brad Carr | K-Line | 29-Apr-22 | 03-Oct-22 | 17-Jan-22 | 10-Jan-22 | 31-Oct-22 | Locates | Materials |  | 49,449.35
452172 | 43 Scott St W, St. Catharines | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Sep-22
635749 | HAMILTON KICKER TX REPLACEMENT - TX 7675 AND 8050 - 2 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 05-Oct-20 | 2 | 2 | 35125.53 | 48392.54 | 27435.53 | 35125.53 | Koeppe, Jeffrey |  | 17-Dec-20 | 22-Sep-22 | 14-Dec-20 | 04-Nov-21 | 25-Mar-22 | N/A | N/A |  | 7,690.00
634123 | 417-423 HIGHWAY 8, STONEY CREEK | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 31-Aug-22
451643 | Mountain URD - Phase 2 - (North) | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 07-Jan-19 |  |  | 1087289.31 | 1479882.47 | 963851.09 | 1087289.31 | Andrew Mehlenbacher | B&M | 12-Mar-20 | 21-Apr-22 | 19-Aug-19 | 04-Nov-19 | 03-Sep-21 | MC/PUCC Permit | MC/PUCC Permit |  | 123,438.22
451264 | Lakeshore Rd Road Widening | 830 - St. Catharines | 150653 | Inactive | 99 | COMPLETE | Medium | Infrast | 2021 | Jakubowski, Mark | Patel, Ketan | 26-Nov-19 |  |  | 1540630.54 | 1431927.87 | 1518711.84 | 1540630.54 | Dan Despres | Wiens | 20-Aug-21 | 18-Jan-22 | 04-Jan-21 | 14-Dec-20 | 13-Aug-21 | MC/PUCC Permit |  |  | 21,918.70
452158 | 12 Dundana Ave, Dundas | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 10-Jul-19 |  |  | 8617.83 | 10480.54 | 8617.83 | 8617.83 | Koeppe, Jeffrey |  | 14-Aug-19 | 17-Jan-22 | 12-Aug-19 | 31-Jul-19 | 14-Aug-19 |  | Customer |  | 0
636039 | 383 DUNDAS ST. E. - WATERDOWN | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 22-Sep-20 |  |  | 517745.59 | 499499.08 | 517745.59 | 517745.59 | Brad Carr |  | 02-Nov-20 | 15-Nov-21 | 26-Oct-20 | 22-Feb-21 | 15-Mar-21 | Customer | Customer |  | 0
451794 | 45 Wellington St.N | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 01-May-19 |  |  | 22137.93 | 35822.85 | 22137.93 | 22137.93 | Koeppe, Jeffrey |  | 07-Jun-19 | 15-Jul-21 | 03-Jun-19 | 07-May-19 | 02-Aug-19 |  | Locates |  | 0
451467 | 81 Robinson St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 25-Jan-18 |  |  | 51234.09 | 50628.1 | 51234.09 | 51234.09 | Roy Owen |  | 02-Mar-18 | 27-Jun-21 | 26-Feb-18 | 15-Nov-18 | 06-Jun-19 |  | Customer |  | 0
451188 | 215 Ottawa St N | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 970.73 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
452105 | Glendale UG Road Crossingx | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 27-May-19 |  |  | 63240 | 89280 | 51240 | 63240 | Frank Giancola | Wiens | 08-Jul-19 | 20-Jul-20 | 02-Jul-19 | 16-Jul-19 | 18-Oct-19 | N/A | N/A |  | 12,000.00
633049 | DEERHURST CONVERSION - HENLEY & DEERHURST URD | 820 - Nebo | 150496 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 28-Nov-19 |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 12-Aug-19
451590 | ABERDEEN #4 O/H FEEDER -PHASE 1 | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 71676.85 |  | 0 | Weaver, Thomas | K-Line |  | 16-Jun-23
635840 | ROAD AUTHORITY - GRINDSTONE BRIDGE OVERHEAD WIRE RELOCATION | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE | Medium | Infrast | 2022 | Jakubowski, Mark | Celic, Dusan | 29-Oct-21 |  |  | 321701.44 | 305659.74 | 337176.4 | 321701.44 | Brad Carr | K-Line | 28-Jan-22 | 04-Jul-22 | 03-Jan-22 | 04-Feb-22 | 21-Apr-22 | Materials | Materials |  | -15,474.96
635756 | HAMILTON KICKER TX REPLACEMENT - TX 13000 - 1 | 820 - Nebo | 150496 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 28-Feb-20 |  |  | 8511.02 | 9587.03 | 3574.01 | 8511.02 | Koeppe, Jeffrey |  | 07-Dec-20 | 21-Apr-22 | 07-Dec-20 | 04-Jun-21 | 04-Jun-21 | N/A | N/A |  | 4,937.01
452157 | 2 Gage Ave S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 16-Aug-19 |  |  | 43027.89 | 23186.79 | 43027.89 | 43027.89 | Koeppe, Jeffrey |  | 23-Sep-19 | 17-Jan-22 | 16-Sep-19 | 13-Sep-19 | 21-Oct-19 |  | Locates |  | 0
636043 | CHEDOKE HEIGHTS - PHASE 1 - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 17-Feb-21 |  |  | 256796.42 | 686697.17 | 299234.01 | 256796.42 | Brad Carr | B&M | 07-May-21 | 13-Jan-22 | 22-Mar-21 | 15-Mar-21 | 25-Aug-21 |  | Customer |  | -42,437.59
633041 | POLE RELOCATION - GRADING CHANGE - CN BRIDGE | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 08-Oct-19 |  |  | 21272.28 | 13937.51 | 21272.28 | 21272.28 | Carr, Brad | K-Line | 04-Nov-19 | 15-Oct-21 | 04-Nov-19 | 26-Nov-19 | 26-Nov-19 |  | Customer |  | 0
451640 | Upper Sherman & Rymal Rd, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 01-Aug-18 |  |  | 74477.79 | 73288.32 | 74076.54 | 74477.79 | Koeppe, Jeffrey |  | 18-Sep-18 | 10-Dec-20 | 05-Sep-18 | 22-Oct-18 | 15-Jan-19 |  | Customer |  | 401.25
632730 | HIGHLAND DUCT STRUCTURE INSTALL | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 11-Sep-19 |  |  | 0 | 82167.78 |  | 0 | Carr, Brad |  | 11-Sep-19 | 03-Dec-20 | 11-Sep-19 | 11-Sep-19 | 11-Sep-19
451528 | ABERDEEN 2 - 2nd Phase Conversion | 820 - Nebo | 150268 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Anderson, Dean | 02-Nov-18 |  |  | 2027116.39 | 2161806.35 | 1752741.62 | 2027116.39 | Carr, Brad | K-Line | 02-Aug-19 | 22-Oct-20 | 02-Jan-19 | 07-Jan-19 | 10-Jul-19 | MC/PUCC Permit |  |  | 274,374.77
451466 | 300 Fourth Ave. St Catharines | 830 - St. Catharines | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | McAlpine, Robert | Paesano, Andrew | 30-Jan-18 |  |  | 50121.3 | 48135.99 | 50121.3 | 50121.3 | Frank Giancola |  | 09-Mar-18 | 24-Aug-20 | 05-Mar-18 | 12-Oct-18 | 29-Jan-19 |  | Customer |  | 0
451076 | DART Pole Rplmnts - Homeside Ave | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 9066.59 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451187 | 360 Beach Rd | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 583.13 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
452171 | 2021 TX Replacement OH - 495 Wentworth - 1 TX. | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 03-Jun-19
451996 | Deerhurst Conversion Phase 1 | 820 - Nebo | 150317 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 28-Nov-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Dec-18
451394 | Confederation GO Station | 820 - Nebo | 150449 | Active | 70 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra | 13-Apr-18 |  |  | 6865.69 | 8205.27 | 6865.69 | 6865.69 | Macdougall, Stephen |  | 01-Jun-18 | 24-Aug-18 | 01-Jun-18 |  |  |  | Filler |  | 0
451332 | 47 Wentworth St S, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 12-Dec-16
636044 | CHEDOKE HEIGHTS - PHASE 2 - SUBD RES EDS | 820 - Nebo | 150588 | Active | 95 | ANALYZE |  |  | 2023 | Velickovski, Goran | Morris, Mark | 24-Feb-21 |  |  | 260444.39 | 276365.05 | 260444.39 | 260444.39 | Brad Carr | B&M | 07-Apr-21 | 26-Jul-23 | 22-Mar-21 | 12-Apr-21 | 17-Feb-23 | Customer | Customer |  | 0
451589 | Skinner Road Housing | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Velickovski, Goran | Morris, Mark | 26-Feb-19 |  |  | 11100.62 | 109538.26 | 8412.55 | 11100.62 | Tony Ierace |  | 04-Apr-19 | 13-Feb-23 | 01-Apr-19 | 01-Apr-19 | 11-Oct-19 |  | Customer |  | 2,688.07
451792 | 695 James St.N (Temp) | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Oosterlinck, David | 14-Dec-18 |  |  | 11062.49 | 8719.73 | 11062.49 | 11062.49 | Macdougall, Stephen |  | 01-Feb-22 | 20-Sep-22 | 01-Feb-22 | 04-Jan-19 | 17-Aug-22 | Customer | Customer |  | 0
452170 | Main St, St. Catharines | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Aug-22
451527 | 2B Arlington Ave, St Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 06-Jun-22
634056 | LOVERS LN, HAMILTON | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 06-Jul-20 |  |  | 10364.72 | 7730.2 | 10364.72 | 10364.72 | Hewitson, Trevor |  | 30-Oct-20 | 20-Feb-22 | 01-Oct-20 | 05-Feb-21 | 04-Feb-21 | Filler | Filler |  | 0
452047 | 111 Fourth Ave, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Nov-21
451894 | 100 Hamilton St N, Waterdown | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED | VerHigh | Res-ICI | 2021 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Jul-21
451945 | Lantern Lane URD | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 18-Mar-19 |  |  | 115418.17 | 106084.91 | 109879.03 | 115418.17 | Carr, Brad | K-Line | 17-May-19 | 18-Feb-21 | 29-Apr-19 | 22-Apr-19 | 26-Jul-19 |  | Customer |  | 5,539.14
451842 | 46 King St. E HAM | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Faisal | Montgomery, Michael | 08-Mar-19 |  |  | 7581.76 | 11871.8 | 7581.76 | 7581.76 | Roy Owen |  | 18-Apr-19 | 16-Feb-21 | 15-Apr-19 | 10-Apr-19 | 10-Apr-19 |  |  |  | 0
451995 | Wilson St - Duct Structure | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Billone, Justin | 04-Jan-19 |  |  | 193993.31 | 112097.46 | 193993.31 | 193993.31 | Carr, Brad | B&M | 01-Mar-19 | 24-Aug-20 | 07-Jan-19 | 07-Jan-19 | 13-Feb-19 |  | MC/PUCC Permit |  | 0
451262 | Hamilton Port Authority Pole Moves | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 52536.01 |  | 0 | Weaver, Thomas |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451393 | 697 Niagara St, st catharines | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Morris, Mark | 01-May-19 |  |  | 0 | 904.28 |  | 0 | Weaver, Thomas |  | 01-May-19 | 24-Aug-20 | 01-May-19 | 01-May-19 | 01-May-19
451075 | Barton St - Delta To WYE Conversion | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 04-Dec-18 |  |  | 134009.54 | 131565.78 | 133493.05 | 134009.54 | Carr, Brad | K-Line | 01-Mar-19 | 24-Aug-20 | 11-Feb-19 | 31-Jan-19 | 02-May-19 |  | Customer |  | 516.49
631350 | Cogeco Make Ready - Birch Ave | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 25-Sep-19 |  |  | 6364.3 | 2292.03 | 6364.3 | 6364.3 | Brian Robinson |  | 29-Oct-19 | 11-May-20 | 29-Oct-19 | 02-Dec-19 | 19-Dec-19 |  |  |  | 0
633315 | 2020 - AUTOMATED SWITCHGEAR INSTALLS | 820 - Nebo | 151065 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 03-Sep-19
452156 | 100 JAMES ST S, HAMILTON | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Laus, Tomislav |  |  |  | 0 | 15039.38 |  | 0 | Weaver, Thomas |  |  | 27-May-19
451791 | 20 George St - CCRA Project | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 03-Sep-19 |  |  | 7776.26 | 9559.4 | 7776.26 | 7776.26 | Roy Owen |  | 02-Oct-19 | 26-Jul-23 | 30-Sep-19 | 06-Nov-19 | 12-Nov-19 |  | Customer |  | 0
451261 | MOUNTAINBROW RD ROAD WIDENING - PART 2 | 820 - Nebo | 150644 | Active | HO | RELEASED | Medium | Infrast | 2023 | Jakubowski, Mark | Celic, Dusan | 29-Sep-22 |  |  | 1022526.52 | 32987.99 | 1022526.52 | 1022526.52 | Brad Carr | K-Line | 29-Dec-22 | 26-Jul-23 | 14-Nov-22 |  |  | MC/PUCC Permit | MC/PUCC Permit |  | 0
451944 | FONTAINBLEU - HOUSES PLANNED CAP B&M COSTS | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Patel, Ketan | 03-Jan-23 |  |  | 0 | 12745.58 |  | 0 | Brad Carr |  | 03-Jan-23 | 30-Jan-23 | 03-Jan-23 | 03-Jan-23 | 03-Jan-23
451392 | Celtic Dr. - 8kV Conversion | 820 - Nebo | 150320 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 28-Nov-19 |  |  | 1550275.51 | 1573258.45 | 1412581.59 | 1550275.51 | Brad Carr | B&M | 22-Jan-21 | 22-Sep-22 | 31-Aug-20 | 28-Sep-20 | 17-Jun-21 | Contractor | Contractor |  | 137,693.92
632932 | JOINT USE PERMIT HW2019-022 - WHITNEY AND EMERSON - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William |  |  |  | 13358.64 | 3024.98 | 13358.64 | 13358.64 | Brad Carr |  | 25-Jan-22 | 18-Jul-22 | 25-Jan-22 | 25-Jan-22 | 25-Jan-22 |  |  |  | 0
634022 | JOINT USE PERMIT HW2019-107 - CENTRE RD, HAMILTON | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 15-Mar-21 |  |  | 7721.02 | 1430.9 | 7721.02 | 7721.02 | Brad Carr | K-Line | 16-Apr-21 | 24-May-22 | 12-Apr-21 | 20-Oct-21 | 20-Oct-21 | Filler | Filler |  | 0
451588 | Glen Morris Dr PMH Unit Drain | 830 - St. Catharines | 150828 | Inactive | 99 | CANCELLED |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 21-Apr-22
451994 | Glenridge Estates | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 03-Sep-19 |  |  | 41893.9 | 32849.31 | 41893.9 | 41893.9 | Frank Giancola | N/A | 23-Oct-19 | 07-Feb-22 | 07-Oct-19 | 20-Dec-19 | 04-Oct-21 | Customer | Customer |  | 0
633256 | 258 BEACH BLVD - NEW UNDERGROUND SERVICE | 820 - Nebo | 150456 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Bharosi, Mohindra | 04-Mar-21 |  |  | 23731.4 | 24343.75 | 23731.4 | 23731.4 | Roy Owen |  | 04-Mar-21 | 29-Nov-21 | 04-Mar-21 | 04-Mar-21 | 04-Mar-21 |  |  |  | 0
636048 | POLE RESIDUAL 2021 PHASE 3 - 14 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 22-May-20 | 14 |  | 175584.88 | 190536.29 | 175584.88 | 175584.88 | Frank Giancola |  | 30-Sep-21 | 05-Jul-21 | 01-Mar-21 | 22-Jan-21 | 14-Apr-21 | Filler | Filler |  | 0
451741 | 1242 Fourth Ave, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 15-Oct-18 |  |  | 47632.41 | 57872.94 | 47632.41 | 47632.41 | Frank Giancola |  | 30-Nov-18 | 24-Aug-20 | 23-Nov-18 | 23-Nov-18 | 29-Mar-19 |  | Customer |  | 0
451893 | 14 Sullivans Lane, Dundas | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bennett, Aaron | 19-Mar-19 |  |  | 7257.58 | 8373.53 | 7257.58 | 7257.58 | Carr, Brad |  | 26-Apr-19 | 24-Aug-20 | 26-Apr-19 | 02-May-19 | 02-May-19 |  | Customer |  | 0
452155 | 98 James St S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-May-19
451070 | Fairleigh Ave Rebuild | 820 - Nebo | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Koeppe, Jeffrey |  |  | 19-Mar-14
636055 | 57 LAKEPORT RD PERM | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2021 | Paesano, Andrew | Dragojevic, Igor | 09-Nov-20 |  |  | 133059.03 | 126850.22 | 127782.03 | 133059.03 | Frank Giancola | Wiens | 29-Dec-20 | 26-Jul-23 | 14-Dec-20 | 16-Dec-20 | 16-Nov-21 | Locates | Customer |  | 5,277.00
451840 | 372 DUNDAS ST. E | 820 - Nebo | 150449 | Active | 98 | COMPLETE | High | Infrast | 2021 | Kappheim, Adam | Sabbah, Amir | 22-Jan-21 |  |  | 61586.69 | 54377.34 | 61586.69 | 61586.69 | Macdougall, Stephen | Fairway | 03-Mar-21 | 26-Jul-23 | 22-Feb-21 | 22-Feb-21 | 12-Jul-21 |  | Customer |  | 0
451174 | 154 Main St.E (Condo Temp) | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Oosterlinck, David | 02-Oct-18 |  |  | 126353.75 | 109176.03 | 126353.75 | 126353.75 | Macdougall, Stephen |  | 01-Feb-22 | 27-Jun-23 | 01-Feb-22 | 12-Oct-18 | 04-Nov-22 | Customer | Customer |  | 0
452154 | 1119 BARTON ST, STONEY CREEK | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 24-Nov-20 |  |  | 96724.02 | 95882.58 | 96724.02 | 96724.02 | Macdougall, Stephen | Fairway | 14-Jan-21 | 22-Sep-22 | 04-Jan-21 | 08-Jan-21 | 06-May-21 | Customer | Customer |  | 0
451328 | 179 Louth St, st catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-Jun-22
634017 | JOINT USE PERMIT HW2019-094 - ANDERSON DR, HAMILTON | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 23-Oct-20 |  |  | 11619.94 | 12063.74 | 11619.94 | 11619.94 | Hewitson, Trevor |  | 31-Dec-20 | 28-Mar-22 | 02-Nov-20 | 24-Mar-21 | 24-Mar-21 | Filler | Filler |  | 0
451943 | 5 Oblate St, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Nov-21
632897 | 245 JAMES ST N | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Sabbah, Amir | 07-Aug-19 |  |  | 9650.67 | 6534.87 | 9650.67 | 9650.67 | Koeppe, Jeffrey |  | 29-Aug-19 | 15-Jul-21 | 29-Aug-19 | 29-Aug-19 | 29-Aug-19 |  |  |  | 0
452100 | 2, 6 & 10 Dennis Ave - Flamborough | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Djuric, Zdravko | 03-Jun-19 |  |  | 27833.67 | 27911.63 | 24333.67 | 27833.67 | Carr, Brad | Fairway | 05-Jul-19 | 15-Jul-21 | 05-Jul-19 | 30-Jul-19 | 30-Jul-19 |  |  |  | 3,500.00
451690 | 71 Innovation Dr, Flamborough | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 23-Oct-18 |  |  | 40426.67 | 43699.17 | 40426.67 | 40426.67 | Roy Owen |  | 14-Dec-18 | 10-Dec-20 | 05-Dec-18 | 03-Jan-19 | 16-Jan-19 |  | Customer |  | 0
451260 | 43 Woodbine Cres | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 04-Apr-19 |  |  | 3487.86 | 2342.91 | 3487.86 | 3487.86 | Koeppe, Jeffrey |  | 17-May-19 | 24-Aug-20 | 17-May-19 | 05-Jun-19 | 05-Jun-19 |  |  |  | 0
451391 | #6 Replacement - Huxley Ave | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 21-Feb-17
451789 | Juravinski Hospital Main Service | 820 - Nebo | 150449 | Active | 98 | COMPLETE | High | ICM | 2019 | Kappheim, Adam | Oosterlinck, David | 12-Apr-19 |  |  | 509902.25 | 421599.53 | 374163.89 | 509902.25 | Roy Owen | K-Line | 29-Nov-19 | 26-Jul-23 | 21-May-19 | 07-May-19 | 26-Nov-19 |  |  |  | 135,738.36
451062 | 120 Cannon St.E | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 15-Oct-15 |  |  | 43459.43 | 53746.48 | 43459.43 | 43459.43 | Tony Ierace | Bethleh | 22-Jan-16 | 26-Jul-23 | 23-Nov-15 | 16-Nov-15 | 30-Aug-19 |  | Customer |  | 0
451172 | DUNDAS AND SPRING CREEK CONDO | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2021 | Kappheim, Adam | Oosterlinck, David | 03-Jun-21 |  |  | 62175.96 | 91778.98 | 62175.96 | 62175.96 | Macdougall, Stephen | Fairway | 15-Jul-21 | 26-Jul-23 | 05-Jul-21 | 15-Oct-21 | 03-Nov-21 | Customer | Customer |  | 0
451327 | 100 Park Street West | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2023 | McAlpine, Robert | Paesano, Andrew |  |  |  | 12623.03 | 0 | 12623.04 | 12623.04 | Jakubowski, Mark |  |  | 23-Mar-23 | [6 empty] | 0
452044 | 2019 Bell Bonds | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 20-Feb-19 |  |  | 2567.58 | 2553.3 | 2567.58 | 2567.58 | Hewitson, Trevor |  | 29-Mar-19 | 09-Aug-22 | 29-Mar-19 | 26-Feb-19 | 28-Nov-19 |  | Filler |  | 0
632889 | WATERDOWN BAY - PHASE 3 (POND 5) | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 18-Nov-20 |  |  | 1163726.02 | 1169088.25 | 1163726.02 | 1163726.02 | Roy Owen | Transpw | 19-Feb-21 | 18-Jan-22 | 14-Dec-20 | 02-Dec-20 | 21-Sep-21 |  | Customer |  | 0
451452 | Butler Cresent - URD | 830 - St. Catharines | 151066 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Billone, Justin | 05-Jul-18 |  |  | 731210.72 | 1050914.79 | 719808.85 | 731210.72 | Carr, Brad | B&M | 28-Dec-18 | 20-Sep-21 | 01-Aug-18 | 04-Sep-18 | 21-Jun-19 | Contractor | Contractor |  | 11,401.87
633240 | U/G PEDESTAL REPLACEMENT 2020 - PH3 | 830 - St. Catharines | 151064 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 16-Dec-19 |  |  | 84626.42 | 118955.97 | 84626.42 | 84626.42 | Frank Giancola |  | 31-Aug-21 | 15-Sep-21 | 05-Apr-21 | 24-Feb-21 | 05-May-21 | Filler | Filler |  | 0
451891 | 305 East 37th St - Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Djuric, Zdravko | 14-Mar-19 |  |  | 26310.46 | 21929.32 | 26310.46 | 26310.46 | Koeppe, Jeffrey |  | 12-Jul-19 | 15-Jul-21 | 08-Jul-19 | 29-Jul-19 | 01-Aug-19 |  | Locates |  | 0
451586 | John SS PH 1, Part 1 | 820 - Nebo | 150309 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Karan, Andjelo | 22-Oct-18 |  |  | 1146595.91 | 1053251.41 | 1016184.48 | 1146595.91 | Carr, Brad | B&M | 24-May-19 | 08-Mar-21 | 03-Dec-18 | 05-Nov-18 | 01-Nov-19 |  | MC/PUCC Permit |  | 130,411.43
451942 | 37 Bayview Ave, St. Catharines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Patel, Ketan | 09-Oct-19 |  |  | 2705.1 | 7299.65 | 2705.1 | 2705.1 | Carr, Brad |  | 09-Oct-19 | 24-Aug-20 | 09-Oct-19 | 09-Oct-19 | 09-Oct-19 |  |  |  | 0
451259 | Manhole Lid Replacements - 2018 | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 1552.87 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451390 | 6075 TWENTY RD E - DEVELOPMENT | 820 - Nebo | 150588 | Inactive | 99 | CANCELLED |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 13-Feb-17
451788 | Winona Crossing - Site A (Temp) | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2021 | Kappheim, Adam | Oosterlinck, David | 14-Aug-18 |  |  | 38749.18 | 42131.26 | 38749.18 | 38749.18 | Tony Ierace |  | 24-Sep-18 | 26-Jul-23 | 17-Sep-18 | 28-Sep-18 | 25-Jun-21 | Customer | Customer |  | 0
451585 | 107 MacNab St N, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 05-Jul-18 |  |  | 101256.83 | 118628.57 | 96516.83 | 101256.83 | Brian Robinson | Bethleh | 15-Aug-18 | 26-Jul-23 | 30-Jul-18 | 12-Jul-18 | 27-Sep-19 |  | Customer |  | 4,740.00
632888 | WATERDOWN BAY - PHASE 3 (POND 4) | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 21-Aug-19 |  |  | 2945070.32 | 2910507.03 | 2945070.32 | 2945070.32 | Roy Owen | Transpw | 08-Jul-20 | 24-Nov-21 | 20-Apr-20 | 06-Apr-20 | 01-Feb-21 |  | Customer |  | 0
633239 | U/G PEDESTAL REPLACEMENT 2020 - PH2 | 830 - St. Catharines | 151064 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 16-Dec-19 |  |  | 151483.38 | 137627.33 | 151483.38 | 151483.38 | Frank Giancola |  | 05-Feb-21 | 15-Sep-21 | 14-Dec-20 | 30-Nov-20 | 11-Feb-21 | Filler | Filler |  | 0
451838 | 20 Jerseyville Rd. W ANC | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Montgomery, Michael | 17-Jan-19 |  |  | 8251.09 | 7492.35 | 8251.09 | 8251.09 | Carr, Brad |  | 27-Feb-19 | 24-Aug-20 | 27-Feb-19 | 20-Feb-19 | 20-Feb-19 |  |  |  | 0
451325 | 275 Ontario St, St. Catharines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paesano, Andrew |  |  |  | 0 | 99440.32 |  | 0 | Weaver, Thomas |  | 08-May-19 | 24-Aug-20 | 08-May-19 | 08-May-19 | 08-May-19
451167 | Fletcher Square - Sw and Tx Rework | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 | 0 | 0 | Weaver, Thomas |  | 14-Nov-22 | 14-Nov-22 | 14-Nov-22 | 14-Nov-22 | 14-Nov-22 |  |  |  | 0
452150 | 206 Bunting Rd | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 05-Jun-19 |  |  | 3978.1 | 1123.18 | 3978.1 | 3978.1 | Frank Giancola |  | 05-Jul-19 | 17-Jan-22 | 05-Jul-19 | 25-Jul-19 | 25-Jul-19 | Customer | Customer |  | 0
451687 | 1629 Third Ave. | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Lustrinelli, Mark | 28-Mar-19 |  |  | 34575.53 | 29191.76 | 34575.53 | 34575.53 | Frank Giancola |  | 15-May-19 | 17-Jan-22 | 06-May-19 | 11-Apr-19 | 02-Aug-19 |  | Customer |  | 0
451324 | 518 Linwell Rd, St Catharines | 830 - St. Catharines | 150588 | Inactive | 99 | CANCELLED |  |  | 2021 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Nov-21
451940 | Ottawa 8 - #6 Replacement | 820 - Nebo | 150333 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Anderson, Dean | 22-Aug-19 |  |  | 566274.91 | 539686.38 | 556505.11 | 566274.91 | Carr, Brad | K-Line | 29-Nov-19 | 22-Oct-20 | 01-Oct-19 | 01-Oct-19 | 27-Nov-19 |  |  |  | 9,769.80
451584 | 141 Park St N, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 1028.14 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 24-Aug-20 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
451450 | Upper Sherman / Rymal | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Vande Kuyt, Greg | Jolie, Chris | 28-Aug-17 |  |  | 125845.46 | 111832.8 | 125845.46 | 125845.46 | Koeppe, Jeffrey |  | 03-Apr-18 | 24-Aug-20 | 12-Mar-18 | 07-Sep-17 | 02-Jun-19 |  | Control/SCADA |  | 0
633995 | 464 WELLAND AVE | 820 - Nebo |  | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 17-Oct-19
451257 | Bluebird Ave Rear Lot - Phase 1 | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 03-Apr-17
451583 | 675-681 Mohawk Rd E, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 04-Feb-19 |  |  | 89049.21 | 95696.67 | 85754.32 | 89049.21 | Koeppe, Jeffrey | Fairway | 02-May-19 | 23-May-23 | 01-Apr-19 | 27-Mar-19 | 17-Jun-19 |  | Customer |  | 3,294.89
452149 | 0 St David's Rd | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 04-Sep-19 |  |  | 12294.4 | 7237.24 | 12294.4 | 12294.4 | Frank Giancola |  | 23-Oct-19 | 22-Sep-22 | 21-Oct-19 | 20-Sep-19 | 25-Sep-19 |  | Customer |  | 0
451686 | 40 Centennial Pkwy N - OH to UG | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Lustrinelli, Mark | 12-Apr-19 |  |  | 16422.01 | 16526.65 | 13894.66 | 16422.01 | Koeppe, Jeffrey |  | 24-May-19 | 17-Aug-22 | 21-May-19 | 23-Apr-19 | 23-Jul-19 |  | MC/PUCC Permit |  | 2,527.35
633989 | PEARL ST S, JACKSON ST, AND CANADA ST, HAMILTON | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jul-20 |  |  | 7279.88 | 7694.19 | 7279.88 | 7279.88 | Hewitson, Trevor |  | 31-Dec-20 | 09-Jun-22 | 19-Oct-20 | 22-Feb-21 | 22-Feb-21 | Filler | Filler |  | 0
451685 | 1643 Third Ave Louth - Raw Perform | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE |  |  | 2019 | Paesano, Andrew | Lustrinelli, Mark | 05-Jun-19 |  |  | 77248.34 | 168353.02 | 77248.34 | 77248.34 | Frank Giancola | Wiens | 30-Jul-19 | 26-Jul-23 | 08-Jul-19 | 16-Jul-19 | 23-Aug-19 | Customer | Customer |  | 0
452040 | BROCK U. ION METER INSTALL (2019) | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 21-Dec-22 |  |  | 0 | 15945.96 |  | 0 | Weaver, Thomas |  | 21-Dec-22 | 16-Mar-23 | 21-Dec-22 | 21-Dec-22 | 21-Dec-22
451938 | ELLIS AVE 3PH EXPANSION | 830 - St. Catharines | 152381 | Inactive | 99 | COMPLETE | Medium | Subdiv | 2021 | Jakubowski, Mark | Patel, Ketan | 08-Jan-21 |  |  | 287379.01 | 263691.62 | 267160.44 | 287379.01 | Brad Carr | B&M | 19-Feb-21 | 11-May-22 | 19-Jan-21 | 25-Jan-21 | 04-Mar-21 | Contractor | Contractor |  | 20,218.57
451835 | 89 Megna Crt. HAM | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Faisal | Montgomery, Michael | 28-Dec-18 |  |  | 10337.35 | 10538.52 | 10337.35 | 10337.35 | Roy Owen |  | 13-Feb-19 | 17-Jan-22 | 11-Feb-19 | 15-Jan-21 | 19-Jan-21 | Customer | Customer |  | 0
633938 | CHEGWIN STREET POLE RELOCATION - 3 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 16-Dec-19 | 3 |  | 37627.2 | 26634.22 | 36642.2 | 37627.2 | Koeppe, Jeffrey |  | 29-Jan-21 | 16-Sep-21 | 21-Jan-21 | 15-Jan-21 | 19-Feb-21 |  | COVID19 |  | 985
451735 | 285 Geneva St, St Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | McAlpine, Robert | Morris, Mark |  |  |  | 0 | 289.62 |  | 0 | Weaver, Thomas |  |  | 15-Jul-21
451255 | 2017 Ham LBDS Replacement | 820 - Nebo | 150337 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Billone, Justin | 31-Aug-18 |  |  | 57889.5 | 58801.71 | 57889.5 | 57889.5 | Carr, Brad | K-Line | 02-Nov-18 | 02-Jul-21 | 01-Oct-18 | 05-Aug-19 | 24-Sep-19 | MC/PUCC Permit | MC/PUCC Permit |  | 0
451447 | York Conversion - OH Removals | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Karan, Andjelo | 08-Jul-19 |  |  | 47777.36 | 36810.71 | 47777.36 | 47777.36 | Carr, Brad | B&M | 13-Sep-19 | 08-Mar-21 | 03-Sep-19 | 15-Jul-19 | 18-Jul-19 |  |  |  | 0
451887 | 16 Murray St - Hamilton | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Djuric, Zdravko | 26-Feb-19 |  |  | 8842.39 | 6195.54 | 8842.39 | 8842.39 | Koeppe, Jeffrey |  | 28-Mar-19 | 24-Aug-20 | 27-Mar-19 | 22-Mar-19 | 22-Mar-19 |  | Customer |  | 0
451386 | Haig/Carlton Duct structure | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jolie, Chris | 22-Aug-17 |  |  | 162958.58 | 9065.15 | 162958.58 | 162958.58 | Dan Despres |  | 08-Jan-18 | 24-Aug-20 | 25-Sep-17 | 28-May-19 | 28-May-19 |  |  |  | 0
451518 | BRCE - Barrie Expansion | 820 - Nebo | 150591 | Active | 10 | ACTIVE |  |  | 2023 | Khuu, Philander | Vandekuyt, Greg |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 04-Sep-17
451385 | #6 REPLACEMENT - ROSSLYN AVE NORTH | 820 - Nebo | 150496 | Active | HL | ACTIVE |  |  | 2023 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 1451.04 |  | 0 | Jakubowski, Mark |  |  | 26-Jul-23
451321 | 26 Upper Mount Albion Rd, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 18-May-18 |  |  | 60313.51 | 61596.1 | 60142.01 | 60313.51 | Roy Owen |  | 25-Jun-18 | 26-Jul-23 | 18-Jun-18 | 12-Sep-18 | 25-Sep-19 | Customer | Customer |  | 171.5
451444 | Marshall Lane Development | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Velickovski, Goran | Morris, Mark | 07-Feb-19 |  |  | 25253.31 | 159256.69 | 25253.31 | 25253.31 | Frank Giancola |  | 08-Apr-19 | 06-Jun-23 | 18-Mar-19 | 16-Sep-19 | 18-Nov-19 | Customer | Customer |  | 0
633878 | 50 GREEN MOUNTAIN ROAD WEST - REMOVAL / DEMOLITION | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Bharosi, Mohindra | 15-Nov-19 |  |  | 9356.13 | 6358.57 | 9356.13 | 9356.13 | Koeppe, Jeffrey |  | 03-Dec-19 | 22-Sep-22 | 02-Dec-19 | 18-Nov-19 | 18-Nov-19 |  |  |  | 0
451684 | 281 Barton St. STC - Gas Station | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Lustrinelli, Mark | 07-Aug-19 |  |  | 20165.17 | 20003.38 | 20165.17 | 20165.17 | Carr, Brad | Fairway | 13-Sep-19 | 17-Aug-22 | 09-Sep-19 | 01-Oct-19 | 28-Oct-19 | MC/PUCC Permit | MC/PUCC Permit |  | 0
452147 | 17 East St. (SCH) | 830 - St. Catharines | 150457 | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 23-Jun-22
451834 | 205 Lovers Lane | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Faisal | Montgomery, Michael | 05-Apr-19 |  |  | 17075.7 | 32281.44 | 17075.7 | 17075.7 | Carr, Brad |  | 05-Apr-19 | 17-Jan-22 | 05-Apr-19 | 06-May-19 | 06-May-19 |  | Customer |  | 0
451886 | 114 Overdale Ave - Flamborough | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Djuric, Zdravko | 06-May-19 |  |  | 7051.19 | 7336.31 | 7051.19 | 7051.19 | Carr, Brad | Clrway | 07-Jun-19 | 15-Jul-21 | 07-Jun-19 | 25-Jul-19 | 25-Jul-19 |  | Customer |  | 0
452092 | 25 Chetwood St, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 04-Apr-19 |  |  | 3894.44 | 3502.02 | 3894.44 | 3894.44 | Carr, Brad |  | 03-May-19 | 24-Aug-20 | 03-May-19 | 26-Apr-19 | 26-Apr-19 |  | Customer |  | 0
451158 | 27 Proctor- Service Relocation | 820 - Nebo | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 2963.13 | 0 | 2963.13 | 2963.13 | Koeppe, Jeffrey |  |  | 04-Jun-15 | [6 empty] | 0
451441 | CCRA - 45 KING ST E-KING WILLIAM RESIDENCE | 820 - Nebo | 150449 | Active | 93 | ANALYZE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav | 22-Feb-23 |  |  | 85091.26 | 110950.52 | 93781.14 | 85091.26 | Roy Owen | B&M | 07-Mar-23 | 26-Jul-23 | 06-Mar-23 | 06-Mar-23 | 04-Apr-23 | Customer | N/A |  | -8,689.88
451383 | 419 Dewitt Rd | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 13-Dec-18 |  |  | 69717.05 | 68603.03 | 66792.05 | 69717.05 | Koeppe, Jeffrey | Bethleh | 13-Feb-19 | 26-Jul-23 | 04-Feb-19 | 22-Mar-19 | 06-Dec-19 | Customer | Customer |  | 2,925.00
633234 | 57 STRATHCONA DR - POLE REPLACEMENT | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 13-Sep-21 |  |  | 451.43 | 13799.72 |  | 451.43 | Dan Despres |  | 13-Sep-21 | 22-Sep-22 | 13-Sep-21 | 13-Sep-21 | 13-Sep-21
452146 | CLAPPISON 5/6 PROPERTIES - SUBD ICI EDS | 820 - Nebo | 151652 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 08-Sep-20 |  |  | 507325.11 | 523881.15 | 507325.11 | 507325.11 | Brad Carr | Transpw | 23-Oct-20 | 09-Aug-22 | 12-Oct-20 | 09-Mar-21 | 13-Apr-21 | MC/PUCC Permit | MC/PUCC Permit |  | 0
452091 | Duke St, Wellington St & Lake St | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 04-May-20 |  |  | 6896.35 | 28892.33 | 6896.35 | 6896.35 | Hewitson, Trevor |  | 30-Nov-20 | 24-May-22 | 02-Nov-20 | 02-Jan-21 | 02-Jan-21 | Filler | Filler |  | 0
451783 | Elllis Ave Condo | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 19-Nov-20 |  |  | 216637.5 | 217062.5 | 216637.5 | 216637.5 | Frank Giancola |  | 30-Dec-20 | 11-May-22 | 29-Dec-20 | 22-Mar-21 | 22-Mar-21 | Customer | Customer |  | 0
451833 | 477 Dundas St. East | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Faisal | Montgomery, Michael | 05-Dec-18 |  |  | 72381.63 | 77720.93 | 66393.43 | 72381.63 | Koeppe, Jeffrey |  | 18-Jan-19 | 08-Feb-21 | 09-Jan-19 | 11-Jan-19 | 18-Apr-19 |  | Customer |  | 5,988.20
451320 | 652 Lawerence Rd, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 26-Mar-18 |  |  | 45277.69 | 0 | 45277.69 | 45277.69 | Koeppe, Jeffrey |  | 30-May-18 | 01-Feb-21 | 22-May-18 | 06-Nov-19 | 06-Nov-19 |  |  |  | 0
451885 | 68 Turnbull Rd - Dundas | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Djuric, Zdravko | 30-Apr-19 |  |  | 5355.7 | 3900.67 | 5355.7 | 5355.7 | Roy Owen |  | 31-May-19 | 24-Aug-20 | 30-May-19 | 29-May-19 | 29-May-19 |  |  |  | 0
451157 | 300 Mohawk Rd E - Trans Rm Removal | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 674.02 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451515 | 1176 Lakeshore Rd W | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2023 | Frigotto, Rodrigo | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Oct-17
633232 | BUM81 FEEDER EXTENSION PART 2 - NORTH OF CARLTON (ST. CATH) | 830 - St. Catharines | 150579 | Active | 95 | ANALYZE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-21 |  |  | 2950963.79 | 2867327.61 | 2762664.56 | 2950963.79 | Brad Carr | K-Line | 31-Aug-22 | 26-Jul-23 | 28-Feb-22 | 07-Mar-22 | 28-Oct-22 | Contractor | Contractor |  | 188,299.23
451382 | 2 Oriole Cres | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 14-Jun-17 |  |  | 18277.66 | 22941.13 | 18247.3 | 18277.66 | Andrew Mehlenbacher |  | 14-Jul-17 | 17-Jan-22 | 12-Jul-17 | 24-Aug-17 | 04-Jul-19 | Customer | Customer |  | 30.36
451156 | 1365 Baseline Rd - Pole Conflicts | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Johnson, William |  |  |  | 0 | 7572.58 |  | 0 | Jakubowski, Mark |  |  | 20-Oct-21
451985 | Rogers Make Ready - Upp. Ottawa | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 15-Jan-19 |  |  | 3672.91 | 7587.88 | 3672.91 | 3672.91 | XPopiel, Joseph |  | 11-Mar-19 | 24-Aug-20 | 11-Mar-19 | 21-Mar-19 | 21-Mar-19 |  | Filler |  | 0
451935 | 1439 Main St E | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dragojevic, Igor | 24-Jan-19 |  |  | 24758.49 | 16174.54 | 22495.78 | 24758.49 | Koeppe, Jeffrey |  | 13-Mar-19 | 24-Aug-20 | 08-Mar-19 | 17-Mar-19 | 17-Mar-19 |  | Customer |  | 2,262.71
451832 | 56 Price Ave | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Montgomery, Michael | 20-Nov-18 |  |  | 23158.62 | 21073.52 | 23158.62 | 23158.62 | Koeppe, Jeffrey |  | 08-Jan-19 | 24-Aug-20 | 02-Jan-19 | 21-Jan-19 | 25-Jan-19 |  | MC/PUCC Permit |  | 0
451579 | 287 Old Guelph Rd, Dundas | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 1348.73 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 24-Aug-20 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
452090 | Bell Make Ready - Winchester Blvd | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 02-Apr-19 |  |  | 8343.42 | 8136.58 | 8343.42 | 8343.42 | XPopiel, Joseph |  | 22-May-19 | 19-May-20 | 21-May-19 | 10-Jun-19 | 12-Jul-19 |  | Locates |  | 0
451782 | 820 Rymal Rd. E | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 | 0 | 0 | Weaver, Thomas |  |  | 25-Jun-18 | [6 empty] | 0
633827 | 970 PARAMOUNT DR - VALLEY PARK LIBRARY UPGRADE | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2021 | Paesano, Andrew | Bharosi, Mohindra | 16-Sep-20 |  |  | 62909.72 | 61541.5 | 62909.72 | 62909.72 | Roy Owen | Fairway | 26-Oct-20 | 26-Jul-23 | 19-Oct-20 | 22-Jan-21 | 26-Apr-21 | Customer | Customer |  | 0
451934 | 3 Green Mountain Rd W | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 07-May-19 |  |  | 46796.12 | 52419.82 | 46796.12 | 46796.12 | Koeppe, Jeffrey | GUCI | 14-Aug-19 | 26-Jul-23 | 05-Aug-19 | 15-Aug-19 | 16-Sep-19 | Customer | Customer |  | 0
451318 | 1670 Garth St, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 19-Jul-17 |  |  | 60457.21 | 69250.83 | 59214.34 | 60457.21 | Roy Owen |  | 06-Sep-17 | 26-Jul-23 | 01-Sep-17 | 03-Jan-18 | 08-Nov-19 | Customer | Customer |  | 1,242.87
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | 830 - St. Catharines | 150579 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Karan, Andjelo | 01-Nov-19 | 3 |  | 2020150.47 | 2311987.74 | 1739814.7 | 2020150.47 | Brad Carr | K-Line | 25-Jun-21 | 22-Sep-22 | 11-Jan-21 | 04-Jan-21 | 26-Aug-21 |  | MC/PUCC Permit |  | 280,335.77
633227 | KENILWORTH TS - STATION UPGRADE | 820 - Nebo | 150587 | Inactive | 99 | COMPLETE |  |  | 2022 | Braletic, Bob | Lustrinelli, Mark | 16-Aug-21 |  |  | 1287508.79 | 1324793.21 | 1059640.5 | 1287508.79 | Tony Ierace |  | 30-Dec-21 | 22-Sep-22 | 23-Aug-21 | 01-Sep-21 | 04-Feb-22 | Lines | N/A |  | 227,868.29
451731 | 425 Glendale Ave | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Lustrinelli, Mark | 17-May-19 |  |  | 2649.22 | 2729.76 | 2649.22 | 2649.22 | Frank Giancola |  | 26-Jun-19 | 17-Aug-22 | 26-Jun-19 | 25-Jul-19 | 25-Jul-19 | Customer | Customer |  | 0
451831 | 95 Howard St. Lynden | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Faisal | Montgomery, Michael | 06-May-19 |  |  | 24052.43 | 35241.49 | 24052.43 | 24052.43 | Koeppe, Jeffrey |  | 14-Jun-19 | 17-Jan-22 | 10-Jun-19 | 22-Jun-19 | 02-Aug-19 | Locates | Locates |  | 0
451628 | 1212 MAIN ST - MAPLE AVE UPGRADE | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE | Medium | Infrast | 2021 | Jakubowski, Mark | Jolie, Chris | 21-Feb-20 |  |  | 999618.35 | 834947.45 | 971160.47 | 999618.35 | Carr, Brad | K-Line | 24-Jul-20 | 15-Sep-21 | 06-Apr-20 | 16-Mar-20 | 13-Jan-21 |  | Control/SCADA |  | 28,457.88
451883 | 11 Oriole Ave - Stoney Creek | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Djuric, Zdravko | 03-Dec-18 |  |  | 40433.59 | 41024.84 | 40433.59 | 40433.59 | Koeppe, Jeffrey |  | 23-Jan-19 | 15-Jul-21 | 15-Jan-19 | 11-Jan-19 | 09-Dec-19 |  | Customer |  | 0
451578 | 959 Upper James St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 03-Jun-19 |  |  | 34842.07 | 28801.85 | 34842.07 | 34842.07 | Koeppe, Jeffrey |  | 26-Jul-19 | 15-Jul-21 | 15-Jul-19 | 12-Jul-19 | 29-Aug-19 |  | Customer |  | 0
451381 | 315 Glendale Ave | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dragojevic, Igor | 15-May-19 |  |  | 0 | 45366.34 |  | 0 | Weaver, Thomas |  | 15-May-19 | 24-Aug-20 | 15-May-19 | 15-May-19 | 15-May-19
452144 | GRANTHAM SS - DECOMMISSIONING | 830 - St. Catharines | 151105 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Jun-19
451513 | 1911 Barton St E | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Hotham, Matthew |  |  | 27-Aug-17
451577 | 11-15 Cannon St W, Hamilton | 820 - Nebo | 150449 | Active | HO | ACTIVE | High | Res-ICI | 2023 | Kappheim, Adam | Bennett, Aaron | 15-May-19 |  |  | 111065.94 | 73976.74 | 111065.94 | 111065.94 | Macdougall, Stephen |  | 25-Mar-22 | 09-Aug-23 | 14-Mar-22 | 02-Jun-19 |  | MC/PUCC Permit | Customer |  | 0
451680 | Brampton LRT | 820 - Nebo | 150490 | Inactive | 99 | CANCELLED |  |  | 2022 | Tobin, Michael | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Feb-23
451380 | 64 Main St East, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 06-Jun-22
451313 | Upper Wentworth & Rymal Rd E, Ham | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 11-May-17 |  |  | 1826.42 | 0 | 1648.28 | 1826.42 | Brad Carr |  | 01-Sep-17 | 01-Dec-21 | 01-Sep-17 | 03-Jun-21 | 03-Jun-21 | Customer | Customer |  | 178.14
451250 | Re-banding 491X and 492X | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 10565.39 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 01-Jun-20 | 28-May-19 | 28-May-19 | 28-May-19
452143 | VINE SS - DECOMMISSIONING | 830 - St. Catharines | 151105 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Jun-19
451512 | Passages Along The Canal - Block 34 | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 | 0 | 0 | Hotham, Matthew |  |  | 14-Aug-17 | [6 empty] | 0
452087 | 115 Hamilton St N, Waterdown | 820 - Nebo | 150449 | Active | 98 | COMPLETE | Medium | Grocery | 2021 | Kappheim, Adam | Bennett, Aaron | 17-Feb-20 |  |  | 56292.94 | 49128.64 | 56292.94 | 56292.94 | Roy Owen |  | 03-Apr-20 | 26-Jul-23 | 01-Apr-20 | 22-Jan-21 | 04-Feb-21 | Customer | Customer |  | 0
451379 | Branthaven Dakota Phase 2 | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 25-Jul-17 |  |  | 21196.76 | 477737.27 | 20921.34 | 21196.76 | Tony Ierace |  | 11-Sep-17 | 07-Feb-23 | 21-Aug-17 | 07-Aug-17 | 20-Aug-19 |  | Customer |  | 275.42
452142 | SC752 - Removal | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 31-Oct-19 |  |  | 15599.63 | 25102.27 | 15599.63 | 15599.63 | Tony Ierace | N/A | 11-Nov-21 | 22-Sep-22 | 04-Nov-21 | 18-Jan-22 | 25-Jan-22 | Lines | Lines |  | 0
451249 | 224 James St S Temp Disc OT | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Johnson, William | 28-May-19 |  |  | 0 | 6250.99 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 09-Aug-22 | 28-May-19 | 28-May-19 | 28-May-19
451312 | 78 Philomena Dr, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 07-Mar-17 |  |  | 1268.79 | 0 | 1268.79 | 1268.79 | Brad Carr |  | 31-Mar-17 | 06-Jun-22 | 31-Mar-17 | 03-Jun-21 | 03-Jun-21 | Customer | Customer |  | 0
451881 | 89 Osler Dr - Dundas | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Djuric, Zdravko | 12-Dec-18 |  |  | 12863.55 | 11679.47 | 12863.55 | 12863.55 | Roy Owen | Clrway | 31-Jan-19 | 22-Mar-21 | 29-Jan-19 | 07-Feb-19 | 06-Jun-19 |  | Customer |  | 0
451151 | Rymal Rd East & Hwy 20 | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 13-Oct-15 |  |  | 18408.38 | 12992.62 | 18408.38 | 18408.38 | Brian Robinson |  | 25-Nov-15 | 16-Feb-21 | 16-Nov-15 | 20-Nov-15 | 27-Sep-19 |  | Customer |  | 0
633822 | NEWTON TS - T2 REPLACEMENT WORK | 820 - Nebo | 151090 | Inactive | 99 | COMPLETE |  |  | 2019 | Braletic, Bob | Lustrinelli, Mark | 25-Oct-19 |  |  | 53204.35 | 34146.63 | 53204.35 | 53204.35 | Roy Owen |  | 22-Nov-19 | 05-Nov-20 | 18-Nov-19 | 14-Nov-19 | 26-Nov-19 |  | Customer |  | 0
451932 | 34 Windemere Rd | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dragojevic, Igor | 01-Mar-19 |  |  | 5886.27 | 7971.05 | 5886.27 | 5886.27 | Koeppe, Jeffrey |  | 12-Apr-19 | 24-Aug-20 | 11-Apr-19 | 11-Apr-19 | 11-Apr-19 |  |  |  | 0
451779 | Kinrade UG Service Install | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 05-Nov-18 |  |  | 36424.73 | 35038.99 | 36424.73 | 36424.73 | XPopiel, Joseph |  | 25-Feb-19 | 24-Aug-20 | 11-Feb-19 | 09-Apr-19 | 03-May-19 |  | Customer |  | 0
452034 | ANIMAL GUARDING-ANNUAL PROGRAM-WEST | 820 - Nebo | 150623 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 28-Jan-19
451311 | 36 Ditton Dr, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 23-Oct-18 |  |  | 64174.97 | 57555.82 | 56313.87 | 64174.97 | Tony Ierace | GUCI | 21-Dec-18 | 26-Jul-23 | 14-Dec-18 | 28-Oct-19 | 20-Nov-19 | Customer | Customer |  | 7,861.10
451728 | 49 COLLEGIATE AVE, STONEY CREEK | 820 - Nebo | 150456 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 07-Oct-20 |  |  | 105171.62 | 99571.59 | 105171.62 | 105171.62 | Macdougall, Stephen | Fairway | 26-Feb-21 | 22-Sep-22 | 30-Nov-20 | 23-Nov-20 | 11-Jun-21 |  | Customer |  | 0
451435 | 41 MOFFATT STREET - DEVELOPMENT | 830 - St. Catharines | 150588 | Inactive | 99 | CANCELLED |  |  | 2022 | Velickovski, Goran | Paesano, Andrew |  |  |  | 0 | 0 | 0 | 0 | Jakubowski, Mark |  |  | 11-Jul-22 | [6 empty] | 0
451981 | Baldwin Conversion - Civil Work | 820 - Nebo | 150309 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Karan, Andjelo | 20-Dec-18 |  |  | 1106417.99 | 1618119.41 | 953306 | 1106417.99 | Scott Borer | B&M | 08-Mar-19 | 08-Mar-21 | 24-Dec-18 | 21-Jan-19 | 18-Dec-19 | Control/SCADA | Control/SCADA |  | 153,111.99
451150 | Dundas St Subdivision | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 23-Mar-17 |  |  | 81793.87 | 226345.99 | 81108.16 | 81793.87 | Brian Robinson |  | 02-Nov-18 | 28-Dec-20 | 29-Oct-18 | 15-Aug-17 | 29-Jan-19 |  | Customer |  | 685.71
451510 | Eringate Court - Development | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark | 20-Aug-18 |  |  | 13387.75 | 8463.59 | 13387.75 | 13387.75 | Andrew Mehlenbacher |  | 19-Oct-18 | 24-Aug-20 | 09-Oct-18 | 27-Nov-18 | 27-Feb-19 |  | Customer |  | 0
451248 | V3578 | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 522.17 |  | 0 | Hewitson, Trevor |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451879 | 118 Glenridge Ave, St. Catharines | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 03-Dec-18 |  |  | 61328.85 | 63093.38 | 57038.39 | 61328.85 | Frank Giancola | Wiens | 29-Jan-19 | 26-Jul-23 | 02-Jan-19 | 18-Dec-18 | 04-Jul-19 |  | Customer |  | 4,290.46
451574 | New Fourth Ave Road Subdivision | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Velickovski, Goran | Morris, Mark | 14-Sep-18 |  |  | 5791.73 | 4010.61 | 5791.73 | 5791.73 | Carr, Brad |  | 02-Nov-18 | 24-May-23 | 29-Oct-18 | 16-Apr-19 | 04-Sep-19 | Customer | Customer |  | 0
452140 | CENTRAL - ST JAMES PL- 16664 (2020) | 820 - Nebo | 150352 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Wardell, Paul | 16-Feb-21 |  |  | 1000752.3 | 1058346.96 | 1076793.8 | 1000752.3 | Brad Carr | B&M | 13-Aug-21 | 22-Sep-22 | 12-Apr-21 | 19-Apr-21 | 01-Oct-21 | Contractor | Customer |  | -76,041.50
451310 | 1361 Upper Sherman Ave, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 07-Dec-16 |  |  | 2685.52 | 0 | 2670.06 | 2685.52 | Andrew Mehlenbacher |  | 30-Dec-16 | 06-Jun-22 | 29-Dec-16 | 30-Oct-18 | 03-Jun-21 | Customer | Customer |  | 15.46
451827 | 1096 Barton St. East | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Faisal | Montgomery, Michael | 27-Feb-19 |  |  | 46499.68 | 45508.23 | 46499.68 | 46499.68 | Koeppe, Jeffrey |  | 15-Apr-19 | 16-Jan-22 | 01-Apr-19 | 29-Mar-19 | 18-Jun-19 |  | Customer |  | 0
451930 | 97 Third Rd E | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Dragojevic, Igor | 27-Nov-18 |  |  | 22100.52 | 40292.81 | 22100.52 | 22100.52 | Koeppe, Jeffrey |  | 07-Jan-19 | 15-Jul-21 | 02-Jan-19 | 27-Dec-18 | 19-Apr-19 |  | Customer |  | 0
633705 | DEERHURST CONVERSION PART 2 - KILLBOURN AVE OH | 820 - Nebo | 150317 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 24-Sep-19
451247 | Fourth Ave - 3-PH Extension | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2023 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 29-Mar-16
451145 | City of Hamilton 3rdParty Transfers | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 09-Apr-15
451573 | WALNUT/JACKSON FEEDER EXPANSION | 820 - Nebo | 150665 | Active | 98 | COMPLETE | High | Res-ICI | 2021 | Jakubowski, Mark | Jolie, Chris | 04-Feb-21 |  |  | 659790.45 | 690508.9 | 657393.61 | 659790.45 | Brad Carr | B&M | 13-May-21 | 26-Jul-23 | 22-Feb-21 | 22-Feb-21 | 10-Jun-21 |  | Contractor |  | 2,396.84
452139 | U/G PEDESTAL REPLACEMENT 2022 (15 PEDS) | 830 - St. Catharines | 151064 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 07-Oct-21 | 15 | 15 | 104035.35 | 75006.12 | 104035.35 | 104035.35 | Frank Giancola |  | 30-Jun-22 | 22-Sep-22 | 15-Nov-21 | 22-Nov-21 | 24-May-22 | Materials | Materials |  | 0
452084 | 15 Queen St S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 18-Jun-19 |  |  | 6206.17 | 4701.41 | 6206.17 | 6206.17 | Koeppe, Jeffrey | Fairway | 09-Jul-19 | 17-Jan-22 | 08-Jul-19 | 22-Jul-19 | 30-Jul-19 |  | Customer |  | 0
451878 | Baldwin #2 Overhead Conversion Ph 1 | 820 - Nebo | 150269 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 26-Nov-18 |  |  | 692773.31 | 715966.38 | 635998.65 | 692773.31 | Carr, Brad | K-Line | 30-Apr-19 | 14-Dec-20 | 04-Feb-19 | 04-Feb-19 | 18-Jul-19 |  | Contractor |  | 56,774.66
451928 | 2 Reservoir Road - Stoney Creek | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Anderson, Dean | 03-Jan-19 |  |  | 170418.57 | 36400.84 | 170418.57 | 170418.57 | XPopiel, Joseph |  | 05-Apr-19 | 24-Aug-20 | 18-Feb-19 | 25-Jan-19 | 19-Mar-19 |  |  |  | 0
451676 | 405 Merritt St, St Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 24-Apr-19 |  |  | 44664.04 | 47245.37 | 44664.04 | 44664.04 | Frank Giancola | Wiens | 11-Jun-19 | 24-Aug-20 | 03-Jun-19 | 29-May-19 | 11-Jul-19 |  | Customer |  | 0
451433 | Cable Replacement on MacTurnbull Dr | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Rolfe, Eric | 28-Jun-18 |  |  | 222137 | 155870.16 | 212076.75 | 290137 | Frank Giancola |  | 12-Sep-18 | 24-Aug-20 | 23-Jul-18 | 17-Aug-18 | 15-Mar-19 |  | MC/PUCC Permit |  | 78,060.25
451246 | 129 Rebecca St | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 586.74 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451144 | Cogeco Third Party Transfers | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 09-Apr-15
451622 | Lake 121X circuit - Cond. Upgrade | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Sep-22
451775 | 3 Rivercrest Dr, St Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Gamboa, Henry | Morris, Mark | 25-Jun-18 |  |  | 2968.22 | 0 | 2968.22 | 2968.22 | Frank Giancola |  | 27-Jul-18 | 03-Feb-22 | 26-Jul-18 | 02-Aug-18 |  | Customer | Customer |  | 0
451927 | Skinner Rd - pad re-location | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Celic, Dusan | 17-Jan-19 |  |  | 118712.87 | 62747.8 | 118712.87 | 118712.87 | Brad Carr | B&M | 29-Nov-19 | 03-Aug-21 | 22-Apr-19 | 23-Apr-19 | 25-Feb-21 | Customer | Customer |  | 0
451978 | SCH 2019 Pole Resduals - Part 1 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 04-Apr-19 |  |  | 35400.09 | 28949.71 | 35400.09 | 35400.09 | Frank Giancola |  | 30-Oct-19 | 08-Mar-21 | 27-May-19 | 07-May-19 | 09-Sep-19 |  | Filler |  | 0
452030 | Relocate Hydro Pole - Baldwin St | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 26-Jul-19 |  |  | 47261.22 | 48823.22 | 47261.22 | 47261.22 | Carr, Brad | K-Line | 30-Aug-19 | 08-Feb-21 | 26-Aug-19 | 14-Oct-19 | 26-Nov-19 |  | Locates |  | 0
451571 | 1318 Rymal Rd.E | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 24-Jan-19 |  |  | 85121.86 | 77101.6 | 85121.86 | 85121.86 | Roy Owen |  | 01-Apr-19 | 16-Nov-20 | 04-Mar-19 | 08-Feb-19 | 05-Apr-19 |  | Customer |  | 0
451431 | 2017 Cogeco Permit Review | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 22-Jan-18 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 22-Jan-18 | 24-Aug-20 | 22-Jan-18 | 22-Jan-19 | 22-Jan-19
451877 | 57 Carlisle Dedicated Feeder | 830 - St. Catharines | 152381 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Johnson, William |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-Aug-18
451143 | Rogers Third Party Transfers | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 09-Apr-15
633651 | 2 BOLD ST, HAMILTON | 820 - Nebo | 150665 | Active | 98 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Patel, Ketan | 06-Jul-20 |  |  | 12473.1 | 9428.74 | 12473.1 | 12473.1 | Brian Robinson |  | 07-Mar-22 | 26-Jul-23 | 07-Mar-22 | 08-Mar-21 | 20-Dec-22 | Customer | Customer |  | 0
451570 | 1280 RYMAL RD E | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2022 | Kappheim, Adam | Oosterlinck, David | 24-Jun-21 |  |  | 321452.7 | 446616.27 | 321452.7 | 321452.7 | Roy Owen |  | 22-Oct-21 | 26-Jul-23 | 02-Aug-21 | 29-Jul-21 | 18-Feb-22 |  | Customer |  | 0
451371 | 2017 HCE Telecomm Work | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2019 | Vande Kuyt, Greg | Jolie, Chris | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-22 | 28-May-19 | 28-May-19 | 28-May-19
451140 | Bell Canada Third Party Transfers | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 22-Aug-22
451305 | PETRIE ST. AND SMITH ST. | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 11-Mar-21 |  |  | 91688.26 | 103895.24 | 91688.26 | 91688.26 | Dan Despres |  | 15-Oct-21 | 14-Feb-22 | 20-Sep-21 | 01-Oct-21 | 05-Nov-21 | Locates | Locates |  | 0
451876 | 20 Gale Cres, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Nov-21
451430 | 5th Concession - Phase 3 | 820 - Nebo | 150696 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Billone, Justin | 12-Oct-18 |  |  | 1586081 | 1724943.96 | 1531116.7 | 1586081 | Carr, Brad | B&M | 08-Nov-19 | 08-Mar-21 | 12-Nov-18 | 26-Nov-18 | 26-Nov-19 | MC/PUCC Permit | N/A |  | 54,964.30
452029 | Central 3 conv (2018 carry-over) | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Wardell, Paul | 01-May-19 |  |  | 46396.2 | 318707.41 |  | 46396.2 | Carr, Brad |  | 15-Feb-19 | 08-Mar-21 | 07-Jan-19 | 26-Apr-19 | 26-Apr-19 | N/A | N/A
451926 | Henley Dr. Rear Yard Rebuild | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 14-Dec-18 |  |  | 103912.64 | 108547.39 | 103912.64 | 103912.64 | Dan Despres |  | 10-May-19 | 08-Mar-21 | 01-Apr-19 | 26-Feb-19 | 20-Jun-19 |  | Contractor |  | 0
452137 | White Gates Dr (FLA) | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-May-19
451505 | PASSAGES ALONG THE CANAL - BLOCK 33 - SUB RES EDS | 830 - St. Catharines | 150588 | Active | 50 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 | 0 | 0 | Hotham, Matthew |  |  | 31-Jul-17 | [6 empty] | 0
451244 | RFC template | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Caucci, Jason |  |  | 14-Mar-16
451620 | 2018 Bell Permit Reviews | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 09-Apr-19 |  |  | 0 | 22463.4 |  | 0 | Weaver, Thomas |  | 09-Apr-19 | 09-Aug-22 | 09-Apr-19 | 09-Apr-19 | 09-Apr-19
452136 | Pole Line Relocate - Mountain Brow | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 30-Aug-19 |  |  | 381826.9 | 422111.61 | 314029.89 | 381826.9 | Carr, Brad | K-Line | 08-Nov-19 | 30-Nov-20 | 30-Sep-19 | 16-Sep-19 | 26-Nov-19 |  | Locates |  | 67,797.01
451304 | Pole Replacement - 34 Bayview Dr | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 28-Aug-19 |  |  | 21225.97 | 29641.04 | 21225.97 | 21225.97 | Dan Despres |  | 17-Oct-19 | 22-Oct-20 | 15-Oct-19 | 21-Oct-19 | 30-Oct-19 |  | Customer |  | 0
451569 | 158 Herkimer St | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 5785.46 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 24-Aug-20 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
452028 | SS VARIOUS IMPROVEMENTS 2019 | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 07-Jan-19
451243 | Hamilton LBDS Replacements - 2016 | 820 - Nebo | 150337 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 07-Mar-16
451772 | RAVENSCLIFFE U/G & REAR LOT CONVERSION | 820 - Nebo | 150351 | Active | 93 | ACTIVE |  |  | 2022 | Beaudrie, Scott | Anderson, Dean | 16-Dec-21 |  |  | 2183520.46 | 2132667.19 | 2101447.56 | 2183520.46 | Brad Carr | B&M | 09-Sep-22 | 26-Jul-23 | 07-Mar-22 | 28-Apr-22 | 28-Dec-22 | Contractor | Contractor |  | 82,072.90
451135 | Waste Water Treatment Plant | 820 - Nebo | 150665 | Active | 98 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Patel, Ketan | 29-Jun-18 |  |  | 500103.92 | 936804.26 | 504058.03 | 500103.92 | Tony Ierace | B&M | 01-Feb-22 | 26-Jul-23 | 01-Feb-22 | 15-Jan-19 | 04-Feb-22 | Customer | Customer |  | -3,954.11
451300 | TX Move Ottawa St -Constellation Dr | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 18-Jul-22
451874 | 139 Oakdale Ave, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Nov-21
451369 | Upper Mount Albion - Overhead | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 25-Sep-18 |  |  | 442266.72 | 420024.65 | 426961.48 | 442266.72 | XPopiel, Joseph |  | 05-Apr-19 | 14-Dec-20 | 29-Oct-18 | 26-Nov-18 | 26-Sep-19 |  | MC/PUCC Permit |  | 15,305.24
451924 | 2350 Third St. Louth | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Laus, Tomislav | 15-Feb-19 |  |  | 26994.3 | 22842.28 | 26994.3 | 26994.3 | Frank Giancola |  | 18-Mar-19 | 24-Aug-20 | 11-Mar-19 | 21-Feb-19 | 18-Mar-19 |  | Customer |  | 0
452135 | Pole Relocate - Kimberly Drive | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 02-Aug-19 |  |  | 13033.86 | 19518 | 13033.86 | 13033.86 | XPopiel, Joseph |  | 06-Sep-19 | 20-Jul-20 | 04-Sep-19 | 25-Nov-19 | 27-Nov-19 |  | Locates |  | 0
451134 | 84 James St, St. Catharines | 830 - St. Catharines | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan | 27-Mar-17 |  |  | 18522.35 | 8905.69 | 18506.89 | 18522.35 | Frank Giancola | Wiens | 01-Feb-22 | 27-Sep-22 | 01-Feb-22 | 13-Jun-17 |  | Customer | Customer |  | 15.46
451873 | 11 Hillgarden Rd, St. Catharines | 820 - Nebo | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Nov-21
451367 | 433 Linwell Rd. | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 17-Aug-18 |  |  | 38233.93 | 50473.02 | 35801.93 | 38233.93 | Dan Despres | GUCI | 10-Oct-18 | 08-Mar-21 | 01-Oct-18 | 05-Nov-18 | 20-Jun-19 | Customer | Customer |  | 2,432.00
451923 | 15 Yale Cres, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 15-Feb-19 |  |  | 68360.67 | 68904.51 | 68360.67 | 68360.67 | Frank Giancola | Wiens | 26-Mar-19 | 24-Aug-20 | 18-Mar-19 | 13-Mar-19 | 30-May-19 |  | Customer |  | 0
451427 | 177 Sherman Ave. N | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Montgomery, Michael | 13-Feb-19 |  |  | 27794.52 | 34773.48 | 27794.52 | 27794.52 | Koeppe, Jeffrey |  | 25-Mar-19 | 24-Aug-20 | 18-Mar-19 | 01-Mar-19 | 15-Apr-19 |  | Customer |  | 0
451821 | PIER 8 - WATERFRONT DEVELOPMENT - SUBD ICI EDS | 820 - Nebo | 151652 | Active | 50 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 | 0 | 0 | Weaver, Thomas | Transpw |  | 25-Jun-18 | [6 empty] | 0
451232 | Myrtle Ave Rebuild | 830 - St. Catharines | 150335 | Inactive | 99 | CANCELLED |  |  | 2023 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Dan Despres |  |  | 23-Mar-23
451770 | RIVERVIEW DRIVE REAR LOT CONVERSION | 820 - Nebo | 150496 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 04-Jan-23 |  |  | 0 | 3666.44 |  | 0 | Brad Carr |  | 04-Jan-23 | 16-Mar-23 | 04-Jan-23 | 04-Jan-23 | 04-Jan-23
451872 | 40 Lighthouse Rd, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-Jun-22
451132 | Residual Poles - East Downtown 2016 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Karan, Andjelo | 31-Mar-15 |  |  | 60999.92 | 99090.27 | 51665.84 | 60999.92 | Koeppe, Jeffrey |  | 28-Apr-17 | 14-Feb-22 | 16-Jan-17 | 09-Jan-17 | 15-Jan-21 |  | Filler |  | 9,334.08
451922 | 110 Gordon Drummond Ave TX Relocate | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Karan, Andjelo | 07-Jan-19 |  |  | 47352.74 | 57858.47 | 47352.74 | 47352.74 | Andrew Mehlenbacher |  | 15-Feb-19 | 04-Oct-21 | 07-Feb-19 | 25-Feb-19 | 27-May-19 | Customer | Customer |  | 0
451617 | Hamilton 2018 Pole Residuals | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 06-Jul-18 |  |  | 63908.61 | 87267.06 | 63908.61 | 63908.61 | Koeppe, Jeffrey |  | 15-May-19 | 14-Dec-20 | 29-Apr-19 | 23-Apr-19 | 12-Dec-19 |  | Filler |  | 0
451670 | MH39A - New Roof | 820 - Nebo | 151065 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 16-Mar-18
451501 | 131 Rockwood Ave URD - SCH | 830 - St. Catharines | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 24-Jul-17
451298 | 1764 South Servic Rd (sch) | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2023 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 08-Aug-16
451500 | 33 Berkley Drive URD - SCH | 830 - St. Catharines | 150496 | Inactive | 99 | CANCELLED |  |  | 2023 | Beaudrie, Scott | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 23-Mar-23
451921 | Bunting M75 Reliability - Part 2 | 830 - St. Catharines | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Sep-22
451363 | October Dr URD (St. Catharines) | 830 - St. Catharines | 151066 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Karan, Andjelo | 10-Aug-18 |  |  | 1066044.1 | 1351742.66 | 786782.06 | 1066044.1 | Carr, Brad | B&M | 30-Nov-18 | 08-Mar-21 | 17-Sep-18 | 29-Oct-18 | 21-Jun-19 | Locates | Contractor |  | 279,262.04
451616 | Hamilton 2018 Pole Residuals | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 06-Jul-18 |  |  | 61107.04 | 76848.63 | 66257.32 | 61107.04 | Koeppe, Jeffrey |  | 31-Dec-19 | 14-Dec-20 | 18-Mar-19 | 20-Feb-19 | 16-Dec-19 |  | Filler |  | -5,150.28
451130 | Fontana Gardens Phase 3 | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 250.68 |  | 0 | Tony Ierace |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451231 | 29 Linden St | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 402.74 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451769 | Central Conversion - Phase 8 | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 28-May-18
451768 | CENTRAL CONVERSION - PHASE 7 | 820 - Nebo | 150352 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 27-Mar-23 |  |  | 683072.92 | 242256.58 | 683072.92 | 683072.92 | Brad Carr | B&M | 25-Sep-23 | 25-Sep-23 | 03-Jul-23 | 17-Jul-23 |  | Materials | Materials |  | 0
451563 | 49 WALNUT ST.S (CONDO) | 820 - Nebo | 150449 | Active | 98 | COMPLETE | VerHigh | Res-ICI | 2021 | Kappheim, Adam | Oosterlinck, David | 05-Feb-21 |  |  | 15759.62 | 21264.75 | 15759.62 | 15759.62 | Roy Owen |  | 12-Mar-21 | 26-Jul-23 | 08-Mar-21 | 20-Apr-21 | 26-Apr-21 | Customer | Customer |  | 0
451818 | 50 LEAVITT BLVD(FORMERLY 36-42 DUNDAS ST.E) - WESCAM BUILDING | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | High | Infrast | 2021 | Kappheim, Adam | Oosterlinck, David | 14-Oct-20 |  |  | 19590.69 | 22237.11 | 19590.69 | 19590.69 | Roy Owen |  | 01-Dec-20 | 22-Sep-22 | 23-Nov-20 | 10-Mar-21 | 01-Apr-21 | Customer | Customer |  | 0
451615 | Hamilton 2018 Pole Residuals - 3 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 06-Jul-18 | 3 |  | 103102.77 | 96089.26 | 88861.67 | 103102.77 | Brian Robinson | K-Line | 13-Dec-18 | 16-Aug-21 | 19-Nov-18 | 29-Aug-18 | 30-Apr-21 | Filler | Filler |  | 14,241.10
451362 | 5272x - 0622x tie - CE conversion | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Wardell, Paul | 31-Aug-18 |  |  | 363827.32 | 400143.74 | 319337.7 | 363827.32 | Roy Owen |  | 07-Dec-18 | 14-Dec-20 | 01-Oct-18 | 03-Dec-18 | 09-Aug-19 | Contractor | Control/SCADA |  | 44,489.62
452131 | 24 King St West | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 07-Jun-19 |  |  | 4832.55 | 1225.62 | 4832.55 | 4832.55 | XPopiel, Joseph |  | 28-Jun-19 | 14-Dec-20 | 27-Jun-19 | 09-Aug-19 | 09-Aug-19 | Customer | Customer |  | 0
451668 | OH Recloser Replacement Project | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Billone, Justin | 13-Jun-18 |  |  | 134039.37 | 190076.51 | 134039.37 | 134039.37 | Brian Robinson |  | 15-May-19 | 24-Aug-20 | 09-Jul-18 | 24-Jul-18 | 17-Apr-19 |  | Filler |  | 0
451920 | Cogeco Make Ready - Central PH1 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 11-Jan-19 |  |  | 6646.12 | 6707.27 | 6646.12 | 6646.12 | Carr, Brad |  | 20-Feb-19 | 24-Aug-20 | 20-Feb-19 | 12-Feb-19 | 12-Feb-19 |  |  |  | 0
451129 | 2015 Pole removals Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 03-Feb-15
451717 | 99 Lincoln Rd, Stoney Creek | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 24-May-19 |  |  | 73624.34 | 85078.39 | 73624.34 | 73624.34 | Koeppe, Jeffrey | GUCI | 30-Jul-19 | 26-Jul-23 | 08-Jul-19 | 17-Jul-19 | 22-Nov-19 | Locates | Locates |  | 0
451767 | CENTRAL CONVERSION - PHASE 6A (2023 WORK) | 820 - Nebo | 150352 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 18-Nov-22 |  |  | 1238371.56 | 567841.55 | 1200431.23 | 1238371.56 | Brad Carr | K-Line | 30-Jun-23 | 02-Oct-23 | 03-Apr-23 | 27-Mar-23 |  |  | Customer |  | 37,940.33
451497 | 592 Old Dundas Rd, Ancaster - S.T.P | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2021 | Kappheim, Adam | Bennett, Aaron | 22-Sep-20 |  |  | 80929.15 | 72274.05 | 80929.15 | 80929.15 | Roy Owen | B&M | 30-Oct-20 | 26-Jul-23 | 26-Oct-20 | 16-Nov-20 | 25-Aug-21 | Customer | Customer |  | 0
451614 | 2019 Ridley Heights Area Rebuild | 830 - St. Catharines | 150381 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 26-Nov-18 |  |  | 292635.81 | 214351.57 | 292635.81 | 292635.81 | Dan Despres | B&M | 18-Mar-19 | 08-Mar-21 | 02-Jan-19 | 21-Jan-19 | 06-Nov-19 | Locates | Contractor |  | 0
451562 | Hilda Street- Pole Replacement- | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 01-May-19 |  |  | 61346.69 | 82447.49 | 61346.69 | 61346.69 | Dan Despres |  | 17-Oct-19 | 14-Dec-20 | 01-Oct-19 | 26-Sep-19 | 13-Dec-19 |  | Lines |  | 0
451667 | Rymal Rd W - Road Work Deficiencies | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Vande Kuyt, Greg | Jolie, Chris | 28-Nov-19 |  |  | 0 | 15701.38 |  | 0 | Weaver, Thomas | N/A | 28-Nov-19 | 24-Aug-20 | 28-Nov-19 | 28-Nov-19 | 28-Nov-19
451295 | Killarney Circle Duct & Pad Rebuild | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 25-Jul-16
451716 | 1053 Barton St, Stoney Creek | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 02-Apr-19 |  |  | 67936.23 | 70750.24 | 67936.23 | 67936.23 | Koeppe, Jeffrey | GUCI | 31-May-19 | 26-Jul-23 | 21-May-19 | 31-May-19 | 18-Sep-19 | Customer | Customer |  | 0
451766 | CENTRAL CONVERSION - PHASE 5 | 820 - Nebo | 150352 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 06-Dec-22 |  |  | 1573765.76 | 1142222.58 | 1573765.76 | 1573765.76 | Brad Carr | B&M | 14-Aug-23 | 14-Aug-23 | 16-Feb-23 | 20-Feb-23 |  | Locates | Materials |  | 0
451666 | ABERDEEN #2 SUBSTATION WORK | 820 - Nebo | 150351 | Active | 80 | PDG SnR |  |  | 2023 | Beaudrie, Scott | Anderson, Dean | 01-May-19 |  |  | 12241.39 | 1060.39 | 12241.39 | 12241.39 | Tony Ierace |  |  | 26-Jul-23 | [6 empty] | 0
451359 | PORT MASTER AREA URD REBUILD | 830 - St. Catharines | 150496 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Rolfe, Eric |  |  |  | 0 | 10699.9 |  | 0 | Jakubowski, Mark |  |  | 26-Jul-23
451294 | ROAD AUTHORITY - MOUNTAINBROW RD AND WATERDOWN RD WIDENING | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Celic, Dusan | 28-Sep-21 |  |  | 307077.65 | 301192.79 | 291048.1 | 307077.65 | Brad Carr | K-Line | 26-Nov-21 | 11-Jul-22 | 01-Nov-21 | 08-Nov-21 | 22-Apr-22 | Locates | Locates |  | 16,029.55
451969 | Burgoyne Bridge Manhole Adjustment | 830 - St. Catharines | 151065 | Inactive | 99 | CANCELLED |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 21815 |  | 0 | Weaver, Thomas |  |  | 15-Jul-21
452073 | 2019 Rogers Bonds | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 11-Mar-19 |  |  | 1065.05 | 4189.11 | 1065.05 | 1065.05 | Hewitson, Trevor |  | 30-Apr-19 | 22-Mar-21 | 30-Apr-19 | 22-Mar-19 | 28-Nov-19 |  | Filler |  | 0
451918 | Collier St and Beard Pl. | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 14-Dec-18 |  |  | 136347.74 | 163079.94 | 123377.46 | 136347.74 | Dan Despres |  | 21-Mar-19 | 08-Mar-21 | 19-Feb-19 | 28-Jan-19 | 04-Jun-19 |  | Control/SCADA |  | 12,970.28
451867 | Madison Condos | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark | 07-Feb-19 |  |  | 28129.68 | 1314689.74 | 28129.68 | 28129.68 | Carr, Brad |  | 03-Apr-19 | 14-Jan-21 | 01-Mar-19 | 01-Mar-19 | 04-Jul-19 |  | Customer |  | 0
452021 | Rogers Make Ready - Highway 8 | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 02-Apr-19 |  |  | 7108.89 | 5971.18 | 7108.89 | 7108.89 | XPopiel, Joseph |  | 10-May-19 | 24-Aug-20 | 09-May-19 | 28-Jun-19 | 12-Jul-19 |  | Locates |  | 0
451224 | 385 McNeilly Rd - CN Rail | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 2335.96 | 29062.98 | 29062.98 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19 |  |  |  | 0
451665 | Pen Centre (sch) | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 02-Apr-19 |  |  | 107355.97 | 97062.64 | 107355.97 | 107355.97 | Frank Giancola |  | 29-May-19 | 26-Jul-23 | 13-May-19 | 27-Sep-19 | 09-Dec-19 | Customer | Customer |  | 0
451917 | 103 Pelham Rd.-West Park Care Home | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 19-Mar-19 |  |  | 48796.63 | 13431.06 | 48796.63 | 48796.63 | Frank Giancola | GUCI | 13-May-19 | 12-Oct-21 | 29-Apr-19 | 02-Apr-19 | 19-Feb-21 | Customer | Customer |  | 0
451765 | Aberdeen #1 Feeder | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Anderson, Dean | 21-Dec-18 |  |  | 682823.42 | 734293.66 | 678533.42 | 682823.42 | Carr, Brad | K-Line | 26-Apr-19 | 22-Oct-20 | 04-Feb-19 | 04-Feb-19 | 29-May-19 |  | MC/PUCC Permit |  | 4,290.00
451560 | AB-2 Substation & Newton TS work | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Anderson, Dean | 18-Apr-18 |  |  | 173802.73 | 178014.3 | 173802.73 | 173802.73 | Roy Owen |  | 03-Jul-18 | 24-Aug-20 | 28-May-18 | 02-May-19 | 02-May-19 |  | Filler |  | 0
451968 | Cedarbrook Landing | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark | 10-Jun-19 |  |  | 30317.54 | 217406.33 | 30317.54 | 30317.54 | Frank Giancola |  | 31-Jul-19 | 23-Mar-20 | 22-Jul-19 | 04-Sep-19 | 08-Sep-19 |  | Customer |  | 0
451495 | 6 Lesterwood St | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Oct-17
451223 | Vault Repairs - St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Frank Giancola |  |  | 22-Feb-16
451420 | 2 Bulls Lane | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Montgomery, Michael | 05-Dec-18 |  |  | 72246.76 | 137909.32 | 72246.76 | 72246.76 | Roy Owen | Fairway | 18-Jan-19 | 17-Jan-22 | 07-Jan-19 | 06-Sep-19 | 01-Oct-19 | Customer | Customer |  | 0
452127 | 1520 Fifth St, St. Catharines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Patel, Ketan | 28-Oct-19 |  |  | 5292.99 | 5218.74 | 5292.99 | 5292.99 | Carr, Brad | Wiens | 28-Oct-19 | 24-Aug-20 | 28-Oct-19 | 28-Oct-19 | 28-Oct-19 |  |  |  | 0
451916 | Highland Rd W - Underground Civil | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 30-Oct-18 |  |  | 388842.33 | 326960.07 | 388842.33 | 388842.33 | Carr, Brad |  | 21-Dec-18 | 24-Aug-20 | 05-Nov-18 | 06-Apr-19 | 06-Apr-19 |  | Customer |  | 0
451356 | 2017 SCH LBDS Replacement Carryover | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 94280.2 |  | 0 | Jakubowski, Mark |  | 07-May-19 | 24-Aug-20 | 07-May-19 | 07-May-19 | 07-May-19
452071 | Cogeco Make Ready - John St N | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 17-May-19 |  |  | 4741.48 | 3880.29 | 4741.48 | 4741.48 | Hewitson, Trevor |  | 28-Jun-19 | 19-May-20 | 27-Jun-19 | 09-Sep-19 | 09-Sep-19 |  |  |  | 0
451763 | The Enclave Townhomes Sub | 830 - St. Catharines | 150588 | Active | 98 | COMPLETE |  |  | 2019 | Velickovski, Goran | Morris, Mark | 28-Sep-18 |  |  | 9278.37 | 150754.86 | 9278.37 | 9278.37 | Frank Giancola |  | 05-Nov-18 | 26-Jul-23 | 01-Nov-18 | 29-Jul-19 | 05-Sep-19 | Customer | Customer |  | 0
451610 | PIER 8 DEVELOPMENT EXPANSION | 820 - Nebo | 152381 | Active | HO | ACTIVE | Low | Comm | 2023 | Jakubowski, Mark | Jolie, Chris | 16-Dec-21 |  |  | 1097552.22 | 802974.13 | 1097552.22 | 1097552.22 | Tony Ierace | B&M | 04-May-22 | 26-Jul-23 | 10-Jan-22 | 31-Jan-22 |  | MC/PUCC Permit | Customer |  | 0
451115 | 2021 TX RENEWAL - KICKER TX OH - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 26-Feb-21 |  |  | 43055.45 | 44792.59 | 73093.95 | 43055.45 | Brad Carr | B&M | 07-May-21 | 12-Apr-22 | 26-Apr-21 | 18-Jun-21 | 15-Jun-21 | Locates | Locates |  | -30,038.50
451863 | 2018 Automated Switches - Part 3 | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Billone, Justin | 01-Nov-18 |  |  | 469409.92 | 514373.21 | 361033.55 | 469409.92 | Carr, Brad | K-Line | 21-Dec-18 | 15-Sep-21 | 26-Nov-18 | 07-Jan-19 | 28-Oct-19 | MC/PUCC Permit | MC/PUCC Permit |  | 108,376.37
451813 | 810 Beeforth Rd | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 13-Sep-19 |  |  | 9553.98 | 11539.98 | 9553.98 | 9553.98 | Koeppe, Jeffrey |  | 18-Oct-19 | 15-Jul-21 | 17-Oct-19 | 28-Oct-19 | 11-Nov-19 |  | Locates |  | 0
451355 | 212 Lakeport Rd (sch) | 830 - St. Catharines |  | Active | 10 | ACTIVE |  |  | 2023 | Henschel, Robert | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 05-Dec-16
451290 | NEILSON PLAZA | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2023 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 20-Jun-16
451220 | 2016 Hamilton Pole Residual | 820 - Nebo | 150335 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Koeppe, Jeffrey |  |  | 04-Jan-16
451712 | 45 King St E, Hamilton - Temp Crane | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2022 | Paesano, Andrew | Laus, Tomislav | 14-Feb-20 |  |  | 47218.03 | 48235.45 | 47218.03 | 47218.03 | Roy Owen |  | 19-Mar-20 | 26-Jul-23 | 16-Mar-20 | 11-Jun-20 | 14-Nov-22 | COVID19 | Customer |  | 0
451812 | 354 King St.W - Temp | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Oosterlinck, David | 21-Jan-20 |  |  | 46893.94 | 56390.46 | 45486.1 | 46893.94 | Roy Owen |  | 21-Feb-20 | 22-Feb-23 | 18-Feb-20 | 03-Mar-20 | 14-Nov-22 | Customer | Customer |  | 1,407.84
451114 | Bromley Gardens - Subdivision | 830 - St. Catharines | 150588 | Inactive | 99 | CANCELLED |  |  | 2022 | Velickovski, Goran | Vandekuyt, Greg |  |  |  | 0 | 0 | 0 | 0 | Destefano, Nick |  |  | 26-Jul-22 | [6 empty] | 0
451914 | Zayo Make Ready - Escarpment Climb | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED | Medium | Comm | 2021 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 38911.24 |  | 0 | Weaver, Thomas | K-Line |  | 03-Aug-21
452017 | NRBN Make Ready - Ridley Rd | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 22-Jan-19 |  |  | 2341.61 | 2568.84 | 2341.61 | 2341.61 | Dan Despres |  | 04-Mar-19 | 22-Mar-21 | 04-Mar-19 | 31-Jan-19 | 31-Jan-19 |  |  |  | 0
452125 | 22 Townline RD. West | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 21-May-19 |  |  | 26375.57 | 36238.41 | 26375.57 | 26375.57 | Dan Despres |  | 25-Jun-19 | 08-Mar-21 | 17-Jun-19 | 06-May-19 | 06-May-19 |  |  |  | 0
451862 | 2018 Pole Residual PH2 St. Cather | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 03-May-19 |  |  | 98450.85 | 56505.97 | 98450.85 | 98450.85 | Frank Giancola |  | 30-Nov-19 | 08-Mar-21 | 15-Jul-19 | 07-Oct-19 | 25-Nov-19 | Filler | Filler |  | 0
451354 | 212 Lakeport Rd, st catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Paesano, Andrew | 29-Jun-18 |  |  | 60433 | 57467.93 | 60433 | 60433 | Frank Giancola |  | 29-Aug-18 | 10-Dec-20 | 07-Aug-18 | 14-Aug-18 | 12-Feb-19 |  | Locates |  | 0
451662 | 2018 Rogers Permit Reviews | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 29-May-19 |  |  | 0 | 35192.18 |  | 0 | Weaver, Thomas |  | 29-May-19 | 24-Aug-20 | 29-May-19 | 29-May-19 | 29-May-19
451492 | 95 Jerome Park Dr, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 18-Sep-17
451811 | 354 KING ST.W - HOTEL | 820 - Nebo | 150449 | Active | 95 | ANALYZE | VerHigh | Res-ICI | 2023 | Kappheim, Adam | Oosterlinck, David | 20-Oct-22 |  |  | 50261.74 | 56476.96 | 50261.74 | 50261.74 | Roy Owen |  | 20-Jan-23 | 01-Aug-23 | 16-Jan-23 | 16-Jan-23 | 10-Feb-23 |  | Customer |  | 0
451711 | 1721 Strathearne Ave, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 02-May-19 |  |  | 11948.43 | 7649.21 | 11948.43 | 11948.43 | Koeppe, Jeffrey |  | 10-Jun-19 | 16-Jan-22 | 06-Jun-19 | 14-Jun-19 | 14-Jun-19 | Locates | Locates |  | 0
451964 | 2019 Ridley Heights ( U/G Portion) | 820 - Nebo | 150381 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 04-Apr-19 |  |  | 1773610.41 | 1715022.65 | 1679465.71 | 1773610.41 | Carr, Brad | B&M | 30-Aug-19 | 08-Mar-21 | 13-May-19 | 06-Jun-19 | 12-Dec-19 | MC/PUCC Permit | Contractor |  | 94,144.70
451861 | 2018 Automated Switches - Part 2 | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Billone, Justin | 21-Sep-18 |  |  | 100506.6 | 108745.36 | 33568.54 | 100506.6 | Dan Despres |  | 24-Oct-18 | 08-Mar-21 | 15-Oct-18 | 23-Nov-18 | 14-Jun-19 | Customer | Customer |  | 66,938.06
451913 | Rogers Make Ready - Barton St | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 26-Aug-19 |  |  | 15528.95 | 11711.39 | 15528.95 | 15528.95 | Brian Robinson |  | 02-Oct-19 | 30-Nov-20 | 30-Sep-19 | 20-Dec-19 | 20-Dec-19 |  |  |  | 0
452124 | Bell Make Ready - Kenilworth Ave | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 24-Jun-19 |  |  | 4970.07 | 2160.55 | 4970.07 | 4970.07 | XPopiel, Joseph |  | 30-Jul-19 | 16-Nov-20 | 29-Jul-19 | 29-Jul-19 | 29-Jul-19 |  |  |  | 0
451416 | 1539 fourth Ave, St Catharines | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2023 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 03-Apr-17
451113 | Green Millen Shores - East (Rec) | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Newitt, Andrew | Vandekuyt, Greg |  |  |  | 0 | 0 |  | 0 | Destefano, Nick |  |  | 14-Aug-15
451351 | 1040 Main St E (Gage Pk. Greenhse) | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Rao, Faisal | Montgomery, Michael | 21-Sep-17 |  |  | 75541.87 | 78774.88 | 75541.87 | 75541.87 | Koeppe, Jeffrey |  | 31-Oct-17 | 26-Jul-23 | 20-Oct-17 | 27-Nov-17 | 13-May-19 |  | Customer |  | 0
451285 | Welland SS 13kV Removal | 830 - St. Catharines | 151105 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 31-May-19 |  |  | 239280.53 | 0 | 229556.51 | 229556.51 | Tony Ierace | Wiens | 05-Nov-19 | 17-Aug-22 | 10-Sep-19 |  |  | Lines | Lines |  | 0
452067 | 425 Lakeshore Rd, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Nov-21
451607 | 201 St Paul St,St Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Paesano, Andrew | Morris, Mark |  |  |  | 0 | 634.8 |  | 0 | Weaver, Thomas |  |  | 15-Jul-21
451217 | 24 Ditton Dr, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 13-Jul-16 |  |  | 6292.33 | 0 | 6292.33 | 6292.33 | Andrew Mehlenbacher | GUCI | 15-Aug-16 | 01-Feb-21 | 15-Aug-16 | 05-Nov-19 | 05-Nov-19 |  | Customer |  | 0
451810 | 354 King St.W - Student Res | 820 - Nebo | 150449 | Active | 10 | ACTIVE | VerHigh | Res-ICI | 2023 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-May-19
451760 | Estimates for COS | 830 - St. Catharines | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 14-May-18
451759 | 32 Towering Heights Blvd - pads | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE | VerHigh | Res-ICI | 2022 | Paesano, Andrew | Dragojevic, Igor | 04-May-20 |  |  | 98433.79 | 99735.87 | 97288.75 | 98433.79 | Frank Giancola |  | 04-Dec-20 | 26-Jul-23 | 30-Nov-20 | 30-Nov-20 | 17-Nov-22 |  | Customer |  | 1,145.04
452122 | CENTRAL CONVERSION - MARKLAND ST | 820 - Nebo | 150352 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Wardell, Paul | 27-Oct-20 |  |  | 1352318.74 | 1408639.48 | 1318964.01 | 1352318.74 | Brad Carr | K-Line | 10-Sep-21 | 22-Sep-22 | 11-Jan-21 | 04-Jan-21 | 01-Oct-21 |  | Contractor |  | 33,354.73
451659 | Smart Grid Fund - Miles (Capital) | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Karan, Andjelo | 31-Aug-18 |  |  | 98875.24 | 107595.27 | 98875.24 | 98875.24 | Dan Despres |  | 19-Oct-18 | 14-Feb-22 | 18-Oct-18 | 12-Oct-18 | 19-Apr-19 |  |  |  | 0
451107 | 2021 EMERGING OH - 2 ANCHOR RELOCATION | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 31-May-21 |  |  | 5091.44 | 3744.36 | 5091.44 | 5091.44 | Dan Despres |  | 09-Jul-21 | 14-Feb-22 | 09-Jul-21 | 28-Jun-21 | 29-Jun-21 |  |  |  | 0
451911 | 43 Woodbine Cres, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 31-May-19 |  |  | 0 | 1770.25 |  | 0 | Weaver, Thomas |  | 31-May-19 | 15-Jul-21 | 31-May-19 | 31-May-19 | 31-May-19
452014 | SCH 2019 Pole Residuals Phase 1 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 20-Feb-19 |  |  | 42489.92 | 48330.35 | 42489.92 | 42489.92 | Dan Despres |  | 30-Sep-19 | 08-Mar-21 | 02-Jul-19 | 11-Jul-19 | 04-Sep-19 | Filler | Filler |  | 0
451284 | Victory Subdivision - Phase 3 | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark | 05-Oct-18 |  |  | 15514.66 | 99243.67 | 15514.66 | 15514.66 | Andrew Mehlenbacher |  | 30-Nov-18 | 18-Feb-21 | 05-Nov-18 | 18-Jan-19 | 15-Apr-19 |  | Customer |  | 0
452066 | 10 Head St, St. Catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 06-Mar-19 |  |  | 7268.15 | 6152.67 | 7268.15 | 7268.15 | Carr, Brad |  | 18-Apr-19 | 24-Aug-20 | 18-Apr-19 | 25-Apr-19 | 25-Apr-19 |  | Customer |  | 0
451350 | V3326 Replacement | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 352.03 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451549 | 8 Kingsborough Dr | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dragojevic, Igor | 07-Feb-19 |  |  | 25142.36 | 15441.23 | 25142.36 | 25142.36 | Koeppe, Jeffrey |  | 15-Mar-19 | 24-Aug-20 | 11-Mar-19 | 18-Mar-19 | 15-Apr-19 |  | Customer |  | 0
451809 | 200 Market St | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-May-19
451962 | MH52 Adjustment | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Johnson, William |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 05-Nov-18
451413 | HALSON SS CLEANUP | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2021 | Newitt, Andrew | Vandekuyt, Greg |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 03-Apr-17
451758 | 32 Towering Heights Blvd - temp | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE |  |  | 2022 | Paesano, Andrew | Dragojevic, Igor | 07-Mar-19 |  |  | 64680.22 | 64656.16 | 72441.83 | 64680.22 | Frank Giancola |  | 01-Feb-22 | 02-Aug-23 | 01-Feb-22 | 23-May-19 | 18-Nov-22 | Customer | Customer |  | -7,761.61
451283 | Thomas Switching Station | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 30-Jul-18 |  |  | 439692.41 | 566476.37 | 291574.7 | 439692.41 | Tony Ierace | B&M | 14-Dec-18 | 22-Sep-22 | 10-Sep-18 | 16-Aug-18 | 17-Jun-21 | Lines | Materials |  | 148,117.71
451858 | BROMLEY GARDENS - SUBD RES EDS | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 12-Mar-21 |  |  | 34909.07 | 165040.38 | 34909.07 | 34909.07 | Frank Giancola |  | 10-May-21 | 14-Dec-21 | 26-Apr-21 | 01-Apr-21 | 03-Sep-21 |  | Customer |  | 0
451106 | Centennial Go Station, Park & Ride | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 12-Jul-17 |  |  | 14347.49 | 16976.54 | 13614.14 | 14347.49 | Andrew Mehlenbacher | Fairway | 14-Aug-17 | 15-Jul-21 | 11-Aug-17 | 24-Aug-18 | 13-Sep-19 |  | Customer |  | 733.35
451548 | 112 King St W, Dundas | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 24-Jan-19 |  |  | 11538.66 | 10605.46 | 11538.66 | 11538.66 | Roy Owen |  | 07-Mar-19 | 15-Jul-21 | 06-Mar-19 | 19-Mar-19 | 07-May-19 |  | Customer |  | 0
451910 | 214 Park St W, Dundas | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 06-May-19 |  |  | 8061.02 | 3145.22 | 8061.02 | 8061.02 | Carr, Brad | Clrway | 13-Jun-19 | 15-Jul-21 | 13-Jun-19 | 13-Sep-19 | 13-Sep-19 |  | Customer |  | 0
451708 | 665 Starthearne Ave, Hamilton | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Laus, Tomislav | 24-Jan-19 |  |  | 14927.15 | 14733 | 14927.15 | 14927.15 | Koeppe, Jeffrey |  | 05-Mar-19 | 24-Aug-20 | 04-Mar-19 | 05-Feb-19 | 20-Feb-19 |  | Customer |  | 0
451707 | 155 Ontario St, St. Catharines - temp | 830 - St. Catharines | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Paesano, Andrew | Laus, Tomislav | 17-Aug-20 |  |  | 69589.71 | 75843.64 | 69589.71 | 69589.71 | Frank Giancola | Wiens | 14-Aug-20 | 26-Jul-23 | 12-Aug-20 | 16-Nov-20 | 27-May-22 | Customer | Customer |  | 0
451656 | 2022 POLE REPLACEMENT-BATCH 2 (12-WP) | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 29-Nov-21 | 12 | 12 | 160352.58 | 150547.84 | 160352.58 | 160352.58 | Frank Giancola |  | 08-Jun-22 | 22-Sep-22 | 02-May-22 | 28-Apr-22 | 20-Jun-22 |  | Filler |  | 0
451807 | Burbank Dr | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Aug-22
451410 | York Conversion Phase 2 | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Karan, Andjelo | 17-Aug-18 |  |  | 1724800.52 | 2201341.19 | 1713813.09 | 1724800.52 | Carr, Brad | B&M | 28-Dec-18 | 20-Sep-21 | 17-Sep-18 | 11-Sep-18 | 20-Jun-19 |  | Control/SCADA |  | 10,987.43
452119 | MH206 - Roof Replacement | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Billone, Justin | 17-May-19 |  |  | 72786.37 | 84735.2 | 61161.37 | 72786.37 | Carr, Brad | B&M | 31-May-19 | 15-Sep-21 | 27-May-19 | 27-May-19 | 19-Jul-19 |  | MC/PUCC Permit |  | 11,625.00
451105 | K-Bar Unit Replace - Westland St | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 15-Feb-17 |  |  | 25408.56 | 24925.76 | 24523.1 | 25408.56 | Frank Giancola |  | 29-Nov-19 | 22-Oct-20 | 12-Jul-17 | 29-Oct-19 | 08-Nov-19 |  | Filler |  | 885.46
451212 | East 36th Kicker Can Removal | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 518.12 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 24-Aug-20 | 28-May-19 | 28-May-19 | 28-May-19
451908 | 107 MacNab St N, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Kappheim, Adam | Bennett, Aaron | 06-Jun-19 |  |  | 20651.33 | 10112.79 | 20651.33 | 20651.33 | Brian Robinson | B&M | 13-Jun-19 | 26-Jul-23 | 10-Jun-19 | 10-Jun-19 | 27-Sep-19 |  | Locates |  | 0
451346 | COURTLEIGH RD AREA U/G RENEWAL | 830 - St. Catharines | 150496 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Rolfe, Eric |  |  |  | 0 | 60626.28 |  | 0 | Jakubowski, Mark |  |  | 26-Jul-23
451806 | Empire Redhill - Temp Temp Pole | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Oosterlinck, David | 14-May-19 |  |  | 16634.05 | 15198.12 | 16634.05 | 16634.05 | Macdougall, Stephen |  | 01-Feb-22 | 28-Sep-22 | 01-Feb-22 | 19-Jul-19 | 22-Aug-22 | MC/PUCC Permit | MC/PUCC Permit |  | 0
451409 | 155 Ontario St, st catharines | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2022 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-Jun-22
452011 | Stroud #3 Phase 6 Completion | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 05-Jun-19 |  |  | 578330.16 | 531550.3 | 523629.49 | 578330.16 | Carr, Brad | B&M | 06-Sep-19 | 08-Mar-21 | 08-Jul-19 | 03-Jun-19 | 24-Sep-19 |  | N/A |  | 54,700.67
451211 | 2016 Pole Residuals Contracted - P2 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 22-Jun-18 |  |  | 52494.47 | 80572.69 | 52494.47 | 52494.47 | XPopiel, Joseph |  | 31-Dec-19 | 22-Oct-20 | 01-Aug-18 | 30-Jul-18 | 21-Aug-19 |  | Filler |  | 0
451756 | 16 Preston Dr, St. Catharines | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 419 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 24-Aug-20 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
452118 | Bell Make Ready - Decew Rd | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 25-Sep-19 |  |  | 6792.82 | 3585.05 | 6792.82 | 6792.82 | Hewitson, Trevor |  | 30-Oct-19 | 04-May-20 | 30-Oct-19 | 31-Oct-19 | 31-Oct-19 |  |  |  | 0
451104 | future 867 cannon e | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 12-Dec-14
451907 | 15 Queen St S, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2021 | Kappheim, Adam | Bennett, Aaron | 19-Sep-19 |  |  | 97457.61 | 142636.96 | 96753.69 | 97457.61 | Macdougall, Stephen |  | 19-Nov-19 | 26-Jul-23 | 28-Oct-19 | 27-Oct-19 | 29-Jan-21 | Customer | Customer |  | 703.92
451958 | King UG Sec Conversion, St Cath | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Johnson, William |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 31-Aug-22
634496 | HAMILTON PCB TX'S UNDERGROUND - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 28-Jan-20 |  |  | 54676.3 | 43106.98 | 54676.3 | 54676.3 | Andrew Mehlenbacher | Fairway | 15-Sep-20 | 14-Feb-22 | 03-Aug-20 | 23-Jun-21 | 07-Jul-21 | Contractor | Contractor |  | 0
451705 | 79 Simpson Rd, St. Catharines | 830 - St. Catharines | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 01-Mar-19 |  |  | 5683.07 | 4822.25 | 5683.07 | 5683.07 | Carr, Brad | Wiens | 15-Apr-19 | 17-Jan-22 | 15-Apr-19 | 29-Oct-19 | 29-Oct-19 | Customer | Customer |  | 0
451654 | Jacobson Ave. Rearlot Rebuild | 830 - St. Catharines | 150381 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Webb-Murre, Paige | 12-Feb-19 |  |  | 491483.9 | 352511.92 | 491483.9 | 491483.9 | Dan Despres |  | 12-Aug-19 | 08-Mar-21 | 25-Mar-19 | 15-Apr-19 | 15-Nov-19 | Locates | Control/SCADA |  | 0
451103 | Milton Ave to Hwy 6 N Large Move | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Johnson, William | 28-May-19 |  |  | 0 | 1198.5 | 0 | 0 | Jakubowski, Mark |  | 28-May-19 | 10-Dec-20 | 28-May-19 | 28-May-19 | 28-May-19 |  |  |  | 0
451755 | 97 Lakeview Dr, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 3981.2 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 24-Aug-20 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
451602 | Burgoyne Bridge Additional Costs | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Karan, Andjelo | 01-May-19 |  |  | 0 | 48357.63 |  | 0 | Weaver, Thomas |  | 07-May-19 | 24-Aug-20 | 07-May-19 | 07-May-19 | 07-May-19
451210 | 2017 Pole Residuals Contracted - P1 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 05-Jul-18 |  |  | 49623.56 | 53324.39 | 49623.56 | 49623.56 | XPopiel, Joseph |  | 19-Sep-18 | 24-Aug-20 | 04-Sep-18 | 04-Apr-19 | 15-Apr-19 |  | Filler |  | 0
451408 | 110 Bellagio Ave, stoney creek | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2019 | Paesano, Andrew | Laus, Tomislav | 05-Sep-18 |  |  | 42962.92 | 37436.77 | 42962.92 | 42962.92 | Andrew Mehlenbacher |  | 22-Oct-18 | 24-Aug-20 | 15-Oct-18 | 17-Oct-18 | 25-Jan-19 |  | Customer |  | 0
452010 | Bell Make Ready - West Ave | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 28-Mar-19 |  |  | 14360.34 | 14238.86 | 14360.34 | 14360.34 | Koeppe, Jeffrey |  | 10-May-19 | 19-May-20 | 08-May-19 | 17-Jun-19 | 26-Jun-19 |  | MC/PUCC Permit |  | 0
451345 | Huxley Ave South - Pole Replacement | 820 - Nebo | 150335 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | Paesano, Andrew |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 14-Nov-16
634308 | COGECO BONDS - 2019 FLAMBOROUGH | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jun-20 |  |  | 1223.48 | 1481.15 | 1223.48 | 1223.48 | Hewitson, Trevor |  | 30-Sep-20 | 13-Jan-22 | 01-Sep-20 | 22-Feb-21 | 22-Feb-21 | Filler | Filler |  | 0
634365 | WATERDOWN 3RD FEEDER - Deep Dive | 820 - Nebo | 150390 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Anderson, Dean | 15-Jul-20 |  |  | 2328847.76 | 2119956.7 | 2170455.76 | 2328847.76 | Brad Carr | K-Line | 18-Dec-20 | 16-Sep-21 | 10-Aug-20 | 18-Sep-20 | 10-Feb-21 | MC/PUCC Permit | MC/PUCC Permit |  | 158,392.00
634382 | JOINT USE PERMIT 20170719-1474-005 - MILL, WELLINGTON S, MCNAB - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 23-Aug-21 |  |  | 8892.28 | 5839.56 | 8892.28 | 8892.28 | K-Line Construction | K-Line | 07-Mar-22 | 30-Jan-23 | 07-Mar-22 | 24-Jan-22 | 24-Jan-22 | Filler | Filler |  | 0
634412 | MCMASTER INNOVATION PARK EXPANSION | 820 - Nebo | 151584 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan | B&M |  | 11-Nov-19
633560 | 2020 - AUTOMATED SWITCHGEAR INSTALLS - PART 2 | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 16-Sep-19
633939 | LAGUNA VILLAGE | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 25-May-20 |  |  | 922362.25 | 830333.33 | 922362.25 | 922362.25 | Roy Owen |  | 17-Jul-20 | 14-Dec-21 | 06-Jul-20 | 06-Nov-20 | 25-Feb-21 | Customer | Customer |  | 0
452111 | U/G Pedestal Replacement PHASE 2 | 830 - St. Catharines | 151064 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Rolfe, Eric | 17-May-19 |  |  | 31317.94 | 31465.29 | 31317.94 | 31317.94 | Frank Giancola |  | 15-Nov-19 | 19-Nov-20 | 02-Jul-19 | 23-Sep-19 | 18-Oct-19 | Filler | Filler |  | 0
634719 | TOWERING HEIGHTS - EMERGENCY CABLE REPAIRS/REPLACEMENT | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Patel, Ketan | 26-Nov-19 |  |  | 58994.63 | 55439.54 | 58994.63 | 58994.63 | Frank Giancola | Wiens | 15-Jan-20 | 15-Sep-21 | 06-Jan-20 | 09-Dec-19 | 19-Dec-19 |  |  |  | 0
634744 | 1324 RYMAL ROAD EAST | 820 - Nebo | 150449 | Active | 95 | COMPLETE | Low | Comm | 2022 | Kappheim, Adam | Djuric, Zdravko | 15-May-20 |  |  | 64354.68 | 46285.25 | 64354.68 | 64354.68 | Roy Owen | Fairway | 22-Mar-22 | 26-Jul-23 | 07-Mar-22 | 18-Jul-22 | 21-Sep-22 | Customer | Customer |  | 0
636209 | VSM51 EXPANSION FOR 57 CARLISLE ST, ST. CATHARINES | 830 - St. Catharines | 151892 | Active | 84 | ACTIVE | Medium | Comm | 2023 | Jakubowski, Mark | Patel, Ketan | 20-Jul-22 |  |  | 1834499 | 1717747.68 | 1728272.04 | 1834499 | Brad Carr | B&M | 28-Feb-23 | 31-Aug-23 | 07-Nov-22 | 21-Nov-22 |  | N/A | N/A |  | 106,226.96
636243 | 101 HANNOVER DR | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2021 | Paesano, Andrew | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Sep-22
636296 | MH20 JAMES STREET SOUTH RAISE LID | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 21-Dec-22 | 1 | 1 | 11835.92 | 13896.37 | 11835.92 | 11835.92 | Weaver, Thomas |  | 21-Dec-22 | 23-May-23 | 21-Dec-22 | 21-Dec-22 | 21-Dec-22 |  |  |  | 0
636297 | MH LID REPAIRS HAMILTON (7 FATHER BIRD TRAIL, 37 FATHER BIRD TRAIL, 496 MAIN ST) | 820 - Nebo | 151065 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636574 | SC1032 UPGRADE - 1 | 820 - Nebo | 151083 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 25-Aug-20 |  |  | 74735.56 | 83925.73 | 74735.56 | 74735.56 | Andrew Mehlenbacher |  | 29-Jun-21 | 25-Apr-22 | 21-Jun-21 | 13-Jun-21 | 24-Jun-21 |  |  |  | 0
636596 | JOINT USE PERMIT HW2020-036 - YORK AND HOPKINS - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 12-Apr-21 |  |  | 15020.62 | 18957.36 | 15020.62 | 15020.62 | Brad Carr | K-Line | 21-May-21 | 22-Mar-22 | 17-May-21 | 20-Oct-21 | 20-Oct-21 | Filler | Filler |  | 0
636597 | JOINT USE PERMIT HW2020-037 - YORK RD - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636620 | 6 ACORN STREET - Temp | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2022 | Kappheim, Adam | Djuric, Zdravko | 15-Jan-21 |  |  | 38324.85 | 49102.62 | 38324.85 | 38324.85 | Macdougall, Stephen | Fairway | 23-Feb-21 | 28-Sep-22 | 15-Feb-21 | 29-Apr-21 |  | Customer | Customer |  | 0
636773 | GAGE TS - STATION UPGRADE | 820 - Nebo | 150585 | Active | 40 | ACTIVE |  |  | 2023 | Braletic, Bob | Lustrinelli, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636781 | CABLE REPLACEMENT-LAKE-LINWELL-GENEVA PH1 | 830 - St. Catharines | 150496 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David | 28-Apr-23 |  |  | 1550073.99 | 55598.58 | 1550073.99 | 1550073.99 | Brad Carr | B&M | 15-Dec-23 | 15-Dec-23 | 05-Jun-23 | 26-Jun-23 |  | MC/PUCC Permit | MC/PUCC Permit |  | 0
636783 | BULA DRIVE EMERGENCY REPLACEMENTS | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 24-Nov-21 |  |  | 196081.6 | 188357.86 | 196081.6 | 196081.6 | Brad Carr | B&M | 27-Dec-21 | 09-Aug-22 | 29-Nov-21 | 29-Nov-21 | 20-May-22 |  | COVID19 |  | 0
636810 | JOINT USE PERMIT HW2020-046 - MACNAB - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 31-Mar-21 |  |  | 8114.44 | 6103.09 | 8114.44 | 8114.44 | Brad Carr | K-Line | 31-Mar-21 | 24-Jan-22 | 31-Mar-21 | 31-Mar-21 | 31-Mar-21 |  |  |  | 0
636811 | JOINT USE PERMIT HW2020-047 - ROYAL, BOWMAN, WILMONT, STROUD - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 10-May-21 |  |  | 9010.16 | 7223.21 | 9010.16 | 9010.16 | Brad Carr | K-Line | 10-May-21 | 05-Jan-22 | 10-May-21 | 10-May-21 | 10-May-21 |  |  |  | 0
636812 | 50 KING ST E | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Kappheim, Adam | Bennett, Aaron | 03-Nov-20 |  |  | 122794.82 | 109167.59 | 122794.82 | 122794.82 | Roy Owen |  | 18-Jan-21 | 22-Sep-22 | 30-Nov-20 | 07-May-21 | 07-May-21 | Customer | Customer |  | 0
636842 | 75 NIAGARA ST / SCH / NS00035622 / 3PH PAD | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 11-May-21 |  |  | 49643.95 | 52968.1 | 49643.95 | 49643.95 | Frank Giancola | Wiens | 21-Jun-21 | 22-Sep-22 | 14-Jun-21 | 17-Jun-21 | 07-Sep-21 | Customer | Customer |  | 0
636864 | CENTRAL 9 STREET LIGHT FEEDER CONVERSION | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636881 | JOINT USE PERMIT HW2020-052 - CENTRAL PARK AND KEMP - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 05-Feb-21 |  |  | 14341.04 | 10646.73 | 14341.04 | 14341.04 | Brad Carr | K-Line | 09-Apr-21 | 24-Jan-22 | 05-Apr-21 | 08-Jun-21 | 08-Jun-21 | Filler | Filler |  | 0
636885 | JOINT USE PERMIT HW2020-056 - HIGHLAND - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jun-20 |  |  | 7765.89 | 6553.44 | 7765.89 | 7765.89 | Hewitson, Trevor |  | 30-Sep-20 | 24-Jan-22 | 01-Sep-20 | 22-Feb-21 | 22-Feb-21 | Filler | Filler |  | 0
636929 | 2023 BRADMON CABLE REPLACEMENT | 830 - St. Catharines | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M
636956 | JR STORK BRIDGE REPLACEMENT - MARTINADALE RD. | 830 - St. Catharines | 150653 | Active | HL | ACTIVE | Low | Infrast | 2023 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 19736.3 |  | 0 | Calvin Arsenault | K-Line |  | 26-Jul-23
636962 | 575 WOODWARD AVE - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 07-Dec-20 |  |  | 478780.43 | 415056.76 | 478780.43 | 478780.43 | Brad Carr | Transpw | 26-Mar-21 | 11-Nov-21 | 15-Jan-21 | 15-Mar-21 | 25-Aug-21 | Customer | Customer |  | 0
636966 | 19 PICARDY DRIVE - SUBD RES EDS | 820 - Nebo | 150588 | Active | 91 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark | 23-Dec-20 |  |  | 326365.92 | 271799.91 | 326365.92 | 326365.92 | Brad Carr | Transpw | 07-May-21 | 31-Jul-23 | 05-Apr-21 | 06-Mar-23 |  | Customer | Customer |  | 0
636967 | 27 RACHAEL DRIVE - SUBD RES EDS | 820 - Nebo | 150588 | Active | 95 | COMPLETE |  |  | 2022 | Gamboa, Henry | Morris, Mark | 23-Dec-20 |  |  | 335532.6 | 286612.4 | 335532.6 | 335532.6 | Brad Carr | Transpw | 07-May-21 | 26-Jul-23 | 05-Apr-21 | 03-May-21 | 11-Feb-22 | Customer | Customer |  | 0
636974 | JOINT USE PERMIT HW2020-059 - ARGYLE, FRASER, EDINBURGH, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 31-Mar-21 |  |  | 9642.13 | 7318.18 | 9642.13 | 9642.13 | Brad Carr | K-Line | 31-Mar-21 | 24-Jan-22 | 31-Mar-21 | 31-Mar-21 | 31-Mar-21 |  |  |  | 0
636975 | JOINT USE PERMIT HW2020-060 - RYMAL W AND ALFRIN - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 18-Jun-21 |  |  | 6577.74 | 5523.58 | 6577.74 | 6577.74 | Brad Carr | K-Line | 16-Jul-21 | 05-Jan-22 | 12-Jul-21 | 13-Aug-21 | 13-Aug-21 | Filler | Filler |  | 0
636982 | 403 ONTARIO ST, ST.CATHARINES - NIAGARA REGION LINHAVEN LODGE | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2022 | Paesano, Andrew | Laus, Tomislav | 26-Mar-21 |  |  | 77627.19 | 218891.86 | 77627.19 | 77627.19 | Frank Giancola |  | 20-May-21 | 01-Aug-23 | 10-May-21 | 19-May-21 | 08-Dec-22 | Materials | Materials |  | 0
636988 | CABLE INJECT - HWY 406/QEW/MARTINDALE | 830 - St. Catharines | 150496 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 29-Nov-22 |  |  | 760050.01 | 31364.96 | 760050.01 | 760050.01 | Brad Carr | Nvinium | 28-Sep-23 | 28-Sep-23 | 23-May-23 | 24-Mar-23 |  |  |  |  | 0
636989 | CABLE INJECT - VANSICKLE | 830 - St. Catharines | 151304 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636996 | 981 BARTON ST STONEY CREEK UPGRADE | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | K-Line |  | 09-Jun-22
637022 | INSULATORS - WEST - NEBO | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 31-May-23
637024 | INSULATORS - WEST - ST.CATHARINES | 830 - St. Catharines | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 31-May-23
637026 | AUTO SW - WEST - NEBO - HORIZONTAL | 820 - Nebo | 150337 | Inactive | 99 | CANCELLED |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 23-Mar-23
637027 | AUTO SW - WEST - NEBO - VERTICAL | 820 - Nebo | 150337 | Inactive | 99 | CANCELLED |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 23-Mar-23
637028 | AUTO SW - WEST - VANSICKLE - HORIZONTAL | 830 - St. Catharines | 150337 | Inactive | 99 | CANCELLED |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 23-Mar-23
637029 | AUTO SW - ITD - ST CATHARINES, 5 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 31-Mar-21 | 5 |  | 322189.92 | 323143.38 | 437158.89 | 322153.92 | Dan Despres |  | 29-Oct-21 | 22-Sep-22 | 06-Sep-21 | 20-Sep-21 | 19-Nov-21 | Locates | Locates |  | -115,004.97
637061 | HORNING TS- MTN FEEDERS -M42X - PHASE 1 | 820 - Nebo | 150376 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean | 29-Nov-22 |  |  | 907149.67 | 580122.17 | 901357.81 | 907149.67 | Tony Ierace |  | 30-May-23 | 31-Aug-23 | 09-Jan-23 | 03-Jan-23 |  |  | N/A |  | 5,791.86
637069 | COGECO BONDS - 2020 AINSLIE WOOD SOUTH - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637070 | COGECO BONDS - 2020 DOWNTOWN HAMILTON - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637071 | COGECO BONDS - 2020 HANNON NORTH - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
634163 | 121 HIGHWAY #8, STONEY CREEK | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 25-May-20 |  |  | 107162.76 | 107969.42 | 107162.76 | 107162.76 | Macdougall, Stephen |  | 24-Jul-20 | 26-Jul-23 | 06-Jul-20 | 13-Jul-20 | 25-Jan-21 | Customer | Customer |  | 0
637101 | POLES - WEST - NEBO | 820 - Nebo | 150335 | Inactive | 99 | CANCELLED |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 23-Mar-23
637102 | POLES - WEST - VANSICKLE | 830 - St. Catharines | 150335 | Inactive | 99 | CANCELLED |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 23-Mar-23
637117 | SISTER VARGA | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Kappheim, Adam | Bennett, Aaron | 21-Jan-22 |  |  | 74030.22 | 50362.73 | 57085.12 | 74030.22 | Roy Owen |  | 21-Jan-22 | 26-Jul-23 | 10-Jan-22 | 10-Jan-22 | 21-Jan-22 |  |  |  | 16,945.10
637119 | ALECTRA WEST - CAPACITOR BANK | 830 - St. Catharines | 151074 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 17-Aug-22
637150 | ROAD AUTHORITY - POLE RELOCATION - CENTRE RD - WATERDOWN | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE | Medium | Infrast | 2021 | Jakubowski, Mark | Celic, Dusan | 20-May-21 |  |  | 210889.1 | 194762.48 | 210889.1 | 210889.1 | Brad Carr | K-Line | 02-Jul-21 | 30-Nov-21 | 14-Jun-21 | 07-Jun-21 | 21-Jun-21 |  |  |  | 0
637162 | GALBRAITH GA-2 8KV TO 27KV CONVERSION | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637163 | 40 MALLARD TRAIL | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Djuric, Zdravko | 11-Sep-20 |  |  | 82891.04 | 78658.12 | 82891.04 | 82891.04 | Macdougall, Stephen | Fairway | 05-Feb-21 | 22-Sep-22 | 05-Feb-21 | 05-Feb-21 | 26-Jan-22 | Customer | Customer |  | 0
637183 | JOINT USE PERMIT HW2020-065 - GOVERNORS RD - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 14-May-21 |  |  | 11100.69 | 8670.68 | 11100.69 | 11100.69 | Brad Carr |  | 14-May-21 | 24-Jan-22 | 14-May-21 | 14-May-21 | 14-May-21 |  |  |  | 0
637196 | 63 LAKEPORT RD, ST.CATHARINES | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2023 | Paesano, Andrew | Laus, Tomislav |  |  |  | 0 | 4897.74 |  | 0 | Calvin Arsenault |  |  | 15-Jun-23
637197 | 1190 MAIN STREET WEST | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637210 | 157 MILL STREET NORTH | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Kappheim, Adam | Djuric, Zdravko | 16-Mar-21 |  |  | 58426.98 | 37307.42 | 58426.98 | 58426.98 | Macdougall, Stephen |  | 27-Apr-21 | 22-Sep-22 | 19-Apr-21 | 25-Jun-21 | 04-Aug-21 | Customer | Customer |  | 0
637225 | NORTH CENTRAL FEEDERS CAPACITY (CARLTON TS TO LINWELL RD/LAKE ST) RELIEF | 830 - St. Catharines | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637228 | WINONA HILLS SUBDIVISION - SUBD RES EDS | 820 - Nebo | 150588 | Active | 95 | COMPLETE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 03-Dec-21 |  |  | 49723.91 | 67803.45 | 49723.91 | 49723.91 | Macdougall, Stephen |  | 04-Mar-22 | 26-Jul-23 | 01-Mar-22 | 09-May-22 | 04-Jan-23 | Locates | Locates |  | 0
637275 | 202 CANNON STREET EAST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Kappheim, Adam | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637277 | OVERHEAD POLE LINE RELOCATION - 149 HARTZEL RD | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 25-Aug-22
637292 | 1565 UPPER JAMES STREET - CULVER PROPERTIES LTD. | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Kappheim, Adam | Bharosi, Mohindra | 26-Aug-20 |  |  | 117490.14 | 115246.12 | 117490.14 | 117490.14 | Roy Owen | Fairway | 14-Oct-20 | 22-Sep-22 | 05-Oct-20 | 09-Oct-20 | 07-Sep-21 | Customer | Materials |  | 0
637306 | 286 BUNTING - PMH3 REMOVAL | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 14-Sep-20 |  |  | 145618.45 | 141710.92 | 145618.45 | 145618.45 | Dan Despres | Wiens | 19-Nov-20 | 01-Nov-21 | 02-Nov-20 | 21-Oct-20 | 22-Apr-21 | Contractor | Contractor |  | 0
637332 | JOINT USE PERMIT HW2020-075 - ROXBOROUGH, ARCHIBALD, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 18-Jun-21 |  |  | 33738.84 | 36617.54 | 33738.84 | 33738.84 | Brad Carr | K-Line | 16-Jul-21 | 08-Feb-22 | 12-Jul-21 | 13-Aug-21 | 13-Aug-21 | Filler | Filler |  | 0
637338 | SECOND FEED INTO SC1390 @ SALERNO DAIRY - 20 MORLEY STREET | 820 - Nebo | 151452 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 04-Sep-20 |  |  | 21701.31 | 19949.12 | 21701.31 | 21701.31 | Roy Owen |  | 11-Nov-20 | 15-Jul-21 | 02-Nov-20 | 11-Jan-21 | 18-Jan-21 | Customer | Customer |  | 0
637349 | CONNAUGHT EXPANSION - PHASE 3 | 820 - Nebo | 152381 | Active | 40 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M
637363 | GALBRAITH GA-2 8KV TO 27KV CONVERSION (E/O DONN AVE) | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637364 | GALBRAITH GA-1 8KV TO 27KV CONVERSION (WEST OF LAKE S/O QUEENSTION) | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637381 | LBDS REPLACEMENT - MUD ST W | 820 - Nebo | 150337 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637395 | 256 LIME KILN ROAD ANCASTER - FAULTY TRANSFORMER | 820 - Nebo | 151452 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Wardell, Paul | 08-Feb-21 |  |  | 49418.77 | 55671.64 | 49418.77 | 49418.77 | Koeppe, Jeffrey |  | 03-May-21 | 22-Sep-22 | 26-Apr-21 | 16-Apr-21 | 21-Jun-21 |  | Customer |  | 0
637400 | WARKDALE DR & ROCKDALE AVE - SUBD RES EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637414 | HAM - NS - MIP PHASE A- 175 LONGWOOD S | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637416 | HAM - NS - MIP PHASE B- 1 LONGWOOD S | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637418 | HAM - NS - MIP PHASE C- 1 LONGWOOD S | 820 - Nebo |  | Active | 10 | ACTIVE |  |  | 2023 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637419 | HAM - NS - TEMP SERVICE - LONGWOOD S | 820 - Nebo | 150456 | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637446 | BATTERIES - AUTO SWITCH | 820 - Nebo | 150334 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637452 | TURNER AVE - UG REAR LOT CONVERSION | 820 - Nebo | 150351 | Active | 93 | ACTIVE |  |  | 2022 | Beaudrie, Scott | Anderson, Dean | 30-Nov-21 |  |  | 663135.92 | 596080.48 | 643971.68 | 663135.92 | Brad Carr | B&M | 05-Aug-22 | 26-Jul-23 | 24-May-22 | 24-May-22 | 28-Dec-22 | Contractor | Contractor |  | 19,164.24
637453 | INGLEWOOD & UNDERCLIFFE CONVERSION | 820 - Nebo | 150352 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Anderson, Dean | 28-Feb-21 |  |  | 641525.11 | 559012.29 | 675718.5 | 641525.11 | Brad Carr | B&M | 06-Aug-21 | 22-Sep-22 | 17-May-21 | 17-May-21 | 10-Dec-21 |  | N/A |  | -34,193.39
637479 | GARDEN CITY SKYWAY WIDENING - ST.CATHARINES | 820 - Nebo | 150644 | Active | HL | ACTIVE | Medium | Infrast | 2023 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 8027.17 |  | 0 | Calvin Arsenault | N/A |  | 26-Jul-23
637484 | 104-106 BAY ST N / HAM | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637490 | 2021 POLE RENEWAL - EAST 21ST ST - 6 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 26-Feb-21 | 6 |  | 96560.17 | 121502.88 | 96560.17 | 96560.17 | Koeppe, Jeffrey |  | 06-Oct-21 | 09-Aug-22 | 13-Sep-21 | 18-Oct-21 | 19-Nov-21 | Locates | Locates |  | 0
637546 | JOINT USE PERMIT HW2020-080 - DUNDURN N AND TOM - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 28-Jan-21 |  |  | 14322.7 | 6674.78 | 14322.7 | 14322.7 | Brad Carr |  | 14-May-21 | 27-Jan-22 | 10-May-21 | 16-Apr-21 | 16-Apr-21 |  |  |  | 0
637561 | EXPANSION WORK FOR 75 NIAGARA ST | 830 - St. Catharines | 152381 | Active | 98 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Patel, Ketan | 07-Feb-21 |  |  | 189969.77 | 194352.5 | 175615.23 | 189969.77 | Brad Carr | Wiens | 25-Jun-21 | 26-Jul-23 | 07-Jun-21 | 08-Mar-21 | 21-Jun-21 |  |  |  | 14,354.54
637586 | JOINT USE PERMIT HW2020-083 - CONCESSION, SHERMAN ACCESS, GAGE S - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637596 | 36 MCDONALD- 6 REAR YARD SERVICE RELOCATE | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 12-Jan-21 |  |  | 90043.73 | 93616.72 | 90043.73 | 90043.73 | Frank Giancola | Wiens | 26-Feb-21 | 20-Sep-21 | 15-Feb-21 | 26-Jan-21 | 19-Apr-21 |  | N/A |  | 0
637617 | DOWNING ST - CITY OF ST. CATHARINES | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 14-Sep-22
637625 | CENTRAL CONVERSION - PHASE 7A | 820 - Nebo | 150352 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M
637667 | MH 90 - LID/ROOF ADJUSTMENTS | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 05-Oct-20 |  |  | 21386.27 | 27312.64 | 21386.27 | 21386.27 | Brad Carr | Fairway | 06-Nov-20 | 04-Oct-21 | 02-Nov-20 | 25-Jan-21 | 27-Jan-21 | Contractor | Contractor |  | 0
637676 | 2022 - WEST CABLE REPLACEMENTS - STONEY CREEK - NORTH OF HWY 8 (PART 1) | 820 - Nebo | 151299 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 21-Nov-22 |  |  | 1520028.78 | 306805.21 | 1517703.34 | 1520028.78 | Brad Carr | B&M | 27-Oct-23 | 31-Oct-23 | 29-May-23 | 22-Jun-23 |  | MC/PUCC Permit | MC/PUCC Permit |  | 2,325.44
637677 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 WEST OF DEWITT (PART 1) | 820 - Nebo | 151299 | Active | 94 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 22-Nov-22 |  |  | 480937.85 | 540871.88 | 480401.21 | 480937.85 | Brad Carr | B&M | 31-May-23 | 26-Jul-23 | 03-Apr-23 | 20-Feb-23 | 24-May-23 |  |  |  | 536.64
637678 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 EAST OF DEWITT (PART 2) | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637686 | MOHAWK RD W & LIME KILN - URD | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637710 | V1061 RELOCATON | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE | High | Res-ICI | 2021 | Jakubowski, Mark | Jolie, Chris | 15-Dec-20 |  |  | 182201.3 | 177247.81 | 179380.7 | 182201.3 | Brad Carr | B&M | 26-Mar-21 | 15-Sep-21 | 01-Mar-21 | 08-Mar-21 | 12-Mar-21 | Materials |  |  | 2,820.60
637719 | JOINT USE PERMIT HW2020-089 - BOBOLINK - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 20-Apr-21 |  |  | 5945.74 | 3184.74 | 5945.74 | 5945.74 | Brad Carr | K-Line | 25-Jun-21 | 05-Jan-22 | 21-Jun-21 | 17-May-21 | 17-May-21 |  |  |  | 0
637720 | JOINT USE PERMIT HW2020-091 - PARK, BROCK N, MARKET N, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Jan-22 |  |  | 9782.71 | 6884.88 | 9782.71 | 9782.71 | Brad Carr | K-Line | 04-Jan-22 | 08-May-23 | 04-Jan-22 | 04-Jan-22 | 04-Jan-22 |  |  |  | 0
637728 | JOINT USE PERMIT HW2020-094 - JAMES, BROCK S, HATT, BOND S - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 28-Jan-21 |  |  | 8155.22 | 6017.25 | 8155.22 | 8155.22 | Brad Carr |  | 14-May-21 | 29-Dec-21 | 10-May-21 | 16-Apr-21 | 16-Apr-21 |  |  |  | 0
637761 | JOINT USE PERMIT HW2020-098 - CREIGHTON, MAYFAIR, GOVERNORS - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 12-Apr-21 |  |  | 8910.95 | 7086.99 | 8910.95 | 8910.95 | Brad Carr | K-Line | 15-Apr-21 | 21-Mar-22 | 12-Apr-21 | 20-Oct-21 | 20-Oct-21 | Filler | Filler |  | 0
637777 | SC6 - AUTO SWITCH REPLACEMENT | 820 - Nebo | 151065 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637780 | COGECO BONDS - 2020 WATSONS LANE - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637781 | COGECO BONDS - 2020 CORKTOWN - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637782 | COGECO BONDS - 2020 CENTENNIAL PKWY S - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637784 | COGECO BONDS - 2020 AINSLIE WOOD EAST - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637812 | 22 CANNON ST E/127 HUGHSON ST N - LINE ISOLATION/RELOCATION | 820 - Nebo | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637861 | 4 VICKERS RD - SUBD RES EDS | 820 - Nebo | 150588 | Active | 84 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark | 30-Sep-22 |  |  | 53416.24 | 24537.62 | 53416.24 | 53416.24 | Macdougall, Stephen |  | 03-Jul-23 | 03-Aug-23 | 03-Apr-23 | 05-May-23 |  | Customer | Customer |  | 0
637889 | POLE 6372 - POLE & ASSOCIATED HARDWARE | 820 - Nebo | 150570 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
637917 | POLE 41797 - REPLACE FUSES ON POLE | 820 - Nebo | 150828 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 05-Oct-22 |  |  | 30246.21 | 15267.96 | 27120.74 | 30246.21 | Koeppe, Jeffrey |  | 09-Nov-22 | 26-Jul-23 | 07-Nov-22 | 19-Dec-22 | 20-Dec-22 | N/A | N/A |  | 3,125.47
637920 | TX RENEWAL PROGRAM 2021 PHASE 1 - STONEY CREEK - 3 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 04-Dec-20 |  |  | 63109.85 | 57336.57 | 63109.85 | 63109.85 | Macdougall, Stephen |  | 28-May-21 | 14-Sep-22 | 22-Feb-21 | 08-Mar-21 | 28-May-21 | Filler | Filler |  | 0
637921 | TX RENEWAL PROGRAM 2021 - PHASE 2 - HAMILTON - 4 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 04-Dec-20 |  |  | 92236.57 | 98723.88 | 92236.57 | 92236.57 | Macdougall, Stephen |  | 29-Oct-21 | 09-Aug-22 | 16-Aug-21 | 13-Sep-21 | 23-Dec-21 | Filler | Filler |  | 0
637929 | 202 DUNDURN STREET SOUTH / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 22-Aug-22
637928 | 90 CARLING ST | 820 - Nebo | 150449 | Active | 70 | ACTIVE |  |  | 2023 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
634973 | JOINT USE PERMIT HW2019-140 - PARKSIDE, YORK, MELVILLE, SYDENHAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 23-Oct-20 |  |  | 11181.88 | 10306.93 | 11181.88 | 11181.88 | Hewitson, Trevor |  | 31-Dec-20 | 11-Jan-22 | 02-Nov-20 | 22-Feb-21 | 22-Feb-21 | Filler | Filler |  | 0
638023 | JOINT USE PERMIT HW2020-103 - CONCESSION AND SHERMAN ACCESS - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
638021 | JOINT USE PERMIT HW2020-101 - REGENT, ANGELINA, OTTAVIANO, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 16-Apr-21 |  |  | 10337.1 | 7975.89 | 10337.1 | 10337.1 | Brad Carr |  | 16-Apr-21 | 27-Jan-22 | 16-Apr-21 | 16-Apr-21 | 16-Apr-21 |  |  |  | 0
638083 | 857 WOODWARD AVE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Dragojevic, Igor | 11-Jun-21 |  |  | 65963.9 | 56050.6 | 65963.9 | 65963.9 | Macdougall, Stephen | Fairway | 23-Jul-21 | 22-Sep-22 | 12-Jul-21 | 16-Aug-21 | 12-Nov-21 | Customer | Customer |  | 0
638102 | 19 COLLIER ST / SCH / UP00055822 / 3PH PAD INSTALL | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 09-Dec-20 |  |  | 32122 | 31203.19 | 32122 | 32122 | Frank Giancola | Wiens | 27-Jan-21 | 26-Jul-23 | 18-Jan-21 | 15-Jan-21 | 09-Apr-21 |  | Customer |  | 0
638110 | JOINT USE PERMIT HW2020-109 - MORGAN, CAROGA, BONAVENTURE, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 16-Apr-21 |  |  | 10955.14 | 7833.67 | 10955.14 | 10955.14 | Brad Carr |  | 16-Apr-21 | 27-Jan-22 | 16-Apr-21 | 16-Apr-21 | 16-Apr-21 |  |  |  | 0
638124 | 161 BROCKLEY DR | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Dragojevic, Igor | 19-Nov-20 |  |  | 49939.9 | 46697.56 | 49939.9 | 49939.9 | Macdougall, Stephen |  | 12-Jan-21 | 22-Sep-22 | 04-Jan-21 | 19-Jan-21 | 02-Jul-21 | Customer | Customer |  | 0
638197 | FOOTHILLS OF WINONA PHASE 1B & 2 - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 12-Apr-21 |  |  | 22429.2 | 195847.87 | 22429.2 | 22429.2 | Roy Owen |  | 04-Jun-21 | 28-Feb-22 | 31-May-21 | 21-Oct-21 | 10-Dec-21 | Customer | Customer |  | 0
638226 | JOINT USE PERMIT HW2020-115 - KILBOURN AND HWY 8 - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 16-Apr-21 |  |  | 5421.23 | 5575.61 | 5421.23 | 5421.23 | Brad Carr |  | 16-Apr-21 | 05-Jan-22 | 16-Apr-21 | 16-Apr-21 | 16-Apr-21 |  |  |  | 0
638264 | ST CATH AUTO SWITCHES - BRANCH PLANT 830 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 21-Dec-22 |  |  | 0 | 195360.42 |  | 0 | Weaver, Thomas |  | 21-Dec-22 | 16-Feb-23 | 21-Dec-22 | 21-Dec-22 | 21-Dec-22
638272 | JOINT USE PERMIT HW2020-122 - GOVERNORS - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 12-Apr-21 |  |  | 39651.75 | 7094.66 | 39651.75 | 39651.75 | K-Line Construction | K-Line | 21-May-21 | 13-Feb-23 | 17-May-21 | 20-Oct-21 | 20-Oct-21 | Filler | Filler |  | 0
638271 | JOINT USE PERMIT HW2020-121 - HILLSIDE S AND ROGERS - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 19-Oct-21 |  |  | 16322 | 16613.02 | 16322 | 16322 | K-Line Construction | K-Line | 28-Jan-22 | 30-Jan-23 | 03-Jan-22 | 24-Jan-22 | 24-Jan-22 | Filler | Filler |  | 0
638270 | JOINT USE PERMIT HW2020-120 - SOUTH W, WOODWARD, HILLSIDE N, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 21-May-21 |  |  | 10651.8 | 10156.3 | 10651.8 | 10651.8 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 07-Mar-22 | 26-Apr-22 | 26-Apr-22 | Filler | Filler |  | 0
638288 | PIER 8 PUMPING STATION - TEMP SERVICE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Jolie, Chris | 15-Dec-20 |  |  | 98165.84 | 87921.56 | 98165.84 | 98165.84 | Macdougall, Stephen | Fairway | 27-Jan-21 | 11-Oct-22 | 11-Jan-21 | 11-Jan-21 | 14-Nov-22 | Customer | Customer |  | 0
638310 | LANG & REID - PHASE 2 / HAM / SR | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Kappheim, Adam | Sabbah, Amir | 05-Oct-20 |  |  | 52238.97 | 0 | 52238.97 | 52238.97 | Roy Owen |  | 02-Dec-20 | 18-Oct-22 | 09-Nov-20 | 06-Apr-21 | 20-Oct-21 | Customer | Customer |  | 0
638314 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 EAST OF DEWITT (PART 3) | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
638323 | ABERDEEN #4 O/H -BAY TO MTN ACCESS | 820 - Nebo | 150351 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Anderson, Dean | 10-Nov-20 |  |  | 658514 | 774592.06 | 963748.7 | 658514 | Koeppe, Jeffrey |  | 15-Jun-21 | 08-Jun-22 | 25-Jan-21 | 01-Feb-21 | 21-May-21 | COVID19 |  |  | -305,234.70
638387 | 4 VICKERS RD. EXPANSION | 820 - Nebo | 152381 | Active | 92 | ANALYZE |  |  | 2023 | Jakubowski, Mark | Jolie, Chris | 25-Oct-22 |  |  | 182263.12 | 150415.78 | 170370.28 | 182263.12 | Brad Carr | B&M | 27-Jan-23 | 26-Jul-23 | 09-Jan-23 | 09-Jan-23 | 23-May-23 | Customer | Customer |  | 11,892.84
638408 | 254 SOUTH SERVICE ROAD / HAM / UP | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2021 | Kappheim, Adam | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 24-Nov-21
638415 | 631 SOUTH TOWN LINE RD / HAM / UP | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Kappheim, Adam | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 13-Jun-22
638413 | JOINT USE PERMIT HW2020-127 - RAINBOW - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 20-Jul-21 |  |  | 11449.14 | 5759.59 | 11449.14 | 11449.14 | Brad Carr |  | 30-Sep-21 | 15-Nov-21 | 30-Aug-21 | 30-Aug-21 | 30-Aug-21 |  |  |  | 0
638412 | JOINT USE PERMIT HW2020-126 - DUNDAS EAST - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 22-Apr-21 |  |  | 14145.44 | 9629.17 | 14145.44 | 14145.44 | Brad Carr | K-Line | 28-May-21 | 14-Dec-21 | 24-May-21 | 20-Oct-21 | 20-Oct-21 | Filler | Filler |  | 0
638420 | TX RENEWAL PROGRAM 2021 - PHASE 4 - 224 GLENRIDGE AVE - 1 | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 03-Dec-20 |  |  | 42179.03 | 69709.7 | 42179.03 | 42179.03 | Frank Giancola |  | 16-Apr-21 | 20-Jul-21 | 12-Apr-21 | 12-Apr-21 | 17-May-21 | Filler | Filler |  | 0
638419 | TX RENEWAL PROGRAM 2021 - PHASE 3 - HAMILTON - 3 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 07-Dec-20 | 3 | 3 | 57206.18 | 55530.61 | 57206.18 | 57206.18 | Koeppe, Jeffrey |  | 01-Apr-22 | 09-Aug-22 | 21-Mar-22 | 07-Mar-22 | 02-May-22 |  | Filler |  | 0
638424 | 237 ARVIN AVE - TK PLASTICS LTD/HAM/UP00070769 /3PHPAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Bharosi, Mohindra | 13-Apr-21 |  |  | 140711.36 | 128710.29 | 102458.78 | 140711.36 | Macdougall, Stephen |  | 08-Jun-21 | 17-Oct-22 | 17-May-21 | 04-Jun-21 | 24-Jan-22 | Customer | Customer |  | 38,252.58
638426 | 2 MEDICORUM PLACE - VICANO CONSTRUCTION LTD/HAM/NS00046555/3PHPAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Bharosi, Mohindra | 09-Feb-21 |  |  | 86740.31 | 74671.79 | 77972.43 | 86740.31 | Roy Owen |  | 12-Mar-21 | 22-Sep-22 | 10-Mar-21 | 02-Jul-21 | 29-Jul-21 | MC/PUCC Permit | MC/PUCC Permit |  | 8,767.88
638427 | 432 HIGHLAND RD -HIGHLAND PACKERS/HAM/UP00056773/3PHPAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Bharosi, Mohindra | 10-Mar-21 |  |  | 150406.32 | 141617.13 | 144667.02 | 150406.32 | Macdougall, Stephen |  | 25-May-21 | 22-Sep-22 | 19-Apr-21 | 14-Apr-21 | 16-Aug-21 |  | Customer |  | 5,739.30
638468 | SC869 - SWITCH REPLACEMENT - GATESTONE DRIVE - 1 | 820 - Nebo | 151083 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 21-Dec-20 |  |  | 88108.77 | 79042.68 | 88108.77 | 88108.77 | Roy Owen |  | 04-Feb-21 | 16-Aug-21 | 25-Jan-21 | 19-Apr-21 | 19-Apr-21 | Filler | Filler |  | 0
638484 | 2021 TX RENEWAL - 21 JONES ST STONEY CREEK - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 06-Oct-21 |  |  | 30309.88 | 32754.2 | 30309.88 | 30309.88 | Roy Owen | Fairway | 02-Nov-21 | 08-Jun-22 | 01-Nov-21 | 23-Dec-21 | 24-Dec-21 | Filler | Filler |  | 0
638518 | 2021 EMERGING UG - CABLE FAULT WILLCHER DR - 3 TX | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 08-Mar-21 |  |  | 89853.76 | 98387.1 | 89853.76 | 89853.76 | Dan Despres | Wiens | 25-Jun-21 | 17-Mar-22 | 14-Jun-21 | 14-Jun-21 | 20-Aug-21 |  | Contractor |  | 0
638523 | AUTO SWITCH INSTALLS - DUNDAS TS FEEDERS, 2 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 28-Dec-20 | 2 |  | 140234.97 | 152399.04 | 140234.97 | 140234.97 | Koeppe, Jeffrey |  | 07-May-21 | 12-Apr-22 | 19-Apr-21 | 22-Mar-21 | 04-Jun-21 |  | N/A |  | 0
638524 | AUTO SWITCH INSTALLS - VANSICKLE TS FEEDER, 4 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 17-Dec-20 | 4 |  | 276812.34 | 342646.34 | 276812.34 | 276812.34 | Dan Despres |  | 02-Jun-21 | 24-Apr-23 | 19-Apr-21 | 05-Apr-21 | 29-Jun-21 |  | Materials |  | 0
638529 | 2021 POLE RENEWAL - VANSICKLE TS - 17 POLES | 830 - St. Catharines | 150335 | Active | 82 | PDG SnR |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 30-Apr-21 | 17 |  | 1297513.62 | 29246.15 | 1297513.62 | 1297513.62 | Brad Carr | K-Line | 21-Jul-23 | 31-Jul-23 | 17-Jul-23 |  |  | Materials |  |  | 0
638548 | TX RENEWAL PROGRAM 2021 PHASE 7 - HAMILTON EAST - 3 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 07-Dec-20 |  |  | 68278.15 | 64001.63 | 68278.15 | 68278.15 | Macdougall, Stephen |  | 30-Jun-21 | 10-Aug-22 | 19-Apr-21 | 24-May-21 | 22-Nov-21 | Filler | Filler |  | 0
638547 | TX RENEWAL PROGRAM 2021 - PHASE 6 - WATERDOWN - 3 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 03-Dec-20 |  |  | 61574.74 | 69539.41 | 61574.74 | 61574.74 | Macdougall, Stephen |  | 11-Jun-21 | 25-Apr-22 | 31-May-21 | 18-Jun-21 | 12-Jul-21 | Filler | Filler |  | 0
638553 | TX RENEWAL PROGRAM 2021 - PHASE 11 - SCH SOUTH 2 - 7 | 830 - St. Catharines | 150336 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-20 | 7 | 6 | 148817.32 | 120557.44 | 173328.44 | 148817.32 | Dan Despres |  | 15-Jun-22 | 26-Jul-23 | 02-May-22 | 16-Jun-22 | 02-Dec-22 | Weather | Locates |  | -24,511.12
638552 | TX RENEWAL PROGRAM 2021 - PHASE 10 - SCH SOUTH 1 - 7 | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 10-Dec-20 | 7 | 5 | 143878.94 | 94553.67 | 143878.94 | 143878.94 | Dan Despres |  | 04-Jan-22 | 09-Aug-22 | 01-Dec-21 | 03-Dec-21 | 11-Apr-22 | Lines | MC/PUCC Permit |  | 0
638551 | TX RENEWAL PROGRAM 2021 - PHASE 9 - SCH NORTH 2 - 9 | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 08-Dec-20 |  |  | 169351.74 | 166592.61 | 169351.74 | 169351.74 | Frank Giancola |  | 13-May-21 | 20-Jul-21 | 05-Apr-21 | 08-Mar-21 | 12-May-21 | Filler | Filler |  | 0
638550 | TX RENEWAL PROGRAM 2021 - PHASE 8 - SCH NORTH 1 - 6 | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 07-Dec-20 |  |  | 98875.07 | 92063.15 | 98875.07 | 98875.07 | Frank Giancola |  | 30-Jul-21 | 20-Sep-21 | 01-Mar-21 | 12-Feb-21 | 11-Mar-21 |  |  |  | 0
638645 | AUTO SWITCH INSTALLS - GLENDALE TS FEEDERS, 6 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 25-Jan-21 | 6 |  | 479841.03 | 444418.39 | 469958.33 | 479841.03 | Brad Carr | B&M | 24-Sep-21 | 22-Sep-22 | 14-Jun-21 | 28-Jun-21 | 23-Sep-21 | Locates |  |  | 9,882.70
638658 | COSTCO ST.CATHARINES - 3 NORTH SERVICE RD | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2021 | Kappheim, Adam | Oosterlinck, David | 24-Nov-20 |  |  | 167745.65 | 265615.94 | 161567.76 | 167745.65 | Frank Giancola | Wiens | 26-Jan-21 | 26-Jul-23 | 11-Jan-21 | 02-Dec-20 | 02-Jul-21 |  | Materials |  | 6,177.89
638667 | 10 NASH ST, ST. CATHARINES - ANCHOR RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
638668 | MOHAWK & UPPER JAMES SWITCH, 1 | 820 - Nebo | 150376 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Anderson, Dean | 19-Mar-21 | 1 |  | 777016.73 | 649019.37 | 787631.9 | 777016.73 | Brad Carr | B&M | 06-Aug-21 | 22-Sep-22 | 25-May-21 | 24-May-21 | 11-Nov-21 |  | Contractor |  | -10,615.17
638721 | JOINT USE PERMIT HW2020-135 - MAIN SOUTH - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 28-Jun-21 |  |  | 4683.83 | 5538.46 | 4683.83 | 4683.83 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 07-Mar-22 | 12-Jan-22 | 12-Jan-22 | Filler | Filler |  | 0
638727 | 41 REID AVE / HAM / NS | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Kappheim, Adam | Sabbah, Amir | 03-Jun-21 |  |  | 80765.48 | 64984.5 | 80765.48 | 80765.48 | Roy Owen | Fairway | 25-Jun-21 | 24-May-23 | 16-Jun-21 | 28-Jun-21 | 02-Jul-21 | Customer | Customer |  | 0
638760 | 1831X RELIABILITY PROJECT | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 01-Sep-21 |  |  | 56835.09 | 28308.91 | 56835.09 | 56835.09 | Macdougall, Stephen |  | 19-Jan-22 | 22-Sep-22 | 10-Jan-22 | 10-Jan-22 | 24-Jan-22 | N/A | N/A |  | 0
638770 | POWERVIEW AVE. POLE LINE REPLACEMENT - 13 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 26-Feb-21 | 13 | 13 | 163862.56 | 153619.88 | 163862.56 | 163862.56 | Dan Despres |  | 16-Mar-22 | 08-Jun-22 | 01-Feb-22 | 14-Feb-22 | 18-Mar-22 | MC/PUCC Permit | MC/PUCC Permit |  | 0
638774 | JOINT USE PERMIT HW2020-137 - GRAYS AND HWY 8 - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 31-Mar-21 |  |  | 6694.25 | 5365.1 | 6694.25 | 6694.25 | Brad Carr | K-Line | 31-Mar-21 | 24-Nov-21 | 29-Mar-21 | 29-Mar-21 | 29-Mar-21 |  |  |  | 0
638773 | JOINT USE PERMIT HW2020-136 - CREIGHTON, BRENTWOOD, GOVERNORS - HAM | 820 - Nebo | 151536 | Active | HO | RELEASED |  |  | 2023 | O'Gay, Brian | Johnson, William | 15-Apr-21 |  |  | 7379.26 | 4653.27 | 7379.26 | 7379.26 | K-Line Construction | K-Line | 31-Mar-22 | 26-Jul-23 | 07-Mar-22 |  |  | Filler | Filler |  | 0
638832 | 112 KING STREET EAST - ROYAL CONNAUGHT PHASE 3,4,5/HAM/NS00039314 /COSUB | 820 - Nebo | 150449 | Active | 40 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
638887 | 223 EAST AVE - EXPANSION | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Kappheim, Adam | Bennett, Aaron | 26-Oct-21 |  |  | 61468.89 | 54868.94 | 61468.89 | 61468.89 | Macdougall, Stephen |  | 29-Dec-21 | 08-Aug-23 | 06-Dec-21 | 06-Dec-21 | 21-Jan-22 |  | COVID19 |  | 0
638901 | 90 CARLING ST - EXPANSION | 820 - Nebo | 150449 | Active | 70 | ACTIVE |  |  | 2023 | Kappheim, Adam | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
638903 | CABLE INJECT - JACOBSON/CHESTNUT/WOODCREST | 830 - St. Catharines | 151279 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 30-Nov-20 |  |  | 125255.5 | 209930.21 | 125255.5 | 125255.5 | Brad Carr | Nvinium | 03-Sep-21 | 18-Aug-22 | 03-Aug-21 | 20-Oct-21 | 31-May-22 | Contractor | Contractor |  | 0
637154 | POLE RELOCATION - 11 SHELLEY AVE, ST. CATHARINES | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 25-Aug-22
638925 | 1190 MAIN ST W EXPANSION WORK | 820 - Nebo | 152381 | Active | 50 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
638930 | 2021 POLE RENEWAL - ROSEMOUNT - 7 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 15-Mar-21 | 7 | 8 | 106822.37 | 106859.56 | 106822.37 | 106822.37 | Dan Despres |  | 02-Feb-22 | 09-Aug-22 | 10-Jan-22 | 03-Jan-22 | 28-Feb-22 |  | Lines |  | 0
638929 | 270 MELVIN AVE - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 01-Jun-21 |  |  | 31211.95 | 234462.62 | 31211.95 | 31211.95 | Roy Owen |  | 10-Mar-22 | 02-Feb-23 | 07-Mar-22 | 15-Mar-22 | 24-May-22 | Customer | Customer |  | 0
638931 | 2021 TX RENEWAL UG - 250 LINWELL RD - 1 TX | 830 - St. Catharines | 150336 | Active | 94 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 31-Jan-23 | 1 | 1 | 129980.39 | 108160.01 | 129980.39 | 129980.39 | Frank Giancola | GUCI | 24-Mar-23 | 09-Aug-23 | 13-Mar-23 | 22-Feb-23 | 12-Apr-23 | Contractor | Contractor |  | 0
638952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 1) | 820 - Nebo | 151303 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 06-May-21 |  |  | 1973542.16 | 2176427.82 | 1764106.06 | 1973542.16 | Brad Carr | B&M | 23-Dec-21 | 16-Mar-23 | 21-Jun-21 | 30-Aug-21 | 23-Dec-21 | Contractor |  |  | 209,436.10
638951 | CARLTON M10 RELIABILITY CONCERNS | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 27-Apr-21 |  |  | 120730.43 | 144157.61 | 112602.15 | 120730.43 | Dan Despres |  | 22-Nov-21 | 09-Aug-22 | 18-Oct-21 | 09-Nov-21 | 14-Feb-22 | Lines | Lines |  | 8,128.28
638954 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (EAST OF UPPER PARADISE) (3A) | 820 - Nebo | 151303 | Active | 92 | ACTIVE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 31-May-22 |  |  | 905115.08 | 964087.39 | 1011181.46 | 905115.08 | Brad Carr | B&M | 09-Dec-22 | 26-Jul-23 | 20-Jun-22 | 05-Sep-22 | 15-Dec-22 | Locates | Locates |  | -106,066.38
638969 | MAUNAL SWITCH RENEWAL - ST. CATHARINES 2021, 1 | 830 - St. Catharines | 150337 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 11-Dec-20 |  |  | 21509.35 | 24997.08 | 21509.35 | 21509.35 | Dan Despres |  | 16-Apr-21 | 05-Jul-21 | 13-Apr-21 | 01-Apr-21 | 05-Apr-21 |  |  |  | 0
638968 | AUTOMATE SWITCH RENEWAL - HAMILTON 2021, 4 | 820 - Nebo | 150337 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 26-Jan-21 | 4 |  | 363415.38 | 379462.21 | 319462.49 | 363415.38 | Brad Carr | B&M | 29-Apr-21 | 25-Apr-22 | 29-Mar-21 | 31-Mar-21 | 18-Jun-21 | Contractor | Contractor |  | 43,952.89
638967 | MAUNAL SWITCH RENEWAL - HAMILTON 2021 - 2 | 820 - Nebo | 150337 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-20 |  |  | 48479.72 | 53497.16 | 73767.12 | 48479.72 | Koeppe, Jeffrey |  | 25-Jun-21 | 25-Apr-22 | 14-Jun-21 | 12-Jul-21 | 27-Oct-21 | Locates | Locates |  | -25,287.40
639008 | 2021 INSULATOR RENWAL - BATCH 2 - 81 INSULATORS | 820 - Nebo | 151725 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 25-Jan-21 |  |  | 66021.06 | 3293.79 | 66021.06 | 66021.06 | Koeppe, Jeffrey |  | 28-Jul-21 | 04-Aug-23 | 19-Jul-21 | 09-Aug-21 |  | Lines | Lines |  | 0
639007 | INSULATOR RENEWAL - HAMILTON 2021 - PHASE 1 | 820 - Nebo | 151725 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 25-Jan-21 |  |  | 163763.67 | 149176.6 | 145084.69 | 163763.67 | Koeppe, Jeffrey |  | 16-Jul-21 | 29-Apr-22 | 21-Jun-21 | 14-May-21 | 08-Oct-21 |  | Lines |  | 18,678.98
639006 | 2021 SWITCH RENEWAL - PHASE 4 - 1 SW | 820 - Nebo | 150337 | Active | 96 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 28-Nov-22 | 1 | 1 | 212423.86 | 134998.93 | 205972.45 | 212423.86 | Koeppe, Jeffrey |  | 05-May-23 | 26-Jul-23 | 17-Apr-23 | 16-Mar-23 | 14-Apr-23 |  |  |  | 6,451.41
639011 | EMERGING OH INSULATOR REPLACMENT 2022 - LAKE M2 | 820 - Nebo | 150828 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 14-Apr-22 |  |  | 85223.45 | 111786.11 | 66470.62 | 85223.45 | Koeppe, Jeffrey |  | 22-Jul-22 | 26-Jul-23 | 04-Jul-22 | 18-Jul-22 | 16-Dec-22 | Filler | Filler |  | 18,752.83
639010 | EMERGING OH INSULATOR REPLACEMENT 2022 - LAKE M4 | 820 - Nebo | 150496 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 29-Apr-22 |  |  | 106174.68 | 100409.5 | 106174.68 | 106174.68 | Koeppe, Jeffrey |  | 07-Jul-22 | 17-Oct-22 | 06-Jun-22 | 18-Jul-22 | 24-Oct-22 | Filler | Filler |  | 0
639016 | TX RENEWAL PROGRAM 2021 - PHASE 15 - EAST 45TH STREET - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-20 | 1 | 1 | 34177.17 | 21200.61 | 34177.17 | 34177.17 | Koeppe, Jeffrey |  | 08-Mar-22 | 09-Aug-22 | 28-Feb-22 | 28-Feb-22 | 04-May-22 | Lines | Filler |  | 0
639015 | TX RENWAL PROGRAM 2021 - PHASE 14 - FERNWOOD CRES - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-20 |  |  | 30676.28 | 25596.72 | 30676.28 | 30676.28 | Koeppe, Jeffrey |  | 24-Sep-21 | 09-Aug-22 | 20-Sep-21 | 15-Sep-21 | 05-Nov-21 |  | Lines |  | 0
639014 | TX RENWAL PROGRAM 2021 - PHASE 13 - ORGAN CRES - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-20 | 1 | 1 | 28606.15 | 24098.25 | 28606.15 | 28606.15 | Koeppe, Jeffrey |  | 18-Mar-22 | 09-Aug-22 | 14-Mar-22 | 18-Feb-22 | 10-May-22 |  | Filler |  | 0
639013 | TX RENWAL PROGRAM - PHASE 12 - EAST 43RD ST - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-20 |  |  | 34416.16 | 46895.55 | 34416.16 | 34416.16 | Koeppe, Jeffrey |  | 14-Dec-21 | 09-Aug-22 | 06-Dec-21 | 24-Nov-21 | 14-Dec-21 |  |  |  | 0
639017 | TX RENEWAL PROGRAM 2021 - PHASE 16 - GRANDFIELD ST - 1 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-20 | 1 | 1 | 25878.96 | 32407.96 | 25878.96 | 25878.96 | Koeppe, Jeffrey |  | 16-Dec-21 | 09-Aug-22 | 13-Dec-21 | 31-Mar-22 | 04-May-22 | Lines | Lines |  | 0
639020 | 2021 - POLE RENEWAL - 2 POLES | 820 - Nebo | 150335 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 16-Dec-21 | 2 | 2 | 45129.1 | 43207.38 | 45129.1 | 45129.1 | Brad Carr | K-Line | 21-Oct-22 | 26-Jul-23 | 10-Oct-22 | 05-Dec-22 | 20-Dec-22 | Locates | Locates |  | 0
639022 | BALDWIN CARRY-OVER WORK 2021 | 820 - Nebo | 150352 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 29-Apr-21 |  |  | 554071.86 | 609366.87 | 505748.73 | 554071.86 | Brad Carr | K-Line | 11-Jun-21 | 21-Aug-22 | 17-May-21 | 03-May-21 | 23-Dec-21 |  | MC/PUCC Permit |  | 48,323.13
639050 | 2022 TX RENEWAL HAM - BATCH 4 - 2 TX | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639049 | 2022 TX RENEWAL HAM - BATCH 3 - 1TX | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639054 | 2021 TX RENEWAL - BATCH 22 - 2 TX | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639053 | 2021 TX RENEWAL UG - BATCH 21 - 1 TX | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639052 | 2021 TX RENEWAL - BATCH 20 - 1 TX | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639051 | 2022 TX RENEWAL HAM - BATCH 5 - 1TX | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639064 | 90 GLOVER ROAD | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Kappheim, Adam | Djuric, Zdravko | 25-Aug-21 |  |  | 53095.47 | 62391.81 | 53095.47 | 53095.47 | Roy Owen |  | 14-Oct-21 | 28-Jul-23 | 04-Oct-21 | 04-Oct-21 | 20-Apr-22 |  | MC/PUCC Permit |  | 0
639079 | 30 LOTTRIDGE ST / HAM / UP / 1PH SERV | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Paesano, Andrew | Dragojevic, Igor | 07-Dec-20 |  |  | 31657.69 | 30162.82 | 31657.69 | 31657.69 | Macdougall, Stephen |  | 18-Jan-21 | 17-Jan-22 | 11-Jan-21 | 02-Feb-21 | 26-Feb-21 | COVID19 | COVID19 |  | 0
639130 | 89 SUSSEX ST, HAMILTON - POLE RELOCATION | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 31-Aug-22
639129 | 7 KIRK ST, ST. CATHARINES - POLE RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 14-Sep-22
639155 | JOINT USE PERMIT HW2020-144 - BUNTING AND LAKESHORE - STC | 830 - St. Catharines | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Mar-21 |  |  | 8407.92 | 5894.04 | 8407.92 | 8407.92 | Brad Carr | K-Line | 09-Apr-21 | 18-May-22 | 05-Apr-21 | 08-Jun-21 | 08-Jun-21 | Filler | Filler |  | 0
639168 | 1 WEST AVE, STONEY CREEK - GUY-WIRE & ANCHOR RELOCATION | 820 - Nebo | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639301 | 61 VILLAGE RD / SCH / UP00009898 / 3PH PAD INSTALL | 830 - St. Catharines | 150455 | Active | HO | RELEASED |  |  | 2023 | Paesano, Andrew | Laus, Tomislav | 14-Jan-22 | 1 |  | 72140 | 2648.04 | 72140 | 72140 | Frank Giancola |  | 04-Mar-22 | 31-Jul-23 | 01-Mar-22 |  |  | Customer | Customer |  | 0
638636 | 2021 TX RENEWAL - 75 VENTURA - 5 | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 28-Feb-21 | 5 | 5 | 43747.85 | 63348.02 | 43747.85 | 43747.85 | Frank Giancola |  | 29-Apr-22 | 22-Sep-22 | 25-Apr-22 | 27-May-22 | 27-May-22 | Customer | Customer |  | 0
639338 | HP95614 RELOCATE - WEST 5TH | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Celic, Dusan | 11-Mar-21 |  |  | 22931.86 | 18629.21 | 22931.86 | 22931.86 | Brad Carr | K-Line | 22-Mar-21 | 31-Jan-22 | 18-Mar-21 | 18-Mar-21 | 19-Apr-21 |  |  |  | 0
639348 | 50 HERRICK AVE / SCH / NS00073409 / 3PH PAD INSTALL - Temp | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Laus, Tomislav | 19-Oct-21 |  |  | 85801.62 | 95095.32 | 85801.62 | 85801.62 | Frank Giancola | Wiens | 29-Nov-21 | 26-Jul-23 | 22-Nov-21 | 17-Nov-21 | 17-Nov-22 |  | Customer |  | 0
639360 | STREETLIGHT CONDUCTOR INSTALL - FIRST RD W | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Celic, Dusan | 28-Jan-21 |  |  | 10883.85 | 4013.65 | 10883.85 | 10883.85 | Koeppe, Jeffrey |  | 11-Mar-21 | 25-May-21 | 10-Mar-21 | 11-Mar-21 | 11-Mar-21 |  |  |  | 0
639368 | 75 JAMES ST SYSTEM EXPANSION | 820 - Nebo | 152381 | Active | 84 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Garcha, Tirath | 23-Mar-23 |  |  | 4919543.96 | 1141150.88 | 4873401.51 | 4919543.96 | Tony Ierace | B&M | 18-Dec-23 | 12-Feb-24 | 01-May-23 | 01-May-23 |  |  |  |  | 46,142.45
639366 | RIDLEY RD RECONSTRUCTION - CITY OF ST. CATHARINES | 830 - St. Catharines | 150653 | Active | 45 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
639433 | MAPLE AVE / KENILWORTH TERM POLE | 820 - Nebo | 152381 | Active | 98 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Jolie, Chris | 30-Jun-21 |  |  | 148213.95 | 133212.08 | 150655.12 | 148213.95 | Brad Carr | B&M | 15-Oct-21 | 26-Jul-23 | 16-Aug-21 | 04-Aug-21 | 02-Dec-21 |  | Contractor |  | -2,441.17
639456 | 63 VINE ST / SCH / NS00077208 / 3PH PAD INSTALL | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2021 | Paesano, Andrew | Laus, Tomislav | 18-Mar-21 |  |  | 42706.46 | 23769.96 | 42706.46 | 42706.46 | Frank Giancola |  | 07-May-21 | 26-Jul-23 | 03-May-21 | 15-Jun-21 | 08-Jul-21 | Customer | Customer |  | 0
639490 | 2021 EMERGING UG - 184 SPRING CREEK - JC267 RELOCATION | 820 - Nebo | 151452 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639492 | 83 CENTENNIAL PARKWAY SOUTH / STC / NS / 3PH PAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Kappheim, Adam | Djuric, Zdravko | 26-Feb-21 |  |  | 66132.97 | 56890.3 | 66132.97 | 66132.97 | Macdougall, Stephen | Fairway | 14-Jul-21 | 22-Sep-22 | 05-Apr-21 | 22-Jun-21 | 13-Aug-21 | Materials | Customer |  | 0
639494 | JOINT USE PERMIT HW2020-149 - WOODWARD AND BRAMPTON - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 20-Jul-21 |  |  | 5345.12 | 5165.5 | 5345.12 | 5345.12 | Brad Carr |  | 30-Sep-21 | 15-Nov-21 | 30-Aug-21 | 30-Aug-21 | 30-Aug-21 |  |  |  | 0
639525 | 2021 EMERGING OH - EAST 16TH - BELL POLES | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 09-Feb-21 |  |  | 86461.18 | 26084.92 | 75421.37 | 86461.18 | Brad Carr | B&M | 26-Feb-21 | 20-Sep-21 | 15-Feb-21 | 15-Feb-21 | 03-Mar-21 | Contractor | Contractor |  | 11,039.81
639563 | ROGERS BONDS - 2020 BATCH 2 - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 22-Apr-21 |  |  | 4363.79 | 1482.64 | 4363.79 | 4363.79 | Hewitson, Trevor |  | 02-Jul-21 | 05-Jan-22 | 07-Jun-21 | 02-Jun-21 | 02-Jun-21 |  |  |  | 0
639581 | UPPER JAMES & LINC PMH SWITCH, 1 | 820 - Nebo | 150376 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Anderson, Dean | 19-Mar-21 | 1 |  | 604557.24 | 605600.73 | 613926.09 | 604557.24 | Brad Carr | B&M | 30-Jul-21 | 22-Sep-22 | 14-Jun-21 | 22-Jun-21 | 02-Nov-21 | Locates | Locates |  | -9,368.85
639656 | 56 DUNDAS ST E PRIVATE LINE BURIAL | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE | High | Comm | 2021 | Jakubowski, Mark | Jolie, Chris | 03-Mar-21 |  |  | 68244.02 | 65545.36 | 69651.97 | 68244.02 | Brad Carr | B&M | 26-Mar-21 | 03-Aug-21 | 15-Mar-21 | 15-Mar-21 | 18-Mar-21 |  |  |  | -1,407.95
639668 | SC1018 - AUTO PMH 10 | 820 - Nebo | 150337 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639669 | SC35 - CANCELLED | 820 - Nebo | 151083 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639670 | SC775 - MANUAL PMH 9 - 1 | 820 - Nebo | 151083 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 26-Feb-21 |  |  | 88668.39 | 88108.44 | 88668.39 | 88668.39 | Tony Ierace |  | 14-Jul-21 | 29-Sep-22 | 05-Jul-21 | 21-Jun-21 | 15-Oct-21 |  | Lines |  | 0
639697 | 2022 ST. CATHARINES POLE REPLACMENTS - 4 POLES | 830 - St. Catharines | 150335 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 08-Aug-22 | 4 | 4 | 66943.27 | 40624.83 | 66943.27 | 66943.27 | Dan Despres |  | 29-Dec-22 | 26-Jul-23 | 19-Dec-22 | 28-Nov-22 | 23-Dec-22 |  |  |  | 0
639696 | 2022 HAMILTON POLE REPLACEMENTS - 4 POLES | 820 - Nebo | 150335 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 30-Sep-22 | 4 | 4 | 112213.42 | 175880.06 | 109191.46 | 112213.42 | Brad Carr | K-Line | 04-Nov-22 | 26-Jul-23 | 24-Oct-22 | 10-Oct-22 | 04-Nov-22 |  |  |  | 3,021.96
639714 | 90 GLOVER RD EXPANSION | 820 - Nebo | 152381 | Active | 98 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Jolie, Chris | 27-Aug-21 |  |  | 620553.94 | 561999.48 | 589643.33 | 620553.94 | Brad Carr | B&M | 05-Nov-21 | 26-Jul-23 | 07-Sep-21 | 07-Sep-21 | 04-Feb-22 |  | Customer |  | 30,910.61
639718 | JOINT USE PERMIT HW2020-153 - LAKESHORE - ST CATH | 830 - St. Catharines | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 10-Mar-21 |  |  | 12494.72 | 9997.03 | 12494.72 | 12494.72 | Brad Carr | K-Line | 31-May-21 | 24-Nov-21 | 05-Apr-21 | 08-Jun-21 | 08-Jun-21 | Filler | Filler |  | 0
639720 | HEYWOOD GS - NEW FEEDER CABLE & POLE | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 12-Jan-21 |  |  | 20398.83 | 81859.06 | 20398.83 | 20398.83 | Frank Giancola |  | 12-Jan-21 | 15-Jul-21 | 12-Jan-21 | 12-Jan-21 | 12-Jan-21 |  |  |  | 0
638637 | VANSICKLE ROAD - TX REPLACEMENT - 4 | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-20 |  |  | 24858.07 | 33916.66 | 24858.07 | 24858.07 | Dan Despres |  | 10-Sep-21 | 17-Mar-22 | 06-Sep-21 | 09-Aug-21 | 13-Aug-21 |  |  |  | 0
639751 | 1 JARVIS - LINE RELOCATION | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Jolie, Chris | 30-Mar-21 |  |  | 167495.48 | 153500.22 | 176098.58 | 167495.48 | Brad Carr | B&M | 14-May-21 | 18-May-22 | 03-May-21 | 03-May-21 | 21-May-21 | Contractor | Contractor |  | -8,603.10
639755 | 120 SPRING VALLEY CRES / HAM / UP | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2023 | Kappheim, Adam | Sabbah, Amir | 12-Apr-22 |  |  | 62398.49 | 97938.52 | 62398.49 | 62398.49 | Roy Owen | Fairway | 30-May-22 | 01-Jun-23 | 24-May-22 | 19-Jan-23 | 15-Feb-23 | Customer | Customer |  | 0
639763 | 344 READ RD- NEW 600A 347/600V SERVICE | 830 - St. Catharines | 150455 | Active | HO | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David | 29-Jun-21 |  |  | 53567.82 | 9874.14 | 53567.82 | 53567.82 | Frank Giancola | Wiens | 11-Mar-22 | 01-Aug-23 | 07-Mar-22 |  |  | Customer | Customer |  | 0
639762 | 502 ONTARIO ST- NEW 600A 120/208V SERVICE | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2023 | Kappheim, Adam | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 22-Feb-23
639768 | 1048 BARTON ST EAST - ISOLATION REQUEST | 820 - Nebo | 150665 | Active | 84 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan | 11-Jan-21 |  |  | 9820.47 | 6208.28 | 9820.47 | 9820.47 | Macdougall, Stephen |  | 12-Jan-21 | 27-Jul-23 | 11-Jan-21 | 15-Jan-21 |  | Customer | Customer |  | 0
639774 | 23 MICHIGAN AVE - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 98 | COMPLETE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 27-Oct-21 |  |  | 36382.87 | 118602.5 | 36382.87 | 36382.87 | Frank Giancola | Wiens | 20-Dec-21 | 28-Jul-23 | 13-Dec-21 | 13-Dec-21 | 28-Oct-22 |  | Customer |  | 0
639776 | 267 CENTENNIAL PW | 820 - Nebo | 150449 | Active | 91 | ACTIVE |  |  | 2023 | Kappheim, Adam | Bennett, Aaron | 22-Nov-21 |  |  | 151988.01 | 122787.52 | 153445.35 | 151988.01 | Macdougall, Stephen | Fairway | 06-Jan-22 | 03-Aug-23 | 20-Dec-21 | 02-Dec-21 |  | Customer | Customer |  | -1,457.34
639786 | 2 BROCK ST SOUTH, DUNDAS - OH LINE ISOLATION | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 31-Aug-22
639859 | 139 PARKDALE AVE-PARKDALE ELEMENTARY UPGRADE/HAM/UP00087734/3PHPAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Frigotto, Rodrigo | Bharosi, Mohindra | 02-Jun-21 |  |  | 77083.97 | 80756.12 | 77083.97 | 77083.97 | Roy Owen | Fairway | 07-Jul-21 | 22-Sep-22 | 28-Jun-21 | 29-Nov-21 | 20-Dec-21 | Customer | Customer |  | 0
639861 | 1160 MAIN STREET EAST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 91 | TEMP |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor | 01-Sep-21 |  |  | 105354.87 | 103573.16 | 93318.04 | 105354.87 | Macdougall, Stephen | Fairway | 12-Oct-22 | 28-Jul-23 | 04-Oct-21 | 12-Nov-21 |  | Locates | Customer |  | 12,036.83
639873 | MILLBANK STREET - SERVICE RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
639878 | SC1127 - AUTO PMH-9 | 830 - St. Catharines | 151083 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 152088.63 | 2248.38 | 152088.63 | 152088.63 | Frank Giancola |  |  | 26-Jul-23 |  |  |  |  | N/A |  | 0
640051 | ROXBOROUGH PARK POLE LINE REMOVAL (HAMILTON) | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 27-Apr-21 |  |  | 121464.67 | 127137.42 | 121464.67 | 121464.67 | Brad Carr | K-Line | 04-Jun-21 | 22-Aug-22 | 17-May-21 | 12-Jul-21 | 15-Jul-21 | Contractor | Contractor |  | 0
640054 | NICHE - 239 LAKESHORE RD - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 82 | RELEASED |  |  | 2023 | Velickovski, Goran | Morris, Mark | 19-Apr-23 |  |  | 304416.97 | 31641.76 | 304416.97 | 304416.97 | Frank Giancola | Transpw | 13-Sep-23 | 13-Sep-23 | 01-Aug-23 | [5 empty] | 0
640102 | JOINT USE PERMIT HW2020-156 - MAIN N, HAMILTON N, WESLEY, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 01-Feb-22 |  |  | 11349.44 | 10172.96 | 11349.44 | 11349.44 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 14-Mar-22 | 07-Feb-22 | 07-Feb-22 | Filler | Filler |  | 0
640153 | AUTO SWITCH INSTALLS - CARLTON TS FEEDERS, 6 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 03-Mar-21 | 6 |  | 393397.26 | 423475.18 | 384232.26 | 393397.26 | Brad Carr | K-Line | 12-Nov-21 | 22-Sep-22 | 04-Oct-21 | 04-Oct-21 | 26-Nov-21 |  | Control/SCADA |  | 9,165.00
640193 | 1160 MAIN ST E - STREET LIGHT SERVICE WIRE RELOCATION | 820 - Nebo | 150665 | Active | 91 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan | 11-Feb-21 |  |  | 13813.73 | 3159.12 | 13813.73 | 13813.73 | Koeppe, Jeffrey |  | 17-Mar-22 | 31-Jul-23 | 14-Mar-22 | 04-Mar-21 |  | Customer | Customer |  | 0
640201 | AUTO SWITCH INSTALLS - BUNTING & CARLTON TS FEEDERS, 3 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 31-Mar-21 | 3 |  | 185288.15 | 251869.1 | 183630.65 | 185288.15 | Frank Giancola |  | 26-Jul-21 | 24-Apr-23 | 07-Jun-21 | 04-Jun-21 | 23-Jul-21 |  |  |  | 1,657.50
640203 | 71 MAIN STREET/DUN/NS00101750/3PHPAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Bharosi, Mohindra | 21-Jan-22 |  |  | 81664.04 | 87120.46 | 81664.04 | 81664.04 | Roy Owen | Fairway | 04-Mar-22 | 17-Apr-23 | 01-Mar-22 | 10-Oct-22 | 09-Nov-22 | Customer | Customer |  | 0
631935 | 2021 - EMERGING UG - 2 POLES & CABLE REPLACEMENT | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 26-Feb-21 |  |  | 60128.5 | 49041.7 | 82151.11 | 60128.5 | Brad Carr | B&M | 31-May-21 | 18-May-22 | 17-May-21 | 18-Jun-21 | 21-Jun-21 | Contractor | Contractor |  | -22,022.61
640244 | CUSTOMER INITIATED SYSTEM EXPANSION - BELL MANOR ST - HAMILTON | 820 - Nebo | 152381 | Active | 91 | ACTIVE | Medium | Comm | 2022 | Jakubowski, Mark | Celic, Dusan | 30-May-22 |  |  | 790582.12 | 699098.11 | 790582.12 | 790582.12 | Brad Carr | B&M | 30-Sep-22 | 26-Jul-23 | 18-Jul-22 | 05-Sep-22 | 15-Dec-22 | Customer | Customer |  | 0
640250 | 30 QUEEN ST - SUBD RES EDS | 820 - Nebo | 150588 | Active | 45 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640253 | CUSTOMER INITIATED SERVICE UPGRADE - 8 TISDALE AVE S - HAMILTON | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Celic, Dusan | 29-Jun-21 |  |  | 111951.96 | 77762.88 | 111951.96 | 111951.96 | Brad Carr | K-Line | 20-Aug-21 | 15-Jun-22 | 09-Aug-21 | 05-Nov-21 | 10-Dec-21 | Locates | N/A |  | 0
640278 | GRAPEVIEW COMMON - SUBD RES EDS | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 24-Jun-21 |  |  | 195879.46 | 185080.52 | 195879.46 | 195879.46 | Frank Giancola | Transpw | 20-Aug-21 | 11-Nov-21 | 09-Aug-21 | 26-Jul-21 | 01-Oct-21 |  | Customer |  | 0
640280 | 5 HAMILTON ST N / HAM / NS | 820 - Nebo | 150449 | Active | 92 | ANALYZE |  |  | 2023 | Kappheim, Adam | Sabbah, Amir | 25-Apr-22 |  |  | 173126.97 | 212055.22 | 119045.71 | 173126.97 | Roy Owen | Fairway | 03-Jun-22 | 02-Aug-23 | 24-May-22 | 01-Nov-22 | 01-May-23 | Locates | Locates |  | 54,081.26
640298 | HORNING TS - MTN FEEDERS - M47X - PHASE 2 | 820 - Nebo | 150376 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean | 23-Jun-22 |  |  | 3378989.82 | 2503663.27 | 3378989.82 | 3378989.82 | Tony Ierace |  | 07-Dec-22 | 26-Jul-23 | 11-Jul-22 | 25-Jul-22 |  | Lines | Materials |  | 0
640308 | GENEVA ST & CARLTON ST POLE RELOCATION | 830 - St. Catharines | 150653 | Inactive | 99 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Patel, Ketan | 09-Jun-21 |  |  | 108528.69 | 85727.48 | 108528.69 | 108528.69 | Frank Giancola | Wiens | 14-Mar-22 | 22-Sep-22 | 07-Mar-22 | 09-Aug-21 | 28-Mar-22 | Locates | Contractor |  | 0
640314 | HORNING TS - MTN FDRS - M47X - O/H- PHASE 4 | 820 - Nebo | 150376 | Active | 82 | RELEASED |  |  | 2023 | Beaudrie, Scott | Anderson, Dean | 24-Apr-23 |  |  | 2248463.11 | 135276.95 | 2248463.11 | 2248463.11 | Brad Carr | K-Line | 10-Nov-23 | 10-Nov-23 | 26-Jun-23 |  |  | Materials | Materials |  | 0
640316 | JOINT USE PERMIT HW2021-005 - BOND N, BOND S, JAMES, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 15-Nov-21 |  |  | 14286.52 | 10637.96 | 14286.52 | 14286.52 | K-Line Construction | K-Line | 07-Jan-22 | 30-Jan-23 | 03-Jan-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
640315 | JOINT USE PERMIT HW2021-004 - NAPIER N, HATT, MATILDA N, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 01-Feb-22 |  |  | 12571.18 | 9712.58 | 12571.18 | 12571.18 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 14-Mar-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
640327 | EDEN PARK - PHASE 2 = SUBD EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640444 | GAGE & BEECHWOOD TX RELOCATION | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 31-May-21 |  |  | 11318.58 | 7007.68 | 11318.58 | 11318.58 | Koeppe, Jeffrey |  | 29-Sep-21 | 22-Aug-22 | 27-Sep-21 | 15-Nov-21 | 19-Nov-21 | Locates | Locates |  | 0
640459 | CITY OF HAMILTON - GRANT BLVD, TX UPGRADE | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-21
640497 | ROXBOROUGH PARK PHASE 2 - SUBD EDS | 820 - Nebo | 150588 | Active | 84 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark | 24-Jun-22 |  |  | 2010170.31 | 1182457.43 | 2010170.31 | 2010170.31 | Macdougall, Stephen | Transpw | 22-Nov-22 | 02-Oct-23 | 09-Aug-22 | 05-Sep-22 |  | Customer | Customer |  | 0
635747 | 2021 POLE RENEWAL - BATCH 1 - 5 POLES | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 31-May-21 | 5 |  | 92761.37 | 66873.39 | 92761.37 | 92761.37 | Brad Carr | K-Line | 15-Oct-21 | 14-Feb-22 | 04-Oct-21 | 05-Oct-21 | 04-Nov-21 | Locates | Locates |  | 0
640513 | YALE CRES - OVERHEAD PRIMARY RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Patel, Ketan | 31-Aug-21 |  |  | 121835.32 | 77226.8 | 121835.32 | 121835.32 | Dan Despres | Wiens | 08-Nov-21 | 22-Feb-23 | 04-Oct-21 | 18-Oct-21 | 25-Nov-21 | N/A | N/A |  | 0
638970 | 2021 EMERGING OH - EAST 25TH ST - BELL POLES | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 15-Jun-21 |  |  | 115586.37 | 122667.69 | 127384.36 | 115586.37 | Brad Carr | B&M | 16-Jul-21 | 25-Apr-22 | 28-Jun-21 | 21-Jun-21 | 24-Jun-21 |  |  |  | -11,797.99
640559 | FOOTHILLS OF WINONA PHASE 3 - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 29-Mar-22 |  |  | 396133.41 | 395689.5 | 396133.41 | 396133.41 | Roy Owen | Transpw | 21-Jun-22 | 29-Nov-22 | 24-May-22 | 08-Aug-22 | 23-Nov-22 | Customer | Customer |  | 0
640563 | HORNING TS - MTN FEEDERS - CIVIL - PHASE 3 | 820 - Nebo | 150376 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
640590 | 198 FIRST RD WEST - PHASE 3 - SUBD EDS | 820 - Nebo | 150588 | Active | HO | RELEASED |  |  | 2023 | Velickovski, Goran | Morris, Mark | 07-Jun-22 |  |  | 186580.92 | 12704.69 | 186580.92 | 186580.92 | Macdougall, Stephen | Transpw | 15-Sep-22 | 31-Jul-23 | 11-Jul-22 |  |  | Customer | Customer |  | 0
640621 | PARK PLACE PHASE 2B - SUBD RES EDS | 820 - Nebo | 150588 | Active | 40 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640629 | AUTO SWITCH INSTALLS - DUNDAS TS - PHASE 2, 3 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 27-Apr-21 | 3 |  | 219274.41 | 241656.74 | 203380.77 | 219274.41 | Brad Carr | K-Line | 01-Oct-21 | 22-Sep-22 | 13-Sep-21 | 07-Oct-21 | 26-Nov-21 | Locates | Locates |  | 15,893.64
640634 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 3, 6 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 27-Apr-21 | 6 |  | 495386.95 | 468131.8 | 477031.43 | 495386.95 | Brad Carr | K-Line | 17-Dec-21 | 22-Sep-22 | 01-Nov-21 | 04-Oct-21 | 26-Nov-21 |  |  |  | 18,355.52
640633 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 2, 5 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 27-Apr-21 | 5 |  | 451355.72 | 384075.34 | 437738.72 | 451355.72 | Brad Carr | K-Line | 05-Nov-21 | 22-Sep-22 | 04-Oct-21 | 27-Sep-21 | 26-Nov-21 |  | N/A |  | 13,617.00
640639 | 191 KING STREET WEST - TEMP SERVICE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Sabbah, Amir | 04-May-21 |  |  | 27679.74 | 41212.21 | 27679.74 | 27679.74 | Roy Owen |  | 10-Jun-21 | 27-Sep-22 | 07-Jun-21 | 02-Aug-21 | 14-Nov-22 | Locates | Locates |  | 0
640670 | 14-18 AUGUSTA ST, HAMILTON - POLE RELOCATION | 820 - Nebo | 150665 | Active | 84 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan | 08-Nov-21 |  |  | 54454.35 | 37881.85 | 54454.35 | 54454.35 | Macdougall, Stephen |  | 14-Dec-21 | 28-Jul-23 | 06-Dec-21 | 21-Jan-22 |  | N/A | N/A |  | 0
640725 | JOINT USE PERMIT HW2021-017 - TEAL, FRANCES, AND CHURCH - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 18-Jun-21 |  |  | 8000.55 | 5824.52 | 8000.55 | 8000.55 | Brad Carr | K-Line | 23-Jul-21 | 24-Jan-22 | 19-Jul-21 | 13-Aug-21 | 13-Aug-21 | Filler | Filler |  | 0
640729 | 318 ONTARIO ST. PMH REPLACEMENT PH1 | 830 - St. Catharines | 151083 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 28-Feb-22 | 1 | 1 | 186195.6 | 198131.56 | 186195.6 | 186195.6 | Frank Giancola | Fairway | 06-Jul-22 | 26-Jul-23 | 27-Jun-22 | 20-Sep-22 | 20-Oct-22 | Locates | Locates |  | 0
636732 | 2021 POLE REPLACEMENTS - UPPER SHERMAN - 2 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 11-May-21 | 2 |  | 34589.3 | 53071.86 | 34589.3 | 34589.3 | Macdougall, Stephen |  | 28-May-21 | 25-Apr-22 | 17-May-21 | 20-May-21 | 04-Jun-21 | Lines | Lines |  | 0
640742 | ROAD AUTHORITY RELOCATION - STRACHAN ST E - ANCHOR RELOCATE | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Celic, Dusan | 12-May-21 |  |  | 13218.56 | 8860.49 | 13218.56 | 13218.56 | Koeppe, Jeffrey |  | 09-Jun-21 | 12-Apr-22 | 07-Jun-21 | 30-Jun-21 | 02-Jul-21 | Locates | Locates |  | 0
634974 | JOINT USE PERMIT HW2019-141 - INVERNESS, E 13, QUEENSDALE | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 19-Feb-21 |  |  | 24941.79 | 31245.71 | 24941.79 | 24941.79 | Brad Carr | K-Line | 30-Apr-21 | 18-Jul-22 | 01-Mar-21 | 08-Jun-21 | 08-Jun-21 | Filler | Filler |  | 0
637726 | JOINT USE PERMIT HW2020-095 - HATT, NAPIER S, MATILDA S - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 19-Feb-21 |  |  | 11239.41 | 7461.75 | 11239.41 | 11239.41 | Brad Carr | K-Line | 30-Apr-21 | 05-Jan-22 | 01-Mar-21 | 08-Jun-21 | 08-Jun-21 | Filler | Filler |  | 0
640772 | 2021 - MH 39A - MANHOLE ROOF REPLACEMENT | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 06-Oct-21 |  |  | 158562.63 | 191440.49 | 208382.92 | 158562.63 | Brad Carr | B&M | 19-Nov-21 | 22-Sep-22 | 25-Oct-21 | 01-Nov-21 | 10-Dec-21 | Contractor | Contractor |  | -49,820.29
640791 | 2782 BARTON STREET-LJM DEVELOPMENTS(HAMILTON)INC./HAM/NS00113246/3PHPAD | 820 - Nebo | 150449 | Active | HO | RELEASED |  |  | 2023 | Kappheim, Adam | Bharosi, Mohindra | 13-May-22 |  |  | 66582.92 | 20301.68 | 66582.92 | 66582.92 | Macdougall, Stephen | Fairway | 12-Aug-22 | 31-Jul-23 | 08-Aug-22 |  |  | Locates | Locates |  | 0
640795 | CHAMBER LID REPLACEMENTS- 2022- PHASE 1 | 820 - Nebo | 151065 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Wardell, Paul | 19-Oct-22 | 1 | 1 | 93617.17 | 123634.55 | 124663.94 | 93617.17 | Brad Carr | B&M | 16-Dec-22 | 26-Jul-23 | 21-Nov-22 | 12-Dec-22 | 14-Dec-22 | Locates | Locates |  | -31,046.77
640808 | JOINT USE PERMIT HW2021-025 - MARION N AND DROMORE - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Oct-21 |  |  | 10997.16 | 8070.51 | 10997.16 | 10997.16 | K-Line Construction | K-Line | 07-Mar-22 | 30-Jan-23 | 07-Mar-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
640813 | 2021 EMERGING UG - RIVERVIEW BLVD REAR LOT CONVERSION | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 01-Sep-21 |  |  | 585116.28 | 666690.01 | 554671.03 | 585116.28 | Brad Carr | B&M | 03-Dec-21 | 22-Sep-22 | 18-Oct-21 | 25-Oct-21 | 14-Jul-22 | Locates | Locates |  | 30,445.25
640812 | 2021 CABLE REPLACEMENT - CLAPPSION TIE POINT - 1300M'S | 820 - Nebo | 151452 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 20-Jul-21 |  |  | 644487.57 | 664926.7 | 448754.27 | 644487.57 | Tony Ierace |  | 27-Oct-21 | 26-Jul-23 | 16-Aug-21 | 05-Dec-21 | 18-Nov-22 | Customer | Customer |  | 195,733.30
640825 | 2021 EMERGING TX - TX-NV1_02 - 1 TX | 830 - St. Catharines | 150336 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640828 | 1190 MAIN STREET WEST - TEMP HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640847 | 40 ZINFANDAL DR - SUBD RES EDS | 820 - Nebo | 150588 | Active | 95 | ANALYZE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 29-Mar-22 |  |  | 197634 | 199355.74 | 197634 | 197634 | Roy Owen | Transpw | 30-May-22 | 01-Aug-23 | 16-May-22 | 21-Nov-22 | 02-Feb-23 | Customer | Customer |  | 0
640851 | JOINT USE PERMIT HW2021-029 - BRAMPTON, BARNABY, RENNIE, ETC - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640859 | 15 NORTHWOOD DR, ST. CATHARINES - BELL POLE RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 22-Aug-22
640858 | 456 WELLAND AVE - POLE RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2021 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-21
640865 | SWANSEA APTS - UPPER GAGE & PEMBERTON | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640868 | 2021 POLE REPLACMENT - BATCH 1 - 6 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 31-May-21 | 6 |  | 65240.37 | 43735 | 65240.37 | 65240.37 | Koeppe, Jeffrey |  | 26-Oct-21 | 26-Apr-22 | 11-Oct-21 | 13-Sep-21 | 10-Nov-21 |  | Locates |  | 0
640869 | 1387 FOURTH AVE - 600A 347/600V UPGRADE | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2022 | Kappheim, Adam | Oosterlinck, David | 20-Aug-21 |  |  | 77010.64 | 79078.37 | 77010.64 | 77010.64 | Frank Giancola | Wiens | 04-Oct-21 | 01-Aug-23 | 27-Sep-21 | 08-Sep-21 | 22-Apr-22 |  | Customer |  | 0
640882 | 555 SANATORIUM ROAD / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 70 | ACTIVE |  |  | 2023 | Kappheim, Adam | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640884 | CUSTOMER INITIATED EXPANSION - ROXBOROUGH PARK INC. DEVELOPMENT - QUEENSTON RD | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | K-Line |  | 22-Nov-21
640900 | JOINT USE PERMIT HW2021-034 - NIAGARA, TECUMSEH, BEAMER - ST CATH | 830 - St. Catharines | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640899 | JOINT USE PERMIT HW2021-033 - GLENCAIRN, MCKENZIE, HEYWOOD - STCATH | 830 - St. Catharines | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640898 | JOINT USE PERMIT HW2021-031 - CLAPHAM RD - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 19-Jul-21 |  |  | 8671.86 | 6637.1 | 8671.86 | 8671.86 | Brad Carr | K-Line | 23-Jul-21 | 24-Jan-22 | 19-Jul-21 | 13-Aug-21 | 13-Aug-21 | Filler | Filler |  | 0
640903 | 280 EASTPORT DR - BELL MOBILITY COMM TOWER | 820 - Nebo | 152381 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 22-Aug-22
640905 | 2021 POLE RENEWAL MINI REBUILD-BOGART AND MELODY ST. - 12 POLES | 830 - St. Catharines | 150335 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 29-Nov-21 | 12 | 12 | 202543.39 | 284594.54 | 202543.39 | 202543.39 | Dan Despres |  | 14-Oct-22 | 26-Jul-23 | 29-Aug-22 | 17-May-22 | 18-Nov-22 | Locates | Locates |  | 0
640915 | 214 MARTINDALE ROAD PADMOUNT REPLACEMENT | 830 - St. Catharines | 150336 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
640926 | 1 JARVIS ST - TEMP | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Bennett, Aaron | 29-Jul-21 |  |  | 46593.51 | 43542.92 | 46593.51 | 46593.51 | Roy Owen |  | 30-Aug-21 | 22-Feb-23 | 23-Aug-21 | 06-Aug-21 | 14-Nov-22 | Customer | Customer |  | 0
634976 | JOINT USE PERMIT HW2019-143 - BARTON E, MONS, AND CAVELL - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 09-Mar-21 |  |  | 9266 | 9715.9 | 9266 | 9266 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 07-Mar-22 | 07-Apr-22 | 07-Apr-22 | Filler | Filler |  | 0
640945 | 192 GLENDALE AVE - SUBD RES EDS | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 05-Oct-21 |  |  | 40829.95 | 82867.6 | 40829.95 | 40829.95 | Frank Giancola |  | 26-Nov-21 | 22-Jun-23 | 22-Nov-21 | 08-Nov-21 | 24-Nov-21 |  |  |  | 0
640944 | 505 HIGHLAND ROAD WEST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Kappheim, Adam | Djuric, Zdravko | 05-Dec-22 |  |  | 218789.79 | 17910.94 | 218789.79 | 218789.79 | Macdougall, Stephen |  | 02-Oct-23 | 02-Oct-23 | 05-Jun-23 |  |  | Materials | Materials |  | 0
640947 | 69 ANSON AVENUE / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Kappheim, Adam | Djuric, Zdravko | 22-Jun-21 |  |  | 106184.16 | 178256.8 | 106184.16 | 106184.16 | Macdougall, Stephen | Fairway | 29-Jul-21 | 08-Aug-23 | 19-Jul-21 | 09-Aug-21 |  | MC/PUCC Permit | MC/PUCC Permit |  | 0
640984 | 60 WOODLEY'S LANE - BELL POLE REPLACEMENT | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Patel, Ketan | 23-Mar-21 |  |  | 20803.14 | 21899.19 | 20803.14 | 20803.14 | Brad Carr | K-Line | 01-Apr-21 | 24-Nov-21 | 29-Mar-21 | 29-Mar-21 | 01-Apr-21 |  |  |  | 0
640990 | CENTRAL CONV - PHASE 5A - TUCKETT, REGINALD REBUILD (NBM DESIGN) | 820 - Nebo | 150352 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 18-Nov-22 |  |  | 270448.47 | 291851.45 | 270448.47 | 270448.47 | Brad Carr | B&M | 14-Jul-23 | 31-Jul-23 | 05-Jun-23 | 17-Apr-23 |  |  | N/A |  | 0
641027 | 264 DUKE ST / HAM / UP | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Kappheim, Adam | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641032 | SC752 AREA - NEW AB TRANSFORMERS | 820 - Nebo | 151452 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Billone, Justin | 10-Aug-21 |  |  | 87999.9 | 79554.53 | 75559.9 | 87999.9 | Tony Ierace | Fairway | 29-Oct-21 | 17-Aug-22 | 04-Oct-21 | 18-Nov-21 | 20-Dec-21 | Lines | Lines |  | 12,440.00
640834 | 380 MCNEILLY RD/HAM/NS/NS00106348/3PHPAD | 820 - Nebo | 150449 | Active | 95 | ANALYZE |  |  | 2022 | Frigotto, Rodrigo | Bharosi, Mohindra | 29-Mar-22 |  |  | 487978.4 | 243396.51 | 243989.2 | 243989.2 | Roy Owen | Fairway | 13-May-22 | 08-Aug-23 | 03-May-22 | 08-Apr-22 | 26-Aug-22 |  | Customer |  | 0
641063 | 284 GLENDALE AVE - 400A 347/600V UPGRADE | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Oosterlinck, David | 16-May-22 |  |  | 64208.86 | 39196.05 | 64208.86 | 64208.86 | Frank Giancola | Wiens | 29-Jun-22 | 26-Jul-23 | 27-Jun-22 | 15-Jul-22 | 28-Jul-22 | Customer | Customer |  | 0
641067 | MIDTOWN - SUBD RES EDS | 820 - Nebo | 150588 | Active | 95 | COMPLETE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 29-Mar-22 |  |  | 778884.16 | 779928.67 | 778884.16 | 778884.16 | Roy Owen | Transpw | 06-Jul-22 | 02-Aug-23 | 24-May-22 | 24-May-22 | 20-Dec-22 | Customer | Customer |  | 0
641068 | STONEGATE PARK - SUBD RES EDS | 820 - Nebo | 150588 | Active | 95 | ANALYZE |  |  | 2023 | Velickovski, Goran | Morris, Mark | 20-Jul-22 |  |  | 22531.69 | 26032.13 | 22531.69 | 22531.69 | Roy Owen |  | 26-Aug-22 | 01-Aug-23 | 22-Aug-22 | 13-Dec-22 | 06-Apr-23 | Customer | Customer |  | 0
641082 | 2023 EMERGING - BELL TRANSFERS EAST 32ND | 820 - Nebo | 150828 | Active | 96 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 19-Jan-23 |  |  | 13360.31 | 15683.06 | 13360.31 | 13360.31 | Brad Carr | K-Line | 24-Feb-23 | 26-Jul-23 | 06-Feb-23 | 13-Feb-23 | 17-Feb-23 |  |  |  | 0
641096 | ROAD AUTHORITY RELOCATION - ANCHOR RELOCATE - KESWICK CRT | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Celic, Dusan | 04-Aug-21 |  |  | 25297.85 | 12594.03 | 25297.85 | 25297.85 | Koeppe, Jeffrey |  | 16-Sep-21 | 13-Apr-22 | 13-Sep-21 | 27-Sep-21 | 27-Sep-21 | Locates | Locates |  | 0
641103 | LAS VILLAS (1076 VANSICKLE N) - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 50 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641119 | MH 8C - ROOF REMOVAL & INSTALL | 820 - Nebo | 151065 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 11-Apr-23 | 1 | 1 | 166661.84 | 154961.57 | 166661.84 | 166661.84 | Brad Carr | B&M | 16-Jun-23 | 26-Jul-23 | 15-May-23 | 29-May-23 |  | Locates |  |  | 0
641121 | 2022 POLE REPLACEMENTS - EAST 43RD ST - 22 POLES | 820 - Nebo | 150335 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 28-Jul-22 | 22 | 22 | 618397.98 | 484171.33 | 289290.61 | 309198.99 | Brad Carr | B&M | 14-Oct-22 | 26-Jul-23 | 06-Sep-22 | 05-Sep-22 | 01-Dec-22 |  | Contractor |  | 19,908.38
641122 | 2022 POLE REPLACEMENTS - EAST 45TH ST - 13 POLES | 820 - Nebo | 150335 | Active | 94 | ANALYZE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 16-Dec-21 | 13 | 13 | 294858.68 | 307725.97 | 255084.61 | 294858.68 | Brad Carr | K-Line | 16-Dec-22 | 26-Jul-23 | 10-Oct-22 | 31-Oct-22 | 17-Nov-22 | Contractor |  |  | 39,774.07
640202 | 2021 - VOICE RADIO INTGR -TRANSITION/VOICE RADIO INTGR - DEWITT TOWER SERVICE | 820 - Nebo | 632833 | Active | 95 | COMPLETE |  |  | 2021 | Haid, Philip G. | Lustrinelli, Mark | 31-Mar-21 |  |  | 11390.63 | 5935.55 | 11390.63 | 11390.63 | Macdougall, Stephen |  | 30-Apr-21 | 26-Jul-23 | 29-Apr-21 | 27-Apr-21 | 28-May-21 |  | N/A |  | 0
641139 | 430 CANNON STREET EAST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 93 | ANALYZE |  |  | 2023 | Kappheim, Adam | Djuric, Zdravko | 27-Apr-22 |  |  | 60066.59 | 55176.65 | 60066.59 | 60066.59 | Macdougall, Stephen | Fairway | 14-Jun-22 | 26-Jul-23 | 06-Jun-22 | 24-May-22 | 26-Jun-23 |  | Customer |  | 0
641138 | JOINT USE PERMIT HW2021-044 - BEACH - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 16-Sep-21 |  |  | 7843.61 | 7561.33 | 7843.61 | 7843.61 | K-Line Construction | K-Line | 07-Mar-22 | 30-Jan-23 | 07-Mar-22 | 08-Nov-21 | 08-Nov-21 | Filler | Filler |  | 0
641143 | PIMLICO DRIVE - URD - VOLTAGE CONVERSION | 820 - Nebo | 150496 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 44750.35 |  | 0 | Brad Carr |  |  | 26-Jul-23
641159 | V63 & V64 VAULT LID REPLACEMENT | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Celic, Dusan | 05-Jul-21 | 2 | 2 | 29763.85 | 36620.47 | 23001.93 | 29763.85 | Brad Carr | Fairway | 27-Aug-21 | 09-Aug-22 | 23-Aug-21 | 23-Aug-21 | 28-Mar-22 |  | Contractor |  | 6,761.92
641164 | CHERYL AVE MINI REBUILD (HAMILTON - 11 | 820 - Nebo | 150335 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 24-Nov-21 | 11 | 11 | 200588.56 | 192675.76 | 200588.56 | 200588.56 | Brad Carr | K-Line | 31-Oct-22 | 26-Jul-23 | 03-Oct-22 | 10-Oct-22 | 25-Oct-22 |  |  |  | 0
641174 | JOINT USE PERMIT HW2021-046 - SCENIC, LESLIE, W28, PRICE - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 01-Feb-22 |  |  | 16433.33 | 12029 | 16433.33 | 16433.33 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 14-Mar-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
641177 | 173 CLINE - ANCHOR REPLACEMENT | 820 - Nebo | 150828 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 20-Jul-20
641176 | 352 INVERNESS - REPLACE EXISTING ANCHORS | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Wardell, Paul | 13-Sep-21 |  |  | 7453.43 | 6960.52 | 7453.43 | 7453.43 | Brad Carr |  | 13-Sep-21 | 09-Aug-22 | 13-Sep-21 | 13-Sep-21 | 13-Sep-21 |  |  |  | 0
641183 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 2) | 820 - Nebo | 151303 | Active | 91 | ACTIVE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 01-Feb-22 |  |  | 1717243.32 | 1709594.38 | 1704883.32 | 1717243.32 | Brad Carr | B&M | 02-Sep-22 | 26-Jul-23 | 14-Mar-22 | 14-Mar-22 | 21-Dec-22 |  | Contractor |  | 12,360.00
641202 | WESTCHESTER APARTMENTS-SUBD EDS | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641224 | JOINT USE PERMIT HW2021-053 - NARDI, POTTRUFF S, CHERRY, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 08-Nov-21 |  |  | 8551.51 | 6821.8 | 8551.51 | 8551.51 | K-Line Construction | K-Line | 28-Jan-22 | 30-Jan-23 | 03-Jan-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
641242 | 196 GLENDALE AVE. - AERIAL TRESPASS RELOCATION | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 30-Apr-21 |  |  | 32604.7 | 42405.01 | 32604.7 | 32604.7 | Frank Giancola | Wiens | 18-Jun-21 | 26-Apr-22 | 16-Jun-21 | 14-May-21 | 30-Jun-21 |  | Customer |  | 0
641252 | 2022 POLE RENEWAL - LINWELL - 6 POLES | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 13-Dec-21 | 6 | 6 | 163279.49 | 84885.2 | 163279.49 | 163279.49 | Frank Giancola |  | 16-Aug-22 | 22-Sep-22 | 05-Jul-22 | 26-Jul-22 | 07-Sep-22 | Locates | Locates |  | 0
641256 | 2021 - TX RENEWAL - WENTWORTH ST - 1 TX | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 09-Jul-21 | 1 |  | 56074.97 | 38198.93 | 56074.97 | 56074.97 | Brad Carr | K-Line | 20-Aug-21 | 26-Apr-22 | 09-Aug-21 | 09-Aug-21 | 20-Aug-21 | Locates | Locates |  | 0
641262 | 75 EASTCHESTER AVE | 830 - St. Catharines | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641275 | 259 MAGNOLIA DRIVE - MANHOLE LID REPAIR | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Anderson, Dean | 30-Jun-21 |  |  | 65055.91 | 49971.08 | 65055.91 | 65055.91 | Brad Carr |  | 10-Sep-21 | 09-Aug-22 | 30-Aug-21 | 25-Oct-21 | 29-Oct-21 | Contractor | Contractor |  | 0
641276 | GLENDALE TS - POLE RELOCATION - CHILD WO FOR 636003 | 830 - St. Catharines | 150570 | Inactive | 99 | COMPLETE |  |  | 2021 | Braletic, Bob | Lustrinelli, Mark | 15-Apr-21 |  |  | 0 | 40666.34 |  | 0 | Frank Giancola |  | 20-Apr-21 | 16-Aug-21 | 29-Mar-21 | 31-Mar-21 | 16-Apr-21 | Locates
641298 | 85 POULETTE ST - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 04-Nov-21 |  |  | 50239.11 | 140717.43 | 50239.11 | 50239.11 | Macdougall, Stephen | Wiens | 17-Dec-21 | 13-Feb-23 | 13-Dec-21 | 24-Jan-22 | 24-Sep-22 | Customer | Customer |  | 0
641328 | 41 GREAT FALLS BLVD - SUBD CAP PROJ | 820 - Nebo | 151653 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Morris, Mark | 21-Jun-21 |  |  | 29863.15 | 23787.08 | 29863.15 | 29863.15 | Roy Owen |  | 29-Jul-21 | 27-Feb-22 | 26-Jul-21 | 23-Aug-21 | 01-Sep-21 | Customer | Customer |  | 0
641364 | SHAMROCK COMMON - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 95 | ANALYZE |  |  | 2022 | Velickovski, Goran | Morris, Mark | 08-Sep-22 |  |  | 32785.52 | 19771.16 | 32785.52 | 32785.52 | Frank Giancola |  | 13-Oct-22 | 28-Jul-23 | 11-Oct-22 | 11-Oct-22 | 26-Jan-23 | Customer | Customer |  | 0
641379 | 55 1/2 ROCKCLIFFE ROAD - UG SERVICE TO BE RELOCATED | 820 - Nebo | 151452 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Wardell, Paul | 14-May-21 |  |  | 28327.65 | 30407.32 | 28147.05 | 28327.65 | Roy Owen |  | 01-Jun-21 | 22-Sep-22 | 31-May-21 | 11-Jun-21 | 11-Jun-21 | Customer | Customer |  | 180.6
641401 | JOINT USE PERMIT HW2021-056 - TROY, DUNN, GRACE, GLOW, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 16-Sep-21 |  |  | 16611.59 | 11919.35 | 16611.59 | 16611.59 | K-Line Construction | K-Line | 07-Mar-22 | 30-Jan-23 | 07-Mar-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
641415 | AUTO SWITCH - SCOTT & HAIG - 1 | 830 - St. Catharines | 150334 | Active | 98 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 10-Sep-21 | 1 | 1 | 271100.63 | 312923.18 | 214581.87 | 271100.63 | Brad Carr | K-Line | 26-Nov-21 | 26-Jul-23 | 01-Nov-21 | 13-Dec-21 | 22-Aug-22 | MC/PUCC Permit | MC/PUCC Permit |  | 56,518.76
641423 | 1675 BURLINGTON ST E / HAM / UP00131450 / 3PH CUST OWNED PAD MOUNTED SW/TX | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav | 12-Aug-22 |  |  | 187377.82 | 281685.29 | 177973.29 | 187377.82 | Macdougall, Stephen | Fairway | 22-Dec-22 | 14-Aug-23 | 30-Nov-22 | 17-Feb-23 |  | Customer | Customer |  | 9,404.53
641427 | 330 NASH RD N / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 92 | ANALYZE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor | 31-Jan-22 |  |  | 67203.94 | 60768.09 | 67203.94 | 67203.94 | Macdougall, Stephen | Fairway | 23-Mar-22 | 31-Jul-23 | 14-Mar-22 | 07-Mar-22 | 28-Mar-23 |  | Customer |  | 0
641446 | 20 EAST AVENUE SOUTH - REMOVAL | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Kappheim, Adam | Djuric, Zdravko | 12-May-21 |  |  | 7964.18 | 5848.06 | 7964.18 | 7964.18 | Roy Owen |  | 17-Jun-21 | 01-Dec-21 | 14-Jun-21 | 27-May-21 | 31-May-21 |  |  |  | 0
641473 | SUMMIT PARK PHASE 11A - SUBD RES EDS | 820 - Nebo | 150588 | Active | 95 | COMPLETE |  |  | 2022 | Gamboa, Henry | Morris, Mark | 06-Dec-21 |  |  | 548339 | 614613.53 | 548339 | 548339 | Roy Owen | Transpw | 04-Apr-22 | 26-Jul-23 | 01-Mar-22 | 28-Feb-22 | 21-Sep-22 |  | Customer |  | 0
641480 | JOINT USE PERMIT HW2021-063 - ALMA, PARKSIDE, AND SYDENHAM - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Mar-22 |  |  | 8700.87 | 7969.63 | 8700.87 | 8700.87 | K-Line Construction | K-Line | 31-May-22 | 30-Jan-23 | 02-May-22 | 14-Mar-22 | 14-Mar-22 |  |  |  | 0
641479 | JOINT USE PERMIT HW2021-062 - GARSIDE S, NORMANDY, BARON S - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Mar-22 |  |  | 11756.79 | 8826.25 | 11756.79 | 11756.79 | K-Line Construction | K-Line | 31-May-22 | 01-May-23 | 02-May-22 | 11-Apr-22 | 11-Apr-22 |  |  |  | 0
641481 | JOINT USE PERMIT HW2021-066 - GLENDALE - ST CATH | 830 - St. Catharines | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641523 | 672 ARVIN AVE / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Frigotto, Rodrigo | Dragojevic, Igor | 13-Aug-21 |  |  | 73029.83 | 65179.67 | 73029.83 | 73029.83 | Macdougall, Stephen | Fairway | 30-Sep-21 | 22-Sep-22 | 20-Sep-21 | 29-Sep-21 | 05-Nov-21 | Locates | Locates |  | 0
641526 | 124 ELEANOR AVE - AERIAL TRESPASS | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Anderson, Dean | 18-May-21 |  |  | 11649.11 | 7672.32 | 11649.11 | 11649.11 | Koeppe, Jeffrey |  | 06-Jul-21 | 09-Aug-22 | 05-Jul-21 | 05-Jul-21 | 06-Jul-21 |  |  |  | 0
641535 | 3-PHASE EXPANSION FOR 75 OLIVER LANE, ST. CATHARINES | 830 - St. Catharines | 152381 | Active | 40 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
641536 | VILLAGE ON THE TWELVE - PH 7 - SUBD EDS | 830 - St. Catharines | 150588 | Inactive | 99 | CANCELLED |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 1099.2 |  | 0 | Calvin Arsenault |  |  | 28-Apr-23
641569 | AUTO SW - ONTARIO ST (SOUTH OF LINWELL), 1 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 30-May-21 | 1 |  | 72099.11 | 75945.66 | 72099.11 | 72099.11 | Brad Carr | K-Line | 29-Oct-21 | 22-Sep-22 | 18-Oct-21 | 11-Oct-21 | 26-Nov-21 |  | N/A |  | 0
641596 | 11 ROBERT ST / HAM / UP | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Sabbah, Amir | 11-Mar-22 |  |  | 151755.93 | 107783.87 | 143205.72 | 151755.93 | Macdougall, Stephen |  | 06-May-22 | 15-Aug-23 | 19-Apr-22 | 13-Apr-22 |  | Customer | Customer |  | 8,550.21
641597 | AUTO SW - HWY 5_WEST OF HWY 6, 1 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Billone, Justin | 30-May-21 | 1 |  | 66096.68 | 68772.2 | 66096.68 | 66096.68 | Koeppe, Jeffrey |  | 12-Aug-21 | 22-Sep-22 | 02-Aug-21 | 12-Jul-21 | 23-Jul-21 |  |  |  | 0
641611 | 75 JAMES ST S & 44 HUGHSON ST S/ HAM / UP00118548 / 3PH CUST OWNED SUB TEMP SRVC | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Frigotto, Rodrigo | Laus, Tomislav | 11-Jul-21 |  |  | 36219.61 | 40853.65 | 36219.61 | 36219.61 | Roy Owen | Fairway | 13-Aug-21 | 23-Sep-22 | 10-Aug-21 | 24-Nov-21 | 22-Dec-21 | Customer | Customer |  | 0
641621 | JOINT USE PERMIT HW2021-067 - ST JOSEPHS, ARKLEDUN, KINGSWAY - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 09-Nov-21 |  |  | 9408.14 | 7856.22 | 9408.14 | 9408.14 | K-Line Construction | K-Line | 07-Jan-22 | 30-Jan-23 | 03-Jan-22 | 11-Apr-22 | 11-Apr-22 | Filler | Filler |  | 0
641654 | JOINT USE PERMIT HW2021-073 - LONGWOOD, DESJARDINS, FRANKLIN, ETC - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641653 | JOINT USE PERMIT HW2021-072 - BARTON EAST - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 16-Sep-21 |  |  | 7843.61 | 5115.35 | 7843.61 | 7843.61 | K-Line Construction | K-Line | 30-Nov-21 | 30-Jan-23 | 01-Nov-21 | 08-Nov-21 | 08-Nov-21 | Filler | Filler |  | 0
641652 | JOINT USE PERMIT HW2021-071 - HEAD, MILL, MERCER, ETC - HAM | 820 - Nebo | 151536 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 14-Feb-22 |  |  | 12116.75 | 8916.41 | 12116.75 | 12116.75 | K-Line Construction | K-Line | 31-Mar-22 | 26-Jul-23 | 23-Mar-22 | 11-Apr-22 | 11-Apr-22 | Filler | Filler |  | 0
641689 | 2021 POLE RENEWAL MINI REBUILD- DURHAM DR AND WILDWOOD RD - 14 POLES | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 30-Nov-21 | 14 | 14 | 160172.92 | 168007.57 | 160172.92 | 160172.92 | Dan Despres |  | 07-Jun-22 | 22-Sep-22 | 25-Apr-22 | 27-Apr-22 | 11-Jul-22 | Locates | Locates |  | 0
641688 | 2021 POLE RENEWAL MINI REBUILD - NORTHGLEN AND CUMBERLAND RD- 10 POLES | 830 - St. Catharines | 150335 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 30-Nov-21 | 10 | 10 | 136861.21 | 178091.93 | 136861.21 | 136861.21 | Dan Despres |  | 14-Nov-22 | 26-Jul-23 | 17-Oct-22 | 23-Jun-22 | 16-Nov-22 |  | Lines |  | 0
641690 | BARNABY ST - POLE RENEWAL - 7 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 16-Dec-21 | 7 | 7 | 110165.12 | 117122.49 | 110165.12 | 110165.12 | Koeppe, Jeffrey |  | 20-Dec-22 | 02-Mar-23 | 21-Nov-22 | 14-Nov-22 | 09-Dec-22 |  |  |  | 0
641699 | 31 SUNRISE CRES (DUNDAS) NEW SEC DUCT | 820 - Nebo | 150496 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 11-Jul-22 |  |  | 31531.35 | 31782.28 | 31531.35 | 31531.35 | Brad Carr | Fairway | 11-Jul-22 | 23-Mar-23 | 11-Jul-22 | 11-Jul-22 | 11-Jul-22 |  |  |  | 0
641698 | 35 TOWERING HEIGHTS BLVD - TRANSFORMER RELOCATION | 830 - St. Catharines | 150336 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641708 | 75 OLIVER LAN ST.CATHARINES - NEW CONDO BUILDING | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David |  |  |  | 0 | 2043.77 |  | 0 | Calvin Arsenault |  |  | 29-May-23
641719 | CENTRAL CONVERSION - PHASE 6B (2022 WORK) | 820 - Nebo | 150352 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 21-Nov-22 |  |  | 1793104.58 | 670031.23 | 1781190.98 | 1793104.58 | Brad Carr | K-Line | 01-Sep-23 | 01-Sep-23 | 01-Jun-23 | 03-Apr-23 |  |  |  |  | 11,913.60
641723 | 360 WENTWORTH STREET NORTH - GUY WIRE RELOCATION | 820 - Nebo | 150496 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Wardell, Paul | 01-Oct-21 |  |  | 152910.75 | 132129.86 | 152910.75 | 152910.75 | Brad Carr | K-Line | 12-Nov-21 | 09-Aug-22 | 01-Nov-21 | 10-Dec-21 | 10-Dec-21 | Locates | Locates |  | 0
641724 | 743 GREEN MOUNTAIN ROAD POLE REPLACEMENT | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 10-Aug-21 |  |  | 7632.5 | 9386.12 | 7632.5 | 7632.5 | Koeppe, Jeffrey |  | 13-Oct-21 | 09-Aug-22 | 11-Oct-21 | 03-Nov-21 | 05-Nov-21 | Locates | Locates |  | 0
641725 | 456 WELLAND AVE - NEW 400A 347/600V SERVICE | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Oosterlinck, David | 11-Aug-21 |  |  | 71663.04 | 62328.89 | 71663.04 | 71663.04 | Frank Giancola | Wiens | 27-Oct-21 | 02-Aug-23 | 18-Oct-21 | 22-Sep-21 | 27-Jan-22 |  | Customer |  | 0
641736 | JOINT USE PERMIT HW2021-075 - BUCKINGHAM, SANDRINGHAM, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 01-Feb-22 |  |  | 24252.22 | 19904.64 | 24252.22 | 24252.22 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 15-Mar-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
641735 | JOINT USE PERMIT HW2021-074 - RED OAK AND MARGARET - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Mar-22 |  |  | 8962.64 | 6014.03 | 8962.64 | 8962.64 | K-Line Construction | K-Line | 31-May-22 | 30-Jan-23 | 02-May-22 | 14-Mar-22 | 14-Mar-22 |  |  |  | 0
641759 | AQUAMARINE II - SUBD RES EDS | 820 - Nebo | 150588 | Active | 82 | RELEASED |  |  | 2023 | Velickovski, Goran | Chu, Zeyu (Andrew) | 17-May-23 |  |  | 17541.2 | 14113.12 | 17541.2 | 17541.2 | Macdougall, Stephen |  | 21-Jun-23 | 28-Jul-23 | 19-Jun-23 |  |  | Customer | Customer |  | 0
641760 | COGECO BONDS - 2021 BATCH ONE - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641761 | BELL BONDS - 2021 BATCH ONE - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641771 | 281 WINONA ROAD POLE REPLACEMENT | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 12-Aug-21 |  |  | 17641.02 | 11141.26 | 17641.02 | 17641.02 | Koeppe, Jeffrey |  | 07-Oct-21 | 09-Aug-22 | 04-Oct-21 | 16-Nov-21 | 19-Nov-21 | Locates | Locates |  | 0
641776 | MANHOLE REPAIRS - 2021 | 820 - Nebo | 151065 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641175 | 90 RIDGE STREET - SERVICE TO BE MOVED AWAY FROM FUTURE POOL | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Wardell, Paul | 21-May-21 |  |  | 20616.93 | 16270.4 | 20616.93 | 20616.93 | Macdougall, Stephen | Fairway | 24-Jun-21 | 02-Mar-23 | 23-Jun-21 | 26-Jul-21 | 26-Jul-21 | Customer | Customer |  | 0
641834 | 20 EAST AVENUE SOUTH / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 95 | ANALYZE |  |  | 2022 | Kappheim, Adam | Djuric, Zdravko | 13-Apr-22 |  |  | 54007.01 | 86680.91 | 51508.46 | 54007.01 | Roy Owen | Fairway | 08-Jun-22 | 26-Jul-23 | 24-May-22 | 02-Aug-22 | 12-Jan-23 | Locates | Locates |  | 2,498.55
641836 | ABB RECLOSERS - 2021 PILOT PROGRAM | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
641844 | 10 MULBERRY ST POLE REPLACEMENT | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Jolie, Chris | 22-Jun-21 |  |  | 35947.8 | 34243.39 | 35947.8 | 35947.8 | Macdougall, Stephen |  | 11-Apr-22 | 22-Sep-22 | 31-Mar-22 | 15-Feb-22 | 31-May-22 | MC/PUCC Permit | MC/PUCC Permit |  | 0
641963 | JOINT USE PERMIT HW2021-083 - MILANO, GUILDWOOD, ADIS, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 14-Feb-22 |  |  | 26472.65 | 18150.4 | 26472.65 | 26472.65 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 23-Mar-22 | 14-Mar-22 | 14-Mar-22 | Filler | Filler |  | 0
641978 | FAIRVIEW PARK - GENEVA STREET, ANCHOR RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Patel, Ketan | 31-Aug-21 |  |  | 9986.17 | 5962.94 | 9986.17 | 9986.17 | Frank Giancola |  | 13-Oct-21 | 31-Mar-22 | 11-Oct-21 | 22-Nov-21 | 03-Dec-21 | Locates | Locates |  | 0
641988 | JOINT USE PERMIT HW2019-061 - LOWDEN AVE - BELL:Y77217 - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 08-Nov-21 |  |  | 24441.92 | 15277.66 | 24441.92 | 24441.92 | K-Line Construction | K-Line | 28-Jan-22 | 30-Jan-23 | 03-Jan-22 | 12-Feb-22 | 12-Feb-22 | Filler | Filler |  | 0
641998 | 2022 POLE RENEWAL - BATCH 1 (8- WP) | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 29-Nov-21 | 8 | 8 | 69180.44 | 78333.87 | 69180.44 | 69180.44 | Frank Giancola |  | 14-Apr-22 | 12-Aug-22 | 04-Apr-22 | 14-Mar-22 | 04-Apr-22 |  |  |  | 0
641999 | 290 GREEN MOUNTAIN RD E | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2021 | Frigotto, Rodrigo | Bennett, Aaron | 13-Sep-21 |  |  | 47524.32 | 44679.58 | 47524.32 | 47524.32 | Roy Owen | B&M | 18-Oct-21 | 22-Mar-23 | 12-Oct-21 | 25-Nov-21 | 30-Nov-21 | Locates | Locates |  | 0
642009 | PROMENADE BLVD OH LINE REPLACE (ST. CATHARINES) | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 24-Nov-21 |  |  | 46916.11 | 28611.31 | 46916.11 | 46916.11 | Dan Despres |  | 30-Mar-22 | 22-Sep-22 | 21-Mar-22 | 17-Mar-22 | 28-Jun-22 |  | N/A |  | 0
642033 | WINONA RD POLE RELOCATIONS (SOUTH OF BASELINE ROAD) HAMILTON | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 01-Sep-21 |  |  | 152110.56 | 129194.98 | 146831.72 | 152110.56 | Brad Carr | K-Line | 15-Oct-21 | 09-Aug-22 | 27-Sep-21 | 01-Nov-21 | 10-Dec-21 | Locates | Locates |  | 5,278.84
638019 | JOINT USE PERMIT HW2020-099 - LOCKE S, GEORGE, NELSON, PEARL S - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 18-Jun-21 |  |  | 8828.79 | 7765.76 | 8828.79 | 8828.79 | Brad Carr | K-Line | 30-Jul-21 | 27-Jan-22 | 26-Jul-21 | 13-Aug-21 | 13-Aug-21 | Filler | Filler |  | 0
642054 | 18 AUGUSTA ST / HAM / NS00131456 / 1500KVA 3PH COMMERCIAL SERVICE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Laus, Tomislav | 03-Dec-21 | 1 |  | 93781.2 | 91445.9 | 93781.2 | 93781.2 | Roy Owen | Fairway | 20-Jan-22 | 22-Sep-22 | 10-Jan-22 | 14-Mar-22 | 21-Mar-22 | Customer | Customer |  | 0
642061 | OH AUTO SWITCHES (DA) 2022 - PART 2 - 4 | 820 - Nebo | 150334 | Active | 98 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 13-Apr-22 | 4 | 4 | 406574.77 | 391909.04 | 406574.77 | 406574.77 | Koeppe, Jeffrey |  | 19-Aug-22 | 26-Jul-23 | 20-Jun-22 | 20-Jul-22 | 09-Dec-22 | Materials | Materials |  | 0
642060 | OH AUTO SWITCHES (DA) 2022 - PART 1 - 6 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 24-Nov-21 | 6 | 6 | 439669.2 | 500067.35 | 439669.2 | 439669.2 | Koeppe, Jeffrey |  | 01-Mar-22 | 17-Aug-22 | 10-Jan-22 | 17-Jan-22 | 31-May-22 | Locates | N/A |  | 0
642109 | 406 PRITCHARD EXPANSION WORK | 820 - Nebo | 152381 | Active | 50 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
642126 | 2022 - POLE REPLACEMENT - BATCH 2 - 4 WP'S | 820 - Nebo | 150335 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 30-Nov-21 | 4 | 4 | 54306.48 | 42031.04 | 54306.48 | 54306.48 | Macdougall, Stephen |  | 02-Dec-22 | 09-Aug-23 | 21-Nov-22 | 08-Nov-22 | 01-Dec-22 |  |  |  | 0
642168 | CUSTOMER INITIATED EXPANSION - ROXBOROUGH PARK, REID AVE NORTH - HAMILTON | 820 - Nebo | 152381 | Active | 93 | ACTIVE | Medium | Res-ICI | 2022 | Jakubowski, Mark | Celic, Dusan | 16-Jun-22 |  |  | 534472.53 | 523884.6 | 511267.62 | 534472.53 | Brad Carr | B&M | 26-Aug-22 | 26-Jul-23 | 11-Jul-22 | 25-Jul-22 | 08-Nov-22 | Contractor | Contractor |  | 23,204.91
642174 | WILD LIFE MITIGATION (ST. CATHARINES) | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 15-Sep-21 |  |  | 83457.76 | 109250.48 | 83457.76 | 83457.76 | Dan Despres |  | 20-Dec-21 | 22-Sep-22 | 15-Nov-21 | 18-Oct-21 | 28-Jul-22 |  | Materials |  | 0
642173 | WILD LIFE MITIGATION (HAMILTON) | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 15-Sep-21 |  |  | 91116.79 | 51684.33 | 91116.79 | 91116.79 | Koeppe, Jeffrey |  | 11-Nov-21 | 21-Aug-22 | 04-Oct-21 | 19-Oct-21 | 10-Dec-21 | Lines | Lines |  | 0
642177 | JOINT USE PERMIT HW2021-090 - GREENCEDAR, VENETIAN, ANTHONY, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 01-Feb-22 |  |  | 21875.79 | 11261.43 | 21875.79 | 21875.79 | Brad Carr | K-Line | 31-Mar-22 | 12-Jun-22 | 15-Mar-22 | 14-Mar-22 | 14-Mar-22 |  |  |  | 0
642189 | 2022 - EMERGING POLE - 7 FOUNDRY ST, DUNDAS | 820 - Nebo | 150828 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean | 06-Jan-23 |  |  | 84411.23 | 87861.29 | 84411.23 | 84411.23 | Brad Carr | K-Line | 10-Mar-23 | 26-Jul-23 | 06-Mar-23 | 14-Mar-23 | 07-Jun-23 | Materials | Materials |  | 0
641094 | CAMPVIEW | 820 - Nebo | 151452 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean | 07-Oct-22 |  |  | 521041.07 | 82529.7 | 521041.07 | 521041.07 | Brad Carr | B&M | 02-Dec-22 | 26-Jul-23 | 14-Nov-22 | 28-Nov-22 |  | Contractor | Contractor |  | 0
642303 | 2022 - TX RENEWAL HAM BATCH 1 - 5 TX'S | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 29-Nov-21 | 5 | 5 | 168274.47 | 112585.24 | 168274.47 | 168274.47 | Macdougall, Stephen |  | 31-Aug-22 | 05-Oct-22 | 25-Jul-22 | 02-Jun-22 | 16-Aug-22 | Filler | Filler |  | 0
642302 | 2022 - TX RENEWAL - SCH BATCH 1 - 4TX'S | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 29-Nov-21 | 4 | 4 | 103445.31 | 69102.24 | 103445.31 | 103445.31 | Frank Giancola |  | 03-Oct-22 | 02-Mar-23 | 06-Sep-22 | 22-Aug-22 | 23-Sep-22 |  |  |  | 0
642307 | 2023 - STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 4) | 820 - Nebo | 151303 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 19-Dec-22 |  |  | 1575497.79 | 1195094.14 | 1575497.79 | 1575497.79 | Brad Carr | B&M | 02-Oct-23 | 02-Oct-23 | 01-Jun-23 | 01-May-23 |  | Design | Materials |  | 0
642319 | 620 RYMAL RD EAST/ HAM / UP | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Sabbah, Amir | 20-Apr-22 |  |  | 74775.85 | 64653.74 | 74775.85 | 74775.85 | Macdougall, Stephen | Fairway | 03-Jun-22 | 28-May-23 | 30-May-22 | 05-Dec-22 | 22-Dec-22 | Customer | Customer |  | 0
642324 | 395 JONES RD / HAM / UP / COS | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 3198.81 |  | 0 | Calvin Arsenault |  |  | 16-May-23
642328 | ROAD AUTHORITY - ST.DAVID'S RD - ROAD URBANIZATION - ST.CATHARINES | 830 - St. Catharines | 150653 | Active | 40 | ACTIVE | Medium | Infrast | 2023 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642398 | 2022 - SWITCH RENEWAL - WEST - HORIZONTAL UNITS - 2 | 820 - Nebo | 150337 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 24-Nov-21 | 2 | 2 | 185715.53 | 169824.03 | 185715.53 | 185715.53 | Koeppe, Jeffrey |  | 16-Jun-22 | 11-Oct-22 | 16-May-22 | 15-Jul-22 | 07-Oct-22 | Locates | Locates |  | 0
642399 | 2022 - SWITCH RENEWAL - WEST - VERTICAL UNITS - 2 | 820 - Nebo | 150337 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 13-Dec-21 | 2 | 2 | 226457.41 | 213227.75 | 226457.41 | 226457.41 | Brad Carr | K-Line | 24-Jun-22 | 22-Sep-22 | 30-May-22 | 27-Jun-22 | 14-Sep-22 | Weather | Weather |  | 0
642444 | EMERGING 2021 - INSULATOR CHANGES. CHURCH ST. | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Rolfe, Eric | 01-Oct-21 |  |  | 42557.6 | 50612.95 | 68736.9 | 42557.6 | Brad Carr | B&M | 12-Nov-21 | 09-Aug-22 | 25-Oct-21 | 25-Oct-21 | 10-Dec-21 |  | Contractor |  | -26,179.30
642461 | 361 GRANTHAM AVE - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642494 | BELL BONDS - Y32921 & C00322 - ST CATH | 830 - St. Catharines | 151536 | Active | 98 | ANALYZE |  |  | 2022 | O'Gay, Brian | Johnson, William | 23-Sep-21 |  |  | 3223.17 | 867.8 | 3223.17 | 3223.17 | K-Line Construction |  | 30-Nov-21 | 26-Jul-23 | 01-Nov-21 | 07-Feb-22 | 13-May-22 | Filler | Filler |  | 0
642497 | JOINT USE PERMIT HW2021-066 - GLENDALE - ST CATH | 830 - St. Catharines | 151536 | Inactive | 99 | CANCELLED |  |  | 2023 | O'Gay, Brian | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642502 | 30 LAURIER AVENUE / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Djuric, Zdravko | 07-Dec-21 |  |  | 47913.52 | 51043.26 | 47913.52 | 47913.52 | Roy Owen | Fairway | 12-Jan-22 | 26-Sep-22 | 10-Jan-22 | 22-Feb-22 | 13-May-22 | Customer | Customer |  | 0
642500 | 1040 QUEENSDALE AVENUE EAST / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Djuric, Zdravko | 19-Jan-22 | 1 |  | 63925.94 | 86580.96 | 63925.94 | 63925.94 | Macdougall, Stephen | Fairway | 10-Mar-22 | 03-Oct-22 | 01-Mar-22 | 14-Mar-22 | 30-May-22 | Customer | Customer |  | 0
642499 | 64 SULPHUR SPRINGS RD / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642503 | 86 CAMERON AVENUE / DUN / UP / 3PH PAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Kappheim, Adam | Djuric, Zdravko | 05-Nov-21 |  |  | 65558.41 | 68011.68 | 65558.41 | 65558.41 | Macdougall, Stephen | Fairway | 13-Jan-22 | 22-Sep-22 | 03-Jan-22 | 12-Jan-22 | 18-Mar-22 | Customer | Customer |  | 0
642505 | OH AUTO SWITCHES (DA) 2022 - PART 3 - 4 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 01-Dec-21 | 4 | 4 | 365294.42 | 360586.5 | 347362.04 | 365294.42 | Koeppe, Jeffrey |  | 10-Jun-22 | 14-Feb-23 | 11-Apr-22 | 02-May-22 | 22-Jul-22 | Locates | N/A |  | 17,932.38
642504 | 2022 TX RENEWAL - BATCH 2 - HAM - 1 TX | 820 - Nebo | 150336 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642512 | OH AUTO SWITCHES (DA) 2022 - PART 4 - 4 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 29-Nov-21 | 4 | 4 | 283407.15 | 268438.05 | 283407.15 | 283407.15 | Dan Despres |  | 26-Apr-22 | 13-Jul-22 | 28-Feb-22 | 28-Feb-22 | 28-Jun-22 |  | Weather |  | 0
642513 | OH AUTO SWITCHES (DA) 2022 - PART 5 - 7 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 31-Mar-22 | 7 | 7 | 428082.12 | 643328.11 | 428082.12 | 428082.12 | Dan Despres |  | 18-Aug-22 | 14-Feb-23 | 06-Jun-22 | 18-May-22 | 16-Dec-22 | Materials | Materials |  | 0
642516 | UG AUTO SWITCHES (DA) 2022 - MH764 - 1 | 820 - Nebo | 150334 | Active | 98 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 30-Mar-22 | 1 | 1 | 365807.78 | 391115.45 | 365807.78 | 365807.78 | Brad Carr | B&M | 23-Jun-22 | 26-Jul-23 | 06-Jun-22 | 16-May-22 | 07-Sep-22 |  | Contractor |  | 0
642517 | UG AUTO SWITCHES (DA) 2023 - MH759 | 820 - Nebo | 150334 | Active | 84 | ACTIVE | High | DA | 2023 | Beaudrie, Scott | Billone, Justin | 25-Nov-22 | 1 |  | 360406.5 | 313556.86 | 360406.5 | 360406.5 | Tony Ierace | B&M | 20-Jun-23 | 15-Aug-23 | 01-Jun-23 | 19-Jun-23 |  | Contractor | Contractor |  | 0
642518 | UG AUTO SWITCHES (DA) 2022 - CLAPPISON - 1 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Wardell, Paul | 27-Jan-22 | 1 | 1 | 447750.27 | 501441.55 | 404232.82 | 447750.27 | Tony Ierace | B&M | 26-Apr-22 | 14-Feb-23 | 21-Mar-22 | 18-Oct-22 | 09-Dec-22 | Weather | N/A |  | 43,517.45
642520 | UG AUTO SWITCHES (DA) 2022 - CARLISLE - 1 | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 27-Jan-22 | 1 | 1 | 147566.89 | 152676.77 | 147566.89 | 147566.89 | Dan Despres |  | 14-Apr-22 | 14-Feb-23 | 04-Apr-22 | 04-Jul-22 | 10-Jul-22 | Customer | Customer |  | 0
642524 | 323 RYMAL ROAD EAST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 70 | ACTIVE |  |  | 2023 | Kappheim, Adam | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642525 | 2021 - OH EMERGING - 2 WYCHWOOD ROAD | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 11-Nov-21 |  |  | 88049.63 | 78629.63 | 88049.63 | 88049.63 | Dan Despres | Wiens | 17-Dec-21 | 22-Sep-22 | 06-Dec-21 | 06-Dec-21 | 16-Feb-22 |  | Lines |  | 0
642563 | PIER 5,6, & 7 - SUBD ICI EDS | 820 - Nebo | 151652 | Active | 80 | PDG SnR |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 251667.23 | 259621.47 | 251667.23 | 251667.23 | Macdougall, Stephen | Transpw | 15-Sep-23 | 15-Sep-23 | 14-Aug-23 | [5 empty] | 0
642566 | 870 QUEENSTON/ HAM / NS | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Kappheim, Adam | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642568 | 2022 EMERGING UG - RIVERVIEW REAR LOT CONVERSION | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-21 |  |  | 926197.58 | 906053.34 | 900505.47 | 926197.58 | Brad Carr | B&M | 31-Mar-22 | 22-Sep-22 | 10-Jan-22 | 10-Jan-22 | 14-Jul-22 |  | Contractor |  | 25,692.11
642567 | 2022 - BELAND AVE N - 1 WP, 1OH TX | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-21 | 1 | 1 | 24299.58 | 22846.44 | 24299.58 | 24299.58 | Macdougall, Stephen |  | 15-Dec-22 | 10-Nov-22 | 07-Nov-22 | 17-Oct-22 | 21-Oct-22 |  |  |  | 0
642577 | 218 ONTARIO ST - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 50 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642637 | 85 CORESLAB DR | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Bennett, Aaron | 17-Dec-21 |  |  | 79020.31 | 64739.11 | 79020.31 | 79020.31 | Macdougall, Stephen | Fairway | 14-Feb-22 | 22-Sep-22 | 07-Feb-22 | 01-Mar-22 | 21-Sep-22 | Customer | Customer |  | 0
642660 | OVERHEAD LINE ISOLATION/REMOVAL, 14-18 AUGUSTA ST | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2021 | Jakubowski, Mark | Patel, Ketan | 07-Sep-21 |  |  | 71448.3 | 35611.56 | 71448.3 | 71448.3 | Macdougall, Stephen |  | 27-Oct-21 | 22-Sep-22 | 11-Oct-21 | 03-Nov-21 | 26-Nov-21 | Locates | Customer |  | 0
642667 | JOINT USE PERMIT HW2021-108 - MILL N AND PARKSIDE - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642683 | CUSTOMER INITIATED RELOCATIONS - AYR AVE/BINGHAM DR | 820 - Nebo | 150665 | Active | 98 | COMPLETE | Medium | Res-ICI | 2022 | Jakubowski, Mark | Celic, Dusan | 30-May-22 |  |  | 321437.76 | 301452.74 | 334798.54 | 321437.76 | Brad Carr | B&M | 16-Sep-22 | 26-Jul-23 | 18-Jul-22 | 18-Jul-22 | 13-Jan-23 | Contractor | Contractor |  | -13,360.78
642696 | WATERDOWN INDUSTRIAL PARK - SUBD ICI EDS | 820 - Nebo | 151652 | Active | 50 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642736 | 406 PRITCHARD RD / HAM / NS | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Kappheim, Adam | Sabbah, Amir | 04-Jul-22 |  |  | 145201.07 | 145878.34 | 145201.07 | 145201.07 | Roy Owen | Fairway | 31-Aug-22 | 08-Aug-23 | 15-Aug-22 | 18-Aug-22 | 09-Nov-22 | Locates | Locates |  | 0
642745 | 87 KENNEDY AVE - REROUTING SERVICE FOR AERIAL TRESPASS | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Wardell, Paul | 20-Dec-21 |  |  | 15152.82 | 15092.06 | 15152.82 | 15152.82 | Brad Carr | Fairway | 18-Feb-22 | 22-Sep-22 | 07-Feb-22 | 17-Mar-22 | 28-Apr-22 | Contractor | Contractor |  | 0
642747 | 141 LOUTH ST | 830 - St. Catharines | 150455 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bennett, Aaron | 19-May-22 |  |  | 70901.6 | 21584.5 | 70901.6 | 70901.6 | Frank Giancola | Wiens | 18-Jul-22 | 31-Jul-23 | 11-Jul-22 | 01-Nov-22 |  | Locates | Locates |  | 0
642748 | 2021 EMERGING OH - HAM - BATCH 3 - 1 TX | 820 - Nebo | 150336 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642750 | KENILWORTH TS - POWER FACTOR CORRECTION - CAP BANK | 820 - Nebo | 150404 | Active | 10 | ACTIVE |  |  | 2023 | Braletic, Bob | Lustrinelli, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642816 | 47 HASTINGS ST | 830 - St. Catharines | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642826 | 1047 BARTON ST / HAM / NS00152347 / 3000KVA 3PH COMMERCIAL SERVICE | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642829 | QUEENSTON RD BURIAL - NASH TO CENTENNIAL | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 13-Jun-22
642832 | HYDRO VAULT LID REPLACEMENT-V77-CHAMPLAIN AVE | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Celic, Dusan | 29-Oct-21 |  |  | 22390.09 | 22496.17 | 14784.9 | 22390.09 | Brad Carr | Fairway | 10-Dec-21 | 17-Jul-22 | 25-Oct-21 | 28-Mar-22 | 28-Mar-22 | Contractor | Contractor |  | 7,605.19
642862 | 2022 - TX RENEWAL HAM - BATCH 3 (UG) - 5 TX | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 29-Nov-21 | 5 | 5 | 43994.99 | 30814.93 | 43994.99 | 43994.99 | Tony Ierace |  | 23-Mar-22 | 22-Sep-22 | 14-Mar-22 | 10-Mar-22 | 25-Mar-22 |  | Weather |  | 0
642909 | JOINT USE PERMIT HW2021-118 - WILSON E - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Mar-22 |  |  | 10790.35 | 8431.75 | 10790.35 | 10790.35 | K-Line Construction | K-Line | 31-May-22 | 30-Jan-23 | 02-May-22 | 14-Mar-22 | 14-Mar-22 |  |  |  | 0
642910 | JOINT USE PERMIT HW2021-119 - BARTON - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Mar-22 |  |  | 10823.88 | 9621.69 | 10823.88 | 10823.88 | K-Line Construction | K-Line | 31-May-22 | 30-Jan-23 | 02-May-22 | 14-Mar-22 | 14-Mar-22 |  |  |  | 0
642916 | JOINT USE PERMIT HW2021-124 - GRAY, BRITANNIA, ROXBOROUGH, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Mar-22 |  |  | 7928.36 | 6676.75 | 7928.36 | 7928.36 | K-Line Construction | K-Line | 31-May-22 | 30-Jan-23 | 02-May-22 | 14-Mar-22 | 14-Mar-22 |  |  |  | 0
642915 | JOINT USE PERMIT HW2021-123 - MOUNTAIN N - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 02-May-22 |  |  | 6136.81 | 5005.51 | 6136.81 | 6136.81 | K-Line Construction | K-Line | 31-May-22 | 30-Jan-23 | 02-May-22 | 14-Mar-22 | 14-Mar-22 |  |  |  | 0
642914 | JOINT USE PERMIT HW2021-122 - CAMPBELL, PROVINCE N, ETC - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
642919 | JOINT USE PERMIT HW2021-127 - CHERRYWOOD, NEW MTN, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 04-Mar-22 |  |  | 6963.6 | 5577.44 | 6963.6 | 6963.6 | K-Line Construction | K-Line | 31-May-22 | 30-Jan-23 | 02-May-22 | 14-Mar-22 | 14-Mar-22 |  |  |  | 0
642974 | 2022 TX RENEWAL HAM - BATCH 7 - 7 TX | 820 - Nebo | 150336 | Active | 96 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 16-Dec-21 | 7 | 7 | 177110.79 | 197519.8 | 177110.79 | 177110.79 | Koeppe, Jeffrey |  | 06-Mar-23 | 29-Aug-23 | 16-Jan-23 | 16-Dec-22 | 17-Mar-23 |  | Materials |  | 0
642973 | 2022 TX RENEWAL HAM - BATCH 6 - 7 TX | 820 - Nebo | 150336 | Active | 96 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 29-Nov-21 | 7 | 7 | 210509.83 | 143306.33 | 210509.83 | 210509.83 | Koeppe, Jeffrey |  | 28-Feb-23 | 26-Jul-23 | 02-Jan-23 | 30-Jan-23 | 01-Mar-23 |  | Materials |  | 0
642972 | 2022 TX RENEWAL HAM - BATCH 5 - 4 TX | 820 - Nebo | 150336 | Active | 96 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 29-Nov-21 | 4 | 4 | 122898.53 | 92858.92 | 122898.53 | 122898.53 | Koeppe, Jeffrey |  | 06-Dec-22 | 26-Jul-23 | 01-Nov-22 | 14-Nov-22 | 10-Feb-23 | Materials | Materials |  | 0
642970 | 2022 TX RENEWAL HAM - BATCH 4 - 5 TX | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 29-Nov-21 | 5 | 5 | 118392.51 | 150510.83 | 118392.51 | 118392.51 | Macdougall, Stephen |  | 10-Aug-22 | 12-Oct-22 | 11-Jul-22 | 11-Jul-22 | 14-Oct-22 | Filler | Filler |  | 0
642975 | 2022 TX RENEWAL HAM - BATCH 8 - 12 TX | 820 - Nebo | 150336 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-21 | 12 | 12 | 271921.05 | 235458.83 | 271921.05 | 271921.05 | Brad Carr | K-Line | 29-Jul-22 | 26-Jul-23 | 27-Jun-22 | 27-Jun-22 | 16-Sep-22 | Locates | Locates |  | 0
642993 | 2022 MINI REBUILD - GRANTHAM AVE - ST. CATHARINES - 20 | 830 - St. Catharines | 150335 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 24-Nov-21 | 20 | 20 | 267376.97 | 459584.27 | 267376.97 | 267376.97 | Dan Despres |  | 31-Mar-23 | 23-Aug-23 | 06-Feb-23 | 14-Mar-23 |  | MC/PUCC Permit | MC/PUCC Permit |  | 0
643004 | 2021 - 50 MAIN STREET (DUNDAS) - TRANSFORMER REPLACEMENT | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 24-Nov-21 | 1 | 1 | 44522.26 | 33387.23 | 44522.26 | 44522.26 | Brad Carr | K-Line | 10-Dec-21 | 22-Aug-22 | 06-Dec-21 | 13-Dec-21 | 15-Mar-22 | Materials | Materials |  | 0
643013 | 2022 - 151 MCNIVEN ROAD LOOP FEED | 820 - Nebo | 151452 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 17-Dec-21 |  |  | 23684.44 | 25939.81 | 23684.44 | 23684.44 | Koeppe, Jeffrey | Fairway | 11-Mar-22 | 26-Jul-23 | 07-Mar-22 | 12-Dec-22 | 23-Jan-23 | MC/PUCC Permit | MC/PUCC Permit |  | 0
643032 | 2022 - CABLE INJECT - MILLEN-BARTON-FRUITLAND | 820 - Nebo | 151300 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 30-Nov-21 |  |  | 976323.22 | 477517.13 | 976323.22 | 976323.22 | Brad Carr | Nvinium | 29-Jul-22 | 26-Jul-23 | 01-Apr-22 | 29-Mar-22 |  | Contractor | Materials |  | 0
643035 | 2022 - ONTARIO STREET SPOT POLES REPLACEMENTS | 830 - St. Catharines | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643055 | ROXBOROUGH PARK EXPANSION - POLE LINE REBUILD - ROXBOROUGH AVE | 820 - Nebo | 152381 | Active | 92 | ANALYZE | Medium | Res-ICI | 2023 | Jakubowski, Mark | Celic, Dusan | 10-Nov-22 |  |  | 1069347.57 | 1010305.68 | 1026664.61 | 1069347.57 | Brad Carr | B&M | 31-Mar-23 | 26-Jul-23 | 09-Jan-23 | 09-Jan-23 | 02-May-23 | Contractor | Contractor |  | 42,682.96
643065 | 925 ARVIN AVE E / HAM / UP00164819 / 3000KVA 3PH COMMERCIAL SERVICE UPG | 820 - Nebo | 150449 | Active | 91 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav | 22-Aug-22 |  |  | 232303.26 | 274882.05 | 232303.26 | 232303.26 | Macdougall, Stephen | Fairway | 05-May-23 | 08-Aug-23 | 05-Oct-22 | 09-Jan-23 |  | Materials | Materials |  | 0
643082 | ROXBOROUGH PARK - PHASE 3 - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | CANCELLED |  |  | 2022 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643083 | STONEGATE BLOCK 26 - SUBD RES EDS | 820 - Nebo | 150588 | Active | 92 | ANALYZE |  |  | 2023 | Velickovski, Goran | Morris, Mark | 30-Sep-22 |  |  | 121294.03 | 126911.09 | 121294.03 | 121294.03 | Roy Owen | Transpw | 28-Jul-22 | 26-Jul-23 | 13-Jun-22 | 08-Aug-22 | 04-Apr-23 | Customer | Customer |  | 0
643112 | 2023 - WEST CABLE REPLACEMENTS - STONEY CREEK - NORTH OF HWY 8 (PART 3) | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643111 | 2022 - WEST CABLE REPLACEMENTS - STONEY CREEK - NORTH OF HWY 8 (PART 2) | 820 - Nebo | 151299 | Active | 94 | ACTIVE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-21 |  |  | 1999586.86 | 2115536.77 | 1792698.75 | 1999586.86 | Brad Carr | B&M | 16-Dec-22 | 26-Jul-23 | 06-Jun-22 | 18-Jul-22 | 15-Dec-22 | Contractor | Contractor |  | 206,888.11
643118 | ABERDEEN #4 O/H FEEDER -PH 2 | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643155 | 300B FOURTH AVE / SCH / NS00102866 / 1000KVA 3PH COMMERCIAL SERVICE | 830 - St. Catharines | 150455 | Active | 95 | ANALYZE |  |  | 2022 | Frigotto, Rodrigo | Laus, Tomislav | 04-Mar-22 | 1 |  | 64788.95 | 49160.97 | 64788.95 | 64788.95 | Frank Giancola |  | 20-Apr-22 | 27-Jul-23 | 18-Apr-22 | 19-Jul-22 | 02-Dec-22 | Customer | Customer |  | 0
643174 | OVERSIZE LOAD MOVE - ST. CATHARINES HOSPITAL | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643176 | NV25 & NV35 - NEW MH ROOF | 830 - St. Catharines | 151065 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 31-Aug-22 | 2 | 2 | 291089.79 | 293903.29 | 340721.53 | 291089.79 | Brad Carr | B&M | 16-Dec-22 | 26-Jul-23 | 24-Oct-22 | 10-Nov-22 | 13-Jan-23 | Contractor | Contractor |  | -49,631.74
643192 | JOINT USE PERMIT HW2021-134 - HATT, MCMURRAY, FOUNDRY, ETC - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643203 | 476 JAMES ST N / HAM / NS / COS | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643207 | 1557 RYMAL RD E / HAM / NS | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643232 | JOINT USE PERMIT HW2021-136 - CANADA, JACKSON AND POULETTE - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643209 | 82 PARKSIDE DR / HAM / NS | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Sabbah, Amir | 22-Aug-22 |  |  | 56811.48 | 63987.8 | 56811.48 | 56811.48 | Roy Owen | Fairway | 28-Sep-22 | 31-May-23 | 26-Sep-22 | 29-Sep-22 | 09-Nov-22 | Locates | Locates |  | 0
643240 | 119 CUSHMAN RD | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Bennett, Aaron | 02-Feb-22 |  |  | 89753.49 | 85310.31 | 89753.49 | 89753.49 | Frank Giancola | Wiens | 22-Apr-22 | 09-Aug-23 | 14-Mar-22 | 22-Feb-22 | 17-May-22 |  | Customer |  | 0
643269 | JOINT USE PERMIT HW2021-140 - RYMAL RD E - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643274 | BELL BONDS - J37171 - LAKESHORE ST.W - ST.CATHARINES | 830 - St. Catharines | 151536 | Inactive | 99 | CANCELLED |  |  | 2023 | O'Gay, Brian | Oosterlinck, David | 16-May-22 |  |  | 1546.85 | 545.55 | 1546.85 | 1546.85 | Frank Giancola |  | 22-Sep-22 | 18-Apr-23 | 04-Jul-22 | 06-Mar-23 | 06-Mar-23 | Filler | Filler |  | 0
643308 | FIFTY RD & SONOMA LANE - POLE CONFLICT - SUBD CAP PROJ | 830 - St. Catharines | 151653 | Active | 95 | COMPLETE |  |  | 2022 | Gamboa, Henry | Morris, Mark | 03-Dec-21 | 1 | 1 | 12125.76 | 14773.1 | 12125.76 | 12125.76 | Macdougall, Stephen |  | 18-Jan-22 | 26-Jul-23 | 17-Jan-22 | 13-Jan-22 | 13-Jan-22 |  |  |  | 0
643312 | 1411 UPPER WELLINGTON ST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643328 | EXPANSION WORK FOR 70 CARLISLE ST, BUS CHARGING STATION FOR CITY OF ST. CATHARIN | 830 - St. Catharines | 152381 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643363 | 51 RALEIGH ST / HAM / UP / 1PH | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Dragojevic, Igor | 20-Dec-21 |  |  | 7591.7 | 0 | 7591.7 | 7591.7 | Roy Owen |  | 11-Jan-22 | 23-Sep-22 | 10-Jan-22 | 17-Feb-22 | 17-Feb-22 | Customer | Customer |  | 0
643384 | 75 OLIVER LANE - ICI | 830 - St. Catharines | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643385 | NV 21 - NEW ROOF + OTHER NV LIDS & ASSOCIATED WORK - 2 | 830 - St. Catharines | 151065 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 13-Dec-21 | 1 | 1 | 207835.91 | 239115.56 | 329543.62 | 207835.91 | Brad Carr | B&M | 25-Feb-22 | 02-Feb-23 | 31-Jan-22 | 10-Feb-22 | 21-Apr-22 | Contractor | Contractor |  | -121,707.71
643389 | 21 RANDALL AVE - OVERHEAD TRESPASS - INGROUND POOL | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Wardell, Paul | 21-Dec-21 |  |  | 9724.51 | 10412.83 | 9724.51 | 9724.51 | Koeppe, Jeffrey |  | 10-Feb-22 | 23-Sep-22 | 09-Feb-22 | 01-Mar-22 | 01-Mar-22 | Locates | Locates |  | 0
643473 | HAMILTON SOUTH MOUNTAIN FEEDERS PART 3 | 820 - Nebo | 150376 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 17-Mar-22 |  |  | 252241.61 | 230819.96 | 226227.74 | 252241.61 | Brad Carr | K-Line | 24-Jun-22 | 26-Jul-23 | 06-Jun-22 | 16-May-22 | 28-Oct-22 |  | Weather |  | 26,013.87
643483 | NV ROOF - T803 | 830 - St. Catharines | 151065 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 28-Jul-22 | 1 | 1 | 103920.23 | 67867.59 | 103920.23 | 103920.23 | Frank Giancola | N/A | 02-Sep-22 | 27-Jul-23 | 22-Aug-22 | 19-Aug-22 |  | N/A | N/A |  | 0
643519 | 2022 SWITCH RENEWAL HAM - BATCH 2 - 1 VIPER | 820 - Nebo | 150337 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 09-Dec-21 | 1 | 1 | 124582.64 | 99552.83 | 124582.64 | 124582.64 | Koeppe, Jeffrey |  | 21-Jan-22 | 10-Aug-22 | 03-Jan-22 | 17-Jan-22 | 02-May-22 | Locates | N/A |  | 0
643536 | 2022 SWITCH RENEAL HAM - 2 MAUNAL LIS | 820 - Nebo | 150337 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 17-Dec-21 | 2 | 2 | 100379.31 | 107294.32 | 100379.31 | 100379.31 | Koeppe, Jeffrey |  | 25-Aug-22 | 14-Oct-22 | 01-Aug-22 | 15-Aug-22 | 07-Oct-22 | Locates | Locates |  | 0
643537 | 2022 - CABLE REPLACEMENT - BEACHVIEW DR | 830 - St. Catharines | 151452 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 25-Mar-22 |  |  | 45637.04 | 36361.68 | 45637.04 | 45637.04 | Dan Despres | Fairway | 13-May-22 | 26-Jul-23 | 09-May-22 | 03-Oct-22 | 07-Oct-22 | MC/PUCC Permit | MC/PUCC Permit |  | 0
643544 | 5 &7 RUSHOLME CRES-REAR YARD TRESPASS | 830 - St. Catharines | 150828 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 11-Jul-22 |  |  | 69817.86 | 84051.7 | 69817.86 | 69817.86 | Brad Carr | K-Line | 12-Aug-22 | 26-Jul-23 | 01-Aug-22 | 03-Oct-22 | 20-Dec-22 | Locates | Locates |  | 0
643554 | 3 HILLCREST AVE-REAR YARD TRESPASS | 830 - St. Catharines | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Rolfe, Eric |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643569 | JOINT USE PERMIT HW2021-150 - ROBINSON - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643572 | 121 MOFFATT - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 82 | RELEASED |  |  | 2023 | Velickovski, Goran | Morris, Mark | 05-Apr-23 |  |  | 36190.03 | 8139.38 | 36190.03 | 36190.03 | Frank Giancola |  | 31-Aug-23 | 31-Aug-23 | 28-Aug-23 |  |  | Customer | Customer |  | 0
643588 | 268 OAKDALE DR | 830 - St. Catharines | 150455 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bennett, Aaron | 22-May-23 |  |  | 63116.34 | 44025.47 | 63116.34 | 63116.34 | Frank Giancola | Fairway | 25-Jul-23 | 01-Aug-23 | 17-Jul-23 | 16-Jun-23 |  |  | Weather |  | 0
643617 | JOINT USE PERMIT HW2021-153 - PARK S, BOLD, AND JAMES S - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643650 | 2022 - BULA DRIVE URD | 830 - St. Catharines | 151452 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 04-May-22 |  |  | 569953.91 | 625463.59 | 524383.46 | 569953.91 | Brad Carr | B&M | 21-Oct-22 | 26-Jul-23 | 15-Aug-22 | 07-Sep-22 | 01-Dec-22 | Locates | Locates |  | 45,570.45
643652 | 66 INNOVATION DRIVE / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Dragojevic, Igor | 06-Jul-22 |  |  | 46124.73 | 45721.63 | 46124.73 | 46124.73 | Roy Owen |  | 17-Aug-22 | 28-Jul-23 | 15-Aug-22 | 23-Aug-22 | 24-Aug-22 | Customer | Customer |  | 0
643812 | JOINT USE PERMIT HW2021-156 - UPPER JAMES - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643935 | BOWSTEAD DR REBUILD (ST. CATHARINES) - 14 | 830 - St. Catharines | 150335 | Active | 95 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 19-May-22 | 14 | 14 | 222719.56 | 161651.54 | 222719.56 | 222719.56 | Dan Despres |  | 06-Mar-23 | 26-Jul-23 | 09-Jan-23 | 02-Dec-22 | 27-Jan-23 |  |  |  | 0
643944 | 2022 EMERGING OH - STROUD SC RELOCATION | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Wardell, Paul | 28-Jan-22 |  |  | 207214.19 | 189373.37 | 207214.19 | 207214.19 | Koeppe, Jeffrey | Fairway | 07-Apr-22 | 23-Sep-22 | 07-Mar-22 | 14-Mar-22 | 29-Apr-22 | Locates | Locates |  | 0
643952 | CUSTOMER INITIATED RELOCATIONS - POLE RELOCATION AYR AVE | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 06-May-22
643954 | 47 HASTINGS ST | 830 - St. Catharines | 150455 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
643957 | 89, 91 WENTWORTH STREET SOUTH / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644003 | 3 ABBOTT ST | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644004 | HWY 8 & GRAY - AUTOMATE INTERSECTION - 3 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 10-Jan-22 | 3 | 3 | 232049.69 | 232251.19 | 232049.69 | 232049.69 | Koeppe, Jeffrey |  | 27-May-22 | 14-Feb-23 | 18-Apr-22 | 02-May-22 | 12-Aug-22 | Locates | Locates |  | 0
644010 | JOINT USE PERMIT HW2021-159 - RYMAL E - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644007 | JOINT USE PERMIT HW2021-157 - BAY N, MULBERRY, AND SHEAFFE - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644015 | 222 ONTARIO STREET - SERVICE RELOCATE | 830 - St. Catharines | 150828 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Rolfe, Eric | 05-May-22 |  |  | 47177.05 | 88410.07 | 47177.05 | 47177.05 | Dan Despres | Fairway | 08-Jul-22 | 26-Jul-23 | 27-Jun-22 | 30-Jan-23 | 23-Feb-23 | Contractor | Contractor |  | 0
644016 | 276 DUNSMURE DRIVE - HAM - NS - 3PH - 1600A | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Pellerin, Patrick | 12-May-23 |  |  | 158692.64 | 80528.89 | 158692.64 | 158692.64 | Macdougall, Stephen | Fairway | 20-Jun-23 | 28-Jul-23 | 12-Jun-23 | 27-Jun-23 |  | Customer | Customer |  | 0
644020 | 281 MARTINGDALE RD | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Bennett, Aaron | 02-Aug-22 |  |  | 62793.45 | 42089.84 | 62793.45 | 62793.45 | Frank Giancola | Wiens | 31-Oct-22 | 02-Aug-23 | 24-Oct-22 | 10-Oct-22 | 05-Dec-22 | Customer | Contractor |  | 0
644047 | 1936 RYMAL RD E / HAM / NS00195485 / 750KVA 3PH COMMERCIAL SERVICE | 820 - Nebo | 150449 | Active | 91 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav | 25-Jul-22 |  |  | 94588.26 | 111292.6 | 94588.26 | 94588.26 | Macdougall, Stephen | Fairway | 14-Oct-22 | 28-Jul-23 | 10-Oct-22 | 14-Dec-22 |  | Customer | Customer |  | 0
644050 | 2022 POLE RENEWAL MINI REBUILD-AQUADALE DR. | 830 - St. Catharines | 150335 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Rolfe, Eric | 05-May-22 | 12 | 12 | 160832.59 | 210527.49 | 160832.59 | 160832.59 | Dan Despres |  | 16-Dec-22 | 26-Jul-23 | 14-Nov-22 | 13-Sep-22 | 01-Dec-22 |  |  |  | 0
644075 | 415 MAIN ST W / HAM / NS00186002 / 750KVA 3PH TEMP SERVICE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Laus, Tomislav | 25-Jul-22 |  |  | 79900.8 | 74820.87 | 79900.8 | 79900.8 | Roy Owen | Fairway | 06-Sep-22 | 03-Oct-22 | 29-Aug-22 | 12-Oct-22 | 14-Nov-22 | Customer | Customer |  | 0
644126 | 415 MAIN ST W / HAM / NS00228428 / 750KVA - 800A 347/600V 3PH PAD SERVICE | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav | 27-Jun-23 |  |  | 74915.28 | 7308.13 | 74915.28 | 74915.28 | Macdougall, Stephen | Fairway | 14-Aug-23 | 14-Aug-23 | 31-Jul-23 | [5 empty] | 0
644148 | CUSTOMER INITIATED DE-ENERGIZE PRIMARY - 324 DUNDAS ST E - WATERDOWN | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2022 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644226 | JOINT USE PERMIT HW2021-167 - JACKSON W, PEARL S, CANADA, ETC - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644238 | CUSTOMER INITIATED RELOCATION OF POLES - HILLYARD & NIAGARA ST (HOPA PIER 14) | 820 - Nebo | 150665 | Active | 81 | PPS INCOMPLETE |  |  | 2023 | Jakubowski, Mark | Karan, Andjelo |  |  |  | 350667.62 | 7895.64 | 350667.62 | 350667.62 | Calvin Arsenault |  |  | 26-Jul-23 | [6 empty] | 0
644340 | 2022- SWITCH GEAR REMOVAL- SC1044 | 830 - St. Catharines | 150334 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 05-Jul-22 | 1 | 1 | 224344.48 | 210597.16 | 224344.48 | 224344.48 | Brad Carr | B&M | 02-Sep-22 | 26-Jul-23 | 15-Aug-22 | 05-Sep-22 | 01-Dec-22 | Contractor | Contractor |  | 0
644348 | 55 QUEENSTON RD/ HAM / NS | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Biasutti, Stephen | 18-May-23 |  |  | 134483.33 | 5825.53 | 134483.33 | 134483.33 | Macdougall, Stephen | Fairway | 04-Jul-23 | 02-Aug-23 | 26-Jun-23 |  |  | Customer | Customer |  | 0
644427 | 2022 BELL TRANSFERS - AUCHMAR ROAD | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 11-Jul-22 | 0 | 0 | 19286.36 | 19780.9 | 19286.36 | 19286.36 | Brad Carr | K-Line | 11-Jul-22 | 23-Sep-22 | 11-Jul-22 | 11-Jul-22 | 11-Jul-22 |  |  |  | 0
644478 | EMERGING - 2022 BEACH CABLE RELOCATION | 820 - Nebo | 151452 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 01-Jun-22 |  |  | 397715.01 | 427340.91 | 97715.01 | 397715.01 | Tony Ierace |  | 23-Aug-22 | 26-Jul-23 | 05-Jul-22 | 04-Jul-22 | 12-Aug-22 |  |  |  | 300,000.00
640268 | JOINT USE PERMIT HW2021-003 - YORK, WILMAR, SLEEPY HOLLOW, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 01-Feb-22 |  |  | 15536.54 | 10275.47 | 15536.54 | 15536.54 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 15-Mar-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
644490 | 150 GLENDALE AVE - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 82 | RELEASED |  |  | 2023 | Velickovski, Goran | Morris, Mark | 11-Jan-23 |  |  | 445386.83 | 83145.34 | 445386.83 | 445386.83 | Frank Giancola | Transpw | 09-Aug-23 | 09-Aug-23 | 01-Aug-23 |  |  | Customer | Customer |  | 0
644503 | 281 BIRCH AVENUE / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644510 | 281 BIRCH AVE EXPANSION - HSR MSF | 820 - Nebo | 152381 | Active | 50 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
644525 | JOINT USE PERMIT HW2020-154 - RAMSEY, OFIELD, LWR HORNING, ETC - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644529 | 477 ARVIN AVE - TAYLOR STEEL LINE REPLACEMENT | 820 - Nebo | 150665 | Active | 40 | ACTIVE | Low | Comm | 2023 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
639719 | JOINT USE PERMIT HW2020-154 - RAMSEY, OFIELD, LWR HORNING, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Johnson, William | 01-Feb-22 |  |  | 15297.27 | 8719.67 | 15297.27 | 15297.27 | K-Line Construction | K-Line | 31-Mar-22 | 30-Jan-23 | 15-Mar-22 | 31-Jan-22 | 31-Jan-22 | Filler | Filler |  | 0
644532 | 2023 - 151 PARNELL ROAD CABLE REPLACEMENT | 830 - St. Catharines | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
644531 | 2023 LAKESHORE CABLE REPLACEMENT | 830 - St. Catharines | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
644535 | PEIR 14 PORT AUTH - HAM - NS - 3PH - 600A | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Frigotto, Rodrigo | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 19-May-22
644556 | 2023 POLE REPLACEMENT- CHESLEY, ANNABELLE – WEST 5TH | 820 - Nebo | 150335 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 19-Dec-22 | 27 |  | 430088.19 | 152854.41 | 430088.19 | 430088.19 | Koeppe, Jeffrey |  | 02-Oct-23 | 04-Oct-23 | 26-Jun-23 | 19-Jun-23 |  |  |  |  | 0
644638 | 158 JAMES STREET SOUTH - SERVICE RELOCATION | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Wardell, Paul | 25-Mar-22 |  |  | 21600.07 | 21537.8 | 21600.07 | 21600.07 | Brad Carr | Fairway | 29-Apr-22 | 23-Sep-22 | 25-Apr-22 | 22-Jul-22 | 22-Aug-22 | Locates | Locates |  | 0
644643 | 63 HIGHWAY 5 W - WATERDOWN - NEW 600A 647/600V SERVICE | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David | 25-Aug-22 |  |  | 147859.04 | 132383.63 | 147859.04 | 147859.04 | Macdougall, Stephen | Fairway | 19-Oct-22 | 09-Aug-23 | 03-Oct-22 | 16-Oct-22 |  | MC/PUCC Permit | MC/PUCC Permit |  | 0
644692 | 15 CHURCH ST - SUBD RES EDS | 820 - Nebo | 150588 | Active | 84 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark | 16-Jan-23 |  |  | 121535.9 | 113217.15 | 121535.9 | 121535.9 | Macdougall, Stephen | Transpw | 11-Apr-23 | 28-Jul-23 | 27-Feb-23 | 14-Mar-23 |  | Customer | Customer |  | 0
644705 | JOINT USE PERMIT HW2022-011 - ABERDEEN, BRUCE, HILTON, JAMES S - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644704 | JOINT USE PERMIT HW2022-009 - FIFTY, MILLIKIN, HWY 8 - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644712 | 57 CARLISLE ST, ST.CATHARINES - PHASE 2 | 830 - St. Catharines | 150455 | Active | 48 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644719 | 206 KING STREET W - HAM - NS - 3PH - 1200A | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644737 | 1 JAMES ST SOUTH - VAULT LID REPLACEMENT | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2022 | Carr, Brad | Billone, Justin | 28-Feb-22 | 1 | 1 | 11574.47 | 8995.16 | 11574.47 | 11574.47 | Brad Carr | Fairway | 25-Mar-22 | 23-Sep-22 | 14-Mar-22 | 22-Aug-22 | 31-Aug-22 | Contractor | Contractor |  | 0
644738 | JOINT USE PERMIT HW2022-013 - SANATORIUM, W15, MOHAWK W - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644742 | 576 ARVIN AVE / HAM / UP / COS | 820 - Nebo | 150449 | Active | 91 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor | 17-Jan-23 |  |  | 73117.09 | 62268.86 | 73117.09 | 73117.09 | Macdougall, Stephen | Fairway | 14-Mar-23 | 04-Aug-23 | 27-Feb-23 | 16-Mar-23 |  | Locates | Locates |  | 0
644750 | QUEEN VICTORIA DR - VAULT LID | 820 - Nebo | 151065 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 18-Aug-22 | 1 | 1 | 13155.56 | 11174.04 | 13155.56 | 13155.56 | Brad Carr | Fairway | 14-Oct-22 | 26-Jul-23 | 03-Oct-22 | 19-Dec-22 | 19-Dec-22 | Contractor | Contractor |  | 0
644778 | 5 MEDICORUM PLACE / FLA / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 92 | ANALYZE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko | 14-Jun-22 |  |  | 74161.78 | 91847.57 | 74161.78 | 74161.78 | Macdougall, Stephen | Fairway | 28-Jul-22 | 26-Jul-23 | 20-Jul-22 | 09-Jan-23 | 21-Jun-23 | Locates | Locates |  | 0
644820 | JOINT USE PERMIT HW2022-017 - OLD DUNDAS AND LOWER LIONS CLUB - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644836 | 881 ARVIN AVE / HAM / UP00193947 / 750KVA 3PH PAD | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav | 28-Oct-22 |  |  | 105399.05 | 79956.95 | 105399.05 | 105399.05 | Macdougall, Stephen | Fairway | 27-Dec-22 | 04-Aug-23 | 12-Dec-22 | 14-Nov-22 |  |  | Locates |  | 0
644839 | 2022 BELL TRANSFERS WEST - HAMILTON | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644862 | 71 REBECCA ST / HAM / NS / COS | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Karbowiak, Kamil |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644908 | 166 MAIN STREET WEST - HAM - NS - 3PH - C.O 5000KVA | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644909 | 371 ONTARIO ST- 400A 347/600V SERVICE UPGRADE | 830 - St. Catharines | 150455 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644910 | 1636 THIRD AVE- 1200A 347/600V SERVICE UPGRADE | 830 - St. Catharines | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 23-Sep-22
644932 | 101 OSLER DR / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 95 | ANALYZE |  |  | 2023 | Frigotto, Rodrigo | Karbowiak, Kamil | 14-Jun-22 | 1 | 1 | 63319.25 | 61150.67 | 63319.25 | 63319.25 | Roy Owen | Fairway | 11-Oct-22 | 10-Aug-23 | 23-Sep-22 | 02-Sep-22 | 19-Apr-23 | Locates | Locates |  | 0
644952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 3B) | 820 - Nebo | 151303 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 01-Dec-22 |  |  | 1846315.42 | 1767600.8 | 1846315.42 | 1846315.42 | Brad Carr | B&M | 04-Aug-23 | 04-Aug-23 | 12-Dec-22 | 12-Dec-22 |  |  |  |  | 0
644959 | JOINT USE PERMIT HW2022-024 - GREENHILL - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644965 | FELKER FALLS - PHASE 3 FREEHOLD RE-ALIGNMENTS-SUBD RES EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
644999 | IMPERIAL WATERDOWN STATION - SERVICE UPGRADE | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645002 | 367 BARTON ST/ STC / UP00192515 / 500KVA - 400A 347/600V 3PH PAD SERVICE | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 2493.65 | 0 | 0 | 0 | Calvin Arsenault |  |  | 02-May-22 | [6 empty] | 0
645044 | 261 KING ST E - HAM - NS - 3PH - 800A | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Pellerin, Patrick | 30-Mar-23 | 1 | 1 | 88487.42 | 111006.87 | 88487.42 | 88487.42 | Macdougall, Stephen | Fairway | 22-Jun-23 | 04-Aug-23 | 12-Jun-23 | 13-Apr-23 |  |  | Customer |  | 0
645052 | 2022-SC REMOVAL - SC1098 -218 MARTINDALE ROAD / S.CATH | 830 - St. Catharines | 150334 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Rolfe, Eric | 29-Apr-22 | 1 | 1 | 60881.97 | 84746.08 | 60881.97 | 60881.97 | Dan Despres | Fairway | 24-Aug-22 | 26-Jul-23 | 15-Aug-22 | 30-Jan-23 | 05-Feb-23 | Locates | Locates |  | 0
645053 | JOINT USE PERMIT HW2022-033 - GREENHILL AND QUIGLEY - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645066 | HWCDSB - 29 JOHN MURRAY - ST JAMES THE APOSTLE | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Ricci, Leonardo | 19-Jul-23 |  |  | 76154.99 | 3315.27 | 76154.99 | 76154.99 | Macdougall, Stephen | Fairway | 29-Aug-23 | 29-Aug-23 | 21-Aug-23 | [5 empty] | 0
645078 | 150 GLENDALE - SUBD CAP PROJ | 830 - St. Catharines | 151653 | Active | 95 | ANALYZE |  |  | 2023 | Velickovski, Goran | Morris, Mark | 20-Oct-22 |  |  | 48566.68 | 37377.02 | 48566.68 | 48566.68 | Frank Giancola |  | 12-Jan-23 | 31-Jul-23 | 03-Jan-23 | 07-Nov-22 | 22-Dec-22 |  | Customer |  | 0
645082 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 EAST OF DEWITT (PART 3) | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645081 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 EAST OF DEWITT (PART 2) | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645080 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 WEST OF DEWITT (PART 3) | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645079 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 WEST OF DEWITT (PART 2) | 820 - Nebo | 150496 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645101 | 41 REID AVE / HAM / NS00280013 / RELOCATE 3PH PAD | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Laus, Tomislav | 16-Sep-22 |  |  | 36617.26 | 22236.49 | 41968.62 | 36617.26 | Roy Owen |  | 07-Nov-22 | 01-Aug-23 | 31-Oct-22 | 11-Oct-22 | 14-Oct-22 |  |  |  | -5,351.36
645116 | 42 - 54 WATERSHOR DR, SERVICE REMOVAL/RELOCATION FOR SUBDIVISION | 820 - Nebo | 150665 | Active | 93 | ANALYZE | Medium | Res-ICI | 2023 | Jakubowski, Mark | Patel, Ketan | 08-Sep-22 |  |  | 117114.43 | 111572.55 | 117114.43 | 117114.43 | Macdougall, Stephen | Fairway | 26-Oct-22 | 26-Jul-23 | 10-Oct-22 | 09-Nov-22 | 18-May-23 | Locates | Locates |  | 0
645118 | 414 CONCESSION 5 RD E-CONNON NURSARIES INC.(WATERDOWN)/HAM/UP00194117/3PHPAD | 820 - Nebo | 150449 | Active | 94 | ANALYZE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra | 11-Jul-22 |  |  | 97652.29 | 61202.07 | 97652.29 | 97652.29 | Roy Owen | Fairway | 20-Oct-22 | 04-Aug-23 | 03-Oct-22 | 09-Jan-23 | 17-Mar-23 | Customer | Customer |  | 0
645119 | 16 CANNON ST EAST - RELOCATION WORK | 820 - Nebo | 150665 | Active | 40 | ACTIVE | Low | Res-ICI | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | K-Line |  | 20-Jul-20
645128 | 2022 EMERGING OVERHEAD - 16 & 22 CANNON ST EAST - AERIAL TRESPASSING | 820 - Nebo | 151452 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 31-Aug-22 |  |  | 562808.82 | 606653.81 | 318178.92 | 562808.82 | Brad Carr | B&M | 11-Nov-22 | 26-Jul-23 | 24-Oct-22 | 11-Oct-22 | 06-Jun-23 |  | Contractor |  | 244,629.90
645163 | 88 JAMES ST | 830 - St. Catharines | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645222 | JOINT USE PERMIT HW2022-041 - CONCESSION 5 E - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645274 | 450 SHERMAN AVE N - HAM - NS - PRIM - 600A | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Pellerin, Patrick | 31-Mar-23 |  |  | 273134.67 | 270525.93 | 273134.67 | 273134.67 | Macdougall, Stephen |  | 24-May-23 | 14-Aug-23 | 01-May-23 | 01-Jun-23 |  | Customer | Customer |  | 0
645353 | 101 HANNOVER DR | 830 - St. Catharines | 150455 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Bennett, Aaron | 25-Aug-22 |  |  | 86402.63 | 28081.95 | 86402.63 | 86402.63 | Frank Giancola | Wiens | 14-Oct-22 | 03-Aug-23 | 05-Oct-22 | 23-Sep-22 |  | Customer | Customer |  | 0
645366 | 525 WELLAND AVE | 830 - St. Catharines | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645371 | 400 JONES RD N / HAM / NS00200340 / 3PH PAD (CANCELLED) | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Bharosi, Mohindra |  |  |  | 124749.99 | 4240.26 | 124749.99 | 124749.99 | Calvin Arsenault |  |  | 20-Jul-20 | [6 empty] | 0
645400 | AUTO SWITCH - SC1012 - 1 | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE | High | DA | 2022 | Beaudrie, Scott | Billone, Justin | 29-Apr-22 | 1 | 1 | 157290.17 | 163215.43 | 157290.17 | 157290.17 | Tony Ierace |  | 28-Jul-22 | 14-Feb-23 | 11-Jul-22 | 13-Jun-22 | 17-Jun-22 |  |  |  | 0
645445 | JOINT USE PERMIT HW2022-044 - BURLINGTON E AND EMERALD N - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645444 | JOINT USE PERMIT HW2022-043 - HIGHWAY 6 - HAM | 820 - Nebo | 151536 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645449 | SC1008 - REPLACEMENT | 820 - Nebo | 151065 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645484 | 2022 OH SERVICE RELOCATION - 527 GLENDALE AVE, ST. CATHARINES | 830 - St. Catharines | 150496 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 28-Jun-22 |  |  | 36083.36 | 27670.61 | 36083.36 | 36083.36 | Dan Despres | Fairway | 08-Jul-22 | 26-Jul-23 | 29-Jun-22 | 20-Jul-22 | 20-Jul-22 | Locates | Locates |  | 0
645576 | 1831X - LBDS INSTALL | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 30-Jun-22 | 1 | 1 | 42423.87 | 34861.38 | 42423.87 | 42423.87 | Koeppe, Jeffrey |  | 01-Nov-22 | 25-Apr-23 | 24-Oct-22 | 24-Oct-22 | 11-Nov-22 |  | Lines |  | 0
645599 | HESTINGS ROAD POLE RELOCATION | 830 - St. Catharines | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
634032 | JOINT USE PERMIT HW2019-120 - JOHN S, CHARLTON E, ST JOSEPHS, ETC, HAMILTON | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | West | 08-Apr-21 |  |  | 12579.79 | 720.04 | 12579.79 | 12579.79 | Brad Carr |  | 08-Apr-21 | 22-Sep-22 | 08-Apr-21 | 08-Apr-21 | 08-Apr-21 |  |  |  | 0
645613 | 40 WARRINGTON STREET / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko | 14-Mar-23 |  |  | 73060.57 | 28408.13 | 73060.57 | 73060.57 | Macdougall, Stephen | Fairway | 16-Jun-23 | 01-Aug-23 | 12-Jun-23 | 01-May-23 |  |  | Customer |  | 0
645648 | 43 HIGHWAY 5 WEST - BUILDING 1, LOT 3 / DUN / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645647 | 43 HIGHWAY 5 WEST - BUILDING 2, LOT 1A / DUN / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645623 | 1200 UPPER JAMES ST - HAM - UP - 3PH - 800A | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645668 | GARTH, STONECHURCH & GLENVALE - CIVIL WORKS | 820 - Nebo | 150376 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Anderson, Dean | 13-Jun-22 |  |  | 655865.19 | 560551.04 | 641157.43 | 655865.19 | Brad Carr | B&M | 29-Sep-22 | 26-Jul-23 | 11-Jul-22 | 17-Oct-22 | 15-Dec-22 | Locates | Locates |  | 14,707.76
645674 | 585 SKINNER ROAD / FLA / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko | 07-Sep-22 |  |  | 54080.16 | 54932.39 | 54080.16 | 54080.16 | Macdougall, Stephen | Fairway | 30-Nov-22 | 28-Jul-23 | 28-Nov-22 | 14-Nov-22 |  |  | Locates |  | 0
645697 | 390 ONTARIO ST | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2022 | Mandic, Goran | Bennett, Aaron | 26-Aug-22 |  |  | 73171.29 | 58839.15 | 73171.29 | 73171.29 | Frank Giancola | Wiens | 06-Oct-22 | 03-Aug-23 | 26-Sep-22 | 22-Aug-22 | 31-Oct-22 | Customer | Customer |  | 0
645739 | 75 NIAGARA ST | 830 - St. Catharines | 150455 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645743 | 110 WEST 27TH ST / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 95 | ANALYZE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor | 06-Jul-22 |  |  | 67366.26 | 68266.2 | 67366.26 | 67366.26 | Macdougall, Stephen | Fairway | 26-Aug-22 | 28-Jul-23 | 22-Aug-22 | 03-Aug-22 | 28-Mar-23 |  | Customer |  | 0
645770 | 444 SEAMAN ST / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Karbowiak, Kamil |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645772 | 1318 RYMAL RD E PRIVATE LINE TEMP BURIAL | 820 - Nebo | 150665 | Active | 40 | ACTIVE | Low | Comm | 2023 | Jakubowski, Mark | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645792 | POLE RELOCATION - 332 QUEENSTON ST | 830 - St. Catharines | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645791 | GLM 5 UPGRADE FOR ELLIS AVE SUBDIVISION | 830 - St. Catharines | 152381 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645790 | ELLIS AVE SUBDIVISION - POLE RELOCATION OFF PHELPS ST | 830 - St. Catharines | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645848 | NIAGARA ST ANCHOR RELOCATION FOR SIDEWALK, ST. CATHARINES | 830 - St. Catharines | 150665 | Active | 50 | ACTIVE | Low | Infrast | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645864 | 1632 BURLINGTON ST E / HAM / UP00226677 / 3MVA - 3000A 347/600V 3PH CUST SUB | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
645669 | CUSTOMER INTITIATED POLE HEIGHT INCREASE - LAKESHORE RD - ST. CATHARINES | 820 - Nebo | 150653 | Inactive | 99 | COMPLETE | Medium | Infrast | 2022 | Jakubowski, Mark | Celic, Dusan | 15-Jul-22 |  |  | 48477.58 | 0 | 48477.58 | 48477.58 | Frank Giancola |  | 30-Aug-22 | 27-Sep-22 | 22-Aug-22 | 19-Aug-22 | 25-Aug-22 |  |  |  | 0
646349 | 35 SUNNYHURST AVE STONEY CREEK | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 29-Dec-22 |  |  | 0 | 50550.16 |  | 0 | Brad Carr | K-Line | 29-Dec-22 | 13-Mar-23 | 29-Dec-22 | 29-Dec-22 | 29-Dec-22
646372 | 178 NEBO RD - GIANEL HOLDINGS INC../HAM/NS00240837/3PHPAD | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra | 27-Sep-22 |  |  | 68291.44 | 66966.56 | 67974.13 | 68291.44 | Macdougall, Stephen | Fairway | 19-Dec-22 | 01-Aug-23 | 28-Nov-22 | 16-Jan-23 |  | Locates | Locates |  | 317.31
646555 | OH TRESPASS 22 JOHN STREET NORTH | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646569 | 600 FERGUSON AVE N PIER 10 - HAM - UP - 400A 347/600V | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Frigotto, Rodrigo | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646570 | 18 KING STREET EAST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646611 | 2022 TX RENEWAL - POLE TRAN P7676 | 820 - Nebo | 150336 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646640 | SC1092 - REMOVAL_TX INSTALL | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646647 | 63 DITTON DR / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 95 | ANALYZE |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David | 29-Nov-22 | 1 | 1 | 39517.55 | 31894.89 | 39517.55 | 39517.55 | Roy Owen |  | 31-Jan-23 | 28-Jul-23 | 30-Jan-23 | 24-Mar-23 | 28-Mar-23 | Customer | Customer |  | 0
646667 | CUSTOMER INITIATED PAD/POLE RELOCATION - CITY OF HAMILTON - JONES ST-STONEYCREEK | 820 - Nebo | 150644 | Active | 45 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646668 | 2023 DA SWITCHES - BATCH 1 - 4 SW | 820 - Nebo | 150334 | Active | 84 | ACTIVE | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 28-Nov-22 | 4 |  | 267307.75 | 87941.68 | 267307.75 | 267307.75 | Koeppe, Jeffrey |  | 06-Apr-23 | 08-Sep-23 | 27-Feb-23 | 13-Mar-23 |  | Materials | Materials |  | 0
646669 | 95 LAKEPORT RD, ST. CATHARINES - POLE RELOCATION | 830 - St. Catharines | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646800 | PRESTIGE DRIVE - DIRECTIONAL BORE | 820 - Nebo | 151452 | Active | 93 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 29-Jul-22 |  |  | 36216.26 | 36581.99 | 36216.26 | 36216.26 | Roy Owen | Fairway | 03-Oct-22 | 27-Jul-23 | 19-Sep-22 | 27-Feb-23 | 21-Apr-23 | Locates | Locates |  | 0
646869 | CUSTOMER INITIATED POLE & ANCHOR REMOVAL - MAIN ST AND DUNDURN ST - CITY OF HAM. | 820 - Nebo | 150644 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646861 | 2023 POLE REPLACEMENT EAST 34TH STREET | 820 - Nebo | 150335 | Active | 92 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 12-Dec-22 | 6 | 6 | 163499.22 | 187213.98 | 142933.66 | 163499.22 | Brad Carr | B&M | 29-Dec-22 | 27-Jul-23 | 12-Dec-22 | 12-Dec-22 | 06-Mar-23 |  | Contractor |  | 20,565.56
646842 | 213 KING ST W / HAM / NS / 3PH CUSTOMER-OWNED SUBSTATION | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646898 | 2023 DA SWITCHES - BATCH 3 - 2 SWITCHES | 820 - Nebo | 150334 | Active | 96 | COMPLETE | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 08-Dec-22 | 2 | 2 | 198758.97 | 181343.08 | 198758.97 | 198758.97 | Koeppe, Jeffrey |  | 01-Jun-23 | 27-Jul-23 | 01-May-23 | 03-Apr-23 | 01-Jun-23 |  |  |  | 0
646897 | 2023 - DA SWITCHES - BATCH 2 - 5 SWITCHES | 820 - Nebo | 150334 | Active | 84 | ACTIVE | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 28-Nov-22 | 5 |  | 375043.33 | 317143.09 | 375043.33 | 375043.33 | Koeppe, Jeffrey |  | 11-May-23 | 06-Sep-23 | 20-Mar-23 | 13-Feb-23 |  |  | Control/SCADA |  | 0
646899 | 2023 DA SWITCHES - BATCH 4 - 3 SWITCHES | 820 - Nebo | 150334 | Active | 82 | RELEASED | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 08-Dec-22 | 3 |  | 323657.5 | 3350.89 | 323657.5 | 323657.5 | Koeppe, Jeffrey |  | 26-Sep-23 | 26-Sep-23 | 14-Aug-23 |  |  | Materials | Materials |  | 0
646948 | 206 HILLYARD ST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel | 03-Jan-23 | 1 |  | 67192.85 | 29949.77 | 67192.85 | 67192.85 | Macdougall, Stephen | Fairway | 13-Oct-23 | 13-Oct-23 | 03-Apr-23 | 24-Mar-23 |  |  | Materials |  | 0
646951 | 2023 DA SWITCHES - BATCH 7 - 3 SWITCHES | 820 - Nebo | 150334 | Active | 93 | ANALYZE | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 19-Dec-22 | 3 | 3 | 335606.01 | 293955.52 | 335606.01 | 335606.01 | Koeppe, Jeffrey |  | 14-Aug-23 | 27-Jul-23 | 19-Jun-23 | 19-May-23 | 10-Jul-23 |  |  |  | 0
646950 | 2023 DA SWITCHES SCH - BATCH 6 - 1 SWITCH | 830 - St. Catharines | 150334 | Active | 96 | COMPLETE | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 29-Nov-22 | 1 | 1 | 77817.19 | 62167.12 | 77817.19 | 77817.19 | Dan Despres |  | 31-Mar-23 | 27-Jul-23 | 27-Mar-23 | 23-Jan-23 | 27-Mar-23 |  |  |  | 0
646977 | 350 DOSCO DR / STC / UP00192515 / 1000KVA - 1200A 347/600V 3PH PAD SERVICE | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
646991 | 2023 CABLE INJECTION - MILLEN/BARTON/FRUITLAND | 820 - Nebo | 151300 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 05-Aug-22 |  |  | 334034.77 | 23514.56 | 334034.77 | 334034.77 | Brad Carr | Nvinium | 28-Jul-23 | 27-Jul-23 | 03-Apr-23 | 24-Mar-23 |  |  |  |  | 0
647001 | 2023 DA SWITCHES - BATCH 8 - 3 SWITCHES | 820 - Nebo | 150334 | Active | 82 | RELEASED | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 19-Dec-22 | 3 |  | 268556.95 | 2766 | 268556.95 | 268556.95 | Koeppe, Jeffrey |  | 27-Oct-23 | 27-Oct-23 | 18-Sep-23 |  |  | Materials | Materials |  | 0
647003 | 2023 DA SWITCHES - BATCH 5 - 1 SWITCH | 820 - Nebo | 150334 | Active | 96 | COMPLETE | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 28-Nov-22 | 1 | 1 | 101330.01 | 109932.29 | 101330.01 | 101330.01 | Koeppe, Jeffrey |  | 07-Jun-23 | 27-Jul-23 | 22-May-23 | 05-May-23 | 06-Jun-23 |  |  |  | 0
647002 | 2023 DA SWITCHES - BATCH 9 - 1 SWITCH | 820 - Nebo | 150334 | Active | 82 | RELEASED | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 25-Nov-22 | 1 |  | 75078.25 | 47744.68 | 75078.25 | 75078.25 | Koeppe, Jeffrey |  | 27-Oct-23 | 27-Oct-23 | 16-Oct-23 | [5 empty] | 0
647009 | 294 VINE STREET | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Ricci, Leonardo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647013 | 2023 - STANLEY ST (ST. CATHARINES) REBUILD - 8 | 830 - St. Catharines | 150335 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 15-Nov-22 | 8 | 8 | 134738.99 | 92794.97 | 134738.99 | 134738.99 | Dan Despres |  | 08-May-23 | 27-Jul-23 | 16-Jan-23 | 03-Jan-23 | 03-Feb-23 |  |  |  | 0
647019 | 180 QUEENSTON STREET | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Ricci, Leonardo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647052 | PIER 5,6, & 7 / HAM / NS / PADS | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647066 | 16 CANNON ST EAST - 500KVA CUSTOMER OWNED SUBSTATION | 820 - Nebo | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
635865 | ONTARIO STREET (RR#42) - ROADWAY RE-CONSTRUCTION | 830 - St. Catharines | 150653 | Active | 93 | ANALYZE | Medium | Infrast | 2023 | Jakubowski, Mark | Patel, Ketan | 17-Nov-22 |  |  | 2062225.59 | 2254990.88 | 1988500.55 | 2062225.59 | Brad Carr | K-Line | 09-Jun-23 | 26-Jul-23 | 03-Jan-23 | 09-Jan-23 | 20-Jul-23 | Locates |  |  | 73,725.04
647076 | 2023 - SPOT POLE REPLACEMENTS #1 - 12 POLES | 820 - Nebo | 150335 | Active | 82 | PDG SnR |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 29-Mar-23 | 12 |  | 223447.61 | 6694.08 | 223447.61 | 223447.61 | Koeppe, Jeffrey |  | 27-Nov-23 | 27-Nov-23 | 02-Oct-23 | [5 empty] | 0
647153 | ANIMALS GUARDS - WEST RECLOSERS | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647155 | CENTRAL VOLTAGE CONVERSION FUSING | 820 - Nebo | 150828 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Wardell, Paul | 27-Oct-22 |  |  | 57231.61 | 60434.85 | 36028.68 | 57231.61 | Brad Carr | K-Line | 09-Dec-22 | 27-Jul-23 | 01-Dec-22 | 14-Nov-22 | 01-Dec-22 |  |  |  | 21,202.93
647157 | CUSTOMER INTITIATED SERVICE RELOCATION / ANCHOR INSTALL - STONECHURC RD W - HAM | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE | Low | Res-ICI | 2022 | Jakubowski, Mark | Celic, Dusan | 21-Jul-22 |  |  | 9756.56 | 4467.58 | 9756.56 | 9756.56 | Koeppe, Jeffrey |  | 27-Sep-22 | 08-Feb-23 | 26-Sep-22 | 27-Oct-22 | 27-Oct-22 | Contractor | Contractor |  | 0
647166 | VINE STREET MINI-REBUILD (BUNTING FEEDER) - 30 | 830 - St. Catharines | 150335 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 30-Nov-22 | 30 |  | 738403.36 | 679079.63 | 738403.36 | 738403.36 | Dan Despres | Fairway | 21-Jun-23 | 26-Sep-23 | 20-Feb-23 | 06-Feb-23 |  | Control/SCADA | Control/SCADA |  | 0
647173 | 2023 - SWITCH RENEWAL - BATCH 4 (ST. CATHARINES) | 830 - St. Catharines | 150337 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 15-Nov-22 | 1 | 1 | 26681.8 | 24199.16 | 26681.8 | 26681.8 | Dan Despres |  | 23-Mar-23 | 27-Jul-23 | 20-Mar-23 | 09-Jan-23 | 10-Jan-23 |  |  |  | 0
647171 | 2023 - SWITCH RENEWAL - BATCH 3 (DUNDAS) | 820 - Nebo | 150337 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647170 | 2023 - SWITCH RENEWAL - BATCH 2 (STONEY CREEK) | 820 - Nebo | 150337 | Active | 92 | ANALYZE | High | Switch | 2023 | Beaudrie, Scott | Karan, Andjelo | 15-Nov-22 | 2 | 2 | 137540.04 | 152097.24 | 137540.04 | 137540.04 | Koeppe, Jeffrey |  | 20-Jul-23 | 27-Jul-23 | 12-Jun-23 | 17-May-23 | 14-Jul-23 |  | Locates |  | 0
647168 | 2023 - SWITCH RENEWAL - BATCH 1 (HAMILTON) - 4 | 820 - Nebo | 150337 | Active | 95 | COMPLETE | High | Switch | 2023 | Beaudrie, Scott | Karan, Andjelo | 15-Nov-22 | 4 | 4 | 282388.1 | 268979.35 | 282388.1 | 282388.1 | Koeppe, Jeffrey |  | 17-Apr-23 | 27-Jul-23 | 06-Mar-23 | 14-Feb-23 | 11-May-23 | Control/SCADA | Locates |  | 0
647174 | 600 JAMES ST N / HAM / NS00226098 / 3PH CUSTOMER-OWNED STATION | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647203 | 318 ONTARIO ST PMG REPLACEMENT - BATCH 2 - 1 PMH | 830 - St. Catharines | 150334 | Active | 96 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 31-Aug-22 | 1 | 1 | 82932.88 | 158142.29 | 82932.88 | 82932.88 | Frank Giancola | Fairway | 26-Oct-22 | 27-Jul-23 | 10-Oct-22 | 20-Sep-22 | 28-Oct-22 |  | Contractor |  | 0
647212 | 2022 OVERHEAD POLE REPLACEMENT - STRATHEARN N/O BURLINGTON | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647218 | 2022 OVERHEAD POLE REPLACEMENT - OTTAWA ST 1-N OF BURLINGTON | 820 - Nebo | 150496 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647287 | 22 AUGUSUTA ST POLE RELCOATION WORK | 820 - Nebo | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647313 | 2022 EMERGING- 19 NORTHWOOD DRIVE | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Billone, Justin | 27-Oct-22 |  |  | 12791.72 | 13180.74 | 12791.72 | 12791.72 | Frank Giancola |  | 22-Nov-22 | 15-Feb-23 | 21-Nov-22 | 08-Nov-22 | 18-Nov-22 |  |  |  | 0
647315 | 2022 EMERGING - 610 READ ROAD (ST. CATHARINES) | 830 - St. Catharines | 150828 | Active | 93 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Karan, Andjelo | 10-Jan-23 |  |  | 62797 | 60138.5 | 62797 | 62797 | Frank Giancola | GUCI | 21-Feb-23 | 27-Jul-23 | 13-Feb-23 | 03-Mar-23 | 09-Mar-23 | Materials | Materials |  | 0
647351 | 2022 BELL TRANSFERS - ELIZABETH PLACE | 820 - Nebo | 150496 | Active | 93 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 31-Aug-22 |  |  | 33916.63 | 35607.09 | 21153.95 | 33916.63 | Brad Carr | K-Line | 23-Sep-22 | 27-Jul-23 | 19-Sep-22 | 15-May-23 | 18-May-23 | N/A | N/A |  | 12,762.68
647357 | MONTGOMERY DRIVE - MINI REBUILD 2023 | 820 - Nebo | 150335 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean | 15-Nov-22 | 23 |  | 663825.82 | 169789.86 | 663098.19 | 663825.82 | Brad Carr | K-Line | 28-Sep-23 | 28-Sep-23 | 19-Jun-23 | 19-Jun-23 |  |  |  |  | 727.63
647390 | 29 NORWICH ROAD - DIRECTIONAL BORE | 820 - Nebo | 151452 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647393 | 163 JACKSON ST W / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647406 | 500 UPPER WELLINGTON ST / HAM / NS00227504 / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647432 | CUSTOMER INITIATED POLE RELOCATION - ST.MARKS CENTRE - HUNTER ST W & BAY ST S | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE | Low | Res-ICI | 2022 | Jakubowski, Mark | Celic, Dusan | 19-Aug-22 |  |  | 9280.42 | 11197.91 | 9280.42 | 9280.42 | Koeppe, Jeffrey |  | 29-Sep-22 | 29-Sep-22 | 29-Sep-22 | 03-Oct-22 | 07-Oct-22 | Locates | Locates |  | 0
647433 | 965 ARVIN AVE E / STC / NS00272946 / 2000KVA 3PH PAD SRVC | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647476 | 16 & 22 ROXANNE DR / HAM / NS00252259 / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647557 | 15 GALE CRES POLE RELOCATION - ST. CATHARINES | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Karan, Andjelo | 18-Aug-22 | 1 | 1 | 15062.61 | 7577.7 | 15062.61 | 15062.61 | Dan Despres |  | 31-Aug-22 | 27-Sep-22 | 29-Aug-22 | 14-Sep-22 | 14-Sep-22 | Locates | Locates |  | 0
647563 | 1072 MAIN ST E / HAM / UP00257860 / 150KVA 120/208 3PH PAD SRVC | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Ogilvie, Jordan | 07-Mar-23 | 1 | 0 | 123326.15 | 52916.08 | 120283.7 | 123326.15 | Macdougall, Stephen | Fairway | 09-Jun-23 | 04-Aug-23 | 29-May-23 | 09-May-23 |  | Materials | Materials |  | 3,042.45
647572 | 257 KING WILLIAM ST - NEW 800A 120/208V SERVICE | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David | 14-Jun-23 |  |  | 73585.47 | 7972.72 | 73585.47 | 73585.47 | Macdougall, Stephen | Fairway | 02-Aug-23 | 08-Aug-23 | 24-Jul-23 | [5 empty] | 0
647573 | 1 JARVIS ST - NEW 2000A 347/600V SERVICE | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David |  |  |  | 112642.06 | 3709.2 | 112642.06 | 112642.06 | Calvin Arsenault |  |  | 03-Oct-23 | [6 empty] | 0
647578 | 1379 UPPER JAMES ST / HAM / UP00275947 / 3PH PAD | 820 - Nebo | 150449 | Active | 95 | ANALYZE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra | 08-Nov-22 |  |  | 86224.96 | 58348.04 | 86224.96 | 86224.96 | Roy Owen | Fairway | 30-Jan-23 | 17-Aug-23 | 09-Jan-23 | 09-Jan-23 | 21-Mar-23 |  | Customer |  | 0
647582 | 318 ONTARIO ST PMH REPLACEMENT - BATCH 3 - 2 PMH | 830 - St. Catharines | 151083 | Active | 82 | RELEASED |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 27-Feb-23 | 2 |  | 455542.19 | 8517.59 | 455542.19 | 455542.19 | Brad Carr | B&M | 30-Nov-23 | 30-Nov-23 | 02-Oct-23 | [5 empty] | 0
647585 | 221 JOHN ST S - NEW 2000A 347/600V SERVICE | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647586 | ROAD AUTHROITY - HIGHWAY 5 & HIGHWAY 6 RELOCATIONS - WATERDOWN | 820 - Nebo | 150644 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647593 | 1962-1976 RYMAL RD.E (RYMAL RD.E & FLETCHER RD) - NEW 1000A 347/600V SERVICE | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647622 | CUSTOMER INITIATED ANCHOR RELOCATE / SECONDARY BUS REMOVAL - FIFTY RD - WINONA | 820 - Nebo | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647624 | 205 ST DAVID'S RD - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 82 | RELEASED |  |  | 2023 | Velickovski, Goran | Chu, Zeyu (Andrew) | 26-May-23 |  |  | 49893.61 | 9869 | 49893.61 | 49893.61 | Frank Giancola |  | 14-Jul-23 | 02-Aug-23 | 10-Jul-23 |  |  | Customer | Customer |  | 0
647653 | 5 EMMETT RD | 830 - St. Catharines | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647694 | 40 BENFIELD DRIVE / SCH / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Mandic, Goran | Djuric, Zdravko | 12-Apr-23 |  |  | 118308.96 | 20808.26 | 118308.96 | 118308.96 | Frank Giancola | Fairway | 13-Nov-23 | 13-Nov-23 | 06-Nov-23 |  |  | Locates |  |  | 0
647701 | MINI POLE REBUILD - SAN FERNANDO DR - HAM - 8 | 820 - Nebo | 150335 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David | 20-Dec-22 | 8 |  | 299498.41 | 165731.05 | 299498.41 | 299498.41 | Koeppe, Jeffrey |  | 22-Jun-23 | 08-Sep-23 | 17-Apr-23 | 03-Apr-23 |  |  | Design |  | 0
647700 | 2022 EMERGING O/H- LATERAL FUSING | 820 - Nebo | 150828 | Active | HO | RELEASED |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David | 28-Nov-22 |  |  | 126974.46 | 44363.1 | 126974.46 | 126974.46 | Brad Carr | K-Line | 17-Feb-23 | 27-Jul-23 | 06-Feb-23 |  |  | Materials | Materials |  | 0
647709 | CUSTOMER INITIATED TEMPORARY LINE - DUNDAS ST E - WATERDOWN | 820 - Nebo | 150665 | Active | 40 | ACTIVE | Low | Res-ICI | 2023 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647711 | CUSTOMER INTITIATED POLE HEIGHT INCREASE - LAKESHORE RD - ST. CATHARINES | 830 - St. Catharines | 150653 | Inactive | 99 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Celic, Dusan | 06-Sep-22 |  |  | 48357.56 | 13743.03 | 48357.56 | 48357.56 | Frank Giancola |  | 06-Sep-22 | 13-Sep-22 | 06-Sep-22 | 06-Sep-22 | 06-Sep-22 |  |  |  | 0
647716 | 2023 CABLE INJECTION - BUNTING/CARLTON/CUSHMAN | 830 - St. Catharines | 150496 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 29-Nov-22 |  |  | 326657.57 | 23075.2 | 326657.57 | 326657.57 | Brad Carr | Nvinium | 23-May-23 | 27-Jul-23 | 01-Mar-23 | 24-Mar-23 |  | Contractor | Contractor |  | 0
647725 | CUSTOMER INITIATED POLE HEIGHT INCREASE - POLE REPLACEMENT - FIFTH ST LOUTH-STC | 830 - St. Catharines | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647726 | JC37 - REPLACEMENT | 820 - Nebo | 151452 | Active | 93 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 10-Feb-23 | 1 | 1 | 67273.51 | 54007.06 | 67273.51 | 67273.51 | Brad Carr | Fairway | 15-Mar-23 | 27-Jul-23 | 06-Mar-23 | 03-May-23 | 19-Jun-23 | MC/PUCC Permit | MC/PUCC Permit |  | 0
647753 | 41 WILSON ST HAMILTON - CUSTOMER-OWNED STATION-NEW CUSTOMER | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647772 | 18 HAYES AVE / HAM / NS00252226 / 3PH PAD | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647830 | 2023 DA SWITCHES - BATCH 12- 1 SW | 820 - Nebo | 150334 | Active | 82 | PDG SnR | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 28-Nov-22 | 1 |  | 96848.93 | 0 | 96848.93 | 96848.93 | Koeppe, Jeffrey |  | 01-Nov-23 | 01-Nov-23 | 23-Oct-23 | [5 empty] | 0
647829 | 2023 DA SWITCHES - BATCH 11 -1 SWITCH | 820 - Nebo | 150334 | Active | 82 | PDG SnR | High | DA | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 25-Nov-22 | 1 |  | 137218.58 | 0 | 137218.58 | 137218.58 | Koeppe, Jeffrey |  | 26-Oct-23 | 26-Oct-23 | 02-Oct-23 |  |  | Materials | Materials |  | 0
647828 | 2023 DA SWITCHES - BATCH 10- 1 SW | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647835 | 1276 UPPER JAMES ST / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | HO | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor | 20-Jan-23 | 1 | 1 | 74884.54 | 9125.17 | 74884.54 | 74884.54 | Macdougall, Stephen | Fairway | 17-Mar-23 | 02-Aug-23 | 06-Mar-23 |  |  | Customer | Customer |  | 0
647839 | HALRT - MAPLE AVE | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 16-Sep-22
647837 | MINI POLE REBUILD - ARTHUR ST - ST.KITTS | 830 - St. Catharines | 150335 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David | 21-Dec-22 | 14 | 14 | 274589.79 | 282698.75 | 274589.79 | 274589.79 | Dan Despres |  | 22-Jun-23 | 27-Jul-23 | 03-Apr-23 | 15-Feb-23 | 12-Apr-23 |  |  |  | 0
647836 | HALRT - MCMASTER TO 403 | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647843 | HALRT - GAGE TO EASTBEND | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647842 | HALRT - DUNSMURE | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647844 | HALRT - ROSEWOOD | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647857 | 175 LAWRENCE ROAD / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647871 | HALRT - ROSEWOOD WATERMAIN EARLY WORKS | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647880 | 55 LEAVITT BLVD / HAM / NS / 3PH | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Biasutti, Stephen | 13-Jul-23 |  |  | 62436.07 | 12395.36 | 62436.07 | 62436.07 | Macdougall, Stephen |  | 25-Aug-23 | 25-Aug-23 | 21-Aug-23 | [5 empty] | 0
647904 | 1 BALFOUR DR / HAM / UP00253391 / 400 AMP UPGRADE | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Ogilvie, Jordan | 09-May-23 |  |  | 72678.27 | 9973.04 | 72678.27 | 72678.27 | Macdougall, Stephen | Fairway | 22-Jun-23 | 21-Aug-23 | 12-Jun-23 |  |  | Customer | Customer |  | 0
647962 | 403 MCNEILLY RD / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
647988 | 54 LAKESHORE DR - SUBD RES EDS | 820 - Nebo | 150588 | Active | 82 | RELEASED |  |  | 2023 | Velickovski, Goran | Chu, Zeyu (Andrew) | 17-May-23 |  |  | 9744.62 | 10909.72 | 9744.62 | 9744.62 | Macdougall, Stephen |  | 28-Jul-23 | 28-Jul-23 | 28-Jul-23 | [5 empty] | 0
648072 | SC4 - SW GEAR INSTALL - HAMILTON | 820 - Nebo | 151083 | Active | 84 | ACTIVE | High | SwGear | 2023 | Beaudrie, Scott | Billone, Justin | 19-Dec-22 | 1 |  | 184490.26 | 160925.63 | 184490.26 | 184490.26 | Tony Ierace | Fairway | 30-May-23 | 14-Aug-23 | 08-May-23 | 01-Jun-23 |  | Contractor | Control/SCADA |  | 0
648079 | SC33 - SW GEAR INSTALL - HAMILTON | 820 - Nebo | 151083 | Active | 93 | ANALYZE | High | SwGear | 2023 | Beaudrie, Scott | Billone, Justin | 19-Dec-22 | 1 | 1 | 256376.31 | 146372.2 | 256376.31 | 256376.31 | Tony Ierace |  | 24-Jul-23 | 27-Jul-23 | 10-Jul-23 | 21-Jun-23 | 10-Jul-23 |  |  |  | 0
648114 | ROAD AUTHORITY - POLE RELOCATION - CITY OF HAMILTON MUT INSTALL - COOTES DR | 820 - Nebo | 150644 | Active | 93 | ANALYZE | Medium | Infrast | 2023 | Jakubowski, Mark | Karan, Andjelo | 08-May-23 |  |  | 11493.84 | 6536.11 | 11493.84 | 11493.84 | Koeppe, Jeffrey |  | 04-Jul-23 | 27-Jul-23 | 03-Jul-23 | 04-Jul-23 | 07-Jul-23 |  | Lines |  | 0
648168 | SHELDON GATE | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Ricci, Leonardo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648177 | SC760 - NEW SWITCH GEAR | 820 - Nebo | 150334 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 06-Dec-22 | 1 | 1 | 161855.06 | 105311.86 | 161855.06 | 161855.06 | Tony Ierace |  | 30-Jan-23 | 27-Jul-23 | 05-Dec-22 | 23-Jan-23 | 27-Jan-23 | Customer | Customer |  | 0
648182 | 179 CATHARINE ST N / HAM / NS00298383 / 500 KVA 120/208 3PH PAD SRVC | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Ogilvie, Jordan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648189 | 2022 EMERGENCY POLE REPLACEMENTS | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648200 | 18 KEEFER ROAD / SCH / UP/ 3PH PAD | 830 - St. Catharines | 150449 | Inactive | 99 | CANCELLED |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 03-May-23
648205 | 440 VICTORIA AVE N / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel | 01-Mar-23 |  |  | 74623.43 | 2654.28 | 74623.43 | 74623.43 | Macdougall, Stephen |  | 05-Oct-23 | 05-Oct-23 | 02-Oct-23 | [5 empty] | 0
648237 | 2023 - O/H AUTOMATION - LAKE TS | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648236 | 2023 - O/H AUTOMATION - ELGIN TS/WINONA TS | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648235 | 2023 - O/H AUTOMATION - BUNTING TS | 830 - St. Catharines | 150334 | Active | 84 | ACTIVE | High | DA | 2023 | Beaudrie, Scott | Oosterlinck, David | 30-Jan-23 | 5 |  | 372742.41 | 211087.23 | 371991.46 | 372742.41 | Dan Despres |  | 08-Sep-23 | 06-Oct-23 | 26-Jun-23 | 10-Apr-23 |  |  | Materials |  | 750.95
648269 | 741 RYMAL ROAD E / HAM / NS00294770 / 300 KVA 120/208 3PH PAD SERVICE | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Ogilvie, Jordan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648308 | 2023-TX RENEWAL ST CATHARINES (TX-P9766_02) | 830 - St. Catharines | 150336 | Active | 82 | PDG SnR |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard | 27-Apr-23 | 1 |  | 120853.04 | 7137.49 | 120853.04 | 120853.04 | Dan Despres |  | 24-Oct-23 | 24-Oct-23 | 16-Oct-23 | [5 empty] | 0
648312 | 41 WILSON - TEMP / HAM / NS / 3PH PAD (SB#NS00229681) | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Gonzales, Leonard | 13-Jul-23 |  |  | 110359.31 | 3973.84 | 110359.31 | 110359.31 | Macdougall, Stephen |  | 12-Sep-23 | 12-Sep-23 | 21-Aug-23 | [5 empty] | 0
648316 | 347 ARVIN AVE / COLONIAL PILLARS (UP00211288) | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648317 | INDIVIDUAL POLE REPLACEMENTS (HAM) | 820 - Nebo | 150335 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648329 | LAVITA ESTATTES - SUBSD RES EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648333 | 1557 RYMAL RD E - HAM / NS | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2022 | Frigotto, Rodrigo | Sabbah, Amir |  | 1 |  | 37196.76 | 34906.98 | 37196.76 | 37196.76 | Roy Owen |  | 28-Dec-22 | 03-Aug-23 | 19-Dec-22 | 07-Dec-22 | 07-Dec-22 |  |  |  | 0
648332 | CHAMBER LID REPLACEMENTS- 2023- PHASE 1 | 820 - Nebo | 151065 | Active | 93 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul | 19-Dec-22 | 1 | 1 | 254655.1 | 232208.94 | 254655.1 | 254655.1 | Brad Carr | B&M | 05-May-23 | 27-Jul-23 | 03-Apr-23 | 03-Apr-23 | 02-May-23 |  |  |  | 0
648339 | 315 EAST 37TH ST / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor | 20-Apr-23 | 1 |  | 98965.8 | 7987.05 | 98965.8 | 98965.8 | Macdougall, Stephen | Fairway | 14-Jul-23 | 10-Aug-23 | 03-Jul-23 |  |  | Customer | Customer |  | 0
648338 | CUSTOMER INITIATED SYSTEM EXPANSION – 500 UPPER WELLINGTON STREET | 820 - Nebo | 152381 | Active | 10 | ACTIVE | Medium | Res-ICI | 2023 | Jakubowski, Mark | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | K-Line |  | 20-Jul-20
648340 | 505 HIGHLAND ROAD WEST - TEMP / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 92 | ANALYZE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko | 06-Dec-22 | 1 | 1 | 49515.02 | 86375 | 49515.02 | 49515.02 | Macdougall, Stephen | Fairway | 26-Jan-23 | 27-Jul-23 | 23-Jan-23 | 28-Dec-22 | 01-Jun-23 |  | Customer |  | 0
648354 | 298 HIGHWAY 8 / HAM / UP00287145 / 3PH PAD | 820 - Nebo | 150449 | Active | 82 | RELEASED |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel | 20-Mar-23 | 1 |  | 121644.53 | 4876.81 | 121644.53 | 121644.53 | Macdougall, Stephen | Fairway | 31-Jul-23 | 31-Jul-23 | 04-Jul-23 |  |  | Contractor | Contractor |  | 0
648357 | HALRT - ONXPRESS | 820 - Nebo | 150593 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648379 | 2023-TX RENEWAL ST CATHARINES (TX-P9371_02) | 830 - St. Catharines | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648378 | 2023-TX RENEWAL ST CATHARINES-WOODROW ST AND STONEGATE DR (1-UG, 2-OH) | 830 - St. Catharines | 150336 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard | 08-May-23 | 3 |  | 160733.89 | 62386.24 | 160733.89 | 160733.89 | Dan Despres | Fairway | 18-Jul-23 | 14-Aug-23 | 03-Jul-23 | 02-Jun-23 |  |  | Contractor |  | 0
648387 | 16 ROXANNE DR / HAM / NS00314645 / 3PH PAD | 820 - Nebo | 150449 | Active | 95 | ANALYZE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel | 03-Feb-23 |  |  | 39935.92 | 36300.99 | 39935.92 | 39935.92 | Roy Owen | Transpw | 15-Mar-23 | 27-Jul-23 | 13-Mar-23 | 03-Mar-23 | 11-Apr-23 |  | Contractor |  | 0
648477 | 100-110 EASTPORT BLVD - HOPA - ALECTRA UTILITIES - HAM CLR2021-322 | 820 - Nebo | 150665 | Active | 93 | COMPLETE |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick | 02-Mar-23 |  |  | 69559.62 | 51225.29 | 69559.62 | 69559.62 | Tony Ierace |  | 12-Apr-23 | 27-Jul-23 | 03-Apr-23 | 27-Mar-23 | 21-Apr-23 |  | Control/SCADA |  | 0
648488 | EXPANSION - 163 JACKSON ST W. HAM. | 820 - Nebo | 152381 | Active | 40 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648492 | 163 JACKSON ST W / HAM / NS / 3PH TEMP | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor | 24-Feb-23 |  |  | 59174.14 | 39555.39 | 59174.14 | 59174.14 | Macdougall, Stephen |  | 02-Jun-23 | 01-Aug-23 | 29-May-23 | 22-Mar-23 |  |  | Materials |  | 0
648503 | LAVITA ESTATES - THE ENCLAVE | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Ricci, Leonardo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648502 | LAVITA ESTATES - FREEHOLDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Ricci, Leonardo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648512 | QEW & PINELANDS & DEWITT HWY CROSSINGS | 820 - Nebo | 150335 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | K-Line |  | 20-Jul-20
648644 | EXPANSION 221 JOHN ST SOUTH, HAM | 820 - Nebo | 152381 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648653 | EXPANSION 41 WILSON ST., HAM | 820 - Nebo | 152381 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648655 | PARK ST VAULT LID REPAIRS (CITY OF HAMILTON) | 820 - Nebo | 150644 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648721 | 2023 - TX RENEWAL - SCH BATCH 1 - 4TX'S | 830 - St. Catharines | 150336 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard | 27-Mar-23 | 4 |  | 103778.65 | 69735.42 | 103778.65 | 103778.65 | Dan Despres |  | 12-Oct-23 | 12-Oct-23 | 25-Sep-23 | 17-Jul-23 |  |  |  |  | 0
648723 | 2023 - TX RENEWAL - BELAND AVENUE SOUTH (TX-27468_01) | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648722 | 2023 - TX RENEWAL - HAM BATCH 1 - 5TX'S & 2 POLES | 820 - Nebo | 150336 | Active | 82 | PDG SnR |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard | 24-May-23 | 5 |  | 120074.86 | 5324.84 | 120074.86 | 120074.86 | Koeppe, Jeffrey |  | 15-Dec-23 | 15-Dec-23 | 27-Nov-23 | [5 empty] | 0
648724 | 2023 - TX RENEWAL - HAM BATCH 2 - 6TX & 3 POLES | 820 - Nebo | 150336 | Active | 82 | Upload Completed |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  | 6 |  | 155461.28 | 6093.04 | 155461.28 | 155461.28 | Calvin Arsenault |  |  | 27-Jul-23 | [6 empty] | 0
648728 | 2023 - TX RENEWAL - HAM BATCH 3 - 7TX'S | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648729 | 2023 - TX RENEWAL - SCH BATCH 2 - 4TX'S | 830 - St. Catharines | 150336 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard | 08-May-23 | 4 |  | 130223.96 | 47775.47 | 130223.96 | 130223.96 | Dan Despres |  | 06-Oct-23 | 06-Oct-23 | 18-Sep-23 | 28-Jun-23 |  |  |  |  | 0
648733 | 2023 -TX RENEWAL - HAM BATCH 4 - 3TX'S | 820 - Nebo | 150336 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  | 3 |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648753 | 100 CENTENNIAL PARKWAY SOUTH / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko | 14-Feb-23 |  |  | 106739.46 | 14809.22 | 106739.46 | 106739.46 | Macdougall, Stephen | Fairway | 19-May-23 | 10-Aug-23 | 08-May-23 | 02-Jun-23 |  | Customer | Customer |  | 0
648761 | 2023 - TX RENEWAL - HAM BATCH 5 - 5TX & 4 POLES | 820 - Nebo | 150336 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  | 5 |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648765 | 588 BARTON STREET E (HALL LIGHTS)/HAM/UP00303324/3PHPAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648766 | 41 STUART ST/ HAM / NS00319486 / 2000KVA 3PH CUST SUB | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648771 | 2023 - TX RENEWAL - HAM BATCH 6 - 5TX'S | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648773 | 206 KING ST W / HAM / NS00309097 / 400A TEMP | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2023 | Frigotto, Rodrigo | Ogilvie, Jordan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 05-Jul-23
648774 | 2023 - TX RENEWAL - SCH BATCH 3 - 4TX'S | 830 - St. Catharines | 150336 | Active | 82 | RELEASED |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard | 08-May-23 | 4 |  | 154226.54 | 8221.46 | 154226.54 | 154226.54 | Dan Despres |  | 17-Oct-23 | 17-Oct-23 | 18-Sep-23 | [5 empty] | 0
648777 | 2023 - TX RENEWAL - HAM BATCH 7 - 6TX'S | 820 - Nebo | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648785 | 82 FERGUSON AVE N / HAM / NS00287202 / 200A 347/600 | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2022 | Frigotto, Rodrigo | Ogilvie, Jordan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648819 | 743 UPPER JAMES ST / HAM / NS00314315 / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648826 | 2023 - TX RENEWAL - HAM BATCH 8 - 6TX'S | 820 - Nebo | 150336 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648825 | 2023 - TX RENEWAL - SCH BATCH 4 - 2TX'S | 830 - St. Catharines | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648833 | 2023-TX RENEWAL HAM (TX-30663_01) | 820 - Nebo | 150336 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648887 | HWY 403 UNDERGROUND CROSSING - MIP | 820 - Nebo | 151584 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648889 | 53 GLENGARRY RD(SCH) - SEC CABLE REPLACEMENT | 820 - Nebo | 151452 | Active | 93 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David | 24-Jan-23 |  |  | 15160.82 | 10243.89 | 15160.82 | 15160.82 | Frank Giancola | GUCI | 24-Feb-23 | 28-Jul-23 | 20-Feb-23 | 06-Feb-23 | 06-Feb-23 |  |  |  | 0
648986 | 400 KING ST E / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649052 | HALRT - SECTION C | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649054 | HALRT - SECTION E | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649053 | HALRT - SECTION D | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649058 | 455 WELLAND AVE - SC - NS | 820 - Nebo | 150455 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649127 | 475 EASTPORT BLVD - HAM - PIER 25 | 820 - Nebo | 152381 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649217 | 332 ONTARIO STREET / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 82 | RELEASED |  |  | 2023 | Mandic, Goran | Djuric, Zdravko | 14-Apr-23 |  |  | 58370.57 | 2664.24 | 58370.57 | 58370.57 | Frank Giancola | Fairway | 10-Nov-23 | 10-Nov-23 | 06-Nov-23 |  |  | Contractor | Contractor |  | 0
649247 | LAKEPOINTE EXECUTIVE COLLECTION - SUBD RES EDS | 820 - Nebo | 150588 | Active | 40 | ACTIVE |  |  | 2023 | Velickovski, Goran | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649275 | 2023 EMERGING - BELL TRANSFER 50 LAKE AVE DR | 820 - Nebo | 150828 | Active | 94 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 17-Feb-23 |  |  | 7956.48 | 10153.67 | 7956.48 | 7956.48 | Brad Carr | K-Line | 30-Jun-23 | 27-Jul-23 | 19-Jun-23 | 18-May-23 | 18-May-23 | MC/PUCC Permit | MC/PUCC Permit |  | 0
649319 | 306 PARKSIDE DR / FLAM / UP00326157 / 750KVA 347/600 3PH PAD SERVICE | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Ogilvie, Jordan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649322 | SAINT ANDREWS DR - BACKYARD PRI. U/G CABLE REPLACEMENT | 820 - Nebo | 151452 | Active | 82 | RELEASED |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David | 11-May-23 |  |  | 46939.24 | 7696.6 | 46939.24 | 46939.24 | Koeppe, Jeffrey |  | 18-Jul-23 | 11-Aug-23 | 04-Jul-23 |  |  | Lines | Lines |  | 0
649323 | CABLE REPLACEMENT-LAKE-LINWELL-GENEVA PH2 | 830 - St. Catharines | 150496 | Active | 84 | RELEASED |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David | 28-Apr-23 |  |  | 1131720.57 | 22470.28 | 1131720.57 | 1131720.57 | Brad Carr | B&M | 30-Nov-23 | 30-Nov-23 | 05-Jun-23 | 17-Jul-23 |  | MC/PUCC Permit | MC/PUCC Permit |  | 0
649329 | 77 JAMES STREET NORTH - CABLE CHAMBER INSTALLATION | 820 - Nebo | 150449 | Active | 40 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649366 | 2023 SPOT POLES - BATCH 6 - 5 POLES | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 7303.35 | 0 | 0 | Calvin Arsenault |  |  | 26-May-23 | [6 empty] | 0
649365 | 2023 - SPOT POLES BATCH 5 - 6 POLES | 820 - Nebo | 150335 | Active | 82 | PDG SnR |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 27-Mar-23 | 6 |  | 165459.06 | 9745.47 | 165459.06 | 165459.06 | Koeppe, Jeffrey |  | 27-Nov-23 | 27-Nov-23 | 13-Nov-23 | [5 empty] | 0
649408 | 185 BURKE ST, WATERDOWN - RES SUBD EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Handy, James |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649405 | 90 SKINNER RD, WATERDOWN - RES SUBD EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Handy, James |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649410 | 495 SKINNER RD, WATERDOWN - RES SUBD EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Handy, James |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649431 | 405 MAIN ST W / HAM / NS00248316 / 750KVA 3PH PAD SRVC | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648561 | RELOCATION - DUE TO TRESPASS - CATHARINE ST. S. & KING ST. E. | 820 - Nebo | 151452 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649449 | 2023 SPOT POLES - BATCH 4 - 4 POLES | 820 - Nebo | 150335 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649448 | 2023 SPOT POLES - BATCH 3 - 7 POLES | 820 - Nebo | 150335 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649447 | 2023 EMERGING - BELL TRANSFER 30 BLAND AVE | 820 - Nebo | 150828 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
451119 | MTO CROSSING - MILLEN RD | 820 - Nebo | 150335 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | K-Line
649505 | LIMERIDGE AND KINGFISHER, HAMILTON - RES SUBD EDS | 820 - Nebo | 150588 | Active | 45 | ACTIVE |  |  | 2023 | Velickovski, Goran | Handy, James |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649538 | 2023 EMERGING - EVANS ST POLE REPLACEMENT | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649544 | 40 LIGHTHOUSE ROAD - CO SUBSTATION UPGRADE | 830 - St. Catharines | 150457 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649562 | 2023 TX REPLACEMENT - 22 EXPORT DRIVE | 830 - St. Catharines | 150336 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 28-Apr-23 | 1 |  | 148043.65 | 13794.59 | 148043.65 | 148043.65 | Dan Despres | GUCI | 23-Aug-23 | 23-Aug-23 | 07-Aug-23 | 02-Jun-23 |  |  |  |  | 0
649564 | 32 & 34 ROYAL HENLEY BLVD / SC / NS / 1PH | 830 - St. Catharines | 150449 | Active | 82 | RELEASED |  |  | 2023 | Mandic, Goran | Boivin, Cameron | 18-May-23 |  |  | 31501.25 | 13126.72 | 31501.25 | 31501.25 | Frank Giancola | Fairway | 19-Jun-23 | 27-Jul-23 | 19-Jun-23 |  |  | Customer | Customer |  | 0
649567 | 500 UPPER WELLINGTON ST / HAM / NS00336471 / 3PH POLE MOUNT BANK | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649625 | 1104 FENNELL AVE E - SERVICE UPGRADE/TX REPLACEMENT | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2023 | Frigotto, Rodrigo | Biasutti, Stephen |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649669 | 401 ONTARIO STREET / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 82 | RELEASED |  |  | 2023 | Mandic, Goran | Djuric, Zdravko | 22-Mar-23 | 1 | 1 | 103729.57 | 2779.48 | 103729.57 | 103729.57 | Frank Giancola | Fairway | 15-Sep-23 | 15-Sep-23 | 11-Jul-23 |  |  | Materials |  |  | 0
649686 | 75 STEEL CIRTY CT - AIM RECYCLING - OH TO UG CONVERSION | 820 - Nebo | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649696 | LAS VILLAS (1076 VANSICKLE N) - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649701 | 323 MILLEN RD - REAR YARD REPLACEMENT WORK | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649707 | 705 & 713 RYMAL ROAD E, HAMILTON - RES SUBD EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Handy, James |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649720 | 122 CUSHMAN ROAD / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko | 14-Apr-23 |  |  | 85284.96 | 15430.97 | 85284.96 | 85284.96 | Frank Giancola | Fairway | 06-Jun-23 | 04-Aug-23 | 29-May-23 | 03-May-23 |  |  | Contractor |  | 0
649757 | 7 STUDEBAKER PL - NEW SERVICE REQUEST (440 VICTORIA AVE N) | 820 - Nebo | 150449 | Active | 79 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Biasutti, Stephen |  |  |  | 64794.19 | 0 | 64794.19 | 64794.19 | Calvin Arsenault |  |  | 20-Jul-20 | [6 empty] | 0
649765 | HALRT - TPSS4 EXPANSION | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649813 | 163 JACKSON ST W / HAM / NS / 3PH TEMP 2 | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649837 | OH CONVERSION - MAPLE (KENILWORTH TO WEIR) | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649836 | YORK/OLYMPIC SWITCH REMOVAL | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649835 | ROYAL CONNAUGHT FOUNDATION RELOCATION | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649834 | NS00290928 - 1508, 1550 UPPER JAMES STREET - PADMOUNT TX INSTALLATION | 820 - Nebo |  | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649846 | 24 BROCK ST N / HAM / NS00228730 / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649845 | 239 LAKESHORE ROAD / SCH / NS / 3PH PAD | 830 - St. Catharines | 150455 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649876 | 2360 FIRST STREET LOUTH / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 82 | RELEASED |  |  | 2023 | Mandic, Goran | Djuric, Zdravko | 11-May-23 |  |  | 93699.08 | 1661.39 | 93699.08 | 93699.08 | Frank Giancola | Fairway | 28-Aug-23 | 28-Aug-23 | 01-Aug-23 | [5 empty] | 0
644052 | 95 LAKEPORT ROAD | 830 - St. Catharines | 150449 | Active | 70 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649926 | HOPA - LIGHTHOUSE RELOCATION - 1160 BEACH BLVD | 820 - Nebo | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649938 | 2023 POLE REPLACEMENT - STEEL CITY COURT - 2 POLES | 820 - Nebo | 150335 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649967 | POLE REPLACEMENT - EVANS ST | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649968 | PADMOUNT TX REPLACEMENT - 379 NIAGARA ST | 830 - St. Catharines | 151452 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649975 | 2023 POLE REPLACEMENT - EXPORT AVE - 4 POLES | 830 - St. Catharines | 150335 | Active | 92 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige | 02-May-23 | 4 | 4 | 94404.35 | 54534.23 | 94404.35 | 94404.35 | Dan Despres |  | 09-Aug-23 | 27-Jul-23 | 24-Jul-23 | 02-Jun-23 | 06-Jul-23 |  |  |  | 0
649974 | 2023 POLE REPLACEMENT - CROCKETT ST - 14 POLES | 820 - Nebo | 150335 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650023 | 367 CONCESSION 5 RD E, WATERDOWN - HAM/NS00334996/3PH/PRIMARY METERING | 820 - Nebo | 150449 | Active | 40 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650063 | 425 ARVIN AVE | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650067 | 2023 - TX RENEWAL - 71 FIR AVE- SC (TX-8316_02) | 830 - St. Catharines | 150336 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650069 | 83 LOUTH STREET - SUBDIVISION CONNECTIONS | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Manojlovic, Stefan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650113 | 1865 RYMAL RD E / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650118 | 107 ST. PAUL STREET / SCH / UP / 3PH PAD | 830 - St. Catharines | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650139 | 801 DUNSMURE RD / HAM / UP / 3PH PAD | 820 - Nebo | 150449 | Active | 82 | Upload Completed |  |  | 2023 | Frigotto, Rodrigo | Oosterlinck, David |  |  |  | 34264.46 | 2838.98 | 34264.46 | 34264.46 | Calvin Arsenault |  |  | 27-Jul-23 | [6 empty] | 0
650145 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS - PART 5 | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650163 | SC1040 - SW GEAR REMOVAL | 830 - St. Catharines | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650211 | SC1043 - SW GEAR REMOVAL & TX INSTALL | 830 - St. Catharines | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650214 | SC1059 - SW GEAR REMOVAL & TX INSTALL | 830 - St. Catharines | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650244 | 150 CHATHAM ST - O/H TRASNFORMER U/G | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
648073 | ESTIMATING WO-1(ST.KITTS) - 15 GALE CRES | 830 - St. Catharines | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650327 | 16 MELBOURNE - SUBDIVISION CONNECTIONS | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Manojlovic, Stefan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650331 | MH99 & MH68C - NEW ROOF | 820 - Nebo | 151065 | Active | 82 | RELEASED |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 24-May-23 | 2 |  | 392155.13 | 10958.75 | 392155.13 | 392155.13 | Brad Carr | B&M | 31-Aug-23 | 31-Aug-23 | 03-Jul-23 |  |  | Contractor | Contractor |  | 0
650367 | NEW STUB POLE AND GUY- MOFFATT ST & MARSHALL LN | 830 - St. Catharines | 150335 | Active | 95 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David | 02-May-23 | 1 | 1 | 7470.71 | 5425.16 | 7470.71 | 7470.71 | Dan Despres |  | 23-May-23 | 27-Jul-23 | 22-May-23 | 15-May-23 | 16-May-23 |  |  |  | 0
649256 | CITY INITIATED POLE HOLD - 584 ABERDEEN AVE | 820 - Nebo | 150644 | Active | 93 | ANALYZE | Medium | Infrast | 2023 | Jakubowski, Mark | Karan, Andjelo | 28-Apr-23 |  |  | 25313.41 | 27428.17 | 25313.41 | 25313.41 | Koeppe, Jeffrey |  | 16-Jun-23 | 27-Jul-23 | 12-Jun-23 | 01-Jun-23 | 16-Jun-23 |  |  |  | 0
650001 | 36 HUNTER ST E / HAM / UP00231752 / 2000KVA 3PH PAD SRVC | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Laus, Tomislav |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650285 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 EAST OF DEWITT (PART 1) | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650427 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS - PART 6 | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650428 | 2023-TX RENEWAL W/ OH REBIULD (EAST 38TH ST AND FENNEL AVE E) | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650430 | MH315 - NEW ROOF | 820 - Nebo | 150496 | Active | 82 | RELEASED |  |  | 2023 | Beaudrie, Scott | Billone, Justin | 21-Jun-23 |  |  | 256858.06 | 1880.56 | 256858.06 | 256858.06 | Brad Carr | B&M | 31-Oct-23 | 31-Oct-23 | 02-Oct-23 | [5 empty] | 0
649580 | 166 BEVERLY COURT - POLE RELOCATION | 820 - Nebo | 150665 | Active | 82 | RELEASED |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick | 01-Jun-23 |  |  | 20022.81 | 6372.56 | 20022.81 | 20022.81 | Macdougall, Stephen | Fairway | 25-Jul-23 | 27-Jul-23 | 24-Jul-23 | [5 empty] | 0
650487 | 550 CENTENNIAL PARKWAY N (NEW COMM UG 3PH) | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Biasutti, Stephen |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650499 | 925 MAIN ST W / HAM / NS00316180 / 3PH PAD | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650509 | 200 GLENDALE AVE N - PRIMARY ISOLATION | 820 - Nebo |  | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650520 | PICARDY DRIVE SEMI DETACHED RELOTTING - SUBDIVISION CONNECTIONS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Chu, Zeyu (Andrew) |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650532 | 455 DUNDAS STREET EAST / FLAM / NS00359881 / 600V 600A TEMP | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Ogilvie, Jordan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650540 | NS00364839 - 1020 UPPER JAMES STREET - PADMOUNT INSTALLATION | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650517 | ELMWOOD 4KV CONVERSION - PHASE 1 | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650559 | 648 KING ST W / HAM / UP00354101 / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
649606 | 75 STEEL CITY COURT - POLE REMOVAL | 820 - Nebo | 150665 | Active | 93 | ANALYZE |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick | 18-May-23 |  |  | 19854.07 | 30158.62 | 19854.07 | 19854.07 | Macdougall, Stephen |  | 20-Jun-23 | 27-Jul-23 | 19-Jun-23 | 02-Jun-23 | 02-Jun-23 |  |  |  | 0
649262 | P96787 - 137 HUGHSON ST S | 820 - Nebo | 150665 | Active | 82 | RELEASED |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick | 22-Jun-23 |  |  | 16832.14 | 10553.88 | 16832.14 | 16832.14 | Macdougall, Stephen |  | 25-Jul-23 | 27-Jul-23 | 24-Jul-23 | [5 empty] | 0
634244 | 46 BAYVIEW DR, ST. CATHARIENS - OH TO UG SERVICE RELOCATION | 830 - St. Catharines | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650579 | 24 DITTON DR / WORKPLACE DESIGN INC /HAM/NS00352041 /3PHPAD | 820 - Nebo | 150449 | Active | 40 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Bharosi, Mohindra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650591 | HONI O/H TRANSFERS- RYMAL RD | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650595 | POLE REPLACEMENT - WILMAR CRT | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650603 | 10 COMMERCE PLACE / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 82 | PDG SnR |  |  | 2023 | Mandic, Goran | Djuric, Zdravko | 23-Jun-23 |  |  | 82975.54 | 2029.49 | 82975.54 | 82975.54 | Macdougall, Stephen | Fairway | 17-Apr-24 | 17-Apr-24 | 08-Apr-24 | [5 empty] | 0
650610 | 455 WELLAND AVENUE / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650626 | 965 ARVIN AVE - EXPANSION | 820 - Nebo | 152381 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650638 | CENTRAL CONVERSION - PHASE 7A | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Wardell, Paul |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650662 | 1865 RYMAL RD E / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650680 | 15 CHURCH STREET / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650740 | 2024 - MINI REBUILD (TRAGINA AVE) NORTH OF VANSITMART AVE | 820 - Nebo | 150336 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650748 | ELMWOOD 4KV CONVERSION - PHASE 2 | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650787 | MH101C - ROOF REPLACEMENT | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 20-Jul-20
650823 | 2023 EMERGING - BELL TRANSFER TAPLEYTOWN ROAD | 820 - Nebo | 150828 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650824 | 461 GREEN RD / HAM / NS / 3PH PAD | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Dragojevic, Igor |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650877 | 2024 - POLE REPLACEMENTS HAM - BATCH 4 | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650876 | 2024 - POLE REPLACEMENTS HAM - BATCH 3 | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650875 | 2024 - POLE REPLACEMENTS HAM - BATCH 2 | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650874 | 2024 - POLE REPLACEMENTS HAM - BATCH 1 | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650885 | 2024 - DA SWITCHES BATCH 8 -1 SWITCH | 830 - St. Catharines | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650884 | 2024 - DA SWITCHES BATCH 7 - 2 SWITCHES | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650883 | 2024 - DA SWITCHES BATCH 6 - 1 SWITCH | 820 - Nebo | 150334 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650882 | 2024 - DA SWITCHES BATCH 5 - 4 SWITCHES | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650881 | 2024 - DA SWITCHES BATCH 4 - 3 SWITCHES | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650880 | 2024 - DA SWITCHES BATCH 3 - 4 SWITCHES | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650879 | 2024 - DA SWITCHES BATCH 2 - 3 SWITCHES | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650878 | 2024 - DA SWITCHES BATCH 1 - 3 SWITCHES | 820 - Nebo | 150334 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650886 | UP00379147 - 510 MOHAWK ROAD - 600A SERVICE UPGRADE | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650889 | 399 FIRST RD W / HAM / NS00362072 / 3PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650898 | 4 GROSVENOR AVE S / HAM / UP00288563 / 1PH PAD | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650907 | 2024 SWITCH RENEWAL SCH - MANUAL (SW 8277) | 830 - St. Catharines | 150337 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650906 | 2024 SWITCH RENEWAL SCH - VIPER (3 UNITS) | 830 - St. Catharines | 150337 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650912 | 2024 SWITCH RENEWAL HAM - MANUAL (8862) | 820 - Nebo | 150337 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650911 | 2024 SWITCH RENEWAL HAM - MANUAL (35413) | 820 - Nebo | 150337 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650910 | 2024 SWITCH RENEWAL HAM - VIPER (462) | 820 - Nebo | 150337 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650909 | 2024 SWITCH RENEWAL HAM - VIPER (111W11) | 820 - Nebo | 150337 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650927 | 29-33 CECIL STREET - SUBD RES EDS | 830 - St. Catharines | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Manojlovic, Stefan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650946 | NS00349205 - 2039 SEVENTH STREET LOUTH - 400A SERVICE UPGRADE | 830 - St. Catharines | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
650981 | 213 KING ST W / HAM / NS00380748 / 3PH PAD TEMP SERVICE | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 399.65 | 0 |  | 0 | Calvin Arsenault |  |  | 13-Jul-23
650986 | 76 RIDLEY ROAD / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651021 | 500 RENNIE ST / HAM / UP / 3PH | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Biasutti, Stephen |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651040 | THE CROSSINGS PHASE 2– SUBDIVISION CONNECTIONS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Chu, Zeyu (Andrew) |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651063 | CCRA - 16 LOCK STREET / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651069 | URBAN CORE (ELECTRICAL DRAWINGS) - SUBDIVISION | 820 - Nebo | 151652 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Chu, Zeyu (Andrew) |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651089 | PROJECT #3 - POLE REPLACEMENTS - JOHN ST N | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Anderson, Dean |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651091 | ELMWOOD 4KV CONVERSION - PHASE 3 | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651093 | 20 PRINCESS ST - SEC CABLE REPLACEMENT | 830 - St. Catharines | 151452 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651092 | USE FOR NEXT HAMILTON PROJECT | 820 - Nebo | 151452 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651107 | PADMOUNT TX REPLACEMENT - 400 SCOTT ST | 830 - St. Catharines | 151452 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651117 | 2023 SPOT POLES - DEPEW AND BEACH | 820 - Nebo | 150335 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651125 | 25 VILLAGE GREEN DR - SEC CABLE REPLACEMENT | 830 - St. Catharines | 151452 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651126 | NS00339637 - 61 BARNABAS STREET NEW SERVICE REQUEST | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651142 | ELMWOOD 4K CONVERSION - PHASE 6 | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651141 | ELMWOOD 4K CONVERSION - BATCH 5 | 820 - Nebo | 150496 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651140 | ELMWOOD 4K CONVERSION - PHASE 1 (FEED) | 820 - Nebo | 150496 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651163 | 420 PARKDALE AVE N | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651199 | 19 HIGHLAND RD E / HAM / NS00326484 / 1PH PAD | 820 - Nebo | 150449 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Perez Rodriguez, Yuniel |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651214 | REBECCA ST CIVIL EARLY WORKS | 820 - Nebo | 152311 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651240 | 2023 - O/H AUTOMATION - BUNTING TS - PARNEL RD | 830 - St. Catharines | 150334 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651259 | 22 CANNON ST E HAMILTON (THE FINERY) | 820 - Nebo | 150665 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651269 | PADMOUNT TX REPLACEMENT - 2 ARLINGTON AVE | 830 - St. Catharines | 151452 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651273 | ROAD AUTHORITY - ST.DAVID'S RD (PHASE 2) - ROAD URBANIZATION - ST.CATHARINES | 830 - St. Catharines | 150653 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Karan, Andjelo |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651306 | NS00381833 - 125 RIFLE RANGE ROAD | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651330 | 58 YORK BLVD / HAM / NS00327663 / 2500A 347/600 3PH SRVC | 820 - Nebo | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Frigotto, Rodrigo | Ogilvie, Jordan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651195 | VICKERS RD - HYDRO TRANSFERS ON BELL POLES | 820 - Nebo | 150828 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651386 | THE FOOTHILLS OF WINONA - PHASE 3 NORTHEAST CORNER OF CONDO BLOCK - RES SUBD EDS | 820 - Nebo | 150588 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Manojlovic, Stefan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651388 | 20 BRADMON DRIVE / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
651389 | 29-33 CECIL STREET / SCH / NS / 3PH PAD | 830 - St. Catharines | 150449 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Djuric, Zdravko |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 20-Jul-20
CN | Central North Region (H1B) | [9 empty] | Central North |  | 605 | 222 | 108341673.32 | 100036636.2 | 47026079 | 47026079 | [5 empty] | 14-Feb-18 | 20-Jul-23
635558 | 2020 CABLE REPLACEMENT - GRID: N2 | 805 - Sandalwood | 151181 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 42509.9 |  | 0 | Dre Danieli |  |  | 26-Jul-23
633530 | 4KV CONV PH3C - APARTMENTS | 805 - Sandalwood | 151138 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 11-Jan-21 |  |  | 885776.78 | 881604.5 | 695427.87 | 885776.78 | Reaburn, Jeff | Transpw | 30-Nov-21 | 26-Sep-23 | 19-Apr-21 | 14-Jun-21 | 17-Dec-21 | Contractor | Contractor |  | 190,348.91
635369 | NATIONAL HOMES GOREWAY (MUNICIPAL) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 26-Oct-20 |  |  | 123057.71 | 105852.96 | 123057.71 | 123057.71 | Richard Cuddy | Transpw | 27-Nov-20 | 26-Jul-23 | 23-Nov-20 | 30-Oct-20 | 14-Oct-21 |  | Customer |  | 0
635642 | 134 KENNEDY RD. S. - SERVICE UPGRADE | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 28-Jul-20 |  |  | 194797.85 | 139047.9 | 186047.85 | 194797.85 | Simon Evason | Somervl | 21-Sep-20 | 26-Jul-23 | 01-Sep-20 | 18-Sep-20 | 20-Oct-21 | Customer | Customer |  | 8,750.00
636024 | 21T-06024B SCOTTISH HEATHER PHASE 4B | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 28-Aug-20 |  |  | 716924.76 | 718328.01 | 716924.76 | 716924.76 | Richard Cuddy | Transpw | 01-Dec-20 | 26-Jul-23 | 05-Oct-20 | 05-Oct-20 | 27-Jan-21 | Customer | Customer |  | 0
633764 | COUNTRYSIDE DR STUB POLE RE-INSTALLATION | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Robinson, David | 10-Oct-19 |  |  | 23300.43 | 18418.27 | 23300.43 | 23300.43 | John Costa | A&W | 08-Nov-19 | 10-May-23 | 04-Nov-19 | 22-Oct-19 | 26-Nov-19 |  |  |  | 0
450920 | 860 AND 870 NORTH PARK DR. | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE | Medium | Comm | 2019 |  | Cavanaugh, Danny | 27-Jun-19 |  |  | 69497 | 70706.36 | 69497 | 69497 | Simon Evason |  | 23-Aug-19 | 11-Jan-22 | 16-Aug-19 | 24-Nov-19 | 25-Nov-19 |  | Customer |  | 0
450646 | 0 SUN PAC BLVD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 06-Oct-21
632815 | THE GORE RD- UNDERGROUND CABLE RELOCATION | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lemire, Blake | 21-Aug-19 |  |  | 45305.73 | 47281.75 | 45305.73 | 45305.73 | Nichol, Sandi | A&W | 27-Sep-19 | 24-Aug-20 | 23-Sep-19 | 30-Aug-19 | 04-Nov-19 |  |  |  | 0
632799 | 4KV CONVERSION PH7-BRAMPTON - 2021 | 805 - Sandalwood | 151138 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 04-Dec-20 |  |  | 1129992.47 | 1143521.75 | 1032245.96 | 1129992.47 | Reaburn, Jeff | Transpw | 21-May-21 | 26-Jul-23 | 11-Jan-21 | 18-Jan-21 | 23-Aug-21 | Locates | Locates |  | 97,746.51
635954 | 625 REMEMBRANCE RD | 805 - Sandalwood | 150386 | Active | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 30-Nov-20 |  |  | 143361.86 | 137753.04 | 143361.86 | 143361.86 | Simon Evason | Somervl | 18-Jan-21 | 26-Jul-23 | 11-Jan-21 | 13-Jan-21 | 11-Feb-21 | Customer | Customer |  | 0
633513 | 26.6 KV SUPPLY TO 750 KVA TX AT 100 MANETT CRES. - FILE# F3-100, REF# NS00905810 | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE | High | Comm | 2022 | Rao, Gaurav | Cavanaugh, Danny | 08-May-20 |  |  | 89923.66 | 76674.59 | 89923.66 | 89923.66 | Simon Evason | Somervl | 29-Jun-20 | 26-Jul-23 | 15-Jun-20 | 02-Oct-20 | 10-Jan-22 | Customer | Customer |  | 0
634901 | HODERO MAYFIELD RD - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 28-Oct-20 |  |  | 289792.44 | 280916 | 289792.44 | 289792.44 | Richard Cuddy | Transpw | 04-Jan-21 | 26-Jul-23 | 30-Nov-20 | 30-Oct-20 | 19-Mar-21 |  | Customer |  | 0
635659 | 160 SALVATION RD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 23-Oct-20 |  |  | 72599.37 | 60193.49 | 63849.37 | 72599.37 | Simon Evason | Somervl | 18-Jan-21 | 26-Jul-23 | 18-Jan-21 | 18-Jan-21 | 23-Feb-21 | Customer | Customer |  | 8,750.00
635873 | PARTACC GATE KENNEDY DEVT - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 93 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 31-Jan-23 |  |  | 1793874.22 | 1782258.27 | 1793874.22 | 1793874.22 | Graham Gegear | Transpw | 23-May-23 | 26-Jul-23 | 15-May-23 | 18-Apr-23 | 21-Jun-23 |  | Lines |  | 0
636041 | CAL-GORE DEVELOPMENT INC. - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Erzek, Ryan | 26-Oct-20 |  |  | 204570.53 | 144135.82 | 204570.53 | 204570.53 | Richard Cuddy | Transpw | 16-Nov-21 | 26-Jul-23 | 16-Nov-21 | 16-Nov-20 | 11-Feb-22 |  | Customer |  | 0
634661 | PARADISE HOMES - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Active | 82 | RELEASED |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne | 26-Apr-23 |  |  | 37099.85 | 8217.04 | 37099.85 | 37099.85 | Graham Gegear | N/A | 26-Jul-23 | 28-Jul-23 | 24-Jul-23 | [5 empty] | 0
450961 | GOREWAY DR | 805 - Sandalwood | 151648 | Inactive | 99 | CANCELLED |  |  | 2022 | Pelleja, Emily | D'Ermes, Michael |  |  |  | 17.08 | 0 |  | 0 | Dre Danieli |  |  | 23-May-23
635371 | NATIONAL HOMES GOREWAY (CONDO) - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Erzek, Ryan | 09-Nov-21 |  |  | 342538.74 | 359630.66 | 342538.74 | 342538.74 | Zenon Lipinski | Transpw | 09-Feb-22 | 26-Jan-23 | 01-Feb-22 | 29-Nov-21 | 26-Aug-22 |  |  |  | 0
450919 | VAN KIRK DR AND BOVAIRD DR W | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lemire, Blake | 02-Apr-19 |  |  | 3500 | 7420.46 | 3500 | 3500 | John Costa |  | 30-Apr-19 | 10-Aug-20 | 30-Apr-19 | 30-Apr-19 | 30-Apr-19 |  |  |  | 0
636446 | 2020 SWITCHGEAR RENEWAL - SITE# 118 | 805 - Sandalwood | 150282 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
636336 | 2021 POLE RENEWAL-GRID C2- 1 POLE | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli
635162 | ROAD AUTHORITY-POLE RELOCATION-REGION OF PEEL-LOC. 3-DIXIE RD (QUEEN TO BOVAIRD) | 805 - Sandalwood | 151807 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli
634731 | BLOCK 7 CREDITVIEW & LAGERFELD DR | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli
633246 | WO TO BE RE-PURPOSED | 805 - Sandalwood | 151010 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 26-Aug-19
450782 | WALLSEND STAGE 1 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 15-Mar-21 |  |  | 50974.25 | 472501.37 | 50974.25 | 50974.25 | Richard Cuddy |  | 27-Apr-21 | 26-Jul-23 | 19-Apr-21 | 01-Apr-21 | 25-May-21 | Customer | Customer |  | 0
450756 | MAYFIELD RD CHING.TO HURONTAR0 | 805 - Sandalwood | 151806 | Active | 84 | ACTIVE |  |  | 2023 | Lacombe, Joel | Robinson, David | 16-Feb-22 |  |  | 2741534.15 | 2730112.24 | 2704310.56 | 2741534.15 | AW Group | A&W | 31-Mar-23 | 26-Oct-23 | 03-Jan-23 | 14-Feb-22 |  |  | Contractor |  | 37,223.59
632773 | 4KV CONVERSION - PHASE 2B | 805 - Sandalwood | 151138 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 11-Jan-21 |  |  | 514493.35 | 471806.61 | 514493.35 | 514493.35 | Reaburn, Jeff | Somervl | 02-Sep-21 | 06-Jul-23 | 01-Jun-21 | 10-May-21 | 15-Sep-21 |  | N/A |  | 0
635711 | MISSISSAUGA RD @ LAGERFELD RD. POLE RELOCATION (LAGERFELD RD EXT. | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2022 | Pelleja, Emily | Robinson, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 02-Feb-23
450352 | POLICE LANDS BLK 51-1 - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Armstrong, Colby | 05-Aug-21 |  |  | 37587.48 | 155435.94 | 37587.48 | 37587.48 | Richard Cuddy |  | 16-Sep-21 | 25-Jan-23 | 07-Sep-21 | 15-Oct-21 | 18-Nov-21 | Customer | Customer |  | 0
450115 | 7995 KENNEDY RD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 01-Sep-22
636447 | 2021 SWITCHGEAR RENEWAL - SITE# 116 | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 11-Jan-21 | 1 |  | 160908.66 | 194543.3 | 160908.66 | 160908.66 | Richard Cuddy |  | 14-Jul-21 | 21-Apr-22 | 28-Jun-21 | 15-Oct-21 | 25-Oct-21 | Materials | Materials |  | 0
636337 | 2021 POLE RENEWAL-GRID F2- 9 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 09-Dec-20 | 9 |  | 308036.36 | 210173.23 | 308036.36 | 308036.36 | Reaburn, Jeff |  | 19-Apr-21 | 14-Feb-22 | 16-Feb-21 | 01-Mar-21 | 23-Apr-21 | Locates | Locates |  | 0
631720 | The Gore Rd and Queen St - STUB POLE INSTALLATION / D/G RELOCATION | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Robinson, David | 29-Aug-19 |  |  | 46377.67 | 37161.57 | 46377.67 | 46377.67 | John Costa | A&W | 27-Sep-19 | 15-Nov-21 | 23-Sep-19 | 13-Sep-19 | 26-Nov-19 |  |  |  | 0
633484 | POLE RELOCATION AT 6401 MAYFIELD RD | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Robinson, David | 17-Sep-19 |  |  | 21090.04 | 21703.95 | 21090.04 | 21090.04 | John Costa |  | 25-Oct-19 | 27-May-21 | 21-Oct-19 | 21-Oct-19 | 07-Nov-19 |  |  |  | 0
450916 | 2019 - VARIOUS LOCATIONS BRAMPTON - tx | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Casey, Ryan | 07-Nov-18 |  |  | 87362.65 | 84793.27 | 87362.65 | 87362.65 | Reaburn, Jeff |  | 11-Apr-19 | 24-Aug-20 | 08-Apr-19 | 22-Mar-19 | 25-Mar-19 |  | Filler |  | 0
450966 | BALMORAL DR/APPLEBY DR - SG | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Miller, Michael | 07-Nov-18 |  |  | 106050.7 | 125767.32 | 106050.7 | 106050.7 | Richard Cuddy |  | 16-Sep-19 | 24-Aug-20 | 03-Sep-19 | 20-Feb-19 | 27-Feb-19 |  |  |  | 0
636416 | 65 ATTMAR DR. - 27.6KV SUPPLY TO 2000 KVA TX | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 04-Jan-21 |  |  | 123489.61 | 98059.03 | 123489.61 | 123489.61 | Simon Evason | Somervl | 07-May-21 | 26-Jul-23 | 19-Apr-21 | 10-May-21 | 18-May-21 | Customer | Customer |  | 0
450350 | 10 & 20 LIGHTBEAM TERRACE | 805 - Sandalwood | 150386 | Active | 92 | COMPLETE |  |  | 2019 | Rao, Gaurav | Bojanic, Dusan | 09-Oct-19 |  |  | 108338.77 | 97124.51 | 108338.77 | 108338.77 | Simon Evason | Somervl | 26-Nov-19 | 26-Jul-23 | 11-Nov-19 | 25-Oct-19 | 12-Dec-19 |  | Customer |  | 0
632772 | 4KV CONVERSION - PHASE 8 | 805 - Sandalwood | 151138 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 30-Nov-21 |  |  | 1942931.54 | 1974477.68 | 1969325.83 | 1942931.54 | AW Group | A&W | 29-Jul-22 | 02-Mar-23 | 01-Feb-22 | 26-Jan-22 | 21-Nov-22 |  | Lines |  | -26,394.29
635052 | 295 QUEEN ST.E. - 27.6KV SUPPLY TO 750 KVA TX | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 18-May-22
450776 | BOVAIRD DR-CREDITVIEW/WORTNGTN | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Robinson, David | 14-Jan-19 |  |  | 340000 | 338941.86 | 285000 | 285000 | Reaburn, Jeff | A&W | 29-Mar-19 | 24-Aug-20 | 18-Feb-19 | 18-Feb-19 | 06-Aug-19 |  |  |  | 0
450641 | 30 LOAFERS LAKE LANE | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 25-Apr-19 |  |  | 59978.64 | 85105.38 | 59978.64 | 59978.64 | Simon Evason | Somervl | 04-Jun-19 | 24-Aug-20 | 27-May-19 | 17-May-19 | 23-May-19 |  |  |  | 0
636453 | 2021 POLE RENEWAL GRID N2-5 POLES | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 5 |  | 0 | 0 |  | 0 | Dre Danieli
632682 | 1600 BOVAIRD DR W | 805 - Sandalwood | 150389 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 30-Jul-19
635889 | 11205 GOREWAY DR (NEW FOREST TERRACE) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli
450179 | Clark Blvd - Rutherford to Dixie | 805 - Sandalwood | 150645 | Active | 40 | H8 |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 | 0 | 0 | Weaver, Thomas | N/A |  | 03-Jul-18 | [6 empty] | 0
632681 | 200 Largerfeld Dr and Creditview Rd - Block 7 | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE | High | Indust | 2021 | Rao, Gaurav | Bojanic, Dusan | 07-Jan-20 |  |  | 67181.83 | 66679.83 | 87911.14 | 67181.83 | Simon Evason | Somervl | 20-Feb-20 | 26-Jul-23 | 10-Feb-20 | 01-Jun-20 | 30-Apr-21 | Customer | Customer |  | -20,729.31
450243 | BOVAIRD DR W & LAGERFELD DR | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 11-Nov-21 |  |  | 112794.39 | 143296.39 | 112794.39 | 112794.39 | Simon Evason | Somervl | 14-Jan-22 | 26-Jul-23 | 04-Jan-22 | 27-Sep-22 | 11-Oct-22 | Customer | Locates |  | 0
450107 | MCVEAN DR: CASTLEMORE-MAYFIELD | 805 - Sandalwood | 150645 | Active | HL | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 11468.33 | 0 | 0 | Weaver, Thomas |  |  | 26-Jul-23 | [6 empty] | 0
450638 | 15 LYNCH ST | 805 - Sandalwood | 150389 | Active | 98 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 25-Nov-20 |  |  | 93756.4 | 98813.55 | 93756.4 | 93756.4 | Simon Evason | Transpw | 11-Jan-21 | 26-Jul-23 | 04-Jan-21 | 15-Jan-21 | 25-Jan-21 | Customer | Customer |  | 0
633438 | 2300 NORTH PARK DRIVE | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 22-Oct-20 |  |  | 94477.61 | 88568.14 | 94477.61 | 94477.61 | Simon Evason | Somervl | 08-Dec-20 | 08-Mar-23 | 30-Nov-20 | 11-Feb-21 | 05-Mar-21 | Customer | Customer |  | 0
632771 | 2020 CABLE INJECTION PROJECT - GRID I3 | 805 - Sandalwood | 151318 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 01-Nov-19 |  |  | 516721.51 | 822858.35 | 516721.51 | 516721.51 | Simon Evason | Nvinium | 07-Jul-21 | 11-Sep-22 | 06-Apr-20 | 10-Mar-20 | 30-May-22 | COVID19 |  |  | 0
636431 | 2020 SWITCHGEAR RENEWAL-SITE# 484(FORMERLY 98)-SANDALWOOD PKWY AND ROSEDALE | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 06-Jan-20 | 1 |  | 162125.08 | 222622.31 | 165125.08 | 162125.08 | Richard Cuddy | A&W | 15-Mar-21 | 21-Apr-22 | 08-Mar-21 | 29-Nov-21 | 22-Dec-21 | Materials | Materials |  | -3,000.00
450913 | 2021 TX RENEWAL- GRID G4-2 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 11-Dec-20 | 2 |  | 34337.21 | 48784.26 | 34337.21 | 34337.21 | Richard Cuddy | Somervl | 02-Mar-21 | 15-Feb-22 | 01-Mar-21 | 08-Jun-21 | 13-Aug-21 | Lines | Lines |  | 0
450110 | QUEEN ST | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2023 | Weaver, Thomas | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 04-Feb-19
636531 | 425 CHRYSLER DR | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 04-Sep-20 |  |  | 256331.76 | 128318.37 | 256331.76 | 256331.76 | Simon Evason | Somervl | 15-Nov-21 | 26-Jul-23 | 15-Nov-21 | 01-Dec-21 | 27-Jan-22 | Customer | Customer |  | 0
635492 | 2023 POLE RENEWAL - POLE#4-ST JOHNS RD - GRID P1 | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 23-Dec-22 | 1 |  | 37840.15 | 13110.99 | 37840.15 | 37840.15 | Graham Gegear |  | 04-Jul-23 | 31-Jul-23 | 03-Jul-23 | [5 empty] | 0
450242 | MAYFIELD-AIRPORT TO THE GORE | 805 - Sandalwood | 151806 | Active | HL | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 99840.41 | 950000 | 950000 | Weaver, Thomas | N/A |  | 26-Jul-23 | [6 empty] | 0
450911 | 10562 HIGHWAY 50 | 805 - Sandalwood | 150386 | Active | 96 | COMPLETE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 10-Jun-22 |  |  | 231706.62 | 227580.07 | 231706.62 | 231706.62 | Simon Evason | Transpw | 26-Sep-22 | 26-Jul-23 | 12-Sep-22 | 22-Nov-22 | 07-Dec-22 | Locates | Locates |  | 0
636432 | 2020 SWITCHGEAR RENEWAL - SITE# 480 (FORMERLY 149)- PETER ROBINSON EAST OF DIXIE | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 06-Jul-20 | 1 |  | 162125.08 | 172738.43 | 165125.08 | 162125.08 | Richard Cuddy | A&W | 15-Mar-21 | 28-Apr-22 | 08-Mar-21 | 20-Sep-21 | 29-Oct-21 | Materials | Materials |  | -3,000.00
632769 | 2020 CABLE INJECTION PROJECT - GRID K3 | 805 - Sandalwood | 150571 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 01-Nov-19 |  |  | 327812.53 | 551318.34 | 327812.53 | 327812.53 | Simon Evason | Nvinium | 18-Dec-20 | 28-Feb-22 | 06-Apr-20 | 08-Sep-20 | 06-Dec-21 | COVID19 | COVID19 |  | 0
450348 | BOVAIRD DR W & HERITAGE RD - PCB TX. | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 19-Jun-19 |  |  | 45215.19 | 43537.97 | 45215.19 | 45215.19 | John Costa |  | 01-Oct-19 | 03-Dec-20 | 11-Sep-19 | 04-Jul-19 | 21-Aug-19 |  | Filler |  | 0
633150 | 2020 - UG REBUILD - ARGENTIA CABLE FAULTS (SECTION 1) | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 19-Aug-19
632768 | 2020 CABLE INJECTION PROJECT - GRID J3 | 805 - Sandalwood | 150571 | Active | 95 | ANALYZE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 01-Nov-19 |  |  | 723893.72 | 2035134.37 | 723893.72 | 723893.72 | Simon Evason | Nvinium | 18-Dec-20 | 26-Jul-23 | 06-Apr-20 | 07-Sep-20 | 04-Jan-23 | COVID19 | COVID19 |  | 0
633375 | C1-6 - 1465 MAYFIELD RD - 27.6KV U/G RADIAL 750KVA | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 05-Feb-20 |  |  | 84130.88 | 62418.22 | 82825.88 | 84130.88 | Simon Evason | Somervl | 12-Nov-20 | 08-Aug-23 | 02-Nov-20 | 13-Aug-21 | 20-Aug-21 | Customer | Customer |  | 1,305.00
450904 | CREDITVIEW RD & VETERANS DR | 805 - Sandalwood | 150692 | Active | 99 | COMPLETE |  |  | 2019 |  | Erzek, Ryan | 26-Mar-19 |  |  | 330719.28 | 317826.13 | 330719.28 | 330719.28 | Richard Cuddy |  | 14-Jun-19 | 26-Jul-23 | 21-May-19 | 04-Apr-19 | 07-Oct-19 |  | Customer |  | 0
450241 | MAYFIELD-THE GORE TO COLERAINE | 805 - Sandalwood | 151806 | Active | HL | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 39899.31 | 900000 | 900000 | Reaburn, Jeff | N/A |  | 26-Jul-23 | [6 empty] | 0
636433 | 2020 SWITCHGEAR RENEWAL-SITE# 478 (FORMERLY 181)-GURU NANAK ST W OF DIXIE | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 06-Jul-20 | 1 |  | 162125.08 | 199778.73 | 165125.08 | 162125.08 | Richard Cuddy | A&W | 15-Mar-21 | 28-Apr-22 | 08-Mar-21 | 27-Sep-21 | 15-Nov-21 | Materials | Materials |  | -3,000.00
450771 | CV PATILDA PH5 ST1 - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 04-Feb-21 |  |  | 78654.36 | 718772.3 | 78654.36 | 78654.36 | Richard Cuddy |  | 31-Mar-21 | 24-Jan-22 | 08-Mar-21 | 07-Mar-21 | 25-May-21 | Customer | Customer |  | 0
450102 | MAYFIELD RD | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Robinson, David | 21-Nov-18 |  |  | 38000 | 52825.6 | 38000 | 38000 | Nichol, Sandi |  | 23-May-19 | 19-Oct-20 | 21-Nov-18 | 03-Dec-18 | 30-Sep-19 |  | Customer |  | 0
450956 | 20 BISCAYNE CRES | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 01-May-19 |  |  | 48064.55 | 70213.01 | 48064.55 | 48064.55 | Simon Evason | N/A | 12-Jun-19 | 24-Aug-20 | 03-Jun-19 | 22-May-19 | 24-May-19 |  |  |  | 0
450634 | NICOLAU PH 2 (21T - 01040B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Simon Evason |  |  | 14-Dec-17
631755 | 2020 CABLE INJECTION PROJECT - GRIDS N2 | 805 - Sandalwood | 150571 | Active | 95 | ANALYZE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 01-Nov-19 |  |  | 857817.57 | 2733988.71 | 857817.57 | 857817.57 | Simon Evason | Nvinium | 18-Dec-20 | 26-Jul-23 | 06-Apr-20 | 06-Mar-20 | 04-Jan-23 | COVID19 | COVID19 |  | 0
450097 | Highway 410 & Williams Pkwy | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2022 | Weaver, Thomas | Robinson, David |  |  |  | 0 | 19536.16 | 0 | 0 | Weaver, Thomas |  |  | 22-Sep-22 | [6 empty] | 0
450955 | Pole Replacement 2019 Batch #4 | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2019 |  | Casey, Ryan | 17-Dec-18 |  |  | 32895.3 | 76868.37 | 32895.3 | 32895.3 | Reaburn, Jeff |  | 13-May-19 | 24-Aug-20 | 06-May-19 | 04-Feb-19 | 05-Feb-19 |  | Filler |  | 0
450240 | CCRA - 14 WESTWYN CRT | 805 - Sandalwood | 150389 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 19-Dec-17
632899 | 4KV CONVERSION - PHASE 6 | 805 - Sandalwood | 151138 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 30-Nov-21 |  |  | 1468555.34 | 1586515.44 | 1468555.34 | 1468555.34 | Reaburn, Jeff | Transpw | 06-Oct-22 | 02-Mar-23 | 01-Feb-22 | 14-Feb-22 | 28-Dec-22 | Locates |  |  | 0
450631 | CASTLEMORE AND EVERGREEN | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lemire, Blake | 02-Apr-19 |  |  | 2760 | 5765.85 | 2760 | 2760 | John Costa |  | 30-Apr-19 | 15-Nov-21 | 29-Apr-19 | 23-Apr-19 | 15-May-19 |  |  |  | 0
450094 | 339 QUEEN ST W Switch Replacement #1 | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 11-Mar-19 |  | 1 | 146575.11 | 124960.66 | 146575.11 | 146575.11 | Reaburn, Jeff |  | 30-Nov-19 | 20-Nov-20 | 03-Jun-19 | 08-Oct-19 | 14-Nov-19 |  |  |  | 0
450339 | MS 14 - 14F3 FEEDER EGRESS REPLACEMENT - substation work | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Zaghloul, Sam | 29-Apr-19 |  |  | 173930 | 194651.08 | 173930 | 173930 | Richard Cuddy |  | 27-Jun-19 | 15-Oct-20 | 27-May-19 | 13-May-19 | 06-Jun-19 |  |  |  | 0
450954 | Switchgear - 5 - County Court and Havelock | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 23-Oct-18 |  |  | 95321.17 | 137693.28 | 95321.17 | 95321.17 | Richard Cuddy |  | 30-Apr-19 | 24-Aug-20 | 15-Apr-19 | 04-Mar-19 | 22-Mar-19 |  |  |  | 0
450769 | 28 TRURO CIR | 805 - Sandalwood | 150692 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Erzek, Ryan | 27-Aug-18 |  |  | 265616.22 | 246397.71 | 265616.22 | 265616.22 | Richard Cuddy |  | 30-Nov-18 | 24-Aug-20 | 01-Oct-18 | 07-Oct-18 | 29-Nov-19 |  | Customer |  | 0
450330 | 9715 WINSTON CHURCHILL BLVD | 805 - Sandalwood | 150784 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 20423.42 |  | 0 | Hotham, Matthew |  |  | 26-Jul-23
450764 | WILLIAMS PKY HWY 10 - KENNEDY | 805 - Sandalwood | 150784 | Inactive | 99 | CANCELLED |  |  | 2022 | Casciato, Adam J | Lemire, Blake |  |  |  | 0 | 20211.7 |  | 0 | Weaver, Thomas |  |  | 22-Sep-22
450953 | 500 DEERHURST DRIVE | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Ferry, Rodnne | 27-Feb-19 |  |  | 79719 | 70286.94 | 79719 | 79719 | Simon Evason | Somervl | 05-Apr-19 | 11-Jan-22 | 25-Mar-19 | 06-Mar-19 | 24-Oct-19 |  | Customer |  | 0
450088 | SW WILLIAMS PKY W MCLAUGHLIN - Switch Replacement #4 | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 11-Mar-19 |  | 1 | 132124.12 | 125951.45 | 132124.12 | 132124.12 | Reaburn, Jeff |  | 18-Oct-19 | 29-Oct-20 | 01-May-19 | 27-Aug-19 | 30-Sep-19 |  |  |  | 0
450629 | 9025 Torbram Rd - ICI | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 19-Mar-19 |  |  | 98804.23 | 62154.08 | 98804.23 | 98804.23 | Simon Evason |  | 06-May-19 | 24-Aug-20 | 23-Apr-19 | 21-Mar-19 | 17-Jun-19 |  | Customer |  | 0
450327 | ROSEDALE VILLAGE PH7A STG2 - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Armstrong, Colby | 24-Jun-19 |  |  | 26109.65 | 263266.35 | 26109.65 | 26109.65 | Richard Cuddy |  | 23-Jul-21 | 10-Jul-23 | 19-Jul-21 | 23-Jul-21 | 26-Jul-21 | Customer | Customer |  | 0
450763 | MAIN ST S & CLARENCE ST | 805 - Sandalwood | 150630 | Inactive | 99 | CANCELLED |  |  | 2022 | Gamboa, Henry | Erzek, Ryan |  |  |  | 0 | 2307.25 |  | 0 | Dre Danieli |  |  | 22-Sep-22
450897 | 2019 SWITCHGEAR REPLACEMENTS - Union St and Nelson | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 23-Oct-18 |  |  | 95405.12 | 100125.86 | 95405.12 | 95405.12 | Richard Cuddy |  | 12-Apr-19 | 24-Aug-20 | 01-Apr-19 | 22-Jan-19 | 07-Feb-19 |  |  |  | 0
450236 | AIRPORT RD/WILLIAMS PKWY | 805 - Sandalwood | 150645 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Boivin, Cameron |  |  |  | 0 | 0 | 2700000 | 2700000 | Weaver, Thomas | K-Line |  | 29-Jan-18 | [6 empty] | 0
450762 | DIXIE RD & MAYFIELD RD - Feeder for the Subdivision | 805 - Sandalwood | 150692 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Erzek, Ryan | 23-Oct-18 |  |  | 47482.08 | 44828.85 | 47482.08 | 47482.08 | Richard Cuddy |  | 18-Dec-18 | 09-Aug-22 | 03-Dec-18 | 09-Jul-19 | 29-Jul-19 |  | Customer |  | 0
450233 | 71 Orenda Rd | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Gaurav | Ferry, Rodnne | 14-Nov-18 |  |  | 50915 | 56886.07 | 50915 | 50915 | Simon Evason |  | 21-Dec-18 | 11-Jan-22 | 10-Dec-18 | 12-Dec-18 | 26-Aug-19 |  | Customer |  | 0
450086 | 71 Orenda Rd - Switch Replacement - #3 | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 11-Mar-19 |  | 1 | 127297.59 | 91249.2 | 127297.59 | 127297.59 | Reaburn, Jeff |  | 30-Sep-19 | 18-Feb-21 | 15-May-19 | 02-Aug-19 | 30-Sep-19 |  |  |  | 0
W116 | Mayfield Rd | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Robinson, David | 01-Apr-19 |  |  | 0 | 1743.95 |  | 0 | Reaburn, Jeff |  | 04-Apr-19 | 29-Apr-19 | 04-Apr-19 | 01-Apr-19 | 04-Apr-19
450620 | 209 Steeles Ave. W. (200 MALTA AVE) | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2019 | 0 | Cavanaugh, Danny | 01-Mar-19 |  |  | 58579 | 54034.1 | 58579 | 58579 | Simon Evason |  | 12-Apr-19 | 22-Sep-22 | 01-Apr-19 | 29-May-19 | 06-Jun-19 |  | Customer |  | 0
450083 | STEELES AVE E-ADVANCE BLVD | 805 - Sandalwood | 151535 | Inactive | 99 | CANCELLED |  |  | 2022 | Tobin, Michael | Chopra, Rabinder |  |  |  | 0 | 33967.48 | 0 | 0 | Weaver, Thomas |  |  | 29-Jun-22 | [6 empty] | 0
450760 | MAYFIELD RD & CREDITVIEW RD | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Erzek, Ryan | 23-Jul-18 |  |  | 353790.43 | 369662.93 | 353790.43 | 353790.43 | Richard Cuddy |  | 20-Mar-19 | 24-Aug-20 | 15-Oct-18 | 07-Oct-18 | 28-Jan-19 |  | Customer |  | 0
450891 | SE OF MAYFIELD & GORDON RANDLE | 805 - Sandalwood | 150630 | Inactive | 99 | CANCELLED |  |  | 2021 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 25-Oct-21
450082 | THE GORE RD & COUNTRYSIDE DR | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2021 | Norman, Greg | Erzek, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 14-Dec-17
450226 | DENISION AVE & HAGGERT AVE | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Armstrong, Colby | 03-Sep-20 |  |  | 87247.39 | 88096.71 | 87247.39 | 87247.39 | Richard Cuddy |  | 15-Oct-20 | 27-Jun-23 | 13-Oct-20 | 14-Dec-20 | 18-Jan-21 | Customer | Customer |  | 0
450081 | ETR 407- TORBRAM RD | 805 - Sandalwood | 151535 | Inactive | 99 | CANCELLED |  |  | 2022 | Tobin, Michael | Chopra, Rabinder |  |  |  | 0 | 32450.27 | 0 | 0 | Weaver, Thomas |  |  | 29-Jun-22 | [6 empty] | 0
450318 | 237B ADVANCE BOULEVARD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 78862.91 | 0 | 78862.91 | 78862.91 | Hotham, Matthew |  |  | 27-Feb-19 | [6 empty] | 0
450946 | BOVAIRD, BRAMALEA & DIXIE | 805 - Sandalwood | 150572 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 32384.44 |  | 0 | Hotham, Matthew |  |  | 26-Jul-23
450315 | 24 MORRIS CRT | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2019 | McAlpine, Robert | Cavanaugh, Danny | 24-Apr-19 |  |  | 37409 | 38327.5 | 37409 | 37409 | Simon Evason | Somervl | 19-Jun-19 | 22-Sep-22 | 17-Jun-19 | 19-Jul-19 | 19-Jul-19 |  | Customer |  | 0
450078 | HWY#50 | 805 - Sandalwood | 150645 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 30363.09 | 500000 | 500000 | Weaver, Thomas |  |  | 10-Feb-22 | [6 empty] | 0
450880 | NEAMSBY STAGE 1 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 15-Mar-21 |  |  | 34999.39 | 284741.41 | 34999.39 | 34999.39 | Richard Cuddy |  | 04-May-21 | 26-Jul-23 | 26-Apr-21 | 29-Apr-21 | 25-May-21 | Customer | Customer |  | 0
450072 | Chinguacousy Park Primary Dist Loop | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2019 | Luimes, John | Miller, Michael | 24-Apr-19 |  |  | 314723.25 | 315549.35 | 314723.25 | 314723.25 | Richard Cuddy |  | 28-Jun-19 | 22-Sep-22 | 20-May-19 | 21-May-19 | 05-Jul-19 |  |  |  | 0
450312 | SNDLWOOD PKWY-MCLAU TO HRTLKE | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Robinson, David |  |  |  | 0 | 20490.43 | 1200000 | 1200000 | Weaver, Thomas |  |  | 20-Sep-22 | [6 empty] | 0
450750 | SCADA-MATE | 805 - Sandalwood | 151010 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 | 0 | 0 | Dre Danieli |  |  | 16-Mar-18 | [6 empty] | 0
450310 | 65 CATHCART CRES | 805 - Sandalwood | 150774 | Inactive | 99 | CANCELLED |  |  | 2022 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 16-May-22
450215 | 100 Sandalwood Pky W | 805 - Sandalwood | 150389 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 21-Jul-21
450942 | VARIOUS LOCATIONS BRAMPTON - Batch 3 - WP Replacement | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 05-Apr-19 |  |  | 79162.99 | 53304.76 | 79162.99 | 79162.99 | John Costa |  | 30-Jul-19 | 22-Oct-20 | 06-May-19 | 07-May-19 | 11-Jul-19 |  | Filler |  | 0
450214 | WCB - STEELES TO MEADOWPINE | 805 - Sandalwood | 151170 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 5320.31 |  | 0 | Dre Danieli |  |  | 26-Jul-23
450309 | 18 AINTREE CRES | 805 - Sandalwood | 150774 | Inactive | 99 | CANCELLED |  |  | 2021 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 18-Aug-21
450605 | 7 BLAIR DR | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 04-Feb-19 |  |  | 31012.33 | 32815.33 | 31012.33 | 31012.33 | Simon Evason |  | 11-Mar-19 | 24-Aug-20 | 06-Mar-19 | 06-Mar-19 | 11-Mar-19 |  |  |  | 0
450941 | VARIOUS LOCATIONS BRAMPTON - Batch 2 - WP Replacement 2019 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 11-Dec-18 |  |  | 157986.12 | 250023.06 | 117486.12 | 157986.12 | Reaburn, Jeff |  | 30-Apr-19 | 24-Aug-20 | 07-Jan-19 | 04-Feb-19 | 25-Apr-19 |  | Filler |  | 40,500.00
450743 | FLINTSHIRE DEVELOPMENT (21T-16005B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 04-Feb-19
450065 | HERITAGE ROAD | 805 - Sandalwood | 150645 | Active | 97 | CANCELLED |  |  | 2023 | Weaver, Thomas | Lemire, Blake |  |  |  | 0 | 20372.21 | 0 | 0 | Weaver, Thomas |  |  | 26-Jul-23 | [6 empty] | 0
450308 | 20 BELMONT DR | 805 - Sandalwood | 150774 | Inactive | 99 | CANCELLED |  |  | 2021 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 18-Aug-21
450602 | GORE (MOSAIK) INC - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Armstrong, Colby | 27-May-21 |  |  | 49480.98 | 504861.2 | 49480.98 | 49480.98 | Richard Cuddy |  | 29-Jul-21 | 23-Jan-23 | 05-Jul-21 | 27-Sep-21 | 15-Oct-21 | Customer | Customer |  | 0
450307 | 329 BALMORAL DR | 805 - Sandalwood | 150774 | Inactive | 99 | CANCELLED |  |  | 2021 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 18-Aug-21
450301 | #1 HWY 7 & CREDITVIEW RD | 805 - Sandalwood | 150389 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 09-Feb-22
450937 | 25 VAN KIRK DR AND REGAN RD - tx | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Casey, Ryan | 07-Nov-18 |  |  | 73670.79 | 51581.46 | 73670.79 | 73670.79 | Simon Evason |  | 18-Apr-19 | 24-Aug-20 | 15-Apr-19 | 21-Apr-19 | 21-Apr-19 |  |  |  | 0
450864 | GEORGIAN MAYFIELD (21T-16003B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | HL | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 3961.1 |  | 0 | Weaver, Thomas |  |  | 26-Jul-23
450210 | BRAMPTON (ZAYO - SENTREX) | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2021 |  | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 12-Apr-21
450731 | TORBRAM ROAD & QUEEN STREET | 805 - Sandalwood | 151635 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Lemire, Blake |  |  |  | 0 | 77009.93 |  | 0 | Weaver, Thomas |  |  | 20-Sep-22
450862 | ICELAND POPPY TRAIL | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Armstrong, Colby | 14-May-19 |  |  | 16345.26 | 78843.28 | 16345.26 | 16345.26 | Richard Cuddy |  | 13-Jun-19 | 11-Jan-22 | 10-Jun-19 | 02-Aug-19 | 02-Aug-19 |  | Customer |  | 0
450209 | 2019 Pole Replacement - Batch #6 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Casey, Ryan | 17-Dec-18 |  |  | 24807.69 | 70765.72 | 24807.69 | 24807.69 | Reaburn, Jeff |  | 06-May-19 | 24-Aug-20 | 29-Apr-19 | 04-Feb-19 | 05-Feb-19 |  | Filler |  | 0
450298 | DIXIE RD & MAYFIELD RD - Subdivision | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Erzek, Ryan | 23-Oct-18 |  |  | 253144.23 | 975911.73 | 253144.23 | 253144.23 | Richard Cuddy |  | 30-Apr-19 | 27-Jun-23 | 02-Jan-19 | 02-Jan-19 | 06-Aug-19 |  | Customer |  | 0
450728 | WILLIAMS PKWY-MCLAUGHLN /NORTH | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Lemire, Blake |  |  |  | 0 | 209376.08 | 0 | 0 | Weaver, Thomas |  |  | 25-Jul-22 | [6 empty] | 0
450855 | 20 WESTWYN COURT | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Ferry, Rodnne | 03-May-19 |  |  | 94332.63 | 63757.26 | 94332.63 | 94332.63 | Simon Evason | Somervl | 25-Jun-19 | 11-Jan-22 | 06-Jun-19 | 31-May-19 | 07-Oct-19 |  | Customer |  | 0
450208 | Goreway Dr. Phase 1 | 805 - Sandalwood | 151648 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 | 0 | 0 | Weaver, Thomas |  |  | 24-Oct-17 | [6 empty] | 0
450207 | 45 Railroad St | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Gaurav | Ferry, Rodnne | 06-May-19 |  |  | 123323.16 | 112272.08 | 123323.16 | 123323.16 | Simon Evason | Somervl | 19-Jul-19 | 22-Mar-23 | 08-Jul-19 | 08-Oct-19 | 22-Nov-19 |  | Customer |  | 0
450852 | AIRPORT RD & COUNTRYSIDE DR | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Erzek, Ryan | 23-Oct-18 |  |  | 63748.18 | 72762.42 | 63748.18 | 63748.18 | Reaburn, Jeff |  | 04-Jan-19 | 24-Aug-20 | 27-Dec-18 | 07-Dec-18 | 04-Mar-19 |  | Locates |  | 0
450206 | 2019 Pole Replacement - Batch #5 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 06-May-19 |  |  | 206050.6 | 182153.24 | 206050.6 | 206050.6 | John Costa |  | 30-Nov-19 | 15-Nov-21 | 02-Jul-19 | 11-Jun-19 | 26-Nov-19 |  | Filler |  | 0
450849 | Forestside Block 5 Townhomes | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Armstrong, Colby | 06-May-19 |  |  | 210918.79 | 128743.76 | 210918.79 | 210918.79 | Richard Cuddy |  | 04-Oct-19 | 29-Dec-20 | 23-Sep-19 | 03-Sep-19 | 09-Sep-19 |  |  |  | 0
450287 | 2239 Bovaird Dr W | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Ferry, Rodnne | 04-Dec-18 |  |  | 7403 | 21820.95 | 7403 | 7403 | Simon Evason |  | 07-Jan-19 | 24-Aug-20 | 04-Jan-19 | 11-Jan-19 | 18-Jan-19 |  | Customer |  | 0
450719 | 5227 MAYFIELD DR | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 05-Mar-18 |  |  | 5876.72 | 2665.32 | 5876.72 | 5876.72 | Simon Evason |  | 26-Mar-18 | 24-Aug-20 | 26-Mar-18 | 29-Mar-18 | 23-May-19 |  | Customer |  | 0
450848 | SE CRNR OF MAYFIELD & KENNEDY | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | Lemire, Blake |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 23-Jul-18
450583 | 200 FIRST GULF BLVD. | 805 - Sandalwood | 150389 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 3556.54 |  | 0 | Dre Danieli |  |  | 19-Dec-17
450712 | STEELES AVE-MISS.RD TO CHING | 805 - Sandalwood | 150645 | Active | HL | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 10167.77 | 500000 | 500000 | Weaver, Thomas |  |  | 26-Jul-23 | [6 empty] | 0
450847 | ALLOA GREEN (WEST) 21T-17001B - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 16-Aug-21 |  |  | 35823.04 | 185195.54 | 35823.04 | 35823.04 | Richard Cuddy |  | 04-Oct-21 | 25-Jan-23 | 27-Sep-21 | 08-Dec-21 | 08-Dec-21 |  | Customer |  | 0
450285 | DENFORD PH 4 (21T-05018B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Henry Gamboa |  |  | 14-Dec-17
450846 | WALNESS (EAST) 21T-11011B - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 16-Aug-21 |  |  | 76860.09 | 691540.5 | 76860.09 | 76860.09 | Richard Cuddy |  | 04-Oct-21 | 26-Jan-23 | 20-Sep-21 | 23-Aug-21 | 10-Dec-21 |  | Customer |  | 0
450198 | KENNEDY RD N, S OF BOVAIRD DR - 2019 Viper SW #6 | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 13-Mar-19 |  | 1 | 95000 | 101327 | 95000 | 95000 | Reaburn, Jeff |  | 15-Nov-19 | 20-Jul-20 | 03-Jun-19 | 06-Aug-19 | 18-Oct-19 |  |  |  | 0
450709 | GOREWAY DR & COUNTRYSIDE DR | 805 - Sandalwood | 151648 | Active | HL | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 45094.48 |  | 0 | Dre Danieli |  |  | 26-Jul-23
450196 | BOVAIRD DR & HWY 410 - 2019 Viper SW #5 | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 13-Mar-19 |  | 1 | 95000 | 132265.6 | 95000 | 95000 | Reaburn, Jeff |  | 15-Dec-19 | 29-Oct-20 | 03-Sep-19 | 06-Aug-19 | 04-Dec-19 |  |  |  | 0
450532 | The Gore Rd and Beamish Crt - Pole Relocate | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Robinson, David | 29-Aug-19 |  |  | 47623.71 | 44444.02 | 47623.71 | 47623.71 | Nichol, Sandi | A&W | 27-Sep-19 | 24-Aug-20 | 23-Sep-19 | 16-Sep-19 | 04-Nov-19 |  |  |  | 0
450282 | 176 MAIN ST S | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 2929.6 |  | 0 | Dre Danieli |  |  | 19-Dec-17
450708 | GOREWAY DR & CASTLEMORE RD | 805 - Sandalwood | 151648 | Active | 98 | ANALYZE |  |  | 2023 | Watters, Maxwell | Lemire, Blake | 12-Apr-21 |  |  | 5001108.62 | 4797312.85 | 4903235.67 | 5001108.62 | AW Group | A&W | 01-Mar-22 | 26-Jul-23 | 01-Jun-21 | 31-May-21 | 12-Jan-23 |  | Customer |  | 97,872.95
450844 | TACC HOLBORN - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Armstrong, Colby | 22-Oct-20 |  |  | 939810.5 | 787018.95 | 939810.5 | 939810.5 | Richard Cuddy | Transpw | 22-Mar-21 | 26-Jul-23 | 07-Dec-20 | 27-Nov-20 | 12-May-21 |  | Customer |  | 0
450494 | ASHLEY OAKS KINGSHOTT TOWNHOMES - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 30-Sep-21 |  |  | 27222.88 | 166039.6 | 27222.88 | 27222.88 | Richard Cuddy |  | 03-Nov-21 | 23-Jan-23 | 01-Nov-21 | 18-Nov-21 | 18-Nov-21 |  | Customer |  | 0
450280 | CUMBERLAND DR/BRISCO ST - 2019 Pole Batch #20 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 06-Aug-20 |  |  | 665148.01 | 534030.36 | 665148.01 | 665148.01 | Reaburn, Jeff | A&W | 11-Dec-20 | 17-Jan-22 | 06-Oct-20 | 22-Oct-20 | 28-Jan-21 | COVID19 | COVID19 |  | 0
450690 | 5907 Steeles Ave E | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Ferry, Rodnne | 14-Feb-19 |  |  | 84832.45 | 74037.56 | 84832.45 | 84832.45 | Simon Evason |  | 25-Mar-19 | 11-Jan-22 | 11-Mar-19 | 28-Feb-19 | 08-Aug-19 |  | Customer |  | 0
450194 | Torbram Rd - 2019 OH Portion | 805 - Sandalwood | 150375 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Miller, Michael | 07-Dec-18 |  |  | 635143 | 1001525.96 | 635143 | 635143 | Nichol, Sandi | A&W | 12-Apr-19 | 24-Aug-20 | 07-Jan-19 | 14-Jan-19 | 05-Apr-19 |  |  |  | 0
450688 | 3455 Queen Street E | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE | High | Comm | 2021 | Rao, Gaurav | Cavanaugh, Danny | 01-Aug-19 |  |  | 142528.63 | 129181.89 | 142528.63 | 142528.63 | Simon Evason | Somervl | 28-Oct-19 | 26-Jul-23 | 15-Oct-19 | 18-Jun-20 | 05-Mar-21 | Customer | Customer |  | 0
450489 | 81 STAFFORD DRIVE | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 03-Mar-20 |  |  | 20719.41 | 11643.42 | 20719.41 | 20719.41 | Simon Evason |  | 01-May-20 | 13-May-22 | 27-Apr-20 |  |  | COVID19 | COVID19 |  | 0
450277 | 2019 Pole Batch #9 - EDGEMONT DR/CHURCH ST E | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Miller, Michael | 17-Dec-18 |  |  | 51277.27 | 144836.59 | 51277.27 | 51277.27 | John Costa |  | 25-Apr-19 | 24-Aug-20 | 01-Apr-19 | 11-Mar-19 | 04-Apr-19 |  | Filler |  | 0
450841 | 275 GARDEN BROOK TRAIL | 805 - Sandalwood |  | Active | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 15-Oct-18 |  |  | 106379.9 | 141245.72 | 106379.9 | 106379.9 | Simon Evason | Transpw | 12-Nov-18 | 24-Aug-20 | 05-Nov-18 | 22-Oct-18 | 26-Feb-19 |  | Customer |  | 0
450687 | 180 Veterans Dr | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2019 | Rao, Gaurav | Bojanic, Dusan | 14-Dec-18 |  |  | 54002.28 | 149164.55 | 54002.28 | 54002.28 | Simon Evason |  | 23-Jan-19 | 26-Jul-23 | 14-Jan-19 | 18-Jan-19 | 12-Apr-19 |  | Customer |  | 0
450480 | 8 GRAFTON CRES | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2019 | McAlpine, Robert | Cavanaugh, Danny | 25-Jun-19 |  |  | 4176 | 7631.61 | 4176 | 4176 | Brian Erskine |  | 25-Jun-19 | 22-Sep-22 | 25-Jun-19 | 02-Jul-19 | 02-Jul-19 |  | Customer |  | 0
450834 | FINANCIAL DR N.SEAPINES/MINER | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Robinson, David | 01-Apr-19 |  |  | 0 | 18656.15 |  | 0 | Reaburn, Jeff |  | 02-Apr-19 | 24-Aug-20 | 02-Apr-19 | 01-Apr-19 | 02-Apr-19
450275 | CHURCH ST E - 2019 Pole Batch #2 | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 05-Dec-18
450446 | MAYFIELD RD-DIXIE TO BRAMALEA | 805 - Sandalwood | 151806 | Active | HL | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 4487.67 |  | 0 | Dre Danieli |  |  | 26-Jul-23
450681 | 5 NEVETS RD | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 22-Jun-18 |  |  | 59638 | 90892.62 | 59638 | 59638 | Simon Evason |  | 13-Aug-18 | 24-Aug-20 | 01-Aug-18 | 02-Jan-19 | 10-Jan-19 |  | Customer |  | 0
450831 | 45 RAILROAD | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne | 20-Nov-18 |  |  | 8135 | 7225.85 | 8135 | 8135 | Simon Evason |  | 21-Dec-18 | 24-Aug-20 | 20-Dec-18 | 19-Dec-18 | 19-Mar-19 |  |  |  | 0
450186 | SUN PAC BLVD BLOCK 1, 2 & 3 | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 1327.43 |  | 0 | Dre Danieli |  |  | 19-Dec-17
450680 | HONI ROW - HERITAGE TO WINSTON | 805 - Sandalwood | 151175 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 03-Jul-20 |  |  | 0 | 6893.74 | 0 | 0 | Dre Danieli |  |  | 13-Sep-23 | [6 empty] | 0
450184 | ROAD AUTHORITY - POLE RELOCATIONS - REGION OF PEEL - DIXIE RD & COUNTRYSIDE DR | 805 - Sandalwood | 151807 | Active | 84 | ACTIVE | High | Infrast | 2023 | Watters, Maxwell | Celic, Dusan | 29-Jan-20 |  |  | 1678788.66 | 1039335.76 | 1678788.66 | 1678788.66 | AW Group | A&W | 03-Jul-20 | 26-Jul-23 | 02-Mar-20 | 04-May-20 |  | MC/PUCC Permit | Customer |  | 0
450828 | 2700 NORTH PARK DR. | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Gaurav | Cavanaugh, Danny | 05-Oct-18 |  |  | 58915 | 44814.9 | 58915 | 58915 | Simon Evason |  | 30-Nov-18 | 22-Sep-22 | 15-Oct-18 | 15-Oct-18 | 22-Jul-19 |  | Customer |  | 0
450442 | 8733 HERITAGE RD | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Robinson, David | 12-Jun-19 |  |  | 6500 | 9303.94 | 6500 | 6500 | Nichol, Sandi |  | 09-Jul-19 | 28-Dec-20 | 08-Jul-19 | 08-Jul-19 | 08-Jul-19 |  |  |  | 0
450679 | HERITAGE HONI ROW TO HWY 407 | 805 - Sandalwood | 151170 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 57917.01 | 0 | 0 | Hotham, Matthew |  |  | 26-Jul-23 | [6 empty] | 0
450271 | 7900 McLaughlin Rd | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 07-Dec-20 |  |  | 35821.93 | 89395.52 | 35821.93 | 35821.93 | Simon Evason | Somervl | 29-Jan-21 | 22-Sep-22 | 18-Jan-21 | 06-Jan-21 | 26-Jan-21 |  |  |  | 0
632971 | JOINT USE PERMIT #HB2019-001 - BOVAIRD DRIVE WEST - BRAMPTON | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 01-Dec-20 |  |  | 18704.55 | 15392.42 | 18704.55 | 18704.55 | John Costa |  | 21-Jan-21 | 30-May-22 | 18-Jan-21 | 25-Feb-21 | 01-Apr-21 | Locates | Weather |  | 0
450430 | 25 PEEL CENTRE DR. | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | McAlpine, Robert | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Hotham, Matthew |  |  | 02-Nov-21
450821 | 6401 MAYFIELD ROAD | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 29-Jul-20 |  |  | 91204.55 | 82018.11 | 91204.55 | 91204.55 | Simon Evason | Somervl | 15-Sep-20 | 26-Jul-23 | 03-Sep-20 | 22-Apr-21 | 08-Oct-21 | Customer | Customer |  | 0
450675 | QUEEN & MAIN ST | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2023 | Watters, Maxwell | Lemire, Blake |  |  |  | 0 | 124909 |  | 0 | Weaver, Thomas |  |  | 28-Mar-23
450425 | 9715 WINSTON CHURCHILL | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 26-Aug-20 |  |  | 85433.1 | 89942.93 | 85433.1 | 85433.1 | Simon Evason | Somervl | 05-Oct-20 | 22-Sep-22 | 28-Sep-20 | 05-Nov-20 | 10-Jun-21 | Customer | Customer |  | 0
450269 | Goreway Grade Separation | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Robinson, David | 21-Mar-18 |  |  | 398190.77 | 1357111 | 398190.77 | 398190.77 | Reaburn, Jeff |  | 11-May-18 | 24-Aug-20 | 03-Apr-18 | 05-Apr-18 | 18-Jan-19 |  |  |  | 0
450165 | BRAMALEA RD-ETR 407 | 805 - Sandalwood | 151535 | Inactive | 99 | CANCELLED |  |  | 2022 | Tobin, Michael | Chopra, Rabinder |  |  |  | 0 | 30874.93 | 0 | 0 | Weaver, Thomas |  |  | 05-Jul-22 | [6 empty] | 0
450164 | 200 EDGEWARE RD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2019 | Rao, Gaurav | Cavanaugh, Danny | 14-Jun-19 |  |  | 89810 | 82610.27 | 89810 | 89810 | Simon Evason | Somervl | 09-Aug-19 | 26-Jul-23 | 22-Jul-19 | 03-Dec-19 | 09-Dec-19 |  | Customer |  | 0
450665 | HWY 410 @ VODDEN ST.EAST | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Robinson, David | 23-Jan-19 |  |  | 425000 | 953200.02 | 425000 | 425000 | Richard Cuddy | Somervl | 08-Mar-19 | 04-Apr-23 | 18-Feb-19 | 18-Feb-19 | 06-Jun-19 |  |  |  | 0
450816 | 3 St.Patrick Rd | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 09-Nov-18 |  |  | 16528.38 | 24219.47 | 16528.38 | 16528.38 | Simon Evason |  | 07-Dec-18 | 24-Aug-20 | 03-Dec-18 | 19-Feb-19 | 19-Feb-19 |  | Customer |  | 0
450402 | 9353 Winston Churchill Blvd - OH PCB Tx. Replacement | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Miller, Michael | 20-Jun-19 |  |  | 49391.71 | 28590.82 | 49391.71 | 49391.71 | John Costa |  | 23-Aug-19 | 15-Nov-21 | 05-Aug-19 | 16-Jul-19 | 02-Aug-19 |  |  |  | 0
450664 | VARIOUS LOCATIONS | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 04-Apr-19 |  |  | 13924.5 | 23872.89 | 13924.5 | 13924.5 | Brian Erskine |  | 30-May-19 | 20-Jul-20 | 15-May-19 | 15-Apr-19 | 15-Apr-19 |  |  |  | 0
450264 | LOTEIGHT CONTHREE (21T-10004B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 70 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Henry Gamboa |  |  | 14-Dec-17
450401 | 2755 WANLESS - Dr. - OH PCB Tx. Replacement | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Miller, Michael | 20-Jun-19 |  |  | 15218.52 | 21903.81 | 15218.52 | 15218.52 | John Costa |  | 30-Sep-19 | 19-Nov-20 | 26-Aug-19 | 14-Aug-19 | 13-Sep-19 |  | Filler |  | 0
450662 | 200 RIVERMONT RD | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 20-Jun-18 |  |  | 70326.54 | 72793.3 | 59255 | 70326.54 | Simon Evason |  | 11-Jul-18 | 26-Jul-23 | 03-Jul-18 | 03-Jul-18 | 14-Jun-19 |  | Customer |  | 11,071.54
450394 | 22 Bowman Ave | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 02-May-19 |  |  | 15000 | 7491.72 | 15000 | 15000 | Richard Cuddy | N/A | 27-May-19 | 22-Mar-21 | 27-May-19 | 27-May-19 | 30-May-19 |  |  |  | 0
450392 | 5 PRECIDIO CRT | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2019 | Rao, Gaurav | Cavanaugh, Danny | 17-Jul-19 |  |  | 105660.6 | 38419.3 | 105660.6 | 105660.6 | Simon Evason |  | 03-Sep-19 | 26-Jul-23 | 03-Sep-19 | 06-Sep-19 | 09-Sep-19 |  | Customer |  | 0
450661 | STEELES AND MALTA AVE | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Erzek, Ryan | 01-Nov-18 |  |  | 51585.31 | 131250.26 | 51585.31 | 51585.31 | Richard Cuddy |  | 09-Jan-19 | 24-Aug-20 | 17-Dec-18 | 08-Jan-19 | 01-Mar-19 |  | Customer |  | 0
450792 | ISLIP (21T-14003B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 16-Apr-18
450136 | EMERY BRAM. HEARTLAKE - SUBD ICI EDS | 805 - Sandalwood | 151673 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 11-Dec-20 |  |  | 185954.33 | 552531.45 | 185954.33 | 185954.33 | Richard Cuddy |  | 09-Apr-21 | 27-Jun-23 | 01-Feb-21 | 22-Feb-21 | 20-Aug-21 | Customer | Customer |  | 0
450370 | 10 & 20 LIGHTBEAM TERRACE | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 02-Nov-21
632972 | JOINT USE PERMIT #HB2019-002 - GOREWAY DRIVE - BRAMPTON | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 20-Nov-20 |  |  | 24103.48 | 19154.6 | 24103.48 | 24103.48 | John Costa |  | 12-Jan-21 | 30-May-22 | 04-Jan-21 | 26-Apr-21 | 04-Jun-21 | Locates | Lines |  | 0
632973 | JOINT USE PERMIT #HB2019-003 - HWY 50 - BRAMPTON | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 30-Oct-20 |  |  | 37990.03 | 37143.04 | 37990.03 | 37990.03 | John Costa |  | 09-Dec-20 | 16-Jun-22 | 07-Dec-20 | 18-Jan-21 | 26-Apr-21 | Locates | Lines |  | 0
633118 | Pole Replacement Batch # 1 | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 13-Aug-19
450905 | GO ELEC RER-CONFLICT KT#30 | 805 - Sandalwood | 150490 | Inactive | 99 | CANCELLED |  |  | 2022 | Khuu, Philander | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 22-Sep-22
450814 | ELIZABETH ST N 7 NELSON ST | 805 - Sandalwood | 150490 | Inactive | 99 | CANCELLED |  |  | 2022 | Newitt, Andrew | Lemire, Blake |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 23-Jun-22
634227 | COUNTRYSIDE VILLAGES 2 (21T-12019B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Armstrong, Colby | 07-Jul-21 |  |  | 331972.14 | 275685.36 | 331972.14 | 331972.14 | Richard Cuddy | Transpw | 07-Sep-21 | 26-Jul-23 | 09-Aug-21 | 19-Oct-21 | 11-Feb-22 | Customer | Customer |  | 0
634443 | TANYAVILLE PHASE 2 - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Armstrong, Colby | 09-Dec-20 |  |  | 37077.72 | 190529.16 | 37077.72 | 37077.72 | Richard Cuddy |  | 06-Apr-21 | 24-Jan-22 | 29-Mar-21 | 29-Jan-21 | 29-Jan-21 |  |  |  | 0
450274 | Heritage Road Pole relocation – six poles | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Erzek, Ryan | 19-Dec-17 |  |  | 183575.09 | 375793.04 | 98652.21 | 183575.09 | Reaburn, Jeff |  | 30-Mar-18 | 17-Aug-20 | 15-Jan-18 | 14-Feb-18 | 01-Apr-19 |  | Customer |  | 84,922.88
450668 | LAGERFELD DR & CREDITVIEW RD | 805 - Sandalwood | 150674 | Active | 99 | COMPLETE |  |  | 2019 |  | Erzek, Ryan | 26-Mar-19 |  |  | 69356.74 | 52042.48 | 69356.74 | 69356.74 | Richard Cuddy |  | 27-May-19 | 26-Jul-23 | 01-May-19 | 04-Apr-19 | 13-Sep-19 |  |  |  | 0
450786 | BRAMALEA RD @ BRAMALEA GO | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Robinson, David | 05-Dec-18 |  |  | 358032.47 | 468291.42 | 350000 | 358032.47 | Reaburn, Jeff | A&W | 25-Jan-19 | 24-Aug-20 | 07-Jan-19 | 17-Dec-18 | 08-Feb-19 |  | Customer |  | 8,032.47
450476 | COUNTRYSIDE DR | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Robinson, David | 05-Sep-19 |  |  | 0 | 17377.97 |  | 0 | Reaburn, Jeff |  | 05-Sep-19 | 17-Aug-22 | 05-Sep-19 | 07-Oct-19 | 07-Oct-19
450345 | UTILITY CORRIDOR ON VALLEYWAY DR - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 15-Oct-21 |  |  | 335568.48 | 352101.05 | 335568.48 | 335568.48 | Reaburn, Jeff | A&W | 30-Nov-21 | 05-May-22 | 01-Nov-21 | 29-Oct-21 | 23-Dec-21 |  | Lines |  | 0
450785 | COUNTRYSIDE DR/MCVEAN DR | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Robinson, David | 16-Nov-18 |  |  | 33000 | 33846.48 | 33000 | 33000 | Reaburn, Jeff |  | 28-Dec-18 | 24-Aug-20 | 27-Dec-18 | 31-Dec-18 | 02-Jan-19 |  |  |  | 0
450171 | HEARTLAKE RD S.OF GLIDDEN RD | 805 - Sandalwood | 150674 | Active | 40 | H8 | Low | Infrast | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 07-Dec-18
450962 | BOVAIRD DR W AND BRISDALE DR | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2021 | Lacombe, Joel | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 28-Jun-21
450614 | HERITAGE RD AND FINANCIAL DR | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lemire, Blake | 26-Feb-19 |  |  | 3200 | 5783.6 | 3200 | 3200 | Brian Erskine |  | 25-Mar-19 | 24-Aug-20 | 25-Mar-19 | 04-Mar-19 | 04-Mar-19 |  |  |  | 0
450730 | CHINGUACOUSY & WANLESS - Road Widening - COB | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2019 | Kafel, Krzysztof | Watters, Maxwell | 25-Jan-19 |  |  | 920764.85 | 920106.54 | 815284.06 | 920764.85 | Reaburn, Jeff | A&W | 30-May-19 | 22-Sep-22 | 22-Feb-19 | 11-Mar-19 | 04-Dec-19 |  |  |  | 105,480.79
634038 | CREDITVIEW /MAYFIELD RD EASEMENT - OH POLE LINE CIRCUIT EXTN | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 22-Oct-19
633536 | C55 150411 ESTIMATE 42M64 MISSISSAUGA RD - WILLIAMS PKY TO EMBLETON RD - PHASE 2 | 805 - Sandalwood | 150411 | Active | HD | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 17586.28 |  | 0 | Dre Danieli |  |  | 26-Jul-23
633574 | 2021 TX RENEWAL-GRID G2-7 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 11-Jan-21 | 7 |  | 74363.84 | 62236.55 | 74363.84 | 74363.84 | Richard Cuddy |  | 31-Aug-21 | 16-Mar-22 | 23-Aug-21 | 02-Aug-21 | 31-Aug-21 |  |  |  | 0
633575 | 2021 TRANSFORMER REPLACEMENTS-GRID G3 | 805 - Sandalwood | 150285 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 17-Sep-19 |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 16-Sep-19
633579 | 2021 TX RENEWAL-GRID J3-4 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 22-Dec-20 | 4 |  | 61149.95 | 50180.9 | 61149.95 | 61149.95 | Richard Cuddy | Somervl | 09-Apr-21 | 16-Mar-22 | 29-Mar-21 | 08-Mar-21 | 04-Aug-21 |  | Lines |  | 0
633572 | 2021 TX RENEWAL-GRID F4-1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 01-Mar-21 | 1 |  | 11631.69 | 12342.07 | 11631.69 | 11631.69 | Richard Cuddy |  | 01-Nov-21 | 16-Mar-22 | 01-Nov-21 | 22-Oct-21 | 22-Oct-21 |  |  |  | 0
633573 | 2021 TX RENEWAL-GRID F5- 1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 01-Mar-21 | 1 |  | 11424.74 | 9603.98 | 11424.74 | 11424.74 | Richard Cuddy |  | 01-Nov-21 | 16-Mar-22 | 01-Nov-21 | 19-Oct-21 | 19-Oct-21 |  |  |  | 0
633571 | 2021 TX RENEWAL-GRID J3-2 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 2 |  | 17460.3 | 23611.62 | 17460.3 | 17460.3 | Richard Cuddy |  | 04-Oct-21 | 15-Feb-22 | 01-Oct-21 | 21-Oct-21 | 21-Oct-21 | Lines | Lines |  | 0
633576 | 2021 TX RENEWAL-GRID G5-1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 01-Mar-21 | 1 |  | 11976.85 | 9598.54 | 11976.85 | 11976.85 | Richard Cuddy |  | 02-Nov-21 | 19-Apr-22 | 02-Nov-21 | 19-Oct-21 | 18-Oct-21 |  |  |  | 0
633570 | 2021 TX RENEWAL-GRID I3-1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 1 |  | 13281.61 | 11964.31 | 13281.61 | 13281.61 | Richard Cuddy |  | 30-Sep-21 | 23-Feb-22 | 30-Sep-21 | 31-Aug-21 | 31-Aug-21 | Lines | Lines |  | 0
633564 | 2021 TX RENEWAL-GRID J2-5 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 5 |  | 53931.06 | 70292.99 | 53931.06 | 53931.06 | Richard Cuddy | Somervl | 08-Oct-21 | 16-Mar-22 | 04-Oct-21 | 15-Oct-21 | 16-Dec-21 | Lines | Lines |  | 0
633568 | 2021 TX RENEWAL-GRID I2-2 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 2 |  | 24953.29 | 22400.05 | 24953.29 | 24953.29 | Richard Cuddy |  | 30-Sep-21 | 23-Feb-22 | 29-Sep-21 | 09-Sep-21 | 09-Sep-21 |  |  |  | 0
633567 | 2021 TX RENEWAL-GRID E3-3 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 3 |  | 33965.6 | 32448.47 | 33965.6 | 33965.6 | Richard Cuddy |  | 29-Sep-21 | 23-Feb-22 | 27-Sep-21 | 02-Sep-21 | 02-Sep-21 |  |  |  | 0
633578 | 2020 TX RENEWAL-GRID I3-2 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 01-Mar-21 | 2 |  | 37195.32 | 55370.2 | 37195.32 | 37195.32 | Richard Cuddy | Somervl | 08-Nov-21 | 10-May-23 | 03-Nov-21 | 13-Dec-21 | 16-Dec-21 | Customer | Customer |  | 0
633819 | INSTALL AUTOMATED SD SG AT SITE#116 | 805 - Sandalwood | 151104 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael | 01-Oct-19 |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 01-Oct-19
633580 | 2021 TX RENEWAL-GRID K2-1 TX | 805 - Sandalwood | 150285 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 01-Mar-21 | 1 |  | 11394.14 | 1229.69 | 11394.14 | 11394.14 | Richard Cuddy |  | 02-Nov-21 | 26-Jul-23 | 02-Nov-21 | [5 empty] | 0
450918 | HERITAGE RD, S OF EMBLETON | 805 - Sandalwood | 150484 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 04-Dec-19 |  |  | 549100.91 | 597433 | 412957.07 | 549100.91 | Reaburn, Jeff | Somervl | 09-Jul-20 | 26-Jul-23 | 01-Apr-20 | 06-Jul-20 | 22-Mar-21 | COVID19 | Customer |  | 136,143.84
634502 | HB2018-017, BELL - THE GORE RD | 805 - Sandalwood | 151538 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 22-Jun-21 |  |  | 50376.04 | 50008.66 | 50376.04 | 50376.04 | John Costa | K-Line | 30-Jul-21 | 26-Jul-23 | 19-Jul-21 | 13-Jul-21 | 10-Aug-21 |  | Locates |  | 0
634510 | 2019 EMERGING - SW 44-31 | 805 - Sandalwood | 150784 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 13-Oct-15
450528 | 209 QUEEN ST E | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE | VerHigh | Res-ICI | 2021 | Rao, Gaurav | Bojanic, Dusan | 16-Mar-20 |  |  | 478353.35 | 541980.43 | 478353.35 | 478353.35 | Simon Evason | Transpw | 25-Jun-20 | 26-Jul-23 | 25-May-20 | 01-Jun-20 | 24-Apr-21 | Customer | Customer |  | 0
636160 | SWGR CONESTOGA DR, N OF SANDALWOOD | 805 - Sandalwood | 151449 | Active | 70 | ACTIVE |  |  | 2023 | Nichol, Alexander | D'Ermes, Michael |  | 5 |  | 0 | 0 |  | 0 | Dre Danieli
636179 | 2021 POLE RENEWAL-CN PROPERTY-POLE REMOVAL- 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 08-Dec-20 | 1 |  | 9383.89 | 2929.08 | 9383.89 | 9383.89 | John Costa |  | 09-Feb-21 | 21-Apr-22 | 08-Feb-21 | 06-May-21 | 06-May-21 | MC/PUCC Permit | MC/PUCC Permit |  | 0
636232 | 85 DEVON RD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 01-Sep-22
636527 | 2021 SWITCHGEAR RENEWAL - SITE# 118 - FERNFOREST DR, S OF SANDALWOOD | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 28-Jan-21 | 1 |  | 163535.67 | 205033.15 | 163535.67 | 163535.67 | Richard Cuddy |  | 06-Jul-21 | 29-Apr-22 | 14-Jun-21 | 22-Nov-21 | 10-Dec-21 | Materials |  |  | 0
636586 | 7324 KENNEDY RD S / BRAM / NS / 3PH PAD (TEMPORARY) | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 26-Mar-21 |  |  | 76306.82 | 78737.11 | 76306.82 | 76306.82 | Simon Evason |  | 05-May-21 | 22-Sep-22 | 26-Apr-21 | 22-Mar-21 | 31-Mar-21 |  |  |  | 0
636837 | JOINT USE PERMIT HB2020-015- NORTH PARK DR. S/O LETHBRIDGE DR. | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 30-Mar-21 |  |  | 13691.13 | 9113.78 | 13691.13 | 13691.13 | John Costa |  | 28-Apr-21 | 11-May-22 | 27-Apr-21 | 27-Apr-21 | 29-Apr-21 |  |  |  | 0
636840 | 4KV CONV PH3D - (MAIN ST S & GUEST ST) | 805 - Sandalwood | 151138 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 11-Jan-21 |  |  | 238888.89 | 225949.94 | 238888.89 | 238888.89 | Reaburn, Jeff | Transpw | 16-Jun-21 | 24-Jan-22 | 03-May-21 | 03-May-21 | 25-May-21 | Contractor |  |  | 0
636869 | 136M1 O/H FEEDER EGRESS - GOREWAY RD (HUMBERWEST PKWY TO YORKLAND BLVD) | 805 - Sandalwood | 150494 | Inactive | 99 | CANCELLED |  |  | 2022 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 13-Jul-22
636871 | STEELES AVE AND HURONTARIO ST GTT | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2022 | Pelleja, Emily | Lemire, Blake |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 11-Jul-22
636894 | 9280 AND 9300 GOREWAY DR - 27.6KV TO 1500 KVA TX | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 28-Aug-20 |  |  | 117764.1 | 100914.95 | 110264.1 | 117764.1 | Simon Evason | Somervl | 27-Oct-20 | 26-Jul-23 | 28-Sep-20 | 09-Oct-20 | 15-Apr-21 | Customer | Customer |  | 7,500.00
636898 | ATTMAR DR AND THE GORE RD - FEEDER EXTENSION | 805 - Sandalwood | 152453 | Active | 98 | COMPLETE |  |  | 2021 | Watters, Maxwell | Lemire, Blake | 21-Jan-21 |  |  | 226345.13 | 234073.63 | 200612.13 | 226345.13 | Richard Cuddy | Somervl | 09-Mar-21 | 15-Aug-23 | 22-Feb-21 | 04-Feb-21 | 10-Dec-21 |  | Lines |  | 25,733.00
636997 | 42M43 OH FEEDER EXTENSION - CHINGUACCOUSAY RD (WANLESS TO MAYFIELD) | 805 - Sandalwood | 150494 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637046 | 45 WEST DR - 27.6KV SUPPLY TO 1500 KVA TX | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 16-Oct-20 |  |  | 156206.57 | 169999.99 | 156206.57 | 156206.57 | Simon Evason | Transpw | 11-Dec-20 | 26-Jul-23 | 01-Dec-20 | 25-Jan-21 | 15-Apr-21 | Customer | Customer |  | 0
637068 | 2021 EMERGING PROJECT - 7835 HWY 50 | 805 - Sandalwood | 151449 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 11-Jan-21 | 1 |  | 183598.18 | 180709.79 | 183598.18 | 183598.18 | Richard Cuddy | Transpw | 30-Jun-21 | 26-Jul-23 | 01-Jun-21 | 19-May-21 | 29-Jul-21 |  | Contractor |  | 0
637109 | CONCRETE POLES -CENTRAL NORTH | 805 - Sandalwood | 150284 | Inactive | 99 | CANCELLED |  |  | 2021 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637110 | WOOD POLES - CENTRAL NORTH | 805 - Sandalwood | 150284 | Inactive | 99 | CANCELLED |  |  | 2021 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637138 | 100 ROCKSPUR COURT | 805 - Sandalwood | 150386 | Active | 98 | CANCELLED |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 8877.6 |  | 0 | Dre Danieli |  |  | 26-Jul-23
637140 | FEEDER CABLE REPLACEMENT GRID H4 - 2021 | 805 - Sandalwood | 151290 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637141 | 2021 POLE RENEWAL-GRID M3- 7 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 07-Dec-20 | 7 |  | 228515.29 | 247753.86 | 228515.29 | 228515.29 | Reaburn, Jeff |  | 18-Feb-21 | 25-Apr-22 | 18-Jan-21 | 06-Apr-21 | 23-Aug-21 | Locates | Locates |  | 0
637142 | 2021 POLE RENEWAL-GRID N5- 4 POLES | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 03-May-21 | 4 | 4 | 84299.73 | 81411.8 | 84299.73 | 84299.73 | John Costa |  | 20-Sep-21 | 10-Aug-23 | 07-Sep-21 | 15-Nov-21 | 31-Dec-21 | Lines | Lines |  | 0
637143 | 2021 POLE RENEWAL-GRID P1- 3 POLES | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637148 | HERITAGE ROAD DEVELOPMENT ENTRANCE POLE RELOCATION | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2021 | Pelleja, Emily | Lemire, Blake | 18-Nov-20 |  |  | 92349.81 | 92654.83 | 70979.47 | 92349.81 | Justin Gregoris |  | 06-Jan-21 | 27-Jun-23 | 14-Dec-20 | 14-Dec-20 | 22-Mar-21 |  | Customer |  | 21,370.34
637170 | COMMUTER DR. - 27.6KV SUPPLY TO ELECTRIC BUS STATION | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 19-Nov-20 |  |  | 171545.44 | 206173.92 | 165328.03 | 171545.44 | Simon Evason | Transpw | 31-Dec-20 | 26-Jul-23 | 17-Dec-20 | 12-Feb-21 | 29-Mar-21 | Customer | Customer |  | 6,217.41
637171 | 1478 QUEEN ST. E.- 27.6KV SUPPLY TO ELECTRIC BUS CHARGING STATION | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 19-Nov-20 |  |  | 107007.93 | 99534.89 | 89507.93 | 107007.93 | Simon Evason | Somervl | 31-Dec-20 | 26-Jul-23 | 17-Nov-20 | 14-Dec-20 | 15-Apr-21 | Customer | Customer |  | 17,500.00
637202 | RELOCATION OF UNDERGROUND 1000 KCMIL CABLE- HUMBERWEST PKWY | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2021 | Pelleja, Emily | Robinson, David | 30-Oct-20 |  |  | 526870.21 | 303489.85 | 526870.21 | 526870.21 | Richard Cuddy | Somervl | 23-Feb-21 | 07-Sep-21 | 07-Dec-20 | 25-Jan-21 | 10-Mar-21 | Customer | Customer |  | 0
637216 | 2021 POLE RENEWAL - P#14 & P#4660 - GRID P1 - 2 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 02-Jun-21 | 2 |  | 41178.45 | 39641.71 | 41178.45 | 41178.45 | John Costa |  | 04-Oct-21 | 25-Apr-22 | 27-Sep-21 | 07-Dec-21 | 15-Dec-21 | Lines | Lines |  | 0
637218 | POLE LINE ENCROACHMENT- #8406 CREDITVIEW RD - | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 07-Sep-20 |  |  | 115000.65 | 126963.23 | 193000.65 | 115000.65 | Reaburn, Jeff | A&W | 30-Jun-21 | 25-Apr-22 | 01-Jun-21 | 10-May-21 | 01-Oct-21 |  | Customer |  | -78,000.00
637233 | 2020 POLE RENEWAL-GRID G2- 1 POLE | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 14-Oct-21 | 1 | 1 | 20274.11 | 14835.06 | 20274.11 | 20274.11 | Reaburn, Jeff | K-Line | 30-Nov-21 | 26-Jul-23 | 15-Nov-21 | 29-Nov-21 | 23-Dec-21 |  |  |  | 0
637234 | 2021 POLE RENEWAL-GRID Q2- 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 03-May-21 | 1 |  | 22829.99 | 15922.18 | 22829.99 | 22829.99 | John Costa |  | 23-Sep-21 | 25-Apr-22 | 21-Sep-21 | 05-Nov-21 | 05-Nov-21 | Lines | Lines |  | 0
637235 | 2020 POLE RENEWAL-GRID I5- 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 18-Feb-22 | 1 | 1 | 29011.81 | 30378.7 | 29011.81 | 29011.81 | K-Line Construction | K-Line | 14-Nov-22 | 02-Mar-23 | 09-Nov-22 | 29-Sep-22 | 30-Sep-22 |  |  |  | 0
637257 | LOST CANYON WAY - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Armstrong, Colby | 14-Jul-21 |  |  | 119297.79 | 100704.23 | 119297.79 | 119297.79 | Richard Cuddy | Transpw | 20-Aug-21 | 23-Jan-23 | 09-Aug-21 | 16-Aug-21 | 20-Aug-21 | Customer |  |  | 0
637352 | FEEDER CABLE REPLACEMENT GRID I3 PHASE 2 - 2023 | 805 - Sandalwood | 151290 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 30-Nov-22 |  |  | 1130305.94 | 87902.05 | 1130305.94 | 1130305.94 | Graham Gegear | Transpw | 29-Aug-23 | 05-Jan-24 | 19-Jun-23 | 05-Jun-23 |  |  |  |  | 0
637353 | FEEDER CABLE REPLACEMENT GRID I3 - 2021 PHASE 1 | 805 - Sandalwood | 151290 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 22-Mar-21 |  |  | 740782.02 | 762747.7 | 740782.02 | 740782.02 | Mark Bobanovic | Transpw | 03-Sep-21 | 26-Jan-23 | 26-Apr-21 | 04-May-21 | 20-Aug-21 | Contractor |  |  | 0
637365 | FEEDER CABLE REPLACEMENT GRID J4 - PH2A (ELECTRICAL) | 805 - Sandalwood | 150572 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 18-Jan-21 |  |  | 330823.1 | 255941.46 | 330823.1 | 330823.1 | Richard Cuddy | Transpw | 31-May-21 | 05-Mar-23 | 15-Apr-21 | 05-Apr-21 | 23-Jul-21 |  | Customer |  | 0
637366 | FEEDER CABLE REPLACEMENT GRID J4 - PH2B (ELECTRICAL&CIVIL) | 805 - Sandalwood | 150572 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 31-Mar-21 |  |  | 2303983.13 | 2257204.01 | 2303983.13 | 2303983.13 | Richard Cuddy | Transpw | 12-Oct-21 | 05-Jul-22 | 01-Jun-21 | 23-Jun-21 | 10-Dec-21 | Contractor |  |  | 0
637367 | 2021 POLE RENEWAL - GRID H1(2 POLES) | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637368 | 2021 POLE RENEWAL - GRID H2(2 POLES) | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637369 | 2023 POLE RENEWAL - GRID I2(1POLE) | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 23-Dec-22 | 1 |  | 29901.48 | 6428.85 | 29901.48 | 29901.48 | Reaburn, Jeff |  | 06-Sep-23 | 06-Sep-23 | 01-Sep-23 | [5 empty] | 0
637370 | 2021 POLE RENEWAL - GRID J4(1POLE) | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637372 | THIS WO IS BEING RE-PURPOSED | 805 - Sandalwood | 150284 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 1088.27 |  | 0 | Dre Danieli |  |  | 26-Jul-23
637373 | 2023 POLE RENEWAL GRID M1-30 (3 POLES) | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 23-Dec-22 | 3 |  | 79546.71 | 19300.97 | 79546.71 | 79546.71 | Graham Gegear |  | 15-Aug-23 | 15-Aug-23 | 01-Aug-23 | [5 empty] | 0
637374 | 2020 POLE RENEWAL GRID O2- 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 02-Jun-21 | 1 |  | 31083.54 | 17213.75 | 31083.54 | 31083.54 | John Costa |  | 08-Oct-21 | 26-Apr-22 | 05-Oct-21 | 15-Nov-21 | 13-Dec-21 | Lines | Lines |  | 0
637382 | 2021POLE RENEWAL GRID O4- 1 POLE | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637383 | 2020 POLE RENEWAL GRID O4-56 (1 POLE) | 805 - Sandalwood | 150284 | Active | HL | H2 |  |  | 2023 | Agostini, Robert | Miller, Michael | 02-Jun-21 | 1 |  | 17364.05 | 10680.95 | 17364.05 | 17364.05 | John Costa |  | 13-Oct-21 | 27-Jul-23 | 12-Oct-21 |  |  | Filler | Filler |  | 0
637384 | 2021 POLE RENEWAL GRID P3- 1 POLE | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637385 | 2021 POLE RENEWAL GRID P4- 1 POLE | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 06-Jan-22
637390 | 1403 QUEEN ST W TOWNHOME DEVT – SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Armstrong, Colby | 13-Jan-22 |  |  | 36225.17 | 310892.58 | 36225.17 | 36225.17 | Richard Cuddy | Conelco | 22-Feb-22 | 22-Jun-23 | 15-Feb-22 | 03-Mar-22 | 20-Dec-22 | Customer | Customer |  | 0
637351 | BOVAIRD DR W & LAGERFELD DR / BRAM / NS / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 06-Jan-21 |  |  | 115135.18 | 66870.92 | 115135.18 | 115135.18 | Simon Evason | Somervl | 05-Mar-21 | 26-Jul-23 | 16-Feb-21 | 25-Jan-21 | 12-Feb-21 |  |  |  | 0
637406 | FEEDER CABLE REPLACEMENT GRID F4-G4 - 2021 | 805 - Sandalwood | 150494 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637415 | 2021 - INSULATOR ORDER - BW | 805 - Sandalwood | 151021 | Active | HL | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637512 | CABLE INJECTION 2021-GRID I3 (CAPITAL BUDGET PROJECT_151318) | 805 - Sandalwood | 151318 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 18-Dec-20 |  |  | 611048.54 | 591428.51 | 611048.54 | 611048.54 | Simon Evason | Nvinium | 31-Aug-21 | 11-Sep-22 | 01-Jun-21 | 01-Mar-21 | 30-May-22 |  | N/A |  | 0
637513 | CABLE INJECTION 2021-GRID G2 (CAPITAL BUDGET PROJECT_151314) | 805 - Sandalwood | 151314 | Active | 95 | ANALYZE |  |  | 2022 | Agostini, Robert | Miller, Michael | 18-Dec-20 |  |  | 461887.84 | 517713.91 | 461887.84 | 461887.84 | Simon Evason | Nvinium | 01-Nov-21 | 26-Jul-23 | 01-Sep-21 | 15-Mar-21 | 04-Jan-23 |  | N/A |  | 0
637515 | CABLE INJECTION 2021-GRID F5 (CAPITAL BUDGET PROJECT_151313) | 805 - Sandalwood | 151313 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael | 15-Dec-20 |  |  | 463032.1 | 476878.27 | 463032.1 | 463032.1 | Novinium Group | Nvinium | 01-Jun-21 | 26-Jul-23 | 29-Mar-21 | 26-Sep-22 |  | Contractor | Contractor |  | 0
637516 | CABLE INJECTION 2021-GRID H2 (CAPITAL BUDGET PROJECT_151316) | 805 - Sandalwood | 151316 | Active | 95 | ANALYZE |  |  | 2022 | Agostini, Robert | Miller, Michael | 18-Dec-20 |  |  | 464304.38 | 578901.03 | 464304.38 | 464304.38 | Simon Evason | Nvinium | 01-Sep-21 | 26-Jul-23 | 02-Jul-21 | 01-Mar-21 | 04-Jan-23 |  | N/A |  | 0
637517 | CABLE INJECTION 2021-GRID E4 (CAPITAL BUDGET PROJECT_151310) | 805 - Sandalwood | 151310 | Active | 95 | ANALYZE |  |  | 2022 | Agostini, Robert | Miller, Michael | 15-Dec-20 |  |  | 469121.8 | 323826.46 | 469121.8 | 469121.8 | Simon Evason | Nvinium | 15-Jul-21 | 26-Jul-23 | 01-Jun-21 | 01-Mar-21 | 04-Jan-23 |  | N/A |  | 0
637518 | CABLE INJECTION 2021-GRID G1 (CAPITAL BUDGET PROJECT_151462) | 805 - Sandalwood | 151462 | Active | 95 | ANALYZE |  |  | 2022 | Agostini, Robert | Miller, Michael | 11-Dec-20 |  |  | 458964.37 | 241221.37 | 458964.37 | 458964.37 | Simon Evason | Nvinium | 16-Jul-21 | 26-Jul-23 | 01-Jun-21 | 06-Apr-21 | 04-Jan-23 |  | N/A |  | 0
637520 | BROOKVALLEY PHASE 2A SUBDIVISION - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Armstrong, Colby | 04-Feb-21 |  |  | 26018.22 | 59172.43 | 26018.22 | 26018.22 | Richard Cuddy |  | 11-Jun-21 | 25-Jan-23 | 07-Jun-21 | 04-Nov-21 | 22-Dec-21 | Customer |  |  | 0
637574 | 4KV CONVERSION PH11-BRAMPTON | 805 - Sandalwood | 151139 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637637 | 180 DELTA PARK BLVD / BRAM / NS / 3PH | 805 - Sandalwood | 150386 | Active | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 27-Nov-20 |  |  | 66416.56 | 60613.19 | 66416.56 | 66416.56 | Simon Evason | Somervl | 12-Jan-21 | 26-Jul-23 | 04-Jan-21 | 05-Jan-21 | 13-Jan-21 | Customer | Customer |  | 0
637679 | 3 EDVAC DR | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 2847.28 |  | 0 | Dre Danieli |  |  | 10-Jul-23
637705 | 24 VODDEN ST. E../ BRAM/ NS00048091/ 3 PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Cavanaugh, Danny | 25-Jun-21 | 1 |  | 62528.46 | 90673.32 | 62528.46 | 62528.46 | Simon Evason | Somervl | 21-Apr-22 | 26-Jul-23 | 11-Apr-22 | 21-Oct-21 | 28-Oct-22 | Customer | Customer |  | 0
637739 | 2021 INSULATOR REPLACEMENT PROGRAM | 805 - Sandalwood | 151021 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 05-Oct-20 |  |  | 353177.94 | 333437.48 | 353177.94 | 353177.94 | John Costa |  | 24-Dec-21 | 10-May-23 | 25-Jan-21 | 02-Apr-21 | 24-Dec-21 | Filler | Filler |  | 0
637748 | 2020 EMERGING PROJECT - 7605 CREDITVIEW RD | 805 - Sandalwood | 150494 | Inactive | 99 | CANCELLED |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 39 | 0 | 0 | 0 | Dre Danieli |  |  | 27-Apr-23 | [6 empty] | 0
637817 | GOREWAY DR PH2.1 COTTRELLE BLVD TO CASTLEMORE RD | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2022 | Pelleja, Emily | Lemire, Blake |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 06-Apr-21
637833 | JOINT USE PERMIT HB2020-026- MAYFIELD ROAD | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 01-Apr-21 |  |  | 8318.87 | 7875.09 | 8318.87 | 8318.87 | John Costa |  | 03-May-21 | 11-May-22 | 03-May-21 | 03-May-21 | 03-May-21 |  |  |  | 0
637868 | HUMBERWEST PKWY AND CASTLEMORE TOWN CENTRE PLAZA ENTRANCE / BRAM / NS / 1-PH | 805 - Sandalwood | 150389 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637881 | 44 WESTWYN CRT | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 27-Apr-21 |  |  | 132377.46 | 139491.55 | 132377.46 | 132377.46 | Simon Evason | Transpw | 14-Jun-21 | 07-Mar-23 | 01-Jun-21 | 13-May-21 | 05-Oct-21 |  | Customer |  | 0
637953 | 2021 DA- S&C ELECTRIC RETROFIT KITS AND 6801M OPERATORS | 805 - Sandalwood | 151104 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
637946 | 2021 EMERGING PROJECT - 45 WEST DR | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 21-Dec-20 |  |  | 35349.92 | 55421.6 | 35349.92 | 35349.92 | John Costa |  | 04-Mar-21 | 16-Jun-22 | 01-Mar-21 | 01-Mar-21 | 26-Apr-21 | Locates | Lines |  | 0
636826 | 2021 CABLE REPLACEMENT - GRID: K4 | 805 - Sandalwood | 150494 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
632755 | #10 PEEL CENTRE DR-FEEDER CABLE ENCROACHMENT | 805 - Sandalwood | 151449 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 28-May-21 |  |  | 155732.34 | 141178.82 | 155732.34 | 155732.34 | Richard Cuddy | Transpw | 17-Sep-21 | 01-Aug-23 | 07-Sep-21 | 25-Oct-21 | 19-Nov-21 | Contractor | Contractor |  | 0
637944 | 150 DELTA PARK BLVD / BRAM / UP / 3PH | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 26-Mar-21 |  |  | 48230.73 | 60411.69 | 48230.73 | 48230.73 | Simon Evason |  | 11-May-21 | 22-Sep-22 | 30-Apr-21 | 13-Apr-21 | 22-Apr-21 |  |  |  | 0
637991 | CNTRYSD VL PH5 ST2 - RES SUBD EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Erzek, Ryan | 28-Jun-22 |  |  | 115123.43 | 571790.98 | 115123.43 | 115123.43 | Zenon Lipinski |  | 18-Oct-22 | 22-Sep-22 | 29-Aug-22 | 15-Aug-22 | 17-Aug-22 |  |  |  | 0
638029 | 2021 EMERGING PROJECT - 41/43 ASHWOOD CRES | 805 - Sandalwood | 151449 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 21-Jun-21 |  |  | 46100.78 | 47086.34 | 46100.78 | 46100.78 | Richard Cuddy | Somervl | 20-Jul-21 | 26-Jul-23 | 19-Jul-21 | 23-Aug-21 | 23-Aug-21 | Contractor | N/A |  | 0
638044 | SUNFIELD MCMURCHY TOWNHOMES – SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 70 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638047 | CABLE INJECTION 2021-GRID J5 (CAPITAL BUDGET PROJECT_151321) | 805 - Sandalwood | 151321 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael | 11-Jan-21 |  |  | 173336 | 30851.08 | 173336 | 173336 | Novinium Group | Nvinium | 30-Dec-21 | 26-Jul-23 | 31-Aug-21 | 20-Jan-23 |  | Contractor | Contractor |  | 0
638046 | CABLE INJECTION 2021-GRID E3 (CAPITAL BUDGET PROJECT_151309) | 805 - Sandalwood | 151309 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 15-Dec-20 |  |  | 170589.27 | 86902.79 | 170589.27 | 170589.27 | Simon Evason | Nvinium | 01-Jun-21 | 02-Mar-23 | 03-May-21 | 17-Mar-21 | 02-Nov-21 |  | N/A |  | 0
638077 | 7685 HURONTARIO ST / BRAM / NS / 3PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638076 | 7900 HURONTARIO ST / BRAM / NS / 3PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Paesano, Andrew | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638075 | 7324 KENNEDY RD S / BRAM / NS / CUSTOMER-OWNED SUBSTATION | 800 - Mavis | 150384 | Active | 92 | ACTIVE |  |  | 2023 | Paesano, Andrew | Tan, Seefon | 18-Nov-21 |  |  | 107160.2 | 75837.68 | 107160.2 | 107160.2 | Mark Bobanovic | Transpw | 14-Feb-22 | 26-Jul-23 | 01-Feb-22 | 14-Jun-22 | 05-Jun-23 | Contractor | Contractor |  | 0
638120 | 2021 POLE RENEWAL -GRID E3- 3 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 18-Dec-20 | 3 |  | 110033.32 | 125350.62 | 110033.32 | 110033.32 | John Costa |  | 16-Feb-21 | 08-Jun-22 | 25-Jan-21 | 01-Mar-21 | 07-May-21 | Locates | Lines |  | 0
638119 | 2021 POLE RENEWAL -GRID E4- 4 POLE | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 14-Oct-21 | 4 | 4 | 127416.58 | 93194.05 | 127416.58 | 127416.58 | K-Line Construction | K-Line | 30-Nov-21 | 26-Jul-23 | 15-Nov-21 | 13-Dec-21 | 31-Dec-21 | Locates | Weather |  | 0
638118 | 2021 POLE RENEWAL -GRID E2- 1 POLE | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 14-Oct-21 | 1 | 1 | 17379.49 | 9722.91 | 17379.49 | 17379.49 | Reaburn, Jeff | K-Line | 10-Dec-21 | 26-Jul-23 | 29-Nov-21 | 08-Dec-21 | 23-Dec-21 |  |  |  | 0
638117 | 2021 POLE RENEWAL - GRID B2- 4 POLES | 805 - Sandalwood | 150284 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638121 | POLE RELOCATIONS (#9079, #9095, #9111) | 805 - Sandalwood | 151674 | Active | 99 | COMPLETE |  |  | 2021 | Gamboa, Henry | Erzek, Ryan | 20-Apr-21 |  |  | 129223.25 | 108541.13 | 129223.25 | 129223.25 | Richard Cuddy |  | 10-Jun-21 | 26-Jul-23 | 10-May-21 | 04-May-21 | 04-Jun-21 |  |  |  | 0
638122 | 238 STEELWELL RD / BRAM / UP / 3PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 26-Jan-21 |  |  | 46509.11 | 44086.58 | 46509.11 | 46509.11 | Simon Evason |  | 11-Mar-21 | 12-Mar-23 | 01-Mar-21 | 28-Jan-21 | 03-May-21 |  | Customer |  | 0
638138 | 1660 NORTH PARK DR / BRAM / UP / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 06-Mar-23 |  |  | 138180.61 | 3676.67 | 138180.61 | 138180.61 | Simon Evason | Somervl | 20-Sep-23 | 20-Sep-23 | 15-Sep-23 | [5 empty] | 0
638167 | 215 VETERANS DR / BRAM / NS / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 12-Apr-21 | 1 |  | 90732.48 | 91353.12 | 90732.48 | 90732.48 | Simon Evason | Somervl | 03-Jun-21 | 26-Jul-23 | 17-May-21 | 04-Jun-21 | 11-Jun-21 | Customer | Customer |  | 0
638176 | WO TO BE REPURPOSED | 805 - Sandalwood | 150282 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638175 | 2021 SWITCHGEAR RENEWAL-SITE 169 - EASTBOURNE DR | 805 - Sandalwood | 150282 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638232 | TREVI HOMES TOWNHOUSE DEVELOPMENT - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638173 | 2021 DISTRIBUTION AUTOMATION 44-497 (44-396), 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Casey, Ryan | 18-Dec-20 |  |  | 91551.94 | 149711.35 | 91551.94 | 91551.94 | Reaburn, Jeff | A&W | 30-Apr-21 | 15-Feb-22 | 19-Apr-21 | 12-Oct-21 | 29-Oct-21 | Filler | Filler |  | 0
638172 | 2021 DISTRIBUTION AUTOMATION 44-499 (44-377), 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Casey, Ryan | 18-Dec-20 |  |  | 130233.65 | 159817.83 | 130233.65 | 130233.65 | Reaburn, Jeff |  | 28-Jul-21 | 12-Apr-22 | 05-Jul-21 | 02-Apr-21 | 16-Apr-21 |  |  |  | 0
638171 | 2021 DISTRIBUTION AUTOMATION 44-498 (44-373), 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Casey, Ryan | 18-Dec-20 |  |  | 151680.9 | 239320.19 | 151680.9 | 151680.9 | Reaburn, Jeff |  | 31-Aug-21 | 12-Apr-22 | 03-Aug-21 | 07-Jun-21 | 25-Jun-21 |  |  |  | 0
638170 | 2021 DISTRIBUTION AUTOMATION 44-496 (44-362), 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Casey, Ryan | 11-Jan-21 |  |  | 97685.52 | 125853.37 | 97685.52 | 97685.52 | John Costa |  | 18-Jun-21 | 12-Apr-22 | 01-Jun-21 | 17-Sep-21 | 27-Sep-21 | Filler | Filler |  | 0
638269 | 20 DAVISELM DR / BRAM / NS / 3PH | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 16-Apr-21 |  |  | 84155.16 | 136290.32 | 84155.16 | 84155.16 | Simon Evason | Transpw | 14-Jan-22 | 14-Mar-23 | 14-Jan-22 | 13-Dec-21 | 14-Jul-22 | Customer | Customer |  | 0
638273 | 150 CENTRAL PARK DR / BRAM / NS / 3PH | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 24-Apr-23
638282 | 2021 SWITCH REPLACEMENT - 44-236, 1 | 805 - Sandalwood | 151104 | Active | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | D'Ermes, Michael | 11-Jan-21 |  |  | 123977.65 | 117402.57 | 123977.65 | 123977.65 | John Costa |  | 28-Jul-21 | 11-Aug-23 | 19-Jul-21 | 18-Oct-21 | 29-Oct-21 | Filler | Filler |  | 0
638281 | 2021 SWITCH REPLACEMENT - 44-220, 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | D'Ermes, Michael | 11-Jan-21 |  |  | 123743.86 | 111436.72 | 123743.86 | 123743.86 | John Costa |  | 16-Jul-21 | 12-Apr-22 | 30-Jun-21 | 23-Aug-21 | 15-Sep-21 | Filler | Filler |  | 0
638280 | 2021 SWITCH REPLACEMENT - 44-218, 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | D'Ermes, Michael | 11-Jan-21 |  |  | 123743.86 | 106317.33 | 123743.86 | 123743.86 | John Costa |  | 02-Jul-21 | 12-Apr-22 | 16-Jun-21 | 05-Aug-21 | 15-Sep-21 | Filler | Filler |  | 0
638317 | 2021 SWITCH REPLACEMENT- 44-243, 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Miller, Michael | 21-Dec-20 |  |  | 89137.04 | 105343.16 | 89137.04 | 89137.04 | John Costa |  | 16-Jul-21 | 12-Apr-22 | 05-Jul-21 | 06-Oct-21 | 16-Nov-21 | Filler | Filler |  | 0
638316 | 2021 SWITCH REPLACEMENT- 44-275, 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Miller, Michael | 21-Dec-20 |  |  | 127921.43 | 127944.5 | 127921.43 | 127921.43 | John Costa |  | 23-Apr-21 | 08-Mar-22 | 29-Mar-21 | 15-Jun-21 | 23-Jul-21 | Filler | Filler |  | 0
638315 | 2021 SWITCH REPLACEMENT- 44-237, 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Miller, Michael | 21-Dec-20 |  |  | 89137.04 | 113832.7 | 89137.04 | 89137.04 | John Costa |  | 07-May-21 | 27-Jan-22 | 26-Apr-21 | 24-May-21 | 08-Jul-21 | Control/SCADA | Control/SCADA |  | 0
638328 | 85 COTTRELLE BLVD / BRAM / NS / 1PH (TEMPORARY - LAYOUT) | 805 - Sandalwood | 150389 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 19-Feb-21
638341 | 25 WILLIAM STREET – SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638347 | 2022 SWITCHGEAR RENEWAL-SITE 261 - BRISDALE DR | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 21-Feb-22 | 1 | 1 | 112741.25 | 107662.91 | 112741.25 | 112741.25 | Zenon Lipinski |  | 31-May-22 | 11-Sep-22 | 16-May-22 | 09-May-22 | 13-May-22 |  |  |  | 0
638348 | 2020 EMERGING PROJECT - 18 ALTON CRT | 805 - Sandalwood | 150494 | Inactive | 99 | CANCELLED |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 04-Apr-23
638365 | 2021 TX RENEWAL-GRID G3-10 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 01-Mar-21 | 10 |  | 345886.92 | 251572.22 | 182943.46 | 172943.46 | Richard Cuddy | Somervl | 30-Sep-21 | 08-May-23 | 07-Sep-21 | 30-Apr-21 | 16-Dec-21 |  |  |  | -10,000.00
638364 | 2021 TX RENEWAL-GRID P3-1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 01-Mar-21 | 1 |  | 10648.43 | 8713.32 | 10648.43 | 10648.43 | Richard Cuddy |  | 18-Oct-21 | 17-Mar-22 | 18-Oct-21 | 28-Sep-21 | 28-Sep-21 |  |  |  | 0
638367 | 2021 TX RENEWAL- 3PH TX- 75 QUARRY EDGE DR | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 11-Jan-21 | 1 |  | 26479.96 | 20196.78 | 26479.96 | 26479.96 | Richard Cuddy |  | 30-Aug-21 | 17-Mar-22 | 30-Aug-21 | 18-Nov-21 | 18-Nov-21 | Lines | Lines |  | 0
638403 | 2021 FEEDER CABLE REPLACEMENT GRID J4 - PH1 (ELECTRICAL&CIVIL) | 805 - Sandalwood | 150572 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 11-Jan-21 |  |  | 575586.88 | 532425.07 | 575586.88 | 575586.88 | Richard Cuddy | Transpw | 11-May-21 | 26-Jul-23 | 01-Apr-21 | 21-May-21 | 23-Jul-21 | Contractor | Contractor |  | 0
638417 | 2021 POLE RENEWAL -GRID I4- 6 POLE | 805 - Sandalwood | 150284 | Active | 70 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638416 | 2021 POLE RENEWAL -4 MARKET ST- 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 11-Dec-20 | 1 |  | 22597.18 | 19447.66 | 22597.18 | 22597.18 | John Costa |  | 04-Mar-21 | 16-Feb-23 | 01-Mar-21 | 01-Mar-21 | 22-Mar-21 | MC/PUCC Permit | MC/PUCC Permit |  | 0
638471 | 2021 TX RENEWAL-GRID D2- 1TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 01-Apr-21 | 1 |  | 12525.4 | 8579.62 | 12525.4 | 12525.4 | Richard Cuddy |  | 09-Nov-21 | 17-Mar-22 | 08-Nov-21 | 27-Nov-21 | 27-Nov-21 | Filler | Filler |  | 0
638470 | 2021 TX RENEWAL-GRID C3- 3 TXS | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 22-Dec-20 | 3 |  | 35786.22 | 32147.02 | 35786.22 | 35786.22 | Richard Cuddy |  | 19-Mar-21 | 15-Feb-22 | 15-Mar-21 | 22-Feb-21 | 02-Mar-21 |  |  |  | 0
450714 | 1713 STEELES AVE E - PERMANENT SERVICE | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 08-Oct-20 |  |  | 87674.98 | 93067.86 | 77432.98 | 87674.98 | Simon Evason | Somervl | 07-Dec-20 | 10-May-23 | 16-Nov-20 | 11-Feb-21 | 26-Mar-21 | Customer | Customer |  | 10,242.00
638474 | 2021 TX RENEWAL-GRID F3 - 2 TXS | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 18-Dec-20 | 2 |  | 24247.6 | 18385.88 | 24247.6 | 24247.6 | Richard Cuddy |  | 29-Apr-21 | 20-Apr-22 | 26-Apr-21 | 20-Aug-21 | 20-Aug-21 | Lines | Lines |  | 0
638473 | 2021 TX RENEWAL-GRID E4 - 1TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 01-Apr-21 | 1 |  | 12525.4 | 9831.76 | 12525.4 | 12525.4 | Richard Cuddy |  | 11-Nov-21 | 17-Mar-22 | 10-Nov-21 | 27-Nov-21 | 27-Nov-21 |  |  |  | 0
638472 | 2021 TX RENEWAL-GRID D3 - 1TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 01-Apr-21 | 1 |  | 12525.4 | 10458.23 | 12525.4 | 12525.4 | Richard Cuddy |  | 10-Nov-21 | 17-Mar-22 | 09-Nov-21 | 28-Nov-21 | 28-Nov-21 | Filler |  |  | 0
638475 | 2021 TX RENEWAL-GRID H3 - 5 TXS | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 18-Dec-20 | 5 |  | 82806.24 | 85641.99 | 82806.24 | 82806.24 | Richard Cuddy |  | 23-Apr-21 | 17-Mar-22 | 12-Apr-21 | 09-Jun-21 | 11-Aug-21 | Lines | Lines |  | 0
638476 | 2021 TX RENEWAL-GRID O3 - 2 TXS | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 01-Mar-21 | 2 |  | 24247.6 | 18869.06 | 24247.6 | 24247.6 | Richard Cuddy |  | 19-Oct-21 | 17-Mar-22 | 14-Oct-21 | 16-Sep-21 | 15-Oct-21 |  |  |  | 0
638490 | 10884 WINSTON CHURCHILL BLVD | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638525 | STEELES AVE. WINSTON CHURCHILL TO MISS RD POLE LINE RELOCATION FOR WIDENI | 805 - Sandalwood | 150645 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638569 | 2021 MINI-POLE REBUILDS - REBUILD 12 CLUSTER ID 14 - 5 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 5 |  | 282853.45 | 324535.06 | 282853.45 | 282853.45 | John Costa | A&W | 15-Nov-21 | 08-Jun-22 | 03-Aug-21 | 12-Oct-21 | 07-Dec-21 | Locates | Contractor |  | 0
638568 | 2021 MINI-POLE REBUILDS - REBUILD 9 CLUSTER ID 78 - 5 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 5 |  | 215705.52 | 207753.11 | 215705.52 | 215705.52 | John Costa | A&W | 15-Nov-21 | 08-Jun-22 | 05-Jul-21 | 23-Aug-21 | 07-Dec-21 | Locates | Locates |  | 0
638567 | 2021 MINI-POLE REBUILDS - REBUILD 6 CLUSTER ID 25 - 5 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 5 |  | 169953.5 | 148965.24 | 169953.5 | 169953.5 | John Costa | A&W | 31-May-21 | 25-Apr-22 | 03-May-21 | 17-May-21 | 08-Jul-21 | Locates | Locates |  | 0
638566 | 2021 MINI-POLE REBUILDS - REBUILD 3 CLUSTER ID 21 - 5 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 5 |  | 218944.81 | 205942.47 | 218944.81 | 218944.81 | John Costa | A&W | 30-Jun-21 | 25-Apr-22 | 01-Jun-21 | 07-Jun-21 | 19-Jul-21 | Locates | Filler |  | 0
638625 | 2021 TX RENEWAL-GRID N3 - 1TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 1 |  | 8813.55 | 8655.43 | 8813.55 | 8813.55 | Richard Cuddy |  | 12-Oct-21 | 27-Jan-22 | 12-Oct-21 | 29-Sep-21 | 29-Sep-21 |  |  |  | 0
638624 | 2021 TX RENEWAL-GRID M3 - 2 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Mar-21 | 2 |  | 19688.71 | 16837.35 | 19688.71 | 19688.71 | Richard Cuddy |  | 13-Oct-21 | 27-Jan-22 | 12-Oct-21 | 15-Sep-21 | 15-Sep-21 |  |  |  | 0
638640 | QUEENS LANE - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 91 | ANALYZE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 15-Feb-23 |  |  | 45367.8 | 47357.2 | 45367.8 | 45367.8 | Graham Gegear |  | 02-Jun-23 | 26-Jul-23 | 29-May-23 | 29-May-23 | 14-Jul-23 |  | Lines |  | 0
638664 | 2021 SWITCHGEAR RENEWAL-SITE 253 - VALLEY CREEK DR | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 04-Jan-21 | 1 |  | 138310.92 | 101592.58 | 138310.92 | 138310.92 | Richard Cuddy |  | 17-Aug-21 | 27-Apr-22 | 03-Aug-21 | 06-Dec-21 | 16-Dec-21 | Lines | Lines |  | 0
638666 | 2021 SWITCHGEAR RENEWAL-SITE 229- 121 DON MINAKER DR | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 11-Jan-21 | 1 |  | 135158.54 | 98966.58 | 135158.54 | 135158.54 | Richard Cuddy |  | 23-Jul-21 | 25-Apr-22 | 12-Jul-21 | 12-Jul-21 | 13-Aug-21 | Lines | Lines |  | 0
638665 | WO TO BE REPURPOSED | 805 - Sandalwood | 150282 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638705 | 46 HALE RD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 03-Nov-21
638704 | 80 HALE RD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 22-Mar-21 |  |  | 98038.68 | 115550.7 | 98038.68 | 98038.68 | Simon Evason | Somervl | 03-May-21 | 08-Mar-23 | 19-Apr-21 | 26-Mar-21 | 14-Jun-21 | Customer | Customer |  | 0
638688 | WO TO BE RE-PURPOSED | 805 - Sandalwood | 150284 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
638731 | 2021 LEFT BEHIND CABLE SEGMENTS - GRID J3 | 805 - Sandalwood | 151181 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 01-Jun-21 |  |  | 664696.79 | 685286.47 | 664696.79 | 664696.79 | Richard Cuddy | Transpw | 16-Aug-21 | 26-Jul-23 | 12-Jul-21 | 12-Jul-21 | 13-Aug-21 |  |  |  | 0
638748 | 150 HOWDEN BLVD / BRAM / SR / 3PH | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 19-Jan-21 |  |  | 37353.38 | 32470.83 | 37353.38 | 37353.38 | Simon Evason | Somervl | 26-Feb-21 | 16-Jun-22 | 22-Feb-21 | 08-Mar-21 | 09-Mar-21 | Contractor | Customer |  | 0
638794 | 292 CONESTOGA DR / BRAM / NS / 3PH | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Tan, Seefon |  |  |  | 46261.37 | 0 | 46261.37 | 46261.37 | Dre Danieli |  |  | 20-Jul-20 | [6 empty] | 0
638806 | CNR POLE LINE REBUILD - CHINGUACOUSY RD AND CNR | 805 - Sandalwood | 150284 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Dec-22 | 41 |  | 2489180.66 | 492469 | 2489180.66 | 2489180.66 | AW Group | A&W | 31-Dec-23 | 03-Jan-24 | 31-May-23 | 26-Jun-23 |  | Contractor |  |  | 0
638830 | JOINT USE PERMIT #HB2020-036 - RUTHERFORD ROAD SOUTH, BRAMPTON | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 02-Apr-21 |  |  | 6166.07 | 5434.03 | 6166.07 | 6166.07 | John Costa |  | 04-May-21 | 04-Jul-22 | 04-May-21 | 04-May-21 | 04-May-21 |  |  |  | 0
638849 | 175 VETERANS DR./ BRAM/ NS00078910/ 500 KVA PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Cavanaugh, Danny | 22-Feb-21 |  |  | 84661.74 | 131521.41 | 84661.74 | 84661.74 | Simon Evason | Somervl | 19-Apr-22 | 26-Jul-23 | 01-Apr-22 | 14-Feb-22 | 20-Sep-22 | Materials | Materials |  | 0
634594 | 100 WEST DRIVE (BESS) - CIA | 805 - Sandalwood | 151512 | Active | 70 | ACTIVE |  |  | 2023 | Dehaijle, Carlton | Ibrahim, Menatalla |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
639000 | KENDALWOOD LAND - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 95 | COMPLETE |  |  | 2022 | Gamboa, Henry | Ferry, Rodnne | 19-Oct-22 |  |  | 809661.75 | 803323.93 | 749278.15 | 809661.75 | Zenon Lipinski | Transpw | 15-Dec-22 | 26-Jul-23 | 23-Nov-22 | 22-Nov-22 | 14-Dec-22 |  |  |  | 60,383.60
639061 | 66 BRAMHALL CIRCLE - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | HD | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 8788.52 |  | 0 | Dre Danieli |  |  | 26-Jul-23
639062 | 2 HANOVER ROAD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 22-Feb-23
639086 | DOWN GUYS WIRES AND ANCHORS RELOCATION - HUMBERWEST PKWY | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2021 | Watters, Maxwell | Robinson, David | 12-Jan-21 |  |  | 13148.11 | 28719.92 | 13148.11 | 13148.11 | Reaburn, Jeff |  | 03-Feb-21 | 29-May-23 | 01-Feb-21 | 26-Jan-21 | 06-May-21 | Locates | Locates |  | 0
639113 | 2022 SWITCHGEAR RENEWAL - SITE# 247 - BRISDALE DR, S OF RANCHERO DR | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 22-Dec-21 | 1 | 1 | 118475.29 | 116672.13 | 118475.29 | 118475.29 | Richard Cuddy |  | 10-May-22 | 26-Feb-23 | 27-Apr-22 | 19-Apr-22 | 28-Apr-22 |  |  |  | 0
639184 | JOINT USE PERMIT #HB2020-041, INNIS LAKE ROAD, BRAMPTON | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 09-Jun-21 |  |  | 5415.5 | 2945.77 | 5415.5 | 5415.5 | John Costa |  | 05-Jul-21 | 16-Jun-22 | 05-Jul-21 | 16-Jul-21 | 16-Jul-21 | Lines | Lines |  | 0
639307 | 225 BALMORAL DR / BRAM / UP00095710 / 3PH | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 28-Jul-22 |  |  | 42499.14 | 11601.08 | 42499.14 | 42499.14 | Simon Evason | Somervl | 17-Jul-23 | 26-Jul-23 | 13-Mar-23 | 02-Aug-22 |  |  | Customer |  | 0
639489 | MAYFIELD DEVELOPMENT (21T-18003B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Armstrong, Colby | 10-Mar-22 |  |  | 65291.22 | 376927.3 | 65291.22 | 65291.22 | Zenon Lipinski | Conelco | 16-May-22 | 18-Jul-23 | 03-May-22 | 01-Apr-22 | 11-May-22 |  |  |  | 0
639711 | 465 DEERHURST DR - SERVICE UPGRADE | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 28-May-21 | 1 |  | 28683.1 | 31083.94 | 28683.1 | 28683.1 | Simon Evason |  | 03-Jun-21 | 08-Mar-23 | 31-May-21 | 20-May-21 | 20-May-21 |  |  |  | 0
639715 | ASHLEY FAMILY HOMES - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Erzek, Ryan | 30-Jul-21 |  |  | 71586.41 | 276252.74 | 71586.41 | 71586.41 | Zenon Lipinski |  | 28-Sep-21 | 23-Jan-23 | 13-Sep-21 | 04-Oct-21 | 10-May-22 | Customer | Customer |  | 0
639739 | BELL SECONDARY TRANSFER POLE 48-0 - 48 DUNBARTON CRES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 05-Feb-21 |  |  | 2731.24 | 3413.24 | 2731.24 | 2731.24 | Brian Erskine |  | 26-Feb-21 | 27-Apr-23 | 26-Feb-21 | 09-Feb-21 | 09-Feb-21 |  |  |  | 0
639748 | 2021 4KV CONV PH3E - (ETOBICOKE DR) | 805 - Sandalwood | 151138 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | D'Ermes, Michael | 28-May-21 |  |  | 156969.74 | 148783.51 | 156969.74 | 156969.74 | Reaburn, Jeff | Nvinium | 30-Nov-21 | 08-May-23 | 05-Jul-21 | 19-Jul-21 | 17-Dec-21 | Locates |  |  | 0
639779 | POLE RELOCATION, QUEEN ST W AND MERCER DR | 805 - Sandalwood | 150645 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli | A&W |  | 20-Jul-20
450748 | 10300 HEART LAKE RD.N. | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 23-Dec-20 |  |  | 122142.9 | 117542.36 | 121255.39 | 122142.9 | Simon Evason | Transpw | 03-Mar-21 | 19-Jun-23 | 16-Feb-21 | 28-Apr-21 | 03-Nov-21 | Customer | Customer |  | 887.51
639838 | 215 VETERANS DR / BRAM / NS / 3PH PAD (TEMP) | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
639849 | 7850 HERITAGE RD/BRA/UP00103588/4.5 MVA C.O. TX'S | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 02-Apr-21 |  |  | 50902.39 | 43945.37 | 50902.39 | 50902.39 | Simon Evason | Somervl | 30-Jul-21 | 08-Mar-23 | 30-Jun-21 | 08-Jun-21 | 07-Dec-21 |  | Customer |  | 0
639857 | 6 ANGELBLUFF CRT / BRAM / NS / 1PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 10-Aug-21 | 1 |  | 35830.54 | 31603.07 | 35830.54 | 35830.54 | Simon Evason | Somervl | 30-Nov-21 | 22-Jun-22 | 13-Sep-21 | 15-Oct-21 | 15-Oct-21 | Customer | Customer |  | 0
640122 | JOINT USE PERMIT HB2021-001- TILBURY COURT | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 25-Jun-21 |  |  | 5954.2 | 5583.4 | 5954.2 | 5954.2 | John Costa | K-Line | 30-Jul-21 | 24-Aug-22 | 26-Jul-21 | 23-Jul-21 | 30-Jul-21 |  |  |  | 0
640154 | 255 BISCAYNE CRES/BRAM/UP00083909/3 MVA C.O. TX | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 03-Nov-22 |  |  | 148424.04 | 5725.59 | 148424.04 | 148424.04 | Simon Evason | Somervl | 06-Dec-23 | 06-Dec-23 | 01-Dec-23 | [5 empty] | 0
640180 | 10 HEDGEDALE RD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan | 28-May-21 | 1 |  | 57414.57 | 51083.12 | 57414.57 | 57414.57 | Simon Evason | Somervl | 06-Jul-21 | 08-Mar-23 | 28-Jun-21 | 05-Jul-21 | 07-Jul-21 | Customer | Customer |  | 0
640246 | 2021 EMERGING PROJECT - MS10 F3 CABLE REPLACEMENT | 805 - Sandalwood | 151449 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 19-Mar-21 |  |  | 151179.61 | 111371.58 | 151179.61 | 151179.61 | Richard Cuddy | Transpw | 31-May-21 | 26-Jul-23 | 03-May-21 | 27-May-21 | 11-Jun-21 | Contractor | Control/SCADA |  | 0
640287 | 10950 GOREWAY DR/BRA/NS00100404/1500 KVA PAD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 29-Apr-21 | 1 |  | 94583.22 | 74676.07 | 94583.22 | 94583.22 | Simon Evason | Somervl | 23-Jul-21 | 08-Mar-23 | 15-Jul-21 | 04-Jun-21 | 18-Oct-21 |  | Customer |  | 0
640292 | 215 WILKINSON RD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 18-May-22
640311 | 917 BOVAIRD DR.W./BRA/NS00097122/150 KVA PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Cavanaugh, Danny | 24-Feb-22 |  |  | 157887.88 | 212206.32 | 157887.88 | 157887.88 | Simon Evason | Transpw | 08-Apr-22 | 26-Jul-23 | 29-Mar-22 | 29-Mar-22 | 19-Sep-22 |  | Customer |  | 0
640492 | 2023 LEFT BEHIND CABLE SEGMENTS - GRID J3 | 805 - Sandalwood | 151449 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Nov-22 |  |  | 499774.94 | 262590.06 | 462496.34 | 499774.94 | Graham Gegear | Transpw | 26-Sep-23 | 04-Dec-23 | 30-Aug-23 | 05-Jun-23 |  |  |  |  | 37,278.60
640494 | 2021 DA- AIRPORT RD S OF WILLIAMS PKWY, 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Casey, Ryan | 28-Apr-21 |  |  | 119273.97 | 69880.26 | 103160.37 | 119273.97 | Reaburn, Jeff | A&W | 18-Oct-21 | 18-Apr-22 | 27-Sep-21 | 07-Jul-21 | 26-Aug-21 |  |  |  | 16,113.60
640496 | 2021-44KV D/A SWITCH REPLACEMENT(44-137) - ITD2021-43, 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | Miller, Michael | 28-Apr-21 | 1 |  | 185234.9 | 227022.27 | 161966.28 | 185234.9 | Reaburn, Jeff | A&W | 06-Oct-21 | 18-Apr-22 | 07-Sep-21 | 26-Jul-21 | 03-Sep-21 |  |  |  | 23,268.62
640527 | 225 MALTA AVE/ BRAM/ NS/00108870/ X 1500 KVA PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 29-Apr-21 | 1 |  | 77965.8 | 79084.07 | 77965.8 | 77965.8 | Simon Evason | Somervl | 14-Jul-21 | 26-Jul-23 | 05-Jul-21 | 13-Dec-21 | 16-Dec-21 | Customer | Customer |  | 0
636033 | 797 MAYFIELD RD / BRAM / NS / 1PH | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 10-Mar-21 |  |  | 22229.62 | 21205.64 | 22229.62 | 22229.62 | Justin Gregoris | Somervl | 22-Apr-21 | 16-Jun-22 | 19-Apr-21 | 24-Mar-21 | 28-Apr-21 | Customer | Customer |  | 0
640645 | 2021 DA- STEELES E OF WINSTON CHURCHILL, 1 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2021 | Agostini, Robert | D'Ermes, Michael | 28-Apr-21 | 1 |  | 94358.88 | 98428.05 | 94358.88 | 94358.88 | Reaburn, Jeff | A&W | 24-Sep-21 | 18-Apr-22 | 07-Sep-21 | 20-Sep-21 | 22-Oct-21 |  |  |  | 0
640646 | 305 FOGAL ROAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 17-Sep-21 | 1 |  | 94863.39 | 92925.64 | 94863.39 | 94863.39 | Simon Evason | Somervl | 14-Feb-22 | 26-Jul-23 | 03-Feb-22 | 15-Feb-22 | 26-Jul-22 | Customer | Customer |  | 0
640658 | 2021 TX RENEWAL-GRID J3- 4TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 10-May-21 | 4 | 4 | 41129.87 | 51028.98 | 41129.87 | 41129.87 | Richard Cuddy |  | 04-Mar-22 | 22-Sep-22 | 01-Mar-22 | 24-Jan-22 | 22-Mar-22 |  | COVID19 |  | 0
640661 | 2021 TX RENEWAL-GRID J4- 3 PHASE PADMOUNT TX | 805 - Sandalwood | 150285 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
640660 | 2021 TX RENEWAL-GRID H2- 2TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 10-May-21 | 2 | 2 | 21913.55 | 29557.26 | 21913.55 | 21913.55 | Richard Cuddy |  | 02-Feb-22 | 22-Sep-22 | 01-Feb-22 | 06-Jan-22 | 06-Jan-22 |  |  |  | 0
640659 | 2021 TX RENEWAL-GRID F4- 1TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 10-May-21 | 1 | 1 | 11787.97 | 12855.52 | 11787.97 | 11787.97 | Richard Cuddy |  | 03-Feb-22 | 22-Sep-22 | 03-Feb-22 | 07-Jan-22 | 07-Jan-22 |  |  |  | 0
640683 | 2021 POLE RENEWAL -GRID I5- 3 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 28-Sep-21 | 3 | 3 | 62760.58 | 56076.55 | 62760.58 | 62760.58 | John Costa | A&W | 30-Nov-21 | 26-Apr-22 | 15-Nov-21 | 13-Dec-21 | 23-Dec-21 | Locates | Locates |  | 0
640682 | 2022 POLE RENEWAL GRID I4 - 4 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Dec-21 | 4 | 4 | 70830.08 | 59343.33 | 70830.08 | 70830.08 | K-Line Construction | K-Line | 26-Aug-22 | 02-Mar-23 | 15-Aug-22 | 12-Sep-22 | 23-Sep-22 | Lines | Lines |  | 0
640681 | 2021 POLE RENEWAL -GRID C4- 4 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 28-Sep-21 | 4 |  | 53947.91 | 72485.98 | 53947.91 | 53947.91 | John Costa | A&W | 30-Nov-21 | 25-Apr-22 | 01-Nov-21 | 29-Nov-21 | 16-Dec-21 |  |  |  | 0
640689 | 2021 POLE RENEWAL GRID J3 - 3 POLES | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
640688 | 2021 POLE RENEWAL GRID G2- 3 POLES | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 14-Oct-21 | 3 | 3 | 69178.32 | 104163.07 | 69178.32 | 69178.32 | Reaburn, Jeff | K-Line | 03-Dec-21 | 26-Jul-23 | 15-Nov-21 | 29-Nov-21 | 23-Dec-21 | Locates |  |  | 0
640693 | 2023 POLE RENEWAL GRID I4 - 1 POLE | 805 - Sandalwood | 150284 | Active | 82 | Upload Completed |  |  | 2023 | Agostini, Robert | Miller, Michael | 29-Dec-22 | 1 |  | 83218.38 | 19747.91 | 83218.38 | 83218.38 | Persaud, Ryan |  | 11-Oct-23 | 03-Aug-23 | 02-Oct-23 | [5 empty] | 0
640692 | 2022 POLE RENEWAL GRID J4 PH1- 6 POLES | 805 - Sandalwood | 150284 | Active | 95 | ANALYZE |  |  | 2022 | Agostini, Robert | Miller, Michael | 20-May-22 | 6 | 6 | 377928.87 | 449374.61 | 377928.87 | 377928.87 | AW Group | A&W | 15-Sep-22 | 26-Jul-23 | 01-Sep-22 | 10-Oct-22 | 03-Jan-23 | Contractor |  |  | 0
640745 | 2022 TX RENEWAL(BATCH#2)2021 CARRY OVER-GRID N2 - 4 TXS | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 20-Dec-21 | 4 |  | 49042.66 | 46939.98 | 49042.66 | 49042.66 | Richard Cuddy |  | 22-Nov-22 | 26-Jan-23 | 14-Nov-22 | 11-Nov-22 | 15-Nov-22 |  |  |  | 0
640748 | 2021 TX RENEWAL(BATCH#2)-GRID F3 - 1 TX | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 31-Mar-22 | 1 | 1 | 15404.24 | 13681.02 | 15404.24 | 15404.24 | Graham Gegear |  | 10-Jan-23 | 26-Jul-23 | 09-Jan-23 | 28-Mar-23 | 28-Mar-23 | Materials | Materials |  | 0
640747 | 2022 TX RENEWAL(BATCH#2)-GRID I3 - 1 TX | 805 - Sandalwood | 150285 | Active | 95 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 31-Mar-22 | 1 | 1 | 15119.38 | 15273.64 | 15119.38 | 15119.38 | Zenon Lipinski |  | 18-Jan-23 | 26-Jul-23 | 17-Jan-23 | 02-Feb-23 | 02-Feb-23 | Materials | Materials |  | 0
640746 | 2022 TX RENEWAL(BATCH#2) CARRIED OVER FROM 2021-GRID G3 - 3 TXS | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 17-Dec-21 | 3 | 3 | 37587.21 | 56704.26 | 37587.21 | 37587.21 | Graham Gegear |  | 02-Mar-23 | 01-Aug-23 | 27-Feb-23 | 05-Jun-23 | 05-Jun-23 | Materials | Materials |  | 0
640817 | 370 MAIN ST.N./ BRAM/ UP00115791/ PRIMARY CABLE RELOCATION | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 13-Apr-21 | 1 |  | 161145.42 | 153776.08 | 161145.42 | 161145.42 | Simon Evason | Transpw | 27-May-21 | 08-Mar-23 | 17-May-21 | 06-May-21 | 15-May-21 |  |  |  | 0
640856 | 75 COTTRELLE BLVD / NS / BRAM / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 03-Aug-21 |  |  | 68507.36 | 91312.47 | 68507.36 | 68507.36 | Simon Evason |  | 21-Sep-21 | 26-Jul-23 | 13-Sep-21 | 29-Nov-21 | 03-Aug-22 | Customer | Customer |  | 0
640880 | FEEDER CABLE REPLACEMENT GRID I3 - 2022 PHASE 2 | 805 - Sandalwood | 151290 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 30-Nov-21 |  |  | 830457.17 | 728827.72 | 830457.17 | 830457.17 | Transpower Group | Transpw | 30-May-22 | 26-Feb-23 | 04-Apr-22 | 09-May-22 | 30-Jun-22 | Contractor | Contractor |  | 0
640886 | 2021 POLE RENEWAL PH1 GRID I5 - 4 POLES | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 14-Oct-21 | 4 | 4 | 129920.96 | 188799.23 | 129920.96 | 129920.96 | Reaburn, Jeff | K-Line | 10-Dec-21 | 26-Jul-23 | 22-Nov-21 | 29-Nov-21 | 23-Dec-21 | Locates |  |  | 0
640893 | 2022 TX RENEWAL(OH)BATCH#2-GRID D4-1TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 31-Mar-22 | 1 | 1 | 12576.79 | 13676.77 | 12576.79 | 12576.79 | Zenon Lipinski |  | 10-Aug-22 | 23-Sep-22 | 09-Aug-22 | 02-Nov-22 | 02-Nov-22 | Lines | Lines |  | 0
640904 | 90 COLLINGWOOD AVE | 805 - Sandalwood | 150386 | Active | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 04-Nov-21 |  |  | 125610.6 | 96680.68 | 125610.6 | 125610.6 | Simon Evason | Transpw | 27-Jan-22 | 26-Jul-23 | 17-Jan-22 | 21-Dec-21 | 10-Jan-22 |  |  |  | 0
640954 | FOREST GATE BLK 102 (21T-10002B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 98 | COMPLETE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 29-Nov-22 |  |  | 318325.39 | 309649.77 | 318325.39 | 318325.39 | Zenon Lipinski | Transpw | 24-Feb-23 | 26-Jul-23 | 20-Feb-23 | 09-Dec-22 | 14-Dec-22 |  |  |  | 0
640981 | KENNEDY TOWNS – SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
640998 | INTERMODAL DR AND MIDAIR CT | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641013 | 565 REMEMBRANCE RD / BRAM / NS00113836 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 18-Nov-22 |  |  | 97193.46 | 3164.85 | 97193.46 | 97193.46 | Simon Evason | Somervl | 11-Jul-23 | 03-Aug-23 | 03-Jul-23 | [5 empty] | 0
641014 | 286 RUTHERFORD RD SOUTH | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 28-Oct-21 |  |  | 160222.58 | 96628.98 | 160222.58 | 160222.58 | Simon Evason | Somervl | 14-Dec-21 | 22-Sep-22 | 29-Nov-21 | 10-Jan-22 | 14-Feb-22 | Customer | Customer |  | 0
641016 | FINANCIAL/BRAM/ NS0011106/ 1000 KVA AND 2000 KVA PAD TX | 805 - Sandalwood | 150386 | Active | HO | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 15-Dec-21 |  |  | 281947.64 | 324527.81 | 258844.51 | 281947.64 | Simon Evason | Transpw | 27-Apr-23 | 15-Aug-23 | 28-Mar-23 | 20-Mar-23 |  | Customer |  |  | 23,103.13
641038 | 125 MCLAUGHLIN RD N / BRAM / UP00118438 / 3PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641039 | SABERWOOD HOMES - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Armstrong, Colby | 12-Aug-22 |  |  | 131268.17 | 126308.1 | 131268.17 | 131268.17 | Zenon Lipinski | Transpw | 06-Oct-22 | 23-Jan-23 | 22-Aug-22 | 01-Sep-22 | 02-Sep-22 | Customer |  |  | 0
641156 | ROAD AUTHORITY RELOCATION - BARTLEY BULL BRIDGE REHAB PROJECT | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2023 | Watters, Maxwell | Robinson, David | 31-Jan-23 |  |  | 25019.94 | 0 | 35409.1 | 35409.1 | Persaud, Ryan | Somervl |  | 27-Feb-23 | [6 empty] | 0
641162 | 2300 NORTH PARK DRIVE DOWN GUY WIRE AND ANCHOR RELOCATION | 805 - Sandalwood | 150674 | Active | 98 | COMPLETE |  |  | 2021 | Watters, Maxwell | Robinson, David | 10-Jun-21 |  |  | 2653.16 | 9061.21 | 2653.16 | 2653.16 | Reaburn, Jeff |  | 07-Jul-21 | 26-Jul-23 | 07-Jul-21 | 17-Jun-21 | 03-Sep-21 |  | Locates |  | 0
641166 | 11801 BRAMALEA RD / BRAM / NS00119574 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 03-Nov-21 |  |  | 54835.13 | 78508.43 | 54835.13 | 54835.13 | Simon Evason | Somervl | 09-Mar-22 | 26-Jul-23 | 28-Feb-22 | 26-Jul-22 | 14-Oct-22 | Customer | Customer |  | 0
641196 | SPRING VALLEY ESTATES - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 82 | RELEASED |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 24-Nov-22 |  |  | 13818.22 | 11396.29 | 13818.22 | 13818.22 | Graham Gegear |  | 17-Jul-23 | 26-Jul-23 | 17-Jul-23 | [5 empty] | 0
641216 | UNDERGROUNDING TO ELIMINATE POLE LINE ENCROACHMENT-8406 CREDITVIEW RD | 805 - Sandalwood | 151449 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641228 | 10639 HEARTLAKE RD / BRAM / UP00121583 / 1PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641230 | CREDITVIEW WOODS - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Paesano, Chelsea | 10-Aug-22 |  |  | 266594.85 | 235286.55 | 266594.85 | 266594.85 | Zenon Lipinski | Transpw | 15-Nov-22 | 26-Jan-23 | 31-Oct-22 | 28-Oct-22 | 02-Dec-22 |  | Contractor |  | 0
641244 | 118 NANPORT ST/ BRAM/ UP00128672/ 5MVA C.O. TX | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 27-Jan-23 |  |  | 183987.89 | 18074.1 | 183987.89 | 183987.89 | Simon Evason | Somervl | 30-Aug-23 | 30-Aug-23 | 24-Aug-23 | [5 empty] | 0
641318 | RAISE NEUTRAL AT 7850 HERITAGE RD ENTRANCE-EMERGING | 805 - Sandalwood | 150784 | Active | 92 | ANALYZE |  |  | 2023 | Watters, Maxwell | Mckeen, Brant | 29-Apr-22 |  |  | 52876.43 | 85581.19 | 52876.43 | 52876.43 | AW Group | A&W | 10-Mar-23 | 01-Aug-23 | 06-Mar-23 | 08-Mar-23 | 17-Jul-23 |  | Contractor |  | 0
641322 | SPRINGBROOK ESTATES - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 82 | RELEASED |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea | 26-May-23 |  |  | 24000.36 | 7921.71 | 24000.36 | 24000.36 | Graham Gegear |  | 04-Jul-23 | 27-Jul-23 | 03-Jul-23 | [5 empty] | 0
641416 | 4 EDVAC/ BRAM/ UP00127303/ 1500 KVA TX | 805 - Sandalwood | 150386 | Active | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Cavanaugh, Danny | 18-Jun-21 | 1 |  | 44122.75 | 46667.71 | 44122.75 | 44122.75 | Simon Evason |  | 22-Sep-21 | 26-Jul-23 | 07-Sep-21 | 06-Jan-22 | 06-Jan-22 | Customer | Customer |  | 0
641436 | 5 DOCKSTEADER ROAD | 805 - Sandalwood | 150386 | Active | 91 | ANALYZE |  |  | 2023 | Rao, Gaurav | Bojanic, Dusan | 01-Nov-21 |  |  | 97604.08 | 87662.43 | 97604.08 | 97604.08 | Simon Evason | Somervl | 13-Jun-22 | 01-Aug-23 | 01-Jun-22 | 23-Jan-23 |  | Customer |  |  | 0
641442 | 709 QUEEN ST W / BRAM / NS00114490 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 17-Nov-21 |  |  | 88462.16 | 73854.32 | 88462.16 | 88462.16 | Simon Evason | Somervl | 03-May-22 | 26-Jul-23 | 20-Apr-22 | 04-Oct-22 | 13-Oct-22 | Customer | Customer |  | 0
641472 | 50 WENTWORTH CRT/ BRAM/ UP00095664/ 150KVA TX | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 09-Aug-21 | 1 |  | 47228.41 | 50644.61 | 47228.41 | 47228.41 | Simon Evason | Somervl | 27-Sep-21 | 07-Mar-23 | 20-Sep-21 | 18-Oct-21 | 18-Oct-21 | Customer | Customer |  | 0
641494 | ROAD AUTHORITY RELOCATION - HERITAGE RD, POLE 11843 TO MAYFIELD RD | 805 - Sandalwood | 150645 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Boivin, Cameron |  |  |  | 0 | 6889.56 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641501 | 350 DEERHURST DR / BRAM / NS00133739 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 23-Aug-21 | 1 |  | 58433.79 | 59933.64 | 58433.79 | 58433.79 | Simon Evason | Somervl | 27-Oct-21 | 26-Jul-23 | 18-Oct-21 | 21-Sep-22 | 28-Sep-22 | Customer | Customer |  | 0
641500 | 10031 MCLAUGHLIN RD N / BRAM / UP00121372 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641503 | 125 IRONSIDE DR / BRAM / NS00096132 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 30-Mar-23 |  |  | 122832.2 | 4837.21 | 119424.15 | 122832.2 | Simon Evason | Transpw | 28-Jun-23 | 28-Jul-23 | 26-Jun-23 | 11-Jul-23 |  | Customer |  |  | 3,408.05
641603 | 2023 CABLE INJECTION -GRID H2 | 805 - Sandalwood | 151318 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 28-Sep-22 |  |  | 357026.33 | 628776.49 | 357026.33 | 357026.33 | Novinium Group | Nvinium | 30-Dec-22 | 26-Jul-23 | 10-Oct-22 | 10-Oct-22 |  |  |  |  | 0
641602 | 2022 CABLE INJECTION -GRID E3 | 805 - Sandalwood | 151318 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 28-Sep-22 |  |  | 1210054.4 | 97187.86 | 1210054.4 | 1210054.4 | Novinium Group | Nvinium | 29-Dec-22 | 26-Jul-23 | 10-Oct-22 | 20-Jan-23 |  | Contractor | Contractor |  | 0
641607 | ESTIMATE - 2022 CABLE INJECTION GRID F3-G3-H2 - (CAPITAL BUDGET PROJECT 151464) | 805 - Sandalwood | 151462 | Active | HD | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 43508.44 |  | 0 | Dre Danieli |  |  | 26-Jul-23
641606 | C55 151463 ESTIMATE - CABLE INJECTION GRID F4 | 805 - Sandalwood | 151462 | Active | HD | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 55932.87 |  | 0 | Dre Danieli |  |  | 26-Jul-23
641605 | 2022 CABLE INJECTION -GRID I3 (CAPITAL BUDGET PROJECT_151318) | 805 - Sandalwood | 151318 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 30-Nov-21 |  |  | 377284.84 | 624305.87 | 377284.84 | 377284.84 | Simon Evason | Nvinium | 29-Dec-22 | 26-Jan-23 | 12-Sep-22 | 04-Apr-22 | 30-May-22 |  |  |  | 0
641604 | C55 151313 ESTIMATE - CABLE INJECTION GRID F5 | 805 - Sandalwood | 151462 | Active | HD | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 62662.64 |  | 0 | Dre Danieli |  |  | 26-Jul-23
641612 | C55 151286 ESTIMATE - CABLE REPLACEMENT GRID H2 | 805 - Sandalwood | 151290 | Active | HD | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 95598.21 |  | 0 | Dre Danieli |  |  | 26-Jul-23
641633 | ROSEDALE VILLAGE PH7B STG1 - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Armstrong, Colby | 12-Aug-22 |  |  | 26688.76 | 471669.89 | 26688.76 | 26688.76 | Zenon Lipinski | Conelco | 12-Sep-22 | 23-Jan-23 | 17-Aug-22 | 13-Sep-22 | 22-Sep-22 | Customer |  |  | 0
641635 | ROSEDALE VILLAGE PH7B STG2 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 84 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 26-Jun-23 |  |  | 60345.93 | 21802.81 | 60345.93 | 60345.93 | Graham Gegear |  | 13-Jul-23 | 04-Aug-23 | 03-Jul-23 | 14-Jul-23 |  | Contractor |  |  | 0
641702 | 11613 BRAMALEA ROAD - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 93 | ANALYZE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea | 01-Sep-22 |  |  | 495196.3 | 495563.43 | 495196.3 | 495196.3 | Graham Gegear | Transpw | 21-Jul-23 | 26-Jul-23 | 10-Jul-23 | 20-Apr-23 | 11-May-23 |  |  |  | 0
641687 | 118 NANPORT ST SYSTEM EXPANSION | 805 - Sandalwood | 152453 | Active | 81 | Upload Completed |  |  | 2023 | Watters, Maxwell | Mckeen, Brant |  |  |  | 646566.35 | 34436.72 | 646566.35 | 646566.35 | Persaud, Ryan | Somervl |  | 26-Jul-23 | [6 empty] | 0
632770 | 2020 CABLE INJECTION PROJECT - GRID O2 | 805 - Sandalwood | 150571 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 01-Nov-19 |  |  | 896368.06 | 976720.47 | 896368.06 | 896368.06 | Novinium Group | Nvinium | 31-Dec-20 | 26-Jul-23 | 21-Oct-20 | 21-Oct-20 |  | Contractor | Contractor |  | 0
641712 | 2022 FEEDER CABLE REPLACEMENT GRID F4 - PH1 | 805 - Sandalwood | 151290 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641718 | 9415 CLARKWAY DR/ BRAM/ NS00137563/ 750 KVA TX | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 07-Jan-22 |  |  | 137526.28 | 40212.01 | 137526.28 | 137526.28 | Simon Evason | Somervl | 13-Nov-23 | 13-Nov-23 | 26-Sep-22 | 20-Jul-22 |  | Customer |  |  | 0
641824 | CUSTOMER INITIATED RELOCATION - 225 BALMORAL DR | 805 - Sandalwood | 150674 | Active | 98 | COMPLETE |  |  | 2021 | Lacombe, Joel | Robinson, David | 21-Oct-21 |  |  | 35636.41 | 39142.47 | 35636.41 | 35636.41 | Richard Cuddy | Somervl | 24-Nov-21 | 27-Jul-23 | 22-Nov-21 | 18-Nov-21 | 18-Nov-21 |  |  |  | 0
641826 | 0 ACE DR | 805 - Sandalwood | 150386 | Active | 95 | ANALYZE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 11-Nov-21 |  |  | 141256.49 | 135041.39 | 141256.49 | 141256.49 | Simon Evason | Somervl | 25-Jan-22 | 26-Jul-23 | 10-Jan-22 | 24-Oct-22 | 02-Dec-22 | Customer | Customer |  | 0
641857 | ROAD AUTHORITY RELOCATION - CHINGUACOUSY RD - MAYFIELD RD TO WANLESS DR - PHASE2 | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Robinson, David | 06-Dec-21 | 9 |  | 366634.51 | 466110.9 | 366634.51 | 366634.51 | AW Group | A&W | 28-Feb-22 | 15-May-23 | 17-Jan-22 | 27-Oct-21 | 18-Feb-22 |  |  |  | 0
641867 | 2022 SWITCHGEAR RENEWAL-SITE 52- SANDALWOOD PKWY E | 805 - Sandalwood | 150282 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641910 | 2023 SCADA SWITCHGEAR INSTALLATION-SITE 6 - DRINKWATER RD | 805 - Sandalwood | 150282 | Active | 82 | RELEASED | High | SwGear | 2023 | Agostini, Robert | Miller, Michael | 23-Dec-22 | 1 |  | 249784.81 | 228044.63 | 249784.81 | 249784.81 | Graham Gegear | Somervl | 01-Jun-23 | 04-Aug-23 | 22-May-23 |  |  | Lines | Lines |  | 0
641911 | 2022 SWITCHGEAR INSTALLATION(REPLACE SF6 SG-SITE 46) - SIR LOU DR | 805 - Sandalwood | 150282 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641927 | 2022 SWITCHGEAR RENEWAL - SITE# 555 - McLaughlin Rd & Steeles Ave. W | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE | High | SwGear | 2022 | Agostini, Robert | D'Ermes, Michael | 22-Dec-21 | 1 |  | 225239.36 | 235277.54 | 213686.13 | 225239.36 | Zenon Lipinski |  | 21-Apr-22 | 26-Feb-23 | 01-Apr-22 | 08-Aug-22 | 15-Dec-22 | Filler | Filler |  | 11,553.23
641972 | 2015 - 2045 STEELES AVE W/BRAM/NS00148780/1500 KVA | 805 - Sandalwood | 150386 | Active | HO | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 07-Jan-22 |  |  | 154756.26 | 135198.11 | 154756.26 | 154756.26 | Simon Evason | Somervl | 03-Oct-22 | 04-Aug-23 | 15-Sep-22 | 15-Feb-22 |  |  | Customer |  | 0
641977 | 2023 POLE RENEWAL PH 2 GRID I5 - 1 POLE | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 1 |  | 64490.98 | 6304.77 | 64490.98 | 64490.98 | Graham Gegear |  | 12-Sep-23 | 03-Aug-23 | 01-Sep-23 | [5 empty] | 0
641984 | 2022 TX RENEWAL-GRID B3- 1TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 20-Dec-21 | 1 | 1 | 15516.28 | 13089.69 | 15516.28 | 15516.28 | Richard Cuddy |  | 18-Nov-22 | 26-Jan-23 | 18-Nov-22 | 30-Nov-22 | 30-Nov-22 | Materials | Materials |  | 0
641986 | TX RENEWAL TBD | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641991 | 2022 TX RENEWAL-GRID F3- 2TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 30-Nov-21 | 2 | 2 | 24708.01 | 24940.39 | 24708.01 | 24708.01 | Richard Cuddy |  | 11-Nov-22 | 26-Jan-23 | 10-Nov-22 | 26-Sep-22 | 30-Sep-22 | Materials | Materials |  | 0
641993 | 2022 TX RENEWAL-GRID G3- 1TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 01-Mar-22 | 1 |  | 14779.8 | 2829.41 | 14779.8 | 14779.8 | Graham Gegear |  | 31-May-23 | 26-Jul-23 | 31-May-23 |  |  | Lines | Lines |  | 0
641992 | 2022 TX RENEWAL TBD | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642003 | 2022 SWITCH RENEWAL - SW44-378 PEEL RGNL RD 4 | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 01-Dec-21 | 1 | 1 | 183743.41 | 114863.36 | 183743.41 | 183743.41 | Zenon Lipinski |  | 22-Jun-22 | 02-Mar-23 | 01-Jun-22 | 18-May-22 | 02-Jun-22 |  |  |  | 0
642002 | 2022 SWITCH RENEWAL - SW44-403 HEART LAKE RD S | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 15-Nov-21 | 1 | 1 | 154054.56 | 110505.14 | 154054.56 | 154054.56 | Zenon Lipinski |  | 15-Jul-22 | 02-Mar-23 | 04-Jul-22 | 09-Sep-22 | 22-Sep-22 | Materials | Materials |  | 0
642001 | 2022 SWITCH RENEWAL - SW44-415 TORBRAM RD | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 30-Nov-21 | 1 | 1 | 113346.41 | 129029.36 | 113346.41 | 113346.41 | Zenon Lipinski |  | 29-Mar-22 | 02-Mar-23 | 21-Mar-22 | 18-Aug-22 | 08-Sep-22 | Materials | Materials |  | 0
642006 | 2022 SWITCHGEAR RENEWAL-SITE 516 SANDALWOOD PKWY (FORMERLY SITE 214) | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE | High |  | 2022 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 1 | 1 | 114804.79 | 119498.92 | 114804.79 | 114804.79 | Zenon Lipinski |  | 24-Aug-22 | 26-Feb-23 | 15-Aug-22 | 13-Oct-22 | 21-Oct-22 | Filler | Filler |  | 0
642062 | 685 REMEMBRANCE RD / BRAM / NS00094732 / 3PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 03-Sep-21 | 1 |  | 148610.87 | 127600.42 | 148610.87 | 148610.87 | Simon Evason | Somervl | 26-Nov-21 | 22-Sep-22 | 15-Nov-21 | 08-Dec-21 | 06-Jan-22 | Locates | Locates |  | 0
642097 | 1 BLAIR DR/ BRAM/UP00118596/ 750 KVA TX | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Cavanaugh, Danny | 09-Sep-21 | 1 |  | 64927.98 | 70359.91 | 64927.98 | 64927.98 | Simon Evason | Somervl | 28-Oct-21 | 08-Mar-23 | 18-Oct-21 | 19-Oct-21 | 08-Dec-21 |  | Customer |  | 0
642110 | 2021 POLE RENEWAL GRID J4 PH2- 2 POLES | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 14-Oct-21 | 2 | 2 | 23262.77 | 19803.27 | 23262.77 | 23262.77 | Reaburn, Jeff | K-Line | 30-Nov-21 | 26-Jul-23 | 22-Nov-21 | 09-Dec-21 | 23-Dec-21 |  |  |  | 0
642112 | 2022 POLE RENEWAL GRID J4 PH3- 3 POLES | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 22-Aug-22 | 3 |  | 177674.83 | 51563.16 | 177674.83 | 177674.83 | AW Group | A&W | 02-Dec-22 | 14-Nov-23 | 14-Nov-22 | [5 empty] | 0
642115 | 2022 D/A SWITCHGEAR INSTALLATION-SITE 339 -WILLIAMS PKY W WEST OF ELBERN MARKELL | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2022 | Agostini, Robert | Miller, Michael | 15-Dec-21 | 1 | 1 | 236364.36 | 227296.42 | 236364.36 | 236364.36 | Zenon Lipinski | Somervl | 22-Apr-22 | 22-Sep-22 | 21-Mar-22 | 04-Apr-22 | 18-Aug-22 | Lines | Lines |  | 0
642118 | 2022 DA- HWY 50 N/O COTTRELLE | 805 - Sandalwood | 151104 | Active | 99 | COMPLETE | High | DA | 2022 | Agostini, Robert | Casey, Ryan | 30-Nov-21 | 1 | 1 | 96507.22 | 127045.15 | 96507.22 | 96507.22 | Justin Gregoris |  | 10-Feb-22 | 26-Jul-23 | 01-Feb-22 | 01-Feb-22 | 06-Apr-22 |  | Lines |  | 0
642119 | 2022 DA- SW 44-436 AIRPORT/NEVETS | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2022 | Agostini, Robert | Casey, Ryan | 30-Nov-21 | 1 | 1 | 132151.2 | 112357.01 | 123646.88 | 132151.2 | AW Group | A&W | 14-Apr-22 | 14-Feb-23 | 04-Apr-22 | 10-Oct-22 | 18-Oct-22 | Materials | Materials |  | 8,504.32
642133 | 151104 2022 DISTRIBUTION AUTOMATION - SWGR 340 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2022 | Agostini, Robert | D'Ermes, Michael | 23-Dec-21 | 1 | 1 | 248628.19 | 238186.27 | 248628.19 | 248628.19 | Zenon Lipinski | Somervl | 24-Mar-22 | 26-Feb-23 | 07-Mar-22 | 25-Jul-22 | 02-Aug-22 | Lines | Lines |  | 0
642134 | NEAMSBY STAGE 2 - SUBD RES EDS | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Erzek, Ryan | 19-Apr-22 |  |  | 76391.9 | 978465.97 | 76391.9 | 76391.9 | Zenon Lipinski | Conelco | 22-Jul-22 | 27-Jan-23 | 18-Jul-22 | 09-Aug-22 | 17-Aug-22 | Customer |  |  | 0
642135 | WALLSEND STAGE 2 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Erzek, Ryan | 28-Jun-22 |  |  | 54022.14 | 299149.62 | 54022.14 | 54022.14 | Zenon Lipinski |  | 16-Aug-22 | 26-Jul-23 | 02-Aug-22 | 02-Aug-22 | 17-Aug-22 |  |  |  | 0
642144 | FORESTSIDE ESTATES - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 82 | RELEASED |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea | 06-Feb-23 |  |  | 34712.71 | 14438.49 | 34712.71 | 34712.71 | Graham Gegear |  | 24-Aug-23 | 24-Aug-23 | 21-Aug-23 | [5 empty] | 0
642199 | 73 PARKHURST SQ / BRAM / SR00151185 / 3PH VAULT | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2021 | Rao, Gaurav | Tan, Seefon | 23-Aug-21 |  |  | 28406.33 | 23624.21 | 28406.33 | 28406.33 | Simon Evason | Somervl | 23-Sep-21 | 16-Jun-22 | 20-Sep-21 | 05-Oct-21 | 06-Oct-21 | Customer | Customer |  | 0
642226 | 2022-44KV D/A SWITCH INSTALLATION(44-325) - ITD2022-19 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2022 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 1 | 1 | 162263.07 | 147925 | 191232.83 | 162263.07 | AW Group | A&W | 24-Jun-22 | 14-Feb-23 | 01-Jun-22 | 01-Aug-22 | 07-Oct-22 | Contractor | Contractor |  | -28,969.76
642237 | ROSEDALE VILLAGE PHASE 7C-2 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642236 | ROSEDALE VILLAGE PH7C STG1 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642248 | 2021 EMERGING PROJECT - SECONDARY SERVICE RENEWAL -10 BELMONT DR | 805 - Sandalwood | 151449 | Active | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Casey, Ryan | 15-Oct-21 |  |  | 40232.48 | 32853.68 | 40232.48 | 40232.48 | Reaburn, Jeff | Somervl | 23-Nov-21 | 26-Jul-23 | 15-Nov-21 | 29-Nov-21 | 06-Dec-21 |  |  |  | 0
642276 | 4KV VOLTAGE CONVERSION - PHASE 9B (CENTRAL NORTH) | 805 - Sandalwood | 151139 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642326 | 2022 DA SW20-1485 - HWY 407 HONI ROW E/O HURONTARIO ST | 805 - Sandalwood | 151104 | Active | 98 | COMPLETE | High | DA | 2022 | Agostini, Robert | D'Ermes, Michael | 30-Dec-21 | 1 | 1 | 96342.31 | 108852.15 | 117893.04 | 96342.31 | AW Group | A&W | 16-May-22 | 26-Jul-23 | 02-May-22 | 20-Jun-22 | 08-Jul-22 | Materials | Materials |  | -21,550.73
642336 | NEXUS SOUTH DEVELOPMENT 21T-14001B - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642342 | 2022 DA- SW 20-1239 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2022 | Agostini, Robert | Casey, Ryan | 30-Dec-21 | 1 | 1 | 130873.84 | 151297.76 | 104294.85 | 130873.84 | AW Group | A&W | 21-Mar-22 | 14-Feb-23 | 28-Feb-22 | 18-Jul-22 | 07-Nov-22 | Lines | Contractor |  | 26,578.99
642348 | 2022-44KV LIS SWITCH INSTALLATION(44-434) | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 1 | 1 | 155614.41 | 114573.89 | 180786.23 | 155614.41 | Justin Gregoris | A&W | 25-Mar-22 | 14-Feb-23 | 28-Feb-22 | 06-Sep-22 | 10-Oct-22 | Lines | Contractor |  | -25,171.82
642351 | 2022 DA SW INSTALLATION - 20-1756 (ITD 2022-19) | 805 - Sandalwood | 150494 | Active | 99 | COMPLETE | High | DA | 2022 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 1 | 1 | 138839.74 | 127155.77 | 138839.74 | 138839.74 | Justin Gregoris |  | 23-Feb-22 | 26-Jul-23 | 01-Feb-22 | 25-Jan-22 | 06-Apr-22 |  | Lines |  | 0
642354 | 2022 DA SW20-1184 - INTERMODAL DR E/O DEVON RD | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE | High | DA | 2022 | Agostini, Robert | D'Ermes, Michael | 29-Dec-21 | 1 | 1 | 132848.94 | 176132.26 | 142058.75 | 132848.94 | AW Group | A&W | 01-Apr-22 | 14-Feb-23 | 14-Mar-22 | 18-Jul-22 | 28-Oct-22 | Lines | Contractor |  | -9,209.81
642402 | 2023 SWITCH RENEWAL - 20-2641 (PREVIOULY SW 20-534 ABS) | 805 - Sandalwood | 151010 | Active | 92 | ANALYZE | High | Switch | 2023 | Agostini, Robert | Casey, Ryan | 05-Oct-22 | 1 | 1 | 110771.49 | 156985.13 | 110771.49 | 110771.49 | AW Group | A&W | 24-Mar-23 | 26-Jul-23 | 06-Mar-23 | 13-Feb-23 | 28-Mar-23 |  |  |  | 0
642415 | THE PAVILION PH 3 - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Inactive | 99 | CANCELLED |  |  | 2022 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642417 | 2850 QUEEN ST E/ BRAM/ NS00148913/ 1500 KVA | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 27-Jun-23 |  |  | 92892.24 | 101359.4 | 92892.24 | 92892.24 | Simon Evason | Somervl | 06-Jul-23 | 01-Aug-23 | 29-Jun-23 | 26-Jun-23 |  |  |  |  | 0
642445 | 2021 EMERGING PROJECT- P1768 WINSTON CHURCHILL BOULEVARD | 805 - Sandalwood | 150784 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642297 | 2022 TX RENEWAL-GRID B3- 1TX | 805 - Sandalwood | 150285 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642451 | 2022 POLE RENEWAL GRID H4 - 17 POLES (HALE RD) | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 21-Dec-21 | 17 | 17 | 522588.4 | 659516.16 | 522588.4 | 522588.4 | Black and McDonald Group | B&M | 30-Jun-22 | 08-May-23 | 18-Apr-22 | 02-Jun-22 | 14-Dec-22 | Locates | Locates |  | 0
642454 | 2022 MINI-POLE REBUILD - GLIDDEN RD - 28 Poles | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 27-Jan-22 | 28 | 28 | 726729.82 | 804907.45 | 685007.21 | 726729.82 | K-Line Construction | K-Line | 03-Oct-22 | 02-Mar-23 | 18-May-22 | 02-Jun-22 | 18-Dec-22 | Locates | Locates |  | 41,722.61
642460 | SPRING VALLEY PHASE 2 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 82 | RELEASED |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 24-Nov-22 |  |  | 20482.35 | 17620.44 | 20482.35 | 20482.35 | Graham Gegear |  | 20-Jul-23 | 28-Jul-23 | 18-Jul-23 | [5 empty] | 0
642476 | BOVAIRD DR W & CREDITVIEW RD / BRAM / NS00157770 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642530 | 2022 TX RENEWAL-GRID F1 - 4TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 20-Dec-21 | 4 | 4 | 43782.59 | 33485.88 | 43782.59 | 43782.59 | Richard Cuddy |  | 12-Dec-22 | 26-Jan-23 | 07-Dec-22 | 13-Oct-22 | 13-Oct-22 | Materials | Materials |  | 0
642529 | 2022 TX RENEWAL-GRID D3 - 5 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 20-Dec-21 | 5 |  | 53107.69 | 50603.55 | 53107.69 | 53107.69 | Richard Cuddy |  | 06-Dec-22 | 26-Jan-23 | 01-Dec-22 | 25-Nov-22 | 25-Nov-22 | Materials |  |  | 0
642528 | 2023 TX RENEWAL-GRID 3PH PAD MCLAUGHLIN | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 22-Dec-22 | 1 |  | 47578.2 | 3598.21 | 47578.2 | 47578.2 | Graham Gegear |  | 10-Aug-23 | 10-Aug-23 | 07-Aug-23 | [5 empty] | 0
642532 | 2022 TX RENEWAL-GRID G2 - 3TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 20-Dec-21 | 3 | 3 | 28490.59 | 30522.8 | 28490.59 | 28490.59 | Richard Cuddy |  | 13-Feb-23 | 13-Feb-23 | 09-Feb-23 | 26-Oct-22 | 28-Oct-22 | Materials | Materials |  | 0
642531 | 2022 TX RENEWAL-GRID F3- 4TX | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-21 | 4 | 4 | 36316.25 | 34862.93 | 36316.25 | 36316.25 | Graham Gegear |  | 08-Feb-23 | 26-Jul-23 | 06-Feb-23 | 04-Apr-23 | 04-Apr-23 | Materials | Materials |  | 0
642544 | 2022 TX RENEWAL - 1PH TX GRID D2 - 1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 10-Dec-21 | 1 | 1 | 11542.57 | 12901.53 | 11542.57 | 11542.57 | Richard Cuddy |  | 28-Mar-22 | 22-Sep-22 | 28-Mar-22 | 15-Mar-22 | 15-Mar-22 |  |  |  | 0
642543 | 2022 TX RENEWAL - 1PH TX CHAPEL ST - 2 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 01-Feb-22 | 2 | 2 | 25359.6 | 19861.23 | 25359.6 | 25359.6 | Richard Cuddy |  | 15-Jul-22 | 26-Jan-23 | 14-Jul-22 | 14-Apr-22 | 14-Apr-22 |  |  |  | 0
642542 | 2022 TX RENEWAL - 3PH TX STEELWELL RD | 805 - Sandalwood | 150285 | Inactive | 99 | Upload Completed |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 09-Dec-21 | 1 | 1 | 30958.43 | 27458.87 | 30958.43 | 30958.43 | Zenon Lipinski |  | 14-Apr-22 | 26-Jan-23 | 12-Apr-22 | 30-Oct-22 | 30-Oct-22 | Materials | Materials |  | 0
642546 | 2022 TX RENEWAL - 1PH TX GRID E3 - 8 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 30-Nov-21 | 8 |  | 64115.99 | 82558.7 | 64115.99 | 64115.99 | Richard Cuddy |  | 06-Mar-23 | 06-Mar-23 | 24-Feb-23 | 12-Dec-22 | 20-Dec-22 |  |  |  | 0
642545 | 2022 TX RENEWAL - 1PH TX GRID I3 - 5 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 30-Nov-21 | 5 | 5 | 41009.21 | 42039.14 | 41009.21 | 41009.21 | Richard Cuddy |  | 10-Mar-22 | 22-Sep-22 | 07-Mar-22 | 26-Jan-22 | 12-Apr-22 |  | COVID19 |  | 0
642547 | 2022 TX RENEWAL - 1PH TX GRID E2 - 1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 09-Dec-21 | 1 | 1 | 8970.71 | 11158.03 | 8970.71 | 8970.71 | Richard Cuddy |  | 07-Sep-22 | 26-Jan-23 | 07-Sep-22 | 16-Aug-22 | 16-Aug-22 | Materials | Materials |  | 0
642549 | DOWN GUY AND ANCHORS RELOCATION -BOVAIRD DR WEST OF CREDITVIEW RD | 805 - Sandalwood | 150674 | Active | 99 | COMPLETE |  |  | 2022 | Watters, Maxwell | Robinson, David | 22-Sep-21 |  |  | 10931.5 | 18538.02 | 10931.5 | 10931.5 | Richard Cuddy |  | 21-Oct-21 | 26-Jul-23 | 18-Oct-21 | 04-Oct-21 | 07-Jan-22 |  | Lines |  | 0
642612 | 2022 TX RENEWAL-GRID H4 - 1 TX(3PH PAD) | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 09-Dec-21 | 1 | 1 | 28003.74 | 30357.49 | 28003.74 | 28003.74 | Richard Cuddy |  | 01-Mar-22 | 22-Sep-22 | 28-Feb-22 | 28-Apr-22 | 28-Apr-22 | COVID19 | Filler |  | 0
642611 | 2022 TX RENEWAL-GRID I2 - 1 TX (1PH MP) | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 09-Dec-21 | 1 | 1 | 9777.81 | 8640.4 | 9777.81 | 9777.81 | Richard Cuddy |  | 27-Jun-22 | 22-Sep-22 | 27-Jun-22 | 17-Mar-22 | 14-Apr-22 |  |  |  | 0
642620 | 152278 2022 CABLE REPLACEMENT - GRID G1 | 805 - Sandalwood | 151449 | Inactive | 99 | COMPLETE |  |  | 2021 | Agostini, Robert | Miller, Michael | 25-Oct-21 |  |  | 537718.73 | 467551.75 | 537718.73 | 537718.73 | Richard Cuddy | Transpw | 08-Dec-21 | 23-Jan-23 | 15-Nov-21 | 08-Nov-21 | 06-Dec-21 |  |  |  | 0
642619 | 2022 TX RENEWAL-GRID H3 - 4 TXS (1PH MP) | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 4 | 4 | 34249.04 | 56313.82 | 34249.04 | 34249.04 | Richard Cuddy |  | 09-Sep-22 | 02-Feb-23 | 06-Sep-22 | 13-Jul-22 | 18-Jul-22 | Materials | Materials |  | 0
642621 | 2022 TX RENEWAL-GRID G3 - 1 TX (1PH MP) | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 1 | 1 | 9777.81 | 11613 | 9777.81 | 9777.81 | Richard Cuddy |  | 06-Sep-22 | 26-Jan-23 | 05-Sep-22 | 17-Aug-22 | 17-Aug-22 | Materials | Materials |  | 0
642623 | 2022 TX RENEWAL-GRID J3 - 5 TXS (1PH MP) | 805 - Sandalwood | 150285 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 5 |  | 40069.84 | 38608.37 | 40069.84 | 40069.84 | Graham Gegear |  | 05-Jun-23 | 31-Jul-23 | 31-May-23 | 11-Jul-23 |  | Lines | Lines |  | 0
642622 | 2022 TX RENEWAL-GRID J3 - 1 TX(3PH PAD) | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 09-Dec-21 | 1 | 1 | 29947.75 | 40708.67 | 29947.75 | 29947.75 | Zenon Lipinski |  | 12-Apr-22 | 02-Feb-23 | 11-Apr-22 | 20-May-22 | 20-May-22 | Materials | Materials |  | 0
642624 | 2022 TX RENEWAL-GRID K3 - 3TXS (1PH MP) | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 3 | 3 | 23800.01 | 31764.54 | 23800.01 | 23800.01 | Graham Gegear |  | 25-Apr-23 | 26-Jul-23 | 21-Apr-23 | 17-May-23 | 17-May-23 | Materials | Materials |  | 0
642625 | 2022 TX RENEWAL-GRID N3 - 2TXS (1PH MP) | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 2 | 2 | 17988.98 | 20427.45 | 17988.98 | 17988.98 | Richard Cuddy |  | 02-Sep-22 | 26-Jan-23 | 01-Sep-22 | 29-Nov-22 | 29-Nov-22 | Materials | Materials |  | 0
642626 | 2022 TX RENEWAL-GRID H3 - 1 TX (3PH PAD) | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 30-Nov-21 | 1 | 1 | 22177.77 | 41482.71 | 22177.77 | 22177.77 | Zenon Lipinski |  | 08-Mar-22 | 02-Feb-23 | 07-Mar-22 | 26-Aug-22 | 26-Aug-22 | Materials | Materials |  | 0
642639 | 15 SKYRIDGE DR / BRAM / NS00305721 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
642648 | 15 BRAMALEA RD / BRAM / NS00143382 / CUSTOMER-OWNED SUBSTATION | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 28-Feb-22 |  |  | 30292.95 | 23978.13 | 30292.95 | 30292.95 | Simon Evason |  | 26-Apr-22 | 08-Mar-23 | 25-Apr-22 | 01-Apr-22 | 14-Apr-22 |  |  |  | 0
642718 | 4395 CASTLEMORE RD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2021 | Rao, Gaurav | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 22-Sep-22
642721 | 10753 HEART LAKE ROAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 08-Apr-22 |  |  | 65908.73 | 10550.56 | 65908.73 | 65908.73 | Simon Evason | Somervl | 07-Dec-23 | 07-Dec-23 | 01-Dec-23 | [5 empty] | 0
642725 | FEEDER EXPANSION -FINANCIAL DRIVE /SOUTH OF LEGENDARY CIR | 805 - Sandalwood | 152453 | Active | 98 | COMPLETE |  |  | 2022 | Watters, Maxwell | Robinson, David | 10-Jan-22 |  |  | 67112.27 | 69333.68 | 67112.27 | 67112.27 | Zenon Lipinski | Somervl | 24-Feb-22 | 26-Jul-23 | 14-Feb-22 | 06-Jun-22 | 30-Jun-22 | Customer | Customer |  | 0
642757 | 12 HENDERSON AVE / BRAM / NS00154354 / 3PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 31-Mar-22 |  |  | 153311.88 | 125852.67 | 153311.88 | 153311.88 | Simon Evason | Transpw | 21-Jun-22 | 08-Mar-23 | 13-Jun-22 | 20-Apr-22 | 08-May-22 |  |  |  | 0
642777 | 125 MCLAUGHLIN RD NORTH | 805 - Sandalwood | 150386 | Active | 82 | PDG SnR |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 139804.09 | 7240.48 | 139804.09 | 139804.09 | Dre Danieli |  |  | 04-Mar-24 | [6 empty] | 0
642781 | TRANSFORMER RELOCATION 6 GERMAIN CIRCLE LOT 217 | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2021 | Pelleja, Emily | Robinson, David | 27-Oct-21 | 1 | 1 | 17907.55 | 16370.92 | 17907.55 | 17907.55 | Richard Cuddy | Somervl | 29-Nov-21 | 14-Apr-23 | 29-Nov-21 | 08-Dec-21 | 08-Dec-21 | Locates | Locates |  | 0
642939 | 8480 & 8470 HWY 50 / BRAM / NS00111989 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE | High |  | 2023 | Rao, Gaurav | Wigley, Graham | 02-Aug-22 |  |  | 461578.25 | 409615.61 | 369224.1 | 461578.25 | Simon Evason | Transpw | 11-Nov-22 | 15-Aug-23 | 11-Oct-22 | 23-Aug-22 |  | Customer |  |  | 92,354.15
642949 | UG CABLE RELOCATION AT STEELES AVE. AND LANCASHIRE | 805 - Sandalwood | 150674 | Active | HO | H2 |  |  | 2023 | Watters, Maxwell | Volkov, Igor | 08-Nov-21 |  |  | 384262.36 | 21747.26 | 285479.41 | 285479.41 | Mark Bobanovic | Somervl | 18-Feb-22 | 26-Jul-23 | 01-Feb-22 |  |  | N/A |  |  | 0
642948 | 70 COACHWORKS CRES | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 17-Mar-22 |  |  | 90753.11 | 68599.51 | 90753.11 | 90753.11 | Simon Evason | Somervl | 21-Apr-22 | 08-Mar-23 | 07-Apr-22 | 26-Apr-22 | 18-May-22 | Customer | Customer |  | 0
643027 | 2022 POLE RENEWAL GRID L4 - 2 POLES (VARIOUS LOCATIONS) | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 28-Feb-22 | 2 | 2 | 68859.68 | 27438.2 | 68859.68 | 68859.68 | K-Line Construction | K-Line | 06-Oct-22 | 02-Mar-23 | 26-Sep-22 | 16-Sep-22 | 16-Sep-22 |  |  |  | 0
643026 | 2022 POLE RENEWAL GRID M1 - 1POLE (MAYFIELD RD) | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643030 | 2022 POLE RENEWAL GRID J5 - 3 POLES (VARIOUS LOCATIONS) | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 28-Feb-22 | 3 | 3 | 136771.87 | 126924.37 | 136771.87 | 136771.87 | K-Line Construction | K-Line | 23-Sep-22 | 02-Mar-23 | 29-Aug-22 | 28-Sep-22 | 30-Sep-22 |  |  |  | 0
643029 | THIS WO IS TO BE RE-PURPOSED FOR USE ON A SIMILAR TYPE POLE RENEWAL PROJECT TBD | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643028 | 2022 POLE RENEWAL GRID L3 - 1 POLE (NORTH PARK DR) | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 28-Feb-22 | 1 | 1 | 27105.26 | 14351.4 | 27105.26 | 27105.26 | K-Line Construction | K-Line | 31-Oct-22 | 02-Mar-23 | 27-Oct-22 | 15-Sep-22 | 15-Sep-22 |  |  |  | 0
643031 | 2022 POLE RENEWAL GRID J4 - 1 POLE (DIXIE RD) | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643056 | KENDALWOOD LAND (EMBLETON) - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Active | 93 | ANALYZE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne | 19-Dec-22 |  |  | 89995.56 | 90999.41 | 89995.56 | 89995.56 | Graham Gegear | N/A | 21-Mar-23 | 26-Jul-23 | 13-Mar-23 | 21-Feb-23 | 09-Mar-23 |  |  |  | 0
643062 | 5 RUTHERFORD RD S/ BRAM/ UP00169083/ 500 KVA VAULT | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 24-Feb-22 |  |  | 86826.3 | 18715.44 | 86826.3 | 86826.3 | Simon Evason | Somervl | 08-Sep-23 | 08-Sep-23 | 01-Sep-23 | 04-Jul-23 |  |  |  |  | 0
643066 | 200 KENNEDY RD S/ BRAM/ NS00172256/ 2000 KVA PAD | 805 - Sandalwood | 150386 | Active | 91 | TEMP |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 09-Mar-22 |  |  | 372067.41 | 398466.15 | 361038.09 | 372067.41 | Simon Evason | Transpw | 28-Nov-22 | 14-Aug-23 | 31-Oct-22 | 22-Nov-22 |  | Customer |  |  | 11,029.32
643069 | 2022 TRANSFORMER COATINGS | 805 - Sandalwood | 150285 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643081 | 2022 POLE RENEWAL -GRID F2- 1 POLES | 805 - Sandalwood | 150284 | Active | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 15-Dec-21 | 1 | 1 | 14942.15 | 20723.29 | 14942.15 | 14942.15 | Justin Gregoris |  | 02-Mar-22 | 26-Jul-23 | 28-Feb-22 | 02-Feb-22 | 14-Mar-22 |  | COVID19 |  | 0
643080 | 2022 POLE RENEWAL -GRID F3- 4 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 16-Dec-21 | 4 | 4 | 56068.97 | 92069.39 | 56068.97 | 56068.97 | K-Line Construction | K-Line | 15-Aug-22 | 02-Mar-23 | 01-Aug-22 | 23-Sep-22 | 23-Sep-22 | Lines | Contractor |  | 0
643079 | 2022 POLE RENEWAL -GRID C4- 1 POLE MISSISSAUGA | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Dec-21 | 1 | 1 | 10633.28 | 18304.52 | 10633.28 | 10633.28 | Justin Gregoris |  | 02-May-22 | 02-Mar-23 | 29-Apr-22 | 13-May-22 | 20-Jun-22 | Locates |  |  | 0
643078 | 2022 POLE RENEWAL -GRID A2- 2 POLES HERITAGE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Dec-21 | 2 | 2 | 20406.94 | 30185.64 | 20406.94 | 20406.94 | Justin Gregoris |  | 25-Feb-22 | 28-Apr-23 | 21-Feb-22 | 02-Feb-22 | 11-Mar-22 |  | COVID19 |  | 0
643077 | 2022 POLE RENEWAL -GRID A3- 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 01-Feb-22 | 1 | 1 | 21240.29 | 10842.49 | 21240.29 | 21240.29 | K-Line Construction | K-Line | 16-Jun-22 | 02-Mar-23 | 13-Jun-22 | 07-Oct-22 | 07-Oct-22 | Lines | Lines |  | 0
643099 | 2022 POLE RENEWAL GRID D5 - 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 04-Mar-22 | 1 | 1 | 26037.58 | 13946.54 | 26037.58 | 26037.58 | K-Line Construction | K-Line | 02-Nov-22 | 02-Mar-23 | 31-Oct-22 | 23-Sep-22 | 23-Sep-22 |  |  |  | 0
643105 | 2023 POLE RENEWAL GRID G3 - POLE 9681 | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Dec-22 | 1 |  | 27417.63 | 11494.48 | 27417.63 | 27417.63 | Graham Gegear |  | 03-Aug-23 | 28-Jul-23 | 01-Aug-23 | [5 empty] | 0
643104 | 2023 POLE RENEWAL GRID G3 - 2 POLES | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Dec-22 | 2 |  | 51574.06 | 11245.89 | 51574.06 | 51574.06 | Graham Gegear |  | 10-Jul-23 | 03-Aug-23 | 29-Jun-23 | [5 empty] | 0
643103 | 2022 POLE RENEWAL GRID G1 - 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 31-Mar-22 | 1 | 1 | 48764.39 | 31325.66 | 48764.39 | 48764.39 | K-Line Construction | K-Line | 24-Nov-22 | 02-Mar-23 | 21-Nov-22 | 07-Oct-22 | 07-Oct-22 |  |  |  | 0
643102 | 2022 POLE RENEWAL GRID F5 - 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 28-Feb-22 | 1 | 1 | 34626.36 | 11325.91 | 34626.36 | 34626.36 | K-Line Construction | K-Line | 18-Nov-22 | 02-Mar-23 | 15-Nov-22 | 07-Oct-22 | 07-Oct-22 |  |  |  | 0
643101 | 2023 POLE RENEWAL GRID F4 - 8 POLES | 805 - Sandalwood | 150284 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Nov-22 | 8 |  | 133262.85 | 82668.67 | 133262.85 | 133262.85 | Graham Gegear |  | 15-Jun-23 | 22-Aug-23 | 29-May-23 | 11-Jul-23 |  | Lines |  |  | 0
643100 | 2023 POLE RENEWAL GRID F1 - 1 POLE | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Dec-22 | 1 |  | 25588.39 | 5315.14 | 25588.39 | 25588.39 | Graham Gegear |  | 28-Jun-23 | 31-Jul-23 | 23-Jun-23 | [5 empty] | 0
643097 | STEELES AVE W AND MCLAUGHLIN RD STRUT GUY | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2022 | Pelleja, Emily | Mckeen, Brant | 10-Dec-21 |  |  | 9259.5 | 3001 | 9259.5 | 9259.5 | Justin Gregoris |  | 03-Feb-22 | 23-Sep-22 | 01-Feb-22 | 31-Jan-22 | 31-Jan-22 |  |  |  | 0
643113 | 2022 POLE RENEWAL -GRID H4- 1 POLES | 805 - Sandalwood | 150494 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 18-Feb-22 | 1 | 1 | 20721.9 | 23365.34 | 20721.9 | 20721.9 | K-Line Construction | K-Line | 08-Nov-22 | 02-Mar-23 | 03-Nov-22 | 23-Sep-22 | 23-Sep-22 |  |  |  | 0
643128 | 100 WHYBANK DR / BRAM / NS00142521 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Wigley, Graham | 16-May-22 |  |  | 138811.47 | 109848.01 | 138811.47 | 138811.47 | Simon Evason | Somervl | 10-Aug-22 | 26-Jul-23 | 02-Aug-22 | 14-Sep-22 | 13-Oct-22 | Customer | Customer |  | 0
639485 | 563 BOVAIRD DR E / UP / BRAM / 1PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 28-Sep-21 |  |  | 30446.96 | 30543.93 | 30446.96 | 30446.96 | Simon Evason | Somervl | 03-Nov-21 | 22-Sep-22 | 01-Nov-21 | 10-Feb-22 | 30-Mar-22 | Customer | Customer |  | 0
643130 | 398 RAILSIDE DR / BRAM / NS00142639 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 02-May-22 |  |  | 105185.83 | 72949.14 | 105185.83 | 105185.83 | Simon Evason | Somervl | 02-Sep-22 | 26-Jul-23 | 22-Aug-22 | 12-Sep-22 | 21-Sep-22 | Customer | Customer |  | 0
643135 | 425 RAILSIDE DR FEEDER EXTENSION | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2022 | Watters, Maxwell | Mckeen, Brant | 12-Apr-22 |  |  | 54453.56 | 38213.7 | 54453.56 | 54453.56 | Reaburn, Jeff |  | 06-Jun-22 | 26-Jul-23 | 30-May-22 | 20-Jun-22 | 29-Aug-22 | Lines | Lines |  | 0
643161 | POLE RELOCATION FOR ROAD WIDENING-THE GORE RD ,QUEEN ST. EAST TO CASTLEMORE RD | 805 - Sandalwood | 151648 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643189 | 25 FREDERICK ST SECONDARY SERVICE RELOCATION | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2021 | Pelleja, Emily | Mckeen, Brant | 10-Dec-21 |  |  | 6490.82 | 1347.96 | 6490.82 | 6490.82 | Justin Gregoris |  | 24-Jan-22 | 23-Sep-22 | 24-Jan-22 | 30-Nov-21 | 30-Nov-21 | xBy-passed |  |  | 0
643190 | 277 VODDEN ST SWITCHGEAR RELOCATION | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2022 | Pelleja, Emily | Mckeen, Brant |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 13-Feb-23
643228 | 11619 HURONTARIO ST SIDEWALK STRUT | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2022 | Pelleja, Emily | Mckeen, Brant | 28-Jul-22 |  |  | 9944.83 | 5188.97 | 9944.83 | 9944.83 | Reaburn, Jeff | A&W | 03-Oct-22 | 24-May-23 | 03-Oct-22 | 16-Sep-22 | 16-Sep-22 |  |  |  | 0
643260 | 95 WALKER DR POLE RELOCATION | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2022 | Pelleja, Emily | Mckeen, Brant |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643296 | 7500 FINANCIAL DR / BRAM / NS00157470 / 1PH PAD (TEMPORARY) | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 07-Dec-21 |  |  | 46824.34 | 52749.74 | 46824.34 | 46824.34 | Simon Evason | Somervl | 31-Jan-22 | 23-Sep-22 | 25-Jan-22 | 28-Feb-22 | 03-Mar-22 | Locates |  |  | 0
643354 | VALES NORTH (21T-19009B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 98 | ANALYZE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea | 03-Nov-22 |  |  | 38327.56 | 124016.07 | 38327.56 | 38327.56 | Zenon Lipinski |  | 26-Apr-23 | 26-Jul-23 | 24-Apr-23 | 16-Dec-22 | 17-Jan-23 |  |  |  | 0
643400 | 5 GREAT LAKES DR / BRAM / UP00186658 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 91 | ANALYZE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 08-Nov-22 |  |  | 63653.77 | 51687.79 | 63653.77 | 63653.77 | Simon Evason |  | 21-Jun-23 | 26-Jul-23 | 19-Jun-23 | 20-Jun-23 | 22-Jun-23 | Customer | Customer |  | 0
643426 | 260 MALTA AVE / BRAM / NS / 3PH | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643466 | HULRT TPSS#11 - SKYWAY DR - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 82 | RELEASED |  |  | 2023 | Paesano, Andrew | Patel, Ketan | 27-Mar-23 |  |  | 60381.2 | 66907.54 | 60381.2 | 60381.2 | Antonio Mina | Somervl | 05-Sep-23 | 05-Sep-23 | 31-Aug-23 | [5 empty] | 0
643469 | HULRT TPSS#14 - STEELES AVE - BRAM - 3PH - PRIMARY | 805 - Sandalwood | 152264 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643468 | HULRT TPSS#13 - RAY LAWSON BLVD - BRAM - 3PH - PRIMARY | 805 - Sandalwood | 152264 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643467 | HULRT TPSS#12 - TOPFLIGHT DR - BRAM - 3PH - PRIMARY | 805 - Sandalwood | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643480 | ROAD AUTHORITY-POLE RELOCATION-REGION OF PEEL-LOC. 2-DIXIE RD (C.SIDE TO BOVAIR) | 805 - Sandalwood | 150645 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643495 | 8 ATLAS CRT / BRAM / UP00159523 / CUSTOMER OWNED SUBSTATION | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 06-Sep-22 |  |  | 19982.21 | 14742.02 | 19982.21 | 19982.21 | Simon Evason |  | 15-Sep-22 | 26-Jul-23 | 13-Sep-22 | 24-Nov-22 | 03-Dec-22 | Customer | Customer |  | 0
643498 | 267 GLIDDEN ROAD / BRAM / NS00182594 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643503 | 11 HWY 50/ BRAM/ NS00171791/ 1000 KVA PAD | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643504 | 2022 SWITCHGEAR REPLACEMENT SITE 207 (GRID K2) - SANDALWOOD PKY E | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Miller, Michael | 26-Jan-22 | 1 | 1 | 115345.48 | 105587.34 | 115345.48 | 115345.48 | Richard Cuddy |  | 28-Apr-22 | 12-Sep-22 | 15-Apr-22 | 11-Apr-22 | 11-Apr-22 |  |  |  | 0
643505 | 142 KENNEDY RD S/ BRAM/ UP00152811/ 750 KVA PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 21-Apr-22 |  |  | 97952.2 | 103808.76 | 97952.2 | 97952.2 | Simon Evason | Somervl | 20-Jul-23 | 04-Aug-23 | 23-Jan-23 | 14-Feb-23 |  | Customer |  |  | 0
643516 | 52 DENISON AVE PRIMARY CIRCUIT ISOLATION | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2021 | Pelleja, Emily | Mckeen, Brant |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
643585 | 2022 EMERGING PROJECT - UG SECONDARY SERVICE RELOCATE | 805 - Sandalwood | 151449 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 18-Feb-22 |  |  | 27790.14 | 35180.39 | 27790.14 | 27790.14 | Zenon Lipinski | Somervl | 14-Apr-22 | 23-Sep-22 | 13-Apr-22 | 13-Apr-22 | 22-Apr-22 |  | Contractor |  | 0
643816 | RAISE NEUTRAL AT 7850 HERITAGE RD | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2022 | Pelleja, Emily | Mckeen, Brant |  |  |  | 10000 | 1137.41 |  | 0 | Dre Danieli |  |  | 26-May-22
644044 | POLE RELOCATION AT BOVAIRD DR AND ELBERN MARKELL DR | 805 - Sandalwood | 150645 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli | A&W |  | 20-Jul-20
644078 | 8250 MCLAUGHLIN ROAD 21T-01007B - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644086 | 11423 KENNEDY RD N PRIMARY ISOLATION | 805 - Sandalwood | 150674 | Active | 84 | ACTIVE |  |  | 2023 | Watters, Maxwell | Mckeen, Brant | 01-Apr-22 |  |  | 33225.57 | 8514.29 | 33225.57 | 33225.57 | Reaburn, Jeff |  | 19-Sep-22 | 26-Jul-23 | 02-May-22 | 13-Jul-23 |  | Customer |  |  | 0
644201 | VAULT TX6419 TO 3PH PAD TX CONVERSION -235 NUGGETT CRT | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644213 | 10378 TORBRAM RD - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644231 | 2023 POLE RENEWAL -GRID I5 HONI ROW | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 30-Nov-22 | 2 |  | 38494.39 | 19120.43 | 38494.39 | 38494.39 | Graham Gegear |  | 14-Jun-23 | 28-Jul-23 | 12-Jun-23 | [5 empty] | 0
644245 | POLE RELOCATION BOVAIRD DR AT CREDITVIEW RD | 805 - Sandalwood | 150645 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli | A&W |  | 20-Jul-20
637088 | 4KV CONVERSION - PHASE 10 | 805 - Sandalwood | 151139 | Active | 95 | ANALYZE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 17-Dec-21 |  |  | 1143817.27 | 1196720.1 | 1143817.27 | 1143817.27 | AW Group | A&W | 12-Sep-22 | 26-Jul-23 | 02-May-22 | 11-Jul-22 | 10-Jan-23 | xDelayed Releas | xDelayed Releas |  | 0
644260 | RIVERSTONE SUBDIVISION - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 98 | COMPLETE |  |  | 2022 | Gamboa, Henry | Armstrong, Colby | 07-Sep-22 |  |  | 114564.77 | 110937.37 | 114564.77 | 114564.77 | Zenon Lipinski | Transpw | 11-Apr-23 | 26-Jul-23 | 03-Apr-23 | 08-Nov-22 | 18-Nov-22 |  |  |  | 0
644289 | TFP MAYCHING - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644299 | 2022 POLE RENEWAL -GRID I4- 1 POLE | 805 - Sandalwood | 150284 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644305 | 133 KENNEDY RD / BRAM / UP00201925 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 93 | ANALYZE |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 04-Jan-23 |  |  | 106196.68 | 95189.72 | 106196.68 | 106196.68 | Simon Evason | Somervl | 15-Mar-23 | 27-Jul-23 | 09-Mar-23 | 27-Feb-23 | 10-Mar-23 |  |  |  | 0
643608 | EDGEMONT DRIVE - KENNEDY RD TIE FOR PHASE 10 | 805 - Sandalwood | 151139 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Dec-21 |  |  | 28425.8 | 10369.04 | 28425.8 | 28425.8 | Reaburn, Jeff | A&W | 03-Jun-22 | 02-Mar-23 | 02-Jun-22 | 20-Jun-22 | 08-Nov-22 | xDelayed Releas | xDelayed Releas |  | 0
644433 | 20 ALL NATIONS DR/ BRAM/ NS00198958/ 1500 & 3000 KVA PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 06-Mar-23 |  |  | 247398.53 | 13876.33 | 247398.53 | 247398.53 | Simon Evason | Somervl | 17-Jul-23 | 02-Aug-23 | 10-Jul-23 | [5 empty] | 0
644451 | 255 ORENDA RD / BRAM / UP00195213 / CUSTOMER OWNED SUBSTATION | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 11-Mar-22 |  |  | 27140.86 | 9082.85 | 27140.86 | 27140.86 | Simon Evason |  | 21-Apr-22 | 08-Mar-23 | 19-Apr-22 | 30-Apr-22 | 08-May-22 | Customer | Customer |  | 0
644466 | POLE RELOCATION AT HEARTLAKE RD AND COUNTRYSIDE DRIVE | 805 - Sandalwood | 151648 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644476 | 4 AUCTION LN / BRAM / NS00204490 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 20-Jun-22 |  |  | 80284.83 | 66578.73 | 80284.83 | 80284.83 | Simon Evason | Somervl | 27-Jan-23 | 26-Jul-23 | 23-Jan-23 | 09-Nov-22 | 02-Dec-22 |  |  |  | 0
644502 | 2022 TX RENEWAL-GRID K2 - 1 TX (1PH MP) | 805 - Sandalwood | 150285 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644501 | 2023 TX RENEWAL-GRID H3 - 2TXS (1PH MP) | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 3 |  | 63788.19 | 13304.34 | 63788.19 | 63788.19 | AW Group | A&W | 08-Aug-23 | 08-Aug-23 | 01-Aug-23 | [5 empty] | 0
644504 | 2023 TX RENEWAL-1TX (3PH PAD)-GRID N4 | 805 - Sandalwood | 150285 | Active | 82 | Upload Completed |  |  | 2023 | Agostini, Robert | Miller, Michael | 05-Dec-22 | 1 |  | 61770.86 | 12621.5 | 61770.86 | 61770.86 | Persaud, Ryan |  | 05-Oct-23 | 05-Oct-23 | 02-Oct-23 | [5 empty] | 0
644526 | 760 WANLESS DR/ BRAM/ NS00202620/ 500 KVA PAD | 805 - Sandalwood | 150386 | Active | 99 | COMPLETE |  |  | 2022 | Rao, Gaurav | Cavanaugh, Danny | 08-Jun-22 |  |  | 177910.04 | 151743.71 | 177910.04 | 177910.04 | Simon Evason | Transpw | 02-Sep-22 | 26-Jul-23 | 22-Aug-22 | 06-Jul-22 | 13-Oct-22 |  | Customer |  | 0
644539 | 2023 TX RENEWAL-GRID E5 - 1 X 3PH TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 |  | 45696.67 | 3427.66 | 45696.67 | 45696.67 | Graham Gegear |  | 03-Nov-23 | 03-Nov-23 | 01-Nov-23 | [5 empty] | 0
644538 | 2023 TX RENEWAL-GRID I4 - 2 X 3PH TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 22-Dec-22 | 2 |  | 87307.77 | 1483.07 | 87307.77 | 87307.77 | AW Group | A&W | 06-Nov-23 | 06-Nov-23 | 01-Nov-23 | [5 empty] | 0
644537 | 2023 TX RENEWAL-GRID K3 - 1TX | 805 - Sandalwood | 150285 | Active | 82 | Upload Completed |  |  | 2023 | Agostini, Robert | Casey, Ryan | 22-Dec-22 | 1 |  | 20070.4 | 4359.95 | 20070.4 | 20070.4 | Persaud, Ryan |  | 03-Oct-23 | 03-Oct-23 | 02-Oct-23 | [5 empty] | 0
644536 | 2023 TX RENEWAL-GRID E4 - 3TX | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Lipinski, Zenon | Casey, Ryan | 28-Dec-22 | 3 | 3 | 61133.5 | 49054.83 | 61133.5 | 61133.5 | AW Group | A&W | 08-Aug-23 | 08-Aug-23 | 01-Aug-23 | 06-Jul-23 | 11-Jul-23 |  |  |  | 0
644540 | 2023 TX RENEWAL-GRID G4 - 1 X 3PH TX | 805 - Sandalwood | 150285 | Active | 82 | Upload Completed |  |  | 2023 | Agostini, Robert | Casey, Ryan | 22-Dec-22 | 1 |  | 38438.86 | 2323.33 | 38438.86 | 38438.86 | Persaud, Ryan |  | 03-Nov-23 | 03-Nov-23 | 01-Nov-23 | [5 empty] | 0
644547 | 2022 POLE RENEWAL -GRID I4- 1 POLE | 805 - Sandalwood | 150284 | Active | 70 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644542 | 340 MAIN ST N / BRAM / NS00180380 / 1PH 400A - 120/240V | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 05-Jul-23
644563 | 2023 TX RENEWAL (GRID L4)- 3PH PAD TX - 2963 QUEEN ST E | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Dec-22 | 1 |  | 39186.38 | 2488.01 | 39186.38 | 39186.38 | Graham Gegear |  | 10-Aug-23 | 10-Aug-23 | 08-Aug-23 | [5 empty] | 0
644565 | 2023 TX RENEWAL (GRID M4)- 3PH PAD TX - 331 INTERMODAL DR | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Dec-22 | 1 |  | 29582.94 | 3305.14 | 29582.94 | 29582.94 | Reaburn, Jeff |  | 03-Oct-23 | 03-Oct-23 | 02-Oct-23 | [5 empty] | 0
644595 | 2023 TX RENEWAL - 1PH TX GRID K4 - 2 TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Dec-22 | 2 |  | 80396.57 | 5757.21 | 80396.57 | 80396.57 | AW Group | A&W | 04-Oct-23 | 04-Oct-23 | 02-Oct-23 | [5 empty] | 0
644594 | 2022 TX RENEWAL - 1PH TX GRID G2 - 1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 01-Mar-22 | 1 | 1 | 11870.27 | 11685.5 | 11870.27 | 11870.27 | Zenon Lipinski |  | 08-Aug-22 | 27-Jan-23 | 08-Aug-22 | 07-Jul-22 | 07-Jul-22 |  |  |  | 0
644596 | 2022 TX RENEWAL - 1PH TX GRID J2 - 1 TX | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | D'Ermes, Michael | 01-Mar-22 | 1 | 1 | 12356.91 | 12731.36 | 12356.91 | 12356.91 | Zenon Lipinski |  | 07-Mar-23 | 07-Mar-23 | 07-Mar-23 | 15-Aug-22 | 15-Aug-22 | Materials | Materials |  | 0
644634 | ARGO TFP BRAMPTON II LTD - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644633 | MOUNT PLEASANT BLOCK 51-3 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644691 | 11685, 11665 & 11645 MCVEAN DR / BRAM / NS00142653 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 91 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 05-Jan-23 |  |  | 361413.18 | 262358.49 | 361413.18 | 361413.18 | Simon Evason | Somervl | 21-Mar-23 | 26-Jul-23 | 13-Mar-23 | 13-Mar-23 | 31-May-23 |  | Customer |  | 0
644701 | 2001 WHARTON WAY UNIT B | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644702 | 6140 OSPREY BLVD | 805 - Sandalwood | 150388 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Bojanic, Dusan |  |  |  | 0 | 252.49 |  | 0 | Dre Danieli |  |  | 20-Jan-23
644756 | 2023 TX RENEWAL (GRID D5) - CHINGUACOUSY RD | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 29-Dec-22 | 1 |  | 36632.72 | 2045.78 | 36632.72 | 36632.72 | Reaburn, Jeff |  | 07-Nov-23 | 07-Nov-23 | 06-Nov-23 | [5 empty] | 0
644755 | 2023 TX RENEWAL (GRID I5) - DIXIE RD AND HWY 407 | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 29-Dec-22 | 1 |  | 33526.7 | 3673.99 | 33526.7 | 33526.7 | Graham Gegear |  | 02-Nov-23 | 02-Nov-23 | 01-Nov-23 | [5 empty] | 0
644772 | 4KV VOLTAGE CONVERSION - PHASE 11B (CENTRAL NORTH) | 805 - Sandalwood | 151139 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644788 | 2022 EMERGING PROJECT - STORM DRAIN REPLACEMENT 136M52FEEDER CABLE RELOCATION | 805 - Sandalwood | 151449 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 11-Oct-22 |  |  | 316330.97 | 306902.19 | 316330.97 | 316330.97 | Zenon Lipinski | Transpw | 16-Nov-22 | 24-Mar-23 | 31-Oct-22 | 21-Nov-22 | 22-Dec-22 | Locates |  |  | 0
644770 | 4KV CONVERSION - PHASE 4B | 805 - Sandalwood | 151139 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 30-Nov-22 |  |  | 841096.72 | 35502.23 | 832534.56 | 841096.72 | Graham Gegear | Transpw | 21-Jun-23 | 08-Aug-23 | 15-May-23 |  |  | MC/PUCC Permit |  |  | 8,562.16
644824 | INSPIRE BLVD/ BRAM/ NS00141758/ 1500 KVA PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 18-Oct-22 |  |  | 100806.75 | 82962.48 | 100806.75 | 100806.75 | Simon Evason | Somervl | 31-May-23 | 02-Aug-23 | 23-May-23 | 05-Jun-23 |  | Customer |  |  | 0
644826 | 400 - 420 PARKHURST SQ/ BRAM/ NS00203828/ 2500 KVA PAD | 805 - Sandalwood | 150386 | Active | 91 | ANALYZE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 31-Aug-22 |  |  | 148870.67 | 179967.9 | 148870.67 | 148870.67 | Simon Evason | Somervl | 27-Jan-23 | 02-Aug-23 | 16-Jan-23 | 06-Jan-23 | 15-Feb-23 |  | Contractor |  | 0
644860 | FEEDER CABLE REPLACEMENT GRID I3 PH1 - 2023 | 805 - Sandalwood | 151290 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 30-Nov-22 |  |  | 1079069.12 | 754265 | 1079069.12 | 1079069.12 | Graham Gegear | Transpw | 16-Jun-23 | 03-Jan-24 | 24-Apr-23 | 01-May-23 |  | Contractor |  |  | 0
644861 | 5556 COUNTRYSIDE DR / BRAM / UP00209353 / 3PH | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644879 | 2023-WHOLESALE METER INSTALLATION UPGRADES AND REGISTRATION-PLEASANT TS-BRAMPTON | 805 - Sandalwood | 152378 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 30-Dec-22 |  |  | 109407.87 | 141987.91 | 109407.87 | 109407.87 | AW Group | A&W | 23-Feb-23 | 08-Aug-23 | 14-Feb-23 | 27-Jan-23 | 17-Jul-23 |  | Contractor |  | 0
644907 | 10 NEWKIRK CRT / BRAM / NS00217909 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 93 | ANALYZE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 07-Feb-23 |  |  | 131186.48 | 127475.15 | 131186.48 | 131186.48 | Simon Evason | Somervl | 23-Mar-23 | 27-Jul-23 | 20-Mar-23 | 07-Mar-23 | 13-Mar-23 |  |  |  | 0
644919 | 4KV CONVERSION PH11C - BRAMPTON | 805 - Sandalwood | 151139 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644921 | 4KV CONVERSION PH11D - BRAMPTON | 805 - Sandalwood | 150494 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645005 | 8007 AIRPORT RD / BRAM / NS00210855 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 91 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 18-Nov-22 |  |  | 69376.41 | 95285.42 | 69376.41 | 69376.41 | Simon Evason | Somervl | 02-Feb-23 | 26-Jul-23 | 01-Feb-23 | 09-Jan-23 | 26-Jun-23 |  | Customer |  | 0
645026 | LAGERFELD TO BOVAIRD DR W / BRAM / NS00202707 / 1PH PAD | 805 - Sandalwood | 150389 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 23-Sep-22
645043 | BRISDALE DR/ BRAM/ NS00211486/ 750 KVA PAD | 805 - Sandalwood | 150386 | Active | HO | RELEASED |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 19-Dec-22 |  |  | 90161.6 | 3683.84 | 90161.6 | 90161.6 | Simon Evason | Somervl | 19-Jul-23 | 28-Jul-23 | 17-Jul-23 | [5 empty] | 0
645086 | AERIAL ENCROACHMENTS POLE#233 - 229/233/235 QUEEN ST W | 805 - Sandalwood | 150284 | Active | 70 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645099 | 20 IRONSIDE DR / BRAM / NS00222656 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 06-Jan-23 |  |  | 48630.47 | 11708.65 | 48630.47 | 48630.47 | Simon Evason |  | 13-Jun-23 | 27-Jul-23 | 12-Jun-23 | 12-Jul-23 |  | Customer |  |  | 0
645113 | 55 EXCHANGE DR / BRAM / NS00220326 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 18-Nov-22 |  |  | 84445.51 | 5023.1 | 84445.51 | 84445.51 | Simon Evason | Somervl | 20-Jul-23 | 31-Jul-23 | 11-Apr-23 | 13-Mar-23 |  |  |  |  | 0
645114 | COUNTRYSIDE VILLAGES PHASE 6 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645210 | 1555 CLARK BLVD / BRAM / UP00204207 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Wigley, Graham | 09-Sep-22 |  |  | 176454.44 | 62650.37 | 176454.44 | 176454.44 | Simon Evason | Somervl | 12-Oct-22 | 26-Jul-23 | 03-Oct-22 | 26-Sep-22 | 01-Oct-22 |  |  |  | 0
645248 | 20 NEWKIRK CRT/ BRAM/ NS00217913/ 2500 KVA PAD | 805 - Sandalwood | 150386 | Active | 91 | ANALYZE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 15-Nov-22 |  |  | 246206.73 | 48549.94 | 246206.73 | 246206.73 | Simon Evason | Somervl | 24-Mar-23 | 28-Jul-23 | 20-Mar-23 | 06-Jan-23 |  |  |  |  | 0
645251 | 2022 POLE RENEWAL -ADVANCE BLVD - GRID I5- 6 POLES PRI ENG | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645262 | 27 RUTHERFORD RD / BRAM / NS00162121 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 21-Oct-22 |  |  | 134388.9 | 111485.52 | 134388.9 | 134388.9 | Simon Evason | Somervl | 31-Jul-23 | 13-Sep-23 | 16-May-23 | 25-Nov-22 |  |  |  |  | 0
645268 | TO LOWER UNDERGROUND 1000KCMIL CABLE ON HUMBERWEST PKWY ACCESST TO 9240 GOREWAY | 805 - Sandalwood | 150645 | Active | 99 | ANALYZE |  |  | 2023 | Pelleja, Emily | Robinson, David | 20-Jun-22 |  |  | 120367.77 | 156069.44 | 120367.77 | 120367.77 | Mark Bobanovic | Somervl | 29-Jul-22 | 26-Jul-23 | 18-Jul-22 | 26-Sep-22 | 31-Jan-23 | Contractor |  |  | 0
645275 | HEART LAKE RD SYSTEM EXPANSION | 805 - Sandalwood | 152364 | Active | 84 | ACTIVE |  |  | 2023 | Watters, Maxwell | Mckeen, Brant | 06-Apr-23 |  |  | 5337606.16 | 750046.36 | 5337606.16 | 5337606.16 | K-Line Construction | K-Line | 01-Nov-23 | 01-Nov-23 | 30-May-23 | 25-May-23 |  |  |  |  | 0
645277 | COUNTRYSIDE DR & HWY 50/ BRAM/ NS00155993/ 2000 AND 3000 KVA PADS | 805 - Sandalwood | 150386 | Active | 45 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644872 | 2023-WHOLESALE METER INSTALLATION UPGRADES AND REGISTRATION-PLEASANT TS-BRAMPTON | 805 - Sandalwood | 152378 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 30-Dec-22 |  |  | 162739.48 | 237354.91 | 143031.16 | 162739.48 | AW Group | A&W | 23-Feb-23 | 26-Jul-23 | 14-Feb-23 | 31-Mar-23 | 17-Jul-23 | Lines | Contractor |  | 19,708.32
645303 | MATTAMY POLICE LANDS WEST (21T-21004B) - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 93 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 20-Dec-22 |  |  | 63862.79 | 77919.53 | 63862.79 | 63862.79 | Graham Gegear | N/A | 03-May-23 | 26-Jul-23 | 26-Apr-23 | 24-Apr-23 | 01-May-23 |  |  |  | 0
645319 | SCADA AMATE SWITCHES INSTALLATION ON EAST DRIVE AND COVENTRY ROAD | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2022 | Watters, Maxwell | Robinson, David | 20-Oct-22 |  |  | 222733.96 | 306660.78 | 222733.96 | 222733.96 | AW Group | A&W | 08-Dec-22 | 23-Jun-23 | 01-Dec-22 | 02-Dec-22 | 22-Dec-22 | Contractor | Contractor |  | 0
645326 | FEEDER EXPANSION QUEEN STREET TO TORBRAM ROAD | 805 - Sandalwood | 152453 | Active | 48 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli | A&W |  | 20-Jul-20
645341 | POLE # 7339 RELOCATION- MAYFIELD RD. AND MARTINBRYNE | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2022 | Watters, Maxwell | Robinson, David | 03-Jun-22 |  |  | 33473.94 | 25056.94 | 33473.94 | 33473.94 | AW Group | A&W | 15-Jul-22 | 23-May-23 | 11-Jul-22 | 20-Jun-22 | 27-Jun-22 |  |  |  | 0
645347 | 151882-2023 CABLE REPLACEMENT - GRID G3(PH A) | 805 - Sandalwood | 151290 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645348 | 151676 - 2023 136M10 FEEDER EXTN GOREWAY TS TO HUMBERWEST PKWY | 805 - Sandalwood | 150494 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644616 | 190 BOVAIRD DR W / BRAM / SR00206666 / 3PH VAULT ROOM | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Tan, Seefon | 11-Apr-22 |  |  | 26643.33 | 16201.7 | 26643.33 | 26643.33 | Simon Evason |  | 11-May-22 | 26-Jul-23 | 02-May-22 | 25-Apr-22 | 22-Jul-22 |  | Customer |  | 0
645361 | BARTLEY BULL PKWY -UG CABLE REPLACEMENT | 805 - Sandalwood | 150645 | Active | 82 | RELEASED |  |  | 2023 | Watters, Maxwell | Robinson, David | 14-Apr-23 |  |  | 134601.03 | 41863.28 | 134601.03 | 134601.03 | Graham Gegear | Somervl | 19-Jul-23 | 28-Jul-23 | 03-Jul-23 | [5 empty] | 0
645396 | EXTNION/CLARK BLVD -RUTHERFORD RD. TO HANSEN-- WDNG OF EASTERN AVE -HANSEN-KNEDY | 805 - Sandalwood | 150645 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645432 | 1071 QUEEN ST W / BRAM / NS00214814 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645431 | 10 & 20 WHYBANK DR / BRAM / NS00204074 / CUSTOMER OWNED SUBSTATION (CCRA) | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 31-Mar-23 |  |  | 67708.72 | 14896.48 | 67708.72 | 67708.72 | Simon Evason | N/A | 11-Jul-23 | 27-Jul-23 | 10-Jul-23 | [5 empty] | 0
645479 | POLE INSTALLATION -HEART LAKE RD | 805 - Sandalwood | 150645 | Active | 95 | COMPLETE |  |  | 2022 | Watters, Maxwell | Robinson, David | 02-Aug-22 | 1 | 1 | 80001.77 | 92224.3 | 80001.77 | 80001.77 | AW Group | A&W | 03-Oct-22 | 26-Jul-23 | 26-Sep-22 | 22-Aug-22 | 19-Sep-22 |  |  |  | 0
645509 | QUEEN GORE EXPANSION | 805 - Sandalwood | 152453 | Active | 40 | ACTIVE |  |  | 2023 | Lacombe, Joel | Mckeen, Brant |  |  |  | 0 | 0 |  | 0 | Dre Danieli | N/A |  | 20-Jul-20
645516 | 20 VICTORIA CRES/ BRAM /NS00231689/ 2000 KVA | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645622 | PARTACC GATE KENNEDY DEVT - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Active | 93 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 24-Nov-22 |  |  | 51038.36 | 52248.22 | 51038.36 | 51038.36 | Graham Gegear |  | 30-Jan-23 | 26-Jul-23 | 24-Jan-23 | 24-Jan-23 | 03-Feb-23 |  | Lines |  | 0
645650 | GORE ROAD DEVELOPMENT - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645688 | 10124 HURONTARIO ST/ BRAM/NS00227114/300 KVA | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645695 | 9535 MISSISSAUGA RD / BRAM / NS00225828 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 95 | CANCELLED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 20-Oct-22 |  |  | 121175.79 | 18397.41 | 121175.79 | 121175.79 | Simon Evason | Somervl | 20-Dec-22 | 03-Oct-23 | 13-Dec-22 | 14-Nov-22 |  |  |  |  | 0
645708 | 2023 CABLE INJECTION -GRID I3 (CAPITAL BUDGET PROJECT_151318) | 805 - Sandalwood | 151318 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 28-Sep-22 |  |  | 532705.4 | 809550.34 | 532705.4 | 532705.4 | Novinium Group | Nvinium | 30-Dec-22 | 26-Jul-23 | 10-Oct-22 | 17-Nov-22 |  | Contractor |  |  | 0
645713 | 11613 BRAMALEA RD/ BRAM/ NS00230857/ 150 KVA PAD | 805 - Sandalwood | 150386 | Active | 91 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 22-Aug-22 |  |  | 42934.67 | 33746.73 | 42934.67 | 42934.67 | Simon Evason |  | 25-Apr-23 | 26-Jul-23 | 25-Apr-23 | 25-Apr-23 |  |  |  |  | 0
645728 | DIXIE RD NOISE WALL ISOLATIONS | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2022 | Pelleja, Emily | Mckeen, Brant |  |  |  | 0 | 495.91 |  | 0 | Dre Danieli |  |  | 24-Jan-23
645755 | 63 EASTERN AVENUE / BRAM / NS00233685 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 08-May-23 |  |  | 79180.27 | 56536.92 | 79180.27 | 79180.27 | Simon Evason | Somervl | 24-Jul-23 | 02-Aug-23 | 17-Jul-23 | 29-May-23 |  |  |  |  | 0
645756 | 155 HEDGEDALE RD / BRAM / UP00247884 / C.O SUBSTATION | 805 - Sandalwood | 150386 | Active | 93 | ANALYZE |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 19-Jan-23 |  |  | 215114.1 | 198606.4 | 215114.1 | 215114.1 | Simon Evason | Somervl | 08-Feb-23 | 01-Aug-23 | 30-Jan-23 | 08-Feb-23 | 04-Mar-23 | Customer | Customer |  | 0
645784 | 2023 CABLE INJECTION 151315 - GRID G5 | 805 - Sandalwood | 151462 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645783 | 2023 CABLE INJECTION 151462 - GRID G1 | 805 - Sandalwood | 151462 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 26-Sep-22 |  |  | 782128.52 | 27083.21 | 782128.52 | 782128.52 | Novinium Group | Nvinium | 29-Dec-22 | 26-Jul-23 | 10-Oct-22 | 20-Jan-23 |  | Contractor |  |  | 0
645782 | 151882-2023 CABLE REPLACEMENT - GRID G3(PH B) | 805 - Sandalwood | 151290 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645785 | 151882-2023 CABLE REPLACEMENT - GRID G3(PH C) | 805 - Sandalwood | 151290 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645788 | 2023 TX RENEWAL-1TX (3PH PAD)-GRID N4 | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 05-Dec-22 | 1 | 1 | 39893.05 | 38468.08 | 39893.05 | 39893.05 | Graham Gegear |  | 05-Apr-23 | 26-Jul-23 | 03-Apr-23 | 18-Mar-23 | 18-Mar-23 |  |  |  | 0
645787 | 2023 TX RENEWAL-1TX (3PH PAD)-GRID N4 | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 05-Dec-22 | 1 |  | 36164.99 | 1713.23 | 36164.99 | 36164.99 | Reaburn, Jeff |  | 12-Oct-23 | 12-Oct-23 | 09-Oct-23 | [5 empty] | 0
645786 | 2023 TX RENEWAL-1TX (3PH PAD)-GRID N4 | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 05-Dec-22 | 1 |  | 34103.92 | 2572.4 | 34103.92 | 34103.92 | Reaburn, Jeff |  | 18-Oct-23 | 18-Oct-23 | 16-Oct-23 | [5 empty] | 0
645832 | GOREWAY DRIVE ANCHOR RELOCATION | 805 - Sandalwood | 150674 | Active | 95 | COMPLETE |  |  | 2022 | Watters, Maxwell | Robinson, David |  |  |  | 15202.87 | 11655.33 | 15202.87 | 15202.87 | AW Group | A&W | 01-Mar-22 | 26-Jul-23 | 01-Jun-21 | 31-May-21 | 05-Jan-23 |  | Customer |  | 0
645852 | 2023-WHOLESALE METER INSTALLATION UPGRADES AND REGISTRATION-PLEASANT TS-BRAMPTON | 805 - Sandalwood | 152378 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 30-Dec-22 |  |  | 191968.9 | 462478.75 | 191968.9 | 191968.9 | AW Group | A&W | 03-Mar-23 | 22-Aug-23 | 06-Feb-23 | 13-Jan-23 | 04-Jul-23 |  | Materials |  | 0
646347 | POLE RELOCATION -HERITAGE ROAD ( COB PROPOSED SATELLITE YARD) | 805 - Sandalwood | 150674 | Active | 95 | COMPLETE |  |  | 2022 | Watters, Maxwell | Robinson, David | 17-Oct-22 |  |  | 24147.76 | 25352.13 | 24147.76 | 24147.76 | AW Group | A&W | 09-Dec-22 | 26-Jul-23 | 05-Dec-22 | 31-Oct-22 | 07-Nov-22 |  |  |  | 0
646355 | 2023 DA SW INSTALLATION - 20-1638(C55 151104) | 805 - Sandalwood | 151104 | Active | 95 | ANALYZE | High | DA | 2023 | Agostini, Robert | Miller, Michael | 02-Dec-22 | 1 | 1 | 127293.11 | 80249.67 | 127293.11 | 127293.11 | AW Group | A&W | 03-Feb-23 | 15-Aug-23 | 23-Jan-23 | 23-Jan-23 | 10-Feb-23 |  |  |  | 0
646444 | 2023 DA 44 KV UNIT UPSTREAM OF D6M16 PME - QUEEN W/O HWY 50 SW 44 528 | 805 - Sandalwood | 151104 | Active | 92 | ANALYZE | High | DA | 2023 | Agostini, Robert | Casey, Ryan | 05-Oct-22 | 1 | 1 | 125761.81 | 178353.28 | 125761.81 | 125761.81 | AW Group | A&W | 30-Jun-23 | 27-Jul-23 | 06-Feb-23 | 06-Apr-23 | 30-May-23 | Contractor |  |  | 0
646443 | 2023 DA 44-516 (PREVIOUSLY 44-445 - STEELES W/O TORBRAM) | 805 - Sandalwood | 151104 | Active | 92 | ANALYZE | High | DA | 2023 | Agostini, Robert | Casey, Ryan | 05-Oct-22 | 1 | 1 | 111657.34 | 143057.88 | 111657.34 | 111657.34 | AW Group | A&W | 17-Feb-23 | 09-Aug-23 | 06-Feb-23 | 30-Jan-23 | 03-Mar-23 |  | Contractor |  | 0
646472 | 2023 DA SW20-807 - QUEEN W/O TORBRAM | 805 - Sandalwood | 151104 | Active | 92 | ANALYZE | High | DA | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Nov-22 | 1 | 1 | 206702.98 | 171423.92 | 206702.98 | 206702.98 | AW Group | A&W | 14-Apr-23 | 26-Jul-23 | 27-Mar-23 | 03-Mar-23 | 04-Apr-23 |  |  |  | 0
646471 | 2023 DA SW20-187 - DELTA PARK S/O NEVETS | 805 - Sandalwood | 151104 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646477 | 2023 SWITCHGEAR RENEWAL - SITE# 114 - HEDGEDALE RD | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646476 | 2023 SWITCHGEAR RENEWAL - SITE# 110 - NORTH PARK DRIVE | 805 - Sandalwood | 150282 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 23-Dec-22 | 1 |  | 71139.32 | 1765.3 | 71139.32 | 71139.32 | Graham Gegear |  | 12-Jul-23 | 04-Aug-23 | 03-Jul-23 | [5 empty] | 0
646475 | 2023 SWITCHGEAR RENEWAL - SITE# 74 - COUNTY COURT BLVD | 805 - Sandalwood | 150282 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 22-Feb-23 | 1 | 1 | 124292.14 | 108576.04 | 124292.14 | 124292.14 | AW Group | A&W | 01-Aug-23 | 01-Aug-23 | 18-Jul-23 | 26-Jun-23 | 05-Jul-23 |  |  |  | 0
646484 | 2023 SWITCH RENEWAL - SW44-315 | 805 - Sandalwood | 151010 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Nov-22 | 1 | 1 | 110983.82 | 98235.93 | 110983.82 | 110983.82 | Graham Gegear |  | 27-Feb-23 | 04-Aug-23 | 10-Feb-23 | 17-Feb-23 | 01-Mar-23 |  |  |  | 0
646482 | 2023 SWITCH RENEWAL - SW44-426 | 805 - Sandalwood | 151010 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 30-Nov-22 | 1 | 1 | 131166.61 | 110888.96 | 131166.61 | 131166.61 | Graham Gegear |  | 19-May-23 | 11-Aug-23 | 08-May-23 | 13-Mar-23 |  |  |  |  | 0
646486 | 2023 SWITCH RENEWAL - 44-408 | 805 - Sandalwood | 151010 | Active | 91 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 05-Oct-22 | 1 | 1 | 105317.6 | 94607.23 | 105317.6 | 105317.6 | Graham Gegear |  | 27-Feb-23 | 03-Aug-23 | 13-Feb-23 | 05-Jun-23 |  | Lines | Lines |  | 0
646485 | 2023 SWITCH RENEWAL - 44-460 | 805 - Sandalwood | 151010 | Active | 95 | ANALYZE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 05-Oct-22 | 1 | 1 | 78612.16 | 92128.29 | 78612.16 | 78612.16 | Zenon Lipinski |  | 30-Jan-23 | 26-Jul-23 | 23-Jan-23 | 11-Jan-23 | 20-Jan-23 |  |  |  | 0
646492 | 2023-44KV SWITCH (44-421) RENEWAL | 805 - Sandalwood | 151010 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 02-Dec-22 | 1 |  | 167359.07 | 2814.59 | 167359.07 | 167359.07 | AW Group | A&W | 14-Jul-23 | 09-Aug-23 | 03-Jul-23 | [5 empty] | 0
646497 | DA SWITCH INSTALLATION | 805 - Sandalwood | 151104 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646559 | QUEEN ST E & MCVEAN DR ANCHOR RELOCATION | 805 - Sandalwood | 150674 | Active | HL | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 869.95 |  | 0 | Dre Danieli |  |  | 27-Jul-23
646560 | 150 BOVAIRD DR W / BRAM / UP00228307 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 18-Nov-22 |  |  | 54218.4 | 393.85 | 54218.4 | 54218.4 | Simon Evason |  | 03-Nov-23 | 03-Nov-23 | 01-Nov-23 | [5 empty] | 0
646572 | 5999 MAYFIELD RD, 11999 & 11899 AIRPORT RD / BRAM / NS00251666 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646574 | 17-29 CLARENCE ST / BRAM / NS00238358 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646646 | MAIN ST. & MARKET ST. / BRAM / NS00222841 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646648 | SCOTTISH HEATHER PHASE 5 -SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646649 | G&A HOLDINGS DEVT PH 1 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646682 | 2023 TX RENEWAL-GRID F4 - 2 TX (1PH MP) | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 2 |  | 33048.09 | 13685.77 | 33048.09 | 33048.09 | AW Group | A&W | 06-Jul-23 | 01-Aug-23 | 03-Jul-23 | [5 empty] | 0
646684 | 2023 TX RENEWAL(OH) - GRID E3 - 1TX | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646689 | 2023 TX RENEWAL-GRID H3 - 5TX (1PH MP) | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 05-Dec-22 | 5 |  | 122624.74 | 3174.54 | 122624.74 | 122624.74 | Graham Gegear |  | 26-Sep-23 | 26-Sep-23 | 05-Sep-23 | [5 empty] | 0
646690 | 2023 TX RENEWAL(OH) - GRID A3 - 1TX (T3139) | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 1 |  | 44148.14 | 4256.66 | 44148.14 | 44148.14 | Graham Gegear |  | 31-Jul-23 | 08-Aug-23 | 21-Jul-23 | [5 empty] | 0
646694 | 2023 VAULT TX RENEWAL - GRID J3 - T8186 - 1285 WILLIAMS PKWY E. | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646693 | 2023 VAULT TX RENEWAL - GRID G3 - T10326 - 186 CHURCH ST E | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646692 | 2023 VAULT TX RENEWAL - GRID F4 - T3569 - 365 KENNEDY RD. S | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646695 | 2023 SWITCHGEAR RENEWAL-SITE 517(PREVIOUSLY 215) - SANDALWOOD PKWY | 805 - Sandalwood | 150282 | Active | 84 | ACTIVE | High | SwGear | 2023 | Agostini, Robert | Casey, Ryan | 29-Dec-22 | 1 |  | 270890.12 | 8221.23 | 270890.12 | 270890.12 | AW Group | A&W | 17-Oct-23 | 17-Oct-23 | 02-Oct-23 | 10-Jul-23 |  |  |  |  | 0
646759 | SWITCHGEAR RENEWAL DA - SITE# 195 - WILLIAMS PKWY | 805 - Sandalwood | 150282 | Active | 82 | RELEASED | High | SwGear | 2023 | Agostini, Robert | D'Ermes, Michael | 29-Dec-22 | 1 |  | 286679.68 | 16650.7 | 286679.68 | 286679.68 | AW Group | A&W | 17-Oct-23 | 18-Oct-23 | 02-Oct-23 | [5 empty] | 0
646806 | FEEDER CABLE REPLACEMENT GRID I3 - 2024 | 805 - Sandalwood | 150494 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646881 | S&C FACEPLATE UPGRADES SW44-425 | 805 - Sandalwood | 150784 | Active | 98 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Aug-22 |  |  | 71564.06 | 102809.6 | 71564.06 | 71564.06 | K-Line Construction | K-Line | 04-Oct-22 | 27-Jul-23 | 03-Oct-22 | 23-Nov-22 | 24-Nov-22 | Contractor | Contractor |  | 0
646882 | 2022 - S&C FACEPLATE UPGRADES - DA 44-427 | 805 - Sandalwood | 150784 | Active | 98 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Aug-22 |  |  | 94998.42 | 73912 | 71564.06 | 94998.42 | K-Line Construction | K-Line | 07-Oct-22 | 27-Jul-23 | 05-Oct-22 | 30-Nov-22 | 30-Nov-22 | Contractor | Contractor |  | 23,434.36
646884 | 2023 NEW DA SW - MISSISSAUGA RD S/O WANLESS DR | 805 - Sandalwood | 151104 | Active | 92 | ANALYZE | High | DA | 2023 | Agostini, Robert | D'Ermes, Michael | 23-Dec-22 | 1 | 1 | 151539.2 | 97355.06 | 151539.2 | 151539.2 | AW Group | A&W | 03-Feb-23 | 11-Aug-23 | 16-Jan-23 | 20-Jan-23 | 03-Mar-23 | Contractor | Contractor |  | 0
645586 | TFP MAYCHING - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Erzek, Ryan | 04-Jul-22 |  |  | 19310.86 | 10266.43 | 19310.86 | 19310.86 | Zenon Lipinski | N/A | 22-Aug-22 | 23-Sep-22 | 22-Aug-22 | 22-Aug-22 | 22-Aug-22 |  |  |  | 0
646918 | S&C FACEPLATE UPGRADES SW44-50 | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Aug-22 |  |  | 74499.56 | 78518.43 | 74499.56 | 74499.56 | K-Line Construction | K-Line | 03-Oct-22 | 25-Apr-23 | 29-Sep-22 | 14-Dec-22 | 14-Dec-22 | Contractor | Contractor |  | 0
646917 | S&C FACEPLATE UPGRADES SW44-432 | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Aug-22 |  |  | 74499.56 | 75384.15 | 74499.56 | 74499.56 | K-Line Construction | K-Line | 28-Sep-22 | 25-Apr-23 | 27-Sep-22 | 14-Dec-22 | 14-Dec-22 | Contractor | Contractor |  | 0
646916 | S&C FACEPLATE UPGRADES SW44-448 | 805 - Sandalwood | 150784 | Active | 98 | COMPLETE |  |  | 2022 | Agostini, Robert | Casey, Ryan | 22-Aug-22 |  |  | 74499.56 | 79484.65 | 74499.56 | 74499.56 | K-Line Construction | K-Line | 27-Sep-22 | 27-Jul-23 | 26-Sep-22 | 02-Dec-22 | 14-Dec-22 | Contractor | Contractor |  | 0
646933 | MAIN ST. & MARKET ST. BLDG B / BRAM / NS00266262 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646934 | THE BRIGHT SIDE AT MAYFIELD VILLAGE 21T-11006B - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646935 | CLARKWAY DRIVE TOWNHOME DEVELOPMENT - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646944 | 2023 POLE RENEWAL- CAMPBELL DR - GRID E3 - (45 POLES) | 805 - Sandalwood | 150284 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael | 30-Dec-22 | 45 |  | 1289452.85 | 1059092.58 | 1289452.85 | 1289452.85 | AW Group | A&W | 07-Jul-23 | 28-Dec-23 | 06-Feb-23 | 24-Feb-23 |  | Locates |  |  | 0
646955 | 2023 SWITCHGEAR RENEWAL-SITE 177 - PARKHURST SQ-BRAMPTON-GRID M4 | 805 - Sandalwood | 150282 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 29-Dec-22 | 1 |  | 173191.37 | 6083.27 | 173191.37 | 173191.37 | Graham Gegear |  | 22-Jun-23 | 23-Mar-26 | 13-Jun-23 | [5 empty] | 0
646956 | THIS WO IS TO BE RE-PURPOSED TO SCADA SG INSTALL-SITE#236 | 805 - Sandalwood | 150282 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646957 | 2023 DA SWITCHGEAR RENEWAL-SITE 212 - FERNFOREST DR. - GRID J2 | 805 - Sandalwood | 150282 | Active | 84 | ACTIVE | High | SwGear | 2023 | Agostini, Robert | Miller, Michael | 29-Dec-22 | 1 |  | 235650.13 | 188056.65 | 235650.13 | 235650.13 | AW Group | A&W | 17-Oct-23 | 18-Oct-23 | 02-Oct-23 | 03-Jul-23 |  |  |  |  | 0
646962 | 8850 MCLAUGHLIN RD S / BRAM / NS00253151 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 01-Jun-23 |  |  | 125823.53 | 705.78 | 125823.53 | 125823.53 | Simon Evason | Somervl | 13-Sep-23 | 13-Sep-23 | 11-Sep-23 | [5 empty] | 0
646963 | 120 SANDALWOOD PKWY W / BRAM / UP00252629 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 81 | PPS INCOMPLETE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 89325 | 3371.23 | 89325 | 89325 | Dre Danieli |  |  | 27-Jul-23 | [6 empty] | 0
646972 | 475 CHRYSLER DRIVE/BRAM/UP00252758/1000 KVA | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 22-Jun-23 |  |  | 95242.94 | 4667.91 | 95242.94 | 95242.94 | Simon Evason | Somervl | 06-Oct-23 | 06-Oct-23 | 02-Oct-23 | [5 empty] | 0
646774 | KENNEDY RD N AND MAYFIELD RD TEMPORARY ANCHOR RELOCATION | 805 - Sandalwood | 150674 | Active | 98 | COMPLETE |  |  | 2022 | Watters, Maxwell | Boivin, Cameron | 30-Aug-22 |  |  | 44694.82 | 11283.77 | 44694.82 | 44694.82 | AW Group | A&W | 30-Sep-22 | 27-Jul-23 | 26-Sep-22 | 03-Oct-22 | 03-Oct-22 |  |  |  | 0
646990 | KENDALWOOD BLOCK 57 TOWNHOMES - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647065 | 12 INDELL LANE / BRAM / UP00266565 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 21-Oct-22 |  |  | 122610.99 | 933.52 | 122610.99 | 122610.99 | Simon Evason | Somervl | 02-Aug-23 | 02-Aug-23 | 31-Jul-23 | [5 empty] | 0
647069 | 2023 POLE RENEWAL -WILKINSON RD - GRID I5 PHASE 1 | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647143 | 3900 EBENEZER RD/ BRAM/ UP00233357/ 2MV | 805 - Sandalwood | 150386 | Active | 45 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647188 | 1925, 1935, 1945, & 1955 COTTRELLE BLVD / BRAM / NS00265694 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 05-May-23 |  |  | 172103.59 | 8587.01 | 172103.59 | 172103.59 | Simon Evason | Somervl | 14-Nov-23 | 14-Nov-23 | 01-Nov-23 | [5 empty] | 0
647189 | 160 SUN PAC BLVD/BRAM/NS00269176/ 150 KVA | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647199 | 2023 POLE RENEWAL -HWY 410 - BOVAIRD TO WILLIAMS PKWY | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647225 | 2023 POLE REBUILD - HWY 410 | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647224 | 2023 POLE REBUILD - HEARTLAKE RD - GRID H4 - PH1 | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647229 | 10 ECO PARK CLOSE / BRAM / NS00217907 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 92 | ANALYZE |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 18-Nov-22 |  |  | 131068.56 | 144784.52 | 131068.56 | 131068.56 | Simon Evason | Somervl | 07-Jul-23 | 27-Jul-23 | 03-Jul-23 | 04-May-23 | 10-May-23 |  |  |  | 0
647228 | 15 NEWKIRK COURT / BRAM / NS00217911 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 18-Nov-22 |  |  | 109750.47 | 106639.57 | 109750.47 | 109750.47 | Simon Evason | Somervl | 16-Jun-23 | 02-Aug-23 | 12-Jun-23 | 26-Jun-23 |  | Customer |  |  | 0
647282 | 5 NEWKIRK CRT / BRAM / NS00217912 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 91 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 06-Jan-23 |  |  | 114186.83 | 111696.01 | 114186.83 | 114186.83 | Simon Evason | Somervl | 19-Apr-23 | 27-Jul-23 | 12-Apr-23 | 13-Apr-23 | 06-Jun-23 | Customer | Customer |  | 0
647281 | 20 ECOPARK CLOSE / BRAM / NS00217908 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 06-Jan-23 |  |  | 135196.19 | 1729.51 | 135196.19 | 135196.19 | Simon Evason | Somervl | 11-Dec-23 | 11-Dec-23 | 04-Dec-23 | [5 empty] | 0
647284 | 2023 TX RENEWAL VAULT T7173 | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647283 | 2024 SWITCH RENEWAL SW 44-414 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647291 | 2023 TX RENEWAL T5664 OH | 805 - Sandalwood | 150494 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 4 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647295 | 2023 TX RENEWAL GRID J3 - 4TX | 805 - Sandalwood | 150285 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 4 |  | 107944.23 | 28325.64 | 107944.23 | 107944.23 | AW Group | A&W | 13-Sep-23 | 08-Aug-23 | 01-Sep-23 | 20-Jul-23 |  |  |  |  | 0
647294 | 2023 TX RENEWAL GRID I3 - 1 TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 |  | 21846.95 | 517.56 | 21846.95 | 21846.95 | Reaburn, Jeff |  | 03-Oct-23 | 03-Oct-23 | 02-Oct-23 | [5 empty] | 0
647293 | 2023 TX RENEWAL GRID G4-1 TX | 805 - Sandalwood | 150285 | Active | 95 | ANALYZE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 | 1 | 16991.38 | 7494.53 | 16991.38 | 16991.38 | Zenon Lipinski |  | 10-Feb-23 | 27-Jul-23 | 09-Feb-23 | 11-Jan-23 | 12-Jan-23 |  |  |  | 0
647292 | 2023 TX RENEWAL GRID E4 - 2TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 |  | 42794.69 | 1999.11 | 42794.69 | 42794.69 | Reaburn, Jeff |  | 05-Oct-23 | 05-Oct-23 | 02-Oct-23 | [5 empty] | 0
647307 | 2023 TX RENEWAL VAULT T2187 (PCB) | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647306 | 2023 TX RENEWAL GRID H3 - 1TX PM | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 |  | 44708.72 | 918.58 | 44708.72 | 44708.72 | Graham Gegear |  | 04-Aug-23 | 01-Aug-23 | 01-Aug-23 | [5 empty] | 0
647305 | 2023 TX RENEWAL GRID M3 - 1 TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 |  | 22801.67 | 892.26 | 22801.67 | 22801.67 | Graham Gegear |  | 02-Aug-23 | 02-Aug-23 | 01-Aug-23 | [5 empty] | 0
647304 | 2023 TX RENEWAL GRID K3 - 4 TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 4 |  | 135534.97 | 2770.97 | 135534.97 | 135534.97 | AW Group | A&W | 18-Oct-23 | 14-Aug-23 | 02-Oct-23 | [5 empty] | 0
647303 | 2023 TX RENEWAL GRID I2 - 1 TX | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 22-Dec-22 | 1 | 1 | 19038.8 | 13583.69 | 19038.8 | 19038.8 | Graham Gegear |  | 01-Jun-23 | 28-Jul-23 | 31-May-23 | 03-May-23 | 03-May-23 |  |  |  | 0
647302 | 2023 TX RENEWAL GRID G4 - 1 TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 |  | 22801.67 | 1118.36 | 22801.67 | 22801.67 | Graham Gegear |  | 02-Aug-23 | 28-Jul-23 | 01-Aug-23 | [5 empty] | 0
647301 | 2023 TX RENEWAL GRID G2 - 6 TX | 805 - Sandalwood | 150285 | Active | 95 | ANALYZE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 6 | 6 | 89003.03 | 62192.04 | 89003.03 | 89003.03 | Zenon Lipinski |  | 30-Mar-23 | 27-Jul-23 | 15-Mar-23 | 06-Feb-23 | 06-Feb-23 |  |  |  | 0
647300 | 2024 SWITCH RENEWAL SW 44-423 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647299 | 2023 TX RENEWAL GRID E5 - 2TX | 805 - Sandalwood | 150285 | Active | 95 | ANALYZE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 2 | 2 | 28434.69 | 15958.24 | 28434.69 | 28434.69 | Zenon Lipinski |  | 06-Feb-23 | 27-Jul-23 | 01-Feb-23 | 13-Jan-23 | 13-Jan-23 |  |  |  | 0
647298 | 2023 TX RENEWAL GRID E3 - 2TX | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 2 | 2 | 35477.74 | 25366.43 | 35477.74 | 35477.74 | AW Group | A&W | 07-Sep-23 | 01-Aug-23 | 01-Sep-23 | 12-Jul-23 | 12-Jul-23 |  |  |  | 0
647297 | 2023 TX RENEWAL GRID D3 - 1TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 |  | 22916.1 | 425.97 | 22916.1 | 22916.1 | Graham Gegear |  | 03-Aug-23 | 31-Jul-23 | 01-Aug-23 | [5 empty] | 0
647296 | 2023 TX RENEWAL GRID D2 - 1- 3PH | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 20-Dec-22 | 1 |  | 29452.94 | 1135.41 | 29452.94 | 29452.94 | Graham Gegear |  | 19-Jul-23 | 28-Jul-23 | 18-Jul-23 | [5 empty] | 0
647310 | 2023 TX RENEWAL T10452 OH | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647309 | 2023 TX RENEWAL T11933 OH | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647308 | 2023 TX RENEWAL T3133 OH -3PH | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647325 | 2023 3PH O/H T10796 RENEWAL | 805 - Sandalwood | 150285 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647331 | 2023 TX RENEWAL - 1PH MP - T9609 - GRID K4 - 119 ELLERSLIE RD. | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647334 | 2023 TX RENEWAL - GRID K2 - 2 TX (1PH MP) | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 2 | 2 | 31326.27 | 22916.36 | 31326.27 | 31326.27 | AW Group | A&W | 06-Nov-23 | 01-Aug-23 | 01-Nov-23 | 13-Jul-23 | 13-Jul-23 |  |  |  | 0
647335 | 2023 TX RENEWAL - GRID G1 - 21 WOODCREEK DR. (1PH MP) | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 1 |  | 19646.49 | 244.89 | 19646.49 | 19646.49 | Reaburn, Jeff |  | 05-Sep-23 | 05-Sep-23 | 01-Sep-23 | [5 empty] | 0
647341 | 2023 TX RENEWAL - GRID J3 - 14 HAWKINS CT (1PH MP) | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 1 | 1 | 14600.06 | 13138.14 | 14600.06 | 14600.06 | Graham Gegear |  | 01-Jun-23 | 28-Jul-23 | 31-May-23 | 02-Jun-23 | 02-Jun-23 |  |  |  | 0
647342 | 2023 TX RENEWAL - GRID N2 - 26 CHEVAL CT (1PH MP) | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 1 | 1 | 15104.41 | 10256.52 | 15104.41 | 15104.41 | Graham Gegear |  | 01-Jun-23 | 28-Jul-23 | 31-May-23 | 05-Jun-23 | 05-Jun-23 | Lines | Lines |  | 0
647344 | 2023 TX RENEWAL (1PH MP) - GRID I3 - 4 TX | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 05-Dec-22 | 4 | 4 | 70117.09 | 47720.59 | 70117.09 | 70117.09 | AW Group | A&W | 09-Nov-23 | 27-Jul-23 | 01-Nov-23 | 18-Jul-23 | 19-Jul-23 |  |  |  | 0
647345 | 2023 TX RENEWAL (1PH MP) - GRID F3 - 8 TX | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 05-Dec-22 | 8 | 8 | 116961.86 | 91699.6 | 116961.86 | 116961.86 | Graham Gegear |  | 31-Aug-23 | 31-Aug-23 | 15-Aug-23 | 15-May-23 | 31-May-23 |  |  |  | 0
647346 | 2023 TX RENEWAL (1PH MP) - GRID F2 - 2 TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 2 |  | 32743.88 | 26917.99 | 32743.88 | 32743.88 | AW Group | A&W | 07-Sep-23 | 01-Aug-23 | 01-Sep-23 | [5 empty] | 0
647347 | 2023 TX RENEWAL (1PH MP) - GRID B3 - 2 TX | 805 - Sandalwood | 150285 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 23-Dec-22 | 1 |  | 28881.57 | 10395.64 | 28881.57 | 28881.57 | Graham Gegear |  | 02-Jun-23 | 31-Jul-23 | 31-May-23 | 19-Jun-23 |  | Lines | Lines |  | 0
647348 | 2023 TX RENEWAL (1PH MP) - GRID G5 - 11 BLOOMINGDALE DR. | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 23-Dec-22 | 1 |  | 12524.63 | 257.89 | 12524.63 | 12524.63 | Reaburn, Jeff |  | 02-Nov-23 | 02-Nov-23 | 01-Nov-23 | [5 empty] | 0
647349 | 2023 TX RENEWAL (1PH MP) - GRID M2 - 2 TX | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 23-Dec-22 | 2 | 2 | 32632.65 | 25650.66 | 32632.65 | 32632.65 | Graham Gegear |  | 06-Jun-23 | 01-Aug-23 | 01-Jun-23 | 29-May-23 | 30-Jun-23 |  | Lines |  | 0
647350 | 2023 TX RENEWAL (1PH MP) - GRID N3 - 9 BLUFFWOOD CRES. | 805 - Sandalwood | 150285 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 22-Dec-22 | 1 | 1 | 15680.76 | 9930.71 | 15680.76 | 15680.76 | Graham Gegear |  | 02-Jun-23 | 28-Jul-23 | 01-Jun-23 | 02-Jun-23 | 02-Jun-23 | Lines |  |  | 0
647353 | 2023 TX RENEWAL (3PH MP) - GRID F1 - 11975 HURONTARIO ST. - T11391 | 805 - Sandalwood | 150285 | Active | 80 | Upload Completed |  |  | 2023 | Agostini, Robert | Miller, Michael | 21-Dec-22 | 1 |  | 29590.23 | 192.08 | 29590.23 | 29590.23 | Persaud, Ryan |  | 21-Dec-23 | 31-Jul-23 | 19-Dec-23 | [5 empty] | 0
647356 | 2023 TX RENEWAL (3PH MP) - 80 GREAT LAKES DR. UNIT #151 - T11819 | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 22-Dec-22 | 1 |  | 53857.4 | 354.98 | 53857.4 | 53857.4 | Reaburn, Jeff |  | 07-Sep-23 | 07-Sep-23 | 01-Sep-23 | [5 empty] | 0
647358 | 2023 TX RENEWAL (3PH MP) - 180 GREAT LAKES DR. - T11815 | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647359 | 2023 TX RENEWAL (3PH MP) - GRID I2 - 70 GREAT LAKES DR. - T11818 | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647360 | 2023 TX RENEWAL (3PH MP) - 28 FINCHGATE BLVD. - T11266 | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 22-Dec-22 | 1 |  | 42640.61 | 255.6 | 42640.61 | 42640.61 | Reaburn, Jeff |  | 13-Dec-23 | 13-Dec-23 | 11-Dec-23 | [5 empty] | 0
647361 | 2023 VAULT TX RENEWAL - GRID H4 - T10489 - 224 RUTHERFORD RD. S. | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647363 | 2023 TX RENEWAL (OH 3PH) - GRID H4 - 85 ORENDA RD. - T11259 | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647362 | 2023 TX RENEWAL (OH 1-PH) - GRID B3 - 2TX - RIVER RD. | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 2 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647366 | 2023 TX RENEWAL GRID G3 - 5TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647368 | 2023 TX RENEWAL GRID H2 - 7TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647370 | 2023 TX RENEWAL (OH 1-PH) - GRID R2 - 5556 COUNTRYSIDE DR. - T4783 | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647372 | 2023 POLE RENEWAL -WILKINSON RD - GRID I5 PHASE 2 | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647374 | AIRPORT ROAD SYSTEM EXPANSION COUNTRYSIDE TO MAYFIELD | 805 - Sandalwood | 152453 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli | A&W |  | 20-Jul-20
647386 | 2023 TX RENEWAL GRID J3 - OH 1TX | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647072 | 3518 EBENEZER ROAD ANCHOR RELOCATION | 805 - Sandalwood | 150674 | Active | HO | H8 |  |  | 2023 | Watters, Maxwell | Mckeen, Brant | 11-Oct-22 |  |  | 19458.77 | 7533.81 | 19458.77 | 19458.77 | AW Group | A&W | 14-Nov-22 | 25-Mar-24 | 14-Nov-22 | 14-Nov-22 |  |  |  |  | 0
647452 | 2023 SWITCHGEAR RENEWAL-SITE 550 (FORMERLY 217) - EDENBROOK HILL RD | 805 - Sandalwood | 150282 | Active | 92 | ANALYZE | High | SwGear | 2023 | Agostini, Robert | Casey, Ryan | 29-Dec-22 | 1 | 1 | 241802.11 | 222928.06 | 241802.11 | 241802.11 | AW Group | A&W | 17-Oct-23 | 18-Oct-23 | 02-Oct-23 | 03-Jul-23 | 20-Jul-23 |  |  |  | 0
647451 | 2023 SWITCHGEAR RENEWAL-SITE 559 (OLD 243) - SANDALWOOD PKWY E | 805 - Sandalwood | 150282 | Active | 84 | ACTIVE | High | SwGear | 2023 | Agostini, Robert | Casey, Ryan | 29-Dec-22 | 1 |  | 251407.24 | 13750.64 | 251407.24 | 251407.24 | AW Group | A&W | 17-Oct-23 | 18-Oct-23 | 02-Oct-23 | 13-Jul-23 |  |  |  |  | 0
647462 | 2023 TX RENEWAL GRID J3 - 1 - 3PH TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 19-Dec-22 | 1 |  | 33310.84 | 550.58 | 33310.84 | 33310.84 | Graham Gegear |  | 24-Jul-23 | 28-Jul-23 | 21-Jul-23 | [5 empty] | 0
647468 | 2023 TX RENEWAL GRID A3 - OH 1TX | 805 - Sandalwood | 150285 | Active | 45 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647467 | 2023 TX RENEWAL GRID L2 - 1TX - SNOWCAP RD. | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 22-Dec-22 | 1 |  | 19883.09 | 387.49 | 19883.09 | 19883.09 | Reaburn, Jeff |  | 05-Sep-23 | 05-Sep-23 | 01-Sep-23 | [5 empty] | 0
647613 | 2023 TX RENEWAL 3PH VAULT T10419 | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647612 | 2023 TX RENEWAL 3PH VAULT T10736 | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647625 | 2023 POLE REBUILD - HEARTLAKE RD - GRID H4 - PH2 | 805 - Sandalwood | 150284 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647639 | 295 QUEEN ST E / BRAM / NS00273540 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647652 | SANDRINGHAM EAST PHASE 1 - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647664 | ROAD AUTHORITY - DIXIE NOISE WALL RELOCATION - ANCHOR CONFLICT | 805 - Sandalwood | 150645 | Active | 82 | RELEASED |  |  | 2023 | Watters, Maxwell | Boivin, Cameron | 02-Jun-23 |  |  | 23487.78 | 4504.16 | 23487.78 | 23487.78 | Graham Gegear |  | 24-Jul-23 | 01-Aug-23 | 19-Jul-23 | [5 empty] | 0
647678 | 2023 TX RENEWAL (GRID F3)- 1PH PAD TX - T1377 | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 22-Dec-22 | 1 |  | 33955.89 | 931.56 | 33955.89 | 33955.89 | Graham Gegear |  | 28-Jul-23 | 28-Jul-23 | 27-Jul-23 | [5 empty] | 0
647704 | 4137 MAYFIELD RD/BRAM/UP00277651/2 X 1500 KVA | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 02-May-23 |  |  | 171307.04 | 67161.7 | 171307.04 | 171307.04 | Simon Evason | Somervl | 21-Jun-23 | 14-Aug-23 | 05-Jun-23 | 06-Jun-23 |  | Customer |  |  | 0
647732 | 5603 COUNTRYSIDE DR / BRAM / NS00231109 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647733 | 25 RAINHAM COURT / BRAM / NS00261138 / CUSTOMER-OWNED SUBSTATION | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647741 | 2023 TX RENEWAL (1PH MP) - GRID K3 - 4 TX | 805 - Sandalwood | 150285 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 22-Dec-22 | 4 |  | 91863.03 | 14841.16 | 91863.03 | 91863.03 | AW Group | A&W | 11-Oct-23 | 04-Aug-23 | 02-Oct-23 | [5 empty] | 0
647745 | 2023 OH TX RENEWAL (GRID H1)- 1PH OH TX - T14921 | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647744 | 2023 TX RENEWAL (GRID G3) - 3 X 1PH PAD TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 3 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647746 | MISSISSAUGA ROAD, MAYFIELD TO YARDMASTER ROAD - STORM GUYING | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jun-23
647749 | 2023 VAULT TX RENEWAL - GRID K3 - T10530 - 1025 N PARK DR | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647747 | 2023 OH TX RENEWAL (GRID P2) - 1PH OH TX - T4810 | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647782 | COUNTRYSIDE DR - POLE RELOCATION | 805 - Sandalwood | 150674 | Active | 45 | ACTIVE |  |  | 2023 | Watters, Maxwell | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647785 | 9124 DIXIE ROAD TOWNHOMES - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644452 | 1930 WANLESS DR / BRAM / NS00206438 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647847 | 29 CLARENCE ST FEEDER EXTENSION | 805 - Sandalwood | 150674 | Active | 10 | H8 |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647868 | 2024 SWITCHGEAR RENEWAL-SITE 249 - (25M E/O SUNNYMEADOW BLVD) | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647900 | 2023 SWITCHGEAR RENEWAL-SITE 171 - KNIGHTSBRIDGE RD - GRID J4 | 805 - Sandalwood | 150282 | Active | 92 | ANALYZE |  |  | 2023 | Agostini, Robert | Miller, Michael | 13-Dec-22 | 1 | 1 | 121827.32 | 112546.2 | 121827.32 | 121827.32 | AW Group | A&W | 25-Jul-23 | 27-Jul-23 | 11-Jul-23 | 12-Jun-23 | 18-Jul-23 |  |  |  | 0
647964 | 8100 MISSISSAUGA RD/BRAM/NS00290296-2X3MVA AND 2 X 3.5MVA C.O. TX'S | 805 - Sandalwood | 150386 | Active | 40 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647999 | KENDALWOOD LAND (HERITAGE) - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Active | 84 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne | 31-Mar-23 |  |  | 48985.38 | 36389.68 | 48985.38 | 48985.38 | Graham Gegear | N/A | 09-Jun-23 | 02-Aug-23 | 05-Jun-23 | 28-Jun-23 |  | Lines |  |  | 0
648030 | 80 ACE DR/ BRAM/ NS00133135/ 3PH PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 02-May-23 |  |  | 87810.08 | 65779.1 | 87810.08 | 87810.08 | Simon Evason | Somervl | 18-Aug-23 | 18-Aug-23 | 14-Aug-23 | 06-Jul-23 |  |  |  |  | 0
648146 | COLRAIN DRIVE - POLE RELOCATION | 805 - Sandalwood | 150674 | Active | 92 | ANALYZE |  |  | 2023 | Watters, Maxwell | Boivin, Cameron | 07-Feb-23 |  |  | 24918.37 | 19987.51 | 24918.37 | 24918.37 | AW Group | A&W | 27-Mar-23 | 27-Jul-23 | 27-Mar-23 | 15-Mar-23 | 15-Mar-23 |  |  |  | 0
647150 | 12 HENDERSON AVE (PERMANENT) / BRAM / NS00274695 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 01-Nov-22 |  |  | 48651.96 | 547.5 | 48651.96 | 48651.96 | Simon Evason |  | 27-Sep-23 | 27-Sep-23 | 25-Sep-23 | [5 empty] | 0
648139 | FEEDER EXPANSION HURONTARIO STREET | 805 - Sandalwood | 152453 | Active | 92 | ANALYZE |  |  | 2023 | Watters, Maxwell | Robinson, David | 24-Mar-23 |  |  | 453081.25 | 360774.07 | 453081.25 | 453081.25 | K-Line Construction | K-Line | 30-Jun-23 | 27-Jul-23 | 24-May-23 | 25-May-23 | 15-Jun-23 | Contractor |  |  | 0
648181 | BRAM EAST SYSTEM EXPANSION | 805 - Sandalwood | 152453 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Mckeen, Brant |  |  |  | 0 | 0 |  | 0 | Dre Danieli | N/A |  | 20-Jul-20
648241 | HERITAGE ROAD LAYOVER FACILITY - 10885 WINSTON CHURCHILL BLVD, BRAMPTON | 805 - Sandalwood | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648288 | 3 LOWRY DR / BRAM / UP00293155 / 3PH | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648300 | 20 NEWKIRK CRT/BRAM/NS00311175/2000 KVA PAD | 805 - Sandalwood | 150386 | Active | 84 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny | 15-Dec-22 |  |  | 73811.54 | 66215.23 | 73811.54 | 73811.54 | Simon Evason |  | 25-Apr-23 | 28-Jul-23 | 25-Apr-23 | 25-Apr-23 |  |  |  |  | 0
648310 | 42 ACE DR / BRAM / NS00260225 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648311 | 241 QUEEN ST E / BRAM / NS00280494 / C.O. TX | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648373 | MCMURCHY AVENUE S. AND STEELE STREET W. - ANCHOR RELOCATION AND POLE SUPPORT | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2023 | Watters, Maxwell | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-23
648374 | 241 QUEEN ST. E. B / BRAM / NS00280494 / C.O. TX | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648463 | MATTAMY GOREWAY - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Active | 93 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne | 09-Mar-23 |  |  | 39468.16 | 39209.73 | 48313.16 | 39468.16 | Graham Gegear | Somervl | 09-May-23 | 27-Jul-23 | 08-May-23 | 09-May-23 | 10-May-23 | Customer | Customer |  | -8,845.00
636909 | 4KV VOLTAGE CONVERSION - PHASE 9A (CENTRAL NORTH) | 805 - Sandalwood | 151139 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael | 20-Dec-22 |  |  | 1376355.28 | 883361.77 | 1376355.28 | 1376355.28 | Reaburn, Jeff |  | 20-Oct-23 | 10-Apr-24 | 31-Jan-23 | 09-Jan-23 |  |  |  |  | 0
636445 | 2023 POLE RENEWAL GRID M1-31 (1 POLE) | 805 - Sandalwood | 150284 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Miller, Michael | 23-Dec-22 | 1 |  | 32968.31 | 8975.86 | 32968.31 | 32968.31 | Reaburn, Jeff |  | 05-Oct-23 | 05-Oct-23 | 02-Oct-23 | [5 empty] | 0
648507 | 9575 MISSISSAUGA RD (TEMP) / BRAM / NS00318432 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 93 | ANALYZE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 06-Jan-23 |  |  | 7101.73 | 9696.14 | 7101.73 | 7101.73 | Simon Evason |  | 17-Jan-23 | 31-Jul-23 | 16-Jan-23 | 30-Jan-23 | 06-Feb-23 | Materials | Materials |  | 0
642674 | 4KV CONVERSION - PHASE 4C | 805 - Sandalwood | 151139 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | Casey, Ryan | 30-Nov-22 |  |  | 250531.39 | 13180.58 | 250531.39 | 250531.39 | Graham Gegear | Transpw | 03-Jul-23 | 31-Jul-23 | 22-Jun-23 | [5 empty] | 0
648555 | 8O BRAMALEA ROAD N / BRAM / NS00304797 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648736 | POLE RELOCATION 8000 MISSISSAUGA RD | 805 - Sandalwood | 150674 | Active | HO | H2 |  |  | 2023 | Watters, Maxwell | Robinson, David | 14-Apr-23 |  |  | 238306.68 | 15549.15 | 238306.68 | 238306.68 | AW Group | A&W | 17-Jul-23 | 27-Jul-23 | 03-Jul-23 | [5 empty] | 0
648745 | 2111 STEELES AV E/BRAM/NS00288291/24 MVA | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644878 | 0 VETERANS DR / BRAM / NS00213835 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 45 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
644877 | 11953 CREDITVIEW RD / BRAM / NS00212968 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648846 | 237 B ADVANCE BLVD. / BRAM / UP00313938 / 3PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Rao, Gaurav | Central North |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648313 | PH2B 42M71 FEEDER EGRESS U/G NORTH - WANLESS DR & CREDITVIEW RD | 805 - Sandalwood | 150408 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 05-May-23 |  |  | 1055241.3 | 69543.32 | 1055241.3 | 1055241.3 | AW Group | A&W | 15-Sep-23 | 31-Jul-23 | 31-Jul-23 | 17-Jul-23 |  |  |  |  | 0
647556 | PH2A 42M71 FEEDER EGRESS U/G SOUTH - BOVAIRD & SALVATION RD | 805 - Sandalwood | 150408 | Active | 82 | RELEASED |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 16-Mar-23 |  |  | 629055.45 | 38336.23 | 629055.45 | 629055.45 | AW Group | A&W | 22-Aug-23 | 22-Aug-23 | 04-Jul-23 | [5 empty] | 0
636815 | PH1 42M71 PH1 FEEDER EGRESS O/H - SALVATION/CREDITVIEW - WANLESS TO BOVAIRD | 805 - Sandalwood | 150408 | Active | 84 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael | 08-Feb-23 |  |  | 982467.57 | 640747.31 | 982467.57 | 982467.57 | AW Group | A&W | 07-Jul-23 | 27-Jul-23 | 17-Apr-23 | 01-May-23 |  | Contractor |  |  | 0
648945 | 10885 WINSTON CHURCHIL BLVD - MX LAYOVER FACILITY, 2 X 4MVA COS | 805 - Sandalwood | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649059 | MAVIS ROAD WIDENING POLE REMOVAL | 805 - Sandalwood | 150645 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649079 | 2023-WHOLESALE METER INSTALLATION UPGRADES AND REGISTRATION PLEASANT TS-BRMP 2 | 805 - Sandalwood | 152378 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649078 | 2023-WHOLESALE METER INSTALLATION UPGRADES AND REGISTRATION-PLEASANT TS-BRAMPTON | 805 - Sandalwood | 152378 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649080 | 2023-WHOLESALE METER INSTALLATION UPGRADES & REGISTRATION PLEASANT TS-42M45 | 805 - Sandalwood | 152378 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649081 | MISSISSAUGA ROAD & LAGERFELD POLE RELOCATION - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Active | 82 | RELEASED |  |  | 2023 | Gamboa, Henry | Armstrong, Colby | 26-Jun-23 |  |  | 51352.66 | 15310.25 | 51352.66 | 51352.66 | Graham Gegear | N/A | 08-Aug-23 | 08-Aug-23 | 31-Jul-23 | [5 empty] | 0
649240 | 2023 EMERGING OH PROJECT - SECONDARY SERVICE - 67 DORSET DRIVE | 805 - Sandalwood | 151449 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649266 | 150 FIRST GULF BLVD / BRAM / NS00321129 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 12-Jul-23 |  |  | 136780.56 | 350.54 | 136780.56 | 136780.56 | Simon Evason | Somervl | 06-Sep-23 | 06-Sep-23 | 28-Aug-23 | [5 empty] | 0
649269 | 8921 MISSISSAUGA RD / BRAM / NS00230159 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 70 | ACTIVE |  |  | 2023 | Rao, Gaurav | Barnum, Corey |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649278 | 30 BRAMTREE COURT / BRAM / NS00281086 / 25MVA C.O TX | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 16-Nov-23
649369 | 15 NEWKIRK COURT / BRAM / UP00XXXXXX / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Wigley, Graham | 17-Jul-23 |  |  | 93188.93 | 0 | 93188.93 | 93188.93 | Simon Evason | N/A | 22-Sep-23 | 22-Sep-23 | 21-Sep-23 | [5 empty] | 0
649429 | 36 ACE DR/BRAM/NS00260224/1500 KVA PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649487 | 735 INTERMODAL DR / BRAM / UP00295000 / C.O SUBSTATION | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649490 | 100 ACE DR / BRAM / UP00332729 / CUSTOMER-OWNED SUBSTATION | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Barnum, Corey |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649276 | 2600 NORTH PARK DR / BRAM / NS00325161 / CO SUBSTATION | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Roopnaraine, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649524 | CLARKWAY DRIVE TOWNHOME DEVELOPMENT - SUBD CAP PROJ | 805 - Sandalwood | 151674 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649522 | 25M14 FDR EXPANSION-JIM YARROW TS TO 55 HEREFORD STREET | 805 - Sandalwood | 152453 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649540 | 210 GREAT LAKES DR / BRAM / NS00327488 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649546 | POLE # 10329 RELOCATION MISSISSAUGA RD AT TCPL | 805 - Sandalwood | 150645 | Active | 92 | ANALYZE |  |  | 2023 | Watters, Maxwell | Robinson, David | 10-Feb-23 |  |  | 37387.82 | 36258.73 | 37387.82 | 37387.82 | AW Group | A&W | 05-Apr-23 | 27-Jul-23 | 05-Apr-23 | 31-May-23 | 31-May-23 | Contractor | Contractor |  | 0
649547 | 235 FLETCHERS CREEK DR/BRAM/NS00304704/NEW METER | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Roopnaraine, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 23-Mar-23
649695 | 80 BEECH ST/BRAM/UP00337564/3PH 500KVA PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Roopnaraine, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649698 | REMOVE D/G AND ANCHORS AND INSTALL STRUT GUY AT POLE # 25 & 37 ON WEST DRIVE | 805 - Sandalwood | 150673 | Active | 92 | ANALYZE |  |  | 2023 | Watters, Maxwell | Robinson, David | 18-May-23 |  |  | 30731.69 | 23760.93 | 30731.69 | 30731.69 | AW Group | A&W | 03-Jul-23 | 27-Jul-23 | 03-Jul-23 | 01-Jun-23 | 01-Jun-23 |  |  |  | 0
649711 | POLE RELOCATION FOR ROAD WIDENING, DIXIE RD - BOVAIRD DR. TO COUNTRYSIDE DR. | 805 - Sandalwood | 150645 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Robinson, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649825 | ROAD AUTHORITY - POLE RELOCATIONS - REGION OF PEEL - DIXIE RD & MAYFIELD RD | 805 - Sandalwood | 150645 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649883 | 2024 D/A SWITCHGEAR INSTALLATION-SITE 219 -SANDALWOOD PKWY W | 805 - Sandalwood | 151104 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649886 | 4316 EBENEZER ROAD DEVELOPMENT | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649906 | GAP POLE LINE REBUILD - MCLAUGHLIN RD N AND CNR | 805 - Sandalwood | 150284 | Active | 70 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649924 | 2024 SWITCHGEAR RENEWAL - SITE# 160 - NORTH PARK DR | 805 - Sandalwood | 150282 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649977 | 2024 D/A SWITCHGEAR INSTALLATION-SITE 2 - MAJOR WM SHARPE DR | 805 - Sandalwood | 151104 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649986 | 2024 D/A SWITCHGEAR INSTALLATION-SITE 236 - SUNNY MEADOW BLVD | 805 - Sandalwood | 151104 | Active | 48 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650018 | 8175 WINSTON CHURCHILL BLVD / BRAM / NS00344368 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650022 | 2024 SWITCHGEAR RENEWAL- SITE 254 | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650021 | 2024 SWITCHGEAR RENEWAL- SITE 160 | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650020 | 2024 SWITCHGEAR RENEWAL- SITE 178 | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650042 | MATTAMY FEEDMILL BLOCK 9 PH 1B | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650041 | MATTAMY FEEDMILL BLOCK 9 PH 1A | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650014 | 3 STRATHEARN AVE / BRAM / UP00349788 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 98 | CANCELLED |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 251.03 |  | 0 | Dre Danieli |  |  | 27-Jul-23
650087 | 10783 CREDITVIEW RD INC - SUBD CAP PROJ | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650094 | 115/125 Yellow Avens Blvd/BRAM/NS00348981/3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Singh, Harmol |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650124 | 329 CLARENCE ST / BRAM / UP00347366 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Barnum, Corey |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650032 | 9535 MISSISSAUGA RD / BRAM / NS00225828 / 3PH PAD (750 KVA) | 805 - Sandalwood | 150386 | Active | 82 | RELEASED |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 12-Jul-23 |  |  | 116939.31 | 62801.18 | 54138.13 | 116939.31 | Simon Evason |  | 16-Aug-23 | 16-Aug-23 | 14-Aug-23 | [5 empty] | 62,801.18
650142 | 15 EDVAC DR. / BRAM / NS00343448 / CELL TOWER | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Roopnaraine, Ryan |  |  |  | 0 | 970.17 |  | 0 | Dre Danieli |  |  | 15-May-23
650186 | 2024 SWITCHGEAR RENEWAL - SITE# 236 - SUNNY MEADOW BLVD | 805 - Sandalwood | 150282 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650188 | 2024 SWITCHGEAR RENEWAL- SITE 219 - SANDALWOOD PKY W | 805 - Sandalwood | 150282 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650189 | 2024 SWITCHGEAR RENEWAL - SITE# 2 - OPP. 154 MAJOR WM SHARPE DR | 805 - Sandalwood | 150282 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650191 | 2024 SWITCHGEAR RENEWAL - SITE# 208 - 71 WORTHINGTON AVE | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650194 | DA 2024 SWITCHGEAR RENEWAL - SITE# 205 - 140 VAN SCOTT DR | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650195 | 2023 SWITCHGEAR RENEWAL - SITE# 235 - 215 SUNNY MEADOW BLVD | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650196 | 2024 SWITCHGEAR RENEWAL - SITE# 204 - 25 PRECIDO CRT | 805 - Sandalwood | 150282 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650200 | 33 GEORGE ST / BRAM / NS00355350 / C.O. TX | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650235 | 922 NORTH PARK DR/BRAM/UP00352149/CUSTOMER OWNED EQUIPMENT UPGRADE | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 626.32 |  | 0 | Dre Danieli |  |  | 20-Jul-23
650221 | 7700 KENNEDY RD / BRAM / NS00354901 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Barnum, Corey |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650275 | 18 KENVIEW BLVD / BRAM / NS00323566 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Barnum, Corey |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650291 | 10794 BRAMALEA RD TOWNHOME ENCLAVE - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650360 | 2024 SWITCH RENEWAL SW 20-455 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650374 | 2111 STEELES AVE EAST - SYSTEM EXPANSION | 805 - Sandalwood | 152453 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650377 | 10799 CREDITVIEW RD - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650384 | 2024 SWITCH RENEWAL SW 20-589 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650387 | 2024 SWITCH RENEWAL SW 20-676 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650386 | 2024 SWITCH RENEWAL SW 44-458 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650385 | 2024 SWITCH RENEWAL SW 44-428 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650293 | 110 GLIDDEN RD / BRAM / NS00359633 / C.O SUBSTATION | 805 - Sandalwood | 150386 | Active | 91 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon | 30-May-23 |  |  | 19124.87 | 12826.31 | 19124.87 | 19124.87 | Simon Evason |  | 15-Jun-23 | 27-Jul-23 | 15-Jun-23 | 31-May-23 | 02-Jun-23 |  |  |  | 0
650393 | 2024 SWITCH RENEWAL SW 20-2025 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650402 | 2024 SWITCH RENEWAL SW 20-269 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650401 | 2024 SWITCH RENEWAL SW 20-2003 | 805 - Sandalwood | 151010 | Active | 48 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650424 | POLE RELOCATION AT 10750 HWY 50 -COLERAINE DRIVE | 805 - Sandalwood | 150674 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650472 | 7600 FINANCIAL DR / BRAM / NS00324134 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 82 | PDG SnR |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 112423.21 | 812.52 | 112423.21 | 112423.21 | Simon Evason | Somervl | 13-Feb-24 | 13-Feb-24 | 06-Feb-24 | [5 empty] | 0
650486 | 1014 HEARTLAKE ROAD - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650495 | 2024 DA SW20-1765 - WANLESS E/O CHINGUACOUSY | 805 - Sandalwood | 150494 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650527 | 2024 SWITCH RENEWAL SW 44-68 | 805 - Sandalwood | 151010 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650558 | 2024 DA 20-643 (C55 151104) | 805 - Sandalwood | 150494 | Active | 40 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650575 | 2024 DA 20-1763-WANLESS DR E/O CHINGUACOUSY RD | 805 - Sandalwood | 150494 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650576 | 2024-44KV D/A SWITCH INSTALLATION(44-292) - WEST DR N/O ORENDA | 805 - Sandalwood | 150494 | Active | 48 | ACTIVE |  |  | 2023 | Agostini, Robert | Miller, Michael |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
641997 | 43 WENTWORTH CRT / BRAM / UP00118833 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650623 | 10 KNIGHTSBRIDGE RD/BRAM/NS00360929/3000 KVA | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Barnum, Corey |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650634 | 33 GEORGE ST (TEMP) / BRAM / NS00374929 / 3PH PAD | 805 - Sandalwood |  | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650656 | DBRAND INVESTMENT CORPORATION LIMITED - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650685 | CUSTOMER INITIATED SYSTEM EXPANSION - BERKSHIRE DEVELOPMENT PHASE 2 42M69 | 805 - Sandalwood | 152453 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650699 | 2024 TX RENEWAL GRID F2- 1TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650698 | 2024 TX RENEWAL GRID E5 - 2TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650697 | 2024 TX RENEWAL GRID E4 - 7TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650696 | 2024 TX RENEWAL GRID E3 - 2TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650694 | 2024 TX RENEWAL GRID D4 - 1- 3PH TX T17631 | 805 - Sandalwood | 150285 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650693 | 2024 TX RENEWAL GRID D3 - 5TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650692 | 2024 TX RENEWAL GRID C5 - 1TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650691 | 2024 TX RENEWAL GRID C3 - 3TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650711 | 2024 TX RENEWAL GRID I3 BATCH 2 - 6TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650710 | 2024 TX RENEWAL GRID I3 BATCH 1 - 6TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650709 | 2024 TX RENEWAL GRID I2 - 1 -3PH TX T11819 | 805 - Sandalwood | 150285 | Active | 10 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650708 | 2024 TX RENEWAL GRID I2 - 1 TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650707 | 2024 TX RENEWAL GRID H3- 8TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650706 | 2024 TX RENEWAL GRID H2- 5TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650705 | 2024 TX RENEWAL GRID G5- 3TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650704 | 2024 TX RENEWAL GRID G4 - 1TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650703 | 2024 TX RENEWAL GRID G3 BATCH 2 - 7TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650702 | 2024 TX RENEWAL GRID G3 BATCH 1 - 6TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650701 | 2024 TX RENEWAL GRID F4 - 2TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650700 | 2024 TX RENEWAL GRID F3- 9TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650720 | 2024 TX RENEWAL GRID O3- 1TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650719 | 2024 TX RENEWAL GRID P3- 1TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650718 | 2024 TX RENEWAL GRID N3- 2TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650717 | 2024 TX RENEWAL GRID K4 - 5TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650716 | 2024 TX RENEWAL GRID K3 - 10TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650715 | 2024 TX RENEWAL GRID J3 BATCH 2 - 7TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650714 | 2024 TX RENEWAL GRID J3 BATCH 1 - 7TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650713 | 2024 TX RENEWAL GRID I3 BATCH 4 - 5TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650712 | 2024 TX RENEWAL GRID I3 BATCH 3 - 6TX | 805 - Sandalwood | 150285 | Active | 50 | ACTIVE |  |  | 2023 | Agostini, Robert | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650810 | MS22 BRAMPTON STATION SERVICE | 805 - Sandalwood | 150637 | Active | 10 | ACTIVE |  |  | 2023 | Dehaijle, Carlton | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650845 | 121949 ONTARIO INC. - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650844 | ASHLEY HERITAGE JOINT VENTURE - SUBD RES EDS | 805 - Sandalwood | 150630 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651026 | 1 & 3 ACADEMIC DR / BRAM / NS00345658 / 3PH PAD | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Wigley, Graham |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651064 | 8100 MISSSISSAUGA RD /BRAM/NS00389309/1500 KVA TEMP | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651111 | WILLIAMS PARKWAY UTILITY RELOCATIONS - MCLAUGHLIN RD. TO DIXIE RD. | 805 - Sandalwood | 150674 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651114 | GOREWAY DRIVE - REQUEST FOR PERMANENT HYDRO POLE DESIGN | 805 - Sandalwood | 150674 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651115 | GOREWAY DRIVE - REQUEST FOR PERMANENT HYDRO POLE DESIGN | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651121 | MCVEAN DRIVE PH2 - COUNTRYSIDE AND MAYFIELD | 805 - Sandalwood | 150645 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651132 | LAGERFIELD DR / BRAM / NS00388530 / 3MVA 3PH PAD | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Barnum, Corey |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651211 | 78 WALKER DR / BRAM / UP00384938 / 4 MVA C.O SUBSTATION | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Tan, Seefon |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651226 | 21 BOVAIRD DR. E / BRAM/ NS00374451 / 44KV CUST SUB | 805 - Sandalwood | 150386 | Active | 10 | ACTIVE |  |  | 2023 | Rao, Gaurav | Roopnaraine, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651260 | GUYING RELOCATION AT 25 RAINHAM CT | 805 - Sandalwood | 150674 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Volkov, Igor |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651246 | 360 CONSERVATION DR/ BRAM / NS00390066 / ICE RINK | 805 - Sandalwood | 150386 | Active | 50 | ACTIVE |  |  | 2023 | Rao, Gaurav | Roopnaraine, Ryan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
CS | Central South Region (ES) | [9 empty] | Central South |  | 455 | 288 | 203500768.99 | 142630966.52 | 71899564 | 71899564 | [5 empty] | 04-Dec-17 | 19-Jul-23
634917 | 86 Dundas St E - EMBLEM DEVELOPMENTS | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Huo, Lisa | 26-Jul-23 |  |  | 368772.46 | 18295.75 | 368772.46 | 368772.46 | Peter Costantini | Somervl | 14-Sep-23 | 14-Sep-23 | 08-Aug-23 | [5 empty] | 0
636307 | QUEENSTON DR PS. 3520 QUEENSTON DR. | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Huo, Lisa | 17-Apr-23 |  |  | 120022.98 | 13526.5 | 120022.98 | 120022.98 | Peter Costantini | Somervl | 02-Aug-23 | 10-Aug-23 | 12-Jul-23 | [5 empty] | 0
635803 | 5105 HURONTARIO ST. PROPOSED MIXED-USE DEVELOPMENT | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Huo, Lisa | 23-May-23 |  |  | 423484.98 | 16851.2 | 423484.98 | 423484.98 | Peter Costantini | Somervl | 16-Aug-23 | 15-Sep-23 | 26-Jun-23 | [5 empty] | 0
635058 | EXPANSION - 151 CITY CENTRE DRIVE - EXCHANGE BUILDING GROUP INC. | 800 - Mavis | 152371 | Active | 81 | Upload Completed |  |  | 2023 | Watters, Maxwell | Garcha, Tirath |  |  |  | 3201239.01 | 353845.48 | 3201239.01 | 3201239.01 | XMoinuddin, Saad | Transpw |  | 26-Jul-23 | [6 empty] | 0
335062 | 36 ELM DRIVE - SOLMAR DEVT - EDGE TOWERS | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mandic, Goran | Garcha, Tirath | 15-Nov-21 |  |  | 104327.96 | 65276.31 | 104327.96 | 104327.96 | Peter Costantini |  | 03-Mar-22 | 26-Jul-23 | 31-Jan-22 | 07-Jan-22 | 28-May-22 |  | Customer |  | 0
409877 | (SG1297) REMOVAL - ROCKWOOD RD. & RATHBURN RD. | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Cudzilo, Tomasz | 11-May-20 |  |  | 814817.88 | 814823.31 | 814817.88 | 814817.88 | Mark Bobanovic | Transpw | 12-Nov-21 | 24-Apr-23 | 14-Sep-21 | 14-Sep-21 | 23-Dec-21 | Lines | Lines |  | 0
635716 | 3020 LENWORTH DRIVE - MISS - NS - 500KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Roy, Akash | 15-Sep-21 |  |  | 83099.8 | 103100.98 | 83099.8 | 83099.8 | Peter Costantini | Somervl | 22-Nov-21 | 22-Nov-22 | 01-Nov-21 | 15-Oct-21 | 11-Nov-21 |  |  |  | 0
317585 | 1344 Fewster Dr. - Inflamax Research Srvice Upgrade | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 2428.76 |  | 0 | Macdougall, Stephen |  |  | 22-Sep-22
305509 | 2015 OTC (INITIAL) - VIEWMARK HOMES 20416 (EHM) | 800 - Mavis | 150652 | Inactive | 99 | CANCELLED |  |  | 2022 | Kafel, Krzysztof | Ricci, Leonardo |  |  |  | 1051354.62 | 5057.51 | 1051354.62 | 1051354.62 | Weaver, Thomas |  |  | 22-Sep-22 | [6 empty] | 0
631313 | QUOTE 1100 CANADIAN PLACE - TEMPORARY SERVICE | 800 - Mavis | 150388 | Inactive | 99 | COMPLETE | Low | Comm | 2021 | Mandic, Goran | Jacinto, Gerardo | 02-Aug-21 |  |  | 23799.81 | 12803.13 | 23799.81 | 23799.81 | Peter Costantini |  | 02-Aug-21 | 22-Sep-22 | 02-Aug-21 | 02-Aug-21 | 02-Aug-21 |  |  |  | 0
411176 | 1850 RATHBURN ROAD EAST-CHELSEA/LORMEL ON THE GREEN I | 800 - Mavis | 152302 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Garcha, Tirath |  |  |  | 0 | 16021.63 |  | 0 | XMoinuddin, Saad |  |  | 22-Sep-22
635539 | JOINT USE PERMIT HM2020-001 - CREDITVIEW RD - MISS | 800 - Mavis | 151537 | Inactive | 99 | CANCELLED |  |  | 2021 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 3574.13 |  | 0 | XMoinuddin, Saad |  |  | 06-Sep-22
380285 | 2018-NE FIELDGATE & PONYTRAIL TH BLOCK 1/0 CABLE REPLACEMENT | 800 - Mavis | 151401 | Inactive | 99 | COMPLETE |  |  | 2019 | Lucic, Marko | Cudzilo, Tomasz | 27-May-19 |  |  | 215714.56 | 214415.83 | 190895.62 | 215714.56 | Paul Tremblay | Transpw | 13-Aug-19 | 09-Aug-22 | 22-Jul-19 | 17-Oct-19 | 19-Nov-19 | MC/PUCC Permit | MC/PUCC Permit |  | 24,818.94
396199 | GO ELEC. - LWL - CONFLICT #LW20 & LW1778 - ALEXANDRA | 800 - Mavis | 150594 | Inactive | 99 | CANCELLED |  |  | 2022 | Tobin, Michael | Khuu, Philander |  |  |  | 0 | 12588.45 |  | 0 | Weaver, Thomas |  |  | 24-May-22
414107 | Port Credit Village West New Feeder | 800 - Mavis | 150363 | Inactive | 99 | COMPLETE | High | Reliab | 2021 | Lucic, Marko | Tempra, Troylan | 27-Jan-20 |  |  | 1743957.05 | 1367230.79 | 1683966.5 | 1743957.05 | Paul Murphy | Transpw | 28-Jan-21 | 12-Apr-22 | 12-Mar-20 | 04-Jun-20 | 28-Jan-21 | Lines | COVID19 |  | 59,990.55
633629 | Mavis Rd & Terry Fox Way - Joint Use Permit | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2021 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 3150 |  | 0 | XMoinuddin, Saad |  |  | 27-Jan-22
423118 | Falconer Dr & Matlock - Bell Make Ready | 800 - Mavis | BELL | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 03-Dec-18 |  |  | 3020.14 | 3840.48 | 3020.14 | 3020.14 | Mark Bobanovic |  | 12-Feb-19 | 15-Nov-21 | 21-Dec-18 | 21-Dec-18 | 12-Feb-19 |  |  |  | 0
635973 | 5300 BRADCO BLVD - SERVICE UPGRADE | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
635625 | POLE REPLACEMENT - BATCH #3 (10 POLES) | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636651 | 13.8KV FEEDER EXTENSION- 9TH LINE- DERRY TO ARGENTIA | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636629 | YS6206 - 2024 DA - BRITANNIA RD W & CREDITVIEW RD - P15738 | 800 - Mavis | 151092 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636212 | 952 MIDDLEGATE ROAD | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
632870 | Burhamthorpe Rd W - UG Cable Repair - 83F3 | 800 - Mavis | 151137 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Aug-19
632816 | South Millway & Erin Mills - rebuild | 800 - Mavis | 151179 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Central South |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 30-Jul-19
416137 | 150 PAISLEY BLVD WEST - CANAHAHNS STACKED TOWNHOMES | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Macasaet, Ricardo |  |  |  | 0 | 2739.21 |  | 0 | Weaver, Thomas |  |  | 14-Mar-19
636224 | 1888 MATTAWA - POLE P16741 | 800 - Mavis | 151537 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William |  |  |  | 22140.05 | 28502.03 | 22140.05 | 22140.05 | K-Line Construction |  | 17-May-21 | 26-Jul-23 | 17-May-21 | 17-May-21 | 17-May-21 |  |  |  | 0
633181 | Cable Injection - Area 58 & 59 | 800 - Mavis | 151436 | Active | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Tempra, Troylan | 23-Sep-19 |  |  | 273692.74 | 52888.15 | 273692.74 | 273692.74 | Glenn Guile |  | 03-Jun-20 | 26-Jul-23 | 01-Nov-19 | 17-Oct-19 | 27-Jan-22 | Filler | Control/SCADA |  | 0
635027 | AREA 46 CABLE INJECTION | 800 - Mavis | 151433 | Active | 91 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 15-Dec-21 |  |  | 967997.47 | 49053.94 | 967997.47 | 967997.47 | Glenn Guile | Nvinium | 27-Dec-22 | 26-Jul-23 | 01-Apr-22 | 16-May-22 |  | Contractor |  |  | 0
430481 | 6620 ROTHSCHILD TRAIL EXPANSION | 800 - Mavis | 152302 | Active | HL | H8 |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 19272.53 |  | 0 | XMoinuddin, Saad |  |  | 26-Jul-23
334035 | 2016 OTC (INITIAL) - ELM DRIVE CONDOMINIUMS (EHM COSTS) | 800 - Mavis | 152302 | Active | 93 | ANALYZE |  |  | 2023 | Lacombe, Joel | Garcha, Tirath | 20-Oct-21 |  |  | 1749413.89 | 1700965.43 | 1635113.84 | 1749413.89 | Matthew Beach | Transpw | 22-Mar-22 | 06-Oct-23 | 08-Nov-21 | 17-Nov-21 | 05-May-23 | Customer | Customer |  | 114,300.05
422844 | PHASE 2 - GOREWAY & CITY LIMITS - GRADE SEPARATION | 800 - Mavis | 150673 | Active | 10 | H8 |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 45184.43 |  | 0 | Weaver, Thomas |  |  | 27-Jun-23
636069 | 985 HYDRO ROAD - MISS - NS - 3PH - 150KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Roy, Akash | 16-Jul-21 |  |  | 60280.89 | 46900.09 | 60280.89 | 60280.89 | Peter Costantini | Somervl | 10-Aug-21 | 22-Nov-22 | 02-Aug-21 | 10-Aug-21 | 20-Aug-21 | Customer | Customer |  | 0
634825 | MTO- WINSTON CHURCHILL BLVD AND 401 | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo | 25-Oct-21 |  |  | 65460.42 | 36130.76 | 65460.42 | 65460.42 | Peter Costantini |  | 10-Feb-22 | 22-Nov-22 | 24-Jan-22 | 31-Oct-21 | 17-May-22 | Customer | Customer |  | 0
283725 | 5358 Mavis Rd - Embee Commercial Development Bldg D & E - | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 22-Sep-22
634126 | POLE REPLACEMENT - BATCH #1 | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Matai, Ihssan (Sam) | 18-Jun-20 | 12 |  | 213582 | 353269.21 | 213582 | 213582 | Paul Murphy |  | 27-Nov-20 | 09-Aug-22 | 02-Nov-20 | 03-Feb-21 | 09-Apr-21 | COVID19 | Locates |  | 0
416073 | 1PH TX REPLACEMENTS - BATCH #1 (9 TX'S) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Cudzilo, Tomasz | 21-Oct-19 |  |  | 0 | 106299.59 |  | 0 | Paul Tremblay |  | 21-Oct-19 | 09-Aug-22 | 21-Oct-19 | 21-Oct-19 | 21-Oct-19 | xBy-passed | xBy-passed
635338 | BEXHILL REBUILD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Matai, Ihssan (Sam) | 19-Oct-20 | 11 |  | 386249.82 | 352998.82 | 386249.82 | 386249.82 | Paul Murphy |  | 07-Jul-21 | 21-Apr-22 | 08-Feb-21 | 05-Feb-21 | 30-Apr-21 | Contractor | Contractor |  | 0
636692 | LENARTHUR DR - LOW SECONDARIES | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Ferry, Rodnne | 09-Mar-21 |  |  | 50947.18 | 39195.83 | 50947.18 | 50947.18 | Gregory Dunfield |  | 08-Jun-21 | 12-Apr-22 | 02-Jun-21 | 16-Aug-21 | 27-Oct-21 | Filler | Filler |  | 0
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | 800 - Mavis | 150594 | Inactive | 99 | COMPLETE | High | MLinx | 2021 | Tobin, Michael | Khuu, Philander | 22-Jan-20 |  |  | 1657293.53 | 2049013.54 | 1497296.02 | 1657293.53 | Rob Elliot | Transpw | 28-Aug-20 | 27-Apr-22 | 25-May-20 | 05-Mar-20 | 04-Feb-21 |  | COVID19 |  | 159,997.51
634072 | GTAA DIXIE ROAD FEEDER EXTENSION (135M2 - CARDIFF) | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED | Low | Infrast | 2021 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 16613.23 |  | 0 | XMoinuddin, Saad |  |  | 28-Feb-22
430406 | Sir Richard Rd - Cable replacement | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2019 | Lucic, Marko | Cudzilo, Tomasz | 17-Oct-19 |  |  | 66551.27 | 35399.5 | 66551.27 | 66551.27 | Glenn Guile | Somervl | 29-Nov-19 | 14-Jun-21 | 18-Nov-19 | 28-Oct-19 | 18-Nov-19 |  |  |  | 0
427143 | SG 1468-3170 FIFTH LINE | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Cudzilo, Tomasz | 16-Apr-19 |  |  | 57676.61 | 40727.4 | 57676.61 | 57676.61 | Glenn Guile |  | 17-Jun-19 | 19-Nov-20 | 27-May-19 | 23-May-19 | 30-May-19 |  |  |  | 0
635626 | WOLFEDALE RD - 5 POLES REPLACEMENT | 800 - Mavis | 151063 | Active | 40 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 146615.57 |  | 0 | XMoinuddin, Saad
636729 | 4220 LIVING ARTS DR. - OXFORD PROPERTIES | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636630 | 2023 ESTIMATES | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636516 | POLE REPLACEMENT -TEDLLO/ORWELL ST REBUILD | 800 - Mavis | 151063 | Active | 10 | H8 |  |  | 2023 | Lacombe, Joel | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
635493 | 2020 TRANSFORMER REPLACEMENT BATCH 6 - 15 UNITS | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Handy, James |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
635103 | 5700 KEATON CRES - PROPOSED 100A CELL TOWER SERVICE | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
632869 | Burnhamthorpe Rd W - UG Cable Repair - 68F7 | 800 - Mavis | 151137 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Aug-19
408532 | MAVIS ROAD - MISSISSAUGA AND BRAMPTON LIMIT - 27.6KV CIRCUIT EXTENSION | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Stolarski, Stephen | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Paul Murphy |  |  | 04-Jun-18
634866 | 2023 (SG1471) REMOVAL - FIELDGATE AND PONYTRAIL | 800 - Mavis | 151855 | Active | 82 | RELEASED |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 28-Apr-23 |  |  | 2156720.38 | 36821.19 | 2156720.38 | 2156720.38 | Antonio Mina | Transpw | 22-Nov-23 | 21-Dec-23 | 28-Aug-23 | [5 empty] | 0
636631 | UTLEY RD - NEW 1-PH PAD TX | 800 - Mavis | 150388 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 15-Jun-23 |  |  | 123748.14 | 24785.55 | 123748.14 | 123748.14 | Antonio Mina | Somervl | 24-Aug-23 | 24-Aug-23 | 16-Aug-23 | 20-Jul-23 |  |  |  |  | 0
635028 | AREA 58 & 59 CABLE INJECTION | 800 - Mavis | 151152 | Active | HL | H2 |  |  | 2023 | Beaudrie, Scott | Tempra, Troylan |  |  |  | 0 | 8011.37 |  | 0 | XMoinuddin, Saad |  |  | 26-Jul-23
633168 | DEZEN TOMKEN COMMERCIAL BLDG | 800 - Mavis | 150384 | Active | 92 | ANALYZE |  |  | 2023 | Mustachi, Randy | Huo, Lisa | 23-May-23 |  |  | 114515.25 | 106499.41 | 114515.25 | 114515.25 | Peter Costantini | Somervl | 21-Jul-23 | 26-Jul-23 | 05-Jul-23 | 25-May-23 | 29-Jun-23 |  |  |  | 0
396172 | GO ELEC. - LWL - CONFLICT #LW18 - HAIG BLVD. | 800 - Mavis | 150594 | Active | 95 | COMPLETE | High | MLinx | 2022 | Khuu, Philander | Khuu, Philander | 28-Jun-21 |  |  | 2490887.38 | 3579607.91 | 1571119.1 | 2490887.38 | Mark Bobanovic | Transpw | 08-Nov-21 | 26-Jul-23 | 16-Aug-21 | 05-Aug-21 | 21-Apr-22 |  | MC/PUCC Permit |  | 919,768.28
635647 | 7330 MISSISSAUGA RD - NEW SERVICE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Pellerin, Patrick | 01-Sep-21 |  |  | 81557.18 | 87070.05 | 81557.18 | 81557.18 | Peter Costantini | Somervl | 28-Oct-21 | 22-Nov-22 | 30-Sep-21 | 27-Sep-21 | 26-Oct-21 |  |  |  | 0
636072 | 185 ENFIELD PLACE -GWL REALTY ADVISORS | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 29-Jun-21 |  |  | 131558.94 | 131595.99 | 131558.94 | 131558.94 | Peter Costantini | Somervl | 28-Jul-21 | 22-Nov-22 | 05-Jul-21 | 05-Jul-21 | 28-Jul-21 |  |  |  | 0
283717 | 5378 Mavis Rd - Embee Commercial Development Bldg B | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 22-Sep-22
422836 | ROGERS MAKE READY -MISSISSAUGA RD S/O EGLINTON | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Gonzales, Leonard | 25-Mar-19 |  |  | 57156.14 | 26754.32 | 57156.14 | 57156.14 | Rob Elliot |  | 09-May-19 | 22-Sep-22 | 24-Apr-19 | 13-Feb-19 | 15-Feb-19 |  |  |  | 0
332849 | 5368 Mavis Rd. - Embee Commercial Development Bldg C | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 01-Sep-22
632758 | Torbram & Derry Rd E - GO elec | 800 - Mavis | 150593 | Inactive | 99 | CANCELLED |  |  | 2022 | Tobin, Michael | Central South |  |  |  | 0 | 23143.83 |  | 0 | Dre Danieli |  |  | 29-Jun-22
635339 | MEADOW WOOD RD REBUILD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) | 03-Mar-21 | 34 | 34 | 959122.84 | 1250819.07 | 1135276.07 | 959122.84 | Paul Murphy |  | 16-Dec-21 | 12-Jun-22 | 15-Mar-21 | 03-May-21 | 19-Jan-22 | Locates | Locates |  | -176,153.23
635187 | 5086 CREDITVIEW ROAD UNDERGROUND RELOCATIONS | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2021 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 3735.29 |  | 0 | XMoinuddin, Saad |  |  | 16-May-22
416065 | 21 PARK ST EAST - TANU CONDOS 1200A SERVICE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 16-Dec-20 |  |  | 143231.52 | 219058.98 | 143231.52 | 143231.52 | Peter Costantini | Somervl | 12-Feb-21 | 28-Mar-22 | 25-Jan-21 | 05-Jan-21 | 29-Mar-21 |  | Customer |  | 0
634962 | 6305 KATESON DR - ORLANDO | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 21-Oct-20 |  |  | 151544.56 | 213429.47 | 151544.56 | 151544.56 | Peter Costantini | Somervl | 10-Dec-20 | 03-Sep-21 | 11-Nov-20 | 10-Nov-20 | 02-Feb-21 | Customer | Customer |  | 0
430334 | Eglinton MUT Relocations | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 17-Oct-19 |  |  | 45103.37 | 30268.77 | 30497.54 | 45103.37 | Paul Murphy |  | 26-Nov-19 | 08-Jan-21 | 18-Nov-19 | 30-Oct-19 | 06-Dec-19 |  | Lines |  | 14,605.83
636519 | 2340 CONFEDERATION PARKWAY | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
635494 | 2020 TRANSFORMER REPLACEMENT BATCH 7 - 9 UNITS | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Handy, James |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
632868 | Elora Dr - UG Cable Repair - 668F2 | 800 - Mavis | 151137 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Aug-19
408946 | 2300 STANFIELD RD. - 2332574 ONTARIO LIMITED/STANFI | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 4424.78 |  | 0 | Weaver, Thomas |  |  | 14-Mar-19
634867 | (SG1191) REPLACEMENT - UNITY DR. | 800 - Mavis | 151091 | Active | HL | H3 |  |  | 2023 | Beaudrie, Scott | Cudzilo, Tomasz | 24-Dec-19 |  |  | 88112.16 | 2154.85 | 88112 | 88112 | XMoinuddin, Saad |  | 14-Apr-20 | 04-Aug-23 | 01-Apr-20 | [5 empty] | 0
634125 | STUB POLE RELOCATIONS AT DIXIE ROAD AND GOLDEN ORCHARD | 800 - Mavis | 150673 | Active | HL | H8 |  |  | 2023 | Watters, Maxwell | Garcha, Tirath |  |  |  | 0 | 3982.91 |  | 0 | XMoinuddin, Saad |  |  | 26-Jul-23
396017 | M-CITY POLELINE RELOCATION - QUARTZ ROAD | 800 - Mavis | 151581 | Active | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 16-Apr-21 |  |  | 176119.61 | 109639.53 | 135751.65 | 176119.61 | Mark Bobanovic | B&M | 28-Jun-21 | 26-Jul-23 | 24-May-21 | 24-Dec-21 | 10-Jan-22 | Customer | Customer |  | 40,367.96
636743 | 2022 - SIR JOHN HOMESTEAD UG CABLE REPLACEMENT PHASE 1 | 800 - Mavis | 151518 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 26-Aug-22 |  |  | 1165234.8 | 1307442.43 | 1165234.8 | 1165234.8 | Antonio Mina | Transpw | 01-Dec-22 | 23-May-23 | 12-Sep-22 | 19-Sep-22 | 07-Nov-22 |  |  |  | 0
633469 | Third Party Transfer Project - TX replacement TX641 | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Lucic, Marko | Beaudrie, Scott |  |  |  | 131.01 | 0 |  | 0 | Dre Danieli |  |  | 27-Mar-23
636413 | CARTTERA MANAGEMENT INC. 2445 SURVEYOR RD. | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mustachi, Randy | Huo, Lisa | 02-May-22 |  |  | 161397.6 | 127240.85 | 161397.6 | 161397.6 | Peter Costantini | Somervl | 01-Jun-22 | 22-Nov-22 | 09-May-22 | 04-May-22 | 06-Jun-22 |  | Customer |  | 0
635660 | 1305 CAWTHRA RD - TX UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Pellerin, Patrick | 30-Aug-21 |  |  | 130324.65 | 95404.2 | 130324.65 | 130324.65 | Peter Costantini | Somervl | 04-Oct-21 | 22-Nov-22 | 20-Sep-21 | 13-Sep-21 | 20-Sep-21 |  |  |  | 0
379217 | CARAVELLE SERVICE UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 01-Jul-21 |  |  | 146582.95 | 106349.18 | 146582.95 | 146582.95 | Peter Costantini |  | 03-Aug-21 | 22-Sep-22 | 03-Aug-21 | 03-Aug-21 | 17-Nov-21 | xBy-passed | xBy-passed |  | 0
632735 | 1070 Meredith Ave | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Pellerin, Patrick | 01-Nov-19 |  |  | 0 | 0 |  | 0 | Paul Murphy |  | 08-Nov-19 | 23-Sep-22 | 07-Nov-19 | 04-Oct-19 | 04-Oct-19
416006 | ELM DRIVE PUBLIC SCHOOL | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Costantini, Peter | Huo, Lisa | 08-Oct-21 |  |  | 195749.11 | 197073.6 | 195749.11 | 195749.11 | Peter Costantini | Somervl | 14-Jan-22 | 22-Sep-22 | 29-Nov-21 | 14-Jan-22 | 25-Jan-22 | Customer | Customer |  | 0
282693 | 5328 Mavis Rd - Embee Commercial Development Bldg F | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 01-Sep-22
632387 | JOINT USE PERMIT #HM2019-028 - OWENWOOD DRIVE - MISSISSAUGA | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 17-Feb-21 |  |  | 9234.41 | 8520.7 | 9234.41 | 9234.41 | Macdougall, Stephen |  | 13-Apr-21 | 01-May-22 | 13-Apr-21 | 07-Jun-21 | 07-Jun-21 | Locates | Locates |  | 0
635205 | 880 AVONHEAD ROAD - NEW SERVICE NS00012665 | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Pellerin, Patrick | 20-Jan-21 |  |  | 79999.73 | 96726.4 | 79999.73 | 79999.73 | Peter Costantini |  | 05-Mar-21 | 15-Aug-21 | 15-Feb-21 | 26-Jan-21 | 18-Mar-21 |  | Customer |  | 0
634965 | 50 CAPSTON DRIVE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 21-Oct-20 |  |  | 151045.11 | 139210.38 | 151045.11 | 151045.11 | Peter Costantini | Somervl | 07-Dec-20 | 09-Sep-21 | 04-Nov-20 | 09-Nov-20 | 21-Apr-21 | Customer | Customer |  | 0
427080 | O/H RELOCATION - 1570 BOTHWELL AVE | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 15-Apr-19 |  |  | 3789.37 | 1430.57 | 3789.37 | 3789.37 | Rob Elliot |  | 23-Apr-19 | 11-Jan-21 | 15-Apr-19 | 15-Apr-19 | 23-Apr-19 |  |  |  | 0
636010 | 7140 TRANMERE DR - TX15235 REPLACEMENT - O/H 500KVA 347/600V | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Lucic, Marko | Ferry, Rodnne |  |  |  | 72569.57 | 0 | 74929.99 | 74929.99 | XMoinuddin, Saad | [9 empty] | 0
636524 | 2360 DIXIE RD - SERVICE UPGRADE | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
635495 | 2020 TRANSFORMER REPLACEMENT BATCH 8 - 12 UNITS | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Handy, James |  |  |  | 0 | 12.61 |  | 0 | XMoinuddin, Saad
633165 | PCB/AGE Transformer Replacements | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 03-Sep-19
632866 | Elora Dr - UG Cable Repair - 68F4 Part 2 | 800 - Mavis | 151137 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Aug-19
635033 | 1030 CANADIAN PLACE - NEW SERVICE REQUEST - NS00014915 | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
331854 | MEADOWVALE GO STATION-NORTH PARKING LOT | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 05-Mar-18
636744 | AREA 30 CABLE INJECTION | 800 - Mavis | 151428 | Active | 91 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 15-Dec-21 |  |  | 575573.03 | 902828.71 | 575573.03 | 575573.03 | Glenn Guile | Nvinium | 27-Dec-22 | 26-Jul-23 | 01-Apr-22 | 30-May-22 |  | Contractor |  |  | 0
633143 | 2020 - UG REBUILD - ARGENTIA CABLE FAULTS (SECTION 2) | 800 - Mavis | 151176 | Active | HL | H2 |  |  | 2023 | Beaudrie, Scott | Cudzilo, Tomasz | 03-Feb-20 |  |  | 2317860.83 | 15397.31 | 2317860.83 | 2317860.83 | XMoinuddin, Saad | Transpw | 03-Jun-20 | 16-Oct-23 | 16-Mar-20 | [5 empty] | 0
408891 | 270 LAKESHORE RD WEST - SHORES OF PORT CREDIT TEMP SERV | 800 - Mavis |  | Active | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Macasaet, Ricardo | 11-Sep-18 |  |  | 90654.9 | 59050.55 | 90654.9 | 90654.9 | Peter Costantini |  | 23-Nov-18 | 26-Jul-23 | 01-Nov-18 | 03-Oct-18 |  | Customer | Customer |  | 0
377641 | 2019 O/H REBUILD - STANFIELD RD, 4.16KV | 800 - Mavis | 151184 | Active | HL | H2 |  |  | 2023 | Antonakos, Tony | Handy, James |  |  |  | 969956.19 | 17630.35 | 440349.1 | 440349.1 | XMoinuddin, Saad |  |  | 06-Nov-23 | [6 empty] | 0
634983 | WINDJAMMER UG REBUILD | 800 - Mavis | 151141 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 08-Jun-20 |  |  | 4613689.28 | 4704847.78 | 4455400.97 | 4613689.28 | Paul Tremblay | Transpw | 19-Feb-21 | 20-Jul-23 | 14-Jul-20 | 28-Sep-20 | 26-Mar-21 | MC/PUCC Permit | MC/PUCC Permit |  | 158,288.31
395997 | 4100 Ponytrail Dr - Chelsea O | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 22-Sep-22
634872 | POLE RELOCATION - MISSISSAUGA RD. & SEVENOAKS DR. | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Garcha, Tirath | 08-Feb-21 |  |  | 152661.11 | 87018.99 | 152661.11 | 152661.11 | Paul Murphy |  | 15-Apr-21 | 22-Sep-22 | 12-Mar-21 | 02-Feb-21 | 20-Apr-21 |  | Customer |  | 0
282221 | 5388 Mavis Rd - Embee Commercial Development Bldg G | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 01-Sep-22
427063 | BLANEFIELD RD POLE REPLACEMENT | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Tempra, Troylan | 01-Apr-19 |  |  | 124047.78 | 133926.2 | 124047.78 | 124047.78 | Paul Murphy |  | 29-Aug-19 | 09-Aug-22 | 22-Jul-19 | 24-Jun-19 | 22-Oct-19 |  | Contractor |  | 0
634204 | FAIR BIRCH DRIVE & BIRCHVIEW DRIVE - OH TO UG RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 04-Jan-21 |  |  | 511421.85 | 405920.03 | 432576.41 | 511421.85 | Paul Tremblay | Transpw | 09-Apr-21 | 30-May-22 | 22-Feb-21 | 26-Feb-21 | 22-Apr-21 | Locates | Weather |  | 78,845.44
428875 | 428875 MGR Group - 1191 Eglinton Ave East | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 02-Jul-19 |  |  | 71009.03 | 75805.57 | 82960.16 | 82960.16 | Macdougall, Stephen | Somervl | 21-Aug-19 | 12-Nov-20 | 05-Aug-19 | 12-Jul-19 | 27-Sep-19 |  | Customer |  | 0
636644 | ERIN MILLS-NORTH SHERIDAN | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
635843 | CENTRAL SOUTH TRANSFORMER REPLACEMENT - TX 8325 | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige |  |  |  | 0 | 16.06 |  | 0 | XMoinuddin, Saad
634018 | M CITY M3 TOWER 3MVA + 3MVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 22-Oct-19
633458 | 1400 Dixie Rd - PCB Transformer Replacement | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 11-Sep-19
632865 | Rathburn Rd W - U/G Cable Repair - 68F4 Part 1 | 800 - Mavis | 151137 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Aug-19
632731 | Rathburn Rd UG rebuild PH4 | 800 - Mavis | 151144 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 30-Jul-19
633142 | 2020 - UG REBUILD - ARGENTIA CABLE FAULTS (SECTION 1) | 800 - Mavis | 151176 | Active | HL | H2 |  |  | 2023 | Beaudrie, Scott | Cudzilo, Tomasz | 21-Feb-20 |  |  | 1440170.7 | 22408.12 | 1440170.7 | 1440170.7 | XMoinuddin, Saad |  |  | 29-Aug-23 | [6 empty] | 0
635762 | CENTRA SOUTH TX REPLACEMENT - BATCH 18 | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Webb-Murre, Paige | 01-Jun-20 |  |  | 24025.07 | 0 | 24025.07 | 24025.07 | Paul Tremblay |  | 29-Jun-20 | 09-Feb-23 | 22-Jun-20 |  |  | Filler |  |  | 0
292921 | PARK - SECTION 1 - ANN TO STAVEBANK | 800 - Mavis | 151186 | Inactive | HL | CANCELLED |  |  | 2022 | Kafel, Krzysztof | Truong, Jimmy | 04-Dec-17 |  |  | 733157.52 | 0 | 979831.05 | 979831.05 | XMoinuddin, Saad |  |  | 22-Sep-22 |  |  |  | xBy-passed | xBy-passed |  | 0
632378 | JOINT USE PERMIT #HM2019-017 - PETER STREET NORTH - MISSISSAUGA | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 17-Feb-21 |  |  | 7633.38 | 4346.46 | 7633.38 | 7633.38 | Macdougall, Stephen |  | 12-Apr-21 | 10-Aug-22 | 12-Apr-21 | 07-Jun-21 | 07-Jun-21 | Locates | Locates |  | 0
415935 | POLE LINE REBUILD ON SUNNINGDALE | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Handy, James | 03-Apr-19 |  |  | 125663.31 | 229311.73 | 125663.31 | 125663.31 | Paul Murphy |  | 23-Jul-19 | 07-Sep-22 | 24-Jun-19 | 05-Jul-19 | 18-Oct-19 | Locates | Lines |  | 0
422756 | EBONY AVE - HOUSE SERVICES | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Ricci, Leonardo | 29-Aug-19 |  |  | 31718.33 | 27424.03 | 31718.33 | 31718.33 | Paul Tremblay | Somervl | 25-Oct-19 | 19-Apr-21 | 21-Oct-19 | 25-Sep-19 | 19-Nov-19 |  | Customer |  | 0
408292 | 2630 FIFTH LINE WEST - ERINVIEW RETIREMENT RESIDENCE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Huo, Lisa | 20-Sep-19 |  |  | 157461.61 | 157065.03 | 157461.61 | 157461.61 | Macdougall, Stephen | Somervl | 29-Nov-19 | 26-Nov-20 | 04-Nov-19 | 02-Oct-19 | 26-Oct-19 |  |  |  | 0
636745 | AREA 38 CABLE INJECTION | 800 - Mavis | 150495 | Active | 40 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
634873 | 5025, 5035, 5065 ERIN MILLS PKWY - LONG TERM CARE - MISS - NS - 3 PH - NS0013744 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
426950 | BARBERTOWN TOWNHOMES | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 22-Mar-19
632834 | P02687 Replacement - 1082 Meredith Ave | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2019 | Beaudrie, Scott | Pellerin, Patrick | 28-Aug-19 |  |  | 0 | 0 |  | 0 | Paul Murphy |  | 07-Nov-19 | 27-Sep-22 | 04-Nov-19 | 04-Oct-19 | 04-Oct-19
633996 | 2650 MEADOWVALE BLVD - MEADOWVALE LIMITED 3MVA UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 21-Jun-21 |  |  | 106765.95 | 123151.77 | 106765.95 | 106765.95 | Peter Costantini | Somervl | 30-Jul-21 | 22-Sep-22 | 26-Jul-21 | 26-Aug-21 | 17-Sep-21 |  | Customer |  | 0
415880 | POLE REPLACEMENT - BATCH #2 (16 POLES) | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Handy, James | 02-Apr-19 |  |  | 148311.84 | 194818.78 | 148311.84 | 148311.84 | Paul Murphy |  | 30-Oct-19 | 02-Sep-22 | 22-Jul-19 | 30-Aug-19 | 25-Oct-19 | Locates |  |  | 0
328161 | 2015 OTC (INITIAL) - 320 DERRY ROAD DEVELOPMENT - EHM COST | 800 - Mavis | 150652 | Inactive | 99 | CANCELLED |  |  | 2022 | Penner, Mitchell | Ricci, Leonardo |  |  |  | 342555.7 | 14243.49 | 342555.7 | 342555.7 | XMoinuddin, Saad |  |  | 22-Feb-22 | [6 empty] | 0
636087 | 2250 HOMELANDS- STARLIGHT INVESTMENTS | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 29-Apr-21 |  |  | 21775.33 | 17314.98 | 21775.33 | 21775.33 | XMoinuddin, Saad |  | 30-Apr-21 | 12-Nov-21 | 30-Apr-21 | 30-Apr-21 | 30-Apr-21 | xBy-passed | xBy-passed |  | 0
378249 | 7675 Torbram Rd. - Freedom Mobile TEMP SERV | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Lucic, Marko | Cudzilo, Tomasz | 04-Dec-17 |  |  | 23455.61 | 8005.03 | 23455.61 | 23455.61 | Peter Costantini |  | 19-Mar-18 | 05-Oct-20 | 19-Mar-18 | 06-Dec-18 |  | Customer | Customer |  | 0
634874 | ERIN MILLS NE BLOCK 2 - RESTAURANTS & RENTAL | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
633451 | 2075 Sherobee Rd - PCB Transformer Replacement | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 11-Sep-19
633083 | Argentia Phase 1 - UG Cable Replacement | 800 - Mavis | 151176 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 16-Aug-19
632713 | UG Feeder Cable Replacement - Mason Hts | 800 - Mavis | 151178 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Central South |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 30-Jul-19
633435 | JOINT USE PERMIT #HM2019-074 - HENSALL STREET - MISSISSAUGA | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 16-Oct-20 |  |  | 35688.35 | 45222.61 | 35688.35 | 35688.35 | Macdougall, Stephen |  | 13-Nov-20 | 06-Oct-22 | 02-Nov-20 | 06-Jan-21 | 29-Jan-21 | Filler | Lines |  | 0
426917 | BELL MAKE READY -LAKESHORE RD W & LORNE PARK | 800 - Mavis | BELL | Inactive | 99 | CANCELLED |  |  | 2022 | O'Gay, Brian | Gonzales, Leonard |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Aug-22
415767 | POLE REPLACEMENT - BATCH #11 (9 POLES) | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 12-Apr-19 |  |  | 132531.37 | 141466.2 | 132531.37 | 132531.37 | Paul Murphy |  | 15-Nov-19 | 09-Aug-22 | 22-Jul-19 | 13-Sep-19 | 11-Nov-19 | Locates |  |  | 0
635925 | (SG1778) REPLACEMENT - WHITE HEART LANE | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 22-Jun-20 |  |  | 91617.05 | 101393.16 | 91617.05 | 91617.05 | Glenn Guile |  | 06-Aug-20 | 04-May-22 | 22-Jul-20 | 11-Jan-21 | 14-Jan-21 | Filler | Filler |  | 0
635764 | CENTRAL SOUTH TX REPLACEMENT - BATCH 20 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 01-Jun-20 |  |  | 82914.84 | 73904.73 | 82914.84 | 82914.84 | Glenn Guile | K-Line | 03-Jul-20 | 22-Nov-21 | 22-Jun-20 | 12-Aug-20 | 15-Jan-21 | Filler | Filler |  | 0
407695 | 35 & 65 WATERGARDEN DR - PERLA CONDOS BY PINNACLE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 13-Aug-19 |  |  | 127852.28 | 86937.97 | 127852.28 | 127852.28 | Paul Tremblay |  | 16-Oct-19 | 01-Dec-20 | 16-Sep-19 | 17-Oct-19 | 18-Dec-19 |  |  |  | 0
395495 | 650 ATWATER - DELLWOOD PARK TOWNHOMES | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 21-Jan-19 |  |  | 85802.73 | 79750.74 | 85802.73 | 85802.73 | Macdougall, Stephen |  | 08-Mar-19 | 29-Oct-20 | 19-Feb-19 | 18-Jan-19 | 27-May-19 |  | Customer |  | 0
634875 | ERIN MILLS NE BLOCK 3 - CONDOMINIUM | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
632830 | LAFARGE CAWTHRA DEPOT | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Aug-19
428664 | CABLE ABANDON - C3780 TO TX8813 - S.E. WINSTON CHURCHILL & THE COLLEGEWAY | 800 - Mavis | 151043 | Active | 70 | ACTIVE |  |  | 2023 | Sidhu, Paul | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 06-Jun-19
422271 | ROMETOWN DR OH REBUILD | 800 - Mavis | 151148 | Active | 10 | ACTIVE |  |  | 2023 | Carter, Gordon | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 28-Dec-18
633978 | 4015 THE EXCHANGE - MISS - BLDG 1 - NS00161127 - 3PH - C.O. TX 3MVA | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Garcha, Tirath | 26-Jul-23 |  |  | 85682.89 | 30705.73 | 85682.89 | 85682.89 | Peter Costantini | N/A | 13-Nov-23 | 13-Nov-23 | 06-Nov-23 | [5 empty] | 0
218587 | CHURCHILL MEADOWS TS - TS TO WINSTON CHURCHILL (FEEDER EGRESS) | 800 - Mavis | 150357 | Inactive | 99 | CANCELLED |  |  | 2022 | Hotham, Matthew | Zaghloul, Sam |  |  |  | 2113614.54 | 357047.54 | 2113614.54 | 2113614.54 | Rob Elliot |  |  | 13-Apr-23 |  | 04-Dec-17 |  |  | MC/PUCC Permit |  | 0
406684 | 2019 - UG REBUILD - COPENHAGEN - SECTION 2 | 800 - Mavis | 151171 | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Cudzilo, Tomasz | 10-Apr-19 |  |  | 2667208.78 | 2701479.68 | 2550825.67 | 2667208.78 | Paul Tremblay | Transpw | 10-Sep-19 | 22-Sep-22 | 30-Apr-19 | 30-Apr-19 | 04-Nov-19 |  | MC/PUCC Permit |  | 116,383.11
633022 | Derry Rd E and Airport Rd - Go Electr Scope # 2 | 800 - Mavis | 150593 | Inactive | 99 | CANCELLED |  |  | 2022 | Tobin, Michael | Chopra, Rabinder |  |  |  | 0 | 56090.33 |  | 0 | Dre Danieli |  |  | 29-Jun-22
426896 | BELL MAKE READY -2109 PREMIUM WAY | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 23-Jul-19 |  |  | 18633.42 | 1971.57 | 18634.42 | 18634.42 | Mark Bobanovic |  | 01-Nov-19 | 21-Dec-20 | 01-Nov-19 | 04-Oct-19 | 04-Oct-19 |  |  |  | 0
633380 | Mavis Rd - Guy Pole Relocations | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Watters, Maxwell | 30-Sep-19 |  |  | 23260.85 | 15259.57 | 23260.85 | 23260.85 | Paul Murphy |  | 11-Oct-19 | 22-Dec-20 | 07-Oct-19 | 15-Oct-19 | 17-Oct-19 | Lines | Lines |  | 0
631920 | MTO HWY401 PATROL YARD 800A UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 23-Sep-19 |  |  | 50338.09 | 40729.27 | 50338.09 | 50338.09 | Macdougall, Stephen |  | 06-Nov-19 | 06-Nov-20 | 28-Oct-19 | 01-Oct-19 | 01-Oct-19 |  |  |  | 0
636105 | REPLACING 3 SPANS OF #6 PRIMARY WITH 1/0 FOR WO415169 ON MELTON COURT | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
395487 | 6688 Kitimat Road - Switchgear | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Truong, Jimmy |  |  |  | 0 | 0 | 150000 | 150000 | Macdougall, Stephen |  |  | 08-Feb-18 | [6 empty] | 0
635766 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #6 | 800 - Mavis | 151043 | Active | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Karan, Andjelo | 01-Jun-20 |  |  | 74043.18 | 99498.19 | 74043.18 | 74043.18 | Glenn Guile |  | 14-Jul-20 | 26-Jul-23 | 22-Jun-20 | 27-Jan-21 | 10-Feb-21 | Filler | Filler |  | 0
632904 | CABLE INJECTION - AREA 46 | 800 - Mavis | 151433 | Active | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Tempra, Troylan | 06-Sep-19 |  |  | 168086.96 | 19908.86 | 168086.96 | 168086.96 | Glenn Guile |  | 17-Dec-19 | 26-Jul-23 | 01-Oct-19 | 30-Sep-19 | 27-Jan-22 | Filler | Control/SCADA |  | 0
415636 | 1PH TX REPLACEMENTS - BATCH #8 (8 TX'S) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lucic, Marko | Tempra, Troylan | 21-Oct-19 |  |  | 70137.41 | 44538.23 | 70137.41 | 70137.41 | Paul Tremblay |  | 21-Oct-19 | 03-Oct-21 | 21-Oct-19 | 21-Oct-19 | 21-Oct-19 | xBy-passed | xBy-passed |  | 0
395479 | Mavis Road Widening - Courtney | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Kafel, Krzysztof | Truong, Jimmy | 17-Dec-18 |  |  | 320044.66 | 373492.04 | 320044.66 | 320044.66 | Paul Murphy |  | 24-Apr-19 | 10-Dec-20 | 11-Feb-19 | 22-Feb-19 | 21-May-19 | Locates | Locates |  | 0
421964 | 2555 ROYAL WINDSOR DRIVE, K+S | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Zaghloul, Sam | 10-Oct-19 |  |  | 104463.73 | 78027.24 |  | 0 | Macdougall, Stephen | Somervl | 19-Nov-19 | 04-Dec-20 | 14-Oct-19 | 22-Oct-19 | 23-Oct-19 |  | Customer
325446 | Toyotoshi Dixie Auto Mall - NE cor of Dixie & Hwy 401 | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Sta. Rita, Leovigildo | Macasaet, Ricardo | 04-Dec-17 |  |  | 145872.6 | 66216.65 | 145872.6 | 145872.6 | Macdougall, Stephen |  | 15-Feb-18 | 29-Oct-20 | 04-Dec-17 | 04-Dec-17 | 08-May-19 |  | Customer |  | 0
633272 | Rathburn Rd - TX replacement | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Huo, Lisa | 04-Sep-19 |  |  | 27640.39 | 24066.92 | 27640.39 | 27640.39 | Macdougall, Stephen |  | 11-Oct-19 | 27-Aug-20 | 07-Oct-19 | 14-Oct-19 | 14-Sep-19 |  | Customer |  | 0
636136 | RESIDENTIAL LAYOUTS 2020 | 800 - Mavis | 150388 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Ross, Stuart |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
631714 | POLE LINE RELOCATION - DERRY RD W (P19183 & P19186) | 800 - Mavis | 150675 | Active | 70 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 09-Jul-19
632719 | JOINT USE PERMIT #HM2019-073 - MISSISSAUGA ROAD - MISSISSAUGA | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 16-Nov-20 |  |  | 45229.51 | 38254.58 | 45229.51 | 45229.51 | Macdougall, Stephen |  | 04-Jan-21 | 03-Oct-22 | 21-Dec-20 | 11-Jan-21 | 02-Feb-21 | Lines | Lines |  | 0
428251 | FEEDER REPLACEMENT 45F1 TO 45F | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2021 | Sidhu, Paul | Cudzilo, Tomasz | 23-Feb-21 |  |  | 420230.59 | 432585.98 | 396202.77 | 420230.59 | Antonio Mina | Transpw | 02-Jun-21 | 28-Mar-22 | 08-Apr-21 | 06-Apr-21 | 23-Aug-21 |  | Contractor |  | 24,027.82
415628 | 1PH TX REPLACEMENTS - BATCH #7 (10 TX'S) | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2019 | Lucic, Marko | Tempra, Troylan | 21-Oct-19 |  |  | 0 | 44350.78 |  | 0 | Paul Tremblay |  | 21-Oct-19 | 02-Jun-21 | 21-Oct-19 | 21-Oct-19 | 21-Oct-19 | xBy-passed | xBy-passed
421420 | 6415 NORTHAM DRIVE - Mitsubishi Canada Aerospace | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 18-Mar-19 |  |  | 1118984.62 | 95277.72 | 117422.76 | 117422.76 | Macdougall, Stephen |  | 31-May-19 | 25-Nov-20 | 01-May-19 | 02-May-19 | 19-Aug-19 |  | Customer |  | 0
426802 | NPL CANADA 400A 1PH SERVICE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 01-Oct-19 |  |  | 0 | 5910 |  | 0 | Macdougall, Stephen |  | 21-Oct-19 | 20-Jul-20 | 21-Oct-19 | 21-Oct-19 | 21-Oct-19
633251 | 7 Elizabeth St N PCB Transformer Replacement | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 11-Sep-19
324638 | 5475 Dixie Rd -OH to UG Conversion | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sidhu, Paul | Ricci, Leonardo | 04-Dec-17 |  |  | 17642.23 | 7132.82 | 17642.23 | 17642.23 | Bourgeois, Craig |  | 26-Jun-18 | 30-Jul-19 | 08-Jan-18 |  |  |  | Customer |  | 0
395399 | 8 Nahani Way - Mississauga Square TEMP SERV | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2022 | Sta. Rita, Leovigildo | Macasaet, Ricardo | 11-Sep-18 |  |  | 65567.44 | 49110.29 | 65567.44 | 65567.44 | Peter Costantini |  | 06-Dec-18 | 22-Sep-22 | 26-Nov-18 | 24-Sep-18 |  |  | Customer |  | 0
633898 | INDWELL LAKESHORE APARTMENTS | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 02-Aug-21 |  |  | 169766.42 | 142754.9 | 169766.42 | 169766.42 | Peter Costantini |  | 03-Aug-21 | 22-Sep-22 | 03-Aug-21 | 03-Aug-21 | 03-Aug-21 | xBy-passed | xBy-passed |  | 0
428082 | ROGERS MAKE READY - 181 KING ST. E. (MP19-0026 NN | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Gonzales, Leonard | 13-May-19 |  |  | 10815.83 | 6447.4 | 10815.83 | 10815.83 | Bourgeois, Craig |  | 23-May-19 | 01-Sep-22 | 22-May-19 | 29-Jul-19 | 29-Jul-19 | Locates | Locates |  | 0
415610 | POLE REPLACEMENT - BATCH #6 (17 POLES) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Tempra, Troylan | 11-Dec-18 |  |  | 191401.36 | 215072.74 | 238365.03 | 191401.36 | Paul Murphy |  | 09-Apr-19 | 09-Aug-22 | 14-Jan-19 | 18-Jan-19 | 25-Feb-19 | Locates |  |  | -46,963.67
421147 | 6500 TOMKEN ROAD - REYNOLDS PRODUCTS 1200AMP SERV | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 29-Mar-19 |  |  | 97344.68 | 69521 | 97344.68 | 97344.68 | Macdougall, Stephen |  | 07-Jun-19 | 20-Jul-20 | 13-May-19 | 15-Apr-19 | 27-May-19 |  |  |  | 0
632871 | Elora Dr - UG Cable Repairs - 83F5 | 800 - Mavis | 151137 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Aug-19
632716 | JOINT USE PERMIT #HM2019-049 - EGLINTON AVENUE WEST - MISSISSAUGA | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 26-Oct-20 |  |  | 31892.41 | 34579.52 | 31892.41 | 31892.41 | Macdougall, Stephen |  | 08-Dec-20 | 23-Jun-22 | 01-Dec-20 | 25-Jan-21 | 12-Feb-21 | Lines | Lines |  | 0
395233 | 190 STATESMAN DRIVE | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Zaghloul, Sam | 07-Mar-19 |  |  | 18752.56 | 165168.85 | 149136.33 | 149136.33 | Macdougall, Stephen |  | 13-Jun-19 | 10-Nov-20 | 15-Apr-19 | 01-Apr-19 | 21-Oct-19 |  | Customer |  | 0
428074 | SQUARE ONE DRIVE EXTENSION - FROM CONFEDERATION TO RATHBURN | 800 - Mavis | 150675 | Active | 70 | H8 |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas | Transpw |  | 16-Apr-19
395209 | Ellisdon sales office temporary 200A 1PH service | 800 - Mavis | 150388 | Active | 99 | COMPLETE |  |  | 2022 | Sta. Rita, Leovigildo | Macasaet, Ricardo | 18-Jul-19 |  |  | 0 | 6266.89 |  | 0 | Peter Costantini |  | 18-Jul-19 | 26-Jul-23 | 18-Jul-19 | 04-Feb-19 | 30-Jan-23 | xBy-passed | Customer
405471 | 630-670 Courtney Valley | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Central North ICI | 03-Oct-18 |  |  | 72771.33 | 49227.25 | 72771.33 | 72771.33 | Bourgeois, Craig |  | 19-Nov-18 | 22-Sep-22 | 05-Nov-18 | 24-Oct-18 | 15-Jan-19 |  | Customer |  | 0
428058 | 4100 PONYTRAIL DR - CHELSEA ON | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 1485.79 |  | 0 | Weaver, Thomas |  |  | 22-Sep-22
415417 | POLE REPLACEMENT - BATCH #4 (17 POLES) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Tempra, Troylan | 11-Dec-18 |  |  | 225789.19 | 252683.68 | 225789.19 | 225789.19 | Paul Murphy |  | 30-Oct-19 | 09-Aug-22 | 08-Apr-19 | 08-May-19 | 25-Oct-19 | Locates |  |  | 0
421008 | EGLINTON AND CREDIT VIEW - VAN HORNE OUTDOOR BILLBOARD | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Jacinto, Gerardo | 28-Mar-19 |  |  | 45628.94 | 46160.7 | 45628.94 | 45628.94 | Peter Costantini |  | 16-May-19 | 05-Nov-20 | 13-May-19 | 23-Jul-19 | 23-Jul-19 |  | Customer |  | 0
426731 | VAN HORNE OUTDOOR BILLBOARD-CP | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Jacinto, Gerardo | 07-Nov-19 |  |  | 30163.01 | 24380.9 | 30163.01 | 30163.01 | Peter Costantini | Somervl | 29-Nov-19 | 29-Oct-20 | 27-Nov-19 | 11-Dec-19 | 14-Dec-19 |  | Customer |  | 0
420961 | QEW - PREMIUM WAY FROM DICKSON | 800 - Mavis | 150673 | Active | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Watters, Maxwell | 12-Aug-19 |  |  | 157929.83 | 110860.51 | 157929.83 | 157929.83 | Mark Bobanovic |  | 31-Dec-19 | 26-Jul-23 | 12-Sep-19 | 03-Sep-20 | 07-Oct-19 | xBy-passed | xBy-passed |  | 0
426693 | FALCONER DRIVE USED POLE INSTA | 800 - Mavis |  | Active | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Watters, Maxwell | 01-Aug-19 |  |  | 0 | 8245.44 |  | 0 | Mark Bobanovic |  | 01-Aug-19 | 26-Jul-23 | 01-Aug-19 | 01-Aug-19 | 01-Aug-19 | xBy-passed | xBy-passed
427987 | TX1964 REPLACEMENT - OVERLOADED/LEAKING | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Handy, James | 22-Apr-19 |  |  | 73116.39 | 46473.84 | 73116.39 | 73116.39 | Paul Murphy |  | 27-Aug-19 | 10-Aug-22 | 19-Aug-19 | 08-May-19 | 17-May-19 |  |  |  | 0
635772 | CENTRAL SOUTH TX REPLACEMENT - BATCH 23 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 22-Jun-20 |  |  | 57869.56 | 44998.62 | 57869.56 | 57869.56 | Glenn Guile | K-Line | 10-Aug-20 | 12-Nov-21 | 27-Jul-20 | 23-Jun-20 | 15-Jan-21 | Filler | Filler |  | 0
394142 | PCB U/G TX8394/5 REPLACEMENT - 3040 & 3050 CONSTITUTION BLVD - PCC # 82 | 800 - Mavis | 151043 | Active | 40 | ACTIVE |  |  | 2023 | Antonakos, Tony | Handy, James |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 14-Mar-19
373771 | McLaughlin Rd Development | 800 - Mavis | 150652 | Inactive | 99 | CANCELLED |  |  | 2022 | Penner, Mitchell | Ricci, Leonardo |  |  |  | 0 | 4909.06 |  | 0 | Weaver, Thomas |  |  | 23-Jul-18
420929 | 4066 - 4072 DIXIE RD - HIGHLIGHT CONDOS | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo | 05-May-22 |  |  | 303068.57 | 305558.17 | 303068.57 | 303068.57 | Peter Costantini | Somervl | 10-Aug-22 | 18-Aug-23 | 18-Jul-22 | 31-Oct-22 |  | Customer |  |  | 0
427872 | LT41053 - SWITCH REPLACEMENT | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 29-Apr-19 |  | 1 | 61107.75 | 71518.32 | 61107.75 | 61107.75 | Paul Murphy |  | 16-Sep-19 | 09-Aug-22 | 03-Sep-19 | 31-May-19 | 07-Jun-19 |  |  |  | 0
415329 | POLE REPLACEMENT - BATCH #5 (6 POLES) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Tempra, Troylan | 07-Mar-19 |  |  | 82334.45 | 104667.75 | 82334.45 | 82334.45 | Paul Murphy |  | 15-Oct-19 | 09-Aug-22 | 15-May-19 | 05-Jul-19 | 04-Oct-19 | xDelayed Releas |  |  | 0
370538 | 2024? UG REBUILD - COPENHAGEN - SECTION 1 | 800 - Mavis | 151451 | Active | HL | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 702.77 |  | 0 | Paul Tremblay |  |  | 26-Jul-23
426634 | 2022 PR - 9WP - GREENWAY POLE LINE REBUILD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Tempra, Troylan | 26-Aug-22 | 9 | 9 | 192786.17 | 164657.16 | 192786.17 | 192786.17 | Mark Bobanovic | K-Line | 07-Dec-22 | 15-Jun-23 | 21-Nov-22 | 02-Dec-22 | 22-Dec-22 | Contractor |  |  | 0
427813 | 401 EXPANSION PROJECT FOR WCC AT CREDITVIEW ROAD & OLD CREDITVIEW ROAD | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2021 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas | K-Line |  | 26-Jul-22
420911 | 1840 Courtney Park Dr. | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Bharosi, Mohindra | 26-Feb-19 |  |  | 67114.42 | 54837.18 | 67114.42 | 67114.42 | Macdougall, Stephen |  | 29-Apr-19 | 12-Nov-20 | 15-Apr-19 | 03-Jul-19 | 09-Jul-19 |  | Customer |  | 0
427792 | 4675 METCALFE AVE - ERIN SQUARE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 02-Nov-20 |  |  | 372359.18 | 392750.7 | 372359.18 | 372359.18 | Peter Costantini | Somervl | 01-Jan-21 | 22-Sep-22 | 09-Nov-20 | 12-Nov-20 | 30-Aug-21 | Customer | Customer |  | 0
426626 | LINCOLN M. ALEXANDER SECONDARY SCHOOL | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Costantini, Peter | Huo, Lisa | 15-Jun-21 |  |  | 161903.63 | 123634.57 | 161903.63 | 161903.63 | Peter Costantini | Somervl | 08-Sep-21 | 22-Sep-22 | 22-Jul-21 | 28-Jun-21 | 27-Sep-21 |  | Customer |  | 0
415193 | TX10389 AT 4179 SHALEBANK CRT | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 13-Nov-18 |  |  | 116189.38 | 96611.54 | 116189.38 | 116189.38 | Paul Tremblay |  | 21-Oct-19 | 09-Aug-22 | 21-Oct-19 | 21-Oct-19 | 21-Oct-19 | xBy-passed | xBy-passed |  | 0
420902 | 1331 MATHESON BLVD E - SERVICE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Bharosi, Mohindra | 10-Dec-18 |  |  | 17040.71 | 16308.58 | 17040.71 | 17040.71 | Macdougall, Stephen |  | 21-Jan-19 | 02-Nov-20 | 21-Jan-19 | 30-Oct-19 | 31-Oct-19 |  | Customer |  | 0
415185 | 1PH TX REPLACEMENTS - BATCH #5 (10 TX'S) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 13-Nov-18 |  |  | 93929 | 57312.07 | 93929 | 93929 | Paul Tremblay |  | 25-Jul-19 | 09-Aug-22 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 | xBy-passed | xBy-passed |  | 0
420890 | QEW - PREMIUM WAY PHASE 2 | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2021 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 28-Jun-21
426618 | REGION WATERMAIN - BELL PEDEST | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Truong, Jimmy | 24-Jun-19 |  |  | 49187.95 | 54440.69 | 46330.84 | 49187.95 | Macdougall, Stephen | Somervl | 03-Sep-19 | 17-Dec-20 | 12-Aug-19 | 24-Jul-19 | 04-Nov-19 |  | Contractor |  | 2,857.11
370239 | 2017 OTC (INITIAL) - MEADOWVALE LANE (EHM COSTS) | 800 - Mavis | 150652 | Inactive | 99 | CANCELLED |  |  | 2022 | Penner, Mitchell | Ricci, Leonardo |  |  |  | 178514.45 | 8849.56 | 178514.45 | 178514.45 | Weaver, Thomas |  |  | 31-Jan-19 | [6 empty] | 0
393511 | Northmount Ave Rebuild | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Bobanovic, Mark | Matai, Ihssan (Sam) | 25-Jun-19 |  |  | 0 | 43028.96 |  | 0 | Mark Bobanovic |  | 25-Jun-19 | 09-Aug-22 | 25-Jun-19 | 25-Jun-19 | 25-Jun-19 | xBy-passed | xBy-passed
427741 | POLE REPLACEMETS - PETRIE WAY REBUILD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Antonakos, Tony | Matai, Ihssan (Sam) | 01-Mar-21 | 9 | 9 | 333711.56 | 348905.07 | 333711.56 | 333711.56 | Paul Murphy |  | 21-Jul-21 | 09-Aug-22 | 01-Apr-21 | 05-Jul-21 | 11-Feb-22 | Lines | Lines |  | 0
415177 | POLE LINE REBUILD - BURSLEM RD (7 POLES) | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 11-Dec-18 |  |  | 186461.8 | 162424.83 | 186461.8 | 186461.8 | Rob Elliot |  | 10-Oct-19 | 09-Aug-22 | 22-Aug-19 | 05-Sep-19 | 03-Dec-19 | xDelayed Releas | Filler |  | 0
420831 | 5150 DIXIE RD - AFFINIA CANADA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 20-Mar-19 |  |  | 147257.36 | 94592.77 | 147257.36 | 147257.36 | Macdougall, Stephen |  | 07-Jun-19 | 02-Nov-20 | 29-Apr-19 | 29-Apr-19 | 03-May-19 |  | Customer |  | 0
426263 | HWY 410 AT DERRY ROAD - HWY CR | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE | VerHigh | Infrast | 2021 | Lacombe, Joel | Gonzales, Leonard | 03-Mar-20 |  |  | 901631.93 | 845129.42 | 901631.93 | 901631.93 | Paul Murphy | A&W | 25-Mar-21 | 22-Sep-22 | 09-Jul-20 | 06-Jul-20 | 18-Jan-21 | COVID19 | COVID19 |  | 0
393211 | RATHBURN -ROAD WEST HULRT PLANT RELOCATIONS | 800 - Mavis | 150479 | Inactive | 99 | COMPLETE |  |  | 2019 | Tobin, Michael | Garcha, Tirath | 05-Jul-18 |  |  | 3958216.9 | 5141206.19 | 3958216.9 | 3958216.9 | Mark Bobanovic |  | 15-Nov-18 | 19-Apr-21 | 05-Jul-18 | 05-Jul-18 | 09-Apr-19 |  | Customer |  | 0
427733 | 6685 CENTURY AVE - MOVATI ATHL | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Bharosi, Mohindra | 19-Jul-19 |  |  | 66449.29 | 68500.19 | 66449.29 | 66449.29 | Macdougall, Stephen |  | 24-Sep-19 | 19-Nov-20 | 03-Sep-19 | 27-Aug-19 | 23-Nov-19 |  |  |  | 0
420638 | 2679 SLOUGH ST. MISSISSAUGA ON | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Central North ICI |  |  |  | 0 | 1824.67 |  | 0 | Macdougall, Stephen |  |  | 05-Dec-18
367232 | 270 DERRY ROAD WEST | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Sta. Rita, Leovigildo | Huo, Lisa | 22-Feb-21 |  |  | 150336.18 | 144293.91 | 150336.18 | 150336.18 | Peter Costantini | Somervl | 27-Apr-21 | 22-Sep-22 | 29-Mar-21 | 01-Mar-21 | 01-Apr-21 |  |  |  | 0
415126 | POLE REPLACEMENT - BATCH #3 (12 POLES) | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Tempra, Troylan | 11-Dec-18 |  |  | 178125.48 | 257608.78 | 178125.48 | 178125.48 | Rob Elliot |  | 30-Sep-19 | 09-Aug-22 | 22-Apr-19 | 25-Apr-19 | 12-Sep-19 | Lines |  |  | 0
420603 | 848 BURNHAMTHORPE RD WEST - TX UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Mandic, Goran | Bharosi, Mohindra | 11-Dec-18 |  |  | 26624.78 | 5467.57 | 26624.78 | 26624.78 | Peter Costantini |  | 09-Jan-19 | 12-Nov-21 | 07-Jan-19 |  |  | Customer | Customer |  | 0
403897 | LAIRD/ WCB MAIN FEEDER RELOCATION | 800 - Mavis | 151451 | Active | 99 | COMPLETE |  |  | 2022 | Antonakos, Tony | Cudzilo, Tomasz | 16-Sep-20 |  |  | 327575.45 | 605833.67 | 312539.59 | 327575.45 | Glenn Guile | Somervl | 20-Nov-20 | 26-Jul-23 | 19-Oct-20 | 08-Mar-21 | 14-Feb-22 | MC/PUCC Permit | MC/PUCC Permit |  | 15,035.86
427629 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE 3 OGDEN AVENUE | 800 - Mavis | 151589 | Active | 84 | ACTIVE |  |  | 2023 | Watters, Maxwell | Watters, Maxwell | 29-Jul-22 |  |  | 1233915.95 | 935827.58 | 1230215.95 | 1233915.95 | Matthew Beach | Transpw | 17-Jul-23 | 03-Nov-23 | 19-Sep-22 | 25-Oct-22 |  |  |  |  | 3,700.00
414916 | SILVER SPEAR II APARTMENT | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 03-May-21 |  |  | 136441.54 | 98518.99 | 136441.54 | 136441.54 | Peter Costantini | Somervl | 04-Jun-21 | 22-Sep-22 | 10-May-21 | 10-May-21 | 30-Nov-21 |  | Customer |  | 0
426044 | 7550 TORBRAM ROAD - TEMPORARY POLE LINE | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Kafel, Krzysztof | Truong, Jimmy | 18-Apr-19 |  |  | 44043.42 | 31836.36 | 44043.42 | 44043.42 | Paul Murphy |  | 21-May-19 | 14-Dec-20 | 13-May-19 | 03-May-19 | 13-May-19 |  |  |  | 0
365051 | 2018 UG Rebuild - Clarkson Section 4 - Constable/Bodley/Halkirk/Tallberg | 800 - Mavis | 150495 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Lucic, Marko |  |  |  | 0 | 0 |  | 0 | Paul Tremblay |  |  | 30-Apr-18
392403 | EXPANSION - OXFORD - BLOCK 8 - PH1 | 800 - Mavis | 152302 | Active | 84 | ACTIVE |  |  | 2023 | Lacombe, Joel | Garcha, Tirath | 29-Apr-22 |  |  | 1529869.24 | 962492.45 | 1335969.25 | 1529869.24 | Antonio Mina | Transpw | 18-Nov-22 | 07-Dec-23 | 30-Jun-22 | 07-Jul-22 |  | Contractor |  |  | 193,899.99
427611 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE 2 HAIG BOULEVARD | 800 - Mavis | 151589 | Inactive | 99 | COMPLETE |  |  | 2022 | Watters, Maxwell | Watters, Maxwell | 29-Oct-21 |  |  | 1889101.43 | 1613379.17 | 1889101.43 | 1889101.43 | Matthew Beach | Somervl | 05-Apr-23 | 26-Mar-23 | 22-Nov-21 | 19-Oct-21 | 18-Nov-22 |  |  |  | 0
419784 | Mississauga Rd - Rogers Make Ready | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 22-Nov-18 |  |  | 11575.77 | 7520.68 | 11575.77 | 11575.77 | Mark Bobanovic | K-Line | 28-Dec-18 | 22-Sep-22 | 21-Dec-18 | 21-Dec-18 | 08-Jan-19 | Customer | Filler |  | 0
414191 | 155 OAKES DRIVE TEMPORARY SERVICE | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 25-Jun-19 |  |  | 0 | 1845.45 |  | 0 | Peter Costantini |  | 25-Jun-19 | 30-Aug-21 | 25-Jun-19 | 25-Jun-19 | 25-Jun-19 | xBy-passed | xBy-passed
425893 | MAVIS ROAD WIDENING PHASE 3 - B/W TWAIN AVE AND HWY 407 | 800 - Mavis | 150673 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-Feb-19
427602 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE 1 DIXIE ROAD | 800 - Mavis | 151589 | Inactive | 99 | COMPLETE | Medium | Infrast | 2022 | Watters, Maxwell | Watters, Maxwell | 04-Aug-20 |  |  | 3184986.34 | 2808949.12 | 3397365.54 | 3184986.34 | Matthew Beach | Somervl | 15-Sep-22 | 15-Jun-23 | 21-Sep-20 | 09-Sep-20 | 18-Nov-22 |  |  |  | -212,379.20
419750 | POLE REPLACEMETS - BATCH #1 (1 POLE) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Handy, James | 14-Mar-19 |  |  | 17757.09 | 7196.8 | 17757.09 | 17757.09 | Paul Murphy |  | 21-Jun-19 | 11-Sep-22 | 17-Jun-19 | 18-Apr-19 | 06-May-19 |  |  |  | 0
403627 | 353-417 Rathburn Rd W | 800 - Mavis | 150652 | Inactive | 99 | CANCELLED |  |  | 2022 | Penner, Mitchell | Ricci, Leonardo |  |  |  | 0 | 11682.99 |  | 0 | Weaver, Thomas |  |  | 23-Jul-18
414115 | U/G FEEDER CABLE REPLACEMENT- AVONWICK AVE WEST OF MAVIS | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lucic, Marko | Tempra, Troylan | 25-Feb-19 |  |  | 199017.26 | 217924.03 | 199017.26 | 199017.26 | Paul Tremblay | Somervl | 16-May-19 | 09-Aug-22 | 01-Apr-19 | 01-Apr-19 | 23-Apr-19 |  |  |  | 0
360751 | 3600-3606 Hurontario St. - Armdale Estate Inc | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Sta. Rita, Leovigildo | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 03-Feb-22
427557 | Queen St S - Bell Make Ready (Y16415) | 800 - Mavis | BELL | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 13-Aug-19 |  |  | 6568.96 | 4606.64 | 6568.96 | 6568.96 | Rob Elliot |  | 16-Sep-19 | 04-Jan-22 | 16-Sep-19 | 22-Aug-19 | 22-Aug-19 |  |  |  | 0
403141 | 4601 Mississauga Rd | 800 - Mavis | 150652 | Inactive | 99 | CANCELLED |  |  | 2022 | Gamboa, Henry | Ricci, Leonardo |  |  |  | 0 | 5143.5 |  | 0 | Weaver, Thomas |  |  | 23-Jul-18
425746 | 927 MEADOW WOOD RD - ARMAGH TRANSITIONAL HOUSING | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Huo, Lisa | 17-Mar-22 |  |  | 115215.65 | 92239.98 | 115215.65 | 115215.65 | Peter Costantini |  | 19-Apr-22 | 08-Aug-23 | 15-Apr-22 | 27-Apr-22 |  | Customer |  |  | 0
403088 | SG1534 - RATHBURN RD. AND GOLDEN ORCHARD DR. | 800 - Mavis | 151144 | Inactive | 99 | CANCELLED |  |  | 2022 | Antonakos, Tony | Cudzilo, Tomasz | 20-Mar-19 |  |  | 168370.55 | 0 | 188126.86 | 188126.86 | Glenn Guile |  | 03-Jun-19 | 26-Apr-23 | 01-May-19 |  |  |  | Customer |  | 0
360743 | 3618 Hurontario St - Enfield Place II | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Sta. Rita, Leovigildo | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 06-Dec-21
427346 | SG1465 REMOVAL - 3079 FIFTH LINE WEST | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Cudzilo, Tomasz | 17-Apr-19 |  |  | 46246.42 | 69224.78 | 46246.42 | 46246.42 | Glenn Guile |  | 02-Jul-19 | 04-Dec-20 | 10-Jun-19 | 04-Jun-19 | 04-Jun-19 |  |  |  | 0
391013 | 4677 Glen Erin Dr. - Mills Square Bldg C | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Zaghloul, Sam | 02-Oct-18 |  |  | 13426 | 83248.41 | 72040.21 | 72040.21 | Macdougall, Stephen |  | 28-Nov-18 | 24-Nov-20 | 13-Nov-18 | 07-Dec-18 | 25-Nov-19 |  | Customer |  | 0
635787 | CENTRAL SOUTH TX REPLACEMENT - BATCH 29 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Webb-Murre, Paige | 22-Jun-20 |  |  | 11041.45 | 7927.63 | 11041.45 | 11041.45 | Glenn Guile |  | 16-Oct-20 | 12-Nov-21 | 12-Oct-20 | 07-Jan-21 | 07-Jan-21 | Filler | Filler |  | 0
419653 | MALTON GO STATION ROW POLELINE | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Watters, Maxwell | 17-Dec-18 |  |  | 62301.41 | 45406.34 | 62301.41 | 62301.41 | Rob Elliot | Somervl | 05-Nov-19 | 28-Jun-21 | 24-Oct-19 | 29-Sep-19 | 26-Oct-19 |  | MC/PUCC Permit |  | 0
427160 | 3480 MORNING STAR DR - WESTWOO | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Bharosi, Mohindra | 09-May-19 |  |  | 30668.5 | 17092.03 | 30668.5 | 30668.5 | Macdougall, Stephen |  | 28-Jun-19 | 04-Dec-20 | 17-Jun-19 | 12-Jul-19 | 18-Aug-19 |  | Customer |  | 0
413850 | 7675 TORBRAM ROAD - CN MALPORT YARD | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 10-Dec-18 |  |  | 23209.96 | 98560.61 | 83707.52 | 101813.52 | Macdougall, Stephen |  | 30-Jan-19 | 20-Nov-20 | 07-Jan-19 | 20-Dec-18 | 05-Jul-19 |  | Customer |  | 18,106.00
360621 | 1580 Britannia Rd. E - Addition / Reno | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Huo, Lisa | 09-Sep-19 |  |  | 134562.13 | 133313.12 | 134562.13 | 134562.13 | Macdougall, Stephen | Somervl | 08-Nov-19 | 26-Nov-20 | 14-Oct-19 | 07-Oct-19 | 19-Nov-19 |  |  |  | 0
425703 | GUYING RELOCATIONS - ERIN MILLS PKWY REGION OF PEEL | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Truong, Jimmy | 29-May-19 |  |  | 23444.61 | 21264.08 | 23444.61 | 23444.61 | Paul Murphy |  | 24-Jun-19 | 21-Dec-20 | 17-Jun-19 | 09-Sep-19 | 10-Oct-19 | Filler | Filler |  | 0
390791 | 7070 Derrycrest Dr. - Chartwell Headquarters | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Bharosi, Mohindra | 04-Dec-17 |  |  | 108300.3 | 105768.27 | 100229.9 | 108300.3 | Macdougall, Stephen |  | 13-Jul-18 | 19-Nov-20 | 14-May-18 | 14-May-18 | 25-Nov-19 |  | Customer |  | 8,070.40
413737 | 6965 VANGUARD DR. GAS STATION | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | MacDougall, Stephen | Huo, Lisa | 20-Sep-19 |  |  | 97710.56 | 85181.26 | 97710.56 | 97710.56 | Macdougall, Stephen | Somervl | 25-Nov-19 | 25-Nov-20 | 04-Nov-19 | 22-Sep-19 | 23-Dec-19 |  | Customer |  | 0
413585 | 6020 WINSTON CHURCHILL BLVD | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2021 | Lacombe, Joel | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 04-Oct-21
400493 | MALTON GO STATION U/G RELOCATI | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Watters, Maxwell | 25-Oct-18 |  |  | 235140.24 | 168638.55 | 235140.24 | 235140.24 | Rob Elliot |  | 27-May-19 | 22-Mar-21 | 15-Apr-19 | 10-Jan-19 | 28-Feb-19 |  |  |  | 0
359152 | 2145 North Sheridan Way - Marriot Residence Inn | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Huo, Lisa | 18-Mar-19 |  |  | 128461.41 | 129865.67 | 128461.41 | 128461.41 | Macdougall, Stephen |  | 31-May-19 | 11-Dec-20 | 01-May-19 | 30-May-19 | 23-Sep-19 |  | Customer |  | 0
425527 | STREETSVILLE VILLAGE BY DEZEN | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mustachi, Randy | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-Feb-19
400346 | 35 AND 65 WATERGARDEN DRIVE - UG SYSTEM EXPANSION | 800 - Mavis | 150675 | Active | 98 | COMPLETE |  |  | 2019 | Kafel, Krzysztof | Watters, Maxwell | 13-Mar-19 |  |  | 524132.41 | 662175.74 | 524132.41 | 524132.41 | Paul Tremblay | Transpw | 25-Jun-19 | 25-Aug-23 | 27-May-19 | 24-Jun-19 | 20-Sep-19 | Customer | Customer |  | 0
418538 | 1775 FIFESHIRE COURT -VARCON CONST - TEMP SERV | 800 - Mavis |  | Active | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 23-Oct-18 |  |  | 28745.04 | 24662.79 | 28745.04 | 28745.04 | Bourgeois, Craig |  | 29-Nov-18 | 28-Jul-23 | 23-Nov-18 | 07-Nov-18 | 01-Dec-19 |  | Customer |  | 0
358803 | PARK - SECTION 2 - STAVEBANK TO KANE | 800 - Mavis | 151186 | Inactive | HL | CANCELLED |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 1561.27 | 0 | 3785.33 | 3785.33 | Paul Murphy |  |  | 06-Jul-22 | [6 empty] | 0
400119 | 128 Queen St - Pole Relocations | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Watters, Maxwell | 19-Nov-18 |  |  | 227704.02 | 206395.65 | 227704.02 | 227704.02 | Rob Elliot |  | 25-Feb-19 | 26-Aug-21 | 07-Jan-19 | 11-Feb-19 | 04-Apr-19 | Customer | Customer |  | 0
413121 | 233 Madill Blvd | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Bharosi, Mohindra | 04-Sep-18 |  |  | 99103.98 | 43396.17 | 99103.98 | 99103.98 | Macdougall, Stephen |  | 02-Nov-18 | 29-Oct-20 | 15-Oct-18 | 16-Jan-19 | 04-Mar-19 |  | Customer |  | 0
418280 | 1325 BURNHAMTHORPE ROAD, MISSISSAUGA | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 21-Jan-20
425404 | SG1248- 334 ADMIRAL BLVD | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2019 | Lucic, Marko | Cudzilo, Tomasz | 12-Mar-19 |  |  | 39718.67 | 133045.79 | 77538.41 | 77538.41 | Paul Tremblay |  | 30-Aug-19 | 28-Jun-21 | 13-May-19 | 10-May-19 | 06-Aug-19 |  |  |  | 0
418221 | Ninth Line - Bell Make Ready Project | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 22-Nov-18 |  |  | 30106.76 | 18398.44 | 30106.76 | 30106.76 | Mark Bobanovic | K-Line | 28-Dec-18 | 22-Sep-22 | 21-Dec-18 | 20-Dec-18 | 08-Jan-19 |  | Lines |  | 0
425236 | 2019 CABLE INJECTION PROGRAM (PARENT WO) | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Antonakos, Tony | Antonakos, Tony -x |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 31-Jan-19
354811 | 2379-2385 Camila Road - TEMP | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Bharosi, Mohindra |  |  |  | 1094.15 | 0 | 1094.15 | 1094.15 | Macdougall, Stephen |  |  | 25-Jun-18 |  |  |  |  | Customer |  | 0
387111 | MTO PROJECT - QEW DIXIE ROAD HIGHWAY LIGHTING SERVICE | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 10-Jan-23 |  |  | 96028.54 | 137154.01 | 96028.54 | 96028.54 | Peter Costantini |  | 17-Apr-23 | 26-Jul-23 | 21-Mar-23 | 21-Mar-23 | 21-Apr-23 |  | Lines |  | 0
417666 | M-CITY ROGERS PHASE-2 3MVA + | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2022 | Mandic, Goran | Macasaet, Ricardo | 01-Jun-20 |  |  | 358861.25 | 329838.79 | 358861.25 | 358861.25 | Antonio Mina |  | 07-Oct-20 | 22-Sep-22 | 02-Jul-20 | 20-Dec-21 | 15-Apr-22 | Customer | Customer |  | 0
412195 | 309 RATHBURN RD WEST - LIVING ARTS PARKING LOT 400AM | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 12-Sep-22
387081 | 360 CITY CENTRE DR. - The Wesley Tower | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 19-Dec-19 |  |  | 0 | 107450.55 |  | 0 | Paul Tremblay |  | 19-Dec-19 | 27-Jan-22 | 19-Dec-19 | 19-Dec-19 | 19-Dec-19 | xBy-passed | xBy-passed
425164 | SG1650 & SG1237- 2875 THOMAS STREET | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Cudzilo, Tomasz | 28-Mar-19 |  |  | 51585.97 | 154766.66 | 51585.97 | 51585.97 | Glenn Guile |  | 23-May-19 | 19-Nov-20 | 01-May-19 | 04-Apr-19 | 25-Apr-19 |  |  |  | 0
352479 | 6740 Meadowvale Town Centre - Meadowvale Town Centre New CIBC | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Sta. Rita, Leovigildo | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 05-Mar-18
425050 | SG1802- 533 MIDDLEBURY DR | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Cudzilo, Tomasz | 18-Mar-19 |  |  | 36573.49 | 51132.17 | 36573.49 | 36573.49 | Glenn Guile |  | 15-May-19 | 19-Nov-20 | 17-Apr-19 | 29-Apr-19 | 14-May-19 |  |  |  | 0
412179 | CAWTHRA AND ATWATER STACKED TOWNHOUSE PROJECT | 800 - Mavis | 150384 | Active | 40 | ACTIVE |  |  | 2023 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 14-Mar-19
386337 | 5399 Rose Cherry Pl. - City of Mississauga - Hershey Service | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2023 | Sidhu, Paul | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 02-Apr-18
424882 | INDIAN RD & MADIGAN'S LANE - Make Ready | 800 - Mavis |  | Active | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 12-Feb-19 |  |  | 58945.25 | 171129.94 | 58945.25 | 58945.25 | Mark Bobanovic | K-Line | 08-Mar-19 | 26-Jul-23 | 05-Mar-19 | 25-Feb-19 | 28-Feb-19 |  |  |  | 0
386151 | 2017 OTC (INITIAL) - M-CITY PHASE 1 (EHM COSTS) | 800 - Mavis | 150652 | Active | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Ricci, Leonardo | 07-May-21 |  |  | 88498.07 | 83213.17 | 88498.07 | 88498.07 | Mark Bobanovic | Transpw | 25-Aug-21 | 26-Jul-23 | 31-May-21 | 30-Aug-21 | 05-Aug-22 | Customer | Customer |  | 0
417463 | 1850 MATHESON BLVD E - CBS CANADA FILM STUDIO | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Bharosi, Mohindra | 10-Dec-18 |  |  | 65793.59 | 75721.74 | 65793.59 | 65793.59 | Macdougall, Stephen |  | 15-Jan-19 | 24-Aug-20 | 07-Jan-19 | 21-Feb-19 | 18-Mar-19 |  | Customer |  | 0
384905 | 4055 Parkside Village Dr. | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2019 | Sta. Rita, Leovigildo | Macasaet, Ricardo | 19-Dec-19 |  |  | 0 | 183969 |  | 0 | Paul Tremblay |  | 19-Dec-19 | 05-Aug-21 | 19-Dec-19 | 15-Oct-19 | 16-Oct-19 | xBy-passed | xBy-passed
397651 | 6775 MARITZ DRIVE-BLUM | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Zaghloul, Sam | 09-Aug-18 |  |  | 63570.82 | 128286.87 | 127184.46 | 127184.46 | Macdougall, Stephen |  | 26-Sep-18 | 16-Feb-21 | 10-Sep-18 | 22-Jul-19 | 09-Dec-19 | Customer | Customer |  | 0
417236 | SILVER BIRCH PUMPING STATION | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 19-Dec-22 |  |  | 382012.19 | 299054.6 | 382012.19 | 382012.19 | Peter Costantini | Somervl | 08-May-23 | 04-Aug-23 | 24-Apr-23 | 24-Apr-23 |  |  |  |  | 0
424794 | 4235 CONFEDERATION PKWY. MISS. - NS-3PH VAULT - OXFORD RENTAL DEVELOPMENT | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Garcha, Tirath | 26-Apr-22 |  |  | 220751.36 | 11861.97 | 220751.36 | 220751.36 | Peter Costantini |  | 21-Aug-23 | 22-Aug-23 | 25-Jul-23 | 25-Jul-23 |  |  |  |  | 0
383881 | 2018 U/G Rebuild - City Centre Drive Cable Renewal | 800 - Mavis | 151172 | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Cudzilo, Tomasz | 23-Apr-19 |  |  | 836311.17 | 894302.35 | 813311.17 | 836311.17 | Paul Tremblay | Transpw | 27-Jun-19 | 09-Aug-22 | 30-Apr-19 | 23-Apr-19 | 16-Jul-19 |  | Locates |  | 23,000.00
396797 | TX REPLACEMENT TX24275 - 3476 B GLEN ERIN DR | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Matai, Ihssan (Sam) | 01-Nov-21 |  |  | 43812.88 | 18595.8 | 43812.88 | 43812.88 | Gregory Dunfield |  | 30-Nov-21 | 08-Jun-22 | 22-Nov-21 | 18-Nov-21 | 18-Nov-21 |  |  |  | 0
411993 | 562 Lynd Ave - Pole Relocation | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Truong, Jimmy | 19-Jul-19 |  |  | 9307.6 | 10274.48 | 10487.65 | 10487.65 | Paul Murphy |  | 28-Aug-19 | 19-Aug-21 | 27-Aug-19 | 16-Aug-19 | 16-Aug-19 |  |  |  | 0
424786 | 395 SQUARE ONE DR. MISS. - NS-3PH VAULT - OXFORD CONDO DEVELOPMENT | 800 - Mavis | 150384 | Active | 93 | ACTIVE |  |  | 2023 | Mandic, Goran | Garcha, Tirath | 26-Apr-22 |  |  | 228756.58 | 171516.51 | 228756.58 | 228756.58 | Antonio Mina |  | 05-May-23 | 26-Jul-23 | 10-Mar-23 | 10-Mar-23 | 26-Apr-23 |  |  |  | 0
383793 | 5100 Erin Mills Parkway-Tesla Supercharging Station | 800 - Mavis | 150384 | Active | HO | RELEASED |  |  | 2023 | Mustachi, Randy | Macasaet, Ricardo | 28-Jun-18 |  |  | 188758.23 | 12048.42 | 188758.23 | 188758.23 | Peter Costantini |  | 22-May-19 | 09-Aug-23 | 01-May-19 |  |  | Customer | Customer |  | 0
417228 | 182 ROSEMERE ROAD - ROSEMERE PUMPING STATION | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Sidhu, Paul | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Jun-21
416541 | STARLIGHT RENTAL CONDOMINIUMS | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mustachi, Randy | Huo, Lisa | 09-Jun-22 |  |  | 115266.87 | 120567.31 | 115266.87 | 115266.87 | Peter Costantini | Somervl | 02-Jun-22 | 22-Sep-22 | 09-May-22 | 30-May-22 | 15-Jun-22 | Customer | Customer |  | 0
396295 | RER MX - LW CONFLICT #LW26 - CLARKSON ROAD NORTH | 800 - Mavis | 150594 | Active | 70 | H2 | High | MLinx | 2023 | Khuu, Philander | Khuu, Philander |  |  |  | 0 | 79607.24 |  | 0 | XMoinuddin, Saad | Transpw | 14-Aug-20 | 22-Sep-22 | 11-May-20
424188 | Winston Churchill Blv Make Ready | 800 - Mavis | ROGERS | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 04-Feb-19 |  |  | 7203.08 | 0 | 7203.08 | 7203.08 | Rob Elliot |  | 20-Feb-19 | 14-Oct-21 | 19-Feb-19 | 04-Feb-19 | 04-Feb-19 |  | Customer |  | 0
383478 | 7355 Goreway Rd - Service Upgrade | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Sidhu, Paul | Zaghloul, Sam | 10-May-18 |  |  | 84464.49 | 71929.41 | 84464.49 | 84464.49 | Macdougall, Stephen |  | 25-Jun-18 | 18-Nov-20 | 04-Jun-18 | 11-Feb-19 | 16-Sep-19 |  | Customer |  | 0
344997 | Queen & Britannia Pole Relocation | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2021 | Hotham, Matthew | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | Paul Murphy |  |  | 03-Apr-18
396252 | RER MX - LW CONFLICT #LW25 & LW1854 - SHAWNMARR/MERLOT CRT | 800 - Mavis | 150594 | Active | 84 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin | 06-Feb-23 |  |  | 3497273.61 | 975369.05 | 3416054.8 | 3497273.61 | Antonio Mina | Transpw | 16-Nov-23 | 06-Feb-24 | 04-May-23 | 14-Oct-22 |  |  |  |  | 81,218.81
411782 | CCRA - 185 ENFIELD PLACE - GREAT WEST LIFE ENFIELD CONDOMINIUMS | 800 - Mavis | 150384 | Active | HO | RELEASED |  |  | 2023 | Mandic, Goran | Garcha, Tirath | 05-Jul-22 |  |  | 221883.86 | 25424.7 | 221883.86 | 221883.86 | Peter Costantini | N/A | 11-Nov-22 | 01-Sep-23 | 12-Sep-22 | [5 empty] | 0
424129 | BELL MAKE READY -DATSUN RD (Y54769) | 800 - Mavis | BELL | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 25-Mar-19 |  |  | 41288.44 | 33454.9 | 41288.44 | 41288.44 | Mark Bobanovic | K-Line | 29-Apr-19 | 22-Sep-22 | 29-Apr-19 | 10-Apr-19 | 30-Apr-19 |  | N/A |  | 0
344321 | 125 Eglinton Ave W - FS 120 | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Huo, Lisa | 24-Sep-18 |  |  | 48826.26 | 165579.24 | 175755.25 | 175755.25 | Macdougall, Stephen |  | 14-Nov-18 | 19-Nov-20 | 22-Oct-18 | 02-Nov-18 | 03-Sep-19 |  | Customer |  | 0
396244 | RER MX - LW CONFLICT #LW1654 - MISSISSAUGA ROAD | 800 - Mavis | 150594 | Active | 99 | COMPLETE |  |  | 2022 | Khuu, Philander | Khuu, Philander | 08-Mar-21 |  |  | 3822570.43 | 2930970.54 | 3822570.43 | 3822570.43 | Mark Bobanovic | Transpw | 06-May-21 | 26-Jul-23 | 15-Feb-21 | 25-Mar-21 | 28-Feb-22 | MC/PUCC Permit | MC/PUCC Permit |  | 0
341471 | 2021 - 2323 & 2300 CONFEDERATION PARKWAY - TX VAULT UPGRADE | 800 - Mavis | 151043 | Active | HO | H2 |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 05-Nov-21 |  |  | 692402.96 | 243514.76 | 692402.96 | 692402.96 | Antonio Mina | Somervl | 09-Mar-22 | 25-Sep-23 | 06-Dec-21 | 17-Jan-22 |  | Locates | MC/PUCC Permit |  | 0
411521 | 7 KIMBEL ST. - IMPACT AUTO | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2023 | Sta. Rita, Leovigildo | Huo, Lisa |  |  |  | 0 | 4281.56 |  | 0 | Weaver, Thomas |  |  | 10-May-23
382707 | 360 City Centre Dr - Daniels CCW Corp. - The Wesley | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Macasaet, Ricardo | 14-Mar-19 |  |  | 305517.96 | 84113.9 | 305517.96 | 305517.96 | Macdougall, Stephen |  | 12-Jul-19 | 24-Feb-21 | 17-Jun-19 | 26-Jun-19 | 31-Oct-19 | Customer | Customer |  | 0
341227 | 2018 UG rebuild - Credit Woodlands Crt./ Wiltshire | 800 - Mavis | 151179 | Inactive | 99 | COMPLETE |  |  | 2019 | Lewis, Kevin | Matai, Ihssan (Sam) | 01-Apr-19 |  |  | 1385397.29 | 1484845.73 | 1385397.29 | 1385397.29 | Mark Bobanovic | Transpw | 25-Jul-19 | 09-Aug-22 | 23-Apr-19 | 23-Apr-19 | 02-Aug-19 |  | Contractor |  | 0
416321 | 1PH TX REPLACEMENTS - BATCH #3 (11 TX'S) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Cudzilo, Tomasz | 21-Oct-19 |  |  | 0 | 54209.62 |  | 0 | Paul Tremblay |  | 21-Oct-19 | 09-Aug-22 | 21-Oct-19 | 21-Oct-19 | 21-Oct-19 | xBy-passed | xBy-passed
396236 | GO ELEC. - LWL - CONFLICT #LW24 - STAVEBANK ROAD | 800 - Mavis | 150594 | Inactive | 99 | CANCELLED |  |  | 2022 | Tobin, Michael | Khuu, Philander |  |  |  | 0 | 11930.6 |  | 0 | Weaver, Thomas |  |  | 24-May-22
381561 | 6211 Second Line West | 800 - Mavis | 150652 | Inactive | 99 | CANCELLED |  |  | 2022 | Penner, Mitchell | Ricci, Leonardo |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 16-May-22
410229 | 1201 Fewster Dr. - SOL CUISINE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | MacDougall, Stephen | Huo, Lisa | 14-Jan-19 |  |  | 105432.91 | 128769.8 | 105432.91 | 105432.91 | Macdougall, Stephen |  | 14-Feb-19 | 24-Aug-20 | 28-Jan-19 | 15-Jan-19 | 10-Mar-19 |  | Customer |  | 0
340216 | Glen Erin & Battleford (Phase 1) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 01-Apr-19 |  |  | 0 | 20582.5 |  | 0 | Paul Tremblay |  | 01-Apr-19 | 22-Sep-22 | 01-Apr-19 | 01-Apr-19 | 01-Apr-19 | xBy-passed | xBy-passed
380955 | 309 Lakeshore Road East & Tx R | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 25-Jun-19 |  |  | 0 | 31912.68 |  | 0 | Bourgeois, Craig |  | 25-Jun-19 | 09-Aug-22 | 25-Jun-19 | 25-Jun-19 | 25-Jun-19 | xBy-passed | xBy-passed
410173 | 5050 SATELLITE DRIVE - SPECTRU | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2019 | Mandic, Goran | Bharosi, Mohindra | 04-Sep-18 |  |  | 53761.57 | 77023.5 | 49470.14 | 56136.82 | Macdougall, Stephen |  | 21-Nov-18 | 06-Nov-20 | 13-Nov-18 | 21-Mar-19 | 29-May-19 |  | Customer |  | 6,666.68
424006 | MEADOWVALE ISLAMIC CENTRE | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 16-Jan-19
396210 | RER MX - LW CONFLICT #LW22 & LW2794 - REVUS AVE. | 800 - Mavis | 150594 | Active | 92 | ANALYZE | High |  | 2023 | Khuu, Philander | Khuu, Philander | 21-Mar-23 |  |  | 3040186.35 | 3094994 | 2752419.17 | 3040186.35 | Paul Murphy | Transpw | 12-Jul-23 | 04-Oct-23 | 04-May-23 | 20-Apr-23 | 30-May-23 |  |  |  | 287,767.18
409957 | OTC (INITIAL) - M-CITY PHASE 1 (EXPANSION COSTS) | 800 - Mavis | 151581 | Active | 98 | COMPLETE | Medium | Res-ICI | 2022 | Watters, Maxwell | Watters, Maxwell | 29-Apr-21 |  |  | 3865773.69 | 3607335.92 | 3400436.62 | 3865773.69 | Mark Bobanovic | Transpw | 21-Dec-21 | 26-Jul-23 | 14-Jun-21 | 31-May-21 | 04-May-22 |  | Customer |  | 465,337.07
380533 | Munden/Pear Tree | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 07-Aug-18 |  |  | 590957.6 | 951929.25 | 590957.6 | 590957.6 | Mark Bobanovic | A&W | 28-Dec-18 | 09-Aug-22 | 29-Oct-18 | 29-Oct-18 | 13-Nov-19 |  | Contractor |  | 0
416233 | 1PH TX REPLACEMENTS - BATCH #2 (10 TX'S) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Cudzilo, Tomasz | 21-Oct-19 |  |  | 0 | 50125.22 |  | 0 | Paul Tremblay |  | 21-Oct-19 | 09-Aug-22 | 21-Oct-19 | 21-Oct-19 | 21-Oct-19 | xBy-passed | xBy-passed
409922 | 3980 CONFEDERATION PKWY - M-CITY ROGERS PHASE-1 3MVA + | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2022 | Mandic, Goran | Macasaet, Ricardo | 29-Jun-20 |  |  | 356648.68 | 309628.8 | 356648.68 | 356648.68 | Antonio Mina |  | 02-Oct-20 | 22-Sep-22 | 29-Jun-20 | 15-Dec-21 | 15-Apr-22 | Customer | Customer |  | 0
416209 | TX 6773 AT 3530 WISNER RD | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Antonakos, Tony | Matai, Ihssan (Sam) | 13-Nov-18 |  |  | 91614.13 | 49636.66 | 91614.13 | 91614.13 | Paul Tremblay |  | 22-Apr-19 | 09-Aug-22 | 22-Apr-19 | 22-Apr-19 | 22-Apr-19 | xBy-passed | xBy-passed |  | 0
423724 | SG 1549 CREDITVIEW RD. N OF SIR MONTY'S DR. | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2019 | Lucic, Marko | Cudzilo, Tomasz | 07-May-19 |  |  | 146163.38 | 130726.26 | 124257.55 | 146163.38 | Macdougall, Stephen | Somervl | 29-Aug-19 | 13-Feb-22 | 24-Jun-19 | 26-Jun-19 | 27-Aug-19 | Contractor |  |  | 21,905.83
634379 | Folkway Rebuild - Phase2 | 800 - Mavis | 151146 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 19-Jun-20 |  |  | 2779472.35 | 3025979.9 | 2731756.26 | 2779472.35 | Paul Tremblay | Transpw | 05-Oct-20 | 21-Apr-22 | 20-Jul-20 | 14-Oct-20 | 26-Mar-21 | MC/PUCC Permit | MC/PUCC Permit |  | 47,716.09
633540 | MISSISSAUGA ROAD SOUTH POLELINE RELOCATION | 800 - Mavis | 150675 | Active | 98 | COMPLETE |  |  | 2021 | Lacombe, Joel | Garcha, Tirath | 09-Jun-21 |  |  | 1660318.54 | 1353016.96 | 1646004.35 | 1660318.54 | Paul Murphy | Transpw | 21-Oct-21 | 26-Jul-23 | 05-Jul-21 | 23-Jul-21 | 30-Nov-21 | Locates | Contractor |  | 14,314.19
426351 | CITY CENTRE NORTH MS - HV2 SWI | 800 - Mavis | 151059 | Inactive | 99 | CANCELLED |  |  | 2021 | Houston, Andrew | Central South |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 11-Mar-21
427258 | AQUITANE M.S. T60 CONTROLLER U | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 02-Mar-21 | 29-Apr-19 | 21-Dec-20 | 21-Dec-20 | 02-Mar-21
428373 | CITY CENTRE HV CABLE REPLACEMENTS | 800 - Mavis | 151048 | Active | 99 | COMPLETE |  |  | 2021 | Houston, Andrew | Zaghloul, Sam | 27-Sep-21 |  |  | 431229.39 | 644285.46 | 431229.39 | 431229.39 | Antonio Mina | Somervl | 24-Nov-21 | 26-Jul-23 | 20-Oct-21 | 04-Oct-21 | 10-Dec-21 |  | Lines |  | 0
379997 | DERRY ROAD EXTENSION PH2 | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Matai, Ihssan (Sam) | 12-Dec-18 |  |  | 198650.1 | 278571.09 | 198650.1 | 198650.1 | Rob Elliot |  | 04-Apr-19 | 24-Aug-20 | 11-Mar-19 | 14-Mar-19 | 16-May-19 |  | MC/PUCC Permit |  | 0
377342 | Courtney Park from Dixie to Shawson | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Matai, Ihssan (Sam) | 24-Sep-18 |  |  | 582126.17 | 675714.41 | 374296.76 | 582126.17 | Paul Murphy |  | 11-Dec-18 | 09-Aug-22 | 01-Nov-18 | 07-Jan-19 | 06-May-19 | Customer | Customer |  | 207,829.41
267215 | Malton MS Feeder Egress | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Watters, Maxwell | 05-Nov-18 |  |  | 254949.82 | 237775.22 | 254949.82 | 254949.82 | Rob Elliot |  | 24-Apr-19 | 24-Aug-20 | 14-Jan-19 | 11-Feb-19 | 05-May-19 |  | Customer |  | 0
634530 | CHURCH STREET - MAIDEN LANE (BORE SHOT) | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 30-Aug-21 |  |  | 144229.31 | 161355.89 | 144229.31 | 144229.31 | Rob Elliot | Transpw | 30-Sep-21 | 06-Apr-22 | 30-Aug-21 | 30-Aug-21 | 28-Oct-21 | xBy-passed | xBy-passed |  | 0
428921 | 428921 - Orlando Corp Retail Building E | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | Low | Comm | 2022 | Mandic, Goran | Macasaet, Ricardo | 27-Nov-19 |  |  | 120806.6 | 120253.82 | 120806.6 | 120806.6 | Peter Costantini |  | 25-Feb-20 | 30-Jan-23 | 13-Jan-20 | 08-May-20 | 25-Oct-22 | Customer | Customer |  | 0
634738 | MTO- MISSISSAUGA ROAD AND HIGHWAY 401 INTERCHANGE | 800 - Mavis | 150384 | Active | 96 | COMPLETE |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo | 29-Oct-21 |  |  | 98182.23 | 74711.03 | 98182.23 | 98182.23 | Peter Costantini | Somervl | 14-Feb-22 | 26-Jul-23 | 10-Jan-22 | 08-Nov-21 | 17-May-22 | Customer | Customer |  | 0
633794 | OH TRANSFORMER REPLACEMENTS - PART 2 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Pellerin, Patrick | 01-Jun-20 |  |  | 136173.14 | 127481.55 | 136173.14 | 136173.14 | Paul Murphy |  | 08-Sep-20 | 11-Nov-21 | 01-Aug-20 | 08-Jan-21 | 03-Feb-21 | Filler | Filler |  | 0
636153 | CNR SPUR LINE CROSSING-TORBRAM-AIRPORT RD | 800 - Mavis | 150823 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636169 | 2200 BROMSGROVE RD. - 1200A NEW SERVICE REQUEST | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Pellerin, Patrick | 18-Jan-21 |  |  | 47630.31 | 80549.54 | 47630.31 | 47630.31 | Peter Costantini |  | 19-Mar-21 | 22-Nov-22 | 01-Mar-21 | 26-Apr-21 | 21-Jun-21 | Customer | Customer |  | 0
636202 | 6550 & 6570 GLEN ERIN DRIVE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 30-Aug-21 |  |  | 101698.64 | 83826.76 | 101698.64 | 101698.64 | Peter Costantini | Somervl | 04-Oct-21 | 22-Nov-22 | 02-Sep-21 | 02-Sep-21 | 05-Oct-21 |  | N/A |  | 0
636298 | 1293 MEREDITH AVE | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 30-May-22
636649 | UG CABLE REPLACEMENT DARCEL AND BRANDON GATE | 800 - Mavis | 150495 | Inactive | 99 | CANCELLED |  |  | 2022 | Sidhu, Paul | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636650 | UG CABLE REPLACEMENT - SIGSBEE AND BRANDON GATE DRIVE- PHASE 2 | 800 - Mavis | 151401 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Matai, Ihssan (Sam) | 26-Mar-21 |  |  | 2160987.55 | 2180063.49 | 2160987.55 | 2160987.55 | Antonio Mina | Transpw | 15-Oct-21 | 10-Apr-23 | 06-May-21 | 03-May-21 | 09-Sep-21 |  |  |  | 0
636667 | AREA 56 DERRY-NINTH LINE CABLE INJECTION 2022 | 800 - Mavis | 150495 | Active | 70 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636765 | 960 BRITANNIA RD E - 3000KVA TRANSFORMER UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Pellerin, Patrick | 17-May-21 |  |  | 118319.75 | 117526.32 | 118319.75 | 118319.75 | Peter Costantini | Somervl | 05-Jul-21 | 22-Nov-22 | 14-Jun-21 | 11-Jun-21 | 12-Jun-21 |  |  |  | 0
636776 | HULRT METROLINX - OMSF EXPANSION PROJECT - KENNEDY & 407 | 800 - Mavis | 152286 | Active | 98 | COMPLETE |  |  | 2021 | Paesano, Andrew | Jolie, Chris | 14-May-21 |  |  | 7096896.44 | 6134206.65 | 7011477.46 | 7096896.44 | Mark Bobanovic | Transpw | 30-Sep-21 | 26-Jul-23 | 15-Jun-21 | 03-Jun-21 | 12-Nov-21 |  | Contractor |  | 85,418.98
636778 | CLARKSON VOLTAGE CONVERSION | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636784 | JOINT USE PERMIT HM2020-015 - SOUTHDOWN - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William |  |  |  | 5088.56 | 4075.39 | 5088.56 | 5088.56 | XMoinuddin, Saad |  |  | 26-Jul-23 |  | 15-Nov-21 | 15-Nov-21 |  |  |  | 0
636785 | JOINT USE PERMIT HM2020-019 - ROYAL WINDSOR, LAKESHORE, SOUTHDOWN - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 18-May-21 |  |  | 4078.82 | 4475.87 | 4078.82 | 4078.82 | Macdougall, Stephen |  | 25-Jun-21 | 22-Sep-22 | 25-Jun-21 | 02-Aug-21 | 02-Aug-21 | Lines | Lines |  | 0
636788 | JOINT USE PERMIT HM2020-024 - SHERIDAN PARK - MISS | 800 - Mavis | 151537 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636791 | JOINT USE PERMIT HM2020-028 - GOREWAY - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 08-Jun-21 |  |  | 6417.48 | 11237.97 | 6417.48 | 6417.48 | Macdougall, Stephen |  | 08-Jul-21 | 22-Sep-22 | 08-Jul-21 | 14-Jul-21 | 14-Jul-21 | Lines | Lines |  | 0
636796 | TRUSCOTT PLAZA - ADDITIONAL CAPACITY | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636797 | MONTEVIDEO & TREVISO PH-1 CABLE REPLACEMENT | 800 - Mavis | 151402 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Tempra, Troylan | 26-Apr-21 |  |  | 2567572.55 | 2605058.4 | 2535761.75 | 2567572.55 | Antonio Mina | Transpw | 02-Sep-21 | 22-Sep-22 | 10-May-21 | 12-May-21 | 27-Sep-21 |  | Contractor |  | 31,810.80
636798 | MONTEVIDEO & TREVISO PH-2 CABLE REPLACEMENT | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636799 | RATHBURN RD W & QUEENBRIDGE CABLE REPLACEMENT | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636800 | RATHBURN RD E & TOMKEN CABLE REPLACEMENT | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636841 | POLE REBUILD - KING ST W REBUILD | 800 - Mavis | 151063 | Active | 80 | H3 |  |  | 2023 | Chigbo Ardern, Linda | Chigbo Ardern, Linda |  | 4 |  | 141673.85 | 75.38 | 141673.85 | 141673.85 | Persaud, Ryan |  |  | 26-Jul-23 | [6 empty] | 0
636846 | DERRY ROAD - CREDITVIEW - MISSAUGA RD - 27.6KV CIRCUIT EXTENSION | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636855 | SOUTHDOWN & LAKESHORE UG CABLE REPLACEMENT | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636873 | UG CABLE REPLACEMENT - MILLCREEK & ERIN MILLS PKWY | 800 - Mavis | 151516 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Tempra, Troylan | 26-May-22 |  |  | 1282612.32 | 1190924.58 | 1274480.86 | 1282612.32 | Antonio Mina | Transpw | 12-Sep-22 | 16-Mar-23 | 30-May-22 | 06-Jun-22 | 28-Oct-22 |  | Contractor |  | 8,131.46
636906 | CABLE REPLACEMENT - EGLINTON & CREDIT VALLEY | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636918 | CABLE REPLACEMENT - DARCEL & BRANDON GATE | 800 - Mavis | 151328 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 29-Jan-21 |  |  | 1566404.85 | 1421032.39 | 1566404.85 | 1566404.85 | Antonio Mina | Transpw | 22-Jun-21 | 23-May-23 | 15-Mar-21 | 13-Apr-21 | 14-Jul-21 | Contractor | Contractor |  | 0
636923 | CABLE REPLACEMENT - OLD CARRIAGE RD | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636943 | CABLE REPLACEMENT PROJECT- QUEENSWAY & MAVIS | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
636983 | AREA 11 - TRUESCOTT AND DOWNSVIEW | 800 - Mavis | 150495 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637001 | 2023 EM OH - ANIMAL ABATEMENT - 54F3 | 800 - Mavis | 150823 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Ferry, Rodnne | 10-Nov-22 |  |  | 57314 | 23188.19 | 57314 | 57314 | Gregory Dunfield |  | 26-Jun-23 | 03-Aug-23 | 13-Jun-23 | 28-Apr-23 |  |  |  |  | 0
637020 | CITATION PLACE INVESTIGATION | 800 - Mavis | 151451 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637030 | AUTOMATED SWITCHES-CENTRAL SOUTH | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637040 | TANU CONDOS - POLE LINE RESTORATION- 29 PARK ST EAST | 800 - Mavis | 150675 | Active | 82 | RELEASED |  |  | 2023 | Watters, Maxwell | Odisho, Carlo | 14-Apr-23 |  |  | 679969.51 | 43816.6 | 679969.51 | 679969.51 | Paul Murphy |  | 19-Dec-23 | 12-Jan-24 | 05-Jul-23 | [5 empty] | 0
637051 | 2531 CAWTHRA RD. 1PH SERVICE | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | MacDougall, Stephen | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637091 | 13 CP - POLE RENEWAL - BURNHAMTHORPE RD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 04-Feb-22 | 13 | 13 | 431274.32 | 439493.29 | 414246.97 | 431274.32 | Mark Bobanovic | K-Line | 08-Mar-23 | 29-May-23 | 22-Sep-22 | 07-Oct-22 | 06-Dec-22 | Lines |  |  | 17,027.35
637032 | INSULATORS RENEWAL - BATCH #2 | 800 - Mavis | 151727 | Active | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 01-Jun-21 |  |  | 107288.53 | 51535.42 | 107288.53 | 107288.53 | Gregory Dunfield |  | 13-Oct-21 | 26-Jul-23 | 13-Sep-21 | 19-Jul-21 | 17-Mar-22 |  | Filler |  | 0
637100 | POLES - CENTRAL SOUTH | 800 - Mavis | 151063 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Billone, Justin |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637177 | VICTORIA & BARRY ST | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637222 | 44KV FEEDER EXTENSION YORK MEADOWPINE | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637294 | LOCATES AND SURVEYING FOR REGION’S SENIORS HEALTH AND WELLNESS VILLAGE | 800 - Mavis | 151169 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637322 | CABLE REPLACEMENT - REID DR AND QUEEN ST SOUTH | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 18-Mar-21 |  |  | 192926.15 | 399158.78 | 192926.15 | 192926.15 | Glenn Guile | Somervl | 07-Jun-21 | 20-Feb-23 | 10-May-21 | 19-May-21 | 12-Aug-21 | Contractor | Contractor |  | 0
637339 | UG CABLE REPLACEMENT - S5230 TO S5227 TOMKEN TO NORTH OF KAMATO | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637340 | UG CABLE REPLACEMENT - L6885 TO L5858 - RATHBURN RD E & HURONTARIO | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637341 | UG CABLE REPLACEMENT - L6405 TO L6177 - FOLKWAY DR & ERIN MILLS PKWY | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 23-Mar-21 |  |  | 800083.18 | 737535.21 | 800083.18 | 800083.18 | Antonio Mina | Transpw | 28-Jun-21 | 25-Apr-22 | 19-Apr-21 | 06-Apr-21 | 17-May-21 |  |  |  | 0
637342 | UG CABLE REPLACEMENT - L105685 TO L5325 ROBERT SPECKWAY & BURNHAMTHORPE RD | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637417 | M CITY M4 TOWER 3MVA + 3MVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637442 | P15298 POLE RELOCATION - 23 DE JONG DRIVE | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 14-Dec-20 |  |  | 26920.37 | 20970.04 | 26920.37 | 26920.37 | Macdougall, Stephen |  | 14-Jan-21 | 12-Nov-21 | 11-Jan-21 | 18-Jan-21 | 26-Jan-21 | Customer | Customer |  | 0
637450 | THE COLLEGEWAY STACKED TOWNHOMES - 3540 COLONIAL DR. | 800 - Mavis | 150384 | Active | 91 | TEMP |  |  | 2023 | Mandic, Goran | Roy, Akash | 29-Mar-22 |  |  | 269136.39 | 296555.87 | 269136.39 | 269136.39 | Peter Costantini | Somervl | 26-May-22 | 23-Aug-23 | 28-Mar-22 | 07-Apr-22 |  | Customer |  |  | 0
637462 | 69 HIGH ST W - POLE P01935 | 800 - Mavis | 151537 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William |  |  |  | 50318.99 | 28805.5 | 50318.99 | 50318.99 | K-Line Construction |  | 17-May-21 | 26-Jul-23 | 17-May-21 | 17-May-21 | 17-May-21 |  |  |  | 0
637475 | MAPLE VALLEY PH1 - SUBD RES EDS | 800 - Mavis | 150652 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637485 | 30 ELM DRIVE - SOLMAR DEVT - BUILDING B | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mandic, Goran | Garcha, Tirath | 15-Nov-21 |  |  | 100925.47 | 61111.82 | 100925.47 | 100925.47 | Peter Costantini |  | 17-Mar-22 | 15-Aug-23 | 14-Feb-22 | 19-May-22 |  | Customer | Customer |  | 0
637493 | BRIGHTWATER DEVELOPMENT PHASE 1 | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637494 | PROPOSED HOTEL - 6916 DIXIE RD. | 800 - Mavis | 150384 | Active | 91 | TEMP |  |  | 2023 | Mustachi, Randy | Huo, Lisa | 22-Apr-22 |  |  | 164240.38 | 119040.35 | 164240.38 | 164240.38 | Peter Costantini | Somervl | 03-Jun-22 | 04-Aug-23 | 16-May-22 | 04-May-22 |  |  | Customer |  | 0
637521 | MONTEVIDEO & TREVISO PH2 CABLE REPLACEMENT | 800 - Mavis | 150495 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637507 | 400 AMBASSADOR DR. - MISS - UP - 3PH 1000KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Roy, Akash | 30-Aug-21 |  |  | 80972.21 | 87671.75 | 80972.21 | 80972.21 | Peter Costantini | Somervl | 28-Oct-21 | 22-Nov-22 | 27-Sep-21 | 04-Oct-21 | 02-Dec-21 | Locates | Customer |  | 0
637539 | PLATINUM DR. DEVELOPMENT - 3503 ODYSSEY DR. BLDG H | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Huo, Lisa | 08-Nov-21 |  |  | 103250.16 | 86954.02 | 103250.16 | 103250.16 | Peter Costantini | Somervl | 18-Jan-22 | 22-Nov-22 | 20-Dec-21 | 18-Nov-21 | 04-Feb-22 | Customer | Customer |  | 0
637540 | PLATINUM DR. DEVELOPMENT - 3460 PLATINUM DR. BLDG B | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Huo, Lisa | 08-Nov-21 |  |  | 212060.67 | 214669.36 | 212060.67 | 212060.67 | Peter Costantini | Somervl | 28-Jan-22 | 22-Nov-22 | 20-Dec-21 | 18-Nov-21 | 08-Feb-22 | Customer | Customer |  | 0
637541 | PLATINUM DR. DEVELOPMENT - 3545 ODYSSEY DR. BLDG I | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 01-Nov-21
637578 | 28 ANN ST | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 13-Jan-23 |  |  | 188623.01 | 167197.81 | 188623.01 | 188623.01 | Peter Costantini | Somervl | 13-Apr-23 | 02-Aug-23 | 01-Mar-23 | 01-Mar-23 |  |  |  |  | 0
637643 | 3073 MERRITT AVE - HABITAT FOR HUMANITY | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2021 | Penner, Mitchell | Ricci, Leonardo | 12-Feb-21 |  |  | 88838.41 | 86023.74 | 88838.41 | 88838.41 | Mark Bobanovic | Transpw | 12-Mar-21 | 12-Nov-21 | 01-Mar-21 | 08-Mar-21 | 19-Mar-21 | Customer | Customer |  | 0
637850 | JOINT USE PERMIT HM2020-032 - DUNDAS WEST - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 20-May-21 |  |  | 10050.86 | 15913.24 | 10050.86 | 10050.86 | Macdougall, Stephen |  | 23-Jun-21 | 31-Aug-22 | 22-Jun-21 | 17-Jun-21 | 17-Jun-21 |  |  |  | 0
637851 | JOINT USE PERMIT HM2020-033 - DUNDAS WEST - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 21-May-21 |  |  | 7239.5 | 9336.32 | 7239.5 | 7239.5 | Macdougall, Stephen |  | 24-Jun-21 | 22-Aug-22 | 24-Jun-21 | 18-Jun-21 | 18-Jun-21 |  |  |  | 0
637882 | 6150 KENNEDY RD. SERVICE UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 17-Nov-21 |  |  | 84543.66 | 13435.11 | 84543.66 | 84543.66 | Peter Costantini |  | 17-Jan-22 | 22-Nov-22 | 04-Jan-22 | 01-Dec-21 | 18-Dec-21 |  |  |  | 0
637892 | SAWMILL VALLEY DR -L6262 TO S140075 UG CABLE REPLACEMENT | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637966 | SWITCHGEAR - PUSH ROD | 800 - Mavis | 151091 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
637615 | CUSTOMER INITIATED SEC. OH REMOVAL& UG INSTALLATION – 28 ANN ST(WESTPORT CONDO) | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Gonzales, Leonard | 16-Aug-21 |  |  | 172324.23 | 111823.01 | 172324.23 | 172324.23 | Paul Murphy | Somervl | 01-Nov-21 | 22-Feb-23 | 27-Sep-21 | 01-Sep-21 | 24-Jan-22 | Customer | Customer |  | 0
635713 | OLD CREDITVIEW ROAD AND CREDITVIEW ROAD POLE RELOCATIONS - REGION OF PEEL | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 26-Aug-21 |  |  | 338890.68 | 328872.29 | 308483.68 | 338890.68 | Mark Bobanovic | K-Line | 08-Oct-21 | 10-May-23 | 27-Sep-21 | 12-Oct-21 | 26-Nov-21 | Contractor | Contractor |  | 30,407.00
634154 | BARBER HOUSE DEVELOPMENT | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Ricci, Leonardo | 16-Jun-21 |  |  | 253369.25 | 228836.43 | 253369.25 | 253369.25 | Antonio Mina | Transpw | 16-Jul-21 | 23-Mar-23 | 28-Jun-21 | 06-Jul-21 | 11-Oct-21 | MC/PUCC Permit | MC/PUCC Permit |  | 0
633868 | 2020 POLE REPLACEMENT BATCH 5 - 17 POLES | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
633867 | 2020 POLE REPLACEMENT BATCH 4 - 12 POLES | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
633866 | 2020 POLE REPLACEMENT BATCH 3 - 13 POLES | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
633864 | 2020 POLE REPLACEMENT BATCH 1 - 13 POLES | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
633795 | OH TRANSFORMER REPLACEMENTS - PART 3 | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
633250 | 1075 CLARKSON RD N - PCB TRANSFORMER REPLACEMENT | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
638016 | POLE RELOCATION SHELL GAS STATION AIRPORT ROAD & BRESLER DRIVE | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 01-Nov-21 |  |  | 181738.39 | 178769.72 | 181738.39 | 181738.39 | Paul Murphy |  | 01-Feb-22 | 13-Oct-22 | 03-Jan-22 | 30-Aug-21 | 05-Dec-22 |  | Customer |  | 0
638130 | 1063 DOUGLAS MCCURDY COMMON | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mustachi, Randy | Gonzales, Leonard | 05-Jul-22 |  |  | 266503.47 | 159104.25 | 266503.47 | 266503.47 | Peter Costantini | Somervl | 17-Oct-22 | 26-Jul-23 | 06-Sep-22 | 06-Jul-22 | 27-Sep-22 |  |  |  | 0
638134 | 97-101 CITY CENTRE DRIVE | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
638193 | 1-15 TRANSFORMER REPLACEMENT - TX7823, TX128054, TX60921, TX60139, TX60216 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 21-Dec-20 |  |  | 130594.11 | 140725.38 | 130594.11 | 130594.11 | Glenn Guile |  | 04-Feb-21 | 09-Aug-22 | 04-Jan-21 | 16-Feb-21 | 23-Mar-21 | Filler | Filler |  | 0
638211 | POLE REPLACEMENTS - HENDERIX CABLES ON DIXIE RD | 800 - Mavis | 151063 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) |  |  |  | 130131.26 | 0 | 130131.26 | 130131.26 | XMoinuddin, Saad |  |  | 20-Jul-20 | [6 empty] | 0
638216 | ODYSSEY DRIVE - PHASE 3 (BUILDING J) | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 01-Nov-21
638215 | ODYSSEY DRIVE - PHASE 3 (BUILDING J & K) | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Huo, Lisa | 08-Oct-21 | 2 |  | 240707 | 233368.8 | 240707 | 240707 | Peter Costantini | Somervl | 21-Jan-22 | 22-Nov-22 | 15-Nov-21 | 18-Oct-21 | 16-Jun-22 |  | Customer |  | 0
638220 | HULRT TPSS10 - BRITANNIA RD E - MISS - NS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
638242 | 300 STATESMAN DR - MISS - UP - 3PH - 1500KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Roy, Akash | 08-Apr-21 |  |  | 45141.35 | 43892.95 | 45141.35 | 45141.35 | Peter Costantini |  | 23-Apr-21 | 18-Nov-21 | 16-Apr-21 | 24-Apr-21 | 24-Apr-21 | Customer | Customer |  | 0
638325 | (SG1155) REPLACEMENT - 5380 TERRY FOX WAY | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 30-Dec-20 |  |  | 165539.32 | 188697.37 | 165539.32 | 165539.32 | Manoj Rao Manjunath | Ainswth | 18-May-21 | 12-Apr-22 | 19-Apr-21 | 01-Dec-21 | 31-Dec-21 | Filler | Filler |  | 0
638330 | 6707 GOREWAY DR - MISS - UP - 3PH - 2000KVA | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Mandic, Goran | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
638334 | GALLOPING CONDUCTORS- INTERPHASE SPACERS | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Matai, Ihssan (Sam) | 29-Jan-21 |  |  | 219565.96 | 99317.23 | 219565.96 | 219565.96 | Paul Murphy |  | 31-Aug-21 | 08-Jun-22 | 24-May-21 | 14-Jun-21 | 30-Sep-21 | Filler | Filler |  | 0
638339 | (SG1683) REPLACEMENT - 4105 CREDIT POINTE DR. | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 30-Dec-20 |  |  | 92438.98 | 100503.68 | 92438.98 | 92438.98 | Antonio Mina |  | 17-May-21 | 12-Apr-22 | 03-May-21 | 28-Jun-21 | 16-Jul-21 | Filler | Filler |  | 0
638338 | (SG1588) REPLACEMENT - 1060 WHITE CLOVER WAY | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 22-Jan-21 |  |  | 93038.9 | 111693.46 | 93038.9 | 93038.9 | Manoj Rao Manjunath | Ainswth | 03-May-21 | 12-Apr-22 | 19-Apr-21 | 01-Dec-21 | 31-Dec-21 | Filler | Filler |  | 0
638337 | (SG1483) REPLACEMENT - WILLOWDALE GDNS & WILLOWDALE CRT | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 30-Dec-20 |  |  | 92421.91 | 104393.8 | 92421.91 | 92421.91 | Antonio Mina |  | 10-May-21 | 12-Apr-22 | 26-Apr-21 | 10-Sep-21 | 22-Oct-21 | Filler | Filler |  | 0
638336 | (SG1205) REPLACEMENT - 320 NAHANI WAY (EASTGATE PKWY) | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 30-Dec-20 |  |  | 88736.26 | 165848.97 | 88736.26 | 88736.26 | Manoj Rao Manjunath | Ainswth | 27-May-21 | 12-Apr-22 | 17-May-21 | 26-Nov-21 | 26-Nov-21 | Lines | Lines |  | 0
430625 | SHAWSON M.S. CABLE REPLACEMENT | 800 - Mavis | 150699 | Inactive | 99 | COMPLETE |  |  | 2021 | Houston, Andrew | Zaghloul, Sam | 26-Oct-20 |  |  | 570102.24 | 742170.1 | 570102.24 | 570102.24 | Glenn Guile | Somervl | 16-Dec-20 | 14-Oct-21 | 02-Nov-20 | 05-Nov-20 | 22-Jan-21 | Locates | COVID19 |  | 0
638363 | 16-30 TRANSFORMER REPLACEMENT - TX20539 TO TX19470 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 21-Dec-20 |  |  | 156733.19 | 160908.46 | 156733.19 | 156733.19 | Glenn Guile |  | 25-Feb-21 | 20-Jul-22 | 18-Jan-21 | 20-May-21 | 13-Dec-21 | Lines | Customer |  | 0
638406 | 31-45 TRANSFORMER REPLACEMENT - TX13497 TO TX18421 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 21-Dec-20 |  |  | 140590.72 | 158638.4 | 140590.72 | 140590.72 | Peter Costantini |  | 10-Mar-21 | 25-Apr-22 | 15-Feb-21 | 14-Jan-21 | 13-Apr-21 |  |  |  | 0
638418 | 202 BURNHAMTHORPE - MISS - NS - 3PH - NS00074364 | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 16-Dec-22 |  |  | 162686.2 | 28292.22 | 162686.2 | 162686.2 | Peter Costantini | Somervl | 13-Feb-23 | 10-Aug-23 | 23-Jan-23 | 23-Jan-23 |  |  |  |  | 0
638462 | 151 CITY CENTRE DRIVE- TEMPORARY SERVICE-ICI | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 18-Jan-21 |  |  | 94649.93 | 49011.4 | 94649.93 | 94649.93 | Peter Costantini |  | 11-Mar-21 | 17-Oct-22 | 16-Feb-21 | 22-Jan-21 | 04-Feb-21 |  |  |  | 0
638515 | JOINT USE PERMIT HM2020-042 - MISSISSAUGA - MISS | 800 - Mavis | 151537 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
638554 | SWGR REPLACEMENT-SG1571, 205 ANNAGEM BVLD | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 30-Dec-20 |  |  | 102857.51 | 38040.33 | 102857.51 | 102857.51 | Manoj Rao Manjunath | Ainswth | 19-May-21 | 22-Sep-22 | 03-May-21 | 26-Nov-21 | 26-Nov-21 | Lines | Lines |  | 0
638558 | SWGR REPLACEMENT-SG1214, 3111 CONVAIR DR | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 31-Jan-21 |  |  | 133833.41 | 3194.29 | 133833.41 | 133833.41 | Glenn Guile |  | 11-May-21 | 22-Sep-22 | 26-Apr-21 | 27-Sep-21 | 27-Sep-21 | Customer | Customer |  | 0
638556 | SWGR REPLACEMENT-SG1503, RIVER GROVE & HIGHBROOK | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 30-Dec-20 |  |  | 102862.37 | 91397.09 | 102862.37 | 102862.37 | Glenn Guile |  | 16-Apr-21 | 09-Aug-22 | 29-Mar-21 | 10-Mar-21 | 30-Mar-21 |  |  |  | 0
638555 | SWGR REPLACEMENT-SG1460, 5750 RIVER GROVE | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 30-Dec-20 |  |  | 102862.37 | 97954.14 | 102862.37 | 102862.37 | Glenn Guile |  | 09-Apr-21 | 09-Aug-22 | 29-Mar-21 | 30-Mar-21 | 09-Apr-21 | Filler | Filler |  | 0
638559 | SWGR REPLACEMENT-SG1800, 5482 MIDDLEBURY DR | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 30-Dec-20 |  |  | 50893.73 | 42082.79 | 50893.73 | 50893.73 | Manoj Rao Manjunath | Ainswth | 08-Mar-21 | 09-Aug-22 | 22-Feb-21 | 01-Dec-21 | 31-Dec-21 | Filler | Filler |  | 0
638647 | 70 MISSISSAUGA ROAD SOUTH | 800 - Mavis | 150384 | Active | 82 | Upload Completed |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 151242.81 | 5771.51 | 151242.81 | 151242.81 | XMoinuddin, Saad |  |  | 26-Jul-23 | [6 empty] | 0
638646 | 46-60 TRANSFORMER REPLACEMENT - TX8081 TO TX12421 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 21-Dec-20 |  |  | 203357.11 | 197371.71 | 203357.11 | 203357.11 | Paul Tremblay |  | 23-Apr-21 | 25-Apr-22 | 15-Mar-21 | 15-Mar-21 | 22-Apr-21 |  |  |  | 0
638650 | 759 WINSTON CHURCHILL BLVD | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 04-Jan-23 |  |  | 81204.32 | 36389.69 | 81204.32 | 81204.32 | Gregory Dunfield |  | 06-Feb-23 | 01-Aug-23 | 23-Jan-23 | 06-Feb-23 |  | Customer | Customer |  | 0
638654 | 61-75 - TRANSFORMER REPLACEMENT - TX12904 TO TX11295 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 30-Dec-20 |  |  | 123367.53 | 121724.05 | 123367.53 | 123367.53 | Glenn Guile |  | 01-Apr-21 | 25-Apr-22 | 01-Mar-21 | 18-Feb-21 | 08-Mar-21 |  |  |  | 0
638656 | 76-90 - TRANSFORMER REPLACEMENT - TX11298 TO TX10708 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 27-Jan-21 |  |  | 161163.52 | 173866.67 | 161163.52 | 161163.52 | Peter Costantini |  | 23-Apr-21 | 15-Sep-22 | 08-Mar-21 | 19-Feb-21 | 07-Dec-21 |  | Filler |  | 0
638657 | 91-105 - TRANSFORMER REPLACEMENT - TX10717 TO TX10568 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 02-Feb-21 |  |  | 152671.48 | 133744.51 | 152671.48 | 152671.48 | Glenn Guile |  | 14-May-21 | 25-Apr-22 | 01-Apr-21 | 17-May-21 | 22-Jun-21 | Lines | Filler |  | 0
638661 | 121-127 - TRANSFORMER REPLACEMENT - TX8385 TO TX4343 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Ferry, Rodnne | 12-Feb-21 | 7 | 7 | 69355.86 | 101797.5 | 69355.86 | 69355.86 | Peter Costantini |  | 29-Mar-21 | 07-Oct-22 | 15-Mar-21 | 16-Mar-21 | 29-Dec-21 | Filler | Filler |  | 0
638659 | 106-120 - TRANSFORMER REPLACEMENT - TX5733 TO TX8967 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Ferry, Rodnne | 26-Jan-21 |  |  | 152428.33 | 127481.01 | 152428.33 | 152428.33 | Paul Tremblay |  | 10-May-21 | 25-Apr-22 | 01-Apr-21 | 26-Apr-21 | 31-May-21 | Filler | Filler |  | 0
638693 | GALLOPING CONDUCTORS- INTERPHASE SPACERS-BATCH 2 | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) | 26-Feb-21 |  |  | 193565.66 | 89745.65 | 193565.66 | 193565.66 | Paul Murphy |  | 23-Mar-22 | 02-Mar-23 | 03-Jan-22 | 22-Feb-22 | 21-Oct-22 | Filler | Filler |  | 0
638713 | EXPANSION - 185 ENFIELD PLACE - GREAT WEST LIFE ENFIELD CONDOMINIUMS | 800 - Mavis | 152302 | Active | 82 | RELEASED |  |  | 2023 | Lacombe, Joel | Garcha, Tirath | 05-Jul-22 |  |  | 1057440.82 | 510154.41 | 1057440.82 | 1057440.82 | Peter Costantini | Somervl | 12-May-23 | 27-Sep-23 | 01-Feb-23 | [5 empty] | 0
638718 | 6950 KENNEDY RD - MISS - NS - 3PH - 500KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Roy, Akash | 08-Apr-21 |  |  | 82398.86 | 75691.81 | 82398.86 | 82398.86 | Peter Costantini | Somervl | 04-Jun-21 | 22-Nov-22 | 10-May-21 | 23-Aug-21 | 11-Oct-21 | Customer | Customer |  | 0
638728 | 1517 BALLYCLARE DR-TX RELOCATE | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 22-Feb-21 |  |  | 53226.43 | 24933.27 | 53226.43 | 53226.43 | Glenn Guile | Somervl | 20-May-21 | 28-Mar-22 | 10-May-21 | 26-Apr-21 | 28-Apr-21 |  |  |  | 0
638758 | RESIDENTIAL STACKED TOWNHOUSES AT 2020-2046 CAMILLA RD. | 800 - Mavis | 150384 | Active | HO | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 12-Jul-22 |  |  | 133647 | 51258 | 133647 | 133647 | Peter Costantini | Somervl | 13-Jul-22 | 11-Aug-23 | 13-Jun-22 | 02-Aug-22 |  | Customer |  |  | 0
638775 | JOINT USE PERMIT HM2020-047 - KANE AND MISSISSAUGA - MISS | 800 - Mavis | 151537 | Active | HL | H8 |  |  | 2023 | O'Gay, Brian | Johnson, William | 02-Mar-21 |  |  | 12392.97 | 6997.5 | 12392.97 | 12392.97 | XMoinuddin, Saad |  | 19-Apr-21 | 27-Jul-23 | 16-Apr-21 |  |  | N/A | N/A |  | 0
638852 | 1150 EGLINTON AVE E - MISS - UP - 1200A UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 01-Sep-22
638872 | 2020 ROGERS BONDS 2 - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 01-Jan-21 |  |  | 2484.93 | 3105.24 | 2484.93 | 2484.93 | Macdougall, Stephen |  | 19-Apr-21 | 28-Mar-22 | 19-Apr-21 | 23-Apr-21 | 23-Apr-21 | Lines | Lines |  | 0
638880 | OH SWITCH RENEWAL BATCH 1 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 27-Jan-21 |  |  | 97203.56 | 99556.08 | 97203.56 | 97203.56 | Paul Murphy |  | 22-Apr-21 | 25-Apr-22 | 22-Mar-21 | 29-Apr-21 | 14-May-21 | Lines | Filler |  | 0
638884 | OH SWITCH RENEWAL BATCH 5 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 28-Dec-20 |  |  | 28160.12 | 22379.37 | 28160.12 | 28160.12 | Macdougall, Stephen |  | 16-Apr-21 | 25-Apr-22 | 05-Apr-21 | 09-Feb-21 | 11-Mar-21 |  |  |  | 0
638883 | OH SWITCH RENEWAL BATCH 4 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 28-Dec-20 |  |  | 61770.35 | 20041.2 | 61770.35 | 61770.35 | Macdougall, Stephen |  | 04-Mar-21 | 17-May-22 | 08-Feb-21 | 13-Jan-21 | 25-Jan-21 |  |  |  | 0
638882 | OH SWITCH RENEWAL BATCH 3 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 31-Dec-20 |  |  | 50075.52 | 37177.13 | 50075.52 | 50075.52 | Macdougall, Stephen |  | 10-Feb-21 | 25-Apr-22 | 25-Jan-21 | 19-Jan-21 | 10-Apr-21 | Filler | Filler |  | 0
638881 | OH SWITCH RENEWAL BATCH 2 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 22-Feb-21 |  |  | 125919.4 | 176064.6 | 125919.4 | 125919.4 | Paul Murphy |  | 26-Apr-21 | 25-Apr-22 | 22-Mar-21 | 17-May-21 | 06-Jul-21 | Filler | Filler |  | 0
429894 | 2340 & 2370 Meadowvale Blvd - BEEDIE PROPOSED WAREHOUSE FACILITY | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 10-Nov-20 |  |  | 195770.7 | 180161.21 | 195770.7 | 195770.7 | Peter Costantini | Somervl | 19-Jan-21 | 22-Sep-22 | 07-Dec-20 | 12-Nov-20 | 05-Jan-21 |  |  |  | 0
638894 | POLE REPLACEMENT (2021) - BATCH #1 | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) | 06-Jan-21 | 9 | 8 | 201500.26 | 126129.33 | 201500.26 | 201500.26 | Paul Murphy |  | 10-Jun-22 | 02-Mar-23 | 02-May-22 | 24-Feb-21 | 29-Apr-22 | Filler | Filler |  | 0
638896 | GALLOPING CONDUCTORS- INTERPHASE SPACERS - BATCH 4 | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) | 26-Feb-21 |  |  | 136686.56 | 108087.48 | 136686.56 | 136686.56 | Matthew Beach |  | 17-Feb-22 | 02-Mar-23 | 03-Jan-22 | 02-Feb-22 | 24-Nov-22 | Materials | Materials |  | 0
638895 | GALLOPING CONDUCTORS- INTERPHASE SPACERS-BATCH 3 | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Matai, Ihssan (Sam) | 29-Jan-21 |  |  | 137000.86 | 40370.12 | 137000.86 | 137000.86 | Rob Elliot |  | 20-Apr-21 | 08-Jun-22 | 08-Mar-21 | 24-Mar-21 | 19-Aug-21 | Filler | Filler |  | 0
638932 | 2023 POLE - 19 WP - ALEXANDRA AVE OH MINI REBUILD | 800 - Mavis | 151063 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 10-Nov-22 | 19 | 19 | 478899.34 | 281239.42 | 452689.9 | 478899.34 | Paul Murphy |  | 09-May-23 | 26-Jul-23 | 16-Jan-23 | 03-Feb-23 | 14-Apr-23 |  |  |  | 26,209.44
638961 | 759 WINSTON CHURCHILL BLVD BUILDING 1 - MISS - NS - 3PH - 1000KVA | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mandic, Goran | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
638962 | 759 WINSTON CHURCHILL BLVD BUILDING 2 - MISS - NS - 3PH - 1000KVA | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 17-Apr-23 |  |  | 282909.53 | 12513.44 | 282909.53 | 282909.53 | Peter Costantini | Somervl | 29-Dec-23 | 29-Dec-23 | 01-Aug-23 | [5 empty] | 0
638989 | (SG1036) REPLACEMENT - 4314 FOREST FIRE LN., 1 | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 30-Dec-20 |  |  | 165738.6 | 181674.78 | 165738.6 | 165738.6 | Antonio Mina |  | 18-May-21 | 12-Apr-22 | 19-Apr-21 | 06-Jul-21 | 19-Nov-21 | Filler | Filler |  | 0
638988 | (SG1035) REPLACEMENT - 4314 FOREST FIRE LN., 1 | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE | High | DA | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 22-Feb-21 |  |  | 166411.82 | 185826.53 | 166411.82 | 166411.82 | Antonio Mina |  | 27-May-21 | 10-May-22 | 26-Apr-21 | 06-Jul-21 | 13-Dec-21 | Filler | Weather |  | 0
638991 | (YS64544) REPLACEMENT - HURONTARIO & HWY 403 | 800 - Mavis | 151092 | Active | 70 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
639070 | MONTEVIDEO & TREVISO PH2 UG CABLE REPLACEMENT | 800 - Mavis | 151402 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Tempra, Troylan | 31-May-21 |  |  | 2120242.9 | 1942132.52 | 2120242.9 | 2120242.9 | Antonio Mina | Transpw | 23-Dec-21 | 22-Sep-22 | 13-Jul-21 | 05-Jul-21 | 27-Sep-21 |  |  |  | 0
639072 | 7300 WEST CREDIT - MISS - NS - 300KVA | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Mandic, Goran | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
639282 | POLE REPLACEMENT (2021) - BATCH #2 | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Matai, Ihssan (Sam) | 26-Feb-21 | 4 |  | 69817.9 | 60668.11 | 69817.9 | 69817.9 | Rob Elliot |  | 16-Jul-21 | 14-Jun-22 | 02-Jul-21 | 16-Jul-21 | 11-Aug-21 | Filler | Filler |  | 0
639316 | RFC#1 FOR "633865" 2020 POLE REPLACEMENT BATCH 2 - 12 POLES | 800 - Mavis | 151063 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
639357 | 190 MATHESON BLVD | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 123397.01 | 4000.38 | 123397.01 | 123397.01 | XMoinuddin, Saad |  |  | 22-Sep-22 | [6 empty] | 0
639370 | 18 CP - QUEENSWAY W OH REBUILD, (FROM DAMIEN WAY TO PINENEEDLE ROW) | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 11-Jul-22 | 18 | 18 | 626398.62 | 698342.07 | 527284.47 | 626398.62 | Mark Bobanovic | K-Line | 10-Feb-23 | 22-Jun-23 | 22-Sep-22 | 19-Sep-22 | 22-Dec-22 | Lines |  |  | 99,114.15
639389 | 7300 WEST CREDIT - MISS - NS - 150KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
639424 | 2104 LAUGHTON AVE - RELOCATE SERVICE DROP | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 21-Jan-21 |  |  | 15407.36 | 14194.7 | 15407.36 | 15407.36 | Macdougall, Stephen |  | 25-Feb-21 | 28-Mar-22 | 23-Feb-21 | 25-Feb-21 | 25-Feb-21 | N/A |  |  | 0
639443 | SWGR REPLACEMENT - SG1445 LAIRD RD & THE COLLEGEWAY | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Tempra, Troylan | 18-Mar-21 |  |  | 157204.94 | 164890.84 | 157204.94 | 157204.94 | Antonio Mina |  | 12-Aug-21 | 26-Aug-22 | 13-Jul-21 | 07-Jul-21 | 13-Dec-21 | Filler | Filler |  | 0
639445 | SWGR REPLACEMENT-SG1504, ACROSS 3067 TACC DR | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 01-Apr-21 |  |  | 49229.15 | 35685.58 | 49229.15 | 49229.15 | Manoj Rao Manjunath | Ainswth | 11-Aug-21 | 09-Aug-22 | 02-Aug-21 | 01-Dec-21 | 31-Dec-21 | Filler | Filler |  | 0
639473 | MONTEVIDEO & TREVISO UG CABLE REPLACEMENT PH3 | 800 - Mavis | 151402 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Tempra, Troylan | 28-Jan-22 |  |  | 1916648.33 | 1863184.77 | 1908114.67 | 1916648.33 | Antonio Mina | Transpw | 11-Aug-22 | 23-Mar-23 | 11-Apr-22 | 19-Apr-22 | 28-Oct-22 | Contractor | Contractor |  | 8,533.66
639551 | 6CP - 2022 POLE RENEWAL - QEW-NORTH SHERIDAN WAY MINI OH REBUILD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Tempra, Troylan | 07-Dec-21 | 6 |  | 287775.65 | 495823.47 | 287775.65 | 287775.65 | Paul Murphy |  | 12-Jul-22 | 02-Mar-23 | 16-May-22 | 30-Jun-22 | 07-Nov-22 | Lines | Lines |  | 0
639554 | 4 POLE - 2021 POLE RENEWAL - BIRCHWOOD & JALNA AREA - 3 | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Tempra, Troylan | 27-May-21 | 4 | 4 | 62722.81 | 61095.96 | 62722.81 | 62722.81 | Gregory Dunfield |  | 05-Nov-21 | 22-Sep-22 | 25-Oct-21 | 10-Dec-21 | 17-Mar-22 | Locates | Locates |  | 0
639555 | 1500 GULLEDEN - MISS - NS - 3PH - 1500KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Roy, Akash | 29-Mar-22 |  |  | 127824.02 | 76795.43 | 127824.02 | 127824.02 | Peter Costantini | Somervl | 15-Jul-22 | 22-Nov-22 | 13-Jun-22 | 31-Aug-22 | 03-Oct-22 | Customer | Customer |  | 0
639723 | 6933 TOMKEN RD - MISS - NS - 3PH - 1000KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Roy, Akash | 17-Mar-22 |  |  | 149234.9 | 90150.69 | 149234.9 | 149234.9 | Peter Costantini | Somervl | 20-May-22 | 22-Nov-22 | 11-Apr-22 | 11-Apr-22 | 09-May-22 |  |  |  | 0
639724 | 60 BRISTOL BOARD E. - SANDALWOOD SQUARE | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
639732 | 7 QTY - SPOT POLE REPLACEMENT BATCH 4 - MISSISSAUGA AND KANE - 0 | 800 - Mavis | 151063 | Active | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 24-Jun-21 | 7 | 7 | 156178.92 | 145284.17 | 156178.92 | 156178.92 | Rob Elliot | B&M | 30-Nov-21 | 26-Jul-23 | 11-Oct-21 | 19-Nov-21 | 06-Apr-22 | Lines | MC/PUCC Permit |  | 0
639731 | 12 QTY - SPOT POLE REPLACEMENT BATCH 3 - MISSISSAUGA AND KANE | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 24-Jun-21 | 12 | 12 | 429791.79 | 444955.37 | 429791.79 | 429791.79 | Paul Murphy | Ainswth | 09-Mar-22 | 28-May-23 | 08-Feb-22 | 14-Dec-21 | 14-Oct-22 |  | Lines |  | 0
639733 | SECOND LINE W OH MINI REBUILD - OLD DERRY RD TO SILVERTHORN MILL AVE | 800 - Mavis | 151063 | Active | 93 | ANALYZE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 15-Dec-21 | 20 | 20 | 560477.08 | 503861.06 | 560477.08 | 560477.08 | Mark Bobanovic | Ainswth | 27-Oct-22 | 16-Feb-24 | 04-Apr-22 | 14-Nov-22 | 21-Dec-22 | Lines | Lines |  | 0
639736 | OH REBUILD - MEREDITH AVE PH2 | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Matai, Ihssan (Sam) | 25-Aug-21 | 15 |  | 234054.95 | 248164.47 | 214312.66 | 234054.95 | Mark Bobanovic | K-Line | 18-Oct-21 | 08-May-23 | 04-Oct-21 | 12-Oct-21 | 18-Nov-21 | Contractor | Contractor |  | 19,742.29
639734 | 18 CP - OH REBUILD - OGDEN AVE PHASE 1 | 800 - Mavis | 151063 | Active | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 04-Feb-22 | 18 | 18 | 489349.82 | 564943.51 | 468802.35 | 489349.82 | Mark Bobanovic | K-Line | 06-Oct-22 | 26-Jul-23 | 06-Jun-22 | 25-Jul-22 | 16-Sep-22 | Lines |  |  | 20,547.47
639740 | CITY PARK (DIXIE) INC - 2116 DIXIE RD | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Ricci, Leonardo | 07-Sep-22 |  |  | 352344.01 | 345927.47 | 352344.01 | 352344.01 | Antonio Mina | Transpw | 13-Dec-22 | 13-Dec-22 | 01-Dec-22 | 31-Oct-22 | 22-Nov-22 |  |  |  | 0
639742 | 920 FOURTH STREET - POLE RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 07-Apr-21 |  |  | 94737.62 | 82227.97 | 94737.62 | 94737.62 | Rob Elliot |  | 09-Jun-21 | 13-Sep-22 | 10-May-21 | 31-May-21 | 17-Sep-21 | MC/PUCC Permit | MC/PUCC Permit |  | 0
639741 | CITY PARK MAIN ST INC - SUBD RES EDS | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
639769 | JOINT USE PERMIT HM2020-059 - SOUTHDOWN - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 17-Feb-21 |  |  | 7522.13 | 3721.71 | 7522.13 | 7522.13 | Macdougall, Stephen |  | 21-Apr-21 | 28-Mar-22 | 20-Apr-21 | 23-Apr-21 | 23-Apr-21 |  |  |  | 0
639782 | MARINA PARK & MEMORIAL PARK WEST CITY WORKS | 800 - Mavis | 150673 | Active | 92 | ANALYZE |  |  | 2023 | Watters, Maxwell | Watters, Maxwell | 06-Sep-22 |  |  | 313280.58 | 294267.42 | 313280.58 | 313280.58 | Paul Murphy | Somervl | 15-Dec-22 | 26-Jul-23 | 24-Oct-22 | 12-Dec-22 | 22-Mar-23 | Locates | Locates |  | 0
639783 | BLOCK 8, 448 BURNHAMTHORPE ROAD WEST | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
639839 | 6110 CANTAY ROAD L5R 3W5 | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 27-May-21 |  |  | 88362.56 | 85322.36 | 88362.56 | 88362.56 | Peter Costantini |  | 09-Jul-21 | 12-Nov-21 | 30-Jun-21 | 03-Jun-21 | 05-Jun-21 |  |  |  | 0
639843 | 4130 PARKSIDE VILLAGE BLOCK 1E | 800 - Mavis | 150384 | Active | 93 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo | 22-Apr-22 |  |  | 373228.58 | 310288.56 | 373228.58 | 373228.58 | Antonio Mina |  | 03-Oct-22 | 26-Jul-23 | 02-Aug-22 | 16-Jan-23 | 14-Mar-23 | Customer | Customer |  | 0
639846 | 430 SQUARE ONE DRIVE & 4130 PARKSIDE VILLAGE | 800 - Mavis | 150384 | Active | 93 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo | 22-Apr-22 |  |  | 491836.31 | 245887.2 | 491836.31 | 491836.31 | Antonio Mina |  | 03-Oct-22 | 26-Jul-23 | 02-Aug-22 | 12-Jan-23 | 07-Mar-23 | Customer | Customer |  | 0
639847 | 1035 SOUTHDOWN ROAD (CONDO UNITS) | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
639868 | 2445 LUCKNOW DR - MISS - UP - 3PH - 1000KVA | 800 - Mavis | 150384 | Active | 95 | ANALYZE |  |  | 2022 | Mandic, Goran | Roy, Akash | 12-Oct-22 |  |  | 133833.44 | 113703.23 | 133833.44 | 133833.44 | Peter Costantini | Somervl | 16-Nov-22 | 26-Jul-23 | 31-Oct-22 | 07-Nov-22 | 01-Dec-22 | Customer | Customer |  | 0
639952 | (SUB-TX) REPLACEMENTS - LENEL CRT | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 22-Feb-21 |  |  | 67752.32 | 80364.16 | 67752.32 | 67752.32 | Glenn Guile |  | 30-Jun-21 | 12-Apr-22 | 16-Jun-21 | 29-Mar-21 | 15-Apr-21 |  |  |  | 0
639951 | (SUB-TX) REPLACEMENTS - TYANDAGA CRT | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Cudzilo, Tomasz | 22-Feb-21 |  |  | 58609.28 | 31686.18 | 58609.28 | 58609.28 | Glenn Guile |  | 15-Jun-21 | 12-Apr-22 | 01-Jun-21 | 30-Apr-21 | 09-Aug-21 | Filler | Filler |  | 0
639950 | 2023 TX (2 X SUB-TX) REPLACEMENTS - BRANT AVE | 800 - Mavis | 151043 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 17-Jan-23 | 2 | 2 | 165082.11 | 171825.85 | 165082.11 | 165082.11 | Glenn Guile | Somervl | 20-Jul-23 | 10-Aug-23 | 04-Jul-23 | 06-Jul-23 | 06-Jul-23 |  |  |  | 0
640106 | 2021 SWGR RENEWAL-SG1433 AT 6550 BATTLEFORD RD | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 09-Feb-21 |  |  | 44621.84 | 43870.8 | 44621.84 | 44621.84 | Manoj Rao Manjunath | Ainswth | 09-Jul-21 | 18-May-22 | 28-Jun-21 | 26-Nov-21 | 26-Nov-21 | Lines | Lines |  | 0
640104 | 2021 SWGR RENEWAL-SG1737 AT 385 PRINCE OF WALES | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Beaudrie, Scott | Tempra, Troylan | 10-Feb-21 |  |  | 49469.02 | 43718.11 | 49469.02 | 49469.02 | Manoj Rao Manjunath | Ainswth | 06-Dec-21 | 18-May-22 | 22-Nov-21 | 03-Dec-21 | 03-Dec-21 | Lines | Lines |  | 0
640111 | 2380 SPEAKMAN DR - 1000KVA TRANSFORMER UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Pellerin, Patrick | 25-Nov-21 |  |  | 113689.69 | 95743.17 | 113689.69 | 113689.69 | Peter Costantini |  | 04-Mar-22 | 22-Nov-22 | 28-Jan-22 | 06-Jan-22 | 28-Mar-22 |  | Customer |  | 0
640121 | OLD DERRY ROAD & GOODERHAM ESTATE BOULEVARD U/G RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 03-Jun-21 |  |  | 244115.54 | 181927.85 | 244115.54 | 244115.54 | Glenn Guile | Transpw | 15-Jul-21 | 22-Sep-22 | 05-Jul-21 | 20-Sep-21 | 08-Nov-21 | Contractor | Contractor |  | 0
640142 | ELETRICAL SERVICE UPGRADE - MARVIN HEIGHTS PS | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 30-Aug-21 |  |  | 93435.55 | 57539.93 | 93435.55 | 93435.55 | Peter Costantini | Somervl | 01-Oct-21 | 22-Nov-22 | 30-Sep-21 | 05-Aug-21 | 12-Aug-21 |  |  |  | 0
640144 | MEDICAL OFFICES | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mustachi, Randy | Huo, Lisa | 26-May-22 |  |  | 113474.9 | 84798.67 | 113474.9 | 113474.9 | Peter Costantini | Somervl | 30-Aug-22 | 26-Jul-23 | 08-Aug-22 | 24-Jun-22 | 26-Sep-22 |  |  |  | 0
640211 | INSULATORS RENEWAL - BATCH #1 | 800 - Mavis | 151727 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Matai, Ihssan (Sam) | 01-Jun-21 |  |  | 131392.46 | 75678.45 | 131392.46 | 131392.46 | Rob Elliot |  | 16-Aug-21 | 08-Jun-22 | 05-Jul-21 | 07-Jul-21 | 19-Aug-21 | Filler | Filler |  | 0
640215 | 4CP - 2022 POLE RENEWAL - MISSISSAUGA RD POLE RENEWAL | 800 - Mavis | 151063 | Active | 99 | ANALYZE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 09-Nov-21 | 4 | 4 | 196766.41 | 107129.1 | 196766.41 | 196766.41 | Matthew Beach |  | 23-Mar-23 | 30-Aug-23 | 30-Jan-23 | 24-Jan-23 | 21-Feb-23 | N/A |  |  | 0
640231 | GOREWAY & BRANDON GATE PRIMARY 1PH EXTENSION | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 04-Mar-21 |  |  | 38707.08 | 5305.39 | 38707.08 | 38707.08 | Macdougall, Stephen |  | 17-Jun-21 | 28-Mar-22 | 31-May-21 | 17-May-21 | 18-May-21 |  |  |  | 0
640239 | 3151 LENWORTH DRIVE | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo | 07-Apr-22 |  |  | 115201.73 | 81635.65 | 115201.73 | 115201.73 | Peter Costantini |  | 06-May-22 | 26-Jul-23 | 14-Apr-22 | 16-Aug-22 | 19-Aug-22 | Customer | Customer |  | 0
639848 | OMSF CUSTOMER OWNED SUB-STATION CONNECTION_MOBILINX | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Bose, Victor |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
426984 | 3465 PLATINUM DRIVE - ERIN MILLS MINUK (BUILDING J) | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 28-Jan-21 |  |  | 329610.72 | 252325.19 | 329610.72 | 329610.72 | Peter Costantini | Somervl | 20-Apr-21 | 22-Sep-22 | 01-Mar-21 | 03-Feb-21 | 23-Mar-21 |  |  |  | 0
426992 | 3525 PLATINUM DRIVE - ERIN MILLS MINUK (BUILDING K) | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 28-Jan-21 |  |  | 37108.91 | 27801.62 | 37108.91 | 37108.91 | Peter Costantini |  | 17-Mar-21 | 22-Sep-22 | 01-Mar-21 | 03-Feb-21 | 23-Mar-21 |  | Customer |  | 0
427004 | 3874 EGLINTON AVE W - ERIN MILLS MINUK (BUILDING G) | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 27-Jan-21 |  |  | 52419.98 | 43367.97 | 52419.98 | 52419.98 | Peter Costantini |  | 19-Feb-21 | 22-Sep-22 | 08-Feb-21 | 03-Feb-21 | 23-Mar-21 |  | Customer |  | 0
427012 | 3910 EGLINTON AVE W - ERIN MILLS MINUK (BUILDING D) | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 27-Jan-21 |  |  | 49449.28 | 75055.86 | 49449.28 | 49449.28 | Peter Costantini |  | 22-Feb-21 | 22-Sep-22 | 08-Feb-21 | 03-Feb-21 | 23-Mar-21 |  | Customer |  | 0
640262 | POLE RENEWAL - MINEOLA RD E EAST OF LOCHLIN TRAIL | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Tempra, Troylan | 22-Feb-21 | 5 |  | 148902.73 | 105880.23 | 148902.73 | 148902.73 | Rob Elliot |  | 15-Sep-21 | 25-Apr-22 | 29-Jul-21 | 03-Sep-21 | 28-Oct-21 | Filler | Filler |  | 0
640325 | POLE RELOCATION - THOMAS ST (P08380) | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Gonzales, Leonard | 11-Apr-22 |  |  | 76775.37 | 74421.94 | 76775.37 | 76775.37 | Rob Elliot |  | 22-Jul-22 | 22-Sep-22 | 07-Jul-22 | 20-Apr-22 | 13-May-22 |  |  |  | 0
640335 | 2180 SPEAKMAN DR - 750KVA TEMP | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Pellerin, Patrick | 07-May-21 |  |  | 170608.77 | 203648.02 | 170608.77 | 170608.77 | Peter Costantini | Somervl | 17-Jun-21 | 22-Sep-22 | 17-May-21 | 18-May-21 | 16-Jun-21 |  |  |  | 0
640477 | 6900 DIXIE ROAD - POLE RELOCATIONS | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 29-Apr-21 |  |  | 77392.4 | 78320.1 | 77392.4 | 77392.4 | Paul Murphy |  | 18-Aug-21 | 30-Mar-22 | 26-Jul-21 | 04-Oct-21 | 29-Oct-21 | Locates | Locates |  | 0
640517 | TX12121 - SHEROBEE POWER TX REMOVALS (PCB) | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Cudzilo, Tomasz | 16-May-22 | 1 | 1 | 446985.13 | 362906.73 | 446985.13 | 446985.13 | Antonio Mina |  | 25-Aug-22 | 04-Apr-23 | 11-Jul-22 | 20-Jul-22 | 26-Jul-22 | Lines |  |  | 0
640516 | TX3570 - POWER TX REMOVALS (PCB) | 800 - Mavis | 151043 | Active | 40 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
640540 | 1293 MEREDITH AVENUE - OH SYSTEM EXPANSION | 800 - Mavis | 152302 | Active | 98 | COMPLETE |  |  | 2022 | Watters, Maxwell | Watters, Maxwell | 24-Feb-22 |  |  | 228408.44 | 249208.81 | 228408.44 | 228408.44 | Paul Murphy |  | 03-Jun-22 | 26-Jul-23 | 25-Apr-22 | 17-Jun-22 | 07-Nov-22 | Customer | Customer |  | 0
640565 | 1890 ALSTEP DRIVE | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mustachi, Randy | Jacinto, Gerardo | 08-Aug-22 |  |  | 207308.57 | 198839.55 | 207308.57 | 207308.57 | Peter Costantini | Somervl | 07-Oct-22 | 26-Jul-23 | 07-Sep-22 | 18-Oct-22 | 07-Nov-22 | Locates | Locates |  | 0
640583 | 16 ELM DRIVE WEST, MISS.- NS -3PH PAD - SOLMAR DEVT - BUILDING C | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Garcha, Tirath | 11-Jan-22 |  |  | 119071.41 | 57491.76 | 119071.41 | 119071.41 | Peter Costantini | N/A | 02-May-22 | 14-Aug-23 | 01-Apr-22 | 18-May-22 |  | Customer |  |  | 0
640589 | BRIGHTWATER TOWNHOMES PH 1 - SUBD RES EDS | 800 - Mavis | 150652 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
640641 | 430 SQUARE ONE DRIVE & 4130 PARKSIDE VILLAGE UG SYSTEM EXPANSION | 800 - Mavis | 150652 | Active | 93 | ANALYZE |  |  | 2023 | Penner, Mitchell | Ricci, Leonardo | 08-Sep-22 |  |  | 843018.26 | 930237.96 | 843018.26 | 843018.26 | Antonio Mina | Transpw | 14-Feb-23 | 26-Jul-23 | 03-Jan-23 | 27-Oct-22 | 21-Mar-23 |  | Customer |  | 0
640669 | QEW & CREDIT RIVER - MISSISSAUGA & QEW CROSSING | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 26-Apr-21 |  |  | 375426.44 | 283339.02 | 375426.44 | 375426.44 | Rob Elliot | Somervl | 07-Jun-21 | 12-Nov-21 | 31-May-21 | 26-May-21 | 12-Aug-21 |  | Customer |  | 0
640673 | 2021 POLE RENEWAL - HONI ROW | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
640679 | (LT31231) REPLACEMENT - 3029 CLAYHILL RD (P6428) | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2021 | Lucic, Marko | Cudzilo, Tomasz | 04-Aug-21 |  |  | 29232.71 | 165741.39 | 29232.71 | 29232.71 | Gregory Dunfield |  | 15-Nov-21 | 22-Sep-22 | 29-Sep-21 | 27-Oct-21 | 03-Dec-21 | Lines | Control/SCADA |  | 0
640678 | (LT71027) REPLACEMENT - 6553 MISSISSAUGA RD (P19606) | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2021 | Lucic, Marko | Cudzilo, Tomasz | 25-Jun-21 |  |  | 132636.62 | 195580.81 | 132636.62 | 132636.62 | Gregory Dunfield |  | 09-Sep-21 | 18-Apr-22 | 19-Aug-21 | 19-Aug-21 | 19-Nov-21 |  | Filler |  | 0
640677 | (YS141716) REPLACEMENT - 808 BRITANNIA RD. W. (P17996) | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2021 | Lucic, Marko | Cudzilo, Tomasz | 25-Jun-21 |  |  | 109392.23 | 104579.26 | 109392.23 | 109392.23 | Gregory Dunfield |  | 18-Aug-21 | 18-Apr-22 | 02-Aug-21 | 20-Sep-21 | 26-Oct-21 | Lines | Filler |  | 0
640676 | NEW AUTO SWITCH INSTALLATION (P21046) - 403 / HURONTARIO, 1 | 800 - Mavis | 151092 | Inactive | 99 | CANCELLED | High | DA | 2021 | Lucic, Marko | Cudzilo, Tomasz | 01-Apr-21 |  |  | 201548.83 | 0 | 231287.13 | 231287.13 | Gregory Dunfield |  | 10-Sep-21 | 26-Jan-22 | 26-Jul-21 |  |  | MC/PUCC Permit | MC/PUCC Permit |  | 0
640675 | (YS101847) REPLACEMENT - 1015 GALESWAY BLVD (P17980) | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2021 | Lucic, Marko | Cudzilo, Tomasz | 25-Jun-21 |  |  | 119616.19 | 117118.67 | 119616.19 | 119616.19 | Gregory Dunfield |  | 28-Sep-21 | 18-Apr-22 | 10-Sep-21 | 01-Sep-21 | 28-Sep-21 |  |  |  | 0
640680 | 2180 SPEAKMAN DR - MISS - NS - 4000A C.O. SERVICE | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mandic, Goran | Pellerin, Patrick | 23-Nov-21 |  |  | 108772.13 | 119059.32 | 108772.13 | 108772.13 | Peter Costantini |  | 21-Dec-21 | 26-Jul-23 | 26-Nov-21 | 15-Dec-21 | 05-Oct-22 | Locates |  |  | 0
640684 | BATCH 1 - TRANSFORMER KIOSK REPLACEMENT | 800 - Mavis | 151043 | Active | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 09-Mar-21 | 4 | 4 | 69995.13 | 89982.33 | 69995.13 | 69995.13 | Glenn Guile |  | 13-May-21 | 26-Jul-23 | 26-Apr-21 | 26-Apr-22 | 23-Dec-22 | Lines | Lines |  | 0
640721 | 1890 ALSTEP DR - MISS - NS - 3PH - 1500KVA TEMP | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Roy, Akash | 25-Sep-21 |  |  | 166541.29 | 135057.11 | 166541.29 | 166541.29 | Peter Costantini | Somervl | 22-Nov-21 | 22-Sep-22 | 30-Sep-21 | 21-Oct-21 | 02-Dec-21 | Customer | Customer |  | 0
640734 | S4585 TO L34024 MAIN FEEDER REMOVAL | 800 - Mavis | 150495 | Active | 40 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
640771 | BRAMALEA ROAD & DERRY ROAD 44KV SYSTEM EXPANSION | 800 - Mavis | 152302 | Active | 98 | COMPLETE |  |  | 2022 | Watters, Maxwell | Watters, Maxwell | 27-Jul-22 |  |  | 369283.09 | 419062.46 | 369283.09 | 369283.09 | Matthew Beach |  | 26-Sep-22 | 26-Jul-23 | 15-Aug-22 | 08-Aug-22 | 21-Sep-22 |  |  |  | 0
640775 | THE COLLEGEWAY STACKED TOWNHOMES - 3401 RIDGEWAY | 800 - Mavis | 151610 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 27-Sep-21 |  |  | 185191.94 | 161213.72 | 185191.94 | 185191.94 | Peter Costantini | Somervl | 27-Oct-21 | 22-Nov-22 | 27-Sep-21 | 15-Sep-21 | 15-Oct-21 |  |  |  | 0
640776 | L7199 TO L7202 GLEN ERIN DR UG CABLE REPLACEMENT | 800 - Mavis | 151883 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Tempra, Troylan | 07-Mar-22 |  |  | 1005601.27 | 865440.51 | 1005601.27 | 1005601.27 | Antonio Mina | Transpw | 16-Aug-22 | 16-Mar-23 | 25-Apr-22 | 24-Mar-22 | 02-Dec-22 |  | MC/PUCC Permit |  | 0
640777 | L4835 TO S4802 JOHN MS UG CABLE REPLACEMENT | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
640782 | JOINT USE PERMIT HM2021-001 - AMERICAN - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 15-Apr-21 |  |  | 11215.86 | 7790.04 | 11215.86 | 11215.86 | Macdougall, Stephen |  | 14-May-21 | 22-Aug-22 | 12-May-21 | 17-May-21 | 17-May-21 | Locates | Locates |  | 0
640790 | FRAM + SLOKKER, 55 PORT ST. E., MISS.- NS00115340 - 3PH PAD | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Garcha, Tirath | 14-Jan-22 |  |  | 137310.86 | 109050.03 | 137310.86 | 137310.86 | Peter Costantini | Somervl | 30-Mar-22 | 12-Oct-22 | 03-Mar-22 | 07-Apr-22 | 19-Oct-22 | Customer | Customer |  | 0
640784 | JOINT USE PERMIT HM2021-003 - ERIN MILLS - MISS | 800 - Mavis | 151537 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
640792 | SKYMARK AVE AND SATELLITE - MISS - NS - 25KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Roy, Akash | 06-Jul-21 |  |  | 44708.4 | 54425.06 | 44708.4 | 44708.4 | Peter Costantini |  | 24-Aug-21 | 22-Nov-22 | 09-Aug-21 | 14-Sep-21 | 16-Sep-21 | Customer | Customer |  | 0
640793 | 2068 SOUTH SHERIDAN - MISS - NS - 300KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Roy, Akash | 07-Jan-22 |  |  | 119634.43 | 68684.35 | 119634.43 | 119634.43 | Peter Costantini | Somervl | 04-Apr-22 | 22-Nov-22 | 21-Feb-22 | 10-Jan-22 | 11-Feb-22 |  |  |  | 0
640798 | EXPANSION - 2180 SPEAKMAN DR - MISSISSAUGA - THP | 800 - Mavis | 152302 | Active | 98 | COMPLETE |  |  | 2022 | Lacombe, Joel | Garcha, Tirath | 20-Oct-21 |  |  | 594055.18 | 394569.61 | 594055.18 | 594055.18 | Peter Costantini | Somervl | 24-Mar-22 | 26-Jul-23 | 29-Nov-21 | 08-Apr-21 | 05-Oct-22 |  | Customer |  | 0
640800 | BATCH 2 - TRANSFORMER KIOSK REPLACEMENT | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Ferry, Rodnne | 24-Mar-21 |  |  | 70001.16 | 68486.42 | 70001.16 | 70001.16 | Glenn Guile |  | 09-Jun-21 | 28-Mar-22 | 28-May-21 | 10-May-21 | 12-May-21 |  | Filler |  | 0
640845 | CUSTOMER INITIATED OH RELOCATION -759 WINSTON CHURCHILL BLVD | 800 - Mavis | 150675 | Active | 82 | RELEASED |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka | 06-Jul-23 |  |  | 502223.38 | 95796.06 | 502223.38 | 502223.38 | Matthew Beach | Somervl | 18-Dec-23 | 18-Dec-23 | 18-Aug-23 | [5 empty] | 0
640852 | JOINT USE PERMIT HM2021-005 - DERRY E - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Johnson, William | 18-May-21 |  |  | 5459.28 | 4996.54 | 5459.28 | 5459.28 | Macdougall, Stephen |  | 21-Jun-21 | 22-Sep-22 | 21-Jun-21 | 02-Jul-21 | 02-Jul-21 | Lines | Filler |  | 0
640854 | ELITE STONE INDUSTRIAL | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Huo, Lisa | 05-Jan-22 |  |  | 111012.32 | 79986.33 | 111012.32 | 111012.32 | Peter Costantini | Somervl | 03-Feb-22 | 22-Nov-22 | 17-Jan-22 | 14-Oct-21 | 21-Jan-22 |  |  |  | 0
640875 | 1293 MEREDITH AVE - MISS - NS - 3PH - 500KVA | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mandic, Goran | Roy, Akash | 05-Apr-22 |  |  | 71325.95 | 64694.66 | 71325.95 | 71325.95 | Peter Costantini | Somervl | 28-Jun-22 | 26-Jul-23 | 13-Jun-22 | 18-Aug-22 | 08-Nov-22 | Customer | Customer |  | 0
638037 | 1408 SEAVIEW - 1PH PADMOUNT TX REPLACEMENT - TX1920 | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Ferry, Rodnne |  |  |  | 0 | ($340.22) |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
638035 | 870 BALTIMORE AVE - 1PH PADMOUNT TX REPLACEMENT - TX2542 | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Ferry, Rodnne |  |  |  | 0 | ($340.22) |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
640890 | M-CITY POLE RELOCATION AT FITZROY STREET | 800 - Mavis | 150675 | Active | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 01-Nov-21 |  |  | 123208.54 | 121541.45 | 92596.42 | 123208.54 | Mark Bobanovic | B&M | 10-Dec-21 | 26-Jul-23 | 06-Dec-21 | 23-Dec-21 | 10-Jan-22 | Materials | Materials |  | 30,612.12
640932 | PORT CREDIT GO - TEMP POWER | 800 - Mavis | 151544 | Active | 97 | CANCELLED |  |  | 2023 | Paesano, Andrew | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 26-Jul-23
640938 | CHILD#1 - 4220 LIVING ARTS DRIVE - DANIELS SQUARE ONE INC -INSTALLATION | 800 - Mavis | 150384 | Active | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo | 07-Oct-21 |  |  | 134805.23 | 118877.83 | 134805.23 | 134805.23 | Peter Costantini | Somervl | 17-Dec-21 | 26-Jul-23 | 25-Oct-21 | 29-Nov-21 | 24-Jan-22 | Locates | Locates |  | 0
640953 | ORLANDO CORPORATION | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa | 16-Nov-21 |  |  | 106212.55 | 66076.55 | 106212.55 | 106212.55 | Peter Costantini | Somervl | 01-Feb-22 | 22-Nov-22 | 11-Jan-22 | 14-Oct-21 | 01-Dec-21 |  |  |  | 0
641028 | 3359 OUTER CIRCLE MISSISSAUGA ROAD | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641047 | 2385 MEADOWPINE BLVD - MISS - NS - 750KVA | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mandic, Goran | Roy, Akash | 25-Aug-22 |  |  | 95916.47 | 88433.94 | 95916.47 | 95916.47 | Peter Costantini | Somervl | 16-Nov-22 | 26-Jul-23 | 07-Nov-22 | 16-Feb-23 |  | Customer | Customer |  | 0
641065 | CREDITVIEW ROAD & OLD CREDITVIEW ROAD POLE RELOCATIONS - MTO | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 26-Aug-21 |  |  | 303801.01 | 283862.79 | 279503.21 | 303801.01 | Mark Bobanovic | K-Line | 20-Oct-21 | 23-May-23 | 11-Oct-21 | 12-Oct-21 | 06-Dec-21 | Contractor | Contractor |  | 24,297.80
641085 | ANIMAL ABATEMENT - UTM | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Ferry, Rodnne | 26-May-21 |  |  | 53555.9 | 42383.25 | 53555.9 | 53555.9 | Manoj Rao Manjunath | Ainswth | 10-Aug-21 | 08-Jun-22 | 19-Jul-21 | 01-Dec-21 | 31-Dec-21 | Filler | Filler |  | 0
396324 | RER MX - LW SCOPE #3 (LW28) - SOUTHDOWN ROAD | 800 - Mavis | 150594 | Active | 84 | ACTIVE |  |  | 2023 | Khuu, Philander | Khuu, Philander | 07-Mar-23 |  |  | 9716998.59 | 2168238.95 | 9716998.59 | 9716998.59 | Mark Bobanovic | Transpw | 31-Aug-23 | 26-Jul-23 | 12-Jun-23 | 24-Apr-23 |  |  |  |  | 0
641133 | 2023 POLE RENEWALS - 2 WP - JALNA AVE POLE RENEWAL | 800 - Mavis | 151063 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 15-Nov-22 | 2 | 2 | 30146.3 | 35188.8 | 30146.3 | 30146.3 | Matthew Beach |  | 14-Feb-23 | 26-Jul-23 | 06-Feb-23 | 27-Mar-23 | 30-Mar-23 |  | Filler |  | 0
641178 | 91 EGLINTON AVE EAST - CONDO SUBDIVISION | 800 - Mavis | 150652 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641240 | PROJECT 151894 _ CABLE REMEDIATION- MAIN FEEDER CABLE (S4802 TO L4835) | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Beaudrie, Scott | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641250 | PROJECT_ 151901 _ CABLE REPLACEMENT PROJECT - (AREA16) - HEMUS SQUARE | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641295 | PROJECT_ 151903 _ CABLE REPLACEMENT PROJECT - (AREA25) - SOUTH MILLWAY | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641306 | CUSTOMER INITIATED EXTENSION OF HYDRO FACILITIES -HAZELHURST RD | 800 - Mavis | 152302 | Active | 84 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka | 02-Feb-23 |  |  | 364992.7 | 219172.59 | 364992.7 | 364992.7 | Matthew Beach |  | 13-Jun-23 | 14-Sep-23 | 29-Mar-23 | 27-Mar-23 |  |  |  |  | 0
641314 | 336 WATLINE - MISS - UP - 3PH - 750KVA | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mustachi, Randy | Paesano, Chelsea | 06-Jun-22 |  |  | 84808.02 | 103545.01 | 84808.02 | 84808.02 | Peter Costantini | N/A | 06-Jul-22 | 26-Jul-23 | 27-Jun-22 | 15-Nov-22 | 03-Dec-22 | Customer | Customer |  | 0
641327 | 2021 MUT CITY OF MISSISSAUGA PROJECT - ALECTRA RELOCATIONS | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 19-Nov-21 |  |  | 404241.76 | 388109.92 | 334191.37 | 404241.76 | Mark Bobanovic | B&M | 14-Jan-22 | 11-Sep-22 | 13-Dec-21 | 22-Dec-21 | 02-Feb-22 | Contractor | Weather |  | 70,050.39
641352 | 7015 KENNEDY RD - MISS - NS - 3PH - 1500KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Roy, Akash | 08-Oct-21 |  |  | 130738.97 | 103832.07 | 130738.97 | 130738.97 | Peter Costantini | Somervl | 13-Dec-21 | 22-Nov-22 | 08-Nov-21 | 05-Nov-21 | 05-Dec-21 |  |  |  | 0
641357 | 2815 EGLINTON AVE W - MISS - NS - 400A | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Pellerin, Patrick | 08-Sep-21 |  |  | 18721.14 | 30365.11 | 18721.14 | 18721.14 | Peter Costantini |  | 04-Jan-22 | 22-Nov-22 | 18-Oct-21 | 08-Nov-21 | 25-Nov-21 | Locates |  |  | 0
641419 | MISSISSAUGA RD & KANE RD MINI REBUILD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Tempra, Troylan | 10-Aug-21 | 0 |  | 288447.39 | 214848.41 | 288447.39 | 288447.39 | Antonio Mina | Transpw | 25-Oct-21 | 22-Sep-22 | 16-Sep-21 | 01-Nov-21 | 30-Nov-21 | Contractor | Contractor |  | 0
641425 | STUB POLE RELOCATION - BURNHAMTHORPE RD. W. | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Garcha, Tirath | 10-May-21 |  |  | 30136.8 | 14414.31 | 30136.8 | 30136.8 | Paul Murphy |  | 02-Jun-21 | 22-Sep-22 | 24-May-21 | 17-May-21 | 04-Jun-21 |  |  |  | 0
412945 | U/G DISTRIBUTION AUTOMATION - CITY CENTRE NORTH, 2 | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2021 | Houston, Andrew | Zaghloul, Sam | 16-Jun-21 | 2 | 2 | 392177.2 | 453194.4 | 392177.2 | 392177.2 | Antonio Mina | Somervl | 03-Nov-21 | 10-Aug-22 | 27-Sep-21 | 06-Sep-21 | 15-Nov-21 |  | Locates |  | 0
641486 | PROPOSED EVENT CENTER - 6916 DIXIE RD. | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641489 | GLEN ERIN & BURNHAMTHORPE UG REBUILD | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641496 | 181 LAKESHORE RD W - MISS - NS - 3PH - 1000KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Roy, Akash | 13-Jan-22 |  |  | 139616.83 | 140850.22 | 139616.83 | 139616.83 | Peter Costantini | Somervl | 20-Apr-22 | 22-Nov-22 | 01-Mar-22 | 25-Feb-22 | 25-Mar-22 |  |  |  | 0
641525 | THE FURLAN GROUP SERVICE UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 30-May-22
641540 | 2022 OH EMERGING - GALLOPING CONDUCTORS- BATCH # 5 | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Dec-21 |  |  | 164624.63 | 66785.04 | 164624.63 | 164624.63 | Matthew Beach |  | 22-Jun-22 | 02-Mar-23 | 28-Mar-22 | 13-Jul-22 | 21-Oct-22 | Filler | Filler |  | 0
641539 | INSULATORS RENEWAL - BATCH #3 | 800 - Mavis | 151727 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641595 | 2020 TRANSFORMER REPLACEMENT BATCH 2 (TX7642RWB/ TX8400RWB) | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Cudzilo, Tomasz | 24-Jun-21 | 2 | 2 | 50535.99 | 68804.35 | 50535.99 | 50535.99 | Antonio Mina |  | 25-Oct-21 | 26-Jan-23 | 18-Oct-21 | 14-Jan-22 | 01-Mar-22 | Lines | Lines |  | 0
641737 | UNDERGROUND REBUILD - BURNHAMTHORPE PHASE 1 | 800 - Mavis | 151408 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 04-May-22 |  |  | 1879494.58 | 1778631.94 | 1879494.58 | 1879494.58 | Antonio Mina | Transpw | 30-Aug-22 | 26-Feb-23 | 18-May-22 | 10-Jun-22 | 28-Oct-22 | Contractor | Contractor |  | 0
641753 | JOINT USE PERMIT HM - INVESTIGATION FOR BELL | 800 - Mavis | 151537 | Inactive | 99 | CANCELLED |  |  | 2022 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 22-Sep-22
641762 | BELL BONDS - Y48653 - MISS | 800 - Mavis | 151537 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641805 | CUST RELOC - NOVAR ROAD & DUNDAS STREET OH TO UG | 800 - Mavis | 152302 | Active | 92 | ANALYZE |  |  | 2023 | Lacombe, Joel | Garcha, Tirath | 09-May-22 |  |  | 718396.39 | 603910.91 | 708814.68 | 718396.39 | Mark Bobanovic | Transpw | 01-Nov-22 | 24-Nov-23 | 21-Jun-22 | 18-Jul-22 | 04-Jan-23 | Contractor | Contractor |  | 9,581.71
641832 | LT31135 - 2022 SR-DUNDAS ST W. E-O OF DUNWIN DR - P10331 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 17-Nov-21 | 1 | 1 | 143012.92 | 202808.58 | 143012.92 | 143012.92 | Paul Murphy |  | 18-Feb-22 | 02-Mar-23 | 26-Jan-22 | 18-Mar-22 | 07-Oct-22 | Lines | Materials |  | 0
641855 | QTY 8 - 2022 TRANSFORMER REPLACEMENT - BATCH 1 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Ferry, Rodnne | 18-Nov-21 | 8 | 8 | 108108.97 | 128896.97 | 108108.97 | 108108.97 | Antonio Mina |  | 14-Apr-22 | 26-Feb-23 | 21-Mar-22 | 07-Mar-22 | 14-Jun-22 |  | Filler |  | 0
641856 | (SG1402) 2022 SG REPLACEMENT - ELMCREEK AND SHORLINE | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 18-Nov-21 | 1 | 1 | 128196.21 | 98651.08 | 128196.21 | 128196.21 | Glenn Guile |  | 11-Feb-22 | 26-Feb-23 | 24-Jan-22 | 23-Mar-22 | 01-Apr-22 | Lines | Lines |  | 0
641865 | LT31097 - 2022 DA - DUNDAS ST & MISS RD - P07936 | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 18-Nov-21 | 1 | 1 | 133287.81 | 130519.06 | 133287.81 | 133287.81 | Paul Murphy |  | 18-Mar-22 | 02-Mar-23 | 21-Feb-22 | 13-Jun-22 | 20-Jul-22 | COVID19 | Materials |  | 0
640878 | 1250 SHAWSON DR - PAVE-AL LIMITED | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo | 07-Jun-21 |  |  | 23110.15 | 12468.52 | 23110.15 | 23110.15 | Macdougall, Stephen |  | 08-Jul-21 | 22-Sep-22 | 05-Jul-21 | 03-May-21 | 07-May-21 |  |  |  | 0
641923 | ROVINELLI HOLDINGS LTD. | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641932 | 3285 MAVIS ROAD - MISS - UP - 600A | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2023 | Mustachi, Randy | Pellerin, Patrick |  |  |  | 0 | 2583.27 |  | 0 | XMoinuddin, Saad |  |  | 22-Jun-23
641933 | 6005 ERIN MILLS - MISS - NS - 1200A (EXP. DEM:846KW PER M-REZA) | 800 - Mavis | 150384 | Active | 95 | ANALYZE |  |  | 2022 | Mustachi, Randy | Jacinto, Gerardo | 15-Sep-22 |  |  | 129481.52 | 111061.92 | 129481.52 | 129481.52 | Peter Costantini | Somervl | 20-Dec-22 | 26-Jul-23 | 21-Nov-22 | 10-Jan-23 | 18-Jan-23 | Customer | Customer |  | 0
641935 | 6155 ERIN MILLS PARKWAY - MISS - NS - 200A | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641947 | PRIMARY REMOVAL & TX RELOCATION - 6650 HURONTARIO ST | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 23-Mar-23
641952 | 2023 POLE RENEWAL - 27 WP - REDSTONE RD POLE RENEWAL | 800 - Mavis | 151063 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 08-Dec-22 | 27 |  | 777585.05 | 324706.85 | 777585.05 | 777585.05 | Matthew Beach |  | 31-Aug-23 | 23-Nov-23 | 30-May-23 | 05-Jun-23 |  | Lines |  |  | 0
642000 | 1331 SHAWSON DR - MISS - NS - 3PH - NS00046456 | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 03-Feb-23 |  |  | 316927.65 | 23326.77 | 252522.27 | 316927.65 | Peter Costantini | Somervl | 17-Aug-23 | 21-Aug-23 | 24-Jul-23 |  |  | Customer |  |  | 64,405.38
642005 | BELL BONDS - Y48653 - MISS | 800 - Mavis | 151537 | Active | 70 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642051 | 6677 MEADOWVALE TOWN CENTRE - MISS - NS - 600A | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642128 | SHELL CANADA LIMITED | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Huo, Lisa | 18-Oct-21 |  |  | 150118.06 | 133797.51 | 150118.06 | 150118.06 | Peter Costantini | Somervl | 24-Feb-22 | 22-Nov-22 | 10-Jan-22 | 07-Dec-21 | 13-Apr-22 | Customer | Customer |  | 0
642131 | 6501 GOREWAY DRIVE (GOREWAY ESSO) | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 27-Apr-22
642148 | BARBERHOUSE POLE RELOCATION | 800 - Mavis | 151612 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Ricci, Leonardo | 28-Sep-21 |  |  | 11708.16 | 11080.79 | 11708.16 | 11708.16 | Gregory Dunfield |  | 11-Nov-21 | 29-Mar-22 | 08-Nov-21 | 25-Nov-21 | 25-Nov-21 | Locates | Locates |  | 0
642155 | 3575 FIELDGATE DR (PEEL DISTRICT SCHOOL BOARD) | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
414001 | 2023 - NORTH-EAST DIXIE - MINI REBUILD (CABLE REPLACEMENT) | 800 - Mavis | 151902 | Active | 82 | RELEASED |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 29-Mar-23 |  |  | 287848.63 | 14870.05 | 287848.63 | 287848.63 | Antonio Mina | Somervl | 02-Aug-23 | 15-Sep-23 | 13-Jun-23 |  |  | Lines |  |  | 0
642219 | 1288 SOUTH ALDO DRIVE - POLE RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 01-Nov-21 |  |  | 45023.14 | 45827.67 | 45023.14 | 45023.14 | Gregory Dunfield |  | 22-Dec-21 | 22-Sep-22 | 10-Dec-21 | 18-Jan-22 | 18-Jan-22 | Locates | Locates |  | 0
642313 | QTY 12 1PH - 2022 TX REPLACEMENT - BATCH 2 | 800 - Mavis | 151043 | Active | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 18-Nov-21 | 12 | 12 | 158286.97 | 167753.68 | 158286.97 | 158286.97 | Glenn Guile |  | 02-Mar-22 | 26-Jul-23 | 24-Jan-22 | 07-Apr-22 | 23-Dec-22 | Lines | Lines |  | 0
642344 | LT31106 - 2022 SR-DUNDAS ST W & ERIN MILLS - P11533 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 18-Nov-21 | 1 | 1 | 162284.39 | 163517.16 | 162284.39 | 162284.39 | Paul Murphy |  | 30-Mar-22 | 02-Mar-23 | 01-Mar-22 | 25-Apr-22 | 15-Sep-22 | Lines | Lines |  | 0
642355 | 2022 UG REBUID - BATTLEFORD&MONTEVIDEOPH2 | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642356 | 2440 TEDLO ST | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642394 | 3990 EGLINTON - MISS - NS - 3PH - 500KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Pellerin, Patrick | 29-Oct-21 |  |  | 148972.93 | 115936.7 | 148972.93 | 148972.93 | Peter Costantini | Somervl | 29-Nov-21 | 10-Feb-23 | 03-Nov-21 | 08-Nov-21 | 17-Dec-21 | Customer |  |  | 0
642404 | 2022 SWGR RENEWAL, SG1041 & SG1194, EXPLORER DR | 800 - Mavis | 151091 | Active | 99 | ANALYZE | High | SwGear | 2022 | Lucic, Marko | Cudzilo, Tomasz | 17-Dec-21 | 3 | 3 | 340820.29 | 393708.74 | 340820.29 | 340820.29 | Antonio Mina |  | 07-Jun-22 | 26-Jul-23 | 25-Apr-22 | 03-Nov-22 | 06-Jan-23 | Filler |  |  | 0
642410 | 2022 SWGR RENEWAL, SG1370, 6807 FOREST PARK DR | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE | High | SwGear | 2022 | Lucic, Marko | Tempra, Troylan | 03-Dec-21 | 1 | 1 | 177228.93 | 160651.14 | 177228.93 | 177228.93 | Antonio Mina |  | 27-May-22 | 26-Feb-23 | 02-May-22 | 04-Mar-22 | 27-May-22 |  |  |  | 0
642409 | 2023 SWGR RENEWAL, SG1341, GLEN ERIN DR | 800 - Mavis | 151091 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  | 1 |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642407 | 2022 SWGR RENEWAL, SG1064, 4181 SLADEVIEW CRES | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE | High | SwGear | 2022 | Lucic, Marko | Tempra, Troylan | 03-Dec-21 | 1 | 1 | 177257.55 | 81716.75 | 177257.55 | 177257.55 | Antonio Mina |  | 31-Mar-22 | 26-Feb-23 | 07-Mar-22 | 17-Oct-22 | 28-Oct-22 | Filler | Filler |  | 0
636535 | MX - EGLINTON WEST EXTENSION - DRILL POWER SUPPLY - COMMERCE & CITATION | 800 - Mavis | 151527 | Inactive | 99 | COMPLETE |  |  | 2021 | Tobin, Michael | Chopra, Rabinder | 27-Aug-21 |  |  | 546635.27 | 589675.66 | 546635.27 | 546635.27 | Antonio Mina | Transpw | 09-Nov-21 | 28-Mar-22 | 06-Sep-21 | 01-Sep-21 | 29-Oct-21 |  |  |  | 0
642422 | 2775 MATHESON BLVD E - MISS - UP - 2500A | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642449 | QTY 12 1PH - 2022 TX REPLACEMENT - BATCH #3 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Ferry, Rodnne | 11-Nov-21 | 12 | 12 | 175443.71 | 183654.27 | 175443.71 | 175443.71 | Peter Costantini |  | 05-May-22 | 26-Feb-23 | 14-Mar-22 | 12-May-22 | 28-Sep-22 | Filler | Filler |  | 0
642452 | EMBLEM DEVELOPMENTS - 89 DUNDAS ST. W. | 800 - Mavis | 150384 | Active | 81 | Upload Completed |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 257470.29 | 30476.37 | 257470.29 | 257470.29 | XMoinuddin, Saad |  |  | 12-Jan-24 | [6 empty] | 0
642457 | 2022 UG REBUILD - GLEN ERIN & BURNHAMTHORPE PHASE 4 | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642456 | 2022 UG REBUILD - GLEN ERIN & BURNHAMTHORPE PHASE 3 | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642455 | 2022 UG REBUILD - GLEN ERIN & BURNHAMTHORPE PHASE 2 | 800 - Mavis | 150495 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642491 | 3660 HURONTARIO RD - MISS - NS - 3PH - 750KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642498 | LT31235 - 2022 SR-QUEENSWAY W & STILLMEADOW RD - P13168 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 17-Nov-21 | 1 | 1 | 125255.05 | 131578.81 | 125255.05 | 125255.05 | Rob Elliot |  | 22-Feb-22 | 02-Mar-23 | 31-Jan-22 | 13-Jan-22 | 02-Feb-22 |  |  |  | 0
642538 | YS153905 - 2022 DA - BRITANNIA RD AND MAVIS RD - P18118 | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 17-Dec-21 | 1 | 1 | 94635.1 | 106586.41 | 94635.1 | 94635.1 | Gregory Dunfield |  | 21-Mar-22 | 02-Mar-23 | 07-Mar-22 | 08-Feb-22 | 14-Mar-22 |  |  |  | 0
642537 | YL41187 - 2022 DA - DIXIE RD AND TONOLLI RD - USC341 | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 17-Nov-21 | 1 | 1 | 130786.17 | 161725.48 | 130786.17 | 130786.17 | Gregory Dunfield |  | 09-Mar-22 | 02-Mar-23 | 14-Feb-22 | 25-Mar-22 | 11-Apr-22 | COVID19 | COVID19 |  | 0
642536 | YL44352 - 2022 DA - DIXIE RD AND PRIMATE RD - P17025 | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 17-Nov-21 | 1 | 1 | 95447.09 | 96771.88 | 95447.09 | 95447.09 | Gregory Dunfield |  | 26-Oct-22 | 02-Mar-23 | 10-Oct-22 | 18-Dec-22 | 18-Dec-22 | N/A |  |  | 0
642540 | LT102038 - 2022 DA - HERITAGE RD AND 407 - P21458 | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 16-Dec-21 | 1 | 1 | 143297 | 170168.44 | 143297 | 143297 | Gregory Dunfield |  | 14-Mar-22 | 02-Mar-23 | 21-Feb-22 | 08-Nov-22 | 17-Dec-22 | Lines | Lines |  | 0
642539 | LT71221 - 2021 DA - MISSISSAUGA RD AND MEADOWVALE BLVD - P18998 | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2021 | Lucic, Marko | Matai, Ihssan (Sam) | 08-Nov-21 | 1 |  | 115415.92 | 158845.77 | 115415.92 | 115415.92 | Gregory Dunfield |  | 21-Dec-21 | 08-Jun-22 | 07-Dec-21 | 01-Dec-21 | 17-Dec-21 |  |  |  | 0
642554 | PSN METROLINX - MISS | 800 - Mavis | 151470 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Bennett, Aaron |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642501 | YL41179 - 2022 SR QUEENSWAY E & EDGEWORTH RD - P11367 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 03-Dec-21 | 1 | 1 | 82369.77 | 98031.2 | 82369.77 | 82369.77 | Gregory Dunfield |  | 13-May-22 | 02-Mar-23 | 25-Apr-22 | 09-Nov-22 | 19-Dec-22 | Filler |  |  | 0
642569 | COOKSVILLE TS FEEDER EXPANSION | 800 - Mavis | 152302 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642573 | 45 AGNES ST - MISS - NS - 1600A | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642473 | BRONTE COLLEGE/TRILLIUM REBUILD (ABOVE GROUND PARKING) | 800 - Mavis | 152330 | Active | 50 | ACTIVE |  |  | 2023 | Jolie, Chris | Su, Jay |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642609 | QEW AT MISSISSAUGA ROAD - MISS - NS - 400A | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642618 | QTY 11 - 1PH TX REPLACEMENT - 2022 - CENTRAL SOUTH - BATCH #4 | 800 - Mavis | 151043 | Active | HL | ACTIVE |  |  | 2023 | Beaudrie, Scott | Ferry, Rodnne |  |  |  | 0 | 7379 |  | 0 | XMoinuddin, Saad |  |  | 26-Jul-23
642627 | (SG1456) 2022 SG REPLACEMENT - 4010 SLADVIEW CRESCENT | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 18-Nov-21 | 1 | 1 | 52498.58 | 52628.35 | 52498.58 | 52498.58 | Antonio Mina |  | 10-Feb-22 | 26-Feb-23 | 31-Jan-22 | 11-Jan-22 | 13-Jan-22 |  |  |  | 0
642709 | SQUARE ONE DRIVE EXTENSION - RATHBURN RD FROM ELORA DR. TO CONFEDERATION PKWY | 800 - Mavis | 150673 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 69.41 |  | 0 | XMoinuddin, Saad |  |  | 28-Jun-23
642740 | 2345 MATHESON BLVD E - MISS - NS - 3PH - 1200A | 800 - Mavis | 150384 | Active | HD | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 4490.52 |  | 0 | XMoinuddin, Saad |  |  | 26-Jul-23
642741 | 745 COURTNEYPARK DR W - MISS - NS - 3PH - 150KW | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Pellerin, Patrick |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642743 | PRPA FACILITY | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642754 | M CITY - PHASE 2 (M3, M4, M5) | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
428171 | 80 THOMAS ST TOWNHOMES | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2022 | Gamboa, Henry | Ricci, Leonardo | 26-Aug-21 |  |  | 642396.61 | 497191.66 | 502396.61 | 642396.61 | Mark Bobanovic | Transpw | 04-May-22 | 09-Dec-22 | 11-Apr-22 | 20-Sep-21 | 22-Nov-22 |  | Contractor |  | 140,000.00
642846 | 6860 REXWOOD ROAD UNIT 1 MISSISSAUGA | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 534.85 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642847 | 15 WATERGARDEN DRIVE | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642963 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE1.1 DIXIE OUTLET MALL | 800 - Mavis | 151589 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 14-Dec-21 |  |  | 1126765.06 | 1025048.15 | 1126765.06 | 1126765.06 | Matthew Beach | Transpw | 07-Apr-22 | 05-Feb-23 | 01-Feb-22 | 09-Feb-22 | 18-Nov-22 | Contractor |  |  | 0
642981 | 1083 EDGELEIGH AVENUE POLE RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 15-Dec-21 | 1 | 1 | 30187.94 | 26233.57 | 30187.94 | 30187.94 | Gregory Dunfield | Somervl | 24-Jan-22 | 09-Aug-22 | 17-Jan-22 | 08-Feb-22 | 08-Feb-22 | Locates | Locates |  | 0
643017 | 7187 KIMBEL STREET - POLE RELOCATION | 800 - Mavis | 152302 | Active | HL | H8 |  |  | 2023 | Watters, Maxwell | Watters, Maxwell |  |  |  | 0 | 2211.84 |  | 0 | XMoinuddin, Saad |  |  | 26-Jul-23
643018 | POLE RELOCATION - 1115 ALGONQUIN DR | 800 - Mavis | 152302 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Gonzales, Leonard | 13-May-22 |  |  | 25481.34 | 4696.19 | 25481.34 | 25481.34 | Gregory Dunfield |  | 04-Jul-22 | 29-Sep-22 | 27-Jun-22 | [5 empty] | 0
643020 | 66 QUEEN STREET SOUTH - POLE RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2021 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 1600.44 |  | 0 | XMoinuddin, Saad |  |  | 29-Dec-21
643088 | TEMP. SERVICE FOR 2020 CAMILLA RD. | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643123 | 6200 CANTAY ROAD UNIT 1 MISSISSAUIGA L5R 3Y9 | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mustachi, Randy | Jacinto, Gerardo | 30-May-22 |  |  | 203361.44 | 171479.46 | 203361.44 | 203361.44 | Peter Costantini | Somervl | 19-Sep-22 | 22-Nov-22 | 15-Aug-22 | 21-Jul-22 | 25-Aug-22 |  |  |  | 0
643132 | 2023 POLE RENEWAL - 19 WP - BONAVENTURE DR | 800 - Mavis | 151063 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 08-Dec-22 | 19 |  | 623115.27 | 321737.34 | 623115.27 | 623115.27 | Paul Murphy |  | 31-Jul-23 | 06-Sep-23 | 31-May-23 | 24-May-23 |  |  |  |  | 0
643163 | ECWE TEMP POWER TBMS | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Paesano, Andrew | Chopra, Rabinder | 05-Jan-22 |  |  | 277782.03 | 196386.22 | 277782.03 | 277782.03 | Antonio Mina | Transpw | 14-Mar-22 | 17-Apr-23 | 14-Feb-22 | 31-Jan-22 | 06-Apr-22 |  | Customer |  | 0
643181 | 2023 POLES - 26 CP - OH REBUILD - OGDEN AVE PHASE 2 | 800 - Mavis | 151063 | Active | 82 | Upload Completed |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 10-Nov-22 | 26 |  | 851292.94 | 6956.11 | 851292.94 | 851292.94 | Persaud, Ryan |  | 31-Dec-23 | 12-Dec-23 | 01-Sep-23 | [5 empty] | 0
643194 | 2510-2520 ROYAL WINDSOR DRIVE | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 20-Mar-23 |  |  | 52449.1 | 37278.94 | 52449.1 | 52449.1 | Gregory Dunfield |  | 31-Mar-23 | 26-Jul-23 | 29-Mar-23 | 29-Mar-23 | 24-Apr-23 |  | Customer |  | 0
643198 | (SG1493) 2022 SG REPLACEMENT - 2935 ARGENTIA ROAD | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2021 | Lucic, Marko | Ferry, Rodnne | 18-Nov-21 |  |  | 57371.29 | 0 | 57371.29 | 57371.29 | Antonio Mina |  | 23-Feb-22 | 20-Jun-23 | 10-Feb-22 | 01-Dec-21 | 01-Dec-21 |  |  |  | 0
643200 | 1 3PH - 2022 TX REPLACEMENT - TX11254 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2022 | Beaudrie, Scott | Ferry, Rodnne | 18-Nov-21 | 1 | 1 | 52931.26 | 7988.1 | 52931.26 | 52931.26 | Glenn Guile |  | 17-Mar-22 | 26-Feb-23 | 14-Mar-22 | 07-Mar-22 | 14-Mar-22 |  |  |  | 0
643199 | (SG1536) 2022 SG REPLACEMENT - 3770 A LAIRD DRIVE | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 18-Nov-21 | 1 | 1 | 57371.29 | 42042.41 | 57371.29 | 57371.29 | Antonio Mina |  | 27-Jan-22 | 26-Feb-23 | 17-Jan-22 | 31-Jan-22 | 03-Feb-22 | Filler | Filler |  | 0
643227 | 1130-1138 MONA ROAD - POLE LINE | 800 - Mavis | 151612 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643226 | 1130-1138 MONA ROAD SUBDIVISION | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
428568 | CAWTHRA RD - ADDITIONAL GUYING AT P04172 | 800 - Mavis | 151144 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 08-Nov-21 |  |  | 33697.75 | 20390.56 | 33697.75 | 33697.75 | Gregory Dunfield |  | 13-Jan-22 | 13-Apr-23 | 03-Jan-22 | 14-Mar-22 | 14-Mar-22 | Lines | Lines |  | 0
643229 | 2022 SWGR RENEWAL, SG1671 REPLACEMENT, 3329 HUXLEY DR | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Cudzilo, Tomasz | 06-Dec-21 | 1 | 1 | 58916.3 | 53397.69 | 58916.3 | 58916.3 | Antonio Mina |  | 27-May-22 | 26-Feb-23 | 16-May-22 | 03-Mar-22 | 04-Mar-22 |  |  |  | 0
643292 | 6389 MISSISSAUGA ROAD - MISS - NS - 3PH - NS00166468 | 800 - Mavis | 150384 | Active | 81 | Upload Completed |  |  | 2023 | Mustachi, Randy | Abucejo, Chariz |  |  |  | 205383.16 | 7790.76 | 205383.16 | 205383.16 | XMoinuddin, Saad |  |  | 26-Jul-23 | [6 empty] | 0
643299 | 3065 GLEN ERIN DR - MISS - UP - 3PH - 500KVA | 800 - Mavis | 150384 | Active | 95 | ANALYZE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 12-Oct-22 |  |  | 100677.88 | 79628.67 | 100677.88 | 100677.88 | Peter Costantini | Somervl | 23-Jan-23 | 26-Jul-23 | 09-Jan-23 | 15-Nov-22 | 16-Feb-23 |  | Customer |  | 0
643302 | 3000 WOODCHESTER DR - MISS - UP - 3PH - 1500KVA | 800 - Mavis | 150384 | Active | HO | RELEASED |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 05-Dec-22 |  |  | 95705.11 | 5253.91 | 95705.11 | 95705.11 | Peter Costantini | Somervl | 16-Feb-23 | 02-Aug-23 | 06-Feb-23 | [5 empty] | 0
643304 | 3050 VEGA BLVD - MISS - NS - 3PH - 1500KVA | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643305 | 7174 DERRYCREST DR - MISS - NS - 3PH - 2000KVA | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Roy, Akash |  |  |  | 116507.99 | 93014.42 | 116507.99 | 116507.99 | Peter Costantini | Somervl | 13-Oct-22 | 22-Nov-22 | 19-Sep-22 | 31-Aug-22 | 13-Sep-22 |  |  |  | 0
643311 | 7055 TRANMERE DRIVE | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643313 | STUDIO BOTTEGGA - SUBD CAP PROJ | 800 - Mavis | 151612 | Active | 93 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea | 30-Nov-22 |  |  | 56333.15 | 62918.02 | 56333.15 | 56333.15 | Antonio Mina | Somervl | 07-Feb-23 | 26-Jul-23 | 01-Feb-23 | 30-Jan-23 | 27-Feb-23 |  | Customer |  | 0
643330 | IMPERIAL OIL PIPELINE INSTALL - ALECTRA POLE RELOCATIONS P17515 & P17514 | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2023 | Watters, Maxwell | Watters, Maxwell | 01-Dec-21 |  |  | 112295.29 | 5979.22 | 112295.29 | 112295.29 | Paul Murphy |  | 30-Mar-22 | 12-Jun-23 | 07-Mar-22 |  |  | Customer |  |  | 0
428710 | LT31137 - 2021 SR-DUNDAS ST W & GLEN ERIN DR - P05560 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 17-Nov-21 | 1 | 1 | 115417.39 | 149685.51 | 115417.39 | 115417.39 | Paul Murphy |  | 26-Jan-22 | 02-Mar-23 | 10-Jan-22 | 16-Mar-22 | 02-Aug-22 | COVID19 | COVID19 |  | 0
643342 | DERRY RD, BRAMALEA RD AND MENKES DR ROAD IMPROVEMENTS - ALECTRA RELOCATIONS | 800 - Mavis | 150673 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
642723 | VOICE RADIO COMMUNICATION – MAINGATE MS | 800 - Mavis | 632833 | Inactive | 99 | CANCELLED |  |  | 2022 | Haid, Philip G. | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643378 | HULRT TPSS#01 - EAGLEWOOD BLVD - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641922 | 3100 DIXIE ROAD - NEW SUBSTATION-FULL REVAMP OF FACILITIES | 800 - Mavis | 150384 | Active | 40 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643448 | HULRT TPSS#04 - DUNDAS ST - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643445 | HULRT TPSS#03 - QUEENSWAY - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643442 | HULRT TPSS#02 - SOUTH SERVICE RD - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643454 | HULRT TPSS#09 - MATHESON BLVD - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643453 | HULRT TPSS#08 - NAHANI WAY - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643452 | HULRT TPSS#07 - HIGHWAY 403 - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643450 | HULRT TPSS#06 - ROBERT SPECK PKWY - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643449 | HULRT TPSS#05 - FAIRVIEW RD - MISS - 3PH - PRIMARY | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643470 | HULRT TPSS#15 - SQUARE ONE DR - MISS - 3PH - PRIMARY | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2021 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
353762 | LT31041 & LT31040 - 2022 SR-QUEENSWAY W & GLENGARRY RD - P08870 & P08872 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 17-Nov-21 | 2 | 2 | 280505.23 | 328122.24 | 280505.23 | 280505.23 | Rob Elliot |  | 04-Apr-22 | 02-Mar-23 | 21-Feb-22 | 24-Mar-22 | 22-Aug-22 | Lines | Materials |  | 0
643487 | 3440 WOLFEDALE ROAD (KALPOLYMER) | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 15-Sep-22 |  |  | 304194.1 | 277232.82 | 304194.1 | 304194.1 | Peter Costantini | Somervl | 03-Feb-23 | 26-Jul-23 | 09-Dec-22 | 14-Sep-22 | 29-Apr-23 |  | Customer |  | 0
643488 | 745 COURTNEYPARK DRIVE WEST | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 80929.21 | 100071.85 | 80929.21 | 80929.21 | Peter Costantini | Somervl | 09-Nov-22 | 10-Aug-23 | 11-Oct-22 | 31-Aug-22 |  |  | Customer |  | 0
643494 | 2775 MATHESON BLVD E | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Jacinto, Gerardo |  |  |  | 0 | 1800.67 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643515 | NINTH LINE SUBDIVISION (MATTAMY HOMES) | 800 - Mavis | 150652 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Ricci, Leonardo | 07-Sep-22 |  |  | 963645.45 | 85403.84 | 963645.45 | 963645.45 | Antonio Mina | El-Con | 12-Dec-22 | 03-Aug-23 | 01-Dec-22 | 18-Nov-22 |  |  |  |  | 0
643559 | 1589 GLENHILL CRESCENT - OH TO UG CONVERSION POLE TO POLE | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 16-Feb-22 |  |  | 68814.17 | 72559.69 | 68814.17 | 68814.17 | Rob Elliot | Somervl | 04-May-22 | 23-Sep-22 | 11-Apr-22 | 05-May-22 | 09-Sep-22 | Locates | COVID19 |  | 0
643563 | QEW CREDIT RIVER IMPROVEMENT PROJECT - POLE RELOCATION NEAR MISSISSAUGA RD | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2021 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643621 | 2620 SPEAKMAN DRIVE - APPLIED AS 2620 SPEAKMAN DR | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 15-Mar-23 |  |  | 242886.23 | 178518.32 | 242886.23 | 242886.23 | Peter Costantini | Somervl | 01-May-23 | 26-Jul-23 | 14-Apr-23 | 04-Apr-23 | 28-Apr-23 |  |  |  | 0
643667 | 16 ELM DRIVE WEST, MISS.- NS00202398 -3PH PAD - TEMPORARY SERVICE | 800 - Mavis | 150384 | Active | 95 | ANALYZE |  |  | 2023 | Mandic, Goran | Garcha, Tirath | 12-Jan-22 |  |  | 37700 | 10114.09 | 37700 | 37700 | Peter Costantini | N/A | 15-Mar-22 | 26-Jul-23 | 02-Mar-22 | 13-Feb-23 | 13-Feb-23 |  |  |  | 0
643675 | 2022 SWGR RENEWAL, SG1581 REMOVAL, 3675 THOMAS ST. | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Cudzilo, Tomasz | 03-Jan-22 | 1 | 1 | 61592.61 | 57726.56 | 61592.61 | 61592.61 | Antonio Mina | Somervl | 09-May-22 | 26-Feb-23 | 02-May-22 | 24-Mar-22 | 02-May-22 |  |  |  | 0
643707 | 100 QUEENSWAY (COLLEGE) - MISS - NS - 3PH - 1000KVA | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643711 | 2022 SWGR RENEWAL, SG1482, MARVIN HEIGHTS PARK AT REDSTONE RD | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE | High | SwGear | 2022 | Lucic, Marko | Tempra, Troylan | 02-Dec-21 | 1 | 1 | 185631.87 | 165531.78 | 185631.87 | 185631.87 | Glenn Guile | Somervl | 19-May-22 | 26-Feb-23 | 25-Apr-22 | 14-Mar-22 | 27-May-22 | Lines | Lines |  | 0
643822 | (SG1734 AND SG1372) 2022 SG REPLACEMENT - 6755 AND 6135 LISGAR DRIVE | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Ferry, Rodnne | 07-Dec-21 | 2 | 2 | 120086.44 | 92142.25 | 120086.44 | 120086.44 | Glenn Guile |  | 12-May-22 | 26-Feb-23 | 25-Apr-22 | 10-Feb-22 | 16-Feb-22 |  |  |  | 0
396164 | RER MX - LW CONFLICT #LW17 - DIXIE ROAD | 800 - Mavis | 150594 | Active | 84 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin | 17-Mar-23 |  |  | 3794103.71 | 2152190.07 | 3794103.71 | 3794103.71 | Matthew Beach | Transpw | 27-Sep-23 | 07-Nov-23 | 20-Mar-23 | 21-Feb-23 |  |  |  |  | 0
396261 | RER MX - LW SCOPE #4 - WINSTON CHURCHILL & BROMSGROVE | 800 - Mavis | 150594 | Active | 84 | ACTIVE |  |  | 2023 | Khuu, Philander | Khuu, Philander | 07-Mar-23 |  |  | 8098035.31 | 2043798.25 | 8098035.31 | 8098035.31 | Mark Bobanovic | Transpw | 31-Aug-23 | 31-Aug-23 | 12-Jun-23 | 12-Jun-23 |  |  |  |  | 0
643961 | YL41184 - 2023 SR MIDDLEGATE RD & STANFIELD RD - P09461 | 800 - Mavis | 151044 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 08-Nov-22 | 1 | 1 | 76321.21 | 56556.09 | 76321.21 | 76321.21 | Paul Murphy |  | 02-Mar-23 | 28-Aug-23 | 23-Jan-23 | 03-Feb-23 | 11-Feb-23 |  |  |  | 0
644014 | 300 STATESMAN DRIVE | 800 - Mavis | 150386 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644036 | 1020 DIXIE ROAD - MISS - NS - 3PH - NS00052877 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644051 | 820 DUNDAS ST E | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644076 | 263 VICTORIA ST | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644080 | 135 CAPITAL CRT | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 09-Nov-22 |  |  | 60024.24 | 5568.79 | 60024.24 | 60024.24 | Peter Costantini |  | 21-Apr-23 | 31-Jul-23 | 14-Apr-23 |  |  | Customer |  |  | 0
644081 | 1480 BRITANNIA RD E | 800 - Mavis | 150384 | Active | 81 | Upload Completed |  |  | 2023 | Mustachi, Randy | Abucejo, Chariz |  |  |  | 274948.96 | 8741.43 | 274948.96 | 274948.96 | XMoinuddin, Saad |  |  | 26-Jul-23 | [6 empty] | 0
644082 | 800 LAKEFRONT PROMENADE | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644085 | TX10286 VAULT REMOVAL (PCB) - 7 ELIZABETH ST. N. | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644092 | 1 FAIRVIEW ROAD | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644097 | (SG1352) 2023 SG REPLACEMENT - 649 QUEENSWAY WEST | 800 - Mavis | 150495 | Active | 70 | ACTIVE |  |  | 2023 | Lucic, Marko | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644115 | RER MX - LW CONFLICT #LW21 - CAWTHRA ROAD - REMOVALS | 800 - Mavis | 150594 | Active | 98 | COMPLETE |  |  | 2022 | Tobin, Michael | Khuu, Philander | 21-Apr-22 |  |  | 16821.64 | 31087.84 | 16821.64 | 16821.64 | Rob Elliot |  | 03-Jun-22 | 26-Jul-23 | 01-Jun-22 | 02-Aug-22 | 04-Aug-22 | Lines | Lines |  | 0
644129 | TX2519 VAULT RENEWAL - 3131 JAGUAR VALLEY DRIVE | 800 - Mavis | 151043 | Active | 82 | RELEASED |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 17-Jan-23 | 1 |  | 259471.15 | 18948.24 | 290819.55 | 259471.15 | Antonio Mina | Somervl | 02-Aug-23 | 25-Aug-23 | 04-Jul-23 |  |  | Lines |  |  | -31,348.40
644128 | TX8769 VAULT RENEWAL - 3233 BRANDON GATE DR | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | ($446.21) |  | 0 | XMoinuddin, Saad |  |  | 18-Aug-22
644127 | TX14496 VAULT RENEWAL - 120 TRADERS BLVD E | 800 - Mavis | 151043 | Active | 40 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644153 | 220 ADMIRAL BLVD INDUSTRIAL BUILDING | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644152 | 290 DERRY RD W PACINI RESTAURANT | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Central South |  |  |  | 0 | 2849.41 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644169 | MEADOWVALE ROTARY PARK | 800 - Mavis | 150384 | Active | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Macasaet, Ricardo |  |  |  | 0 | 2697.27 |  | 0 | XMoinuddin, Saad |  |  | 26-Jul-23
644208 | 1101 CLARKSON ROAD - NEW SERVICE - 347/600V - 2500A | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mandic, Goran | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644229 | PROLOGIS ARGENTIA 58MW 44KV CO SUBSTATION | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644228 | PROLOGIS MILLCREEK 58MW 44KV CO SUBSTATION | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644230 | P06387 - BURNHAMTHORPE RD W & GRAND PARK DR - P06387 - LT31057 REMOVAL | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 22-Mar-22 |  |  | 106883.95 | 167664.47 | 106883.95 | 106883.95 | Gregory Dunfield |  | 28-Mar-22 | 02-Mar-23 | 28-Mar-22 | 20-Mar-22 | 04-Apr-22 |  | Lines |  | 0
644234 | 2470 STANFIELD ROAD - UPGRADE SERVICE - 347/600V - 8000KVA | 800 - Mavis | 150384 | Active | HO | ACTIVE |  |  | 2023 | Mustachi, Randy | Ferry, Rodnne | 14-Jul-22 |  |  | 249617.63 | 187664.59 | 249617.63 | 249617.63 | Peter Costantini | Somervl | 08-Jun-23 | 21-Aug-23 | 10-Apr-23 | 06-Sep-22 |  |  |  |  | 0
644236 | U/G DISTRIBUTION AUTOMATION - GROSSBEAK MS | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE | High | SwGear | 2022 | Houston, Andrew | Zaghloul, Sam | 27-May-22 | 2 | 2 | 579686.89 | 668043.42 | 459814.15 | 579686.89 | Antonio Mina | Transpw | 05-Aug-22 | 14-Feb-23 | 30-May-22 | 30-May-22 | 14-Jul-22 |  |  |  | 119,872.74
644246 | 1077 NORTH SERVICE ROAD - 3MVA PADMOUNT TRANSFORMER TESLA CHARGING STATION | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia | 26-Jul-23 |  |  | 292985.6 | 15618.35 | 292985.6 | 292985.6 | Peter Costantini | Somervl | 25-Aug-23 | 25-Aug-23 | 14-Aug-23 | [5 empty] | 0
644247 | 5980 HURONTARIO STREET - MISS - NS - 3PH - 1MVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644248 | 2645 ROYAL WINDSOR DRIVE - MISS - NS - 3PH - 2MVA | 800 - Mavis | 150384 | Active | HO | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 09-Jan-23 |  |  | 183274.55 | 111854.53 | 183274.55 | 183274.55 | Peter Costantini | Somervl | 23-May-23 | 09-Aug-23 | 08-May-23 | 27-Apr-23 |  |  |  |  | 0
644249 | 2475 MEADOWPINE BLVD. - MISS - NS00193451 - 3PH - 2000KVA | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mandic, Goran | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644250 | 135 CITY CENTRE DRIVE - NS - 3PH - 3MVA | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
641238 | METROLINX | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2021 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 27115.59 |  | 0 | Gregory Dunfield |  | 25-Jan-22 | 22-Nov-22 | 25-Jan-22 | 01-Dec-21 | 01-Dec-21 | xBy-passed | xBy-passed
644263 | 3105 PEPPER MILL CRT - MISS - NS00156882 - 3PH | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mandic, Goran | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644404 | 6295 NORTHAM DR UNIT 1-4 PAD TX 1 MVA | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mandic, Goran | Hulnitski, Pavel | 09-Jan-23 |  |  | 109808.91 | 154896.06 | 109808.91 | 109808.91 | Peter Costantini | Somervl | 21-Apr-23 | 26-Jul-23 | 11-Apr-23 | 01-Feb-23 |  |  |  |  | 0
644424 | HEMUS SQUARE UG CABLE REPLACEMENT | 800 - Mavis | 151901 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 18-Jan-23 |  |  | 1145499.14 | 68782.04 | 1145499.14 | 1145499.14 | Antonio Mina | Transpw | 12-Oct-23 | 24-Aug-23 | 17-Aug-23 | 23-Jun-23 |  |  |  |  | 0
644426 | 100 QUEENSWAY (HOSPITAL) - MISS - NS - 3PH - PRIMARY FEEDS | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mandic, Goran | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644434 | 2023 SWGR RENEWAL - SG1449, 3500 LAIRD RD | 800 - Mavis | 151091 | Active | 92 | ANALYZE | High | SwGear | 2023 | Lucic, Marko | Tempra, Troylan | 08-Dec-22 | 1 | 1 | 164800.89 | 60801.22 | 164800.89 | 164800.89 | Antonio Mina |  | 01-Mar-23 | 11-Aug-23 | 08-Feb-23 | 07-Mar-23 | 21-Mar-23 | Lines | Lines |  | 0
644474 | SG1314 - 2023 SG RENEWAL - 5825 EXPLORER DR | 800 - Mavis | 151091 | Active | 70 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  | 1 |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644475 | SG1814 - 2022 SG RENEWAL - NORTH OF 5884 TURNEY DR | 800 - Mavis | 151091 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644479 | 2425 MEADOWPINE BLVD/ MISS/ NS / 3 PH PAD TX | 800 - Mavis | 150384 | Active | 91 | ANALYZE |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 22-Nov-22 |  |  | 474625.5 | 375610.88 | 474625.5 | 474625.5 | Peter Costantini | Somervl | 09-Mar-23 | 26-Jul-23 | 07-Feb-23 | 02-Feb-23 | 28-Jun-23 |  | Customer |  | 0
644493 | 2023 SWGR RENEWAL - SG1159, 3086 FIELDGATE DR | 800 - Mavis | 151091 | Active | 92 | ANALYZE | High | SwGear | 2023 | Lucic, Marko | Tempra, Troylan | 08-Dec-22 | 1 | 1 | 162996.31 | 161429.76 | 162996.31 | 162996.31 | Antonio Mina |  | 16-Jun-23 | 26-Jul-23 | 05-Jun-23 | 10-May-23 | 24-May-23 | Lines |  |  | 0
644495 | 2023 SWGR REPLACEMENT - SG1830, 3750 BRANDON GATE | 800 - Mavis | 151091 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  | 1 |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644494 | 2023 SWGR RENEWAL - SG1131, HILLCREST AVE AT ROCK HARBOUR RD | 800 - Mavis | 151091 | Active | 92 | ANALYZE | High | SwGear | 2023 | Lucic, Marko | Tempra, Troylan | 08-Dec-22 | 1 | 1 | 164816.72 | 153659.17 | 164816.72 | 164816.72 | Glenn Guile |  | 14-Feb-23 | 26-Jul-23 | 03-Feb-23 | 03-Apr-23 | 28-Apr-23 |  | Lines |  | 0
644551 | LT71089 - 2022 DA - ERIN MILLS PKWY & BRITTANNIA RD W - P20409 | 800 - Mavis | 151092 | Inactive | 99 | COMPLETE | High | DA | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Mar-22 | 1 | 1 | 157533.45 | 139178.9 | 145934.98 | 157533.45 | Gregory Dunfield |  | 15-Jun-22 | 02-Mar-23 | 16-May-22 | 16-May-22 | 13-Dec-22 | Materials | Materials |  | 11,598.47
644562 | 3055 VEGA BLVD - MISS - NS00161258 - 3PH | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644613 | 780 SOUTH SHERIDAN WAY SHELL ELECTRIC CHARGERS 500KVA NEW TX | 800 - Mavis | 150384 | Active | 95 | ANALYZE |  |  | 2023 | Mandic, Goran | Hulnitski, Pavel | 06-Oct-22 |  |  | 85031.72 | 90583.76 | 85031.72 | 85031.72 | Peter Costantini | Somervl | 10-Feb-23 | 26-Jul-23 | 16-Jan-23 | 29-Nov-22 | 27-Jan-23 |  |  |  | 0
644639 | 2023 SWGR RENEWAL, SG1539 REMOVAL, 2330 ARGENTIA RD. | 800 - Mavis | 151091 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 01-Dec-22 | 1 | 1 | 212290.93 | 190322.73 | 212290.93 | 212290.93 | Antonio Mina | Somervl | 03-Mar-23 | 26-Jul-23 | 08-Feb-23 | 21-Mar-23 | 10-May-23 | Lines | Lines |  | 0
644716 | 2023 EM UG-DOUBLE LUGGED FDR RECONFIGURATION KINGSBRIDGE GARDEN CIRCLE | 800 - Mavis | 151451 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 12-Jan-23 |  |  | 676639.25 | 71505.07 | 678149.34 | 676639.25 | Antonio Mina | Transpw | 31-May-23 | 26-Sep-23 | 18-Apr-23 | 20-Apr-23 |  | Contractor | Contractor |  | -1,510.09
644725 | NEW IN-LINE SWITCH ON P06390 AT BURNHAMTHORPE RD W & GRAND PARK DR | 800 - Mavis | 151910 | Active | HO | H8 |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 14-Mar-22 | 1 |  | 25884.86 | 3930.23 | 25884.86 | 25884.86 | Gregory Dunfield |  | 21-Jun-22 | 01-Aug-23 | 15-Jun-22 |  |  | Customer | Customer |  | 0
644759 | 7300 WEST CREDIT- MISS- NS00077654-3PH-150KVA | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mandic, Goran | Roy, Akash | 07-Jul-22 |  |  | 122433.18 | 124979.35 | 122433.18 | 122433.18 | Peter Costantini | Somervl | 14-Oct-22 | 10-Aug-23 | 19-Sep-22 | 18-Nov-22 |  | Customer |  |  | 0
644763 | 1399 CAWTHRA ROAD - SERVICE UPGRADE - 1000A 347/600V | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia | 05-Jul-23 |  |  | 70200.8 | 18016.65 | 70200.8 | 70200.8 | Peter Costantini | N/A | 12-Sep-23 | 12-Sep-23 | 08-Sep-23 | [5 empty] | 0
644773 | 5270 SOLAR DRIVE - WAREHOUSE DESIGN | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 20-Oct-22 |  |  | 280065.68 | 258343.25 | 280065.68 | 280065.68 | Peter Costantini | Somervl | 14-Dec-22 | 26-Jul-23 | 05-Dec-22 | 14-Dec-22 | 21-Apr-23 | Materials | Customer |  | 0
644782 | ANCHOR RELOCATION AT P06498 - NOVAR RD. | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Garcha, Tirath | 23-Feb-22 | 1 | 1 | 8430.76 | 4716.22 | 8430.76 | 8430.76 | Paul Murphy |  | 29-Mar-22 | 23-Sep-22 | 28-Mar-22 | 16-Mar-22 | 17-Mar-22 |  |  |  | 0
644801 | 2023 SWGR RENEWAL, SG1512 REMOVAL, SW BURNHAMTHORPE RD & CREDIT WOODLANDS | 800 - Mavis | 151091 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 01-Dec-22 | 1 | 1 | 210773.04 | 123149.24 | 210773.04 | 210773.04 | Antonio Mina | Somervl | 26-Jun-23 | 26-Jul-23 | 20-Mar-23 | 21-Mar-23 | 19-Jul-23 | Lines | Lines |  | 0
644804 | PREMIUM WAY TEMPORARY STUB POLE INSTALLATIONS | 800 - Mavis | 152302 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 09-Jun-22 |  |  | 26363.63 | 18231.14 | 26363.63 | 26363.63 | Paul Murphy |  | 27-Jul-22 | 23-Sep-22 | 25-Jul-22 | 24-Jun-22 | 30-Jun-22 |  |  |  | 0
644858 | NATIONAL HOMES (1240 BRITANNIA RD) - SUBD RES EDS | 800 - Mavis | 150652 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644859 | SKY-CAWTHRA HOMES | 800 - Mavis | 150652 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644865 | 157 CITY CENTRE DRIVE - MISS - BLDG 3 - NS00199572 - 3PH - 3MVA | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Garcha, Tirath | 24-Apr-23 |  |  | 227212.48 | 12250.67 | 227212.48 | 227212.48 | Peter Costantini | Transpw | 30-Nov-23 | 30-Nov-23 | 01-Nov-23 | [5 empty] | 0
644864 | 4023 THE EXCHANGE - MISS - BLDG 2 - NS00161140 - 3PH - C.O. TX 3MVA | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Garcha, Tirath | 26-Jul-23 |  |  | 56749.26 | 11538.61 | 56749.26 | 56749.26 | Peter Costantini | N/A | 30-Oct-23 | 30-Oct-23 | 23-Oct-23 | [5 empty] | 0
644840 | 2022 EM OH, P12296 ADDITIONAL GUYING - CAWTHRA RD | 800 - Mavis | 150823 | Active | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Mar-22 | 1 | 1 | 46065.61 | 17752.16 | 46065.61 | 46065.61 | Gregory Dunfield |  | 23-Jun-22 | 26-Jul-23 | 13-Jun-22 | 04-May-22 | 20-Jun-22 |  | Lines |  | 0
644905 | 6620 ROTHSCHILD TRAIL- 800A- 750KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644930 | 6501 GOREWAY DRIVE (GOREWAY ESSO) | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mustachi, Randy | Jacinto, Gerardo | 02-Nov-22 |  |  | 102962.39 | 59546.61 | 102962.39 | 102962.39 | Peter Costantini | Somervl | 13-Dec-22 | 26-Jul-23 | 05-Dec-22 | 17-Nov-22 | 13-Dec-22 |  |  |  | 0
644938 | 2023 EM OH - EXBURY CRES & BLANFIELD RD | 800 - Mavis | 150823 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 10-Nov-22 |  |  | 110339.41 | 12795.3 | 110339.41 | 110339.41 | Gregory Dunfield |  | 13-Jul-23 | 04-Aug-23 | 27-Jun-23 | 28-Apr-23 |  |  |  |  | 0
644962 | HURONTARIO (LCBO) - MISS - NS00212505 - 3PH | 800 - Mavis | 151610 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
644964 | 86 DUNDAS STREET EAST DEVELOPMENT - POLE RELOCATION | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 28-Mar-22
644997 | 2022 EM UG, 1 FAIRVIEW RD. EAST - DUCTBANK RELOCATION | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2022 | Lucic, Marko | Cudzilo, Tomasz | 16-Jun-22 |  |  | 36780.23 | 226564.59 | 36780.23 | 36780.23 | Antonio Mina | Somervl | 06-Jul-22 | 23-May-23 | 22-Jun-22 | 22-Jun-22 | 15-Jul-22 |  |  |  | 0
644989 | 5100 SATELLITE DRIVE - MISS - NS00219622 - 3PH | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash | 19-Jan-23 |  |  | 204663.04 | 141919.2 | 204663.04 | 204663.04 | Peter Costantini | Somervl | 01-May-23 | 02-Aug-23 | 24-Apr-23 | 05-May-23 |  | Customer |  |  | 0
645075 | QEWCR - PREMIUM WAY PERMANENT POLE INSTALLATIONS BETWEEN LYNCHMERE AND DICKSON | 800 - Mavis | 150673 | Active | 82 | RELEASED |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka | 21-Apr-23 |  |  | 1024616.7 | 31500.04 | 1024616.7 | 1024616.7 | K-Line Construction | K-Line | 29-Sep-23 | 02-Oct-23 | 03-Jul-23 | [5 empty] | 0
645098 | 2023 EM OH MISSISSAUGA RD FR KANE RD TO INDIAN RD REPLACE NO 6 CONDUCTORS | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 10-Nov-22 |  |  | 53896.92 | 47290.64 | 46904.92 | 53896.92 | Matthew Beach |  | 03-Feb-23 | 17-Jul-23 | 23-Jan-23 | 25-Jan-23 | 21-Feb-23 |  |  |  | 6,992.00
645130 | 1445 LEWISHAM DR- 300KVA - 800A UPGRADE | 800 - Mavis | 151610 | Active | 84 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 14-Jul-22 |  |  | 105703.15 | 52241.12 | 105703.15 | 105703.15 | Peter Costantini | Somervl | 29-Jun-23 | 15-Aug-23 | 09-Jun-23 | 04-Jul-23 |  | Customer |  |  | 0
645232 | 2140 GORDON DRIVE - 100KVA -600A 1-PHASE UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mustachi, Randy | Hulnitski, Pavel | 07-Jun-22 |  |  | 70068.31 | 56524.26 | 70068.31 | 70068.31 | Peter Costantini | Somervl | 31-Aug-22 | 22-Nov-22 | 08-Aug-22 | 24-Jun-22 | 19-Jul-22 |  |  |  | 0
645271 | 2340 CONFEDERATION PARKWAY-TEMPORARY | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 16-Nov-22 |  |  | 276586.4 | 46052.52 | 276586.4 | 276586.4 | Peter Costantini |  | 26-Sep-23 | 26-Sep-23 | 05-Sep-23 | [5 empty] | 0
645276 | RER MX - LW29 - WINSTON CHURCHILL/HONI CONNECTION | 800 - Mavis | 150594 | Active | 84 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin | 07-Feb-23 |  |  | 1385658.02 | 1243231.47 | 1375196.44 | 1385658.02 | Paul Murphy | Transpw | 12-Sep-23 | 29-Dec-23 | 06-Apr-23 | 14-Feb-23 |  |  |  |  | 10,461.58
645193 | 6370 BELGRAVE RD | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 21-Sep-22 |  |  | 147319.19 | 136428.76 | 147319.19 | 147319.19 | Peter Costantini | Somervl | 13-Apr-23 | 02-Aug-23 | 28-Nov-22 | 28-Nov-22 |  | Customer | Customer |  | 0
645301 | 6767 PACIFIC CIR | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645302 | 5105 HURONTARIO | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 347.8 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645322 | 3069 WOLFEDALE SUBSTATION REPLACEMENT WITH PADMOUNTED TX | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645334 | BRITANNIA ROAD WEST ANCHOR RELOCATIONS - REGION OF PEEL | 800 - Mavis | 150675 | Active | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell |  |  |  | 17051.08 | 18461.31 | 17051.08 | 17051.08 | Gregory Dunfield |  | 05-Jul-22 | 26-Jul-23 | 05-Jul-22 | 16-Jul-22 | 16-Jul-22 | xBy-passed | xBy-passed |  | 0
645335 | 6927 MARITZ DRIVE - NS00223023 - C.O. SUB - 15MVA | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645337 | RESIDENTIAL LAYOUTS 2022 | 800 - Mavis | 150388 | Inactive | 99 | CANCELLED |  |  | 2023 | Mustachi, Randy | Ross, Stuart |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645360 | 2023 - YL74635 TO YL64085 MAIN FEEDER REMOVAL (C5M37-27.6KV) | 800 - Mavis | 151895 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 31-Jan-23 |  |  | 796122.71 | 715639.73 | 796122.71 | 796122.71 | Antonio Mina | Transpw | 14-Jul-23 | 02-Nov-23 | 12-Jun-23 | 15-May-23 | 17-Jul-23 |  |  |  | 0
645362 | 2023 - MISSISSAUGA VALLEY AND BLOOR - REAR LOT RELOCATIONS (PHASE 1) | 800 - Mavis | 150495 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645418 | LT41053 - BURNHAMTHORPE RD E & FIELDGATE DR - P05397 | 800 - Mavis | 150690 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645317 | LT61106 - 2023 DA - BURNHAMTHORPE RD W AND WINSTON CHURCHILL BLVD - P20893 | 800 - Mavis | 151092 | Active | 92 | ANALYZE | High | DA | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 08-Nov-22 | 1 | 1 | 135271.23 | 153534.12 | 135271.23 | 135271.23 | Matthew Beach |  | 14-Feb-23 | 26-Jul-23 | 30-Jan-23 | 02-Mar-23 | 11-Apr-23 | Lines | Lines |  | 0
645429 | HARMONY CROSSING - SUBD RES EDS | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645434 | MATHESON BLVD EAST MUT - POLE RELOCATION | 800 - Mavis | 150675 | Active | 92 | ANALYZE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka | 28-Mar-23 |  |  | 28280.95 | 30460.44 | 28280.95 | 28280.95 | Gregory Dunfield |  | 19-May-23 | 26-Jul-23 | 17-May-23 | 05-May-23 | 05-May-23 |  |  |  | 0
645443 | 2023 - SIR JOHN HOMESTEAD UG CABLE REPLACEMENT PHASE 2 | 800 - Mavis | 151518 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Ferry, Rodnne | 17-Jan-23 |  |  | 1354651.37 | 708423.71 | 1354651.37 | 1354651.37 | Antonio Mina | Transpw | 09-Jun-23 | 23-Aug-23 | 17-Apr-23 | 20-Apr-23 |  | Contractor | Contractor |  | 0
645524 | 5475 DIXIE RD | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645528 | (SG1327 AND SG1330) 2023 SG REPLACEMENT - ERIN CENTRE AND MISSISSAUGA RD | 800 - Mavis | 151091 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Ferry, Rodnne | 08-Dec-22 | 2 | 2 | 68200.54 | 62341.26 | 68200.54 | 68200.54 | Antonio Mina | Somervl | 16-Mar-23 | 26-Jul-23 | 08-Feb-23 | 10-Mar-23 | 21-Mar-23 | Lines | Lines |  | 0
645578 | POLE REPLACEMENT P17137 - MISSISSAUGA RD & ROTHESAYCT | 800 - Mavis | 151063 | Active | 40 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645583 | 2585 MEADOWPINE BLVD | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645585 | 6301 SILVER DART DR | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 417.37 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645587 | 0 AIRPORT RD | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645590 | 1115 CARDIFF BLVD - MISS - UP - 3PH - UP00225289 | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 27-Oct-22 |  |  | 198604.33 | 124957.54 | 198604.33 | 198604.33 | Peter Costantini | Somervl | 01-Feb-23 | 09-Aug-23 | 16-Jan-23 | 15-Nov-22 |  |  |  |  | 0
645593 | 800 HYDRO RD | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645592 | 175 WATLINE AVE | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645665 | 3160 DERRY RD E - MISS - NS - 3PH - 2500KVA - NS00211487 | 800 - Mavis | 150384 | Active | 95 | ANALYZE |  |  | 2023 | Mustachi, Randy | Roy, Akash | 18-Nov-22 |  |  | 200086.41 | 243852.77 | 200086.41 | 200086.41 | Peter Costantini | Somervl | 20-Jan-23 | 26-Jul-23 | 03-Jan-23 | 16-Dec-22 | 31-Jan-23 |  | Customer |  | 0
645685 | ANTIGUA ROAD DEVELOPMENT - SUBD RES EDS | 800 - Mavis | 150652 | Active | 70 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645706 | (1925(B) & 1965(A) 0 MEADOWVALE BLVD / TRIBAL PARTNERS | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo | 17-Jul-23 |  |  | 609131.94 | 9791.36 | 609131.94 | 609131.94 | Peter Costantini | Somervl | 02-Oct-23 | 02-Oct-23 | 05-Sep-23 | [5 empty] | 0
645731 | BRIGHTWATER DEVELOPMENT - PINE AVE SOUTH SECONDARY RELOCATIONS | 800 - Mavis | 150675 | Active | 98 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 22-Aug-22 |  |  | 71752.84 | 55224.36 | 71752.84 | 71752.84 | Gregory Dunfield | Somervl | 18-Nov-22 | 26-Jul-23 | 07-Nov-22 | 13-Dec-22 | 13-Dec-22 | Customer | Customer |  | 0
645747 | OH TRANSFORMER REMOVAL AT 250 LAKESHORE RD E - P03775 | 800 - Mavis | 150823 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645773 | AREA 39 CABLE INJECTION ERIN MILLS & THOMAS ST | 800 - Mavis | 150495 | Active | 40 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645814 | 2390 ARGENTIA RD - MISS - UP - 3PH - 150KVA - NS00240339 | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash | 24-Jan-23 |  |  | 99554.13 | 63303.82 | 99554.13 | 99554.13 | Peter Costantini | Somervl | 23-Jun-23 | 15-Aug-23 | 05-Jun-23 | 04-Jul-23 |  | Customer |  |  | 0
645833 | 100 QUEENS WAY W (PARKADE) - MISS - NS - 3PH - NS00201108 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
645847 | 2023 EM OH - ANIMAL ABATEMENT - 52F1 | 800 - Mavis | 150823 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Ferry, Rodnne | 10-Nov-22 |  |  | 45377.79 | 34563.46 | 45377.79 | 45377.79 | Gregory Dunfield |  | 12-Jun-23 | 31-Jul-23 | 01-Jun-23 | 28-Apr-23 |  |  |  |  | 0
646354 | 6005 ERIN MILLS - MISS - NS - 1200A (EXP. DEM:846KW PER M-REZA) | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
646353 | 6005 ERIN MILLS - MISS - NS - 1200A (EXP. DEM:846KW PER M-REZA) | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
646361 | LT117748 & LT118866 - 2023 DA - BRITANNIA RD AND NINTH LINE - P19900 & P19899 | 800 - Mavis | 151092 | Active | 82 | RELEASED | High | DA | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Nov-22 | 2 |  | 215088.01 | 5954.05 | 215088.01 | 215088.01 | Matthew Beach |  | 21-Jul-23 | 17-Aug-23 | 03-Jul-23 | [5 empty] | 0
646363 | LT101406 - 2023 DA - BRITANNIA E OF NINTH LINE - P06928 | 800 - Mavis | 151092 | Active | 84 | ACTIVE | High | DA | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Nov-22 | 1 |  | 150622.48 | 193509.84 | 150622.48 | 150622.48 | Matthew Beach |  | 22-Aug-23 | 23-Aug-23 | 07-Aug-23 | 15-May-23 |  |  |  |  | 0
646362 | LT102149 -2023 DA - THOMAS ST & OSCAR PETERSON BLVD - P08389 | 800 - Mavis | 151092 | Active | 82 | RELEASED | High | DA | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Nov-22 | 1 |  | 143750.69 | 3122.97 | 143750.69 | 143750.69 | Gregory Dunfield |  | 20-Jul-23 | 15-Aug-23 | 04-Jul-23 | [5 empty] | 0
646366 | L34526 - 2023 DA - DUNDAS ST W & WINSTON CHURCHILL BLVD - P10706 | 800 - Mavis | 151092 | Active | 84 | ACTIVE | High | DA | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 09-Dec-22 | 1 |  | 103493.92 | 89869.71 | 103493.92 | 103493.92 | Paul Murphy |  | 17-Oct-23 | 17-Oct-23 | 03-Oct-23 | 24-May-23 |  |  |  |  | 0
646365 | L65375 - 2023 DA - EGLINTON AVE W & NINTH LINE - P08467 | 800 - Mavis | 151092 | Active | 82 | RELEASED | High | DA | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 09-Dec-22 | 1 |  | 156856.62 | 4346.94 | 156856.62 | 156856.62 | Matthew Beach |  | 31-Oct-23 | 31-Oct-23 | 25-Sep-23 | [5 empty] | 0
646364 | LT61120 - 2023 DA - THOMAS ST & HIGHBANK RD - P16164 | 800 - Mavis | 151092 | Active | 82 | RELEASED | High | DA | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Nov-22 | 1 |  | 149150.12 | 4928.21 | 149150.12 | 149150.12 | Gregory Dunfield |  | 24-Aug-23 | 25-Aug-23 | 08-Aug-23 | [5 empty] | 0
646573 | 4116 PARKSIDE VILLAGE DRIVE | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
646654 | UG CABLE REPLACEMENT-MILLCREEK & ERIN MILLS PKWY PHASE 2 | 800 - Mavis | 151516 | Active | 91 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 09-Mar-23 |  |  | 1365322.91 | 1037124.93 | 1365322.91 | 1365322.91 | Antonio Mina | Transpw | 04-Jul-23 | 31-Aug-23 | 24-Apr-23 | 24-Apr-23 |  |  |  |  | 0
646670 | 855 BRITANNIA ROAD EAST / MISS / NS | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
646673 | 2180 MEADOWVALE BLVD - MISS - UP - 3PH - UP00250361 | 800 - Mavis | 150384 | Active | HO | RELEASED |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 28-Mar-23 |  |  | 118895.54 | 4843.26 | 118895.54 | 118895.54 | Peter Costantini | Somervl | 19-Jun-23 | 15-Aug-23 | 01-Jun-23 | [5 empty] | 0
646698 | 6627 TENTH LINE WEST - MISS - NS - 3PH - NS00242317 | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 22-Jun-23 |  |  | 154196.27 | 6469.12 | 154196.27 | 154196.27 | Peter Costantini | Somervl | 01-Aug-23 | 11-Aug-23 | 18-Jul-23 | [5 empty] | 0
646781 | LT31164 & LT31165 - 2023 SR - BURNHAMTHORPE RD W & KARIYA DR - P06560 & P06559 | 800 - Mavis | 151044 | Active | 82 | RELEASED |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 19-Jan-23 | 2 |  | 236667.74 | 7273.16 | 236667.74 | 236667.74 | Gregory Dunfield |  | 26-Sep-23 | 27-Sep-23 | 11-Sep-23 | [5 empty] | 0
646779 | LT31159 - 2023 SR - GLEN ERIN DR & BURNHAMTHORPE RD W - P20804 | 800 - Mavis | 151044 | Active | 92 | ANALYZE | High | Switch | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Nov-22 | 1 | 1 | 141798.1 | 202155.59 | 141798.1 | 141798.1 | Paul Murphy |  | 07-Sep-23 | 07-Sep-23 | 05-Sep-23 | 27-Feb-23 | 05-Jun-23 |  |  |  | 0
646777 | LT91046 - 2023 SR -TORBRAM RD & KIMBEL ST - P14737 | 800 - Mavis | 151044 | Active | 92 | ANALYZE | High | Switch | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 07-Nov-22 | 1 | 1 | 204662.71 | 195619.79 | 204662.71 | 204662.71 | Paul Murphy |  | 03-May-23 | 27-Jul-23 | 21-Mar-23 | 07-Mar-23 | 31-Mar-23 |  |  |  | 0
646782 | LT710049 - 2023 SR - CREDITVIEW RD & SIR MONTEY'S DR - P19364 | 800 - Mavis | 151044 | Active | 82 | RELEASED | High |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 08-Dec-22 | 1 |  | 156879.37 | 5557.34 | 156879.37 | 156879.37 | Gregory Dunfield |  | 21-Jul-23 | 10-Aug-23 | 11-Jul-23 | [5 empty] | 0
646854 | 2550 HURONTARIO ST.(LCBO) - MISS - NS - 3PH - NS00212505 | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
646891 | EXPANSION - 152 BURNHAMTHORPE RD WEST - EXCHANGE DISTRICT SOUTH | 800 - Mavis | 152302 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
646892 | 1106 WESTMOUNT AVE MISSISSAUGA - POLE RELOCATION | 800 - Mavis | 152302 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
646901 | 1110 CENTRAL PARKWAY WEST - POLE RELOCATION MISSISSAUGA | 800 - Mavis | 150675 | Active | 84 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo | 29-Mar-23 |  |  | 149995.2 | 14510.54 | 149995.2 | 149995.2 | Matthew Beach |  | 04-Jul-23 | 30-Aug-23 | 31-May-23 | 23-Jun-23 |  | Lines |  |  | 0
646908 | AVIATION RD & LAKESHORE RD E POLE RELOCATIONS | 800 - Mavis | 150675 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
646923 | 5835 AIRPORT ROAD SUNCOR ENERGY - POLE RELOCATIONS | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 3279.86 |  | 0 | XMoinuddin, Saad |  |  | 23-Sep-22
646952 | 2023 TX RENEWAL TX10094 & TX10095- 11 JOHN ST S | 800 - Mavis | 151043 | Active | 91 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 08-Dec-22 | 2 | 2 | 230844.81 | 133124.67 | 99386.13 | 230844.81 | Antonio Mina |  | 28-Jul-23 | 31-Aug-23 | 23-Jun-23 | 06-Jun-23 |  |  |  |  | 131,458.68
647011 | YL41062 - 2023 SR - HENSALL ST & CLAIRCREST AVE - P11345 | 800 - Mavis | 151044 | Active | 82 | RELEASED | High | Switch | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 08-Dec-22 | 1 |  | 131560.18 | 4980.62 | 131560.18 | 131560.18 | Gregory Dunfield |  | 19-Oct-23 | 19-Oct-23 | 10-Oct-23 | [5 empty] | 0
647012 | L34312 - 2023 SR - WOLFDALE RD & DUNDAS ST W - P07317 | 800 - Mavis | 151044 | Active | 82 | RELEASED | High | Switch | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 08-Dec-22 | 1 |  | 120567.97 | 12081.35 | 120567.97 | 120567.97 | Paul Murphy |  | 17-Oct-23 | 18-Oct-23 | 02-Oct-23 | [5 empty] | 0
647073 | MX - ECWE - AUC RELOCATIONS - COMMERCE TO ORBITER - PM | 800 - Mavis | 152439 | Active | 10 | ACTIVE |  |  | 2023 | Tobin, Michael | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647128 | 6501 MISSISSAUGA RD - 1500KVA - 1600A - INDUSTRIAL BUILDING | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647191 | 1440 ALDO DRIVE MISSISSAUGA - POLE RELOCATION | 800 - Mavis | 150675 | Active | 92 | ANALYZE |  |  | 2023 | Lacombe, Joel | Watters, Maxwell | 07-Sep-22 |  |  | 12515.25 | 5098.33 | 12515.25 | 12515.25 | Gregory Dunfield |  | 18-Oct-22 | 28-Jul-23 | 17-Oct-22 | 24-Feb-23 | 08-Mar-23 | Customer | Customer |  | 0
647193 | 129 HIGH STREET WEST - PADMOUNT TX RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647200 | 15 CP - 2023 POLE RENEWAL ROYAL WINDSOR DR 15 POLES | 800 - Mavis | 151063 | Active | 82 | RELEASED |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 15-Mar-23 | 15 |  | 977607.46 | 31770.45 | 977607.46 | 977607.46 | Paul Murphy | Somervl | 27-Dec-23 | 27-Dec-23 | 01-Sep-23 | [5 empty] | 0
647201 | WATERGARDEN DRIVE SWITCHGEAR 2457 RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 01-Sep-22
647227 | 2329 DOULTON DR - 1 PHASE 600A - 167KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647269 | EXPANSION - REGION OF PEEL - 85 ACORN PLACE | 800 - Mavis | 152302 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647318 | 4 1PH - 2023 TX - BATCH #1 - PCBS | 800 - Mavis | 151043 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Ferry, Rodnne | 30-Nov-22 | 4 | 4 | 60990.92 | 146185.29 | 60990.92 | 60990.92 | Antonio Mina | Somervl | 19-Jul-23 | 10-Aug-23 | 03-Jul-23 | 17-Jan-23 | 18-Jul-23 |  |  |  | 0
643921 | 6990 REXWOOD RD NEW TX ELECTRIC CHARGERS | 800 - Mavis | 150384 | Active | 91 | ACTIVE |  |  | 2023 | Mandic, Goran | Hulnitski, Pavel | 22-Aug-22 |  |  | 91917.51 | 69697.31 | 91917.51 | 91917.51 | Peter Costantini | Somervl | 28-Apr-23 | 26-Jul-23 | 03-Apr-23 | 06-Oct-22 | 27-Apr-23 |  |  |  | 0
647381 | 2023 EMERGING-POLE REMOVAL & UG SERVICE RELOCATION - 1413 GLENBURNIE RD | 800 - Mavis | 150823 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 15-Mar-23 |  |  | 75335.62 | 31414.04 | 75335.62 | 75335.62 | Antonio Mina | Somervl | 23-May-23 | 02-Aug-23 | 03-May-23 | 06-Jun-23 | 06-Jun-23 | Contractor | Contractor |  | 0
647384 | U/G DISTRIBUTION AUTOMATION - WINSTON MS | 800 - Mavis | 151092 | Active | 50 | ACTIVE |  |  | 2023 | Houston, Andrew | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647391 | 2022 - 2323 & 2300 CONFEDERATION PARKWAY - TX VAULT UPGRADES | 800 - Mavis | 151043 | Active | 70 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647450 | 152 BURNHAMTHORPE ROAD WEST - L5B4N4 (BUILDING D) | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647449 | 152 BURNHAMTHORPE ROAD WEST - L5B4N4 (BUILDING C) | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647448 | 152 BURNHAMTHORPE ROAD WEST - L5B4N4 (BUILDING B) | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647447 | 152 BURNHAMTHORPE ROAD WEST - L5B4N4 (BUILDING A) | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
640112 | 7134 AIRPORT - 150KVA TRANSFORMER UPGRADE | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Central South |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647553 | 2023 SWGR RENEWAL - SG1745 RODEO DR | 800 - Mavis | 151091 | Active | 92 | ANALYZE | High | SwGear | 2023 | Lucic, Marko | Tempra, Troylan | 09-Dec-22 | 1 | 1 | 267141.05 | 70578.09 | 267141.05 | 267141.05 | Antonio Mina | Somervl | 28-Aug-23 | 01-Sep-23 | 03-Aug-23 | 24-May-23 | 01-Jun-23 |  |  |  | 0
647623 | 2023 SWGR RENEWAL - SG1606, 3270 TACC DR | 800 - Mavis | 151091 | Active | 92 | ANALYZE | High | SwGear | 2023 | Lucic, Marko | Tempra, Troylan | 09-Dec-22 | 1 | 1 | 201793.85 | 43343.93 | 201793.85 | 201793.85 | Glenn Guile | Somervl | 28-Aug-23 | 01-Sep-23 | 03-Aug-23 | 30-May-23 | 17-Jul-23 |  |  |  | 0
647667 | 1644 GLENBURNIE ROAD - POLE RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2022 | Lacombe, Joel | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647727 | 2222 SOUTH SHERIDAN WAY #BLDG 1 - MISS - UP - 3PH - UP00279681 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647728 | 3473 WOLFEDALE RD- MISS - NS - 3PH - NS00243955 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647729 | 971 MATHESON BLVD E- MISS - UP - 3PH - UP00250505 | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 255.06 |  | 0 | XMoinuddin, Saad |  |  | 25-Jan-23
647730 | 5505 AMBLER DR - MISS - UP - 3PH - UP00262738 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647734 | 5985 RODEO DR UNIT 1 - MISS - UP - 3PH - UP00266122 | 800 - Mavis | 150384 | Active | 84 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene | 28-Mar-23 |  |  | 140955.66 | 11766.04 | 140955.66 | 140955.66 | Peter Costantini | Somervl | 16-Nov-23 | 16-Nov-23 | 01-Nov-23 | 22-Jun-23 |  |  |  |  | 0
647735 | 3650 DIXIE RD - MISS - UP - 3PH - UP00268034 | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647736 | 2495 MEADOWPINE BLVD UNIT 1 - MISS - UP - 3PH - UP00269320 | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 08-Feb-23
647755 | 7391 PACIFIC CIR BUILDING 9 - MISS - UP - 3PH - UP00279838 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647748 | P18440 POLE RELOCATION - 1400 AIMCO BLVD | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Watters, Maxwell | 05-Oct-22 |  |  | 12618.86 | 5589.74 | 12618.86 | 12618.86 | Gregory Dunfield |  | 22-Nov-22 | 03-Feb-23 | 21-Nov-22 | 24-Oct-22 | 24-Oct-22 |  |  |  | 0
647784 | 6760 CAMPOBELLO RD - MISS - UP - 3PH - UP00199289 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647793 | 3520 LAIRD RD. UNIT 1 - MISS - UP - 3PH - UP00271173 | 800 - Mavis | 150384 | Active | 95 | COMPLETE |  |  | 2022 | Mustachi, Randy | Yoon, Irene | 16-Nov-22 |  |  | 309821.26 | 244977.85 | 309821.26 | 309821.26 | Peter Costantini | Somervl | 28-Dec-22 | 27-Jul-23 | 01-Dec-22 | 18-Nov-22 | 02-Dec-22 |  |  |  | 0
647796 | KENAIDAN CONTRACTING LTD. | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2022 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647801 | QTY 1 1PH - 2023 TX O/H REPLACEMENT - BATCH #2 | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2023 | Lucic, Marko | Ferry, Rodnne |  |  |  | 10605.04 | 0 | 10605.04 | 10605.04 | XMoinuddin, Saad |  |  | 20-Jul-20 | [6 empty] | 0
647804 | 181 SUPERIOR BLVD - TRANSFORMER VAULT UPGRADE | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647822 | CENTRAL PARKWAY - PROP. INDUSTRIAL DEVELOPMENT | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647846 | LAKESHORE ROAD EAST & HYDRO ROAD POLE RELOCATIONS | 800 - Mavis | 150675 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647866 | 1079 ROOSEVELT ROAD - POLE RELOCATION | 800 - Mavis | 150675 | Active | 70 | ACTIVE |  |  | 2023 | Watters, Maxwell | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
647916 | 1 3PH - 2023 TX - TX12407 AT PENGILLEY PLACE | 800 - Mavis | 151043 | Active | 95 | ANALYZE |  |  | 2023 | Lucic, Marko | Ferry, Rodnne | 30-Nov-22 | 1 | 1 | 31568.24 | 25115.93 | 31568.24 | 31568.24 | Antonio Mina |  | 07-Feb-23 | 27-Jul-23 | 03-Feb-23 | 13-Jan-23 | 13-Jan-23 |  |  |  | 0
647973 | OH REBUILD - COURTNEY PARK & DIXIE | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
637258 | 2460 ROYAL WINDSOR DR - MISS - UP - 3PH 1500KVA CUST. OWNEDTX | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2022 | Mandic, Goran | Pellerin, Patrick | 05-Oct-22 |  |  | 21763.89 | 13631.22 | 21763.89 | 21763.89 | Gregory Dunfield |  | 14-Oct-22 | 19-Jan-23 | 13-Oct-22 | 13-Oct-22 | 14-Oct-22 |  |  |  | 0
648028 | 181 LAKESHORE ROAD WEST (BLDG. C1, C4, H) | 800 - Mavis | 150384 | Active | 82 | Upload Completed |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 231741.71 | 9051.04 | 231741.71 | 231741.71 | XMoinuddin, Saad |  |  | 27-Jul-23 | [6 empty] | 0
648029 | 2023 UG EMERGING - FEEDER TRANSFER-LONGSIDE DR AT HURONTARIO | 800 - Mavis | 151451 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 14-Mar-23 |  |  | 79160.73 | 67784.23 | 79160.73 | 79160.73 | Antonio Mina | Somervl | 29-May-23 | 02-Aug-23 | 03-May-23 | 10-May-23 | 17-Jul-23 | Contractor | Contractor |  | 0
648032 | BRIGHTWATER BUILDING D | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648043 | 30 HANSON RD - MISS - 3PH - 3000KVA - UP00281380 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648044 | 320 DERRY ROAD DEVELOPMENT - SUBD RES EDS | 800 - Mavis | 150652 | Active | 40 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648060 | 385 RATHBURN RD E - MISS - 3PH - 3000KVA - UP00283954 | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648065 | 6927 MARITZ DR - MISS - 3PH - PRI SW GEAR - NS00223023 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648064 | 4100 WESTMINSTER PL - MISS - 3PH - 3000KVA - UP00281773 | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648105 | PORT CREDIT SERVICE - 2 X 1500KVA 347/600V TXS | 800 - Mavis | 151948 | Active | 50 | ACTIVE |  |  | 2023 | Paesano, Andrew | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648118 | METROLINX | 800 - Mavis | 151948 | Active | 10 | ACTIVE |  |  | 2023 | Tobin, Michael | Patel, Ketan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648141 | 2023 TX RENEWAL - 7 1PH - BATCH 2 - LEAKERS | 800 - Mavis | 151043 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 31-Jan-23 | 7 | 7 | 128166.81 | 119225.48 | 128166.81 | 128166.81 | Antonio Mina |  | 10-May-23 | 16-Aug-23 | 26-Apr-23 | 06-Apr-23 | 13-May-23 |  | Lines |  | 0
648150 | 2023 SWGR RENEWAL - SG1646 REMOVAL ANNAGEM BLVD | 800 - Mavis | 151091 | Active | 92 | ANALYZE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 13-Dec-22 | 1 | 1 | 88658.88 | 70339.46 | 88658.88 | 88658.88 | Glenn Guile | Somervl | 22-Mar-23 | 27-Jul-23 | 08-Feb-23 | 06-Jan-23 | 28-Apr-23 |  | Lines |  | 0
648275 | EXPANSION - OXFORD - BLOCK 8 - PH2 | 800 - Mavis | 152302 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648301 | 580 SECRETARIAT CRT CO SUBSTATION | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 01-Dec-22
648315 | THE ERINDALE ACADEMY SCHOOL ADDITION | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
643486 | 1139 LORNE PARK ROAD | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648341 | 1245 EGLINTON AVE W 1500KVA PT | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648365 | 2023 - MISSISSAUGA VALLEY AND BLOOR - 41 MISS. VALLEY BLVD. | 800 - Mavis | 151424 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 23-Mar-23 |  |  | 1136112.69 | 25381.65 | 1136112.69 | 1136112.69 | Antonio Mina | Transpw | 12-Sep-23 | 12-Sep-23 | 17-Jul-23 | 19-Jul-23 |  |  |  |  | 0
648433 | GTAA 135M2 DEDICATED FEEDER EXPANSION | 800 - Mavis | 152302 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648442 | 1035 RONSA COURT - MISS - UP - 3PH - UP00299770 | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Yoon, Irene |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648447 | M CITY M5 TOWER 3MVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648464 | BRONTE COLLEGE/TRILLIUM REBUILD (TEMP WORK) | 800 - Mavis | 152330 | Active | 82 | RELEASED |  |  | 2023 | Jolie, Chris | Su, Jay | 18-Apr-23 |  |  | 277853.95 | 14358.59 | 277853.95 | 277853.95 | Antonio Mina | Transpw | 24-Jul-23 | 06-Sep-23 | 14-Jun-23 |  |  | Design |  |  | 0
648494 | THP SWITCHGEAR LOCATIONS & DUCTBANK TO HWY 10 | 800 - Mavis | 152302 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648546 | 0 SLATE DR EXPANSION | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648556 | 2023 CABLE INJECTION AREA 46 | 800 - Mavis | 151433 | Active | 91 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 30-Dec-22 |  |  | 1930769.27 | 265496.62 | 1930769.27 | 1930769.27 | Glenn Guile | Nvinium | 29-Dec-23 | 29-Dec-23 | 16-Feb-23 | 20-Jan-23 |  |  |  |  | 0
648585 | 5150 NINTH LINE (PH 2) - SUBD RES EDS | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648668 | 4005 HICKORY DR - NEW 500KVA - 600A - APPLEWOOD TOWNS | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 10-Jul-23 |  |  | 149217.87 | 4916.95 | 149217.87 | 149217.87 | Peter Costantini | Somervl |  | 17-Oct-23 | [6 empty] | 0
648674 | 1100 COURTNEYPARK DR E, 6400 SHAWSON DR, 1111 TRISTAR DR - SERVICE REMOVAL | 800 - Mavis | 150384 | Active | 95 | ANALYZE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 03-Jan-23 |  |  | 96162.96 | 28776.55 | 96162.96 | 96162.96 | Peter Costantini |  | 22-Feb-23 | 27-Jul-23 | 09-Jan-23 | 05-Jan-23 | 12-Jan-23 |  |  |  | 0
648737 | 2023 CABLE INJECTION AREA 30 | 800 - Mavis | 151428 | Active | 91 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan | 30-Dec-22 |  |  | 1390973.96 | 58805.14 | 1390973.96 | 1390973.96 | Glenn Guile | Nvinium | 29-Dec-23 | 29-Dec-23 | 16-Feb-23 | 20-Jan-23 |  |  |  |  | 0
648748 | OH REBUILD - COURTNEY PARK & DIXIE - PHASE 4 | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648747 | OH REBUILD - COURTNEY PARK & DIXIE - PHASE 3 | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648746 | OH REBUILD - COURTNEY PARK & DIXIE - PHASE 2 | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648762 | RER MX - KT CONFLICT #KT25 - GOREWAY DR: NASHUA DR TO ZAHAVY WAY | 800 - Mavis | 150593 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Su, Jay |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648763 | RER MX - KT CONFLICT #1048 - MALTON GO: CROSSING EAST OF DERRY RD. | 800 - Mavis | 150593 | Active | 10 | ACTIVE |  |  | 2023 | Khuu, Philander | Su, Jay |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648764 | RER MX - KT CONFLICT #KT27 - MALTON GO CROSSING: EAST OF MALTON STATION 2 | 800 - Mavis | 150593 | Active | 10 | ACTIVE |  |  | 2023 | Khuu, Philander | Su, Jay |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648768 | 5500 DIXIE RD - MISS - NS - 3PH - 2000KVA - NS00305191 | 800 - Mavis | 150388 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648778 | MAVIS ROAD WIDENING PHASE 2 - B/W DERRY RD W AND TWAIN AVE | 800 - Mavis | 150673 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648781 | UG CABLE REPLACEMENT-MILLCREEK & ERIN MILLS PKWY PHASE 3 | 800 - Mavis | 151516 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648827 | 5980 HURONTARIO - CIRCLE K EV CHARGERS - 600A | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648829 | 2980 ARGENTIA ROAD - CIRCLE K EV CHARGERS - 600A | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648828 | CLARKSON VILLAGE RES. DEVELOPMENT -OTC - (THE CRAFTSMAN CONDOS) | 800 - Mavis |  | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Garcha, Tirath |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648830 | 1345 TP LAKESHORE RD. E. | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648839 | LAKEVIEW DEVELOPMENT COMMUNITY PHASE 1 - SUBD ICI EDS | 800 - Mavis | 151610 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
648925 | 1110 LORNE PARK RD - SUBD RES EDS | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
648801 | 2025 SWGR RENEWAL- SG1567, LISGAR DRIVE | 800 - Mavis | 151091 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Central South |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
648890 | 2025 SWGR RENEWAL-SG1582, RED BUSH PARK | 800 - Mavis | 151091 | Active | 70 | ACTIVE |  |  | 2023 | Lucic, Marko | Central South |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
648918 | 2024 STAVEBANK POLE RENEWAL | 800 - Mavis | 151063 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Central South |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
648931 | POLE RELOCATION - 6020 WINSTON CHRUCHILL BLVD | 800 - Mavis | 150675 | Active | 40 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
648947 | 2023 TX RENEWAL, BATCH 2 - PRIORITIZED LIST (TX10316) | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2022 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
648958 | 2070 HADWEN RD 1000KVA PADMOUNT TRANSFORMER | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649082 | 250 DERRY ROAD WEST | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649105 | 4310 SHERWOODTOWNE BLVD | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649111 | 6501-6559 MISSISSAUGA RD - SERVICE REMOVALS | 800 - Mavis | 150384 | Active | 92 | ANALYZE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia | 15-Mar-23 |  |  | 81539.09 | 20737.94 | 81539.09 | 81539.09 | Peter Costantini | Somervl | 04-May-23 | 27-Jul-23 | 24-Apr-23 | 17-May-23 | 26-Jun-23 | Customer | Customer |  | 0
649135 | 551 AVONHEAD - MISS - NS - 3PH - PRIMARY CONN | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649252 | 45 GLENN HAWTHORNE BLVD TRANSFORMER UPGRADE | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649253 | 7095 REXWOOD RD - VAULT UPGRADE | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649254 | SLATE DR DEVELOPMENT | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649255 | 85 ACORN PL | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649320 | 5400 EXPLORER DRIVE | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
396869 | 2023 - UNDERGROUND REBUILD - BURNHAMTHORPE PHASE 2 | 800 - Mavis | 151408 | Active | 84 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 18-Jan-23 |  |  | 1248115.93 | 378456.41 | 1248115.93 | 1248115.93 | Antonio Mina | Transpw | 27-Jun-23 | 25-Aug-23 | 22-May-23 | 23-May-23 |  | Contractor |  |  | 0
649393 | 4530 ERIN MILLS PKWY - CIRCLE K EV CHARGERS - 600A | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649545 | 6610 EDWARDS BLVD - 3PH - 3000KVA TX | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649576 | ECWE - ICI PORTION | 800 - Mavis | 152439 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649581 | 6933 TOMKEN RD - BUILDING 3 - MISS - NS - 3PH - 150KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649634 | CAWTHRA ROAD CORRIDOR POLE RELOCATION | 800 - Mavis | 150673 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649672 | 2024 SWGR RENEWAL-SG1101, 6255 CANTAY ROAD | 800 - Mavis | 151091 | Active | 70 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649685 | 596 LOLITA GARDENS | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Central South |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649693 | 2167 ROYAL WINDSOR DR | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Sobiera, Patricia | Mustachi, Randy |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649719 | 3570 HAVENWOOD DR - COM GULLEDEN PARK - 300KVA - 400A | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649766 | BLACK WALNUT TRAIL & SMOKE TREE RD PADMONT TRANSFORMER | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Sobiera, Patricia | Mustachi, Randy |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649769 | 265 COURTNEYPARK DR E | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Sobiera, Patricia | Mustachi, Randy |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649787 | CUSTOMER INITIATED POLE RELOCATION - 1106 WESTMOUNT AVE | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 03-May-23
649869 | CENTRAL PARKWAY - PROP. INDUSTRIAL DEVELOPMENT BLDG. A | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649909 | TX12166 VAULT REMOVAL - 70 PARK ST E | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649908 | TX7678 VAULT REMOVAL - 2258 BROMSGROVE RD | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649921 | 320 INDIAN VALLEY TRAIL - 167KVA - 600A - 120/240V | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649923 | TX2756 VAULT REMOVAL - 3151 JAGUAR VALLEY BLVD | 800 - Mavis | 151043 | Active | 45 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649937 | THREE RESIDENTIAL TOWERS - 189 DUNDAS ST. W. | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649939 | BRIGHTWATER BLOCK G | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649969 | CUSTOMER INITIATED POLE RELOCATION - 6616 MCLAUGHLIN | 800 - Mavis | 150675 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649971 | 7440 TORBRAM RD - MISS - UP00314070 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649972 | DICKSON ROAD OH REBUILD - PHASE 1 | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Dejanovic, Dejan | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
649973 | 1100 COURTNEY PARK EAST - MISS - NS00320244 - 3PH - 2000KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650003 | 2024 SWGR RENEWAL -SG1791, 6200 CANTAY ROAD | 800 - Mavis | 151091 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650004 | 323 TRADERS BLVD - 400A - 300KVA TX | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650009 | 6085 CREDITVIEW RD - 2000A - TX TBD - TESLA CHARGERS | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650007 | 6616 MCLAUGHLIN ROAD - SUBD RES EDS | 800 - Mavis | 150652 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650011 | 1700 DERRY RD E - 1600A - 1500KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650010 | RER MX - KT CONFLICT KT1048 & KT27 - MALTON GO CROSSINGS | 800 - Mavis | 150593 | Active | 10 | ACTIVE |  |  | 2023 | Jolie, Chris | Su, Jay |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650013 | 6915 DIXIE RD - 1200A - 1000KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650015 | BRISTOLWOOD TEMP. POWER | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650044 | 900 SOUTHDOWN RD | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Sobiera, Patricia | Mustachi, Randy |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650080 | 2024 SWGR RENEWAL -SG1490, CHURCHILL MEADOWS AND ERIN CENTRE BLVD. | 800 - Mavis | 151091 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650103 | 3233 BRANDON GATE VAULT REMOVAL AND RELOCATION | 800 - Mavis | 150675 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650114 | 1381 LAKESHORE RD E - NEW 1600A - 1500KVA 347/600 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650121 | LISGAR STORMWATER PUMPING STATION | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Sobiera, Patricia | Mustachi, Randy |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650128 | CITY PARK HOMES POLE RELOCATION - SUBD CAP PROJ | 800 - Mavis | 151612 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650138 | 2240 SPEAKMAN DR - CO TX 4000KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650164 | CABLE REPLACEMENT - CHIGWEL COURT | 800 - Mavis | 151451 | Active | 82 | RELEASED |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 03-Jul-23 |  |  | 120731.81 | 6819.91 | 120731.81 | 120731.81 | Antonio Mina | Somervl | 28-Aug-23 | 28-Aug-23 | 16-Aug-23 | [5 empty] | 0
650176 | 5500 ROSE CHERRY PL - PT UPGRADE | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650182 | LAKEVIEW COMMUNITY DEVELOPMENT - EXPANSION | 800 - Mavis | 152302 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650185 | 2024 SWGR RENEWAL-SG1146, 1940 ARGENTIA - WALMART | 800 - Mavis | 151091 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
636632 | DS61129 - 2023 DA - EGLINTON AVE W & CREDIT VALLEY RD - P20709 | 800 - Mavis | 151092 | Active | 82 | RELEASED | High | DA | 2023 | Lucic, Marko | Matai, Ihssan (Sam) | 31-Mar-23 | 1 |  | 158054.48 | 8169.94 | 158054.48 | 158054.48 | Gregory Dunfield |  | 10-Nov-23 | 13-Nov-23 | 25-Oct-23 | [5 empty] | 0
650137 | CAWTHRA AND BLOOR_ MISSISSAUGA_ BETWEN B44328 AND TX5568 | 800 - Mavis | 151451 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650287 | LT31095- 2024 SWITCH RENEWAL- LINCOLN GREEN WY & ERIN MILLS PKWY - P11509 | 800 - Mavis | 151044 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650286 | LT71107- 2024 SWITCH RENEWAL- BRITANNIA RD - P08327 | 800 - Mavis | 151044 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650289 | CUSTOMER INITIATED SWITCHGEAR AND TRANSFORMER RELOCATION - WEBB DR | 800 - Mavis | 150673 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Odisho, Carlo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650330 | 1445 COURTNEYPARK DR E- MISS - 800A - 750KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650332 | YL8292 - 2024 SR DERRY RD E & TOMKEN RD - P19095 | 800 - Mavis | 151044 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650333 | LT61097 - 2024 SR ERIN MILLS PKWY & BANFIELD RD - P16139 | 800 - Mavis | 151044 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650336 | YL21351 - 2024 SR LAKESHORE RD W & LORNE PARK AVE - P05058 | 800 - Mavis | 151044 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650335 | YL6764 - 2024 SR EGLINTON AVE W & MAVIS RD - P08109 | 800 - Mavis | 151044 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650334 | YL21212 - 2024 SR - 1880 CARRERA CRT ON CNR ROW - P10-166 | 800 - Mavis | 151044 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650379 | LT31039 - 2024 SR - 2342 PYRAMID CRES ON HONI ROW - P10108 | 800 - Mavis | 151044 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650258 | 2024 SWGR RENEWAL - SG1435 FALCONER DR | 800 - Mavis | 151091 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Tempra, Troylan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650436 | 591 SECRETARIAT COURT - 600V - 600A - 500KVA | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650462 | 5400 EXPLORER DRIVE | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650473 | 6616 MCLAUGHLIN RD - MISS - 3PH - 750KVA - NS00370280 | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650481 | 1177 AEROWOOD DR - PT UPGRADE | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650485 | 1505 ARGENTIA STREET - 1200KVA 13.8KV 600-347 | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650542 | 6191 ATLANTIC DR - PT INSTALLATION | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650543 | CUSTOMER INITIATED OH POLE RELOCATION - LAKEFRONT PROMENADE | 800 - Mavis | 150675 | Active | 50 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650547 | TX4340 VAULT REMOVAL - 2235 HURONTARIO ST | 800 - Mavis | 151043 | Active | 82 | RELEASED |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 13-Jul-23 | 1 |  | 27046.77 | 7900.03 | 27046.77 | 27046.77 | Antonio Mina |  | 08-Sep-23 | 08-Sep-23 | 01-Sep-23 | [5 empty] | 0
650550 | TX2297 VAULT REMOVAL - 2339 PARK TOWERS AVE | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650549 | TX15863 VAULT REMOVAL - 325 CENTRAL PKWY W | 800 - Mavis | 151043 | Active | 79 | Upload Completed |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 84377.71 | 6347.89 | 84377.71 | 84377.71 | Persaud, Ryan |  |  | 27-Jul-23 | [6 empty] | 0
650548 | TX8783 VAULT REMOVAL - 3100 KIRWIN AVE | 800 - Mavis | 151043 | Active | 82 | RELEASED |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz | 13-Jul-23 | 1 |  | 95882.33 | 7123.97 | 95882.33 | 95882.33 | Antonio Mina |  | 15-Sep-23 | 15-Sep-23 | 01-Sep-23 | [5 empty] | 0
650573 | SR00361629 - 958-960 EAST AVENUE - PERMANENT SERVICE REMOVAL | 800 - Mavis | 150384 | Active | 82 | RELEASED |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel | 19-Jul-23 |  |  | 20512.31 | 2658.84 | 20512.31 | 20512.31 | Peter Costantini | N/A | 22-Aug-23 | 22-Aug-23 | 21-Aug-23 | [5 empty] | 0
635804 | 91 EGLINTON AVE. E., SALE OFFICE | 800 - Mavis |  | Active | 40 | ACTIVE |  |  | 2023 | Mandic, Goran | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650605 | 3350 WOLFEDALE RD | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650607 | 3075 LENWORTH DR | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650612 | SG1345- 2024 DA - 3535 CEDAR CREEK DR | 800 - Mavis | 151092 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650639 | CITY OF MISSISSAUGA - POLE RELOCATIONS - MAIN ST / SCARBORO ST BRIDGES | 800 - Mavis | 150673 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650640 | CITY OF MISSISSAUGA - POLE RELOCATIONS - DERRY RD E & TOMKEN RD | 800 - Mavis | 150673 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650653 | 1444 - 1458 CAWTHRA RD - SUBD RES EDS | 800 - Mavis | 150652 | Active | 10 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650669 | 2024 TX RENEWAL PROGRAM (100 X 1PH-TX) | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650728 | SHOPPERS DRUG MART | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650749 | YS74580 - 2024 DA - SECOND LINE W & DONWAY DR - P19822 | 800 - Mavis | 151092 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650750 | LT91275 & LT91274 - 2024 DA - GORWAY DR & NASHUA DR - P14628 & P14535 | 800 - Mavis | 151092 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650751 | YS64146 - 2024 DA - MAVIS RD & AVONWICK AVE - P18750 | 800 - Mavis | 151092 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650755 | SG1345- 2024 DA - CEDAR CREEK DR & LEXICON DR | 800 - Mavis | 151092 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650754 | S5426 - 2024 DA - TOMKEN RD & MIA CRT - P17401 | 800 - Mavis | 151092 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650752 | S130399 - 2024 DA - CAWTHRA RD & BLOOR ST - P22037 | 800 - Mavis | 151092 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650919 | CUSTOMER INITIATED OH POLE RELOCATION - KING AND CAMILLA DEVELOPMENT | 800 - Mavis | 150675 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650938 | 3600 HURONTARIO ST | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650012 | 1650 - DERRY RD E - 1200A - 1000KVA | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651010 | 2024 TX RENEWAL PROGRAM (18 X 1PH-TX) | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651009 | 2024 TX RENEWAL PROGRAM (17 X 1PH-TX) | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651015 | 2024 TX RENEWAL PROGRAM (GROUP7: 3 X 1PH-TX) | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651014 | 2024 TX RENEWAL PROGRAM (GROUP6: 7 X 1PH-TX) | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651013 | 2024 TX RENEWAL PROGRAM (GROUP5: 12 X 1PH-TX) | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651012 | 2024 TX RENEWAL PROGRAM (GROUP4: 17 X 1PH-TX) | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651017 | 2180 SPEAKMAN DR - TEMP. 750KVA TX REMOVAL | 800 - Mavis | 150384 | Active | 50 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651033 | 2024 TX RENEWAL PROGRAM - TX19441 - 6835 PROFESSIONAL CRT | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
650729 | 2024 TX RENEWAL PROGRAM -TX4948 -1399 CAWTHRA RD | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651039 | 2024 TX RENEWAL PROGRAM -TX61133 - 2975 ARGENTIA RD | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651038 | 2024 TX RENEWAL PROGRAM -TX13519 - 5901 TOMKEN RD | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651037 | 2024 TX RENEWAL PROGRAM -TX12111 - 1480 BRITTANIA RD E | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651036 | 2024 TX RENEWAL PROGRAM -TX14135 - 6850 MILCREEK DR | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651035 | 2024 TX RENEWAL PROGRAM -TX19718 - 2555 HENSALL ST | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651034 | 2024 TX RENEWAL PROGRAM - TX20196 - 2993 ERIN CENTRE BLVD | 800 - Mavis | 151043 | Active | 50 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651084 | P06290 - 2024 POLE RENEWAL - SPOT POLE 2 | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651083 | P16323 - 2024 POLE RENEWAL - SPOT POLE 1 | 800 - Mavis | 151063 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Meneses, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651104 | YL21262 - 2024 SR SOUTHDOWN RD & NINE GREEKS TRL - P12561 | 800 - Mavis | 151044 | Active | 48 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651108 | YL64151 - 2024 SR MAVIS RD & BRITANNIA RD W - P18000 | 800 - Mavis | 151044 | Active | 48 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651113 | YL5488 - 2024 SR BRITANNIA RD E & KENNEDY RD S - P18297 | 800 - Mavis | 151044 | Active | 48 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651112 | YL8325 - 2024 SR KENNEDY RD S & AMBASSADOR DR - P17172 | 800 - Mavis | 151044 | Active | 48 | ACTIVE |  |  | 2023 | Lucic, Marko | Matai, Ihssan (Sam) |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651118 | 1060 EGLINTON AVE E - MISS - 3PH - KVA - IN SPA | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651119 | 1082 LAKESHORE RD E - MISS - 3PH - KVA - IN SPA | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Roy, Akash |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651150 | 6501 MISSISSAUGA ROAD - POLE RELOCATIONS | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651151 | CUSTOMER INITIATED OH POLE RELOCATION - 3115 LENWORTH DR | 800 - Mavis | 150675 | Active | 10 | ACTIVE |  |  | 2023 | Watters, Maxwell | Wickramasinghe, Dinuka |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651152 | 5105 HURONTARIO ST. DEVELOPMENT PH2 | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Huo, Lisa |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651153 | CABLE REPLACEMENT - MAIN FEEDER CABLE (L6262 TO S140075) | 800 - Mavis | 151424 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651170 | WESTERN MS STATION SERVICE | 800 - Mavis | 150637 | Active | 10 | ACTIVE |  |  | 2023 | Shah, Akshay | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651169 | SHAWANAGA MS STATION SERVICE | 800 - Mavis | 150637 | Active | 10 | ACTIVE |  |  | 2023 | Shah, Akshay | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651173 | 2024 - 2323 CONFEDERATION PARKWAY - TX VAULT UPGRADE | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651172 | 2023 - 2300 CONFEDERATION PARKWAY - TX VAULT UPGRADE | 800 - Mavis | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Lucic, Marko | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651174 | 5495 DIXIE RD | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651198 | 551 AVONHEAD RD - CO SUBSTATION REMOVAL | 800 - Mavis | 150384 | Active | 70 | ACTIVE |  |  | 2023 | Mustachi, Randy | Hulnitski, Pavel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651231 | 780 SOUTHDOWN RD - REMOVAL | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
648203 | 580 SECRETARIAT CRT - SYSTEM EXPANSION | 800 - Mavis | 152302 | Active | 82 | PPS INCOMPLETE |  |  | 2023 | Watters, Maxwell | Central South |  |  |  | 493045.07 | 23989.99 | 493045.07 | 493045.07 | Persaud, Ryan |  |  | 27-Jul-23 | [6 empty] | 0
430271 | MAPLE VALLEY DEVELOPMENTS PH 2 - SUBD RES EDS | 800 - Mavis | 150652 | Active | 50 | ACTIVE |  |  | 2023 | Gamboa, Henry | Paesano, Chelsea |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
651375 | 6710 HURONTARIO ST | 800 - Mavis | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Mustachi, Randy | Jacinto, Gerardo |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
651382 | 800 LAKEFRONT PROMENADE | 800 - Mavis | 150384 | Active | 45 | ACTIVE |  |  | 2023 | Mustachi, Randy | Sobiera, Patricia |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jul-20
EAST | East Region (PS) | [9 empty] | East |  | 1,288.00 | 950 | 358169971.41 | 273851145.08 | 130610091 | 130610091 | [5 empty] | 01-Nov-17 | 30-Oct-23
636449 | 636449 - ICI NEW REC CENTRE CONNECCTION/ 371 CORNELL CENTRE BLVD | 815 - Addiscott | 101791 | Active | 95 | COMPLETE |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A | 11-Mar-21 |  |  | 64329.93 | 60198.23 | 64329.93 | 64329.93 | Dave Lindsay | Somervl | 25-May-21 | 26-Jul-23 | 28-Apr-21 | 19-Nov-21 | 05-May-22 | Customer | Customer |  | 0
635549 | 635549 - ICI UPGRADE/ 30 STATION ST | 815 - Addiscott | 101791 | Active | 96 | ANALYZE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 07-Jan-22 |  |  | 60251.74 | 50886.28 | 60251.74 | 60251.74 | Dave Lindsay | Somervl | 18-Mar-22 | 26-Jul-23 | 22-Feb-22 |  | 09-Mar-23 | Customer | Customer |  | 0
636633 | 636633 - STORM HARDENING - MAJOR MACKENZIE DR - WESTON RD TO JANE ST - VAUGHAN | 815 - Addiscott | 103659 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 18-Nov-20 |  |  | 298015.76 | 552910.07 | 298015.76 | 298015.76 | Reginald Clarke | K-Line | 30-Apr-21 | 26-Jul-23 | 31-Mar-21 | 23-Feb-21 | 25-Jan-22 |  | Control/SCADA |  | 0
632674 | 632674 - 9560, 9570 KEELE STREET, VAUGHAN, ON | 815 - Addiscott | 101887 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Alarcon, Alejandro | 28-May-21 |  |  | 47186.38 | 38769.51 | 47186.38 | 47186.38 | Dave Lindsay | Somervl | 30-Jul-21 | 26-Jul-23 | 09-Jul-21 | 02-Sep-21 | 18-Jul-22 | Customer | Customer |  | 0
635056 | 6061-6079 RUTHERFORD ROAD CONDOMINIUM SUBDIVISION CONNECTIONS | 815 - Addiscott | 101887 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 14-Apr-23 |  |  | 627820.08 | 563509.76 | 579268.35 | 627820.08 | Dave Lindsay | Transpw | 16-Jun-23 | 01-Aug-23 | 12-Jun-23 | [5 empty] | 48,551.73
632863 | 632863 - 56-60 ELIZABETH ST SOUTH/ ICI NEW APARTMENT CONDO | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 17-Dec-21 |  |  | 112625.88 | 7073.16 | 112625.88 | 112625.88 | Dave Lindsay | Somervl | 01-Mar-22 | 09-Aug-23 | 02-Feb-22 |  |  | Customer | Customer |  | 0
634066 | 634066 - POLE RELOCATIONS - 1890 HWY 7 | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 22-Jul-21 |  |  | 533866.15 | 521003.67 | 533866.15 | 533866.15 | Macdonald, Steve | K-Line | 08-Dec-21 | 26-Jul-23 | 27-Oct-21 | 08-Oct-21 | 03-Dec-21 |  |  |  | 0
452840 | RER - MX - RELOC - GOWAN ST - BARRIE LINE (2166) - RAILWAY CROSSINGS | 825 - Patterson | 150591 | Active | HL | ACTIVE |  |  | 2023 | Khuu, Philander | Grahovac, John |  |  |  | 0 | 63165.34 |  | 0 | Persaud, Ryan |  |  | 26-Jul-23
635857 | 635857 - CHAMPLAIN SHORES PH1/INSPECT & CONNECT | 825 - Patterson | 101887 | Active | 95 | ANALYZE |  |  | 2023 | Penner, Mitchell | Perks, Dan | 18-Nov-22 |  |  | 463329.51 | 466069.64 | 463329.51 | 463329.51 | Lotto, Jay |  | 17-Feb-23 | 26-Jul-23 | 10-Jan-23 | 21-Mar-23 | 21-Mar-23 | Customer | Customer |  | 0
452579 | 452579 - ICI PADMOUNT TX INSTALLATION/39, 53, 67 JEFFERSON SIDE RD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Paterson, Greg | 03-May-22 |  |  | 103819.69 | 12439.56 | 103819.69 | 103819.69 | Dave Lindsay | Somervl | 14-Jul-22 | 14-Aug-23 | 14-Jun-22 |  |  | Customer | Customer |  | 0
636661 | UG CABLE REPLACEMENT - A01, HENDERSON-YONGE-BLOOMINGTON-BATHURST | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 65174.44 |  | 0 | Wong, Henry |  |  | 09-May-23
636203 | 287 KING STREET SOUTH, ALLISTON - KINGSMERE RETIREMENT LIVING | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED | VerHigh | Res-ICI | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 4320.57 |  | 0 | Wong, Henry |  |  | 21-Feb-23
636063 | 636063 - ICI PADMOUNT TX INSTALLATION/LOT 21 ADDISON HALL CIRCLE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 07-Apr-21 |  |  | 40279.42 | 38109.96 | 40279.42 | 40279.42 | Dave Lindsay | Somervl | 14-Jun-21 | 14-Feb-23 | 20-May-21 | 03-Nov-21 | 11-Feb-22 | Customer | Customer |  | 0
633199 | 633199 - 111 BRADFORD ST | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 03-Sep-20 |  |  | 77246.58 | 63291.82 | 77246.58 | 77246.58 | Lotto, Jay | HapAmp | 04-Nov-20 | 06-Apr-22 | 19-Oct-20 | 01-Oct-20 | 31-Jan-22 |  | Customer |  | 0
635720 | 635720 - 58 LAKESIDE TERRACE, BARRIE - TOWER A | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2021 | Cranley, Stephen | Harris, Geoff L. | 25-Jun-20 |  |  | 101800.61 | 90824.34 | 101800.61 | 101800.61 | Lotto, Jay | HapAmp | 24-Aug-20 | 06-Apr-22 | 10-Aug-20 | 24-Jun-21 | 04-Aug-21 | Customer | Customer |  | 0
636575 | 636575 - ICI PADMOUNT TX INSTALLATION/2 KING ST S | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 24-Sep-20 |  |  | 45072.6 | 41667 | 45072.6 | 45072.6 | Lotto, Jay | HapAmp | 13-Nov-20 | 06-Apr-22 | 26-Oct-20 | 15-Oct-20 | 19-Feb-21 |  | Customer |  | 0
453497 | 453497 (WO 318736) Bell JU Permit 18-152. TOLLENDAL MILL ROAD, BARRIE | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 04-Oct-19 |  |  | 11422.1 | 6606.4 | 11422.1 | 11422.1 | Aulis, John -x |  | 20-Nov-19 | 15-Sep-21 | 18-Nov-19 | 12-Nov-19 | 13-Nov-19 |  |  |  | 0
453266 | (WO 318306) 62 Sherwood Forest Dr. Pole Relocation, Markham | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Barry, Kenneth | 16-Jul-19 |  |  | 18403.89 | 13155.39 | 18403.89 | 18403.89 | Macdonald, Larry |  | 20-Aug-19 | 05-Aug-21 | 06-Aug-19 | 22-Aug-19 | 22-Aug-19 |  |  |  | 0
635632 | CHATFIELD DR. TOWNHOME DEVELOPMENTS / I&C | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636012 | BEETON MEADOWS/INSPECT AND CONNECT | 825 - Patterson | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | Wong, Henry
634913 | LALU 1053 16TH AVENUE DEVELOPMENTS INC. / INSPECT & CONNECT | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
631392 | (WO 631392 ) 2019 POLE REPLACEMENT PROGRAM/ REPLACE P27562 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 09-Jul-19 |  |  | 64982.28 | 35188.67 | 64982.28 | 64982.28 | Shortt, Derek B. |  | 15-Sep-19 | 29-Oct-20 | 02-Aug-19 | 24-Jul-19 | 05-Sep-19 |  |  |  | 0
453965 | 453965 (WO 319332) HE2019-027 - Rogers MCCOWAN RD & 16TH AVE | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 15-Oct-19 |  |  | 8021.85 | 4720.32 | 8021.85 | 8021.85 | Macdonald, Larry |  | 10-Dec-19 | 20-Oct-20 | 12-Nov-19 | 21-Nov-19 | 21-Nov-19 | Filler |  |  | 0
453426 | 453426 (WO 318619) 2019 Pad TX Repl. - Batch 4 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 24-Sep-19 |  |  | 157498.05 | 117183 | 157498.05 | 157498.05 | Steve Rumble | Somervl | 11-Dec-19 | 20-Jul-20 | 21-Oct-19 | 25-Nov-19 | 20-Dec-19 | Filler | Filler |  | 0
635451 | TRU HOME 2 HOTEL - WOODBINE AVE. #8332 | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Wong, Henry
453583 | (WO318875) 2019 Distribution Automation. 8707 JANE ST | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 30-Apr-19 |  | 1 | 73906 | 86266.48 | 73906 | 73906 | Macdonald, Steve | K-Line | 09-Aug-19 | 25-May-20 | 22-Jul-19 | 09-Sep-19 | 03-Oct-19 |  |  |  | 0
636227 | ICI POLE RELOCATION/130 ST JOHNS SIDEROAD | 815 - Addiscott | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Wong, Henry
635547 | 5305/5307 HIGHWAY 7 E / ICI PADMOUNT INSTALL | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
453142 | (WO318014) 16th & McCowan Dev | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alarcon, Alejandro | 27-May-19 |  |  | 42135.37 | 306736.55 | 42135.37 | 42135.37 | Steve Rumble |  | 11-Sep-19 | 10-Feb-20 | 29-Jul-19 | 17-Jun-19 | 08-Oct-19 |  |  |  | 0
634778 | 539 TIFFIN ST, BARRIE - NEW 3 PHASE SERVICE | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Wong, Henry
635969 | 635969 - AMUSMENT DR. - #11 AT MAJOR MACKENZIE DR., JUNCTION | 815 - Addiscott | 101791 | Active | 96 | ANALYZE |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 15-Jul-20 |  |  | 55088.96 | 63296.35 | 55088.96 | 55088.96 | Dave Lindsay | Somervl | 12-Jan-22 | 26-Jul-23 | 23-Dec-21 | 02-Nov-22 | 06-Mar-23 | Customer | Customer |  | 0
636636 | INSULATOR REPLACEMENT - STEELES AVE - YONGE ST TO NORTHWEST DR (JANE ST) | 815 - Addiscott | 101781 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 117256 |  | 0 | Wong, Henry |  |  | 26-Jul-23
636240 | 636240- KING AND BOND MUNICIPAL SEMIS | 815 - Addiscott | 101887 | Active | 84 | H8 |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 30-Nov-20 |  |  | 81068.88 | 14603.81 | 81068.88 | 81068.88 | Dave Lindsay |  | 14-Jan-21 | 28-Jul-23 | 12-Jan-21 | 03-Dec-20 |  |  | Customer |  | 0
636064 | 636064 - ICI PADMOUNT TX INSTALLATION/LOT 22 ADDISON HALL CIRCLE | 815 - Addiscott | 101791 | Active | 99 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 07-Apr-21 |  |  | 54192.38 | 71623.02 | 54192.38 | 54192.38 | Dave Lindsay | Somervl | 14-Jun-21 | 26-Jul-23 | 20-May-21 | 01-Dec-21 | 09-Mar-23 | Customer | Customer |  | 0
635018 | BLOCK 40/47 - LORMEL | 815 - Addiscott | 101887 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 10-Apr-23 |  |  | 472805.04 | 395166.05 | 472805.04 | 472805.04 | Dave Lindsay | Transpw | 11-Sep-23 | 11-Sep-23 | 01-Jun-23 | [5 empty] | 0
453133 | 453133 - DORMER BOND TOWNHOMES | 815 - Addiscott | 101887 | Active | 99 | ANALYZE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 18-Jan-21 |  |  | 52428.97 | 304061.18 | 52428.97 | 52428.97 | Dave Lindsay |  | 19-Mar-21 | 26-Jul-23 | 08-Mar-21 | 24-Mar-22 | 09-Mar-23 | Customer | Customer |  | 0
636542 | 636542 - 25 STEELE VALLEY RD / ICI 1PH PAD TX INSTALLATION | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2021 | Joshi, Namrata | Mann, Drew | 17-Jul-20 |  |  | 28817.08 | 32636.37 | 28817.08 | 28817.08 | Dave Lindsay | Somervl | 30-Oct-20 | 26-Jul-23 | 19-Oct-20 | 14-Jul-21 | 21-Jul-21 | Customer | Customer |  | 0
453659 | 453659 - KINGS VILLA | 815 - Addiscott | 101887 | Active | 82 | H8 |  |  | 2023 | Penner, Mitchell | D'Onofrio, Tony | 28-Mar-22 |  |  | 144278.05 | 14800.88 | 144278.05 | 144278.05 | Dave Lindsay | Transpw | 17-Jun-22 | 14-Aug-23 | 17-May-22 |  |  | Customer | Customer |  | 0
452839 | 452839 - RER - MX - RELOC - HURST RD - BARRIE LINE (1929) - RAILWAY CROSSINGS | 825 - Patterson | 150591 | Active | 96 | COMPLETE |  |  | 2023 | Khuu, Philander | Grahovac, John | 21-Jul-22 |  |  | 259858.43 | 347543.42 | 244527.12 | 259858.43 | Dan Kish | K-Line | 20-Sep-22 | 26-Jul-23 | 06-Sep-22 | 30-Jul-22 | 20-Mar-23 |  | MC/PUCC Permit |  | 15,331.31
636704 | 636704 - 73 WOOTEN WAY N / ICI PAD TX INSTALLATION | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 24-Nov-20 |  |  | 64178.32 | 69055.49 | 64178.32 | 64178.32 | Dave Lindsay | Somervl | 03-May-22 | 27-Jun-23 | 01-Apr-22 | 11-Jul-22 | 07-Oct-22 | Customer | Customer |  | 0
635587 | 635587 - KING RD, YONGE ST TO BOND CRES | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander | 08-Nov-21 |  |  | 120072.61 | 109608.17 | 120072.61 | 120072.61 | Ryan Walsh |  | 21-Jan-22 | 26-Jan-23 | 04-Jan-22 | 04-Jan-22 | 24-Jan-22 |  | Weather |  | 0
634625 | 634625 - HIGHWAY NO. 7 WEST - #2926 (EDGELEY STRATA PARK) | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 20-Nov-20 |  |  | 180088.47 | 142620.35 | 180088.47 | 180088.47 | Dave Lindsay | Somervl | 26-Jan-21 | 24-Aug-22 | 31-Dec-20 | 21-Jul-21 | 15-Sep-21 | Customer | Customer |  | 0
636603 | 636603 - STORM HARDENING - WESTON - HWY 7 TO LANGSTAFF - VAUGHAN | 815 - Addiscott | 103659 | Inactive | 99 | CANCELLED |  |  | 2022 | Tenorlas, Reynaldo | Roy, James |  |  |  | 613454.34 | 0 | 613454.34 | 613454.34 | Wong, Henry | K-Line |  | 05-Jul-22 | [6 empty] | 0
454271 | (WO 454271) Yonge St & King Rd Temp O/H Relocation | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 7191.23 |  | 0 | Persaud, Ryan |  |  | 23-Jun-22
634840 | 634840 - HE2019-120, ROGERS - JANE ST | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 05-Mar-21 |  |  | 14210.4 | 7789.45 | 14210.4 | 14210.4 | Macdonald, Larry |  | 19-Apr-21 | 18-Jan-22 | 19-Apr-21 | 23-Apr-21 | 23-Apr-21 |  |  |  | 0
633197 | ALECTRA U/G RELOCATIONS - STEELCASE RD WEST X JOHN ST. | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 6098.58 |  | 0 | Persaud, Ryan |  |  | 29-Dec-21
633214 | 633214 - JOINT USE PERMIT #HE2019-091 - CONDRINGTON STREET - BARRIE | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 01-Nov-19 |  |  | 5538.74 | 3772.65 | 5538.74 | 5538.74 | Aulis, John -x |  |  | 15-Dec-21 |  | 21-Nov-19 | 21-Nov-19 |  |  |  | 0
635331 | 635331 - ICI NEW CONDOMINIUM/ 8010 KIPLING AVE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 08-Dec-20 |  |  | 96470.44 | 44792.6 | 96470.44 | 96470.44 | Dave Lindsay | Somervl | 12-Feb-21 | 01-Dec-21 | 18-Jan-21 | 18-Feb-21 | 08-Oct-21 | Lines | Customer |  | 0
453834 | (WO319171) Padmount Transformer replacement with O/H Transformer ( ESA Driven) - #6 Cumberland – Bar | 825 - Patterson | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 25-Jun-19 |  |  | 91312 | 58357.44 | 91312 | 91312 | Jeremy Wright | HapAmp | 08-Aug-19 | 26-Apr-21 | 25-Jul-19 | 30-Jul-19 | 27-Aug-19 | Customer | Customer |  | 0
634961 | 634961 - 82 SCIBERRAS - ESA EMERGING PROJECT - REAR LOT CONDUCTOR HEIGHT ADJUSTMENT | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 17-Dec-19 |  |  | 21443.7 | 31427.86 | 21443.7 | 21443.7 | Macdonald, Larry |  | 20-Dec-19 | 29-Oct-20 | 20-Dec-19 | 20-Dec-19 | 20-Dec-19 |  |  |  | 0
636035 | KEELE ST. - #7625, OFFICE BUILDING | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Wong, Henry
453582 | (WO318873) 2019 Distribution Automation. JANE ST N/O MAJOR MACK DR W | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 15-Mar-19 |  | 1 | 74864 | 60397.41 | 74864 | 74864 | Macdonald, Steve | K-Line | 14-Jun-19 | 25-May-20 | 13-May-19 | 02-Jul-19 | 11-Jul-19 |  |  |  | 0
634920 | 9797-9785 KEELE STREET (HERITAGE VILLAGE) / INSPECT & CONNECT WO | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
453425 | 453425 (WO 318618) 2019 Pad TX Repl. - Batch 3 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 25-Sep-19 |  |  | 250606.22 | 119767.03 | 250606.22 | 250606.22 | Steve Rumble | Somervl | 31-Dec-19 | 24-Feb-20 | 28-Oct-19 | 21-Oct-19 | 03-Dec-19 |  |  |  | 0
452947 | 452947 (WO 317300) Replace Tx 31-114 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  |  | 36690 | 19805.24 | 36690 | 36690 | Steve Rumble | Somervl | 23-Oct-19 | 24-Feb-20 | 23-Aug-19 | 16-Sep-19 | 27-Sep-19 |  |  |  | 0
635884 | PARENT W.O. FOR INSPECT.CONNECT/I&C - GREENSBOROUGH TOWNHOUSES | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Wong, Henry
453495 | (WO 318734) 2019 Pole Replacement Batch 05 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 04-Dec-18 |  |  | 139489 | 104450.13 | 139489 | 139489 | Morrow, Joe |  | 30-Jun-19 | 27-Jan-20 | 02-Jan-19 | 22-Jan-19 | 27-Jun-19 |  |  |  | 0
635064 | PHASE 2-OH&UG RELOC. AT MAJOR MACKENZIE DR(W. OF LESLIE ST-E. OF WOODBINE AVE) | 815 - Addiscott | 151587 | Active | 70 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | Wong, Henry
632846 | (WO632846) 1452 WELLINGTON ST AURORA | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 31-Jul-19
632657 | RER - MX - RELOC - ST. JOHN'S SIDEROAD - BARRIE LINE (1453) - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Active | 50 | ACTIVE |  |  | 2023 | Khuu, Philander | Grahovac, John |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 31-Jul-19
453961 | (WO 319328) 17-052 - Bell PEELAR RD & JANE ST | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 |  | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Apr-19
453265 | 453265 (WO 318302) Trans_PS_Enbridge Gas | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Aug-18
633988 | HOLLAND ST. W 44KV FEEDER EXTENSION PHASE 2 | 825 - Patterson | 101781 | Active | HL | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 115433.75 |  | 0 | Persaud, Ryan |  |  | 26-Jul-23
636488 | 636488 - DUCHESS OF OXFORD MODERN | 815 - Addiscott | 101887 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Alarcon, Alejandro | 04-Aug-21 |  |  | 285796.16 | 283364 | 285796.16 | 285796.16 | Dave Lindsay | Transpw | 28-Oct-21 | 26-Jul-23 | 17-Sep-21 | 01-Dec-21 | 05-May-22 | Customer | Customer |  | 0
635971 | 635971 - ANDRIN WISMER HOMES LIMITED | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 01-Jun-21 |  |  | 54456.25 | 46192 | 54456.25 | 54456.25 | Dave Lindsay |  | 06-Aug-21 | 26-Jul-23 | 16-Jul-21 | 19-Jul-21 | 02-Mar-23 | Customer | Customer |  | 0
636637 | 2021 INSULATOR REPLACEMENT - STEELES AVE - WESTON RD TO ISLINGTON AVE | 815 - Addiscott | 150009 | Active | HL | Upload Completed |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 18-Nov-20 |  |  | 306784.39 | 24771.74 | 306784.39 | 306784.39 | Wong, Henry | K-Line |  | 25-Aug-23 | [6 empty] | 0
636066 | 636066 - ICI NEW COMMERCIAL CONNECTION/ RUTHERFORD PUMPING STATION | 815 - Addiscott | 101791 | Active | 95 | COMPLETE |  |  | 2022 | Dibratto, Susan | Diefenbaker, Trevor A | 10-Sep-21 |  |  | 151014.19 | 147729.38 | 151014.19 | 151014.19 | Dave Lindsay | Somervl | 01-Dec-21 | 26-Jul-23 | 27-Oct-21 | 25-Oct-21 | 19-Jul-22 | Customer | Customer |  | 0
635065 | 635065 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.1 | 815 - Addiscott | 151587 | Active | 98 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 01-Apr-21 |  |  | 1955792.92 | 2038101.4 | 1870186.88 | 1955792.92 | Macdonald, Steve | K-Line | 29-Apr-22 | 26-Jul-23 | 14-Feb-22 | 31-May-21 | 17-Sep-22 |  | Materials |  | 85,606.04
633196 | 633196 - NEW CONDOMINIUM/ 8888 YONGE ST | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 25-Aug-21 |  |  | 352626.88 | 15495.33 | 253224.59 | 352626.88 | Dave Lindsay | Transpw | 16-Nov-21 | 21-Aug-23 | 07-Oct-21 |  |  | Customer | Customer |  | 99,402.29
635657 | 635657 - JOINT USE PERMIT HE2020-003, WESTON ROAD, VAUGHAN | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 11-Feb-22 |  |  | 40874.89 | 45766.72 | 40874.89 | 40874.89 | Macdonald, Steve | K-Line | 04-May-22 | 26-Jul-23 | 04-Apr-22 | 04-Apr-22 | 04-Apr-22 |  |  |  | 0
635904 | 635904 - GEMTERRA WOODBINE, MARKHAM | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Estrada, Michael | 28-Jul-22 |  |  | 210274.46 | 205224.23 | 210274.46 | 210274.46 | Dave Lindsay | Transpw | 11-Oct-22 | 26-Jul-23 | 09-Sep-22 | 13-Aug-22 | 07-Oct-22 |  |  |  | 0
636551 | 636551 - 2021 CABLE INJECTION - V37 - LANGSTAFF & WESTON RD, VAUGHAN | 815 - Addiscott | 150134 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 02-Dec-20 |  |  | 2209530.91 | 182707.12 | 2209530.91 | 2209530.91 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 01-Jan-21 | 08-Feb-22 | Contractor | MC/PUCC Permit |  | 0
454269 | ROYAL ORCHARD NORTH PH 1/REAR LOT CONVERSION | 815 - Addiscott | 150047 | Active | HL | H2 |  |  | 2023 | Tenorlas, Reynaldo | Handy, James | 29-Oct-19 |  |  | 1481779.35 | 15684.42 | 1481779.35 | 1481779.35 | Persaud, Ryan |  |  | 27-Jul-23 | [6 empty] | 0
453424 | 453424 (WO 318617) 2019 Pad TX Repl. - Batch 2 | 815 - Addiscott | 2019 Pad Transformer Repl. | Active | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 25-Jun-19 |  |  | 101392 | 50184.11 | 101392 | 101392 | Cory Ruiter | Somervl | 29-Nov-19 | 26-Jul-23 | 01-Oct-19 | 28-Aug-19 | 29-Oct-19 |  |  |  | 0
636706 | 636706 - HUNTINGTON RD. - #7900 INDUSTRIAL/COMMERCIAL | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Yuen, Paul | 02-Jul-21 |  |  | 63764.18 | 68146.06 | 63764.18 | 63764.18 | Dave Lindsay | Somervl | 30-Mar-22 | 18-Jul-23 | 25-Feb-22 | 13-May-22 | 07-Oct-22 | Customer | Customer |  | 0
453960 | (WO319326) 4300 Hwy 7 E | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 13-Feb-23
452576 | (WO315069) New 1 Phase Service. Bradford W.G. | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 145.82 |  | 0 | Persaud, Ryan |  |  | 13-Jul-22
453113 | (WO317979) Changes to Metering | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 2001.75 |  | 0 | Persaud, Ryan |  |  | 13-Jul-22
634877 | 634877 - 342 KING ST, BARRIE - COMMERCIAL BUILDINGS | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | High | Comm | 2021 | Cranley, Stephen | Harris, Geoff L. | 07-Oct-20 |  |  | 87380.98 | 54581.87 | 87380.98 | 87380.98 | Lotto, Jay | HapAmp | 18-Dec-20 | 06-Apr-22 | 30-Nov-20 | 05-Jun-21 | 17-Dec-21 | Customer | Customer |  | 0
453658 | 453658 (WO 318967) 71 Commerce Park Dr - New 3ph | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 14-Aug-19 |  |  | 69910.53 | 50404.35 | 69910.53 | 69910.53 | Jeremy Wright | HapAmp | 28-Oct-19 | 10-Jan-22 | 11-Oct-19 | 11-Dec-19 | 16-Dec-19 |  |  |  | 0
636308 | 636308 - 9111 KEELE ST / ICI PAD TX INSTALLATION | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 17-Jul-20 |  |  | 63007.13 | 65254.19 | 60932.13 | 63007.13 | Dave Lindsay | Somervl | 25-Sep-20 | 15-Oct-21 | 15-Sep-20 | 03-Nov-20 | 27-Apr-21 | Customer | Customer |  | 2,075.00
453494 | (WO 318733) 2019 Pole Replacement Batch 04 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 12-Dec-18 |  |  | 156263 | 169319.54 | 156263 | 156263 | Shortt, Derek B. |  | 28-Aug-19 | 04-Feb-21 | 27-Feb-19 | 07-Feb-19 | 14-Aug-19 |  |  |  | 0
452696 | 452696 (WO 316261) Rutherford GO Station | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Diefenbaker, Trevor A | 11-Oct-19 |  |  | 19361.59 | 31417.64 | 19361.59 | 19361.59 | Steve Rumble | Somervl | 12-Nov-19 | 29-Jun-20 | 11-Nov-19 | 03-Dec-19 | 10-Dec-19 | Customer | Customer |  | 0
636062 | 2020 POLE REPLACEMENTS INNISFIL ST AND PERRY ST | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | Wong, Henry
453581 | 453581 (WO 318872) 2019 Distribution Automation. MAJOR MACK DR W/O JANE ST | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 20-Jun-19 |  | 1 | 104365 | 115573.3 | 104365 | 104365 | Macdonald, Steve | K-Line | 13-Sep-19 | 24-Feb-20 | 12-Aug-19 | 16-Dec-19 | 19-Dec-19 |  |  |  | 0
454270 | (WO319675) 2019 Padmount Transformer Replacement - Batch 12 | 815 - Addiscott | 2019 Pad Transformer Repl. | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 25-Jun-19 |  |  | 41761.3 | 32266.89 | 50234 | 41761.3 | Steve Rumble |  | 15-Oct-19 | 27-Jan-20 | 02-Sep-19 | 21-Aug-19 | 10-Oct-19 |  |  |  | -8,472.70
452946 | ( WO 317299) Replace 13-22 | 815 - Addiscott | 2018 Pad Transformer Repl. | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 11-Nov-18 |  |  | 17683 | 8778.55 | 17683 | 17683 | Steve Rumble | Somervl | 30-Oct-19 | 27-Jan-20 | 25-Oct-19 | 19-Aug-19 | 09-Oct-19 |  |  |  | 0
633502 | (WO 633502) SECONDARY ALLEY JUMPER REMOVAL AT 65 JOHN ST. - BRADFORD | 825 - Patterson |  | Inactive | 99 | CANCELLED |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 11-Sep-19
636638 | INSULATOR REPLACEMENT - DUFFERIN ST - MMD TO KING VAUGHAN RD | 815 - Addiscott | 101781 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 42251.53 |  | 0 | Wong, Henry |  |  | 26-Jul-23
634946 | 634946 - PALA CONDOMINIUM DEVELOPMENT | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Swales, Mathew | 17-May-21 |  |  | 262701.09 | 240830 | 262701.09 | 262701.09 | Dave Lindsay | Transpw | 31-Aug-21 | 26-Jul-23 | 29-Jun-21 | 19-Oct-21 | 07-Oct-22 | Customer | Customer |  | 0
636077 | 636077 - 440 VETERANS DR/INSPECT AND CONNECT | 825 - Patterson | 101887 | Active | 99 | ANALYZE |  |  | 2023 | Penner, Mitchell | Perks, Dan | 09-Nov-22 |  |  | 117801.45 | 109036.65 | 117801.45 | 117801.45 | Lotto, Jay | Transpw | 23-Jan-23 | 01-Aug-23 | 03-Jan-23 | 20-Feb-23 | 23-Feb-23 | Customer | Customer |  | 0
634884 | 634884 - ICI NEW COMMERCIAL SERVICE/ 180 CACHET WOODS COURT | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 17-Dec-21 |  |  | 61548.88 | 38461.63 | 61548.88 | 61548.88 | Dave Lindsay | Somervl | 24-Feb-22 | 26-Jul-23 | 02-Feb-22 | 20-Mar-23 | 29-Mar-23 | Customer | Customer |  | 0
452837 | 452837 (WO 316793) METROLINX CROSSING Minet's Point - Lakeshore Dr to Yonge St | 825 - Patterson | 150591 | Active | 91 | ACTIVE | High | MLinx | 2023 | Khuu, Philander | Grahovac, John | 29-Jan-20 |  |  | 2758651.26 | 3784439.94 | 1803848.5 | 2758651.26 | Shane Christopher | Transpw | 15-Mar-22 | 26-Jul-23 | 01-Mar-22 | 08-Aug-22 |  | Customer |  |  | 954,802.76
453261 | 453261 - 1521 19TH AVENUE PHASE 1 | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 27-Oct-21 |  |  | 778013.28 | 424683.63 | 778013.28 | 778013.28 | Dave Lindsay | Transpw | 20-Jan-22 | 16-Aug-23 | 08-Dec-21 | 09-May-22 |  | Customer | Customer |  | 0
636498 | 636498 - 4 ADDISON HALL CIRCLE, AURORA - 3 PHASE SERVICE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 16-Jul-20 |  |  | 58561.91 | 54288.1 | 58561.91 | 58561.91 | Dave Lindsay | Somervl | 11-Dec-20 | 27-Jun-23 | 23-Nov-20 | 05-Jul-22 | 07-Oct-22 | Customer | Customer |  | 0
636552 | 636552 - 2021 CABLE INJECTION - M15 - 16TH AVE & MARKHAM RD, MARKHAM | 815 - Addiscott | 151341 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 246208.77 | 252974.44 | 246208.77 | 246208.77 | Horlings, Jake | Nvinium | 31-Dec-21 | 02-Mar-23 | 01-Jan-21 | 10-Oct-21 | 06-Dec-21 | Contractor |  |  | 0
453815 | (WO319139) WELLINGTON ST E & HWY 404 | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 22-Sep-22
635021 | 635021 - 759 YONGE ST, BARRIE - PAINSWICK PARK | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | Medium | Comm | 2021 | Cranley, Stephen | Harris, Geoff L. | 30-Apr-21 |  |  | 20948.97 | 15424.84 | 20948.97 | 20948.97 | Lotto, Jay |  | 18-Jun-21 | 17-Aug-22 | 14-Jun-21 | 29-Sep-21 | 01-Oct-21 | Customer | Customer |  | 0
636249 | 636249 - TRANSIT CITY (EAST BLOCK) – SUBD CONDO TOWER EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | Penner, Mitchell | Graham, Bruce W. | 13-May-21 |  |  | 610216.29 | 613590.2 | 610216.29 | 610216.29 | Dave Lindsay | Transpw | 12-Oct-21 | 15-Dec-21 | 29-Jun-21 | 11-Jun-21 | 15-Sep-21 |  |  |  | 0
635079 | 635079 - CABLE REPLACEMENT, M14 MAJOR BUTTONS AND RICHWOOD - 14TP030 TO 14U030 | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 19-Aug-20 |  |  | 532574.71 | 542307.4 | 576289.71 | 532574.71 | Lamb, Tim | Transpw | 30-Oct-20 | 15-Jul-21 | 05-Oct-20 | 01-Dec-20 | 01-Feb-21 | Contractor | Contractor |  | -43,715.00
635367 | POLE REPLACEMENT PROJECT FOR 20-30 WELDRICK RD W. SUBDIVISION | 815 - Addiscott | 151531 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
453422 | (WO318615) 2019 Pdmt TX Rep North Batch 1 | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 20-Feb-19 |  |  | 133204 | 99879.74 | 133204 | 133204 | Jeremy Wright |  | 31-May-19 | 24-Aug-20 | 25-Feb-19 | 05-Mar-19 | 22-May-19 |  | Filler |  | 0
453112 | (WO 317978) Add 1x 27.6kV CCT - ELGIN MILLS RD-LESLIE TO WOODBINE | 815 - Addiscott | 101781 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 27-Nov-18 |  |  | 458505 | 560607.57 | 458505 | 458505 | Morrow, Joe |  | 29-Nov-19 | 24-Aug-20 | 21-Feb-19 | 04-Feb-19 | 06-Jun-19 |  |  |  | 0
453959 | 453959 (WO 319325) 196 Citation Dr | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 11-Jun-19 |  |  | 55358.61 | 46736.2 | 55358.61 | 55358.61 | Steve Rumble | Somervl | 23-Oct-19 | 21-Aug-20 | 09-Oct-19 | 12-Sep-19 | 19-Oct-19 |  |  |  | 0
635661 | 305 SAUNDERS RD, BARRIE - NEW 3 PHASE SERVICE | 825 - Patterson | 101919 | Active | 50 | ACTIVE | High | Indust | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Wong, Henry
454267 | 454267 - BAYVIEW PUMP STN CABLE REPL/BAYVIEW PUMP STATION CABLES | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 08-Oct-19 |  |  | 10195.2 | 15930.64 | 10195.2 | 10195.2 | Morrow, Joe | Transpw | 12-Nov-19 | 24-Feb-20 | 11-Nov-19 | 08-Nov-19 | 12-Nov-19 |  |  |  | 0
452945 | 452945 (WO 317298) Replace 24-73 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 11-Nov-18 |  |  | 0 | 20637.69 | 36112 | 36112 | Steve Rumble | Somervl | 21-Oct-19 | 24-Feb-20 | 19-Aug-19 | 01-Aug-19 | 23-Sep-19 |  |  |  | 0
454105 | (WO319497) 65 Malmo Crt | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Diefenbaker, Trevor A | 29-May-19 |  |  | 17401.74 | 7601.88 | 17401.74 | 17401.74 | Steve Rumble | Somervl | 04-Jul-19 | 24-Feb-20 | 01-Jul-19 | 25-Jun-19 | 25-Jun-19 |  |  |  | 0
453580 | 453580 (WO 318871) 2019 Distribution Automation. MAJOR MACK DR W/O VELLORE PARK AVE | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 30-Apr-19 |  | 1 | 81246 | 97764.14 | 81246 | 81246 | Macdonald, Steve | K-Line | 30-Aug-19 | 24-Feb-20 | 19-Jul-19 | 15-Oct-19 | 29-Oct-19 |  |  |  | 0
633437 | OH RELOCATION AT 4902 AND 4908 HWY 7, VAUGHAN | 815 - Addiscott | 101761 | Active | 40 | H8 |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 03-Sep-19
453493 | (WO 318731) 18-118 York Region JU App | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 | O'Gay, Brian | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Oct-18
636507 | 636507 - POLE INSTALLATION DONNA MAE SUBDIVISION | 815 - Addiscott | 151531 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Alarcon, Alejandro | 28-Dec-21 |  |  | 32644.84 | 22267.33 | 32644.84 | 32644.84 | Reginald Clarke |  | 08-Mar-22 | 26-Jul-23 | 07-Mar-22 | 08-Jun-22 | 08-Jun-22 | Customer | Customer |  | 0
636639 | INSULATOR REPLACEMENT - KING VAUGHAN RD - DUFFERIN ST TO BATHURST ST | 815 - Addiscott | 150009 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 29390.66 |  | 0 | Wong, Henry |  |  | 26-Jul-23
635121 | 635121 - 200 ABERDEEN AVE | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 07-Oct-22 |  |  | 82625.88 | 6380.9 | 82625.88 | 82625.88 | Dave Lindsay | Somervl | 21-Dec-22 | 08-Aug-23 | 25-Nov-22 |  |  | Customer | Customer |  | 0
635032 | 635032 - OH AND UG RELOCATION AT JANE ST (NORTH OF TESTON RD), VAUGHAN | 815 - Addiscott | 101761 | Active | 98 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 11-Mar-21 |  |  | 749128.4 | 801141.6 | 744128.4 | 749128.4 | Ryan Walsh |  | 19-Aug-21 | 27-Sep-23 | 12-Apr-21 | 29-Apr-21 | 06-Jul-21 |  |  |  | 5,000.00
635906 | 635906 - 1623 WELLINGTON STREET, AURORA | 815 - Addiscott | 101761 | Active | 98 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 13-May-21 |  |  | 18138.24 | 13606.5 | 18138.24 | 18138.24 | Macdonald, Larry |  | 04-Aug-21 | 26-Jul-23 | 03-Aug-21 | 21-Jul-21 | 21-Jul-21 |  |  |  | 0
452692 | 452692 (WO 316252) 1756 ST. JOHNS SD RD | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Perks, Dan | 27-Aug-19 |  |  | 391252.34 | 462766.89 | 391252.34 | 391252.34 | Dave Lindsay | Transpw | 09-Dec-19 | 24-Apr-23 | 28-Oct-19 | 30-Apr-19 | 27-Apr-21 |  | Lines |  | 0
453956 | 453956 - RA RELOCATIONS - CHATHAM ST PENETANG | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2022 | Lacombe, Joel | Corriveau, Tom N | 07-Jan-22 |  |  | 452770.53 | 408031.44 | 452770.53 | 452770.53 | Dan Kish | K-Line | 08-Mar-22 | 08-Mar-23 | 22-Feb-22 | 22-Jan-22 | 28-Feb-22 |  |  |  | 0
636554 | 636554 - 2021 CABLE INJECTION - M14 - HWY 7 & 9TH LINE RD, MARKHAM | 815 - Addiscott | 151343 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 262697.21 | 725722.22 | 262697.21 | 262697.21 | Horlings, Jake | Nvinium | 31-Dec-21 | 22-Sep-22 | 01-Jan-21 | 11-Jul-21 | 06-Dec-21 | Contractor |  |  | 0
634993 | 634993 - DISSETTE STREET, BRADFORD - RELOCATE POLES FOR NEW DEVELOPMENT | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2021 | Pelleja, Emily | Harrington, James | 22-Apr-21 |  |  | 296929.42 | 231962.19 | 296929.42 | 296929.42 | Dan Kish | K-Line | 22-Jun-21 | 22-Sep-22 | 08-Jun-21 | 26-Apr-21 | 15-May-21 |  |  |  | 0
635979 | OH RELOCATION AT STEELES AVE W AND PALM GATE BLVD, VAUGHAN | 815 - Addiscott | 101763 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 57850.84 |  | 0 | Wong, Henry |  |  | 22-Sep-22
635665 | 635665 - ICI TRANSFORMER UPGRADE/ 500 EGLIN MILLS ROAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 21-Jun-21 |  |  | 34847.57 | 40781.5 | 34847.57 | 34847.57 | Dave Lindsay |  | 10-Aug-21 | 15-Feb-22 | 03-Aug-21 | 15-Sep-21 | 15-Sep-21 | Customer | Customer |  | 0
453656 | (WO318965) 45 Rodinea Rd | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Paterson, Greg | 07-Feb-19 |  |  | 16203.02 | 8709.95 | 16203.02 | 16203.02 | Steve Rumble | Somervl | 12-Apr-19 | 02-Jun-21 | 05-Apr-19 | 27-Apr-19 | 27-Apr-19 | Customer | Customer |  | 0
453574 | 453574 (WO 318865) 2019 Pole Replacement Batch 10 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 24-Jan-19 |  |  | 144733 | 128588.11 | 144733 | 144733 | Morrow, Joe |  | 15-Dec-19 | 15-Mar-21 | 25-Jul-19 | 19-Aug-19 | 18-Nov-19 |  |  |  | 0
453812 | 453812 (WO 319135) Pole Betterment. Tottenham. BATCH 2 (16 Poles) | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Pollock, Kim | 08-Oct-19 |  |  | 289426.6 | 329392.05 | 217224.6 | 289425.62 | Jeremy Wright |  | 31-Dec-19 | 08-Mar-21 | 11-Nov-19 | 18-Nov-19 | 19-Dec-19 | Filler |  |  | 72,201.02
633164 | 633164 - M44 Cochrane 44C-004 to M38FA1006 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 16-Sep-19 |  |  | 687740.72 | 617867.72 | 687740.72 | 687740.72 | Lamb, Tim | Transpw | 22-Nov-19 | 29-Oct-20 | 09-Oct-19 | 30-Sep-19 | 08-Nov-19 |  |  |  | 0
453111 | (WO 317977) Add 1x 27.6kV CCT - ELGIN MILLS RD-BAYVIEW TO LESLIE | 815 - Addiscott | 101781 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 27-Nov-18 |  |  | 315977 | 317340.38 | 315977 | 315977 | Morrow, Joe |  | 29-Nov-19 | 24-Aug-20 | 21-Feb-19 | 04-Feb-19 | 29-Jul-19 |  |  |  | 0
453259 | (WO318292) Highway No. 50 - #8865 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Yuen, Paul | 13-Sep-18 |  |  | 101488.12 | 68247.12 | 101488.12 | 101488.12 | Steve Rumble | Somervl | 30-Oct-18 | 10-Aug-20 | 12-Oct-18 | 19-Feb-19 | 10-Apr-19 | Customer | Customer |  | 0
452944 | 452944 (WO 317293) Replace 2 Transformers in V16 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 02-Nov-18 |  |  | 63215 | 21067.18 | 63215 | 63215 | Steve Rumble | Somervl | 24-Oct-19 | 24-Feb-20 | 23-Aug-19 | 16-Sep-19 | 30-Sep-19 | Filler |  |  | 0
453421 | 453421 (WO 318614) Cornell Centre Midrise Ph 2. ADAM SELLERS ST. - #58 AT RUSTLE WOODS | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 07-Nov-18 |  |  | 65636.65 | 55528.32 | 65636.65 | 65636.65 | Steve Rumble | Somervl | 28-Dec-18 | 24-Feb-20 | 17-Dec-18 | 12-Nov-19 | 19-Nov-19 | Customer | Customer |  | 0
632410 | (WO632410) 640 APPLEWOOD CRES - DEMOLITION | 815 - Addiscott | PARENT WORK ORDER INDUST/COMM | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Diefenbaker, Trevor A | 02-Aug-19 |  |  | 6904.91 | 4109 | 6904.91 | 6904.91 | Steve Rumble | N/A | 18-Sep-19 | 10-Feb-20 | 17-Sep-19 | 11-Sep-19 | 11-Sep-19 |  |  |  | 0
636640 | INSULATOR REPLACEMENT - KEELE ST - MMD TO RUTHERFORD RD | 815 - Addiscott | 150009 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 33076.2 |  | 0 | Wong, Henry |  |  | 26-Jul-23
634895 | 634895 - 185 DUNLOP ST E, BARRIE - CONDO DEVELOPMENT | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 25-Apr-22 |  |  | 276776.36 | 163548.09 | 276776.36 | 276776.36 | Lotto, Jay | HapAmp | 16-Sep-22 | 26-Jul-23 | 08-Jun-22 | 15-Aug-22 | 25-Oct-22 | Customer | Customer |  | 0
452827 | 452827 - ROYAL HILL - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan | 14-Apr-21 |  |  | 218712.64 | 29046.7 | 218712.64 | 218712.64 | Dave Lindsay |  | 25-Jun-21 | 09-Aug-23 | 28-May-21 | 25-Apr-23 |  | Customer | Customer |  | 0
453255 | (WO 318266) Leslie Street - Elgin Mills to 19th Avenue | 815 - Addiscott | 101762 | Active | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Battistella, Alexander | 21-Jan-19 |  |  | 536819.83 | 530521.63 | 496669 | 536819.83 | Shortt, Derek B. | Transpw | 06-Aug-19 | 26-Jul-23 | 12-Mar-19 | 11-Apr-19 | 30-Jun-19 | Customer |  |  | 40,150.83
636555 | 636555 - 2021 CABLE INJECTION - M20 - 14TH AVE & MCCOWAN RD, MARKHAM | 815 - Addiscott | 151348 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 589042.5 | 577826.8 | 589042.5 | 589042.5 | Horlings, Jake | Nvinium | 31-Dec-21 | 02-Mar-23 | 01-Jan-21 | 06-Jun-21 | 06-Dec-21 | Contractor |  |  | 0
454095 | 454095 - Anne St & Hwy 400 Pole Relocations for Bridge | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE | Medium | Infrast | 2021 | Pelleja, Emily | Harrington, James | 07-Jan-21 |  |  | 3067584.03 | 2524182.79 | 3067584.03 | 3067584.03 | Jeremy Wright | HapAmp | 02-Sep-21 | 22-Sep-22 | 11-Jan-21 | 07-Jan-21 | 14-Dec-21 |  | Lines |  | 0
636747 | POLE REPLACEMENT 2020 - 41 GUARDSMAN RD | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 02-May-22
635176 | 635176 - 131 ELLIS DRIVE, BARRIE - 3 PHASE SERVICE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | High | Indust | 2021 | Cranley, Stephen | Harris, Geoff L. | 30-Apr-21 |  |  | 64252.21 | 61761.48 | 64252.21 | 64252.21 | Lotto, Jay |  | 05-Jul-21 | 06-Apr-22 | 14-Jun-21 | 31-May-21 | 06-Oct-21 |  | Customer |  | 0
632819 | (WO 632819) YRRTC-Y2.2 DUCTBANK RELOCATION - 10579 YONGE STREET | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Lacombe, Joel |  |  |  | 0 | 16299.45 |  | 0 | Persaud, Ryan |  |  | 22-Nov-21 |  | 27-Aug-19 | 27-Aug-19
452679 | 452679 - EDGEHILL MANOR - SUBD RES EDS | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 14-Oct-20 |  |  | 117232.9 | 111093.01 | 117232.9 | 117232.9 | Lotto, Jay | Transpw | 22-Dec-20 | 01-Nov-21 | 07-Dec-20 | 21-Jan-21 | 03-Mar-21 | Customer |  |  | 0
453811 | 453811 (WO 319134) Pole Betterment. Tottenham. BATCH 1 (21 Poles) | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Pollock, Kim | 05-Jul-19 |  |  | 275683 | 262585.69 | 275683 | 275683 | Jeremy Wright |  | 31-Dec-19 | 15-Sep-21 | 26-Aug-19 | 09-Oct-19 | 06-Dec-19 |  |  |  | 0
634740 | 634740 - ICI NEW COMMERCIAL SERVICE / 721 WESTBURNE DR | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 28-Sep-20 |  |  | 122523.1 | 88669.44 | 122523.1 | 122523.1 | Dave Lindsay | Somervl | 17-Dec-20 | 12-Jul-21 | 23-Nov-20 | 18-Jan-21 | 27-Apr-21 | Customer | Customer |  | 0
452573 | 452573 (WO 315062) GO Transit Station | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | High | Transit | 2021 | Dibratto, Susan | Yuen, Paul | 16-Oct-19 |  |  | 107734.88 | 89283.86 | 107734.88 | 107734.88 | Dave Lindsay | Somervl | 10-Mar-20 | 12-Jul-21 | 13-Feb-20 | 30-Oct-20 | 27-Apr-21 | Customer | Customer |  | 0
454265 | 454265 - Regina Rd. #21 (Vaughan), Hwy. #7 & Martin Grove Rd. | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Yuen, Paul | 07-Aug-19 |  |  | 70958.5 | 58874.36 | 70958.5 | 70958.5 | Steve Rumble | Somervl | 26-Sep-19 | 01-Feb-21 | 06-Sep-19 | 24-Nov-19 | 03-Dec-19 |  | Customer |  | 0
633158 | 633158 - 100 BULLOCK DR | 815 - Addiscott | PARENT WORK ORDER INDUST/COMM | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Mann, Drew | 03-Sep-19 |  |  | 63629.37 | 31961.65 | 63629.37 | 63629.37 | Steve Rumble | Somervl | 10-Oct-19 | 29-Oct-20 | 01-Oct-19 | 30-Sep-19 | 23-Oct-19 |  | Customer |  | 0
453573 | 453573 (WO 318864) 2019 Pole Replacement Batch 09 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 24-Jan-19 |  |  | 214297 | 218031.07 | 214297 | 214297 | Morrow, Joe |  | 30-Oct-19 | 22-Oct-20 | 23-Jul-19 | 05-Aug-19 | 28-Oct-19 |  |  |  | 0
452943 | 452943 (WO 317292) Replace 2 Transformers in V15 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  |  | 34205 | 18362.62 | 34205 | 34205 | Steve Rumble | Somervl | 30-Nov-19 | 24-Feb-20 | 22-Jul-19 | 03-Sep-19 | 14-Nov-19 | Filler | Filler |  | 0
453654 | SOUTHGATE PHASE 2/INSPECT & CONNECT | 825 - Patterson | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Jan-19
634900 | 634900 - OH AND UG RELOCATION AT SIMMONS ST, VAUGHAN | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 05-Oct-21 |  |  | 555613.31 | 615956.46 | 630630.38 | 555613.31 | Morrow, Joe |  | 18-Mar-22 | 26-Jul-23 | 24-Jan-22 | 31-Jan-22 | 23-Mar-22 | Customer | Customer |  | -75,017.07
635183 | 635183 - 15186 YONGE ST, AURORA | 815 - Addiscott | 101791 | Active | HO | RELEASED | VerHigh | Res-ICI | 2023 | Cranley, Stephen | Harris, Geoff L. | 09-Aug-22 |  |  | 94447.99 | 12787.76 | 94447.99 | 94447.99 | Dave Lindsay | Somervl | 31-Oct-22 | 14-Aug-23 | 27-Sep-22 |  |  | Customer | Customer |  | 0
636556 | 636556 - 2021 CABLE INJECTION - V16 - LANGSTAFF RD & DUFFERIN ST, VAUGHAN | 815 - Addiscott | 151349 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 1228678.76 | 178602.51 | 1228678.76 | 1228678.76 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 23-May-21 |  | Contractor | Contractor |  | 0
452826 | 452826 - COUNTRY WIDE BLOCK 40/47 | 815 - Addiscott | 101887 | Active | 84 | H8 |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 18-May-21 |  |  | 83378.25 | 59049.5 | 83378 | 83378 | Dave Lindsay |  | 28-Jul-21 | 21-Aug-23 | 02-Jul-21 | 28-Jul-21 |  | Customer | Customer |  | 0
454235 | 454235 (WO 319635) Hwy 7 - Dufferin/Langstaff to Bowes/Hwy 7 | 815 - Addiscott | 103659 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 07-Nov-19 |  |  | 253294.18 | 559614.3 | 253294.18 | 253294.18 | Macdonald, Steve | K-Line | 01-Oct-20 | 26-Jul-23 | 08-Sep-20 | 01-Dec-20 | 05-Feb-21 | Lines |  |  | 0
453653 | 453653 - MAPLEVIEW DRIVE AND PRINCE WILLIAM WAY, BARRIE - RELOCATE POLES FOR RD WIDENING | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Harrington, James | 14-Jul-21 |  |  | 716809.78 | 630978.51 | 716809.78 | 716809.78 | Dan Kish | K-Line | 08-Sep-21 | 08-Mar-23 | 25-Aug-21 | 21-Jul-21 | 10-Sep-21 |  | Contractor |  | 0
636088 | 636088 - 2021 VAULT REPLACEMENTS V25 - MULCASTER | 825 - Patterson | 151526 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 25-Nov-21 |  |  | 154214.64 | 94729.68 | 154214.64 | 154214.64 | Lotto, Jay | HapAmp | 18-Feb-22 | 22-Sep-22 | 06-Jan-22 | 01-Dec-21 | 09-Dec-21 |  |  |  | 0
454260 | 454260 - Hughson @ Lunar Pole Relocation | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 10-Sep-19 |  |  | 13906.6 | 12234.07 | 13906.6 | 13906.6 | Macdonald, Larry |  | 31-Oct-19 | 31-Aug-22 | 07-Oct-19 | 11-Oct-19 | 11-Oct-19 |  |  |  | 0
452569 | 452569 (WO 315040) 9000 Jane St. Carisma Condo | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 26-Feb-20 |  |  | 91700.32 | 61666.84 | 91700.32 | 91700.32 | Dave Lindsay | Transpw | 14-Aug-20 | 21-Apr-22 | 03-Aug-20 | 29-Mar-21 | 30-Jun-21 | Customer | Customer |  | 0
633851 | 633851 - 681 YONGE ST, BARRIE - NEW 3 PHASE SERVICE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2021 | Cranley, Stephen | Harris, Geoff L. | 30-Jun-20 |  |  | 94250.77 | 75690.34 | 94250.77 | 94250.77 | Lotto, Jay | HapAmp | 14-Sep-20 | 15-Jul-21 | 24-Aug-20 | 22-Jul-20 | 05-Mar-21 |  |  |  | 0
453419 | (WO318611) CAN-AR & Hwy 50 (8905 Hwy 50. Vaughan) | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 27-Mar-19 |  |  | 132867.45 | 106956.36 | 132867.45 | 132867.45 | Steve Rumble | Somervl | 14-May-19 | 21-Jun-21 | 03-May-19 | 04-Jun-19 | 19-Jul-19 |  | Customer |  | 0
453810 | 453810 (WO 319133) Pole Betterment. Alliston. BATCH 4 (2 Poles) | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Pollock, Kim | 18-Sep-19 |  |  | 85294.43 | 73222.83 | 85294.43 | 85294.43 | Jeremy Wright |  | 29-Oct-19 | 29-Oct-20 | 15-Oct-19 | 06-Dec-19 | 20-Dec-19 |  |  |  | 0
453572 | (WO 318863) 2019 Pole Replacement Batch 08 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 02-Jan-19 |  |  | 126386 | 126565.22 | 126386 | 126386 | Morrow, Joe |  | 13-Sep-19 | 26-Nov-20 | 19-Jul-19 | 03-Jun-19 | 07-Aug-19 |  |  |  | 0
453252 | 453252 (WO 318259) Pole relocation Hwy 27 and CPR | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Barry, Kenneth | 22-Aug-19 |  |  | 461049.93 | 399073.91 | 461049.93 | 461049.93 | Macdonald, Steve | K-Line | 21-Oct-19 | 04-May-20 | 20-Sep-19 | 25-Sep-19 | 04-Nov-19 |  |  |  | 0
452942 | ( WO 317284) Replace 10 Transformers in V30 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  |  | 279476 | 142188.22 | 279476 | 279476 | Steve Rumble | Somervl | 01-Nov-19 | 24-Feb-20 | 23-Jun-19 | 21-Jul-19 | 15-Oct-19 |  | Filler |  | 0
452672 | 452672 (WO 315938) ICI Padmount Transformer Installation | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Stephens, Barry N. | Dibratto, Susan | 06-Apr-18 |  |  | 223027.94 | 197868.48 | 223027.94 | 223027.94 | Steve Rumble | Transpw | 21-Dec-18 | 24-Feb-20 | 22-Nov-18 | 11-Oct-18 | 10-Nov-19 |  |  |  | 0
317375 | (WO317375) Expo Condos Ph 3 & 4 | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Dibratto, Susan | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 01-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
636557 | 636557 - 2022 CABLE INJECTION - M31 - OLD KENNEDY RD & STEELES AVE E, MARKHAM | 815 - Addiscott | 151360 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 |  |  | 1302095.7 | 1667866.65 | 1302095.7 | 1302095.7 | Horlings, Jake | Nvinium | 31-Dec-22 | 26-Jul-23 | 01-Jan-22 | 01-Jan-22 |  |  |  |  | 0
636102 | 636102 - 8960 JANE ST / VAU / NS/ CO-STN | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 08-Jun-22 |  |  | 46900.2 | 53636.84 | 46900.2 | 46900.2 | Dave Lindsay | Somervl | 12-Aug-22 | 20-Jul-23 | 22-Jul-22 | 27-Oct-22 | 08-Dec-22 | Customer | Customer |  | 0
632814 | (WO632814) 100 MILL ST E | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 13-Feb-23
453952 | 453952 (WO 319316) HE2019-017 - Bell BLOOMINGTON RD AND BAYVIEW CRT S | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 15-Oct-19 |  |  | 4058.58 | 3330.15 | 4058.58 | 4058.58 | Macdonald, Larry |  | 10-Dec-19 | 22-Sep-22 | 08-Nov-19 | 07-Nov-19 | 07-Nov-19 |  |  |  | 0
633125 | 633125 - CEDARTRAIL SUBDIVISION/INSPECT AND CONNECT | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 04-Jun-20 |  |  | 137391.02 | 132561.29 | 137391.02 | 137391.02 | Dave Lindsay | Transpw | 25-Sep-20 | 24-Oct-21 | 31-Aug-20 | 07-Dec-20 | 17-Feb-21 | Customer | Customer |  | 0
632360 | 632360 - PCB Transformer Batch 2 | 825 - Patterson | 151450 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 22-Oct-19 |  |  | 191354.56 | 93851.19 | 191354.56 | 191354.56 | Jeremy Wright |  | 31-Dec-19 | 20-Oct-21 | 14-Nov-19 | 14-Nov-19 | 09-Dec-19 |  |  |  | 0
454258 | (WO 319663) OH Transfer existing circuits to new Hydro One poles at Yonge & Regatta intersection | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 20-Jun-19 |  |  | 47127 | 64696.57 | 47127 | 47127 | Macdonald, Larry |  | 30-Sep-19 | 29-Apr-21 | 30-Jul-19 | 10-Sep-19 | 10-Sep-19 |  |  |  | 0
633843 | 633843 - POLE REPLACEMENT 2019 - P31527 - EMERGENCY REPLACEMENT | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 23-Oct-19 |  |  | 19056.73 | 18775.63 | 19056.73 | 19056.73 | Macdonald, Larry |  | 16-Dec-19 | 22-Oct-20 | 11-Nov-19 | 09-Dec-19 | 11-Dec-19 |  |  |  | 0
453251 | (WO318257) 430 Holland St. West- Bradford Boston Pizza | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Martin, Shane | 21-Nov-18 |  |  | 72825.77 | 66787.29 | 72825.77 | 72825.77 | Jeremy Wright | Transpw | 28-Dec-18 | 12-Oct-20 | 12-Nov-18 | 20-Dec-18 | 10-Jun-19 | Customer | Customer |  | 0
453418 | (WO318610) Build Two Feeder Ties on Hwy 50 between Vaughan and Brampton | 815 - Addiscott | 150264 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 27-Nov-18 |  |  | 80846 | 80615.33 | 80846 | 80846 | Macdonald, Steve | K-Line | 19-Jun-19 | 24-Aug-20 | 03-Jun-19 | 03-Jun-19 | 07-Aug-19 |  |  |  | 0
452825 | 452825 (WO 316749) Water Pumping Station | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Martin, Shane | 25-Sep-19 |  |  | 32592.81 | 36001.59 | 32592.81 | 32592.81 | Jeremy Wright |  | 28-Oct-19 | 17-Aug-20 | 21-Oct-19 | 21-Oct-19 | 23-Oct-19 |  |  |  | 0
453809 | 453809 (WO 319132) Pole Betterment. Alliston. BATCH 3 (15 Poles) | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Pollock, Kim | 17-May-19 |  |  | 192908 | 94675 | 192908 | 192908 | Jeremy Wright |  | 30-Nov-19 | 20-Jul-20 | 01-Aug-19 | 27-May-19 | 18-Nov-19 |  | Filler |  | 0
454093 | 454093 (WO 319485) Replace P32141 BAYVIEW AVE & LAURELEAF, MARKHAM | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 19-Jun-19 |  |  | 81411 | 67112 | 81411 | 81898.65 | Shortt, Derek B. |  | 07-Nov-19 | 20-Jul-20 | 16-Oct-19 | 03-Dec-19 | 17-Dec-19 |  |  |  | 487.65
453648 | (WO 318954) Replace P28996 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 08-Mar-19 |  |  | 26107 | 25582.68 | 26107 | 26107 | Macdonald, Steve | K-Line | 18-Sep-19 | 25-May-20 | 13-Aug-19 | 20-Aug-19 | 20-Aug-19 |  |  |  | 0
635694 | CUSTOMER CAPITAL PROJECT FOR SUNSET BEACH POLE RELOCATION | 815 - Addiscott | 151531 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
452567 | (WO315030) 8,10,18 Rouge Valley | 815 - Addiscott | ICI Padmount Tx Installation | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Paterson, Greg | 13-Mar-19 |  |  | 97785.83 | 90543.74 | 97785.83 | 97785.83 | Steve Rumble | Somervl | 15-Apr-19 | 13-Jan-20 | 01-Apr-19 | 16-Apr-19 | 14-Jun-19 |  | Customer |  | 0
635203 | 8300 KEELE ST / ICI PAD TX UPGRADE | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
452671 | PARENT W.O. FOR INSPECT/CONNE/I&C SUNSET BEACH SUBDIVISION | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
635051 | 635051 - TRANSFORMER REPLACEMENT 2020 - BATCH 15 - REPLACE 7 TXS | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 27-Jan-20 | 7 | 7 | 62094.37 | 28109.89 | 62094.37 | 62094.37 | Dave Lindsay |  | 04-Dec-20 | 26-Jul-23 | 23-Nov-20 | 31-Oct-22 | 31-Oct-22 | Filler | Filler |  | 0
633895 | 2020 SWITCH RENEWAL - EAST - BARRIE - 136 BERCY ST. | 825 - Patterson | 101027 | Active | HL | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 20663.57 |  | 0 | Persaud, Ryan |  |  | 26-Jul-23
636112 | 636112 - DONNA MAE ESTATES | 815 - Addiscott | 101887 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Alarcon, Alejandro | 16-Mar-22 |  |  | 83925.85 | 74785.58 | 83925.85 | 83925.85 | Dave Lindsay | Transpw | 25-May-22 | 03-Aug-23 | 03-May-22 | 13-Aug-22 | 08-Dec-22 | Customer | Customer |  | 0
453951 | 453951 - BRADFORD EAST DEV. BLK170/INSPECT AND CONNECT | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 07-Oct-22 |  |  | 140869.22 | 142065.25 | 140869.22 | 140869.22 | Lotto, Jay | Transpw | 20-Dec-22 | 20-Dec-22 | 24-Nov-22 | 26-Sep-22 | 26-Sep-22 |  |  |  | 0
453097 | (WO 317896) OH Relocation - 7089 YONGE STREET, MARKHAM, ON | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Zhang, Jiacheng | 27-Feb-19 |  |  | 208546 | 98978.55 | 208546 | 208546 | Macdonald, Steve | K-Line | 23-May-19 | 22-Sep-22 | 15-Apr-19 | 20-May-19 | 06-Jun-19 | Contractor | Contractor |  | 0
453570 | 453570 (WO 318860) NEW WESTMINSTER DRIVE. CONDO | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 23-Jun-20 |  |  | 114284.53 | 84868.22 | 114284.53 | 114284.53 | Dave Lindsay | Somervl | 28-Aug-20 | 31-Aug-22 | 26-Aug-20 | 22-Jun-21 | 21-Jul-21 | Customer | Customer |  | 0
453487 | 453487 (WO 318721) 2019 Cable Injection - (M44) - Konrad Cres | 815 - Addiscott | 150208 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 25-Jan-19 |  |  | 844830 | 534595.81 | 844830 | 844830 | Horlings, Jake | Nvinium | 02-Dec-19 | 10-Aug-22 | 22-Apr-19 | 25-Jun-19 | 19-Nov-21 | Contractor | Contractor |  | 0
635204 | 635204 - 11110 JANE ST / VAU / NS / 3PH CO-STN | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 19-Apr-21 |  |  | 37697.03 | 34166.79 | 37697.03 | 37697.03 | Dave Lindsay | Somervl | 18-Jun-21 | 08-Jun-22 | 31-May-21 | 27-Sep-21 | 11-Feb-22 | Customer | Customer |  | 0
636558 | 636558 - 2021 SUNNIDALE UG CABLE REPLACEMENT | 825 - Patterson | 151336 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 01-Jan-21 |  |  | 1898516.03 | 1932214.3 | 1898516.03 | 1898516.03 | Lotto, Jay | Transpw | 28-May-21 | 21-Apr-22 | 06-Apr-21 | 03-May-21 | 19-Oct-21 | Contractor | Contractor |  | 0
633058 | 633058 - GO VILLAGE PH2 / INSPECT & CONNECT | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 16-Apr-21 |  |  | 671157.7 | 641730.06 | 671157.7 | 671157.7 | Lotto, Jay | Transpw | 09-Jul-21 | 10-Nov-21 | 31-May-21 | 15-Jun-21 | 01-Oct-21 | Customer | Customer |  | 0
453417 | (WO318607) Cauthers Crescent Extension | 825 - Patterson | 101887 | Inactive | 99 | CANCELLED |  |  | 2021 |  | Perks, Dan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 25-Oct-21
632805 | 632805 - 63 ERIC T SMITH WAY | 815 - Addiscott | 101919 | Inactive | 99 | COMPLETE | Low | Comm | 2021 | Cranley, Stephen | Paterson, Greg | 11-Oct-19 |  |  | 43126.47 | 47397.08 | 43126.47 | 43126.47 | Dave Lindsay | Somervl | 10-Dec-19 | 12-Jul-21 | 15-Nov-19 | 17-Nov-20 | 22-Mar-21 | Customer | Customer |  | 0
632359 | 632359 - PCB TRANSFORMER REPLACEMENTS BARRIE BATCH 1 | 825 - Patterson | 151450 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 21-Oct-19 |  |  | 96516.91 | 71131.61 | 96516.91 | 96516.91 | Jeremy Wright |  | 20-Dec-19 | 27-May-21 | 14-Nov-19 | 04-Nov-19 | 06-Dec-19 |  |  |  | 0
453808 | 453808 (WO 319131) Pole Betterment. Alliston. BATCH 2 (18 Poles) | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Pollock, Kim | 12-Apr-19 |  |  | 307716 | 262363.68 | 307716 | 307716 | Jeremy Wright |  | 31-Dec-19 | 14-Dec-20 | 25-Jun-19 | 09-Jul-19 | 22-Nov-19 |  | Filler |  | 0
453647 | 453647 (WO 318953) Pole Replacement 2019 - Replace 3 poles at Yonge, Aurora | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 11-Dec-18 |  |  | 38642 | 32222.99 | 38642 | 38642 | Macdonald, Larry |  | 30-Aug-19 | 19-Nov-20 | 03-Jun-19 | 21-Oct-19 | 24-Nov-19 |  |  |  | 0
453249 | BEAR CREEK LANDING - SUBD RES EDS | 825 - Patterson | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Feb-19
636425 | 636425 - HIGHWAY NO. 27 - #7300 (CATHOLIC CEMETERY) | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 16-Apr-21 |  |  | 64784.21 | 29435.87 | 64784.21 | 64784.21 | Dave Lindsay | Somervl | 29-Jun-21 | 10-Aug-23 | 31-May-21 | 16-Sep-21 |  | Customer | Customer |  | 0
633894 | 2020 SWITCH RENEWAL - EAST - BARRIE - 169 BROCK ST. | 815 - Addiscott | 101027 | Active | HL | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 13839.01 |  | 0 | Persaud, Ryan |  |  | 26-Jul-23
636566 | PHASE 1 - UG CABLE REPLACEMENT - 14TH, OLD KENNEDY, STEELES, WARDEN | 815 - Addiscott | 101781 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 161943.18 |  | 0 | Wong, Henry |  |  | 26-Jul-23
452819 | 452819 (WO 316697) Hydro Relocation - HWY 427 EXTENSION, HUNTINGTON Rr, MAJOR MACK DR, VAUGHAN | 815 - Addiscott | 101762 | Active | 98 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 31-Dec-18 |  |  | 213879 | 172973.47 | 213879 | 213879 | Macdonald, Steve | N/A | 31-Dec-19 | 26-Jul-23 | 06-May-19 | 06-May-19 | 07-Jun-21 |  | Lines |  | 0
454089 | 454089 - INTERCHANGE WAY - #250 - MULTIPLE RESIDENTIAL CONDOS | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Yuen, Paul | 15-Apr-21 |  |  | 163871.66 | 134206.83 | 163871.66 | 163871.66 | Dave Lindsay | Somervl | 22-Mar-22 | 17-Jul-23 | 28-Jan-22 | 13-May-22 | 18-Jul-22 | Customer | Customer |  | 0
454125 | 454125 (WO 319518) V18 - Major Mackenzie and Keele (2020 Cable Injection) | 815 - Addiscott | 150025 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 01-Nov-19 |  |  | 1112683.66 | 1285428.23 | 1112683.66 | 1112683.66 | Horlings, Jake | Nvinium | 30-Dec-20 | 21-Apr-22 | 06-Jan-20 | 08-Jun-20 | 05-Apr-22 | Contractor | Contractor |  | 0
453804 | (WO319127) cable relocation. ROSE BRANCH DRIVE, RICHMOND HILL | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 02-May-19 |  |  | 75393 | 70136.95 | 72693 | 75393 | Lamb, Tim | Transpw | 15-Jul-19 | 29-Mar-21 | 02-Jul-19 | 09-Jul-19 | 23-Sep-19 |  |  |  | 2,700.00
453646 | 453646 (WO 318952) Orlon Cres - Reduce secondary service dips | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 29-Aug-19 |  |  | 184008.78 | 169106.77 | 184008.78 | 184008.78 | Lamb, Tim | Transpw | 22-Oct-19 | 14-Dec-20 | 01-Oct-19 | 11-Nov-19 | 11-Dec-19 |  |  |  | 0
452939 | ( WO 317278) Replace 23 Transformers in V53 V54 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Nov-18 |  |  | 191912 | 147762.62 | 191912 | 191912 | Steve Rumble |  | 25-Apr-19 | 20-Jul-20 | 21-Jan-19 | 17-Jan-19 | 21-Mar-19 |  |  |  | 0
453237 | 453237 (WO 318240) M43 Steeles and Quail Valley | 815 - Addiscott | 150256 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 11-Jun-19 |  |  | 819759.31 | 833871 | 812067 | 819759.31 | Cory Ruiter | Transpw | 13-Sep-19 | 20-Jul-20 | 01-Aug-19 | 03-Sep-19 | 18-Dec-19 | Contractor | Contractor |  | 7,692.31
636116 | PARENT W.O. FOR INSPECT/CONNECT/I&C -KING AND BOND DEVELOPMENT | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Wong, Henry
633670 | 19TH AVE, BAYVIEW RD TO LESLIE ST | 815 - Addiscott | 101762 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 24-Sep-19
453568 | (WO 318858) POLE RELOCATIONS | 815 - Addiscott | 150591 | Inactive | 99 | CANCELLED |  |  | 2022 | O'Gay, Brian | Grahovac, John |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 15-Nov-18
636567 | PHASE 2 - UG CABLE REPLACEMENT - 14TH, OLD KENNEDY, STEELES, WARDEN | 815 - Addiscott | 101781 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 90689.43 |  | 0 | Wong, Henry |  |  | 26-Jul-23
452818 | 452818 (WO 316696) Hydro Relocation - HWY 427 EXTENSION, RUTHERFORD RD, EAST OF HUNTINGTON RD, VGN | 815 - Addiscott | 101762 | Active | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Zhang, Jiacheng | 01-Nov-18 |  |  | 2981400 | 249592.12 | 2981400 | 2981400 | Macdonald, Steve |  | 02-Jan-19 | 26-Jul-23 | 01-Jan-19 | 01-Jan-19 | 01-Oct-19 |  | Customer |  | 0
453485 | 453485 (WO 318719) 2019 Cable Injection - (M27) - Kennedy, 16th, McCowan-Hwy 7 | 815 - Addiscott | 150015 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 25-Jan-19 |  |  | 1102924 | 896395.3 | 1102924 | 1102924 | Horlings, Jake | Nvinium | 31-Dec-20 | 10-Aug-22 | 02-Jan-20 | 15-Jun-20 | 19-Nov-21 | Contractor | Contractor |  | 0
453803 | 453803 (WO 319126) HWY 404 AND 16TH AVE. Pad Tx relocation | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE | High | Infrast | 2021 | Lacombe, Joel | Gonzales, Leonard | 29-Apr-20 |  |  | 537800.4 | 566748.84 | 537800.4 | 537800.4 | Dave Lindsay | Transpw | 17-Jul-20 | 11-Jan-22 | 22-Jun-20 | 22-Jun-20 | 11-Nov-21 |  | Contractor |  | 0
453645 | 453645 (WO 318951) 9272 BAYVIEW AVENUE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 26-Sep-19 |  |  | 49557.23 | 43446.23 | 49557.23 | 49557.23 | Dave Lindsay | Somervl | 21-Nov-19 | 23-Aug-21 | 11-Nov-19 | 01-Sep-20 | 27-Apr-21 | Customer | Customer |  | 0
453114 | 453114 (WO 317980) M48/R05 19th Av - Leslie to Woodbine - New 27.6kV Pole Line | 815 - Addiscott | 102545 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 31-Oct-19 |  |  | 1488597.52 | 1527118.06 | 1237828.5 | 1488597.52 | Ryan Walsh | Transpw | 16-Dec-20 | 11-Aug-21 | 05-Oct-20 | 23-Sep-20 | 06-Jan-21 |  |  |  | 250,769.02
632767 | 632767 - REPLACE P23179 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 01-Aug-19 |  |  | 18656.66 | 13998.54 | 18656.66 | 18656.66 | Macdonald, Larry |  | 31-Oct-19 | 29-Oct-20 | 06-Sep-19 | 22-Oct-19 | 22-Oct-19 |  |  |  | 0
633023 | 633023 - 141 & 151 KING ST, BARRIE - NEW 3 PHASE SERVICE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 04-Oct-19 |  |  | 50248.74 | 36458.86 | 50248.74 | 50248.74 | Jeremy Wright | HapAmp | 19-Nov-19 | 29-Oct-20 | 11-Nov-19 | 11-Dec-19 | 19-Dec-19 |  |  |  | 0
453414 | (WO 318602) Pole Replacement 2019 Batch 3 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  |  | 152103 | 71783.3 | 152103 | 152103 | Morrow, Joe |  | 30-Jun-19 | 22-Oct-20 | 02-Jan-19 | 07-Jan-19 | 27-Jun-19 |  |  |  | 0
454088 | 454088 (WO 319479) 8251 Keele St | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Paterson, Greg | 18-Nov-19 |  |  | 35160.8 | 26227.22 | 35160.8 | 35160.8 | Steve Rumble | Somervl | 11-Dec-19 | 19-Oct-20 | 02-Dec-19 | 13-Dec-19 | 20-Dec-19 | Customer | Customer |  | 0
453566 | (WO318854) ZAYO J/U permit HE2018-144. WELHAM ROAD, BARRIE | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Harrington, James | 01-Nov-17 |  |  | 0 | 5831.93 |  | 0 | Jeremy Wright |  | 25-Jul-19 | 05-Oct-20 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
453233 | (WO318234) Trans Canada Pipe Line-Phase 2 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 24-May-19 |  |  | 110638.62 | 102164.18 | 110638.62 | 110638.62 | Steve Rumble | Somervl | 21-Jun-19 | 24-Feb-20 | 11-Jun-19 | 03-Jun-19 | 17-Jun-19 |  |  |  | 0
452563 | ( WO 314953) WOODBRIDGE PARK RESIDENTIAL | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alarcon, Alejandro | 22-May-19 |  |  | 90563.94 | 314238.01 | 90563.94 | 90563.94 | Steve Rumble |  | 30-Aug-19 | 10-Feb-20 | 01-Aug-19 | 02-Jul-19 | 23-Oct-19 |  | Customer |  | 0
636134 | 636134 - BRENTWOOD SUBDIVISION VAUGHAN / I&C WO | 815 - Addiscott | 101887 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Sabbah, Amir | 11-Aug-22 |  |  | 117378.53 | 108199.82 | 117378.53 | 117378.53 | Dave Lindsay | Transpw | 13-Oct-22 | 26-Jul-23 | 26-Sep-22 | 05-Dec-22 | 08-Dec-22 | Customer | Customer |  | 0
636568 | PHASE 3 - UG CABLE REPLACEMENT - 14TH, OLD KENNEDY, STEELES, WARDEN | 815 - Addiscott | 101781 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 453.38 |  | 0 | Wong, Henry |  |  | 26-Jul-23
452817 | 452817 (WO 316695) OH Relocation - HWY 427 EXTENSION, LANGSTAFF RD, EAST OF HUNTINGTON RD, VAUGHAN | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 07-Oct-19 |  |  | 156850.14 | 104260.43 | 156850.14 | 156850.14 | Macdonald, Steve |  | 30-Apr-20 | 24-Apr-23 | 07-Oct-19 | 07-Oct-19 | 07-Jun-21 | Contractor | Contractor |  | 0
454086 | (WO319477) 5875 HIGHWAY 7 - VAUGHAN | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Barry, Kenneth |  |  |  | 0 | 8474.42 |  | 0 | Persaud, Ryan |  |  | 14-Mar-23
632279 | (WO632279 ) JOINT USE PERMIT HE2019-063 - BAYVIEW PARK LANE/ SUNSET BEACH ROAD | 815 - Addiscott | 151495 | Inactive | 99 | CANCELLED |  |  | 2021 | O'Gay, Brian | Martin, Shane |  |  |  | 0 | 3857.67 |  | 0 | Persaud, Ryan |  |  | 22-Sep-22
636429 | 636429 - ICI NEW APARTMENT/ 4310 HWY 7 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Diefenbaker, Trevor A | 12-Feb-21 |  |  | 72684 | 68807.52 | 72684 | 72684 | Dave Lindsay | Somervl | 27-Apr-21 | 31-Aug-22 | 26-Mar-21 | 20-Jan-21 | 11-Feb-22 |  | Customer |  | 0
452642 | 452642 (WO 315651) Rutherford Road (Westburne Drive to Confederation PKWY), Vaughan | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Barry, Kenneth | 13-Sep-18 |  |  | 2041325.4 | 2619815.25 | 1594118 | 2041325.4 | Morrow, Joe | Transpw | 23-Nov-18 | 09-Aug-22 | 17-Sep-18 | 05-Nov-18 | 01-Oct-19 |  |  |  | 447,207.40
454123 | 454123 (WO 319516) V36 - Steeles and Pine Valley (2020 Cable Injection) | 815 - Addiscott | 150021 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 27-Nov-19 |  |  | 227528.77 | 229181.79 | 227528.77 | 227528.77 | Horlings, Jake | Nvinium | 30-Dec-20 | 21-Apr-22 | 27-Jan-20 | 01-Jan-20 | 22-Mar-22 | Contractor | Contractor |  | 0
632732 | 632732 - CONNECT BELL BONDS - COSTA ROAD - VAUGHAN | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 04-Oct-19 |  |  | 12142.34 | 1642.48 | 1410.16 | 1410.16 | Don Rothman |  | 16-Oct-19 | 24-Jun-21 | 15-Oct-19 | 29-Oct-19 | 29-Oct-19 |  |  |  | 0
452561 | 452561 (WO 314890) New Condo Development | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Martin, Shane | 13-Sep-19 |  |  | 145902.19 | 136921.94 | 145902.19 | 145902.19 | Jeremy Wright | Transpw | 19-Oct-19 | 01-Feb-21 | 15-Oct-19 | 19-Dec-19 | 13-Dec-19 | Customer |  |  | 0
453225 | (WO318215) 7200 Martin Grove | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 06-May-19 |  |  | 118742.8 | 100439.27 | 118742.8 | 118742.8 | Steve Rumble | Somervl | 02-Jul-19 | 13-Oct-20 | 10-Jun-19 | 18-Jun-19 | 21-Jun-19 |  | Customer |  | 0
453565 | (WO 318853) JU HE2018-148 Bell | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Battistella, Alexander | 29-Mar-19 |  |  | 8651 | 5178.2 | 8651 | 8651 | Macdonald, Larry |  | 25-Jul-19 | 24-Aug-20 | 06-May-19 | 06-May-19 | 08-May-19 |  |  |  | 0
452935 | ( WO 317246) REPLACE 3 SWITCHGEARS | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  | 3 | 232554 | 189608.32 | 232554 | 232554 | Lamb, Tim | Somervl | 30-Jun-19 | 24-Feb-20 | 01-Apr-19 | 06-Apr-19 | 10-Jun-19 |  | Filler |  | 0
632925 | (WO 632925) FUTURE WORK ST. JOHNS SIDE ROAD BAYVIEW TO 404 | 815 - Addiscott |  | Inactive | 99 | CANCELLED | Medium | Infrast | 2022 | Corriveau, Tom N | Barry, Kenneth |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 09-Aug-19
453478 | (WO318712) AMBER ST. - #120 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 06-Dec-18 |  |  | 111700.34 | 54133.69 | 111700.34 | 111700.34 | Steve Rumble | Somervl | 18-Mar-19 | 20-Jun-19 | 04-Mar-19 | 02-May-19 | 29-May-19 | Customer | Customer |  | 0
636434 | 636434 - 2920 HIGHWAY 7/ VAU / NS / ICI CO-SUBSTATION | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 04-Aug-22 |  |  | 59189.79 | 43410.58 | 59189.79 | 59189.79 | Dave Lindsay | Somervl | 10-Nov-22 | 03-Aug-23 | 19-Oct-22 | 11-May-23 |  | Customer | Customer |  | 0
454085 | 454085 - RESIDENTIAL SUBDIVISION - OBSERVATORY NORTH PHASE 2 | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 20-Oct-21 |  |  | 44454.8 | 23059.43 | 44454.8 | 44454.8 | Dave Lindsay |  | 15-Dec-21 | 08-Aug-23 | 02-Dec-21 | 17-May-22 |  | Customer | Customer |  | 0
453477 | 453477 - DUCKWORTH STREET RELOCATIONS/RELOCATE FOR ROAD WIDEINING | 825 - Patterson | 152255 | Active | 91 | ACTIVE |  |  | 2023 | Pelleja, Emily | Harrington, James | 12-Dec-22 |  |  | 2199921.72 | 1537480.72 | 2287597.19 | 2199921.72 | Mark Timbers | HapAmp | 01-May-23 | 26-Jul-23 | 16-Jan-23 | 09-Jan-23 |  |  | Design |  | -87,675.47
454240 | 454240 - ROAD AUTHORITY RELOCATION-UG-HWY 404 MID-BLOCK CROSSING | 815 - Addiscott | 101762 | Active | 82 | RELEASED |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng | 30-Mar-23 |  |  | 2676838.33 | 229343.88 | 2676838.33 | 2676838.33 | Dave Lindsay | Transpw | 19-Dec-23 | 19-Dec-23 | 08-Jun-23 | [5 empty] | 0
452641 | 452641 (WO 315634) CoRNELL BUS TERMINAL | 815 - Addiscott | 101791 | Active | 99 | ANALYZE |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 17-Oct-18 |  |  | 131070.13 | 145871.51 | 131070.13 | 131070.13 | Dave Lindsay | Transpw | 13-Dec-18 | 26-Jul-23 | 21-Nov-18 | 08-May-19 | 09-Mar-23 | Customer | Customer |  | 0
453563 | PARENT W.O. FOR INSPECT/CONNE/I&C:1890 HIGHWAY 7-ROSE GARDEN | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 10000 |  | 0 | Persaud, Ryan |  |  | 24-Apr-23
452816 | ( WO 316694) UG Relocation - HWY 427 AND ZENWAY BLVD, VAUGHAN - UG Reloc due to HWY 427 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Zhang, Jiacheng | 02-Jan-19 |  |  | 39067 | 35771.7 | 39067 | 39067 | Macdonald, Steve | B&M | 25-Jul-19 | 22-Sep-22 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
454122 | 454122 (WO 319515) V01 - Yonge-Steeles-Bathurst-Centre (2020 Cable Injection) | 815 - Addiscott | 150014 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 29-Oct-19 |  |  | 1219621.33 | 913281.59 | 1219621.33 | 1219621.33 | Horlings, Jake | Nvinium | 30-Dec-20 | 21-Apr-22 | 06-Jan-20 | 01-Jan-20 | 25-Jan-22 | Contractor | Contractor |  | 0
633891 | 633891 - 2021 DISTRIBUTION AUTOMATION - EAST - BARRIE - LT-B40704 - BROCK ST | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Bowman, Todd J | Walters, Geoffrey D | 30-Nov-20 |  |  | 137161.58 | 196979.73 | 137161.58 | 137161.58 | Dan Kish |  | 30-Aug-21 | 12-Apr-22 | 03-Aug-21 | 26-Oct-21 | 05-Nov-21 | Filler | Filler |  | 0
453411 | (Wo 318598) Pole Relocation - 19th Avenue & Hwy 48, Markham | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 27-Mar-19 |  |  | 28871 | 32493.38 | 28871 | 28871 | Macdonald, Steve | K-Line | 15-May-19 | 14-Oct-21 | 29-Apr-19 | 01-Jul-19 | 11-Jul-19 |  |  |  | 0
453800 | 453800 (WO 319123) DA - S‐B1019 - 62 Ardagh Road - InLine Switch to Automated 44kV - Barrie | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 09-Oct-19 |  |  | 239514.29 | 224726.63 | 239514.29 | 239514.29 | Dan Kish | K-Line | 13-Dec-19 | 29-Oct-20 | 25-Nov-19 | 20-Nov-19 | 11-Dec-19 |  |  |  | 0
453082 | 453082 (WO 317837) 81 Performance Drive | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 25-Jan-19 |  |  | 61808.2 | 46732.04 | 61808.2 | 61808.2 | Steve Rumble | Somervl | 25-Mar-19 | 24-Feb-20 | 13-Mar-19 | 24-Oct-19 | 25-Nov-19 | Customer | Customer |  | 0
453217 | FRATTAROLI SUBDIVISION/INSPECT & CONNECT | 825 - Patterson | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 |  | Fitz Randolph, Kim C |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Feb-19
454082 | (WO319472) 4080 Hwy 7 | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 13-Feb-23
632255 | (WO632255) 144 MARKHAM ROAD, UG CABLE RELOCATION | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 2040.09 |  | 0 | Persaud, Ryan |  |  | 22-Sep-22
633890 | 633890 - 2021 Vault Lid Renewal - V16 - 42 Maple Ave. | 825 - Patterson | 151526 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 31-Mar-20 |  |  | 137860 | 72976.44 | 137860 | 137860 | Lotto, Jay |  | 17-Dec-20 | 21-Apr-22 | 07-Dec-20 | 29-Sep-21 | 19-Oct-21 | Materials | Materials |  | 0
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE | High | MLinx | 2021 | Vande Kuyt, Greg | Grahovac, John | 04-Oct-19 |  |  | 1554201.75 | 1738111.65 | 980351.14 | 1554201.75 | Shane Christopher | Transpw | 30-Sep-20 | 27-Jan-22 | 02-Jul-20 | 23-Mar-20 | 22-Jan-21 | Customer | Customer |  | 573,850.61
632726 | 632726 - 14 CEDAR AVE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 27-Aug-20 |  |  | 63965.91 | 54015.12 | 63965.91 | 63965.91 | Dave Lindsay | Somervl | 13-Nov-20 | 09-Dec-21 | 19-Oct-20 | 16-Sep-20 | 25-Jan-21 |  | Customer |  | 0
453562 | 453562 (WO 318829) 1588 ST. JOHN'S SIDE ROAD | 825 - Patterson | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Fitz Randolph, Kim C | 28-Nov-18 |  |  | 10952 | 6110.09 | 10952 | 10952 | Steve Rumble | K-Line | 14-Aug-19 | 15-Oct-21 | 12-Aug-19 | 24-Jul-19 | 01-Aug-19 |  |  |  | 0
452815 | ( WO 316693) Hydro Relocation - HWY 427 AND HWY 7, VAUGHAN - Hydro Reloc due to HWY 427 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Zhang, Jiacheng | 02-Jan-19 |  |  | 200000 | 136544.9 | 200000 | 200000 | Macdonald, Steve |  | 25-Jul-19 | 03-Oct-21 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
453799 | 453799 (WO 319122) S-B355846 – 555 Bayview - InLine switch to 44kV Automated – Barrie | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 11-Jun-19 |  |  | 170479 | 172343.28 | 170479 | 170479 | Dan Kish |  | 30-Nov-19 | 01-Jul-21 | 01-Aug-19 | 03-Sep-19 | 11-Oct-19 | Filler |  |  | 0
452640 | 452640 (WO 315625) Extension of Duct Banks on Leslie St | 815 - Addiscott | 101764 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Gonzales, Leonard | 06-Aug-19 |  |  | 246407.61 | 220316.48 | 246407.61 | 246407.61 | Lamb, Tim | Transpw | 05-Sep-19 | 04-Feb-21 | 12-Aug-19 | 01-Oct-19 | 04-Nov-19 |  |  |  | 0
453409 | 453409 (WO 318596) Holiday Inn Hotel. ERIC T SMITH WAY | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Martin, Shane | 27-Dec-18 |  |  | 74600.18 | 69377.42 | 74600.18 | 74600.18 | Steve Rumble | Somervl | 07-Mar-19 | 17-Aug-20 | 25-Feb-19 | 29-Jul-19 | 03-Oct-19 |  | Customer |  | 0
452547 | 452547 - INSPECT/CONNE/I&C MODERN MANORS | 815 - Addiscott | 101887 | Active | HO | RELEASED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 09-Aug-22 |  |  | 151245.3 | 37302.01 | 151245.3 | 151245.3 | Dave Lindsay | Transpw | 26-Oct-22 | 09-Aug-23 | 27-Sep-22 |  |  | Customer | Customer |  | 0
453634 | 453634 - CORNELL ROUGE PH9 | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 17-Mar-21 |  |  | 121109.4 | 110400.86 | 121109.4 | 121109.4 | Dave Lindsay | Transpw | 14-May-21 | 26-Jul-23 | 28-Apr-21 | 19-Mar-21 | 27-Apr-21 |  |  |  | 0
453474 | PARENT W.O. FOR UNPLANNED/18-115 ROGERS JU APPLICATION | 815 - Addiscott | 151495 | Inactive | 99 | CANCELLED |  |  | 2023 | O'Gay, Brian | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 19-Jul-23
453943 | (WO319304) 130 Old Kennedy Road | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 4938.27 |  | 0 | Persaud, Ryan |  |  | 14-Mar-23
453797 | 453797 - SC13413 – PMH-9 change out to PVI-9 switch gear – 101 Marsellus – Barrie | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 28-Jan-19 |  |  | 28894 | 149208.15 | 28894 | 28894 | Jeremy Wright |  | 02-Dec-19 | 22-Sep-22 | 27-Sep-19 | 24-Nov-19 | 26-Nov-19 |  |  |  | 0
633889 | 633889 - 2021 DISTRIBUTION AUTOMATION - EAST - BRADFORD - LT-B1055 - 2620 8TH LINE, 1 | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Bowman, Todd J | Walters, Geoffrey D | 09-Dec-20 |  |  | 218547.68 | 186922.13 | 218547.68 | 218547.68 | Dan Kish | K-Line | 17-Feb-21 | 15-Nov-21 | 18-Jan-21 | 17-May-21 | 28-May-21 | Filler | Filler |  | 0
453215 | (WO 318194) Pine Valley pole relocations, Vaughan | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Battistella, Alexander | 21-Jan-19 |  |  | 130566 | 45512.88 | 130566 | 130566 | Macdonald, Steve | K-Line | 30-Apr-19 | 24-Oct-21 | 19-Feb-19 | 11-Mar-19 | 02-May-19 |  |  |  | 0
632723 | 632723 - 98 AUTO VAUGHAN DR (Car Dealership) | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Low | Comm | 2021 | Dibratto, Susan | Mann, Drew | 28-Jan-20 |  |  | 50946.53 | 39875.07 | 50588.53 | 50946.53 | Dave Lindsay | Somervl | 09-Apr-20 | 26-Feb-21 | 30-Mar-20 | 28-Sep-20 | 13-Jan-21 | Customer | Customer |  | 358
452814 | ( WO 316692) OH Relocation - HWY 427 AND STEELES AVE, VAUGHAN - OH Reloc due to HWY 427 | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2019 | Corriveau, Tom N | Zhang, Jiacheng | 02-Jan-19 |  |  | 0 | 0 |  | 0 | Macdonald, Steve |  | 25-Jul-19 | 15-Feb-21 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
453561 | (WO 318828) JU HE2018-145 Bell | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 | O'Gay, Brian | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 05-Nov-18
452637 | HONEY HILL SUBDIVISION - RES SUBD EDS | 825 - Patterson | 101887 | Active | HO | RELEASED |  |  | 2023 | Penner, Mitchell | Handy, James | 22-Dec-22 |  |  | 632740.19 | 164861.64 | 632740.19 | 632740.19 | Lotto, Jay | Transpw | 25-May-23 | 21-Aug-23 | 03-Apr-23 |  |  | Customer | Customer |  | 0
453796 | 453796 - VIA RENZO DR. #95 - BLDG. DC3 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Yuen, Paul | 22-Sep-21 |  |  | 328950 | 438387.3 | 328950 | 328950 | Dave Lindsay | Somervl | 17-Feb-22 | 17-Jul-23 | 20-Dec-21 | 13-Dec-21 | 07-Oct-22 |  | Customer |  | 0
453214 | 453214 - INSPECT/CONNE/OAK KNOLLSUBDIVISION PHASE 4 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 06-Nov-20 |  |  | 167379.41 | 178857.04 | 167379.41 | 167379.41 | Dave Lindsay | Transpw | 06-Jan-21 | 10-May-21 | 18-Dec-20 | 11-Nov-20 | 13-Jan-21 |  | Customer |  | 0
452546 | (WO 314306) 8600 Woodbine Ave N. of Hwy 7 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 01-Nov-17 |  |  | 0 | 112314.13 |  | 0 | Steve Rumble | Transpw | 25-Jul-19 | 10-Aug-20 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
453471 | (WO 318701) Replace 44TV070 & 44TV047 | 815 - Addiscott | 101027 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 06-Dec-18 |  | 2 | 44641 | 23802 | 44641 | 44641 | Lamb, Tim |  | 30-Aug-19 | 20-Jul-20 | 13-Feb-19 | 24-Jul-19 | 24-Jul-19 |  | Filler |  | 0
452812 | (WO 316688) Fire Station No. 7 - 4 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Yuen, Paul | 16-Oct-18 |  |  | 66336.09 | 65857.24 | 66336.09 | 66336.09 | Steve Rumble | Somervl | 30-Nov-18 | 10-Mar-20 | 15-Nov-18 | 05-Jul-19 | 16-Aug-19 |  | Customer |  | 0
454229 | (WO319629) 800 Tesma Way | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Paterson, Greg | 24-Jul-19 |  |  | 8326.44 | 7547.23 | 8326.44 | 8326.44 | Steve Rumble | N/A | 23-Sep-19 | 24-Feb-20 | 23-Aug-19 | 24-Aug-19 | 10-Oct-19 | Customer | Customer |  | 0
453557 | 453557 (WO 318824) Replace Pole P33876 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-May-19 |  |  | 58870 | 76248.91 | 58870 | 58870 | Morrow, Joe | Transpw | 28-Jun-19 | 24-Feb-20 | 07-Jun-19 | 09-Nov-19 | 12-Nov-19 |  |  |  | 0
631941 | (WO631941) 256 OLD YONGE ST | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 23-Jul-19
454080 | (WO 319469) Pole/Grading Issues Extra Cost LESLIE - ELGIN TO 19TH | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Apr-19
453633 | TRANSFORMER AND SECONDARY DUCT BANK INSTALLATION FOR CATHEDRAL TOWN SUB. PH I | 815 - Addiscott | 151531 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 27-Feb-19
452636 | 452636 - AUTUMNHILL DEVELOPMENTS | 815 - Addiscott | 101887 | Active | 82 | H8 |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 14-Jun-21 |  |  | 22682.56 | 23892.11 | 22682.56 | 22682.56 | Dave Lindsay |  | 06-Aug-21 | 28-Jul-23 | 04-Aug-21 |  |  | Customer | Customer |  | 0
454228 | (WO319628) 6251 13th Line | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 366.52 |  | 0 | Persaud, Ryan |  |  | 13-Jul-22
632698 | (WO632698) 80 DONEY CRESCENT | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 03-Feb-22
452929 | 452929 - AURORA GLEN SHIMVEST SUBD - BLK 161 SCRIVNER DRIVE | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 08-Dec-20 |  |  | 5506.49 | 108500.41 | 5506.49 | 5506.49 | Dave Lindsay |  | 26-Jan-21 | 10-Jun-21 | 21-Jan-21 | 10-Dec-20 | 13-Jan-21 |  |  |  | 0
453213 | 453213 (WO 318191) REPLACEMENT OF POLE P40762 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 08-Mar-19 |  |  | 42095 | 73300.57 | 42095 | 42095 | Morrow, Joe |  | 11-Oct-19 | 14-Dec-20 | 27-Sep-19 | 04-Nov-19 | 05-Nov-19 |  |  |  | 0
453792 | (WO 319111) OH, Tap Removals for Warden Ave Express Feeders, Hwy 7 east of Rodick Rd | 815 - Addiscott | 100229 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 22-Jan-19 |  |  | 10068 | 16363.95 | 10068 | 10068 | Shortt, Derek B. |  | 30-May-19 | 22-Oct-20 | 20-Mar-19 | 07-Jul-19 | 18-Jul-19 |  |  |  | 0
453396 | (WO318556) 322 KING STREET | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Martin, Shane | 14-Nov-18 |  |  | 61208.17 | 42304.26 | 61208.17 | 61208.17 | Jeremy Wright | HapAmp | 10-Jan-19 | 19-Oct-20 | 20-Dec-18 | 17-Jun-19 | 17-Jul-19 |  | Customer |  | 0
631940 | 631940 - 31 KEYES COURT | 815 - Addiscott | PARENT WORK ORDER INDUST/COMM | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Mann, Drew | 15-Aug-19 |  |  | 61552.77 | 55051.21 | 61552.77 | 61552.77 | Steve Rumble | Somervl | 15-Nov-19 | 01-Jun-20 | 04-Nov-19 | 02-Oct-19 | 17-Dec-19 |  | Customer |  | 0
453631 | 453631 (WO 318931) HIGHWAY NO. 50 - #7171 AT GIBRALTAR RD. | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 31-Jan-19 |  |  | 82372.4 | 71827.92 | 82372.4 | 82372.4 | Steve Rumble | Somervl | 09-May-19 | 24-Feb-20 | 18-Apr-19 | 15-Oct-19 | 03-Dec-19 | Customer | Customer |  | 0
453470 | (WO318700) SW - REPL BATCH 2019 - 10 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 11-Nov-18 |  | 1 | 89063.05 | 67911.13 | 233853 | 89063.05 | Lamb, Tim | Somervl | 30-Oct-19 | 24-Feb-20 | 20-Sep-19 | 10-Sep-19 | 10-Oct-19 |  |  |  | -144,789.95
452545 | (WO 314304) 568 RIVERLANDS AVENUE | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 24-Jul-18 |  |  | 56880.47 | 58451.98 | 56880.47 | 56880.47 | Steve Rumble | Transpw | 01-Mar-19 | 13-Jan-20 | 07-Feb-19 | 17-Sep-18 | 03-Jul-19 |  |  |  | 0
453049 | (WO317673) Deergate Holdings Inc. | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
452923 | 452923 - NEW RESIDENTIAL SUBDIVISION - VILLAGE GATE BROWNSTONES | 815 - Addiscott | 101887 | Active | 91 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 25-Apr-22 |  |  | 79896.17 | 97322.82 | 79896.17 | 79896.17 | Dave Lindsay |  | 21-Jul-22 | 16-Aug-23 | 07-Jun-22 | 06-Jun-22 |  |  | Customer |  | 0
452635 | 452635 - RAKI SOUTH - STAGE 1 (PHASE 1) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 82 | H8 |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 14-Jun-21 |  |  | 61143.3 | 44996.23 | 61143.3 | 61143.3 | Dave Lindsay |  | 06-Aug-21 | 08-Aug-23 | 04-Aug-21 |  |  | Customer | Customer |  | 0
454076 | FIFTH AVENUE HOMES, KING WEST – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P | 19-Apr-23 |  |  | 177744.01 | 27538.85 | 177744.01 | 177744.01 | Con-Elco Limited |  | 04-May-23 | 02-Aug-23 | 06-Feb-23 | 01-May-23 |  | Contractor |  |  | 0
453048 | (WO317660) Highway 89 and 10th SdRd, Pole Relocations | 825 - Patterson | 101763 | Active | 98 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Harrington, James | 12-Apr-19 |  |  | 28969 | 37180.26 | 28969 | 28969 | Jeremy Wright |  | 30-Apr-19 | 26-Jul-23 | 23-Apr-19 | 29-Apr-19 | 10-May-19 | Customer | Customer |  | 0
453212 | 453212 (WO 318189) Hydro Relocation - HWY 427 EXTN, MAJOR MACK DR, Wes of HUNTINGTON RD, VAUGHAN - | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 29-Apr-19 |  |  | 57507 | 33078.41 | 57507 | 57507 | Macdonald, Steve |  | 07-Jun-21 | 22-Sep-22 | 07-Jun-21 | 07-Jun-21 | 07-Jun-21 |  |  |  | 0
631939 | 631939 - 9700 9TH LINE MARKHAM | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Diefenbaker, Trevor A | 18-May-21 |  |  | 124821.53 | 66991.88 | 124821.53 | 124821.53 | Dave Lindsay | Somervl | 06-Aug-21 | 31-Aug-22 | 02-Jul-21 | 17-Nov-21 | 11-Feb-22 | Customer | Customer |  | 0
454226 | YRRTC-Y2.2-SEC. SERV. RELOC./YRRTC-Y2.2-UG SEC. SERV. RELOC | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Lacombe, Joel | 15-Aug-19 |  |  | 80062.08 | 237238.38 | 80062.08 | 80062.08 | Steve Rumble | Transpw | 29-Aug-19 | 09-Aug-22 | 21-Aug-19 | 01-Aug-19 | 09-Oct-19 |  | Lines |  | 0
453394 | (WO318550) 277 Cityview Blvd | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 02-Jan-19 |  |  | 146245.68 | 140685.16 | 146245.68 | 146245.68 | Steve Rumble | Somervl | 30-Jul-19 | 01-Aug-21 | 15-Jul-19 | 03-May-19 | 30-Aug-19 |  |  |  | 0
452809 | 452809 - 35 Reid Drive - Warehouse | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 17-Nov-20 |  |  | 54555.75 | 43366.87 | 54555.75 | 54555.75 | Lotto, Jay | HapAmp | 21-Jan-21 | 21-Jun-21 | 28-Dec-20 | 22-Oct-20 | 26-Jan-21 |  | Customer |  | 0
452543 | ( WO 314095) BLOOMINGTON GO STATION | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 01-Nov-17 |  |  | 287532.42 | 463287.61 | 287532.42 | 287532.42 | Steve Rumble | Transpw | 22-Jan-19 | 21-Jun-21 | 17-Jan-19 | 21-May-18 | 13-May-19 |  |  |  | 0
453550 | (WO 318815) YRRTC - H2-West - Phase 5.3 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Zhang, Jiacheng | 28-Jan-19 |  |  | 230922 | 304464.08 | 230922 | 230922 | Macdonald, Steve | K-Line | 30-May-19 | 04-Feb-21 | 05-Mar-19 | 20-Feb-19 | 02-May-19 |  |  |  | 0
453469 | (WO318699) SW - REPL BATCH 2019 - 9 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 28-Nov-18 |  | 2 | 136361.88 | 67347.55 | 201134 | 136361.88 | Steve Rumble | Somervl | 30-Jul-19 | 24-Feb-20 | 25-Mar-19 | 04-Jun-19 | 05-Jul-19 |  | Filler |  | -64,772.12
452634 | 452634 - RICHVIEW 19 DEVELOPMENTS | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 14-Jun-21 |  |  | 90143.34 | 60289.53 | 76338.07 | 90143.34 | Dave Lindsay |  | 02-Sep-21 | 15-Aug-23 | 04-Aug-21 | 07-Mar-22 |  | Customer | Customer |  | 13,805.27
453764 | 453764 - BRYNE DRIVE - BARRIE -ROAD WIDENING/RELOCATE | 825 - Patterson | 101764 | Active | 92 | COMPLETE |  |  | 2023 | Lacombe, Joel | Murray, Jake R | 19-May-22 |  |  | 472790.11 | 424934.04 | 472790.11 | 472790.11 | Mark Timbers | HapAmp | 10-Nov-22 | 26-Jul-23 | 12-Sep-22 | 15-Feb-23 | 19-May-23 | Design | Design |  | 0
453046 | 453046 - LEE AVENUE SUBDIVISION | 815 - Addiscott | 101887 | Active | 82 | H8 |  |  | 2023 | Penner, Mitchell | D'Onofrio, Tony | 14-May-21 |  |  | 171164.16 | 13026.8 | 171164.16 | 171164.16 | Dave Lindsay | Transpw | 30-Jul-21 | 14-Aug-23 | 29-Jun-21 |  |  | Customer | Customer |  | 0
452808 | 452808 - LAKEVIEW TOWNHOMES BARRIE - SUBD RES EDS | 825 - Patterson | 101887 | Active | HO | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan | 09-Nov-21 |  |  | 41839.05 | 22693.85 | 41839.05 | 41839.05 | Lotto, Jay | HapAmp | 24-Jan-22 | 09-Aug-23 | 21-Dec-21 |  |  | Customer | Customer |  | 0
454108 | 2020 REAR LOT / BLAKE - KEMPENFLET AREA | 825 - Patterson | 150044 | Active | HL | H2 |  |  | 2023 | Obeng, Nana | Pollock, Kim | 10-Jan-20 |  |  | 620447.19 | 34685.12 | 620447.19 | 620447.19 | Persaud, Ryan |  |  | 27-Jul-23 | [6 empty] | 0
453937 | 453937 (WO 319298 ) Stouffville to 404 Pole Line Extension | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 08-Oct-19 |  |  | 153760.07 | 127797.51 | 153760.07 | 153760.07 | Morrow, Joe | Transpw | 03-Dec-19 | 13-Apr-23 | 07-Nov-19 | 04-Nov-19 | 29-Nov-19 |  |  |  | 0
452541 | (WO314058) Richmond Towns - 219/227 Major Mack. | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 5752.2 |  | 0 | Persaud, Ryan |  |  | 08-Mar-23
453626 | 453626 - MAPLEVIEW DR. POLE RELOCATIONS/RELOCATE FOR RD WIDENING | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2021 | Pelleja, Emily | Battistella, Alexander | 19-Mar-21 |  |  | 659610.37 | 439600.87 | 659610.37 | 659610.37 | Jeremy Wright |  | 16-Aug-21 | 09-Jun-22 | 30-Apr-21 | 31-May-21 | 09-Aug-21 | Lines |  |  | 0
454073 | 454073 (WO 319460) Primont Cornell 2 Detached | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Alarcon, Alejandro | 01-Nov-19 |  |  | 43087.15 | 37704.35 | 43087.15 | 43087.15 | Dave Lindsay |  | 10-Dec-19 | 31-Mar-22 | 09-Dec-19 | 25-Nov-21 | 25-Nov-21 | Customer | Customer |  | 0
453549 | 453549 - UPSIDE TOWNS, GEORGE KIRBY | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | D'Onofrio, Tony | 19-Jan-21 |  |  | 282796.93 | 318665.36 | 282796.93 | 282796.93 | Dave Lindsay |  | 22-Mar-21 | 11-Jan-22 | 01-Mar-21 | 08-Feb-21 | 22-Mar-21 |  |  |  | 0
631918 | 631918 - 2019 PCB TRANSFORMER REPLACEMENT/ REPLACE M49TP105 | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 30-Aug-19 |  |  | 23345.92 | 9152.31 | 23345.92 | 23345.92 | Lamb, Tim | Somervl | 04-Nov-19 | 03-May-21 | 28-Oct-19 | 21-Oct-19 | 20-Nov-19 |  |  |  | 0
453468 | (WO318698) SWGR Repl 2019 - Batch 8 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 26-Feb-19 |  | 3 | 299003 | 188733.46 | 299003 | 299003 | Steve Rumble | Somervl | 30-Oct-19 | 24-Feb-20 | 24-Jun-19 | 19-Sep-19 | 09-Oct-19 |  | Filler |  | 0
453763 | 453763 (WO 319081) Bell - HE2018-157 | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2022 |  | Martin, Shane |  |  |  | 0 | 93.54 |  | 0 | Wong, Henry |  |  | 26-Jul-23
452532 | ( WO 313699) TOWN HOME BLOCK (16TH & MARKHAM RD) | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Active | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Estrada, Michael | 01-Nov-17 |  |  | 0 | 88420.11 | 79945.06 | 79945.06 | Cory Ruiter | Conelco | 25-Jul-19 | 26-Jul-23 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
452804 | OH TO UG CONVERSION, JANE ST (NORTH OF HWY 7-NORTH OF PORTAGE PARKWAY), VAUGHAN | 815 - Addiscott | 151632 | Active | 10 | H8 |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 59619.98 | 25000 | 25000 | Persaud, Ryan | Transpw |  | 27-Jun-23 | [6 empty] | 0
453936 | ROGERS PERMIT HE2019-004/ROGERS PERMIT HE2019-004 | 825 - Patterson | 151495 | Inactive | 99 | CANCELLED |  |  | 2023 | Decaire, Kevin | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 15-May-23
454072 | 454072 (WO 319459) FRED GRANT SQUARE TX UPGRADE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 18-Jul-19 |  |  | 36511.91 | 30209.43 | 36511.91 | 36511.91 | Jeremy Wright |  | 28-Oct-19 | 29-Dec-21 | 27-Sep-19 | 17-Nov-19 | 17-Nov-19 |  |  |  | 0
452920 | 452920 - INSPECT/CONNE/I&C 1335 ELGIN MILLS ROAD EAST | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Alarcon, Alejandro | 24-Sep-20 |  |  | 78402.68 | 72705.87 | 78402.68 | 78402.68 | Dave Lindsay | Transpw | 13-Jan-21 | 10-Jun-21 | 02-Nov-20 | 02-Nov-20 | 13-Jan-21 | xBy-passed | xBy-passed |  | 0
631917 | 631917 - 2019 PCB TRANSFORMER REPLACEMENT/ REPLACE 1-186 | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 30-Aug-19 |  |  | 24814.14 | 7815.12 | 24814.14 | 24814.14 | Lamb, Tim | Somervl | 04-Nov-19 | 26-Apr-21 | 28-Oct-19 | 27-Sep-19 | 11-Dec-19 |  |  |  | 0
453044 | (WO317650) 136 BARRIE ST, BRADFORD - LOFT | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 01-Nov-18 |  |  | 54791.76 | 48612.03 | 54791.76 | 54791.76 | Jeremy Wright | HapAmp | 13-Dec-18 | 17-Aug-20 | 21-Nov-18 | 04-Dec-18 | 03-Jun-19 |  | Customer |  | 0
453625 | (WO318923) 1443 DENISON AVENUE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Stephens, Barry N. | Dibratto, Susan | 29-Mar-19 |  |  | 74130.68 | 47679.81 | 74130.68 | 74130.68 | Steve Rumble | Somervl | 31-May-19 | 27-Jul-20 | 16-May-19 | 01-May-19 | 10-Oct-19 |  | Customer |  | 0
453206 | PARENT W.O. FOR INSPECT/CONNE/COUNTRY WIDE HOMES (TESTON RD) | 815 - Addiscott | 101887 | Active | 40 | H8 |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 27-Feb-19
452633 | RESIDENTIAL SUBDIVISION - CENTERFIELD DEVELOPMENT P2 | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
453386 | 453386 - PARKGATE HOLDINGS DEVELOPMENT | 815 - Addiscott | 101887 | Active | 82 | H8 |  |  | 2023 | Penner, Mitchell | D'Onofrio, Tony | 10-May-21 |  |  | 61943.6 | 38495.77 | 61943.6 | 61943.6 | Dave Lindsay |  | 06-Jul-21 | 31-Jul-23 | 24-Jun-21 |  |  | Customer | Customer |  | 0
453466 | (WO318696) SWGR Repl 2019 - Batch 4 | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 03-Dec-18 |  | 2 | 157826.69 | 51331.28 | 227374 | 157826.69 | Shane Christopher | Somervl | 25-Jun-19 | 26-Jul-23 | 03-Jun-19 | 08-May-19 | 08-May-19 |  |  |  | -69,547.31
453547 | (WO318809) MAKE READY SUB'D 107 HALL ST | 815 - Addiscott | 151531 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Feb-23
453624 | (WO318921) 558 HOLLAND STREET WEST | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 17119.44 |  | 0 | Persaud, Ryan |  |  | 13-Jul-22
454204 | 454204 (WO 454204) Tenth Line Pole Relocation | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 03-Oct-19 |  |  | 43402.7 | 27837.48 | 43402.7 | 43402.7 | Morrow, Joe |  | 21-Nov-19 | 19-Nov-21 | 07-Nov-19 | 18-Nov-19 | 18-Nov-19 |  |  |  | 0
631916 | 631916 - 2019 PCB TRANSFORMER REPLACEMENT/ REPLACE 26-24 | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 30-Aug-19 |  |  | 24814.14 | 8504.95 | 24814.14 | 24814.14 | Lamb, Tim | Somervl | 04-Nov-19 | 03-May-21 | 28-Oct-19 | 27-Sep-19 | 26-Nov-19 |  |  |  | 0
452918 | ( WO 317140) V17SL3013 - Dufferin St s-o Rutherford | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 04-Dec-18 |  | 1 | 75556 | 73853.59 | 75556 | 75556 | Macdonald, Steve | K-Line | 30-May-19 | 18-Mar-21 | 04-Mar-19 | 23-Jul-19 | 10-Sep-19 |  |  |  | 0
452632 | RESIDENTIAL SUBDIVISION - LONG BODY DEVELOPMENT | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
453622 | 453622 - DYKIE SUBDIVISION - SUBD RES EDS | 825 - Patterson | 101887 | Active | 98 | COMPLETE |  |  | 2021 | Penner, Mitchell | Perks, Dan | 23-Apr-21 |  |  | 84256.53 | 74983.08 | 84256.53 | 84256.53 | Lotto, Jay | Transpw | 25-Jun-21 | 26-Jul-23 | 08-Jun-21 | 05-Jul-21 | 13-Jul-21 | Customer | Customer |  | 0
452528 | 452528 (WO 313534) St. John's Sideroad- Bayview Ave To Hwy 404 | 815 - Addiscott | 101762 | Active | 99 | COMPLETE | High | Infrast | 2021 | Corriveau, Tom N | Barry, Kenneth | 11-Sep-20 |  |  | 1092760.45 | 1194078.91 | 1092760.45 | 1092760.45 | Macdonald, Steve | K-Line | 30-Dec-20 | 26-Jul-23 | 19-Oct-20 | 15-Oct-20 | 08-Mar-21 |  | COVID19 |  | 0
453728 | 453728 (WO 319045) Ballantry Cornell Phase 8 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 211454.96 |  | 0 | Dave Lindsay |  | 30-Dec-21 | 20-Mar-23 | 30-Dec-21 | 30-Dec-21 | 30-Dec-21
453202 | 453202 (WO 318166) Incon Property Holdings (Maple Grove) Ltd. | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Alarcon, Alejandro | 10-Jan-20 |  |  | 30067.72 | 147742.56 | 30067.72 | 30067.72 | Dave Lindsay |  | 12-Mar-20 | 15-Aug-22 | 04-Mar-20 | 29-Feb-20 | 21-Jul-21 |  | COVID19 |  | 0
452917 | ( WO 317139) V17SL3010 - Rutherford w-o Dufferin | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 04-Dec-18 |  | 1 | 78609 | 67181.77 | 78609 | 78609 | Macdonald, Steve | K-Line | 30-May-19 | 15-Mar-21 | 06-Mar-19 | 30-Aug-19 | 10-Sep-19 |  |  |  | 0
453382 | 453382 (WO 318529) V01 Clark and Yonge (York Hill Phase 4) | 815 - Addiscott | 151114 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 30-Sep-19 |  |  | 1446934.74 | 1798733.59 | 1867871.74 | 1446934.46 | Lamb, Tim | Transpw | 13-Dec-19 | 28-Jan-21 | 15-Oct-19 | 04-Oct-19 | 12-Dec-19 |  |  |  | -420,937.28
454196 | 454196 (WO 319593) - 131 Big Bay Point Road, Barrie | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 13-Nov-19 |  |  | 59797.68 | 49555.48 | 59797.68 | 59797.68 | Lotto, Jay | HapAmp | 03-Dec-19 | 19-Oct-20 | 25-Nov-19 | 16-Dec-19 | 24-Dec-19 |  | Customer |  | 0
454067 | (WO319454) CLARK AVE AND SOUTH PROMENADE | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alarcon, Alejandro | 19-Jun-19 |  |  | 44081 | 32959.69 | 44081 | 44081 | Lamb, Tim | Transpw | 08-Aug-19 | 28-Oct-20 | 24-Jul-19 | 30-Jul-19 | 01-Aug-19 |  | Contractor |  | 0
453037 | (WO317591) 150 Gibraltar | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Stephens, Barry N. | Dibratto, Susan | 11-Sep-18 |  |  | 157367.38 | 148863.35 | 157367.38 | 157367.38 | Steve Rumble | Transpw | 25-Oct-18 | 24-Aug-20 | 12-Oct-18 | 01-Feb-19 | 26-Mar-19 | Customer | Customer |  | 0
453546 | (WO318800) Left-Behind Cable Segments. V15 GLEN SHIELDS AV | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 26-Jun-19 |  |  | 350825 | 249482 | 350825 | 350825 | Lamb, Tim | Transpw | 19-Sep-19 | 23-Jul-20 | 26-Aug-19 | 03-Oct-19 | 21-Oct-19 |  |  |  | 0
453465 | (WO318695) SWGR Repl 2019 - Batch 2 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 03-Dec-18 |  | 3 | 135441 | 79737.03 | 135441 | 135441 | Steve Rumble | Somervl | 28-Jun-19 | 13-Jan-20 | 25-Mar-19 | 11-Apr-19 | 30-Apr-19 |  | Filler |  | 0
317235 | ( WO 317235) REPLACE A05SP2011 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Gonzales, Leonard | 16-Jul-18 |  |  | 23641.25 | 8238.66 | 23641.25 | 23641.25 | Lamb, Tim |  | 30-Oct-18 | 01-Apr-19 | 30-Jul-18 | 06-Dec-18 | 23-Jan-19 |  | Filler |  | 0
453201 | PRIMONT HOMES EDS | 815 - Addiscott | 101887 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Kinsella, William P | 24-Apr-23 |  |  | 799651.46 | 113784.28 | 799651.46 | 799651.46 | Dave Lindsay | Transpw | 13-Jun-23 | 03-Aug-23 | 05-Jun-23 | [5 empty] | 0
453620 | 453620 (WO 318914) Metrolinx Electrical ETR 407 - BIRCHMOUNT RD TO KENNEDY RD | 815 - Addiscott | 150592 | Active | 84 | H8 | High | MLinx | 2023 | Khuu, Philander | Grahovac, John | 30-Jan-20 |  |  | 2837066.97 | 3399790.61 | 2837066.97 | 2837066.97 | Shane Christopher | Transpw | 03-Jul-20 | 26-Jul-23 | 11-May-20 | 26-Jun-20 |  | Customer | Customer |  | 0
631659 | 631659 - 155 REGALCREST COURT | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 18-Sep-19 |  |  | 15079.71 | 4460.81 | 15079.71 | 15079.71 | Dave Lindsay |  | 07-Jan-22 | 02-Aug-23 | 24-Dec-21 |  |  | Customer | Customer |  | 0
452521 | 452521 - UG RELOCATION/GLEN SHIELDS AVE BRIDGE, VAUGH | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Zhang, Jiacheng | 13-Oct-20 |  |  | 520225.58 | 508041.98 | 520225.58 | 520225.58 | Horlings, Jake | Transpw | 21-Dec-20 | 22-Sep-22 | 07-Dec-20 | 19-Apr-21 | 23-Jun-21 | Materials | Materials |  | 0
454012 | (WO 319395) Replace P32953 - 80 Torbay Rd | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-May-22
633440 | 633440 - DISTRIBUTION AUTOMATION 2021 - A09SL2015 - AURORA, 1 | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 11-Nov-20 |  |  | 144879.57 | 162892.83 | 121118.97 | 144879.57 | Macdonald, Steve | K-Line | 30-Aug-21 | 12-Apr-22 | 23-Aug-21 | 02-Aug-21 | 17-Sep-21 |  | MC/PUCC Permit |  | 23,760.60
453933 | 453933 - LESLIE ELGIN - BLOCK 52 SUBDIVISION | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | D'Onofrio, Tony | 12-Mar-21 |  |  | 278855.17 | 262978.7 | 278855.17 | 278855.17 | Dave Lindsay | Transpw | 19-May-21 | 07-Feb-22 | 28-Apr-21 | 31-May-21 | 11-Nov-21 | Customer | Customer |  | 0
453034 | 453034 (WO 317586) Pine Valley Enclave II Dev | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Graham, Bruce W. | 07-Sep-20 |  |  | 185360.82 | 178350.68 | 185360.82 | 185360.82 | Dave Lindsay | Transpw | 20-Nov-20 | 14-Jun-21 | 26-Oct-20 | 26-Oct-20 | 17-Feb-21 |  | Customer |  | 0
452916 | (WO 317135) A10SL2010 - Bayview n-o Wellington | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Tempra, Troylan | 19-Dec-17 |  | 1 | 90565 | 65974.48 | 90565 | 90565 | Macdonald, Steve | K-Line | 30-May-18 | 15-Mar-21 | 27-Feb-18 | 03-Jun-19 | 05-Jun-19 |  |  |  | 0
453718 | 453718 (WO 319035) Pole Betterment. Alliston. BATCH 1 (21 Poles) | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Pollock, Kim | 14-Mar-19 |  |  | 258164.64 | 243301.9 | 238847 | 258164.64 | Jeremy Wright |  | 15-Oct-19 | 18-Feb-21 | 01-May-19 | 11-Apr-19 | 27-Sep-19 |  | Filler |  | 19,317.64
633136 | (WO 633136) DISTRIBUTION AUTOMATION 2020 - 27S15 - RICHMOND HILL | 815 - Addiscott | 100886 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Roy, James |  |  |  | 120170.1 | 16558.39 | 120170.1 | 120170.1 | Persaud, Ryan |  |  | 13-Oct-20 | [6 empty] | 0
453381 | 453381 (WO 318527) 95 ERIC T SMITH WAY - Flex Office Development | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Martin, Shane | 21-Nov-18 |  |  | 44555.2 | 40182.01 | 44555.2 | 44555.2 | Steve Rumble | Somervl | 15-Jan-19 | 13-Oct-20 | 07-Jan-19 | 22-Aug-19 | 27-Nov-19 | Customer | Customer |  | 0
453464 | 453464 (WO 318694) Repl. Switchgear - Batch 7 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 27-Nov-18 |  | 3 | 207741 | 146728.79 | 207741 | 207741 | Lamb, Tim | Somervl | 30-Oct-19 | 24-Feb-20 | 01-Apr-19 | 26-Jul-19 | 04-Oct-19 |  |  |  | 0
453929 | (WO319288) ISLINGTON AVE. - #9230 | 815 - Addiscott |  | Active | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Yuen, Paul | 01-May-19 |  |  | 68987.94 | 54547.56 | 68987.94 | 68987.94 | Shane Christopher | Somervl | 08-Jul-19 | 26-Jul-23 | 17-Jun-19 | 28-May-19 | 16-Jul-19 |  |  |  | 0
453200 | PARENT W.O. FOR INSPECT/CONNE/I & C BAYVIEW CREEK - RICHMOND | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 8849.56 |  | 0 | Persaud, Ryan |  |  | 23-May-23
453534 | 453534 (WO 318786) Relocate Pole for Culvert. INNISFIL STREET N/O TIFFIN STREET, BARRIE | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Harrington, James | 24-May-19 |  |  | 108545 | 102750.95 | 108545 | 108545 | Dan Kish | HapAmp | 25-Jul-19 | 13-Sep-22 | 08-Jul-19 | 02-Jul-19 | 13-Aug-19 |  |  |  | 0
452798 | (WO316615) New Commercial Property | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 1217.94 |  | 0 | Persaud, Ryan |  |  | 13-Jul-22
454010 | (WO 319393) Replace P33141 - 295 Steelcase Rd E | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-May-22
452915 | 452915 (WO 317132) V36SP1006 - 17 Vinyl Crt | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 03-Dec-18 |  | 1 | 239613 | 140704.31 | 239613 | 239613 | Steve Rumble | Transpw | 01-Oct-19 | 25-Jan-21 | 12-Aug-19 | 30-Sep-19 | 25-Nov-19 |  |  |  | 0
453712 | 453712 (WO 319028) 200 Cachet Woods Crt | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 10-Jul-19 |  |  | 54093.54 | 54315.38 | 54093.54 | 54093.54 | Steve Rumble | Somervl | 25-Oct-19 | 04-Aug-20 | 15-Oct-19 | 11-Oct-19 | 04-Dec-19 |  | Customer |  | 0
454026 | 454026 (WO 319413) M43 Steelcase and Idema - Convert 43T-024 | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 18-Jun-19 |  |  | 105161 | 107495.22 | 105161 | 105161 | Cory Ruiter | Transpw | 31-Oct-19 | 04-May-20 | 21-Oct-19 | 05-Sep-19 | 15-Nov-19 |  | Contractor |  | 0
452520 | 452520 (WO 313379) Highway No. 7 East - #3972 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 15-Oct-18 |  |  | 78437.46 | 17121.1 | 78437.46 | 78437.46 | Steve Rumble | Transpw | 26-Nov-18 | 24-Feb-20 | 13-Nov-18 | 22-Jun-19 | 08-Oct-19 |  | Customer |  | 0
453033 | PARENT W.O. FOR INSPECT/CONNE/I&C - MAPLEQUEST VAUGHAN DEV. | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
633134 | 633134 - DISTRIBUTION AUTOMATION 2021 - A06SL2024 - AURORA, 1 | 815 - Addiscott | 100886 | Active | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 04-Nov-20 |  |  | 136087.26 | 169052.8 | 108488.54 | 136087.26 | Macdonald, Steve | K-Line | 20-Aug-21 | 26-Jul-23 | 13-Aug-21 | 18-Sep-21 | 01-Oct-21 | MC/PUCC Permit | MC/PUCC Permit |  | 27,598.72
454009 | EMERGING POLE REPLACEMENT/6735 5TH LINE | 825 - Patterson | 100867 | Active | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim |  |  |  | 96871.01 | 83004.91 | 96871.01 | 96871.01 | Persaud, Ryan |  |  | 26-Jul-23 | [6 empty] | 0
453533 | (WO318785) 25 ALBERT STREET WEST, ALLISTON | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 273.59 |  | 0 | Jeremy Wright |  |  | 13-Jul-22
452628 | 452628 (WO 315584) Mackenzie Creek Condo Dev | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 18-Jun-18 |  |  | 0 | 654206.89 |  | 0 | Dave Lindsay | Transpw | 28-Nov-18 | 13-Jan-22 | 20-Nov-18 | 25-Nov-19 | 07-Dec-21 | Lines | Lines
453199 | (WO318157) 357 Yonge St, Barrie | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 21-Nov-18 |  |  | 75111.89 | 117567.51 | 75111.89 | 75111.89 | Jeremy Wright | HapAmp | 15-Jan-19 | 12-Oct-20 | 21-Dec-18 | 29-Mar-19 | 10-May-19 | Customer | Customer |  | 0
315355 | (WO 315355) HW 50 - CASTLEMORE TO MAYFIELD | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Lacombe, Joel |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  | 25-Jul-19 | 29-Jun-20 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
454025 | 454025 (WO 319412) 8550 Keele St | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Paterson, Greg | 24-Jul-19 |  |  | 82347.93 | 63606.56 | 82347.93 | 82347.93 | Steve Rumble | Somervl | 08-Oct-19 | 04-May-20 | 23-Sep-19 | 04-Nov-19 | 11-Nov-19 | Customer | Customer |  | 0
453031 | 453031 (WO 317577) 180 VIA RENZO @ ULTIMATE DR | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 25-Jan-19 |  |  | 82589.66 | 59711.15 | 82589.66 | 82589.66 | Steve Rumble | Somervl | 01-May-19 | 24-Feb-20 | 17-Apr-19 | 19-Sep-19 | 23-Sep-19 |  | Customer |  | 0
453711 | (WO319027) Soltan-Ahmadi Residence. BALDING BLVD. - #90 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 01-Apr-19 |  |  | 26844.89 | 34437.33 | 26844.89 | 26844.89 | Steve Rumble | Somervl | 14-Jun-19 | 24-Feb-20 | 06-Jun-19 | 25-Jul-19 | 07-Oct-19 |  | Customer |  | 0
452914 | 452914 (WO 317117) 70 Melbourne Drive | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Perks, Dan | 18-Apr-18 |  |  | 59299.3 | 364536.63 | 59299.3 | 59299.3 | Jeremy Wright | Transpw | 20-Aug-18 | 10-Feb-20 | 09-Jul-18 | 18-Jul-19 | 04-Nov-19 | Customer | Customer |  | 0
452797 | RESIDENTIAL SUBDIVISION - PRIMA VISTA ESTATES PH 3 | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 27-Feb-19
633132 | 633132 - DISTRIBUTION AUTOMATION 2021 - A06SL2042 - AURORA, 1 | 815 - Addiscott | 100886 | Active | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 04-Nov-20 |  |  | 161834.27 | 159753.67 | 144609.45 | 161834.27 | Macdonald, Steve | K-Line | 12-Aug-21 | 26-Jul-23 | 04-Aug-21 | 13-Sep-21 | 01-Oct-21 | MC/PUCC Permit | MC/PUCC Permit |  | 17,224.82
452796 | 452796 - PRIMA VISTA ESTATES PH 2 | 815 - Addiscott | 101887 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Estrada, Michael | 23-Mar-22 |  |  | 589000.93 | 48532.45 | 589000.93 | 589000.93 | Dave Lindsay |  | 10-Jun-22 | 26-Jul-23 | 05-May-22 | 17-May-22 | 18-Jul-22 | Customer | Customer |  | 0
453703 | (WO 319018) Grandview & Younge Anchor Relocation HE2019-022 | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Battistella, Alexander | 27-Mar-19 |  |  | 7517 | 3033.93 | 7517 | 7517 | Macdonald, Larry |  | 30-Oct-19 | 09-Aug-22 | 30-Jul-19 | 21-Aug-19 | 23-Aug-19 |  |  |  | 0
453461 | 453461 - SRF VAUGHAN SUBDIVSION | 815 - Addiscott | 101896 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 22-Oct-20 |  |  | 96491.39 | 98359.26 | 96491.39 | 96491.39 | Dave Lindsay | Transpw | 21-Dec-20 | 10-Nov-21 | 07-Dec-20 | 30-Nov-20 | 22-Mar-21 |  | Customer |  | 0
454022 | (WO319409) Connect Bell Bond. WESTON RD. S/O COLOSSUS DRIVE | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Cavanaugh, Danny | 06-May-19 |  |  | 731 | 0 | 731 | 731 | Don Rothman |  | 09-Oct-19 | 05-Oct-20 | 09-Oct-19 | 09-Oct-19 | 09-Oct-19 |  |  |  | 0
452626 | 452626 (WO 315551) 7089 Yonge Street | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 18-May-18 |  |  | 84546.88 | 94924.85 | 84546.88 | 84546.88 | Steve Rumble | Transpw | 11-Jul-19 | 29-Jun-20 | 04-Jul-19 | 05-Jul-19 | 20-Nov-19 | Customer | Customer |  | 0
633131 | 633131 - DISTRIBUTION AUTOMATION 2021 - A10SL2035 - AURORA, 1 | 815 - Addiscott | 100886 | Active | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 04-Nov-20 |  |  | 148066.27 | 170901.05 | 116757.7 | 148066.27 | Macdonald, Steve | K-Line | 03-Aug-21 | 26-Jul-23 | 26-Jul-21 | 19-Jul-21 | 19-Jul-21 |  |  |  | 31,308.57
453365 | (WO 318501) 520 WORTH BOULEVARD | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Battistella, Alexander | 16-Nov-18 |  |  | 43153 | 48697.53 | 42713 | 43153 | Lamb, Tim | Transpw | 09-Jul-19 | 22-Sep-22 | 01-Jul-19 | 05-Jun-19 | 17-Jun-19 |  |  |  | 440
453197 | (WO318155) Harbour Pointe - Penetanguishene | 825 - Patterson | 101763 | Inactive | 99 | CANCELLED |  |  | 2021 | O'Gay, Brian | Harrington, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 22-Sep-22 | 01-Jan-21
453702 | 453702 (WO 319017) HE2019-001 | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 11-Oct-19 |  |  | 4562.4 | 1420.92 | 4562.4 | 4562.4 | Don Rothman |  | 25-Nov-19 | 09-Aug-22 | 25-Nov-19 | 27-Nov-19 | 27-Nov-19 |  |  |  | 0
453027 | 453027 (WO 317549) Medical Growing. 7163 3RD LINE TOTTENHAM | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 04-Oct-19 |  |  | 40688.26 | 35941.31 | 40688.26 | 40688.26 | Jeremy Wright | HapAmp | 28-Oct-19 | 10-Jan-22 | 15-Oct-19 | 05-Nov-19 | 13-Nov-19 |  | Customer |  | 0
452795 | 452795 (WO 316607) Belterra Phase 6 | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 17-Sep-20 |  |  | 1179528.19 | 1169723.7 | 1179528.19 | 1179528.19 | Lotto, Jay | Transpw | 31-Mar-21 | 22-Nov-21 | 14-Dec-20 | 30-Oct-20 | 07-Oct-21 |  | Customer |  | 0
453612 | 453612 (WO 318906) Pole Repl 2019 - Batch 12 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 25-Jan-19 |  |  | 145896 | 171105.28 | 145896 | 145896 | Shortt, Derek B. |  | 31-Dec-19 | 22-Oct-20 | 11-Jul-19 | 05-Sep-19 | 03-Dec-19 |  |  |  | 0
315241 | (WO315241) New 3 Ph. Service | 825 - Patterson |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  | 25-Jul-19 | 09-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
453196 | 453196 - PRIMA VISTA PH4 | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 11-Nov-21 |  |  | 383354.35 | 360299.82 | 383354.35 | 383354.35 | Dave Lindsay |  | 11-Nov-21 | 26-Jul-23 | 11-Nov-21 | 11-Nov-21 | 11-Nov-21 |  |  |  | 0
453919 | 453919 - PRIMA VISTA PH 4 MUNICIPAL | 815 - Addiscott | 101887 | Active | 98 | COMPLETE |  |  | 2021 | Penner, Mitchell | Estrada, Michael | 18-May-21 |  |  | 62964.16 | 30892.54 | 62964.16 | 62964.16 | Dave Lindsay |  | 07-Jul-21 | 26-Jul-23 | 30-Jun-21 | 11-Nov-21 | 08-Dec-21 | Customer | Customer |  | 0
452901 | (WO 317039) - O/H - 16th Ave & McCowan Rd Pole installation | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Battistella, Alexander | 29-May-18 |  |  | 50753 | 186878.03 | 50753 | 50753 | Shortt, Derek B. |  | 20-Nov-18 | 26-Jul-23 | 25-Oct-18 | 08-Nov-18 | 24-Jan-19 |  | MC/PUCC Permit |  | 0
633130 | 633130 - DISTRIBUTION AUTOMATION 2020 - A10SL2026 - AURORA, 1 | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 04-Nov-20 |  |  | 130788.23 | 140571.45 | 100788.23 | 130788.23 | Macdonald, Larry |  | 23-Jun-21 | 10-Aug-22 | 14-Jun-21 | 28-Jun-21 | 09-Aug-21 | Filler | Filler |  | 30,000.00
453701 | 453701 - HIGHWAY NO. 7 - #6800 - HOTEL | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 04-Nov-20 |  |  | 51856.67 | 55268.38 | 51856.67 | 51856.67 | Dave Lindsay | Somervl | 19-Jan-21 | 14-Feb-22 | 17-Dec-20 | 03-Nov-20 | 11-Nov-21 |  | Customer |  | 0
452482 | 452482 (WO 312575) JANE ST. #9075 & #9085 AT RIVERROCK GATE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | High | Res-ICI | 2021 | Dibratto, Susan | Yuen, Paul | 12-Dec-19 |  |  | 371556.59 | 284602.69 | 371556.59 | 371556.59 | Dave Lindsay | Transpw | 10-Feb-20 | 01-Dec-21 | 27-Jan-20 | 22-Jan-20 | 08-Feb-21 |  | Customer |  | 0
453459 | (WO 318687) Cable repl. Emerging. M31. COTTSMORE CR AND HIGHGATE DR | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 10-Dec-18 |  |  | 168192 | 143601.65 | 168192 | 168192 | Lamb, Tim | Transpw | 22-Mar-19 | 26-Apr-21 | 08-Mar-19 | 23-Apr-19 | 23-Apr-19 |  |  |  | 0
453530 | (WO318780) 430 FERDALE DR, BARRIE - APARTMENTS | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 05-Apr-19 |  |  | 63580.96 | 47913 | 63580.96 | 63580.96 | Jeremy Wright | HapAmp | 07-Jun-19 | 21-Jan-21 | 27-May-19 | 04-Jun-19 | 29-Jul-19 | Customer | Customer |  | 0
453611 | 453611 (WO 318905) Pole Repl 2019 - Batch 11 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 19-Mar-19 |  |  | 201796 | 92999.43 | 201796 | 201796 | Shortt, Derek B. |  | 30-Nov-19 | 22-Oct-20 | 04-Jul-19 | 16-Aug-19 | 04-Nov-19 |  |  |  | 0
452624 | (WO315545) Belle Vie OHM / Markham Manor Inc. | 815 - Addiscott | 151531 | Active | 50 | H8 |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 27-Feb-19
452794 | PARENT W.O. FOR INSPECT/CONNE/I&C 11280 LESLIE MAINT 316585 | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
453917 | 453917 - ICI PADMOUNT TX INSTALLATION/2815 14TH AVE | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Paterson, Greg | 13-Nov-20 |  |  | 191592.61 | 162793.65 | 191592.61 | 191592.61 | Dave Lindsay | Somervl | 08-Feb-21 | 26-Jul-23 | 28-Dec-20 | 11-Jan-21 | 30-Jun-21 | Lines | Customer |  | 0
452792 | 452792 - LINDVEST ZZEN P. VAL. PH3 | 815 - Addiscott | 101887 | Active | 95 | ANALYZE |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 13-Sep-22 |  |  | 445009.12 | 50878.64 | 445009.12 | 445009.12 | Dave Lindsay |  | 29-Dec-22 | 26-Jul-23 | 03-Nov-22 |  | 06-Mar-23 | Customer | Customer |  | 0
452476 | ( WO 312394) CORNELL ROUGE PH 4D | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Kinsella, William P | 01-Nov-17 |  |  | 0 | 1706182.89 | 845818.77 | 845818.77 | Cory Ruiter |  | 25-Jul-19 | 26-Jul-23 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
454019 | (WO 319406) HWY 7 & Valleymede Drive | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 15-Jul-19 |  |  | 258115.04 | 538213.19 | 258115.04 | 258115.04 | Steve Rumble | Transpw | 10-Sep-19 | 27-Sep-22 | 21-Aug-19 | 04-Sep-19 | 04-Sep-19 |  | Customer |  | 0
453024 | (WO317546) Hydro Relocation - HWY 427 EXTENSION, HUNTINGTON RD AND MAJOR MACKENZIE DR, VAUGHAN - Tem | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Zhang, Jiacheng | 01-Jan-19 |  |  | 120000 | 31245.95 | 120000 | 120000 | Macdonald, Steve |  | 25-Jul-19 | 31-Jan-22 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
453458 | (WO 318686) ASHCROFT CT AND ANDREA LN | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 14-Mar-19 |  |  | 108986 | 78216.56 | 108986 | 108986 | Lamb, Tim | Transpw | 14-May-19 | 08-Feb-21 | 06-May-19 | 23-May-19 | 23-May-19 |  |  |  | 0
454141 | V37 Ainsley Grove and Airdrie (37-P1 to 37-36) | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 29-Aug-19 |  |  | 494797.27 | 466980.83 | 494797.27 | 494797.27 | Lamb, Tim | Transpw | 28-Oct-19 | 24-Feb-21 | 23-Sep-19 | 19-Sep-19 | 21-Oct-19 |  |  |  | 0
453195 | (WO 318150) JU 18-087 New anchor and down guy | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Battistella, Alexander | 06-Dec-18 |  |  | 14209 | 12161.7 | 14209 | 14209 | Macdonald, Larry |  | 15-Mar-19 | 05-Oct-20 | 02-Jan-19 | 26-Aug-19 | 26-Aug-19 |  |  |  | 0
453700 | 453700 (WO 319015) NORTHERN PINES BLVD. - #1 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 05-Mar-19 |  |  | 32701.88 | 27925.04 | 32701.88 | 32701.88 | Steve Rumble | Somervl | 29-Mar-19 | 24-Feb-20 | 25-Mar-19 | 02-Oct-19 | 06-Nov-19 | Customer | Customer |  | 0
453528 | (WO318778) Promenade Mall - Condo & Offic. BATHURST ST. & CENTRE ST. | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 25-Oct-18
453023 | 453023 (WO 317545) OH Relocation - HWY 427 EXTN, LANGSTAFF RD, EAST OF HUNTINGTON RD, VAUGHAN-Temp | 815 - Addiscott | 101762 | Active | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 01-Jan-19 |  |  | 26745 | 35323.15 | 26745 | 26745 | Macdonald, Steve |  | 07-Jun-21 | 26-Jul-23 | 07-Jun-21 | 07-Jun-21 | 07-Jun-21 |  |  |  | 0
452791 | ICI PADMOUNT TX INSTALLATION/3600 MAJOR MAC (TESLA) | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Stephens, Barry N. | Paterson, Greg |  |  |  | 0 | 4651.96 |  | 0 | Persaud, Ryan | Transpw |  | 24-Apr-23
452457 | (WO310938) The Remington Centre | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 1168.82 |  | 0 | Persaud, Ryan |  |  | 14-Feb-23
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE | High | MLinx | 2021 | Khuu, Philander | Grahovac, John | 09-Dec-19 |  |  | 1486374.12 | 1483101.92 | 966566.2 | 1486374.12 | Shane Christopher | Transpw | 01-May-20 | 22-Sep-22 | 24-Feb-20 | 26-Jun-20 | 30-Mar-21 | Customer | Customer |  | 519,807.92
633127 | 633127 - TRANSFORMER REPLACEMENT 2020 BATCH 10 - VAUGHAN - 30 UNITS | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Murray, Jake R - vacancy | 27-Nov-19 |  |  | 353619.34 | 236068.83 | 353619.34 | 353619.34 | Dave Lindsay | Somervl | 16-Apr-20 | 08-Jun-22 | 14-Feb-20 | 25-Jun-20 | 07-Dec-21 | Filler | Filler |  | 0
452620 | 452620 (WO 315510) Mapleview Drive East Development | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 04-Mar-20 |  |  | 693394.07 | 734913.48 | 693394.07 | 693394.07 | Lotto, Jay | Transpw | 24-Aug-20 | 07-Mar-22 | 26-Jun-20 | 27-Nov-20 | 15-Mar-21 | COVID19 | COVID19 |  | 0
454140 | (WO454140) 24 Elva Crt rush cable replacement | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 31-Jul-19 |  |  | 180494.28 | 125629.13 | 180494.28 | 180494.28 | Lamb, Tim | Transpw | 14-Aug-19 | 27-Apr-21 | 01-Aug-19 | 12-Aug-19 | 23-Sep-19 |  |  |  | 0
453456 | (WO 318684) Replace 44TV030 & 44TV028 | 815 - Addiscott | 101027 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 06-Dec-18 |  | 2 | 44641 | 7714.02 | 44641 | 44641 | Steve Rumble |  | 13-May-19 | 21-Dec-20 | 13-Feb-19 | 01-Jun-19 | 01-Jul-19 |  | Filler |  | 0
453193 | (WO318147) Edgehill Drive - Make Ready Work to Raise Secondary Guards for Permit 18-086 | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Harrington, James | 25-Apr-19 |  |  | 5589 | 4890.14 | 5589 | 5589 | Aulis, John -x |  | 17-Jun-19 | 05-Oct-20 | 16-May-19 | 07-May-19 | 07-May-19 |  |  |  | 0
453916 | 453916 (WO 319274) 280 Hunters Valley | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Paterson, Greg | 16-Aug-19 |  |  | 82322.05 | 64048.97 | 82322.05 | 82322.05 | Steve Rumble | Somervl | 27-Nov-19 | 10-Aug-20 | 11-Nov-19 | 21-Nov-19 | 25-Nov-19 | Customer |  |  | 0
454018 | MAPLEVIEW DRIVE (YONGE STREET TO PRINCE WILLIAM WAY), BARRIE - ROAD WIDENING | 825 - Patterson | 101764 | Active | 48 | ACTIVE | High | DA | 2023 | Lacombe, Joel | Harrington, James |  | 1 |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 07-May-19
452790 | (WO316565) Major Mackenzie Drive Phase 1 | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 127.96 |  | 0 | Persaud, Ryan |  |  | 07-Mar-23
452454 | 452454 - 10TH SIDEROAD - BRADFORD/POLE LINE RELOCATION | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Harrington, James | 14-Jun-21 |  |  | 1150873.03 | 932638.78 | 1150873.03 | 1150873.03 | Dan Kish | K-Line | 09-Aug-21 | 22-Sep-22 | 26-Jul-21 | 05-Jun-21 | 10-Sep-21 |  | Contractor |  | 0
453915 | 453915 (WO 319272) I&C Dogliola Development | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 01-Oct-20 |  |  | 209459.1 | 224270.63 | 209459.1 | 209459.1 | Dave Lindsay | Conelco | 30-Nov-20 | 28-Feb-22 | 23-Nov-20 | 30-Oct-20 | 22-Jan-21 |  | Customer |  | 0
453455 | 453455 (WO 318683) Pole Relocation - MAJOR MACKENZIE DRIVE | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 03-Oct-19 |  |  | 233407.67 | 195616.06 | 233407.67 | 233407.67 | Macdonald, Steve | K-Line | 15-Nov-19 | 28-Dec-21 | 30-Oct-19 | 15-Oct-19 | 27-Nov-19 |  |  |  | 0
453698 | 453698 - I & C UNION VILLAGE PHASE 1 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Graham, Bruce W. | 03-Dec-20 |  |  | 126888.01 | 881807.56 | 126888.01 | 126888.01 | Dave Lindsay |  | 10-Feb-21 | 09-Dec-21 | 14-Jan-21 | 15-Jan-21 | 30-Jun-21 | Customer | Customer |  | 0
454134 | (WO 319527) Guy Wire relocation INTERSECTION OF LOCKE AND JANE ST. | 815 - Addiscott | 101763 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 15-Jul-19 |  |  | 7450.26 | 3954.63 | 7450.26 | 7450.26 | Macdonald, Larry |  | 12-Aug-19 | 10-May-21 | 06-Aug-19 | 10-Sep-19 | 10-Sep-19 |  |  |  | 0
453332 | (WO 453332) Joint Use Permit 18-008- Stouffville Road- | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 12-Aug-19 |  |  | 13518.42 | 5575.52 | 13518.42 | 13518.42 | Macdonald, Larry |  | 05-Sep-19 | 09-Nov-20 | 26-Aug-19 | 24-Sep-19 | 24-Sep-19 | Filler | Filler |  | 0
453014 | 453014 (WO 317528) 2018 Shirley Ave & Vine Cres. - Rear Lot O/H to U/G Conversion - Barrie | 825 - Patterson | 150041 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Pollock, Kim | 21-Dec-17 |  |  | 786533 | 747732.46 | 786533 | 786533 | Jeremy Wright | Transpw | 25-Oct-19 | 29-Oct-20 | 08-Jul-19 | 08-Jul-19 | 18-Nov-19 |  |  |  | 0
453526 | (WO318775) Hydro One Scada Switch Install. FERNDALE DRIVE, BARRIE | 825 - Patterson | 101763 | Inactive | 99 | CANCELLED |  |  | 2022 | O'Gay, Brian | Harrington, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 25-Oct-18
316999 | (WO316999) New TX for Service Upgrade | 825 - Patterson |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  | 25-Jul-19 | 09-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
453607 | RER - MX - RELOC - KEELE ST - BARRIE LINE (1910) - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE |  |  | 2023 | Khuu, Philander | Grahovac, John | 16-Nov-22 |  |  | 169714.32 | 167441.58 | 161238.03 | 169714.32 | Macdonald, Steve | K-Line | 13-Jan-23 | 16-Jul-23 | 04-Jan-23 | 21-Nov-22 | 10-Dec-22 |  |  |  | 8,476.29
452451 | (WO310348) 4 Don Hillock Drive. Best Western Hotel | 825 - Patterson | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 22-Sep-22
454016 | 454016 - HWY 27 & HWY 7 | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander | 25-Jun-21 |  |  | 1307128 | 1300763.9 | 1307128 | 1307128 | Shane Christopher | Transpw | 23-Aug-21 | 22-Sep-22 | 09-Aug-21 | 16-Aug-21 | 10-Jan-22 | Contractor | Contractor |  | 0
452785 | 452785 - LINDVEST ZZEN P.VAL. PH2 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 22-Mar-21 |  |  | 438619.23 | 478139.77 | 438619.23 | 438619.23 | Dave Lindsay |  | 19-May-21 | 10-Nov-21 | 03-May-21 | 01-Apr-21 | 15-Sep-21 |  | Customer |  | 0
453524 | (WO318773) Replace SWG 15-L20. 113 VICEROY RD | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 26-Apr-19 |  | 1 | 86057 | 23115.97 | 86057 | 86057 | Lamb, Tim | Transpw | 02-Jul-19 | 14-Dec-20 | 06-May-19 | 08-Jun-19 | 08-Jun-19 |  |  |  | 0
453325 | (WO 318446) JU 18-135 | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Martin, Shane | 05-Jun-19 |  |  | 6746 | 2211.3 | 6746 | 6746 | Macdonald, Larry |  | 30-Oct-19 | 09-Nov-20 | 24-Sep-19 | 03-Oct-19 | 03-Oct-19 | Filler |  |  | 0
453454 | 453454 (WO 318682) 2019 STORM HARDENING - ANNE ST. FROM NEELANDS TO CUNDLES - Barrie | 825 - Patterson | 101781 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 17-Apr-19 |  |  | 416125 | 346735.51 | 416125 | 416125 | Dan Kish |  | 15-Jul-19 | 29-Oct-20 | 22-Apr-19 | 22-Apr-19 | 10-Sep-19 |  |  |  | 0
453697 | 453697 (WO 319011) Batch 17 - Replace 7 Poles | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 11-Feb-19 |  |  | 68890 | 98205.6 | 68890 | 68890 | Macdonald, Larry |  | 31-Dec-19 | 22-Oct-20 | 03-Jun-19 | 16-Sep-19 | 02-Dec-19 |  |  |  | 0
453189 | (WO318133) New 3 Phase Service | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Martin, Shane | 21-Jun-19 |  |  | 53014.42 | 50940.51 | 53014.42 | 53014.42 | Jeremy Wright | HapAmp | 08-Aug-19 | 19-Oct-20 | 25-Jul-19 | 17-Sep-19 | 02-Dec-19 |  | Customer |  | 0
454130 | 454130 (WO 319523) 81 & 91 King Street, Barrie | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 03-Oct-19 |  |  | 20599.75 | 15441.19 | 20599.75 | 20599.75 | Jeremy Wright | HapAmp | 07-Nov-19 | 10-Aug-20 | 04-Nov-19 | 06-Dec-19 | 18-Dec-19 | Customer | Customer |  | 0
314669 | ( WO 314669) 7818 DUFFERIN BUILDING A | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble | Transpw | 25-Jul-19 | 01-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
316993 | (WO316993) Main Monarch Castlepoint N Ph2. S/O KIRBY RD. & W/O KIPLING AVE. | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 24-Aug-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
453606 | RER - MX - RELOC - KEELE ST - BARRIE LINE (1908,1909) - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Active | 82 | H3 |  |  | 2023 | Khuu, Philander | Grahovac, John | 16-Nov-22 |  |  | 177812.98 | 81194.81 | 177812.98 | 177812.98 | Macdonald, Steve | K-Line | 23-Jun-23 | 26-Jul-23 | 05-Jun-23 | [5 empty] | 0
452976 | 452976 - MARKHAMONE POLE RELOCATION | 815 - Addiscott | 151531 | Active | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 29-Jul-21 |  |  | 133095.77 | 66307.85 | 133095.77 | 133095.77 | Macdonald, Larry |  | 04-Oct-21 | 26-Jul-23 | 13-Sep-21 | 20-Sep-21 | 24-Sep-21 |  |  |  | 0
453187 | (WO318125) 107 Hall Street | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 4345.33 |  | 0 | Persaud, Ryan |  |  | 07-Mar-23
453912 | 453912 (WO 319269) 3733 Highway 7 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Paterson, Greg | 24-Jul-19 |  |  | 60096.05 | 39260.23 | 60096.05 | 60096.05 | Steve Rumble | N/A | 11-Nov-19 | 23-Aug-21 | 28-Oct-19 | 12-Dec-19 | 20-Dec-19 |  | Customer |  | 0
452784 | 452784 (WO 316550) Lindvest Pine Valley Phase 1 | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Estrada, Michael | 28-May-19 |  |  | 79565.91 | 724123.16 | 79565.91 | 79565.91 | Steve Rumble |  | 08-Nov-19 | 02-Jun-21 | 16-Sep-19 | 03-Jun-19 | 16-Oct-19 |  |  |  | 0
453689 | (WO 319002) Replace P31121 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 22-Feb-19 |  |  | 20230 | 33744.02 | 20230 | 20230 | Macdonald, Steve | K-Line | 13-Sep-19 | 25-May-20 | 13-Aug-19 | 20-Aug-19 | 09-Sep-19 |  |  |  | 0
452890 | (WO316986) 155 Snivley St | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alarcon, Alejandro | 28-May-19 |  |  | 13606.98 | 111738.29 | 13606.98 | 13606.98 | Steve Rumble | Transpw | 31-Jul-19 | 12-Feb-20 | 15-Jul-19 | 29-Jul-19 | 29-Jul-19 |  | Customer |  | 0
318691 | (WO318691) Repl. Switchgear - Batch 1 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Handy, James | 01-Nov-18 |  | 3 | 96374 | 106230.78 | 96374 | 96374 | Steve Rumble |  | 12-Mar-19 | 17-May-19 | 12-Mar-19 | 19-Mar-19 | 02-Apr-19 | Filler | Filler |  | 0
452450 | (WO310346) Edenbrook Homes Subd. | 825 - Patterson | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Fitz Randolph, Kim C |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Feb-19
452614 | 452614 (WO 315445) 13200 Yonge St School | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Stephens, Barry N. | Dibratto, Susan | 11-Feb-19 |  |  | 65044.67 | 56583.09 | 65044.67 | 65044.67 | Steve Rumble | Somervl | 28-May-19 | 05-Jan-22 | 03-May-19 | 02-Jul-19 | 12-Sep-19 |  | Customer |  | 0
453452 | (Wo 318679) Pole Relocation- BAYVIEW AVENUE, BLOOMINGTON TO VANDORF | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander | 11-Mar-19 |  |  | 246449 | 122882.35 | 246449 | 246449 | Shortt, Derek B. |  | 04-Jul-19 | 29-Mar-21 | 04-Apr-19 | 04-Apr-19 | 09-May-19 |  |  |  | 0
452751 | 452751 (WO 316490) Hwy 404 and Hwy 7 Crossing | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 11-Feb-19 |  |  | 363086 | 458807.41 | 363086 | 372557.8 | Macdonald, Steve | K-Line | 24-Jun-19 | 15-Mar-21 | 29-May-19 | 30-Jul-19 | 28-Nov-19 |  |  |  | 9,471.80
454128 | (WO454128) 12895 BAYVIEW AVE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Diefenbaker, Trevor A | 16-Jul-19 |  |  | 39421.04 | 24297.27 | 39421.04 | 39421.04 | Steve Rumble | N/A | 28-Oct-19 | 21-Jan-21 | 26-Aug-19 | 16-Sep-19 | 16-Sep-19 |  |  |  | 0
454013 | 454013 (WO 319396) Replace P33217 - 95 Steelcase Rd E | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 31-May-19 |  |  | 124810 | 84489 | 124810 | 124810 | Shortt, Derek B. |  | 15-Nov-19 | 20-Jul-20 | 30-Sep-19 | 21-Oct-19 | 04-Nov-19 |  |  |  | 0
452885 | UPPER EAST SIDE TOWNS - RES SUBD EDS | 825 - Patterson | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Fitz Randolph, Kim C |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Feb-19
452884 | 452884 (WO 316940) Uptown Phase 3 - Verdale | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Stephens, Barry N. | Dibratto, Susan | 28-Jan-19 |  |  | 131915 | 129234.67 | 131915 | 131915 | Dave Lindsay | Somervl | 25-Mar-19 | 14-Feb-23 | 13-Mar-19 | 25-Aug-21 | 27-Oct-21 | Customer | Customer |  | 0
452738 | (WO316473) New Commercial Plaza | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 1293.52 |  | 0 | Persaud, Ryan |  |  | 13-Jul-22
452439 | (WO309672) 6857 & 7005 Industrial Parkway | 825 - Patterson | 101896 | Inactive | 99 | CANCELLED |  |  | 2021 | Cranley, Stephen | Perks, Dan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 01-Nov-21
453183 | (WO318119) Pole Betterment Batch #1 – Yonge St and Big Bay Pt.Rd ( approx 22 poles) | 825 - Patterson | 101781 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Pollock, Kim | 30-Nov-18 |  |  | 742586 | 258748.18 | 742586 | 742586 | Jeremy Wright | Transpw | 01-Apr-19 | 03-Oct-21 | 02-Jan-19 | 07-Jan-19 | 28-Mar-19 |  | Filler |  | 0
633039 | 633039 - 2020 Padmount Transformer Replacement Batch 8 - Vaughan/Markham | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 10-Jan-20 |  |  | 292423.45 | 222992.96 | 292423.45 | 292423.45 | Dave Lindsay | Somervl | 30-Dec-20 | 15-Jul-21 | 23-Nov-20 | 02-Oct-20 | 30-Mar-21 |  | Filler |  | 0
453603 | 453603 (WO 318896) ROAD CROSSING RELOCATE. MAJOR MACK DRIVE & BARONS STREET | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Graham, Bruce W. | 06-May-19 |  |  | 50517 | 44193.04 | 50517 | 50517 | Steve Rumble | Transpw | 11-Jul-19 | 07-Jan-21 | 24-Jun-19 | 24-Jun-19 | 31-Oct-19 |  | Customer |  | 0
452610 | (WO315397) YRRTC - Y2.1 - Stage 8 Yonge St - Weldrick to Elmwood | 815 - Addiscott | 101762-1 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Lacombe, Joel | 01-Nov-17 |  |  | 6466282.22 | 7698977.14 | 6715199 | 6715199 | Steve Rumble | K-Line | 28-Sep-18 | 31-Dec-20 | 01-Jun-18 | 06-Nov-17 | 22-Aug-19 |  | Customer |  | 0
454011 | 454011 (WO 319394) Replace P33146 - 395 Steelcase Rd E | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 31-May-19 |  |  | 53536 | 15556.99 | 53536 | 53536 | Shortt, Derek B. |  | 30-Sep-19 | 22-Oct-20 | 16-Sep-19 | 02-Dec-19 | 03-Dec-19 |  |  |  | 0
452973 | (WO 317452) 201 Romina Drive | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 19-Sep-18 |  |  | 38564.55 | 40331.94 | 38564.55 | 38564.55 | Steve Rumble | Transpw | 30-Nov-18 | 27-Jul-20 | 23-Nov-18 | 05-Nov-18 | 19-Jul-19 |  |  |  | 0
453303 | (WO318416) (Leslie&19th)-1521 19th Avenue PH4 | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
453995 | 453995 (WO 319375) WOODBINE AVE. - #9046 | 815 - Addiscott | 101791 | Active | 92 | COMPLETE |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 14-May-19 |  |  | 30680.15 | 23912.68 | 30680.15 | 30680.15 | Reginald Clarke | N/A | 16-Jul-19 | 26-Jul-23 | 11-Jul-19 | 07-Jul-20 | 30-Oct-23 | Customer | Customer |  | 0
452428 | 452428 - 1623 Wellington Street Developments | 815 - Addiscott | 101896 | Active | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Swales, Mathew | 18-Jan-21 |  |  | 221288.4 | 218589.61 | 221288.4 | 221288.4 | Dave Lindsay | Transpw | 06-Apr-21 | 26-Jul-23 | 08-Mar-21 | 26-Nov-21 | 05-May-22 | Customer | Customer |  | 0
453449 | 453449 - ROGERS JOINT USE 18-153 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 29-Nov-21 |  |  | 26208.84 | 22130.56 | 26208.84 | 26208.84 | Reginald Clarke |  | 06-Jan-22 | 26-Jul-23 | 05-Jan-22 | 05-Apr-22 | 06-Apr-22 | Locates | Locates |  | 0
453519 | (WO318767) 162 ST. JOHN'S SIDEROAD | 825 - Patterson | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Jeremy Wright |  |  | 22-Sep-22
453601 | 453601 - RER - MX - RELOC - ELGIN MILLS RD E - STOUFFVILLE LINE (6) - RAILWAY CROSSINGS | 815 - Addiscott | 150592 | Inactive | 99 | COMPLETE |  |  | 2022 | Khuu, Philander | Grahovac, John | 01-Oct-21 |  |  | 424215 | 308174.39 | 424215 | 424215 | Macdonald, Steve | K-Line | 17-Dec-21 | 17-Aug-22 | 29-Nov-21 | 06-Dec-21 | 29-Jan-22 | Contractor | Weather |  | 0
452737 | 452737 (WO 316470) Yonge - Go Village - Phase One | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 11-Jun-20 |  |  | 393878.45 | 378110.81 | 393878.45 | 393878.45 | Lotto, Jay | Transpw | 27-Nov-20 | 15-Aug-22 | 14-Oct-20 | 01-Feb-21 | 13-Jul-21 | Customer | Customer |  | 0
452970 | 452970 - DIGRAM DEVELOPMENTS MARKHAM 2 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Graham, Bruce W. | 26-Jan-21 |  |  | 17493.82 | 152706.34 | 17493.82 | 17493.82 | Dave Lindsay |  | 29-Mar-21 | 06-Apr-22 | 10-Mar-21 | 03-Sep-21 | 08-Dec-21 | Customer | Customer |  | 0
453182 | 453182 (WO 318114 ) A02 - Princeton Heights | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Fitz Randolph, Kim C | 03-Dec-18 |  |  | 23013.12 | 145563.48 | 23013.12 | 23013.12 | Dave Lindsay |  | 20-Aug-19 | 04-Nov-21 | 01-Aug-19 | 23-Feb-21 | 27-Apr-21 | Customer | Customer |  | 0
453686 | (WO318999) 2019 Steeles and NewWestminster Ph3 | 815 - Addiscott | 150142 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 27-Feb-19 |  |  | 224627 | 13607.16 | 222505 | 224626.81 | Lamb, Tim | Transpw | 29-May-19 | 01-Feb-21 | 20-Mar-19 | 20-Mar-19 | 10-Jun-19 |  |  |  | 2,121.81
452609 | (WO315396) YRRTC-Y2.1-STAGE 7 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Lacombe, Joel | 01-Nov-17 |  |  | 4222556.44 | 5298630.22 | 4251298 | 4251298 | Steve Rumble | K-Line | 31-Oct-18 | 03-Jun-20 | 01-Nov-17 | 01-Nov-17 | 22-Aug-19 |  |  |  | 0
453302 | (WO318414) (Leslie&19th)-1521 19th Avenue PH3 | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
316911 | (WO316911) 7200 Victoria Park Ave | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Yuen, Paul | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 01-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
317917 | (WO317917) 1 Ph. Transformer Installation | 825 - Patterson |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  | 25-Jul-19 | 09-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
452874 | BLOOMINGTON POLE RELOCATIONS/POLE RELOCATIONS | 815 - Addiscott | 101762 | Active | HL | H3 |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 963.16 | 150000 | 150000 | Macdonald, Steve |  |  | 26-Jul-23 | [6 empty] | 0
453301 | (WO318412) (Leslie&19th)-1521 19th Avenue PH2 | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | East |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Feb-23
452608 | ( WO 315393) YRRTC - Y2.1 - Stage 4 - Baif Blvd. to Major Mac W | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Lacombe, Joel | 18-Jan-18 |  |  | 7243670 | 10649358.93 | 7243670 | 7243670 | Steve Rumble | K-Line | 31-Oct-18 | 24-Aug-20 | 05-Feb-18 | 02-Apr-18 | 22-Aug-19 |  |  |  | 0
453517 | 453517 (WO 318763) 560 & 510 COPPER CREEK DR | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 13-May-19 |  |  | 113927.33 | 107973.28 | 113927.33 | 113927.33 | Steve Rumble | Somervl | 20-Aug-19 | 24-Feb-20 | 05-Aug-19 | 08-Jul-19 | 25-Oct-19 |  | Customer |  | 0
453685 | (WO318998) 2019 Steeles and NewWestminster Ph2 | 815 - Addiscott | 150142 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 27-Feb-19 |  |  | 248555 | 174376.4 | 241113 | 248554.94 | Lamb, Tim | Transpw | 31-Oct-19 | 20-Mar-20 | 20-May-19 | 17-Jun-19 | 21-Oct-19 |  | Contractor |  | 7,441.94
452416 | SERENA HOMES - SUBD RES EDS | 825 - Patterson | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Feb-19
453298 | 453298 - WEST ALLISTON 3 PHASE 1 - SUBD RES EDS | 825 - Patterson | 101887 | Active | 99 | ANALYZE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 04-Feb-21 |  |  | 488079.02 | 525571.06 | 488079.02 | 488079.02 | Lotto, Jay |  | 07-Sep-22 | 26-Jul-23 | 12-Aug-22 | 13-Apr-22 | 12-Jun-22 |  |  |  | 0
452607 | 452607 (WO 315386) 46 MAIN ST. NORTH, MARKHAM | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 01-Nov-17 |  |  | 76438.6 | 5314.76 | 76438.6 | 84914.89 | Dave Lindsay | Transpw | 28-Dec-22 | 10-Aug-23 | 30-Nov-22 | [5 empty] | 8,476.29
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE | High | MLinx | 2021 | Vande Kuyt, Greg | Grahovac, John | 22-Oct-19 |  |  | 2003219.96 | 1990123.54 | 1556424.96 | 2003219.96 | Shane Christopher | Transpw | 13-Mar-20 | 15-Feb-22 | 02-Dec-19 | 27-Apr-20 | 23-Feb-21 | Contractor | Customer |  | 446,795.00
453684 | 453684 (WO 318997) 2019 Steeles and NewWestminster Ph1 | 815 - Addiscott | 150142 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 27-Feb-19 |  |  | 511722 | 566853.03 | 402370 | 511721.82 | Lamb, Tim | Transpw | 03-Sep-19 | 18-Jun-21 | 06-May-19 | 27-May-19 | 27-Nov-19 |  | Contractor |  | 109,351.82
453890 | 453890 (WO 319235) HIGHWAY NO. 7 EAST - #2830 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Yuen, Paul | 24-May-19 |  |  | 34025.43 | 40944.47 | 34025.43 | 34025.43 | Steve Rumble | Somervl | 11-Jul-19 | 27-Feb-20 | 04-Jul-19 | 29-Oct-19 | 06-Nov-19 | Customer | Customer |  | 0
453993 | 453993 (WO 319370) NEW HUNTINTGTON RD. - #450 AT HUNTINGTON RD. | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Yuen, Paul | 13-May-19 |  |  | 54668.94 | 35927.77 | 54668.94 | 54668.94 | Steve Rumble | Somervl | 10-Sep-19 | 24-Feb-20 | 28-Aug-19 | 17-Oct-19 | 29-Oct-19 |  |  |  | 0
452733 | BLUEGROVE INVESTMENTS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Feb-19
453444 | FOREST HILL HOMES LTD RESIDENTIAL SUBDIVISION CONNECTIONS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 21-Sep-18
453516 | (WO 318762) 18-156 Rogers JU Application | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 | O'Gay, Brian | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 09-Oct-18
453175 | 453175 - JOINT USE PERMIT 18-079 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 17-Jan-22 |  |  | 55033.59 | 31794.11 | 55033.59 | 55033.59 | Reginald Clarke |  | 16-Mar-22 | 26-Jul-23 | 21-Feb-22 | 25-Jan-22 | 27-Jan-22 |  |  |  | 0
452965 | 452965 (WO 317382) Bishop's Gate Ph. 3 | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alarcon, Alejandro | 28-Jan-19 |  |  | 123283.8 | 57949.37 | 123283.8 | 123283.8 | Cory Ruiter | Transpw | 09-Apr-19 | 26-Jul-23 | 01-Apr-19 | 18-Nov-19 | 25-Nov-19 | Customer | Customer |  | 0
453598 | 453598 (WO 318891) - NINTH LINE - 19TH AVENUE TO ELGIN MILLS ROAD E | 815 - Addiscott | 150592 | Active | 98 | ANALYZE | High | MLinx | 2023 | Khuu, Philander | Grahovac, John | 08-Nov-19 |  |  | 400492.5 | 588788.58 | 391311 | 400492.5 | Macdonald, Steve | K-Line | 19-Aug-22 | 26-Jul-23 | 18-Jul-22 | 29-May-22 | 13-Feb-23 | Customer | Customer |  | 9,181.50
453443 | (WO318641) 2019 - Pdmt TX Rep. Batch 11 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 03-Dec-18 |  |  | 89808.8 | 74255.82 | 99008 | 89808.8 | Steve Rumble |  | 04-Jun-19 | 31-Aug-22 | 01-Apr-19 | 01-Apr-19 | 09-May-19 |  | Filler |  | -9,199.20
453682 | (WO 318994) JU HE2018-153 Bell | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Battistella, Alexander | 31-Jul-19 |  |  | 11133.64 | 11786.46 | 11133.64 | 11133.64 | Macdonald, Larry |  | 30-Oct-19 | 12-Oct-21 | 05-Sep-19 | 09-Oct-19 | 09-Oct-19 |  |  |  | 0
452732 | 452732 (WO 316450) Union Condominium Development | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alarcon, Alejandro | 26-Mar-18 |  |  | 18947.27 | 213059.44 | 18947.27 | 18947.27 | Steve Rumble | Conelco | 24-Sep-18 | 04-May-20 | 04-Jun-18 | 18-Jul-18 | 17-Dec-19 | Customer | Customer |  | 0
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE | High | MLinx | 2021 | Vande Kuyt, Greg | Grahovac, John | 28-Apr-20 |  |  | 3022820.74 | 3140671.69 | 2453670.74 | 3022820.74 | Shane Christopher | Transpw | 06-Nov-20 | 21-Mar-22 | 15-Jun-20 | 11-Jun-20 | 15-Mar-21 |  | Customer |  | 569,150.00
453512 | 453512 - BOX GROVE RESIDENTIAL E | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 15-Oct-20 |  |  | 886639.07 | 787866.94 | 886639.07 | 886639.07 | Dave Lindsay | Transpw | 18-Dec-20 | 10-May-21 | 07-Dec-20 | 28-Nov-20 | 22-Jan-21 |  | Contractor |  | 0
453678 | 453678 (WO 318990) 2019 - 44KV INSULATOR REPLACEMENT PROGRAM - BARRIE | 825 - Patterson | 102537 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 17-Dec-18 |  |  | 147000 | 116646.75 | 147000 | 147000 | Jeremy Wright |  | 31-Dec-19 | 29-Dec-20 | 14-Jan-19 | 10-Dec-19 | 24-Dec-19 |  |  |  | 0
453441 | 453441 (WO 318638) Storm Hardening 2019 Keele | 815 - Addiscott | 103659 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 10-Jun-19 |  |  | 1024259 | 675826.87 | 1024259 | 1024259 | Shortt, Derek B. | Transpw | 19-Dec-19 | 29-Oct-20 | 19-Jul-19 | 25-Jul-19 | 19-Dec-19 |  |  |  | 0
453296 | (WO318399) 120 ELLIS DRIVE, BARRIE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Martin, Shane | 08-Jan-19 |  |  | 58359.74 | 50145.29 | 58359.74 | 58359.74 | Jeremy Wright | HapAmp | 01-Mar-19 | 19-Oct-20 | 19-Feb-19 | 17-Jun-19 | 11-Jul-19 |  | Customer |  | 0
453173 | 453173 (WO 318092) Langstaff Road - Pole Repl. | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 24-Jan-19 |  |  | 274429 | 172817 | 274429 | 274429 | Macdonald, Larry |  | 30-Oct-19 | 20-Jul-20 | 05-Jun-19 | 06-Jun-19 | 25-Nov-19 |  |  |  | 0
453887 | 453887 (WO 319231) 241 TRADE VALLEY DRIVE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Diefenbaker, Trevor A | 26-Sep-19 |  |  | 80091.11 | 92618.2 | 80091.11 | 80091.11 | Steve Rumble | Somervl | 03-Dec-19 | 24-Feb-20 | 25-Nov-19 | 15-Oct-19 | 25-Nov-19 |  |  |  | 0
313385 | (WO313385) 9750 YONGE STREET | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Dibratto, Susan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  | 25-Jul-19 | 07-May-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
452962 | (WO317363) Pole Relocate at Elgin Mills Road East | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Graham, Bruce W. | 06-Feb-19 |  |  | 252416 | 99639.12 | 252416 | 252416 | Morrow, Joe |  | 22-May-19 | 09-Aug-22 | 03-Apr-19 | 25-Apr-19 | 06-Jun-19 |  |  |  | 0
452728 | (WO316436) 21 MILL STREET | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2021 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 10634.28 |  | 0 | Persaud, Ryan |  |  | 23-Feb-22
453676 | (WO318987) 5328 Hwy 7 E | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 06-May-19 |  |  | 47768.69 | 41022.87 | 47768.69 | 47768.69 | Steve Rumble | N/A | 17-Jul-19 | 23-Aug-21 | 21-May-19 | 01-Aug-19 | 13-Aug-19 |  | Customer |  | 0
453509 | (WO318751) UG Cable Replacement. M44 400-430 COCHRANE DR | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Nov-18 |  |  | 293147.15 | 292542.9 | 249023 | 293147.15 | Lamb, Tim | Transpw | 22-Mar-19 | 26-Apr-21 | 15-Mar-19 | 15-Mar-19 | 17-Mar-19 |  |  |  | 44,124.15
453440 | (WO 318637) MARCO CR AND AIRDRIE DR | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 30-May-19 |  |  | 201520 | 157301.74 | 201520 | 201520 | Lamb, Tim | Transpw | 24-Jul-19 | 26-Apr-21 | 08-Jul-19 | 16-Jul-19 | 23-Sep-19 |  |  |  | 0
453172 | (WO318090) 3 CONCERT WAY - PERMANENT | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 31-Jan-19 |  |  | 11358.67 | 13584.42 | 11358.67 | 11358.67 | Jeremy Wright | HapAmp | 14-Jun-19 | 20-Jul-20 | 06-Jun-19 | 08-May-19 | 15-May-19 |  |  |  | 0
452600 | 452600 (WO 315270) M43 Idema OH Pole Line Extension | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 250660 | 250425 | 250660 | 250660 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 15-Nov-19 | Contractor | Contractor |  | 0
453882 | (WO 319224) HE2019-008 - York Region | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 |  | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 05-Feb-19
453988 | 453988 - 110 YOUNG ST/ALLR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 99 | ANALYZE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 30-Jun-22 |  |  | 98383.68 | 85447.93 | 98383.68 | 98383.68 | Lotto, Jay | HapAmp | 20-Sep-22 | 11-Aug-23 | 19-Aug-22 | 12-Sep-22 | 09-Jan-23 | Customer | Customer |  | 0
453595 | RER - MX - RELOC - MCCOWAN RD - STOUFFVILLE LINE (10) - RAILWAY CROSSINGS | 815 - Addiscott | 150592 | Active | 82 | Upload Completed |  |  | 2023 | Khuu, Philander | Grahovac, John |  |  |  | 1509353.07 | 546952.35 | 1509353.07 | 1509353.07 | Persaud, Ryan | K-Line |  | 26-Jul-23 | [6 empty] | 0
453171 | 453171 - INDUSTRIAL PKWY- RELOCATE POLE/RELOCATE POLE FOR INTERSECTION | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Harrington, James | 22-Apr-21 |  |  | 46489.49 | 17115.31 | 46489.49 | 46489.49 | Dan Kish |  | 16-Jun-21 | 16-Mar-23 | 08-Jun-21 | 31-May-21 | 14-Jun-21 |  |  |  | 0
453291 | 453291 (WO 318390) Phase 1.1 BATHURST STREET(N. OF SUMMERIDGE DR TO N. OF NER ISRAEL DR), VAUGHAN | 815 - Addiscott | 150343 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Zhang, Jiacheng | 12-Mar-19 |  |  | 1372052 | 1410743.45 | 1372052 | 1372052 | Macdonald, Steve | K-Line | 08-Jul-19 | 29-Dec-21 | 08-Apr-19 | 08-Apr-19 | 28-Aug-19 |  |  |  | 0
452864 | (WO 316883) YRRTC related-H2W-Hwy 400 Crossing at Hwy 7 | 815 - Addiscott | 101762-1 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Zhang, Jiacheng | 13-Apr-18 |  |  | 3176161.33 | 3248365.89 | 3176161.33 | 3176161.33 | Steve Rumble |  | 08-Feb-19 | 08-Mar-21 | 01-Jun-18 | 24-May-18 | 12-Feb-19 |  |  |  | 0
453437 | 453437 (WO 318631) DA P4872 - Royal Parkside Dr. - Air Break to Automated 44kV | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 24-Jun-19 |  |  | 174165 | 165369.89 | 174165 | 174165 | Dan Kish |  | 30-Sep-19 | 22-Oct-20 | 15-Jul-19 | 05-Aug-19 | 09-Sep-19 |  | Filler |  | 0
452599 | 452599 (WO 315269) M43 Steelcase and Idema - 161-183 Idema | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 268491 | 178721 | 249377 | 268491.2 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 15-Nov-19 | Contractor | Contractor |  | 19,114.20
452726 | 452726 (WO 316431) M43 Steelcase and Idema - 87 Steelcase | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 168626 | 172691 | 168626 | 168626 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 15-Nov-19 | Contractor | Contractor |  | 0
453675 | (WO 318986) Batch 15 - Replace 16 Poles | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 11-Feb-19 |  |  | 113338 | 123144.76 | 113338 | 113338 | Macdonald, Steve | K-Line | 30-Sep-19 | 25-May-20 | 03-Jun-19 | 18-Jun-19 | 10-Sep-19 |  |  |  | 0
313235 | (WO313235) 300 EARL STEWART DR, AURORA | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  | 25-Jul-19 | 02-Jan-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
453594 | 453594 (WO 318887) MARKHAM ROAD - RAMONA BLVD TO BEECH ST-METROLINX CROSSING #ST9 | 815 - Addiscott | 150592 | Active | 82 | H8 | High | MLinx | 2023 | Khuu, Philander | Grahovac, John | 29-Jan-20 |  |  | 1241586.47 | 56226.67 | 1241586.47 | 1241586.47 | Shane Christopher | Transpw | 05-Jun-20 | 26-Jul-23 | 04-May-20 |  |  | Customer | Customer |  | 0
452958 | (WO317332) 8th Line and Langford Blvd, Bradford - Pole Relocations | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Harrington, James | 21-Feb-19 |  |  | 201229 | 107418.31 | 201229 | 201229 | Jeremy Wright |  | 15-May-19 | 13-Apr-23 | 25-Mar-19 | 11-Mar-19 | 10-Apr-19 |  |  |  | 0
452721 | (WO316397) 850 Elgin Mills Road East | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 5752.21 |  | 0 | Persaud, Ryan |  |  | 07-Mar-23
453986 | (WO319355) 8 TRUMAN ROAD | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED | Low | Comm | 2022 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 01-Sep-22
453506 | (WO318746) 545 TIFFIN STREET | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Martin, Shane |  |  |  | 0 | 195.43 |  | 0 | Jeremy Wright |  |  | 13-Jul-22
453878 | 453878 (WO 319220) LESLIE ST WILLIAM LOGAN. guy pole conflict | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Graham, Bruce W. | 16-Sep-19 |  |  | 9431.13 | 17394.61 | 9431.13 | 9431.13 | Macdonald, Steve | K-Line | 15-Oct-19 | 14-Oct-21 | 15-Oct-19 | 15-Oct-19 | 29-Oct-19 |  |  |  | 0
453436 | 453436 (WO 318630) 2019 Pdmt TX Rep North Batch 5 | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 01-May-19 |  |  | 140676 | 158363.83 | 140676 | 140676 | Jeremy Wright |  | 30-Nov-19 | 02-Jun-21 | 20-May-19 | 16-Sep-19 | 29-Nov-19 |  | Filler |  | 0
452862 | ( WO 316880) 100 GIBRALTAR RD (HWY 50 & HWY7) | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 01-Nov-17 |  |  | 114002.05 | 99743.06 | 114002.05 | 114002.05 | Steve Rumble | Somervl | 12-Aug-19 | 03-Feb-21 | 31-Jul-19 | 17-Jul-19 | 19-Aug-19 |  |  |  | 0
452598 | 452598 (WO 315268) M43 Steelcase and Idema - 207-297 Idema | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 819879.52 | 850772 | 765051 | 819879.72 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 18-Dec-19 | Contractor | Contractor |  | 54,828.72
453290 | (WO 318388) 25 Farrell Rd. | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 14-Aug-18 |  |  | 65970.3 | 65172.05 | 65970.3 | 65970.3 | Steve Rumble | Transpw | 04-Dec-18 | 24-Feb-20 | 21-Nov-18 | 24-Sep-18 | 09-Oct-19 |  |  |  | 0
313234 | (WO313234) S/W corner Yonge & Elderberry | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  | 25-Jul-19 | 02-Jan-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
453593 | 453593 - RER - MX - RELOC - 19TH AVE - STOUFFVILLE LINE (4) - RAILWAY CROSSINGS | 815 - Addiscott | 150592 | Inactive | 99 | COMPLETE |  |  | 2022 | Khuu, Philander | Grahovac, John | 30-Sep-21 |  |  | 422900.75 | 426696.12 | 422900.75 | 422900.75 | Macdonald, Steve | K-Line | 30-Dec-21 | 31-Aug-22 | 29-Nov-21 | 06-Dec-21 | 29-Jan-22 | Contractor | Weather |  | 0
453505 | (WO318745) 430 FERNDALE RD, APARTMENT BUILDING | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 10975.99 |  | 0 | Jeremy Wright |  |  | 13-Jul-22
452719 | 452719 - RAISE NEUTRAL HEIGHT AND INSTALL BOLLARDS, VAUGHAN | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Zhang, Jiacheng | 15-Dec-20 |  |  | 55486.38 | 27032.56 | 55486.38 | 55486.38 | Macdonald, Larry | Transpw | 24-Feb-21 | 08-Jun-22 | 09-Feb-21 | 19-Jan-21 | 12-Feb-21 |  |  |  | 0
453435 | (WO318629) 2019 Pdmt TX Rep North Batch 4 | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 24-Apr-19 |  |  | 129626 | 113881.85 | 129626 | 129626 | Jeremy Wright |  | 31-Jul-19 | 02-Jun-21 | 06-May-19 | 14-May-19 | 22-Jul-19 | Filler | Filler |  | 0
452597 | 452597 (WO 315267) M43 Steelcase and Idema - 57 and 67 Steelcase | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 259909 | 271995 | 194904 | 259909.41 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 15-Nov-19 | Contractor | Contractor |  | 65,005.41
452956 | 452956 (WO 317326) Yonge St. - #8868 at Westwood | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 12-Nov-18 |  |  | 49234.29 | 40338.67 | 49234.29 | 49234.29 | Dave Lindsay | Somervl | 07-Jan-19 | 25-Apr-22 | 17-Dec-18 | 24-May-19 | 30-Jun-21 | Customer | Customer |  | 0
453874 | (WO 319215) YRRTC-Y2.1-PERMANENT POLES | 815 - Addiscott | 101762-1 | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Lacombe, Joel |  |  |  | 0 | 354634 |  | 0 | Persaud, Ryan |  |  | 21-Nov-21 |  | 30-Mar-19 | 30-Mar-19 | xBy-passed | xBy-passed
453434 | (WO318628) 2019 PDMT TX REP NORTH BATCH 3 | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 04-Apr-19 |  |  | 130671 | 111244.03 | 130671 | 130671 | Jeremy Wright |  | 01-Aug-19 | 02-Jun-21 | 22-Apr-19 | 10-May-19 | 11-Jul-19 |  | Filler |  | 0
452596 | 452596 (WO 315266) M43 Steelcase and Idema - 77 Steelcase | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 161194 | 160773 | 161194 | 161194 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 15-Nov-19 | Contractor | Contractor |  | 0
452718 | 452718 (WO 316390) M43 Steelcase and Idema - 8 Steelcase | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 105908 | 115666 | 105908 | 105908 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 15-Nov-19 | Contractor | Contractor |  | 0
453284 | 453284 (WO 318378) 30 Sims Crescent | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 14-Aug-18 |  |  | 134527 | 145668.38 | 134527 | 134527 | Steve Rumble | Transpw | 04-Oct-18 | 26-Feb-20 | 10-Sep-18 | 02-Jul-19 | 21-Aug-19 |  | Customer |  | 0
453504 | (WO 318744) Pole Replacement 2019 Batch 7 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 04-Dec-18 |  |  | 143287 | 95664.24 | 143287 | 145834.79 | Morrow, Joe |  | 30-Jul-19 | 24-Feb-20 | 02-Jan-19 | 25-Apr-19 | 11-Jul-19 |  |  |  | 2,547.79
453983 | (WO319352) PINE VALLEY RD. - #10150 | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 07-May-19
452854 | (WO316864) 70 Leek Cres | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 06-May-19 |  |  | 41770.16 | 28498.44 | 41770.16 | 41770.16 | Steve Rumble |  | 20-Jun-19 | 21-Jun-21 | 20-May-19 | 24-May-19 | 26-May-19 |  |  |  | 0
453433 | (WO318627) 2019 Pdmt TX Rep North Batch 2 | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 15-Mar-19 |  |  | 112104 | 82545.16 | 112104 | 112104 | Jeremy Wright |  | 30-Aug-19 | 02-Jun-21 | 08-Apr-19 | 15-Jul-19 | 07-Aug-19 | Filler | Filler |  | 0
453979 | 453979 (WO 319348 ) 185 Cundles Road East, Barrie | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Harris, Geoff L. | 27-Sep-19 |  |  | 49324.36 | 37534.1 | 49324.36 | 49324.36 | Jeremy Wright |  | 11-Nov-19 | 19-Oct-20 | 04-Nov-19 | 03-Dec-19 | 11-Dec-19 |  |  |  | 0
452595 | 452595 (WO 315265) M43 Steelcase and Idema - 76 Steelcase | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 205912 | 210204 | 205912 | 205912 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 15-Nov-19 | Contractor | Contractor |  | 0
453277 | 453277 - JU Permit 18-134 | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 27-Aug-19 |  |  | 23262.98 | 25173 | 23262.98 | 23262.98 | Macdonald, Larry |  | 30-Oct-19 | 20-Jul-20 | 24-Sep-19 | 17-Oct-19 | 17-Oct-19 | Filler |  |  | 0
452716 | ( WO 316370) Rebuild Pole Line on Warden Ave into 4 cct - From 16th Ave to Major Mackenzie Drive | 815 - Addiscott | 100229 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Tempra, Troylan | 12-Feb-18 |  |  | 1789407 | 1924453 | 1494629 | 1931349 | Shortt, Derek B. |  | 19-Jul-19 | 20-Jul-20 | 20-Aug-18 | 30-Aug-18 | 15-Jul-19 |  |  |  | 436,720.00
453588 | 453588 (WO 318881) 2019 Distribution Automation. 6720 HUNTINGTON RD, VAUGHAN | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 27-Feb-19 |  | 1 | 74212 | 112756.81 | 74212 | 74212 | Macdonald, Steve | K-Line | 09-Aug-19 | 25-May-20 | 19-Jul-19 | 01-Oct-19 | 29-Oct-19 |  |  |  | 0
453873 | (WO319214) Main Street Unionville - #206 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 27-Mar-19 |  |  | 72951.02 | 69597.77 | 72951.02 | 72951.02 | Steve Rumble | Somervl | 07-Jun-19 | 24-Feb-20 | 21-May-19 | 08-Jul-19 | 19-Jul-19 |  | Customer |  | 0
453503 | (WO 318743) Pole Replacement 2019 Batch 6 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 03-Dec-18 |  |  | 124999 | 203957.69 | 124999 | 124999 | Morrow, Joe |  | 30-Jul-19 | 10-Feb-20 | 02-Jan-19 | 04-Feb-19 | 10-Jul-19 |  |  |  | 0
453870 | 453870 (WO 319210) Elgin Mills Rd at Melbourne St - south side | 815 - Addiscott | 101761 | Active | 82 | H8 |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 09-Aug-19 |  |  | 9001.41 | 795.21 | 9001.41 | 9001.41 | Dave Lindsay |  | 21-Nov-19 | 31-Jul-23 | 18-Nov-19 |  |  | Customer | Customer |  | 0
452853 | (WO316862) Woodbridge Meadows | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Feb-23
452954 | 452954 (WO 317322) JU 17-140 | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 27-Aug-19 |  |  | 17508.58 | 14100.05 | 17508.58 | 17508.58 | Macdonald, Larry |  | 30-Oct-19 | 09-Nov-20 | 25-Sep-19 | 04-Nov-19 | 04-Nov-19 | Filler | Filler |  | 0
453587 | (WO318880) 2019 Distribution Automation. MAJOR MACK DR W W/O BATHURST ST | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 09-Apr-19 |  | 1 | 71713 | 46721.62 | 71713 | 71713 | Macdonald, Steve | K-Line | 30-Aug-19 | 22-Oct-20 | 21-May-19 | 14-May-19 | 14-May-19 |  |  |  | 0
453502 | 453502 (WO 318742) Left-Behind Cable Replacement, M27 16th and Kennedy | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 04-Sep-19 |  |  | 396828.39 | 341242 | 396828.39 | 396828.39 | Lamb, Tim | Transpw | 01-Nov-19 | 20-Jul-20 | 01-Oct-19 | 30-Oct-19 | 11-Dec-19 | Contractor | Contractor |  | 0
452594 | 452594 (WO 315264) M43 Steelcase and Idema - 10 Steelcase | 815 - Addiscott | 150035 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Apr-19 |  |  | 186523 | 197955 | 186523 | 186523 | Cory Ruiter | Transpw | 30-Sep-19 | 20-Jul-20 | 01-Jul-19 | 15-Jul-19 | 15-Nov-19 | Contractor | Contractor |  | 0
453432 | 453432 (WO 318626) 2019 Padmount Transformer Replacement Batch 10 - Vaughan | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 24-Sep-19 |  |  | 234729.93 | 128008 | 234729.93 | 234729.93 | Steve Rumble | Somervl | 22-Nov-19 | 20-Jul-20 | 21-Oct-19 | 23-Nov-19 | 14-Dec-19 | Filler | Filler |  | 0
453971 | 453971 (WO 319339) Replace V01SL3013 w/ Recloser | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 09-Apr-19 |  |  | 82966 | 105224.99 | 82966 | 82966 | Macdonald, Steve | K-Line | 16-Aug-19 | 04-May-20 | 19-Jul-19 | 01-Oct-19 | 29-Oct-19 |  |  |  | 0
452713 | 452713 (WO 316366) Medical Offices. 1 Eaglet Court Offices | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 12-Sep-18 |  |  | 70554.46 | 98113.96 | 70554.46 | 70554.46 | Steve Rumble | Transpw | 26-Nov-18 | 04-May-20 | 13-Nov-18 | 22-Oct-19 | 12-Nov-19 | Customer | Customer |  | 0
452590 | 452590 - BRADFORD EAST DEVELOPMENTS PH2/INSPECT AND CONNECT | 825 - Patterson | 101887 | Active | 99 | ANALYZE |  |  | 2022 | Cranley, Stephen | Cranley, Stephen | 03-Nov-22 |  |  | 560001.76 | 546405.45 | 560001.76 | 560001.76 | Lotto, Jay | Transpw |  | 26-Jul-23 |  | 01-Aug-22 | 01-Aug-22 | xBy-passed | xBy-passed |  | 0
452850 | ( WO 316842) Hydro Relocation - PROCTOR AVE AND HENDERSON AVE, MARKHAM | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 74.82 | 0 | 20000 | 20000 | Persaud, Ryan |  |  | 23-May-23 | [6 empty] | 0
453867 | (WO 319207) RA-Service pole relocation | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Barry, Kenneth | 15-May-19 |  |  | 11292 | 12301.43 | 11292 | 11292 | Macdonald, Larry |  | 21-Jun-19 | 04-Feb-21 | 05-Jun-19 | 13-Jun-19 | 14-Jun-19 |  |  |  | 0
452953 | ( WO 317321) Relocate Poles for Rd widening - HARVIE ROAD (HWY 400 TO ESSA ROAD), BARRIE | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Harrington, James | 01-Nov-17 |  |  | 2348216 | 2256150.32 | 2348216 | 2348216 | Dan Kish | K-Line | 31-May-19 | 31-Dec-20 | 02-Jan-19 | 15-Jan-19 | 24-May-19 | Locates |  |  | 0
453501 | 453501 (WO 318740) Left-Behind Cable Replacement. M33 WARDEN AV AND HWY 7 | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 29-Aug-19 |  |  | 133958.62 | 117467.15 | 133958.62 | 133958.62 | Lamb, Tim | Transpw | 01-Oct-19 | 14-Dec-20 | 23-Sep-19 | 21-Oct-19 | 19-Nov-19 |  |  |  | 0
453145 | 453145 (WO 318021) J, K, L McNaughton & EagleRock | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Paterson, Greg | 27-Mar-19 |  |  | 90075.28 | 57992.65 | 90075.28 | 90075.28 | Steve Rumble | Transpw | 24-Jun-19 | 13-Oct-20 | 11-Jun-19 | 01-Nov-19 | 03-Dec-19 | Customer | Customer |  | 0
453970 | (WO 319338) V44SL3072 - 5020 Islington Ave | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 21-Jun-19 |  | 1 | 87533 | 109635.29 | 87533 | 87533 | Macdonald, Steve | K-Line | 13-Sep-19 | 04-May-20 | 13-Aug-19 | 09-Sep-19 | 02-Oct-19 |  |  |  | 0
453866 | MAPLE GROVE AVE. - POLE RELOCATIONS | 815 - Addiscott | 101762 | Active | HL | H8 |  |  | 2023 | Corriveau, Tom N | Barry, Kenneth |  |  |  | 0 | 6087.06 |  | 0 | Persaud, Ryan |  |  | 26-Jul-23
452710 | 452710 - MARKHAMONE DEV. LTD. | 815 - Addiscott | 101887 | Active | 98 | ANALYZE |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 29-Aug-22 |  |  | 237633.37 | 45461.51 | 237633.37 | 237633.37 | Dave Lindsay |  | 15-Nov-22 | 26-Jul-23 | 14-Oct-22 | 20-Oct-22 | 06-Mar-23 | Customer | Customer |  | 0
453144 | 453144 - PARENT W.O. FOR INSPECT/CONNE/I & C VAUGHAN NW RESDENCES DEV | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 19-Dec-22 |  |  | 806310.06 | 771921.43 | 806310.06 | 806310.06 | Dave Lindsay | Transpw | 03-Apr-23 | 09-Aug-23 | 20-Mar-23 | 13-Mar-23 |  | N/A | N/A |  | 0
452589 | 452589 (WO 315223) Bradford East Developments Phase 1. CIVIL only | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Perks, Dan | 21-Sep-18 |  |  | 809593.36 | 812100.44 | 809593.36 | 809593.36 | Jeremy Wright | Transpw | 17-Dec-18 | 29-Dec-21 | 01-Nov-18 | 22-Oct-18 | 16-Dec-19 |  | Customer |  | 0
453499 | (WO318738) Left-Behind Cable Replacement. M37 Riviera Dr and Rodick Rd | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 11-Apr-19 |  |  | 164458 | 130514 | 164458 | 164458 | Lamb, Tim | Transpw | 05-Jun-19 | 20-Jul-20 | 21-May-19 | 17-Jun-19 | 01-Aug-19 |  | Contractor |  | 0
453585 | 453585 (WO 318877) 2019 Distribution Automation. WESTON RD N/O LANGSTAFF | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 27-Feb-19 |  | 1 | 69022 | 113012.19 | 69022 | 69022 | Macdonald, Steve | K-Line | 16-Aug-19 | 25-May-20 | 23-Jul-19 | 27-Nov-19 | 02-Dec-19 |  |  |  | 0
453428 | 453428 (WO 318622) 2019 Padmount Transformer Replacement Batch 6 - Vaughan | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 24-Sep-19 |  |  | 325208.31 | 233031.37 | 325208.31 | 325208.31 | Steve Rumble | Somervl | 31-Dec-19 | 24-Feb-20 | 21-Oct-19 | 23-Nov-19 | 11-Dec-19 | Filler |  |  | 0
453968 | 405 ESSA RD - SEAN MASON HOMES/INSPECT AND CONNECT | 825 - Patterson | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 17-May-19
452586 | 452586 - 210 EDWARD ST, AURORA | 815 - Addiscott | 101791 | Active | 99 | COMPLETE | Low | Comm | 2022 | Cranley, Stephen | Harris, Geoff L. | 18-Aug-21 |  |  | 61133.39 | 70069.29 | 61133.39 | 61133.39 | Dave Lindsay | Somervl | 05-Nov-21 | 26-Jul-23 | 01-Oct-21 | 26-Jan-22 | 07-Oct-22 | Customer | Customer |  | 0
452705 | PARENT W.O. FOR INSPECT/CONNE/I&C MAJOR MACKENZIE SOUTH | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 7522.12 |  | 0 | Persaud, Ryan |  |  | 16-Mar-23
452842 | 452842 (WO 316815) 3900 Windflower Gate (Tesla) | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Stephens, Barry N. | Paterson, Greg |  |  |  | 0 | 2892.45 |  | 0 | Persaud, Ryan |  |  | 28-Feb-23
453143 | 453143 - INSPECT/CONNE/I&C - 1696913 ONTARIO INC. | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | D'Onofrio, Tony | 01-Feb-21 |  |  | 179630.14 | 182131.28 | 179630.14 | 179630.14 | Dave Lindsay | Transpw | 07-Apr-21 | 11-Jan-22 | 15-Mar-21 | 15-Oct-21 | 02-Dec-21 | Customer | Customer |  | 0
453267 | 453267 (WO 318308) 100 Eagle Rock Way | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | High | Res-ICI | 2019 | Cranley, Stephen | Paterson, Greg | 23-Oct-18 |  |  | 109478.51 | 123531.84 | 109478.51 | 109478.51 | Steve Rumble | Somervl | 12-Dec-18 | 01-Aug-21 | 30-Nov-18 | 04-Feb-19 | 03-Dec-19 | Customer | Customer |  | 0
453498 | 453498 (WO 318737) Left-Behind Cable Replacement. V37 LANGSTAFF RD AND WESTON AV | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 30-May-19 |  |  | 491085 | 429791.45 | 491085 | 491085 | Lamb, Tim | Transpw | 13-Aug-19 | 23-Dec-20 | 08-Jul-19 | 26-Aug-19 | 27-Nov-19 |  | Contractor |  | 0
453427 | 453427 (WO 318621) 2019 Pad TX Repl. - Batch 5 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 24-Sep-19 |  |  | 194796.33 | 53408.28 | 194796.33 | 194796.33 | Steve Rumble | Somervl | 20-Dec-19 | 22-Oct-20 | 21-Oct-19 | 23-Nov-19 | 16-Dec-19 | Filler |  |  | 0
453584 | 453584 (WO 318876) 2019 Distribution Automation. LANGSTAFF RD E/O WESTON RD | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 27-Feb-19 |  | 1 | 68906 | 105293.42 | 68906 | 68906 | Macdonald, Steve | K-Line | 29-Jul-19 | 25-May-20 | 22-Jul-19 | 28-Nov-19 | 29-Nov-19 |  |  |  | 0
453966 | (WO 319333) BELL COMMUNICATION BONDS LANGSTAFF RD & WOODCROFT LN | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 |  | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Apr-19
453836 | PARENT W.O. FOR UNPLANNED/TX: M16TP3006 RE-LOCATION | 815 - Addiscott | 151531 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 25-Jan-19
453662 | Barrie TS Upgrade Feeders and Metering | 825 - Patterson |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | East |  |  |  | 0 | 0 | 2123665 | 2123665 | Persaud, Ryan |  |  | 17-Aug-18 | [6 empty] | 0
634124 | 634124 - 189 BULLOCK DR / ICI PADMOUNT TX UPGRADE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Low | Comm | 2021 | Joshi, Namrata | Mann, Drew | 15-May-20 |  |  | 75325.57 | 64544.26 | 75325.57 | 75325.57 | Dave Lindsay | Somervl | 25-Jun-20 | 21-Apr-22 | 15-Jun-20 | 25-May-21 | 17-Aug-21 | Customer | Customer |  | 0
634133 | 634133 - ICI TRANSFORMER UPGRADE/100 ANNA RUSSELL WAY | 815 - Addiscott | 101791 | Active | 84 | H8 |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 04-Nov-20 |  |  | 99812.18 | 89466.71 | 99812.18 | 99812.18 | Dave Lindsay | Somervl | 19-Jan-21 | 04-Aug-23 | 18-Dec-20 | 21-Jan-21 |  | Customer | Customer |  | 0
634137 | ICI NEW INDUSTRIAL CONNECTION/57 KING RD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 29-Oct-19
634156 | 634156 - TESTON RD. PINE VALLEY TO WESTON - POLE RELOCATION | 815 - Addiscott | 151909 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 26-Mar-21 |  |  | 4462892.98 | 1524432.15 | 4520823.93 | 4462892.98 | Morrow, Joe | Transpw | 30-Dec-21 | 07-Mar-23 | 03-May-21 | 26-Apr-21 | 31-Aug-21 |  |  |  | -57,930.95
634084 | 2027 REAR LOT EASTERN AVE IN TOTTENHAM | 825 - Patterson | 101781 | Active | 40 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 29-Oct-19
634344 | 634344 - STORM HARDENING 2020 - WOODBINE - RIVIERA TO DENISON | 815 - Addiscott | 103659 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 25-May-20 |  |  | 1001729.31 | 1042939.15 | 630883.05 | 1001729.31 | Macdonald, Steve | K-Line | 12-Nov-20 | 05-Jan-22 | 14-Sep-20 | 09-Jan-21 | 27-Mar-21 | Lines |  |  | 370,846.26
634364 | 634364 - FEEDER RE-CONFIGURATION ON HUNTINGTON RD | 815 - Addiscott | 151478 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 14-Nov-19 |  |  | 28955.31 | 42606.29 | 28955.31 | 28955.31 | Macdonald, Larry |  | 06-Dec-19 | 29-Oct-20 | 25-Nov-19 | 11-Dec-19 | 14-Dec-19 |  |  |  | 0
634430 | 634430 - ICI PADMOUNT TX INSTALLATION/400 CROSSLAND BLVD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 14-May-21 |  |  | 27754.22 | 49375.5 | 27754.22 | 27754.22 | Lotto, Jay | HapAmp | 21-Jul-21 | 06-Apr-22 | 29-Jun-21 | 01-Nov-21 | 18-Nov-21 | Customer | Customer |  | 0
634431 | 634431 - ICI PADMOUNT TX INSTALLATION/100 MILL ST E | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 20-Dec-19 |  |  | 48556.2 | 53670.54 | 48556.2 | 48556.2 | Lotto, Jay | HapAmp | 03-Feb-20 | 06-Apr-22 | 27-Jan-20 | 14-Jul-20 | 15-Nov-21 | Customer | Customer |  | 0
453630 | 453630 - RER - MX - RELOC - KENNEDY RD - STOUFFVILLE LINE (16) - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE | High | MLinx | 2022 | Khuu, Philander | Grahovac, John | 03-Dec-19 |  |  | 153810.09 | 182296.74 | 153810.09 | 153810.09 | Shane Christopher | Transpw | 27-Mar-20 | 05-Jul-22 | 24-Feb-20 | 10-Nov-21 | 23-Mar-22 | Customer | Customer |  | 0
633456 | 633456 - HATPIN CONDOMINIUM DEVELOPMENT/ INSPECT & CONNECT | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 14-Oct-20 |  |  | 103749.13 | 76353.88 | 103749.13 | 103749.13 | Dave Lindsay | Transpw | 17-Dec-20 | 07-Sep-21 | 26-Nov-20 | 30-Apr-21 | 21-Jul-21 | Customer | Customer |  | 0
633592 | PARENT W.O INSPECT/CONNECT/I&C-"DICKSON 48 DEVELOPMENT ST2- WEST GORMLEY PH. 2" | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Sep-19
633498 | 633498 - JOINT USE PERMIT HB2019-009 | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 05-Oct-20 |  |  | 14141.92 | 10341.42 | 14141.92 | 14141.92 | Richard Cuddy |  | 12-Nov-20 | 16-Jun-22 | 09-Nov-20 | 06-Jan-21 | 12-Feb-21 | Locates | Locates |  | 0
633700 | 633700 - PARENT W.O INSPECT/CONNECT/I&C-"NEW SUBDIVISION BLOCK 3- ARNOLD" | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2021 | D'Onofrio, Tony | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 19-Jul-21
453306 | 453306 - RUTHERFORD RD. PH.3 - BATHURST TO PETER RUPERT | 815 - Addiscott | 151553 | Inactive | 99 | COMPLETE | Medium | Infrast | 2021 | Corriveau, Tom N | Barry, Kenneth | 15-Jul-21 |  |  | 4618424.26 | 4315700.96 | 4618424.26 | 4618424.26 | Ryan Walsh | Transpw | 30-Dec-21 | 22-Sep-22 | 09-Aug-21 | 03-Aug-21 | 21-Dec-21 |  |  |  | 0
633501 | JOINT USE PERMIT HB2019-010- THE GORE ROAD- KELWAYS CIRCLE TO HWY 50 | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 13-Sep-21 |  |  | 34070.14 | 18887.97 | 34070.14 | 34070.14 | Justin Gregoris | K-Line | 01-Feb-22 | 30-Apr-23 | 01-Feb-22 | 29-Apr-22 | 29-Apr-22 | Contractor | Contractor |  | 0
453710 | 453710 - ROGERS - HE2019-003 | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane | 07-Oct-19 |  |  | 6406.98 | 3497.05 | 6406.98 | 6406.98 | Macdonald, Larry | N/A | 04-Nov-19 | 12-Oct-21 | 04-Nov-19 | 07-Nov-19 | 07-Nov-19 | Filler | Filler |  | 0
633680 | 633680 - BONDING REQUEST LOCATED ON P54405, WESTON ROAD SOUTH OF HWY 7 | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane |  |  |  | 0 | 711.62 |  | 0 | Persaud, Ryan |  |  | 15-Jul-21 |  | 15-Nov-19 | 15-Nov-19 | xBy-passed | xBy-passed
633703 | 633703 - POLE RELOCATION BLOCK 3- ARNOLD | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Alarcon, Alejandro | 23-Apr-21 |  |  | 224485.77 | 232783.02 | 224485.77 | 224485.77 | Dave Lindsay | Transpw | 03-Aug-21 | 05-Jan-22 | 10-Jun-21 | 27-May-21 | 15-Jul-21 |  | Customer |  | 0
634107 | 634107 - 435 CITYVIEW BLVD / ICI PADMOUNT TX INSTALLATION | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Mann, Drew | 21-Jan-20 |  |  | 85305.11 | 0 | 85305.11 | 85305.11 | Persaud, Ryan |  |  | 22-Sep-22 | [6 empty] | 0
634021 | 634021 - ICI NEW COMMERCIAL SERVICE/ 1 PINE VALLEY DR | 815 - Addiscott | 101791 | Active | 96 | ANALYZE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 02-Nov-20 |  |  | 71214.73 | 63834.16 | 71214.73 | 71214.73 | Dave Lindsay | Somervl | 19-Jan-21 | 26-Jul-23 | 15-Dec-20 | 01-Feb-22 | 09-Mar-23 | Customer | Customer |  | 0
633955 | 633955 - ICI PADMOUNT TX INSTALLATION/134 FIRST COMMERCE DR | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 08-Oct-19
633585 | 633585 - GREEN LANE - #1 | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2021 | Dibratto, Susan | Dibratto, Susan |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 05-Jan-22
634467 | 634467 - 24 LANSDOWNE AVE | 815 - Addiscott | 101761 | Active | 98 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan | 13-Jul-22 |  |  | 33564.51 | 25622.37 | 33564.51 | 33564.51 | Kristine Gordon |  | 21-Sep-22 | 26-Jul-23 | 19-Sep-22 | 19-Oct-22 | 27-Oct-22 | Locates | Locates |  | 0
634501 | 634501 - 381 BRADWICK DR / ICI VAULT TX UPGRADE | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 05-Jul-22
634568 | 634568 - POLE REPLACEMENT 2020 - REPLACE HP AT CREDISTONE RD, VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-May-22
634569 | 634569 - POLE REPLACEMENT 2020 - REPLACE P43255 AT 8000 KEELE ST, VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-May-22
634571 | 634571 - POLE REPLACEMENT 2020 - REPLACE P52314 AT 7777 KIPLING AVE, VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-May-22
634523 | 20-30 WELDRICK ROAD WEST / INSPECT & CONNECT | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 21-Nov-19
634545 | 634545 - AURORA MILLS SUBD RES EDS | 815 - Addiscott | 101896 | Active | 93 | COMPLETE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir | 17-Apr-23 |  |  | 405973.14 | 416275.89 | 405973.14 | 405973.14 | Dave Lindsay | Transpw | 09-Jun-23 | 09-Aug-23 | 29-May-23 | 30-May-23 | 22-Jun-23 |  |  |  | 0
634450 | C4-22 - 58 SKY HARBOUR DR - 27.6KV 800KVA | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2022 | Rao, Gaurav | Bojanic, Dusan | 08-Oct-20 |  |  | 175253.01 | 221676.8 | 175253.01 | 175253.01 | Simon Evason | Transpw | 14-Dec-21 | 26-Jul-23 | 14-Dec-21 | 02-Dec-21 | 24-Jan-22 | Customer | Customer |  | 0
634457 | G3-90 - 188 QUEEN ST E - 400A 347/600V | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2023 | Rao, Gaurav | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 11-Nov-19
635159 | 635159 - MTO- 407 AND YORK DURHAM LINE - POLE REPLACEMENTS - MARKHAM | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 24-Sep-20 |  |  | 93617.85 | 102802.97 | 75617.85 | 93617.85 | Morrow, Joe |  | 03-Dec-20 | 16-Mar-21 | 23-Nov-20 | 04-Dec-20 | 07-Jan-21 | Lines |  |  | 18,000.00
636142 | 2021 POLE REPLACEMENTS- MARKHAM - P52024,P52021,P52020 | 815 - Addiscott | 100867 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 2245.57 |  | 0 | Wong, Henry |  |  | 26-Jul-23
636143 | 636143 - 2021 POLE REPLACEMENTS- MARKHAM - HIGHWAY 7 CROSSING- MTO | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 20-Jan-21 |  |  | 34803.44 | 30893.47 | 34803.44 | 34803.44 | Macdonald, Larry |  | 08-Apr-21 | 04-Jul-21 | 06-Apr-21 | 17-Mar-21 | 17-Mar-21 |  |  |  | 0
636155 | 636155 - ICI NEW CONDO / 7820 BAYVIEW AVE | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 16-Mar-22 |  |  | 155712.82 | 15466.81 | 155712.82 | 155712.82 | Dave Lindsay | Somervl | 10-Jun-22 | 21-Aug-23 | 03-May-22 |  |  | Customer | Customer |  | 0
636149 | RER - MX - RELOC - RUTHERFORD RD - BARRIE LINE (1902) - ADDITIONAL COSTS | 815 - Addiscott | 150591 | Active | 70 | ACTIVE |  |  | 2023 | Khuu, Philander | Grahovac, John |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636207 | 2 LANSDOWNE AVE / ICI PAD TX INSTALLATION | 815 - Addiscott | 101791 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636242 | ICI SERVICE UPGRADE/ 12 BOND CRES | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Dibratto, Susan | Diefenbaker, Trevor A |  |  |  | 0 | 985.07 |  | 0 | Wong, Henry
636257 | ICI NEW TOWNHOUSE CONDOS/ 1 DIAMONDWOOD ROAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 5860.67 |  | 0 | Wong, Henry |  |  | 10-May-23
636258 | 636258 - CARVAL HOMES MAPLE GROVE DEVELOPMENT / I&C WO | 815 - Addiscott | 101887 | Active | 82 | H8 |  |  | 2023 | Penner, Mitchell | Swales, Mathew | 16-Aug-21 |  |  | 152683.56 | 23915.04 | 152683.56 | 152683.56 | Dave Lindsay | Transpw | 26-Oct-21 | 03-Aug-23 | 01-Oct-21 |  |  | Customer | Customer |  | 0
636271 | 636271 - BERCZY GLEN PHASE 1 - ROMAN PROPERTY / I&C WO | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 11-Jun-21 |  |  | 100623.51 | 932265.8 | 100623.51 | 100623.51 | Dave Lindsay |  | 30-Aug-21 | 07-Feb-22 | 28-Jul-21 | 13-Oct-21 | 08-Dec-21 | Customer | Customer |  | 0
636273 | 636273 - BERCZY GLEN PHASE 1 - RINAS PROPERTY / I&C WO | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 11-Jun-21 |  |  | 46054.78 | 268307.39 | 46054.78 | 46054.78 | Dave Lindsay |  | 31-Aug-21 | 11-Jan-22 | 28-Jul-21 | 23-Aug-21 | 08-Dec-21 | Customer | Customer |  | 0
636602 | 636602 - STORM HARDENING - HUNTINGTON - RUTHERFORD TO LANGSTAFF - VAUGHAN | 815 - Addiscott | 103659 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 02-Nov-20 |  |  | 977426.7 | 364389.42 | 657284.08 | 977426.7 | Macdonald, Steve | K-Line | 18-Jun-21 | 01-May-22 | 29-Mar-21 | 17-May-21 | 29-May-21 | Materials | N/A |  | 320,142.62
636604 | 636604 - STORM HARDENING - HWY 27 - MAJOR MACKENZIE TO RUTHERFORD - VAUGHAN | 815 - Addiscott | 103659 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Roy, James |  |  |  | 728197.05 | ($4,415.05) | 728197.05 | 728197.05 | Wong, Henry | K-Line |  | 02-May-22 | [6 empty] | 0
636605 | 636605 - STORM HARDENING - HWY 7 - COCHRANE DR TO LESLIE ST - MARKHAM | 815 - Addiscott | 103659 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 08-Jun-21 |  |  | 214480.89 | 241748.17 | 214480.89 | 214480.89 | Macdonald, Steve | K-Line | 12-Nov-21 | 26-Jul-23 | 25-Oct-21 | 12-Oct-21 | 03-Dec-21 |  | Contractor |  | 0
636606 | 636606 - STORM HARDENING - CENTRE ST - HWY 7 TO GREENWOOD TS - MARKHAM | 815 - Addiscott | 103659 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 18-Nov-20 |  |  | 121621.12 | 169516.25 | 80270.7 | 121621.12 | Ryan Walsh |  | 12-Apr-21 | 05-Aug-21 | 05-Apr-21 | 10-Feb-21 | 11-May-21 |  |  |  | 41,350.42
636653 | 636653 - 2023 CABLE INJECTION - M25 - 14TH-MCCOWAN-STEELES-OLD KENNEDY | 815 - Addiscott | 151363 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 |  |  | 957069.6 | 698313.85 | 957069.6 | 957069.6 | Horlings, Jake | Nvinium | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 23-Feb-23 |  |  |  |  | 0
636654 | 636654 - 2023 CABLE INJECTION, M39 - 16TH-WARDEN-HWY 7-WOODBINE | 815 - Addiscott | 151362 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 |  |  | 1061163.62 | 54775.46 | 1061163.62 | 1061163.62 | Horlings, Jake | Nvinium | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 01-Jan-23 |  |  |  |  | 0
636655 | 636655 - 2021 CABLE INJECTION/M45 - HWY 7 AND WOODBINE | 815 - Addiscott | 151346 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James | 03-Nov-20 |  |  | 346855.99 | 11341 | 346855.99 | 346855.99 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 01-Jan-21 |  |  | Contractor |  | 0
636656 | 636656 - 2021 CABLE INJECTION, M51 - 14TH-BAYVIEW-STEELES-YONGE | 815 - Addiscott | 151345 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 03-Nov-20 |  |  | 262709.51 | 175924.49 | 262709.51 | 262709.51 | Horlings, Jake | Nvinium | 31-Dec-21 | 22-Sep-22 | 01-Jan-21 | 26-Jan-21 | 19-Nov-21 | Contractor |  |  | 0
636657 | 636657 - 2021 CABLE INJECTION/R16 - MAJOR MACK-BAYVIEW-16TH-YONGE | 815 - Addiscott | 151344 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James | 03-Nov-20 |  |  | 471468.23 | 2358.96 | 471468.23 | 471468.23 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 01-Jan-21 |  |  | Contractor |  | 0
636658 | 636658 - 2021 CABLE INJECTION/V40 - TESTON-WESTON-MAJOR MACK-PINE VALLEY | 815 - Addiscott | 151347 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James | 03-Nov-20 |  |  | 274218.78 | 242417.09 | 274218.78 | 274218.78 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 21-Feb-21 |  | Contractor | Contractor |  | 0
636659 | 2024 CABLE INJECTION, V50 - HWY 7-KIPLING-STEELES-HWY 27 | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 5658.83 |  | 0 | Wong, Henry |  |  | 07-Apr-22
636660 | 636660 - 2023 UG CABLE REPLACEMENT - V51 - HWY 7 - RAINBOW DR - IMPALA CRES | 815 - Addiscott | 151912 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 10-Apr-23 |  |  | 949901.7 | 151385.5 | 932089.82 | 949901.7 | Horlings, Jake | Transpw | 18-Jul-23 | 08-Aug-23 | 29-Jun-23 | 21-Jun-23 |  | Contractor |  |  | 17,811.88
636662 | 636662 - 2023 UG CABLE REPLACEMENT - V41, STEPHANIE BLVD | 815 - Addiscott | 151912 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 19-Jun-23 |  |  | 2675031.62 | 80367.96 | 2675031.62 | 2675031.62 | Horlings, Jake | Transpw | 22-Dec-23 | 22-Dec-23 | 06-Sep-23 | [5 empty] | 0
636663 | 636663 - 2021 UG CABLE REPLACEMENT - V44, WALLACE, FAIRGROUND, PARK, WAKELIN, YELLOW PINE | 815 - Addiscott | 151326 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 30-Mar-21 |  |  | 729422.31 | 765153.17 | 822878.31 | 729422.31 | Horlings, Jake | Transpw | 10-Aug-21 | 25-Apr-22 | 12-May-21 | 27-Apr-21 | 10-Sep-21 |  | Contractor |  | -93,456.00
636767 | 2023 BARRIE TS FEEDER EGRESS RELOCATIONS | 825 - Patterson | 150259 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636779 | 2021 8TH LINE BRADFORD UG CABLE REPLACEMENT - CANCELLED | 825 - Patterson | 101781 | Active | 10 | ACTIVE |  |  | 2023 | Bowman, Todd J | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636780 | 636780 - 2021 DUNLOP BARRIE UG CABLE REPLACEMENT | 825 - Patterson | 151334 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 04-Jun-21 |  |  | 797484.5 | 1078858.17 | 797484.5 | 797484.5 | Dan Kish | Transpw | 03-Dec-21 | 22-Sep-22 | 19-Jul-21 | 09-Oct-21 | 05-Dec-21 | Contractor |  |  | 0
636801 | 636801 - 2021 VAULT LID RENEWAL PROGRAM - V18 - 145 DUNLOP ST E | 825 - Patterson | 151526 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 28-Jun-21 |  |  | 164770.16 | 164093.61 | 164770.16 | 164770.16 | Lotto, Jay | HapAmp | 01-Dec-21 | 09-Aug-22 | 05-Nov-21 | 07-Sep-21 | 23-Sep-21 |  |  |  | 0
636802 | 636802 - 2021 VAULT LID RENEWAL PROGRAM - V13 - 49 HIGH ST | 825 - Patterson | 151526 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 19-Aug-21 |  |  | 152462.13 | 172754.08 | 152462.13 | 152462.13 | Lotto, Jay | HapAmp | 22-Dec-21 | 25-Apr-22 | 05-Nov-21 | 06-Oct-21 | 22-Oct-21 |  |  |  | 0
636804 | 636804 - 2021 VAULT LID RENEWAL PROGRAM - V49 - MAPLE AVE | 825 - Patterson | 151526 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 29-Jul-21 |  |  | 102833.48 | 60726.45 | 102833.48 | 102833.48 | Lotto, Jay | HapAmp | 22-Dec-21 | 25-Apr-22 | 05-Nov-21 | 04-Oct-21 | 03-Nov-21 |  |  |  | 0
636809 | 16 MAIN ST UNIONVILLE - YORK UNI MARKHAM CENTRE CAMPUS / ICI CUSTOMER-OWNED SUB | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
454268 | 454268 - 175 ENGELHARD DR - PARK SERV/175 ENGELHARD DR - PARK SERV | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 22-Mar-22 |  |  | 84631.34 | 84094.17 | 84631.34 | 84631.34 | Dave Lindsay | Somervl | 03-Jun-22 | 17-Jul-23 | 04-May-22 | 21-Jul-22 | 07-Oct-22 | Customer | Customer |  | 0
453115 | 15132-15136 YONGE ST, AURORA/15132-15136 YONGE ST, AURORA | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Cranley, Stephen |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636849 | ICI PADMOUNT TX INSTALLATION/37 JOHNSON ST | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 07-Jun-23 |  |  | 36766.88 | 10132.22 | 36766.88 | 36766.88 | Lotto, Jay | HapAmp | 27-Sep-23 | 27-Sep-23 | 18-Sep-23 | [5 empty] | 0
636850 | 636850 - ICI PADMOUNT TX INSTALLATION/200 DISSETTE ST | 825 - Patterson | 101919 | Active | 84 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 26-Jan-21 |  |  | 67330.49 | 52009.44 | 67330.49 | 67330.49 | Lotto, Jay | HapAmp | 07-Apr-21 | 04-Aug-23 | 10-Mar-21 | 31-May-21 |  | Customer | Customer |  | 0
636852 | ICI PADMOUNT TX INSTALLATION/55 DUNLOP ST W | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636861 | 636861 - 700 MAPLEVIEW DRIVE - BLOCK 6 EAST/INSPECT AND CONNECT | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 12-Jan-21 |  |  | 373504.76 | 361186.62 | 373504.76 | 373504.76 | Lotto, Jay | Transpw | 25-Mar-21 | 08-Feb-22 | 26-Feb-21 | 16-Jun-21 | 14-Dec-21 | Customer | Customer |  | 0
636863 | 636863 - 700 MAPLEVIEW DRIVE - BLOCK 8/INSPECT AND CONNECT | 825 - Patterson | 101887 | Active | 98 | COMPLETE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 12-Jan-21 |  |  | 265373.3 | 261204.73 | 265373.3 | 265373.3 | Lotto, Jay | Transpw | 19-Dec-22 | 26-Jul-23 | 18-Nov-22 | 13-Aug-22 | 04-Oct-22 |  |  |  | 0
636872 | 636872 - AMBER MS F2 FEEDER CONVERSION | 815 - Addiscott | 151484 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 01-Dec-20 |  |  | 735554.01 | 749194.89 | 591910.82 | 735554.01 | Ryan Walsh | Somervl | 02-Jul-21 | 20-Sep-21 | 03-May-21 | 24-Feb-21 | 11-May-21 |  |  |  | 143,643.19
636895 | 636895 - PRATO ESTATES - AURORA 2B / I&C WO | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 11-Jan-21 |  |  | 19907.53 | 115059.3 | 19907.53 | 19907.53 | Dave Lindsay |  | 26-Feb-21 | 11-Jan-22 | 23-Feb-21 | 27-Jul-21 | 11-Nov-21 | Customer | Customer |  | 0
636919 | 7551 HUNTINGTON RD / ICI CO-SUBSTATION INSTALLATION | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636922 | 636922 - JOINT USE HE2020-037- SUNNIDALE RD.- FERNDALE DR. TO ANNE ST. | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 15-Nov-21 |  |  | 15495.42 | 16265.22 | 15495.42 | 15495.42 | Steve Rumble |  | 15-Dec-21 | 29-Mar-22 | 13-Dec-21 | 14-Dec-21 | 14-Dec-21 | Lines |  |  | 0
636949 | 636949 - DUCT INSTALLATION 9075 9085 JANE ST | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Graham, Bruce W. | 19-Feb-21 |  |  | 3167.38 | 2341.5 | 3167.38 | 3167.38 | Shane Christopher |  | 06-Apr-21 | 01-Nov-21 | 06-Apr-21 | 17-Jun-21 | 17-Jun-21 | Customer | Customer |  | 0
636961 | 636961 - HYDRO POLE RELOCATION AT YONGE STREET & TYLER STREET IN AURORA | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Watters, Maxwell | 18-Jun-21 |  |  | 489695.76 | 466688.87 | 489695.76 | 489695.76 | Shane Christopher | Transpw | 20-Aug-21 | 22-Sep-22 | 30-Jul-21 | 10-Aug-21 | 25-Oct-21 | Contractor | Contractor |  | 0
636970 | 636970 - ANGLIN SUBDIVISION / I&C WO | 815 - Addiscott | 101887 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Sabbah, Amir | 08-Jul-22 |  |  | 114263.04 | 32713.13 | 114263.04 | 114263.04 | Dave Lindsay |  | 16-Sep-22 | 26-Jul-23 | 19-Aug-22 | 19-Jul-22 | 07-Oct-22 |  | Customer |  | 0
636990 | 636990 - BADGER DEVELOPEMENT - INDUSTRIAL SUBDIVISION | 815 - Addiscott | 101896 | Active | 98 | ANALYZE |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 20-Oct-21 |  |  | 864937.57 | 804256.14 | 864937.57 | 864937.57 | Dave Lindsay |  | 06-Jan-22 | 26-Jul-23 | 07-Dec-21 |  | 01-Mar-23 | Customer | Customer |  | 0
636992 | YONGE ST. - #9350 (RESIDENTIAL/RETAIL CONDOS) | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637008 | 2020 POLE REPLACEMENTS BATCH 6 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Bowman, Todd J | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637033 | 637033 - ROAD AUTHORITY RELOCATION-ESSA ROAD AND FAIRVIEW ROAD | 825 - Patterson | 101764 | Active | 99 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 12-May-22 |  |  | 602865.93 | 542181.41 | 595820.53 | 602865.93 | Dan Kish | HapAmp | 07-Sep-22 | 26-Jul-23 | 24-Jun-22 | 21-Jun-22 | 16-Aug-22 |  |  |  | 7,045.40
637052 | 637052 - 40 THOMPSONS ROAD - RES SUBD EDS | 825 - Patterson | 101887 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 14-Jul-21 |  |  | 50149.48 | 67225.62 | 50149.48 | 50149.48 | Lotto, Jay | HapAmp | 23-Sep-22 | 26-Jul-23 | 09-Sep-22 | 13-Jun-22 | 29-Aug-22 |  |  |  | 0
637054 | 637054 - 305 ADDISON HALL CIRCLE - 3 PHASE SERVICE | 815 - Addiscott | 101791 | Active | 95 | ANALYZE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 16-Jul-20 |  |  | 59990.75 | 56891.91 | 59990.75 | 59990.75 | Dave Lindsay | Somervl | 11-Dec-20 | 26-Jul-23 | 23-Nov-20 | 22-Jun-22 | 09-Mar-23 | Customer | Customer |  | 0
637073 | 637073 - JOINT USE HE2020-040- MAIN ST. PENETANGUISHENE | 825 - Patterson | 151495 | Inactive | 99 | CANCELLED |  |  | 2021 | O'Gay, Brian | Martin, Shane | 14-Dec-20 |  |  | 10106.58 | 5425.01 | 10106.58 | 10106.58 | Steve Rumble |  | 26-Jan-21 | 23-Aug-22 | 25-Jan-21 |  | 13-Oct-21 |  |  |  | 0
637074 | DOUGHTON RD. - #216 | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637007 | 637007 - ICI INDUSTRIAL BUILDING/ 27 DIRECTOR COURT | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 29-Jul-21 |  |  | 118111.78 | 120087.48 | 118111.78 | 118111.78 | Dave Lindsay | Somervl | 06-Oct-21 | 09-May-22 | 09-Sep-21 | 03-Nov-21 | 11-Nov-21 | Customer | Customer |  | 0
637056 | 637056 - ICI NEW SERVICE/ 10192 9TH LINE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Joshi, Namrata | Diefenbaker, Trevor A | 27-Nov-20 |  |  | 87145.03 | 71736.03 | 87145.03 | 87145.03 | Dave Lindsay | Somervl | 12-Feb-21 | 21-Apr-22 | 11-Jan-21 | 12-Jul-21 | 08-Oct-21 | Customer | Customer |  | 0
637057 | 637057 - ICI NEW COMMERCIAL SERVICE/ 7896 HUNTINGTON RD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 26-Aug-20 |  |  | 77482.03 | 58121.63 | 77482.03 | 77482.03 | Dave Lindsay | Somervl | 12-Nov-20 | 21-Apr-22 | 02-Nov-20 | 09-Oct-20 | 26-May-21 |  | Customer |  | 0
454199 | 454199 - ICI NEW COMMERCIAL SERVICE/1387 DENISON ST | 815 - Addiscott | 101791 | Active | 84 | H8 |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 15-May-20 |  |  | 59913.26 | 55302.62 | 59913.26 | 59913.26 | Dave Lindsay | Somervl | 31-Jul-20 | 31-Jul-23 | 13-Jul-20 | 15-Jun-20 |  |  | Customer |  | 0
637118 | 2020 POLE REPLACEMENTS BATCH 7 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Bowman, Todd J | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637145 | 637145 - 2022 EMERGING UG, 1330 CASTLEMORE - TRANSFORMER INSTALLATION | 815 - Addiscott | 151450 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 18-Nov-22 | 1 |  | 210853.27 | 20653.12 | 210853.27 | 210853.27 | Dave Lindsay | Somervl | 23-May-23 | 11-Aug-23 | 24-Apr-23 | 15-Jun-23 |  | Contractor |  |  | 0
637153 | 637153 - 430 ESSA ROAD, BARRIE | 825 - Patterson | 101919 | Active | 95 | COMPLETE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 15-Dec-20 |  |  | 62038.82 | 53531.05 | 62038.82 | 62038.82 | Lotto, Jay | HapAmp | 22-Feb-21 | 26-Jul-23 | 01-Feb-21 | 01-Feb-21 | 07-Feb-22 |  | Customer |  | 0
637186 | 637186 - 14452 YONGE ST/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 08-Jul-22 |  |  | 127829.62 | 76371.85 | 127829.62 | 127829.62 | Dave Lindsay | Somervl | 23-Sep-22 | 10-Aug-23 | 19-Aug-22 | 03-Feb-23 |  | Customer | Customer |  | 0
637194 | 637194 - LEAKING 3PH PADMOUNT TX REPLACEMENT AT 53 BAYFIELD ST. - BARRIE | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 19-May-22 | 1 | 1 | 82891.21 | 103700.93 | 82891.21 | 82891.21 | Lotto, Jay | HapAmp | 18-Jul-22 | 22-Sep-22 | 01-Jul-22 | 12-Jun-22 | 12-Jun-22 |  |  |  | 0
637204 | PARENT W.O FOR INSPECT/CONNECT/I&C - NASHVILLE HEIGHTS - MEDIUM DENSITY BLOCK | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 07-Dec-21 |  |  | 299943.32 | 297123.02 | 299943.32 | 299943.32 | Dave Lindsay |  | 07-Dec-21 | 11-Jan-22 | 07-Dec-21 | 07-Dec-21 | 07-Dec-21 | xBy-passed |  |  | 0
637206 | 637206 - MAPLE PARK HOMES SUBDIVISION | 815 - Addiscott | 101887 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Swales, Mathew | 26-Jul-21 |  |  | 145541.8 | 139684.06 | 145541.8 | 145541.8 | Dave Lindsay | Transpw | 12-Oct-21 | 26-Jul-23 | 09-Sep-21 | 13-Aug-22 | 07-Oct-22 | Customer | Customer |  | 0
637208 | 637208 - CLINTON DRIVE EXTENSION / I&C WO | 815 - Addiscott | 101887 | Active | 91 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir | 11-Aug-22 |  |  | 114934.22 | 99676.7 | 114934.22 | 114934.22 | Dave Lindsay | Transpw | 19-Oct-22 | 01-Aug-23 | 26-Sep-22 | 01-Nov-22 |  | Customer |  |  | 0
637281 | 637281 - 2901 RUTHERFORD RD / ICI NEW C.O.-SUBSTATION | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Joshi, Namrata | Mann, Drew | 10-Nov-21 |  |  | 69715.78 | 19094.17 | 69715.78 | 69715.78 | Dave Lindsay | Somervl | 16-Aug-22 | 26-Jul-23 | 01-Aug-22 |  |  | Customer | Customer |  | 0
637282 | 637282 - JOINT USE HE2020-046- RIVERMEDE RD.- KEELE ST. TO RAYETTE DR. | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 22-Jan-21 |  |  | 16977.34 | 7507.92 | 16977.34 | 16977.34 | Macdonald, Larry |  | 02-Mar-21 | 21-Aug-22 | 01-Mar-21 | 17-Mar-21 | 17-Mar-21 |  |  |  | 0
637321 | 637321 - PENNON RD. - #43 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 14-Jul-20 |  |  | 40521.45 | 26674.94 | 40521.45 | 40521.45 | Dave Lindsay | Somervl | 18-Sep-20 | 09-Dec-21 | 08-Sep-20 | 08-Jan-21 | 26-May-21 | Customer | Customer |  | 0
637324 | 637324 - 150 ADDISON HALL CIRCLE/AUR/NS/3 PHASE PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 10-Aug-20 |  |  | 67756.8 | 54695.41 | 67756.8 | 67756.8 | Dave Lindsay | Somervl | 23-Oct-20 | 06-Apr-22 | 05-Oct-20 | 27-Oct-21 | 11-Nov-21 | Customer | Customer |  | 0
637375 | 637375 - 700 MAPLEVIEW DRIVE - PHASE 2 - SUBD RES EDS | 825 - Patterson | 101887 | Active | 96 | COMPLETE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 12-Jan-21 |  |  | 331581.66 | 335833.29 | 331581.66 | 331581.66 | Lotto, Jay | Transpw | 16-Mar-21 | 26-Jul-23 | 26-Feb-21 | 15-Jun-21 | 22-Mar-22 | Customer | Customer |  | 0
637378 | 637378 - 700 MAPLEVIEW DRIVE - BLOCK 17 - SUBD RES EDS | 825 - Patterson | 101887 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 12-Jan-21 |  |  | 448770.72 | 429715.09 | 448770.72 | 448770.72 | Lotto, Jay | Transpw | 06-Apr-21 | 26-Jul-23 | 26-Feb-21 | 11-Nov-21 | 22-Mar-22 | Customer | Customer |  | 0
637387 | 637387 - WOODEND PLACE DEVELOPMENT (PHASE) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 99 | ANALYZE |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 10-Aug-22 |  |  | 475512.8 | 440208.71 | 475512.8 | 475512.8 | Dave Lindsay |  | 28-Oct-22 | 26-Jul-23 | 28-Sep-22 | 24-Aug-22 | 01-Mar-23 |  |  |  | 0
637429 | 637429 - 100 LINE DRIVE/ VAU/ NS/ CUSTOMER-OWNED STATION | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 02-Feb-21 |  |  | 12508.14 | 7308.14 | 12508.14 | 12508.14 | Dave Lindsay |  | 31-Aug-21 | 28-Jul-23 | 27-Aug-21 |  |  | Customer | Customer |  | 0
637455 | 637455 - 5440 16TH AVE / MAR / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 27-Nov-20 |  |  | 77027.38 | 69102.45 | 54677.38 | 54677.38 | Dave Lindsay | Somervl | 11-Feb-21 | 30-Mar-22 | 11-Jan-21 | 01-Sep-21 | 11-Nov-21 | Customer | Customer |  | 0
637427 | CUSTOMER EMERGING PROJECT - CARVAL HOMES MAPLE GROVE DEVELOPMENT - POLE UPGRADE | 815 - Addiscott | 151531 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637473 | 49 COLLIER ST / BAR / NS / 3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 12-Nov-21
637478 | BAY MOORINGS SUBD - POLE UPGRADES | 825 - Patterson | 151531 | Active | 99 | ANALYZE |  |  | 2023 | Penner, Mitchell | Perks, Dan | 01-Feb-23 |  |  | 52843.07 | 20736.52 | 52843.07 | 52843.07 | Lotto, Jay |  | 31-Jan-23 | 26-Jul-23 | 31-Jan-23 | 01-Feb-23 | 01-Feb-23 | xBy-passed |  |  | 0
637481 | 74 BOND CRESCENT DEVELOPMENT (PHASE) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 30-May-23 |  |  | 99518.65 | 84897.22 | 99518.65 | 99518.65 | Dave Lindsay | Transpw | 25-Sep-23 | 25-Sep-23 | 18-Sep-23 | [5 empty] | 0
637495 | 637495 - UNION VILLAGE - (PHASE 1C) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 82 | H8 |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 07-Jun-21 |  |  | 43058.33 | 26362.69 | 43058.33 | 43058.33 | Dave Lindsay |  | 24-Aug-21 | 10-Aug-23 | 03-Aug-21 |  |  | Customer | Customer |  | 0
637508 | 637508 - 300 EARL STEWART DR/AURORA/NS/3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 02-Jul-21 |  |  | 66901.8 | 82367.49 | 66901.8 | 66901.8 | Dave Lindsay | Somervl | 21-Sep-21 | 24-Aug-22 | 17-Aug-21 | 10-Aug-21 | 11-Feb-22 |  | Customer |  | 0
637522 | 75 MELBOURNE ST / BRAD / SR / 1 PH PAD | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637524 | 637524 - 9560 ISLINGTON AVE / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 20-Jan-21 |  |  | 105494.27 | 96143.92 | 105494.27 | 105494.27 | Dave Lindsay | Somervl | 29-Mar-21 | 26-Jul-23 | 01-Mar-21 | 21-Jun-21 | 15-Sep-21 | Customer | Customer |  | 0
637531 | 637531 - 21 AND 31 PERFORMANCE DR/RHL/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 95 | COMPLETE |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A | 03-Nov-20 |  |  | 109448.55 | 136325.39 | 109448.55 | 109448.55 | Dave Lindsay | Somervl | 05-Jan-21 | 28-Jul-23 | 16-Dec-20 | 21-Oct-22 | 08-Dec-22 | Customer | Customer |  | 0
637543 | 637543 - 77 MELBOURNE ST / BRAD / NS / 3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 19-Feb-21 |  |  | 52174.44 | 60860.44 | 52174.44 | 52174.44 | Lotto, Jay | HapAmp | 29-Apr-21 | 19-Jul-21 | 06-Apr-21 | 11-Mar-21 | 18-Mar-21 |  |  |  | 0
637544 | 637544 - 571 WELHAM RD / BAR / NS / NEW CUSTOMER OWNED STN | 825 - Patterson | 101919 | Active | 84 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 18-Aug-21 |  |  | 67345.71 | 73372.37 | 67345.71 | 67345.71 | Lotto, Jay |  | 14-Oct-23 | 03-Aug-23 | 01-Oct-23 | 03-Nov-21 |  | Customer | Customer |  | 0
637555 | 33 DICKSON HILL ROAD/ MAR/ UP/ 1PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 29-Mar-21
637556 | 637556 - CREDITSTONE RD. - #777 (EXISTING BUILDING) | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 19-Aug-20 |  |  | 84033.39 | 76246.26 | 84033.39 | 84033.39 | Dave Lindsay | Somervl | 27-Nov-20 | 15-Jul-21 | 02-Nov-20 | 30-Oct-20 | 04-Mar-21 |  |  |  | 0
637599 | 637599 - LAWRENCE AVE & PALMER AVE, RICHMOND HILL POLE RELOCATION | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 05-Jul-21 |  |  | 23845.35 | 13053.29 | 23845.35 | 23845.35 | Macdonald, Larry |  | 10-Sep-21 | 22-Sep-22 | 17-Aug-21 | 27-Jul-21 | 27-Jul-21 |  |  |  | 0
637601 | RAKI SOUTH - STAGE 2 (PHASE 2) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637609 | 637609 - 33 COMMERCE VALLEY DR / MAR / UP / CO-STN | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Mann, Drew | 17-Aug-21 |  |  | 43437.88 | 46689.12 | 43437.88 | 43437.88 | Dave Lindsay |  | 13-Oct-21 | 18-Jul-23 | 01-Oct-21 | 13-Nov-21 | 11-Feb-22 | Customer | Customer |  | 0
637641 | 1430518 ONTARIO LTD - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637600 | 637600 - POLE LINE EXPANSION FOR BERCZY GLEN SUBDIVISION | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2021 | Penner, Mitchell | Swales, Mathew | 10-Jun-21 |  |  | 92767.21 | 115034.93 | 92767.21 | 92767.21 | Macdonald, Steve | K-Line | 27-Oct-21 | 08-Jun-22 | 04-Oct-21 | 30-Aug-21 | 10-Sep-21 |  |  |  | 0
637622 | 637622 - MARKLAND TOWNHOUSE DEVELOPMENT / I&C WO | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Swales, Mathew | 21-Feb-22 |  |  | 279602.7 | 273882.77 | 279602.7 | 279602.7 | Dave Lindsay | Transpw | 09-May-22 | 22-Jun-23 | 06-Apr-22 | 27-Jun-22 | 18-Jul-22 | Customer | Customer |  | 0
637657 | MORROW ROAD, BARRIE - REMOVE SECONDARY AND OLD POLES | 825 - Patterson | 101764 | Active | 99 | COMPLETE |  |  | 2022 | Pelleja, Emily | Harrington, James |  |  |  | 0 | 17596.66 |  | 0 | Wong, Henry |  |  | 26-Jul-23
637658 | 637658 - SANDSTORM PHASE 8A - SUBD RES EDS | 825 - Patterson | 101887 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 10-Jun-21 |  |  | 486734.69 | 464781.15 | 486734.69 | 486734.69 | Lotto, Jay | Transpw | 16-Sep-21 | 26-Jul-23 | 27-Jul-21 | 22-Nov-21 | 08-Mar-22 | Customer | Customer |  | 0
637660 | SANDSTORM PHASE 8B - SUBD RES EDS | 825 - Patterson | 101887 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Handy, James | 12-Jun-23 |  |  | 566766.18 | 93606.82 | 566766.18 | 566766.18 | Lotto, Jay | Transpw | 01-Oct-23 | 01-Sep-23 | 18-Aug-23 | [5 empty] | 0
637668 | 637668 - FAIRTREE BLOCK 153 CONDO BLOCK TOWNHOMES / I&C WO | 815 - Addiscott | 101887 | Active | 98 | COMPLETE |  |  | 2022 | Penner, Mitchell | Swales, Mathew | 10-Aug-21 |  |  | 562083.63 | 564931.26 | 562083.63 | 562083.63 | Dave Lindsay | Transpw | 26-Oct-21 | 26-Jul-23 | 28-Sep-21 | 29-Nov-21 | 05-May-22 | Customer | Customer |  | 0
637680 | 637680 - CUSTOMER CAPITAL PROJECT FOR MAPLE PARK HOMES SUBDIVISION - POLE UPGRADES | 815 - Addiscott | 151531 | Active | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 21-Jul-21 |  |  | 20396.25 | 14986.22 | 20396.25 | 20396.25 | Macdonald, Larry |  | 10-Sep-21 | 26-Jul-23 | 07-Sep-21 | 16-Sep-21 | 16-Sep-21 |  | Filler |  | 0
637707 | 637707 - JOINT USE HE2020-053 | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 14-Apr-21 |  |  | 9801.35 | 7215.94 | 9801.35 | 9801.35 | Don Rothman |  | 07-May-21 | 21-Aug-22 | 07-May-21 | 21-Apr-21 | 21-Apr-21 |  |  |  | 0
637729 | 637729 - JOINT USE PERMIT HE2020-054 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 16-Sep-21 |  |  | 22346.6 | 16867.07 | 22346.6 | 22346.6 | Reginald Clarke |  | 01-Nov-21 | 26-Jul-23 | 01-Nov-21 | 27-Oct-21 | 27-Oct-21 |  |  |  | 0
637732 | 637732 - 99 GREAT GULF DR / VAU / NS / 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 22-Sep-20 |  |  | 57832.7 | 57112.27 | 57832.7 | 57832.7 | Dave Lindsay | Somervl | 20-Nov-20 | 12-Jul-21 | 06-Nov-20 | 19-Mar-21 | 27-Apr-21 | Customer | Customer |  | 0
637733 | 637733 - YONGE ST. - #13042, RES/RETAIL CONDO | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 18-May-21 |  |  | 33742.4 | 12295.97 | 33742.4 | 33742.4 | Reginald Clarke |  | 06-Dec-23 | 06-Dec-23 | 04-Dec-23 |  |  | Customer | Customer |  | 0
637741 | 637741 - CLEGG RD. - #105/MAR/NS/CUSTOMER-OWN SUBSTATION | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 28-Mar-23 |  |  | 313020.78 | 138690.38 | 313020.78 | 313020.78 | Dave Lindsay | Somervl | 29-Jun-23 | 05-Sep-23 | 09-May-23 | 09-May-23 |  |  |  |  | 0
637749 | 637749 - HONEYFIELD BLK 395 - SUBD RES EDS | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 26-Jan-21 |  |  | 297019.3 | 257218.02 | 297019.3 | 297019.3 | Lotto, Jay |  | 08-Apr-21 | 11-Nov-21 | 10-Mar-21 | 13-Apr-21 | 31-May-21 | Customer | Customer |  | 0
637751 | 9773 KEELE STREET SUBDIVISION / I&C WO | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637846 | 637846 - 95 & 105 ONEIDA CRES / RHL / 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 26-Oct-20 |  |  | 82559.03 | 83134.19 | 82559.03 | 82559.03 | Dave Lindsay |  | 14-Dec-20 | 25-Apr-22 | 07-Dec-20 | 10-Feb-22 | 10-Feb-22 | Customer | Customer |  | 0
637879 | JEFFERSON CONDO BLOCK DEVELOPEMENT (PHASE) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637894 | 637894 - 6 DAVID EYER ROAD/ RHL/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 93 | ANALYZE |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 01-Sep-21 |  |  | 100291.79 | 142894.66 | 100291.79 | 100291.79 | Dave Lindsay | Somervl | 09-Nov-21 | 26-Jul-23 | 13-Oct-21 | 15-May-23 | 13-Jun-23 | Customer | Customer |  | 0
637895 | 637895 - 8025 JANE ST/ VAU/ NS00055586/ CUSTOMER-OWNED STATION | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 01-Mar-21 |  |  | 120304.23 | 110358.07 | 120304.23 | 120304.23 | Dave Lindsay | Somervl | 01-Jun-21 | 21-Apr-22 | 12-Apr-21 | 31-Mar-21 | 21-Jul-21 |  | Customer |  | 0
637900 | 637900 - 50 KEYES CRT / VAU / NS / 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 21-Sep-20 |  |  | 68817.18 | 67717.51 | 68817.18 | 68817.18 | Dave Lindsay | Somervl | 04-Dec-20 | 15-Jul-21 | 19-Nov-20 | 29-Oct-20 | 27-Apr-21 |  | Customer |  | 0
637910 | 637910 - KEYES CRT. - #51 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 17-Sep-20 |  |  | 99549.8 | 82058.28 | 99549.8 | 99549.8 | Dave Lindsay | Somervl | 29-Jan-21 | 21-Apr-22 | 11-Jan-21 | 29-Oct-20 | 22-Mar-21 |  | Customer |  | 0
632891 | 632891 - 9135 BATHURST ST / ICI PADMOUNT TX INSTALLATION | 815 - Addiscott | 101791 | Active | 99 | ANALYZE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 07-Aug-20 |  |  | 101056.63 | 89982.34 | 101056.63 | 101056.63 | Dave Lindsay | Somervl | 30-Oct-20 | 26-Jul-23 | 05-Oct-20 | 18-Sep-20 | 09-Mar-23 |  | Customer |  | 0
637972 | 637972 - 170 BURTON AVE/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 01-Dec-20 |  |  | 41106.46 | 56284.07 | 41106.46 | 41106.46 | Lotto, Jay | HapAmp | 23-Feb-21 | 06-Apr-22 | 02-Feb-21 | 04-Jan-21 | 30-Apr-21 |  | Customer |  | 0
637943 | 637943 - YONGE AND SILVER MAPLE/ RHL/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 19-Feb-21 |  |  | 82104.93 | 62718.06 | 82104.93 | 82104.93 | Dave Lindsay | Somervl | 04-May-21 | 04-Oct-21 | 06-Apr-21 | 26-Feb-21 | 22-Mar-21 |  |  |  | 0
633682 | PADMOUNT NORTH BATCH 1 - BARRIE | 825 - Patterson |  | Inactive | 99 | CANCELLED |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
633681 | BONDING REQUEST LOCATED ON P54172, HWY 7 | 815 - Addiscott | 101763 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Martin, Shane |  |  |  | 0 | 894.63 |  | 0 | Don Rothman |  |  | 15-Jul-21 |  | 29-Nov-19 | 29-Nov-19 | xBy-passed | xBy-passed
632895 | PARENT W.O. FOR INSPECT/CONNE/I&C - 4038 HWY 7 | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
632886 | STEGMANS MILL RD. - #357 TO #375 | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2021 | Dibratto, Susan | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 29-Mar-21
632864 | RELOCATION DESIGN FOR FUTURE DEVELOPMENT | 825 - Patterson | 101761 | Inactive | 99 | CANCELLED |  |  | 2021 | Bowman, Todd J | Pollock, Kim |  |  |  | 6949.22 | 701.82 | 6949.22 | 6949.22 | Wong, Henry |  |  | 29-Aug-22 | [6 empty] | 0
632843 | 632843 - 2021 Distribution Automation - DUCKWORTH & CUNDLES 44KV AUTOMATED LIS TIE SWITCH | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Bowman, Todd J | Walters, Geoffrey D | 22-Dec-20 |  |  | 102794.32 | 175634.04 | 102794.32 | 102794.32 | Dan Kish | K-Line | 28-Sep-21 | 14-Feb-22 | 07-Sep-21 | 25-Sep-21 | 15-Oct-21 | Filler | Filler |  | 0
632362 | 17 CENTRE STREET RELOCATION | 825 - Patterson | 100867 | Inactive | 99 | CANCELLED |  |  | 2022 | Bowman, Todd J | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638007 | JOINT USE PERMIT HE2020-061 | 825 - Patterson | 151495 | Inactive | 99 | CANCELLED |  |  | 2022 | O'Gay, Brian | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 12-Apr-22
632790 | 632790 - NASHVILLE DEVELOPMENTS (BARONS EAST) - SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 20-Jul-21 |  |  | 252597.11 | 246365.44 | 252597.11 | 252597.11 | Dave Lindsay | Transpw | 14-Oct-21 | 05-Jan-22 | 15-Sep-21 | 23-Aug-21 | 11-Nov-21 |  | Customer |  | 0
638082 | 638082 - 1SC39 RTU FEED AT LESLIE AND WEST BEAVER CREEK | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 19-Feb-21 |  |  | 70744.73 | 70082.57 | 82520.73 | 70744.73 | Horlings, Jake | Somervl | 22-Apr-21 | 07-Mar-22 | 06-Apr-21 | 09-Jun-21 | 07-Jul-21 | Contractor | Contractor |  | -11,776.00
638115 | 638115 - 50 ALLIANCE BLVD/BAR/UP/3PH PAD PHASE 2 | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 23-Apr-21 |  |  | 89024.77 | 93097.01 | 89024.77 | 89024.77 | Lotto, Jay |  | 14-Jun-21 | 23-Aug-21 | 04-Jun-21 | 29-May-21 | 29-May-21 |  |  |  | 0
638116 | 638116 - THOMAS COOK AVE. - #2, CARVILLE COMMUNITY CENTRE, LIBRARY AND DISTRICT PARK | 815 - Addiscott | 101791 | Active | 95 | COMPLETE |  |  | 2022 | Joshi, Namrata | Yuen, Paul | 08-Jul-22 |  |  | 90529.99 | 69845.58 | 90529.99 | 90529.99 | Dave Lindsay | Somervl | 16-Sep-22 | 10-Aug-23 | 19-Aug-22 | 13-Oct-22 | 08-Dec-22 | Customer |  |  | 0
638126 | 638126 - 6675 LANGSTAFF RD / VAU / NS / 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 06-Oct-20 |  |  | 136291.3 | 128166.64 | 136291.3 | 136291.3 | Dave Lindsay | Somervl | 28-Dec-20 | 17-May-21 | 11-Dec-20 | 02-Nov-20 | 21-Mar-21 | Customer | Customer |  | 0
638143 | 6805 5TH LINE, TOT,(NS), 3 PHASE PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 07-Jul-23 |  |  | 29685.32 | 11175.41 | 29685.32 | 29685.32 | Lotto, Jay | N/A | 03-Nov-23 | 03-Nov-23 | 30-Oct-23 | [5 empty] | 0
638157 | 638157 - 2022 SUNNIDALE UG CABLE REPLACEMENT PHASE 3 | 825 - Patterson | 151336 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim | 20-Dec-21 |  |  | 1586766.23 | 1715732.8 | 1586766.23 | 1586766.23 | Lotto, Jay | Transpw | 12-Jul-22 | 27-Apr-23 | 01-Apr-22 | 09-May-22 | 23-Aug-22 | Contractor | Contractor |  | 0
638159 | 638159 - BRIAR HILL SUBDIVISION - HILLSIDE - SUBD RES EDS | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 25-Feb-21 |  |  | 256566.06 | 280436.26 | 256566.06 | 256566.06 | Lotto, Jay | Transpw | 07-May-21 | 22-Nov-21 | 08-Apr-21 | 22-Mar-21 | 18-Jun-21 |  | Customer |  | 0
638190 | 638190 - TRANSFORMER REPLACEMENT 2021 - BATCH 5 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 119682.28 | 119972.58 | 119682.28 | 119682.28 | Dave Lindsay | Somervl | 04-May-21 | 26-Jul-23 | 12-Apr-21 | 26-May-21 | 28-Oct-21 | Filler | Filler |  | 0
638189 | 638189 - TRANSFORMER REPLACEMENT 2021 - BATCH 4 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 127433.78 | 142224.77 | 110506.78 | 127433.78 | Dave Lindsay | Somervl | 18-May-21 | 22-Sep-22 | 01-Apr-21 | 01-Jun-21 | 01-Nov-21 | Filler | Filler |  | 16,927.00
638188 | 638188 - TRANSFORMER REPLACEMENT 2021 - BATCH 3 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 152290.86 | 156719.36 | 152290.86 | 152290.86 | Dave Lindsay | Somervl | 05-May-21 | 26-Jul-23 | 22-Mar-21 | 13-Apr-21 | 23-Dec-21 | Filler | Filler |  | 0
638187 | 638187 - TRANSFORMER REPLACEMENT 2021 - BATCH 2 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 43000.95 | 39210.04 | 43000.95 | 43000.95 | Horlings, Jake | Somervl | 24-Mar-21 | 26-Jul-23 | 01-Mar-21 | 03-May-21 | 05-Jun-21 | Filler | Filler |  | 0
638186 | 638186 - TRANSFORMER REPLACEMENT 2021 - BATCH 1 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 277192.09 | 222563.18 | 277192.09 | 277192.09 | Horlings, Jake | Somervl | 05-May-21 | 05-Jan-22 | 01-Mar-21 | 11-Feb-21 | 30-Jun-21 |  | Filler |  | 0
638206 | 638206 - PROJECT RAINBOW SITE 1 | 815 - Addiscott | 152600 | Active | 82 | RELEASED |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander | 05-Jul-23 |  |  | 5265892.91 | 379341.9 | 5265892.91 | 5265892.91 | Macdonald, Steve | K-Line | 29-Dec-23 | 29-Dec-23 | 21-Aug-23 | [5 empty] | 0
638212 | 638212 - GREENRIDGE - SUBD RES EDS | 825 - Patterson | 101887 | Active | 93 | COMPLETE |  |  | 2023 | Penner, Mitchell | Perks, Dan | 07-Oct-22 |  |  | 466523.91 | 476677.74 | 466523.91 | 466523.91 | Lotto, Jay | Transpw | 22-Dec-22 | 09-Aug-23 | 24-Nov-22 | 07-Nov-22 | 05-May-23 | Customer | Customer |  | 0
638217 | 2440 TESTON RD/VAUGHAN/NS 1PH OH TX | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Dibratto, Susan | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638218 | 220 CACHET WOODS CRT / MAR / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638229 | 638229 - TORONTO RV RD. 1PH. TO 3PH CONVERSION | 815 - Addiscott | 101761 | Active | 98 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Barry, Kenneth | 22-Jun-21 |  |  | 154018.12 | 135676.38 | 154018.12 | 154018.12 | Ryan Walsh |  | 14-Sep-21 | 26-Jul-23 | 09-Aug-21 | 06-Jul-21 | 23-Jul-21 |  |  |  | 0
638231 | 638231 - DUFFERIN ST. POLE RELOCATION | 815 - Addiscott | 101762 | Active | 93 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R | 17-Feb-22 |  |  | 287872.98 | 327777.13 | 287872.98 | 287872.98 | Morrow, Joe |  | 24-Jun-22 | 28-Aug-23 | 09-May-22 | 18-Apr-22 | 06-Jun-22 | Materials | N/A |  | 0
638241 | 638241 - 2021 CABLE INJECTION - V34 - KIRBY & JANE, VAUGHAN | 815 - Addiscott | 151357 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 03-Nov-20 |  |  | 111679.08 | 369595.47 | 111679.08 | 111679.08 | Horlings, Jake | Nvinium | 31-Dec-21 | 22-Sep-22 | 01-Jan-21 | 14-Mar-21 | 25-Jan-22 | Contractor | MC/PUCC Permit |  | 0
638240 | 638240 - 2021 CABLE INJECTION - V44 - LANGSTAFF & PINE VALLEY, VAUGHAN | 815 - Addiscott | 151356 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 03-Nov-20 |  |  | 564812.97 | 515970.16 | 564812.97 | 564812.97 | Horlings, Jake | Nvinium | 31-Dec-21 | 22-Sep-22 | 01-Jan-21 | 28-Feb-21 | 31-Dec-21 | Contractor | Contractor |  | 0
638246 | 638246 - 2021 CABLE INJECTION - V25 - MAJOR MACKENZIE & KEELE, VAUGHAN | 815 - Addiscott | 151457 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 03-Nov-20 |  |  | 689232.25 | 915571.41 | 689232.25 | 689232.25 | Horlings, Jake | Nvinium | 31-Dec-21 | 21-Mar-22 | 01-Jan-21 | 17-Jan-21 | 08-Feb-22 | Filler | MC/PUCC Permit |  | 0
638245 | 638245 - 2021 CABLE INJECTION - V02 - BATHURST & ATKINSON, VAUGHAN | 815 - Addiscott | 151365 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 03-Nov-20 |  |  | 555746.07 | 130063.77 | 555746.07 | 555746.07 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 03-Oct-21 |  | Contractor | Contractor |  | 0
638244 | 638244 - 2021 CABLE INJECTION - M16 - MAJOR MACKENZIE & NINTH LINE, MARKHAM | 815 - Addiscott | 151359 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 03-Nov-20 |  |  | 920461.66 | 738689.14 | 920461.66 | 920461.66 | Horlings, Jake | Nvinium | 31-Dec-21 | 02-Mar-23 | 01-Jan-21 | 04-Jul-21 | 05-Dec-21 | Contractor |  |  | 0
638243 | 638243 - 2021 CABLE INJECTION - V62 - KIRBY & HWY 27, VAUGHAN | 815 - Addiscott | 151358 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 03-Nov-20 |  |  | 132448.69 | 3703.62 | 132448.69 | 132448.69 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 01-Jan-21 | 25-Jan-22 | Contractor | MC/PUCC Permit |  | 0
638247 | 638247 - 233 DUNLOP ST W/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 30-Sep-21 |  |  | 72525.15 | 50695.1 | 72525.15 | 72525.15 | Lotto, Jay | HapAmp | 09-Dec-21 | 22-Sep-22 | 12-Nov-21 | 12-Dec-21 | 21-Jul-22 | Customer | Customer |  | 0
638260 | 638260 - SWITCHGEAR REPLACEMENT 2021 - BATCH 7 | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 02-Nov-20 |  |  | 415393.2 | 123199.13 | 415393.2 | 415393.2 | Horlings, Jake | Somervl | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 16-May-21 | 22-Dec-21 | Filler |  |  | 0
638259 | 638259 - SWITCHGEAR REPLACEMENT 2021 - BATCH 6 | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 02-Nov-20 |  |  | 663591.7 | 509487.01 | 742948.49 | 663591.7 | Horlings, Jake | Somervl | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 13-Mar-21 | 24-Dec-21 | Filler |  |  | -79,356.79
638258 | 638258 - SWITCHGEAR REPLACEMENT 2021 - BATCH 5 | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 02-Nov-20 |  |  | 442894.71 | 244627.49 | 442894.71 | 442894.71 | Horlings, Jake | Somervl | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 21-Jun-21 | 25-Nov-21 | Filler |  |  | 0
638257 | 638257 - SWITCHGEAR REPLACEMENT 2021 - BATCH 4 | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 02-Nov-20 |  |  | 173382.62 | 167559.08 | 173382.62 | 173382.62 | Horlings, Jake | Somervl | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 29-Apr-21 | 21-Jul-21 | Filler |  |  | 0
638256 | 638256 - SWITCHGEAR REPLACEMENT 2021 - BATCH 3 | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 02-Nov-20 |  |  | 593347.67 | 593136.03 | 593347.67 | 593347.67 | Horlings, Jake | Somervl | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 30-Jan-21 | 23-Jun-21 | Filler |  |  | 0
638255 | 638255 - SWITCHGEAR REPLACEMENT 2021 - BATCH 2 | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 02-Nov-20 |  |  | 98835.32 | 111543.65 | 98835.32 | 98835.32 | Horlings, Jake | Somervl | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 16-Jan-21 | 22-Dec-21 | Filler |  |  | 0
638254 | 638254 - SWITCHGEAR REPLACEMENT 2021 - BATCH 1 | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 02-Nov-20 |  |  | 35651.45 | 48224.43 | 35651.45 | 35651.45 | Horlings, Jake |  | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 18-Nov-21 | 18-Nov-21 | Filler |  |  | 0
638261 | 638261 - M20 SARAH JANE COURT - CABLE FAILURE REPLACEMENT | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 22-Feb-21 |  |  | 196022.48 | 189526.11 | 196022.48 | 196022.48 | Horlings, Jake | Transpw | 26-Apr-21 | 05-Jan-22 | 06-Apr-21 | 01-May-21 | 21-May-21 | Contractor | Contractor |  | 0
638266 | 638266 - YONGE ST. - #8188, RESIDENTIAL/RETAIL CONDO/VAU/NS/CUSTOMER-OWN SUBSTATION | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 05-Dec-22 | 1 | 1 | 73245.74 | 12487.97 | 73245.74 | 73245.74 | Dave Lindsay | Somervl | 22-Feb-23 | 22-Feb-24 | 20-Feb-23 | [5 empty] | 0
638292 | 4 DON HILLOCK DR/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638300 | 638300 - 2021 DA - V45SL3007 - VAUGHAN, 1 | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 26-May-21 |  |  | 87437.51 | 92657.41 | 87437.51 | 87437.51 | Macdonald, Steve | K-Line | 01-Oct-21 | 12-Apr-22 | 23-Sep-21 | 20-Sep-21 | 20-Sep-21 |  |  |  | 0
638299 | 638299 - 2022 DA - R25SL1005 - RICHMOND HILL | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2022 | Tenorlas, Reynaldo | Roy, James | 26-Nov-21 | 1 | 1 | 108592.55 | 89612.03 | 108592.55 | 108592.55 | Reginald Clarke |  | 14-Feb-22 | 22-Sep-22 | 01-Feb-22 | 02-Feb-22 | 09-Mar-22 | Filler | Filler |  | 0
638298 | 638298 - DISTRIBUTION AUTOMATION 2021 - NEW - VAUGHAN, 1 | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 14-Apr-21 |  |  | 129432.3 | 134517.97 | 116432.68 | 129432.3 | Macdonald, Steve | K-Line | 15-Sep-21 | 12-Apr-22 | 09-Sep-21 | 02-Aug-21 | 14-Aug-21 |  |  |  | 12,999.62
638297 | 638297 - DISTRIBUTION AUTOMATION 2021 - TBD - VAUGHAN, 1 | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 14-Apr-21 |  |  | 147083.58 | 155961.8 | 165024.57 | 147083.58 | Macdonald, Steve | K-Line | 08-Sep-21 | 12-Apr-22 | 31-Aug-21 | 10-Jul-21 | 24-Jul-21 |  |  |  | -17,940.99
638296 | 638296 - 2022 DA - 45SL3002 - VAUGHAN | 815 - Addiscott | 100886 | Active | 99 | ANALYZE | High | DA | 2022 | Tenorlas, Reynaldo | Roy, James | 29-Nov-21 | 1 | 1 | 126546.68 | 180618.47 | 126546.68 | 126546.68 | Kristine Gordon |  | 15-Feb-22 | 26-Jul-23 | 01-Feb-22 | 15-Mar-22 | 13-Apr-22 | Filler | Filler |  | 0
638295 | 638295 - DISTRIBUTION AUTOMATION 2021 - NEW UNIT - VAUGHAN, 1 | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 16-Mar-21 |  |  | 103033.67 | 113338.78 | 103033.67 | 103033.67 | Macdonald, Larry |  | 13-Jul-21 | 15-Feb-22 | 28-Jun-21 | 12-Jul-21 | 09-Aug-21 | Filler | Filler |  | 0
638294 | 638294 - DISTRIBUTION AUTOMATION 2021 - R12SL3004 - RH, 1 | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Tenorlas, Reynaldo | Roy, James | 18-Mar-21 |  |  | 91894.69 | 114429.02 | 91894.69 | 91894.69 | Macdonald, Larry |  | 25-Jun-21 | 12-Apr-22 | 14-Jun-21 | 19-Jul-21 | 13-Aug-21 | Filler | Filler |  | 0
638293 | 638293 - DISTRIBUTION AUTOMATION 2022 - M33SUG001 - MARKHAM | 815 - Addiscott | 100886 | Active | 98 | COMPLETE | High | DA | 2022 | Tenorlas, Reynaldo | Roy, James | 02-Jun-22 | 1 | 1 | 174289.9 | 163761.09 | 174289.9 | 174289.9 | Horlings, Jake | Somervl | 18-Aug-22 | 17-Aug-23 | 15-Jul-22 | 09-Nov-22 | 08-Dec-22 | Contractor | Contractor |  | 0
638302 | 638302 - 2021 CABLE INJECTION/M22 – MAJOR MACKENZIE – HWY 48 – 16TH – MCCOWAN | 815 - Addiscott | 151350 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 03-Nov-20 |  |  | 231608.15 | 124896.24 | 231608.15 | 231608.15 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 24-Jan-21 | 05-Dec-21 | Contractor |  |  | 0
638304 | 638304 - 2021 CABLE INJECTION/V41 – KIRBY – WESTON – TESTON – PINE VALLEY | 815 - Addiscott | 151353 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 02-Nov-20 |  |  | 162409.62 | 225755.24 | 162409.62 | 162409.62 | Horlings, Jake | Nvinium | 31-Dec-21 | 22-Sep-22 | 01-Jan-21 | 17-Oct-21 | 19-Nov-21 | Contractor |  |  | 0
638303 | 638303 - 2021 CABLE INJECTION/M32 – HWY 7 – MAIN – 14TH – WARDEN | 815 - Addiscott | 151351 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 03-Nov-20 |  |  | 1222804.71 | 1103661.21 | 1222804.71 | 1222804.71 | Horlings, Jake | Nvinium | 31-Dec-21 | 22-Sep-22 | 01-Jan-21 | 04-Apr-21 | 05-Dec-21 | Contractor |  |  | 0
638308 | 2021 CABLE INJECTION/V18 – MAJOR MACKENZIE – KEELE | 815 - Addiscott | 150025 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638307 | 638307 - 2021 CABLE INJECTION/V38 – RUTHERFORD – WESTON | 815 - Addiscott | 150261 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James | 04-Dec-20 |  |  | 100000.89 | 103976.35 | 100000.89 | 100000.89 | Horlings, Jake | Nvinium | 31-Dec-21 | 26-Jul-23 | 01-Jan-21 | 01-Jan-21 |  |  |  |  | 0
638306 | 638306 - 2021 CABLE INJECTION/V52 – RUTHERFORD – KIPLING – LANGSTAFF – HWY 27 | 815 - Addiscott | 151354 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 02-Nov-20 |  |  | 183714.95 | 459623.28 | 183714.95 | 183714.95 | Horlings, Jake | Nvinium | 31-Dec-21 | 22-Sep-22 | 01-Jan-21 | 01-Jan-21 | 16-May-22 |  | Contractor |  | 0
638309 | 2021 CABLE INJECTION/V36 – STEELES – PINE VALLEY | 815 - Addiscott | 150021 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Handy, James |  |  |  | 212309.44 | 0 | 212528.76 | 212528.76 | Wong, Henry |  |  | 29-Dec-20 | [6 empty] | 0
638318 | 638318 - HUNGINGTON RD. - #9151 - MULTIPLE TENANTS AND WAREHOUSE | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 30-Mar-21 |  |  | 125642.62 | 187927.08 | 125642.62 | 125642.62 | Dave Lindsay | Somervl | 14-Jun-21 | 26-Jul-23 | 12-May-21 | 10-Jun-21 | 29-Mar-23 | Customer | Customer |  | 0
638324 | 638324 - 8811 HUNTINGTON RD/ VAU/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 95 | COMPLETE |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A | 22-Mar-21 |  |  | 117073.97 | 133444.53 | 105278.87 | 117073.97 | Dave Lindsay | Somervl | 22-Jun-21 | 26-Jul-23 | 06-May-21 | 26-Aug-21 | 07-Oct-22 | Customer | Customer |  | 11,795.10
638322 | 638322 - UG CABLE REPLACEMENT, V16 BRADWICK DR - 16-L20 TO V16SP3109 (CABLE FAILURE) | 815 - Addiscott | 151450 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 08-Jan-21 |  |  | 142460.63 | 117656.17 | 142460.63 | 142460.63 | Lamb, Tim | Transpw | 22-Mar-21 | 26-Jul-23 | 08-Mar-21 | 10-Apr-21 | 10-Apr-21 | Contractor | Contractor |  | 0
638321 | 638321 - 8555 HUNTINGTON RD / VAU / NS / 3PH PAD | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Dibratto, Susan | Mann, Drew | 29-Jul-21 |  |  | 120845.88 | 158662.48 | 120845.88 | 120845.88 | Dave Lindsay | Somervl | 08-Oct-21 | 26-Jul-23 | 10-Sep-21 | 31-Jan-23 | 21-Feb-23 | Customer | Customer |  | 0
638319 | 638319 - 6680 LANGSTAFF ROAD/ VAU/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 28-Apr-21 |  |  | 112615.9 | 154895.11 | 112615.9 | 112615.9 | Dave Lindsay | Somervl | 16-Jul-21 | 17-Aug-23 | 10-Jun-21 | 17-Sep-21 | 14-Apr-23 | Customer | Customer |  | 0
638368 | 638368 - 7050 MAJOR MACKENZIE DR / VAU / UP / 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Joshi, Namrata | Mann, Drew | 05-Mar-21 |  |  | 101154.8 | 96895.63 | 101154.8 | 101154.8 | Dave Lindsay | Somervl | 13-May-21 | 13-Jul-22 | 16-Apr-21 | 20-Apr-21 | 03-Jun-21 | Customer | Customer |  | 0
638386 | 638386 - 375 NEW HUNTINGTON/ VAU/ NS/ 3-PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 05-Mar-21 |  |  | 183159.25 | 174013.19 | 183159.25 | 183159.25 | Dave Lindsay | Somervl | 12-May-21 | 21-Apr-22 | 16-Apr-21 | 21-Apr-21 | 26-May-21 | Customer | Customer |  | 0
638388 | 638388 - DUFFERIN ST. - #8020 - CITY OF VAUGHAN - DUFFERIN OPERATIONS CENTER | 815 - Addiscott | 101791 | Active | 84 | H8 |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 23-Apr-21 |  |  | 57740.68 | 19711.23 | 57740.68 | 57740.68 | Dave Lindsay | Somervl | 21-Jul-21 | 17-Aug-23 | 10-Jun-21 | 28-May-21 |  |  | Customer |  | 0
638389 | 21 LILY STREET, BEETON - RELOCATE POLES | 825 - Patterson | 101763 | Active | 99 | COMPLETE |  |  | 2021 | Lacombe, Joel | Lemire, Blake |  |  |  | 1704.38 | 6131.69 | 1704.38 | 1704.38 | Persaud, Ryan |  |  | 26-Jul-23 |  | 31-Dec-21 | 31-Dec-21 | xBy-passed | xBy-passed |  | 0
638391 | 638391 - SWITCH REPLACEMENT - M49SL3108 | 815 - Addiscott | 101027 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 03-Nov-21 |  |  | 78076.72 | 0 | 78076.72 | 78076.72 | Macdonald, Larry |  | 21-May-21 | 20-Jul-21 | 11-May-21 | [5 empty] | 0
638390 | 638390 - SWITCH REPLACEMENT - M52SL3110 | 815 - Addiscott | 101027 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 10-Nov-21 |  |  | 62752.06 | 0 | 62752.06 | 62752.06 | Macdonald, Larry |  | 10-May-21 | 20-Jul-21 | 03-May-21 | [5 empty] | 0
638395 | 638395 - SWITCH REPLACEMENT - A03SL2000, A03SL2003 AND A02SL2003 | 815 - Addiscott | 101027 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 03-Nov-21 |  |  | 25503.14 | 22462.95 | 44592.9 | 25503.14 | Macdonald, Larry |  | 24-Jun-21 | 25-Apr-22 | 21-Jun-21 | 05-Jul-21 | 09-Aug-21 | Filler | Filler |  | -19,089.76
638394 | 638394 - SWITCH REPLACEMENT - V19SL3019 | 815 - Addiscott | 101027 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 10-Nov-21 |  |  | 67596.1 | 73564.03 | 67596.1 | 67596.1 | Macdonald, Larry |  | 06-Jul-21 | 25-Apr-22 | 28-Jun-21 | 03-Jul-21 | 13-Jul-21 | Filler | Filler |  | 0
638393 | 638393 - SWITCH REPLACEMENT - M43SL3083 | 815 - Addiscott | 101027 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 03-Nov-21 |  |  | 106317.09 | 0 | 106317.09 | 106317.09 | Macdonald, Larry |  | 09-Jun-21 | 20-Jul-21 | 25-May-21 | [5 empty] | 0
638397 | 638397 - 29 EAST WILMOT ST / RHL / UP / 3PH VAULT | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 25-Feb-21 |  |  | 69793.19 | 67385.64 | 69793.19 | 69793.19 | Dave Lindsay | Somervl | 21-May-21 | 18-Jan-22 | 08-Apr-21 | 11-Nov-21 | 11-Nov-21 | Customer | Customer |  | 0
638421 | ISLINGTON AVE. - #7082 (CONDO)/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638465 | 638465 - 783 BAYVIEW DRIVE/BAR/UPGRADE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 19-Feb-21 |  |  | 28009.26 | 42539.11 | 28009.26 | 28009.26 | Lotto, Jay | HapAmp | 27-Apr-21 | 19-Jul-21 | 06-Apr-21 | 19-Mar-21 | 19-Mar-21 |  |  |  | 0
638537 | 638537 - 2021 POLE REPLACEMENTS ALLISTON BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 31-Mar-21 |  |  | 400631.72 | 542027.77 | 400631.72 | 400631.72 | Jeremy Wright | K-Line | 17-Sep-21 | 25-Apr-22 | 28-Jun-21 | 21-Jun-21 | 02-Sep-21 |  |  |  | 0
638539 | 638539 - 2021 POLE REPLACEMENTS BARRIE BATCH 5 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 31-Mar-21 |  |  | 162363.17 | 154659.95 | 162363.17 | 162363.17 | Jeremy Wright |  | 27-Jul-21 | 15-Aug-22 | 28-Jun-21 | 13-Sep-21 | 09-Nov-21 | Filler | Filler |  | 0
638538 | 638538 - 2021 POLE REPLACEMENTS ALLISTON BATCH 2 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 03-May-21 |  |  | 377617.05 | 321373.54 | 377617.05 | 377617.05 | Jeremy Wright |  | 23-Dec-21 | 08-Jun-22 | 01-Nov-21 | 28-Sep-21 | 06-Dec-21 |  |  |  | 0
638543 | 638543 - 2021 POLE REPLACEMENTS BARRIE BATCH 4 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 08-Mar-21 |  |  | 220759.15 | 268220.3 | 220759.15 | 220759.15 | Dan Kish | HapAmp | 28-Jul-21 | 26-Apr-22 | 15-Jun-21 | 14-Jun-21 | 22-Oct-21 |  | Filler |  | 0
638542 | 638542 - 2021 POLE REPLACEMENTS BARRIE BATCH 3 | 825 - Patterson | 100867 | Active | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 31-Dec-20 |  |  | 234986.06 | 248204.14 | 234986.06 | 234986.06 | Dan Kish |  | 26-Mar-21 | 26-Jul-23 | 01-Mar-21 | 02-Mar-21 | 06-Oct-21 | Filler | Filler |  | 0
638541 | 638541 - 2021 POLE REPLACEMENTS BARRIE BATCH 2 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 31-Dec-20 |  |  | 252098.51 | 264014.01 | 252098.51 | 252098.51 | Dan Kish |  | 08-Apr-21 | 25-Apr-22 | 26-Feb-21 | 28-Jan-21 | 26-Oct-21 |  | Filler |  | 0
638540 | 638540 - 2021 POLE REPLACEMENTS BARRIE BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 31-Dec-20 |  |  | 225171.56 | 210142.48 | 225171.56 | 225171.56 | Dan Kish |  | 05-Mar-21 | 25-Apr-22 | 22-Feb-21 | 03-Feb-21 | 06-Oct-21 |  | Filler |  | 0
638545 | 638545 - 2021 POLE REPLACEMENTS PENETANG BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 01-Jun-21 |  |  | 36095.22 | 32296.14 | 36095.22 | 36095.22 | Dan Kish |  | 13-Aug-21 | 22-Sep-22 | 06-Aug-21 | 01-Oct-21 | 09-Dec-21 | Filler | Filler |  | 0
638544 | 638544 - 2021 POLE REPLACEMENTS BRADFORD BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 01-Jun-21 |  |  | 137782.23 | 151441.02 | 137782.23 | 137782.23 | Dan Kish |  | 13-Dec-21 | 08-Jun-22 | 18-Nov-21 | 01-Dec-21 | 13-Dec-21 | Filler |  |  | 0
638546 | 638546 - 2021 POLE REPLACEMENTS TOTTENHAM BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 03-May-21 |  |  | 84804.84 | 64849.96 | 84804.84 | 84804.84 | Dan Kish |  | 01-Dec-21 | 25-Apr-22 | 18-Nov-21 | 08-Nov-21 | 01-Dec-21 |  |  |  | 0
638557 | 638557 - JOINT USE PERMIT HE2020-068 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 22-Jun-21 |  |  | 7576.55 | 5538.26 | 7576.55 | 7576.55 | Steve Rumble |  | 03-Aug-21 | 22-Aug-22 | 03-Aug-21 | 13-Jul-21 | 13-Jul-21 |  |  |  | 0
638561 | 638561 - JOINT USE PERMIT #HE2020-069, YONGE ST. RICHMOND HILL, ONTARIO | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 12-Apr-21 |  |  | 6218.3 | 5254.48 | 6218.3 | 6218.3 | Macdonald, Larry |  | 21-May-21 | 21-Aug-22 | 21-May-21 | 14-Apr-21 | 14-Apr-21 |  |  |  | 0
638572 | 638572 - POLE REPLACEMENT 2021 - BATCH 1 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 08-Dec-20 |  |  | 264718.8 | 240576.64 | 344010.8 | 264718.8 | Morrow, Joe |  | 25-Jun-21 | 28-Jan-22 | 11-Jan-21 | 21-Jan-21 | 02-Feb-21 |  |  |  | -79,292.00
638576 | 638576 - POLE REPLACEMENT 2021 - BATCH 4 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 10-Dec-20 |  |  | 179661.41 | 183907.39 | 153661.41 | 179661.41 | Morrow, Joe |  | 18-Mar-21 | 20-Sep-21 | 01-Mar-21 | 01-Mar-21 | 09-Mar-21 |  |  |  | 26,000.00
638575 | 638575 - POLE REPLACEMENT 2021 - BATCH 3 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 08-Dec-20 |  |  | 148314.77 | 148134.7 | 196314.77 | 148314.77 | Morrow, Joe |  | 25-Feb-21 | 05-Jul-21 | 11-Jan-21 | 21-Jan-21 | 23-Feb-21 |  |  |  | -48,000.00
638574 | 638574 - POLE REPLACEMENT 2021 - BATCH 2 - 9 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 03-Dec-20 |  |  | 199380.77 | 192580.95 | 145380.77 | 199380.77 | Ryan Walsh |  | 04-Feb-21 | 05-Jul-21 | 11-Jan-21 | 11-Jan-21 | 03-Feb-21 |  |  |  | 54,000.00
638589 | 638589 - 2022 POLE RENEWAL - BATCH 1 - 15 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 08-Nov-21 | 15 | 15 | 226973.61 | 220766.64 | 226973.61 | 226973.61 | Morrow, Joe |  | 08-Feb-22 | 07-Mar-23 | 03-Jan-22 | 03-Jan-22 | 23-Jan-22 |  |  |  | 0
638587 | 638587 - POLE REPLACEMENT 2021 - BATCH 15 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 09-Apr-21 |  |  | 168351.18 | 118754.42 | 168351.18 | 168351.18 | Macdonald, Larry |  | 15-Oct-21 | 25-Nov-21 | 31-May-21 | 05-May-21 | 22-Jul-21 |  |  |  | 0
638586 | 638586 - POLE REPLACEMENT 2021 - BATCH 14 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 19-Feb-21 |  |  | 19445.74 | 16739.06 | 35765.74 | 17605.74 | Morrow, Joe |  | 07-May-21 | 04-Jul-21 | 01-May-21 | 30-Mar-21 | 30-Mar-21 |  |  |  | -18,160.00
638585 | 638585 - POLE REPLACEMENT 2021 - BATCH 13 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 09-Mar-21 |  |  | 57480.23 | 45196.25 | 54214.03 | 57480.23 | Reginald Clarke |  | 07-Sep-21 | 25-Jul-23 | 30-Aug-21 | 13-Oct-21 | 12-Nov-21 | Filler | Filler |  | 3,266.20
638584 | 638584 - 2021 POLE RENEWAL - BATCH 12 - 6 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 12-Mar-21 |  |  | 65236.96 | 64774.44 | 81236.96 | 65236.96 | Macdonald, Larry |  | 20-May-21 | 20-Sep-21 | 03-May-21 | 08-Apr-21 | 27-Apr-21 |  |  |  | -16,000.00
638583 | 638583 - POLE REPLACEMENT 2021 - BATCH 11 | 815 - Addiscott | 100867 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 16-Mar-21 | 1 | 1 | 118125.79 | 154234.72 | 118125.79 | 118125.79 | Reginald Clarke | K-Line | 17-Sep-21 | 26-Jul-23 | 30-Aug-21 | 13-Oct-21 | 15-Jan-22 | Filler | Filler |  | 0
638582 | 638582 - POLE REPLACEMENT 2021 - BATCH 10 | 815 - Addiscott | 100867 | Active | 99 | ANALYZE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 17-Feb-21 | 3 | 3 | 184810.79 | 295868.55 | 184810.79 | 184810.79 | Kristine Gordon |  | 21-Oct-21 | 26-Jul-23 | 20-Sep-21 | 22-Nov-21 | 20-Dec-22 | Filler | Filler |  | 0
638581 | 638581 - POLE REPLACEMENT 2022 - BATCH 9 | 815 - Addiscott | 100867 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 26-Apr-21 | 20 | 20 | 297715.67 | 451000.95 | 297715.67 | 297715.67 | Morrow, Joe |  | 24-May-22 | 26-Jul-23 | 04-Apr-22 | 04-Apr-22 | 14-Dec-22 |  | Control/SCADA |  | 0
638580 | 638580 - POLE REPLACEMENT 2021 - BATCH 8 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 03-Dec-20 |  |  | 290751.23 | 285515.87 | 308349.94 | 290751.23 | Ryan Walsh |  | 21-Apr-21 | 30-Nov-21 | 01-Mar-21 | 17-Feb-21 | 19-Apr-21 |  |  |  | -17,598.71
638579 | 638579 - POLE REPLACEMENT 2021 - BATCH 7 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 01-Dec-20 |  |  | 75583.04 | 76000.17 | 59583.04 | 75583.04 | Ryan Walsh |  | 21-Jan-21 | 06-Apr-21 | 11-Jan-21 | 05-Jan-21 | 14-Jan-21 |  |  |  | 16,000.00
638578 | 638578 - POLE REPLACEMENT 2021 - BATCH 6 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 10-Dec-20 |  |  | 85160.65 | 91813.56 | 142038.99 | 85160.65 | Ryan Walsh |  | 08-Mar-21 | 05-Jul-21 | 15-Feb-21 | 08-Feb-21 | 23-Feb-21 |  |  |  | -56,878.34
638577 | 638577 - POLE REPLACEMENT 2021 - BATCH 5 | 815 - Addiscott | 100867 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 03-Dec-20 |  |  | 200713.29 | 187901.52 | 216393 | 200713.29 | Reginald Clarke |  | 19-Feb-21 | 26-Jul-23 | 11-Jan-21 | 15-Feb-21 | 03-Nov-21 | Filler | Filler |  | -15,679.71
638597 | 638597 - 2021 PADMOUNT TX REPLACEMENT BATCH 1 - BARRIE - 1X 3PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 11-Jan-21 |  |  | 41851.29 | 48855.5 | 41851.29 | 41851.29 | Lotto, Jay |  | 29-Oct-21 | 17-Mar-22 | 28-Oct-21 | 30-Dec-21 | 30-Dec-21 | Customer | Customer |  | 0
638598 | 638598 - 2021 PADMOUNT TX REPLACEMENT BATCH 2 - BARRIE - 4X 1PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 11-Jan-21 |  |  | 34164.66 | 25170.07 | 34164.66 | 34164.66 | Lotto, Jay |  | 23-Jun-21 | 17-Mar-22 | 14-Jun-21 | 03-Jun-21 | 17-Jun-21 |  |  |  | 0
638599 | 638599 - 2021 PADMOUNT TX REPLACEMENT BATCH 3 - BARRIE - 7X 1PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 11-Jan-21 |  |  | 52815.25 | 23826.94 | 52815.25 | 52815.25 | Lotto, Jay |  | 19-Nov-21 | 17-Mar-22 | 02-Nov-21 | 07-Oct-21 | 19-Oct-21 |  |  |  | 0
638600 | 638600 - 2021 PADMOUNT TX REPLACEMENT BATCH 4 - BRADFORD - 1X 3PH & 1X 1PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 30-Dec-20 |  |  | 40815.11 | 8717.2 | 40815.11 | 40815.11 | Lotto, Jay |  | 18-Jun-21 | 17-Mar-22 | 14-Jun-21 | 03-Jun-21 | 03-Jun-21 |  |  |  | 0
638601 | 638601 - 2021 PADMOUNT TX REPLACEMENT BATCH 5 - BEETON - 1X 3PH & 2X 1PH | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 30-Dec-20 |  |  | 39658.48 | 37070.24 | 39658.48 | 39658.48 | Lotto, Jay |  | 26-Oct-21 | 17-Mar-22 | 15-Oct-21 | 29-Sep-21 | 19-Oct-21 |  |  |  | 0
638603 | 638603 - POLE REPLACEMENT 2021 - REPLACE P51710 - RAILWAY CROSSING | 815 - Addiscott | 100867 | Active | 99 | ANALYZE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-May-21 | 1 | 1 | 96562.89 | 90427.25 | 96562.89 | 96562.89 | Kristine Gordon |  | 01-Sep-21 | 26-Jul-23 | 18-Aug-21 | 02-Sep-21 | 05-Dec-22 | Filler | Filler |  | 0
638604 | 638604 - POLE REPLACEMENT 2021 - REPLACE P37765 - RAILWAY CROSSING | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 09-Mar-21 | 1 |  | 33766.76 | 29715.41 | 33766.76 | 33766.76 | Ryan Walsh |  | 27-Apr-21 | 31-Oct-21 | 26-Apr-21 | 16-Mar-21 | 16-Mar-21 |  |  |  | 0
638610 | 638610 - TRANSFORMER REPLACEMENT 2021 - BATCH 11 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 04-Feb-21 |  |  | 117681.6 | 105888.48 | 117681.6 | 117681.6 | Horlings, Jake | Somervl | 12-Jul-21 | 17-Mar-22 | 01-Jun-21 | 12-Aug-21 | 28-Oct-21 | Filler | Filler |  | 0
638609 | 638609 - TRANSFORMER REPLACEMENT 2021 - BATCH 10 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 04-Feb-21 |  |  | 325038.2 | 278587.69 | 325038.2 | 325038.2 | Dave Lindsay | Somervl | 05-Aug-21 | 26-Jul-23 | 01-Jun-21 | 28-Jun-21 | 05-Nov-21 | Filler | Filler |  | 0
638608 | 638608 - TRANSFORMER REPLACEMENT 2021 - BATCH 9 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 12-Jan-21 |  |  | 71650.48 | 66600.67 | 71650.48 | 71650.48 | Lamb, Tim |  | 13-Apr-21 | 26-Jul-23 | 18-Mar-21 | 08-May-21 | 15-May-21 | Filler | Filler |  | 0
638607 | 638607 - TRANSFORMER REPLACEMENT 2021 - BATCH 8 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 04-Feb-21 | 13 | 7 | 199487.7 | 132632.39 | 199487.7 | 199487.7 | Horlings, Jake | Somervl | 23-Jul-21 | 26-Jul-23 | 01-Jun-21 | 03-Sep-21 | 04-Apr-22 | Filler | Filler |  | 0
638606 | 638606 - TRANSFORMER REPLACEMENT 2021 - BATCH 7 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 12-Feb-21 |  |  | 258378.34 | 236335.86 | 273434.34 | 258378.34 | Horlings, Jake | Somervl | 03-Aug-21 | 17-Mar-22 | 01-Jun-21 | 08-Jul-21 | 21-Dec-21 | Filler | Filler |  | -15,056.00
638605 | 638605 - TRANSFORMER REPLACEMENT 2021 - BATCH 6 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 12-Jan-21 | 6 | 6 | 129038.91 | 142022.78 | 129038.91 | 129038.91 | Dave Lindsay | Somervl | 29-Jun-21 | 09-Aug-23 | 01-Jun-21 | 06-Aug-21 | 02-Dec-22 | Filler | Filler |  | 0
638622 | 638622 - 7537 WOODBINE AVE / MARKHAM / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 06-Apr-21 |  |  | 63162.91 | 51402.66 | 63162.91 | 63162.91 | Dave Lindsay | Somervl | 17-Jun-21 | 15-Jun-23 | 19-May-21 | 03-Nov-21 | 19-Jul-22 | Customer | Customer |  | 0
638623 | 8TH LINE IN ALLISTON POLE RELOCATION | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim | 26-Jan-22 |  |  | 32794.63 | 36712.88 | 32794.63 | 32794.63 | Jeremy Wright |  |  | 22-Sep-22 |  | 26-Jan-22 | 26-Jan-22 | xBy-passed | xBy-passed |  | 0
638628 | HUNTINGTON RD. - #9571/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638627 | 638627 - 160 HOLLAND ST. - BRADFORD - 3PH PADMOUNT TRANSFORMER REPLACEMENT | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 10-Mar-21 |  |  | 85362.06 | 92818.58 | 85362.06 | 85362.06 | Lotto, Jay | HapAmp | 13-May-21 | 17-Mar-22 | 26-Apr-21 | 12-Apr-21 | 14-Apr-21 |  |  |  | 0
638631 | 638631 - 2021 Distribution Automation - Essa & Beacon -13.8kV Automated Intellirupter, 1 | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Bowman, Todd J | Walters, Geoffrey D | 26-Apr-21 |  |  | 75537.14 | 87172.52 | 75537.14 | 75537.14 | Jeremy Wright |  | 29-Jun-21 | 12-Apr-22 | 18-Jun-21 | 16-Aug-21 | 06-Oct-21 | Filler | Filler |  | 0
638630 | 638630 - LESLIE ELGIN BLOCK 284 – SUBD RES EDS | 815 - Addiscott | 101887 | Active | HO | RELEASED |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 22-Sep-22 |  |  | 325607.34 | 10794.31 | 325607.34 | 325607.34 | Dave Lindsay | Transpw | 30-Nov-22 | 08-Aug-23 | 04-Nov-22 |  |  | Customer | Customer |  | 0
638629 | 638629 - 2021 Distribution Automation -Bryne Dr & Commerce Park Dr-13.8kV Automated Intellirupter, 1 | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Bowman, Todd J | Walters, Geoffrey D | 26-Apr-21 |  |  | 78503.75 | 82310.88 | 78503.75 | 78503.75 | Jeremy Wright |  | 29-Jun-21 | 10-Aug-22 | 18-Jun-21 | 16-Aug-21 | 12-Oct-21 | Filler | Filler |  | 0
638633 | 7-TOWN CRIER DEVELOPMENT – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638632 | 638632 - 2021 - DISTRIBUTION AUTOMATION - BARRIE - TIFFIN & MILLER - 44KV AUTOMATED LIS | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE | High | DA | 2021 | Bowman, Todd J | Walters, Geoffrey D | 01-Mar-21 |  |  | 152705.61 | 176953.72 | 152705.61 | 152705.61 | Dan Kish | K-Line | 22-Sep-21 | 12-Apr-22 | 07-Sep-21 | 18-Sep-21 | 25-Oct-21 | Filler | Filler |  | 0
638634 | HILDEBRAND LIMITED – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638638 | 638638 - 11801 KEELE ST/VAU/NS/1PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 08-Dec-20 |  |  | 40152.14 | 22505.06 | 40152.14 | 40152.14 | Dave Lindsay | Somervl | 03-Mar-21 | 23-Aug-21 | 02-Feb-21 | 22-Dec-20 | 27-Apr-21 |  | Customer |  | 0
638644 | 638644 - CAL-CROWN (THREE) DEVELOPMENT (PHASE 1) – SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Alarcon, Alejandro | 11-May-21 |  |  | 157173.41 | 136655.31 | 157173.41 | 157173.41 | Dave Lindsay |  | 19-Jul-21 | 07-Sep-21 | 24-Jun-21 | 17-May-21 | 21-Jul-21 |  | Customer |  | 0
636103 | 636103 - JOINT USE PERMIT #HE2020-014, PENETANGUSHENE ROAD, BARRIE | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 05-Oct-20 |  |  | 6255.51 | 4521.63 | 6255.51 | 6255.51 | Steve Rumble |  | 07-Dec-20 | 22-Aug-22 | 07-Dec-20 | 20-Apr-21 | 20-Apr-21 | Lines | Lines |  | 0
638652 | 2021 - SWITCHGEAR RENEWAL - BARRIE - SC13520 - 46 DEAN AVE | 825 - Patterson | 100859 | Inactive | 99 | CANCELLED |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 1130.97 | 0 |  | 0 | Wong, Henry |  |  | 22-Sep-22
638655 | 2021 - SWITCHGEAR RENEWAL - BARRIE - SC13649 - 141 MADELAINE DR | 825 - Patterson | 100859 | Inactive | 99 | CANCELLED |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638675 | 638675 - POLE REPLACEMENT 2021 - REPLACE P21843 - HWY 407 & MARKHAM RD | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 22-Mar-21 |  |  | 47954.35 | 41282.87 | 47954.35 | 47954.35 | Macdonald, Larry |  | 10-Jun-21 | 25-Nov-21 | 03-Jun-21 | 27-May-21 | 09-Aug-21 |  | Filler |  | 0
638674 | 638674 - POLE REPLACEMENT 2021 - REPLACE P930 & P932 - HWY 7 & HWY 427 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 09-Apr-21 |  |  | 182815.12 | 167896.31 | 118800.39 | 182815.12 | Macdonald, Steve | K-Line | 03-Sep-21 | 25-Apr-22 | 25-Aug-21 | 07-Oct-21 | 29-Oct-21 | MC/PUCC Permit | MC/PUCC Permit |  | 64,014.73
638673 | 638673 - YONGE ST & CATHERINE AVE | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Watters, Maxwell | 18-Jun-21 |  |  | 262267.03 | 265614.42 | 249934.03 | 262267.03 | Shane Christopher | Transpw | 13-Aug-21 | 26-Jul-23 | 30-Jul-21 | 26-Jul-21 | 25-Oct-21 |  | Contractor |  | 12,333.00
638685 | 638685 - 1360 BLOOMINGTON RD/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 22-Nov-21 |  |  | 71718.8 | 84264.99 | 71718.8 | 71718.8 | Dave Lindsay |  | 04-Feb-22 | 14-Jun-22 | 06-Jan-22 | 12-Apr-22 | 05-May-22 | Customer | Customer |  | 0
453263 | 453263 - CITYVIEW BLVD AT TESTON RD/SPLIT 1/0 LOOP | 815 - Addiscott | 150576 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 02-Nov-20 |  |  | 236553.52 | 231658.92 | 236553.52 | 236553.52 | Horlings, Jake | Somervl | 09-Apr-21 | 09-Dec-21 | 10-Mar-21 | 03-May-21 | 04-Jun-21 | Contractor | Contractor |  | 0
638709 | 638709 - 1 BIG BAY POINT RD/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 18-Jan-21 |  |  | 62086.25 | 75133.32 | 62086.25 | 62086.25 | Lotto, Jay | HapAmp | 01-Apr-21 | 06-Apr-22 | 08-Mar-21 | 02-Mar-21 | 30-Apr-21 |  | Customer |  | 0
638708 | 638708 - POLE REPLACEMENT 2022 - VTS4 CROSSOVERS | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 17-Mar-21 | 5 | 5 | 139041.99 | 113114.77 | 139041.99 | 139041.99 | Morrow, Joe |  | 07-Feb-23 | 23-May-23 | 16-Jan-23 | 03-Jan-23 | 11-Jan-23 |  |  |  | 0
638692 | 151 LILLIAN CRESENT/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 15-May-23 |  |  | 28180.93 | 5599.54 | 28180.93 | 28180.93 | Lotto, Jay | HapAmp | 25-Jul-23 | 02-Aug-23 | 18-Jul-23 | [5 empty] | 0
638771 | 638771 - WOODBINE AND HONDA BLVD/ MAR/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 22-Jul-21 |  |  | 168852.12 | 134859.22 | 168852.12 | 168852.12 | Dave Lindsay | Transpw | 30-Sep-21 | 18-Jul-23 | 02-Sep-21 | 23-Nov-21 | 08-Dec-21 | Customer | Customer |  | 0
638791 | 638791 - CAL-LESLIE DEVELOPMENT - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 98 | ANALYZE |  |  | 2022 | Penner, Mitchell | Estrada, Michael | 03-Dec-21 |  |  | 138619.52 | 121690.35 | 138619.52 | 138619.52 | Dave Lindsay |  | 24-Jan-22 | 26-Jul-23 | 18-Jan-22 | 11-Feb-22 | 05-May-22 | Customer | Customer |  | 0
638820 | 638820 - TRANSFORMER REPLACEMENT 2021 - 13 UNITS - BATCH 13 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 05-Feb-21 | 13 | 11 | 200919.14 | 215630.2 | 200919.14 | 200919.14 | Dave Lindsay | Somervl | 23-Jul-21 | 26-Jul-23 | 01-Jun-21 | 09-Aug-21 | 13-Jun-22 | Filler | Filler |  | 0
638819 | 638819 - TRANSFORMER REPLACEMENT 2021 - BATCH 12 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 12-Jan-21 |  |  | 214346.57 | 176284.9 | 214346.57 | 214346.57 | Horlings, Jake | Somervl | 26-May-21 | 17-Mar-22 | 18-Mar-21 | 22-Apr-21 | 23-Jun-21 | Filler | Filler |  | 0
638822 | 638822 - ADESSO TOWNS – SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Graham, Bruce W. | 04-May-21 |  |  | 64315.98 | 62176.53 | 64315.98 | 64315.98 | Dave Lindsay | Transpw | 05-Jul-21 | 11-Jan-22 | 16-Jun-21 | 25-Jun-21 | 08-Dec-21 | Customer | Customer |  | 0
638827 | 638827 - 233 DUNLOP ST W, BARRIE | 825 - Patterson | 101763 | Active | 98 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 20-Oct-21 |  |  | 167046.76 | 133094.36 | 167046.76 | 167046.76 | Jeremy Wright |  | 29-Dec-21 | 26-Jul-23 | 01-Dec-21 | 15-Nov-21 | 15-Dec-21 |  |  |  | 0
638831 | 7 TOWN CRIER DEVELOPMENT - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
636534 | 636534 - 70 DEAN AVE, BARRIE - 3 PHASE SERVICE | 825 - Patterson | 101919 | Active | HO | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 14-Jul-20 |  |  | 145921.21 | 207824.38 | 145921.21 | 145921.21 | Lotto, Jay | HapAmp | 15-Dec-20 | 10-Aug-23 | 30-Nov-20 | 30-Oct-20 |  |  | Customer |  | 0
638843 | 45 PENETANG ST/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
453886 | 453886 - SOUTH 14TH SUBDIVISION - SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 22-Oct-20 |  |  | 1018732.97 | 1213470.93 | 1018732.97 | 1018732.97 | Dave Lindsay | Transpw | 22-Jan-21 | 12-Oct-21 | 02-Nov-20 | 23-Oct-20 | 30-Jun-21 |  | Customer |  | 0
638855 | 638855 - FAIRTREE BLOCK 152 CONDO BLOCK SEMI DETACHED (PHASE 1) - SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 04-Feb-21 |  |  | 517277.06 | 512182.97 | 517277.06 | 517277.06 | Dave Lindsay | Transpw | 13-Apr-21 | 06-Apr-22 | 18-Mar-21 | 27-Mar-21 | 21-Jul-21 | Customer | Customer |  | 0
638878 | 638878 - BLOCK 40/47 (3 MODEL HOMES) – SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 08-Apr-21 |  |  | 56643.56 | 44539.29 | 56643.56 | 56643.56 | Dave Lindsay |  | 15-Jun-21 | 06-Apr-22 | 21-May-21 | 24-Apr-21 | 23-Jun-21 |  | Customer |  | 0
638879 | 5863 HIGHWAY 7 & MCPHILLIPS - KFC - MARKHAM | 815 - Addiscott | 101761 | Active | 50 | H8 |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638854 | 119065 VICTORIA SQUARE - MARKHAM | 815 - Addiscott | 101762 | Active | 40 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638886 | 638886 - 25 GRENCER RD/BRAD/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 01-Feb-21 |  |  | 39033.58 | 47952.34 | 39033.58 | 39033.58 | Lotto, Jay | HapAmp | 08-Apr-21 | 06-Apr-22 | 16-Mar-21 | 19-Mar-21 | 23-Mar-21 |  |  |  | 0
638100 | WEST BEAVER CREEK AND WEST PEARCE ST./RHL/NS/1PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 28-Mar-23 |  |  | 56724.71 | 3432.74 | 56724.71 | 56724.71 | Dave Lindsay | Somervl | 26-Jun-23 | 08-Aug-23 | 15-May-23 | [5 empty] | 0
638902 | 638902 - CREDITSTONE RD. - #551 (EXISTING CNR FACILITY) | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 18-Dec-20 |  |  | 12615.82 | 3423.03 | 12615.82 | 12615.82 | Dave Lindsay |  | 06-Jan-22 | 02-Aug-23 | 23-Dec-21 |  |  | Customer | Customer |  | 0
638938 | 638938 - SOUTH 14 SUBDIVISION - POLE RELOCATION | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael | 04-Jun-21 |  |  | 25841.07 | 10124.79 | 25841.07 | 25841.07 | Macdonald, Larry |  | 16-Jul-21 | 10-Oct-21 | 12-Jul-21 | 14-Jul-21 | 14-Jul-21 |  |  |  | 0
638955 | 638955 - 7709 MARKHAM RD / MARKHAM / NS / 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Joshi, Namrata | Mann, Drew | 03-May-21 |  |  | 64324.65 | 70946.3 | 64324.65 | 64324.65 | Dave Lindsay | Somervl | 16-Jul-21 | 21-Apr-22 | 16-Jun-21 | 17-Nov-21 | 08-Dec-21 | Customer | Customer |  | 0
638959 | 638959 - LORMEL PHASE 3 - SUBD RES EDS | 825 - Patterson | 101887 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 06-Jan-21 |  |  | 74426.59 | 2428.85 | 74426.59 | 74426.59 | Lotto, Jay | Transpw | 06-Apr-21 | 26-Jul-23 | 19-Feb-21 | 27-Jan-21 | 02-May-22 |  | Customer |  | 0
638958 | 77 FOX ST - POLE RELOCATION | 825 - Patterson | 151531 | Active | 99 | ANALYZE |  |  | 2023 | Penner, Mitchell | Perks, Dan | 19-Dec-22 | 1 |  | 26185.99 | 24571.8 | 26185.99 | 26185.99 | Dan Kish |  | 06-Feb-23 | 26-Jul-23 | 06-Feb-23 | 18-Jul-22 | 09-Jan-23 |  |  |  | 0
638963 | 53 JACOB KEEFER/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
638965 | 638965 - ESNA PARK DR. - #100 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 30-Mar-21 |  |  | 55461.8 | 59957.69 | 55461.8 | 55461.8 | Dave Lindsay | Somervl | 08-Jun-21 | 07-Mar-22 | 12-May-21 | 16-Jul-21 | 17-Aug-21 | Customer | Customer |  | 0
638974 | 638974 - TRANSFORMER RELOCATION - KLEINDOR SUBD | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 05-Jul-21 |  |  | 104712.35 | 99541.43 | 104712.35 | 104712.35 | Dave Lindsay | Transpw | 16-Sep-21 | 05-Jan-22 | 18-Aug-21 | 26-Jul-21 | 16-Sep-21 |  |  |  | 0
638977 | 638977 - FLEURY PARK WASHROOMS/AUR/NS/1PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 05-Jul-21 |  |  | 24862.48 | 21174.25 | 24862.48 | 24862.48 | Dave Lindsay | Somervl | 07-Sep-21 | 17-Aug-22 | 17-Aug-21 | 05-Apr-22 | 05-May-22 | Customer | Customer |  | 0
638978 | ALLURE AT THE GATES OF CLARENCE / 1115 CLARENCE - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
638980 | 638980 - BETHESDA SDRD, ANCHUSA DR TO LESLIE ST | 815 - Addiscott | 152102 | Active | 93 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander | 22-Feb-22 |  |  | 556230.69 | 503893.66 | 540397.08 | 556230.69 | Morrow, Joe | Transpw | 24-Jun-22 | 26-Jul-23 | 11-Apr-22 | 04-Apr-22 | 29-Jun-23 |  |  |  | 15,833.61
638987 | 638987 - POLE REBUILD 2021 - HUNTINGTON RD FROM RUTHERFORD RD TO MAJOR MACKENZIE DR | 815 - Addiscott | 100867 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 12-Aug-21 |  |  | 442681.41 | 482952.46 | 377645.84 | 442681.41 | Macdonald, Steve | K-Line | 22-Oct-21 | 26-Jul-23 | 20-Sep-21 | 13-Sep-21 | 26-Nov-21 |  | Control/SCADA |  | 65,035.57
638992 | 638992 - KING EAST (PHASE 3) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 05-Nov-21 |  |  | 144265.19 | 91506.68 | 144265.19 | 144265.19 | Dave Lindsay | Transpw | 18-Jan-22 | 28-Jul-23 | 17-Dec-21 | 13-Aug-22 |  | Customer | Customer |  | 0
638993 | 2022 EMERGING OH, AVIVA PARK DR - INSTALL RECLOSER | 815 - Addiscott | 101355 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 101814.47 | 41024.46 | 101814.47 | 101814.47 | Wong, Henry |  |  | 26-Jul-23 | [6 empty] | 0
638996 | WELLINGBROOK TOWNHOMES - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
638999 | 5925 14TH LINE/ALL/NS/3 PH PAD | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 10000 |  | 0 | East Coordinator |  |  | 20-Jul-20
639019 | 639019 - JOINT USE PERMIT #HE2020-075 - ADJALA TECHUMSETH TOWNLINE - TOTTENHAM | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 06-May-21 |  |  | 9247.53 | 6541.37 | 9247.53 | 9247.53 | Steve Rumble |  | 07-Jun-21 | 22-Aug-22 | 04-Jun-21 | 29-Jun-21 | 29-Jun-21 | Lines | Lines |  | 0
639057 | 105 CLEGG ROAD - MARKHAM | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Corriveau, Tom N |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 22-Aug-22
639059 | 639059 - 177 ROBERT ST E/PEN/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 26-Jul-21 |  |  | 48463.62 | 53488.25 | 48463.62 | 48463.62 | Lotto, Jay | HapAmp | 04-Oct-21 | 06-Apr-22 | 08-Sep-21 | 05-Aug-21 | 17-Sep-21 |  |  |  | 0
639063 | 639063 - 101 BRADWICK DR / VAU / SR / VAULT DEMO | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 04-Jan-21 |  |  | 21004.63 | 19336.74 | 21004.63 | 21004.63 | Dave Lindsay | Somervl | 02-Mar-21 | 14-Jun-21 | 09-Feb-21 | 08-Feb-21 | 17-Feb-21 |  |  |  | 0
639069 | 639069 - PHASE 4-UG. FOR DC 3. VIA RENZO DR AND PERFORMANCE DR, RICHMOND HILL | 815 - Addiscott | 151587 | Active | 98 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 13-Oct-21 |  |  | 1636522.4 | 1627665.13 | 1599828.18 | 1636522.4 | Dave Lindsay | Transpw | 09-Mar-22 | 26-Jul-23 | 24-Nov-21 | 05-Nov-21 | 07-Oct-22 |  | Customer |  | 36,694.22
639087 | 639087 - 55M12 FEEDER EXTENSION TO NORTH SIDE OF HWY 7 | 815 - Addiscott | 151866 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 08-Jan-21 |  |  | 125002.83 | 140643.85 | 122496.84 | 125002.83 | Ryan Walsh |  | 10-Mar-21 | 17-Aug-22 | 15-Feb-21 | 18-Jan-21 | 25-Feb-21 |  |  |  | 2,505.99
639102 | 639102 - TRANSFORMER REPLACEMENT 2021 - REPLACE 15-210 & 15-254 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 12-Jan-21 | 2 | 2 | 130395.75 | 107981.96 | 130395.75 | 130395.75 | Horlings, Jake | Somervl | 02-Feb-22 | 22-Sep-22 | 19-Jan-22 | 19-Mar-22 | 29-Mar-22 | Filler | Filler |  | 0
639122 | AURORA-HYDRO ONE- WELLINGTON ST E, BAYVIEW TO LESLIE | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2023 | Corriveau, Tom N | Corriveau, Tom N |  |  |  | 0 | 0 |  | 0 | Tom Corriveau |  |  | 02-May-23
639124 | 639124 - 7537-7541 WOODBINE AVE / MAR / SR / 3PH PAD DEMO | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 09-Dec-20 |  |  | 22028.94 | 14904.36 | 22028.94 | 22028.94 | Dave Lindsay | Somervl | 09-Feb-21 | 26-Jul-23 | 21-Jan-21 | 05-Apr-21 | 05-Apr-21 | Lines | Lines |  | 0
639221 | 639221 - REPLACE AND RELOCATE 7T5 - 13433 LESLIE ST | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 09-Feb-21 |  |  | 43773.41 | 38603.76 | 43773.41 | 43773.41 | Horlings, Jake | Somervl | 12-Apr-21 | 17-Mar-22 | 23-Mar-21 | 06-Apr-21 | 06-Aug-21 | Contractor | Contractor |  | 0
639349 | 639349 - CONNECTION OF BELL BONDS- HWY 27, VAUGHAN | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 18-Feb-21 |  |  | 1020.4 | 1006.25 | 1020.4 | 1020.4 | Don Rothman |  | 06-Apr-21 | 17-Aug-22 | 06-Apr-21 | 20-Apr-21 | 20-Apr-21 |  |  |  | 0
639372 | 639372 - KLEINDOR RESIDENTAL SUBDIVISION (PHASE 3) -SUBD RES EDS | 815 - Addiscott | 101887 | Active | 95 | ANALYZE |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 29-Jul-22 |  |  | 160336.03 | 17423.98 | 160336.03 | 160336.03 | Dave Lindsay |  | 07-Nov-22 | 26-Jul-23 | 19-Oct-22 |  | 09-Mar-23 | Customer | Customer |  | 0
639398 | 639398 - JOINT USE PERMIT #HE2020-079, MAJOR MACKENZIE DR E., MARKHAM | 815 - Addiscott | 151495 | Active | 98 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 02-Mar-22 |  |  | 47915.4 | 27601.54 | 47915.4 | 47915.4 | Macdonald, Steve | K-Line | 19-May-22 | 26-Jul-23 | 19-Apr-22 | 19-Apr-22 | 19-Apr-22 |  |  |  | 0
452602 | 452602 - 101 Cathedral High St | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A | 24-Nov-20 |  |  | 78393.44 | 64614.96 | 78393.44 | 78393.44 | Dave Lindsay | Somervl | 15-Jan-21 | 26-Jul-23 | 04-Jan-21 | 22-Jun-22 | 19-Jul-22 | Customer | Customer |  | 0
639416 | 639416 - CAL-CROWN DEVELOPMENT (PHASE 2) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 98 | ANALYZE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 25-Nov-21 |  |  | 20085.41 | 52780.2 | 20085.41 | 20085.41 | Dave Lindsay |  | 24-Jan-22 | 26-Jul-23 | 14-Jan-22 |  | 01-Mar-23 | Customer | Customer |  | 0
639420 | 639420 - 204 MAPLEVIEW DR W/BAR/UP/3PH PAD | 825 - Patterson | 101919 | Active | 99 | ANALYZE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 08-Oct-21 |  |  | 106505.27 | 90483.65 | 106505.27 | 106505.27 | Lotto, Jay |  | 02-Dec-21 | 26-Jul-23 | 19-Nov-21 | 28-Jun-22 | 06-Jul-22 | Customer | Customer |  | 0
639432 | 639432 - 5950 14TH AVENUE/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 18-Jun-21 |  |  | 109966.79 | 110943.31 | 109966.79 | 109966.79 | Dave Lindsay | Somervl | 25-Aug-21 | 18-Jan-22 | 03-Aug-21 | 13-Oct-21 | 27-Oct-21 | Customer | Customer |  | 0
639440 | 639440 - KENNEDY ROAD AND 16TH AVENUE - HYDRO RELOCATION | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Murray, Jake R | 19-Aug-21 |  |  | 598316.69 | 549296.4 | 598316.69 | 598316.69 | Macdonald, Steve | K-Line | 05-Nov-21 | 29-Jun-23 | 04-Oct-21 | 23-Aug-21 | 10-Dec-21 |  | MC/PUCC Permit |  | 0
639464 | 639464 - 418 DUNLOP ST W/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 10-Aug-22 |  |  | 97364.68 | 75794.77 | 97364.68 | 97364.68 | Lotto, Jay | HapAmp | 01-Nov-22 | 26-Jul-23 | 26-Sep-22 | 20-Sep-22 | 14-Oct-22 |  |  |  | 0
639475 | 639475 -122 QUEEN ST S/TOT/NS/1PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 04-Aug-21 |  |  | 53242.66 | 36153.56 | 53242.66 | 53242.66 | Lotto, Jay | HapAmp | 13-Oct-21 | 10-Aug-22 | 15-Sep-21 | 17-Sep-21 | 17-Dec-21 | Customer | Customer |  | 0
639474 | 129 ANNE ST S/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 05-Dec-22 | 1 |  | 52344.83 | 41456.07 | 52344.83 | 52344.83 | Lotto, Jay |  | 21-Feb-23 | 02-Aug-23 | 13-Feb-23 | 02-Feb-23 | 02-Feb-23 |  |  |  | 0
639476 | 639476 - BEAR CREEK LANDING - REMOVALS | 825 - Patterson | 151531 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 19-Oct-21 |  |  | 24449.29 | 19688.93 | 24449.29 | 24449.29 | Lotto, Jay | HapAmp | 21-Dec-21 | 27-Jan-22 | 01-Dec-21 | 15-Nov-21 | 15-Nov-21 |  |  |  | 0
639495 | 700 MAPLEVIEW DRIVE - BLOCK 16 - SUBD RES EDS | 825 - Patterson | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
639521 | KLEINDOR RESIDENTAL SUBDIVISION (PHASE 3) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
639528 | 639528 - 2021 TX RENEWAL, REPLACE AND RELOCATE 15TP197 - 43 MAIN ST N | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 06-May-21 |  |  | 153273.23 | 199582.54 | 153273.23 | 153273.23 | Horlings, Jake | Somervl | 23-Jul-21 | 19-Apr-22 | 17-Jun-21 | 20-Sep-21 | 25-Sep-21 | Contractor | Contractor |  | 0
639530 | 639530 - 22 CHURCH ST/AUR/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 18-May-21 |  |  | 83412.14 | 95282.29 | 83412.14 | 83412.14 | Dave Lindsay | Somervl | 30-Jul-21 | 26-Jul-23 | 02-Jul-21 | 11-Oct-22 | 06-Mar-23 | Customer | Customer |  | 0
639537 | 639537 - JOINT USE PERMIT #HE2020-084, HWY 7, MARKHAM | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 12-Apr-21 |  |  | 7322.49 | 4646.33 | 7322.49 | 7322.49 | Macdonald, Larry |  | 10-May-21 | 21-Aug-22 | 10-May-21 | 22-Apr-21 | 22-Apr-21 |  |  |  | 0
639556 | 639556 - BARRIE TS - TEMPORARY POLE RELOCATIONS | 825 - Patterson | 150259 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 23-Dec-20 |  |  | 92326.54 | 57078.8 | 92326.54 | 92326.54 | Dan Kish |  | 02-Feb-21 | 15-Nov-21 | 11-Jan-21 | 11-Jan-21 | 15-Jan-21 |  |  |  | 0
639566 | LESLIE ST. DEFICIENCIES | 815 - Addiscott | 101762 | Active | HL | COMPLETE |  |  | 2021 | Corriveau, Tom N | Barry, Kenneth | 07-May-21 |  |  | 66618.23 | 64610.08 | 55886.05 | 66618.23 | Macdonald, Steve | K-Line | 28-May-21 | 26-Jul-23 | 25-May-21 | 01-Jun-21 | 12-Jun-21 | Contractor | Contractor |  | 10,732.18
639568 | 639568 - 2022 TX RENEWAL – BATCH 10 – 5 TX | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 5 | 5 | 105388.21 | 79111.71 | 105388.21 | 105388.21 | Dave Lindsay | Somervl | 11-Feb-22 | 26-Jul-23 | 19-Jan-22 | 12-May-22 | 21-Jul-22 | Filler | Filler |  | 0
639567 | 639567 - 2022 TX RENEWAL – BATCH 9 – 19 TX | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 17 | 17 | 342938.09 | 282245.2 | 342938.09 | 342938.09 | Dave Lindsay | Somervl | 25-Mar-22 | 12-Jul-23 | 19-Jan-22 | 13-Jun-22 | 18-Aug-22 | Filler | Filler |  | 0
639569 | 639569 - 2022 TX RENEWAL - 8T76 | 815 - Addiscott | 101508 | Active | 80 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 3 |  | 48197.6 | 3820.75 | 48197.6 | 48197.6 | Dave Lindsay |  | 22-Sep-23 | 22-Sep-23 | 18-Sep-23 |  |  | Filler | Filler |  | 0
453511 | 453511 - 18-155 BELL JU APPLICATION | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 07-Dec-20 |  |  | 23885.46 | 18571.19 | 23885.46 | 23885.46 | Macdonald, Larry |  | 18-Jan-21 | 15-Dec-21 | 11-Jan-21 | 09-Mar-21 | 09-Mar-21 |  |  |  | 0
454135 | 454135 - I & C UNION VILLAGE PH 1 NORTH | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Graham, Bruce W. | 04-Dec-20 |  |  | 86760.05 | 650121.68 | 86760.05 | 86760.05 | Dave Lindsay |  | 02-Feb-21 | 10-Nov-21 | 14-Jan-21 | 05-Mar-21 | 21-Jul-21 | Customer | Customer |  | 0
639657 | 639657 - 2021 BENSON BARRIE UG CABLE REPLACEMENT | 825 - Patterson | 151337 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 09-Apr-21 |  |  | 1261489.08 | 1299478.88 | 1261489.08 | 1261489.08 | Lotto, Jay | Transpw | 12-Jul-21 | 24-Apr-23 | 21-May-21 | 11-May-21 | 07-Sep-21 |  | Contractor |  | 0
639678 | 639678 - JOINT USE PERMIT #HE2020-087, 14TH AVE, MARKHAM | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 10-Nov-21 |  |  | 31533.65 | 26026.62 | 31533.65 | 31533.65 | Reginald Clarke |  | 23-Dec-21 | 26-Jul-23 | 20-Dec-21 | 17-May-22 | 18-May-22 | Locates | Locates |  | 0
639677 | 10165 VICTORIA SQUARE BOULEVARD – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
639693 | 639693 - INSTALL POLE TO MAKE READY ADESSO | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Graham, Bruce W. | 06-May-21 |  |  | 13062.36 | 7133.48 | 13062.36 | 13062.36 | Macdonald, Larry |  | 16-Jun-21 | 03-Nov-21 | 14-Jun-21 | 09-Jun-21 | 09-Jun-21 |  |  |  | 0
639722 | 639722 - LESLIE ST. POLE REALIGNMENT | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Barry, Kenneth | 07-May-21 |  |  | 280584.46 | 234833.72 | 280584.46 | 280584.46 | Macdonald, Steve | K-Line | 09-Jul-21 | 22-Sep-22 | 23-Jun-21 | 31-May-21 | 03-Jul-21 |  |  |  | 0
639729 | SHINING HILL (PHASE 2) - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
639735 | 639735 - TRANSFORMER RELOCATION AT 81 HOLT DRIVE - ALLISTON | 825 - Patterson | 151531 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 09-Sep-22 |  |  | 53324.78 | 22031.87 | 53324.78 | 53324.78 | Lotto, Jay | HapAmp | 17-Nov-22 | 17-Nov-22 | 21-Oct-22 | 03-Oct-22 | 03-Oct-22 |  |  |  | 0
639784 | 639784 - POLE REPLACEMENT 2021 - AURORA PARK POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 29-Jan-21 |  |  | 48912.66 | 48185 | 48912.66 | 48912.66 | Morrow, Joe |  | 26-Mar-21 | 05-Jul-21 | 15-Mar-21 | 16-Feb-21 | 01-Mar-21 |  |  |  | 0
639788 | 639788 - 219 CHAMPLAIN RD/PEN/NS/1PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 29-Apr-21 |  |  | 38090.77 | 33709.66 | 38090.77 | 38090.77 | Lotto, Jay | HapAmp | 08-Jul-21 | 06-Apr-22 | 14-Jun-21 | 10-Jun-21 | 15-Jul-21 |  | Customer |  | 0
639787 | 639787 - 441 HURONIA RD/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 02-Dec-21 |  |  | 69139.57 | 57218.29 | 69139.57 | 69139.57 | Lotto, Jay | HapAmp | 11-Feb-22 | 05-Dec-22 | 14-Jan-22 | 24-Sep-22 | 28-Nov-22 | Customer | Customer |  | 0
639867 | 639867 - 2021 POLE RENEWAL - CN CROSSING - 14TH AVE (LEFTOVER) | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 12-Jan-21 |  |  | 48600 | 50685.19 | 48600 | 48600 | Macdonald, Steve | K-Line | 16-Mar-21 | 03-May-21 | 08-Mar-21 | 04-Feb-21 | 13-Feb-21 |  |  |  | 0
640069 | 640069 - JOINT USE PERMIT HE2021-002- NASHVILLE ROAD @ KLEIN'S CRES. | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 07-Sep-21 |  |  | 9542.27 | 8027.19 | 9542.27 | 9542.27 | Reginald Clarke |  | 27-Oct-21 | 26-Jul-23 | 27-Oct-21 | 03-Nov-21 | 03-Nov-21 |  |  |  | 0
639766 | 639766 - JOINT USE PERMIT #HE2021-001- PARKER AVE- MAPLE GROVE AVE TO ELM GROVE AVE | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 23-Mar-22 |  |  | 6690.08 | 8028.09 | 6690.08 | 6690.08 | Macdonald, Steve | K-Line | 09-Jun-22 | 26-Jul-23 | 09-May-22 | 09-May-22 | 09-May-22 |  |  |  | 0
640071 | 161 YORK BLVD / RHL / NS / 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640107 | 640107 - 2022 TX RENEWAL - 16T314 | 815 - Addiscott | 101508 | Active | 80 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 1 |  | 64560.19 | 3116.81 | 64560.19 | 64560.19 | Dave Lindsay |  | 22-Sep-23 | 22-Sep-23 | 18-Sep-23 |  |  | Filler | Filler |  | 0
640105 | 640105 - 2022 TX RENEWAL - 8T419 | 815 - Addiscott | 101508 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 3 | 3 | 54043.29 | 119193.06 | 54043.29 | 54043.29 | Dave Lindsay |  | 25-Jan-22 | 26-Jul-23 | 19-Jan-22 | 06-Nov-22 | 15-Mar-23 | Filler | Filler |  | 0
640109 | SUNRISE ACQUISITIONS (HIGHWAY 7) INC. - SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2021 | D'Onofrio, Tony | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640137 | 640137 - BUROAK TRANSFORMER RELOCATION | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Murray, Jake R | 10-Jun-21 |  |  | 57568.59 | 43511.25 | 57568.59 | 57568.59 | Horlings, Jake | Somervl | 17-Aug-21 | 31-Aug-22 | 23-Jul-21 | 13-Jul-21 | 16-Jul-21 |  |  |  | 0
640136 | PORTAGE PARKWAY ROAD WIDENING - VAUGHAN | 815 - Addiscott | 152100 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640208 | 640208 - 2021 POLE RENEWAL - BATHURST ST - METROLINX CROSSING | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 20-Sep-21 | 8 | 8 | 338982.68 | 339609.68 | 324509.45 | 338982.68 | Macdonald, Steve | K-Line | 26-Nov-21 | 09-Aug-22 | 08-Nov-21 | 07-Mar-22 | 08-Apr-22 | MC/PUCC Permit | MC/PUCC Permit |  | 14,473.23
640209 | 640209 - NORTH RIVERMEDE - #475 (RECOVERY OF EXISTING TRANSFORMER) | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 27-Jan-21 |  |  | 29224.9 | 1450.87 | 29224.9 | 29224.9 | Dave Lindsay | Somervl | 14-Jul-22 | 26-Jul-23 | 30-Jun-22 |  |  | Customer | Customer |  | 0
640220 | 88 NASHVILLE RD/ VAU/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 2551.8 |  | 0 | East Coordinator |  |  | 24-May-23
640233 | 640233 - JOINT USE PERMIT HE2021-004 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 13-Sep-21 |  |  | 16639.8 | 9179.48 | 16639.8 | 16639.8 | Reginald Clarke |  | 01-Nov-21 | 26-Jul-23 | 01-Nov-21 | 27-Oct-21 | 27-Oct-21 |  |  |  | 0
640243 | 640243 - 2021 EMERGING UG, V16 BRADWICK DR - 16-L40 TO 16-L38 CABLE REPLACEMENT | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 14-May-21 |  |  | 134167.79 | 136698.82 | 134167.79 | 134167.79 | Horlings, Jake | Transpw | 09-Jul-21 | 25-Apr-22 | 25-Jun-21 | 05-Jul-21 | 28-Aug-21 | Contractor | Contractor |  | 0
640252 | 640252 - HIGHWAY NO. 50 - #8865 - INDUSTRIAL/COMMERCIAL BLDG UPGRADE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 30-Mar-21 |  |  | 140175.1 | 143191.28 | 140175.1 | 140175.1 | Dave Lindsay | Somervl | 17-Jun-21 | 07-Mar-22 | 12-May-21 | 30-Jul-21 | 15-Sep-21 | Customer | Customer |  | 0
640255 | 3301 HWY 7 / VAU / NS / CO-SUB | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640269 | 640269 - ANCHOR CONFLICTS - BAYVIEW AVE & VANDORF SDRD | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 08-Mar-21 |  |  | 14935.6 | 15142.9 | 22035.6 | 14935.6 | Macdonald, Larry |  | 22-Apr-21 | 17-Jul-22 | 19-Apr-21 | 21-Apr-21 | 22-Apr-21 |  |  |  | -7,100.00
454133 | 454133 - JOINT USE HE2019-044 | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 17-Nov-20 |  |  | 21879.81 | 13294.86 | 21879.81 | 21879.81 | Macdonald, Larry |  | 23-Feb-21 | 24-Jan-22 | 22-Feb-21 | 28-Feb-21 | 28-Feb-21 |  |  |  | 0
640281 | 640281 - JOINT USE PERMIT HE2021-008 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 25-Mar-22 |  |  | 11798.89 | 8019.74 | 11798.89 | 11798.89 | Macdonald, Steve | K-Line | 09-Jun-22 | 26-Jul-23 | 09-May-22 | 09-May-22 | 09-May-22 |  |  |  | 0
640291 | 640291 - 23M25 FEEDER RELOCATION FOR BARRIE TS UPGRADES | 825 - Patterson | 150259 | Active | 82 | RELEASED |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 706194.18 | 338323.74 | 706194.18 | 706194.18 | Lotto, Jay | Transpw | 20-Oct-23 | 23-Oct-23 | 02-Oct-23 | [5 empty] | 0
640290 | 4600 HIGHWAY 7, MARKHAM, MARKVILLE FORD | 815 - Addiscott | 101761 | Active | 40 | H8 |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640301 | 164 ANNE ST N/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640304 | 640304 - 2021 POLE RENEWAL - RELOCATION OF P48765 AT KIPLING AVE & HURRICANE AVE | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 31-Mar-21 |  |  | 25906.05 | 0 | 25906.05 | 25906.05 | Macdonald, Larry |  | 02-Jun-21 | 03-Aug-21 | 31-May-21 |  |  | Filler | Filler |  | 0
640303 | CUSTOMER INITIATED EXPANSION-55 DUNLOP ST W, BARRIE - 44KV FEEDER EXTENSION | 825 - Patterson | 101763 | Active | 48 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640310 | POLE UPGRADES FOR CARVAL HOMES MAPLE GROVE SUB - SUBD CUSTOMER CAPITAL I&C | 815 - Addiscott | 151531 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640313 | 640313 - 1 REID DR/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 26-Jul-21 |  |  | 60497.78 | 70437.3 | 60497.78 | 60497.78 | Lotto, Jay | HapAmp | 05-Oct-21 | 22-Sep-22 | 08-Sep-21 | 15-Nov-21 | 15-Sep-22 | Customer | Customer |  | 0
640320 | 640320 - 78 MAIN ST. PENETANG - ARIEL ENCROACHMENT SECONDARY SERVICE RELOCATION | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Walters, Geoffrey D | 29-Jul-21 |  |  | 28615.42 | 24179.85 | 28615.42 | 28615.42 | Steve Rumble |  | 23-Sep-21 | 22-Aug-22 | 15-Sep-21 | 13-Oct-21 | 13-Oct-21 | Lines | Lines |  | 0
640323 | UNION VILLAGE (PHASE 2) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
453883 | 453883 - NEW SUBDIVISION 4031 16TH AVENUE | 815 - Addiscott | 101887 | Active | 98 | COMPLETE |  |  | 2021 | Penner, Mitchell | Alarcon, Alejandro | 26-Jan-21 |  |  | 97672.86 | 102354.3 | 97672.86 | 97672.86 | Dave Lindsay | Transpw | 30-Mar-21 | 26-Jul-23 | 10-Mar-21 | 16-Apr-21 | 21-Jul-21 | Customer | Customer |  | 0
640434 | POETRY LIVING (PARKSIDE) LTD. - SUBD RES EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640439 | 640439 - GOULDING AVE PRIVATE ROAD EXTENSION - SUBD COMMERICAL EDS | 815 - Addiscott | 101896 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Swales, Mathew | 22-Oct-21 |  |  | 181082.12 | 184838.63 | 181082.12 | 181082.12 | Dave Lindsay | Transpw | 29-Dec-21 | 26-Jul-23 | 08-Dec-21 | 26-Nov-21 | 05-May-22 |  | Customer |  | 0
640442 | CALDARI RD & RIVERROCK GATE - SWITCHGEAR RELOCATION | 815 - Addiscott | 101761 | Active | 50 | H8 |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640456 | 640456 - 85 VOGELL RD/RHL / NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 95 | COMPLETE |  |  | 2022 | Dibratto, Susan | Diefenbaker, Trevor A | 05-Nov-21 |  |  | 95401.05 | 99680.19 | 95401.05 | 95401.05 | Dave Lindsay | Somervl | 18-Jan-22 | 28-Jul-23 | 17-Dec-21 | 13-May-22 | 08-Dec-22 | Customer | Customer |  | 0
640457 | 11724 DUFFERIN ST / VAU / NS / 1PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 06-Jun-22
640458 | 640458 - 21 PATTERSON RD/BAR/NS/CUSTOMER OWNED STN | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 09-Apr-21 |  |  | 17785.32 | 11051.06 | 17785.32 | 17785.32 | Lotto, Jay |  | 21-May-21 | 22-Nov-21 | 21-May-21 | 01-May-21 | 14-May-21 |  |  |  | 0
640467 | 640467 - 2021 EMERGING UG, M46 MARKLAND ST AND HILLMOUNT RD LOOP SPLIT | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 11-Nov-21 |  |  | 291409.28 | 296301.27 | 257344.28 | 291409.28 | Horlings, Jake | Somervl | 23-Feb-22 | 09-Aug-22 | 23-Dec-21 | 16-Dec-21 | 07-Apr-22 |  | Customer |  | 34,065.00
640466 | A05 GOLF LINKS DRIVE, SWITCHGEAR & CABLE REPLACEMENT | 815 - Addiscott | 151450 | Inactive | 99 | CANCELLED |  |  | 2022 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 22-Sep-22
640469 | HIGHLAND GATE - SUBDIVISION RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 02-Dec-21 |  |  | 0 | 24934.97 |  | 0 | Dave Lindsay |  | 02-Dec-21 | 06-Mar-22 | 02-Dec-21 | 02-Dec-21 | 02-Dec-21 | xBy-passed | xBy-passed
640472 | 525 ESSA RD/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Harris, Geoff L. | Cranley, Stephen |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640474 | 640474 - POLE REPLACEMENT 2022 - REPLACE 2 RAIL CROSSING POLES | 815 - Addiscott | 100867 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 09-Dec-21 | 2 |  | 119173.79 | 52847.41 | 107486.93 | 119173.79 | Reginald Clarke |  | 15-Dec-23 | 16-Oct-23 | 04-Dec-23 | [5 empty] | 11,686.86
640498 | 640498 - BELL BOND CONNECTIONS- MAPLEVIEW DRIVE WEST, BARRIE | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 22-Feb-21 |  |  | 748.96 | 1348.74 | 748.96 | 748.96 | Steve Rumble |  | 08-Apr-21 | 17-Aug-22 | 08-Apr-21 | 09-Mar-21 | 09-Mar-21 |  |  |  | 0
640515 | 640515 - CONNECTION OF BELL BOND- RUTHERFORD ROAD- P49496 | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 18-Feb-21 |  |  | 748.96 | 630.04 | 748.96 | 748.96 | Don Rothman |  | 06-Apr-21 | 17-Aug-22 | 06-Apr-21 | 20-Apr-21 | 20-Apr-21 |  |  |  | 0
640518 | 640518 - CONNECTION OF BELL BONDS- VARIOUS LOCATIONS, VAUGHAN | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 18-Feb-21 |  |  | 1267.79 | 1075.4 | 1267.79 | 1267.79 | Don Rothman |  | 06-Apr-21 | 17-Aug-22 | 06-Apr-21 | 20-Apr-21 | 20-Apr-21 |  |  |  | 0
640520 | 640520 - 2021 LEFT-BEHIND - M37 CABLE REPLACEMENTS, 4 SEGMENTS | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 10-Jun-21 |  |  | 374447.6 | 342396.94 | 341028.6 | 374447.6 | Horlings, Jake | Transpw | 11-Aug-21 | 25-Apr-22 | 23-Jul-21 | 27-Jul-21 | 13-Oct-21 | Contractor | Contractor |  | 33,419.00
640523 | 640523 - 2021 LEFT-BEHIND - V36 CABLE REPLACEMENT, 36-L20 TO 36-L21 | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 14-Jun-21 |  |  | 216412.55 | 199444.36 | 216412.55 | 216412.55 | Horlings, Jake | Transpw | 09-Aug-21 | 18-May-22 | 26-Jul-21 | 28-Oct-21 | 06-Nov-21 | Contractor | Contractor |  | 0
640522 | 640522 - 2021 LB CABLE REPLACEMENT - V18 BARHILL, 3 SEGMENTS | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 25-Jun-21 |  |  | 362389.94 | 327516.9 | 362389.94 | 362389.94 | Horlings, Jake | Transpw | 02-Sep-21 | 25-Apr-22 | 09-Aug-21 | 27-Jul-21 | 25-Aug-21 |  | Contractor |  | 0
640521 | 640521 - 2021 LEFT-BEHIND - M40 CABLE REPLACEMENTS, 2 SEGMENTS | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 21-Jun-21 |  |  | 222136.59 | 193381.26 | 222136.59 | 222136.59 | Horlings, Jake | Transpw | 25-Aug-21 | 25-Apr-22 | 03-Aug-21 | 05-Aug-21 | 31-Aug-21 | Contractor | Contractor |  | 0
640526 | 640526 - 2021 LB CABLE REPLACEMENT - V43 BRUCE ST, 43-69 TO V43FA3037 | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 09-Aug-21 |  |  | 419488.32 | 419288.92 | 419488.32 | 419488.32 | Horlings, Jake | Transpw | 12-Oct-21 | 25-Apr-22 | 20-Sep-21 | 01-Oct-21 | 26-Oct-21 | Contractor | Contractor |  | 0
640525 | 640525 - 2021 LEFT-BEHIND - V38 CABLE REPLACEMENT, 38-180 TO 38-181 | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 29-Jun-21 |  |  | 53610.12 | 43450.16 | 53610.12 | 53610.12 | Horlings, Jake | Somervl | 30-Aug-21 | 25-Apr-22 | 11-Aug-21 | 28-Jul-21 | 06-Aug-21 |  |  |  | 0
640524 | 640524 - 2021 LEFT-BEHIND - V37 CABLE REPLACEMENTS, 3 SEGMENTS | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 13-Jul-21 |  |  | 168191.13 | 136064.28 | 168191.13 | 168191.13 | Horlings, Jake | Somervl | 14-Oct-21 | 25-Apr-22 | 25-Aug-21 | 14-Oct-21 | 12-Nov-21 | Contractor | Contractor |  | 0
640544 | 640544 - 36 WHITE OAKS RD/BAR/NS/1PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 08-Oct-21 |  |  | 40442.3 | 33613.28 | 40442.3 | 40442.3 | Lotto, Jay | HapAmp | 14-Dec-21 | 15-Aug-22 | 19-Nov-21 | 03-Nov-21 | 01-Dec-21 |  |  |  | 0
640546 | 201 FAIRVIEW RD/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 94 | COMPLETE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 26-Dec-22 | 1 | 1 | 53182.52 | 71835.01 | 53182.52 | 53182.52 | Lotto, Jay | HapAmp | 21-Feb-23 | 26-Jul-23 | 13-Feb-23 | 02-Feb-23 | 20-Feb-23 |  |  |  | 0
640618 | 640618 - 541 ESSA ROAD - SUBD RES EDS | 825 - Patterson | 101887 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 23-Sep-22 |  |  | 97825.69 | 90366.33 | 97825.69 | 97825.69 | Lotto, Jay | Transpw | 25-Nov-22 | 26-Jul-23 | 04-Nov-22 | 25-Oct-22 | 04-Nov-22 |  |  |  | 0
640636 | 2021 VAULT LID RENEWAL PROGRAM - V16 - 42 MAPLE AVE. - EXTRA LOCATION | 825 - Patterson | 151526 | Active | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 52489.6 |  | 0 | East Coordinator |  |  | 26-Jul-23
640638 | 2021 VAULT LID RENEWAL PROGRAM - V25 - 41 MULCASTER ST | 825 - Patterson | 151526 | Active | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 7769.85 |  | 0 | East Coordinator |  |  | 26-Jul-23
640649 | 640649 - EQUIPMENT REMOVAL FOR SHINING HILL PHASE 2 - SUB CUST CAP | 815 - Addiscott | 151531 | Active | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Swales, Mathew | 09-Mar-21 |  |  | 11579.89 | 6524.81 | 11579.89 | 11579.89 | Dave Lindsay |  | 26-Apr-21 | 26-Jul-23 | 20-Apr-21 | 27-Apr-21 | 27-Apr-21 | Lines | Lines |  | 0
640663 | 640663 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.2 | 815 - Addiscott | 151587 | Active | 98 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 29-Apr-22 |  |  | 1556638.48 | 1367165.25 | 1529061.01 | 1556638.48 | Macdonald, Steve | K-Line | 26-Aug-22 | 26-Jul-23 | 20-Jun-22 | 09-May-22 | 17-Sep-22 |  | Customer |  | 27,577.47
640665 | 640665 - BIG BAY POINT ROAD - HYDRO CROSSING RELOCATION | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 13-Apr-21 |  |  | 134246.56 | 138541.21 | 134246.56 | 134246.56 | Lotto, Jay | Transpw | 23-Jun-21 | 22-Sep-22 | 28-May-21 | 25-May-21 | 01-Jun-21 | Contractor |  |  | 0
640690 | 640690 - 2022 TX RENEWAL – 8T523 & 15T372 | 815 - Addiscott | 101508 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 2 |  | 52080.2 | 69840.05 | 52080.2 | 52080.2 | Dave Lindsay | Somervl | 15-Feb-22 | 03-Aug-23 | 19-Jan-22 | 18-Aug-22 |  | Filler | Filler |  | 0
640691 | 640691 - 2022 POLE RENEWAL - FONTHILL BLVD & KREIGHOFF AVE, MARKHAM (2021 CARRYOVER) | 815 - Addiscott | 100867 | Active | 99 | ANALYZE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 14-Jun-21 | 3 | 3 | 51996.54 | 54149.81 | 51996.54 | 51996.54 | Kristine Gordon |  | 10-Jun-22 | 26-Jul-23 | 30-May-22 | 29-Nov-22 | 29-Nov-22 | Filler | Filler |  | 0
640709 | 640709 - BRADWICK DR. - #101 | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2022 | Dibratto, Susan | Yuen, Paul | 28-Apr-21 |  |  | 59100.98 | 70333.05 | 59100.98 | 59100.98 | Dave Lindsay | Somervl | 22-Feb-22 | 26-Jul-23 | 28-Jan-22 | 02-Jun-22 | 19-Jul-22 | Customer | Customer |  | 0
640711 | 640711 - 1501 CREDISTONE RD/ VAU/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 07-Jan-22 |  |  | 98643.86 | 81187.29 | 98643.86 | 98643.86 | Dave Lindsay | Somervl | 21-Mar-22 | 26-Jul-23 | 22-Feb-22 | 13-Dec-22 | 20-Mar-23 | Customer | Customer |  | 0
640732 | 640732 - 2021 PADMOUNT TX REPLACEMENT EXTRA BATCH 1 - BARRIE 1PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 03-May-22 | 12 | 7 | 84698.81 | 60022.58 | 84698.81 | 84698.81 | Lotto, Jay |  | 05-Jul-22 | 22-Sep-22 | 14-Jun-22 | 06-May-22 | 06-May-22 |  |  |  | 0
640733 | 640733 - 2021 PADMOUNT TX REPLACEMENT EXTRA BATCH 7 - BARRIE | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 01-Apr-22 | 2 | 1 | 41895.23 | 32848.03 | 41895.23 | 41895.23 | Lotto, Jay |  | 31-May-22 | 22-Sep-22 | 23-May-22 | 25-Aug-22 | 25-Aug-22 | Materials | Materials |  | 0
640805 | 640805 - JOINT USE PERMIT HE2020-076 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 08-Jul-21 |  |  | 8324.03 | 5632.86 | 8324.03 | 8324.03 | Steve Rumble |  | 06-Aug-21 | 30-Mar-22 | 05-Aug-21 | 13-Aug-21 | 18-Aug-21 | Lines | Lines |  | 0
640815 | “1600 TESTON ROAD RESIDENTIAL SUBDIVISION” – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640821 | 9681 ISLINGTON AVE | 815 - Addiscott | 101761 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 4305.01 |  | 0 | East Coordinator | K-Line |  | 07-Feb-23
640823 | 640823 - JOINT USE PERMIT HE2021-022 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 25-Aug-21 |  |  | 14448.05 | 8355.94 | 14448.05 | 14448.05 | Macdonald, Larry |  | 12-Oct-21 | 26-Jul-23 | 12-Oct-21 | 12-Oct-21 | 12-Oct-21 |  |  |  | 0
640826 | 640826 - 2021 EMERGING UG, A10 BATSON DR, CABLE FAILURE REPLACEMENTS | 815 - Addiscott | 151450 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 30-Mar-21 |  |  | 521712.35 | 478641.7 | 521712.35 | 521712.35 | Lamb, Tim | Transpw | 08-Jun-21 | 26-Jul-23 | 11-May-21 | 15-Apr-21 | 14-May-21 |  |  |  | 0
640843 | 640843 - 64/66 GOLF LINKS DR - SWITCHGEAR REMOVAL | 815 - Addiscott | 151531 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 07-Jan-22 |  |  | 246315.79 | 283393.48 | 246315.79 | 246315.79 | Dave Lindsay | Transpw | 06-Apr-22 | 26-Jul-23 | 22-Feb-22 | 11-Mar-22 | 05-May-22 | Customer | Customer |  | 0
640853 | 640853 - LEE AVENUE POLE REPLACEMENT | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Alarcon, Alejandro | 02-Dec-21 |  |  | 19313.53 | 20271.02 | 19313.53 | 19313.53 | Reginald Clarke |  | 02-Feb-22 | 18-Jul-23 | 31-Jan-22 | 16-Mar-22 | 17-May-22 | Locates | Customer |  | 0
640866 | 640866 - 930 ELGIN MILLS RD / RHL / 3PH PAD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Mann, Drew | 03-Jan-23 | 1 |  | 93226.68 | 16054.26 | 93226.68 | 93226.68 | Dave Lindsay | Somervl | 06-Apr-23 | 01-Aug-23 | 15-Mar-23 |  |  | Materials | Materials |  | 0
640867 | VICTORIA SQUARE BLVD - PHASE 1 - CITY OF MARKHAM | 815 - Addiscott | 101762 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640872 | 640872 - DICKSON 48 PHASE 2 - STAGE 1 - SUBD RESIDENTIAL EDS | 815 - Addiscott | 151531 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Swales, Mathew | 18-Aug-21 |  |  | 17850.04 | 12908.26 | 17850.04 | 17850.04 | Dave Lindsay |  | 06-Oct-21 | 26-Jul-23 | 01-Oct-21 | 11-Feb-22 | 05-May-22 | Customer | Customer |  | 0
640891 | 640891 - CUSTOMER INITIATED OH RELOCATION - 88 SIMMONS ST, VAUGHAN | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Zhang, Jiacheng | 21-Jun-21 |  |  | 16757.07 | 17196.91 | 16757.07 | 16757.07 | Ryan Walsh |  | 05-Aug-21 | 25-Aug-22 | 04-Aug-21 | 06-Jul-21 | 03-Aug-21 |  |  |  | 0
640894 | 640894 - 2021 POLE RENEWAL - GUY WIRE REPLACEMENTS, SAFETY CONCERNS FROM CITY OF MARKHAM | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 16-Mar-21 |  |  | 10915.22 | 9630.02 | 18715.22 | 10915.22 | Macdonald, Larry |  | 30-Apr-21 | 20-Sep-21 | 26-Apr-21 | 17-Mar-21 | 19-Mar-21 |  |  |  | -7,800.00
640895 | 640895 - 55 GOULDING AVE, AURORA - 3 PHASE SERVICE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 25-Oct-21 |  |  | 76674.19 | 61891.25 | 76674.19 | 76674.19 | Dave Lindsay | Somervl | 04-Jan-22 | 22-Sep-22 | 07-Dec-21 | 30-May-22 | 19-Jul-22 | Customer | Contractor |  | 0
640906 | 37 JOHNSON STREET - 44KV POLE LINE EXTENSION | 825 - Patterson | 101763 | Active | 50 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640912 | 640912 - JOINT USE PERMIT HE2021-027 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 21-Jul-21 |  |  | 6197.41 | 5118.93 | 6197.41 | 6197.41 | Steve Rumble |  | 20-Aug-21 | 18-Jan-22 | 20-Aug-21 | 01-Sep-21 | 08-Sep-21 |  |  |  | 0
640916 | 640916 - JOINT USE PERMIT HE2021-030 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 21-Jul-21 |  |  | 6922.61 | 3790.73 | 6922.61 | 6922.61 | Steve Rumble |  | 20-Aug-21 | 24-Aug-22 | 20-Aug-21 | 12-Aug-21 | 12-Aug-21 |  |  |  | 0
640921 | 640921 - JOINT USE PERMIT HE2021-032 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 16-Feb-22 |  |  | 12500.52 | 22349.68 | 12500.52 | 12500.52 | Macdonald, Steve | K-Line | 04-May-22 | 26-Jul-23 | 04-Apr-22 | 04-Apr-22 | 04-Apr-22 |  |  |  | 0
640930 | 640930 - 356 KING ROAD – SUBD RES EDS | 815 - Addiscott | 151531 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 02-Mar-22 |  |  | 56196.71 | 8827.7 | 56196.71 | 56196.71 | Dave Lindsay |  | 03-May-22 | 26-Jul-23 | 18-Apr-22 | 01-Nov-22 |  | Customer | Customer |  | 0
640936 | 640936 - 15520 YONGE ST/AUR/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 93 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 24-Mar-22 |  |  | 118883.15 | 120190.67 | 118883.15 | 118883.15 | Dave Lindsay | Somervl | 20-Jun-22 | 26-Jul-23 | 05-May-22 | 15-Nov-22 | 03-May-23 | Customer | Customer |  | 0
640939 | KENNEDY MM MARKHAM LTD. – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640949 | 640949 - 2021 EMERG. UG CABLE REPLACEMENT BRADFORD | 825 - Patterson | 150014 | Inactive | 99 | COMPLETE |  |  | 2021 | Bowman, Todd J | Pollock, Kim | 06-May-21 |  |  | 487912.02 | 481165.07 | 487912.02 | 487912.02 | Lotto, Jay | Transpw | 15-Jul-21 | 22-Nov-21 | 17-Jun-21 | 27-Apr-21 | 31-May-21 |  |  |  | 0
454205 | 454205 - RER - MX - RELOC - KIRBY RD - BARRIE LINE (1907) - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE |  |  | 2021 | Vande Kuyt, Greg | Grahovac, John | 10-Mar-21 |  |  | 333250.49 | 354264.57 | 333250.49 | 333250.49 | Macdonald, Steve |  | 28-May-21 | 15-Feb-22 | 03-May-21 | 19-Apr-21 | 29-Apr-21 |  |  |  | 0
640958 | 640958 - 299 ANNE ST N - SUBD CAP | 825 - Patterson | 151531 | Inactive | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Perks, Dan | 30-Mar-21 |  |  | 30180.11 | 24607.57 | 30180.11 | 30180.11 | Lotto, Jay | HapAmp | 11-Jun-21 | 14-Dec-21 | 19-May-21 | 29-Apr-21 | 22-Jun-21 |  | Customer |  | 0
640960 | 640960 - PINE VALLEY DR. - #10150 (BELL SERVICE) | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Yuen, Paul | 28-Apr-22 |  |  | 51837.29 | 35995.92 | 51837.29 | 51837.29 | Dave Lindsay | Somervl | 04-Jul-22 | 27-Jun-23 | 10-Jun-22 | 18-Aug-22 | 07-Oct-22 | Customer | Customer |  | 0
640971 | 640971 - HUNT AVENUE SUBDIVISION - SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Swales, Mathew | 21-Jan-22 |  |  | 202952.82 | 185767.49 | 202952.82 | 202952.82 | Dave Lindsay | Transpw | 08-Apr-22 | 25-May-22 | 04-Mar-22 | 04-Feb-22 | 17-Mar-22 |  |  |  | 0
640976 | 640976 - HARBOUR POINTE PHASE IV - SUBD RES EDS | 825 - Patterson | 101887 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 06-Sep-22 |  |  | 209045.73 | 205471.94 | 209045.73 | 209045.73 | Lotto, Jay | Transpw | 21-Nov-22 | 14-Aug-23 | 19-Oct-22 | 28-Nov-22 | 13-Dec-22 | Customer | Customer |  | 0
640980 | 640980 - MARKHAM SIDEWALK PROGRAM | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 25-May-21 |  |  | 13279.88 | 12083.42 | 13279.88 | 13279.88 | Macdonald, Larry |  | 20-Jul-21 | 22-Sep-22 | 19-Jul-21 | 09-Aug-21 | 09-Aug-21 | Filler | Filler |  | 0
454254 | 454254 - ICI NEW CONDOMINIUM CONNECTION/9 CLEGG ROAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A | 19-Mar-21 |  |  | 82597.03 | 95627.34 | 82597.03 | 82597.03 | Dave Lindsay | Somervl | 31-May-21 | 03-Oct-22 | 30-Apr-21 | 19-Jul-22 | 07-Oct-22 | Customer | Customer |  | 0
640987 | HIGHWAY NO. 7 WEST - #2851/VAU/NS/CUSTOMER-OWN SUBSTATION | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640992 | 7713 KENNEDY RD / MAR / NS / 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641015 | 641015 - JOINT USE PERMIT HE2021-034 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 10-Jan-22 |  |  | 14688.77 | 7338.28 | 14688.77 | 14688.77 | Reginald Clarke |  | 16-Feb-22 | 26-Jul-23 | 15-Feb-22 | 27-Apr-22 | 27-Apr-22 | Locates | Locates |  | 0
641017 | 3850 & 3836 MAJOR MACKENZIE DR WEST SUBDIVISION - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir | 16-Jan-23 |  |  | 203844.33 | 31895.54 | 203844.33 | 203844.33 | Dave Lindsay |  | 24-Mar-23 | 26-Jul-23 | 20-Mar-23 | 19-Jan-23 | 30-Jan-23 |  |  |  | 0
641019 | 641019 - LINDWIDE DEVELOPMENT - (PHASE 1) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 93 | ANALYZE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 03-Aug-22 |  |  | 73793.52 | 58771.11 | 73793.52 | 73793.52 | Dave Lindsay |  | 04-Nov-22 | 26-Jul-23 | 14-Sep-22 | 17-Aug-22 | 06-Mar-23 | Customer | Customer |  | 0
641031 | 641031 - 38 POYNTZ ST, PENETANGUISHENE - 400A 120/240V SERVICE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 09-Nov-21 |  |  | 31967.77 | 24619.58 | 31967.77 | 31967.77 | Lotto, Jay | HapAmp | 20-Jan-22 | 06-Apr-22 | 21-Dec-21 | 17-Nov-21 | 17-Nov-21 |  |  |  | 0
641045 | 46-56 PATTERSON RD - SUBD RES EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641050 | 641050 - NASHVILLE RD & BARONS ST - SOUTH SIDE | 815 - Addiscott | 101761 | Active | 92 | ANALYZE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander | 02-Jun-23 |  |  | 189803.09 | 113500.38 | 189803.09 | 189803.09 | Macdonald, Steve | K-Line | 04-Aug-23 | 26-Jul-23 | 17-Jul-23 | 02-Jun-23 | 22-Jul-23 |  |  |  | 0
641056 | HYDRO POLE RELOCATION - 7713 KENNEDY RD, MARKHAM, ON | 815 - Addiscott | 101761 | Active | 50 | H8 |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641064 | 2851 HWY 7 - HYDRO POLE RELOCATION - VAUGHAN | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Yuen, Paul |  |  |  | 0 | 1788.18 |  | 0 | East Coordinator |  |  | 22-Sep-22
641083 | 641083 - 3255 RUTHERFORD RD BUILDING D / VAU / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 94 | COMPLETE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 14-Apr-22 |  |  | 82265.13 | 79592.47 | 82265.13 | 82265.13 | Dave Lindsay | Somervl | 07-Jul-22 | 14-Aug-23 | 07-Jun-22 | 15-Sep-22 | 21-Apr-23 | Customer | Customer |  | 0
641086 | 70 ALLSTATE PRKW/ MAR/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 98 | CANCELLED |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A |  |  |  | 0 | 11132.66 |  | 0 | East Coordinator |  |  | 26-Jul-23
641116 | 641116 - 130 VESPRA ST/BAR/UP/3PH PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 20-Jun-22 |  |  | 80022.67 | 71633.97 | 80022.67 | 80022.67 | Lotto, Jay | HapAmp | 02-Sep-22 | 26-Jul-23 | 04-Aug-22 | 28-Jun-22 | 16-Sep-22 |  | Customer |  | 0
641130 | 641130 - 135 INDUSTRIAL PARKWAY N/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 30-Sep-21 |  |  | 30191.5 | 69878.58 | 30191.5 | 30191.5 | Dave Lindsay | Somervl | 06-Dec-21 | 26-Jul-23 | 15-Nov-21 | 27-Oct-21 | 11-Nov-21 |  |  |  | 0
641151 | 641151 - 95 CLEGG RD / MAR / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 30-Aug-21 |  |  | 141030.63 | 173511.41 | 141030.63 | 141030.63 | Dave Lindsay | Somervl | 15-Nov-21 | 18-Jul-22 | 12-Oct-21 | 14-Jan-22 | 17-Mar-22 | Customer | Customer |  | 0
641167 | 641167 - 1400 CREDITSTONE RD. | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Yuen, Paul | 29-Sep-21 |  |  | 107760.65 | 113973.93 | 107760.65 | 107760.65 | Dave Lindsay |  | 09-Feb-22 | 05-Oct-22 | 28-Jan-22 | 07-Oct-22 | 07-Oct-22 | Customer | Customer |  | 0
641168 | 641168 - 160 HENDERSON AVE/RHL/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 96 | ANALYZE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 19-Nov-21 |  |  | 83155.47 | 57208.46 | 83155.47 | 83155.47 | Dave Lindsay | Somervl | 11-Feb-22 | 26-Jul-23 | 07-Jan-22 | 18-Aug-22 | 06-Mar-23 | Customer | Customer |  | 0
641182 | JOHN MCCRAE STREET EXTENSION – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P | 20-Apr-23 |  |  | 79713.19 | 57539.51 | 79161.61 | 79713.19 | Dave Lindsay |  | 21-Jul-23 | 04-Aug-23 | 10-Jul-23 | 02-Feb-23 |  |  |  |  | 551.58
641198 | 641198 - POLE REPLACEMENT 2021 - REPLACE P33475 ON INDUSTRIAL PARKWAY S | 815 - Addiscott | 100867 | Active | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Roy, James | 26-Aug-21 |  |  | 33143.51 | 31777.92 | 33143.51 | 33143.51 | Reginald Clarke |  | 01-Nov-21 | 26-Jul-23 | 25-Oct-21 | 22-Nov-21 | 22-Nov-21 | Filler | Filler |  | 0
641197 | 641197 - VOLTAGE CONVERSION - CONVERT CUSTOMERS ON MORGAN MS INTO 27.6KV SUPPLY, MARKHAM | 815 - Addiscott | 151476 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 17-May-22 |  |  | 1236870.6 | 930506.55 | 1236870.6 | 1236870.6 | Morrow, Joe | Somervl | 01-Mar-23 | 26-Jul-23 | 25-Jul-22 | 11-Aug-22 | 29-Dec-22 | Lines |  |  | 0
641204 | 311 SAUNDERS RD/BAR/SR/3 PHASE PAD | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641206 | HONEY HILL SUBD - CAP POLE RELOCATIONS | 825 - Patterson | 151531 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641235 | 641235 - STRUT INSTALLATION VILLAGE GATE BROWNSTONES | 815 - Addiscott | 151531 | Active | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Alarcon, Alejandro | 23-Sep-21 |  |  | 13013.35 | 7024.64 | 13013.35 | 13013.35 | Reginald Clarke |  | 15-Nov-21 | 26-Jul-23 | 15-Nov-21 | 22-Nov-21 | 22-Nov-21 |  |  |  | 0
641237 | 641237 - 2023 CABLE REPLACEMENT – M44 – COCHRANE DR - SCOLBERG RD - PHASE 1 | 815 - Addiscott | 151913 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 14-Apr-23 |  |  | 1937933.7 | 924429.33 | 1922146.1 | 1937933.7 | Horlings, Jake | Aecon | 11-Sep-23 | 11-Sep-23 | 15-May-23 | 24-Apr-23 |  |  |  |  | 15,787.60
641236 | 2023 CABLE REPLACEMENT – M21 – RAYMERVILLE DR - PHASE 1 | 815 - Addiscott | 151329 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 24-Mar-23 |  |  | 1492534.91 | 665506.8 | 1492534.91 | 1492534.91 | Horlings, Jake | Transpw | 26-Jul-23 | 31-Aug-23 | 01-May-23 | 27-Apr-23 |  |  |  |  | 0
641241 | 641241 - MAJOR MACKENZIE DR. EAST - #4638 | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 03-Jun-21 |  |  | 51745.09 | 34219.14 | 51745.09 | 51745.09 | Dave Lindsay | Somervl | 12-Aug-21 | 09-Aug-23 | 16-Jul-21 | 15-Jul-21 |  |  | Customer |  | 0
641254 | CABLE REPLACEMENT - (V24) - LANGSTAFF - JANE - RUTHERFORD - KEELE, VAUGHAN | 815 - Addiscott | 101781 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 41416.21 |  | 0 | East Coordinator |  |  | 26-Jul-23
641253 | CABLE REPLACEMENT - (V17) - LANGSTAFF - KEELE - RUTHERFORD - DUFFERIN, VAUGHAN | 815 - Addiscott | 101781 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641283 | 5546 MAJOR MACKENZIE DR / MAR / UP / 1PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Dibratto, Susan | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 22-Sep-22
641284 | 641284 - 130 ADDISON HALL CIRCLE/AUR/NS/3 PH | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 29-Sep-21 |  |  | 27354.28 | 41742.66 | 27354.28 | 27354.28 | Dave Lindsay | Somervl | 08-Dec-21 | 22-Sep-22 | 12-Nov-21 | 01-Dec-21 | 15-Mar-22 | Customer | Customer |  | 0
641289 | 641289 - 17 MILLWOOD PARKWAY DEVELOPMENT – SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Alarcon, Alejandro | 04-Jul-22 |  |  | 110563.11 | 98412.03 | 110563.11 | 110563.11 | Dave Lindsay | Transpw | 08-Sep-22 | 04-Jul-23 | 17-Aug-22 | 17-Aug-22 | 08-Dec-22 | Customer | Customer |  | 0
641293 | 641293 - 400 FIRST COMMERCE DR/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 99 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 17-Feb-22 |  |  | 81205.23 | 66389.57 | 81205.23 | 81205.23 | Dave Lindsay | Somervl | 27-Apr-22 | 26-Jul-23 | 01-Apr-22 | 10-Aug-22 | 09-Mar-23 | Customer | Customer |  | 0
641296 | 641296 - HWY 400 CROSSING, SUNNIDALE ROAD | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander | 21-Apr-22 |  |  | 105555.46 | 51711.25 | 105555.46 | 105555.46 | Dan Kish |  | 10-Jun-22 | 24-Apr-23 | 02-Jun-22 | 13-May-22 | 22-Jul-22 |  | Lines |  | 0
641317 | 641317 - 2021 EMERGING OH, RISER TAP CHANGES FOR FEEDER LOAD BALANCING | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 11-May-21 |  |  | 49538.13 | 65832.68 | 49538.13 | 49538.13 | Macdonald, Larry |  | 15-Jun-21 | 26-Apr-22 | 01-Jun-21 | 27-May-21 | 14-Jul-21 |  | Control/SCADA |  | 0
641332 | 641332 - JOINT USE PERMIT HE2021-038- 8025 JANE STREET | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 12-Nov-21 |  |  | 6117.26 | 4631.43 | 6117.26 | 6117.26 | Reginald Clarke |  | 22-Dec-21 | 26-Jul-23 | 22-Dec-21 | 09-Dec-21 | 09-Dec-21 |  |  |  | 0
641344 | 641344 - HIGHWAY NO. 50 - #7805 | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2022 | Dibratto, Susan | Yuen, Paul | 14-Jun-21 |  |  | 140794.28 | 160661.59 | 140794.28 | 140794.28 | Dave Lindsay | Somervl | 09-Mar-22 | 17-Aug-23 | 28-Jan-22 | 28-Sep-22 | 08-Dec-22 | Customer | Customer |  | 0
641345 | 641345 - 400 HURONIA RD/BAR/UP/CUSTOMER OWNED STATION | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 09-Jul-21 |  |  | 12773.59 | 8837.18 | 12773.59 | 12773.59 | Lotto, Jay |  | 01-Sep-21 | 08-May-22 | 30-Aug-21 | 26-Oct-21 | 03-Nov-21 | Customer | Customer |  | 0
641348 | 641348 - 8188 YONGE AND UPLANDS - OVERHEAD WIRE RELOCATION -RICHMOND HILL | 815 - Addiscott | 101761 | Active | 93 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan | 14-Sep-22 |  |  | 157864.42 | 86384.86 | 157864.42 | 157864.42 | Kristine Gordon |  | 24-Nov-22 | 26-Jul-23 | 14-Nov-22 | 08-Nov-22 | 04-Jan-23 |  | Customer |  | 0
641350 | 641350 - 6685 LANGSTAFF ROAD/VAU/NS/ 3-PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A | 10-Sep-21 |  |  | 142280.58 | 70762.86 | 142280.58 | 142280.58 | Dave Lindsay | Somervl | 18-Nov-21 | 18-Jul-23 | 27-Oct-21 | 22-Feb-22 | 17-Mar-22 | Customer | Customer |  | 0
641355 | MARYDALE AVENUE SUBDIVISION – SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 7844.09 |  | 0 | East Coordinator |  |  | 07-Mar-23
641363 | 641363 - 2023 CABLE INJECTION, V31 - LANGSTAFF-WESTON-RUTHERFORD-JANE | 815 - Addiscott | 151458 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 27-Jul-22 |  |  | 1068316.64 | 433514.4 | 1068316.64 | 1068316.64 | Horlings, Jake | Nvinium | 15-Dec-23 | 15-Dec-23 | 07-Sep-22 | 01-Jan-23 |  | Contractor | Contractor |  | 0
641362 | 641362 - 2023 CABLE INJECTION, V23 - HWY 7-KEELE-LANGSTAFF-JANE | 815 - Addiscott | 151364 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 27-Jul-22 |  |  | 11747825.33 | 631074.25 | 11747825.33 | 11747825.33 | Horlings, Jake | Nvinium | 15-Dec-23 | 15-Dec-23 | 07-Sep-22 | 01-Jan-23 | 21-Dec-22 | Contractor | Contractor |  | 0
641361 | 641361 - 2023 CABLE REPLACEMENT, AVIVA PARK RECONFIGURATION | 815 - Addiscott | 151914 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 19-Dec-22 |  |  | 1493670.3 | 61068.93 | 1493670.3 | 1493670.3 | Horlings, Jake | Transpw | 16-Oct-23 | 16-Oct-23 | 01-Aug-23 | [5 empty] | 0
641360 | 641360 - 2022 CABLE REPLACEMENT - A05 - MURRAY DR - GOLF LINKS, AURORA - PHASE 1 | 815 - Addiscott | 151911 | Active | 96 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 23-Dec-21 |  |  | 1014880.68 | 1116469.26 | 998999.83 | 1014880.68 | Dave Lindsay | Transpw | 31-May-22 | 26-Jul-23 | 01-Apr-22 | 21-Apr-22 | 09-Dec-22 | Contractor | Contractor |  | 15,880.85
641329 | DEVON LANE SUBDIVISION – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641366 | 641366 - 4795 CW LEACH RD/ALL/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 22-Nov-21 |  |  | 81441.49 | 104839.71 | 81441.49 | 81441.49 | Lotto, Jay | HapAmp | 01-Feb-22 | 22-Sep-22 | 06-Jan-22 | 17-Aug-22 | 26-Aug-22 | Customer | Customer |  | 0
641370 | 641370 - 4134 16TH AVE/MAR/SR/3PH VAULT | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 21-May-21 |  |  | 14229.07 | 11284.16 | 14229.07 | 14229.07 | Dave Lindsay |  | 07-Jul-21 | 21-Apr-22 | 02-Jul-21 | 21-Jul-21 | 21-Jul-21 | Customer | Customer |  | 0
641381 | 641381 - 100 INDUSTRIAL RD/BRA/UP/3 PHASE PAD | 825 - Patterson | 101919 | Active | 94 | COMPLETE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 29-Mar-23 |  |  | 67364.61 | 58895.56 | 67364.61 | 67364.61 | Lotto, Jay | HapAmp | 23-May-23 | 26-Jul-23 | 11-May-23 | 29-Apr-23 | 29-Apr-23 |  |  |  | 0
641389 | 641389 - 101 MILANI BLVD / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 04-Nov-21 |  |  | 234958.08 | 233756.7 | 234958.08 | 234958.08 | Dave Lindsay | Somervl | 28-Jan-22 | 13-Jul-22 | 16-Dec-21 | 20-Jan-22 | 05-May-22 | Customer | Customer |  | 0
641398 | 641398 - 30 HERITAGE RD / MAR / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 26-Apr-23 |  |  | 165404.5 | 73008.3 | 165404.5 | 165404.5 | Dave Lindsay | Somervl | 20-Jun-23 | 16-Aug-23 | 23-May-23 | 06-Jun-23 |  | Customer |  |  | 0
641407 | 641407 - BLENCATHRA HILL - #18 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Yuen, Paul | 20-Jul-21 |  |  | 40012.5 | 39525.34 | 40012.5 | 40012.5 | Dave Lindsay | Somervl | 22-Sep-21 | 08-May-22 | 02-Sep-21 | 20-Oct-21 | 08-Dec-21 | Customer | Customer |  | 0
641408 | 641408 - NASHVILLE - SWC - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir | 28-Nov-22 |  |  | 1396972.6 | 1386339.03 | 1396972.6 | 1396972.6 | Dave Lindsay | Transpw | 07-Feb-23 | 09-Aug-23 | 11-Jan-23 | 14-Apr-23 |  | Customer |  |  | 0
641435 | ROAD AUTHORITY RELOCATION-UG-CACHET WOODS CRT | 815 - Addiscott | 101762 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641448 | 641448 - ELBAY DEVELOPMENTS – SUBD RES EDS | 815 - Addiscott | 101887 | Active | HO | RELEASED |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 06-Jul-22 |  |  | 106139.5 | 9919.15 | 106139.5 | 106139.5 | Dave Lindsay | Transpw | 15-Sep-22 | 11-Aug-23 | 17-Aug-22 |  |  | Customer | Customer |  | 0
641460 | 641460 - 5011 TESTON RD/ VAU/ UP/ 1PH PAD | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2021 | Joshi, Namrata | Diefenbaker, Trevor A | 04-Nov-21 |  |  | 12932.42 | 6180.58 | 12932.42 | 12932.42 | Reginald Clarke |  | 22-Dec-21 | 26-Jul-23 | 20-Dec-21 | 07-Dec-21 | 07-Dec-21 |  |  |  | 0
641474 | 641474 - MURRY DR, EAST OF NISBET DR | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 28-Oct-21 |  |  | 57098.36 | 60612.06 | 39236.68 | 57098.36 | Macdonald, Steve | K-Line | 14-Dec-21 | 28-Mar-23 | 13-Dec-21 | 26-Nov-21 | 03-Dec-21 |  |  |  | 17,861.68
641484 | 9465 WESTON ROAD - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641493 | 3 JARVIS AVE/AUR/UP/1PH PAD | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 26-Apr-23 |  |  | 59599.13 | 37353.54 | 59599.13 | 59599.13 | Dave Lindsay | HapAmp | 05-May-23 | 28-Jul-23 | 01-May-23 | 01-May-23 |  |  | Customer |  | 0
641487 | 641487 - 2022 CABLE INJECTION - V25 | 815 - Addiscott | 151457 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 10-Nov-21 |  |  | 754839.36 | 716109.86 | 754839.36 | 754839.36 | Horlings, Jake | Nvinium | 31-Dec-22 | 26-Jul-23 | 01-Jan-22 | 01-Jan-22 |  |  |  |  | 0
641495 | 641495 - HIGHWAY NO. 400 - #12001 (ONROUTE)/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 30-Jan-23 |  |  | 63038.94 | 67225.31 | 63038.94 | 63038.94 | Dave Lindsay |  | 07-May-23 | 26-Jul-23 | 05-May-23 | 19-Jan-23 | 09-Jun-23 |  |  |  | 0
641499 | 641499 - BELL BOND CONNECTION- MAJOR MACK WEST OF WESTON ROAD | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 23-Sep-21 |  |  | 1267.79 | 670.55 | 1267.79 | 1267.79 | Don Rothman |  | 29-Oct-21 | 17-Aug-22 | 29-Oct-21 | 28-Nov-21 | 28-Nov-21 |  |  |  | 0
641498 | 641498 - BELL BOND CONNECTIONS- PINE VALLEY DR.- MAJOR MACK TO PINE HEIGHTS DR. | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 16-Jun-21 |  |  | 1527.2 | 1266.32 | 1527.2 | 1527.2 | Don Rothman |  | 14-Jul-21 | 17-Aug-22 | 14-Jul-21 | 12-Jul-21 | 12-Jul-21 |  |  |  | 0
641521 | 641521 - 2022 CABLE INJECTION - M38 - HWY 7 - WARDEN - WOODBINE, MARKHAM | 815 - Addiscott | 151352 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 |  |  | 1545855.99 | 3368.73 | 1545855.99 | 1545855.99 | Horlings, Jake | Nvinium | 31-Dec-22 | 26-Jul-23 | 01-Jan-22 | 01-Jan-22 |  |  |  |  | 0
641520 | 641520 - 2022 CABLE INJECTION - V37 - LANGSTAFF & WESTON, VAUGHAN | 815 - Addiscott | 150134 | Active | 96 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 |  |  | 1697717.11 | 160410.02 | 1697717.11 | 1697717.11 | Horlings, Jake | Nvinium | 31-Dec-22 | 26-Jul-23 | 01-Jan-22 | 01-Jan-22 | 29-Dec-22 |  |  |  | 0
641527 | 9704 MCCOWAN RD/MAR/NS/CUSTOMER-OWNED SUB | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641533 | 641533 - JOINT USE PERMIT HE2021-054- CHURCHILL DR. & ELLIS DR. | 825 - Patterson | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 07-Mar-22 |  |  | 11211.32 | 8606.97 | 11211.32 | 11211.32 | Dan Kish |  | 01-Apr-22 | 26-Jul-23 | 01-Apr-22 | 30-Mar-22 | 30-Mar-22 |  |  |  | 0
641537 | 55 LINE DR / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 1580.7 |  | 0 | East Coordinator |  |  | 27-Jun-23
641547 | BLOCK 18 PROPERTIES INC.– SUBD RES EDS | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641553 | 641553 - RAVINES OF RAINBOW CREEK (PHASE 2) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 14-Apr-23 |  |  | 220344.16 | 214670.06 | 220344.16 | 220344.16 | Dave Lindsay | Transpw | 07-Jun-23 | 04-Aug-23 | 29-May-23 | 26-Oct-22 | 09-Jun-23 |  | Customer |  | 0
641558 | MAIN STREET MARKHAM - #144 | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641562 | 641562 - 317 SAUNDERS RD/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 18-Aug-21 |  |  | 75438.84 | 95191.4 | 75438.84 | 75438.84 | Lotto, Jay | HapAmp | 01-Nov-21 | 09-Aug-23 | 01-Oct-21 | 05-Oct-21 | 02-Dec-22 | Customer | Customer |  | 0
641563 | 344 JOHN ST/RHL/UP/3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 12317.94 |  | 0 | East Coordinator |  |  | 03-Jul-23
641564 | ROAD AUTHORITY RELOC-16TH AVE(W. OF LESLIE ST-E. OF LESLIE ST)-PHASE 1 | 815 - Addiscott | 101762 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641575 | 641575 - 2022 TX VAULT RENEWAL, MAIN ST N UNIONVILLE (4 LOCATIONS) | 815 - Addiscott | 151526 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 11-Jul-22 | 4 | 4 | 493123.05 | 518039.75 | 457020.8 | 493123.05 | Horlings, Jake | HapAmp | 12-Oct-22 | 26-Jul-23 | 24-Aug-22 | 19-Oct-22 | 04-Nov-22 | Filler | Filler |  | 36,102.25
641616 | 641616 - 50 INTERCHANGE WAY / VAU / SR / SEC DEMO | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Joshi, Namrata | Mann, Drew | 10-Jun-21 |  |  | 3443.02 | 2640.99 | 3443.02 | 3443.02 | Dave Lindsay |  | 27-Jul-21 | 22-Apr-22 | 26-Jul-21 | 21-Jul-21 | 21-Jul-21 |  |  |  | 0
641618 | 641618 - HIGHLAND GATE PHASE 3- SUBD RES EDS | 815 - Addiscott | 101887 | Active | 93 | ANALYZE |  |  | 2023 | Penner, Mitchell | Perks, Dan | 19-Dec-22 |  |  | 25880.77 | 35821.49 | 25880.77 | 25880.77 | Dave Lindsay |  | 16-Mar-23 | 26-Jul-23 | 13-Mar-23 | 27-Jan-23 | 03-May-23 |  | Customer |  | 0
641620 | 641620 - 2021 POLE RENEWAL - 37 IDLESWIFT DR, VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Canale, Alfred | 14-May-21 |  |  | 11214 | 5514.9 | 11214 | 11214 | Macdonald, Larry |  | 30-Jun-21 | 26-Apr-22 | 28-Jun-21 | 10-Aug-21 | 10-Aug-21 | Filler | Filler |  | 0
633140 | (WO 633140) DISTRIBUTION AUTOMATION 2020 - 57SP13 - VAUGHAN | 815 - Addiscott | 100886 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 2773.04 |  | 0 | Wong, Henry |  |  | 15-Mar-21
633141 | (WO 633141) DISTRIBUTION AUTOMATION 2020 - 57SP17 - VAUGHAN | 815 - Addiscott | 100886 | Inactive | 99 | CANCELLED |  |  | 2021 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 2911.24 |  | 0 | Wong, Henry |  |  | 15-Mar-21
641639 | 641639 - GUNN STREET/PEEL STREET POLE RELOCATION - ROAD WIDENING | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Harrington, James | 07-Jan-22 |  |  | 63898.08 | 48882.15 | 63898.08 | 63898.08 | Jeremy Wright |  | 19-Jan-22 | 22-Sep-22 | 05-Jan-22 | 05-Jan-22 | 07-Feb-22 |  | Lines |  | 0
641645 | 5TH LINE, TOTTENHAM - RELOCATE POLES FOR NEW DEVELOPMENT | 825 - Patterson | 101763 | Active | 70 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641649 | 2022 CABLE INJECTION - V51 | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel |  |  |  | 0 | 4026.43 |  | 0 | East Coordinator |  |  | 27-Apr-22
641648 | 641648 - 2022 CABLE INJECTION - M26 | 815 - Addiscott | 151355 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 10-Nov-21 |  |  | 1421579.31 | 443626.34 | 1421579.31 | 1421579.31 | Horlings, Jake | Nvinium | 31-Dec-22 | 26-Jul-23 | 01-Jan-22 | 01-Jan-22 |  |  |  |  | 0
641673 | 641673 - JOINT USE PERMIT HE2021-056 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 28-Sep-21 |  |  | 6662.69 | 4328.68 | 6662.69 | 6662.69 | Steve Rumble |  | 28-Oct-21 | 24-Aug-22 | 28-Oct-21 | 13-Oct-21 | 13-Oct-21 |  |  |  | 0
641694 | 641694 - SUNSET SIX – SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2021 | Penner, Mitchell | Alarcon, Alejandro | 30-Aug-21 |  |  | 64314.99 | 56248.53 | 64314.99 | 64314.99 | Dave Lindsay | Transpw | 02-Nov-21 | 22-Sep-22 | 12-Oct-21 | 14-Oct-21 | 02-Dec-21 | Customer | Customer |  | 0
641711 | 385 BASALTIC RD / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641713 | 11430 LESLIE STREET - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641716 | 641716 - 1 COMMERCE ST / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Mann, Drew | 17-Aug-21 |  |  | 76255.72 | 79846.47 | 76255.72 | 76255.72 | Dave Lindsay | Somervl | 29-Oct-21 | 27-Jan-22 | 01-Oct-21 | 27-Oct-21 | 02-Dec-21 | Customer | Customer |  | 0
641738 | MARKHAM RD. - #7650 AT HIGHGLEN AVE. (IVY CHARGING STATION) | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2021 | Dibratto, Susan | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 05-Jan-22
641766 | 641766 - MILL STREET & ROUGE STREET, MARKHAM | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 12-Jul-21 |  |  | 18412.97 | 6775.49 | 18412.97 | 18412.97 | Macdonald, Larry |  | 26-Aug-21 | 22-Sep-22 | 24-Aug-21 | 11-Aug-21 | 11-Aug-21 |  |  |  | 0
641777 | 641777 - 4600 HWY 7/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 94 | COMPLETE |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 19-Jan-22 |  |  | 115902.87 | 99367.17 | 115902.87 | 115902.87 | Dave Lindsay | Somervl | 14-Apr-22 | 26-Jul-23 | 04-Mar-22 | 25-Jan-22 | 20-Mar-23 | Customer | Customer |  | 0
641780 | HUNTINGTON RD, RUTHERFORD RD TO LANGSTAFF RD (SEG 1) | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 09-Jun-22
641781 | 641781 - HUNTINGTON RD, MAJOR MACKENZIE DR TO EAST CORNERS BLVD (DEV) | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander | 16-Dec-21 |  |  | 541529.12 | 618386.73 | 531282.54 | 541529.12 | Morrow, Joe | Transpw | 19-Jul-22 | 26-Jul-23 | 09-May-22 | 11-May-22 | 04-Oct-22 | Materials | Customer |  | 10,246.58
641784 | 2022 SG REPL - BATCH 2 - MARKHAM | 815 - Addiscott | 103659 | Inactive | 99 | CANCELLED |  |  | 2022 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 22-Aug-22
641783 | 641783 - 2022 SG REPL - BATCH 1 - AURORA | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 01-Dec-21 | 2 | 2 | 86835.95 | 60960.86 | 86835.95 | 86835.95 | Horlings, Jake |  | 31-Dec-22 | 26-Jul-23 | 01-Jan-22 | 23-Jan-22 | 01-Nov-22 | Filler |  |  | 0
641790 | 641790 - 2022 SG REPL - BATCH 8 - VAUGHAN | 815 - Addiscott | 100859 | Active | 92 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Dec-21 | 8 | 8 | 689728.45 | 665914.64 | 689728.45 | 689728.45 | Horlings, Jake | Somervl | 31-Dec-22 | 07-Dec-23 | 01-Jan-22 | 13-May-22 | 07-Jun-23 | Filler | Filler |  | 0
641789 | 2022 SG REPL - BATCH 7 - VAUGHAN | 815 - Addiscott | 100859 | Inactive | 99 | CANCELLED |  |  | 2022 | Tenorlas, Reynaldo | Roy, James |  | 10 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 02-Feb-23
641788 | 2022 SG REPL - BATCH 6 - VAUGHAN | 815 - Addiscott | 100859 | Inactive | 99 | CANCELLED |  |  | 2022 | Tenorlas, Reynaldo | Roy, James |  | 8 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 02-Feb-23
641787 | 2022 SG REPL - BATCH 5 - VAUGHAN | 815 - Addiscott | 100859 | Inactive | 99 | CANCELLED |  |  | 2022 | Tenorlas, Reynaldo | Roy, James |  | 9 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 02-Feb-23
641786 | 641786 - 2022 SG REPL - BATCH 4 - VAUGHAN | 815 - Addiscott | 100859 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Dec-21 | 8 |  | 707612.02 | 620023.87 | 707612.02 | 707612.02 | Horlings, Jake | Somervl | 31-Dec-22 | 11-Dec-23 | 01-Jan-22 | 17-Apr-22 |  | Filler |  |  | 0
641785 | 641785 - 2022 SG REPL - BATCH 3 - RICHMOND HILL | 815 - Addiscott | 100859 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 01-Dec-21 | 1 | 1 | 93906.56 | 92136.38 | 93906.56 | 93906.56 | Horlings, Jake | Somervl | 31-Dec-22 | 14-Aug-23 | 01-Jan-22 | 21-Jul-22 | 08-Dec-22 | Filler |  |  | 0
641797 | 641797 - 2022 SG REPL - AUTO 43-L17 - VAUGHAN | 815 - Addiscott | 100859 | Active | 99 | COMPLETE | High | SwGear | 2022 | Tenorlas, Reynaldo | Roy, James | 16-Mar-22 | 1 | 1 | 162268.04 | 167027.16 | 162268.04 | 162268.04 | Horlings, Jake | Somervl | 27-May-22 | 14-Aug-23 | 29-Apr-22 | 02-Dec-22 | 02-Dec-22 | Filler | Filler |  | 0
641796 | 641796 - 2022 SG REPL - AUTO 17-L80 - VAUGHAN | 815 - Addiscott | 100859 | Active | 99 | COMPLETE | High | SwGear | 2022 | Tenorlas, Reynaldo | Roy, James | 16-Mar-22 | 1 | 1 | 168278.5 | 160295.83 | 168278.5 | 168278.5 | Horlings, Jake | Somervl | 02-Jun-22 | 26-Jul-23 | 29-Apr-22 | 05-Jul-22 | 01-Sep-22 | Filler | Filler |  | 0
641795 | 641795 - 2022 SG REPL - AUTO 9SC32 - RH | 815 - Addiscott | 100859 | Active | 99 | COMPLETE | High | SwGear | 2022 | Tenorlas, Reynaldo | Roy, James | 16-Mar-22 | 1 | 1 | 177493.68 | 187281.98 | 177493.68 | 177493.68 | Horlings, Jake | Somervl | 02-Jun-22 | 26-Jul-23 | 29-Apr-22 | 05-Jul-22 | 01-Sep-22 | Filler | Filler |  | 0
641794 | 641794 - 2022 SG REPL - AUTO 39SUG001 - MARKHAM | 815 - Addiscott | 100859 | Active | 99 | COMPLETE | High | SwGear | 2022 | Tenorlas, Reynaldo | Roy, James | 28-Feb-22 | 1 | 1 | 250400.47 | 238654.21 | 250400.47 | 250400.47 | Horlings, Jake | Somervl | 03-Jun-22 | 26-Jul-23 | 26-Apr-22 | 05-Jul-22 | 28-Jul-22 | Filler | Filler |  | 0
641793 | 641793 - 2022 SG REPL - AUTO 21SUG007 - MARKHAM | 815 - Addiscott | 100859 | Active | 99 | COMPLETE | High | SwGear | 2022 | Tenorlas, Reynaldo | Roy, James | 01-Dec-21 | 1 | 1 | 164689.11 | 191280.61 | 164689.11 | 164689.11 | Horlings, Jake | Somervl | 31-Dec-22 | 26-Jul-23 | 01-Jan-22 | 15-Sep-22 | 04-Nov-22 | Filler |  |  | 0
641792 | 641792 - 2022 SG REPL - AUTO 43SUG002 - MARKHAM | 815 - Addiscott | 100859 | Active | 99 | COMPLETE | High | SwGear | 2022 | Tenorlas, Reynaldo | Roy, James | 07-Feb-22 | 1 | 1 | 180858.26 | 204178.66 | 180858.26 | 180858.26 | Horlings, Jake | Somervl | 27-Jun-22 | 26-Jul-23 | 01-Jun-22 | 15-Sep-22 | 04-Nov-22 | Filler | Filler |  | 0
641791 | 641791 - 2022 SG REPL - AUTO 31SUG009 - MARKHAM | 815 - Addiscott | 100859 | Active | 99 | COMPLETE | High | SwGear | 2022 | Tenorlas, Reynaldo | Roy, James | 07-Feb-22 | 1 | 1 | 171636.03 | 195510.57 | 171636.03 | 171636.03 | Horlings, Jake | Somervl | 20-May-22 | 26-Jul-23 | 26-Apr-22 | 21-Sep-22 | 04-Nov-22 | Filler | Filler |  | 0
641798 | NASHVILLE - SWC - CUST CAPITAL EQUIPMENT REMOVALS | 815 - Addiscott | 151531 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641801 | 641801 - HUNTINGTON RD & LANGSTAFF RD | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander | 02-Dec-21 |  |  | 93956.54 | 130013.61 | 93956.54 | 93956.54 | Morrow, Joe |  | 19-May-22 | 23-May-23 | 09-May-22 | 05-May-22 | 09-May-22 | Materials |  |  | 0
641802 | 641802 - 8484 & 8470 DUFFERIN ST / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 06-Oct-21 |  |  | 78790.41 | 52899.94 | 78790.41 | 78790.41 | Dave Lindsay | Somervl | 17-Dec-21 | 17-Jul-22 | 18-Nov-21 | 17-Nov-21 | 11-Feb-22 |  | Customer |  | 0
641813 | 641813 - SUNSHINE VILLAGE - SUBD RES EDS | 825 - Patterson | 101887 | Active | HO | RELEASED |  |  | 2023 | Penner, Mitchell | Perks, Dan | 29-Nov-22 |  |  | 301412.27 | 54605.23 | 301412.27 | 301412.27 | Lotto, Jay | Transpw | 06-Feb-23 | 04-Aug-23 | 12-Jan-23 |  |  | Customer | Customer |  | 0
641816 | 641816 - WOODBINE AVE. - #10950 & #10952 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Yuen, Paul | 18-Aug-21 |  |  | 164686.81 | 158857.25 | 164686.81 | 164686.81 | Dave Lindsay | Somervl | 02-Mar-22 | 25-Jun-23 | 28-Jan-22 | 06-Feb-22 | 05-May-22 | Customer | Customer |  | 0
641817 | BIG BAY POINT TOWNS - SUBD RES EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641819 | 9113-9125 BATHURST STREET ENCLAVE TOWNHOMES – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641830 | 641830 - 2023 EMERGING UG, M14 NEW SWITCHGEAR AT 4 RICHWOOD DR | 815 - Addiscott | 151450 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Handy, James | 06-Dec-22 |  |  | 198743.44 | 30113.42 | 198743.44 | 198743.44 | Horlings, Jake | Transpw | 31-Aug-23 | 31-Aug-23 | 03-Jul-23 | [5 empty] | 0
641800 | YONGE NORTH SUBWAY EXTENSION - EEB3 - METROLINX | 815 - Addiscott | 151546 | Active | 70 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641828 | AURORA GO STN IMPROVEMENTS GUY POLE RELOCATION - METROLINX | 815 - Addiscott | 150591 | Active | 70 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator | K-Line |  | 20-Jul-20
641825 | 641825 - AURORA GO SCANLON PARKING LOT POLE RELOCATION - METROLINX | 815 - Addiscott | 150591 | Active | 84 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin | 09-Dec-22 |  |  | 122250.15 | 165256.16 | 122250.15 | 122250.15 | Reginald Clarke |  | 14-Mar-23 | 16-Aug-23 | 21-Feb-23 | 14-Feb-23 |  |  |  |  | 0
641873 | 76 NOVAN CRES/AUR/UP/1PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641872 | 641872 - 2022 DA - 09MSS002 - MARKHAM | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2022 | Tenorlas, Reynaldo | Roy, James | 24-Nov-21 | 1 | 1 | 149210.62 | 138762.25 | 149210.62 | 149210.62 | Reginald Clarke |  | 18-Feb-22 | 22-Sep-22 | 01-Feb-22 | 31-Jan-22 | 17-Feb-22 |  |  |  | 0
641871 | 641871 - 2022 DA - V26SL3004 - VAUGHAN | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2022 | Tenorlas, Reynaldo | Roy, James | 24-Nov-21 | 1 | 1 | 123918.39 | 172043.69 | 123918.39 | 123918.39 | Reginald Clarke |  | 17-Feb-22 | 22-Sep-22 | 01-Feb-22 | 16-Feb-22 | 15-Mar-22 | Filler | Filler |  | 0
641870 | 641870 - 2022 DA - V25SL3088 - VAUGHAN | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2022 | Tenorlas, Reynaldo | Roy, James | 26-Nov-21 | 1 | 1 | 101263.75 | 84882.86 | 101263.75 | 101263.75 | Reginald Clarke |  | 11-Feb-22 | 22-Sep-22 | 01-Feb-22 | 23-Feb-22 | 03-Mar-22 | Filler | Filler |  | 0
641869 | 641869 - 2022 DA - 27MSS-2 - MARKHAM | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE | High | DA | 2022 | Tenorlas, Reynaldo | Roy, James | 26-Nov-21 | 1 | 1 | 107004.01 | 98900.77 | 107004.01 | 107004.01 | Kristine Gordon |  | 14-Feb-22 | 22-Sep-22 | 01-Feb-22 | 11-May-22 | 09-Jun-22 | Filler | Filler |  | 0
641868 | 641868 - 2022 DA - M21SP3038 - MARKHAM | 815 - Addiscott | 100886 | Active | 84 | ACTIVE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 29-Mar-22 | 1 | 0 | 169517.46 | 143601.54 | 169517.46 | 169517.46 | Horlings, Jake | Somervl | 15-Jun-22 | 08-Aug-23 | 19-May-22 | 22-Dec-22 |  | Filler | Filler |  | 0
641877 | 509 & 521 BAYFIELD ST/BAR/UP/CUSTOMER OWNED STN | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641880 | 490 HOLLAND ST/BRA/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641884 | 641884 - JOINT USE PERMIT HE2021-063 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 28-Sep-21 |  |  | 6662.69 | 4240.98 | 6662.69 | 6662.69 | Steve Rumble |  | 28-Oct-21 | 24-Aug-22 | 28-Oct-21 | 14-Oct-21 | 14-Oct-21 |  |  |  | 0
641890 | GARDEN HOMES (MARKHAM) DEVELOPMENT – SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2022 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641916 | 641916 - 2022 POLE RENEWAL - YORK & DURHAM LINE - 5 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 01-Dec-21 | 5 | 5 | 98257.52 | 92806 | 98257.52 | 98257.52 | Ryan Walsh |  | 19-Jan-22 | 08-Jun-22 | 04-Jan-22 | 04-Jan-22 | 31-Jan-22 |  |  |  | 0
641915 | 641915 - 2022 POLE REBUILD - OAKBANK RD - 9 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 21-Dec-21 | 9 | 9 | 112563.75 | 147405.05 | 112563.75 | 112563.75 | Morrow, Joe |  | 13-Jul-22 | 22-Sep-22 | 27-Jun-22 | 27-Jun-22 | 11-Aug-22 |  |  |  | 0
641914 | 641914 - 2022 POLE REBUILD - IDLESWIFT DR - 22 POLES | 815 - Addiscott | 100867 | Active | 93 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 06-Jun-22 | 22 | 22 | 324498.71 | 362585.02 | 324498.71 | 324498.71 | Morrow, Joe |  | 27-Feb-23 | 26-Jul-23 | 03-Jan-23 | 03-Jan-23 | 28-Mar-23 |  | Customer |  | 0
641918 | 641918 - 2022 TX RENEWAL - BATCH 2 - 7 TX | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 7 | 7 | 75680.4 | 75671.71 | 75680.4 | 75680.4 | Dave Lindsay |  | 04-Feb-22 | 26-Jul-23 | 19-Jan-22 | 04-May-22 | 13-Jun-22 | Filler | Filler |  | 0
641917 | 641917 - 2022 TX RENEWAL - BATCH 1 - 15 TX | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 15 | 15 | 229290.34 | 206293.82 | 229290.34 | 229290.34 | Horlings, Jake | Somervl | 17-Mar-22 | 26-Jul-23 | 19-Jan-22 | 25-Jan-22 | 22-Jun-22 | Filler | Filler |  | 0
641921 | 641921 - 2022 SWGR REPLACEMENT - SC13220 - BARRIE - 33 CLOUGHLEY DR. | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 01-Dec-21 | 1 | 1 | 27427.67 | 29039.21 | 27427.67 | 27427.67 | Lotto, Jay |  | 27-Jan-22 | 22-Sep-22 | 25-Jan-22 | 02-Sep-22 | 02-Sep-22 | Filler | Filler |  | 0
641920 | 641920 - 2022 SWGR REPLACEMENT - SC4627 - BARRIE - 2 VICTORIA ST. | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 01-Dec-21 | 1 | 1 | 26398.56 | 24470.05 | 26398.56 | 26398.56 | Lotto, Jay |  | 27-Jan-22 | 22-Sep-22 | 25-Jan-22 | 14-Jan-22 | 14-Jan-22 |  |  |  | 0
641924 | 641924 - 2022 SWGR REPLACEMENT - SC4450 - BARRIE - 160 BURNS CIRCLE | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 01-Dec-21 | 1 | 1 | 31361.74 | 29807.47 | 31361.74 | 31361.74 | Lotto, Jay |  | 27-Jan-22 | 26-Sep-22 | 25-Jan-22 | 23-Sep-22 | 23-Sep-22 | Filler | Filler |  | 0
641926 | 641926 - 40 ALBERT ST - POLE RELOCATION - MARKHAM | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2021 | Murray, Jake R | Corriveau, Tom N | 22-Sep-21 |  |  | 19760.61 | 15615.16 | 19760.61 | 19760.61 | Reginald Clarke |  | 19-Nov-21 | 26-Jul-23 | 16-Nov-21 | 02-Nov-21 | 02-Nov-21 |  |  |  | 0
641925 | 641925 - 2022 SWGR REPLACEMENT - SC13536 - BARRIE - 75 HANMER ST. EAST | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE | High | SwGear | 2022 | Bowman, Todd J | Walters, Geoffrey D | 10-Dec-21 | 1 | 1 | 143155.91 | 147144.73 | 143155.91 | 143155.91 | Lotto, Jay | HapAmp | 05-Apr-22 | 22-Sep-22 | 25-Feb-22 | 01-Jun-22 | 29-Jun-22 | Filler | Filler |  | 0
641646 | 641646 - SPAN GUY TRANSFER ON STEELES AVE W - JU1500079 POLE REMOVAL | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 03-Jun-21 |  |  | 14856 | 14681.58 | 14856 | 14856 | Macdonald, Larry |  | 20-Jul-21 | 26-Apr-22 | 19-Jul-21 | 19-Aug-21 | 19-Aug-21 | Filler | Filler |  | 0
454264 | 454264 - ICI NEW CONDOMINIUM CONNECTION/175 MILWAY AVE | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 14-Jun-21 |  |  | 49152.77 | 10658.56 | 49152.77 | 49152.77 | Dave Lindsay |  | 05-Aug-21 | 03-Aug-23 | 27-Jul-21 |  |  | Customer | Customer |  | 0
452551 | INSTALL 4 NEW CCTS OVER CNYARD/INSTALL 4 NEW CCTS OVER CNYARD | 815 - Addiscott | 101036 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 94982.72 | 1062510 | 1062510 | Persaud, Ryan |  |  | 10-Feb-22 | [6 empty] | 0
452725 | (WO 452725 was 316430) Cable Replacement - V22 - 251 Doney Cres | 815 - Addiscott | 101781 | Inactive | 99 | CANCELLED |  |  | 2022 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan | Transpw |  | 20-Nov-17
641934 | 641934 - 2022 TX RENEWAL - BATCH 3 - 13 TX | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 10-Nov-21 | 13 | 13 | 221918.76 | 227754.61 | 221918.76 | 221918.76 | Dave Lindsay | Somervl | 11-Mar-22 | 01-Sep-23 | 19-Jan-22 | 11-Feb-22 | 02-Dec-22 | Filler | Filler |  | 0
641937 | 641937 - 2023 TX RENEWAL - BATCH 10 - 19 TX | 815 - Addiscott | 101508 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 | 19 |  | 495858.42 | 100300.02 | 510581.48 | 495858.42 | Dave Lindsay | Somervl | 15-Mar-23 | 21-Sep-23 | 01-Jan-23 | 20-Mar-23 |  | Filler |  |  | -14,723.06
641936 | 641936 - 2022 TX RENEWAL - BATCH 4 - 17 TX | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 03-Mar-22 | 17 | 17 | 317479.81 | 237101.78 | 317479.81 | 317479.81 | Dave Lindsay | Somervl | 28-Jun-22 | 19-Jul-23 | 26-Apr-22 | 19-Apr-22 | 18-Aug-22 |  | Filler |  | 0
641938 | 641938 - 2022 DISTRIBUTION AUTOMATION - BARRIE - FAIRVIEW RD. | 825 - Patterson | 100886 | Active | 99 | COMPLETE | High | DA | 2022 | Bowman, Todd J | Walters, Geoffrey D | 29-Dec-21 | 1 | 1 | 194179.67 | 140880.44 | 194179.67 | 194179.67 | Dan Kish |  | 21-Mar-22 | 26-Jul-23 | 01-Mar-22 | 07-Feb-22 | 30-Mar-22 |  | Lines |  | 0
641939 | 641939 - 2022 DISTRIBUTION AUTOMATION - BARRIE - WELLINGTON ST. EAST OF BAYFIELD | 825 - Patterson | 100886 | Active | 99 | COMPLETE | High | DA | 2022 | Bowman, Todd J | Walters, Geoffrey D | 29-Dec-21 | 1 | 1 | 249636.46 | 178571.88 | 249636.46 | 249636.46 | Dan Kish |  | 08-Apr-22 | 26-Jul-23 | 01-Mar-22 | 02-Feb-22 | 21-Jun-22 |  | Weather |  | 0
641940 | 641940 - 2022 DISTRIBUTION AUTOMATION - BARRIE - BAYVIEW & BALDWIN | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE | High | DA | 2022 | Bowman, Todd J | Walters, Geoffrey D | 29-Dec-21 | 1 | 1 | 226073.89 | 192131.55 | 226073.89 | 226073.89 | Dan Kish |  | 13-Apr-22 | 22-Sep-22 | 10-Mar-22 | 08-Mar-22 | 30-Mar-22 |  |  |  | 0
641942 | 641942 - 2022 DISTRIBUTION AUTOMATION - AURORA - INDUSTRIAL PARKWAY | 815 - Addiscott | 100886 | Active | 98 | COMPLETE | High | DA | 2022 | Bowman, Todd J | Walters, Geoffrey D | 24-Jan-22 | 1 | 1 | 241744.98 | 216192.05 | 241744.98 | 241744.98 | Kristine Gordon |  | 30-May-22 | 26-Jul-23 | 13-Apr-22 | 14-Jun-22 | 15-Aug-22 | Filler | Filler |  | 0
641946 | 641946 - 135 SPY CRT/MAR/UP/3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 28-Sep-21 |  |  | 58224.1 | 49735.18 | 58224.1 | 58224.1 | Dave Lindsay | Somervl | 09-Dec-21 | 23-Feb-22 | 12-Nov-21 | 16-Nov-21 | 08-Dec-21 | Customer |  |  | 0
641950 | 641950 - 2022 DISTRIBUTION AUTOMATION - AURORA - ENGELHARD DR. | 815 - Addiscott | 100886 | Active | 96 | ANALYZE | High | DA | 2022 | Bowman, Todd J | Walters, Geoffrey D | 25-Jan-22 | 1 | 1 | 205358.83 | 228548.54 | 205358.83 | 205358.83 | Kristine Gordon |  | 05-Jul-22 | 26-Jul-23 | 31-May-22 | 13-Jun-22 | 24-Nov-22 | Filler | Materials |  | 0
641974 | 428 LITTLE AVE - SUBD RES EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641989 | DUMMY WORK ORDER | 815 - Addiscott | 101763 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642037 | 642037 - VMC BLOCK 3N – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 20-Jan-23 |  |  | 3035821.47 | 808405.97 | 3035821.47 | 3035821.47 | Dave Lindsay | Transpw | 30-Nov-23 | 30-Nov-23 | 06-Mar-23 | 10-Feb-23 |  |  |  |  | 0
642039 | 642039 - 20 ST. PAUL'S CRESCENT/BAR/NS/3PH | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Harris, Geoff L. | 18-Aug-21 |  |  | 17321.01 | 6067.46 | 17321.01 | 17321.01 | Lotto, Jay |  | 07-Oct-21 | 14-Aug-22 | 01-Oct-21 | 08-Sep-21 | 07-Sep-21 |  |  |  | 0
642041 | 642041 - DICKSON 48 PHASE 2 - STAGE 2 - SUBD RESIDENTIAL EDS | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir | 18-Aug-22 |  |  | 115489.97 | 14836.34 | 115489.97 | 115489.97 | Dave Lindsay |  | 28-Oct-22 | 26-Jul-23 | 04-Oct-22 | 08-Sep-22 | 06-Mar-23 | Customer | Customer |  | 0
642063 | 642063 - 6830 4TH LINE/TOT/NS/3PH PAD | 825 - Patterson | 101919 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 21-Mar-23 |  |  | 41673.08 | 36072.5 | 41673.08 | 41673.08 | Lotto, Jay | HapAmp | 23-May-23 | 26-Jul-23 | 09-May-23 | 05-Jun-23 | 29-Jun-23 | Customer | Customer |  | 0
642067 | HARRIS AVENUE DEVELOPMENT – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 79 | PPS INCOMPLETE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 174536.55 | 41429.84 | 174536.55 | 174536.55 | East Coordinator |  |  | 26-Jul-23 | [6 empty] | 0
642073 | 642073 - 829 ESSA RD - SUBD RES EDS - NET ZERO SUBDIVISION | 825 - Patterson | 101887 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 29-Nov-21 |  |  | 131739.8 | 130130.82 | 131739.8 | 131739.8 | Lotto, Jay | Transpw | 03-Feb-22 | 26-Jul-23 | 14-Jan-22 | 25-Apr-22 | 05-May-22 | Customer | Customer |  | 0
642084 | 339,341 VETERANS DR - SUBD RES EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642083 | 642083 - 55 DUNLOP ST W/BAR/SR/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 19-Jul-21 |  |  | 19311.71 | 9003.83 | 19311.71 | 19311.71 | Lotto, Jay | HapAmp | 14-Sep-21 | 19-May-22 | 30-Aug-21 | 02-Aug-21 | 20-Sep-21 |  | Customer |  | 0
640913 | 640913 - JOINT USE PERMIT HE2021-028 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 24-Jun-21 |  |  | 3665 | 2145.1 | 3665 | 3665 | Steve Rumble |  | 23-Jul-21 | 21-Aug-22 | 23-Jul-21 | 21-Jul-21 | 21-Jul-21 |  |  |  | 0
642098 | 642098 - 65 WELHAM RD/BAR/SR/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 19-Jul-21 |  |  | 17632.41 | 9251.14 | 17632.41 | 17632.41 | Lotto, Jay | HapAmp | 14-Sep-21 | 19-May-22 | 30-Aug-21 | 30-Jul-21 | 09-Aug-21 |  |  |  | 0
642099 | 642099 - QUEEN'S PARK (WELLINGTON D1 CITY PROJECT), BARRIE - RELOCATE POLES FOR RD WORKS | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2022 | Pelleja, Emily | Harrington, James | 03-Mar-22 |  |  | 241527.09 | 138791.88 | 241527.09 | 241527.09 | Dan Kish |  | 27-May-22 | 22-Sep-22 | 14-Apr-22 | 20-Apr-22 | 25-May-22 | Lines |  |  | 0
642105 | GARDEN HOMES (MARKHAM) DEVELOPMENT – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642116 | 642116 - 65 WELHAM RD/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 17-Feb-22 |  |  | 68656.59 | 55172.22 | 68656.59 | 68656.59 | Lotto, Jay | HapAmp | 28-Apr-22 | 22-Sep-22 | 01-Apr-22 | 22-Mar-22 | 19-Sep-22 | Customer | Customer |  | 0
642140 | 642140 - 2022 POLE REBUILD - PARKWAY AVE - 4 POLES | 815 - Addiscott | 100867 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 01-Dec-21 | 4 | 4 | 64779.49 | 63819.94 | 64779.49 | 64779.49 | Morrow, Joe |  | 25-Jul-22 | 26-Jul-23 | 14-Jul-22 | 14-Jun-22 | 11-Aug-22 |  |  |  | 0
642162 | 480 MILLER PARK AVE/BRA/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642182 | 642182 - TFP AURORA DEVELOPMENT - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Swales, Mathew | 09-Nov-22 |  |  | 456739.05 | 491024.12 | 369009.05 | 456739.05 | Dave Lindsay | Transpw | 03-Feb-23 | 26-Jul-23 | 11-Jan-23 | 14-Feb-23 | 03-May-23 | Contractor | Customer |  | 87,730.00
642186 | 7515 MARTIN GROVE RD / VAU / UP / 1PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 2654.06 |  | 0 | East Coordinator |  |  | 20-Jul-20
642198 | 642198 - RUTHERFORD RD. PH.3 - PETER RUPERT INTERSECTION | 815 - Addiscott | 151553 | Active | 95 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Barry, Kenneth | 01-Mar-22 |  |  | 153995.66 | 398153.5 | 153995.66 | 153995.66 | Morrow, Joe |  | 29-Apr-22 | 26-Jul-23 | 13-Apr-22 | 28-Mar-21 | 02-May-21 |  | COVID19 |  | 0
642218 | 642218 - 2022 TX RENEWAL - 23T672 | 815 - Addiscott | 101508 | Active | 96 | ANALYZE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 11-Mar-22 | 3 | 3 | 47310.96 | 68557.48 | 47310.96 | 47310.96 | Dave Lindsay |  | 26-Apr-22 | 26-Jul-23 | 26-Apr-22 |  | 06-Mar-23 | Filler | Filler |  | 0
642217 | 642217 - 2022 TX RENEWAL - BATCH 8 - 4 TX | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 12 | 12 | 88589.77 | 92006.19 | 88589.77 | 88589.77 | Horlings, Jake |  | 02-Feb-22 | 22-Sep-22 | 19-Jan-22 | 10-Mar-22 | 17-May-22 | Filler | Filler |  | 0
642216 | 642216 - 2022 TX RENEWAL - BATCH 6 - 14 TX | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-Nov-21 | 14 | 14 | 219091.27 | 184792.25 | 219091.27 | 219091.27 | Horlings, Jake | Somervl | 15-Mar-22 | 05-Sep-23 | 19-Jan-22 | 25-Jan-22 | 08-Dec-22 | Filler | Filler |  | 0
642222 | 642222 - 8440 HWY 27 | 815 - Addiscott | 101761 | Active | 99 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander | 30-May-22 |  |  | 17775.57 | 19084.09 | 17775.57 | 17775.57 | Kristine Gordon |  | 20-Jul-22 | 26-Jul-23 | 18-Jul-22 | 06-Dec-22 | 06-Dec-22 | Customer | Customer |  | 0
642223 | 642223 - 2023 TX RENEWAL - BATCH 11 - 22 TX | 815 - Addiscott | 101508 | Active | 93 | ANALYZE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 | 22 | 20 | 460812.13 | 278555.01 | 460812.13 | 460812.13 | Horlings, Jake | Somervl | 21-Mar-23 | 27-Sep-23 | 01-Jan-23 | 09-Mar-23 | 19-Jul-23 | Filler | Filler |  | 0
642225 | DUFFERIN ST & LANGSTAFF RD - ANCHOR CONFLICT | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 22-Sep-22
642224 | PATTERSON STREET N POLE REPLACEMENTS, BEETON - ROAD AUTHORITY INITIATED | 825 - Patterson | 101764 | Active | 95 | COMPLETE |  |  | 2023 | Lacombe, Joel | Harrington, James | 31-Jan-23 |  |  | 397656.08 | 356261.99 | 397656.08 | 397656.08 | Dan Kish | K-Line | 28-Apr-23 | 26-Jul-23 | 27-Feb-23 | 06-Feb-23 | 17-Mar-23 |  |  |  | 0
642227 | WELLINGTON D1 PHASE 1 POLE REPLACEMENTS, BARRIE - ROAD AUTHORITY INITIATED | 825 - Patterson | 101764 | Active | 79 | Upload Completed |  |  | 2023 | Lacombe, Joel | Mckeen, Brant |  |  |  | 557969.7 | 43546.01 | 557969.7 | 557969.7 | East Coordinator |  |  | 26-Jul-23 | [6 empty] | 0
642232 | 642232 - 2022 PDMT TX REPLACEMENT BATCH 1 - BARRIE - 18X 1PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 22-Mar-22 | 18 | 18 | 145935.49 | 240815.3 | 145935.49 | 145935.49 | Lotto, Jay |  | 03-Jun-22 | 25-Oct-22 | 04-May-22 | 03-May-22 | 27-Sep-22 |  | Materials |  | 0
642238 | 642238 - 2022 PDMT TX REPLACEMENT BATCH 2 - NEW TECH - 19X 1PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 10-May-22 | 19 | 19 | 190598.24 | 182353.63 | 190598.24 | 190598.24 | Lotto, Jay | HapAmp | 13-Sep-22 | 02-Nov-22 | 21-Jul-22 | 29-Sep-22 | 24-Oct-22 | Materials | Materials |  | 0
642239 | 642239 - 2022 PDMT TX REPLACEMENT BATCH 3 - BARRIE - 5X 3PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 10-Jun-22 | 5 | 5 | 138687.22 | 76775 | 138687.22 | 138687.22 | Lotto, Jay | HapAmp | 22-Aug-22 | 12-Oct-22 | 04-Aug-22 | 29-Sep-22 | 19-Oct-22 | Materials | Materials |  | 0
642240 | 642240 - 2022 PDMT TX REPLACEMENT BATCH 4 - BARRIE - 19X 1PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 01-Apr-22 | 19 | 19 | 186527.08 | 180389.05 | 186527.08 | 186527.08 | Lotto, Jay | HapAmp | 14-Jul-22 | 01-May-23 | 23-May-22 | 09-May-22 | 29-Sep-22 |  | Lines |  | 0
642242 | 642242 - 2022 PDMT TX REPLACEMENT BATCH 5 - BARRIE - 17X 1PH TX'S | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 01-Apr-22 | 17 | 17 | 127955.6 | 117819.68 | 127955.6 | 127955.6 | Lotto, Jay |  | 21-Jun-22 | 22-Sep-22 | 23-May-22 | 29-Jun-22 | 15-Jul-22 | Materials | Materials |  | 0
641764 | 47 GEORGE STREET HYDRO RELOCATION - NEW TECUMSETH | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2021 | Murray, Jake R | Corriveau, Tom N |  |  |  | 0 | 13652.47 |  | 0 | East Coordinator |  |  | 22-Sep-22
642251 | TIMES UPTOWN DEVELOPMENT, PHASE 3 – SUBD RES EDS | 815 - Addiscott | 101896 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642269 | 642269 - DIXON COURT - SUBD CAP | 825 - Patterson | 151531 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Perks, Dan | 29-Oct-21 |  |  | 55099.9 | 52853.03 | 55099.9 | 55099.9 | Lotto, Jay | HapAmp | 29-Dec-21 | 26-Jul-23 | 14-Dec-21 | 27-Apr-22 | 28-Apr-22 | Customer | Customer |  | 0
642278 | 642278 - 61 THOMPSON RD W/PEN/NS/1 PHASE PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 19-Jan-22 |  |  | 36772.26 | 31894.14 | 36772.26 | 36772.26 | Lotto, Jay | HapAmp | 25-Mar-22 | 01-Aug-23 | 04-Mar-22 | 20-Dec-22 | 20-Dec-22 | Customer | Customer |  | 0
642287 | BLOCK 59 DEVELOPMENTS – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642295 | ADDITIONAL DUCTS FOR METROLINX RER CROSSING ENHANCEMENTS | 815 - Addiscott | 152272 | Active | 10 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640861 | 640861 - JOINT USE PERMIT HE2021-026 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 19-Aug-21 |  |  | 8141.79 | 5032.25 | 8141.79 | 8141.79 | Steve Rumble |  | 17-Sep-21 | 30-Mar-22 | 17-Sep-21 | 21-Sep-21 | 21-Sep-21 | Lines | Lines |  | 0
642309 | 642309 - 2022 POLE REPLACEMENTS BARRIE BATCH 2 CLAPPERTON ST | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim | 13-Dec-21 | 16 | 16 | 217138.44 | 256185.14 | 217138.44 | 217138.44 | Jeremy Wright |  | 08-Apr-22 | 22-Sep-22 | 24-Feb-22 | 03-Mar-22 | 20-Apr-22 | Filler | Filler |  | 0
642308 | 642308 - 2022 POLE REPLACEMENTS BARRIE BATCH 1 EUGENIA | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim | 10-Dec-21 | 13 | 13 | 160512.81 | 232324.46 | 160512.81 | 160512.81 | Jeremy Wright |  | 18-Feb-22 | 22-Sep-22 | 24-Jan-22 | 04-Jan-22 | 20-Apr-22 |  | Filler |  | 0
642310 | 2021 POLE REPLACEMENTS ALLISTON BATCH 2 | 825 - Patterson | 100867 | Active | 40 | ACTIVE |  |  | 2023 | Bowman, Todd J | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Active | 96 | COMPLETE |  |  | 2022 | Khuu, Philander | Grahovac, John | 20-Jul-21 |  |  | 3588076.59 | 3291482.48 | 3122362 | 3588076.59 | Shane Christopher | Transpw | 14-Sep-21 | 26-Jul-23 | 31-Aug-21 | 20-Aug-21 | 29-Sep-22 |  | Contractor |  | 465,714.59
642318 | 642318 - JOINT USE PERMIT HE2021-088 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 25-Feb-22 |  |  | 16325.69 | 11772.31 | 16325.69 | 16325.69 | Reginald Clarke |  | 19-May-22 | 26-Jul-23 | 19-Apr-22 | 07-Apr-22 | 03-May-22 |  |  |  | 0
642325 | ANATOLIAN DRIVE - # 35 (LANGSTAFF RD. #6560)/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642338 | 9825 YONGE ST/RH/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642339 | 642339 - 2022 CABLE REPLACEMENT, M31 BIRCHMOUNT AND DENISON ST | 815 - Addiscott | 152281 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 26-Apr-22 |  |  | 1052323.82 | 1082160.76 | 790053.68 | 1052323.82 | Horlings, Jake | Aecon | 05-Jul-22 | 24-Apr-23 | 09-Jun-22 | 08-Jun-22 | 06-Oct-22 |  | Contractor |  | 262,270.14
642343 | CHURCH STREET POLE RELOCATIONS, ALLISTON - RELOCATE FOR ROAD AUTHORITY | 825 - Patterson | 101764 | Active | 45 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642371 | 468 SIMCOE ROAD, BRADFORD | 825 - Patterson | 101763 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 603.46 |  | 0 | East Coordinator |  |  | 26-Jul-22
642382 | 642382 - POLE RELOCATION 9113-9125 BATHRUST STREET | 815 - Addiscott | 151531 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Alarcon, Alejandro | 22-Jan-17 |  |  | 24617.21 | 22992.31 | 24617.21 | 24617.21 | Reginald Clarke |  | 17-Mar-22 | 26-Jul-23 | 14-Mar-22 | 24-Mar-22 | 24-Mar-22 | Customer | Customer |  | 0
642389 | 642389 - 2851 HIIGHWAY NO. 7 WEST - TEMPORARY SERVICE | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2022 | Joshi, Namrata | Yuen, Paul | 13-Jan-22 |  |  | 185936.38 | 244584.69 | 185936.38 | 185936.38 | Dave Lindsay | Somervl | 22-Nov-22 | 18-Aug-23 | 14-Oct-22 | 22-Feb-22 | 08-Dec-22 |  |  |  | 0
642412 | 642412 - MAJOR MACKENZIE RELOACTIONS - KEELE TO JANE | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Murray, Jake R | 28-Apr-22 |  |  | 586598.67 | 628553.15 | 586598.67 | 586598.67 | Morrow, Joe | Transpw | 12-Jul-22 | 22-Sep-22 | 13-Jun-22 | 24-May-22 | 11-Aug-22 |  | Control/SCADA |  | 0
642413 | 642413 - HIGH ST POLE RELOCATION - POLE RELOCATION FOR CITY SIDEWALK, CITY INITIATED | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Harrington, James | 20-Sep-21 |  |  | 41219.67 | 21196.72 | 41219.67 | 41219.67 | Dan Kish |  | 11-Nov-21 | 31-Aug-22 | 02-Nov-21 | 18-Oct-21 | 22-Oct-21 |  |  |  | 0
642414 | ECCLES ST N, BARRIE - STUB POLE INSTALLATION FOR CITY OF BARRIE INITIATED WORK | 825 - Patterson | 101763 | Inactive | 99 | CANCELLED |  |  | 2021 | Corriveau, Tom N | Harrington, James |  |  |  | 0 | 1920.23 |  | 0 | East Coordinator |  |  | 11-Jul-22
642420 | 642420 - 61 MCPHERSON ST/MAR/UP/3PH VAULT | 815 - Addiscott | 101791 | Active | 96 | ANALYZE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 08-Feb-22 |  |  | 75274.4 | 70280.67 | 75274.4 | 75274.4 | Dave Lindsay |  | 13-Apr-22 | 26-Jul-23 | 29-Mar-22 |  | 09-Mar-23 | Customer | Customer |  | 0
642424 | 642424 - POLE REPLACEMENT SUNSET SIX | 815 - Addiscott | 151531 | Active | 99 | COMPLETE |  |  | 2021 | D'Onofrio, Tony | Alarcon, Alejandro | 30-Aug-21 |  |  | 18245.37 | 14899.16 | 18245.37 | 18245.37 | Macdonald, Larry |  | 20-Oct-21 | 26-Jul-23 | 18-Oct-21 | 29-Sep-21 | 29-Sep-21 |  |  |  | 0
642446 | 642446 - 2022 POLE REBUILD - KING VAUGHAN RD - 4 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 17-Mar-22 | 4 | 4 | 105142.99 | 104676.41 | 105142.99 | 105142.99 | Macdonald, Steve | K-Line | 28-Oct-22 | 02-Mar-23 | 24-Oct-22 | 26-Sep-22 | 08-Oct-22 |  |  |  | 0
642448 | 642448 - 2022 POLE RENEWAL - P49523 | 815 - Addiscott | 100867 | Active | 99 | ANALYZE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 09-Nov-21 | 1 | 1 | 18364.16 | 21085.31 | 18364.16 | 18364.16 | Kristine Gordon |  | 07-Jan-22 | 26-Jul-23 | 04-Jan-22 | 07-Apr-22 | 08-Apr-22 | Filler | Filler |  | 0
642447 | 642447 - 2022 POLE RENEWAL - P44985 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 14-Mar-22 | 1 | 1 | 61673.88 | 44203.47 | 61673.88 | 61673.88 | Morrow, Joe |  | 21-Dec-22 | 12-Mar-23 | 12-Dec-22 | 22-Nov-22 | 23-Nov-22 |  |  |  | 0
642465 | JEFFERSON SOUTH SUBDIVISION – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642472 | 642472 - 447 BAYVIEW DRIVE/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 14-Dec-21 |  |  | 72562.49 | 49994.22 | 72562.49 | 72562.49 | Lotto, Jay | HapAmp | 23-Feb-22 | 26-Jul-23 | 26-Jan-22 | 06-Jan-22 | 08-Jun-22 |  | Customer |  | 0
642474 | 642474 - 2022 SWITCH RENEWAL - ALLISTON - 44KV AUTOMATED LIS - AB-B1027 | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Bowman, Todd J | Walters, Geoffrey D | 25-Aug-22 | 1 | 1 | 224612.2 | 191566.3 | 224612.2 | 224612.2 | Dan Kish |  | 04-Nov-22 | 20-Mar-23 | 06-Oct-22 | 21-Dec-22 | 05-Jan-23 | Lines | Lines |  | 0
642475 | 642475 - 2022 SWITCH RENEWAL - BRADFORD- 194 SIMCOE RD. - 13.8KV AUTOMATED LIS - AB-13800 | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Bowman, Todd J | Walters, Geoffrey D | 28-Feb-22 | 1 | 1 | 164111.95 | 152368.46 | 164111.95 | 164111.95 | Dan Kish |  | 04-May-22 | 02-Mar-23 | 12-Apr-22 | 19-Apr-22 | 03-Aug-22 | Lines | Materials |  | 0
642477 | 642477 - 2022 SWITCH RENEWAL -BRADFORD- 226 BARRIE ST.- 13.8KV AUTOMATED LIS - AB-13743 | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Bowman, Todd J | Walters, Geoffrey D | 30-Jun-22 | 1 | 1 | 142588.15 | 135197.4 | 142588.15 | 142588.15 | Dan Kish |  | 01-Sep-22 | 02-Mar-23 | 18-Aug-22 | 31-Aug-22 | 16-Sep-22 | Lines | Lines |  | 0
642481 | 642481 - 2022 SWITCH RENEWAL -BRADFORD- 43 CHURCH ST. - 13.8KV AUTOMATED LIS - AB-13747 | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Bowman, Todd J | Walters, Geoffrey D | 30-Jun-22 | 1 | 1 | 144064.79 | 104026.51 | 144064.79 | 144064.79 | Dan Kish | HapAmp | 08-Sep-22 | 17-Oct-22 | 18-Aug-22 | 17-Oct-22 | 26-Oct-22 | Lines | Lines |  | 0
642484 | 642484 - 2022 SWITCH RENEWAL - BRADFORD- EDWARD ST.- 13.8KV AUTOMATED LIS - AB-13783 | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Bowman, Todd J | Walters, Geoffrey D | 28-Feb-22 | 1 | 1 | 181886.48 | 140474.47 | 181886.48 | 181886.48 | Dan Kish |  | 13-May-22 | 08-Mar-23 | 19-Apr-22 | 12-Sep-22 | 07-Oct-22 | MC/PUCC Permit | MC/PUCC Permit |  | 0
642483 | 642483 - 2022 SWITCH RENEWAL - BRADFORD- 380 WALKER RD. - 13.8KV AUTOMATED LIS - AB-13804 | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Bowman, Todd J | Walters, Geoffrey D | 11-May-22 | 1 | 1 | 105226.1 | 104831.71 | 105226.1 | 105226.1 | Dan Kish |  | 06-Jul-22 | 22-Sep-22 | 27-Jun-22 | 12-Sep-22 | 12-Sep-22 | Lines | Lines |  | 0
642487 | 642487 - 2022 POLE REPLACEMENT - BAYVIEW AVE - 11 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 26-Nov-21 | 11 | 11 | 315529.12 | 327061.24 | 337230.28 | 315529.12 | Macdonald, Steve | K-Line | 25-Nov-22 | 25-Nov-22 | 31-Oct-22 | 19-Sep-22 | 05-Nov-22 |  |  |  | -21,701.16
642486 | 642486 - 2022 SWITCH RENEWAL -BRADFORD- 305 BARRIE ST- 13.8KV AUTOMATED LIS - AB-13744 | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Bowman, Todd J | Walters, Geoffrey D | 30-Jun-22 | 1 | 1 | 129844.31 | 96390.22 | 129844.31 | 129844.31 | Dan Kish |  | 01-Sep-22 | 02-Mar-23 | 18-Aug-22 | 26-Oct-22 | 04-Nov-22 | Lines | Lines |  | 0
642485 | 642485 - 2022 POLE REPLACEMENT - ROYAL RD, INDUSTRIAL PKWY - 4 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 07-Feb-22 | 4 | 4 | 125125.64 | 125015.3 | 120142.79 | 125125.64 | Macdonald, Steve | K-Line | 09-Nov-22 | 02-Mar-23 | 31-Oct-22 | 14-Nov-22 | 17-Dec-22 | Contractor | Contractor |  | 4,982.85
642489 | 642489 - 25 ALBERT ST W/ALL/SR/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 19-Oct-21 |  |  | 16721.83 | 1859.81 | 16721.83 | 16721.83 | Lotto, Jay | HapAmp | 17-Dec-21 | 19-May-22 | 02-Dec-21 | 22-Oct-21 | 22-Oct-21 |  |  |  | 0
642490 | 642490 - 27 DIRECTOR COURT/VAU/SR/3PH PAD | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2021 | Dibratto, Susan | Diefenbaker, Trevor A | 10-Sep-21 |  |  | 11113.55 | 2785.11 | 11113.55 | 11113.55 | Dave Lindsay | Somervl | 15-Nov-21 | 26-Jul-23 | 27-Oct-21 | 04-Oct-21 | 02-Dec-21 |  | Customer |  | 0
642495 | HUNTINGTON RD, EAST CORNERS BLVD TO NASHVILLE RD (SEG 2) | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 09-Jun-22
642496 | HUNTINGTON RD, RUTHERFORD RD TO MCGILLIVRAY RD (SEG 3) | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642511 | 642511 - 2022 POLE REPLACEMENTS BRADFORD BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Obeng, Nana | Pollock, Kim | 04-Oct-22 | 14 | 14 | 205359.91 | 186111.34 | 205359.91 | 205359.91 | Dan Kish |  | 27-Dec-22 | 04-Apr-23 | 17-Nov-22 | 08-Nov-22 | 21-Dec-22 |  |  |  | 0
642510 | 642510 - 2022 POLE REPLACEMENTS THORNTON BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim | 28-Feb-22 | 32 | 32 | 506909.12 | 467400.87 | 506909.12 | 506909.12 | Dan Kish | HapAmp | 07-Jul-22 | 19-Oct-22 | 15-Apr-22 | 16-May-22 | 27-Sep-22 | Filler | Filler |  | 0
642509 | 642509 - 2022 POLE REPLACEMENTS BEETON BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Obeng, Nana | Pollock, Kim | 30-Aug-22 | 13 | 13 | 371425.91 | 331819.87 | 371425.91 | 371425.91 | Dan Kish | K-Line | 16-Nov-22 | 06-Apr-23 | 12-Oct-22 | 07-Sep-22 | 23-Dec-22 |  |  |  | 0
642508 | 642508 - 2022 POLE REPLACEMENTS TOTTENHAM BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim | 01-Dec-21 | 4 | 4 | 66983.69 | 48634 | 66983.69 | 66983.69 | Dan Kish |  | 07-Mar-22 | 22-Sep-22 | 24-Feb-22 | 21-Feb-22 | 11-Mar-22 |  | Filler |  | 0
642507 | 642507 - 2022 POLE REPLACEMENTS ALLISTON BATCH 2 ALBERT | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim | 01-Dec-21 | 5 | 5 | 81377.4 | 78840.05 | 81377.4 | 81377.4 | Dan Kish |  | 09-Feb-22 | 22-Sep-22 | 27-Jan-22 | 26-Jan-22 | 01-Feb-22 |  |  |  | 0
642506 | 642506 - 2022 POLE REPLACEMENTS ALLISTON BATCH 1 EAST AVE | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Bowman, Todd J | Pollock, Kim | 01-Dec-21 | 4 | 4 | 64102.57 | 91922.39 | 64102.57 | 64102.57 | Dan Kish |  | 01-Feb-22 | 22-Sep-22 | 18-Jan-22 | 04-Jan-22 | 18-Jan-22 |  |  |  | 0
642514 | 642514 - 2023 CABLE REPLACEMENT, A10 BATSON DR UG REBUILD | 815 - Addiscott | 152379 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 |  |  | 1945437.63 | 1097074.65 | 1945437.63 | 1945437.63 | Horlings, Jake | Transpw | 04-Aug-23 | 16-Aug-23 | 11-Apr-23 | 28-Apr-23 |  | Contractor |  |  | 0
642523 | 2022 STORM HARDENING - LANGSTAFF - VAUGHAN | 815 - Addiscott | 103659 | Active | 97 | CANCELLED |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 1218099.95 | 0 | 1238871.59 | 1238871.59 | Wong, Henry |  |  | 24-Oct-23 | [6 empty] | 0
642522 | 642522 - 2023 STORM HARDENING - ST. JOHN'S SDRD - AURORA | 815 - Addiscott | 103659 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 24-Apr-23 |  |  | 1651698.72 | 82179.26 | 1651698.72 | 1651698.72 | Morrow, Joe |  | 10-Oct-23 | 10-Oct-23 | 14-Aug-23 | [5 empty] | 0
642521 | 642521 - 2022 STORM HARDENING - LESLIE ST - AURORA | 815 - Addiscott | 103659 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 19-Apr-23 |  |  | 1025533.42 | 709001.42 | 1015533.42 | 1025533.42 | Morrow, Joe |  | 11-Sep-23 | 05-Sep-23 | 10-Jul-23 | 02-Jun-23 |  |  |  |  | 10,000.00
642526 | 642526 - 2021 EMERGING UG, A11SP2000 CABLE FAULT REPLACEMENT | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2021 | Tenorlas, Reynaldo | Handy, James | 13-Aug-21 |  |  | 103757.8 | 76397.57 | 103757.8 | 103757.8 | Horlings, Jake | Somervl | 08-Nov-21 | 22-Sep-22 | 24-Sep-21 | 07-Sep-21 | 13-Oct-21 |  |  |  | 0
642576 | 642576 - SECONDARY SERVICE TRANSFER - 2200 STEELES AVE W | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 13-Dec-21 |  |  | 36910.03 | 45161.04 | 36910.03 | 36910.03 | Dave Lindsay | Somervl | 25-Mar-22 | 22-Sep-22 | 04-Mar-22 | 01-Apr-22 | 18-Jul-22 | Customer | Customer |  | 0
642255 | ALECTRA EAST - POLEMOUNT TRANSFORMER RELOCATION | 815 - Addiscott | 151531 | Active | 70 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642640 | KEELE AND KIRBY POLE RELOCATIONS - VAUGHAN | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2023 | Corriveau, Tom N | Murray, Jake R | 23-Aug-22 |  |  | 102855.87 | 0 | 102855.87 | 102855.87 | Morrow, Joe |  | 22-Nov-22 | 30-May-23 | 09-Nov-22 | [5 empty] | 0
642642 | 642642 - VTS4 PART 3 - YR1 - ADD 2 CCTS TESTON - WESTON TO 400 | 815 - Addiscott | 100340 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 08-Apr-22 |  |  | 502711.09 | 796673.22 | 502711.09 | 502711.09 | Morrow, Joe |  | 09-Sep-22 | 02-Mar-23 | 27-Jun-22 | 31-Aug-22 | 21-Nov-22 | Customer | Customer |  | 0
642649 | 642649 - 9270 MCCOWAN RD. | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 02-Jun-22 |  |  | 60383.57 | 8323.18 | 60383.57 | 60383.57 | Dave Lindsay | Somervl | 12-Aug-22 | 08-Aug-23 | 19-Jul-22 |  |  | Customer | Customer |  | 0
642651 | 642651 - DISTRIBUTION LOOP IMPROVEMENT ON VOGELL RD RICHMOND HILL | 815 - Addiscott | 151916 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 31-Dec-21 |  |  | 122184.39 | 123380.49 | 122184.39 | 122184.39 | Horlings, Jake | Somervl | 25-Apr-22 | 22-Sep-22 | 01-Apr-22 | 20-Apr-22 | 13-Jul-22 | Contractor | Contractor |  | 0
642652 | 642652 - 30 INTERCHANGE WAY / VAU / SR / SECONDARY DEMO | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2021 | Joshi, Namrata | Mann, Drew | 30-Aug-21 |  |  | 4462.95 | 5302.68 | 4462.95 | 4462.95 | Dave Lindsay |  | 14-Oct-21 | 09-May-22 | 12-Oct-21 | 11-Nov-21 | 11-Nov-21 | Customer | Customer |  | 0
642653 | 129 COLLIER ST/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642659 | 642659 - 2 NEWBRIDGE AVE -SECONDARY RELOCATION | 815 - Addiscott | 101761 | Active | 99 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Murray, Jake R | 11-Apr-22 |  |  | 31629.5 | 20940.54 | 31629.5 | 31629.5 | Kristine Gordon |  | 10-Jun-22 | 26-Jul-23 | 01-Jun-22 | 09-Sep-22 | 09-Sep-22 | Customer | Customer |  | 0
642680 | 642680 - 2023 CABLE INJECTION - M21 - HWY 7 - MARKHAM - 16TH - MCCOWAN | 815 - Addiscott | 151361 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 |  |  | 1236046.09 | 1374105.56 | 1236046.09 | 1236046.09 | Horlings, Jake | Nvinium | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 23-Feb-23 |  |  |  |  | 0
642679 | 642679 - 2022 CABLE INJECTION - A09 - WELLINGTON - YONGE - ST JOHNS - BATHURST | 815 - Addiscott | 151520 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 |  |  | 1032790.34 | 361780.62 | 1032790.34 | 1032790.34 | Horlings, Jake | Nvinium | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 01-Jan-23 |  |  |  |  | 0
642682 | 642682 - 2022 CABLE INJECTION - M19 | 815 - Addiscott | 151366 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 10-Nov-21 |  |  | 2013453.72 | 2703454.91 | 2013453.72 | 2013453.72 | Horlings, Jake | Nvinium | 31-Dec-22 | 26-Jul-23 | 01-Jan-22 | 01-Jan-22 |  |  |  |  | 0
642684 | 642684 - 2022 POLE RENEWAL - P49859 & P28092 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 09-Nov-21 | 2 | 2 | 28649.45 | 14790.9 | 48939.97 | 28649.45 | Macdonald, Steve | K-Line | 02-Nov-22 | 02-Mar-23 | 31-Oct-22 | 31-Oct-22 | 02-Nov-22 |  |  |  | -20,290.52
642685 | 642685 - VTS4 PART 3 - YR1 - ADD 2 CCTS TESTON - 400 TO JANE | 815 - Addiscott | 100340 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 13-May-22 |  |  | 324137.72 | 427965.61 | 324137.72 | 324137.72 | Morrow, Joe |  | 31-Aug-22 | 02-Mar-23 | 02-Aug-22 | 31-Aug-22 | 07-Dec-22 | Customer | Customer |  | 0
642688 | 642688 - VIA BORGHESE TX RELOCATION | 815 - Addiscott | 151531 | Active | 95 | ANALYZE |  |  | 2022 | Penner, Mitchell | Estrada, Michael | 25-Nov-21 |  |  | 63356.09 | 62040.48 | 63356.09 | 63356.09 | Dave Lindsay |  | 04-Feb-22 | 26-Jul-23 | 12-Jan-22 | 12-May-22 | 19-Jul-22 | Customer | Customer |  | 0
642687 | 642687 - WOODEND PLACE RADIAL TX RELOCATION | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Estrada, Michael | 02-Dec-21 |  |  | 64869.52 | 53896.21 | 64869.52 | 64869.52 | Dave Lindsay | Transpw | 08-Feb-22 | 26-May-22 | 14-Jan-22 | 25-Jan-22 | 17-Mar-22 | Customer | Customer |  | 0
642711 | 642711 - 377 HARTWELL WAY/AUR/NS/3PH | 815 - Addiscott | 101791 | Active | 82 | H8 |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 28-Mar-22 |  |  | 75117.43 | 5928.27 | 75117.43 | 75117.43 | Dave Lindsay | Somervl | 14-Jun-22 | 09-Aug-23 | 17-May-22 |  |  | Customer | Customer |  | 0
642719 | 642719 - 306 ST JOHNS SIDEROAD/AURORA/NS/3PH PAD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 30-Nov-22 | 1 |  | 119712.31 | 86867.15 | 119712.31 | 119712.31 | Dave Lindsay | Somervl | 21-Feb-23 | 02-Aug-23 | 13-Feb-23 | [5 empty] | 0
642722 | HARRIS AVE DEVELOPMENT - POLE RELOCATION | 815 - Addiscott | 151531 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642468 | 642468 - ZZEN LIVINGSTON DEVELOPMENT (PHASE 1) – SUBD RES EDS | 815 - Addiscott | 101896 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 04-Mar-22 |  |  | 1553726.63 | 1592350.18 | 1553726.63 | 1553726.63 | Dave Lindsay | Transpw | 10-Jun-22 | 26-Jul-23 | 18-Apr-22 | 13-Aug-22 | 20-Mar-23 | Customer | Customer |  | 0
642737 | 642737 - 2022 EMERGING UG, V36 WESTON, STEELES AND PEARCE - V36SP3108 TO 36-L3 | 815 - Addiscott | 152289 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 16-Dec-21 |  |  | 755935.23 | 608794.67 | 755935.23 | 755935.23 | Horlings, Jake | Transpw | 19-Apr-22 | 22-Sep-22 | 01-Apr-22 | 04-Apr-22 | 07-May-22 | Contractor | Contractor |  | 0
642755 | 700 MAPLEVIEW DRIVE - BLOCK 23 - SUBD RES EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Perks, Dan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642758 | 47 GEORGE STREET HYDRO RELOCATION - NEW TECUMSETH | 825 - Patterson | 101763 | Active | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Murray, Jake R |  |  |  | 97.91 | 0 | 97.91 | 97.91 | East Coordinator |  | 01-Dec-21 | 26-Jul-23 | 01-Dec-21 | 01-Dec-21 | 01-Dec-21 |  |  |  | 0
642763 | ANATOLIAN DR. - #400/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642764 | 9151 HUNTINGTON RD/ VAU/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642765 | 6560 LANGSTAFF RD/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
454201 | 454201 - MONTANARO DEVELOPMENT (WEST GORMLEY) | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Swales, Mathew | 15-Sep-21 |  |  | 22092.38 | 16853.61 | 22092.38 | 22092.38 | Dave Lindsay |  | 10-Nov-21 | 26-Jul-23 | 04-Nov-21 | 06-Jun-22 | 06-Mar-23 | Customer | Customer |  | 0
642812 | 422 BARONS ST / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 70 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642817 | 8811 HUNTINGTON RD BLDG 2 / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642844 | 642844 - 2022 POLE RENEWAL - 3 POLES | 815 - Addiscott | 100867 | Active | 93 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 13-Dec-21 | 2 | 2 | 52717.76 | 83176.34 | 52717.76 | 52717.76 | Morrow, Joe |  | 21-Dec-22 | 26-Jul-23 | 14-Dec-22 | 13-Dec-22 | 21-Feb-23 |  | Customer |  | 0
642843 | 642843 - 2022 POLE RENEWAL - BATCH 6 - 7 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 03-Feb-22 | 13 | 13 | 144322.26 | 147082.39 | 144322.26 | 144322.26 | Macdonald, Steve | K-Line | 25-Nov-22 | 19-Jul-23 | 14-Nov-22 | 14-Nov-22 | 17-Dec-22 |  | Contractor |  | 0
642842 | 642842 - 2022 POLE RENEWAL - BATCH 3 - 10 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 09-Dec-21 | 9 | 9 | 115173.76 | 114545.09 | 115173.76 | 115173.76 | Morrow, Joe |  | 01-Apr-22 | 26-Aug-22 | 14-Mar-22 | 07-Feb-22 | 02-May-22 |  | Control/SCADA |  | 0
642841 | 642841 - 2022 POLE RENEWAL - BATCH 2 - 18 POLES | 815 - Addiscott | 100867 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 09-Dec-21 | 18 | 20 | 297061.7 | 328310.42 | 297061.7 | 297061.7 | Morrow, Joe |  | 05-Aug-22 | 26-Jul-23 | 27-Jun-22 | 31-May-22 | 01-Sep-22 |  | Filler |  | 0
642840 | 642840 - 2022 POLE REBUILD - LESLIE ST | 815 - Addiscott | 100867 | Active | 84 | H4 |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 17 |  | 254564.93 | 164260.1 | 254564.93 | 254564.93 | Morrow, Joe |  | 25-May-23 | 09-Aug-23 | 26-Apr-23 | 03-Apr-23 |  |  |  |  | 0
642853 | KING EAST DEVELOPMENT (PHASE 2) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642057 | 642057 - JOINT USE PERMIT HE2021-071 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 28-Sep-21 |  |  | 8067.47 | 6215.05 | 8067.47 | 8067.47 | Steve Rumble |  | 28-Oct-21 | 24-Aug-22 | 28-Oct-21 | 20-Oct-21 | 20-Oct-21 |  |  |  | 0
642864 | 642864 - 385 ELSON ST/ MAR/ NS/ 1 PH PAD | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Dibratto, Susan | Diefenbaker, Trevor A | 27-Jan-22 |  |  | 56321.49 | 5076.92 | 56321.49 | 56321.49 | Dave Lindsay | Somervl | 05-Apr-22 | 04-Aug-23 | 11-Mar-22 | 31-Jan-23 |  | Customer | Customer |  | 0
642868 | AZURIA BERCZY GLEN / I&C WO | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Swales, Mathew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642929 | 642929 - 2022 EMERGING UG, R16 WELDRICK RD E AND CLARISSA DR, CABLE REPLACEMENT | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 13-Jan-22 |  |  | 376450.55 | 363270.06 | 376450.55 | 376450.55 | Horlings, Jake | Somervl | 11-Mar-22 | 22-Sep-22 | 25-Feb-22 | 08-Feb-22 | 22-Jun-22 |  | Locates |  | 0
642947 | 642947 - 390 KERRYBROOK DRIVE POLE RELOCATION- RICHMONDHILL | 815 - Addiscott | 101763 | Active | 99 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan | 04-Jul-22 |  |  | 25761.97 | 20615.15 | 25761.97 | 25761.97 | Kristine Gordon |  | 26-Sep-22 | 26-Jul-23 | 26-Sep-22 | 23-Sep-22 | 23-Sep-22 |  |  |  | 0
642978 | 5841 KIRBY RD. | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642977 | 2024 CUNDLES AND JANINE UG CABLE REPLACEMENT | 825 - Patterson | 101781 | Active | 48 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
642992 | ROAD AUTHORITY RELOCATION-OH&UG-NEW MAJOR MACKENZIE DR AND TIMER CREEK DR | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
641406 | 641406 - JOINT USE PERMIT HE2021-050 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 29-Oct-21 |  |  | 5801.62 | 2885.37 | 5801.62 | 5801.62 | Steve Rumble |  | 26-Nov-21 | 08-Aug-22 | 26-Nov-21 | 01-Dec-21 | 01-Dec-21 | Lines | Lines |  | 0
642996 | 642996 - 6870 13TH LINE/ALL/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 13-May-22 |  |  | 66429.1 | 46139.53 | 66429.1 | 66429.1 | Lotto, Jay | HapAmp | 28-Jul-22 | 22-Sep-22 | 01-Jul-22 | 05-Sep-22 | 05-Sep-22 | Customer | Customer |  | 0
642998 | 642998 - 2022 POLE REPLACEMENT - BATCH 9 - 14 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 30-May-22 | 14 | 9 | 256258.72 | 210318.43 | 337490.22 | 256258.72 | Macdonald, Steve | K-Line | 23-Nov-22 | 23-Nov-22 | 07-Nov-22 | 31-Oct-22 | 23-Nov-22 |  |  |  | -81,231.50
642999 | 642999 - 2022 POLE REPLACEMENT - BATCH 7 - 21 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 31-Jan-22 | 21 | 21 | 359051.91 | 309715.9 | 359051.91 | 359051.91 | Morrow, Joe |  | 02-Jun-22 | 28-Jun-23 | 04-Apr-22 | 04-Apr-22 | 01-Sep-22 |  | Filler |  | 0
643002 | 643002 - 87 GOULDING AVE/AUR/NS/3 PHASE PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 27-Jul-22 |  |  | 74059.94 | 64400.95 | 74059.94 | 74059.94 | Dave Lindsay | Somervl | 06-Oct-22 | 14-Feb-23 | 07-Sep-22 | 11-Aug-22 | 07-Oct-22 |  | Customer |  | 0
643003 | 140 MARYCROFT AVE / VAU / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 02-Sep-22
643008 | 643008 - 1623 WELLINGTON ST/AUR/NS/3 PHASE PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 22-Aug-22 |  |  | 167286.74 | 158505.28 | 167286.74 | 167286.74 | Dave Lindsay | Somervl | 08-Nov-22 | 10-May-23 | 04-Oct-22 | 08-Sep-22 | 07-Oct-22 |  |  |  | 0
454137 | 454137 - BEVERLEY GLEN BLVD. - #2 - 4 BLDGS/RESIIDENTIAL CONDOS - 4 BLDGS | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Dibratto, Susan | Yuen, Paul | 30-Sep-21 |  |  | 93636.81 | 7984.61 | 93636.81 | 93636.81 | Dave Lindsay |  | 08-Aug-22 | 02-Aug-23 | 29-Jul-22 |  |  | Customer | Customer |  | 0
643038 | 643038 - 45 ERIC T SMITH WAY/AUR/3 PHASE PAD | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 21-Mar-22 |  |  | 110885.95 | 67723.86 | 110885.95 | 110885.95 | Dave Lindsay | Somervl | 31-May-22 | 26-Jul-23 | 03-May-22 | 17-Sep-22 | 06-Mar-23 | Customer | Customer |  | 0
643040 | C.W. LEACH ROAD, ALLISTON - ROAD EXTENSION WITH ROAD WORKS. | 825 - Patterson | 101764 | Active | 50 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643057 | 643057 - 850 GIBRALTAR RD. | 815 - Addiscott | 101791 | Active | 96 | ANALYZE |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 19-Apr-22 |  |  | 173988.88 | 167430.46 | 173988.88 | 173988.88 | Dave Lindsay | Somervl | 05-Jul-22 | 26-Jul-23 | 03-Jun-22 |  | 09-Mar-23 | Customer | Customer |  | 0
643058 | 105 EDGEHILL DR/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643067 | ON THE MARK PHASE 2 – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643084 | 643084 - 691 SIMCOE RD/BRAD/NS/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 03-Dec-21 |  |  | 52635.63 | 42604.25 | 52635.63 | 52635.63 | Lotto, Jay | HapAmp | 07-Feb-22 | 07-Apr-22 | 17-Jan-22 | 27-Jan-22 | 07-Feb-22 | Customer |  |  | 0
643086 | 2022 TESTON ROAD POLE INSTALLATIONS | 815 - Addiscott | 101762 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643115 | 643115 - KENNEDY RD & BUR OAK AVE | 815 - Addiscott | 101763 | Active | 99 | COMPLETE |  |  | 2021 | Corriveau, Tom N | Battistella, Alexander | 09-Nov-21 |  |  | 18544.27 | 8235.16 | 18544.27 | 18544.27 | Reginald Clarke |  | 21-Dec-21 | 26-Jul-23 | 20-Dec-21 | 23-Dec-21 | 23-Dec-21 | Weather | Weather |  | 0
639764 | 639764 - JOINT USE PERMIT #HE2020-089, SUNSET BEACH RD, RICHMOND HILL | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 19-Oct-21 |  |  | 11573.6 | 9454.43 | 11573.6 | 11573.6 | Reginald Clarke |  | 22-Nov-21 | 26-Jul-23 | 22-Nov-21 | 22-Nov-21 | 22-Nov-21 |  |  |  | 0
643121 | 7033 LESLIE ST/MAR/UP/ CUST OWNED STATION | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643122 | 643122 - 259 INNISFIL ST/BAR/SR/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2021 | Cranley, Stephen | Paterson, Greg | 08-Oct-21 |  |  | 14003.53 | 6684.25 | 14003.53 | 14003.53 | Lotto, Jay | HapAmp | 07-Dec-21 | 07-Apr-22 | 19-Nov-21 | 19-Oct-21 | 19-Oct-21 |  |  |  | 0
643125 | 643125 - 2022 LB CABLE REPLACEMENTS - M27 WATERBRIDGE LN, MAIN ST UNIONVILLE, ROSEMEAD CL | 815 - Addiscott | 150263 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 21-Jul-22 |  |  | 1141112.91 | 1082643.57 | 1141112.91 | 1141112.91 | Horlings, Jake | Transpw | 28-Oct-22 | 26-Jul-23 | 01-Sep-22 | 30-Aug-22 | 29-Oct-22 |  |  |  | 0
643126 | 2291 MAJOR MACKENZIE DRIVE WEST (PHASE) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
640833 | 640833 - JOINT USE PERMIT HE2021-024 | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2021 | O'Gay, Brian | Martin, Shane | 28-Sep-21 |  |  | 14419.88 | 7985.24 | 14419.88 | 14419.88 | Reginald Clarke |  | 29-Oct-21 | 26-Jul-23 | 29-Oct-21 | 05-Nov-21 | 05-Nov-21 |  |  |  | 0
643139 | 643139 - 8550 KEELE ST - POLE RELOCATION | 815 - Addiscott | 101763 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan | 19-May-22 |  |  | 46293.11 | 39061.88 | 46293.11 | 46293.11 | Morrow, Joe |  | 08-Jul-22 | 28-Apr-23 | 04-Jul-22 | 30-May-22 | 06-Jun-22 |  |  |  | 0
643148 | 643148 - 5336 HWY 7 E / MAR / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 08-Jun-22 |  |  | 94490.18 | 10294.98 | 94490.18 | 94490.18 | Dave Lindsay | Somervl | 19-Aug-22 | 09-Aug-23 | 22-Jul-22 | 12-Jun-23 |  | Customer | Customer |  | 0
643149 | 643149 - 101 MILANI BLVD PH2 / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 08-Mar-22 |  |  | 131690.68 | 17282.97 | 131690.68 | 131690.68 | Dave Lindsay | Somervl | 20-May-22 | 15-Aug-23 | 19-Apr-22 | 05-Apr-22 |  |  | Customer |  | 0
643166 | 643166 - 2022 POLE RENEWAL - BATCH 5 - 6 POLES | 815 - Addiscott | 100867 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 10-Mar-22 | 6 | 6 | 97698.54 | 102806.89 | 97698.54 | 97698.54 | Macdonald, Steve | K-Line | 27-Oct-22 | 26-Jul-23 | 17-Oct-22 | 14-Nov-22 | 17-Dec-22 | Contractor | Contractor |  | 0
643165 | 643165 - 2022 POLE RENEWAL - BATCH 4 - 9 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Feb-22 | 9 | 9 | 167501.07 | 152393.44 | 167501.07 | 167501.07 | Morrow, Joe |  | 15-Feb-23 | 26-Jul-23 | 09-Jan-23 | 09-Jan-23 | 18-Jan-23 |  |  |  | 0
643168 | 643168 - 2022 POLE RENEWAL - P46443 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 04-May-22 | 1 | 1 | 39734.82 | 42545.82 | 39734.82 | 39734.82 | Macdonald, Steve | K-Line | 04-Nov-22 | 28-Jun-23 | 02-Nov-22 | 03-Oct-22 | 03-Oct-22 |  |  |  | 0
643167 | 643167 - 2022 POLE RENEWAL - BATCH 8 - 4 POLES | 815 - Addiscott | 100867 | Active | 99 | ANALYZE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 17-Mar-22 | 4 | 4 | 86665.64 | 79111.07 | 86665.64 | 86665.64 | Kristine Gordon |  | 14-Jun-22 | 26-Jul-23 | 16-May-22 | 12-Oct-22 | 25-Oct-22 | Filler | Filler |  | 0
643169 | 643169 - 2022 POLE REBUILD - THISTLEWOOD RD - 5 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 06-May-22 | 5 | 5 | 125756.77 | 117711.76 | 125756.77 | 125756.77 | Morrow, Joe |  | 16-Dec-22 | 16-Mar-23 | 12-Dec-22 | 05-Dec-22 | 08-Dec-22 |  |  |  | 0
643171 | 643171 - 2022 POLE RENEWAL - P44186 | 815 - Addiscott | 100867 | Active | 99 | ANALYZE |  |  | 2022 | Tenorlas, Reynaldo | Canale, Alfred | 17-Mar-22 | 1 | 1 | 36135.22 | 43513.29 | 36135.22 | 36135.22 | Kristine Gordon |  | 03-Jun-22 | 26-Jul-23 | 01-Jun-22 | 03-Nov-22 | 15-Dec-22 | Filler | Filler |  | 0
643178 | 643178 - CHAMPLAIN SHORES – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 95 | COMPLETE |  |  | 2022 | Penner, Mitchell | Handy, James | 24-Jan-23 |  |  | 248211.07 | 250612.92 | 248211.07 | 248211.07 | Lotto, Jay | Transpw | 01-May-23 | 26-Jul-23 | 03-Apr-23 | 19-Dec-22 | 20-Dec-22 | Customer | Customer |  | 0
643202 | 643202 - 2022 CABLE REPLACEMENT, V40 GREENBROOKE | 815 - Addiscott | 152290 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Handy, James | 01-Jun-22 |  |  | 705734.58 | 601623.4 | 705734.58 | 705734.58 | Horlings, Jake | Transpw | 08-Aug-22 | 23-Sep-22 | 14-Jul-22 | 04-Jul-22 | 29-Jul-22 |  |  |  | 0
643217 | 643217 - 2022 STORM HARDENING - HWY 27 - MAJOR MACKENZIE TO RUTHERFORD - VAUGHAN | 815 - Addiscott | 103659 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 25-Nov-21 |  |  | 715735.52 | 891996.55 | 715735.52 | 715735.52 | Morrow, Joe |  | 28-Mar-22 | 26-Jul-23 | 04-Jan-22 | 22-Feb-22 | 29-Apr-22 | MC/PUCC Permit | MC/PUCC Permit |  | 0
643216 | 643216 - 2022 STORM HARDENING - WESTON - HWY 7 TO LANGSTAFF - VAUGHAN | 815 - Addiscott | 103659 | Active | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Roy, James | 11-Jul-22 |  |  | 580017 | 629307.1 | 529273.98 | 580017 | Macdonald, Steve | K-Line | 10-Nov-22 | 26-Jul-23 | 03-Oct-22 | 06-Sep-22 | 05-Nov-22 |  |  |  | 50,743.02
643218 | ASA HARVIE ROAD SUBDIVISION – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | D'Onofrio, Tony |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643220 | 9 CHURCHILL DR/BAR/UP/3PH PAD | 825 - Patterson | 101919 | Active | 79 | PPS INCOMPLETE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 56998.86 | 6304.28 | 56998.86 | 56998.86 | East Coordinator |  |  | 26-Jul-23 | [6 empty] | 0
643239 | 643239 - 2022 TX RENEWAL - 1-468 - 1 TX | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 26-Nov-21 | 1 | 1 | 41245.38 | 33218.78 | 41245.38 | 41245.38 | Dave Lindsay | Somervl | 07-Feb-22 | 24-Jul-23 | 19-Jan-22 | 18-Aug-22 | 10-Nov-22 | Filler | Filler |  | 0
643241 | HIGHWAY NO. 7 EAST - #3997/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 20-Jun-23 |  |  | 105096.48 | 9015.91 | 105096.48 | 105096.48 | Dave Lindsay | Somervl | 21-Jul-23 | 03-Aug-23 | 13-Jul-23 | [5 empty] | 0
643250 | TFP AURORA DEVELOPMENT, PHASE 1 (WEST) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Handy, James | 14-Apr-23 |  |  | 1114037.57 | 548787.1 | 1114037.57 | 1114037.57 | Dave Lindsay | Transpw | 01-Aug-23 | 01-Aug-23 | 26-Jul-23 | [5 empty] | 0
643255 | 643255 - CEDAR AVE AND HIGH TECH RD - UTILITY RELOCATION - RICHMOND HILL | 815 - Addiscott | 101763 | Active | 80 | H8 |  |  | 2023 | Corriveau, Tom N | Murray, Jake R | 22-Jun-22 |  |  | 118088.81 | 22373.95 | 118088.81 | 118088.81 | Morrow, Joe |  | 19-Oct-23 | 19-Oct-23 | 02-Oct-23 | [5 empty] | 0
643291 | 643291 - 9554 WESTON ROAD HYDRO POLE RELOCATION - VAUGHAN | 815 - Addiscott | 101763 | Active | 99 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan | 19-May-22 |  |  | 12304.84 | 5758.72 | 12304.84 | 12304.84 | Kristine Gordon |  | 11-Jul-22 | 26-Jul-23 | 11-Jul-22 | 06-Apr-22 | 06-Apr-22 |  |  |  | 0
643314 | 5315 KIRBY ROAD – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643316 | 1, 3, 5 ,7 MERINO ROAD – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro | 17-Apr-23 |  |  | 81131.58 | 84246.4 | 81131.58 | 81131.58 | Dave Lindsay | Transpw | 21-Jun-23 | 14-Aug-23 | 05-Jun-23 | 05-Jun-23 |  | N/A |  |  | 0
639680 | 639680 - JOINT USE PERMIT #HE2020-088, 14TH AVE., MARKHAM | 815 - Addiscott | 151495 | Active | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Bradley, Alex | 27-Oct-21 |  |  | 13417.71 | 8753.48 | 13417.71 | 13417.71 | Reginald Clarke |  | 06-Dec-21 | 26-Jul-23 | 06-Dec-21 | 05-Apr-22 | 05-Apr-22 | Locates | Locates |  | 0
643339 | STEELES AVE GRADE SEPARATION - EXTRAS | 815 - Addiscott | 150591 | Active | 50 | ACTIVE |  |  | 2023 | Khuu, Philander | Grahovac, John |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643343 | SANDMILL PHASE 1 (IN NORTH LESLIE SECONDARY PLAN) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643345 | DUFFERIN VISTAS SUBDIVISION (PHASE 1) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643347 | 643347 - HUNTINGTON RD & HWY 7 | 815 - Addiscott | 101763 | Active | 99 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander | 30-May-22 |  |  | 29037.59 | 23596.26 | 29037.59 | 29037.59 | Kristine Gordon |  | 21-Jul-22 | 26-Jul-23 | 18-Jul-22 | 25-Jul-22 | 11-Oct-22 | Customer | Customer |  | 0
643356 | 643356 - 2022 EAST NORTH PCB UG TX REPLACEMENT BARRIE | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Obeng, Nana | Pollock, Kim | 07-Oct-22 | 1 | 1 | 30769.72 | 31682.44 | 30769.72 | 30769.72 | Lotto, Jay | HapAmp | 14-Dec-22 | 14-Dec-22 | 24-Nov-22 | 27-Oct-22 | 27-Oct-22 |  |  |  | 0
643359 | 643359 - 2022 EAST NORTH PCB UG TX REPLACEMENT TOTTENHAM | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2022 | Obeng, Nana | Pollock, Kim | 20-Oct-22 | 1 | 1 | 21856.19 | 37180.56 | 21856.19 | 21856.19 | Lotto, Jay | HapAmp | 07-Dec-22 | 08-Mar-23 | 05-Dec-22 | 17-Nov-22 | 17-Nov-22 |  |  |  | 0
643360 | 643360 - 4433, 4455, 4477 MAJOR MACKENZIE DR. W - POLE RELOCATION | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2022 | Penner, Mitchell | Estrada, Michael | 07-Feb-22 |  |  | 64994.66 | 59302.56 | 64994.66 | 64994.66 | Dave Lindsay | Transpw | 20-Apr-22 | 23-Sep-22 | 22-Mar-22 | 29-Mar-22 | 05-May-22 | Customer | Customer |  | 0
643365 | 125 ENGELHARD DR/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643396 | 15 ADELINE AVE. - TOTTENHAM - POLE REPLACEMENT & UG RISER RELOCATION | 825 - Patterson | 101355 | Active | 50 | ACTIVE |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643399 | MILLER PARK FEEDER AND SWITCHGEAR(S) INSTALLATION | 825 - Patterson | 101763 | Active | 79 | Upload Completed |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 437485.29 | 27887.55 | 437485.29 | 437485.29 | East Coordinator |  |  | 26-Jul-23 | [6 empty] | 0
643417 | 643417 - VARIOUS LOCATIONS - VAUGHAN- GUYING RELOCATIONS | 815 - Addiscott | 101762 | Active | 84 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R | 25-Apr-22 |  |  | 108124.91 | 43461.51 | 108124.91 | 108124.91 | Kristine Gordon |  | 17-Jun-22 | 02-Aug-23 | 08-Jun-22 | 20-Oct-22 |  | Locates |  |  | 0
643425 | 643425 - 2022 POLE REPLACEMENTS ALLISTON BATCH 3 NELSON | 825 - Patterson | 100867 | Active | 94 | ANALYZE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 19-Oct-22 | 17 | 17 | 241620.03 | 283239.3 | 241620.03 | 241620.03 | Mark Timbers |  | 27-Dec-22 | 26-Jul-23 | 30-Nov-22 | 05-Jan-23 | 26-Jun-23 | Lines | Lines |  | 0
643431 | 2022 LITTLE FAIRVIEW HARVIE FERNDALE UG CABLE REPLACEMENT DESIGN ONLY | 825 - Patterson | 101781 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643430 | 2022 COOK AND STEEL UG CABLE REPLACEMENT DESIGN ONLY | 825 - Patterson | 101781 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643414 | 643414 - 10 STEEL ST, BARRIE - POLE RELOCATION - | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan | 09-Nov-22 |  |  | 49122.57 | 12182.95 | 49122.57 | 49122.57 | Dan Kish |  | 24-Feb-23 | 04-Jul-23 | 23-Jan-23 |  | 19-Dec-22 |  |  |  | 0
643491 | 330 AND 336 STEELES AVE. EAST – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643508 | KEELE ST - STEELES TO SNIDERCROFT - GUYING REMOVALS | 815 - Addiscott | 101762 | Active | 50 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643512 | 643512 - 100 WILLOUGHBY WAY/ALL/NS/3PH PAD | 825 - Patterson | 101919 | Active | 99 | ANALYZE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 23-Feb-22 |  |  | 54748.82 | 45670.73 | 54748.82 | 54748.82 | Lotto, Jay | HapAmp | 03-May-22 | 26-Jul-23 | 08-Apr-22 | 27-May-22 | 17-Jun-22 | Customer | Customer |  | 0
643513 | 643513 - 118 ST. VINCENT/BAR/UP/1PH PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 08-Jul-22 |  |  | 45764.25 | 41180.96 | 45764.25 | 45764.25 | Lotto, Jay | HapAmp | 07-Sep-22 | 26-Jul-23 | 19-Aug-22 | 23-Sep-22 | 17-Oct-22 | Customer | Customer |  | 0
643528 | THE RESIDENCES OF KLEINBURG VILLAGE – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643532 | 643532 - 783 HURONIA RD/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. | 09-Aug-22 |  |  | 83014.33 | 59090.34 | 83014.33 | 83014.33 | Lotto, Jay | HapAmp | 26-Oct-22 | 26-Jul-23 | 26-Sep-22 | 14-Oct-22 | 04-Nov-22 | Customer | Customer |  | 0
643533 | RUTHERFORD HEIGHTS ENCLAVE TOWNHOMES | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643549 | 20 ROSE ST/BAR/SR/3 PHASE SERVICE REMOVAL | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 11058.76 | 6523.2 | 11058.76 | 11058.76 | East Coordinator |  |  | 11-Apr-23 |  |  | 31-Aug-21 |  |  |  | 0
643550 | 643550 - 2022 POLE REPLACEMENTS BARRIE BATCH 3 | 825 - Patterson | 100867 | Active | 99 | COMPLETE |  |  | 2022 | Obeng, Nana | Pollock, Kim | 11-May-22 | 30 | 30 | 522169.89 | 456542.92 | 522169.89 | 522169.89 | Dan Kish |  | 03-Oct-22 | 11-Sep-23 | 27-Jun-22 | 07-Oct-22 | 21-Dec-22 | Filler | Filler |  | 0
643558 | 643558 - 2023 CABLE REPLACEMENT - A05 - TRILLIUM DR - GOLF LINKS IN AURORA - PHASE 2 WEST | 815 - Addiscott | 151911 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 13-Dec-22 |  |  | 1045914.12 | 44522.37 | 1033081.35 | 1045914.12 | Dave Lindsay | Transpw | 07-Sep-23 | 07-Sep-23 | 18-Jul-23 | 09-May-23 |  |  |  |  | 12,832.77
643577 | KEELE ST ROAD WIDENING - STEELES AVE WEST TO HIGHWAY 407 | 815 - Addiscott | 101762 | Active | 70 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643582 | 236 DUNLOP ST, W/BAR/UP/1 PHASE PAD | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2022 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 12-May-22
643596 | 35 SILTON RD/ VAU/ UP/ 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Dibratto, Susan | Diefenbaker, Trevor A |  |  |  | 0 | 4097.3 |  | 0 | East Coordinator |  |  | 23-Sep-22
643600 | UNION CITY - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643672 | 643672 - 41 PERFORMANCE DR. | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Dibratto, Susan | Yuen, Paul | 17-Dec-21 |  |  | 87952.64 | 63697.39 | 87952.64 | 87952.64 | Dave Lindsay | Somervl | 01-Mar-22 | 17-Jul-23 | 01-Feb-22 | 21-Jul-22 | 07-Oct-22 | Customer | Customer |  | 0
643673 | 11007 YONGE STREET - POLE RELOCATION | 815 - Addiscott | 151587 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643755 | BERCZY WARDEN HOLDINGS DEVELOPMENT P.1 -SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643837 | 643837 - ROAD AUTHORITY RELOCATION-HWY 400 AND LITTLE AVENUE | 825 - Patterson | 101764 | Active | 92 | COMPLETE |  |  | 2023 | Pelleja, Emily | Zhang, Jiacheng | 24-Oct-22 |  |  | 846511.74 | 834423.58 | 819314.71 | 846511.74 | Dan Kish | K-Line | 20-Dec-22 | 26-Jul-23 | 06-Dec-22 | 21-Nov-22 | 27-Jan-23 |  | Contractor |  | 27,197.03
643855 | ISLINGTON AVE. - #7082, TOWER 3 AND 4/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643856 | NAO TOWNS P2 -SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643869 | HIGHLAND GATE PH4 - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643882 | BERCZY WARDEN - SYSTEM EXPANSION | 815 - Addiscott | 152359 | Active | 70 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643898 | 2911 MAJOR MACKENZIE/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 06-Jul-23 |  |  | 101820.26 | 11388.28 | 101820.26 | 101820.26 | Dave Lindsay | N/A | 13-Oct-23 | 13-Oct-23 | 25-Sep-23 | [5 empty] | 0
643928 | KIRBY ROAD - POLE RELOCATION | 815 - Addiscott | 151587 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643927 | 9999 MARKHAM RD DEVELOPMENT PH1- SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643933 | 7200 MARKHAM RD / MAR / NS / CO-STN | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
643958 | 15094 YONGE ST/AUR/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644019 | 644019 - CUSTOMER INITIATED UG RELOCATION-EAGLE ROCK WAY, VAUGHAN | 815 - Addiscott | 101763 | Active | 98 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan | 16-Nov-22 |  |  | 377879.69 | 223776.66 | 377879.69 | 377879.69 | Horlings, Jake | Transpw | 27-Jan-23 | 26-Jul-23 | 29-Dec-22 | 16-Jan-23 | 10-Mar-23 | Contractor | Contractor |  | 0
644022 | HUNTINGTON ROAD, NORTH OF NASHVILLE ROAD - BLOCK 62 W | 815 - Addiscott | 101763 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644031 | 644031 - 8361 YONGE ST/MAR/UP/1PH PAD | 815 - Addiscott | 101791 | Active | 95 | COMPLETE |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A | 22-Sep-22 |  |  | 56736.69 | 60030.06 | 56736.69 | 56736.69 | Dave Lindsay | Somervl | 05-Dec-22 | 10-Aug-23 | 07-Nov-22 | 11-Nov-22 | 08-Dec-22 |  |  |  | 0
644091 | 51 BRADFORD ST, BARRIE - BARRIE LAKESHORE DEV CONDOS 44KV | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644095 | 644095 - 230 LOCKHART/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 18-Jul-22 |  |  | 100025.92 | 68256.69 | 100025.92 | 100025.92 | Lotto, Jay | HapAmp | 29-Sep-22 | 09-Aug-23 | 31-Aug-22 | 16-Jan-23 | 25-Jan-23 | Customer | Customer |  | 0
644103 | FERNDALE MEADOWS PH 2-SUBD RES EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644105 | 11430 LESLIE ST -SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644113 | 644113 - 73 WOOTTEN WAY / MAR / SR / 1PH PAD TX DEMO | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 22-Dec-21 |  |  | 24328.4 | 25213.28 | 24328.4 | 24328.4 | Dave Lindsay | Somervl | 23-Feb-22 | 14-Jul-22 | 03-Feb-22 | 25-Jan-22 | 11-Feb-22 |  |  |  | 0
644114 | 350 HUNTER'S VALLEY RD / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Mann, Drew | 19-Dec-22 | 1 |  | 150794.88 | 20855.96 | 150794.88 | 150794.88 | Dave Lindsay | Somervl | 11-Sep-23 | 11-Sep-23 | 05-Sep-23 | [5 empty] | 0
644117 | 644117 - CUSTOMER INITIATED EXPANSION-MARKHAM, 19TH AVE | 815 - Addiscott | 152359 | Active | 97 | CANCELLED |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng | 11-Aug-22 |  |  | 1388222.1 | 61167.4 | 1388222.1 | 1388222.1 | Morrow, Joe |  | 04-May-23 | 24-Nov-23 | 09-Jan-23 | 01-Sep-22 |  |  |  |  | 0
644146 | HIGHLAND GATE PH 5-SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644149 | 644149 - CUSTOMER INITIATED UG RELOCATION-70 CONNIE CRES, VAUGHAN | 815 - Addiscott | 101761 | Active | 98 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Zhang, Jiacheng | 04-May-22 |  |  | 39436.07 | 18810.73 | 39436.07 | 39436.07 | Dave Lindsay |  | 11-Jul-22 | 14-Aug-23 | 22-Jun-22 | 22-Aug-22 | 08-Dec-22 | Customer | Customer |  | 0
644175 | 11430 LESLIE ST BLK 38 - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644205 | HIGHWAY NO. 7 WEST - #3940, W/O WESTON RD. | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644206 | YORK DOWNS GOLF COURSE PH1 - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644223 | 644223 - POLE REPLACEMENT AUTUMNHILL DEVELOPMENT | 815 - Addiscott | 151531 | Active | 99 | ANALYZE |  |  | 2022 | Penner, Mitchell | Alarcon, Alejandro | 13-Jul-22 |  |  | 53017.72 | 45809.67 | 53017.72 | 53017.72 | Kristine Gordon |  | 15-Sep-22 | 26-Jul-23 | 06-Sep-22 | 20-Sep-22 | 21-Nov-22 | Locates | Locates |  | 0
644227 | 644227 - 460 WILLIAM GRAHAM DR/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 23-Jun-22 |  |  | 61194.27 | 8227.73 | 61194.27 | 61194.27 | Dave Lindsay | Somervl | 02-Sep-22 | 10-Aug-23 | 05-Aug-22 |  |  | Customer | Customer |  | 0
644239 | 5445 KIRBY ROAD PH1- SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644242 | 644242 - VMC SW QUADRANT - ALECTRA RELOCATIONS | 815 - Addiscott | 101762 | Active | 95 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Watters, Maxwell | 21-Oct-22 |  |  | 557394.33 | 396825.37 | 517342.2 | 557394.33 | Morrow, Joe | Transpw | 03-Mar-23 | 26-Jul-23 | 12-Dec-22 | 05-Dec-22 | 15-May-23 |  | Control/SCADA |  | 40,052.13
644243 | POLE REPLACEMENT VMC MENKES | 815 - Addiscott | 151531 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644253 | 135 KARACHI DR / MAR / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Mann, Drew | 13-Apr-23 |  |  | 75549.89 | 9052.48 | 75549.89 | 75549.89 | Dave Lindsay | Somervl | 18-Aug-23 | 18-Aug-23 | 01-Aug-23 | [5 empty] | 0
644256 | 11300 YONGE ST / RHL / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644261 | PINE VALLEY AND RUTHERFORD RD _ VAUGHAN | 815 - Addiscott | 101762 | Active | 82 | H8 |  |  | 2023 | Corriveau, Tom N | Murray, Jake R | 17-Jan-23 |  |  | 164514.64 | 17936.29 | 164514.64 | 164514.64 | Macdonald, Steve |  | 05-Jul-23 | 13-Sep-23 | 26-Jun-23 | [5 empty] | 0
644275 | ATKINSON AVE. - #300 | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 02-May-22
644276 | 10988 WARDEN AVE/ MAR/NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644296 | BAYVIEW DRIVE, BARRIE - ROAD AUTHORITY PROJECT | 825 - Patterson | 101764 | Active | 48 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644301 | 644301 - 234 LOCKHART/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 18-Jul-22 |  |  | 95509.41 | 65388.22 | 95509.41 | 95509.41 | Lotto, Jay | HapAmp | 29-Sep-22 | 08-Aug-23 | 31-Aug-22 | 16-Jan-23 | 25-Jan-23 | Customer | Customer |  | 0
644302 | 644302 - 2 SCANLON CRT/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 03-Nov-22 |  |  | 136826.55 | 6075.37 | 136826.55 | 136826.55 | Dave Lindsay | Somervl | 27-Jan-23 | 14-Aug-23 | 22-Dec-22 | [5 empty] | 0
644303 | 644303 - 177 CHURCH ST/BRAD/UP/3PH PAD | 825 - Patterson | 101919 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 03-Aug-22 |  |  | 88881.39 | 68595.32 | 88881.39 | 88881.39 | Lotto, Jay | HapAmp | 19-Oct-22 | 26-Jul-23 | 16-Sep-22 | 21-Mar-23 | 14-Jun-23 | Materials | Materials |  | 0
644309 | BIRCHMOUNT RD. SOUTH - #7900/MAR/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 24-Mar-23 |  |  | 439508.96 | 280108.19 | 439508.96 | 439508.96 | Dave Lindsay | Somervl | 14-Jun-23 | 01-Sep-23 | 08-May-23 | 04-May-23 |  |  |  |  | 0
644311 | 644311 - 32 DON HILLOCK DR/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 30-Jun-22 |  |  | 63298.02 | 2126.69 | 63298.02 | 63298.02 | Dave Lindsay | Somervl | 09-Sep-22 | 02-Aug-23 | 19-Aug-22 |  |  | Customer | Customer |  | 0
644310 | 9332-9346 KENNEDY RD / MAR / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644273 | MATTAMY BERCY GLEN RINAS PHASE 2-SUBD RED EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644264 | MATTAMY BERCY GLEN ROMAN PHASE 2-SUBD/RES/EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644342 | SUBDIVISION PROPERLIVING DEVELOPMENT | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644412 | MARKHAM FILM STUDIO SYSTEM EXPANSION - 19TH AVE TO WARDEN AVE | 815 - Addiscott | 152359 | Inactive | 99 | CANCELLED |  |  | 2023 | Corriveau, Tom N | Watters, Maxwell |  |  |  | 0 | 26940.43 |  | 0 | East Coordinator |  |  | 23-May-23
641469 | 641469 - JOINT USE PERMIT HE2021-049 | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2022 | O'Gay, Brian | Martin, Shane | 02-Feb-22 |  |  | 9407.64 | 5701.92 | 9407.64 | 9407.64 | Steve Rumble |  | 28-Feb-22 | 14-Aug-22 | 25-Feb-22 | 15-Feb-22 | 15-Feb-22 |  |  |  | 0
644441 | YNSE SYSTEM EXPANSION - YONGE ST TO LANGSTAFF RD | 815 - Addiscott | 152323 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Chopra, Rabinder |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644440 | 644440 - 1591 ELGIN MILLS RD / RHL / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 28-Nov-22 |  |  | 120312.35 | 69253.73 | 120312.35 | 120312.35 | Dave Lindsay | Somervl | 01-Mar-23 | 14-Aug-23 | 06-Feb-23 | 05-Jan-23 |  |  |  |  | 0
644477 | BLOCK 62 W - HUNTINGTON ROAD WEST KLEINBURG EXPANSION | 815 - Addiscott | 152359 | Active | 50 | H8 |  |  | 2023 | Corriveau, Tom N | Watters, Maxwell |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644480 | 644480 - ELGIN MILLS RD. EAST - #1591 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Yuen, Paul | 27-May-22 |  |  | 73744.94 | 46864.24 | 73744.94 | 73744.94 | Dave Lindsay | Somervl | 08-Aug-22 | 13-Jul-23 | 08-Jul-22 | 27-Oct-22 | 05-Dec-22 | Customer | Customer |  | 0
644513 | 420 ADDISON HALL CIRCLE/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644523 | 644523 - 6885 LANGSTAFF RD/VAU/NS/CUST OWNED | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 14-Sep-22 |  |  | 390995.16 | 175079.85 | 390995.16 | 390995.16 | Dave Lindsay | Somervl | 28-Dec-22 | 29-Aug-23 | 02-Nov-22 |  |  | Customer | Customer |  | 0
644533 | 644533 - THE BOND DEVELOPMENT – SUBD RES | 815 - Addiscott | 101887 | Active | 93 | ANALYZE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir | 10-Aug-22 |  |  | 72808.07 | 63616.87 | 72432.43 | 72808.07 | Dave Lindsay | Transpw | 19-Oct-22 | 26-Jul-23 | 04-Oct-22 | 17-Aug-22 | 24-Aug-22 |  |  |  | 375.64
644589 | UNION VILLAGE PH2B - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644627 | TFP AUORA DEVELOPMENT (MS) -CAP RED EDS | 815 - Addiscott | 151531 | Active | 10 | ACTIVE |  |  | 2023 | D'Onofrio, Tony | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644636 | 644636 - RUTHERFORD RD. - #3650 | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 18-Aug-22 |  |  | 67125.72 | 19258.59 | 67125.72 | 67125.72 | Dave Lindsay | Somervl | 31-Oct-22 | 08-Aug-23 | 04-Oct-22 |  |  | Customer | Customer |  | 0
644642 | 644642 - 258 CHURCH ST/ALL/NS/3PH PAD | 825 - Patterson | 101919 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 12-Oct-22 |  |  | 75860.98 | 63006.47 | 75860.98 | 75860.98 | Lotto, Jay | HapAmp | 27-Dec-22 | 08-Aug-23 | 30-Nov-22 | 23-Mar-23 | 08-May-23 | Customer | Customer |  | 0
644649 | 644649 - 440 HANLAN RD/ VAU/ UP/ 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A | 14-Jun-22 |  |  | 159582.05 | 129673.44 | 159582.05 | 159582.05 | Dave Lindsay | Somervl | 26-Aug-22 | 16-Mar-23 | 29-Jul-22 | 21-Jul-22 | 07-Oct-22 |  | Customer |  | 0
452834 | 452834 - RER - MX - RELOC - DISSETTE ST - BARRIE LINE (66) - RAILWAY CROSSINGS | 825 - Patterson | 150591 | Active | 99 | COMPLETE |  |  | 2022 | Vande Kuyt, Greg | Grahovac, John | 01-Feb-22 |  |  | 167798.71 | 189299.84 | 159927.31 | 167798.71 | Dan Kish | K-Line | 30-Mar-22 | 26-Jul-23 | 16-Mar-22 | 24-Feb-22 | 25-Mar-22 |  |  |  | 7,871.40
644717 | VISTA HILLSIDE PHASE 5&6 - RES SUBD EDS | 825 - Patterson | 101887 | Active | 82 | Upload Completed |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 517847.35 | 5694.49 | 517847.35 | 517847.35 | East Coordinator |  |  | 26-Jul-23 | [6 empty] | 0
452832 | 452832 - RER - MX - RELOC - GIVEN RD & BRIDGE ST - BARRIE LINE (1924) - RAILWAY CROSSINGS | 825 - Patterson | 150591 | Active | 99 | COMPLETE |  |  | 2022 | Vande Kuyt, Greg | Grahovac, John | 23-Feb-22 |  |  | 210561.26 | 220527.7 | 201660.72 | 210561.26 | Dan Kish | K-Line | 22-Apr-22 | 26-Jul-23 | 08-Apr-22 | 01-Mar-22 | 19-Apr-22 |  |  |  | 8,900.54
644746 | 645 VETERANS DRIVE/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 84 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 12-Dec-22 | 1 |  | 149554.47 | 24557.77 | 149554.47 | 149554.47 | Lotto, Jay | HapAmp | 19-Apr-23 | 04-Aug-23 | 06-Apr-23 | 06-Apr-23 |  | Customer | Customer |  | 0
644757 | 644757 - CREDITSTONE RD. - #777 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Yuen, Paul | 13-May-22 |  |  | 93485.35 | 52233.35 | 93485.35 | 93485.35 | Dave Lindsay | Somervl | 21-Jul-22 | 28-Jun-23 | 01-Jul-22 | 18-Aug-22 | 07-Oct-22 | Customer | Customer |  | 0
644771 | 644771 - 304 DUNLOP ST W/BAR/SR/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 18-Jul-22 |  |  | 17562.93 | 9546.74 | 17562.93 | 17562.93 | Lotto, Jay | HapAmp | 20-Sep-22 | 23-Sep-22 | 02-Sep-22 | 23-Jul-22 | 23-Jul-22 |  |  |  | 0
644779 | RA RELOCATIONS - FULLER AVENUE AND ROBERT STREET EAST, PENETANGUISHENE | 825 - Patterson | 101764 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644783 | GARDEN HOMES (MARKHAM) DEV- SUBD RES EDS | 815 - Addiscott | 151531 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644791 | 19TH AVE FILM STUDIO / MAR / NS / 3PH AU TRANS | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 8630.93 |  | 0 | East Coordinator |  |  | 23-May-23
644792 | 300 ATKINSON AVE / NS / VAU / 3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Mann, Drew | 06-Jun-23 |  |  | 190365.38 | 11034.73 | 190365.38 | 190365.38 | Dave Lindsay | Somervl | 02-Oct-23 | 02-Oct-23 | 26-Sep-23 | [5 empty] | 0
644793 | 341 MAPLEVIEW DR W/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 31-Mar-23 |  |  | 77985.02 | 44539.28 | 77985.02 | 77985.02 | Lotto, Jay | HapAmp | 19-Jun-23 | 26-Jul-23 | 12-Jun-23 | 24-Apr-23 | 26-Jun-23 |  | Customer |  | 0
644808 | 125 SIMCOE ROAD, BRADFORD - RELOCATE POLES FOR NEW DEVELOPMENT | 825 - Patterson | 101763 | Active | 92 | ANALYZE |  |  | 2023 | Lacombe, Joel | Harrington, James | 22-May-23 |  |  | 294614.13 | 241590.74 | 294614.13 | 294614.13 | Mark Timbers | K-Line | 14-Jul-23 | 26-Jul-23 | 15-Jun-23 | 02-Jun-23 | 08-Jul-23 |  |  |  | 0
644825 | 15783 YONGE ST/AUR/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644830 | 8905 BATHURST ST/ RHL/UP/3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 2931.06 |  | 0 | East Coordinator |  |  | 20-Jul-20
644873 | HIGHWAY NO. 27 - #8336 | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644906 | INSTALL 4 NEW CCTS OVER CNYARD PT2 - OUTSIDE YARD | 815 - Addiscott | 101036 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644914 | 10-24 GROVE ST E/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644760 | 45 TYLER ST - POLE RELOCATIONS | 815 - Addiscott | 101763 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644876 | 644876 - CAPLINK SYSTEM EXPANSION - 6685 LANGSTAFF | 815 - Addiscott | 152359 | Active | 98 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan | 05-Oct-22 |  |  | 214780.49 | 216724.57 | 214780.49 | 214780.49 | Morrow, Joe |  | 20-Dec-22 | 26-Jul-23 | 28-Nov-22 | 02-Nov-22 | 07-Dec-22 |  |  |  | 0
644924 | BGLG - ELGIN MILLS ROAD | 815 - Addiscott | 152359 | Active | 40 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644931 | 67 OWEN ST/BAR/NS/3 PH PAD | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644933 | 2023 CABLE REPLACEMENT - A05 - MURRAY DR & GOLF LINKS DR - AURORA - PHASE 2 EAST | 815 - Addiscott | 151911 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 13-Dec-22 |  |  | 981341.7 | 28789 | 981341.7 | 981341.7 | Dave Lindsay | Transpw | 07-Nov-23 | 07-Nov-23 | 08-Sep-23 | [5 empty] | 0
644748 | CHILD WO - MARKHAM TS#1 T1/T2 DIFFERENTIAL PROTECIONS UPGRADE - LABOUR | 815 - Addiscott | 150079 | Inactive | 99 | CANCELLED |  |  | 2023 | Reesor, Gerald | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644967 | ROGERS SERVICE BEHIND 7100 KEELE ST / VAU / UP / 1PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
644998 | 644998 - POLE REPLACEMENT PRIMONT ISLINGTON | 815 - Addiscott | 151531 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P | 17-Jan-23 |  |  | 48711.8 | 37339.37 | 48711.8 | 48711.8 | Kristine Gordon |  | 05-Apr-23 | 02-Aug-23 | 27-Mar-23 | 21-Mar-23 |  |  |  |  | 0
645007 | 7 SEINCLIFFE - POOL CLEARANCE DEVIATION | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645014 | BUNKERS CREEK POLE REPLACEMENTS - CITY OF BARRIE INITIATED CULVERT REPLACEMENTS | 825 - Patterson | 101763 | Inactive | 99 | CANCELLED |  |  | 2023 | Pelleja, Emily | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645013 | DYMENTS CREEK POLE RELOCATIONS - CITY OF BARRIE INITIATED CULVERT REPLACEMENTS | 825 - Patterson | 101763 | Inactive | 99 | CANCELLED |  |  | 2023 | Pelleja, Emily | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645016 | 152 KING ST/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645039 | 645039 - 185 DUNLOP STREET EAST, BARRIE - VAULT REPLACEMENT FOR NEW DEVELOPMENT | 825 - Patterson | 101763 | Active | 92 | ANALYZE |  |  | 2023 | Lacombe, Joel | Mckeen, Brant | 23-Jun-23 |  |  | 219741.39 | 31746.49 | 181993.69 | 219741.39 | Lotto, Jay | HapAmp | 10-Oct-23 | 10-Oct-23 | 08-Aug-23 | 12-Jul-23 | 19-Jul-23 |  |  |  | 37,747.70
645047 | SUBDIVISION EMERALDS OF MAPLE GROVE | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645049 | 521 BIG BAY POINT RD/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645057 | ROUGESIDE PROMENADE/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645060 | HIGHWAY NO. 27 - #7845/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 11-Apr-23 |  |  | 115519.08 | 6469.55 | 115519.08 | 115519.08 | Dave Lindsay | Somervl | 10-Aug-23 | 20-Sep-23 | 21-Jun-23 | [5 empty] | 0
645070 | ADDITNG ARRESTORS - TRANSIT JOBS - METROLINX | 815 - Addiscott | 151450 | Active | 40 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645122 | 21 MILLS RD/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 02-May-23 |  |  | 108737.35 | 8550.92 | 108737.35 | 108737.35 | Lotto, Jay | HapAmp | 14-Aug-23 | 14-Aug-23 | 31-Jul-23 | [5 empty] | 0
645126 | RER - MX - RELOC - HIGHWAY 7 - STOUFFVILLE LINE (772) - RAILWAY CROSSINGS | 815 - Addiscott | 150592 | Active | 50 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator | K-Line |  | 20-Jul-20
645155 | SWITCHGEAR REMOVAL APPLEMILL - VMC | 815 - Addiscott | 151531 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
453619 | RER - MX - RELOC - 16TH AVE - STOUFFVILLE LINE (778) - RAILWAY CROSSINGS | 815 - Addiscott | 150592 | Active | 82 | H8 |  |  | 2023 | Khuu, Philander | Grahovac, John | 16-Mar-22 |  |  | 467104.1 | 61675.15 | 453778.85 | 467104.1 | Macdonald, Steve | K-Line | 16-Jan-25 | 16-Jan-25 | 01-Oct-24 | [5 empty] | 13,325.25
645166 | 447 BAYFIELD ST/BAR/NS/3 PH PAD | 825 - Patterson | 101919 | Active | 95 | ANALYZE |  |  | 2023 | Harris, Geoff L. | Cranley, Stephen | 05-Dec-22 | 1 |  | 162346.44 | 193117.88 | 162346.44 | 162346.44 | Lotto, Jay | HapAmp | 14-Feb-23 | 11-Aug-23 | 30-Jan-23 | 29-Nov-22 | 29-Nov-22 |  |  |  | 0
645175 | 616 APPLEWOOD CRES / VAU / NS / 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645176 | 645176 - 240 MILANI BLVD / VAU / NS / 3PH PAD | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 10-Aug-22 |  |  | 76541.22 | 60382.96 | 76541.22 | 76541.22 | Dave Lindsay | Somervl | 25-Oct-22 | 03-Aug-23 | 28-Sep-22 | 23-Jun-23 |  | Customer | Customer |  | 0
645192 | PORTAGE PKWY - SYSTEM EXPANSION | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2023 | Corriveau, Tom N | Jolie, Chris |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 03-Jul-23
645209 | 645209 - BERZCY WARDEN SINGLE POLE RELOACTIONS | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Murray, Jake R | 13-Jun-22 |  |  | 106907.25 | 98019.07 | 106907.25 | 106907.25 | Morrow, Joe |  | 29-Aug-22 | 25-May-23 | 15-Aug-22 | 11-Aug-22 | 04-Oct-22 |  | Contractor |  | 0
645216 | DUFFERIN ST & LANGSTAFF RD - PLATFORM CONFLICT | 815 - Addiscott | 101761 | Active | 98 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan | 02-Feb-23 |  |  | 14251.59 | 5372.95 | 14251.59 | 14251.59 | Morrow, Joe |  | 01-Feb-23 | 26-Jul-23 | 01-Feb-23 | 02-Feb-23 | 02-Feb-23 | xBy-passed |  |  | 0
645220 | 645220 - 7200 MARKHAM RD/ MAR/ SR/ 3PH PAD | 815 - Addiscott | 101791 | Active | 94 | COMPLETE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 03-May-22 |  |  | 19393.05 | 16483.97 | 19393.05 | 19393.05 | Dave Lindsay |  | 24-Jun-22 | 26-Jul-23 | 14-Jun-22 | 06-Jun-22 | 31-Oct-22 | Customer | Customer |  | 0
645229 | 146 OLD KENNEDY ROAD DEVELOPMENT - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645239 | PHASE 1-OH&UG RELOC. AT WOODBINE AVE(MAJOR MACKENZIE DR-16THE AVE) AND 16TH AVE | 815 - Addiscott | 151587 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R - vacancy |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645241 | 36 APPLE CREEK BLVD/ MAR/ NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 20-Apr-23 |  |  | 266870.46 | 8991.53 | 266870.46 | 266870.46 | Dave Lindsay | Somervl | 16-Aug-23 | 16-Aug-23 | 08-Aug-23 | [5 empty] | 0
645244 | 645244 - 36 APPLE CREEK/MAR/SR/3PH PAD | 815 - Addiscott | 101791 | Active | 94 | COMPLETE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 05-Jul-22 |  |  | 50640.55 | 40753.38 | 50640.55 | 50640.55 | Dave Lindsay | Somervl | 21-Sep-22 | 26-Jul-23 | 17-Aug-22 | 25-Sep-22 | 04-Apr-23 | Customer | Customer |  | 0
645247 | 547 BAYFIELD ST/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
453628 | 453628 - HUNTINGTON RD. - #8500 - 180 CORPORATE OFFI | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 05-Apr-22 |  |  | 105204.5 | 103094.04 | 105204.5 | 105204.5 | Dave Lindsay | Somervl | 12-Jul-22 | 26-Jul-23 | 02-Jun-22 | 22-Dec-22 | 03-May-23 | Customer | Customer |  | 0
645278 | BYRNE DR- PHASE 2 - BARRIE | 825 - Patterson | 101764 | Active | 10 | ACTIVE |  |  | 2023 | Pelleja, Emily | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645295 | 19TH AVE. - #3751 | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 1255.39 |  | 0 | East Coordinator |  |  | 20-Jul-20
645296 | NAO TOWNS -PHASE 1 - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645306 | 16 LUNAR CRESCENT, MARKHAM | 815 - Addiscott | 101763 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
454150 | 454150 - ICI SWITCHING ROOM/HS1 & HS2 ON BIRCHMOUNT RD | 815 - Addiscott | 101791 | Active | 93 | ANALYZE |  |  | 2023 | Dibratto, Susan | Paterson, Greg | 04-Apr-22 |  |  | 194045.07 | 204219.96 | 194045.07 | 194045.07 | Dave Lindsay | Somervl | 28-Jun-22 | 26-Jul-23 | 02-Jun-22 | 06-Jun-22 | 29-Mar-23 | Customer | Customer |  | 0
645323 | 2705 & 2755 ELGIN MILLS ROAD | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645328 | 645328 - 2023 CABLE INJECTION - R23 - BATHURST - WELDRICK - YONGE - MAJOR MACKENZIE | 815 - Addiscott | 152386 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 |  |  | 1534112.1 | 1214792.66 | 1534112.1 | 1534112.1 | Horlings, Jake | Nvinium | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 01-Jan-23 |  |  |  |  | 0
645358 | 2023 POLE RENEWAL - P33437 - 41 GUARDSMAN RD - CUSTOMER OWNED SEC | 815 - Addiscott | 100867 | Active | 79 | Upload Completed |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 11-Jun-23 | 1 |  | 47880.6 | 18083.43 | 47880.6 | 47880.6 | Wong, Henry |  |  | 26-Jul-23 | [6 empty] | 0
645357 | 645357 - 2023 POLE RENEWAL - P44936 - 150 CREDITSTONE RD - CUSTOMER OWNED SEC | 815 - Addiscott | 100867 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 15-May-23 | 1 |  | 50166.19 | 18747.55 | 50166.19 | 50166.19 | Kristine Gordon | Somervl | 31-Oct-23 | 31-Oct-23 | 10-Oct-23 | [5 empty] | 0
645356 | 2023 POLE RENEWAL- P32953 - 245 TORBAY RD - CUSTOMER OWNED SEC | 815 - Addiscott | 100867 | Active | 79 | Upload Completed |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 11-Jun-23 | 1 |  | 109238.23 | 18738.56 | 109238.23 | 109238.23 | Wong, Henry |  |  | 26-Jul-23 | [6 empty] | 0
645355 | 2023 POLE RENEWAL - P33141 - 295 STEELCASE RD E - CUSTOMER OWNED SEC | 815 - Addiscott | 100867 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  | 1 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645365 | 645365 - MARKHAM RD. - 9763 & 9757/MAR/NS/CUSTOMER-OWN SUBSTATION | 815 - Addiscott | 101791 | Active | 95 | ANALYZE |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 22-Jul-22 |  |  | 62055.78 | 5111.21 | 62055.78 | 62055.78 | Dave Lindsay | Somervl | 28-Sep-22 | 04-Aug-23 | 02-Sep-22 | 05-Dec-22 | 24-Feb-23 | Customer | Customer |  | 0
645374 | 645374 - 152 WELLS STREET, AURORA - POLE RELOCATION | 815 - Addiscott | 101761 | Active | 95 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan | 09-Aug-22 |  |  | 13393.56 | 18463.48 | 13393.56 | 13393.56 | Morrow, Joe |  | 12-Dec-22 | 26-Jul-23 | 12-Dec-22 | 07-Nov-22 | 07-Nov-22 |  |  |  | 0
645373 | 645373 - 2023 POLE REPLACEMENT - REPLACE P52314 - 7777 KIPLING AVE | 815 - Addiscott | 100867 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 18-Apr-23 | 1 |  | 84124.95 | 31494.71 | 84124.95 | 84124.95 | Kristine Gordon | Somervl | 14-Jun-23 | 28-Jul-23 | 12-Jun-23 | 15-Jun-23 |  | Filler |  |  | 0
645372 | 645372 - 2023 POLE REPLACEMENT - REPLACE P43255 - 8000 KEELE ST | 815 - Addiscott | 100867 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 15-May-23 | 1 |  | 68913.47 | 19656.39 | 68913.47 | 68913.47 | Kristine Gordon | Somervl | 30-Nov-23 | 30-Nov-23 | 13-Nov-23 | [5 empty] | 0
645370 | EARL GLEN DEVELOPMENT PHASE 1 | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645378 | 85 TORBAY RD / MAR / SR / 3PH VAULT DEMO | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Mann, Drew | 04-Jul-23 |  |  | 18195.87 | 2119.43 | 18195.87 | 18195.87 | Dave Lindsay | Somervl | 21-Aug-23 | 21-Aug-23 | 17-Aug-23 | [5 empty] | 0
645393 | 2024 CABLE INJECTION, V26 - TESTON - KEELE - MAJOR MACKENZIE - JANE | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645392 | 2024 CABLE INJECTION, V24 - LANGSTAFF - JANE - RUTHERFORD - KEELE | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645391 | 645391 - 2023 CABLE INJECTION, V17 - JACOB KEFFER PARKWAY AREA OF VAUGHAN | 815 - Addiscott | 151461 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 |  |  | 2299691.97 | 318225.6 | 2299691.97 | 2299691.97 | Horlings, Jake | Nvinium | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 01-Jan-23 |  |  |  |  | 0
645403 | KIM WO - 2024 BUDGET | 825 - Patterson |  | Active | 10 | ACTIVE |  |  | 2023 | Bowman, Todd J | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645413 | 241 KING ST/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 27-Jun-23 |  |  | 102826.61 | 11100.77 | 102826.61 | 102826.61 | Lotto, Jay | HapAmp | 21-Dec-23 | 21-Dec-23 | 11-Dec-23 | [5 empty] | 0
645412 | 251 KING ST/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 27-Jun-23 |  |  | 116005.98 | 4934.7 | 116005.98 | 116005.98 | Lotto, Jay | HapAmp | 02-Oct-23 | 02-Oct-23 | 15-Sep-23 | [5 empty] | 0
645426 | RUTHERFORD GRADE SEPARTION POLE RESETTING | 815 - Addiscott | 101762 | Active | 95 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Murray, Jake R | 19-Apr-22 |  |  | 185972.03 | 33156.75 | 185972.03 | 185972.03 | Tom Corriveau |  | 25-Apr-22 | 26-Jul-23 | 19-Apr-22 | 19-Apr-22 | 25-Apr-22 |  |  |  | 0
645427 | BIRCH WEST DEVELOPMENT - PHASE 3 EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645436 | CONCENTRIC NEUTRALS TO SINGLE POINT - RAIL CROSSINGS - METROLINX | 815 - Addiscott | 151450 | Inactive | 99 | CANCELLED |  |  | 2022 | Vande Kuyt, Greg | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645450 | CABLE REPLACEMENT - (A09) - WELLINGTON - YONGE - ST JOHNS - BATHURST, AURORA | 815 - Addiscott | 101781 | Active | 40 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645451 | 2024 CABLE REPLACEMENT - M15 - 16TH - MARKHAM - 9TH - HWY 7, MARKHAM | 815 - Addiscott | 101781 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645454 | 2022 POLE REPLACEMENTS 38 PRIDHAM PLACE TOTTENHAM | 825 - Patterson | 100867 | Active | 40 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645464 | 2024 CABLE REPLACEMENT, V26 - ST JOAN ARC AVE, KILLIAN RD, STERLING CR, MARWOOD | 815 - Addiscott | 101781 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645466 | GUY WIRES REMOVAL AT 16TH AVENUE AND MARKHAM RD | 815 - Addiscott | 101763 | Active | 95 | COMPLETE |  |  | 2022 | Corriveau, Tom N | Murray, Jake R | 11-May-22 |  |  | 653.44 | 977.84 | 653.44 | 653.44 | Tom Corriveau |  | 11-May-22 | 26-Jul-23 | 11-May-22 | 11-May-22 | 11-May-22 |  |  |  | 0
645488 | 645488 - 2022 VAULT LID RENEWAL PROGRAM - V23 - 37 MULCASTER ST | 825 - Patterson | 151526 | Active | 95 | ANALYZE |  |  | 2022 | Bowman, Todd J | Walters, Geoffrey D | 25-Aug-22 | 1 | 1 | 251816.67 | 273345.78 | 251816.67 | 251816.67 | Lotto, Jay | HapAmp | 23-Nov-22 | 26-Jul-23 | 06-Oct-22 | 14-Nov-22 | 25-Nov-22 | Materials | Materials |  | 0
645489 | 645489 - 2023 VAULT LID RENEWAL PROGRAM - V15 - 2 CHASE MCEACHERN WAY | 825 - Patterson | 151526 | Active | 82 | RELEASED |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D | 17-Feb-23 |  |  | 391998.91 | 19814.78 | 391998.91 | 391998.91 | Lotto, Jay | HapAmp | 30-Nov-23 | 30-Nov-23 | 13-Oct-23 | [5 empty] | 0
645494 | 2023 VAULT LID RENEWAL PROGRAM - V17 - 43 MAPLE AVE. | 825 - Patterson | 151526 | Active | 82 | RELEASED |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D | 31-Jan-23 | 1 |  | 204193.74 | 24744.84 | 204193.74 | 204193.74 | Lotto, Jay | HapAmp | 31-Aug-23 | 31-Aug-23 | 17-Jul-23 | [5 empty] | 0
645496 | 2023 VAULT LID RENEWAL PROGRAM - V3 - 38 MAPLE AVE. | 825 - Patterson | 151526 | Active | 48 | ACTIVE |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D |  | 1 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645495 | 2023 VAULT LID RENEWAL PROGRAM - V1- 1 DUNLOP ST WEST | 825 - Patterson | 151526 | Active | 50 | ACTIVE |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D |  | 1 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645497 | 2023 VAULT LID RENEWAL PROGRAM - V24 - 75 COLLIER ST. | 825 - Patterson | 151526 | Active | 48 | ACTIVE |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D |  | 1 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645499 | 10 ENTERPRISE NORTH/MAR/NS/CUST OWNED | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645502 | 2023 VAULT LID RENEWAL PROGRAM - V4 - 39 DUNLOP ST. WEST | 825 - Patterson | 151526 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645504 | 27 DEBRA CRES - BARRIE - UG SECONDARY SERVICE REPLACEMENT | 825 - Patterson | 151450 | Active | 10 | ACTIVE |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645506 | 227 ROSE ST. - BARRIE - UNDERGROUND SECONDARY SERVICE REPLACEMENT | 825 - Patterson | 151450 | Active | 10 | ACTIVE |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645584 | 2024 CABLE REPLACEMENT, M33 - VILLAGE PKWY, BRIARWOOD RD AND RAE CR | 815 - Addiscott | 101781 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645588 | BAYVIEW AND ELGIN MILLS RD TOWER A / RHL / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
634810 | 634810 - 25 ALBERT ST W/ALL/NS/3PH PAD | 825 - Patterson | 101919 | Active | 99 | ANALYZE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 05-May-22 |  |  | 76525.31 | 61073.31 | 76525.31 | 76525.31 | Lotto, Jay | HapAmp | 12-Jul-22 | 26-Jul-23 | 20-Jun-22 | 11-May-22 | 30-May-22 |  |  |  | 0
645591 | 645591 - 5336 HWY 7 E / MAR / SR / 3PH OH BANK DEMO | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2022 | Joshi, Namrata | Mann, Drew | 19-May-22 |  |  | 5057.99 | 5554.4 | 5057.99 | 5057.99 | Kristine Gordon |  | 12-Jul-22 | 26-Jul-23 | 11-Jul-22 | 26-Jun-22 | 26-Jun-22 |  |  |  | 0
645607 | BLOOMINGTON RD, ACADEMY DR TO YONGE ST | 815 - Addiscott | 101763 | Active | 50 | H8 |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645614 | 14TH AVE @ MCCOWAN - POLE RELOCATION | 815 - Addiscott | 101763 | Active | 70 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645640 | NINTH LINE ROAD RE-CONFIGURATION - CITY OF MARKHAM | 815 - Addiscott | 101762 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645643 | PROJECT RAINBOW SITE 2 | 815 - Addiscott | 152601 | Active | 45 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645687 | 645687 - 217 VICTORIA ST W/ALL/NS/3PH PAD | 825 - Patterson | 101919 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 03-Nov-22 |  |  | 71615.09 | 39491.83 | 71615.09 | 71615.09 | Lotto, Jay | HapAmp | 26-Jan-23 | 26-Jul-23 | 27-Dec-22 | 09-Feb-23 | 30-May-23 | MC/PUCC Permit | MC/PUCC Permit |  | 0
645686 | 645686 - 10 GROVE ST E/BAR/NS/TEMP 3PH PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 21-Mar-23 |  |  | 85018 | 9405.04 | 85018 | 85018 | Lotto, Jay | HapAmp | 24-Nov-23 | 24-Nov-23 | 06-Nov-23 | [5 empty] | 0
645689 | 645689 - 550 BAYFIELD ST/BAR/UP/3PH PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 21-Mar-23 |  |  | 72021.06 | 6250.1 | 72021.06 | 72021.06 | Lotto, Jay | HapAmp | 05-Jun-23 | 04-Aug-23 | 17-May-23 | [5 empty] | 0
645696 | WOODBINE AVE. - #7530/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645698 | 2022 EMERGING UG, T8975 - 189 HOLLAND ST. EAST - SINKING 3PH TX REPLACEMENT | 825 - Patterson | 101824 | Active | 10 | ACTIVE |  |  | 2023 | Lotto, Jay | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645700 | 645700 - 9825 YONGE ST/RH/SR/3PH PAD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 30-Jun-22 |  |  | 16949.83 | 4646.13 | 16949.83 | 16949.83 | Dave Lindsay | Somervl | 07-Sep-22 | 02-Aug-23 | 17-Aug-22 |  |  | Customer | Customer |  | 0
645702 | 645702 - 9839 YONGE ST/RH/SR/3PH PAD | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 30-Jun-22 |  |  | 21219.27 | 10903.97 | 21219.27 | 21219.27 | Dave Lindsay | Somervl | 07-Sep-22 | 02-Aug-23 | 17-Aug-22 | 24-Sep-22 | 03-Apr-23 | Customer | Customer |  | 0
645733 | HIGHWAY NO. 7 WEST AND COMMERCE ST - VMC BLK E2 | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645741 | MAINTENANCE- CHARLIEVILLE ENCLAVE TOWNHOMES-AURORA | 815 - Addiscott |  | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645740 | CHARLIEVILLE ENCLAVE TOWNHOMES-AURORA | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645745 | 126 JOHN ST/BRA/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645748 | MAPLEVIEW DEVELOPMENTS LTD | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645751 | MAINTENANCE - MAPLEVIEW DEVELOPMENTS LTD - BARRIE | 825 - Patterson |  | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645752 | 7647 KENNEDY ROAD TOWNHOMES | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645757 | 290 RODINEA RD / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645762 | MAJOR MAC & ISLINGTON - GUYING RECONFIGURATION | 815 - Addiscott | 101762 | Active | 70 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645776 | 645776 - 9600 KEELE STREET | 815 - Addiscott | 101791 | Active | 99 | ANALYZE |  |  | 2022 | Joshi, Namrata | Yuen, Paul | 05-Jul-22 |  |  | 6319.53 | 4907.29 | 6319.53 | 6319.53 | Kristine Gordon |  | 23-Aug-22 | 26-Jul-23 | 22-Aug-22 | 28-Jul-22 | 28-Jul-22 |  |  |  | 0
645821 | 645821 - 2023 SWITCH RENEWAL - A06SL2027 - AURORA | 815 - Addiscott | 101027 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 23-Nov-22 | 1 | 1 | 119569.49 | 110774.54 | 119569.49 | 119569.49 | Reginald Clarke |  | 09-Jun-23 | 08-Aug-23 | 30-May-23 | 03-May-23 |  |  |  |  | 0
645820 | 645820 - 2023 SWITCH RENEWAL - A10SL2034 - AURORA | 815 - Addiscott | 101027 | Active | 80 | H2 |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 15-Dec-22 | 1 |  | 118407.86 | 49714.39 | 118407.86 | 118407.86 | Wong, Henry |  |  | 26-Jul-23 | [6 empty] | 0
645819 | 645819 - 2023 SWITCH RENEWAL - A11SL2009 - AURORA | 815 - Addiscott | 101027 | Active | 92 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 09-Nov-22 | 1 | 1 | 128785.33 | 85495.3 | 128785.33 | 128785.33 | Reginald Clarke |  | 22-Jun-23 | 26-Jul-23 | 12-Jun-23 | 02-May-23 | 15-May-23 |  |  |  | 0
645818 | 645818 - 2023 SWITCH RENEWAL - A10SL2000 - AURORA | 815 - Addiscott | 101027 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 25-Nov-22 | 1 |  | 146639.54 | 45676.42 | 146639.54 | 146639.54 | Reginald Clarke |  | 12-Jul-23 | 10-Aug-23 | 26-Jun-23 | 15-May-23 |  |  |  |  | 0
645817 | 645817 - 2023 DA - A11SL2008 - AURORA | 815 - Addiscott | 101027 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 07-Oct-22 | 1 | 1 | 168134.59 | 93636.3 | 168134.59 | 168134.59 | Reginald Clarke |  | 14-Dec-22 | 26-Jul-23 | 28-Nov-22 | 14-Mar-23 | 22-Mar-23 | Control/SCADA | Control/SCADA |  | 0
645816 | 645816 - 2023 SWITCH REPLACEMENT - A01SL2008 - AURORA | 815 - Addiscott | 101027 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 1 |  | 150630.16 | 44443.17 | 150630.16 | 150630.16 | Reginald Clarke |  | 20-Jul-23 | 04-Aug-23 | 10-Jul-23 | 15-May-23 |  |  |  |  | 0
645826 | 645826 - 8470 HIGHWAY 27/VAU/NS/3-PH PAD | 815 - Addiscott | 101791 | Active | 94 | COMPLETE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 31-Oct-22 |  |  | 143157.31 | 89448.1 | 143157.31 | 143157.31 | Dave Lindsay | Somervl | 30-Jan-23 | 26-Jul-23 | 14-Dec-22 | 07-Mar-23 | 07-Mar-23 | Customer | Customer |  | 0
645827 | PEBBLELANE COURT - #19/RHL/NS/1PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 29-Mar-23 |  |  | 43840.06 | 3449.21 | 43840.06 | 43840.06 | Dave Lindsay | N/A | 14-Jun-23 | 02-Aug-23 | 31-May-23 | [5 empty] | 0
645849 | 120 MILANI BLVD / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Mann, Drew | 19-Apr-23 |  |  | 298554.81 | 9009.97 | 298554.81 | 298554.81 | Dave Lindsay | Somervl | 28-Aug-23 | 28-Aug-23 | 21-Aug-23 | [5 empty] | 0
645850 | 645850 - 8405 HUNTINGTON RD / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 10-Aug-22 |  |  | 134885.22 | 143914.22 | 134885.22 | 134885.22 | Dave Lindsay | Somervl | 27-Oct-22 | 04-Aug-23 | 28-Sep-22 | 14-Apr-23 |  | Customer | Customer |  | 0
645856 | 645856 - HIGHWAY 7, BUR OAK TO WILLIAM FORSTER | 815 - Addiscott | 101763 | Active | 95 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander | 15-Dec-22 |  |  | 238159.18 | 257720.59 | 234306.97 | 238159.18 | Macdonald, Steve | K-Line | 29-Mar-23 | 26-Jul-23 | 06-Mar-23 | 27-Mar-23 | 22-Apr-23 | Contractor | Contractor |  | 3,852.21
645862 | 2 CHASE MCEACHERN WAY/BAR/SR/REMOVAL | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
645866 | 645866 - CREDITSTONE RD. - #551/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 84 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 04-Jan-23 | 1 |  | 149298.97 | 9467.94 | 149298.97 | 149298.97 | Dave Lindsay | Somervl | 05-May-23 | 01-Aug-23 | 17-Apr-23 | 20-Mar-23 |  |  | Materials |  | 0
646357 | 646357 - 9355 LESLIE ST / RHL / UP / 3PH PAD RELOCATION | 815 - Addiscott | 101791 | Active | 99 | ANALYZE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 25-Aug-22 |  |  | 78849.69 | 75040.88 | 78849.69 | 78849.69 | Dave Lindsay | Somervl | 16-Nov-22 | 26-Jul-23 | 19-Oct-22 | 14-Oct-22 | 06-Mar-23 |  |  |  | 0
646367 | 168 OLD KENNEDY RD/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646368 | 388 SPINNAKER WAY/ VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 23-Nov-22 |  |  | 135179.4 | 105606.67 | 135179.4 | 135179.4 | Dave Lindsay | Somervl | 13-Feb-23 | 26-Jul-23 | 11-Jan-23 | 16-Mar-23 | 21-Mar-23 | Customer |  |  | 0
646369 | 7979 WESTON RD / VAU / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646371 | MILL STREET, MARKHAM | 815 - Addiscott | 101763 | Active | 70 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646381 | 646381 - WOODBRIDGE AVE. - #260/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 11-Nov-22 |  |  | 126606.95 | 3920.13 | 126606.95 | 126606.95 | Dave Lindsay | Somervl | 02-Feb-23 | 14-Aug-23 | 03-Jan-23 | [5 empty] | 0
646446 | 646446 - 2023 SG REPL - BATCH 1 - MARKHAM | 815 - Addiscott | 100859 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 3 |  | 244762.77 | 170124.53 | 244762.77 | 244762.77 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 05-Jun-23 | 07-Feb-23 |  |  |  |  | 0
646450 | 646450 - 2023 SG REPL - BATCH 5 - VAUGHAN | 815 - Addiscott | 100859 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 4 |  | 385973.91 | 269185.79 | 385973.91 | 385973.91 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 09-Mar-23 |  |  |  |  | 0
646449 | 646449 - 2023 SG REPL - BATCH 4 - VAUGHAN | 815 - Addiscott | 100859 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 5 |  | 376217.85 | 248790.76 | 455249.82 | 376217.85 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 09-Mar-23 |  |  |  |  | -79,031.97
646447 | 646447 - 2023 SG REPL - BATCH 2 - RICHMOND HILL | 815 - Addiscott | 100859 | Active | 94 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 2 | 2 | 177757.79 | 149781.64 | 177757.79 | 177757.79 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 09-Mar-23 | 21-Apr-23 |  |  |  | 0
646462 | 2023 SG REPL - AUTO 31-L87 - VAUGHAN | 815 - Addiscott | 100859 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  | 1 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646461 | 646461 - 2023 SG REPL - AUTO 31-L71 - VAUGHAN | 815 - Addiscott | 100859 | Active | 92 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 18-Nov-22 | 1 | 1 | 103991.28 | 86091.08 | 103991.28 | 103991.28 | Horlings, Jake |  | 31-Dec-23 | 26-Jul-23 | 05-Jun-23 | 09-May-23 | 09-May-23 |  |  |  | 0
646459 | 646459 - 2023 SG REPL - AUTO 16-L216 - VAUGHAN | 815 - Addiscott | 100859 | Active | 94 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 18-Nov-22 | 1 | 1 | 108699.71 | 102151.93 | 108699.71 | 108699.71 | Horlings, Jake |  | 31-Dec-23 | 26-Jul-23 | 01-Jan-23 | 09-Mar-23 | 09-Mar-23 |  |  |  | 0
646458 | 646458 - 2023 SG REPL - AUTO 16-L186 - VAUGHAN | 815 - Addiscott | 100859 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 18-Nov-22 | 1 |  | 91787.38 | 66713.91 | 91787.38 | 91787.38 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 09-Mar-23 |  |  |  |  | 0
646457 | 646457 - 2023 SG REPL - AUTO 15-L51 - VAUGHAN | 815 - Addiscott | 100859 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 16-Nov-22 | 1 |  | 109334.79 | 87684.7 | 109334.79 | 109334.79 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 01-Jan-23 | 09-Mar-23 |  |  |  |  | 0
646455 | 646455 - 2023 SG REPL - AUTO 25SUG001 - MARKHAM | 815 - Addiscott | 100859 | Active | 82 | RELEASED | High | SwGear | 2023 | Tenorlas, Reynaldo | Roy, James | 07-Dec-22 | 1 |  | 160362.5 | 12324.4 | 160362.5 | 160362.5 | Horlings, Jake | N/A | 08-Jun-23 | 31-Jul-23 | 05-Jun-23 | [5 empty] | 0
646454 | 646454 - 2023 SG REPL - AUTO A05SP2002 - AURORA | 815 - Addiscott | 100859 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 16-Nov-22 | 1 |  | 62691.87 | 8110.53 | 62691.87 | 62691.87 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 05-Jun-23 | [5 empty] | 0
646465 | 646465 - 2023 SG REPL - AUTO 51-L73 - VAUGHAN | 815 - Addiscott | 100859 | Active | 82 | RELEASED | High | SwGear | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 1 |  | 175009.52 | 11957.58 | 175009.52 | 175009.52 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 05-Jun-23 | [5 empty] | 0
646464 | 646464 - 2023 SG REPL - AUTO 37-L4 - VAUGHAN | 815 - Addiscott | 100859 | Active | 82 | RELEASED | High | SwGear | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 1 |  | 152345.89 | 13336.13 | 152345.89 | 152345.89 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 05-Jun-23 | [5 empty] | 0
646469 | 11 SPRING FARM RD/AUR/NS/3PH PAD | 825 - Patterson | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  | 1 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646495 | 646495 - 8885 WOODBINE AVE/MAR/UP/ 3PH PAD | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 22-Nov-22 |  |  | 99015.05 | 58721.37 | 99015.05 | 99015.05 | Dave Lindsay | Somervl | 07-Feb-23 | 27-Jul-23 | 10-Jan-23 | 14-Apr-23 | 03-May-23 | Customer | Customer |  | 0
646509 | 646509 - 2023 POLE RENEWAL - BATCH 4 - 12 POLES - MARKHAM | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 12 | 12 | 206429.26 | 188680.37 | 206429.26 | 206429.26 | Morrow, Joe |  | 27-Mar-23 | 27-Jul-23 | 27-Feb-23 | 21-Feb-23 | 16-Mar-23 |  |  |  | 0
646508 | 646508 - 2023 POLE RENEWAL - BATCH 3 - 10 POLES - MARKHAM | 815 - Addiscott | 100867 | Active | 95 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 10 | 10 | 209210.73 | 193980.58 | 209210.73 | 209210.73 | Morrow, Joe |  | 07-Jun-23 | 27-Jul-23 | 10-May-23 | 28-Apr-23 | 23-May-23 |  |  |  | 0
646506 | 2023 POLE REBUILD - MACHELL - 9 POLES | 815 - Addiscott | 100867 | Active | 40 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  | 9 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646505 | 646505 - 2023 POLE RENEWAL - BATCH 2 - 8 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 25-Nov-22 | 9 | 9 | 266465.29 | 238257.69 | 266465.29 | 266465.29 | Morrow, Joe |  | 06-Jul-23 | 27-Jul-23 | 29-May-23 | 14-Apr-23 | 28-Apr-23 |  |  |  | 0
646504 | 646504 - 2023 POLE REBUILD - CATHERINE ST - 19 POLES | 815 - Addiscott | 100867 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 09-Jun-23 | 19 |  | 362359.09 | 51402.02 | 362359.09 | 362359.09 | Reginald Clarke |  | 05-Oct-23 | 05-Oct-23 | 05-Sep-23 | [5 empty] | 0
646503 | 646503 - 2023 POLE RENEWAL - BATCH 1 - 6 POLES | 815 - Addiscott | 100867 | Active | 93 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 28-Nov-22 | 8 | 8 | 175028.28 | 173326.43 | 171111.75 | 175028.28 | Reginald Clarke |  | 07-Feb-23 | 27-Jul-23 | 16-Jan-23 | 31-Jan-23 | 01-Mar-23 | Materials | Materials |  | 3,916.53
646535 | 2023 POLE REBUILD - JOHN ST (RAILWAY) | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  | 5 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646533 | 646533 - 2023 POLE RENEWAL - BATCH 14 - 10 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 10 | 10 | 57110.73 | 43166.29 | 57110.73 | 57110.73 | Morrow, Joe |  | 08-Mar-23 | 27-Jul-23 | 27-Feb-23 | 21-Feb-23 | 27-Feb-23 |  |  |  | 0
646532 | 646532 - 2023 POLE RENEWAL - BATCH 10 - 10 POLES | 815 - Addiscott | 100867 | Active | 93 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 10 | 10 | 107464.32 | 79136.67 | 107464.32 | 107464.32 | Morrow, Joe |  | 27-Jun-23 | 27-Jul-23 | 08-Jun-23 | 28-Mar-23 | 04-Apr-23 |  |  |  | 0
646531 | 646531 - 2023 POLE RENEWAL - BATCH 9 - 12 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 12 | 12 | 179552.11 | 112791.64 | 179552.11 | 179552.11 | Morrow, Joe |  | 31-Mar-23 | 27-Jul-23 | 27-Feb-23 | 21-Feb-23 | 28-Mar-23 |  |  |  | 0
646530 | 646530 - 2023 POLE RENEWAL - BATCH 8 - 7 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 6 | 6 | 120264.43 | 123813.3 | 120264.43 | 120264.43 | Morrow, Joe |  | 09-May-23 | 27-Jul-23 | 17-Apr-23 | 03-Apr-23 | 02-Jun-23 |  | Weather |  | 0
646529 | 646529 - 2023 POLE RENEWAL - BATCH 7 - 4 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 4 | 4 | 45111.4 | 39925.1 | 45111.4 | 45111.4 | Morrow, Joe |  | 07-Mar-23 | 01-Aug-23 | 27-Feb-23 | 24-Jan-23 | 10-Feb-23 |  |  |  | 0
646528 | 646528 - 2023 POLE RENEWAL - BATCH 6 - 7 POLES | 815 - Addiscott | 100867 | Active | 93 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 08-Nov-22 | 7 | 7 | 97268.14 | 97472.34 | 97268.14 | 97268.14 | Morrow, Joe |  | 06-Feb-23 | 27-Jul-23 | 30-Jan-23 | 24-Jan-23 | 21-Feb-23 |  | Customer |  | 0
646527 | 646527 - 2023 POLE RENEWAL - BATCH 5 - 8 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 08-Nov-22 | 7 | 7 | 58048.85 | 30344.63 | 58048.85 | 58048.85 | Morrow, Joe |  | 26-Jan-23 | 27-Jul-23 | 16-Jan-23 | 03-Jan-23 | 18-Jan-23 |  |  |  | 0
646548 | 646548 - 2023 TX RENEWAL - BATCH 4 - 18 TX | 815 - Addiscott | 101508 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 18 |  | 449185.81 | 114864.83 | 449185.81 | 449185.81 | Dave Lindsay | Somervl | 25-May-23 | 25-Sep-23 | 01-Apr-23 | 24-Apr-23 |  | Locates |  |  | 0
646547 | 646547 - 2023 TX RENEWAL - BATCH 3 - 8 TX | 815 - Addiscott | 101508 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 8 |  | 145650.03 | 101015.54 | 145650.03 | 145650.03 | Horlings, Jake | Somervl | 14-Feb-23 | 25-Aug-23 | 01-Jan-23 | 09-Mar-23 |  | Filler |  |  | 0
646545 | 646545 - 2023 TX RENEWAL - BATCH 2 - 16 TX | 815 - Addiscott | 101508 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 16 |  | 446596.23 | 237397.15 | 446596.23 | 446596.23 | Horlings, Jake | Somervl | 07-Mar-23 | 15-Sep-23 | 01-Jan-23 | 09-Mar-23 |  | Filler |  |  | 0
646544 | 646544 - 2023 TX RENEWAL - BATCH 1 - 16 TX | 815 - Addiscott | 101508 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 16 | 16 | 449171.68 | 349061.15 | 449171.68 | 449171.68 | Horlings, Jake | Somervl | 09-Mar-23 | 27-Jul-23 | 01-Jan-23 | 09-Mar-23 | 20-Apr-23 | Filler | Filler |  | 0
646557 | 646557 - 19 PEBBLELANE COURT | 815 - Addiscott | 101761 | Active | 82 | RELEASED |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander | 02-Jun-23 |  |  | 57249.2 | 24596.52 | 57249.2 | 57249.2 | Macdonald, Steve | K-Line | 21-Jul-23 | 27-Jul-23 | 17-Jul-23 |  |  | Design |  |  | 0
646581 | 2023 - POLE REBUILD - PEMBERTON RD, KERSEY CRES, & YONGEHURST RD - 11 POLES | 815 - Addiscott | 100867 | Active | 79 | Upload Completed |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  | 11 |  | 253835.64 | 44878.08 | 253835.64 | 253835.64 | Wong, Henry |  |  | 27-Jul-23 | [6 empty] | 0
646583 | 646583 - 2022 - EMERGING OH - AIDA PL REMOVALS | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel | 27-Jul-22 |  |  | 11683.21 | 0 | 11683.21 | 11683.21 | Reginald Clarke |  | 12-Sep-22 | 23-Mar-23 | 08-Sep-22 | 28-Jul-22 | 28-Jul-22 |  |  |  | 0
646582 | 2023 - POLE REBUILD - CHELETENHAM AVE, HWY27/HWY7, & TRCA ZONED POLES - 12 POLES | 815 - Addiscott | 100867 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel |  | 12 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646593 | 646593 - 2023 - POLE RENEWAL - ROCKWELL RD & DONCREST RD - 4 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 10-Nov-22 | 4 | 4 | 43044 | 23759.88 | 43044 | 43044 | Morrow, Joe |  | 05-Apr-23 | 27-Jul-23 | 27-Mar-23 | 06-Mar-23 | 16-Mar-23 |  |  |  | 0
646592 | 646592 - 2023 - POLE RENEWAL - LESLIE ST - 4 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 07-Nov-22 | 5 | 5 | 59168.55 | 54734.87 | 59168.55 | 59168.55 | Morrow, Joe |  | 15-Feb-23 | 02-Aug-23 | 07-Feb-23 | 24-Jan-23 | 10-Feb-23 |  |  |  | 0
646591 | 646591 - 2023 - POLE RENEWAL - THORNHEIGHTS RD & LANGSTAFF RD E - 3 POLES | 815 - Addiscott | 100867 | Active | 93 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 07-Nov-22 | 3 | 3 | 80346.64 | 52627.67 | 80346.64 | 80346.64 | Kristine Gordon |  | 21-Mar-23 | 27-Jul-23 | 17-Mar-23 | 20-Mar-23 | 04-Apr-23 | Filler | Filler |  | 0
646590 | 646590 - 2023 - POLE RENEWAL - P37687 & P13162 - 2 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 02-Nov-22 | 2 | 2 | 35959.36 | 31038.15 | 35959.36 | 35959.36 | Kristine Gordon |  | 01-Mar-23 | 27-Jul-23 | 21-Feb-23 | 20-Mar-23 | 21-Mar-23 | Filler | Filler |  | 0
646589 | SOFIA COURT - #10/RHL/NS/CUSTOMER-OWN SUBSTATION | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646588 | 646588 - 2023 - POLE RENEWAL - P40465 & P40555 - 2 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 08-Dec-22 | 2 | 2 | 49146.45 | 24505.42 | 49146.45 | 49146.45 | Kristine Gordon |  | 16-Mar-23 | 27-Jul-23 | 02-Mar-23 | 01-Mar-23 | 13-Mar-23 |  |  |  | 0
646587 | 646587 - 2023 - POLE RENEWAL - BATCH 13 - 7 POLES | 815 - Addiscott | 100867 | Active | 93 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 02-Nov-22 | 7 | 7 | 92621.15 | 82957.93 | 92621.15 | 92621.15 | Reginald Clarke |  | 10-Feb-23 | 27-Jul-23 | 02-Feb-23 | 20-Mar-23 | 16-Apr-23 | Customer | Customer |  | 0
646585 | 646585 - 2023 - POLE RENEWAL - BATCH 12 - 6 POLES | 815 - Addiscott | 100867 | Active | 93 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 09-Nov-22 | 7 | 7 | 62119.61 | 44785.38 | 62119.61 | 62119.61 | Reginald Clarke |  | 01-Feb-23 | 27-Jul-23 | 23-Jan-23 | 31-Jan-23 | 13-Mar-23 | Materials | Materials |  | 0
646584 | 646584 - 2023 - POLE RENEWAL - BATCH 11 - 8 POLES | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 02-Nov-22 | 8 | 8 | 51414.42 | 48671.48 | 51414.42 | 51414.42 | Morrow, Joe |  | 25-Apr-23 | 27-Jul-23 | 17-Apr-23 | 06-Mar-23 | 03-Apr-23 |  |  |  | 0
646603 | PARENT W.O. FOR INSPECT/CONNECT/ I&C - BELMONT TOWNHOUSE DEVELOPMENT (EAST) | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646606 | ALECTRA EAST - SUBDIVISION MAINTENANCE - BELMONT TOWNHOUSE DEVELOPMENT WEST | 815 - Addiscott |  | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646605 | PARENT W.O. FOR INSPECT/CONNECT/ I&C - BELMONT TOWNHOUSE DEVELOPMENT (WEST) | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646610 | 243 SIXTEENTH AVE TOWNHOME ENCLAVE - SUBD RESEDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646623 | 646623 - 2023 DA - M16SL1005 - MARKHAM | 815 - Addiscott | 100886 | Active | 84 | ACTIVE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 15-Nov-22 | 1 |  | 118486.41 | 123995.37 | 118486.41 | 118486.41 | Reginald Clarke |  | 07-Jun-23 | 02-Aug-23 | 30-May-23 | 13-Apr-23 |  |  |  |  | 0
646621 | 646621 - 2023 DA - NEW UNIT ON MCCOWAN - MARKHAM | 815 - Addiscott | 100886 | Active | 92 | COMPLETE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 16-Nov-22 | 1 | 1 | 108963.03 | 123743.29 | 108963.03 | 108963.03 | Reginald Clarke |  | 23-May-23 | 27-Jul-23 | 15-May-23 | 24-Apr-23 | 03-May-23 |  |  |  | 0
646620 | 646620 - 2023 DA - V37SL3045 - VAUGHAN | 815 - Addiscott | 100886 | Active | 93 | COMPLETE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 15-Nov-22 | 1 | 1 | 100518.74 | 82668.88 | 100518.74 | 100518.74 | Reginald Clarke |  | 15-Mar-23 | 27-Jul-23 | 06-Mar-23 | 09-Feb-23 | 16-Feb-23 |  |  |  | 0
646619 | 646619 - 2023 DA - V37SL3042 - VAUGHAN | 815 - Addiscott | 100886 | Active | 93 | COMPLETE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 15-Nov-22 | 1 | 1 | 99352.98 | 90405.75 | 99352.98 | 99352.98 | Reginald Clarke |  | 03-Mar-23 | 27-Jul-23 | 22-Feb-23 | 25-Jan-23 | 15-Feb-23 |  |  |  | 0
646618 | 646618 - 2023 DA - NEW UNIT ON LESLIE - RICHMOND HILL | 815 - Addiscott | 100886 | Active | 92 | COMPLETE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 16-Nov-22 | 1 | 1 | 109515.86 | 125364.13 | 109515.86 | 109515.86 | Reginald Clarke |  | 19-May-23 | 27-Jul-23 | 10-May-23 | 01-May-23 | 04-May-23 |  |  |  | 0
646617 | 646617 - 2023 DA - V65SL3004 - VAUGHAN | 815 - Addiscott | 100886 | Active | 93 | COMPLETE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 15-Nov-22 | 1 | 1 | 92579.45 | 91736.63 | 92579.45 | 92579.45 | Reginald Clarke |  | 21-Feb-23 | 27-Jul-23 | 13-Feb-23 | 16-Mar-23 | 23-Mar-23 | Customer | Customer |  | 0
646616 | 646616 - 2023 DA - NEW UNIT ON MMD - VAUGHAN | 815 - Addiscott | 100886 | Active | 93 | COMPLETE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 16-Nov-22 | 1 | 1 | 116850.37 | 108000.38 | 116850.37 | 116850.37 | Reginald Clarke |  | 20-Mar-23 | 27-Jul-23 | 06-Mar-23 | 05-Apr-23 | 26-Apr-23 | Lines | Lines |  | 0
646615 | 646615 - 2023 DA - V29SL1008 - VAUGHAN | 815 - Addiscott | 100886 | Active | 96 | COMPLETE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 15-Nov-22 | 1 | 1 | 99346.51 | 78152.24 | 99346.51 | 99346.51 | Reginald Clarke |  | 09-Feb-23 | 27-Jul-23 | 31-Jan-23 | 12-Jan-23 | 18-Jan-23 |  |  |  | 0
646614 | 646614 - 2023 DA - V29SL1007 - VAUGHAN | 815 - Addiscott | 100886 | Active | 96 | COMPLETE | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 15-Nov-22 | 1 | 1 | 111772.39 | 92605.25 | 111772.39 | 111772.39 | Reginald Clarke |  | 30-Jan-23 | 08-Aug-23 | 17-Jan-23 | 12-Jan-23 | 18-Jan-23 |  |  |  | 0
646641 | MACKENZIE COMMON DEVELOPMENT EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646652 | DENISON ST/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646653 | BAYVIEW AND ELGIN MILLS RD TOWER B / RHL / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646656 | WIGNAL CRES. | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646655 | 8261 HWY 50 / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646737 | 10-24 GROVE ST E BUILDING B/BAR/NS/CUSTOMER OWNED SUBSTATION | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646760 | VTS4 PART 3 YR2 - FEEDERS TO KIRBY N SIDE | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646764 | VTS4 PART 3 YR3 - 2 CCTS ON WESTON FROM MMD TO RUTHERFORD | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646763 | VTS4 PART 3 YR2 - FEEDERS ON PINE VALLEY FROM TESTON TO MMD | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646762 | VTS4 PART 3 YR2 - FEEDERS ON TESTON FROM KIPLING TO PINE VALLEY | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646761 | VTS4 PART 3 YR2 - FEEDERS ON KIPLING FROM KIRBY TO TESTON | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646772 | 106 SCIBERRAS RD - POOL ENROACHMENT | 815 - Addiscott | 101761 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646783 | 646783 - 2022 CABLE REPLACEMENT, V38 - DIANAWOOD RIDGE - CWO V38 INJECTION | 815 - Addiscott | 150261 | Active | 80 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 04-Nov-22 |  |  | 82544.75 | 9293.52 | 82544.75 | 82544.75 | Horlings, Jake | Nvinium | 03-Jul-23 | 27-Jul-23 | 08-May-23 |  |  | Contractor |  |  | 0
646846 | 646846 - MAJOR MACK AT VOGELL RELOCATE CONFLICT POLE | 815 - Addiscott | 151531 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. | 13-Mar-23 |  |  | 84276.9 | 73556.42 | 84276.9 | 84276.9 | Kristine Gordon |  | 30-May-23 | 14-Aug-23 | 10-May-23 | 08-Jun-23 |  | Filler |  |  | 0
646843 | 61-83 HAYHOE AVE SUBDIVISION - INSPECT/CONNECT/ I&C | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646840 | 15094 YONGE STREET, AURORA - SYSTEM EXPANSION | 815 - Addiscott | 101761 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646839 | LESLIE ST GUYING RECONFIGURATION | 815 - Addiscott | 101761 | Active | 82 | RELEASED |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan | 25-Jan-23 |  |  | 19967.41 | 4912.61 | 19967.41 | 19967.41 | Kristine Gordon |  | 06-Sep-23 | 06-Sep-23 | 05-Sep-23 | [5 empty] | 0
646883 | 120 BIG BAY POINT BARRIE RISER RELOCATION | 825 - Patterson | 151450 | Inactive | 99 | COMPLETE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 11-Jan-23 | 1 | 1 | 80025.53 | 53663.17 | 80025.53 | 80025.53 | Lotto, Jay | HapAmp | 14-Mar-23 | 14-Mar-23 | 27-Feb-23 | 01-Feb-23 | 01-Feb-23 | xBy-passed |  |  | 0
646886 | 646886 - 2022 POLE REPLACEMENTS BARRIE 96 MORROW ROAD | 825 - Patterson | 100867 | Active | 92 | COMPLETE |  |  | 2023 | O'Gay, Brian | Martin, Shane | 31-Oct-22 | 1 | 1 | 7678.97 | 8006.8 | 7678.97 | 7678.97 | Dan Kish | K-Line | 25-Nov-22 | 27-Jul-23 | 25-Nov-22 | 23-Jan-23 | 30-Jan-23 |  | Contractor |  | 0
646894 | MINTO'S UNIONVILLE HOME SOCIETY - TOWNHOME ENCLAVE / MARKHAM | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646915 | 6565 HIGHWAY 7/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646937 | 646937 - 2022 UG EMERGING - BARRIE - 3PH LEAKING TX - T2004 - 15 SARJEANTS DR. | 825 - Patterson | 151450 | Active | 84 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 29-Jun-23 |  |  | 209916.89 | 97673.62 | 209916.89 | 209916.89 | Lotto, Jay | HapAmp | 31-Aug-23 | 31-Aug-23 | 24-Jul-23 | 12-Jul-23 |  |  |  |  | 0
646947 | 2022 UG EMERGING - BRADFORD - T9345 - 76 HOLLAND ST. WEST - PMH-9 & 3PH TX | 825 - Patterson | 151450 | Active | 50 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646960 | 339 VETERANS DRIVE/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646964 | MONTEVERDI ESTATES - TOWN OF AURORA | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
646966 | 646966 - 2023 POLE RENEWAL - P49406 | 815 - Addiscott | 100867 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 4 | 4 | 38090.44 | 25817.03 | 38090.44 | 38090.44 | Morrow, Joe |  | 05-Jul-23 | 27-Jul-23 | 28-Jun-23 | 14-Apr-23 | 28-Apr-23 |  |  |  | 0
646975 | 646975 - 2023 SWITCH REPLACEMENT - A05SL2054 - AURORA (AUTO) | 815 - Addiscott | 101027 | Active | 96 | COMPLETE | High | Switch | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 05-Dec-22 | 1 | 1 | 117438.4 | 117497.44 | 117438.4 | 117438.4 | Reginald Clarke |  | 28-Mar-23 | 04-Aug-23 | 20-Mar-23 | 31-Jan-23 | 31-Jan-23 |  |  |  | 0
646974 | 646974 - 2023 SWITCH REPLACEMENT - V26SL3011 - VAUGHAN (AUTO) | 815 - Addiscott | 101027 | Active | 92 | ANALYZE | High | Switch | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 | 1 | 1 | 178894.62 | 174746.39 | 178894.62 | 178894.62 | Reginald Clarke |  | 06-Jul-23 | 27-Jul-23 | 19-Jun-23 | 15-May-23 | 27-Jun-23 |  |  |  | 0
646973 | 2024 SWITCH REPLACEMENT - R21SL3018 (AUTOMATED) - RICHMOND HILL | 815 - Addiscott | 101027 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  | 1 |  | 0 | 14933.74 | 0 | 0 | East Coordinator |  |  | 25-May-23 | [6 empty] | 0
646981 | 95 BIG BAY POINT RD/BAR/NS/3 PH PAD | 825 - Patterson | 101919 | Active | 82 | Upload Completed |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 108743.13 | 12609.08 | 108743.13 | 108743.13 | East Coordinator |  |  | 27-Jul-23 | [6 empty] | 0
646992 | 2024 CABLE INJECTION - R23 - BATHURST-WELDRICK-YONGE-CARVILLE, RICHMOND HILL | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647006 | 47 ELM GROVE - RICHMOND HILL | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647005 | 2024 CABLE INJECTION, V17 - LANGSTAFF - RAILWAY - RUTHERFORD - DUFFERIN | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647015 | TOTTENHAM REAR LOT PHASE 1 RESTORATION 79 QUEEN STREET | 825 - Patterson | 151450 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647016 | 647016 - NASHVILLE RD & BARONS ST - NORTH SIDE | 815 - Addiscott | 101761 | Active | 92 | ANALYZE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander | 14-Jun-23 |  |  | 32414.6 | 40171.36 | 32414.6 | 32414.6 | Macdonald, Steve | K-Line | 21-Jul-23 | 27-Jul-23 | 17-Jul-23 | 03-Jul-23 | 22-Jul-23 |  |  |  | 0
647017 | MILL STREET MS REBUILD RESTORATION 44 MILL STREET | 825 - Patterson | 151450 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647080 | 647080 - 2023 TX VAULT RENEWAL, MAIN ST N UNIONVILLE (1 LOCATION AND GRADING ADJUSTMENTS) | 815 - Addiscott | 151526 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 23-May-23 |  |  | 146492.51 | 12452.13 | 146492.51 | 146492.51 | Horlings, Jake | HapAmp | 22-Sep-23 | 22-Sep-23 | 11-Sep-23 | [5 empty] | 0
647103 | 647103 - 2023 TX RENEWAL - A09TA2036 - 1 TX | 815 - Addiscott | 101508 | Active | 92 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 22-Mar-23 | 1 | 1 | 19055.09 | 11301.73 | 19055.09 | 19055.09 | Kristine Gordon |  | 07-Jun-23 | 27-Jul-23 | 05-Jun-23 | 16-Jun-23 | 16-Jun-23 | Weather | Weather |  | 0
647100 | 647100 - 2023 TX RENEWAL - BATCH 20 - 14 TX | 815 - Addiscott | 101508 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 | 16 |  | 343297.65 | 181896.13 | 342747.65 | 343297.65 | Dave Lindsay | Somervl | 02-Mar-23 | 13-Sep-23 | 01-Jan-23 | 20-Mar-23 |  | Filler |  |  | 550
647098 | 647098 - 2023 TX RENEWAL - BATCH 18 - 9 TX | 815 - Addiscott | 101508 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 | 9 |  | 232535.09 | 22392.66 | 232535.09 | 232535.09 | Dave Lindsay | Somervl | 16-Feb-23 | 29-Aug-23 | 01-Jan-23 | 17-Apr-23 |  | Lines |  |  | 0
647097 | 647097 - 2023 TX RENEWAL - BATCH 17 - 10 TX | 815 - Addiscott | 101508 | Active | 91 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel | 01-Nov-22 | 11 | 11 | 306759.38 | 89937.3 | 306759.38 | 306759.38 | Dave Lindsay | Somervl | 20-Feb-23 | 31-Aug-23 | 01-Jan-23 | 20-Mar-23 |  | Filler |  |  | 0
647104 | 647104 - 1 ANNA RUSSELL WAY/MAR/SR/SWITCH GEAR | 815 - Addiscott | 101791 | Active | 94 | ANALYZE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 24-Mar-23 |  |  | 81566.14 | 52756.4 | 81566.14 | 81566.14 | Dave Lindsay | Somervl | 24-May-23 | 17-Aug-23 | 08-May-23 | 24-Apr-23 | 09-Jun-23 |  | Customer |  | 0
647110 | HONEYFIELD BLOCK 393/394 - SUBD RES EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647115 | 647115 - 8554 HUNTINGTON RD / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Mann, Drew | 01-Jun-23 |  |  | 250788.66 | 21742.68 | 250788.66 | 250788.66 | Dave Lindsay | Somervl | 29-Jun-23 | 09-Aug-23 | 19-Jun-23 | [5 empty] | 0
647116 | MILLWOOD PKWY - PRIMARY CABLE SPLICE | 815 - Addiscott | 101761 | Active | 96 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan | 01-Feb-23 |  |  | 10105.32 | 6431.95 | 10105.32 | 10105.32 | Horlings, Jake |  | 02-Feb-23 | 27-Jul-23 | 02-Feb-23 | 02-Feb-23 | 02-Feb-23 | xBy-passed |  |  | 0
647122 | 10 ALDERSON CT/ALL/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 21-Mar-23 |  |  | 54506.71 | 45083.73 | 54506.71 | 54506.71 | Lotto, Jay |  | 20-Jul-23 | 08-Aug-23 | 09-Jun-23 | [5 empty] | 0
647123 | 10 CANDAC VALLEY/AUR/NS/1 PHASE PAD | 825 - Patterson | 101791 | Active | 48 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647124 | 50 INDUSTRIAL PKWY N/AUR/NS/3 PHASE PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647134 | 2023 DISTRIBUTION AUTOMATION - BARRIE - GEORGIAN DR. & GALLIE CT. | 825 - Patterson | 100886 | Active | 82 | RELEASED | High | DA | 2023 | Obeng, Nana | Walters, Geoffrey D | 29-May-23 | 1 |  | 194085.45 | 8235.94 | 194085.45 | 194085.45 | Mark Timbers |  | 30-Nov-23 | 30-Nov-23 | 01-Nov-23 | [5 empty] | 0
647138 | 2023 DISTRIBUTION AUTOMATION - BARRIE - BELLFARM E/O ST. VINCENT | 825 - Patterson | 100886 | Active | 84 | ACTIVE | High | DA | 2023 | Bowman, Todd J | Walters, Geoffrey D | 19-May-23 | 1 |  | 285380.54 | 245593.19 | 285380.54 | 285380.54 | Mark Timbers | K-Line | 14-Jul-23 | 27-Jul-23 | 03-Jul-23 | 12-Jun-23 |  |  |  |  | 0
647142 | 2023 DISTRIBUTION AUTOMATION - BARRIE - CEDAR POINT DR S/O EDGEHILL | 825 - Patterson | 100886 | Active | 50 | ACTIVE | High | DA | 2023 | Bowman, Todd J | Walters, Geoffrey D |  | 1 |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647167 | 647167 - OH, 33 CENTER STREET - BRADFORD - ANCHOR ENCROACHMENT RELOCATION. | 825 - Patterson | 101355 | Active | 95 | COMPLETE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 18-Oct-22 |  |  | 50875.01 | 39584.11 | 50875.01 | 50875.01 | Mark Timbers | HapAmp | 06-Jan-23 | 27-Jul-23 | 03-Jan-23 | 21-Nov-22 | 25-May-23 | Lines | Contractor |  | 0
647182 | 9520 JANE ST - SYSTEM REPAIR | 815 - Addiscott | 101355 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647183 | COUNTRY RIDGE ESTATES – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647185 | 647185 - CENTERFIELD DEVELOPMENT - PHASE 2B - RICHMOND HILL | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir | 17-Apr-23 |  |  | 48911.22 | 40488.93 | 48911.22 | 48911.22 | Dave Lindsay | N/A | 13-Jun-23 | 27-Jul-23 | 12-Jun-23 | 22-Mar-23 | 02-Jun-23 |  | Contractor |  | 0
647204 | SHINING HILL ESTATES PHASE 3 STAGE 1 - RES SUBD EDS | 815 - Addiscott | 101887 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Handy, James | 15-Jun-23 |  |  | 62663.7 | 34513.34 | 62663.7 | 62663.7 | Dave Lindsay | N/A | 02-Aug-23 | 15-Aug-23 | 17-Jul-23 | [5 empty] | 0
647214 | 647214 - BARRIE - 2023 PADMOUNT TX REPLACEMENT BATCH 1 | 825 - Patterson | 101508 | Active | 95 | COMPLETE |  |  | 2023 | Bowman, Todd J | Walters, Geoffrey D | 03-May-23 | 9 | 3 | 174795.19 | 79309.48 | 174795.19 | 174795.19 | Lotto, Jay | HapAmp | 14-Sep-23 | 14-Sep-23 | 05-Sep-23 | 24-May-23 | 30-May-23 |  |  |  | 0
647221 | BRADFORD - 2023 PADMOUNT TX REPLACEMENT BATCH 2 | 825 - Patterson | 101508 | Active | 84 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 03-May-23 | 5 | 0 | 64266.7 | 24643.54 | 64266.7 | 64266.7 | Lotto, Jay |  | 01-Nov-23 | 01-Nov-23 | 23-Oct-23 | 15-May-23 |  |  |  |  | 0
647223 | 647223 - PENETANG - 2023 PADMOUNT TX REPLACEMENT - BATCH 4 | 825 - Patterson | 101508 | Active | 82 | RELEASED |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 03-May-23 | 3 |  | 60254.34 | 2149.55 | 60254.34 | 60254.34 | Lotto, Jay |  | 14-Nov-23 | 14-Nov-23 | 13-Nov-23 | [5 empty] | 0
647222 | NEW TECH - 2023 PADMOUNT TX REPLACEMENT BATCH 3 | 825 - Patterson | 101508 | Active | 91 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 03-May-23 | 2 | 1 | 49759.27 | 14023.34 | 49759.27 | 49759.27 | Lotto, Jay |  | 10-Nov-23 | 10-Nov-23 | 06-Nov-23 | 24-May-23 | 06-Jun-23 |  |  |  | 0
647226 | 647226 - MAJOR MAC & SUSSEX - POLE RELOCATION | 815 - Addiscott | 101762 | Active | 99 | ANALYZE |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan | 07-Sep-22 |  |  | 13254.82 | 15778.02 | 13254.82 | 13254.82 | Morrow, Joe |  | 15-Nov-22 | 27-Jul-23 | 14-Nov-22 | 14-Nov-22 | 14-Nov-22 |  |  |  | 0
647280 | 647280 - ULTIMATE DR. - #168/RHL/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 10-Feb-23 | 1 | 1 | 141438.9 | 3192.38 | 141438.9 | 141438.9 | Dave Lindsay | Somervl | 12-Jul-23 | 03-Aug-23 | 10-Jul-23 | [5 empty] | 0
647286 | 2022 POLE REPLACEMENTS ALLISTON BATCH 4 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Bowman, Todd J | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647321 | FAIRTREE BLOCK 150 CONDO BLOCK TOWNHOMES - MARKHAM | 815 - Addiscott | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647329 | BERCZY GLEN PHASE 1 - DUCT BANK CORRECTION | 815 - Addiscott | 150494 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647330 | BERCZY GLEN PHASE 1 - TRANSFORMER RELOCATION | 815 - Addiscott | 150494 | Active | 79 | Upload Completed |  |  | 2023 | Penner, Mitchell | Brockley, Ryan |  |  |  | 96339.6 | 15591.3 | 96339.6 | 96339.6 | East Coordinator |  |  | 27-Jul-23 | [6 empty] | 0
647332 | COMMERCE ST. - #1 AT HWY. 7/VAU/NS/CUSTOMER OWNED TX | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647333 | APPLEMILL AVE. - #1 AT BUTTERMILL AVE./3PH/NS/CUSTOMER OWN TX. | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647355 | 111 AUTO VAUGHAN DR / VAU / UP / 3PH PAD TX RELOCATION | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647373 | 647373 - 316 EDGELEY BLVD/VAU/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  | 1 | 1 | 125651.14 | 93275.25 | 125651.14 | 125651.14 | Dave Lindsay | Somervl | 03-Mar-23 | 27-Jul-23 | 27-Feb-23 | 06-Feb-23 | 16-Mar-23 |  | Customer |  | 0
647387 | NASHVILLE PHASE 2B SUBDIVISION - VAUGHAN | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647392 | 647392 - 2023 POLE RENEWAL - BATCH 15 - 7 POLES | 815 - Addiscott | 100867 | Active | 92 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 22-Mar-23 | 7 | 7 | 87948.99 | 75105.04 | 87948.99 | 87948.99 | Morrow, Joe |  | 20-Jul-23 | 27-Jul-23 | 04-Jul-23 | 28-Apr-23 | 29-May-23 |  |  |  | 0
647395 | 647395 - 13837 YONGE ST/AUR/UP/3 PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. | 05-Jun-23 |  |  | 116462.61 | 10480.92 | 116462.61 | 116462.61 | Dave Lindsay | Somervl | 28-Jun-23 | 15-Aug-23 | 12-Jun-23 | [5 empty] | 0
647418 | 647418 - FEEDER 26M14 PHASE BALANCING | 815 - Addiscott | 152285 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 01-Nov-22 |  |  | 66639.8 | 1787.92 | 66639.8 | 66639.8 | Reginald Clarke |  | 14-Aug-23 | 30-Oct-23 | 04-Apr-23 | [5 empty] | 0
647419 | LINDWIDE DEVELOPMENT - PHASE 2 - MARKHAM | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647429 | 168 OLD KENNEDY RD - TRANSFORMER RELOCATION | 815 - Addiscott | 101761 | Active | 50 | H8 |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647442 | 647442 - 32 WELLINGTON ST W/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 96 | COMPLETE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 12-Dec-22 | 1 | 1 | 98425.29 | 48681.59 | 98425.29 | 98425.29 | Dave Lindsay | Somervl | 14-Mar-23 | 27-Jul-23 | 06-Mar-23 | 26-Jan-23 | 10-Mar-23 |  |  |  | 0
647443 | 115 ADDISON HALL CIRCLE /AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 23-Jun-23 |  |  | 135950.59 | 7290.42 | 135950.59 | 135950.59 | Dave Lindsay | Somervl | 11-Sep-23 | 11-Sep-23 | 28-Aug-23 | [5 empty] | 0
647446 | 647446 - 2023 POLE REBUILD - YONGE AND UPLANDS | 815 - Addiscott | 100867 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 08-Jun-23 |  |  | 217926.72 | 155026.41 | 217926.72 | 217926.72 | Reginald Clarke |  | 18-Sep-23 | 18-Sep-23 | 14-Aug-23 | 11-Jul-23 |  |  |  |  | 0
647445 | 155 ADDISON HALL CIRCLE/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 23-Jun-23 |  |  | 107879.69 | 4889.2 | 107879.69 | 107879.69 | Dave Lindsay | Somervl | 11-Sep-23 | 11-Sep-23 | 28-Aug-23 | [5 empty] | 0
647444 | 135 ADDISON HALL CIRCLE/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 23-Jun-23 |  |  | 109179.54 | 6476.18 | 109179.54 | 109179.54 | Dave Lindsay | Somervl | 11-Sep-23 | 11-Sep-23 | 28-Aug-23 | [5 empty] | 0
647461 | BRCE - BARRIE EXPANSION - BARRIE LINE - TEMP RAILWAY CROSSING | 825 - Patterson | 150591 | Active | 70 | ACTIVE |  |  | 2023 | Khuu, Philander | Grahovac, John |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647528 | 2023 SWGR REPLACEMENT - SC4475 - 249 LITTLE AVE. - BARRIE | 825 - Patterson | 100859 | Active | 82 | RELEASED |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 15-Sep-22 | 1 |  | 47039.58 | 3099.72 | 47039.58 | 47039.58 | Lotto, Jay | HapAmp | 31-Jul-23 | 02-Aug-23 | 17-Jul-23 | [5 empty] | 0
647531 | 2023 SWGR REPLACEMENT - SC13532 - 156 CUMMING DR. - BARRIE | 825 - Patterson | 100859 | Active | 95 | COMPLETE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 19-Oct-22 | 1 | 1 | 20242.09 | 14107.77 | 20242.09 | 20242.09 | Lotto, Jay |  | 13-Feb-23 | 28-Jul-23 | 13-Feb-23 | 24-Apr-23 | 28-Apr-23 | Materials | Materials |  | 0
647541 | 647541 - 2023 SWGR REPLACEMENT - SC13530 - 52 CUMMING DR. - BARRIE | 825 - Patterson | 100859 | Active | 95 | ANALYZE |  |  | 2022 | Obeng, Nana | Walters, Geoffrey D | 18-Oct-22 | 1 | 1 | 20242.09 | 17454.82 | 20242.09 | 20242.09 | Lotto, Jay | HapAmp | 28-Oct-22 | 27-Jul-23 | 26-Oct-22 | 26-Oct-22 | 26-Oct-22 |  |  |  | 0
647551 | 647551 - 2023 LEFT-BEHIND CABLE REPLACEMENTS - M33 AND M19 | 815 - Addiscott | 150263 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 03-Jun-23 |  |  | 746528.99 | 38450.9 | 746528.99 | 746528.99 | Horlings, Jake | Transpw | 08-Dec-23 | 08-Dec-23 | 16-Oct-23 | [5 empty] | 0
647550 | 647550 - 2023 LEFT-BEHIND CABLE REPLACEMENTS - M37 AND M32 | 815 - Addiscott | 150263 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 24-May-23 |  |  | 490439.43 | 29363.85 | 490439.43 | 490439.43 | Horlings, Jake | Transpw | 24-Aug-23 | 24-Aug-23 | 31-Jul-23 | [5 empty] | 0
647549 | 647549 - 2023 LEFT-BEHIND CABLE REPLACEMENTS - V40 AND V18 | 815 - Addiscott | 150263 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 26-May-23 |  |  | 690291.97 | 45317.68 | 690291.97 | 690291.97 | Horlings, Jake | Transpw | 20-Oct-23 | 23-Oct-23 | 08-Sep-23 | [5 empty] | 0
647552 | 1100 BETHESDA SIDE RD / RHL / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647564 | 426 VETERANS DRIVE, RES SUBD EDS | 825 - Patterson | 101887 | Active | 82 | Upload Completed |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 137448.42 | 7396.32 | 137448.42 | 137448.42 | East Coordinator |  |  | 27-Jul-23 | [6 empty] | 0
647571 | BELTERRA ESTATES, PHASE 5 - ALLISTON - RES SUBD EDS | 825 - Patterson | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647574 | MAJOR MACKENZIE DR. W - 3600/TEMP/VAU/NS/PAD | 815 - Addiscott | 101791 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647576 | 647576 - 2710 14TH AVE/MAR/UP/3PH VAULT | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 23-May-23 |  |  | 92346.74 | 6996.13 | 92346.74 | 92346.74 | Dave Lindsay | N/A | 13-Sep-23 | 13-Sep-23 | 01-Sep-23 | [5 empty] | 0
647575 | RUTHERFORD RD - #2850/VAU/UP/PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647559 | PIONEER TRAIL, BARRIE - RES SUBD EDS | 825 - Patterson | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647583 | MACKENZIE COMMON DEVELOPMENT - BLOCK 2 - RICHMOND HILL | 815 - Addiscott | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647619 | GROVE STREET WEST (#10-24) - 44KV SYSTEM EXPANSION | 825 - Patterson | 101763 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647632 | 160 MCNABB ST / MAR / UP / CO-STN | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647643 | KING SHAVER TOWNHOUSE DEVELOPMENT - RICHMOND HILL | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Alarcon, Alejandro |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647657 | POLE RELOCATION WESTON RD P42121 | 815 - Addiscott | 151531 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647681 | PARSONS GLEN, DAYFOOT ST - BEETON - RES SUBD EDS | 825 - Patterson | 101887 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647758 | MACKENZIE COMMONS - POLE RELOCATION | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647766 | 647766 - CUSTOMER CAPITAL PARENT WO#: 4433, 4455, 4477 MAJOR MACKENZIE DR W - VAUGHAN | 815 - Addiscott | 101887 | Active | 95 | COMPLETE |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 31-Jan-23 |  |  | 16455.38 | 8331.8 | 16455.38 | 16455.38 | Kristine Gordon |  | 27-Apr-23 | 27-Jul-23 | 24-Apr-23 | 18-Apr-23 | 18-Apr-23 |  |  |  | 0
647768 | 835 CLARK AVE W/VAU/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647797 | PORTAGE PKWY & EDGELEY ST - SWITCHGEAR REMOVAL | 815 - Addiscott | 101761 | Active | 50 | H8 |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647798 | 47 MILLS RD/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 01-Jun-23 |  |  | 87419.21 | 7679.15 | 87419.21 | 87419.21 | Lotto, Jay | HapAmp | 16-Oct-23 | 16-Oct-23 | 09-Oct-23 | [5 empty] | 0
647803 | BIRCHMOUNT & CITIZEN CT / MAR / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647808 | DUFFERIN - MAJOR MACKENZIE DR TO TESTON | 815 - Addiscott | 101762 | Active | 40 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647815 | BARRIE - 215 INNISFIL ST. - 3PH LEAKING TX REPLACEMENT - T2049 | 825 - Patterson | 101824 | Active | 50 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647813 | BARRIE - 90 WELHAM RD. - 3PH LEAKING TX REPLACEMENT - T2401 | 825 - Patterson | 101824 | Active | 50 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647816 | 107 DUNLOP ST E/BAR/UP/3PH PAD | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647817 | 96 BROCK ST/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647827 | 647827 - OLD BLOOMINGTON RD - POLE RELOCATIONS | 815 - Addiscott | 101761 | Active | 95 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan | 16-May-23 |  |  | 92957.34 | 77582.82 | 92957.34 | 92957.34 | Macdonald, Steve | K-Line | 03-Jul-23 | 27-Jul-23 | 26-Jun-23 | 03-Jun-23 | 03-Jun-23 |  |  |  | 0
647855 | 647855 - 2023 TX RENEWAL - 48-1 - 1 TX | 815 - Addiscott | 101508 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  | 1 | 1 | 14481.5 | 10309.76 | 14481.5 | 14481.5 | Kristine Gordon |  |  | 27-Jul-23 |  | 04-Apr-23 | 04-Apr-23 |  |  |  | 0
647870 | DUNHAM DR/ALL/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 48 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647869 | 547 BAYFIELD ST CAR WASH/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647888 | 14452 YONGE ST HOUSING PROJECT/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647906 | HWY W NO. 2160-2180 VAU/NS/CUS | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647915 | STOUFFVILLE RD WIDENING - BAYVIEW AVE TO HWY 404 | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647951 | HWY 400 WIDENING - MAJOR MAC AND RUTHERFORD | 815 - Addiscott | 101762 | Active | 70 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
647970 | CABLE HIT @ 404 & 16TH AVE | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 07-Jun-23
647994 | 647994 - V51 - UG EMERGING CABLE REPLACEMENT - BELLONA ST | 815 - Addiscott | 151450 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 23-Mar-23 |  |  | 140344.67 | 12714.5 | 140344.67 | 140344.67 | Horlings, Jake | Transpw | 18-Jul-23 | 31-Jul-23 | 10-Jul-23 | [5 empty] | 0
647996 | 251 CITYVIEW BLVD / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648020 | 12370 KEELE ST/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 70 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648033 | 648033 - 2023 DA EMERGING - M15SL3025 - MARKHAM | 815 - Addiscott | 101355 | Active | 95 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 03-May-23 | 1 | 1 | 128702.06 | 95661.81 | 128702.06 | 128702.06 | Reginald Clarke |  | 30-May-23 | 27-Jul-23 | 23-May-23 | 23-May-23 | 08-Jun-23 |  | MC/PUCC Permit |  | 0
648035 | 648035 - 2023 SUNNIDALE UG CABLE REPLACEMENT PHASE 4 | 825 - Patterson | 151336 | Active | 84 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 24-Feb-23 |  |  | 1753429.18 | 268463.59 | 1753429.18 | 1753429.18 | Lotto, Jay | Transpw | 31-Aug-23 | 30-Oct-23 | 08-May-23 | 29-May-23 |  | Contractor | Contractor |  | 0
648050 | YONGE STREET & BROOKSIDE ROAD | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2022 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648056 | 19-186 SHAVER/CARVAL - RICHMOND HILL | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648062 | 648062 - 8100 WARDEN AVE / MAR / UP / 1PH DUCT RELOCATION | 815 - Addiscott | 101791 | Active | 93 | ANALYZE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 02-Dec-22 |  |  | 10451.41 | 10552.96 | 10451.41 | 10451.41 | Dave Lindsay |  | 23-Jan-23 | 27-Jul-23 | 18-Jan-23 | [5 empty] | 0
648063 | BARRIE - 79 BELLFARM RD. FAILING POLE REPLACEMENT | 825 - Patterson | 101824 | Active | 84 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 31-May-23 |  |  | 381055.77 | 156785.72 | 381055.77 | 381055.77 | Mark Timbers | K-Line | 23-Jun-23 | 27-Jul-23 | 12-Jun-23 | 12-Jun-23 |  |  | Contractor |  | 0
648086 | 8311 WESTON RD/VAU/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 24-May-23 |  |  | 129772.93 | 7693.41 | 129772.93 | 129772.93 | Dave Lindsay | Somervl | 08-Nov-23 | 08-Nov-23 | 01-Nov-23 | [5 empty] | 0
648097 | 390 ADDISON HALL/AUR/NS/3 PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 93293.31 | 6436.85 | 93293.31 | 93293.31 | Dave Lindsay | Somervl | 11-Sep-23 | 11-Sep-23 | 25-Aug-23 | [5 empty] | 0
648100 | 126 ALLENVALE DR/AUR/NS/1 PHASE PAD | 815 - Addiscott | 101791 | Active | 48 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648106 | NASHVILLE RD. - #6990 VAU/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | PDG SnR |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 31-May-23 |  |  | 97845.93 | 2035.46 | 97845.93 | 97845.93 | East Coordinator |  |  | 11-Apr-24 | [6 empty] | 0
648110 | V37 - UG EMERGING CABLE REPLACEMENT - 37-L117 TO 37-L4 | 815 - Addiscott | 151450 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648109 | 648109 - V15 - UG EMERGING CABLE REPLACEMENT - V15FA3077 TO SPLICE PIT | 815 - Addiscott | 151450 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 24-May-23 |  |  | 128000.5 | 16067.74 | 128000.5 | 128000.5 | Dave Lindsay | Somervl | 04-Aug-23 | 04-Aug-23 | 17-Jul-23 | [5 empty] | 0
648120 | 9999 MARKHAM RD DEVELOPMENT PH2- SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648137 | SMARTCENTRES ALLISTON, COMM-RES SUBD EDS | 825 - Patterson | 101896 | Active | 48 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648145 | 648145 - HIGHWAY NO. 7 EAST - #4111 MAR/SR/PAD | 815 - Addiscott | 101791 | Active | 93 | ANALYZE |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 19-Dec-22 | 1 | 1 | 21081.65 | 14443.4 | 21081.65 | 21081.65 | Dave Lindsay | Somervl | 07-Mar-23 | 27-Jul-23 | 06-Mar-23 | 14-Apr-23 | 03-May-23 | Customer | Customer |  | 0
648155 | 8261 HIGHWAY 50 - SYSTEM EXPANSION | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648171 | 648171 - POLE REPLACEMENTS - SHINING HILL ESTATES PHASE 3 STAGE 1 | 815 - Addiscott | 101887 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James | 15-Jun-23 |  |  | 286372.51 | 117278.31 | 230412.43 | 286372.51 | Macdonald, Steve |  | 31-Aug-23 | 13-Sep-23 | 17-Jul-23 | 17-Jul-23 |  |  |  |  | 55,960.08
648207 | 2023 POLE REPLACEMENTS THORNTON BATCH 1 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648209 | 2023 POLE REPLACEMENTS TOTTENHAM BATCH 1 | 825 - Patterson | 100867 | Active | 48 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648208 | 2023 POLE REPLACEMENTS PENETANG BATCH 1 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648212 | 648212 - 2023 POLE REPLACEMENTS BARRIE BATCH 1 | 825 - Patterson | 100867 | Active | 82 | RELEASED |  |  | 2023 | Obeng, Nana | Pollock, Kim | 24-Feb-23 | 13 |  | 189984.13 | 23417.51 | 189984.13 | 189984.13 | Mark Timbers | HapAmp | 11-Oct-23 | 11-Oct-23 | 01-Sep-23 | [5 empty] | 0
648211 | 2023 POLE REPLACEMENTS ALLISTON BATCH 1 | 825 - Patterson | 100867 | Active | 50 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648210 | 2023 POLE REPLACEMENTS BEETON BATCH 1 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648215 | 2023 POLE REPLACEMENTS BARRIE BATCH 4 | 825 - Patterson | 100867 | Active | 82 | RELEASED |  |  | 2023 | Obeng, Nana | Pollock, Kim | 24-Feb-23 | 19 |  | 579242.77 | 36281.44 | 579242.77 | 579242.77 | Mark Timbers |  | 19-Dec-23 | 19-Dec-23 | 01-Sep-23 | [5 empty] | 0
648214 | 2023 POLE REPLACEMENTS BARRIE BATCH 3 | 825 - Patterson | 100867 | Active | 95 | COMPLETE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 08-Mar-23 | 4 | 4 | 60521.01 | 68170.57 | 60521.01 | 60521.01 | Lotto, Jay | HapAmp | 23-May-23 | 27-Jul-23 | 01-May-23 | 16-May-23 | 06-Jun-23 | Materials | Materials |  | 0
648213 | 2023 POLE REPLACEMENTS BARRIE BATCH 2 | 825 - Patterson | 100867 | Active | 82 | RELEASED |  |  | 2023 | Obeng, Nana | Pollock, Kim | 09-Jun-23 |  |  | 560391.41 | 137768.5 | 560391.41 | 560391.41 | Mark Timbers | K-Line | 10-Oct-23 | 09-Aug-23 | 01-Aug-23 | [5 empty] | 0
648221 | 2023 POLE REPLACEMENTS BARRIE BATCH 10 | 825 - Patterson | 100867 | Active | 95 | COMPLETE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 01-Feb-23 | 4 | 4 | 100159.5 | 60974.73 | 100159.5 | 100159.5 | Lotto, Jay | HapAmp | 09-Jun-23 | 24-Aug-23 | 01-May-23 | 24-Apr-23 | 12-May-23 |  |  |  | 0
648220 | 648220 - 2023 POLE REPLACEMENTS BARRIE BATCH 9 | 825 - Patterson | 100867 | Active | 84 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 16-Mar-23 | 19 |  | 312047.25 | 196758.45 | 312047.25 | 312047.25 | Mark Timbers | HapAmp | 31-Jul-23 | 21-Sep-23 | 01-Jun-23 | 28-Jun-23 |  |  |  |  | 0
648219 | 2023 POLE REPLACEMENTS BARRIE BATCH 8 | 825 - Patterson | 100867 | Active | 84 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 24-Feb-23 | 14 |  | 377656.47 | 135064.69 | 377656.47 | 377656.47 | Mark Timbers | HapAmp | 22-Aug-23 | 28-Sep-23 | 01-Jun-23 | 12-Jul-23 |  |  |  |  | 0
648218 | 648218 - 2023 POLE REPLACEMENTS BARRIE BATCH 7 | 825 - Patterson | 100867 | Active | 95 | COMPLETE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 30-Jan-23 | 6 | 6 | 112091.85 | 109705.93 | 112091.85 | 112091.85 | Lotto, Jay |  | 05-Jun-23 | 16-Aug-23 | 03-Apr-23 | 24-Feb-23 | 12-Apr-23 |  |  |  | 0
648217 | 648217 - 2023 POLE REPLACEMENTS BARRIE BATCH 6 | 825 - Patterson | 100867 | Active | 95 | COMPLETE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 30-Jan-23 | 5 | 5 | 61185.79 | 68102.36 | 61185.79 | 61185.79 | Lotto, Jay |  | 23-Mar-23 | 04-Aug-23 | 06-Mar-23 | 13-Mar-23 | 13-Apr-23 | Locates | Locates |  | 0
648216 | 648216 - 2023 POLE REPLACEMENTS BARRIE BATCH 5 | 825 - Patterson | 100867 | Active | 82 | RELEASED |  |  | 2023 | Obeng, Nana | Pollock, Kim | 24-Feb-23 | 13 |  | 526685.71 | 28414.28 | 526685.71 | 526685.71 | Lotto, Jay | HapAmp | 08-Nov-23 | 25-Oct-23 | 15-May-23 | [5 empty] | 0
648226 | 2023 POLE REPLACEMENTS BRADFORD BATCH 3 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648225 | 2023 POLE REPLACEMENTS BRADFORD BATCH 2 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648224 | 2023 POLE REPLACEMENTS BRADFORD BATCH 1 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648222 | 2023 POLE REPLACEMENTS BARRIE BATCH 11 | 825 - Patterson | 100867 | Active | 94 | COMPLETE |  |  | 2023 | Obeng, Nana | Pollock, Kim | 28-Feb-23 | 22 | 22 | 368844.68 | 370363.72 | 368844.68 | 368844.68 | Mark Timbers | K-Line | 31-Jul-23 | 27-Jul-23 | 15-May-23 | 15-May-23 | 17-Jun-23 |  |  |  | 0
648227 | 648227 - ENTERPRISE BLVD. - #500 MAR/NS/1PH PAD | 815 - Addiscott | 101791 | Active | HO | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 19-Dec-22 | 1 |  | 52991.7 | 20540.24 | 52991.7 | 52991.7 | Dave Lindsay | Somervl | 08-Mar-23 | 28-Jul-23 | 06-Mar-23 | [5 empty] | 0
648244 | APPLEMILL AVE. & BUTTERMILL AVE VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648266 | CUSTOMER CAPITAL WO#: 1430518 ONTARIO LTD | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648267 | 2023 CABLE REPLACEMENT - A05 - MURRAY DR - A05SP2004 | 815 - Addiscott | 151911 | Inactive | 99 | CANCELLED |  |  | 2022 | Tenorlas, Reynaldo | Kahlon, Aneel |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648273 | 2628908 ONTARIO INC. | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648282 | 1 STEELE CASE RD/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648289 | 648289 - 2023 SWITCH RENEWAL - BARRIE - AB-B39 - PATTERSON RD. | 825 - Patterson | 101027 | Active | 95 | ANALYZE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 26-Jan-23 | 1 | 1 | 92159.09 | 75764.64 | 92159.09 | 92159.09 | Dan Kish | K-Line | 16-Feb-23 | 27-Jul-23 | 13-Feb-23 | 30-Jan-23 | 06-Feb-23 |  |  |  | 0
648295 | 169 CITYVIEW BLVD / VAU / NS / 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648299 | 90 RIVIERA DR / MAR / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 2057.9 |  | 0 | East Coordinator |  |  | 30-Jan-23
648304 | 648304 - 2023- POLE REPLACEMENT- P43709- 9280 KEELE ST | 815 - Addiscott | 100867 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 03-May-23 |  |  | 56137.21 | 16911.37 | 56137.21 | 56137.21 | Kristine Gordon | Somervl | 31-Oct-23 | 31-Oct-23 | 16-Oct-23 | [5 empty] | 0
648303 | 93 BRADFORD ST/BAR/SR/3PH PAD | 825 - Patterson | 101919 | Active | 99 | ANALYZE |  |  | 2022 | Cranley, Stephen | Paterson, Greg | 07-Dec-22 | 1 |  | 11808.28 | 10469.5 | 11808.28 | 11808.28 | Lotto, Jay | HapAmp | 04-Jan-23 | 28-Jul-23 | 30-Dec-22 | 29-Dec-22 | 29-Dec-22 |  |  |  | 0
648305 | 2023- POLE REBUILD- 14800 YONGE STREET | 815 - Addiscott | 100867 | Active | 97 | CANCELLED |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 28820.28 |  | 0 | East Coordinator |  |  | 27-Jul-23
648318 | ALLSTATE PARKWAY - #200 MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648343 | 80 BIG BAY POINT, BARRIE - COMM-IND SUBD EDS | 825 - Patterson | 101896 | Active | 50 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648345 | 50 WELHAM RD, BARRIE - COMM-IND SUBD EDS | 825 - Patterson | 101896 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648360 | 175 FOUR VALLEY DR / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648372 | 648372 - HUNTINGTON ROAD - POLELINE RELOCATION | 815 - Addiscott | 101761 | Active | 79 | Upload Completed |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 510384.26 | 24625.67 | 510384.26 | 510384.26 | Wong, Henry |  |  | 27-Jul-23 | [6 empty] | 0
648375 | 2023 SWITCH RENEWAL - BARRIE - AB-B22 - BEACON RD. 44KV LIS REPLACEMENT | 825 - Patterson | 101027 | Active | 79 | Upload Completed |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 227419.79 | 15014.38 | 227419.79 | 227419.79 | Wong, Henry |  |  | 27-Jul-23 | [6 empty] | 0
648377 | 2023 SWITCH RENEWAL - PENETANG - AB-B1001 - JOHN ST. 44KV LIS REPLACEMENT | 825 - Patterson | 101027 | Active | 79 | Upload Completed |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 154013.81 | 12170.21 | 154013.81 | 154013.81 | Wong, Henry |  |  | 27-Jul-23 | [6 empty] | 0
648376 | 2023 SWITCH RENEWAL- BARRIE - AB-B73 - HURONIA RD. 44KV LIS REPLACEMENT | 825 - Patterson | 101027 | Active | 79 | Upload Completed |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 255695.49 | 14046.25 | 255695.49 | 255695.49 | Wong, Henry |  |  | 27-Jul-23 | [6 empty] | 0
648383 | 35 GRENCER RD/BRAD/NS/3PH PAD | 825 - Patterson | 101919 | Active | 70 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648412 | 648412 - WOODBRIDGE AVENUE BRIDGE IMPROVEMENTS | 815 - Addiscott | 101761 | Active | 94 | ANALYZE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander | 13-Jan-23 |  |  | 128822.77 | 121341.06 | 128822.77 | 128822.77 | Horlings, Jake | Transpw | 13-Apr-23 | 27-Jul-23 | 17-Mar-23 | 23-Mar-23 | 10-Jul-23 | Contractor | Contractor |  | 0
648421 | 2023 DA - BARRIE - ARDAGH RD & MAYFAIR DR. - NEW 13.8KV RECLOSER | 825 - Patterson | 100886 | Active | 79 | Upload Completed | High | DA | 2023 | Obeng, Nana | Walters, Geoffrey D |  | 1 |  | 117351.5 | 19990.23 | 117351.5 | 117351.5 | East Coordinator |  |  | 27-Jul-23 | [6 empty] | 0
648425 | 2023 DA - BARRIE - BURTON AVE E/O ROBINSON ST - NEW 44KV AUTOMATED LIS | 825 - Patterson | 100886 | Active | 82 | RELEASED | High | DA | 2023 | Obeng, Nana | Walters, Geoffrey D | 30-May-23 | 1 |  | 239601.7 | 19752.59 | 239601.7 | 239601.7 | Mark Timbers | N/A | 22-Nov-23 | 22-Nov-23 | 01-Nov-23 |  |  | Materials |  |  | 0
648436 | 2023 SWITCHGEAR REPLACEMENT - A05 - A05SP2004 | 815 - Addiscott | 151911 | Active | 82 | PDG SnR |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 168631.32 | 2032.39 | 168631.32 | 168631.32 | Wong, Henry |  |  | 27-Jul-23 | [6 empty] | 0
648439 | RA WESTON ROAD WIDENING PHASE 1 - HWY 407 TO FIELDSTONE DR | 815 - Addiscott | 101762 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648460 | YONGE NORTH SUBWAY EXTENSION - EEB4 - METROLINX | 815 - Addiscott | 151546 | Active | 50 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648458 | YONGE NORTH SUBWAY EXTENSION - CLARK - METROLINX | 815 - Addiscott | 151546 | Active | 10 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648457 | 648457 - 2023 UG TX RENEWAL - BARRIE - T9625 - 70 PIONEER TRAIL - LEAKING 1PH TX REMOVAL | 825 - Patterson | 101508 | Active | 95 | ANALYZE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D | 20-Dec-22 | 1 | 1 | 18729.01 | 7306 | 18729.01 | 18729.01 | Lotto, Jay | HapAmp | 05-Apr-23 | 27-Jul-23 | 16-Mar-23 | 01-Feb-23 | 21-Feb-23 |  |  |  | 0
646463 | 646463 - 2023 SG REPL - AUTO 36-L147 - VAUGHAN | 815 - Addiscott | 100859 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 01-Nov-22 | 2 |  | 260810.77 | 149399.54 | 181377.81 | 260810.77 | Horlings, Jake | Somervl | 31-Dec-23 | 29-Dec-23 | 05-Jun-23 | 06-Jul-23 |  |  |  |  | 79,432.96
648486 | 648486 - 2023 DA - V31SL3063 - VAUGHAN | 815 - Addiscott | 100886 | Active | 82 | RELEASED | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 23-May-23 | 1 |  | 98222.07 | 78403.79 | 98222.07 | 98222.07 | Reginald Clarke |  | 10-Oct-23 | 10-Oct-23 | 02-Oct-23 | [5 empty] | 0
648485 | 648485 - 2023 DA - V31SL3065 - VAUGHAN | 815 - Addiscott | 100886 | Active | 82 | RELEASED | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James |  | 1 |  | 102702.07 | 71341.11 | 102702.07 | 102702.07 | Reginald Clarke |  | 18-Sep-23 | 18-Sep-23 | 11-Sep-23 | [5 empty] | 0
648484 | 648484 - 2023 DA - A10SL2044 - AURORA | 815 - Addiscott | 100886 | Active | 82 | RELEASED | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 18-Apr-23 | 1 |  | 199728.19 | 26379.55 | 199728.19 | 199728.19 | Reginald Clarke |  | 09-Aug-23 | 21-Aug-23 | 17-Jul-23 | [5 empty] | 0
648482 | 648482 - 2023 DA - V51SL1007 - VAUGHAN | 815 - Addiscott | 100886 | Active | 82 | RELEASED | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 28-Jun-23 | 1 |  | 124920.77 | 17883.56 | 124920.77 | 124920.77 | Reginald Clarke |  | 13-Oct-23 | 13-Oct-23 | 02-Oct-23 | [5 empty] | 0
648481 | 648481 - 2023 DA - V25SL3076 - VAUGHAN | 815 - Addiscott | 100886 | Active | 82 | RELEASED | High | DA | 2023 | Tenorlas, Reynaldo | Roy, James | 18-Apr-23 | 1 |  | 109973.38 | 19461.79 | 109973.38 | 109973.38 | Reginald Clarke |  | 15-Aug-23 | 15-Aug-23 | 08-Aug-23 | [5 empty] | 0
648513 | 2023 EMERGING OH - BRADFORD - AB13805 - 13.8KV MANUAL LIS INSTALLATION | 825 - Patterson | 101027 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648514 | 177 WHITMORE RD - SG RELOCATION | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648526 | 10TH SIDE ROAD NEW TECUSMETH - POLE RELOCATION | 825 - Patterson | 101763 | Active | 94 | COMPLETE |  |  | 2023 | Lacombe, Joel | Boivin, Cameron |  |  |  | 40238.81 | 38557.9 | 40238.81 | 40238.81 | Sajeevan Kunasegaram |  | 03-Jul-23 | 27-Jul-23 | 03-Jul-23 | 30-May-23 | 30-May-23 | xBy-passed | xBy-passed |  | 0
648528 | 391 WEST PARK, BLOCK 106 - BRADFORD - RES SUBD EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648545 | CUSTOMER INITIATED OH RELOCATION - 16TH AVE AND 9TH LINE, MARKHAM | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648551 | 2023 CABLE REPLACEMENT - V51 - BAINBRIDGE AVE | 815 - Addiscott | 151912 | Active | 79 | Upload Completed |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 1327553.14 | 48364.81 | 1327553.14 | 1327553.14 | East Coordinator | Transpw |  | 27-Jul-23 | [6 empty] | 0
648552 | 2023 CABLE REPLACEMENT - V51 - WOODCROFT LANE | 815 - Addiscott | 151912 | Active | 84 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred | 26-May-23 |  |  | 621544.54 | 36748.72 | 621544.54 | 621544.54 | Dave Lindsay | Transpw | 24-Nov-23 | 20-Nov-23 | 16-Oct-23 | 18-Jul-23 |  |  |  |  | 0
648612 | TFP AURORA DEVELOPMENT, PHASE 2 (EAST) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648659 | DUDLEY AVE. - #160 MAR/UP/3 PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648663 | 145 WELLINGTON ST W/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Cranley, Stephen |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648662 | CABLE HIT @ 16TH AVE WEST OF 404 | 815 - Addiscott | 101762 | Inactive | 99 | CANCELLED |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 07-Jun-23
648669 | 16TH AVE & HWY 404 - CABLE REPLACEMENT | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648688 | 2022 - 114 HOLLAND STREET EMERGING CABLE REPLACEMENT IN BRADFORD | 825 - Patterson | 151450 | Active | 95 | COMPLETE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 152185.68 | 141504.2 | 152185.68 | 152185.68 | Lotto, Jay |  | 06-Jun-23 | 27-Jul-23 | 29-May-23 | 15-May-23 | 30-May-23 | xBy-passed |  |  | 0
648689 | 447 BAYVIEW DRIVE/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648716 | BERCZY WARDEN PHASE 2 - MARKHAM | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648730 | 2023 UG CABLE REPLACEMENT - V51 - RAINBOW DR | 815 - Addiscott | 101781 | Active | HL | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Kahlon, Aneel |  |  |  | 0 | 986.61 |  | 0 | East Coordinator |  |  | 27-Jul-23
648734 | BATHURST ST. - #9600 VAU/NS/3 PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648738 | 10356 HUNTINGTON RD/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2022 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 340.18 |  | 0 | East Coordinator |  |  | 03-Feb-23
454198 | 4433, 4455, 4477 MAJOR MA RESIDENTIAL SUBDIVISION CONNECTIONS | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Estrada, Michael | 17-Apr-23 |  |  | 410702.91 | 383294.51 | 410702.91 | 410702.91 | Dave Lindsay | Transpw | 07-Jul-23 | 26-Jul-23 | 29-May-23 | 18-Apr-23 | 27-Apr-23 |  |  |  | 0
648742 | 648742 - 2023 - POLE RENEWAL - P51551 - 1 POLE | 815 - Addiscott | 100867 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 08-May-23 |  |  | 33077.89 | 16232.42 | 33077.89 | 33077.89 | Kristine Gordon | Somervl | 09-Nov-23 | 09-Nov-23 | 06-Nov-23 | [5 empty] | 0
648759 | 217 DUNLOP ST E/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 48 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648780 | WESTON RD. - #7979 UNIT 1 VAU/UP/3 PH PAD | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648800 | 10443 HWY 27 / VAU / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Mann, Drew | 29-Mar-23 |  |  | 49462.7 | 45969.77 | 49462.7 | 49462.7 | Dave Lindsay | N/A | 19-May-23 | 02-Aug-23 | 09-May-23 | [5 empty] | 0
648803 | 11 LANSDOWNE AVENUE, VAUGHAN - ANCHOR RELOCATION | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648821 | 351 NEW ENTERPRISE WAY/VAU/NS/CUST OWNED | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648822 | 434 STEELES AVE W / VAU / SR / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 95 | ANALYZE |  |  | 2023 | Joshi, Namrata | Mann, Drew | 24-Feb-23 |  |  | 14148.48 | 7385.99 | 14148.48 | 14148.48 | Dave Lindsay | Somervl | 20-Apr-23 | 27-Jul-23 | 11-Apr-23 | 09-Mar-23 | 09-Mar-23 |  |  |  | 0
648930 | CUSTOMER INITIATED EXPANSION-MARKHAM,WOODBINE AVE(S. OF HWY 7-N. OF MMD),PHASE 5 | 815 - Addiscott | 151587 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649044 | 649044 - 22 ROSEMARY AVE - POLE RELOCATION - RICHMOND HILL | 815 - Addiscott | 101762 | Active | 93 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan | 03-Apr-23 |  |  | 15882.8 | 14794.79 | 15882.8 | 15882.8 | Macdonald, Steve | K-Line | 24-May-23 | 27-Jul-23 | 23-May-23 | 28-Apr-23 | 28-Apr-23 |  |  |  | 0
649106 | 10800 JANE ST/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649108 | ROYAL GATE BLVD. - #20 VAG/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649123 | 3201 HWY 7 / VAU / NS / CO-STN | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649222 | ROAD AUTHORITY RELOC-16TH AVE(E. OF LESLIE ST-W. OF HWY 404)-PHASE 2 | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649248 | 1 INTERCHANGE WAY / VAU / NS / CO-STN | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649249 | 380 ESNA PARK DR / MAR / UP / 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649270 | 9929 KEELE ST / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649273 | ISLINGTON AVE. - #9630 | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649277 | 649277 - ANCHOR REMOVAL & INSTALLATION VILLAGE GATE BROWNSTONES | 815 - Addiscott | 101887 | Active | 94 | ANALYZE |  |  | 2023 | Penner, Mitchell | Kinsella, William P | 16-May-23 |  |  | 15964.12 | 13796.03 | 15964.12 | 15964.12 | Kristine Gordon | N/A | 22-Mar-23 | 27-Jul-23 | 22-Mar-23 | 22-Mar-23 | 22-Mar-23 |  |  |  | 0
649279 | 821 BIG BAY POINT, BARRIE - RES SUBD EDS | 825 - Patterson | 101887 | Inactive | 99 | CANCELLED |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648965 | 648965 - 2023-EMERGING-AERIAL TRESPASS- 9 MILNE LANE | 815 - Addiscott | 101355 | Active | 96 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) | 19-Jan-23 |  |  | 16765.64 | 7488.87 | 16765.64 | 16765.64 | Kristine Gordon |  | 10-Mar-23 | 27-Jul-23 | 08-Mar-23 | 02-Feb-23 | 02-Feb-23 |  |  |  | 0
649321 | PROJECT RAINBOW PH 2 CONNECTIONS / VAU / NS / CO-SUB | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649389 | 5988/5960 8TH LINE BEETON/NS/CUSTOMER OWNED STN | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649394 | 481 YONGE ST/AUR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649404 | 2023 EMERGING - HWY 7 AND MAIN ST UNIONVILLE | 815 - Addiscott | 101355 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649412 | 649412 - 2023 DA EMERGING - A07SL2003 - AURORA | 815 - Addiscott | 101355 | Active | 82 | RELEASED |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 28-Jun-23 |  |  | 138258.23 | 20205.07 | 138258.23 | 138258.23 | Reginald Clarke |  | 17-Nov-23 | 17-Nov-23 | 06-Nov-23 | [5 empty] | 0
649413 | 649413 - 2023 DA EMERGING - MSH - TWO NEW RECLOSERS - MARKHAM | 815 - Addiscott | 101355 | Active | 95 | COMPLETE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James | 04-May-23 | 2 | 2 | 241918.2 | 241495.7 | 241918.2 | 241918.2 | Reginald Clarke |  | 14-Jun-23 | 27-Jul-23 | 23-May-23 | 23-May-23 | 06-Jun-23 |  |  |  | 0
649418 | EMERGING CABLE REPLACEMENT - PETERMAR DR - VAUGHAN | 815 - Addiscott | 151450 | Inactive | 99 | CANCELLED |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator | Somervl |  | 25-May-23
649433 | 164 INNISFIL ST/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 10 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649492 | 14 EAST'S CORNERS BLVD | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649504 | 649504 - KENNEDY RD. #7997 MAR/SR/OH TRANS | 815 - Addiscott | 101791 | Active | 94 | COMPLETE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 7477.96 | 5884.87 | 7477.96 | 7477.96 | Kristine Gordon |  | 08-Feb-23 | 27-Jul-23 | 08-Feb-23 | 08-Feb-23 | 08-Feb-23 |  |  |  | 0
649513 | 5875 HWY 7 - DUCT BANK RE-ALIGNMENT - VAUGHAN | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649525 | BARRIE - 49 TRUMAN RD. - 44KV PME REPLACEMENT | 825 - Patterson | 151719 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649551 | 20 LLOYD ST/VAU/SR/CUST OWNED | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A | 05-Jul-23 |  |  | 37828.95 | 4746.93 | 37828.95 | 37828.95 | Dave Lindsay | Somervl | 27-Jul-23 | 01-Aug-23 | 24-Jul-23 | [5 empty] | 0
649552 | 11085 KEELE ST/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649563 | BAYVIEW AVE, HWY 7 TO 16TH AVE | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649577 | BERNADOTTE DR. - #15 MAR/NS/1PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649588 | KING VAUGHAN RD/VAU/NS/3 PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649590 | HENDERSON DR & MCCLENNY DR | 815 - Addiscott | 101761 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649592 | HIGHWAY NO. EAST - #4077 MAR/NS/ 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649603 | 10TH SIDE ROAD NEW TECUSMETH - POLE RELOCATION | 825 - Patterson | 101763 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Boivin, Cameron |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649617 | VMC GRAYWOOD DEVELOPMENT - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649618 | ALECTRA EAST SUBD EAST - SUBDIVISION MAINTENANCE - VMC GRAYWOOD DEVELOPMENT | 815 - Addiscott |  | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649622 | MAPLE HEIGHTS, VAUGHAN - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Sabbah, Amir |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649624 | 566 HOLLAND ST/BRAD/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649627 | 12 INDUSTRIAL CRT/BRAD/UP/3PH PAD | 825 - Patterson | 101919 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Paterson, Greg | 14-Apr-23 |  |  | 36226.48 | 20554.6 | 36226.48 | 36226.48 | Lotto, Jay |  | 18-May-23 | 27-Jul-23 | 15-May-23 | 28-Apr-23 | 15-May-23 |  |  |  | 0
649633 | JANE ST. - #11110 VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 28-Apr-23 |  |  | 210252.15 | 3682.15 | 210252.15 | 210252.15 | Dave Lindsay | Somervl | 08-Mar-24 | 08-Mar-24 | 08-Feb-24 | [5 empty] | 0
649637 | KIPLING AVE NORTH OF TESTON ROAD | 815 - Addiscott | 101761 | Active | 70 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649639 | KING EAST DEVELOPMENT - PHASE 2B - SUBD RED EDS | 815 - Addiscott | 101887 | Active | 40 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649664 | 160 OXFORD - APLIN MARTIN RESIDENTIAL SUBDIVISION CONNECTIONS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649697 | VOLTAGE CONVERSION - CONVERT CUSTOMERS ON AMBER MS INTO 27.6KV SUPPLY, MARKHAM | 815 - Addiscott | 101781 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649699 | I&C IVYLEA SUBD | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649700 | ALECTRA EAST MAINTENANCE SUBD IVYLEA | 815 - Addiscott |  | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649709 | JANE ST PUMPING STATION / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649734 | WELLINGTON D1 PHASE 3 POLE REPLACEMENTS, BARRIE - ROAD AUTHORITY INITIATED | 825 - Patterson | 101764 | Active | 50 | ACTIVE |  |  | 2023 | Lacombe, Joel | Mckeen, Brant |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649732 | WELLINGTON D1 PHASE 2 POLE REPLACEMENTS, BARRIE - ROAD AUTHORITY INITIATED | 825 - Patterson | 101764 | Active | 50 | ACTIVE |  |  | 2023 | Lacombe, Joel | Mckeen, Brant |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649730 | EUGENIA STREET POLE REPLACEMENTS, BARRIE - ROAD AUTHORITY INITIATED | 825 - Patterson | 101764 | Active | 50 | ACTIVE |  |  | 2023 | Lacombe, Joel | Mckeen, Brant |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649750 | 649750 - 9699 BATHURST STREET | 815 - Addiscott | 101761 | Active | 92 | COMPLETE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander | 01-May-23 |  |  | 7659.39 | 16557.87 | 7659.39 | 7659.39 | Kristine Gordon |  | 12-Jun-23 | 27-Jul-23 | 12-Jun-23 | 31-May-23 | 31-May-23 |  |  |  | 0
649756 | YNSE - CUSTOMER INITIATED EXPANSION - PROJECT MANAGEMENT | 815 - Addiscott | 152323 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Morris, Mark |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649770 | ROAD AUTHORITY RELOC-16TH AVE(E. OF HWY 404-W. OF WOODBINE AVE)-PHASE 3 | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649778 | 484 BIG BAY POINT P54916 INSTALL ADDITIONAL ANCHORING | 825 - Patterson | 100867 | Active | 70 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649779 | BEETON MEADOWS POLE RELOCATION | 825 - Patterson | 101763 | Active | 40 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649780 | RER - MX - RELOC - ACCESS RD @ KEELE ST - BA2525 - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Active | 40 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649781 | 123 HILLSVIEW DR / RHL / UP / 3PH PAD TXS | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649783 | JANE ST, HWY 7 TO TESTON RD | 815 - Addiscott | 101761 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649841 | MALMO COURT - #65 VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649860 | 2023 - 236 BAYFIELD SEC. RELOCATION IN BARRIE | 825 - Patterson | 151450 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649875 | CAPLINK SYSTEM EXPANSION - 351 NEW ENTERPRISE WAY | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649881 | 500 COPPER CREEK/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649882 | EMERGING CABLE REPLACEMENT - WADE GATE - VAUGHAN | 815 - Addiscott | 151450 | Active | 82 | PDG SnR |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 58446.08 | 8438.82 | 58446.08 | 58446.08 | Wong, Henry | Somervl |  | 27-Jul-23 | [6 empty] | 0
649896 | HWY 7, CORNELL ROUGE BLVD & DC PKWY | 815 - Addiscott | 101761 | Active | 40 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649901 | MS302 LV CABLE REPLACEMENT | 825 - Patterson | 152490 | Active | 48 | ACTIVE |  |  | 2023 | Burns, David | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649914 | ROBINSON GLEN (PHASE 1A) – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649915 | 1667 CREDITSTONE RD/VAU/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649917 | 80 YORK HILL BLVD / VAU / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649919 | 2800 HWY 7 / VAU / NS / CO-STN | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649918 | ROBINSON GLEN PHASE 1B - SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649951 | PROMENADE DEVELOPMENT - PHASE 1A, EDS CONNECTIONS | 815 - Addiscott | 101887 | Active | 79 | PPS INCOMPLETE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 41067.95 | 12306.03 | 41067.95 | 41067.95 | East Coordinator |  |  | 27-Jul-23 | [6 empty] | 0
649963 | RA - NORTHEAST VAUGHAN - POLE RELOCATION | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649965 | 2023 - 10-24 GROVE STREET PRIMARY AND SEC CABLE REPLACEMENT | 825 - Patterson | 151450 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649976 | YNSE - LANGSTAFF AVE - TEMP 3M SERV ICE (NS) / CUSTOMER OWNER S/S | 815 - Addiscott | 152323 | Active | 10 | ACTIVE |  |  | 2023 | Paesano, Andrew | Morris, Mark |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649996 | 2023 CABLE REPLACEMENT - M15 - LARKIN AVE AREA OF MARKHAM | 815 - Addiscott | 101781 | Inactive | 99 | CANCELLED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649998 | 2024 CABLE REPLACEMENT – M44 – COCHRANE DR - SCOLBERG RD - PHASE 1 | 815 - Addiscott | 151913 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649997 | 2024 CABLE REPLACEMENT – M21 – RAYMERVILLE DR - PHASE 2 | 815 - Addiscott | 151329 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649981 | 11014 YONGE STREET DEVELOPMENT - SUBDIVISION CONNECTIONS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Manojlovic, Stefan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650033 | CARRVILLE ROAD ENCLAVE TOWNHOMES - SUBDIVISION CONNECTIONS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | East |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650053 | 253 TIFFIN ST/BAR/UP/ | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650081 | 2023 POLE RENEWAL - P21 & P17 - COLD CREEK RD & NASHVILLE RD | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650083 | BUR OAK AVE. - #1801 MAR/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650082 | 205 TORBAY RD/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650084 | 9825 YONGE ST - TEMP/RIC/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650085 | GOULDING AVE/AUR/NS/3 PHASE PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650097 | VTS4 PART 3 - YR1 - JANE & TESTON - ADDITIONAL WORK | 815 - Addiscott | 100340 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650119 | PROMENADE DEVELOPMENT - PHASE 1B, EDS CONNECTIONS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650140 | 50 ANNE ST N POLE RELOCATION | 825 - Patterson | 101763 | Active | 91 | ACTIVE |  |  | 2023 | Lacombe, Joel | Mckeen, Brant | 29-May-23 |  |  | 35523.97 | 28195.93 | 35523.97 | 35523.97 | Mark Timbers | K-Line | 07-Jul-23 | 27-Jul-23 | 03-Jul-23 | 02-Jun-23 |  |  |  |  | 0
650141 | RELOCATE POLES FOR MTO - DUNLOP STREET AND HIGHWAY 400, BARRIE | 825 - Patterson | 101764 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650181 | GILBRALTAR RD. - #865 VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 82 | Upload Completed |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 211782.76 | 3756.65 | 211782.76 | 211782.76 | East Coordinator |  |  | 27-Jul-23 | [6 empty] | 0
650198 | 50 LOCKHART RD/BAR/UP/3 PHASE PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650236 | BLOCK 59 DEVELOPMENTS - LANGSTAFF – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650222 | MATTAMY BERCZY GLEN RINAS PHASE 3 | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Brockley, Ryan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650255 | CABLE REPLACEMENT (A05) - HIGHLAND GATE TO BATHURST - AURORA | 815 - Addiscott | 151911 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650265 | 2024 SWITCH REPLACEMENT - A06SL2048 (AUTOMATED) - AURORA | 815 - Addiscott | 101027 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650264 | 2024 SWITCH REPLACEMENT - A02SL2001 (AUTOMATED) - AURORA | 815 - Addiscott | 101027 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650263 | 2024 SWITCH REPLACEMENT - A06SL2047 (AUTOMATED) - AURORA | 815 - Addiscott | 101027 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650266 | 2024 SWITCH REPLACEMENT - R21SL3018 (AUTOMATED) - RICHMOND HILL | 815 - Addiscott | 101027 | Inactive | 99 | CANCELLED |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650326 | 65 WELHAM RD/BAR/UP/3PH PAD | 825 - Patterson | 101919 | Active | 45 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650325 | 440 ESSA RD/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650324 | 15820 BAYVIEW AVE/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650241 | MAVRINAC BLVD & WELLINGTON ST E/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650151 | 960 16TH SIDEROAD/AUR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
649871 | 93 RAWSON AVE/BAR/UP/3PH PAD | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650348 | ELGIN MILLS RD. EAST - #10755 RICH/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650361 | 2911 MAJOR MACKENZIE DR W/VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650363 | EMERGING CABLE REPLACEMENT - CHESTNUT GATE - MARKHAM | 815 - Addiscott | 151450 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650362 | EMERGING CABLE REPLACEMENT - GREEN LANE - MARKHAM | 815 - Addiscott | 151450 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650370 | ESSEX AVE. - #145 RIC/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650371 | 3928 HIGHWAY 7/MAR/NS/CUST OWNED | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650388 | 2800 HWY 7, VAUGHAN - CUSTOMER INITIATED - SWITCHGEAR RELOCATIONS | 815 - Addiscott | 101761 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650442 | 2024 DA - A11SL2006 - AURORA | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650441 | 2024 DA - A10SL2015 - AURORA | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650450 | 2024 DA - V39SL3025 - VAUGHAN | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650449 | 2024 DA - V33SL3005 - VAUGHAN | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650448 | 2024 DA - R17SA3114 - RH | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650447 | 2024 DA - NEW UNIT ON MCCOWAN - MARKHAM | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650446 | 2024 DA - V25SL3026 - VAUGHAN | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650445 | 2024 DA - V08SL3007 - VAUGHAN | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650444 | 2024 DA - V32SL3017 - VAUGHAN | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650443 | 2024 DA - 39-L42 - VAUGHAN | 815 - Addiscott | 100886 | Active | 45 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650452 | HUNTINGTON RD & LANGSTAFF RD | 815 - Addiscott | 101761 | Active | 82 | PDG SnR |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 29340.99 | 2775.32 | 29340.99 | 29340.99 | East Coordinator |  |  | 27-Jul-23 | [6 empty] | 0
650453 | JANESSA COURT, VAUGHAN - RES SUBD EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650455 | 209 MILANI BLVD / VAU / NS / 3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650369 | 46 BRIAROSE AVE / VAU / NS / 1PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650279 | 20 BLENCATHRA HILL / MAR / NS / 1PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650273 | 205 COMMERCE VALLEY DR E / MAR / NS / CO-STN | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650460 | YONGE ST. - #7859 MAR/UP/3PH PAD | 815 - Addiscott | 101791 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650465 | 1 FLATO DR/MAR/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650489 | 2024 STORM HARDENING - BAYVIEW - AURORA | 815 - Addiscott | 103659 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650490 | 2024 STORM HARDENING - VANDORF - AURORA | 815 - Addiscott | 103659 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650507 | 175 ERIC T SMITH WAY/AUR/NS/3 PHASE PAD | 815 - Addiscott | 101791 | Active | 45 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650516 | HIGHWAY NO. 7 WEST - #2899 VAU/NS/CUST | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650526 | UG EMERGING - 300 HOLLAND ST. W - 3PH PDMT TX | 825 - Patterson | 151450 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650533 | 27 KORDA GATE / VAU / UP / CO-SUB | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650537 | RA WESTON ROAD WIDENING PHASE 2 - RUTHERFORD RD | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650541 | MAJOR MACKENZIE DR. WEST - #3100 VAU/NS/3PH PAD | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
454227 | RER-MX-RELOC-INDUSTRIAL PKWY-BARRIE LINE(43,1918,1919,1920,2160)-RAILWAY CROSSIN | 815 - Addiscott | 150591 | Active | 50 | ACTIVE |  |  | 2023 | Khuu, Philander | Grahovac, John |  |  |  | 0 | 0 |  | 0 | Wong, Henry
650574 | ROAD AUTHORITY RELOC-16TH AVE(E. OF WOODBINE AVE-W. OF KENNEDY RD) | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650578 | HUNTER'S VALLEY - ROAD EXTENSION - VAUGHAN | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650627 | RUTHERFORD RD. - #6531 VAU/NS/CUS | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650629 | MX - AURORA IMPROVEMENTS - 95 DUNNING AVE RELOCATION | 815 - Addiscott | 150591 | Active | 10 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650675 | OH, TOTTENHAM - 5 BROWN ST. - INSTALL 200A FUSED INLINES | 825 - Patterson | 101355 | Active | 48 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650676 | OH- BARRIE - 2024 DA - BIG BAY POINT & YONGE ST. - 44KV AUTOMATED LIS | 825 - Patterson | 100886 | Active | 50 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650648 | UG - BARRIE - 24 FERNDALE INDUSTRIAL DR - T3937 LEAKING 3PH TX | 825 - Patterson | 101508 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650646 | UG- BARRIE - 448 DUNLOP ST. WEST - T2005 LEAKING 3PH TX REPLACEMENT | 825 - Patterson | 101508 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650645 | UG - BARRIE - 110 DUNLOP ST. WEST - T946 LEAKING 3PH TX | 825 - Patterson | 101508 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650677 | OH - BRADFORD - 2024 DA - 8TH LINE E/O YONGE ST. - 44KV AUTOMATED LIS | 825 - Patterson | 100886 | Active | 50 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650678 | OH- BRADFORD - 2024 DA - 10TH SIDEROAD S/O REAGENS - 44KV AUTOMATED LIS | 825 - Patterson | 100886 | Active | 50 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650687 | SHINING HILL ESTATES PHASE 3 STAGE 2 - RES SUBD EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650695 | ROAD AUTHORITY RELOC-16TH AVE(W. OF WOODBINE AVE-E. OF WOODBINE AVE)-PHASE 4 | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650179 | 650179 - TX AND RISER REMOVALS - ARCHERHILL COURT, AURORA | 815 - Addiscott | 151531 | Active | 82 | RELEASED |  |  | 2023 | Penner, Mitchell | Handy, James | 12-Jul-23 |  |  | 19108.88 | 2066.55 | 19108.88 | 19108.88 | Dave Lindsay |  | 14-Aug-23 | 14-Aug-23 | 01-Aug-23 | [5 empty] | 0
650737 | CENTURY PLACE - #1 VAU/NS/CUS OWNED TX. | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650756 | WOODBINE AVENUE TOWNHOME DEVELOPMENT – SUBD RES EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650761 | 2024 TX RENEWAL - BATCH 22 - 12 TX- AURORA | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650763 | 2024 TX RENEWAL - BATCH 23 - 7 TX- AURORA | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650762 | 155 GARDEN AVE - RICHMOND HILL | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650767 | 2024 TX RENEWAL - BATCH 26 - 25TX- MARKHAM | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650766 | 2024 TX RENEWAL - BATCH 25 - 19 TX- MARKHAM | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650765 | 2024 TX RENEWAL - BATCH 24 - 14 TX- MARKHAM | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650753 | 5965 HIGHWAY 7 | 815 - Addiscott | 101791 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650771 | 3120 STEELES AVE E | 815 - Addiscott | 101791 | Active | 40 | ACTIVE |  |  | 2023 | Hart, Dylan | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650772 | 9085 JANE ST | 815 - Addiscott | 101791 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650775 | 491 BOWES RD | 815 - Addiscott | 150384 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
648901 | POLE REPLACEMENTS - BAYVIEW DR FOR 80 BIG BAY DEV | 825 - Patterson | 151531 | Active | 48 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650797 | 2024 TX RENEWAL - BATCH 29 - 5TX -RICHMOND HILL | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650796 | 2024 TX RENEWAL - BATCH 28 - 9TX -RICHMOND HILL | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650795 | 2024 TX RENEWAL - BATCH 27 - 8TX- RICHMOND HILL | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650800 | 2024 TX RENEWAL - BATCH 32 - 18TX -VAUGHAN | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650799 | 2024 TX RENEWAL - BATCH 31 - 10TX -RICHMOND HILL | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650798 | 2024 TX RENEWAL - BATCH 30 - 15TX -RICHMOND HILL | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650801 | 2024 TX RENEWAL - BATCH 33 - 15TX -VAUGHAN | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650802 | 2024 TX RENEWAL - BATCH 34 - 14TX -VAUGHAN | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650807 | 2024 TX RENEWAL - BATCH 38 - 11TX -VAUGHAN | 815 - Addiscott |  | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650806 | 2024 TX RENEWAL - BATCH 37 - 16TX -VAUGHAN | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650804 | 2024 TX RENEWAL - BATCH 36 - 17TX -VAUGHAN | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650803 | 2024 TX RENEWAL - BATCH 35 - 23TX -VAUGHAN | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650809 | 2024 TX RENEWAL - BATCH 40 - 4TX -VAUGHAN | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650808 | 2024 TX RENEWAL - BATCH 39 - 8TX -VAUGHAN | 815 - Addiscott | 101508 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650816 | WOODBINE AVE. - #8885 MAR/SR/VAULT RECOVERY | 815 - Addiscott | 101791 | Active | 82 | RELEASED |  |  | 2023 | Joshi, Namrata | Yuen, Paul | 27-Jun-23 |  |  | 11308.48 | 681.79 | 11308.48 | 11308.48 | Dave Lindsay | N/A | 04-Jul-23 | 27-Jul-23 | 04-Jul-23 | [5 empty] | 0
650829 | BERCZY ELGIN DEVELOPMENT - MARKHAM | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650828 | 124 WESTWOOD LANE | 815 - Addiscott | 101791 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650832 | 2800 HWY 7 | 815 - Addiscott | 150384 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650811 | 11110 JANE ST - POLE RELOCATION | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650851 | 2024 - POLE REBUILD - MAJOR MACKENZIE/LESLIE - 4 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650852 | 2024 - POLE REBUILD - MAJOR MACKENZIE/ELMWOOD - 12 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650853 | 2024 POLE REBUILD - DUNLOP ST/BEDFORD PARK AVE - 10 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650854 | 2022 POLE REBUILD - PEMBERTON RD - 10 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650855 | 2023 - POLE REBUILD - KERSEY CRES/ YONGEHURST RD - 10 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650857 | 2024 POLE REBUILD - HILLSIDE - 11 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650856 | 2024 POLE REBUILD - WESTWOOD - 15 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650859 | 2024 POLE RENEWAL - BATCH 2 - 10 POLES | 815 - Addiscott | 100867 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650858 | 2024 POLE RENEWAL - BATCH 1 - 11 POLES | 815 - Addiscott | 100867 | Active | 50 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650531 | 99 MAPLEVIEW DR E/BAR/NS/3PH PAD | 825 - Patterson | 101919 | Active | 48 | ACTIVE |  |  | 2023 | Cranley, Stephen | Paterson, Greg |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650860 | 2024 POLE REBUILD - OAK AVE - 9 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650861 | 2024 POLE REPLACEMENT - DUNHAM/JASPER/HAIDA/KITMAT - 9 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650866 | 2024 POLE REBUILD - AURORA/KING - 2 POLES | 815 - Addiscott | 100867 | Active | 97 | CANCELLED |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650864 | 2024 POLE REBUILD - VARIOUS LOCATION AURORA - 5 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650862 | 2024 POLE REBUILD - INDUSTRIAL PKWY/WELLINGTON ST E - 3 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650870 | BLOCK 59 HYDRO POLE RELOCATION - VAUGHAN | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650893 | 3300 HWY 7 / MAR / NS / CO-SUBSTN | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650892 | 2024 - POLE REBUILD - BAYVIEW/ STOUFFVILLE RD - 5 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Li, Jun Xun (John) |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650899 | CACHET WOODS CRT / MAR / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650914 | CUSTOMER INITIATED EXPANSION-MARKHAM(BUTTONVILLE TS AT 16TH AVE AND RODICK RD) | 815 - Addiscott | 151587 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Zhang, Jiacheng |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650918 | 2024 POLE REBUILD - KING VAUGHAN RD | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650917 | 2024 POLE REBUILD - BATHURST ST AND KING RD | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650916 | 2024 POLE REBUILD - SUNSET BEACH RD AND LAKE AVE | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650926 | BAYVIEW DRIVE & LITTLE AVE, BARRIE - ROAD AUTHORITY PROJECT | 825 - Patterson | 101764 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650939 | DI BENEDETTO LAND - EQUIPMENT REMOVALS | 815 - Addiscott | 101685 | Active | 70 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650074 | 125 SIMCOE RD/BRA/SR/3 PHASE PAD - REMOVAL | 825 - Patterson | 101919 | Active | 94 | ANALYZE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 8940.92 | 3407.77 | 8940.92 | 8940.92 | East Coordinator |  |  | 27-Jul-23 |  | 12-Jun-23 | 13-Jun-23 | xBy-passed | xBy-passed |  | 0
650941 | LESLIE ST, NORTH OF 19TH AVE | 815 - Addiscott | 101761 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650945 | HURONIA ROAD IMPROVEMENTS - LOCKHARD TO MCKAY AND MCKAY TO HWY 400 | 825 - Patterson | 101764 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650953 | SOFIA SEWER UPGRADE - CLAPPERTON, OWEN AND SOPHIA RD | 825 - Patterson | 101764 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650957 | 410 YONGE ST AND 343 LITTLE AVE - RES SUBD EDS | 825 - Patterson | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651025 | RUTHERFORD AND DUFFERIN, YORK REGION | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650528 | 6640 HIGHWAY 7 / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651053 | DUFERIN - KEELE TO LANGSTAFF | 815 - Addiscott | 101762 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651051 | 40 & 60 HARRIS AVE - RICHMOND HILL | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651058 | 658 MAPLEVIEW DR E/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651068 | 311 KING ST, BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651072 | 32 DAFFODIL AVE MARKHAM | 815 - Addiscott | 151578 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651075 | DUFFERIN VISTAS SUBDIVISION PHASE 2 - VAUGHAN | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651079 | SMART VMC RESIDENCES (ONE) - EDS SUBDIVISION - VAUGHAN | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Kinsella, William P |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651094 | 2023 EMERGING - JANE & TESTON POLE RELOCATION - VAUGHAN | 815 - Addiscott | 101355 | Active | 79 | Upload Completed |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 70718.82 | 9048.93 | 70718.82 | 70718.82 | East Coordinator |  |  | 27-Jul-23 | [6 empty] | 0
651103 | 67 OWEN STREET, BARRIE - 4.16KV POLE LINE EXTENSION | 825 - Patterson | 101763 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Harrington, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651133 | HIGHMOUNT CONDOMINIUMS - MARKHAM | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Estrada, Michael |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650684 | 8905 BATHURST ST / RHL / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 50 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651143 | 125 SIMCOE RD/BRA/NS/3 PHASE PAD | 825 - Patterson | 101824 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651148 | 560 ESSA RD/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651154 | 1331 TESTON RD | 815 - Addiscott | 101791 | Active | 40 | ACTIVE |  |  | 2023 | Joshi, Namrata | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651158 | NAVY LANE DAYLIGHTING POLE RELOCATION - JURY DR AND FULLER AVE | 825 - Patterson | 101763 | Active | 10 | ACTIVE |  |  | 2023 | Lacombe, Joel | Diefenbaker, Trevor A |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651166 | 2023 CABLE REPLACEMENT - M31 - PHASE 1B - 14TH AVE | 815 - Addiscott | 101781 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651176 | 28 RAWSON AVE/BAR/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 50 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651206 | 497 WELLINGSTON ST HOMES - RES SUBD EDS | 815 - Addiscott | 101887 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651208 | 8905 BATHURST ST, RICHMOND HILL - POLE RELOCATION | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651217 | 2695 ELGIN MILLS ROAD EAST | 815 - Addiscott | 151578 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Abucejo, Chariz |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651225 | PROMENADE MALL TESLA SUPERCHARGER / VAU / NS / 3PH PAD TX | 815 - Addiscott | 101791 | Active | 10 | ACTIVE |  |  | 2023 | Joshi, Namrata | Mann, Drew |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651229 | 2023 POLE REPLACEMENTS BARRIE BLAKE ST | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
453928 | 453928 - MARKHAM BIRCHMOUNT FEEDER EXTENSION: STAGE 1 - SUBD EDS | 815 - Addiscott | 101896 | Active | 84 | ACTIVE |  |  | 2023 | Penner, Mitchell | Brockley, Ryan | 12-Jul-23 |  |  | 93392.6 | 80281.8 | 93392.6 | 93392.6 | Dave Lindsay | Conelco | 25-Jul-23 | 27-Jul-23 | 24-Jul-23 | 07-Jul-23 |  |  |  |  | 0
651230 | RER - MX - RELOC - MOSLEY ST - BARRIE LINE (1921) - RAILWAY CROSSINGS | 815 - Addiscott | 150591 | Active | 40 | ACTIVE |  |  | 2023 | Khuu, Philander | Washburn, Martin |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651232 | BRIAR HILL T21650 AND SERVICE RELOCATIONS | 825 - Patterson | 151531 | Active | 10 | ACTIVE |  |  | 2023 | Penner, Mitchell | Handy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651235 | 2024 POLE RENEWAL - 407 POLES - 3 POLES | 815 - Addiscott | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651236 | 2024 VAULT RENEWAL - 2 LOCATIONS - MARKHAM | 815 - Addiscott | 151526 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Roy, James |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651251 | 41 FREDERICK ST/BRA/NS/3 PHASE PAD | 825 - Patterson | 101919 | Active | 45 | ACTIVE |  |  | 2023 | Cranley, Stephen | Harris, Geoff L. |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651272 | INDUSTRIAL PARKWAY NORTH - AURORA ON- HYDRO POLE GUY WIRE RELOCATION | 815 - Addiscott | 101763 | Active | 50 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Murray, Jake R |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651274 | 2024 POLE REPLACEMENTS TOTTENHAM BATCH 1 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651277 | 2024 POLE REPLACEMENTS THORNTON BATCH 1 | 825 - Patterson | 100867 | Active | 40 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651276 | 2024 POLE REPLACEMENTS ALLISTON BATCH 1 | 825 - Patterson | 100867 | Active | 40 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651275 | 2024 POLE REPLACEMENTS TOTTENHAM BATCH 2 | 825 - Patterson | 100867 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651278 | 2024 POLE REPLACEMENTS THORNTON BATCH 2 | 825 - Patterson | 100867 | Active | 40 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651295 | 9064 WOODBINE, VAUGHAN - ANCHOR RELOCATION | 815 - Addiscott | 101761 | Active | 10 | ACTIVE |  |  | 2023 | Corriveau, Tom N | Silcock, Jordan |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651325 | 2023 EAST NORTH PCB UG TX REPLACEMENT BARRIE BATCH 4 | 825 - Patterson | 101508 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650784 | UG - BARRIE - 2024 SWGR REPLACEMENTS - SC13039 - 1 GOLDEN MEADOW RD. | 825 - Patterson | 100859 | Active | 48 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
650783 | UG - BARRIE - 2024 SWGR REPLACEMENTS - SC13474 - 171 GOLDEN MEADOW RD. | 825 - Patterson | 100859 | Active | 48 | ACTIVE |  |  | 2023 | Obeng, Nana | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651339 | 2024 TX RENEWAL PROGRAM -T9050 - 26 HOLLAND ST E BRADFORD | 825 - Patterson | 151043 | Active | 40 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651338 | 2024 TX RENEWAL PROGRAM -T6814 - 299 TUPPER BLVD | 825 - Patterson | 151043 | Active | 40 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651340 | 2024 TX RENEWAL PROGRAM -T7213 & T7172 TOTTENHAM | 825 - Patterson | 151043 | Active | 40 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651347 | 2024 TX RENEWAL PROGRAM - BARRIE BATCH 7 - 6 UNITS | 825 - Patterson | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651346 | 2024 TX RENEWAL PROGRAM - BARRIE BATCH 6 - 9 UNITS | 825 - Patterson | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651345 | 2024 TX RENEWAL PROGRAM - BARRIE BATCH 5 - 10 UNITS | 825 - Patterson | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651344 | 2024 TX RENEWAL PROGRAM - BARRIE BATCH 4 - 10 UNITS | 825 - Patterson | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651343 | 2024 TX RENEWAL PROGRAM - BARRIE BATCH 3 - 10 UNITS | 825 - Patterson | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651342 | 2024 TX RENEWAL PROGRAM - BARRIE BATCH 2 - 10 UNITS | 825 - Patterson | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651341 | 2024 TX RENEWAL PROGRAM - BARRIE BATCH 1 - 11 UNITS | 825 - Patterson | 151043 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651349 | 2024 CABLE INJECTION - 8TH LINE AND HWY 11 BRADFORD | 825 - Patterson | 151363 | Active | 10 | ACTIVE |  |  | 2023 | Obeng, Nana | Pollock, Kim |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651363 | 2024 LEFT BEHIND CABLE REPLACEMENT - A09 | 815 - Addiscott | 150263 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
651364 | 2024 LEFT BEHIND CABLE REPLACEMENT - M25 & M19 | 815 - Addiscott | 150263 | Active | 10 | ACTIVE |  |  | 2023 | Tenorlas, Reynaldo | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 20-Jul-20
SOUTH-WEST | South-West Region (Guelph) | [9 empty] | South-West |  | 470 | 340 | 22334915.38 | 17690158.22 |  | 0 | [5 empty] | 18-Feb-20 | 17-Jul-23
1018695 | NiMa Trails, Phase 1B Subdivision | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Kingswell, Dean J |  |  |  | 394748 | 0 | 394748 | 394748 | Stevens, Carl |  |  | 01-Apr-22 |  | 18-Jan-21 | 01-Mar-22 |  |  |  | 0
646220 | Silver Maple - 120 Westmount Road | 840 - Southgate | 151696 | Active | 95 | COMPLETE |  |  | 2022 | Velickovski, Goran | Kingswell, Dean J | 18-Feb-21 |  |  | 197590.07 | 184857.82 | 197590.07 | 197590.07 | Stevens, Carl | Drexler | 28-Feb-22 | 26-Jul-23 | 03-Jan-22 | 23-Aug-21 | 09-Sep-22 | Customer | Customer |  | 0
1085690 | 1131 Gordon Street Townhomes | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Kingswell, Dean J | 13-May-21 |  |  | 37162.62 | 19112.88 | 37162.62 | 37162.62 | Stevens, Carl |  | 30-Apr-21 | 31-Dec-21 | 30-Apr-21 | 04-Oct-21 | 01-Nov-21 |  |  |  | 0
1107154 | Harts Village, Phase 2 Subdivision | 840 - Southgate |  | Inactive | 99 | COMPLETE | High | Subdiv | 2022 |  | Kingswell, Dean J |  |  |  | 408091.46 | 25522.52 | 408091.46 | 408091.46 | Stevens, Carl |  |  | 04-Jan-22 |  | 30-Nov-20 | 27-Jan-22 | Customer |  |  | 0
646221 | Guelph West Reinforcement, Phase 3 - Edinburgh Road North | 840 - Southgate | 151089 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Harrison, Eric | 04-Feb-21 | 15 | 15 | 648023.9 | 592902.74 | 648023.9 | 648023.9 | Manes, Bradley |  | 29-Dec-21 | 07-Jul-23 | 01-Nov-21 | 06-Aug-21 | 29-Apr-22 |  |  |  | 0
1126105 | 164 and 168 Deerpath Drive Townhomes | 840 - Southgate |  | Inactive | 99 | COMPLETE | High | Subdiv | 2021 |  | Kingswell, Dean J |  |  |  | 337987.33 | 43263.12 | 337987.33 | 337987.33 | Stevens, Carl |  |  | 31-Dec-21 |  | 14-Aug-20 | 01-Mar-21 | Customer |  |  | 0
646219 | 85 Mullin Dr Townhomes | 840 - Southgate | 151696 | Active | 84 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 289497.32 | 163261.95 | 289497.32 | 289497.32 | Stevens, Carl | Drexler | 05-Sep-22 | 23-Aug-23 | 18-Feb-20 | 18-Feb-20 |  | Customer | Customer |  | 0
1082576 | 73 & 93 Arthur St S | 840 - Southgate |  | Inactive | 99 | COMPLETE | High | Res-ICI | 2021 |  | South-West |  |  |  | 0 | 528.03 | 0 | 0 | Stevens, Carl |  |  | 31-Dec-21 | 16-Mar-20 | 16-Mar-20 | 14-May-21 |  |  |  | 0
123456 | Test - Keep for Discussion Tab Comment | 805 - Sandalwood |  | Active | HL | ACTIVE |  |  | 2023 |  | Danieli, Andrea |  |  |  | 57 | 5 | 7 | 57 | Dre Danieli |  |  | 24-Jul-23 | [6 empty] | 50
1001255 | Massey & Michener Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 0 | 29130.14 |  | 0 |  |  |  | 16-Dec-20 |  | 27-Jan-22 | 27-Jan-22
1129628 | Main St N - Rail crossing - Rockwood | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Jamkodjian, Cassandra |  |  |  | 0 | 3651.5 |  | 0 |  |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22
1155355 | 89 Beechwood Avenue Townhomes | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Kingswell, Dean J | 04-Mar-21 |  |  | 48928.45 | 59850.74 | 48928.45 | 48928.45 | Stevens, Carl |  |  | 19-Dec-22 |  | 05-Apr-21 | 03-May-21 |  |  |  | 0
1037067 | Speedvale - Riverview - 386 Speedvale | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Harrison, Eric |  |  |  | 0 | 337888.43 |  | 0 |  |  |  | 16-Dec-20 |  | 27-Jan-22 | 27-Jan-22
1132376 | Z6003 Pole 208 Woodlawn Rd W | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Patenaude, Mélanie | 28-Oct-21 | 1 |  | 42654.81 | 35930.5 | 42654.81 | 42654.81 | Manes, Bradley |  | 30-Nov-21 | 01-Apr-22 | 29-Nov-21 | 19-Jan-22 | 19-Jan-22 |  |  |  | 0
935908 | Paisley St & Dublin St N | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 0 | 2866.7 |  | 0 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 02-May-22 | 02-May-22
1078053 | Cedar and Water St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 0 | 23203.11 | 0 | 0 |  |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1079630 | Dowler St - Rockwood | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Harrison, Eric |  |  |  | 0 | 82.01 |  | 0 |  |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22
1117011 | Pole 33 Massey Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Bolton, Ian |  |  |  | 0 | 154.91 |  | 0 |  |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22
1081608 | Delhi St pole #76 | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Manes, Bradley |  |  | 04-Jan-22 |  | 20-Oct-20 | 29-Jan-21
1118940 | Arthur St N & Norwich St E | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 0 | 1756.42 |  | 0 |  |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22
1157566 | 389 Speedvale Ave W – Transite - Royal Rd - Pole 5 to BK01275 | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Patenaude, Mélanie |  |  |  | 104928.47 | 76035.16 | 104928.47 | 104928.47 | Stevens, Carl |  |  | 31-Dec-21 |  | 07-Dec-20 | 10-Feb-21 |  |  |  | 0
1159146 | 353 & 355 Victoria Rd N - Transite | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Patenaude, Mélanie |  |  |  | 90090.1 | 58889.29 | 90090.1 | 90090.1 | Lauryssen, John |  |  | 31-Dec-21 |  | 02-Feb-21 | 03-Jun-21 |  |  |  | 0
1146282 | PMSG005 - 130 Stone Rd West - pad switch replacement | 840 - Southgate | 151087 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra |  |  |  | 83283.01 | 85103.73 | 83283.01 | 83283.01 | Stevens, Carl |  |  | 31-Dec-21 |  | 18-Nov-21 | 18-Nov-21 |  |  |  | 0
1146288 | PMSG031 - Edinburgh Rd S @ Terraview Cres - pad switch replacement | 840 - Southgate | 151087 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra | 19-Feb-21 |  |  | 81742.15 | 83359.52 | 81742.15 | 81742.15 | Stevens, Carl |  |  | 31-Dec-21 |  | 01-Apr-21 | 30-Apr-21 |  |  |  | 0
1152590 | 395 Edinburgh Rd N - temp | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 69945.73 | 3190.4 | 69945.73 | 69945.73 | Stevens, Carl |  |  | 01-Apr-22 |  | 14-Dec-20 | 03-Jan-22 |  |  |  | 0
1166443 | 71 Wyndham St - temp | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 85916.47 | 1308.08 | 85916.47 | 85916.47 | Stevens, Carl |  |  | 04-Jan-22 |  | 02-Nov-20 | 27-Jan-22 |  |  |  | 0
1162545 | Temp U/G Service - 166 Deerpath Dr Townhomes | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McGregor, Brendan |  |  |  | 500.72 | 500.72 | 0 | 0 | Stevens, Carl |  |  | 31-Dec-21 |  | 30-Oct-20 | 19-Mar-21 |  |  |  | 0
1171873 | Pole 91 Stevenson St N | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 380.59 | 8685.92 | 380.59 | 380.59 | Manes, Bradley |  |  | 04-Jan-22 |  | 15-Feb-21 | 15-Feb-21 |  |  |  | 0
1171984 | Temp O/H Service - 299 York Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 6174 | 0 | 6174 | 6174 | Manes, Bradley |  |  | 04-Jan-22 |  | 19-Mar-21 | 27-Jan-22 |  |  |  | 0
1146109 | 245 Hanlon Creek Blvd - Per Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McGregor, Brendan |  |  |  | 60800.01 | 32620.56 | 60800.01 | 60800.01 | Stevens, Carl |  |  | 04-Jan-22 |  | 14-Dec-20 | 10-Feb-21 |  |  |  | 0
1135276 | 140 Huron Street Townhomes | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Kingswell, Dean J |  |  |  | 183.68 | 65205.79 | 183.68 | 183.68 | Stevens, Carl |  |  | 04-Jan-22 |  | 26-Mar-21 | 22-Apr-21 |  |  |  | 0
1162819 | Queen Street - Derry St to Eramosa Rd) | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Patenaude, Mélanie |  |  |  | 1339.76 | 69441.45 | 1339.76 | 1339.76 | Lauryssen, John |  | 12-Feb-21 | 31-Dec-21 | 18-Jan-21 | 18-Jan-21 | 25-Feb-21 |  |  |  | 0
1159314 | Gladstone Avenue, Phase 2 | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric |  |  |  | 81292.69 | 83712.67 | 81292.69 | 81292.69 | Manes, Bradley |  | 18-Feb-21 | 31-Dec-21 | 18-Jan-21 | 25-Dec-20 | 23-Apr-21 |  |  |  | 0
1171912 | Pole 44 Watson Parkway South | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 11989.19 | 13410.5 | 11989.19 | 11989.19 | Manes, Bradley |  |  | 04-Jan-22 |  | 08-Jan-21 | 08-Jan-21 |  |  |  | 0
1164228 | Pole 4 Riverview Dr. | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 12715.45 | 6077.29 | 12715.45 | 12715.45 | Manes, Bradley |  |  | 04-Jan-22 |  | 08-Jan-21 | 08-Jan-21 |  |  |  | 0
1173656 | Pole 3 Sloan Ave | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 11087.48 | 8776.01 | 11087.48 | 11087.48 | Manes, Bradley |  |  | 31-Dec-21 |  | 18-Jan-21 | 09-Feb-21 |  |  |  | 0
1164227 | Pole 2 Kitchener Ave | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 6071.48 | 2459.27 | 6071.48 | 6071.48 | Manes, Bradley |  |  | 04-Jan-22 |  | 08-Jan-21 | 08-Jan-21 |  |  |  | 0
1173657 | Pole 9 Hayes Ave | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 0 | 19226.79 | 12136.7 | 12136.7 | Manes, Bradley |  |  | 04-Jan-22 |  | 18-Jan-21 | 08-Feb-21 |  |  |  | 0
1173658 | Pole 26 Windsor St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 6885.87 | 4208.62 | 6885.87 | 6885.87 | Manes, Bradley |  |  | 04-Jan-22 |  | 08-Jan-21 | 08-Jan-21 |  |  |  | 0
1173659 | Pole 18 Windsor St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 18072.1 | 20314.79 | 18072.1 | 18072.1 | Manes, Bradley |  |  | 31-Dec-21 |  | 18-Jan-21 | 03-Jun-21 |  |  |  | 0
1179568 | Pole 62 Waverly Dr | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 6259.03 | 15938.33 | 6259.03 | 6259.03 | Manes, Bradley |  |  | 04-Jan-22 |  | 08-Jan-21 | 22-Jan-21 |  |  |  | 0
1158768 | BrightonSt, Liac Pl,Sumac Pl Pole Line Rebuild | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 21-Dec-20 |  |  | 164424.48 | 122267.2 | 164424.48 | 164424.48 | Manes, Bradley |  | 22-Jan-21 | 31-Dec-21 | 18-Jan-21 | 19-Feb-21 | 23-Apr-21 |  |  |  | 0
1165997 | 65 & 75 Quarterman Road | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McGregor, Brendan |  |  |  | 158076.18 | 145930.78 | 158076.18 | 158076.18 | Stevens, Carl |  |  | 31-Dec-21 |  | 18-Dec-20 | 13-Aug-21 |  |  |  | 0
1176661 | Pole 3 Fair Road - w/o Arrow Road | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Patenaude, Mélanie |  |  |  | 25709.35 | 19556.49 | 25709.35 | 25709.35 | Manes, Bradley |  |  | 31-Dec-21 |  | 18-Jan-21 | 18-Jan-21 |  |  |  | 0
1169016 | Pole A2 Inverness Drive (N1316) & Pole 33 Balmoral Drive (N1317) | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Patenaude, Mélanie |  |  |  | 4707.83 | 0 | 4707.83 | 4707.83 | Manes, Bradley |  |  | 31-Dec-21 |  | 18-Dec-20 | 03-Jun-21 |  |  |  | 0
1181397 | Pole 132 College Ave E | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 02-Dec-20 |  |  | 6255.4 | 12105.44 | 6255.4 | 6255.4 | Manes, Bradley |  |  | 04-Jan-22 |  | 18-Jan-21 | 18-Jan-21 |  |  |  | 0
1179566 | Pole 10 Hamel Ave Dist OH | 840 - Southgate | 151089 | Inactive | 99 | COMPLETE |  |  | 2022 |  | Consultant, NBM | 02-Dec-20 |  |  | 8514.07 | 3242.97 | 11757.04 | 11757.04 | Manes, Bradley |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1180585 | Hanlon Road - Overhead Switch Replacement Poles | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 02-Dec-20 |  |  | 18587.4 | 19450 | 18587.4 | 18587.4 | Manes, Bradley |  |  | 04-Jan-22 |  | 18-Jan-21 | 18-Jan-21 |  |  |  | 0
1179565 | Pole 3 Algoma Drive | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 02-Dec-20 |  |  | 11516.09 | 12292.4 | 11516.09 | 11516.09 | Manes, Bradley |  |  | 04-Jan-22 |  | 05-Feb-21 | 05-Feb-21 |  |  |  | 0
1181670 | Hanlon Road - LIS L0181 Replacement Dist OH Poles | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 24453.43 | 16576.27 | 24453.43 | 24453.43 | Manes, Bradley |  |  | 01-Apr-22 |  | 01-Mar-22 | 01-Mar-22 |  |  |  | 0
1163908 | Lowes Road West | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 12969.09 | 53411.23 | 12969.09 | 12969.09 | Lauryssen, John |  | 29-Jan-21 | 04-Jan-22 | 28-Dec-20 | 15-Dec-20 | 25-Feb-21 |  |  |  | 0
1179567 | Pole 52 Waverly Drive | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 10172.21 | 13499.74 | 10172.21 | 10172.21 | Lauryssen, John |  |  | 04-Jan-22 |  | 11-Jan-21 | 18-Jan-21 |  |  |  | 0
1181388 | Pole R11 Dunlop Drive | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 5972.18 | 21987.3 | 5972.18 | 5972.18 | Lauryssen, John |  |  | 04-Jan-22 |  | 01-Apr-21 | 01-Apr-21 |  |  |  | 0
1158579 | Lowes Road - Subivision | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Kingswell, Dean J |  |  |  | 189348.8 | 154932.35 | 189348.8 | 189348.8 | Stevens, Carl |  |  | 04-Jan-22 |  | 05-Jul-21 | 18-Nov-21 |  |  |  | 0
1181382 | Pole 7 Duke Street | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Consultant, NBM |  |  |  | 8271.64 | 17483.39 | 11972.91 | 11972.91 | Calvin Arsenault |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1181396 | Pole 23 Dunlop Drive | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Consultant, NBM |  |  |  | 0 | 17703.29 | 7638.82 | 7638.82 | Calvin Arsenault |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1177691 | Islington Dr, Inverness Dr and Glenbrook Ave | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 297189.86 | 315020.46 | 297189.86 | 297189.86 | Lauryssen, John |  |  | 04-Jan-22 |  | 05-Feb-21 | 26-May-21 |  |  |  | 0
1182109 | Replacement of Polymer Insulators - Various Locations | 840 - Southgate | 151086 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Patenaude, Mélanie | 16-Dec-20 |  |  | 0 | 91059.03 | 79128.98 | 79128.98 | Lauryssen, John |  |  | 04-Jan-22 |  | 01-Mar-21 | 24-Dec-21 |  |  |  | 0
1177677 | Bagot St Phase 2 , Suffolk St W and Merion St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 241674.3 | 349997.08 | 241674.3 | 241674.3 | Lauryssen, John |  |  | 31-Dec-21 |  | 25-May-21 | 15-Oct-21 |  |  |  | 0
1187903 | Pole 73 Elmira Rd N - East of Independence Pl - Scadamate Switch | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE | High | DA | 2021 |  | Harrison, Eric | 04-Feb-21 |  |  | 69395.46 | 70349.29 | 69395.46 | 69395.46 | Manes, Bradley |  |  | 04-Jan-22 |  | 26-Jul-21 | 30-Jul-21 |  |  |  | 0
1182189 | Block 25 Longfellow Ave - NiMa Trails Pumping Station | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McGregor, Brendan | 04-Feb-21 |  |  | 38666.69 | 36703.12 | 38666.69 | 38666.69 | Stevens, Carl |  |  | 04-Jan-22 |  | 14-May-21 | 14-May-21 |  |  |  | 0
1161145 | Sackville St, Morris St, Harris St & Johnston St - Pole Line Rebuild | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM |  |  |  | 128808.83 | 129086.43 | 128808.83 | 128808.83 | Manes, Bradley |  |  | 31-Dec-21 |  | 01-Apr-21 | 14-May-21 |  |  |  | 0
1187911 | 332 Gosling Gardens - South Mills Condo Bldg | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McGregor, Brendan | 08-Feb-21 |  |  | 12399.18 | 11588.72 | 12399.18 | 12399.18 | Stevens, Carl |  |  | 04-Jan-22 |  | 17-Feb-21 | 17-Feb-21 |  |  |  | 0
1146289 | PMS - 52 Beaver Meadow Drive | 840 - Southgate | 151087 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra |  |  |  | 84652.96 | 83630.05 | 84652.96 | 84652.96 | Stevens, Carl |  |  | 04-Jan-22 |  | 01-Mar-21 | 16-Mar-21 |  |  |  | 0
1146285 | PMG - 110 Stone Road West | 840 - Southgate | 151087 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra | 19-Feb-21 |  |  | 83357.7 | 96137.86 | 83357.7 | 83357.7 | Stevens, Carl |  |  | 04-Jan-22 |  | 28-May-21 | 28-May-21 |  |  |  | 0
1146287 | PMS - Teal Drive | 840 - Southgate | 151087 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra |  |  |  | 81742.15 | 82720.84 | 81742.15 | 81742.15 | Stevens, Carl |  |  | 04-Jan-22 |  | 29-Mar-21 | 31-Mar-21 |  |  |  | 0
1188012 | Pole 23 Mackenzie Street | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 04-Mar-21 |  |  | 5622.74 | 6514.42 | 5622.74 | 5622.74 | Manes, Bradley |  |  | 04-Jan-22 |  | 22-Mar-21 | 26-Mar-21 |  |  |  | 0
1188014 | pole 6 Hanlon Road | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 04-Mar-21 |  |  | 13283.03 | 11111.65 | 13283.03 | 13283.03 | Manes, Bradley |  |  | 31-Dec-21 |  | 30-Apr-21 | 30-Apr-21 |  |  |  | 0
1184336 | 27 Crestwood Place | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Dyce, Stephen A | 16-Mar-21 |  |  | 3147.99 | 1853.19 | 3147.99 | 3147.99 | Stevens, Carl |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1177661 | Bagot St Phase 1, London Rd W and Mercer St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 14-Jan-21 |  |  | 271420 | 286882.2 | 271420 | 271420 | Lauryssen, John |  |  | 04-Jan-22 | 16-Feb-21 | 18-Jan-21 | 25-May-21 |  |  |  | 0
1152570 | Beechwood Ave - North of Waterloo Ave - Customer Capital Work | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 18-Mar-21 |  |  | 8025.75 | 17432.45 | 8025.75 | 8025.75 | Stevens, Carl |  |  | 31-Dec-21 |  | 12-Apr-21 | 23-Apr-21 |  |  |  | 0
1190839 | Third Party Transfer - Rogers - 73 Elmira Road North | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 27-May-21 |  |  | 5167.18 | 2612.1 | 5167.18 | 5167.18 | Manes, Bradley |  | 31-May-21 | 04-Jan-22 | 31-May-21 | 25-Jun-21 | 25-Jun-21 |  |  |  | 0
646228 | P-Pasmore Street and Clara Street, Rockwood | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Chris McDonald | 06-Aug-21 | 12 | 12 | 94445.41 | 178842.75 | 94445.41 | 94445.41 | Manes, Bradley | Drexler | 08-Jun-22 | 31-Jul-23 | 30-May-22 | 08-Aug-22 | 12-Dec-22 | N/A | Contractor |  | 0
645981 | P-NIMA TRAILS, PHASE 1C SUBDIVISION (COILS) | 840 - Southgate | 151696 | Active | 40 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
1193314 | P-Algoma Drive (off Monana Road) | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 26-Aug-21 |  |  | 144689 | 162764.04 | 144689 | 144689 | Lauryssen, John |  | 31-Aug-21 | 04-Jan-22 | 19-Jul-21 | 04-Oct-21 | 29-Nov-21 |  |  |  | 0
1193333 | P-Riverview Drive and Wolseley Road | 840 - Southgate | 151089 | Inactive | 99 | COMPLETE |  |  | 2022 |  | Consultant, NBM | 16-Aug-21 |  |  | 170346.64 | 1035.04 | 170346.64 | 170346.64 | Manes, Bradley |  |  | 01-Apr-22 |  | 08-Nov-21 |  |  |  |  | 0
1193519 | P-601 /ekmira Road North/GUE/NS/1Ph UG SEC SERVICE | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 13-Aug-21 |  |  | 5931.11 | 6785.44 | 5931.11 | 5931.11 | Stevens, Carl |  |  | 31-Dec-21 |  | 04-Oct-21 | 04-Oct-21 |  |  |  | 0
645983 | P-DOWLER STREET DEVELOPMENT - ROCKWOOD | 840 - Southgate | 151696 | Active | 70 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
646229 | P-675 Victoria Road North Townhomes | 840 - Southgate | 151696 | Active | 91 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J | 28-May-21 |  |  | 171974.38 | 209357.2 | 171974.38 | 171974.38 | Stevens, Carl | Drexler | 28-May-21 | 26-Jul-23 | 28-May-21 | 23-Aug-21 |  | Customer | Customer |  | 0
1193004 | 990 York Road | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Danieli, Andrea | 08-Apr-21 |  |  | 0 | 11449.33 | 4373.64 | 4373.64 | Stevens, Carl |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1193576 | 576 Woolwich Street | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 29-Apr-22
645982 | P-1882 GORDON STREET/GUE/NS/3 PH PAD | 840 - Southgate | 151551 | Active | HO | RELEASED |  |  | 2023 | McAlpine, Robert | McGregor, Brendan | 04-Jul-22 |  |  | 124160.63 | 8258.62 | 124160.63 | 124160.63 | Stevens, Carl |  | 20-Jun-23 | 16-Aug-23 | 31-May-23 |  |  | Customer | Customer |  | 0
1193782 | 18 Industrial Street/GUE/NS/3PH SEC SERVICE | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Danieli, Andrea |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 29-Apr-22
1175332 | 1 Wilbert Street - Temp O/H Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 2228 | 0 | 2228 | 2228 | Manes, Bradley |  |  | 01-Apr-22 |  | 19-Mar-21 | 03-Jan-22 |  |  |  | 0
646223 | Silvercreek Parkway North at Curtis Drive - OH primary H1 crossing installation - | 840 - Southgate | 151453 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra | 08-Sep-21 |  |  | 35517.43 | 25705.68 | 35517.43 | 35517.43 | Lauryssen, John |  | 26-Mar-21 | 08-Mar-23 | 26-Mar-21 | 06-Dec-21 | 02-Dec-22 | Customer | Customer |  | 0
1159210 | Ptarmigan Drive and Merganser Drive | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra | 26-Mar-21 |  |  | 25636.84 | 33079.52 | 25636.84 | 25636.84 | Stevens, Carl |  | 26-Mar-21 | 04-Jan-22 | 26-Mar-21 | 03-Sep-21 | 03-Sep-21 |  |  |  | 0
1155218 | Norwich Street Pedestrian Bridge - Line Isolation | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McGregor, Brendan | 26-Mar-21 |  |  | 9500 | 5637.75 | 9500 | 9500 | Manes, Bradley |  | 26-Mar-21 | 04-Jan-22 | 26-Mar-21 | 28-May-21 | 28-May-21 |  |  |  | 0
1182711 | Montana Road - J0356Y Switch Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 01-Apr-21 |  |  | 16452.97 | 13540.78 | 16452.97 | 16452.97 | Lauryssen, John |  |  | 04-Jan-22 | 01-Apr-21 | 11-Jun-21 | 11-Jun-21 |  |  |  | 0
1182716 | Pleasant Rd - J0382R Switch Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 01-Apr-21 |  |  | 16452.97 | 15186.74 | 16452.97 | 16452.97 | Lauryssen, John |  |  | 31-Dec-21 |  | 14-Jun-21 | 14-Jun-21 |  |  |  | 0
1184255 | 415 Elizabeth Street | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Dyce, Stephen A | 01-Apr-21 |  |  | 15766.15 | 20283.99 | 15766.15 | 15766.15 | Stevens, Carl |  |  | 04-Jan-22 |  | 22-Apr-21 | 22-Apr-21 |  |  |  | 0
1175473 | 117 Guelph Street, Rockwood | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan | 01-Apr-21 |  |  | 16597.65 | 2340.95 | 16597.65 | 16597.65 | Stevens, Carl |  |  | 01-Apr-22 |  | 22-Apr-21 | 04-Feb-22 |  |  |  | 0
1196263 | Pole 15 Arthur St S - anchor relocation only - customer capital work | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 28-May-21 | 1 |  | 3990.4 | 4385.81 | 3990.4 | 3990.4 | Manes, Bradley |  | 28-May-21 | 04-Jan-22 | 28-May-21 | 20-Aug-21 | 20-Aug-21 |  |  |  | 0
1168011 | Arthur Street North (from Palmer St to Rose St) & New St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 08-Apr-21 |  |  | 214021.51 | 277817.62 | 214021.51 | 214021.51 | Lauryssen, John |  |  | 31-Dec-21 |  | 16-Jun-21 | 08-Oct-21 |  |  |  | 0
1188015 | Pole 12 Dennis St, Rockwood | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 08-Apr-21 |  |  | 11537.12 | 15983.81 | 11537.12 | 11537.12 | Manes, Bradley |  |  | 31-Dec-21 |  | 18-Oct-21 | 18-Oct-21 |  |  |  | 0
1188019 | Pole 1 Bridge Street, Roockwood | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 08-Apr-21 |  |  | 7245.14 | 7775.39 | 7245.14 | 7245.14 | Manes, Bradley |  |  | 04-Jan-22 |  | 23-Aug-21 | 26-Aug-21 |  |  |  | 0
1195678 | P-100 Victoria Road South / GUE / NS | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Danieli, Andrea | 04-Jun-21 |  |  | 370.5 | 0 | 11134 | 11134 | Stevens, Carl |  | 04-Jun-21 | 01-Apr-22 | 04-Jun-21 | 04-Oct-21 |  |  |  |  | 0
1196115 | P-27 Vanier Drive / GUE / NS / 1PH UG Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Consultant, NBM |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
1182717 | Western Avenue - 0253R Switch Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 16-Apr-21 |  |  | 16452.97 | 15343.59 | 16452.97 | 16452.97 | Lauryssen, John |  |  | 31-Dec-21 |  | 15-Jun-21 | 15-Jun-21 |  |  |  | 0
1187356 | 49 Rhonda Road Townhome Rehab | 840 - Southgate | 151371 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 16-Apr-21 |  |  | 583504.65 | 660013.44 | 583504.65 | 583504.65 | Stevens, Carl |  |  | 04-Jan-22 |  | 10-May-21 | 06-Dec-21 |  |  |  | 0
1183092 | Metcalfe Street - 0272Y Switch Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 16-Apr-21 |  |  | 23363.21 | 21481.9 | 23363.21 | 23363.21 | Lauryssen, John |  |  | 04-Jan-22 |  | 21-Jun-21 | 23-Jul-21 |  |  |  | 0
1196963 | P-207 Metcalfe Street / GUE / UP / 1PH Pole Mounted Tranformer | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 07-May-21 |  |  | 4376.45 | 2468.95 | 4376.45 | 4376.45 | Manes, Bradley |  | 07-May-21 | 04-Jan-22 | 07-May-21 | 08-Oct-21 | 08-Oct-21 |  |  |  | 0
646230 | P-455 Watson Parkway North / GUE / NS | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2022 | McGregor, Brendan | Dyce, Stephen A | 19-Nov-21 |  |  | 99076.28 | 77555.76 | 99076.28 | 99076.28 | Stevens, Carl |  | 14-Jan-22 | 26-Jul-23 | 10-Jan-22 | 03-Jan-22 | 31-Dec-21 |  |  |  | 0
646227 | Queen St (548) - Eramosa Rd to Grange St | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | South-West | 13-Sep-21 | 15 | 15 | 120793.59 | 157549.88 | 120793.59 | 120793.59 | Lauryssen, John |  | 28-Mar-22 | 26-Jul-23 | 10-Jan-22 | 03-Jan-22 | 17-Mar-22 |  |  |  | 0
1186556 | 50 Golds Court | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 22-Apr-21 |  |  | 87550 | 111787.26 | 87550 | 87550 | Stevens, Carl |  |  | 31-Dec-21 | 29-Apr-21 | 04-Oct-21 | 01-Nov-21 |  |  |  | 0
1186551 | 350 Hanlon Creek Boulevard | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 22-Apr-21 |  |  | 64397.5 | 16972.88 | 64397.5 | 64397.5 | Stevens, Carl |  |  | 04-Jan-22 | 29-Apr-21 | 01-Nov-21 | 18-Nov-21 |  |  |  | 0
1189028 | Forest Street - LIS L0850 Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 22-Apr-21 |  |  | 78661.94 | 104588.26 | 78661.94 | 78661.94 | Lauryssen, John |  |  | 31-Dec-21 | 29-Apr-21 | 30-Jul-21 | 30-Jul-21 |  |  |  | 0
1183098 | Highview Place - 0336B Switch Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 22-Apr-21 |  |  | 20858.57 | 18278.91 | 20858.57 | 20858.57 | Lauryssen, John |  |  | 31-Dec-21 | 29-Apr-21 | 21-Jun-21 | 21-Jun-21 |  |  |  | 0
1194148 | 65 Lemon St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 30-Apr-21 |  |  | 6000 | 4867.24 | 6000 | 6000 | Stevens, Carl |  | 03-May-21 | 31-Dec-21 | 03-May-21 | 04-Oct-21 | 04-Oct-21 |  |  |  | 0
1187448 | 1533 Gordon Street | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan | 07-May-21 |  |  | 0 | 24198.86 |  | 0 | Stevens, Carl |  | 07-May-21 | 01-Apr-22 | 07-May-21 | 10-Jan-22 | 10-Jan-22
1183101 | Ridgewood Ave - 0254B Switch Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 07-May-21 |  |  | 0 | 26178.12 |  | 0 | Lauryssen, John |  | 07-May-21 | 04-Jan-22 | 07-May-21 | 18-Oct-21 | 18-Oct-21
1183103 | Glenburnie Drive - 0317Y Switch Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 07-May-21 |  |  | 0 | 26197.41 |  | 0 | Lauryssen, John |  | 07-May-21 | 31-Dec-21 | 07-May-21 | 10-Sep-21 | 10-Sep-21
1183104 | Kerr Street - 0347R Switch Replacement | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 07-May-21 |  |  | 0 | 23811.16 |  | 0 | Lauryssen, John |  | 07-May-21 | 31-Dec-21 | 07-May-21 | 14-Jul-21 | 14-Jul-21
1197821 | P-27 Norwich Street East / GUE / NS / 1PH UG SEC SERVICE | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max |  |  |  | 11833.2 | 10717.91 | 11833.2 | 11833.2 | Stevens, Carl |  | 25-Oct-21 | 31-Dec-21 | 25-Oct-21 | 01-Nov-21 | 01-Nov-21 |  |  |  | 0
1198393 | P-505 Kortright Road West / GUE / NS | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Joshi, Namrata | 12-Aug-21 |  |  | 2210 | 5754.91 | 2210 | 2210 | Stevens, Carl |  | 16-Aug-21 | 29-Apr-22 | 16-Aug-21 | [5 empty] | 0
1198394 | P-505 Kortright Road West / GUE /NS | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Joshi, Namrata |  |  |  | 2259.85 | 0 | 2259.85 | 2259.85 | Stevens, Carl |  |  | 27-May-22 |  | 03-Jan-22 | 31-Dec-21 |  |  |  | 0
1198303 | P-Temp OH Service - 15 Harcourt Dr / GUE / NS / 1PH OH TEMP SEC SERVICE | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 03-Jan-22 | 31-Dec-21
645991 | Pole A60 York Road (West of Waterworks Place) | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1199111 | Harts Lane West (off Gordon Street) | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 14-May-21 |  |  | 9553 | 17690 | 9553 | 9553 | Lauryssen, John |  |  | 31-Dec-21 |  | 15-Jul-21 | 09-Sep-21 |  |  |  | 0
1199375 | P-Pole 308 Edinburgh Rd S | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 21-May-21 | 1 |  | 4544 | 6370 | 4544 | 4544 | Manes, Bradley |  | 31-May-21 | 31-Dec-21 | 31-May-21 | 01-Jun-21 | 01-Jun-21 |  |  |  | 0
1199395 | P-Pole 121 College Ave | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 12-Aug-21 |  |  | 14999.62 | 10221 | 14999.62 | 14999.62 | Manes, Bradley |  | 06-Sep-21 | 31-Dec-21 | 06-Sep-21 | 13-Sep-21 | 13-Sep-21 |  |  |  | 0
645992 | P-151 CITYVIEW DR N/GUE/NS/1PH UG SERVICES | 840 - Southgate | 151550 | Active | 84 | ACTIVE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 17-Mar-23 |  |  | 9947.44 | 9551.19 | 9947.44 | 9947.44 | Stevens, Carl | Drexler | 01-May-23 | 26-Jul-23 | 01-May-23 | 02-Jun-23 |  | Customer | Customer |  | 0
646231 | 8 RYDE RD/GUE/UP | 840 - Southgate | 151551 | Active | 91 | ACTIVE |  |  | 2023 | McAlpine, Robert | McGregor, Brendan | 04-Nov-21 |  |  | 130019.54 | 157798.02 | 130019.54 | 130019.54 | Stevens, Carl |  | 30-Jun-22 | 26-Jul-23 | 30-Jun-22 | 13-Mar-23 |  | MC/PUCC Permit | MC/PUCC Permit |  | 0
1200968 | P-82 Creighton Ave/GUE/NS/1PH UG SEC Relocation | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 27-May-21 |  |  | 1286 | 2059 | 1286 | 1286 | Stevens, Carl |  | 31-May-21 | 31-Dec-21 | 31-May-21 | 09-Jun-21 | 09-Jun-21 |  |  |  | 0
645993 | P-120 HURON ST / GUE / NS | 840 - Southgate | 151551 | Active | 96 | COMPLETE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 19-Jul-22 |  |  | 83797.03 | 67579.45 | 83797.03 | 83797.03 | Stevens, Carl | Drexler | 14-Sep-22 | 01-Aug-23 | 06-Sep-22 | 08-Feb-23 | 08-Feb-23 | Customer | Customer |  | 0
1201533 | P-120 Gzowski St / ROC / NS / 1PH UG Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 06-Aug-21 |  |  | 3183.37 | 1500 | 3183.37 | 3183.37 | Stevens, Carl |  | 13-Aug-21 | 31-Dec-21 | 06-Aug-21 | 04-Oct-21 | 04-Oct-21 |  |  |  | 0
1201695 | 41 Richardson St / GUE / UP / 1PH Polemounted TX Upgrade | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max | 28-May-21 | 1 |  | 1868 | 0 | 1868 | 1868 | Manes, Bradley |  | 28-May-21 | 29-Apr-22 | 28-May-21 | [5 empty] | 0
1190278 | Pole 4 Heather Ave | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 21-May-21 | 1 |  | 10166.47 | 6310.84 | 10166.47 | 10166.47 | Manes, Bradley |  | 31-May-21 | 31-Dec-21 | 31-May-21 | 01-Jun-21 | 01-Jun-21 |  |  |  | 0
1194611 | Governors Rd & Malcolm Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 21-May-21 | 2 |  | 21385.51 | 27470.51 | 21385.51 | 21385.51 | Lauryssen, John |  | 01-Jul-21 | 31-Dec-21 | 14-Jun-21 | 09-Aug-21 | 20-Aug-21 |  |  |  | 0
646232 | P-Maple St (from Forest St to L0199) | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Chris McDonald | 13-Aug-21 | 5 | 5 | 45706.17 | 194283.11 | 45706.17 | 45706.17 | Lauryssen, John |  | 28-Mar-22 | 26-Jul-23 | 10-Jan-22 | 13-Jan-22 | 28-Mar-22 |  |  |  | 0
1202625 | P-Temp OH Service - 10 Winston Cres/GUE/NS/1PH SEC Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 03-Jan-22 | 31-Dec-21
1202771 | P-Golfview Rd - 0293B Switch Replacement Project | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric | 04-Jun-21 |  |  | 22401 | 16033 | 22401 | 22401 | Lauryssen, John |  | 04-Jun-21 | 31-Dec-21 | 04-Jun-21 | 30-Jul-21 | 30-Jul-21 |  |  |  | 0
646000 | HIGHWAY 6 WIDENING (GUELPH CURLING CLUB) | 840 - Southgate | 152405 | Active | 82 | RELEASED | Medium | Res-ICI | 2023 | Jakubowski, Mark | Chris McDonald | 22-Jun-23 |  |  | 840231.03 | 40511.46 | 840231.03 | 840231.03 | Stevens, Carl | Drexler | 10-Oct-23 | 10-Oct-23 | 17-Jul-23 | [5 empty] | 0
1203593 | P-Pole 94 Downey Road | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | South-West |  |  |  | 6059.48 | 3280 | 6059.48 | 6059.48 | Manes, Bradley |  |  | 31-Dec-21 |  | 05-Aug-21 | 05-Aug-21 |  |  |  | 0
646002 | P-Pole 84 Stone Rd W | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1204023 | P-Nima Trails Blk 122 - Shakespeare Dr / GUE / NS | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | Joshi, Namrata |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
1203921 | Ironwood Rd 311 - BK0203 TX Replacement | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra | 11-Jun-21 | 1 |  | 6843.54 | 5311 | 6843.54 | 6843.54 | Stevens, Carl |  | 09-Aug-21 | 04-Jan-22 | 09-Aug-21 | 19-Nov-21 | 19-Nov-21 |  |  |  | 0
1204022 | Ptarmigan Dr 60 Unit 8 - BK04730 TX Replacement | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra | 11-Jun-21 | 1 |  | 6843.54 | 6694.59 | 6843.54 | 6843.54 | Stevens, Carl |  | 10-Aug-21 | 04-Jan-22 | 10-Aug-21 | 19-Nov-21 | 19-Nov-21 |  |  |  | 0
1203952 | P-188 Niska Rd / GUE / NS / 1PH UG Secondary Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 18-Jun-21 |  |  | 2999.96 | 287.48 | 2999.96 | 2999.96 | Stevens, Carl |  | 28-Jun-21 | 01-Apr-22 | 14-Jun-21 | [5 empty] | 0
1203959 | P-523 Kortright Rd W / GUE / NS / 1PH Sec Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 18-Jun-21 |  |  | 1773.72 | 0 | 1773.72 | 1773.72 | Stevens, Carl |  | 28-Jun-21 | 27-May-22 | 21-Jun-21 | 30-Nov-21 | 30-Nov-21 |  |  |  | 0
1184128 | 25 Wellington St W | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Dyce, Stephen A |  |  |  | 51195.17 | 10943.58 | 51195.17 | 51195.17 | Stevens, Carl |  |  | 31-Dec-21 |  | 14-Jun-21 | 13-Aug-21 |  |  |  | 0
646003 | 101 COOPER DRIVE / GUE / NS | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McAlpine, Robert | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1205068 | P-Gryphon Place Cable Replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | Harrison, Eric |  |  |  | 0 | 29569.77 |  | 0 | Stevens, Carl |  |  | 31-Dec-21 |  | 04-Oct-21 | 04-Oct-21
646233 | 152 Arthur St S - Service Conflict | 840 - Southgate | 151051 | Active | 95 | COMPLETE |  |  | 2023 | Jakubowski, Mark | South-West | 04-Jun-21 |  |  | 0 | 2398.7 |  | 0 | Manes, Bradley |  | 30-May-22 | 26-Jul-23 | 30-May-22 | 31-Dec-22 | 31-Dec-22 | Customer | Customer
1205333 | P-1657 Gordon St / GUE / NS / 1PH SEC Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 1983.12 | 0 | 1983.12 | 1983.12 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 03-Jan-22 | 31-Dec-21 |  |  |  | 0
1205160 | Stevenson St. N.- Pole Hold | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  |  | 27-May-22 |  | 03-Jan-22 | 31-Dec-21
1205239 | P-Temp OH Service - 54 Phelan Crt / GUE / NS / OH Temp | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan | 06-Aug-21 |  |  | 4851.65 | 0 | 4851.65 | 4851.65 | Manes, Bradley |  |  | 01-Apr-22 |  | 16-Aug-21 | 03-Jan-22 |  |  |  | 0
1205242 | P-Temp OH Service - 100 Victoria Rd S / GUE / NS / OH Temp | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 03-Jan-22 | 31-Dec-21
1204762 | P-171 Lou's Blvd Rockwood - BK80294 TX Replacement | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra | 24-Jun-21 | 1 |  | 6179 | 5550.44 | 6179 | 6179 | Stevens, Carl |  | 26-Jul-21 | 04-Jan-22 | 28-Jun-21 | 29-Nov-21 | 10-Dec-21 |  |  |  | 0
1187673 | 87 Cassino Ave | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Harrison, Eric |  |  |  | 7125.65 | 3778.85 | 7125.65 | 7125.65 | Calvin Arsenault |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
645966 | P-55 TEAL DRIVE TOWNHOMES | 840 - Southgate | 151696 | Active | 50 | ACTIVE |  |  | 2023 | Velickovski, Goran | South-West |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
646225 | 131 Malcolm Road - New CEVA Bld - New U/G Service | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2022 | McGregor, Brendan | Dyce, Stephen A | 18-Jun-21 |  |  | 81928 | 89358.21 | 81928 | 81928 | Stevens, Carl |  | 21-Jun-21 | 26-Jul-23 | 14-Jun-21 | 10-Jan-22 | 10-Jan-22 |  | Customer |  | 0
1205793 | P-25 Poppy Dr / GUE / UP | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Joshi, Namrata | 27-Jan-22 |  |  | 13357.78 | ($14,632.18) | 13357.78 | 13357.78 | Stevens, Carl |  | 18-Mar-22 | 01-Apr-22 | 07-Mar-22 | 11-Feb-22 | 11-Feb-22 |  |  |  | 0
646234 | 396-398 Silvercreek Pkwy N / GUE / UP | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2022 | McAlpine, Robert | Dyce, Stephen A | 22-Oct-21 |  |  | 63584.93 | 52489.21 | 63584.93 | 63584.93 | Stevens, Carl |  | 08-Nov-21 | 26-Jul-23 | 25-Oct-21 | 04-Feb-22 | 13-May-22 |  | N/A |  | 0
1205794 | 1219 Edinburgh Rd S-Resupply Rogers Box from Secondary Bus | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McGregor, Brendan | 17-Aug-21 |  |  | 6170.6 | 0 | 6170.6 | 6170.6 | Lauryssen, John |  |  | 01-Apr-22 |  | 13-Dec-21 | 13-Dec-21 |  |  |  | 0
646235 | P-Dawson Rd - SCADAMate R0155 | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE | High | Switch | 2022 | Bolton, Ian J | Harrison, Eric | 02-Dec-21 | 1 | 1 | 68274.89 | 75587.57 | 68274.89 | 68274.89 | Lauryssen, John |  | 03-Jun-22 | 13-Mar-23 | 30-May-22 | 20-Jul-22 | 26-Jul-22 | Locates | Locates |  | 0
1205876 | P-24 Corporate Crt-PMSG024 Replacement | 840 - Southgate | 151087 | Inactive | 99 | COMPLETE |  |  | 2022 |  | Jamkodjian, Cassandra | 16-Dec-21 | 2 | 2 | 85124.09 | 97979.53 | 85124.09 | 85124.09 | Stevens, Carl |  | 18-Mar-22 | 01-Apr-22 | 14-Mar-22 | 31-Jan-22 | 31-Jan-22 |  |  |  | 0
1205880 | P-44 Corporate Crt-PMSG025 Replacement | 840 - Southgate | 151087 | Inactive | 99 | COMPLETE |  |  | 2022 |  | Jamkodjian, Cassandra | 16-Dec-21 | 2 | 2 | 88807.7 | 104272.7 | 88807.7 | 88807.7 | Stevens, Carl |  | 11-Mar-22 | 01-Apr-22 | 28-Feb-22 | 31-Jan-22 | 31-Jan-22 |  |  |  | 0
1206278 | P-145 Speedvale Ave W/GUE/UP | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | Joshi, Namrata |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
1206187 | Main St N, Rockwood | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Jamkodjian, Cassandra |  |  |  | 0 | 10187.07 |  | 0 | Calvin Arsenault |  |  | 04-Jan-22 |  | 27-Jan-22 | 27-Jan-22
646004 | P-Woodlawn Rd W Reconstruction | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1206587 | P-Dormie Lane to Pole R23 | 840 - Southgate | 151089 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian | Consultant, NBM | 21-Sep-21 | 22 | 22 | 175324.78 | 206067.39 | 175324.78 | 175324.78 | Lauryssen, John |  | 28-Mar-22 | 27-May-22 | 10-Jan-22 | 29-Nov-21 | 28-Mar-22 |  |  |  | 0
1206827 | P-6 Mayfield Ave/GUE/UP/1 PH UG Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 06-Aug-21 |  |  | 6068.34 | 4741.56 | 6068.34 | 6068.34 | Stevens, Carl |  | 27-Aug-21 | 04-Jan-22 | 27-Aug-21 | 04-Oct-21 | 04-Oct-21 |  |  |  | 0
1206826 | Arthur St S and Elizabeth St/GUE/NS/1PH Sec Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 1815.71 | 0 | 1815.71 | 1815.71 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 03-Jan-22 | 31-Dec-21 |  |  |  | 0
646005 | P-Pole 13 Cambridge St | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1207371 | P-Pole 12 Powell St W | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 26-Aug-21 | 1 |  | 0 | 17135.79 |  | 0 | Manes, Bradley |  | 31-Aug-21 | 31-Dec-21 | 31-Aug-21 | 15-Oct-21 | 15-Oct-21
1207266 | York Rd.- Pole Hold | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
1208145 | P-Lowes Rd Pole 11 | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | South-West |  |  |  | 275 | 2809.51 | 275 | 275 | Manes, Bradley |  |  | 31-Dec-21 |  | 28-Jun-21 | 28-Jul-21 |  |  |  | 0
1208535 | 101 Cooper Drive Temp / GUE / NS | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McGregor, Brendan | 28-Oct-21 |  |  | 43838.39 | 0 | 43838.39 | 43838.39 | Manes, Bradley |  | 29-Nov-21 | 01-Apr-22 | 29-Nov-21 | 31-Dec-21 | 31-Dec-21 |  |  |  | 0
646006 | POLE 69 SOUTHGATE DR | 840 - Southgate | 151089 | Active | 92 | ANALYZE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 23-Sep-22 | 1 | 1 | 40308.98 | 25319.97 | 40308.98 | 40308.98 | Manes, Bradley |  | 25-Nov-22 | 26-Jul-23 | 24-Nov-22 | 09-Jun-23 | 09-Jun-23 | Materials | Materials |  | 0
1208975 | P-Pole 8 Maltby Rd E | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | South-West |  |  |  | 6061.87 | 8100.58 | 6061.87 | 6061.87 | Manes, Bradley |  |  | 31-Dec-21 |  | 06-Aug-21 | 06-Aug-21 |  |  |  | 0
1208982 | P-Pole 111 Victoria Rd S | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | South-West | 28-Jul-21 |  |  | 6331.87 | 6128.94 | 6331.87 | 6331.87 | Manes, Bradley |  | 28-Jul-21 | 31-Dec-21 | 28-Jul-21 | 19-Aug-21 | 20-Aug-21 |  |  |  | 0
646007 | POLE 29 MAPLE ST | 840 - Southgate | 151089 | Active | 82 | PDG SnR |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 12-Jun-23 | 1 |  | 18406.48 | 0 | 18406.48 | 18406.48 | Manes, Bradley |  | 03-Nov-23 | 03-Nov-22 | 01-Nov-23 | [5 empty] | 0
646236 | P-Pole 9 Manor Park Cres | 840 - Southgate | 151247 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | South-West | 28-Feb-22 | 1 | 1 | 17078 | 20823.58 | 17078 | 17078 | Manes, Bradley |  | 01-Jun-22 | 26-Jul-23 | 30-May-22 | 20-Jun-22 | 27-Jun-22 | Customer | Customer |  | 0
646008 | P-Pole 110 Hanlon Rd | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
646226 | 54 Phelan Court - Commercial Servicing | 840 - Southgate | 151551 | Inactive | 99 | COMPLETE |  |  | 2022 | McGregor, Brendan | McGregor, Brendan | 29-Jul-21 |  |  | 83153.62 | 85203.39 | 83153.62 | 83153.62 | Stevens, Carl |  | 28-Jul-21 | 19-Jun-23 | 28-Jul-21 | 04-Oct-21 | 28-Apr-22 |  |  |  | 0
1180645 | 2 Worton Avenue | 840 - Southgate | 151371 | Inactive | 99 | COMPLETE |  |  | 2021 |  | South-West |  |  |  | 164744.1 | 211447.01 | 164744.1 | 164744.1 | Stevens, Carl |  |  | 04-Jan-22 | 01-Sep-21 | 07-Sep-21 | 15-Oct-21 |  |  |  | 0
645972 | P-NIMA TRAILS, PHASE 1C SUBDIVISION | 840 - Southgate | 151696 | Active | 40 | ACTIVE |  |  | 2023 | Velickovski, Goran | South-West |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
1209366 | P-70 Division St - BK01431 Replacement | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra | 26-Aug-21 | 1 |  | 83412.39 | 84397.53 | 83412.39 | 83412.39 | Stevens, Carl |  | 04-Oct-21 | 04-Jan-22 | 04-Oct-21 | 01-Nov-21 | 31-Dec-21 |  |  |  | 0
646010 | P-Arthur St & Elizabeth St - Pole Removal | 840 - Southgate | 151052 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
1211397 | P-370 Stone Rd W/GUE/UP | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Dyce, Stephen A | 06-Oct-21 |  |  | 0 | 0 | 0 | 0 | Stevens, Carl |  | 06-Oct-21 | 04-Jan-22 | 06-Oct-21 | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1211706 | 313 Metcalfe St/GUE/UP/1ph TX Upgrade | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West | 06-Aug-21 |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  | 10-Sep-21 | 04-Jan-22 | 10-Sep-21 | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1211855 | 7 Stevenson St N/GUE/NS/1 PH UG Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 12-Aug-21 |  |  | 1559.14 | 339.82 | 1559.14 | 1559.14 | Stevens, Carl |  | 16-Aug-21 | 04-Jan-22 | 16-Aug-21 | 18-Nov-21 | 27-Jan-22 |  |  |  | 0
646013 | P-755 Stone Rd E/GUE/NS-Site Servicing | 840 - Southgate | 151551 | Inactive | 99 | CANCELLED |  |  | 2022 | McAlpine, Robert | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646014 | BAKER ST &CHAPEL LN REDEVELOPMENT | 840 - Southgate | 151052 | Active | 84 | ACTIVE |  | Comm | 2023 | Jakubowski, Mark | Fisher, Cody | 25-Aug-22 |  |  | 444433.35 | 350809.71 | 444433.35 | 444433.35 | Lauryssen, John | Drexler | 29-Nov-22 | 22-Sep-23 | 19-Sep-22 | 26-Sep-22 |  | Materials | Materials |  | 0
646015 | P-Metcalfe St Reconstruction | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646237 | P-York Rd Reconstruction | 840 - Southgate | 151089 | Active | 94 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 06-Jan-22 | 5 | 5 | 134750.5 | 228004 | 99682.75 | 134750.5 | Lauryssen, John |  | 17-Apr-23 | 28-Jul-23 | 03-Apr-23 | 05-Dec-22 | 28-Mar-23 | N/A |  |  | 35,067.75
646239 | P-Hayes Ave (South of York Rd) | 840 - Southgate | 151089 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Chris McDonald | 22-Dec-21 | 8 | 8 | 88276.01 | 121172.48 | 88276.01 | 88276.01 | Lauryssen, John |  | 13-Jun-22 | 15-Mar-23 | 30-May-22 | 13-Sep-22 | 31-Oct-22 | N/A |  |  | 0
646240 | P-Woodlawn Rd E Reconstruction | 840 - Southgate | 151089 | Active | 94 | ANALYZE |  |  | 2023 | Beaudrie, Scott | South-West | 27-Jan-22 | 15 | 15 | 169401.46 | 223288.15 | 169401.46 | 169401.46 | Lauryssen, John |  | 16-Jun-22 | 28-Jul-23 | 30-May-22 | 20-Jun-22 | 12-May-23 | Locates | Locates |  | 0
646241 | P-Glenhill Pl Rebuild | 840 - Southgate | 151089 | Active | 94 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 09-Dec-21 | 14 | 14 | 88338.72 | 136456.88 | 88338.72 | 88338.72 | Manes, Bradley |  | 02-Feb-23 | 21-Aug-23 | 09-Jan-23 | 13-Mar-23 | 04-Apr-23 | N/A | N/A |  | 0
1169159 | 425 Watson Pky N | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Dyce, Stephen A |  |  |  | 47100.83 | 30648.95 | 52210.86 | 52210.86 | Calvin Arsenault |  |  | 29-Apr-22 | [6 empty] | 0
646242 | P-1 Mont St/GUE/NS | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2022 | McAlpine, Robert | South-West | 02-Dec-21 |  |  | 39904.1 | 42556.68 | 39904.1 | 39904.1 | Stevens, Carl |  | 30-Jun-22 | 26-Jul-23 | 30-Jun-22 | 19-May-22 | 19-May-22 |  |  |  | 0
1213536 | P-Pole 86 Waverley Dr | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Consultant, NBM | 26-Aug-21 | 1 |  | 8887.67 | 13915.15 | 8887.67 | 8887.67 | Manes, Bradley |  | 31-Aug-21 | 04-Jan-22 | 31-Aug-21 | 15-Oct-21 | 15-Oct-21 |  |  |  | 0
1213533 | 68 Cheltonwood Ave/GUE/UP/1 PH TX Upgrade | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 26-Aug-21 |  |  | 3623.91 | 7385.98 | 3623.91 | 3623.91 | Stevens, Carl |  | 30-Aug-21 | 04-Jan-22 | 30-Aug-21 | 14-Sep-21 | 14-Sep-21 |  |  |  | 0
1214061 | P-165 Emma St/GUE/UP/1 PH Service Upgrade | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
646243 | P-In Front of 110 Municipal St - UD558 Vault Replacement | 840 - Southgate | 151453 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Patenaude, Mélanie | 29-Sep-21 | 1 | 1 | 5945 | 11012.84 | 5945 | 5945 | Stevens, Carl |  | 30-Jun-22 | 26-Jul-23 | 30-Jun-22 | 13-Jul-22 | 18-Jul-22 | Customer | Customer |  | 0
1214056 | P-In Front of 28 Crane St - UD284 Vault Replacement | 840 - Southgate | 151222 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Patenaude, Mélanie | 29-Sep-21 | 1 | 1 | 31158 | 46973.3 | 31158 | 31158 | Stevens, Carl |  | 06-Oct-21 | 04-Jan-22 | 06-Oct-21 | 01-Nov-21 | 19-Nov-21 |  |  |  | 0
646244 | P-In Front of 150 Woolwich St- UD169 Vault Replacement | 840 - Southgate | 151453 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Patenaude, Mélanie | 29-Sep-21 | 1 | 1 | 8993 | 10642.33 | 8993 | 8993 | Stevens, Carl |  | 06-Oct-21 | 26-Jul-23 | 06-Oct-21 | 11-Apr-22 | 25-May-22 |  | N/A |  | 0
1214058 | Across the road from 97 Gosling Dr (Right beside bus stop) - UD276 Vault Replacement | 840 - Southgate | 151222 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Patenaude, Mélanie | 12-Oct-21 | 1 | 1 | 5771.99 | 3053.2 | 5771.99 | 5771.99 | Stevens, Carl |  | 01-Nov-21 | 01-Apr-22 | 01-Nov-21 | 03-Jan-22 | 31-Dec-21 |  |  |  | 0
1214059 | P-In Front of 288 Starwood Dr - UD598 Vault Replacement | 840 - Southgate | 151222 | Inactive | 99 | COMPLETE |  |  | 2022 |  | Patenaude, Mélanie | 12-Oct-21 | 1 | 1 | 37242.61 | 74625.21 | 57936.13 | 57936.13 | Stevens, Carl |  | 18-Oct-21 | 04-Jan-22 | 18-Oct-21 | 06-Dec-21 | 14-Jan-22 |  |  |  | 0
646245 | P-In Front of 215 Woolwich St - UD172 Sidewalk Vault Repair | 840 - Southgate | 151453 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Patenaude, Mélanie | 06-Oct-21 | 1 | 1 | 9362.91 | 9656.06 | 9362.91 | 9362.91 | Stevens, Carl |  | 06-Oct-21 | 26-Jul-23 | 06-Oct-21 | 04-Apr-22 | 11-Apr-22 |  | N/A |  | 0
1214243 | Pole 13 Maltby Rd W | 840 - Southgate | 1510891 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Dyce, Stephen A | 26-Aug-21 | 1 |  | 0 | 3950 | 0 | 0 | Manes, Bradley |  | 30-Aug-21 | 04-Jan-22 | 30-Aug-21 | 12-Nov-21 | 12-Nov-21 |  |  |  | 0
646022 | P-In Front of 155 Dawson Rd - Manholes 61, 141, 147 Repairs | 840 - Southgate | 151453 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646023 | P-Btw 171 & 165 Dawson Rd - Manhole 137 Repairs | 840 - Southgate | 151453 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1214242 | P-262 Main St S/ROC/UP/1PH Commercial Isolation | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646024 | P-55 BAKER ST NORTH TOWER/GUE/NS | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646025 | P-55 BAKER ST SOUTH TOWER/GUE/NS | 840 - Southgate | 151551 | Active | 48 | ACTIVE |  |  | 2023 | McGregor, Brendan | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646027 | P-755-757 Stone Rd E/GUE/NS & Pole Line Ext | 840 - Southgate | 151052 | Active | 10 | ACTIVE |  |  | 2023 | McAlpine, Robert | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646026 | P-757 STONE RD E/GUE/NS-SITE SERVICING | 840 - Southgate | 151551 | Active | 82 | RELEASED |  |  | 2023 | McAlpine, Robert | McGregor, Brendan | 24-Jul-23 |  |  | 49320.57 | 2056.3 | 49320.57 | 49320.57 | Manes, Bradley | Drexler | 25-Aug-23 | 24-Aug-23 | 21-Aug-23 | [5 empty] | 0
646222 | 20 Gosling Gardens - Apartment Buildings | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2022 | McGregor, Brendan | McGregor, Brendan | 22-Oct-21 |  |  | 56684.77 | 54974.97 | 56684.77 | 56684.77 | Stevens, Carl |  | 18-Oct-21 | 26-Jul-23 | 18-Oct-21 | 10-Jan-22 | 14-Apr-22 |  | N/A |  | 0
1215073 | 32 Pondview Cres/GUE/UP/1PH TX Upgrade | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McIntyre, Max | 31-Aug-21 |  |  | 3046.49 | 5806.91 | 3046.49 | 3046.49 | Stevens, Carl |  | 06-Sep-21 | 31-Dec-21 | 06-Sep-21 | 17-Sep-21 | 17-Sep-21 |  |  |  | 0
646246 | P-61 Mary St/GUE/UP/OH to UG Service Upgrade | 840 - Southgate | 151550 | Active | 96 | COMPLETE |  |  | 2022 | McGregor, Brendan | McIntyre, Max | 06-Oct-21 | 1 |  | 4682.23 | 6529.84 | 4682.23 | 4682.23 | Stevens, Carl |  | 06-Oct-21 | 26-Jul-23 | 06-Oct-21 | 02-May-22 | 29-Jul-22 | Customer | Customer |  | 0
1136109 | 19 Elmira Rd S - Costs TX Swap | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | McGregor, Brendan | 26-Aug-21 | 1 |  | 8752.43 | 2341.98 | 8752.43 | 8752.43 | Stevens, Carl |  | 06-Sep-21 | 04-Jan-22 | 06-Sep-21 | 01-Nov-21 | 01-Nov-21 |  |  |  | 0
1216254 | 166 College Ave W/GUE/SR/3PH Primary Service Removal | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 12-Oct-21 |  |  | 1605.9 | 4414.5 | 6020.4 | 6020.4 | Stevens, Carl |  | 01-Nov-21 | 04-Jan-22 | 01-Nov-21 | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1216257 | 176 College Ave W/GUE/SR/1 PH Service Removal | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 28-Oct-21 |  |  | 2006.82 | 2315.82 | 2006.82 | 2006.82 | Stevens, Carl |  | 30-Nov-21 | 01-Apr-22 | 29-Nov-21 | 11-Feb-22 | 11-Feb-22 |  |  |  | 0
646030 | 140 DENNIS ST, ROCKWOOD - BK 80199 DECOMMISSION | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra | 19-Oct-22 | 1 | 1 | 7733.09 | 4256.91 | 7733.09 | 7733.09 | Manes, Bradley |  | 05-Dec-22 | 08-Mar-23 | 05-Dec-22 | 24-Oct-22 | 24-Oct-22 |  |  |  | 0
646031 | 125 RICHARDSON ST, ROCKWOOD - BK80162 REPLACEMENT | 840 - Southgate | 151058 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 04-Nov-22 | 1 | 1 | 22361.09 | 18913.07 | 22361.09 | 22361.09 | Manes, Bradley |  | 13-Dec-22 | 27-Jul-23 | 12-Dec-22 | 21-Dec-22 | 13-Jan-23 |  | Locates |  | 0
646247 | 203 Main St S, Rockwood - BK 80282 Replacement | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra | 28-Oct-21 | 1 | 1 | 3770.87 | 5080 | 3770.87 | 3770.87 | Stevens, Carl |  | 06-Sep-22 | 08-Mar-23 | 06-Sep-22 | 19-Jul-22 | 19-Jul-22 |  |  |  | 0
646032 | 51 Victoria Rd N - BK00924 Replacement | 840 - Southgate | 151393 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646248 | 121 Bagot St - Townhomes Rehab | 840 - Southgate | 151453 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Harrison, Eric | 12-Oct-21 |  |  | 671843.48 | 713898.28 | 671843.48 | 671843.48 | Stevens, Carl | Drexler | 30-Nov-21 | 07-Jul-23 | 01-Nov-21 | 01-Nov-21 | 12-Dec-22 | Customer | Customer |  | 0
646249 | Marlborough Rd & Kitchener Ave Rebuild | 840 - Southgate | 151089 | Active | HL | H2 |  |  | 2023 | Bolton, Ian J | Chris McDonald | 06-Jan-22 | 17 |  | 116456.58 | 16798.88 | 116456.58 | 116456.58 | Lauryssen, John |  | 29-Dec-23 | 20-Dec-23 | 30-Nov-23 |  |  | N/A |  |  | 0
646250 | Forest St, Foreshill Dr & Wolfond Cres Rebuild | 840 - Southgate | 151089 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Chris McDonald | 06-Jan-22 | 17 | 17 | 194590.04 | 330325.43 | 194590.04 | 194590.04 | Manes, Bradley |  | 29-Apr-22 | 08-Mar-23 | 04-Apr-22 | 28-Mar-22 | 09-Jun-22 |  |  |  | 0
646251 | Beverley St (Morris St to Johnston St) & Harris St | 840 - Southgate | 151089 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Chris McDonald | 16-Dec-21 | 9 | 9 | 93961.89 | 103215.7 | 93961.89 | 93961.89 | Lauryssen, John |  | 18-Mar-22 | 19-Apr-23 | 01-Mar-22 | 18-Feb-22 | 01-Apr-22 |  |  |  | 0
646252 | Kensington St & Cathcart St Rebuild | 840 - Southgate | 151089 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West | 13-Jan-22 | 14 | 14 | 111466.52 | 141100.02 | 111466.52 | 111466.52 | Lauryssen, John |  | 17-Jun-22 | 10-Aug-23 | 30-May-22 | 16-May-22 |  |  | N/A |  | 0
646253 | Stevenson St N & Kensington St Rebuild | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2022 | Beaudrie, Scott | South-West | 01-Mar-22 | 21 | 21 | 208595.22 | 327941.68 | 208595.22 | 208595.22 | Lauryssen, John |  | 30-Jun-22 | 03-Aug-23 | 30-May-22 | 15-Jun-22 | 19-Oct-22 | Locates | Locates |  | 0
646254 | 20 Bellevue St/GUE/UP/OH to UG Service Installation | 840 - Southgate | 151550 | Active | 96 | COMPLETE |  |  | 2022 | McGregor, Brendan | McIntyre, Max | 01-Mar-22 |  |  | 6284.83 | 2229.57 | 6284.83 | 6284.83 | Stevens, Carl |  | 30-Jun-22 | 26-Jul-23 | 30-Jun-22 | 17-Jun-22 | 17-Jun-22 |  |  |  | 0
646255 | 505 Southgate Dr - BK06334 Replacement | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra | 28-Oct-21 | 1 | 1 | 22173.71 | 20841.5 | 22173.71 | 22173.71 | Stevens, Carl |  | 06-Sep-22 | 08-Mar-23 | 06-Sep-22 | 24-Oct-22 | 31-Oct-22 | Materials | Materials |  | 0
646256 | 1030 Gordon St - BK05073 Replacement | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra | 04-Nov-21 | 1 | 1 | 22173.71 | 21892.16 | 22173.71 | 22173.71 | Stevens, Carl |  | 06-Sep-22 | 15-Mar-23 | 06-Sep-22 | 21-Nov-22 | 21-Nov-22 | Materials | Materials |  | 0
646257 | 247 Eramosa Rd - BK05054 Replacement | 840 - Southgate | 151058 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra | 04-Nov-21 | 1 | 1 | 18850.91 | 16587.47 | 18850.91 | 18850.91 | Stevens, Carl |  | 06-Sep-22 | 08-Mar-23 | 06-Sep-22 | 17-Oct-22 | 18-Oct-22 | Materials | Materials |  | 0
646258 | 710 Woolwich St/GUE/Up | 840 - Southgate | 151551 | Active | 92 | ANALYZE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan | 03-Mar-22 |  |  | 32035 | 35822.51 | 32035 | 32035 | Stevens, Carl |  | 30-Jun-22 | 26-Jul-23 | 30-Jun-22 | 13-Dec-22 | 13-Jul-23 | Customer | Customer |  | 0
1185676 | Gosling Gardens 304 - 2021 Rogers Power Supply Connections | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West |  |  |  | 965.67 | 0 | 1462.21 | 1462.21 | Calvin Arsenault |  |  | 01-Apr-22 | [6 empty] | 0
1226277 | 67 Vancouver Dr/GUE/UP/1PH TX Upgrade | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 28-Oct-21 |  |  | 3102.1 | 792.05 | 3894.15 | 3894.15 | Stevens, Carl |  | 30-Nov-21 | 04-Jan-22 | 29-Nov-21 | 03-Jan-22 | 03-Jan-22 |  |  |  | 0
646047 | 14 LINCOLN CRES - BK04951 REPLACEMENT | 840 - Southgate | 151058 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 18-Nov-22 | 1 | 1 | 22236.17 | 15046.82 | 22236.17 | 22236.17 | Manes, Bradley |  | 10-Feb-23 | 28-Jul-23 | 08-Feb-23 | 10-Jan-23 | 31-Jan-23 |  |  |  | 0
646049 | 10 SURREY ST E - BK02696 REPLACEMENT | 840 - Southgate | 151058 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 04-Nov-22 | 1 | 1 | 21804.08 | 18859.44 | 21804.08 | 21804.08 | Manes, Bradley |  | 16-Dec-22 | 28-Jul-23 | 14-Dec-22 | 06-Jan-23 | 06-Jan-23 | Materials | Materials |  | 0
646050 | 127 FIFE RD - BK00700 REPLACEMENT | 840 - Southgate | 151058 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 07-Dec-22 | 1 | 1 | 11706.09 | 5874.97 | 11706.09 | 11706.09 | Manes, Bradley |  | 14-Feb-23 | 27-Jul-23 | 13-Feb-23 | 02-Jan-23 | 06-Jan-23 |  |  |  | 0
646051 | 41 NICKLIN CRES - BK00488 REPLACEMENT | 840 - Southgate | 151058 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 18-Nov-22 | 1 | 1 | 21356.95 | 17157.83 | 21356.95 | 21356.95 | Manes, Bradley |  | 08-Feb-23 | 28-Jul-23 | 06-Feb-23 | 10-Jan-23 | 31-Jan-23 |  |  |  | 0
646052 | 17 STRATHMERE PL - BK00318 REPLACEMENT | 840 - Southgate | 151058 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 04-Nov-22 | 1 | 1 | 21629.16 | 15067.81 | 21629.16 | 21629.16 | Manes, Bradley |  | 05-Jul-23 | 27-Jul-23 | 04-Jul-23 | 06-Jan-23 | 11-Jan-23 | Materials | Materials |  | 0
646053 | P-20 Dunkirk Ave - BK00085 Replacement | 840 - Southgate | 151058 | Inactive | 99 | CANCELLED |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646055 | 199 WESTWOOD RD U85 - BK03171 REPLACEMENT | 840 - Southgate | 151058 | Active | 92 | ANALYZE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 05-Dec-22 | 1 | 1 | 12589.05 | 16914.36 | 12589.05 | 12589.05 | Stevens, Carl |  | 06-Sep-23 | 06-Sep-23 | 05-Sep-23 | 31-May-23 | 31-May-23 | Lines | Lines |  | 0
646056 | 11 CHERRY BLOSSOM CIR - BK04853 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 19-Dec-22 | 1 |  | 12588.77 | 1823.44 | 12588.77 | 12588.77 | Stevens, Carl |  | 05-Jul-23 | 27-Jul-23 | 04-Jul-23 | [5 empty] | 0
646059 | 31 DOVERCLIFFE RD - BK05096 REPLACEMENT | 840 - Southgate | 151058 | Active | 94 | ANALYZE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 05-Dec-22 | 1 | 1 | 11764.28 | 10632.44 | 11764.28 | 11764.28 | Stevens, Carl |  | 09-Feb-23 | 27-Jul-23 | 08-Feb-23 | 25-Apr-23 | 25-Apr-23 | Lines | Lines |  | 0
646060 | 32 BEAVER MEADOW - BK05125 REPLACEMENT | 840 - Southgate | 151058 | Active | 94 | COMPLETE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 05-Dec-22 | 1 | 1 | 12030.57 | 10693.92 | 12030.57 | 12030.57 | Stevens, Carl |  | 10-Feb-23 | 27-Jul-23 | 09-Feb-23 | 03-Apr-23 | 03-Apr-23 | Lines | Lines |  | 0
646062 | 252 STARWOOD DR - BK06063 REPLACEMENT | 840 - Southgate | 151058 | Active | HO | RELEASED |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 19-Dec-22 | 1 |  | 12725.56 | 1975.35 | 12725.56 | 12725.56 | Stevens, Carl |  | 05-May-23 | 27-Jul-23 | 04-May-23 | [5 empty] | 0
646064 | 69 DOYLE DR - BK06190 REPLACEMENT | 840 - Southgate | 151058 | Active | 94 | ANALYZE |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 05-Dec-22 | 1 | 1 | 13303.01 | 11425 | 13303.01 | 13303.01 | Stevens, Carl |  | 14-Feb-23 | 27-Jul-23 | 13-Feb-23 | 25-Apr-23 | 25-Apr-23 | Lines | Lines |  | 0
646065 | 90 MARSH CRES - BK06918 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 05-Dec-22 | 1 |  | 12588.72 | 1884.3 | 12588.72 | 12588.72 | Stevens, Carl |  | 06-Sep-23 | 06-Sep-23 | 05-Sep-23 |  |  | Lines | Lines |  | 0
646069 | 49 MILSON CRES - BK07086 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 05-Dec-22 | 1 |  | 12589.05 | 1823.44 | 12589.05 | 12589.05 | Stevens, Carl |  | 06-Sep-23 | 06-Sep-23 | 05-Sep-23 |  |  | Lines | Lines |  | 0
1218544 | P-12 Shallmar Crt/GUE/UP/1 PH Pad TX Upgrade | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 04-Nov-21 | 1 |  | 2935.21 | 6603.01 | 9538.22 | 9538.22 | Stevens, Carl |  | 30-Nov-21 | 04-Jan-22 | 29-Nov-21 | 27-Jan-22 | 27-Jan-22 |  |  |  | 0
1218546 | P-200 Hanlon Creek Blvd | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | South-West | 02-Dec-21 |  |  | 73924.31 | 586.64 | 73924.31 | 73924.31 | Stevens, Carl | Drexler | 17-Jan-22 | 25-Feb-22 | 17-Jan-22 | 25-Feb-22 | 25-Feb-22 |  |  |  | 0
646259 | P-78 Starwood Dr/Temp/GUE/NS | 840 - Southgate | 151551 | Active | 91 | TEMP |  |  | 2023 | McAlpine, Robert | McGregor, Brendan | 20-Jan-22 | 1 |  | 48842.28 | 50335.35 | 48842.28 | 48842.28 | Stevens, Carl |  | 30-Jun-22 | 26-Jul-23 | 30-Jun-22 | 16-May-22 |  | Customer | Customer |  | 0
646260 | P-7 Quebec St - Manhole Lid Replacement (MHS10010) | 840 - Southgate | 151222 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Patenaude, Mélanie | 28-Oct-21 | 1 | 1 | 9036.23 | 12352.19 | 9036.23 | 9036.23 | Stevens, Carl |  | 30-Jun-22 | 26-Jul-23 | 30-Jun-22 | 12-Dec-22 | 12-Dec-22 | Contractor | Contractor |  | 0
646261 | P-75 Walnut Dr-UD Vault Lid Replacement (UD303) | 840 - Southgate | 151222 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Patenaude, Mélanie | 28-Oct-21 | 1 | 1 | 8548.39 | 11641.6 | 8548.39 | 8548.39 | Stevens, Carl |  | 30-Nov-21 | 26-Jul-23 | 29-Nov-21 | 11-Apr-22 | 25-May-22 | N/A | N/A |  | 0
646262 | P-200 Woolwich St - UD Vault Lid Replacement (UD171) | 840 - Southgate | 151222 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Patenaude, Mélanie | 28-Oct-21 | 1 | 1 | 8548.39 | 6512.52 | 8548.39 | 8548.39 | Stevens, Carl |  | 30-Nov-21 | 26-Jul-23 | 29-Nov-21 | 04-Apr-22 | 11-Apr-22 | N/A | N/A |  | 0
646075 | P-55 BAKER ST LIBRARY/GUE/NS | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646076 | P-824 WOOLWICH ST/GUE/NS | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1227763 | P-9 King Edward Pl | 840 - Southgate | 151085 | Inactive | 99 | COMPLETE |  |  | 2021 |  | Jamkodjian, Cassandra | 28-Oct-21 |  |  | 6344.77 | 31530.83 | 37875.6 | 37875.6 | Stevens, Carl |  | 28-Oct-21 | 04-Jan-22 | 28-Oct-21 | 18-Nov-21 | 30-Nov-21 |  |  |  | 0
646077 | P-166 COLLEGE AVE W/GUE/NS | 840 - Southgate | 151551 | Active | 84 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A | 03-Aug-22 |  |  | 91493.4 | 32522.62 | 83859.01 | 91493.4 | Stevens, Carl | Drexler | 07-Oct-22 | 10-Aug-23 | 19-Sep-22 | 20-Feb-23 |  | Customer | Customer |  | 7,634.39
1165751 | Golds Court - Pole Line Extension | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2021 |  | South-West | 27-Oct-21 |  |  | 27361.04 | 41104.42 | 27361.04 | 27361.04 | Lauryssen, John |  | 28-Oct-21 | 31-Dec-21 | 28-Oct-21 | 30-Nov-21 | 30-Nov-21 |  |  |  | 0
646078 | P-1408 GORDON ST/GUE/NS | 840 - Southgate | 151551 | Active | 40 | ACTIVE |  |  | 2023 | McGregor, Brendan | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1228452 | P-2071 Gordon St/GUE/UP/1 PH Secondary UG Conversion | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
646263 | P-Vancouver Dr & Edmonton Dr - Pole Line RC | 840 - Southgate | 151089 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Harrison, Eric | 19-Nov-21 | 27 | 27 | 319000 | 321534.79 | 319000 | 319000 | Manes, Bradley |  | 29-Apr-22 | 08-Mar-23 | 28-Mar-22 | 25-Mar-22 | 08-Jul-22 |  |  |  | 0
646080 | POLE 8 STARWOOD DRIVE RELOCATION | 840 - Southgate | 151052 | Inactive | 99 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Fisher, Cody | 15-Aug-22 | 1 | 1 | 17793.76 | 38112.87 | 17793.76 | 17793.76 | Manes, Bradley |  | 20-Sep-22 | 07-Mar-23 | 19-Sep-22 | 10-Oct-22 | 14-Oct-22 | Locates | Locates |  | 0
646264 | 30 Hanlon Creek Blvd/GUE/NS | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2022 | McAlpine, Robert | South-West | 27-Jan-22 |  |  | 101522.21 | 96225.9 | 101522.21 | 101522.21 | Stevens, Carl |  | 14-Mar-22 | 26-Jul-23 | 14-Mar-22 | 05-Dec-22 | 05-Dec-22 | Customer | Customer |  | 0
646081 | SUFFOLK ST W-PHASE 1 (EDINBURGH RD N-YORKSHIRE ST N),NORTH ST, HOME | 840 - Southgate | 151089 | Active | 91 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 27-Sep-22 | 22 | 22 | 794220.56 | 444904.41 | 775925.56 | 794220.56 | Stevens, Carl | Drexler | 13-Jul-23 | 10-Aug-23 | 04-May-23 | 24-Apr-23 |  | MC/PUCC Permit | MC/PUCC Permit |  | 18,295.00
646087 | P-905 WOODLAWN RD W/GUE/UP | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A | 13-Jul-22 |  |  | 130522.66 | 108302.72 | 130522.66 | 130522.66 | Stevens, Carl |  | 21-Oct-22 | 16-Aug-23 | 29-Aug-22 | 31-Jan-23 | 01-Feb-23 | Customer | Customer |  | 0
646083 | P-SUFFOLK ST W - PHASE 2 (YORKSHIRE ST N TO NORFOLK ST) | 840 - Southgate | 151089 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Chris McDonald | 06-Sep-22 | 14 |  | 274896.31 | 51934 | 274896.31 | 274896.31 | Manes, Bradley | Drexler | 26-Sep-23 | 26-Sep-23 | 01-Aug-23 | [5 empty] | 0
646085 | YORKSHIRE ST N (LONDON RD W TO NORTHUMBERLAND ST) & LIVERPOOL ST | 840 - Southgate | 151089 | Active | 94 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 05-Jul-22 | 40 | 40 | 550228.89 | 724121.32 | 380907.1 | 550228.89 | Manes, Bradley |  | 22-Dec-22 | 28-Jul-23 | 04-Oct-22 | 24-Nov-22 | 08-May-23 | Materials | Materials |  | 169,321.79
1230398 | Downey Rd & Woodland Glen Dr/GUE/NS/NEW OH Sec Span | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 16-Dec-21 |  |  | 0 | 2440.89 |  | 0 | Manes, Bradley |  | 10-Dec-21 | 01-Apr-22 | 10-Dec-21 | 28-Feb-22 | 28-Feb-22
1230395 | 14 Jane St/GUE/NS/1 PH OH Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | ($72.94) |  | 0 | Calvin Arsenault |  |  | 29-Apr-22
646265 | 30 Hanlon Creek Blvd/GUE/NS/1 PH Temp Service | 840 - Southgate | 151550 | Active | 96 | COMPLETE |  |  | 2022 | McGregor, Brendan | McIntyre, Max | 09-Dec-21 |  |  | 4357.08 | 3579.88 | 4357.08 | 4357.08 | Manes, Bradley |  | 10-Dec-21 | 26-Jul-23 | 10-Dec-21 | 09-May-22 | 20-Jan-23 | Customer | Customer |  | 0
1231368 | Heath Rd - Replacement of Existing UG Services | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West | 02-Dec-21 |  |  | 90916.33 | 45662.35 | 90916.33 | 90916.33 | Stevens, Carl | Drexler | 24-Jan-22 | 01-Apr-22 | 24-Jan-22 | 10-Jan-22 | 11-Mar-22 |  |  |  | 0
646266 | 14 Jane St/GUE/NS/New 1Ph UG Service | 840 - Southgate | 151550 | Active | 96 | COMPLETE |  |  | 2022 | McGregor, Brendan | McIntyre, Max | 01-Mar-22 |  |  | 6235.5 | 6004.61 | 6235.5 | 6235.5 | Stevens, Carl |  | 01-Mar-22 | 26-Jul-23 | 01-Mar-22 | 09-May-22 | 19-Dec-22 | Customer | Customer |  | 0
646267 | Pole 153 & 155 Speedvale Ave W Replacement | 840 - Southgate | 151051 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | South-West | 01-Mar-22 | 2 |  | 22740 | 59429.64 | 22740 | 22740 | Manes, Bradley |  | 01-Jun-22 | 08-Mar-23 | 30-May-22 | 04-Apr-22 | 14-Apr-22 |  |  |  | 0
1231743 | Lewis Rd SCADAMate R0780 Installation | 840 - Southgate | 151109 | Inactive | 99 | COMPLETE | High | Switch | 2022 |  | South-West | 09-Dec-21 | 1 | 1 | 57559.65 | 56336.22 | 57559.65 | 57559.65 | Lauryssen, John |  | 04-Apr-22 | 04-Apr-22 | 04-Apr-22 | 31-Jan-22 | 31-Jan-22 |  |  |  | 0
1231744 | Lewis Rd SCADAMate R0781 Installation | 840 - Southgate | 151390 | Inactive | 99 | COMPLETE | High | DA | 2022 |  | South-West | 09-Dec-21 | 1 | 1 | 57559.65 | 53293.23 | 57559.65 | 57559.65 | Manes, Bradley |  | 18-Apr-22 | 01-Apr-22 | 18-Apr-22 | 04-Apr-22 | 08-Apr-22 |  |  |  | 0
646268 | Speedvale Ave W SCADAMate R0110 Installation | 840 - Southgate | 151390 | Inactive | 99 | COMPLETE | High | DA | 2022 | Bolton, Ian J | South-West | 09-Dec-21 | 1 | 1 | 57559.65 | 56190.22 | 57559.65 | 57559.65 | Manes, Bradley |  | 02-May-22 | 08-Mar-23 | 02-May-22 | 28-Mar-22 | 28-Mar-22 |  |  |  | 0
646269 | P-Imperial Rd N LIS L0817 Replacement | 840 - Southgate | 151247 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Harrison, Eric | 02-Dec-21 | 1 |  | 1504.8 | 32028.5 | 1504.8 | 1504.8 | Lauryssen, John |  | 30-May-22 | 13-Mar-23 | 30-May-22 | 26-Jul-22 | 29-Jul-22 |  |  |  | 0
1084146 | 735 Woolwich St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Dyce, Stephen A | 19-Nov-21 |  |  | 85045.18 | 36381.67 | 85045.18 | 85045.18 | Manes, Bradley |  | 10-Jan-22 | 01-Apr-22 | 10-Jan-22 | 28-Mar-22 |  |  |  |  | 0
1231875 | P-51 Woodlawn Rd W/GUE/UP/1PH Meter Relocation | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
646271 | P-Wellington St W-SCADAMate R0132 Installation | 840 - Southgate | 151390 | Inactive | 99 | COMPLETE | High | DA | 2022 | Bolton, Ian J | Harrison, Eric | 09-Dec-21 | 1 | 1 | 57575.85 | 52064.72 | 57575.85 | 57575.85 | Lauryssen, John |  | 28-Mar-22 | 08-Mar-23 | 10-Jan-22 | 14-Mar-22 | 28-Mar-22 |  |  |  | 0
646270 | P-26 Paul Ave/GUE/NS/1PH OH Temp Service | 840 - Southgate | 151550 | Active | 95 | ANALYZE |  |  | 2023 | McGregor, Brendan | McIntyre, Max |  |  |  | 5880.67 | 499.42 | 5880.67 | 5880.67 | Stevens, Carl |  | 05-Apr-22 | 26-Jul-23 | 04-Apr-22 | 11-Apr-22 | 02-Jun-23 | Customer | Customer |  | 0
646272 | P-71 Hanlon Creek Blvd/GUE/NS/1PH Temp Service | 840 - Southgate | 151550 | Active | 91 | TEMP |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 27-Jan-22 |  |  | 3919.63 | 3780.81 | 3919.63 | 3919.63 | Stevens, Carl |  | 28-Mar-22 | 26-Jul-23 | 28-Feb-22 | 11-Apr-22 |  | Customer | Customer |  | 0
646273 | P-Willow Rd - SCADAMate R0459 Installation | 840 - Southgate | 151390 | Inactive | 99 | COMPLETE | High | DA | 2022 | Bolton, Ian J | Harrison, Eric | 09-Dec-21 | 1 | 1 | 58103.17 | 54876.42 | 58103.17 | 58103.17 | Lauryssen, John |  | 28-Mar-22 | 08-Mar-23 | 10-Jan-22 | 14-Mar-22 | 04-Apr-22 |  |  |  | 0
646116 | P-201 ELMIRA RD S/GUE/NS | 840 - Southgate | 151551 | Active | 95 | ANALYZE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 28-Sep-22 |  |  | 76264.53 | 31439.66 | 76264.53 | 76264.53 | Stevens, Carl | Drexler | 02-Dec-22 | 04-Aug-23 | 14-Nov-22 | 31-May-23 | 16-Jun-23 | Customer | Customer |  | 0
1232849 | P-138 College Ave W/GUE/UP/Commercial Isolation | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 1188.03 |  | 0 | Stevens, Carl |  |  | 27-May-22 |  | 03-Jan-22 | 31-Dec-21
646118 | P-435 WOODLAWN RD W (TESLA CHARGER)/GUE/NS | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1233085 | P-675 Victoria Rd N/GUE/NS/1PH Temp Service | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
646119 | P-Yeadon Dr Pole 5 | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
1194613 | 19 Dormie Lane | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 09-Dec-21 |  |  | 7391.92 | 4613.78 | 7391.92 | 7391.92 | Stevens, Carl |  | 30-Dec-21 | 27-May-22 | 30-Dec-21 | 03-Jan-22 | 31-Dec-21 |  |  |  | 0
646121 | FERGUSON ST (HURON ST TO MORRIS ST) & MORRIS ST (ELIZABETH ST TO GJR | 840 - Southgate | 151089 | Active | 94 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Patenaude, Mélanie | 15-Dec-22 | 13 | 13 | 373641.95 | 328681.43 | 343581.03 | 373641.95 | Lauryssen, John | Drexler | 20-Mar-23 | 10-Aug-23 | 23-Jan-23 | 23-Jan-23 | 18-May-23 |  | Design |  | 30,060.92
1234019 | 18 Vista Terrace/GUE/UP/1PH TX Upgrade | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max | 30-Dec-21 |  |  | 4045.44 | 4662.4 | 4045.44 | 4045.44 | Stevens, Carl |  | 30-Dec-21 | 29-Apr-22 | 30-Dec-21 | [5 empty] | 0
1234692 | Young St Pole 3 | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Consultant, NBM | 23-Dec-21 | 1 |  | 2201.85 | 2056.31 | 2201.85 | 2201.85 | Manes, Bradley |  | 31-Mar-22 | 01-Apr-22 | 28-Mar-22 | [5 empty] | 0
646274 | P-Exhibition St - LIS L0575 Replacement | 840 - Southgate | 151247 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Harrison, Eric | 11-Feb-22 |  |  | 26873.4 | 29170.33 | 26873.4 | 26873.4 | Manes, Bradley |  | 28-Mar-22 | 08-Mar-23 | 28-Mar-22 | 28-Mar-22 | 08-Apr-22 |  |  |  | 0
1234837 | P-Joint Use Transfer-Bell-Inkerman,Hearn,Chadwick,Allan,St Arnaud | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West | 11-Feb-22 |  |  | 0 | 6566.19 |  | 0 | Stevens, Carl |  | 01-Mar-22 | 01-Apr-22 | 01-Mar-22
646283 | P-P65 Wellington St/GUE/NS/1PH OH Temp Service | 840 - Southgate | 151550 | Active | 96 | COMPLETE |  |  | 2022 | McGregor, Brendan | South-West | 03-Feb-22 |  |  | 4419.13 | ($1,965.91) | 4419.13 | 4419.13 | Manes, Bradley |  | 30-May-22 | 26-Jul-23 | 30-May-22 | 10-Jun-22 | 27-Dec-22 | Customer | Customer |  | 0
646284 | 100 Victoria Rd S/GUE/NS | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2022 | McAlpine, Robert | McGregor, Brendan | 27-Jan-22 |  |  | 58623.49 | 53718.92 | 58623.49 | 58623.49 | Stevens, Carl |  | 24-Jun-22 | 26-Jul-23 | 20-Jun-22 | 11-Apr-22 | 05-May-22 |  |  |  | 0
1236307 | 35 Miller St/GUE/UP/1PH Pad TX Upgrade | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max |  |  |  | 8604.68 | 0 | 8604.68 | 8604.68 | Calvin Arsenault |  |  | 29-Apr-22 | [6 empty] | 0
646285 | P-201 Elmira Rd S/GUE/NS/Temp Service | 840 - Southgate | 151551 | Active | 95 | COMPLETE |  |  | 2022 | McGregor, Brendan | McIntyre, Max |  |  |  | 0 | 7075.3 |  | 0 | Stevens, Carl |  | 09-May-22 | 26-Jul-23 | 02-May-22 | 11-Apr-22 | 26-Dec-22 | Customer | Customer
1236938 | P-363 Elizabeth St/GUE/UP/Commercial Service Isolation | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 525.88 |  | 0 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 03-Jan-22 | 31-Dec-21
1236937 | 6 Mayfield Ave/GUE/UP/1 PH UG Service Additional Charges | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 501.37 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
646224 | Edinburgh Road South at College Avenue West | 840 - Southgate | 151453 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra | 27-Jan-22 |  |  | 34059.81 | 41646.31 | 34059.81 | 34059.81 | Stevens, Carl |  | 13-Jun-22 | 10-Mar-23 | 13-Jun-22 | 13-Jun-22 | 30-Jun-22 | Customer |  |  | 0
646138 | P-721 WOOLWICH ST/GUE/UP | 840 - Southgate | 151551 | Active | 92 | ANALYZE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A | 03-Aug-22 |  |  | 102203.86 | 81651.42 | 102203.86 | 102203.86 | Stevens, Carl | Drexler | 23-Sep-22 | 08-Aug-23 | 12-Sep-22 | 21-Mar-23 | 29-Jun-23 | Customer | Customer |  | 0
1237738 | 120 Country Club Drive Townhomes Rehab | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Harrison, Eric |  |  |  | 0 | 1647.81 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
1237757 | 82 Creighton Ave/GUE/NS/1PH UG SEC Relocation 2022 Charges | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 556.28 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
646286 | P-18 Alma St N/GUE/NS/Install New UG Sec Service | 840 - Southgate | 151550 | Active | 96 | COMPLETE |  |  | 2022 | McGregor, Brendan | McIntyre, Max | 01-Mar-22 |  |  | 7910.27 | 10375.5 | 7910.27 | 7910.27 | Stevens, Carl |  | 01-Mar-22 | 26-Jul-23 | 01-Mar-22 | 11-Apr-22 | 20-Jan-23 | Customer | Customer |  | 0
646139 | P-708 WOOLWICH ST - PH 2 STACKED TOWNS/GUE/NS/3PH PAD | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 12-Sep-22
1238253 | 415 Elmira Rd - Emergency PMSG063 Replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Jamkodjian, Cassandra |  |  |  | 0 | 35603.39 |  | 0 | Calvin Arsenault |  |  | 01-Apr-22
646140 | P-NIMA TRAILS PHASE 2 SUBDIVISION | 840 - Southgate | 151696 | Active | 50 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | Drexler |  | 27-May-22
646143 | 905 WOODLAWN RD W | 840 - Southgate | 152405 | Active | 95 | COMPLETE |  |  | 2022 | Jakubowski, Mark | Fisher, Cody | 07-Nov-22 |  |  | 100594.39 | 69302.97 | 100594.39 | 100594.39 | Lauryssen, John |  | 04-Jan-23 | 08-Aug-23 | 12-Dec-22 | 05-Dec-22 | 23-Dec-22 |  |  |  | 0
646287 | P-12 Heather Ave/GUE/UP/Service Relocation | 840 - Southgate | 151550 | Active | 96 | COMPLETE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 28-Mar-22 |  |  | 3826.7 | 2004.25 | 3826.7 | 3826.7 | Stevens, Carl |  | 30-Jun-22 | 26-Jul-23 | 30-Jun-22 | 12-Dec-22 | 12-Dec-22 | Customer | Customer |  | 0
646144 | P-Farquhar St Transformer Relocation | 840 - Southgate | 151052 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
859455 | Joint Use Transfer - Rogers - Willow Rd Reconstruction | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West | 04-Mar-22 |  |  | 8288 | 0 | 8288 | 8288 | Stevens, Carl |  | 01-Mar-22 | 01-Apr-22 | 01-Mar-22 | [5 empty] | 0
645920 | DOUGLAS STREET ALLEYWAY | 840 - Southgate | 151393 | Active | 40 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
645903 | BIRD LANDING SUBDIVISION - POPPY DR W AND GOSLING GARDENS | 840 - Southgate | 151696 | Active | 50 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 | 0 | 0 | Stevens, Carl |  |  | 27-May-22 | [6 empty] | 0
646153 | Fdr-Cityview Estates, Phase 2 Subdivision | 840 - Southgate | 151696 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 | 0 | 0 | Stevens, Carl |  |  | 27-May-22 | [6 empty] | 0
646154 | Cityview Estates, Phase 2 Subdivision | 840 - Southgate | 151696 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 | 0 | 0 | Stevens, Carl |  |  | 27-May-22 | [6 empty] | 0
646155 | 46 Goldenview Drive Townhomes | 840 - Southgate | 151696 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 | 0 | 0 | Stevens, Carl |  |  | 27-May-22 | [6 empty] | 0
646156 | P-300 GRANGE ROAD TOWNHOMES | 840 - Southgate | 151696 | Active | 91 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J | 14-Nov-22 |  |  | 178498.8 | 139945.59 | 178498.8 | 178498.8 | Stevens, Carl | Drexler | 17-Apr-23 | 04-Aug-23 | 12-Dec-22 | 25-Apr-22 |  | Customer | Customer |  | 0
646157 | P-117 MARSHALL DRIVE TOWNHOMES | 840 - Southgate | 151696 | Active | 45 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 | 0 | 0 | Stevens, Carl |  |  | 27-May-22 | [6 empty] | 0
645906 | P-VICTORIA PARK VILLAGE, PHASE 2 SUBDIVISION | 840 - Southgate | 151696 | Active | 40 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 | 0 | 0 | Stevens, Carl |  |  | 27-May-22 | [6 empty] | 0
1239939 | 55 Baker St/GUE/NS/1 PH OH Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 250.85 |  | 0 | Manes, Bradley |  | 02-May-22 | 27-May-22 | 02-May-22 | 03-Jan-22 | 31-Dec-21
646288 | 78 Starwood Drive/GUE/NS/1PH Overhead Temp Service | 840 - Southgate | 151550 | Active | 95 | COMPLETE |  |  | 2022 | McGregor, Brendan | McIntyre, Max |  |  |  | 3896.8 | 841.04 | 3896.8 | 3896.8 | Stevens, Carl |  | 09-May-22 | 26-Jul-23 | 02-May-22 | 11-Apr-22 | 19-Jul-22 | Customer | Customer |  | 0
1242267 | 265 Woodlawn Rd W/GUE/NS/1PH OH Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  | 04-Apr-22 | 27-May-22 | 04-Apr-22 | 03-Jan-22 | 31-Dec-21
1241767 | 735 Woolwich Street - New Office Building | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Dyce, Stephen A |  |  |  | 0 | 3213.87 |  | 0 | Stevens, Carl |  | 06-May-22 | 27-May-22 | 02-May-22 | 11-Apr-22
646150 | P-10 SHELLDALE CRES/GUE/NS/3PH PAD | 840 - Southgate | 151551 | Active | 84 | ACTIVE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 19-Jul-22 |  |  | 59816.56 | 31680.11 | 59816.56 | 59816.56 | Stevens, Carl | Drexler | 15-Sep-22 | 02-Aug-23 | 06-Sep-22 | 09-Mar-23 |  | Customer | Customer |  | 0
646146 | Rotten Pole Replacement Pole 13-14 Valley Rd | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
1240661 | Hammond Manufacturing - 394 Edinburgh Rd N | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 29-Apr-22 | [6 empty] | 0
646160 | 990 York Road/GUE/UP | 840 - Southgate | 151551 | Inactive | 99 | CANCELLED |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 17-May-23
646165 | P-105 Victoria Road North | 840 - Southgate | 151052 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646166 | P - PARK AVE - REAR LOT CONVERSION PROJECT | 840 - Southgate | 151085 | Active | 96 | COMPLETE |  |  | 2022 | Bolton, Ian J | Harrison, Eric | 17-Jun-22 |  |  | 940835.39 | 956565.87 | 940835.39 | 940835.39 | Stevens, Carl | Drexler | 16-Dec-22 | 09-Nov-23 | 25-Jul-22 | 04-Jul-22 | 19-Dec-22 |  |  |  | 0
645978 | Pole 18 Fairview Boulevard | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 | 0 | 0 | Calvin Arsenault |  |  | 27-May-22 | [6 empty] | 0
1244430 | Secondary Cable Replacement - 14 Mountford Dr | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | South-West |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1244493 | 710 Woolwich St/GUE/NS/1PH OH TEMP Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 02-May-22
1246632 | 98 Farley Drive - Urban Lofts | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 02-May-22
1246619 | 731 Woolwich St. | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2022 |  | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  | 02-May-22 | 27-May-22 | 02-May-22 | 02-May-22 | 02-May-22
1247456 | P- 142 Brant Ave / GUE / UP / 1PH Rogers Power supply connection | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646172 | 545, 641 AND 685 SPEEDVALE AVE W | 840 - Southgate | 151052 | Active | 92 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 28-Apr-23 |  |  | 30466.23 | 12815.4 | 30466.23 | 30466.23 | Lauryssen, John |  | 09-Jun-23 | 03-Aug-23 | 01-Jun-23 | 01-Jun-23 | 09-Jun-23 |  |  |  | 0
646173 | MUNICIPAL ST, EDINBURGH RD S | 840 - Southgate |  | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Jamkodjian, Cassandra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646174 | 45 DAWSON RD / GUE / UP | 840 - Southgate | 151551 | Active | 96 | COMPLETE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 19-Jul-22 |  |  | 49199.1 | 44710.93 | 49199.1 | 49199.1 | Stevens, Carl | Drexler | 12-Aug-22 | 01-Aug-23 | 08-Aug-22 | 22-Feb-23 | 22-Feb-23 | Customer | Customer |  | 0
1247897 | P-12 Wyndham St N / GUE / UP / Commercial Service Isolation | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1247913 | P- 20 Stevenson St S / GUE / UP / Commercial Service Isolation | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
1247865 | 39 Oak St. / GUE / NS / 1PH OH Temp Service | 840 - Southgate |  | Inactive | 99 | CANCELLED |  |  | 2022 |  | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  | 09-May-22 | 27-May-22 | 09-May-22 | 02-May-22
646176 | P-755 Stone Rd E /GUE / NS/ 1PH OH Temp Service | 840 - Southgate | 151550 | Inactive | 99 | CANCELLED |  |  | 2023 | McGregor, Brendan | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646177 | P-Victoria Rd S and Florence Ln / GUE / NS / 1PH OH Temp Service | 840 - Southgate | 151550 | Inactive | 99 | CANCELLED |  |  | 2022 | McGregor, Brendan | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 27-May-22
646179 | P-391 VICTORIA RD N / GUE / UP / 3PH PAD | 840 - Southgate | 151551 | Active | HO | RELEASED |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 05-Apr-23 | 1 |  | 78987.81 | 3013.6 | 78987.81 | 78987.81 | Stevens, Carl | Drexler | 16-Jun-23 | 16-Aug-23 | 29-May-23 |  |  | Customer |  |  | 0
646186 | PMSG043 REPLACEMENT - MASSEY RD E/O IMPERIAL RD N | 840 - Southgate | 151087 | Active | HO | RELEASED | High | SwGear | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 19-Dec-22 | 1 |  | 222964.57 | 4162.89 | 222964.57 | 222964.57 | Stevens, Carl | Drexler | 19-Jun-23 | 10-Aug-23 | 01-Jun-23 |  |  | Materials |  |  | 0
646188 | MACDONELL ST & NORFOLK ST PMSG071 REPLACEMENT | 840 - Southgate | 151087 | Active | 93 | ANALYZE | High | SwGear | 2023 | Bolton, Ian J | Jamkodjian, Cassandra | 20-Dec-22 | 1 | 1 | 124360.47 | 113857.22 | 124360.47 | 124360.47 | Stevens, Carl |  | 12-Jul-23 | 03-Aug-23 | 04-Jul-23 | 31-May-23 | 29-Jun-23 | Customer | Customer |  | 0
646189 | P-40 CORK ST E / GUE / UP / 1PH SUBM | 840 - Southgate | 151551 | Active | 84 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A | 01-Feb-23 |  |  | 18906.89 | 18405.76 | 18906.89 | 18906.89 | Stevens, Carl | Drexler | 07-Mar-23 | 27-Jul-23 | 06-Mar-23 | 31-May-23 |  | Customer | Customer |  | 0
646199 | 100 Victoria Road South / GUE / NS | 840 - Southgate | 151551 | Inactive | 99 | CANCELLED |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646194 | P-DUBLIN ST N - REAR LOT CONVERSION | 840 - Southgate | 151085 | Active | 84 | ACTIVE |  |  | 2023 | Bolton, Ian J | Harrison, Eric | 07-Oct-22 |  |  | 112009.53 | 123870.15 | 112009.53 | 112009.53 | Stevens, Carl |  | 08-Dec-22 | 04-Aug-23 | 14-Nov-22 | 28-Nov-22 |  | Customer | Customer |  | 0
646195 | P-GLASGOW ST N - REAR LOT CONVERSION | 840 - Southgate | 151453 | Active | 84 | ACTIVE |  |  | 2023 | Bolton, Ian J | Harrison, Eric | 28-Mar-23 | 4 |  | 127576.09 | 43917.9 | 127576.09 | 127576.09 | Stevens, Carl | Drexler | 21-Jun-23 | 31-Aug-23 | 08-May-23 | 12-Jun-23 |  | Lines | Lines |  | 0
646206 | 98 Farley Drive - Urban Lofts | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
646190 | P-MILTOWNE - 149 RICHARDSON ST. ROCKWOOD | 840 - Southgate | 151696 | Active | 40 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 27-May-22
645910 | WESTWOOD RD - OVERPASS REPLACEMENT AT HANLON EXPWY (POLE LINE R/C PORT | 840 - Southgate | 151051 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Harrison, Eric |  |  |  | 154003.38 | 114707.34 | 154003.38 | 154003.38 | Manes, Bradley |  | 19-Sep-22 | 26-Jul-23 | 25-Jul-22 | 22-Aug-22 | 16-Nov-22 | Customer | Customer |  | 0
645944 | 131 MALCOLM ROAD - NEW CEVA BLDG - POLE LINE EXTENSION | 840 - Southgate | 151052 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646936 | 278 COLLEGE AVE W / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646968 | 21-009 METCALFE RECONSTRUCTION - HYDRO CONFLICTS | 840 - Southgate | 151052 | Active | 92 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 23-Mar-23 |  |  | 125632.53 | 74141.58 | 125632.53 | 125632.53 | Stevens, Carl | Drexler | 15-May-23 | 10-Aug-23 | 01-May-23 | 14-Apr-23 | 02-Jun-23 |  | Filler |  | 0
646967 | POLE 21 KENT ST | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647079 | ROTTEN POLE REPLACEMENTS - P5 GRAHAM ST | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 23-Sep-22 | 1 | 1 | 13274.75 | 9572.35 | 13274.75 | 13274.75 | Manes, Bradley |  | 01-Dec-22 | 28-Jul-23 | 28-Nov-22 | 09-Jan-23 | 11-Jan-23 |  | Materials |  | 0
647149 | 65 MALTBY RD / GUE / NS / 1PH POLE | 840 - Southgate | 151550 | Active | 95 | COMPLETE |  |  | 2022 | McGregor, Brendan | Shereefdeen, Zuhair | 12-Sep-22 |  |  | 20469.24 | 10560.65 | 20469.24 | 20469.24 | Manes, Bradley | Drexler | 12-Oct-22 | 28-Jul-23 | 11-Oct-22 | 28-Nov-22 | 28-Nov-22 | Customer | Customer |  | 0
646045 | P-93 ARTHUR ST S/GUE/UP | 840 - Southgate | 151551 | Active | HO | RELEASED |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A | 03-Aug-22 |  |  | 73249.33 | 1975.57 | 73249.33 | 73249.33 | Stevens, Carl |  | 02-Jun-23 | 28-Jul-23 | 31-May-23 |  |  | Customer |  |  | 0
647187 | HWY 6 / HANLON EXPRESSWAY RECONSTRUCTION | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647208 | 10 GOLDIE AVE - BK00149 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Fisher, Cody | 24-Mar-23 | 1 |  | 17836.09 | 2192.24 | 17836.09 | 17836.09 | Manes, Bradley |  | 03-Oct-23 | 03-Oct-23 | 02-Oct-23 | [5 empty] | 0
647211 | 8 ROSEWOOD AVE - BK00506 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Fisher, Cody | 24-Mar-23 | 1 |  | 23200.05 | 2743.42 | 23200.05 | 23200.05 | Manes, Bradley |  | 20-Oct-23 | 20-Oct-23 | 17-Oct-23 | [5 empty] | 0
647215 | 162 WATERLOO AVE - BK02901 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Fisher, Cody | 24-Mar-23 | 1 |  | 27991.2 | 4535.15 | 27991.2 | 27991.2 | Manes, Bradley |  | 06-Oct-23 | 06-Oct-23 | 03-Oct-23 | [5 empty] | 0
647232 | 20 ARMSTRONG AVE - BK01861 REPLACEMENT | 840 - Southgate | 151058 | Inactive | 99 | CANCELLED |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647230 | 9 PAISLEY ST (OPP) - BK00509 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Fisher, Cody | 24-Mar-23 | 1 |  | 19226.26 | 2042.98 | 19226.26 | 19226.26 | Lauryssen, John |  | 22-Aug-23 | 22-Aug-23 | 21-Aug-23 | [5 empty] | 0
647238 | 102 WYNDHAM ST N - BK06503 REPLACEMENT | 840 - Southgate | 151058 | Inactive | 99 | CANCELLED |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647237 | 351 ERAMOSA RD - BK00537 REPLACEMENT | 840 - Southgate | 151058 | Inactive | 99 | CANCELLED |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647323 | 21-009 METCALFE RECONSTRUCTION - HYDRO CONFLICTS TEMP RELOCATION | 840 - Southgate | 151051 | Inactive | 99 | COMPLETE |  |  | 2022 | Bolton, Ian J | Chris McDonald | 15-Aug-22 |  |  | 35312.04 | 20534.12 | 35312.04 | 35312.04 | Stevens, Carl |  | 15-Aug-22 | 08-Mar-23 | 15-Aug-22 | 15-Aug-22 | 15-Aug-22 | xBy-passed | xBy-passed |  | 0
646151 | P-LEE ST SEMI'S/GUE/NS | 840 - Southgate | 151550 | Active | 95 | ANALYZE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 06-Sep-22 | 1 |  | 37568.8 | 31380.59 | 37568.8 | 37568.8 | Stevens, Carl | Drexler | 13-Oct-22 | 28-Jul-23 | 11-Oct-22 | 16-Mar-23 | 30-Mar-23 | Customer | Customer |  | 0
647434 | 29 SUMMIT CRES - BK03256 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Fisher, Cody | 24-Mar-23 | 1 |  | 17195.15 | 2357.04 | 17195.15 | 17195.15 | Lauryssen, John |  | 16-Aug-23 | 16-Aug-23 | 15-Aug-23 | [5 empty] | 0
647456 | 14 JUNE AVE - BK00180 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Fisher, Cody | 24-Mar-23 | 1 |  | 31941.51 | 2657.17 | 31941.51 | 31941.51 | Lauryssen, John |  | 08-Aug-23 | 08-Aug-23 | 01-Aug-23 | [5 empty] | 0
647455 | 103 WINSTON CRES - BK00372 REPLACEMENT | 840 - Southgate | 151058 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Fisher, Cody | 24-Mar-23 | 1 |  | 23745.79 | 3597.49 | 23745.79 | 23745.79 | Lauryssen, John |  | 14-Aug-23 | 14-Aug-23 | 09-Aug-23 | [5 empty] | 0
647479 | P8 MALTBY RD ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Chris McDonald | 05-Dec-22 | 1 |  | 19175.86 | 1738.04 | 19175.86 | 19175.86 | Lauryssen, John |  | 07-Sep-23 | 07-Sep-23 | 05-Sep-23 |  |  | Lines | Lines |  | 0
647478 | P97 GORDON ST ROTTEN POLE REPLACEMENT | 840 - Southgate | 151247 | Active | HO | RELEASED |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 19-Dec-22 | 1 | 0 | 43382.82 | 0 | 43382.82 | 43382.82 | Stevens, Carl | Drexler | 05-Apr-23 | 05-Apr-23 | 03-Apr-23 |  |  | Customer | Customer |  | 0
647477 | P87 FORESTELL RD ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 21-Nov-22 | 1 | 1 | 19846.99 | 7048.06 | 19846.99 | 19846.99 | Lauryssen, John |  | 16-Feb-23 | 31-Jul-23 | 13-Feb-23 | 09-Jan-23 | 01-Feb-23 |  |  |  | 0
647483 | P64 WATERLOO AVE ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 94 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 25-Nov-22 | 1 | 1 | 35824.99 | 25976.46 | 35824.99 | 35824.99 | Manes, Bradley |  | 01-Mar-23 | 01-Aug-23 | 20-Feb-23 | 27-Feb-23 | 28-Mar-23 | Lines | Lines |  | 0
647482 | P68 SPEEDVALE AVE W ROTTEN POLE REPLACEMENT | 840 - Southgate | 151247 | Active | HO | RELEASED |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 19-Dec-22 | 1 |  | 59635.7 | 0 | 59635.7 | 59635.7 | Lauryssen, John | Drexler | 18-Apr-23 | 18-Apr-23 | 03-Apr-23 |  |  | Lines |  |  | 0
647481 | P3 WATSON RD S ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 94 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 19-Dec-22 | 1 | 1 | 29327.23 | 16493.41 | 29327.23 | 29327.23 | Lauryssen, John |  | 05-May-23 | 12-Sep-23 | 20-Mar-23 | 24-Apr-23 | 05-May-23 | Lines | Lines |  | 0
647480 | P18 RIDGEWAY AVE ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 05-Dec-22 | 1 | 1 | 18601.08 | 7327.55 | 18601.08 | 18601.08 | Lauryssen, John |  | 08-Mar-23 | 28-Jul-23 | 06-Mar-23 | 03-Jan-23 | 11-Jan-23 |  |  |  | 0
647492 | P63 PALMER ST ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | HO | RELEASED |  |  | 2023 | Bolton, Ian J | Chris McDonald | 25-Nov-22 | 1 |  | 17608.31 | 0 | 17608.31 | 17608.31 | Manes, Bradley |  | 03-Mar-23 | 07-Sep-23 | 01-Mar-23 |  |  | Materials | Materials |  | 0
647491 | P50 WATSON RD S ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | HO | RELEASED |  |  | 2023 | Bolton, Ian J | Chris McDonald | 05-Dec-22 | 1 |  | 32294.68 | 0 | 32294.68 | 32294.68 | Lauryssen, John |  | 10-Mar-23 | 07-Sep-23 | 08-Mar-23 | [5 empty] | 0
647490 | P46 WATSON PKWY S ROTTEN POLE REPLACEMENT | 840 - Southgate | 151247 | Active | 94 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 19-Dec-22 | 1 | 1 | 18075.38 | 9230.31 | 18075.38 | 18075.38 | Lauryssen, John |  | 20-Apr-23 | 28-Jul-23 | 17-Apr-23 | 06-Apr-23 | 10-Apr-23 |  |  |  | 0
647494 | P18, 20, 22, 24 BRENTWOOD POLE REPLACEMENT | 840 - Southgate | 151247 | Active | 70 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  | 4 |  | 0 | 0 |  | 0 | Manes, Bradley |  |  | 20-Jul-20
647493 | P17 YORK RD ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 05-Dec-22 | 1 | 1 | 19127.61 | 10596.37 | 19127.61 | 19127.61 | Lauryssen, John |  | 15-Mar-23 | 28-Jul-23 | 13-Mar-23 | 09-Jan-23 | 10-Jan-23 |  |  |  | 0
647497 | P29 CLIVE AVE ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 25-Nov-22 | 1 | 1 | 23033.37 | 23659.26 | 23033.37 | 23033.37 | Manes, Bradley |  | 10-Mar-23 | 28-Jul-23 | 06-Mar-23 | 06-Jan-23 | 01-Feb-23 |  |  |  | 0
647502 | P3 KENT ST ROTTEN POLE REPLACEMENT | 840 - Southgate | 151247 | Active | 50 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647500 | POLE A86, A88, A89 AND A91 PAISLEY RD ROTTEN POLE REPLACEMENT | 840 - Southgate | 151247 | Active | 40 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647499 | P136 VICTORIA RD N ROTTEN POLE REPLACEMENT | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647498 | P13 DUBLIN ST ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 94 | COMPLETE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 19-Dec-22 | 1 | 1 | 18192 | 17498.26 | 18192 | 18192 | Lauryssen, John |  | 25-Apr-23 | 27-Jul-23 | 20-Apr-23 | 20-Apr-23 | 21-Apr-23 |  |  |  | 0
647503 | P107 EDINBURGH RD S ROTTEN POLE REPLACEMENT | 840 - Southgate | 151089 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Chris McDonald | 19-Oct-22 | 1 | 1 | 47532.57 | 53763.87 | 47532.57 | 47532.57 | Manes, Bradley |  | 20-Dec-22 | 02-Aug-23 | 12-Dec-22 | 07-Nov-22 | 16-Nov-22 |  |  |  | 0
647504 | P17 LEMON ST TRANSFORMER INSTALLATION | 840 - Southgate | 151089 | Active | 92 | ANALYZE |  |  | 2023 | Bolton, Ian J | Chris McDonald | 19-Oct-22 | 1 | 1 | 21709.63 | 17420.24 | 21709.63 | 21709.63 | Manes, Bradley |  | 12-Dec-22 | 28-Jul-23 | 07-Dec-22 | 16-Jan-23 | 27-Feb-23 | Materials | Materials |  | 0
645917 | POLES 43 & 47 PAISLEY STREET | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645915 | POLE A10 VICTORIA ROAD NORTH | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645913 | POLE 119 ERAMOSA ROAD | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647598 | EXHIBITION ST & VERNEY ST RECONSTRUCTION | 840 - Southgate | 151089 | Active | 84 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 27-Mar-23 | 21 |  | 639047.28 | 206178.27 | 639047.28 | 639047.28 | Lauryssen, John |  | 13-Dec-23 | 28-Nov-23 | 17-Jul-23 | 12-Jun-23 |  |  |  |  | 0
647597 | EXHIBITION ST & CLARKE ST W RECONSTRUCTION | 840 - Southgate | 151089 | Active | 82 | RELEASED |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 24-Mar-23 | 18 |  | 452247.06 | 35051.9 | 452247.06 | 452247.06 | Lauryssen, John |  | 19-Dec-23 | 19-Dec-23 | 25-Sep-23 | [5 empty] | 0
647614 | 1882 GORDON ST / GUE / NS / TEMP 3PH PAD | 840 - Southgate | 151551 | Active | 95 | ANALYZE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan | 14-Sep-22 | 1 |  | 44078.6 | 33468.94 | 44078.6 | 44078.6 | Stevens, Carl |  | 07-Oct-22 | 02-Aug-23 | 06-Oct-22 | 13-Mar-23 | 14-Apr-23 | Customer | Customer |  | 0
646021 | POLE 86 WAVERLEY DR | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645971 | POLE R3 MAIN STREET - ROCKWOOD | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645970 | POLE 17 ALMA STREET - ROCKWOOD | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645953 | POLE 2 GRANGE STREET | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645942 | POLE 51 STEVENSON STREET NORTH | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645926 | POLE 9 OMAR STREET | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645925 | POLE 64 SUFFOLK STREET WEST | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645924 | POLE A86 PAISLEY ROAD | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645923 | POLE 83 WATER STREET | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645922 | POLE 108 WOOLWICH STREET | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645919 | POLES A91 & A93 PAISLEY ROAD | 840 - Southgate | 151247 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645946 | SPEEDVALE AVE W FROM ELMIRA RD N TO IMPERIAL RD N - POLE LINE REBUILD | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645945 | YORK RD FROM ONTARIO ST TO STEVENSON ST S - POLE LINE REBUILD | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 14-Aug-23
647626 | 110 STEVENSON ST S / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647627 | 945 WOODLAWN RD W / GUE / UP / 3PH PAD | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647511 | 23 VICTORIA RD N / GUE / NS / NEW 1PH BELL POWER SUPPLY | 840 - Southgate | 151550 | Active | 40 | ACTIVE |  |  | 2023 | McGregor, Brendan | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647640 | BAKER ST & CHAPEL LN UNDERGROUND RECONSTRUCTION | 840 - Southgate | 152399 | Active | 50 | ACTIVE | Medium | Infrast | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli | Drexler |  | 20-Jul-20
647656 | 146 SPEEDVALE AVE W / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647661 | BAKER ST 55 /GUE/NS/ LIBRARY TEMP | 840 - Southgate | 151550 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647663 | BAKER ST 55 /GUE/NS/SOUTH TOWER TEMP | 840 - Southgate | 151550 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647714 | PAISLEY ST RECONSTRUCTION (GLASGOW ST N TO EDINBURGH RD N) | 840 - Southgate | 151089 | Active | 70 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647713 | KATHLEEN ST AND BARTON ST RECONSTRUCTION | 840 - Southgate | 151089 | Active | 50 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647786 | 29 DELHI ST / GUE / NS / 200A UG C/W 1X100MM DUCT | 840 - Southgate | 151550 | Active | 95 | COMPLETE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair | 07-Oct-22 |  |  | 5396.58 | 1846.65 | 5396.58 | 5396.58 | Stevens, Carl | Drexler | 06-Dec-22 | 27-Jul-23 | 05-Dec-22 | 13-Feb-23 | 13-Mar-23 | Customer | Customer |  | 0
647800 | 70 LOWES RD INFILL / GUE / NS / THREE NEW SEVERED SERVICES AT 70 LOWES RD | 840 - Southgate | 151550 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647814 | POLE 83 MASSEY RD - CAP BANK INSTALLATION Z6026 | 840 - Southgate | 151245 | Active | HO | RELEASED |  |  | 2023 | Bolton, Ian J | Harrison, Eric | 10-Nov-22 | 1 |  | 50622.96 | 5908.91 | 50622.96 | 50622.96 | Lauryssen, John |  | 03-Apr-23 | 28-Jul-23 | 31-Mar-23 | [5 empty] | 0
647509 | 12 SPEEDVALE AVE W / GUE / NS / NEW 1PH BELL POWER SUPPLY | 840 - Southgate | 151550 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647854 | 78 STARWOOD DRIVE/GUE/NS/1PH OVERHEAD TEMP SERVICE (2ND ON SITE) | 840 - Southgate | 151550 | Inactive | 99 | CANCELLED |  |  | 2023 | McGregor, Brendan | McIntyre, Max |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 15-Feb-23
647901 | 585 HANLON CREEK BLVD / GUE / NS / NEW 1PH TEMP SERVICE C/W TRANSFORMER | 840 - Southgate | 151550 | Active | 95 | COMPLETE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 15-Nov-22 |  |  | 9678 | 2803.48 | 9678 | 9678 | Manes, Bradley |  | 20-Dec-22 | 27-Jul-23 | 19-Dec-22 | 21-Nov-22 | 10-Feb-23 |  |  |  | 0
647957 | 364 MASSEY RD / GUE / UP / 3PH PAD | 840 - Southgate | 151551 | Active | 82 | RELEASED |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 23-May-23 |  |  | 92042.03 | 2579.93 | 92042.03 | 92042.03 | Stevens, Carl | Drexler | 18-Aug-23 | 18-Aug-23 | 08-Aug-23 | [5 empty] | 0
645962 | RIDGEWOOD AVE BK00277 | 840 - Southgate | 151058 | Active | 95 | COMPLETE |  |  | 2022 | Bolton, Ian J | Jamkodjian, Cassandra | 07-Nov-22 | 1 | 1 | 21525.23 | 17717.43 | 21525.23 | 21525.23 | Manes, Bradley |  | 22-Dec-22 | 27-Jul-23 | 21-Dec-22 | 29-Dec-22 | 29-Dec-22 | Filler |  |  | 0
647991 | ROBERTSON DR AND ST ANDREW ST RECONSTRUCTION | 840 - Southgate | 151089 | Active | 92 | ANALYZE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody | 07-Mar-23 | 14 | 14 | 355040.32 | 226135.28 | 355040.32 | 355040.32 | Lauryssen, John |  | 20-Jul-23 | 11-Sep-23 | 01-May-23 | 19-Apr-23 | 09-Jun-23 |  |  |  | 0
647995 | 24 AND 111 MACDONELL ST - UD VAULT 150 AND 201 REPAIRS | 840 - Southgate | 151222 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Harrison, Eric | 19-Dec-22 | 1 |  | 25376.52 | 12054.82 | 25376.52 | 25376.52 | Stevens, Carl | Drexler | 29-Jun-23 | 02-Aug-23 | 05-Jun-23 |  |  | Lines | Lines |  | 0
648000 | OPPOSITE 632 COLLEGE AVE W - UD VAULT 447 REPAIR | 840 - Southgate | 151222 | Active | HO | RELEASED |  |  | 2023 | Bolton, Ian J | Harrison, Eric | 19-Dec-22 | 1 |  | 13091.12 | 16196.11 | 13091.12 | 13091.12 | Stevens, Carl | Drexler | 29-Jun-23 | 31-Jul-23 | 05-Jun-23 | [5 empty] | 0
647876 | JOINT USE PERMIT HG2022-031 - Z60568-1P - GUELPH | 840 - Southgate | 152389 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647875 | JOINT USE PERMIT HG2022-030 - Z60269-1P - GUELPH | 840 - Southgate | 152389 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647874 | JOINT USE PERMIT HG2022-029 - Z60239-3P - GUELPH | 840 - Southgate | 152389 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
647710 | JOINT USE PERMIT HG2022-027 - Z60239-2P | 840 - Southgate | 152389 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Johnson, William |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
646009 | NEW FIBRE INSTALLATION - ROGERS - 435 STONE RD W | 840 - Southgate | 152389 | Active | 10 | ACTIVE |  |  | 2023 | O'Gay, Brian | Oosterlinck, David |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648151 | 41 LORNA DR / GUE / NS / 200A UG C/W 1X100MM DUCT | 840 - Southgate | 151550 | Active | 95 | COMPLETE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair | 01-Nov-22 |  |  | 3645.12 | 2586.54 | 3645.12 | 3645.12 | Stevens, Carl | Drexler | 06-Dec-22 | 28-Jul-23 | 05-Dec-22 | 24-May-23 | 24-May-23 | Customer | Customer |  | 0
648174 | 188 NISKA RD - UD VAULT 25 REPAIR | 840 - Southgate | 151222 | Active | 82 | RELEASED |  |  | 2023 | Bolton, Ian J | Harrison, Eric | 19-Dec-22 | 1 | 0 | 17893.36 | 4025.53 | 17893.36 | 17893.36 | Stevens, Carl | Drexler | 29-Jun-23 | 02-Aug-23 | 05-Jun-23 |  |  | Lines | Lines |  | 0
648175 | 183 WOOLWICH ST - UD VAULT 174 REPAIR | 840 - Southgate | 151222 | Active | 92 | ANALYZE |  |  | 2023 | Bolton, Ian J | Harrison, Eric | 19-Dec-22 | 1 | 1 | 18498.62 | 5021.43 | 18498.62 | 18498.62 | Stevens, Carl | Drexler | 14-Jul-23 | 02-Aug-23 | 10-Jul-23 | 10-Jul-23 | 14-Jul-23 |  |  |  | 0
648176 | 202 LONDON RD W - ANCHOR RELOCATION PROJECT | 840 - Southgate | 151089 | Active | 91 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric | 23-May-23 | 1 | 1 | 15500.56 | 16303.43 | 15500.56 | 15500.56 | Lauryssen, John |  | 26-Jun-23 | 27-Jul-23 | 26-Jun-23 | 19-Jun-23 |  |  |  |  | 0
648234 | L0920 SWITCH RENEWAL PROJECT – IMPERIAL RD S SOUTH OF SPEEDVALE AVE W | 840 - Southgate | 151109 | Active | 92 | ANALYZE | High | Switch | 2023 | Bolton, Ian J | Harrison, Eric | 23-Mar-23 | 1 |  | 94008.55 | 88475.4 | 94008.55 | 94008.55 | Lauryssen, John |  | 08-Sep-23 | 27-Jul-23 | 01-Sep-23 | 19-Jun-23 | 17-Jul-23 |  |  |  | 0
648277 | 150 ALMA ST / ROC / NS / 400A 1PH SERVICE | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648281 | 18 INDUSTRIAL ST / GUE / UP / 3PH OH | 840 - Southgate | 151551 | Active | 84 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A | 09-May-23 |  |  | 94729.99 | 83809 | 94729.99 | 94729.99 | Stevens, Carl |  | 29-Jun-23 | 02-Aug-23 | 12-Jun-23 | 12-Jun-23 |  |  |  |  | 0
648363 | 80 STARWOOD DR/GUE/NS/3PH PAD | 840 - Southgate | 151551 | Active | 82 | RELEASED |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 23-May-23 |  |  | 142844.17 | 3672.95 | 142844.17 | 142844.17 | Stevens, Carl |  | 06-Jul-23 | 01-Aug-23 | 03-Jul-23 |  |  | Materials | Materials |  | 0
648489 | UNIT 56-539 WILLOW RD / GUE / UP / 3X100A UG C/W 2X3/0 AL. CABLES | 840 - Southgate | 151550 | Active | 95 | COMPLETE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair | 26-Jan-23 |  |  | 3217.06 | 8469.99 | 3217.06 | 3217.06 | Stevens, Carl | Drexler | 14-Feb-23 | 27-Jul-23 | 14-Feb-23 | 20-Mar-23 | 23-Mar-23 | Customer |  |  | 0
648527 | 540 HANLON CREEK BLVD / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 82 | RELEASED |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair | 22-Jun-23 |  |  | 184016 | 983.4 | 184016 | 184016 | Stevens, Carl | Drexler | 31-Aug-23 | 31-Aug-23 | 14-Aug-23 | [5 empty] | 0
648553 | 2023 DA- CLAIR RD SCADAMATE R1069 | 840 - Southgate | 151390 | Active | 82 | RELEASED | Low | DA | 2023 | Bolton, Ian J | Harrison, Eric | 29-May-23 | 1 |  | 103649.33 | 9057.9 | 103649.33 | 103649.33 | Manes, Bradley |  | 19-Sep-23 | 05-Sep-23 | 05-Sep-23 | [5 empty] | 0
648576 | 585 HANLON CREEK BLVD / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 82 | RELEASED |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 22-May-23 |  |  | 227923.08 | 12233.76 | 227923.08 | 227923.08 | Stevens, Carl | Drexler | 14-Aug-23 | 17-Aug-23 | 24-Jul-23 | [5 empty] | 0
647209 | 54 CAMPBELL ROAD /GUE/NS/ SINGLE PHASE TEMP SERVICE | 840 - Southgate | 151550 | Active | 95 | COMPLETE |  |  | 2022 | McGregor, Brendan | Dyce, Stephen A | 07-Dec-22 |  |  | 8867.73 | 7536.37 | 8867.73 | 8867.73 | Manes, Bradley |  | 30-Dec-22 | 27-Jul-23 | 30-Dec-22 | 21-Dec-22 | 21-Dec-22 |  |  |  | 0
648794 | P-816 WOOLWICH ST CONDO/GUE/NS | 840 - Southgate | 151551 | Active | 70 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
648885 | 300 WATER ST RECONSTRUCTION | 840 - Southgate | 151052 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649192 | YORK RD PH3 HYDRO CONFLICTS | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649367 | 141 FOUNTAIN ST E - METROLINX / GUE / NS / 1PH POLE | 840 - Southgate | 151550 | Active | 84 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair | 17-Mar-23 | 1 |  | 26701.97 | 10893.39 | 26701.97 | 26701.97 | Stevens, Carl | Drexler | 12-Apr-23 | 28-Jul-23 | 10-Apr-23 | 31-May-23 |  | Customer | Customer |  | 0
648450 | 93 ARTHUR ST. - TEMP/GUE/NS/ | 840 - Southgate | 151550 | Active | 95 | COMPLETE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A | 17-Mar-23 |  |  | 7290.51 | 4136.58 | 7290.51 | 7290.51 | Stevens, Carl |  | 18-Apr-23 | 28-Jul-23 | 17-Apr-23 | 30-Mar-23 | 30-Mar-23 |  |  |  | 0
649510 | 805 WOODLAWN RD W / GUE / UP / 3PH PAD | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649559 | 176 & 224 JANEFIELD AVE - TOWNHOMES REHAB - BLOCK 'O' UNITS 286-446 | 840 - Southgate | 151453 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649560 | SILVERCREEK POLE RELOCATION | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649595 | 520 SPEEDVALE AVE. E. - TOWNHOMES | 840 - Southgate | 151696 | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649597 | 77 VICTORIA RD. N. - TOWNHOMES | 840 - Southgate |  | Active | 10 | ACTIVE |  |  | 2023 | Velickovski, Goran | Kingswell, Dean J |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645994 | 151 CITYVIEW DR N / GUE / NS / 1PH UG SERVICES | 840 - Southgate | 151550 | Active | 95 | ANALYZE |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 17-Mar-23 | 1 |  | 10543.49 | 10202.48 | 10543.49 | 10543.49 | Stevens, Carl | Drexler | 02-May-23 | 27-Jul-23 | 01-May-23 | 14-Apr-23 | 14-Apr-23 |  |  |  | 0
649722 | 30 BETT CRT / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 82 | RELEASED |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair | 23-May-23 |  |  | 115681.5 | 1145.93 | 115681.5 | 115681.5 | Stevens, Carl |  | 13-Jul-23 | 01-Aug-23 | 10-Jul-23 |  |  | Materials | Materials |  | 0
649794 | 171 HURON ST / GUE / UP / 1PH POLE | 840 - Southgate | 151550 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649842 | 30 BETT CRT / GUE / NS / 1PH POLE TEMP | 840 - Southgate | 151550 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649844 | 80 DUNLOP DR / GUE / NS / 3PH 13.8KV | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649922 | 181 ELMIRA RD S BUILDING B / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649891 | 1080 SOUTHGATE DR / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649970 | 168 ALMA ST / ROC/ NS / 1PH POLE | 840 - Southgate | 151550 | Active | 45 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
649992 | 70 EDGEHILL DR/ GUE / NS / 200A UG C/W 1X100MM DUCT | 840 - Southgate | 151550 | Active | 82 | RELEASED |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair | 21-Jun-23 |  |  | 8674.67 | 1007.03 | 8674.67 | 8674.67 | Stevens, Carl | Drexler | 24-Jul-23 | 27-Jul-23 | 24-Jul-23 | [5 empty] | 0
649999 | 181 ELMIRA RD S, BUILDING B / GUE / NS / TEMP SERVICE | 840 - Southgate | 151550 | Active | 82 | RELEASED |  |  | 2023 | McGregor, Brendan | McIntyre, Max | 22-May-23 |  |  | 35142.1 | 23906.54 | 35142.1 | 35142.1 | Stevens, Carl | Drexler | 07-Jul-23 | 01-Aug-23 | 03-Jul-23 |  |  | Customer | Customer |  | 0
650057 | 162 COLE RD/ GUE / NS / 200A UG C/W 1X100MM DUCT | 840 - Southgate | 151550 | Active | 95 | ANALYZE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair | 27-Apr-23 |  |  | 7052.46 | 4324.31 | 7052.46 | 7052.46 | Stevens, Carl | Drexler | 15-May-23 | 27-Jul-23 | 15-May-23 | 05-Jun-23 | 29-Jun-23 | Customer | Customer |  | 0
650089 | YORK RD RECONSTRUCTION - CHANGE ORDER | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  | 1 |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650123 | POLE LINE EXPANSION | 840 - Southgate | 152405 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650212 | 240 WATERLOO AVE - TRANSITE DUCT REMOVAL | 840 - Southgate | 151393 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650213 | 77 WESTMOUNT RD - TRANSITE DUCT REMOVAL | 840 - Southgate | 151393 | Active | 70 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650233 | 201 ELMIRA RD S BUILDING C / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650239 | SHADYBROOK CRES UNDERGROUND RECONSTRUCTION | 840 - Southgate | 151453 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650366 | YORK RD PHASE 4 | 840 - Southgate | 151051 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Smith, Alex |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650508 | SUFFOLK ST W-PHASE 1 CHANGE ORDER ESTIMATE | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Chris McDonald |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650518 | 540 HANLON CREEK BLVD / GUE / NS / 3PH PAD TEMP | 840 - Southgate | 151550 | Active | 79 | Upload Completed |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 34963.76 | 1598.58 | 34963.76 | 34963.76 | Dre Danieli |  |  | 27-Jul-23 | [6 empty] | 0
650572 | 423 WOOLWICH ST / GUE / UP / 1PH PAD | 840 - Southgate | 151551 | Active | 45 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650248 | 477 MAIN ST S / RCK / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650637 | 390 YORK RD/ GUE / UP / 200A UG C/W 1X100MM DUCT | 840 - Southgate | 151550 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650770 | 65 MACDONELL ST - SIDEWALK VAULT REPAIR | 840 - Southgate | 151222 | Active | 10 | ACTIVE |  |  | 2023 | Bolton, Ian J | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650915 | 1859 VICTORIA RD S GUE / NS / 1PH POLE | 840 - Southgate | 151550 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650923 | 545, 641 AND 685 SPEEDVALE AVE W - CHANGE ORDER | 840 - Southgate | 151052 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650985 | 1080 SOUTHGATE DR / GUE / NS / 1PH POLE TEMP | 840 - Southgate | 151550 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
645933 | P-25 POPPY DRIVE WEST | 840 - Southgate | 151551 | Active | 50 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651031 | C.O.G. BUS EV CHARGING STATION - FEEDER EXPANSION | 840 - Southgate | 152405 | Active | 10 | ACTIVE |  |  | 2023 | Jakubowski, Mark | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651059 | WOODLAWN RD E RECONSTRUCTION (VICTORIA RD N TO ATTO DR) - SITE SERVICE | 840 - Southgate |  | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Fisher, Cody |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651102 | 2024 DA GUELPH - PMSG089 SWITCHGEAR REPLACEMENT HANLON PKY | 840 - Southgate | 151390 | Active | 48 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651101 | 2024 DA GUELPH - SILVERCREEK PKY N SCADAMATE R1258 | 840 - Southgate | 151390 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651100 | 2024 DA GUELPH - ARKELL RD SCADAMATE R0429 | 840 - Southgate | 151390 | Active | 50 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651146 | 2024 74 & 176 JANEFIELD AVE - TOWNHOMES REHAB - BLOCK 'N' UNITS 2 - 284 | 840 - Southgate | 151453 | Active | 45 | ACTIVE |  |  | 2023 | Beaudrie, Scott | Harrison, Eric |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
650321 | 426 CLAIR RD W / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 45 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651213 | 162 COLE RD/ GUE / NS / 1X100MM DUCT & CABLE | 840 - Southgate | 151550 | Active | 45 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651220 | 65 DELHI ST / GUE / UP / 3PH PAD | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651245 | 426 CLAIR RD W / GUE / NS / 1PH POLE TEMP | 840 - Southgate | 151550 | Active | 45 | ACTIVE |  |  | 2023 | McGregor, Brendan | Shereefdeen, Zuhair |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651281 | P- 25 POPPY DR W - TEMP/GUE/NS | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | Dyce, Stephen A |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651287 | 2024 - POLE REPLACEMENTS SW - BATCH 1 | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651288 | 2024 - POLE REPLACEMENTS SW - BATCH 2 | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651289 | 2024 - POLE REPLACEMENTS SW - BATCH 3 | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651290 | 2024 - POLE REPLACEMENTS SW - BATCH 4 | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651291 | 2024 - POLE REPLACEMENTS SW - BATCH 5 | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651292 | 2024 - POLE REPLACEMENTS SW - BATCH 6 | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651293 | 2024 - POLE REPLACEMENTS SW - BATCH 7 | 840 - Southgate | 151089 | Active | 10 | ACTIVE |  |  | 2023 | Beaudrie, Scott | South-West |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
651372 | 388 ARKELL RD / GUE / NS / 3PH PAD | 840 - Southgate | 151551 | Active | 10 | ACTIVE |  |  | 2023 | McGregor, Brendan | McGregor, Brendan |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 20-Jul-20
2018 | 2018 Alectra Projects | [9 empty] | Alectra Utilities |  |  |  | 188002.18 | 3949874.37 |  | 0 | [5 empty] | 25-Jul-19 | 25-Jul-19
East 2018 | East | [9 empty] | Alectra Utilities |  |  |  | 188002.18 | 3949874.37 |  | 0 | [5 empty] | 25-Jul-19 | 25-Jul-19
EAST-SYSTEM ACCESS | EAST-System Access | [9 empty] | East |  |  |  | 188002.18 | 3949874.37 | 74686364 | 74686364 | [5 empty] | 25-Jul-19 | 25-Jul-19
E-NEW CONN | East-New Connections | [9 empty] | East |  |  |  | 188002.18 | 3918297.1 | 31886408 | 31886408 | [5 empty] | 25-Jul-19 | 25-Jul-19
SNRSD | SOUTH - New Residential Subdivision Development | [9 empty] | East |  |  |  | 92061.48 | 3782938.39 | 13230615 | 13230615 | [5 empty] | 25-Jul-19 | 25-Jul-19
314813 | ( WO 314813) MATTAMY HOMES PHASE 1B (AURORA) (SERVICES ONLY) | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Fitz Randolph, Kim C | 01-Nov-17 |  |  | 0 | 4443.92 | 26068.43 | 26068.43 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
315020 | ( WO 315020) 77 EAGLEVIEW HEIGHTS PH 1 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 01-Nov-17 |  |  | 0 | 384650.32 | 400602.6 | 400602.6 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
315084 | ( WO 315084) GLEN RIDGES ESTATES SUBDIVISION | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Fitz Randolph, Kim C | 01-Nov-17 |  |  | 0 | 245418.7 | 156713.75 | 156713.75 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
313906 | ( WO 313906) MADISON LEGACY BLOCK 11 SUBDIVISION | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 01-Nov-17 |  |  | 0 | 515968.81 | 245197.71 | 245197.71 | Steve Rumble |  | 25-Jul-19 | 28-Dec-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
318503 | (WO318503) George Kirby and Ilan Ramon | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Graham, Bruce W. | 01-Nov-18 |  |  | 0 | 14304.89 |  | 0 | Cory Ruiter |  | 25-Jul-19 | 28-Dec-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
315692 | ( WO 315692) GERMANA PLACE DEVELOPMENT | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alarcon, Alejandro | 01-Nov-17 |  |  | 60794.02 | 54574.58 | 60794.02 | 60794.02 | Steve Rumble |  | 25-Jul-19 | 28-Dec-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
314247 | ( WO 314247) LESILE ELGIN PHASE 1 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alarcon, Alejandro | 01-Nov-17 |  |  | 0 | 1512377.97 | 1529991.2 | 1529991.2 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
310640 | ( WO 310640) THE GRAND CHATEAUS ON BAYVIEW PH2 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Perks, Dan | 01-Nov-17 |  |  | 0 | 8472.79 | 11426.34 | 11426.34 | Steve Rumble | Conelco | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
314733 | ( WO 314733) CORSICA RESIDENTIAL PHASE 3 SUBDIVISION | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 01-Nov-17 |  |  | 0 | 18224.7 | 36709.26 | 36709.26 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
315057 | ( WO 315057) BG AURORA PHASE 1 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Fitz Randolph, Kim C | 01-Nov-17 |  |  | 0 | 685742.26 | 466118.54 | 466118.54 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
316314 | ( WO 316314) 77 EAGLEVIEW HEIGHTS PH 2 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 01-Nov-17 |  |  | 0 | 322679.59 | 328257.73 | 328257.73 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
314731 | (WO 314731) Corsica Residential Development PH2 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 01-Nov-17 |  |  | 31267.46 | 16079.86 | 42502.47 | 42502.47 | Steve Rumble |  | 25-Jul-19 | 07-Sep-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
SICI | SOUTH - New Services Commercial, Industrial, Institutional Services | [9 empty] | East |  |  |  | 95940.7 | 135358.71 | 5000741 | 5000741 | [5 empty] | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
314729 | ( WO 314729) Corsica Ph 1 subdivision | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 01-Nov-17 |  |  | 0 | 64426.45 | 51062.03 | 51062.03 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
317334 | (WO 317334) Toronto Montessori School - Vault to Pad Conversion | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dibratto, Susan | 30-Jan-18 |  |  | 83851 | 63338.3 | 83851 | 83851 | Steve Rumble |  | 25-Jul-19 | 28-Dec-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
315984 | (WO 315984) 211 West Park Ave - Temp. UG, Bradford | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Perks, Dan | 11-Apr-18 |  |  | 0 | 1683.36 | 5975.08 | 5975.08 | Jeremy Wright |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
318214 | (WO318214) 201 Staffern Dr | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 13-Jun-18 |  |  | 12089.7 | 5910.6 | 12089.7 | 12089.7 | Steve Rumble |  | 25-Jul-19 | 18-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
E-ECW | East-Emerging Customer Work | [9 empty] | East |  |  |  | 0 | 31577.27 | 1415157 | 1415157 | [5 empty] | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
SCUP | SOUTH - Unforseen Projects Initiated by the Customer PS | [9 empty] | East |  |  |  | 0 | 31577.27 | 1079136 | 1079136 | [5 empty] | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
317040 | ( WO 317040) Transformer Relocation - LOT 104 STARKWEATHER STREET | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Fitz Randolph, Kim C | 02-Oct-17 |  |  | 0 | 0 | 3821.56 | 3821.56 | Steve Rumble |  | 25-Jul-19 | 28-Dec-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
317115 | ( WO 317115) Pole Installation future riser - LENNOX AVE - PARENT W.O. FOR UNPLANNED | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alarcon, Alejandro | 11-Sep-17 |  |  | 0 | 31577.27 | 26631.98 | 26631.98 | Steve Rumble |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
2019 | 2019 Alectra Projects | [9 empty] | Alectra Utilities |  |  | 21 | 26585987.7 | 26053660.21 |  | 0 | [5 empty] | 01-Nov-17 | 20-Dec-19
West 2019 | West | [9 empty] | Alectra Utilities |  |  |  | 1987220.61 | 4925171.62 |  | 0 | [5 empty] | 06-Jun-18 | 19-Sep-19
452075 | Cogeco Make Ready - Cosby Rd | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 2207.17 |  | 0 | Weaver, Thomas |  | 12-Apr-19 | 19-May-20 | 12-Apr-19 | 12-Apr-19 | 12-Apr-19
452074 | Cogeco Make Ready - Burlington St | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 1090.96 |  | 0 | Weaver, Thomas |  | 29-Mar-19 | 19-May-20 | 29-Mar-19 | 29-Mar-19 | 29-Mar-19
632831 | COGECO MAKE READY - GREEN MOUNTAIN RD | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 19-Sep-19 |  |  | 3582.7 | 1052.99 | 3582.7 | 3582.7 | Dre Danieli |  | 19-Sep-19 | 19-May-20 | 19-Sep-19 | 19-Sep-19 | 19-Sep-19 |  |  |  | 0
452068 | Cogeco Make Ready - Park St | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 07-Mar-19 |  |  | 3175.68 | 2377.57 | 3175.68 | 3175.68 | Carr, Brad | K-Line | 22-Mar-19 | 19-May-20 | 22-Mar-19 | 21-Mar-19 | 21-Mar-19 |  |  |  | 0
451871 | Bell Make Ready - Millen Overpass | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 14-May-19 |  |  | 0 | 4684.6 |  | 0 | Weaver, Thomas |  | 14-May-19 | 19-May-20 | 14-May-19 | 14-May-19 | 14-May-19
452020 | Bell Make Ready - Secord St | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 26-Feb-19 |  |  | 4806.38 | 6893.18 | 4806.38 | 4806.38 | Dan Despres |  | 04-Apr-19 | 19-May-20 | 04-Apr-19 | 21-Mar-19 | 16-May-19 |  |  |  | 0
451925 | 387/389 Ontario St - Down to Strut | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 759.17 |  | 0 | Weaver, Thomas |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
451859 | Cogeco Make Ready - Lodor St | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan |  |  |  | 0 | 770.95 |  | 0 | Weaver, Thomas |  | 11-Jan-19 | 04-May-20 | 11-Jan-19 | 11-Jan-19 | 11-Jan-19
451855 | Rogers Make Ready - Nash Rd | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 22-Oct-18 |  |  | 8666.43 | 16412.66 | 8666.43 | 8666.43 | XPopiel, Joseph |  | 28-Dec-18 | 04-May-20 | 27-Dec-18 | 18-Jan-19 | 29-May-19 |  | Customer |  | 0
451856 | Rogers Make Ready - Chatham St | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 15-Jan-19 |  |  | 7252.05 | 13856.8 | 7252.05 | 7252.05 | XPopiel, Joseph |  | 08-Mar-19 | 04-May-20 | 07-Mar-19 | 25-Apr-19 | 25-Apr-19 |  | Filler |  | 0
451202 | Skyway Bridge Reconstrution | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 0 |  | 0 | Dan Despres |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
451227 | 793 Beach Blvd | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
451242 | Park and Cross Guy Move | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
451245 | 140 Kenilworth Ave N Parkette | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 0 | 0 | 0 | Jakubowski, Mark |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19 |  |  |  | 0
451360 | St Paul Upgrade - Louth to First | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
451358 | 2017 Rogers Work | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
451254 | 300 King St W, Ham | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 2502 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
451516 | 4th Concession Road Upgrade | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | McAlpine, Robert | Paesano, Andrew | 06-May-19 |  |  | 0 | 1150.1 |  | 0 | Weaver, Thomas |  | 06-May-19 | 04-May-20 | 06-May-19 | 06-May-19 | 06-May-19
451263 | 725 Limeridge Road East | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Johnson, William | 01-Oct-18 |  |  | 20766.05 | 27280.07 | 20766.05 | 20766.05 | Koeppe, Jeffrey |  | 07-Nov-18 | 04-May-20 | 01-Nov-18 | 23-Oct-18 | 05-May-19 |  | Customer |  | 0
451678 | Bell Make Ready - S.Service Rd -SCH - work not require now | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 6901.38 |  | 0 | Weaver, Thomas |  | 08-Jan-19 | 04-May-20 | 08-Jan-19 | 08-Jan-19 | 08-Jan-19
451956 | Cogeco Make Ready - Mulberry St | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan |  |  |  | 0 | 1165.77 |  | 0 | Weaver, Thomas |  | 12-Feb-19 | 04-May-20 | 12-Feb-19 | 12-Feb-19 | 12-Feb-19
451825 | Bell Make Ready - Pelham Rd | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 29-Jan-19 |  |  | 7745.38 | 15216.22 | 7745.38 | 7745.38 | Dan Despres |  | 08-Mar-19 | 04-May-20 | 08-Mar-19 | 10-Feb-19 | 10-Feb-19 |  |  |  | 0
451623 | 9281x Reroute from Kenilworth | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Vande Kuyt, Greg | Jolie, Chris | 28-May-19 |  |  | 0 | 97870.24 |  | 0 | Weaver, Thomas |  | 07-May-19 | 04-May-20 | 07-May-19 | 07-May-19 | 07-May-19
452079 | Cogeco Make Ready - Glover Rd | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 26-Mar-19 |  |  | 2218.38 | 2580.76 | 2218.38 | 2218.38 | XPopiel, Joseph |  | 02-May-19 | 04-May-20 | 02-May-19 | 02-May-19 | 02-May-19 |  |  |  | 0
451970 | Rogers Make Ready - Sanatorium Rd | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 17-Jan-19 |  |  | 11356.26 | 18588.02 | 11356.26 | 11356.26 | XPopiel, Joseph |  | 29-Mar-19 | 04-May-20 | 27-Mar-19 | 22-Mar-19 | 22-Mar-19 |  |  |  | 0
452060 | Rogers Make Ready - Hwy 6 | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 08-Mar-19 |  |  | 7878.18 | 4134.08 | 7878.18 | 7878.18 | XPopiel, Joseph |  | 18-Apr-19 | 04-May-20 | 16-Apr-19 | 15-Apr-19 | 15-Apr-19 |  |  |  | 0
451974 | Rogers Make Ready - Frid St | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 12-Feb-19 |  |  | 7436.31 | 12177.06 | 7436.31 | 7436.31 | XPopiel, Joseph |  | 03-Apr-19 | 04-May-20 | 02-Apr-19 | 16-Apr-19 | 21-Apr-19 |  |  |  | 0
451984 | Cogeco Make Ready - Macklin St S | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 15-Jan-19 |  |  | 5315.52 | 9017.08 | 5315.52 | 5315.52 | XPopiel, Joseph |  | 28-Feb-19 | 04-May-20 | 27-Feb-19 | 18-Mar-19 | 18-Mar-19 |  | Filler |  | 0
452041 | Primary Cable Isolation - S.Service | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan |  |  |  | 0 | 555.42 |  | 0 | Weaver, Thomas |  | 07-Mar-19 | 04-May-20 | 07-Mar-19 | 07-Mar-19 | 07-Mar-19
451991 | Rogers Make Ready - Upper Ottawa | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 11-Jan-19 |  |  | 6600.95 | 13553.88 | 6600.95 | 6600.95 | XPopiel, Joseph |  | 26-Feb-19 | 04-May-20 | 25-Feb-19 | 13-Mar-19 | 13-Mar-19 |  | Filler |  | 0
451983 | Rogers Make Ready - Dundas St E | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 15-Jan-19 |  |  | 9858.08 | 10966.9 | 9858.08 | 9858.08 | XPopiel, Joseph |  | 20-Mar-19 | 04-May-20 | 18-Mar-19 | 26-Apr-19 | 26-Apr-19 |  |  |  | 0
451990 | Cogeco Make Ready - Highland Rd W | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 10-Jan-19 |  |  | 3639.39 | 5546.68 | 3639.39 | 3639.39 | Carr, Brad | K-Line | 25-Feb-19 | 04-May-20 | 25-Feb-19 | 29-Jan-19 | 29-Jan-19 |  |  |  | 0
451799 | 7/9 Abby Ave | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 15-Apr-19 |  |  | 12190.77 | 16462.15 | 12190.77 | 12190.77 | Frank Giancola | Wiens | 07-Jun-19 | 04-May-20 | 05-Jun-19 | 30-May-19 | 30-May-19 |  |  |  | 0
451993 | Cogeco Make Ready - Centennial Pkwy | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 15-Jan-19 |  |  | 3166.11 | 5482.4 | 3166.11 | 3166.11 | XPopiel, Joseph |  | 05-Mar-19 | 04-May-20 | 05-Mar-19 | 06-Feb-19 | 06-Feb-19 |  |  |  | 0
451804 | 1675 Burlington St.E | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 15-Apr-19 |  |  | 37873.71 | 54418.87 | 37873.71 | 37873.71 | Andrew Mehlenbacher |  | 03-May-19 | 04-May-20 | 23-Apr-19 | 17-Apr-19 | 17-Apr-19 |  |  |  | 0
452022 | OH Prim Relocate - North Service Rd | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 22-Jan-19 |  |  | 55544.19 | 90894.46 | 55544.19 | 55544.19 | Carr, Brad | B&M | 15-Feb-19 | 04-May-20 | 28-Jan-19 | 14-Jan-19 | 28-Jan-19 |  | Customer |  | 0
451946 | Rogers Make Ready - Mohawk Rd W | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 22-Oct-18 |  |  | 9299.4 | 7949.64 | 9299.4 | 9299.4 | XPopiel, Joseph |  | 07-Jan-19 | 04-May-20 | 02-Jan-19 | 18-Dec-18 | 14-Jan-19 |  |  |  | 0
451558 | Longwood Rd Frid - Aberdeen | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
451268 | St Anthony School - Bollards | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 28-May-19 | 04-May-20 | 28-May-19 | 28-May-19 | 28-May-19
452109 | Pole Relocation - 20 Winona Park Dr | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Jakubowski, Mark | Celic, Dusan | 03-May-19 |  |  | 8160.03 | 6803.28 | 8160.03 | 8160.03 | XPopiel, Joseph |  | 04-Jun-19 | 30-Mar-20 | 03-Jun-19 | 31-May-19 | 04-Jun-19 |  | Customer |  | 0
452033 | 21 Rivercrest Dr | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Kappheim, Adam | Oosterlinck, David | 09-May-19 |  |  | 19491.69 | 19328.04 | 19491.69 | 19491.69 | Carr, Brad | K-Line | 24-May-19 | 30-Mar-20 | 13-May-19 | 13-May-19 | 13-May-19 |  |  |  | 0
451781 | Life-288 Glover Rd | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark | 04-Dec-18 |  |  | 56321.81 | 51724.33 | 56321.81 | 56321.81 | Koeppe, Jeffrey |  | 31-Jan-19 | 13-Jun-19 | 16-Jan-19 | 11-Jan-19 | 31-May-19 |  | Customer |  | 0
451752 | 97 Lakeview Dr, Stoney Creek | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 07-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
451215 | 125 Rifle Range Rd, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 0 | 0 | 0 | Weaver, Thomas |  | 06-Jun-19 | 07-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 |  |  |  | 0
451748 | 905 Upper Ottawa St, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bennett, Aaron | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 07-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
16171 | 95 Rockcliffe | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
15772 | 1318 Upper Wellington St | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
15767 | 659 Parkdale - Temp Upgrade | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 22-Jul-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
15776 | 150 James St.po\S | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
16160 | 539 Barton St.E | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
16164 | 1344 Highway 8 | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
15771 | 170 Concession St | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
16161 | 2 Ottawa St.N | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
16165 | 2411 Barton St.E (Rear) | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Oosterlinck, David | 06-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19 | 06-Jun-19
16346 | 30 Golfwood Dr | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Djuric, Zdravko | 05-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 05-Jun-19 | 05-Jun-19 | 05-Jun-19 | 05-Jun-19 | 05-Jun-19
16358 | 201 Highway 5 West - Flamborough | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Djuric, Zdravko | 05-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 05-Jun-19 | 05-Jun-19 | 05-Jun-19 | 05-Jun-19 | 05-Jun-19
16354 | 4 Penlake Crt - Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Djuric, Zdravko | 05-Jun-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 05-Jun-19 | 05-Jun-19 | 05-Jun-19 | 05-Jun-19 | 05-Jun-19
12696 | 2 Witherspoon St - Trouble Call | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 61389.58 |  | 0 | Hotham, Matthew |  | 28-May-19 | 31-May-19 | 28-May-19 | 28-May-19 | 28-May-19
14444 | St Catharines Locate Requests | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19
14098 | HCE Fiber Installations 2015 | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jolie, Chris | 28-May-19 |  |  | 0 | 0 |  | 0 | Hewitson, Trevor |  | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19
451256 | 2017 St Cath LBDS Replacement | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19
14420 | 197 King Wm - Steel Lounge | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19
451228 | 500 James St N | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 28-May-19 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19 | 28-May-19
15474 | 97 5th Concession Rd. E FLA | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 904.17 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
15487 | 75 Oliver Lane STC | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 882.84 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
451829 | 75 Blake St. HAM | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 933.11 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
451425 | 1615 Upper Wellington St. | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 1463.79 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
16278 | 80 Queen St. S | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 2442.12 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
15448 | 257 Main St. E HAM | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 684.92 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
15469 | 52 Brydale Crt. DUN | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 746.49 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
14683 | 1040 Main St E (Gage Park) | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 3702.04 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
451349 | 367 5th Concession Rd East | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 1756.59 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
16284 | 30 John St. N | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 1875.65 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
16288 | 1457 Main St. W Ham | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 1234.3 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
16274 | 113-123 Emerald St. S | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 1416.53 |  | 0 | Weaver, Thomas |  | 06-May-19 | 24-May-19 | 06-May-19 | 06-May-19 | 06-May-19
13256 | 2017 Pole Residual | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 05-Jul-18 |  |  | 26811.88 | 26264.08 | 26811.88 | 26811.88 | XPopiel, Joseph |  | 23-Nov-18 | 10-May-19 | 14-Nov-18 | 18-Jan-19 | 13-Mar-19 |  | Filler |  | 0
16443 | Cogeco Make Ready - Bond St N | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 11-Jan-19 |  |  | 2207.97 | 1930.35 | 2207.97 | 2207.97 | Carr, Brad | K-Line | 21-Feb-19 | 07-May-19 | 21-Feb-19 | 29-Jan-19 | 29-Jan-19 |  |  |  | 0
14800 | Cameron Drive Deficiencies | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Wardell, Paul | 01-May-19 |  |  | 0 | 61068.27 |  | 0 | Jakubowski, Mark |  | 07-May-19 | 07-May-19 | 07-May-19 | 07-May-19 | 07-May-19
451681 | Stations Facility Upgrades | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Billone, Justin | 07-May-19 |  |  | 0 | 33077.48 |  | 0 | Weaver, Thomas |  | 07-May-19 | 07-May-19 | 07-May-19 | 07-May-19 | 07-May-19
16536 | Cogeco Make Ready - Broadway Ave | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 28-Feb-19 |  |  | 3887.15 | 5225.39 | 3887.15 | 3887.15 | Dan Despres |  | 18-Apr-19 | 07-May-19 | 18-Apr-19 | 21-Mar-19 | 09-Apr-19 |  |  |  | 0
16283 | 2 Hillyard St. HAM | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Montgomery, Michael | 06-May-19 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 06-May-19 | 06-May-19 | 06-May-19 | 06-May-19 | 06-May-19
16039 | 29 Powerglen Rd, St.Catharines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Laus, Tomislav | 25-Jan-19 |  |  | 15686.39 | 13871.36 | 15686.39 | 15686.39 | Frank Giancola |  | 01-Mar-19 | 02-May-19 | 22-Feb-19 | 13-Feb-19 | 14-Mar-19 |  | Customer |  | 0
15717 | 289 Winona Rd, Stoney Creek | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Laus, Tomislav | 27-Nov-18 |  |  | 2454.53 | 1304.26 | 2454.53 | 2454.53 | Carr, Brad | N/A | 31-Dec-18 | 02-May-19 | 31-Dec-18 | 21-Mar-19 | 21-Mar-19 |  | Customer |  | 0
15551 | 8-12-14-16 Brookdale Ave | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Rolfe, Eric | 12-Mar-18 |  |  | 22406.6 | 27720.6 | 22406.6 | 22406.6 | Carr, Brad |  | 20-Apr-18 | 02-May-19 | 16-Apr-18 | 11-Jul-18 | 22-Jan-19 |  | Customer |  | 0
14439 | Glenridge Pedestals - 2018 | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Johnson, William | 06-Oct-17 |  |  | 13092.47 | 1309.32 | 13092.47 | 13092.47 | Frank Giancola |  | 31-Aug-18 | 26-Apr-19 | 27-Aug-18 | 03-May-19 | 03-May-19 |  | Locates |  | 0
14655 | Elgin TS Bus Relocations | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Jolie, Chris |  |  |  | 0 | 2324701.67 |  | 0 | Jakubowski, Mark |  | 23-Apr-19 | 23-Apr-19 | 23-Apr-19 | 23-Apr-19 | 23-Apr-19
16413 | 2595 Fifth St. | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dragojevic, Igor | 24-Jan-19 |  |  | 11297.18 | 10962.16 | 11297.18 | 11297.18 | Frank Giancola |  | 28-Feb-19 | 18-Apr-19 | 27-Feb-19 | 21-Feb-19 | 18-Mar-19 |  | Customer |  | 0
13225 | Ottawa/Campbell Rear Alley Rebuild | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Webb-Murre, Paige | 17-Aug-18 |  |  | 134647.48 | 144945.22 | 127053.43 | 134647.48 | Destefano, Nick |  | 09-Nov-18 | 18-Apr-19 | 15-Oct-18 | 24-Sep-18 | 03-Jan-19 |  | Customer |  | 7,594.05
15353 | 16 Astra Street - Pad Relocation | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Webb-Murre, Paige | 10-Aug-18 |  |  | 20910.64 | 2977.24 | 20910.64 | 20910.64 | Andrew Mehlenbacher |  | 12-Nov-18 | 09-Apr-19 | 05-Nov-18 | 02-Apr-19 | 02-Apr-19 |  | MC/PUCC Permit |  | 0
16175 | 460 Sanatorium Rd | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Oosterlinck, David | 21-Dec-18 |  |  | 14248.15 | 17116.21 | 14248.15 | 14248.15 | Roy Owen |  | 20-Feb-19 | 29-Mar-19 | 06-Feb-19 | 23-Jan-19 | 30-Jan-19 |  | Customer |  | 0
16450 | 140 Glendale Ave, St. Kitts | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Patel, Ketan | 18-Dec-18 |  |  | 3854.43 | 3661.56 | 3854.43 | 3854.43 | Carr, Brad |  | 28-Jan-19 | 29-Mar-19 | 28-Jan-19 | 15-Jan-19 | 15-Jan-19 |  |  |  | 0
16340 | 542 Upper Sherman Ave - Hamilton | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Djuric, Zdravko | 06-Sep-18 |  |  | 9962.68 | 8113.45 | 9962.68 | 9962.68 | Koeppe, Jeffrey |  | 19-Oct-18 | 29-Mar-19 | 18-Oct-18 | 25-Jan-19 | 25-Jan-19 |  | Customer |  | 0
16428 | 5A Hazel St, St. Catharines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Patel, Ketan | 03-Dec-18 |  |  | 8104.18 | 7524.78 | 8104.18 | 8104.18 | Carr, Brad |  | 08-Jan-19 | 29-Mar-19 | 08-Jan-19 | 14-Jan-19 | 14-Jan-19 |  |  |  | 0
15964 | Jacobson UG Services | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Webb-Murre, Paige | 18-Apr-18 |  |  | 11330.04 | 25348.48 | 9949.54 | 11330.04 | Hewitson, Trevor |  | 11-Jun-18 | 29-Mar-19 | 11-Jun-18 | 06-Jun-18 | 08-Jan-19 |  | Customer |  | 1,380.50
16332 | 124 St. David's Rd, St. Catharines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Patel, Ketan | 14-Dec-18 |  |  | 13772.76 | 15893.84 | 13772.76 | 13772.76 | Hewitson, Trevor |  | 01-Feb-19 | 29-Mar-19 | 01-Feb-19 | 07-Jan-19 | 07-Jan-19 |  |  |  | 0
15502 | Horning TS - Switch Gear Rebuild | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Billone, Justin | 27-Jul-18 |  |  | 1144881.53 | 1299172.71 | 1144881.53 | 1144881.53 | Roy Owen |  | 30-Nov-18 | 28-Mar-19 | 08-Oct-18 | 29-Oct-18 | 25-Feb-19 |  | Customer |  | 0
15477 | 460 Dundas St. E | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Montgomery, Michael | 26-Apr-18 |  |  | 29578.22 | 38415.96 | 29578.22 | 29578.22 | Koeppe, Jeffrey |  | 11-Jun-18 | 28-Mar-19 | 04-Jun-18 | 25-Jul-18 | 19-Feb-19 |  | Customer |  | 0
15857 | 265, 275 Sherman Ave N, Hamilton | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bennett, Aaron | 25-Sep-18 |  |  | 25882.02 | 30116.36 | 25882.02 | 25882.02 | Andrew Mehlenbacher |  | 27-Nov-18 | 28-Mar-19 | 05-Nov-18 | 03-Jan-19 | 16-Jan-19 |  | N/A |  | 0
16033 | 391 Highland Rd E, Stoney Creek | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Laus, Tomislav | 06-Dec-18 |  |  | 18031.36 | 19941.29 | 18031.36 | 18031.36 | Koeppe, Jeffrey |  | 30-Jan-19 | 28-Mar-19 | 29-Jan-19 | 19-Dec-18 | 25-Jan-19 |  |  |  | 0
15874 | 1132 Lakeshore Rd W, St Catharines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paesano, Andrew | 26-Jan-18 |  |  | 1766.74 | 312.08 | 1766.74 | 1766.74 | Hewitson, Trevor |  | 03-Apr-18 | 28-Mar-19 | 03-Apr-18 | 16-Jan-19 | 16-Jan-19 |  | Customer |  | 0
16407 | 27 Ridgewood Rd | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dragojevic, Igor | 14-Dec-18 |  |  | 16666.27 | 15323.31 | 16666.27 | 16666.27 | Frank Giancola |  | 07-Feb-19 | 22-Mar-19 | 04-Feb-19 | 17-Jan-19 | 13-Feb-19 |  | Customer |  | 0
16323 | East 8th St Pole Replacement | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Webb-Murre, Paige | 26-Sep-18 |  |  | 27345.6 | 24203.24 | 23445.6 | 27345.6 | XPopiel, Joseph |  | 05-Feb-19 | 22-Mar-19 | 28-Jan-19 | 08-Jan-19 | 25-Jan-19 |  |  |  | 3,900.00
16403 | Cogeco Make Ready - Broadway Ave | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 12-Dec-18 |  |  | 2451.12 | 2825.65 | 2451.12 | 2451.12 | Frank Giancola |  | 14-Jan-19 | 19-Mar-19 | 14-Jan-19 | 03-Jan-19 | 03-Jan-19 |  |  |  | 0
16317 | Cogeco Make Ready - Mountain Ave | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Celic, Dusan | 13-Dec-18 |  |  | 4416.88 | 2332.07 | 4416.88 | 4416.88 | XPopiel, Joseph |  | 17-Jan-19 | 19-Mar-19 | 17-Jan-19 | 10-Jan-19 | 10-Jan-19 |  |  |  | 0
15916 | 2018-Pole Residuals-St. Catherines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Rolfe, Eric | 16-Jul-18 |  |  | 89180.89 | 80951.52 | 89180.89 | 89180.89 | Dan Despres |  | 03-Jan-19 | 22-Feb-19 | 17-Dec-18 | 10-Dec-18 | 21-Jan-19 |  | Locates |  | 0
16538 | Cogeco Make Ready - John St N | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Celic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 12-Feb-19 | 12-Feb-19 | 12-Feb-19 | 12-Feb-19 | 12-Feb-19
15572B | HUC600 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 5908.95 |  | 0 | Weaver, Thomas |  |  | 09-Jan-19
15571B | HUC345 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 8163.75 |  | 0 | Weaver, Thomas |  |  | 09-Jan-19
15568B | HUC185 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 6695.02 |  | 0 | Weaver, Thomas |  |  | 09-Jan-19
15567B | HUC91 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 7292.34 |  | 0 | Weaver, Thomas |  |  | 09-Jan-19
15569B | HUC190 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 8280.92 |  | 0 | Weaver, Thomas |  |  | 09-Jan-19
15566B | HUC43 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 10371.07 |  | 0 | Weaver, Thomas |  |  | 09-Jan-19
15573B | HUC601 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 6801.12 |  | 0 | Weaver, Thomas |  |  | 09-Jan-19
13101 | December Ice Storm Damage St. Catharines | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Jakubowski, Mark |  |  |  | 0 | 0 |  | 0 | Stinson, Jim |  |  | 26-Apr-19
15575B | HUC1361 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 1164 |  | 0 | Weaver, Thomas |  |  | 20-Dec-18
451458 | HUC250 | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 1280.07 |  | 0 | Weaver, Thomas |  |  | 20-Dec-18
451463 | HUC1045 - FIT - 1045 Upper Paradise Road | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Lustrinelli, Mark |  |  |  | 0 | 272 |  | 0 | Weaver, Thomas |  |  | 20-Dec-18
451955 | 70 Bobolink | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Oct-18
13420 | Paramount Sub- Additional Tx's | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Billone, Justin | 05-Feb-18 |  |  | 0 | 383.76 |  | 0 | Destefano, Nick |  | 26-Mar-19 | 06-Jul-18 | 26-Mar-19 | 26-Mar-19 | 26-Mar-19
451774 | 149 Read Rd | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 12-Jun-18
451541 | 19 Page St | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Oct-17
451472 | 1160 Lakeshore Rd W, St Catharines | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2019 | Gamboa, Henry | Morris, Mark |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 26-Jun-17
13011A | 36 Queenston St(SCH) | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alectra Utilities | 16-May-19 |  |  | 0 | 10141.7 |  | 0 | Weaver, Thomas |  | 16-May-19 | 16-May-19 | 16-May-19 | 16-May-19 | 16-May-19
CN 2019 | CN | [9 empty] | Alectra Utilities |  |  |  | 7291694.83 | 7651071.53 |  | 0 | [5 empty] | 16-Apr-18 | 20-Dec-19
450802 | MAYFIELD RD AND BRAMALEA RD | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | D'Ermes, Michael | 29-May-19 |  |  | 96705.33 | 90470.93 | 96705.33 | 96705.33 | Richard Cuddy |  | 10-Oct-19 | 09-Aug-22 | 10-Sep-19 | 17-Jul-19 | 30-Sep-19 |  |  |  | 0
450804 | WINSTON CHURCHILL/EMBELTON | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 06-Jun-19 |  |  | 100337.39 | 91348.42 | 100337.39 | 100337.39 | Richard Cuddy |  | 14-Nov-19 | 09-Aug-22 | 21-Oct-19 | 06-Aug-19 | 10-Sep-19 |  |  |  | 0
450969 | Cable Injection - Brampton (F3-G3-H3) - 2019 | 805 - Sandalwood | 150571 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | D'Ermes, Michael | 27-Mar-19 |  |  | 1343485.79 | 1057639.71 | 1343485.79 | 1343485.79 | Simon Evason | Nvinium | 29-Nov-19 | 09-Aug-22 | 15-Apr-19 | 20-May-19 | 20-Dec-19 |  | Contractor |  | 0
450108 | INSULATOR REPLACMENT 2019 | 805 - Sandalwood | 151021 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 13-Nov-18 |  |  | 317091.7 | 265119.11 | 317091.7 | 317091.7 | John Costa |  | 31-Dec-19 | 09-Aug-22 | 04-Feb-19 | 11-Mar-19 | 20-Dec-19 |  | Filler |  | 0
450945 | BOVAIRD,BRAMALEA TO TORBRAM - OH Portion | 805 - Sandalwood | 150375 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 25-Jun-19 |  |  | 409445.62 | 402470.51 | 382397.02 | 409445.62 | Reaburn, Jeff | A&W | 31-Oct-19 | 09-Aug-22 | 06-Aug-19 | 12-Jul-19 | 04-Dec-19 |  |  |  | 27,048.60
450959 | PROFESSOR LK & FAIRWAY HEIGHTS | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Miller, Michael | 08-Jul-19 |  |  | 1443064.91 | 1545985.56 | 1443064.91 | 1443064.91 | Mark Bobanovic | Transpw | 15-Nov-19 | 24-Apr-23 | 12-Aug-19 | 23-Aug-19 | 20-Dec-19 |  | Contractor |  | 0
450213 | Cable Injection - Brampton H3 - 2019 | 805 - Sandalwood | 150571 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | D'Ermes, Michael | 27-Mar-19 |  |  | 1093100.86 | 417621.3 | 1093100.86 | 1093100.86 | Simon Evason | Nvinium | 29-Nov-19 | 22-Apr-21 | 15-Apr-19 | 10-Jun-19 | 20-Dec-19 |  | Contractor |  | 0
450212 | BOVAIRD - QUEEN, MAIN - KENNDY Cable injectoin G3 - 2019 | 805 - Sandalwood | 150571 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | D'Ermes, Michael | 27-Mar-19 |  |  | 200146.09 | 201876.56 | 200146.09 | 200146.09 | Simon Evason | Nvinium | 29-Nov-19 | 01-Feb-21 | 15-Apr-19 | 16-Sep-19 | 20-Dec-19 |  | Contractor |  | 0
450633 | Creditview - Dist Automation 2019 | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 21-May-19 |  |  | 95000 | 79818.78 | 95000 | 95000 | Richard Cuddy |  | 19-Sep-19 | 25-Jan-21 | 19-Aug-19 | 11-Jul-19 | 02-Aug-19 |  |  |  | 0
450806 | QUEEN ST E & GATEWAY BLVD | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 06-Jun-19 |  |  | 99632 | 105214.24 | 99632 | 99632 | Richard Cuddy |  | 28-Oct-19 | 25-Jan-21 | 01-Oct-19 | 19-Sep-19 | 27-Nov-19 |  |  |  | 0
450349 | WINSTON CHURCHILL & BOVAIRD - PCB Tx. | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 14-Jun-19 |  |  | 14637.44 | 20773.72 | 14637.44 | 14637.44 | John Costa |  | 10-Sep-19 | 27-Jan-21 | 03-Sep-19 | 02-Aug-19 | 02-Aug-19 |  | Filler |  | 0
450193 | VARIOUS LOCATIONS-BRAMPTON - Phase 2 UG Portion | 805 - Sandalwood | 150277 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Miller, Michael | 25-Jun-19 |  |  | 150698.11 | 155720.32 | 150698.11 | 150698.11 | Nichol, Sandi |  | 30-Nov-19 | 25-Jan-21 | 03-Sep-19 | 28-Oct-19 | 26-Nov-19 |  |  |  | 0
450944 | 10F6 Extension - MS-1 Elizabeth St 4.16kV Voltage Conversion - Ph5 - OH Portion | 805 - Sandalwood | 150424 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Casey, Ryan | 16-May-19 |  |  | 706774.86 | 650698.99 | 679386.53 | 706774.86 | Reaburn, Jeff | A&W | 28-Nov-19 | 25-Jan-21 | 02-Jul-19 | 08-Jul-19 | 04-Dec-19 |  |  |  | 27,388.33
450237 | 4.16KV-27.6KV PH2 CONV(2019) | 805 - Sandalwood | 150424 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Miller, Michael | 19-Dec-18 |  |  | 546377.83 | 1538894.8 | 546377.83 | 546377.83 | Nichol, Sandi |  | 08-Apr-19 | 10-Aug-20 | 17-Dec-18 | 17-Dec-18 | 13-May-19 |  |  |  | 0
450842 | Churchville Rd - 27.6kV Pole Line Rebuild | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2019 |  | D'Ermes, Michael | 26-Oct-18 |  |  | 422510.38 | 878561.92 | 407090.5 | 422510.38 | Reaburn, Jeff | A&W | 28-Dec-18 | 10-Aug-20 | 12-Nov-18 | 19-Nov-18 | 22-Feb-19 |  |  |  | 15,419.88
450939 | 239 QUEEN ST E -tx | 805 - Sandalwood | 150494 | Inactive | 99 | CANCELLED |  |  | 2019 | Agostini, Robert | Casey, Ryan | 07-Nov-18 |  |  | 79182.91 | 15754.22 | 79182.91 | 79182.91 | Simon Evason |  | 24-Apr-19 | 06-Jan-20 | 23-Apr-19 | 20-Dec-19 | 20-Dec-19 |  | Customer |  | 0
450948 | 9025 TORBRAM RD - tx - Capital | 805 - Sandalwood | 150494 | Inactive | 99 | CANCELLED |  |  | 2019 | Agostini, Robert | Miller, Michael | 07-Nov-18 |  |  | 25870.9 | 3015.54 | 25870.9 | 25870.9 | Simon Evason |  | 04-Nov-19 | 06-Jan-20 | 04-Nov-19 | 20-Dec-19 | 20-Dec-19 |  | Filler |  | 0
NA37 | 296 ORENDA RD. | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Cavanaugh, Danny | 15-Apr-19 |  |  | 11724 | 9397.87 | 11724 | 11724 | Simon Evason |  | 17-May-19 | 27-Jun-19 | 13-May-19 | 24-May-19 | 27-Apr-19 |  | Customer |  | 0
NB21 | 10254 Hurontario St. | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Cavanaugh, Danny | 12-Apr-19 |  |  | 7000 | 3592.32 | 7000 | 7000 | Simon Evason |  | 03-May-19 | 27-Jun-19 | 02-May-19 | 24-May-19 | 02-May-19 |  | Customer |  | 0
W938 | 59 MCLAUGHLIN ROAD NORTH | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bojanic, Dusan | 23-Apr-18 |  |  | 5810 | 6565.44 | 5810 | 5810 | Simon Evason |  | 07-May-18 | 27-Jun-19 | 07-May-18 | 07-May-18 | 23-May-19 |  | Customer |  | 0
T372 | 9659 Winston Churchill Blvd | 805 - Sandalwood |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Cavanaugh, Danny | 03-Apr-18 |  |  | 16750 | 10346.27 | 16750 | 16750 | Simon Evason |  | 26-Apr-18 | 23-May-19 | 23-Apr-18 | 16-Apr-18 | 18-Jan-19 |  | Customer |  | 0
Y891 | FERNFOREST DR AND KALAHARI RD - SG | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Casey, Ryan | 07-Nov-18 |  |  | 106348.71 | 100185 | 106348.71 | 106348.71 | Richard Cuddy |  | 19-Aug-19 | 30-Apr-19 | 05-Aug-19 | 05-Feb-19 | 19-Feb-19 |  |  |  | 0
G841 | RICHMOND DR & BARTLEY BULL PKY | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Hotham, Matthew |  |  | 14-Nov-18
D285 | VARIOUS LOCATIONS-KENVIEW BLD | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Casey, Ryan |  |  |  | 0 | 0 |  | 0 | Hotham, Matthew |  |  | 05-Nov-18
Y155 | TOMKEN RD. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Aug-18
L737 | Queen St and The Gore Road -Two Stub poles | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Central North |  |  |  | 0 | 0 | 0 | 0 | Jakubowski, Mark |  |  | 12-Oct-17 | [6 empty] | 0
X103 | SANDALWOOD PKY W & VETERANS DR | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-Apr-18
T883 | 25 PEEL CENTRE DR | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Jan-18
M806 | Rivermont Rd and Fiancial Dr. (M173) | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Erzek, Ryan |  |  |  | 0 | 0 |  | 0 | Richard Cuddy |  |  | 19-Jan-18
T538 | CREDITVIEW RD & WANLESS DR | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Armstrong, Colby |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 11-Jan-18
O842 | 58 church St E | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Erzek, Ryan |  |  |  | 0 | 0 |  | 0 | Nichol, Sandi |  |  | 10-Jan-18
T543 | 5203 OLD CASTLEMORE RD | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 05-Jan-18
M966 | Dist Cable Rehab 42M46 & 42M476 - Electrical Work | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Gamboa, Henry |  |  |  | 0 | 0 |  | 0 | Simon Evason |  |  | 02-Jan-18
P616 | 1100 CENTRAL PARK DR. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 21-Dec-17
H145 | H145 | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Central North |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 20-Dec-17
N482 | Intermodal and CN Rail | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
C948 | sw corner Queen St. & CreditviewRd. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
P745 | 11613 Bramalea Rd | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
N479 | Hwy 407 and Airport Rd | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
N672 | 10639 Heartlake Rd | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
Q188 | 101 West Drive | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
N623 | 200 STEELWELL RD | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
N649 | 200 STEELWEL RD (TEMP SERVICE ) | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
P491 | 130 SANDALWOOD PKWY WEST | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
B136 | Remembrance Rdr | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Hotham, Matthew |  |  | 19-Dec-17
C922 | 2001 North Park Dr | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
M598 | 4864 Castlemore Rd | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
C335 | 56A Wellington St. W. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
N194 | SE corner Bovaird Dr. and Hurontario St. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
J185 | 10916 Coleraine Dr. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
N359 | 1105 Queen St E | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
N771 | 31 Hansen Rd.S. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
P748 | 7625 Finch Ave. W. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
B287 | 66A Main St.S. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
Z704 | NE corner Steeles and Chinguacousy Rd | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
R468 | 2074/2084 Steeles Ave. E. | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cavanaugh, Danny |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
M895 | 23 Avondale Blvd | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bojanic, Dusan |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
B878 | Geddes lane n of Demaris Dr | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
P198 | 1685 Queen St E | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Ferry, Rodnne |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Dec-17
B363 | WILLIAMS PKWY & ROYAL WEST DR | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Central North |  |  |  | 0 | 0 |  | 0 | Simon Evason |  |  | 14-Dec-17
B872 | MAYFIELD RD AND DIXIE ROAD | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Gamboa, Henry |  |  |  | 0 | 0 |  | 0 | Simon Evason |  |  | 14-Dec-17
N215 | DIXIE RD & SANDALWOOD PKY E | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | D'Ermes, Michael |  |  |  | 0 | 0 |  | 0 | Hotham, Matthew |  |  | 14-Dec-17
F194 | WILLIAMS PKWY & ROYAL WEST DR | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Erzek, Ryan |  |  |  | 0 | 0 |  | 0 | Simon Evason |  |  | 14-Dec-17
M894 | 22 NEOPOLITAN RD | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Erzek, Ryan |  |  |  | 0 | 0 |  | 0 | Simon Evason |  |  | 14-Dec-17
F193 | WILLIAMS PKWY & ROYAL WEST DR | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Erzek, Ryan |  |  |  | 0 | 0 |  | 0 | Simon Evason |  |  | 14-Dec-17
I917 | BONNIE BRAE & CHINGUACOUSY | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Erzek, Ryan |  |  |  | 0 | 0 |  | 0 | Simon Evason |  |  | 12-Dec-17
D062 | Queen Street west – Chinguacousy Road to Mississauga Road- pull old poles | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Central North |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 12-Oct-17
CS 2019 | CS | [9 empty] | Alectra Utilities |  |  |  | 3581495.43 | 3442527.57 |  | 0 | [5 empty] | 04-Dec-17 | 09-Apr-19
395604 | 368 Meadow Wood Lane | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 | Kafel, Krzysztof | Watters, Maxwell | 03-Dec-18 |  |  | 0 | 19281.13 | 0 | 0 | Mark Bobanovic | K-Line | 07-Feb-19 | 04-May-20 | 05-Dec-18 | 05-Dec-18 | 07-Feb-19 |  |  |  | 0
413809 | 27.6KV FEEDER EXTENSION TRADERS - HURONTARIO-KENNEDY | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2019 | Antonakos, Tony | Cudzilo, Tomasz |  |  |  | 0 | 603.19 |  | 0 | Paul Tremblay |  |  | 04-May-20
427670 | DUNDAS ST W E-O DUNWIN DR - REPLACE LT31135 | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2019 | Carter, Gordon | Tempra, Troylan | 18-Apr-19 |  |  | 51333.75 | 0 | 51333.75 | 51333.75 | Paul Murphy |  | 30-Aug-19 | 30-Aug-19 | 19-Aug-19 | [5 empty] | 0
427696 | SG LT31039 - SHERIDAN PARK DR W-O HOMELANDS | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2019 | Carter, Gordon | Tempra, Troylan | 22-Apr-19 |  |  | 39120.19 | 0 | 39120.19 | 39120.19 | Paul Murphy |  | 15-Aug-19 | 15-Aug-19 | 12-Aug-19 | [5 empty] | 0
389589 | 2270 Speakman Dr .- Muslim Assoc. Conversion to Alectra TX - | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Zaghloul, Sam | 02-Oct-18 |  |  | 146187.67 | 149630.82 | 122553.67 | 146187.67 | Macdougall, Stephen |  | 20-Dec-18 | 26-Apr-19 | 03-Dec-18 | 07-Nov-18 | 22-Feb-19 |  | Customer |  | 23,634.00
424874 | POLE RELOCATION - WCH BLVD | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Truong, Jimmy | Truong, Jimmy | 23-Jan-19 |  |  | 8047.16 | 8491.43 | 8047.16 | 8047.16 | Paul Murphy |  | 06-Feb-19 | 08-Apr-19 | 06-Feb-19 | 07-Feb-19 | 29-Mar-19 |  |  |  | 0
417261 | 21 COVENTRY RD POLE TRANSFER | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Truong, Jimmy |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Apr-19
400944 | 3210 Hurontario Street-Cooksville GO Station | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Zaghloul, Sam | 03-Oct-18 |  |  | 226138.68 | 235205.86 | 226138.68 | 226138.68 | Macdougall, Stephen |  | 14-Dec-18 | 09-Apr-19 | 05-Nov-18 | 16-Oct-18 | 18-Mar-19 |  | Customer |  | 0
373579 | 938 East Ave. - Region of Peel Paramedics Station - TEMP SERV. | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bharosi, Mohindra | 04-Dec-17 |  |  | 18513.72 | 14992.85 | 18513.72 | 18513.72 | Bourgeois, Craig |  | 12-Jun-18 | 25-Mar-19 | 01-Mar-18 | 13-Aug-18 | 26-Feb-19 |  | Customer |  | 0
374045 | 3105 Argentia Rd. - Tesla Supercharger Meadowvale | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Macasaet, Ricardo | 30-Jul-18 |  |  | 229169.66 | 229077.17 | 229169.66 | 229169.66 | Macdougall, Stephen | Somervl | 09-Nov-18 | 25-Mar-19 | 29-Oct-18 | 21-Dec-18 | 15-Feb-19 |  | Customer |  | 0
335071 | The Grand Mirage Phase 3 Bldg C - 349 Rathburn Rd W | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Macasaet, Ricardo | 04-Dec-17 |  |  | 78689.94 | 68740.64 | 78689.94 | 78689.94 | Macdougall, Stephen |  | 26-Jul-18 | 09-Apr-19 | 05-Jul-18 | 07-May-18 | 15-Mar-19 |  | Customer |  | 0
417471 | 7605 BATH ROAD - HOPE AERO SERVICE UPGRADE | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Bharosi, Mohindra | 05-Nov-18 |  |  | 83826.74 | 71368.69 | 83826.74 | 83826.74 | Macdougall, Stephen |  | 18-Jan-19 | 25-Mar-19 | 10-Dec-18 | 03-Dec-18 | 14-Jan-19 |  | Customer |  | 0
358070 | FOLKWAY DR. MF FRO | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Cudzilo, Tomasz | 23-Apr-18 |  |  | 794223.56 | 791481.16 | 694213.33 | 794223.56 | Paul Tremblay |  | 13-Aug-18 | 25-Mar-19 | 01-May-18 | 30-Mar-18 | 15-Feb-19 |  |  |  | 100,010.23
325593 | HOLBURNE/OGDEN OH REBUILD - SE | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Matai, Ihssan (Sam) | 16-Jul-18 |  |  | 772101.68 | 564475.79 | 1018209.67 | 772101.68 | Rob Elliot |  | 27-Nov-18 | 25-Mar-19 | 06-Aug-18 | 05-Sep-18 | 28-Feb-19 |  |  |  | -246,107.99
421999 | PSN MAKE READY -NINTH LINE (DEEPWOODS HEIGHTS TO JANICE DR) | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Gonzales, Leonard |  |  |  | 0 | 18230.94 |  | 0 | Weaver, Thomas |  | 31-Jan-19 | 25-Mar-19 | 06-Dec-18 | 06-Dec-18 | 31-Jan-19
404620 | 2299 HOGAN DRIVE | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Zaghloul, Sam | 25-Sep-18 |  |  | 214986.89 | 216659.92 | 214986.89 | 214986.89 | Macdougall, Stephen |  | 13-Nov-18 | 25-Mar-19 | 25-Sep-18 | 25-Sep-18 | 04-Mar-19 |  |  |  | 0
418714 | 2017/18 - FOLKWAY SG1758 BACKU | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Cudzilo, Tomasz |  |  |  | 0 | 93987.97 |  | 0 | Paul Tremblay |  | 24-Jan-19 | 25-Mar-19 | 14-Jan-19 | 14-Jan-19 | 24-Jan-19
382854 | Adonis Supermarket - 2561 Stanfield Rd | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Huo, Lisa | 20-Feb-19 |  |  | 121203.39 | 84824.1 | 121203.39 | 121203.39 | Macdougall, Stephen |  | 06-Apr-19 | 17-Apr-19 | 06-Mar-19 | 25-Feb-19 | 15-Mar-19 |  |  |  | 0
425797 | MALTON GO STATION - RAISE NEUTURAL CONDUCTORS | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Watters, Maxwell |  |  |  | 0 | 0 | 6000 | 6000 | Weaver, Thomas |  | 09-Apr-19 | 13-Feb-19 | 09-Apr-19 | 09-Apr-19 | 09-Apr-19 |  |  |  | 0
405331 | 648 HAZELHURST RD - SUPER SUCK | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Bharosi, Mohindra | 06-Jul-18 |  |  | 53193.72 | 6238.03 | 53193.72 | 53193.72 | Bourgeois, Craig |  | 06-Sep-18 | 13-Feb-19 | 27-Aug-18 | 05-Sep-18 |  |  | Customer |  | 0
415978 | POLE REPLACEMENT - BATCH #12 (6 POLES) | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2019 | Antonakos, Tony | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Jan-19
303976 | ORLANDO Spec Bldg A - 6005 Erin Mills Pkwy | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Cudzilo, Tomasz |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 14-Jan-19
418255 | 15 SQUARE ONE DRIVE-CITY CENTRE NORTH- CABLE REPLACEMENT | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Zaghloul, Sam |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 11-Mar-19 | 09-Oct-18 | 09-Oct-18 | 15-Oct-18 | 11-Mar-19
412110 | SQUARE ONE PARKING LOT BLOCK 4 & 5 | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Macasaet, Ricardo |  |  |  | 0 | 0 |  | 0 | Paul Tremblay |  |  | 26-Jul-18
405307 | BURNHAMTHORPE O/H TO U/G CONVE | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Watters, Maxwell |  |  |  | 0 | 0 | 0 | 0 | Weaver, Thomas |  |  | 17-Apr-18 | [6 empty] | 0
369772 | Peel Paramedic Station S3 - 1188 Lakeshore Rd. W | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alectra Utilities | 04-Dec-17 |  |  | 14857.89 | 16681.79 | 14857.89 | 14857.89 | Bourgeois, Craig |  | 14-Jun-18 | 19-Feb-19 | 18-May-18 | 04-Apr-18 | 16-Jan-19 |  | Customer |  | 0
411619 | 2411 MOTORWAY BLVD - ERIN PARK | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alectra Utilities | 04-Sep-18 |  |  | 37292.65 | 27685.48 | 37301.65 | 37301.65 | Macdougall, Stephen |  | 11-Dec-18 | 04-Feb-19 | 03-Dec-18 | 14-Jan-19 | 18-Jan-19 |  | Customer |  | 0
268226 | Creditview - Britannia to Agentia - Brdige Widening - carry over from 2017 | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Alectra Utilities | 27-Dec-17 |  |  | 692608.14 | 824870.61 | 692608.14 | 692608.14 | Rob Elliot |  | 14-Dec-18 | 11-Feb-19 | 04-Dec-17 | 04-Dec-17 | 01-Feb-19 |  | Customer |  | 0
East 2019 | East | [9 empty] | Alectra Utilities |  |  | 21 | 13725576.83 | 10034889.49 |  | 0 | [5 empty] | 01-Nov-17 | 05-Nov-19
453586 | (WO318878) 2019 Distribution Automation. 9980 DUFFERIN ST, VAUGHAN | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 15-Mar-19 |  | 1 | 73648 | 53507.88 | 73648 | 73648 | Macdonald, Steve | K-Line | 14-Jun-19 | 25-May-20 | 13-May-19 | 03-Jun-19 | 06-Jun-19 |  |  |  | 0
453613 | (WO 318907) Pole Repl 2019 - Batch 13 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 24-Jan-19 |  |  | 72142 | 23627.57 | 72142 | 72142 | Morrow, Joe |  | 23-Apr-19 | 25-May-20 | 28-Feb-19 | 20-Mar-19 | 11-Apr-19 |  |  |  | 0
454015 | (WO 319399) Pole Replacement 2019 - Replace 2 poles at Old Bloomington Rd., Aurora | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Canale, Alfred | 15-Apr-19 |  |  | 23225 | 6974.92 | 23225 | 23225 | Macdonald, Larry |  | 30-Aug-19 | 25-May-20 | 07-May-19 | 23-May-19 | 23-Jun-19 |  |  |  | 0
452577 | (WO315087) Summitpines Estates - Inspect and Connect | 825 - Patterson | Summitpines Estates | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Perks, Dan | 15-Nov-18 |  |  | 437522.16 | 448648.87 | 437522.16 | 437522.16 | Jeremy Wright | Transpw | 23-Apr-19 | 30-Mar-20 | 08-Feb-19 | 29-Jul-19 | 07-Oct-19 | Customer | Customer |  | 0
453615 | (WO 318909) YRRTC-Y2.1-9839 YONGE ST - OH to UG Service Conversion. | 815 - Addiscott | YRRTC-Y2.1-9839 Yonge St | Inactive | 99 | COMPLETE |  |  | 2019 | Lacombe, Joel | Lacombe, Joel | 22-Feb-19 |  |  | 45952 | 19418.45 | 45952 | 45952 | Steve Rumble |  | 25-Jan-19 | 27-Jan-20 | 18-Jan-19 | 25-Feb-19 | 28-Feb-19 |  |  |  | 0
318609 | 318609 - 20 Baif Blvd. Cable replacement | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Chiuco, Joseph-x | 25-Sep-18 |  |  | 89952 | 1951.28 | 89952 | 89952 | Lamb, Tim |  | 02-Jan-19 | 27-Jan-20 | 09-Oct-18 |  |  |  | Customer |  | 0
453548 | (WO318810) PUCCINI DR & AIDA PL. I&C 47, 47A, 49 RICHMOND HILL. | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Estrada, Michael | 05-Jun-19 |  |  | 82986.01 | 85048.16 | 82986.01 | 82986.01 | Steve Rumble |  |  | 27-Jan-20 |  |  | 05-Nov-19 | xBy-passed | xBy-passed |  | 0
453543 | (WO318795) MAPLEVIEW DRIVE AND STUNDEN LANE, BARRIE | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 | Corriveau, Tom N | Harrington, James | 16-Sep-19 |  |  | 10047.26 | 6264.06 | 10047.26 | 10047.26 | Jeremy Wright |  | 18-Oct-19 | 27-Jan-20 | 17-Oct-19 | 27-Sep-19 | 27-Sep-19 |  |  |  | 0
453163 | (WO318075) 544&550 St. Vincent St | 825 - Patterson | 544 & 550 St. Vincent Street | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Perks, Dan | 01-Nov-18 |  |  | 147230.95 | 149116.53 | 147230.95 | 147230.95 | Jeremy Wright | Transpw | 19-Mar-19 | 06-Feb-20 | 04-Mar-19 | 17-Jun-19 | 02-Jul-19 | Customer | Customer |  | 0
452932 | (WO 317239) REPLACE SWGRS 31-L22 & 31-L20 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  | 2 | 145146 | 65287.72 | 145146 | 145146 | Lamb, Tim | Somervl | 15-Oct-19 | 27-Jan-20 | 17-Jan-19 | 23-Mar-19 | 02-Sep-19 |  | Filler |  | 0
452941 | ( WO 317280) Replace 11 Transformers in V43 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Nov-18 |  |  | 187126 | 106942.42 | 187126 | 187126 | Steve Rumble | Somervl | 13-Mar-19 | 27-Jan-20 | 21-Jan-19 | 21-Jan-19 | 18-Feb-19 |  |  |  | 0
453062 | (WO317742) 138M7 - AB-B1034 - Dufferin St - Air Break to Automated 44kV - Alliston | 825 - Patterson | AB-B1033 End of Life Replacemt | Inactive | 99 | COMPLETE |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D | 06-Dec-18 |  | 1 | 128040 | 128488.7 | 128040 | 128040 | Jeremy Wright |  | 08-Mar-19 | 29-Jan-20 | 13-Feb-19 | 21-Feb-19 | 26-Jun-19 | Filler | Filler |  | 0
453467 | (WO318697) SWGR Repl 2019 - Batch 6 | 815 - Addiscott | SWGR Repl 2019 - Batch 6 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 26-Feb-19 |  | 1 | 87410.05 | 11474.37 | 225669 | 87410.05 | Lamb, Tim |  | 25-Jul-19 | 27-Jan-20 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | -138,258.95
316918 | (WO316918) 388 Spinnaker Way | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 31-Jul-18 |  |  | 32681.25 | 0 | 32681.25 | 32681.25 | Steve Rumble |  | 14-Sep-18 | 27-Jan-20 | 10-Sep-18 | 01-Nov-18 | 12-Sep-19 | Customer | Customer |  | 0
453463 | 453463 (WO 318693) Repl. Switchgear - Batch 5 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 03-Dec-18 |  | 1 | 74713 | 71598.7 | 74713 | 74713 | Steve Rumble | Somervl | 30-Nov-19 | 28-Jan-20 | 17-Jun-19 | 22-Apr-19 | 05-Nov-19 |  |  |  | 0
453462 | 453462 (WO318692) Repl. Switchgear - Batch 3. R15 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 02-Nov-18 |  | 3 | 56563.67 | 50824.43 | 193361.72 | 56564.39 | Steve Rumble | K-Line | 11-Mar-19 | 14-Feb-20 | 19-Feb-19 | 23-Jun-19 | 02-Jul-19 |  | Filler |  | -136,797.33
453375 | (WO318519) UG Cable Replacement. ARROWHEAD DR AND WIGWOSS DR | 815 - Addiscott | 100890 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 13-Feb-19 |  |  | 223318 | 191438.72 | 223318 | 223318 | Lamb, Tim | Transpw | 30-Jun-19 | 28-Jan-20 | 22-Apr-19 | 03-Jun-19 | 28-Jun-19 |  | Filler |  | 0
453447 | 453447 (WO 318672) Replace 38TV109 | 815 - Addiscott | 101027 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 06-Dec-18 |  | 1 | 25991 | 23932.07 | 25991 | 25991 | Lamb, Tim |  | 13-May-19 | 27-Jan-20 | 13-Feb-19 | 09-Oct-19 | 16-Oct-19 |  | Filler |  | 0
452509 | (WO 313222) WyView Subdivision | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alarcon, Alejandro | 01-Nov-17 |  |  | 213896.96 | 195891.48 | 213896.96 | 213896.96 | Steve Rumble | Transpw | 25-Jul-19 | 03-Mar-20 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
317403 | (WO 317403) Esso Gas Station | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 22-Jan-18 |  |  | 56053.79 | 0 | 56053.79 | 56053.79 | Steve Rumble |  | 15-Jun-18 | 27-Jan-20 | 01-Jun-18 | 01-Apr-18 | 12-Sep-19 |  | Customer |  | 0
453186 | (WO318123) 340 PENETANGUISHENE ROAD, BARRIE | 825 - Patterson | Hewitts Place Lots | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Perks, Dan | 01-Nov-18 |  |  | 69661.23 | 71340.32 | 69661.23 | 69661.23 | Jeremy Wright | Transpw | 01-Mar-19 | 27-Jan-20 | 18-Feb-19 | 08-Jul-19 | 17-Sep-19 |  | Customer |  | 0
453614 | (WO 318908) REPLACE 15-L18 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 26-Apr-19 |  | 1 | 82820 | 80853.45 | 82820 | 82820 | Lamb, Tim | Transpw | 02-Jul-19 | 27-Jan-20 | 06-May-19 | 15-Jun-19 | 15-Jun-19 |  | Filler |  | 0
452617 | (WO315501) Yorkton Limited Phase 2. Royal Aberdeen Rd/ Yorkton Blvd | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Estrada, Michael | 19-Nov-18 |  |  | 583231.35 | 610178.59 | 583231.35 | 583231.35 | Steve Rumble | Transpw | 01-Mar-19 | 27-Jan-20 | 11-Feb-19 | 06-Dec-18 | 21-Oct-19 |  |  |  | 0
452933 | ( WO 317244) REPLACE 16-L30 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  | 1 | 79171 | 72311.38 | 79171 | 79171 | Lamb, Tim | Somervl | 30-Apr-19 | 13-Jan-20 | 05-Feb-19 | 30-Mar-19 | 04-Apr-19 |  | Filler |  | 0
452936 | ( WO 317247) REPLACE 43-L34 | 815 - Addiscott | 2019 Switchgear Replacement | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  | 1 | 84241 | 61455.98 | 84241 | 84241 | Lamb, Tim | Somervl | 15-Mar-19 | 13-Jan-20 | 11-Feb-19 | 02-Jan-19 | 23-Feb-19 |  | Filler |  | 0
452934 | ( WO 317245) REPLACE 29-L12 | 815 - Addiscott | 2019 Switchgear Replacement | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  | 1 | 71892 | 103518.62 | 71892 | 71892 | Lamb, Tim | Somervl | 01-Apr-19 | 13-Jan-20 | 01-Apr-19 | 23-Mar-19 | 23-Mar-19 |  |  |  | 0
316139 | ( WO 316139) Proposed Townhouse Development | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dibratto, Susan | 02-May-18 |  |  | 73111.48 | 0 | 73111.48 | 73111.48 | Steve Rumble | Transpw | 29-Aug-18 | 16-Sep-19 | 30-Jul-18 | 01-Jul-18 | 12-Sep-19 |  | Customer |  | 0
317237 | (WO 317237) REPLACE A05SP2008 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Roy, James | 01-Nov-18 |  | 1 | 41962 | 30551.27 | 41962 | 41962 | Lamb, Tim | Somervl | 17-Jan-19 | 16-Sep-19 | 07-Jan-19 | 01-Jan-19 | 31-Jan-19 |  | Filler |  | 0
453610 | (WO 318904) KEELE ST - KIRBY ST TO KING VAUGHAN RD- Metrolinx Electrical | 815 - Addiscott | 150591 | Inactive | 99 | CANCELLED |  |  | 2019 | Vande Kuyt, Greg | Grahovac, John |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 04-Sep-19
319173 | (WO 319173) Pole Relocation- 13200 YONGE STREET, RICHMOND HILL | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 20-Feb-19 |  |  | 15607 | 8324.89 | 15607 | 15607 | Macdonald, Steve | K-Line | 30-May-19 | 06-Aug-19 | 25-Mar-19 | 04-Apr-19 | 04-Apr-19 |  |  |  | 0
453670 | (WO 318980) Hwy 407 and Woodbine Ave Insulator Replacement | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 03-Jan-19 |  |  | 105105.72 | 113389.44 | 106364 | 104121.62 | Macdonald, Larry |  | 30-May-19 | 06-Aug-19 | 28-Feb-19 | 02-May-19 | 02-May-19 |  |  |  | -2,242.38
318816 | (WO 318816) Replace Pole P23136 - Markham | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Canale, Alfred | 03-Dec-18 |  |  | 21894 | 24539.59 | 21894 | 21894 | Macdonald, Steve | K-Line | 30-May-19 | 06-Aug-19 | 27-Feb-19 | 04-Mar-19 | 17-Mar-19 |  |  |  | 0
453413 | (WO 318601) 2019 Pole Replacement Batch 02 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Roy, James | 01-Nov-18 |  |  | 114722 | 115067 | 114722 | 114722 | Macdonald, Larry |  | 21-Feb-19 | 06-Aug-19 | 02-Jan-19 | 07-Jan-19 | 05-Feb-19 |  |  |  | 0
453531 | (WO 318781) YRRTC - H2-West - Phase 4.3 | 815 - Addiscott | YRRTC - H2-West - Phase 4.3 | Inactive | 99 | COMPLETE |  |  | 2019 | O'Gay, Brian | Zhang, Jiacheng | 03-Dec-18 |  |  | 251315 | 208115.81 | 251315 | 251315 | Lyle, Sedore | K-Line | 30-Jan-19 | 06-Aug-19 | 11-Jan-19 | 14-Jan-19 | 07-Mar-19 |  |  |  | 0
318600 | (WO 318600) 2019 Pole Replacement Batch 01 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Roy, James | 01-Nov-18 |  |  | 185386 | 110881.47 | 185386 | 165083.87 | Shortt, Derek B. |  | 01-Mar-19 | 06-Aug-19 | 02-Jan-19 | 25-Jan-19 | 14-Mar-19 |  |  |  | -20,302.13
318605 | (WO 318605) Westwood Gardens Pole Relocation | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Barry, Kenneth | 16-Nov-18 |  |  | 16035 | 17879.04 | 16035 | 16035 | Macdonald, Larry |  | 28-Feb-19 | 06-Aug-19 | 18-Dec-18 | 14-Jan-19 | 14-Jan-19 |  |  |  | 0
454238 | (WO 319639) V15 Baldwin Dr V15FA1004 to 15-L7 - Rush | 815 - Addiscott | UG Cable Replacement | Inactive | 99 | CANCELLED |  |  | 2019 | Tenorlas, Reynaldo | Handy, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 25-Jun-19
454239 | (WO319641) INTERCHANGE WAY X EXCHANGE AVENUE | 815 - Addiscott | MICRO GENERATION-FIT GENERATOR | Inactive | 99 | CANCELLED |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 19-Jun-19
452975 | (WO 317472) Commercial Building - Service Shop | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Yuen, Paul | 30-Jan-18 |  |  | 50884.06 | 30062.96 | 50884.06 | 50884.06 | Steve Rumble | Somervl | 30-Nov-18 | 28-Jun-19 | 09-Nov-18 | 03-Jun-19 | 06-Jun-19 | Customer | Customer |  | 0
452698 | ( WO 316266) NINE TEN WEST CARVILLE DISTRICT | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alarcon, Alejandro | 01-Nov-17 |  |  | 303660.09 | 186172.47 | 303660.71 | 303660.71 | Steve Rumble |  | 25-Jul-19 | 24-Jun-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
316318 | (WO 316318) PEAK GARDENS PHASE 2 - 3947 HWY 7 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alarcon, Alejandro | 01-Nov-17 |  |  | 84116.13 | 0 | 84116.13 | 84116.13 | Steve Rumble |  | 25-Jul-19 | 25-Jun-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
453181 | (WO318108) 707 Creditstone Road | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Dibratto, Susan | Dibratto, Susan | 19-Nov-18 |  |  | 61625.46 | 40763.23 | 61625.46 | 61625.46 | Steve Rumble | Somervl | 07-Jan-19 | 26-Jun-19 | 19-Dec-18 | 03-Apr-19 | 16-May-19 | Customer | Customer |  | 0
452861 | (WO 316877) 168/176 Elgin Mills Rd | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alarcon, Alejandro | 01-Nov-17 |  |  | 54863.15 | 45945.51 | 54863.15 | 54863.15 | Steve Rumble | Transpw | 25-Jul-19 | 10-Jul-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
453275 | (WO318353) Lowering of Duct Bank - Glen Meadows & Bayview Ave | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Graham, Bruce W. | 03-Dec-18 |  |  | 20016 | 18973.61 | 20016 | 20016 | Steve Rumble | Transpw | 21-Feb-19 | 21-Jun-19 | 12-Feb-19 | 29-Apr-19 | 13-May-19 | Customer | Customer |  | 0
318222 | (WO 318222) Relocations for Markham Sidwalks | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 05-Dec-18 |  |  | 22239 | 32165.42 | 22239 | 22239 | Macdonald, Larry |  | 30-May-19 | 21-May-19 | 14-Mar-19 | 07-Mar-19 | 07-Mar-19 |  |  |  | 0
318754 | (WO 318754) Span Pole Removal 63 Larmont St | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 14-Feb-19 |  |  | 18781 | 15694.71 | 18781 | 18781 | Macdonald, Larry |  | 30-May-19 | 21-May-19 | 26-Mar-19 | 28-Mar-19 | 28-Mar-19 |  |  |  | 0
318149 | (WO 318149) JU 18-065 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 14-Feb-19 |  |  | 11976 | 14586.32 | 11976 | 11976 | Macdonald, Larry |  | 12-Jun-19 | 21-May-19 | 21-Mar-19 | 05-Apr-19 | 05-Apr-19 |  |  |  | 0
318305 | (WO318305) Pole Relocation - Victoria Square Blvd | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alarcon, Alejandro | 17-Jan-19 |  |  | 31267 | 20574.12 | 31267 | 31267 | Macdonald, Larry |  | 30-May-19 | 21-May-19 | 05-Mar-19 | 14-Mar-19 | 14-Mar-19 |  |  |  | 0
318221 | (WO 318221) Relocations for Vaughan Sidewalks | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Barry, Kenneth | 25-Mar-19 |  |  | 18883 | 14619.95 | 18883 | 18883 | Macdonald, Larry |  | 10-May-19 | 21-May-19 | 23-Apr-19 | 01-Apr-19 | 12-Apr-19 |  |  |  | 0
319500 | (WO 319500) Transfer cct HONI pole - RHYONGE & REGATTA - RICHMOND HILL | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 10-May-19
316894 | (WO316894) Pavilia Park Towns. Highway 7 & Saddlecreek Dr | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 21-Sep-18 |  |  | 181666.76 | 192616.68 | 181666.76 | 181666.76 | Steve Rumble |  | 20-Nov-18 | 03-Jun-19 | 24-Oct-18 | 20-Nov-18 | 11-Feb-19 | Customer | Customer |  | 0
310939 | ( WO 310939) CENTRO 7777 WESTON (RETAIL AND OFFICE) | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Yuen, Paul | 01-Nov-17 |  |  | 249656.34 | 205439.5 | 249656.34 | 249656.34 | Steve Rumble | Transpw | 19-Sep-18 | 05-Jun-19 | 05-Feb-18 | 01-Nov-17 | 22-Apr-19 |  | Contractor |  | 0
453508 | (WO318748) KING-VAUGHAN RD. - 3230 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 12-Dec-18 |  |  | 73480.77 | 53928.92 | 73480.77 | 73480.77 | Steve Rumble | Somervl | 06-Feb-19 | 23-May-19 | 10-Jan-19 | 04-Feb-19 | 24-Apr-19 | Customer | Customer |  | 0
315453 | (WO315453) Zima Parkway Pole Line Upgrade | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Perks, Dan | 01-Mar-19 |  |  | 130567 | 111400.88 | 130567 | 130567 | Dan Kish |  | 01-Apr-19 | 06-May-19 | 11-Mar-19 | 06-Mar-19 | 12-Apr-19 |  | Locates |  | 0
315521 | (WO315521) 8451 & 8457 Islington Avenue | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 02-Jan-19 |  |  | 155679.89 | 159444.74 | 155679.89 | 155679.89 | Steve Rumble | Transpw | 07-Mar-19 | 23-May-19 | 19-Feb-19 | 29-Mar-19 | 29-Mar-19 | Customer | Customer |  | 0
452892 | (WO 316992) Monarch Castlepoint Kipling North Development Ph. 2 | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Estrada, Michael | 15-Aug-18 |  |  | 613947.8 | 44006.92 | 613947.8 | 613947.8 | Steve Rumble | Transpw | 01-Mar-19 | 24-Jun-19 | 23-Nov-18 | 06-Dec-18 | 05-Apr-19 | Customer | Customer |  | 0
318264 | (WO318264 ) Barrie - Bear Creek (Aspen Woods) - Inspect and Connect | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Perks, Dan | 16-Nov-18 |  |  | 519756.33 | 513697.69 | 519756.33 | 519756.33 | Jeremy Wright | Transpw | 01-May-19 | 21-May-19 | 20-Dec-18 | 28-Feb-19 | 10-Apr-19 | Customer | Customer |  | 0
452940 | ( WO 317279) Replace 4 Transformers in V58 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 01-Nov-18 |  |  | 98306 | 73058.07 | 98306 | 98306 | Steve Rumble |  | 12-Apr-19 | 05-Jun-19 | 01-Mar-19 | 05-Mar-19 | 16-Apr-19 | Filler | Filler |  | 0
316581 | (WO316581) Regent St. Development | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Graham, Bruce W. | 05-Mar-19 |  |  | 96870.93 | 98966.52 | 96870.93 | 96870.93 | Steve Rumble | Transpw | 10-Apr-19 | 08-May-19 | 01-Apr-19 | 12-Mar-19 | 25-Mar-19 |  |  |  | 0
453429 | (WO318623) 2019 Padmount Transformer Replacement Batch 8 - Vaughan | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2019 | Tenorlas, Reynaldo | Handy, James | 20-Nov-18 |  |  | 95809 | 73870.53 | 95809 | 95809 | Steve Rumble |  | 23-Apr-19 | 18-Jun-19 | 04-Mar-19 | 04-Mar-19 | 16-Apr-19 |  |  |  | 0
452891 | (WO316990) Monarch Castlepoint Kipling South Development Ph. 2 | 815 - Addiscott | PARENT W.O. FOR INSPECT/CONNE | Inactive | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Estrada, Michael | 23-Aug-18 |  |  | 584280.72 | 41975 | 584280.72 | 584280.72 | Steve Rumble | Conelco | 22-Mar-19 | 19-Jun-19 | 28-Jan-19 | 07-Jan-19 | 05-Apr-19 |  | Customer |  | 0
452948 | ( WO 317311) 2019 AB-B76 - P4491 - Huronia Rd. - Air Break to manual 44kV LIS - Barrie | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Walters, Geoffrey D | 01-Nov-17 |  | 1 | 131177.48 | 104395.02 | 121032 | 131177.48 | Jeremy Wright |  | 05-Feb-19 | 07-May-19 | 16-Jan-19 | 14-Jan-19 | 12-Feb-19 | Filler |  |  | 10,145.48
318817 | (WO 318817) Replace Pole P50098 - Markham | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Canale, Alfred | 25-Jan-19 |  |  | 15906 | 19505.82 | 15906 | 15906 | Macdonald, Steve |  | 01-Apr-19 | 29-Apr-19 | 05-Mar-19 | 04-Mar-19 | 19-Mar-19 |  |  |  | 0
316841 | (WO 316841) JU 17-094 Bullock Drive | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 03-Oct-18 |  |  | 13940 | 16727.82 | 13940 | 13940 | Macdonald, Larry |  | 30-Nov-18 | 29-Apr-19 | 29-Oct-18 | 16-Jan-19 | 16-Jan-19 |  | Filler |  | 0
318732 | (WO 318732) 18-097 Rogers JU Application | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 04-Feb-19 |  |  | 4525 | 2413.56 | 4525 | 4525 | Macdonald, Larry |  | 24-Apr-19 | 29-Apr-19 | 28-Feb-19 | 19-Mar-19 | 19-Mar-19 |  | Filler |  | 0
315376 | (WO315376) S/G Pole Relocate at Kevi Subdivision | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Graham, Bruce W. | 22-Oct-18 |  |  | 17787 | 8829.47 | 17787 | 17787 | Macdonald, Larry |  | 19-Dec-18 | 29-Apr-19 | 27-Nov-18 | 17-Jan-19 | 17-Jan-19 |  | Filler |  | 0
317008 | (WO 317008) JU 17-126 Pole Replacement and Down guy replacement | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 04-Dec-18 |  |  | 33900 | 27332.65 | 33900 | 33900 | Macdonald, Larry |  | 19-Mar-19 | 29-Apr-19 | 02-Jan-19 | 19-Feb-19 | 19-Feb-19 |  | Filler |  | 0
317075 | (WO 317075) Joint Use 17-130 Rivermede & Bowes RD | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 04-Dec-18 |  |  | 7965 | 7821.24 | 7965 | 7965 | Macdonald, Larry |  | 15-Mar-19 | 29-Apr-19 | 02-Jan-19 | 31-Jan-19 | 31-Jan-19 |  | Filler |  | 0
318440 | (WO 318440) JU 17-156 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 14-Feb-19 |  |  | 11752 | 7487.73 | 11752 | 11752 | Macdonald, Larry |  | 12-Jun-19 | 29-Apr-19 | 21-Mar-19 | 21-Mar-19 | 21-Mar-19 |  | Filler |  | 0
312191 | (WO312191) 3150 Major Mackenzie Dr | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dibratto, Susan | 15-Jun-18 |  |  | 182388.34 | 199171.1 | 182388.34 | 182388.34 | Lyle, Sedore |  | 18-Dec-18 | 29-Apr-19 | 25-Oct-18 | 23-Jan-19 | 12-Feb-19 |  | Customer |  | 0
316549 | (WO 316549) Joint Use 17-054 Make Ready | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 04-Dec-18 |  |  | 14646 | 9943.48 | 14646 | 14646 | Macdonald, Larry |  | 19-Mar-19 | 29-Apr-19 | 02-Jan-19 | 20-Mar-19 | 20-Mar-19 |  | Filler |  | 0
318702 | (WO 318702) JU 18-045 Anchor and Down Guy Installation | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Battistella, Alexander | 04-Dec-18 |  |  | 6909 | 3357.42 | 6909 | 6909 | Macdonald, Larry |  | 27-Feb-19 | 29-Apr-19 | 21-Dec-18 | 06-Feb-19 | 06-Feb-19 |  | Filler |  | 0
454066 | (WO 319453) BELL POLE REPLACEMENT 193 KRIEGHOFF AVENUE | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 23-Apr-19
454017 | (WO 319401) 10725 Reesor Road | 815 - Addiscott | PARENT W.O. FOR UNPLANNED | Inactive | 99 | CANCELLED |  |  | 2019 | Corriveau, Tom N | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 09-Apr-19
317380 | (WO 317380) 22 Esna Park Dr | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
315364 | (WO 315364) 9225 Bathurst St | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
316464 | (WO 316464) 1600 Major Mackenzie Dr E | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble | Transpw | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
313887 | (WO 313887) Brownstones Phase 2 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dibratto, Susan | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
317273 | (WO 317273) Replace 12 Transformers in V53 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Gonzales, Leonard | 02-Mar-18 |  |  | 208349 | 206704.49 | 208349 | 208349 | Steve Rumble |  | 03-Aug-18 | 08-Apr-19 | 25-Jun-18 | 25-Jul-19 | 25-Jul-19 | Filler | Filler |  | 0
317404 | (WO 317404) 7233 Hwy 27 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
318349 | (WO318349) Alliston - Briar Hill Vistas Ph 6 | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Perks, Dan | 19-Oct-18 |  |  | 253208.82 | 254865.4 | 253208.82 | 253208.82 | Jeremy Wright | Transpw | 14-Dec-18 | 17-Apr-19 | 23-Nov-18 | 17-Dec-18 | 15-Jan-19 |  | Customer |  | 0
317779 | (317779) 122 Main Street- New Shoppers Drug Mart | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Martin, Shane | 24-Sep-18 |  |  | 62903.23 | 57796.27 | 62903.23 | 62903.23 | Jeremy Wright | HapAmp | 02-Jan-19 | 12-Apr-19 | 07-Dec-18 | 25-Oct-18 | 01-Feb-19 |  | Customer |  | 0
318174 | (WO318174 ) McKenzie Pioneer | 825 - Patterson | 150008 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Pollock, Kim | 03-Dec-18 |  |  | 110099 | 118954.44 | 110099 | 110099 | Jeremy Wright |  | 11-Feb-19 | 08-Apr-19 | 02-Jan-19 | 02-Jan-19 | 08-Feb-19 |  |  |  | 0
316511 | ( WO 316511) ADENA VIEWS SUBDIVISION | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Perks, Dan | 01-Nov-17 |  |  | 311187.56 | 269384.73 | 344024.58 | 344024.58 | Steve Rumble | Transpw | 17-Sep-18 | 08-May-19 | 20-Jul-18 | 25-Jul-19 | 25-Jul-19 | Customer | Customer |  | 0
314240 | (WO 314240) Choice Properties- Commercial Development | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Martin, Shane | 19-Apr-18 |  |  | 88392.79 | 72907.63 | 88329.79 | 88329.79 | Jeremy Wright |  | 31-Aug-18 | 08-Apr-19 | 31-Aug-18 | 12-Oct-18 | 07-Jan-19 |  | Customer |  | 0
314091 | ( WO 314091) 251 Langstaff Rd | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
317789 | (WO317789) 10483 Islington Ave | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble | Transpw | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
316686 | (WO 316686) 7875 Hwy 50 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
318632 | (WO318632 ) PMH-9 - BROWNING TRAIL SWITCHGEAR REPLACEMENT - Barrie | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Walters, Geoffrey D | 30-Nov-18 |  | 1 | 24861 | 23524.19 | 24861 | 24861 | Jeremy Wright |  | 21-Feb-19 | 09-Apr-19 | 19-Feb-19 | 01-Feb-19 | 07-Feb-19 |  |  |  | 0
318710 | (WO318710) LANGFORD BLVD AND HOLLAND STREET, BRADFORD. | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Harrington, James | 06-Dec-18 |  |  | 134118 | 0 | 134118 | 134118 | Jeremy Wright | Transpw | 21-Jan-19 | 08-Apr-19 | 14-Jan-19 | 10-Dec-18 | 10-Jan-19 |  |  |  | 0
317663 | (WO317663) Royal Richmond - 305 Bloomington Rd | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 31-Aug-18 |  |  | 263476.56 | 259896.61 | 263476.56 | 263476.56 | Steve Rumble |  | 05-Oct-18 | 17-Apr-19 | 19-Sep-18 | 14-Feb-19 | 14-Feb-19 | Customer | Customer |  | 0
317081 | (WO317081) Snidercroft Rd. - #211 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Yuen, Paul | 14-Jun-18 |  |  | 72576.62 | 38602.58 | 72576.62 | 72576.62 | Steve Rumble | Transpw | 28-Dec-18 | 15-Apr-19 | 28-Nov-18 | 04-Dec-18 | 15-Jan-19 | Customer | Customer |  | 0
316185 | (WO 316185) Vaughan Mills (Tesla) | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
316717 | (WO 316717) 150 NEW HUNTINGTON RD | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
312306 | (WO 312306) 20 Brodie Dr | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
316270 | (WO 316270) 161 Milani Blvd | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Steve Rumble |  | 25-Jul-19 | 08-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
318612 | (WO 318612) 8125 Highway 50 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dibratto, Susan | 10-Oct-18 |  |  | 78259.4 | 56057.15 | 78259.4 | 78259.4 | Steve Rumble | Somervl | 15-Nov-18 | 11-Apr-19 | 02-Nov-18 | 05-Nov-18 | 15-Jan-19 | Customer | Customer |  | 0
313166 | ( WO 313166) 3940 HIGHWAY 8 - PEAK GARDENS SUBDIVION | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alarcon, Alejandro | 01-Nov-17 |  |  | 119613.76 | 118613.27 | 119613.76 | 119613.76 | Steve Rumble | Transpw | 02-Nov-18 | 25-Apr-19 | 03-Sep-18 | 09-Oct-18 | 20-Feb-19 | Customer | Customer |  | 0
316428 | ( WO 316428) Steeles and New Westminister - Phase 3 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Chiuco, Joseph-x | 02-Aug-18 |  |  | 974628 | 838310.25 | 974628 | 974628 | Cory Ruiter | Transpw | 30-Nov-18 | 16-May-19 | 27-Aug-18 | 16-Oct-18 | 02-Jan-19 | Contractor | Contractor |  | 0
315906 | (WO315906) Prima Vista Estates - Phase 1. Teston Road & Pine Valley Drive | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 24-May-18 |  |  | 59373.48 | 39661.36 | 59373.49 | 59373.49 | Steve Rumble |  | 23-Apr-19 | 28-May-19 | 19-Feb-19 | 07-Feb-19 | 07-Feb-19 |  |  |  | 0
317310 | ( WO 317310) 2019 AB-B68 - P6579 - Collier St. - Air Break to manual 44kV LIS - Barrie | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Walters, Geoffrey D | 01-Nov-17 |  | 1 | 182069 | 154941.53 | 182069 | 182069 | Dan Kish |  | 06-Mar-19 | 04-Apr-19 | 21-Jan-19 | 28-Jan-19 | 23-Feb-19 | MC/PUCC Permit |  |  | 0
317296 | ( WO 317296) Replace V39TP1001 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Roy, James | 18-Jan-18 |  |  | 10707 | 8264.96 | 10707 | 10707 | Steve Rumble |  | 22-Mar-19 | 02-Apr-19 | 18-Mar-19 | 30-Jan-19 | 30-Jan-19 |  |  |  | 0
317228 | ( WO 317228) REPLACE 8 SWITCHGEARS IN V31 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Gonzales, Leonard | 05-Feb-18 |  |  | 460856 | 495824.57 | 460856 | 460856 | Lamb, Tim |  | 25-Jul-19 | 01-Apr-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
319026 | (WO319026) 241 Hanlan Rd | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 07-Feb-19 |  |  | 27271.93 | 27859.13 | 27271.93 | 27271.93 | Steve Rumble |  | 01-Apr-19 | 01-Apr-19 | 18-Feb-19 | 01-Mar-19 | 03-Mar-19 | Customer |  |  | 0
315723 | (WO 315723) 275 Woodbridge Avenue | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dibratto, Susan | 01-Jun-18 |  |  | 79356.23 | 36961.63 | 79356.23 | 79356.23 | Steve Rumble | Transpw | 02-Nov-18 | 04-Apr-19 | 22-Oct-18 | 12-Oct-18 | 01-Feb-19 |  | Customer |  | 0
317781 | (WO317781) 2019 End of Life Automated Switch Replacements - AB-B1031 - Albert St. E & Douglas Dr. | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Walters, Geoffrey D | 07-Jun-18 |  | 1 | 157545 | 139829.89 | 157545 | 157545 | Dan Kish |  | 23-Jan-19 | 02-Apr-19 | 02-Jan-19 | 02-Jan-19 | 11-Jan-19 |  |  |  | 0
315929 | (WO315929) Mosaik Phase 3 - Block 40/47 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Estrada, Michael | 24-May-18 |  |  | 29388.56 | 20587.59 | 29388.56 | 29388.56 | Steve Rumble | Conelco | 12-Mar-19 | 18-Apr-19 | 19-Feb-19 | 22-Oct-18 | 07-Feb-19 |  |  |  | 0
316392 | (WO316392 ) 100 Lawford Rd | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Paterson, Greg | 22-Nov-18 |  |  | 34735.3 | 28784.87 | 34735.3 | 34735.3 | Steve Rumble | Somervl | 11-Dec-18 | 04-Apr-19 | 06-Dec-18 | 07-Jan-19 | 31-Jan-19 | Customer | Customer |  | 0
318587 | (WO 318587) 145 GIBRALTAR ROAD | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Dibratto, Susan | 10-Oct-18 |  |  | 123526.87 | 104357.87 | 123526.87 | 123526.87 | Steve Rumble | Somervl | 23-Nov-18 | 04-Apr-19 | 12-Nov-18 | 12-Nov-18 | 18-Feb-19 |  | Customer |  | 0
452866 | (WO316888) Gandhi Lane #12 & #32 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2019 | Cranley, Stephen | Yuen, Paul | 03-Oct-18 |  |  | 124725.28 | 90467.27 | 124725.28 | 124725.28 | Steve Rumble | Somervl | 11-Dec-18 | 09-Apr-19 | 23-Nov-18 | 20-Nov-18 | 12-Mar-19 |  | Customer |  | 0
318633 | (318633_ PMH-3 - 2 NEELANDS ST. SWITCHGEAR SLEEVE OUT - Barrie | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Walters, Geoffrey D | 30-Nov-18 |  | 1 | 12356 | 7276.68 | 12356 | 12356 | Jeremy Wright | HapAmp | 04-Mar-19 | 01-Apr-19 | 25-Feb-19 | 14-Mar-19 | 20-Mar-19 |  | Filler |  | 0
318291 | (WO 318291) - Primary Service Fitness center. 325 Woodbridge Ave | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Yuen, Paul | 14-Aug-18 |  |  | 113578.97 | 129519.68 | 59080.6 | 113578.97 | Steve Rumble | Transpw | 01-Oct-18 | 24-Apr-19 | 10-Sep-18 | 10-Sep-18 | 06-Mar-19 |  | Customer |  | 54,498.37
318636 | (WO318636) 2019 PMH-3 - 141 HANMER ST. WEST SWITCHGEAR SLEEVE OUT - Barrie | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2019 |  | Walters, Geoffrey D | 30-Nov-18 |  | 1 | 12356 | 5773.83 | 12356 | 12356 | Jeremy Wright |  | 07-Mar-19 | 01-Apr-19 | 05-Mar-19 | 12-Mar-19 | 14-Mar-19 | Filler |  |  | 0
316806 | (WO316806) 32 WELLINGTON ST. AURORA | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Harris, Geoff L. | 14-Nov-18 |  |  | 44901.84 | 45862.65 | 44901.84 | 44901.84 | Steve Rumble | Somervl | 07-Jan-19 | 03-Apr-19 | 20-Dec-18 | 04-Dec-18 | 14-Jan-19 |  | Customer |  | 0
316922 | (WO316922) S/GEAR RELOCATION - CANADA DRIVE & VEDETTE WAY - CANADA DR - S/GEAR RELOCATI | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Zhang, Jiacheng | 04-Jan-19 |  |  | 143810 | 151770.2 | 89077 | 143810 | Lamb, Tim | Transpw | 01-Mar-19 | 25-Apr-19 | 21-Jan-19 | 21-Jan-19 | 11-Feb-19 |  |  |  | 54,733.00
318169 | (WO318169) Edgehill Townhomes | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Perks, Dan | 19-Oct-18 |  |  | 66009.8 | 58658.88 | 66009.8 | 66009.8 | Jeremy Wright | Transpw | 15-Nov-18 | 04-Apr-19 | 09-Nov-18 | 01-Mar-19 | 25-Mar-19 |  | Customer |  | 0
319345 | (WO 319345) Replace P27562 - 341 Steelcase Rd W., Markham | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2019 |  | Canale, Alfred |  |  |  | 58795 | 0 | 58795 | 58795 | Shortt, Derek B. |  |  | 25-Mar-19 | [6 empty] | 0
452913 | (WO 317116) Big Bay Point Urban Townhomes | 825 - Patterson | ICI BAR BIG BAY PT TOWNHOME TX | Inactive | 99 | CANCELLED |  |  | 2019 | Cranley, Stephen | Martin, Shane | 06-Apr-18 |  |  | 89975.38 | 4762.5 | 89975.38 | 89975.38 | Jeremy Wright | Transpw | 18-Sep-18 | 11-Apr-19 | 31-Jul-18 | [5 empty] | 0
318941 | (WO 318941) Transfer cct HONI pole - Yonge | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James | 04-Jan-19 |  |  | 5789 | 146.79 | 5789 | 5789 | Shortt, Derek B. |  | 06-Mar-19 | 06-Mar-19 | 19-Feb-19 | [5 empty] | 0
318950 | (WO 318950) Transfr cct HONI pole - Aurora | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James | 04-Jan-19 |  |  | 8221 | 146.79 | 8221 | 8221 | Shortt, Derek B. |  | 06-Mar-19 | 06-Mar-19 | 19-Feb-19 | [5 empty] | 0
319216 | (WO 319216) Batch 18 - Replace 4 Poles | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2019 |  | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 05-Feb-19
319010 | (WO 319010) Batch 16 - Replace 11 Poles | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2019 |  | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Jan-19
318985 | (WO 318985) Batch 14 - Replace 9 Poles | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2019 |  | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Shortt, Derek B. |  |  | 02-Jan-19
317286 | ( WO 317286) Replace 11 Transformers in V26 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Roy, James | 02-Mar-18 |  |  | 132132 | 91802.92 | 132132 | 132132 | Steve Rumble |  | 25-Jul-19 | 28-Dec-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
318874 | (WO318874) 2019 Distribution Automation. RUTHERFORD RD E/O JANE ST | 815 - Addiscott | 100886 | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 13-Nov-18
316300 | (WO316300) 2381423 Ontario Inc | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Graham, Bruce W. |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 30-Nov-18
317709 | (WO 317709) 407 and Woodbine Ave | 815 - Addiscott | 150403 | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James |  |  |  | 0 | 0 | 0 | 0 | Persaud, Ryan |  |  | 20-Jul-18 | [6 empty] | 0
318091 | (WO 318091) 16th Avenue - Pole Repl. | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James |  |  |  | 0 | 0 | 0 | 0 | Persaud, Ryan |  |  | 20-Jul-18 | [6 empty] | 0
318093 | (WO 318093) Huntington Road- Pole Repl | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James |  |  |  | 0 | 0 | 0 | 0 | Persaud, Ryan |  |  | 20-Jul-18 | [6 empty] | 0
318764 | (WO 318764) Remove Pole P25069 | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 09-Oct-18
318833 | (WO 318833) 2019 3 Rpl Pole - Markham | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 15-Nov-18
318835 | (WO 318835) 2019 5 Rpl Pole - Markham | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Canale, Alfred |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 15-Nov-18
314351 | ( WO 314351) VILLAGES OF FAIRTREE - EAST VILLAGE | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alarcon, Alejandro | 01-Nov-17 |  |  | 786406.31 | 12026.17 | 798711.31 | 798711.31 | Steve Rumble | Transpw | 25-Jul-19 | 20-Feb-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
316191 | (WO 316191) Pole Relocation Leslie St Stouffville Rd to Bloomington Rd | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Jun-18
314652 | (WO 314652) Aurora Go station Pole Relocation | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 | 400000 | 400000 | Persaud, Ryan |  |  | 20-Jun-18 | [6 empty] | 0
311826 | ( WO 311826) KLEINDOR DEVELOPMENT INC. PH#2 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Kinsella, William P | 01-Nov-17 |  |  | 0 | 67063.65 | 86020.69 | 86020.69 | Steve Rumble | Conelco | 25-Jul-19 | 17-Sep-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
318704 | (WO 318704) 18-120 Rogers JU Application | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Sep-18
318728 | (WO 318728) 18-103 Rogers JU Application | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Oct-18
315290 | (WO315290) New 3 Ph. Service | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Martin, Shane | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Jeremy Wright | Transpw | 25-Jul-19 | 09-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
318511 | (WO 318511) Road Widening - Elgin Mills Road W, Bathurst to Yonge, Richmond Hill | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 09-Oct-18
316180 | (WO316180) 39 BURKE ST, PENETANG | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Harris, Geoff L. | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Jeremy Wright |  | 25-Jul-19 | 09-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
313976 | (WO313976) 30 KING ST. SOUTH, ALLISTON | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Martin, Shane | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Jeremy Wright |  | 25-Jul-19 | 09-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
452647 | (WO 315764) Centre Street Riser Installation, Bradford ( Control Room Driven - Add'tl Spend Req'd) | 825 - Patterson | Install New Pole and Riser | Inactive | 99 | CANCELLED |  |  | 2019 | Bowman, Todd J | Pollock, Kim |  |  |  | 0 | 0 | 60000 | 60000 | Jeremy Wright |  |  | 13-Jun-18 | [6 empty] | 0
318727 | (WO 318727) 18-106 Rogers JU Application | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Oct-18
318729 | (WO 318729) 18-137 Rogers JU Application | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Oct-18
318706 | (WO 318706) Hydro Relocation- STEELES AV E - KENNEDY TO MIDLAND | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Chiuco, Joseph-x |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 28-Sep-18
318730 | (WO 318730) 18-131 Rogers JU Application | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Battistella, Alexander |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Oct-18
318210 | (WO318210) New 3 Phase Service | 825 - Patterson |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Martin, Shane |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 09-Oct-18
318109 | (WO318109) Redstone Townhomes | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Yuen, Paul |  |  |  | 0 | 0 |  | 0 | Steve Rumble |  |  | 01-Oct-18
318188 | (WO318188) Tottenham Fire Hall Relocations | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Pollock, Kim | 01-Nov-17 |  |  | 0 | 0 | 0 | 0 | Wong, Henry |  | 25-Jul-19 | 20-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
318640 | (WO318640) 2019 - Pdmt TX Rep. Batch 7 | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Roy, James |  |  |  | 0 | 0 |  | 0 | Steve Rumble |  |  | 21-Sep-18
453453 | (WO318681) BARRIE TS RECONSTRUCTION / UPGRADE FOR HYDRO ONE ( Cancelled) | 825 - Patterson | BARRIE TS RECONSTRUCTION | Inactive | 99 | CANCELLED |  |  | 2019 | Bowman, Todd J | Walters, Geoffrey D |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 21-Sep-18
318447 | (WO 318447) Pole Relocation - 4671 14th Avenue, Markham | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2019 |  | Barry, Kenneth |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 09-Oct-18
316371 | (WO316371) New Retirement Home | 825 - Patterson |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Martin, Shane | 01-Nov-17 |  |  | 0 | 0 |  | 0 | Jeremy Wright |  | 25-Jul-19 | 09-Oct-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19
317442 | ( WO 317442) (M44) - Konrad Cr (690m) | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alectra Utilities | 29-May-18 |  |  | 199300 | 166282.82 | 199300 | 199300 | Lamb, Tim |  | 25-Jul-19 | 21-Jan-19 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
316942 | ( WO 316942) Larkin Ave, M15 | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alectra Utilities | 27-Feb-18 |  |  | 113970 | 166260.5 | 113970 | 113970 | Lamb, Tim |  | 25-Jul-19 | 16-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
317825 | (WO 317825) UG Secondary Service Relocation - 54 Sanderson cr | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2019 |  | Alectra Utilities | 02-Mar-18 |  |  | 17719 | 585.51 | 17719 | 17719 | Lamb, Tim | Transpw | 25-Jul-19 | 17-Jul-18 | 25-Jul-19 | 25-Jul-19 | 25-Jul-19 |  |  |  | 0
2020 | 2020 Alectra Projects | [7 empty] | 2020 |  | Alectra Utilities |  | 135 | 206 | 230175132.84 | 228877641.32 |  | 0 | [5 empty] | 10-May-17 | 31-Dec-20
WEST 2020 | West Region | [7 empty] | 2020 |  | Alectra Utilities |  |  | 12 | 61298913.26 | 63762836.95 |  | 0 | [5 empty] | 10-May-17 | 30-Dec-20
451012 | 433 Pelham Road | 830 - St. Catharines | 150828 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | 6453.22 |  | 0 | Jakubowski, Mark |  |  | 08-Jan-21
451016 | Parkside Drive - HWY 6 to Main St. | 820 - Nebo | 150644 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Caucci, Jason |  |  | 21-Dec-20
451043 | Transfer of Hydro One Cust. - Rymal | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Newitt, Andrew | Alectra Utilities | 13-Jul-15 |  |  | 159886.86 | 105989.08 | 119141.3 | 159886.86 | Koeppe, Jeffrey |  | 15-May-19 | 02-Jul-21 | 01-Nov-16 | 02-Aug-19 | 13-Jan-20 | Customer | Customer |  | 40,745.56
451058 | Salerno Dairy (Parkdale and Rennie) | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 21-Jan-19 |  |  | 53207.94 | 59913.08 | 51995.26 | 53207.94 | Roy Owen |  | 12-Mar-19 | 26-Jul-23 | 25-Feb-19 | 20-Mar-19 | 14-Aug-20 | Customer | Customer |  | 1,212.68
451080 | King & Dundurn, Shoppers Plaza | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Roy Owen |  |  | 05-Jan-15
451095 | SuperCrawl-James St N-King-Murray | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 16-Jul-15 |  |  | 3792.42 | 0 | 3792.42 | 3792.42 | Brian Robinson |  |  | 16-Jul-15 | [6 empty] | 0
451112 | First Rd and Green Mountain | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Jakubowski, Mark | Alectra Utilities | 29-Aug-19 |  |  | 1339825.79 | 1249426.02 | 1320818.23 | 1339825.79 | Carr, Brad | B&M | 28-Feb-20 | 30-Nov-20 | 30-Sep-19 | 18-Nov-19 | 27-May-20 | Customer | Customer |  | 19,007.56
451123 | 111 Brockley Dr | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 28-Jun-18 |  |  | 85563.24 | 77608.58 | 85563.24 | 85563.24 | XPopiel, Joseph | GUCI | 10-Aug-18 | 28-Jan-21 | 23-Jul-18 | 16-Aug-18 | 24-Apr-20 | Customer | Customer |  | 0
451136 | Highland F3 4kV Feeder Removal | 820 - Nebo | 150269 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 31-Mar-15 |  |  | 203350.62 | 141702.5 | 203350.62 | 203350.62 | Carr, Brad | K-Line | 20-Dec-19 | 14-Dec-20 | 18-Nov-19 | 18-Nov-19 | 25-Feb-20 |  | Contractor |  | 0
451163 | 85 Mary St | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 01-May-18 |  |  | 135541.28 | 178993.31 | 135541.28 | 135541.28 | Koeppe, Jeffrey | B&M | 03-Aug-18 | 26-Jul-23 | 23-Jul-18 | 05-Sep-18 | 20-Feb-20 | Customer | Customer |  | 0
451169 | 225 Ray St N | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 10-Feb-17 |  |  | 12196.92 | 12032.63 | 10976.53 | 12196.92 | Koeppe, Jeffrey |  | 01-Jun-17 | 17-Jan-22 | 31-May-17 | 10-May-17 | 23-Nov-20 | Customer | Customer |  | 1,220.39
451208 | Kicker Can Removal – 49 Gage Ave N | 820 - Nebo | 150335 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 3924.25 |  | 0 | Brian Robinson |  |  | 29-Dec-20
451218 | 135 Trenholme Cres, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 30-May-16
451219 | 12 West Ave, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Aug-16
451253 | Victora Ave N Pole Move - CN | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 02-Oct-19 |  |  | 120876.21 | 151400.95 | 89582.02 | 120876.21 | Carr, Brad | K-Line | 28-Feb-20 | 16-Nov-20 | 04-Nov-19 | 25-Nov-19 | 24-Feb-20 | MC/PUCC Permit | MC/PUCC Permit |  | 31,294.19
451258 | Stryker Development | 820 - Nebo | 150588 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 29-Apr-21
451281 | John Substation Conversion | 820 - Nebo | 150310 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 02-Nov-18 |  |  | 1506387.16 | 1549365.23 | 1355841.05 | 1506387.16 | Carr, Brad | K-Line | 15-Nov-19 | 08-Mar-21 | 03-Jun-19 | 21-May-19 | 24-Feb-20 |  | Contractor |  | 150,546.11
451286 | Stoneycreek Mountain URD | 820 - Nebo | 150336 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 04-Oct-21
451289 | Taylor SS- Cable Removals | 830 - St. Catharines | 151105 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 12-Nov-18 |  |  | 96063.31 | 156477.98 | 96063.31 | 96063.31 | Andrew Mehlenbacher |  | 23-May-19 | 03-Aug-21 | 08-Apr-19 | 28-May-19 | 08-Jan-20 | Filler | Filler |  | 0
451292 | 175-177 Russell Ave | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | Gamboa, Henry | Alectra Utilities | 24-Jun-19 |  |  | 111390.33 | 122395.64 | 111390.33 | 111390.33 | Frank Giancola | Transpw | 22-Aug-19 | 22-Mar-22 | 12-Aug-19 | 01-Jun-20 | 29-Jun-20 | Customer | Customer |  | 0
451293 | 350 Scott Street | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Feb-20 |  |  | 50730.75 | 67836.88 | 50730.75 | 50730.75 | Dan Despres |  | 29-Apr-20 | 08-Mar-21 | 13-Apr-20 | 28-Sep-20 | 26-Oct-20 | COVID19 | COVID19 |  | 0
451330 | 120 Springvally Cres, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1292.56 |  | 0 | Weaver, Thomas |  |  | 24-Oct-16
451331 | 1342 Stone Church Rd E, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1752.87 | 9357.17 | 9357.17 | Weaver, Thomas |  |  | 07-Nov-16 | [6 empty] | 0
451333 | 191 James St N, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 3332.02 | 10518.9 | 10518.9 | Weaver, Thomas |  |  | 12-Dec-16 | [6 empty] | 0
451334 | 685 Robson Rd, Waterdown | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1290.99 |  | 0 | Weaver, Thomas |  |  | 09-Jan-17
451338 | 111 Church St, st catharines | 820 - Nebo | 150455 | Active | 98 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 24-May-19 |  |  | 67288.03 | 56224.67 | 67288.03 | 67288.03 | Frank Giancola | Fairway | 28-Jun-19 | 26-Jul-23 | 17-Jun-19 | 20-Dec-19 | 07-Jan-20 | Customer | Customer |  | 0
451340 | 2017 Pole Residual - Stirton St | 820 - Nebo | 150335 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 1839.75 |  | 0 | Jakubowski, Mark |  |  | 29-Dec-20
451364 | 77 Yates, st catharines | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2020 | Paesano, Andrew | Alectra Utilities | 18-Apr-19 |  |  | 201192.83 | 106120.69 | 186732.44 | 201192.83 | Frank Giancola | B&M | 19-Jun-19 | 22-Sep-22 | 27-May-19 | 11-Nov-19 | 15-Sep-20 | Customer | Customer |  | 14,460.39
451370 | York Rd Bridge Alterations | 820 - Nebo | 150828 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 28-May-20 |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  | 28-May-20 | 07-Jun-21 | 28-May-20
451374 | TX Structure Removal – Melvin Ave | 820 - Nebo | 150335 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 1749.31 |  | 0 | Jakubowski, Mark |  |  | 29-Dec-20
451388 | 108 James St N, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 13-Feb-17
451398 | 500 James St N, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Frigotto, Rodrigo | Alectra Utilities | 18-Dec-18 |  |  | 105937.24 | 93560.91 | 105937.24 | 105937.24 | Roy Owen | Fairway | 01-Mar-19 | 26-Jul-23 | 19-Feb-19 | 15-Jan-20 | 08-Apr-20 | Customer | Customer |  | 0
451399 | 202 Valley Rd, Waterdown | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 484.14 |  | 0 | Weaver, Thomas |  |  | 21-Apr-17
451400 | 581 Barton St E, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-May-17
451402 | 823 Highway 6 N, Waterdown | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 12-Jun-17
451404 | 823 Highway 6 N, Waterdown | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 9994.68 | 0 | 9994.68 | 9994.68 | Weaver, Thomas |  |  | 12-Jun-17 | [6 empty] | 0
451405 | 81 Skylark Dr, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 26-Jun-17
451406 | 470 Upper Sherman Ave, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 7027.54 | 0 | 7027.54 | 7027.54 | Weaver, Thomas |  |  | 03-Jul-17 | [6 empty] | 0
451411 | Main / Hess Apartments | 820 - Nebo | 150828 | Inactive | 99 | CANCELLED |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities |  |  |  | 0 | 30311.74 |  | 0 | Jakubowski, Mark |  |  | 20-Mar-17
451419 | 357 Wilson St E | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Frigotto, Rodrigo | Alectra Utilities | 12-Mar-19 |  |  | 139201.23 | 158113.91 | 139201.23 | 139201.23 | Koeppe, Jeffrey | Fairway | 10-May-19 | 26-Jul-23 | 23-Apr-19 | 05-May-19 | 29-Jan-20 | Customer | Customer |  | 0
451421 | 130 Osler Dr. DUN | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 17-May-19 |  |  | 23929.97 | 21892.79 | 23929.97 | 23929.97 | Roy Owen |  | 21-Jun-19 | 17-Jan-22 | 19-Jun-19 | 20-Jun-19 | 06-Jan-20 | Customer | Customer |  | 0
451422 | 375 Wilson St. East | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 14-Mar-19 |  |  | 181057.6 | 293344.59 | 153898.75 | 181057.6 | Roy Owen | GUCI | 23-May-19 | 26-Jul-23 | 15-Apr-19 | 20-Aug-19 | 14-Jul-20 | MC/PUCC Permit | COVID19 |  | 27,158.85
451423 | 153 Nash Rd. S HAM | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Jan-18
451424 | 1 Redfern Ave. (Scenic Woods Dev) (Temp) | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 17-Aug-18 |  |  | 94642.19 | 91490.6 | 94642.19 | 94642.19 | Roy Owen | Fairway | 28-Sep-18 | 25-Nov-21 | 19-Sep-18 | 21-Mar-19 | 14-Jan-20 | Customer | Customer |  | 0
451426 | 428 Main St. W HAM | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 25-Jun-18
451428 | 1 Redfern Ave. HAM | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 09-Jul-18
451429 | 440 Victoria Ave. N HAM | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 27-Dec-19 |  |  | 51618.37 | 63212.81 | 51618.37 | 51618.37 | Koeppe, Jeffrey |  | 10-Feb-20 | 26-Jul-23 | 03-Feb-20 | 20-Jan-20 | 30-Jan-20 |  |  |  | 0
451468 | Gibson Ave - Development | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 03-Oct-19 |  |  | 32426.75 | 96197.66 | 32426.75 | 32426.75 | Koeppe, Jeffrey |  | 29-Nov-19 | 11-Jan-21 | 25-Nov-19 | 13-Nov-19 | 31-Jan-20 | Customer | Customer |  | 0
451471 | Hallcrest Ave Rebuild-St.Catharines | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 14-Dec-20
451488 | 807 Alexander Rd, Ancaster | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 11-Jul-17
451490 | 297 Ottawa St N , Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 17606.93 | 0 | 17606.93 | 17606.93 | Hotham, Matthew |  |  | 07-Aug-17 | [6 empty] | 0
451491 | 272 Park St S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 11-Sep-17
451493 | 64 Munroe St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 18-Sep-17
451494 | 360 Beach Rd, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 25-Sep-17
451502 | Geneva St. and Wellend Ave. | 830 - St. Catharines | 150337 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 1185.45 |  | 0 | Hotham, Matthew |  |  | 29-Dec-20
451514 | 467 Charlton Ave E | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 25-Jun-18 |  |  | 170170.03 | 176332.4 | 167354.19 | 170170.03 | Koeppe, Jeffrey | Fairway | 28-Dec-18 | 26-Jul-23 | 30-Nov-18 | 03-May-19 | 19-Jun-20 | Customer | Customer |  | 2,815.84
451525 | TX Room Decommission-28 Rebecca ST | 820 - Nebo | 150336 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Jakubowski, Mark |  |  | 10-Dec-20
451526 | Central Park - Development | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 18-Apr-18 |  |  | 35755.48 | 39502.53 | 35755.48 | 35755.48 | Carr, Brad |  | 07-Jun-18 | 22-Sep-22 | 28-May-18 | 28-Sep-18 | 03-Feb-20 | Customer | Customer |  | 0
451537 | Confederation Beach Sports Park | 820 - Nebo | 150449 | Active | 98 | COMPLETE | Medium | Comm | 2020 | Paesano, Andrew | Alectra Utilities | 04-Jun-20 |  |  | 54489 | 52769.08 | 54489 | 54489 | Roy Owen | Fairway | 07-Aug-20 | 26-Jul-23 | 27-Jul-20 | 26-Jun-20 | 25-Sep-20 |  | Customer |  | 0
451538 | 124 Balsam Ave S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
451550 | 600 Tenth Rd E | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 06-Nov-17
451551 | 31 Ditton Dr | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 06-Nov-17
451552 | 1851 Brampton St | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 11-Dec-17
451559 | Stroud Lane SS feeder removals | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 30-Aug-18 |  |  | 39722.27 | 24317 | 39722.27 | 39722.27 | Andrew Mehlenbacher |  | 05-Dec-18 | 31-Dec-20 | 05-Nov-18 | 01-May-19 | 04-May-20 | Control/SCADA | Control/SCADA |  | 0
451561 | Juravinski Hosptial Back-up Feeder | 820 - Nebo | 151009 | Active | 98 | COMPLETE | VerHigh | Health | 2020 | Jakubowski, Mark | Alectra Utilities | 29-Mar-19 |  |  | 1589878.05 | 1551290.28 | 1233856.35 | 1589878.05 | Carr, Brad | K-Line | 29-Nov-19 | 26-Jul-23 | 01-May-19 | 25-Apr-19 | 14-Feb-20 | MC/PUCC Permit | MC/PUCC Permit |  | 356,021.70
451564 | Bell Pole - Winona Crossing | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 637.62 |  | 0 | Weaver, Thomas |  |  | 20-Nov-17
451567 | 659 Parkdale Ave | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 11-Dec-17
451575 | Village on the Twelve Subdivision | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE | VerHigh | Subdiv | 2020 | Gamboa, Henry | Alectra Utilities | 30-Oct-19 |  |  | 13487.51 | 77201.09 | 13487.51 | 13487.51 | Frank Giancola | Wiens | 19-Dec-19 | 29-Dec-20 | 16-Dec-19 | 05-Nov-19 | 15-Jun-20 | Customer | Customer |  | 0
451576 | 8 Emming Crt, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 20-Nov-17
451581 | 204 Hillyard St, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Frigotto, Rodrigo | Alectra Utilities | 27-Feb-19 |  |  | 79124.5 | 82178.09 | 79124.5 | 79124.5 | Koeppe, Jeffrey | GUCI | 30-Apr-19 | 26-Jul-23 | 10-Apr-19 | 08-Apr-19 | 11-Aug-20 | Customer | Customer |  | 0
451587 | John SS PH 1, Part 2 | 820 - Nebo | 150309 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 05-Oct-18 |  |  | 1324302.44 | 1668243.83 | 1303742.44 | 1324302.44 | Scott Borer |  | 03-Sep-19 | 10-Oct-21 | 02-Jan-19 | 10-Apr-19 | 13-Nov-20 | MC/PUCC Permit | MC/PUCC Permit |  | 20,560.00
451601 | Yates St , St Catharines | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 01-Oct-18 |  |  | 8692.81 | 144053.41 | 8692.81 | 8692.81 | Frank Giancola |  | 01-Nov-18 | 26-Jul-23 | 29-Oct-18 | 12-Oct-18 | 08-Dec-20 | Customer | Customer |  | 0
451603 | 155 Ontario (temp) - St Catharines | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 23-Feb-18 |  |  | 18095.63 | 0 | 18095.63 | 18095.63 | Frank Giancola |  | 03-Apr-18 | 27-Jul-22 | 23-Mar-18 | 18-Feb-19 | 25-Feb-20 | Customer | Customer |  | 0
451608 | John Sub. Conv. 2019 - PH 2, PART 1 | 820 - Nebo | 150310 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 02-Nov-18 |  |  | 2253286.94 | 2668550.09 | 1815276.22 | 2253286.94 | Carr, Brad | K-Line | 28-Jun-19 | 08-Mar-21 | 14-Jan-19 | 24-May-19 | 16-Jul-20 | MC/PUCC Permit | MC/PUCC Permit |  | 438,010.72
451609 | Salerno Dairy | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities | 18-Sep-18 |  |  | 410021.9 | 432939.11 | 410021.9 | 410021.9 | Roy Owen | B&M | 05-Nov-18 | 24-Aug-20 | 29-Oct-18 | 29-Oct-18 | 14-Jan-20 |  | Customer |  | 0
451618 | Hamilton 2018 Pole Residuals | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Aug-18 |  |  | 108187.77 | 102395.08 | 108187.77 | 108187.77 | Carr, Brad | K-Line | 06-Dec-19 | 14-Dec-20 | 18-Nov-19 | 27-Jan-20 | 24-Feb-20 | Locates | Locates |  | 0
451624 | Baldwin #1 2018 URD Phase 1 | 820 - Nebo | 150351 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 26-Nov-18 |  |  | 137494.75 | 151504.38 | 137494.75 | 137494.75 | Andrew Mehlenbacher |  | 04-Jul-19 | 15-Sep-21 | 10-Jun-19 | 02-Jul-19 | 24-Sep-20 | Control/SCADA | Control/SCADA |  | 0
451629 | 49 Dunbar Ave | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 19-Mar-18
451630 | 600 Second Rd. E. | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 16-Jul-18 |  |  | 15126.18 | 25744.31 | 5316.31 | 15126.18 | Carr, Brad | Fairway | 20-Aug-18 | 17-Jan-22 | 20-Aug-18 | 18-Sep-18 | 11-Jan-20 | Customer | Customer |  | 9,809.87
451632 | 23 Royce Ave | 820 - Nebo | 150449 | Active | 98 | COMPLETE | High | Infrast | 2020 | Paesano, Andrew | Alectra Utilities | 21-Nov-19 |  |  | 66727.16 | 63393.08 | 73123.2 | 66727.16 | Koeppe, Jeffrey |  | 14-Apr-20 | 26-Jul-23 | 06-Apr-20 | 06-Apr-20 | 17-Aug-20 |  | COVID19 |  | -6,396.04
451633 | 1224 Stone Church Rd E | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 30-Apr-18
451636 | 72 Sherman Ave S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Jan-18
451637 | Wentworth St Railway Crossing - Juravinski | 820 - Nebo | 151009 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 13-Sep-19 |  |  | 447710.36 | 401125.52 | 320071.79 | 447710.36 | Carr, Brad | K-Line | 08-Nov-19 | 15-Sep-21 | 07-Oct-19 | 18-Nov-19 | 05-Oct-20 | Locates | Locates |  | 127,638.57
451638 | Baldwin #2 Overhead Conversion Ph 1 | 820 - Nebo | 150268 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 03-Jun-19 |  |  | 2166145.73 | 2303892.34 | 1997747.69 | 2166145.73 | Carr, Brad | K-Line | 21-Feb-20 | 02-Jul-21 | 02-Jul-19 | 22-Jul-19 | 20-Nov-20 | Locates | Customer |  | 168,398.04
451639 | Rear Alley-Btwn John & Hughson St S | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 07-Jun-19 |  |  | 882857.79 | 929624.13 | 870414.59 | 882857.79 | Carr, Brad | B&M | 22-Nov-19 | 24-Aug-20 | 08-Jul-19 | 08-Jul-19 | 24-Feb-20 | Customer | Customer |  | 12,443.20
451644 | Central Conversion 2019 - Phase 1 | 820 - Nebo | 150352 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 21-Jun-19 |  |  | 1939267.23 | 1384542.2 | 1886334.57 | 1939267.23 | Carr, Brad | K-Line | 13-Dec-19 | 18-Feb-21 | 03-Sep-19 | 10-Sep-19 | 24-Feb-20 | Contractor | Contractor |  | 52,932.66
451648 | Upper Sherman Extension | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Velickovski, Goran | Alectra Utilities | 21-Jun-19 |  |  | 358775.82 | 407087.05 | 358775.82 | 358775.82 | Carr, Brad | Transpw | 07-Aug-19 | 22-Sep-22 | 22-Jul-19 | 22-Nov-19 | 14-Feb-20 | Customer | Customer |  | 0
451651 | 634 Upper Sherman Ave, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 20-Feb-18
451652 | 227 Templemead Dr, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 20-Feb-18
451655 | Explore Townhomes - Albright Road | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 07-Feb-19 |  |  | 213115.06 | 1154813.07 | 213115.06 | 213115.06 | Andrew Mehlenbacher |  | 10-May-19 | 11-Feb-21 | 18-Mar-19 | 30-Jul-19 | 14-Feb-20 | Customer | Customer |  | 0
451658 | 125 Wilson St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 26-Feb-18
451671 | 464 Welland Ave, St Catharines | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 20-Dec-19 |  |  | 55535.1 | 58328.07 | 55535.1 | 55535.1 | Frank Giancola |  | 11-Feb-20 | 26-Jul-23 | 03-Feb-20 | 16-Jan-20 | 21-Aug-20 |  | Customer |  | 0
451672 | Urban Core Developments - Victoria Ave | 820 - Nebo | 150665 | Active | 98 | COMPLETE |  |  | 2020 | Velickovski, Goran | Alectra Utilities | 05-Oct-18 |  |  | 72348.16 | 67534.87 | 72348.16 | 72348.16 | Koeppe, Jeffrey |  | 04-Dec-18 | 26-Jul-23 | 19-Nov-18 | 19-Nov-18 | 13-Jan-20 | Customer | Customer |  | 0
451673 | Flamborough Power Center | 820 - Nebo | 150588 | Active | 95 | COMPLETE |  |  | 2020 | Velickovski, Goran | Alectra Utilities | 05-Jul-18 |  |  | 57168.93 | 74027.52 | 53092.5 | 57168.93 | Roy Owen |  | 10-Sep-18 | 26-Jul-23 | 20-Aug-18 | 26-Jul-18 | 14-Jan-20 |  | Customer |  | 4,076.43
451677 | Waterdown Bay - Hydro Supply | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 27-Apr-18 |  |  | 3691.59 | 3818.72 | 3691.59 | 3691.59 | Carr, Brad |  | 05-Jun-18 | 07-Sep-21 | 04-Jun-18 | 07-Jun-18 | 03-Nov-20 | Customer | Customer |  | 0
451691 | 85 Holton Ave. S | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 335.88 |  | 0 | Weaver, Thomas |  |  | 27-Jul-18
451692 | 56 Third Rd E | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 49.3 |  | 0 | Weaver, Thomas |  |  | 27-Jul-18
451693 | 37 Henley Dr, St.Catharines | 820 - Nebo | 150455 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
451694 | 565 Seaman St, Stoney Creek | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
451696 | 2070 Rymal Rd E, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE | Low | Comm | 2020 | Paesano, Andrew | Alectra Utilities | 23-Jan-20 |  |  | 71006.63 | 62698.23 | 71006.63 | 71006.63 | Roy Owen | Fairway | 10-Mar-20 | 26-Jul-23 | 02-Mar-20 | 02-Mar-20 | 25-Sep-20 |  | Customer |  | 0
451697 | 462 & 464 Mary St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
451698 | 229 Read Rd, St. Catharines | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE |  |  | 2020 | Frigotto, Rodrigo | Alectra Utilities | 07-Jan-20 |  |  | 55619.68 | 46931.9 | 55619.68 | 55619.68 | Frank Giancola | Wiens | 24-Feb-20 | 26-Jul-23 | 18-Feb-20 | 03-Jul-20 | 30-Jun-20 | Customer | Customer |  | 0
451699 | 54-42 Lakeshore Rd, Stoney Creek | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 04-Aug-20
451703 | 44 Leckie Ave | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 05-Nov-18
451704 | Lower Davis Creek Flood Control | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 04-Aug-20
451709 | 738 Mud St E, Stoney Creek | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
451710 | 7 Gertrude St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
451714 | 31 John St N, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 28-Jan-19
451715 | 117 Park St S, Hamilton | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 04-Aug-20
451718 | 7 Gertrude St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
451719 | 82 Parkside Dr, Flamborough | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
451720 | 2750 King St E, Stoney Creek | 820 - Nebo | 150449 | Active | 98 | COMPLETE | VerHigh | Res-ICI | 2020 | Paesano, Andrew | Alectra Utilities | 09-Jan-20 |  |  | 224281.34 | 222433.94 | 224281.34 | 224281.34 | Roy Owen | Fairway | 31-Mar-20 | 26-Jul-23 | 18-Feb-20 | 13-Mar-20 | 08-Jun-20 | Customer | Customer |  | 0
451721 | 1212 Main St. E - Bell Station | 820 - Nebo | 150449 | Active | 98 | COMPLETE | High | Comm | 2020 | Paesano, Andrew | Alectra Utilities | 09-Apr-20 |  |  | 95727.37 | 83535.2 | 95727.37 | 95727.37 | Roy Owen | Fairway | 17-Jul-20 | 26-Jul-23 | 11-May-20 | 20-Apr-20 | 30-Jun-20 |  |  |  | 0
451723 | 212 Natinal Dr. | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 25-Mar-19
451724 | 121 Hwy 8, Stoney Creek | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 23-Apr-19
451725 | 198 Welland Ave. St. Kitts | 820 - Nebo | 150455 | Active | 98 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 02-Oct-19 |  |  | 40398.04 | 45463.51 | 40398.04 | 40398.04 | Frank Giancola | Wiens | 15-Nov-19 | 01-Aug-23 | 04-Nov-19 | 24-Oct-19 | 10-Aug-20 | Customer | Customer |  | 0
451730 | 10 Newman Rd, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Dec-21
451732 | CHH Demo - James St N & MacNab St N | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-May-19
451733 | 23 Southmeadow Cres. | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-May-19
451734 | 284 Winona Rd, Stoney Creek | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-May-19
451736 | Effort Square T75 - 140 King St E | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 19-Mar-19 |  |  | 396215.6 | 537801.76 | 362193.99 | 396215.6 | Carr, Brad | B&M | 18-Oct-19 | 08-Mar-21 | 18-Sep-19 | 13-Sep-19 | 14-Feb-20 | Customer | Customer |  | 34,021.61
451739 | Concession & U Gage Pole Replacment - Juravinski | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 02-Apr-18 |  |  | 94552.5 | 12079.99 | 94552.5 | 94552.5 | Weaver, Thomas |  | 05-Feb-20 | 04-May-20 | 05-Feb-20 | 05-Feb-20 | 05-Feb-20 |  |  |  | 0
451742 | 38 West Ave N, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 14-May-18
451743 | Humphrey Street Townhomes Sub | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 04-Dec-18 |  |  | 16995.44 | 236763.36 | 11619.31 | 16995.44 | Andrew Mehlenbacher |  | 12-Feb-19 | 10-May-21 | 04-Feb-19 | 20-Mar-19 | 04-Dec-20 | Customer | Customer |  | 5,376.13
451745 | Royce Ave Expansion - Stoneycreek | 820 - Nebo | 150665 | Active | 98 | COMPLETE | High | Infrast | 2020 | Jakubowski, Mark | Alectra Utilities | 20-Jan-20 |  |  | 340377.92 | 377444.64 | 318283.45 | 340377.92 | Scott Borer | N/A | 01-Jun-20 | 26-Jul-23 | 01-Apr-20 | 02-Mar-20 | 06-Oct-20 |  | COVID19 |  | 22,094.47
451750 | 43 Farmer Crt, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1769.09 |  | 0 | Weaver, Thomas |  |  | 23-Jul-18
451751 | 729 Centre Rd, Flamborough | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1591.28 |  | 0 | Weaver, Thomas |  |  | 23-Jul-18
451753 | 1911 Barton St E, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 616.83 |  | 0 | Weaver, Thomas |  |  | 07-Aug-18
451776 | 85 Holton Ave S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 25-Jun-18
451778 | 105 Vansickle Rd, St.Catharines | 830 - St. Catharines | 150455 | Active | 95 | COMPLETE | VerHigh | Res-ICI | 2020 | Frigotto, Rodrigo | Alectra Utilities | 31-Jan-19 |  |  | 79619.45 | 68199.51 | 79619.45 | 79619.45 | Frank Giancola | Wiens | 28-Mar-19 | 26-Jul-23 | 11-Mar-19 | 15-Feb-19 | 01-May-20 | Customer | Customer |  | 0
451780 | 480 King William St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 25-Jun-18
451784 | Empire-Red Hill Ph. 3 & 4 | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 07-Feb-19 |  |  | 52564.51 | 907174.2 | 52564.51 | 52564.51 | Carr, Brad |  | 25-Jul-19 | 18-Jan-22 | 20-May-19 | 06-May-19 | 24-Feb-20 | Customer | Customer |  | 0
451785 | 90 Beach Rd 12MVA Expansion | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 17-Aug-22
451786 | 63 Worsley Rd | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 03-Jul-18
451787 | 856 Barton St.E | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 09-Oct-19 |  |  | 38277 | 25732.04 | 38277 | 38277 | Koeppe, Jeffrey | Fairway | 15-Nov-19 | 15-Jul-21 | 13-Nov-19 | 07-Nov-19 | 28-Jan-20 | Customer | Customer |  | 0
451790 | 479 King St.E | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 14-Dec-18 |  |  | 21227.62 | 2140.68 | 21227.62 | 21227.62 | Koeppe, Jeffrey |  | 15-Feb-19 | 15-Jul-21 | 11-Feb-19 |  |  |  | Customer |  | 0
451793 | 154 Main St.E(Temp Service) | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 18-Jan-19 |  |  | 42972.57 | 50326 | 42972.57 | 42972.57 | Roy Owen | Fairway | 25-Feb-19 | 20-Jul-20 | 18-Feb-19 | 01-May-19 | 14-Jan-20 |  | Customer |  | 0
451800 | Port Dalhousie Marina | 830 - St. Catharines |  | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Dec-20
451805 | 87 Kennedy Ave | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 23-Apr-20 | 10-Dec-20 | 23-Apr-20 | 23-Apr-20 | 23-Apr-20
451808 | Biggar St Wire Removal | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 12-Apr-21
451814 | Nora Frances School | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 04-Nov-19 |  |  | 53381.95 | 45899.9 | 53381.95 | 53381.95 | Roy Owen |  | 09-Dec-19 | 26-Jul-23 | 05-Dec-19 | 28-Nov-19 | 14-Feb-20 | Customer | Customer |  | 0
451815 | 623 Upper James St | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Frigotto, Rodrigo | Alectra Utilities | 21-Nov-19 |  |  | 94853.08 | 90950.62 | 94853.08 | 94853.08 | Koeppe, Jeffrey | B&M | 07-Jan-20 | 26-Jul-23 | 19-Dec-19 | 13-Jan-20 | 31-Jul-20 | Customer | Customer |  | 0
451816 | 954 Concession St | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 12-Aug-20 |  |  | 36499.18 | 54955.62 | 36499.18 | 36499.18 | Koeppe, Jeffrey |  | 22-Sep-20 | 25-Mar-21 | 14-Sep-20 | 09-Sep-20 | 07-Oct-20 |  | Customer |  | 0
451817 | 806 Beeforth Rd | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-May-19
451820 | 92 Barton St.E | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 127.73 |  | 0 | Weaver, Thomas |  |  | 10-Jun-19
451826 | 620 King St. EAST HAM | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 09-Jul-18
451828 | 390 Rymal Rd W HAM | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Aug-18
451830 | Riverwalk Condos FLA | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 07-Aug-18
451836 | 21 John St. S | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 15-Oct-18
451839 | 858 Burlington St. E, HAM | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 02-Jan-19
451841 | 195 James St. S. | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 28-Jan-19
451843 | 156 5th Conc Rd. E WTD | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 04-Feb-19
451845 | 560 - 580 Highland Rd W, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 23-Jul-18
451846 | 323 Aberdeen Ave, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 23-Jul-18
451848 | Rymal and Nebo 27kV Expansion | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities | 23-Nov-18 |  |  | 1090260.92 | 1381019.54 | 1090260.92 | 1090260.92 | Carr, Brad | B&M | 03-May-19 | 15-Sep-21 | 07-Jan-19 | 07-Jan-19 | 03-Jun-20 |  |  |  | 0
451850 | Main / Broadway MH Install for LRT | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas | N/A | 24-Jan-20 | 23-Jul-18 | 24-Jan-20 | 24-Jan-20 | 24-Jan-20
451865 | 2018 Manhole & Vault Lid Repairs | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 04-Nov-20 |  |  | 0 | 57330.28 |  | 0 | Carr, Brad |  | 04-Nov-20 | 08-Mar-21 | 04-Nov-20 | 04-Nov-20 | 04-Nov-20
451869 | Wentworth -10 #6 Replacement | 820 - Nebo | 150345 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Jul-19 |  |  | 298365.93 | 495178.61 | 298365.93 | 298365.93 | Scott Borer |  | 17-Mar-20 | 01-Jul-21 | 06-Jan-20 | 06-Jan-20 | 13-Nov-20 | Locates | COVID19 |  | 0
451870 | 201 Concession 5th E, Flamborough | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 07-Aug-18
451875 | Skinner Rd. Re work | 820 - Nebo | 150588 | Inactive | 99 | CANCELLED |  |  | 2020 | Beaudrie, Scott | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas | N/A | 17-Jun-20 | 22-Mar-21 | 17-Jun-20 | 17-Jun-20 | 17-Jun-20
451882 | 11 Morningstar Crt | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 2821.6 |  | 0 | Weaver, Thomas |  |  | 24-Sep-18
451884 | 41 Hopkins Crt - Dundas | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 2093.86 |  | 0 | Weaver, Thomas |  |  | 15-Oct-18
451888 | 15 Tevere Pl - Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 2297 |  | 0 | Weaver, Thomas |  |  | 17-Dec-18
451889 | 137 Peter St - Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 2693.16 |  | 0 | Weaver, Thomas |  |  | 14-Jan-19
451890 | 530 Scenic Dr - Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 2454.16 |  | 0 | Weaver, Thomas |  |  | 28-Jan-19
451892 | 26 Berry Hill Ave - Flamborough | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 11-Mar-19
451895 | 85 Coreslab Dr, Waterdown | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED | High | Indust | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 5319.27 |  | 0 | Weaver, Thomas |  |  | 15-Oct-18
451896 | 45 Ewen Rd, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1369.34 |  | 0 | Weaver, Thomas |  |  | 12-Nov-18
451897 | 77 Leland St, Hamilton | 820 - Nebo | 150449 | Active | 98 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 14541.67 |  | 0 | Weaver, Thomas |  | 31-Mar-20 | 26-Jul-23 | 31-Mar-20 | 31-Mar-20 | 31-Mar-20
451900 | 90 Beach Rd, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1410.8 |  | 0 | Weaver, Thomas |  |  | 17-Dec-18
451901 | 77 Leland St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2020 | Kappheim, Adam | Alectra Utilities | 16-Apr-20 |  |  | 45597.1 | 50032.02 | 45597.1 | 45597.1 | Koeppe, Jeffrey |  | 26-May-20 | 22-Sep-22 | 19-May-20 | 19-May-20 | 08-Jun-20 |  | Customer |  | 0
451903 | 33 Stoneridge Crt, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1012.7 |  | 0 | Weaver, Thomas |  |  | 14-Jan-19
451904 | 10 Sherman Rise, Dundas | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1069.38 |  | 0 | Weaver, Thomas |  |  | 28-Jan-19
451905 | 200 Sherman Ave S, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1613.51 |  | 0 | Weaver, Thomas |  |  | 04-Feb-19
451909 | 119 Hwy 5, Waterdown | 820 - Nebo | 150449 | Active | 98 | COMPLETE | High | Indust | 2020 | Frigotto, Rodrigo | Alectra Utilities | 07-Feb-20 |  |  | 77960.94 | 66918.22 | 77960.94 | 77960.94 | Roy Owen | Fairway | 27-Mar-20 | 26-Jul-23 | 18-Mar-20 | 08-Jun-20 | 17-Jun-20 | Customer | Customer |  | 0
451915 | The Orchard - Formerly Simpson Rd Condos | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 25-Nov-19 |  |  | 197842.39 | 162188.53 | 197842.39 | 197842.39 | Frank Giancola |  | 14-Jan-20 | 11-Jan-21 | 06-Jan-20 | 03-Aug-20 | 13-Aug-20 | Customer | Customer |  | 0
451931 | 240 Margaret Ave | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 22-Oct-18
451933 | 991 Main St E | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 26-Nov-18
451936 | 37 & 39 Galbraith Dr | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Dec-18
451937 | Waterdown Bay - Pond 1 | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 03-May-19 |  |  | 11591.47 | 137371.58 | 11591.47 | 11591.47 | Carr, Brad |  | 05-Jun-19 | 02-Jun-21 | 27-May-19 | 13-Sep-19 | 03-Nov-20 | Customer | Customer |  | 0
451939 | Hamilton 2019 Pole Residuals Phase1 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 08-Jun-20 |  |  | 157978.01 | 221031.51 | 206825.77 | 157978.01 | Carr, Brad | B&M | 21-Aug-20 | 02-Jul-21 | 20-Jul-20 | 20-Jul-20 | 09-Sep-20 |  | Contractor |  | -48,847.76
451941 | 27 Lombardy Ave, St. Catharines | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 25-May-20 |  |  | 92610.21 | 66548.43 | 87774.93 | 92610.21 | Frank Giancola | Wiens | 21-Jul-20 | 26-Jul-23 | 29-Jun-20 | 02-Jul-20 | 19-Aug-20 | Locates | Customer |  | 4,835.28
451952 | 331X_Part 2 | 820 - Nebo | 151250 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 04-Apr-19 |  |  | 919724.95 | 1100808.87 | 770492.55 | 919724.95 | Andrew Mehlenbacher | B&M | 22-Aug-19 | 15-Jul-21 | 13-May-19 | 14-May-19 | 19-Oct-20 | Control/SCADA | Control/SCADA |  | 149,232.40
451953 | 331X_Part 3 | 820 - Nebo | 151250 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 15-Apr-19 |  |  | 774665.54 | 1129746.95 | 728865.21 | 774665.54 | Andrew Mehlenbacher | B&M | 30-Aug-19 | 15-Jul-21 | 13-May-19 | 14-May-19 | 30-Nov-20 | Control/SCADA | Control/SCADA |  | 45,800.33
451954 | Fontainbleu Reliability | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 21-Oct-19 |  |  | 605492.82 | 85120.05 | 617580.23 | 605492.82 | Carr, Brad | B&M | 09-Jan-20 | 08-Mar-21 | 18-Nov-19 | 28-Oct-19 | 29-Sep-20 |  | Contractor |  | -12,087.41
451957 | Towering Heights Expansion | 830 - St. Catharines | 150665 | Active | 98 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 13-Jul-20 |  |  | 255128.91 | 221035.48 | 240512.52 | 255128.91 | Frank Giancola | B&M | 27-Oct-20 | 15-Aug-23 | 14-Sep-20 | 16-Oct-20 | 20-Nov-20 | Customer | Customer |  | 14,616.39
451959 | Juravinski - Gage St Escarpment | 820 - Nebo | 151009 | Active | 98 | COMPLETE | VerHigh | Health | 2020 | Jakubowski, Mark | Alectra Utilities | 25-Sep-19 |  |  | 774954.39 | 603664.28 | 742182.74 | 774954.39 | Carr, Brad | K-Line | 20-Dec-19 | 26-Jul-23 | 28-Oct-19 | 24-Feb-20 | 20-Apr-20 | MC/PUCC Permit | Control/SCADA |  | 32,771.65
451960 | Juravinski - Cannon/Gage Upgrades | 820 - Nebo | 151009 | Active | 98 | COMPLETE | VerHigh | Health | 2020 | Jakubowski, Mark | Alectra Utilities | 29-Mar-19 |  |  | 3910321.52 | 4087233.3 | 3617493.57 | 3910321.52 | Carr, Brad | B&M | 06-Nov-19 | 26-Jul-23 | 01-May-19 | 13-May-19 | 16-Apr-20 | MC/PUCC Permit | MC/PUCC Permit |  | 292,827.95
451963 | Bell Pole Relocation - GM & Upp Cen | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Dec-20
451965 | 2018 Pole Residual Phase 3 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-May-19 |  |  | 147913.58 | 163678.99 | 147913.58 | 147913.58 | Dan Despres |  | 03-Jan-20 | 14-Dec-20 | 11-Nov-19 | 30-Dec-19 | 11-Feb-20 | Filler | Filler |  | 0
451966 | U. Gage & Loconder Dr - cable | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 20-Jan-20 |  |  | 2997686.94 | 3466392.1 | 2989649.15 | 2997686.94 | Carr, Brad | B&M | 30-Oct-20 | 30-May-22 | 01-Apr-20 | 16-Mar-20 | 23-Dec-20 |  | Contractor |  | 8,037.79
451967 | Jacobson Ave - UG Portion | 830 - St. Catharines | 151066 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 20-Sep-19 |  |  | 1898503.62 | 1920569.82 | 1822800.4 | 1898503.62 | Carr, Brad | B&M | 03-Apr-20 | 15-Jul-21 | 01-Oct-19 | 30-Sep-19 | 27-May-20 |  | Contractor |  | 75,703.22
451971 | Hamilton Mountain URD 2019 Part 4 | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities | 01-May-19 |  |  | 0 | 4328.3 |  | 0 | Weaver, Thomas |  |  | 24-Aug-20
451972 | 60 Vola Court - Rotten Poles | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 19-Mar-19 |  |  | 148253.75 | 136276.5 | 114513.56 | 148253.75 | Carr, Brad | K-Line | 22-Nov-19 | 14-Dec-20 | 28-Oct-19 | 11-Feb-20 | 07-May-20 | Locates | Materials |  | 33,740.19
451973 | 176 Pelham Rd Pole Move | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 23-Dec-19 |  |  | 12040.47 | 11148.24 | 12040.47 | 12040.47 | Frank Giancola |  | 07-Feb-20 | 16-Nov-20 | 05-Feb-20 | 16-Jan-20 | 17-Jan-20 |  |  |  | 0
451976 | Ottawa 4 - #6 Replacement | 820 - Nebo | 150333 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 1213776.8 | 968986.02 | 1137791.1 | 1213776.8 | Carr, Brad | K-Line | 06-Nov-20 | 15-Sep-21 | 20-Jul-20 | 20-Jul-20 | 23-Dec-20 |  | Contractor |  | 75,985.70
451977 | Eleanor & Stonechurch PMH (16458) | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-May-19 |  |  | 411787.76 | 442336.28 | 403885.57 | 411787.76 | Carr, Brad | B&M | 16-Dec-19 | 31-Dec-20 | 10-Sep-19 | 11-Nov-19 | 14-Feb-20 | Contractor | Contractor |  | 7,902.19
451979 | Wentworth St Escarpment Climb - Juravinski | 820 - Nebo | 151009 | Active | 98 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 04-Jun-19 |  |  | 406655.25 | 437299.29 | 317516.83 | 406655.25 | Carr, Brad | K-Line | 16-Aug-19 | 26-Jul-23 | 02-Jul-19 | 24-Sep-19 | 24-Feb-20 | MC/PUCC Permit | MC/PUCC Permit |  | 89,138.42
451980 | URD-Limeridge W & Kendale Switches | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 1441315.33 | 1422134.8 | 1341655.17 | 1441315.33 | Carr, Brad | B&M | 16-Oct-20 | 20-Sep-21 | 01-Apr-20 | 16-Mar-20 | 17-Nov-20 |  | Customer |  | 99,660.16
451982 | Pole Relocate-Birch Ave & Barton St | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 30-Dec-19 |  |  | 28991.48 | 25740.56 | 28991.48 | 28991.48 | Carr, Brad | K-Line | 28-Feb-20 | 09-Aug-21 | 24-Feb-20 | 24-Feb-20 | 30-Jun-20 |  | Contractor |  | 0
451988 | Beach Blvd - Rear Alley Relocation | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 05-Sep-19 |  |  | 41115.29 | 27975.46 | 41115.29 | 41115.29 | XPopiel, Joseph |  | 31-Oct-19 | 03-Dec-20 | 21-Oct-19 | 02-Dec-19 | 21-Feb-20 | Locates | Locates |  | 0
451992 | Life - recoverable re-locations | 820 - Nebo | 150588 | Inactive | 99 | CANCELLED |  |  | 2020 | Gamboa, Henry | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Dec-20
452003 | 12 Silverdale Dr | 830 - St. Catharines | 150455 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
452012 | Hamilton 2019 Pole Removals | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jan-19 |  |  | 0 | 297979.83 |  | 0 | Brian Robinson |  | 31-Dec-19 | 21-Dec-20 | 01-Jan-19 | 31-Dec-19 | 03-Feb-20 | Filler | Filler
452013 | St. Catharines 2019 Pole Removals | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jan-19 |  |  | 0 | 266778.57 |  | 0 | Brian Robinson |  | 31-Dec-19 | 08-Mar-21 | 01-Jan-19 | 31-Dec-19 | 03-Feb-20 | N/A | N/A
452015 | SCH 2019 Pole Residuals Phase 2 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-May-19 |  |  | 95156.09 | 128445.44 | 95156.09 | 95156.09 | Dan Despres | N/A | 04-Feb-20 | 14-Dec-20 | 06-Jan-20 | 20-Jan-20 | 10-Feb-20 | Locates | Locates |  | 0
452016 | Juravinski - Circuit 8621 X Install - Part 2 | 820 - Nebo | 151009 | Active | 98 | COMPLETE | High | Health | 2020 | Jakubowski, Mark | Alectra Utilities | 29-Mar-19 |  |  | 400974.9 | 544144.27 | 282553.73 | 400974.9 | Tony Ierace |  | 12-Jul-19 | 26-Jul-23 | 13-May-19 | 29-Jul-19 | 16-Oct-20 | Lines | Lines |  | 118,421.17
452018 | 391X - Feeder Extension | 820 - Nebo | 151066 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 04-Apr-19 |  |  | 403943.15 | 383581.67 | 403943.15 | 403943.15 | Andrew Mehlenbacher | Fairway | 29-Aug-19 | 23-Aug-21 | 15-May-19 | 16-Jul-19 | 10-Sep-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
452019 | York and Willowglen Pole Replace | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 18-Feb-20 |  |  | 76389.28 | 33751.81 | 69932.28 | 76389.28 | Carr, Brad | K-Line | 18-Feb-20 | 08-Mar-21 | 18-Feb-20 | 18-Feb-20 | 18-Feb-20 |  | xBy-passed |  | 6,457.00
452031 | #6 Replacement - WL4-WL1 | 820 - Nebo | 150350 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Nov-19 |  |  | 1215547.33 | 829740.42 | 1215547.33 | 1215547.33 | Scott Borer |  | 15-Oct-20 | 01-Jul-21 | 06-Jan-20 | 20-Jan-20 | 13-Nov-20 | Locates | Locates |  | 0
452042 | Cogeco Make Ready - Queendale Ave E | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 02-Aug-19 |  |  | 13335.83 | 9654.24 | 13335.83 | 13335.83 | Scott Borer |  | 12-Sep-19 | 11-Jul-22 | 09-Sep-19 | 14-Nov-19 | 31-Jan-20 | Locates | Locates |  | 0
452045 | Hydro Pole Relocates - Dundas St E | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 13-Jan-20 |  |  | 501411.18 | 408091.73 | 456255.21 | 501411.18 | Carr, Brad | K-Line | 26-Jun-20 | 19-Nov-20 | 16-Mar-20 | 09-Mar-20 | 06-Aug-20 |  | COVID19 |  | 45,155.97
452053 | SCH 2019 Pole Residuals Phase 3 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-May-19 |  |  | 138041.39 | 141780.33 | 121513.81 | 138041.39 | Carr, Brad | B&M | 31-Jan-20 | 14-Dec-20 | 06-Jan-20 | 19-Dec-19 | 24-Feb-20 |  | Contractor |  | 16,527.58
452054 | SCH 2019 Pole Residuals Phase 4 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-May-19 |  |  | 60447.86 | 72857.83 | 60447.86 | 60447.86 | Carr, Brad | A&W | 31-Jan-20 | 14-Dec-20 | 06-Jan-20 | 06-Jan-20 | 29-Jan-20 |  |  |  | 0
452055 | SCH 2019 Pole Residuals Phase 5 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-May-19 |  |  | 132949.93 | 125865.1 | 132949.93 | 132949.93 | Dan Despres |  | 06-Mar-20 | 02-Jul-21 | 03-Feb-20 | 13-Feb-20 | 17-Aug-20 | Locates | Locates |  | 0
452056 | SCH 2019 Pole Residuals Phase 6 | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-May-19 |  |  | 135770.89 | 119865.64 | 135770.89 | 135770.89 | Dan Despres |  | 15-Apr-20 | 02-Jul-21 | 09-Mar-20 | 09-Mar-20 | 28-Sep-20 |  | COVID19 |  | 0
452058 | Wentworth - 12 # 6 Replacement | 820 - Nebo | 150345 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 21-Jun-19 |  |  | 211153.31 | 340295.84 | 211153.31 | 211153.31 | XPopiel, Joseph |  | 16-Jan-20 | 29-Oct-20 | 25-Nov-19 | 05-Sep-19 | 17-Jan-20 |  | Locates |  | 0
452059 | U/G Pedestal Replacement-St cath | 820 - Nebo | 151064 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 28-May-19 |  |  | 106904.43 | 93867.39 | 106904.43 | 106904.43 | Frank Giancola |  | 31-Dec-19 | 19-Nov-20 | 06-Aug-19 | 11-Nov-19 | 28-Feb-20 | Materials | Materials |  | 0
452061 | 65 Guise St Structure Conversion | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 17-Jul-20 |  |  | 396377.49 | 399816.17 | 301480.65 | 396377.49 | Carr, Brad | B&M | 04-Sep-20 | 14-Dec-21 | 06-Aug-20 | 10-Aug-20 | 20-Aug-20 | Contractor |  |  | 94,896.84
452062 | Discovery Dr. Structure Relocation | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas | B&M |  | 15-Sep-21
452065 | LBDS-Switch Replacement-St. Cath. | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-May-19 |  |  | 114837.88 | 156059.12 | 114837.88 | 114837.88 | Dan Despres |  | 21-Oct-19 | 08-Mar-21 | 09-Sep-19 | 24-Sep-19 | 07-Feb-20 | Filler | Filler |  | 0
452069 | Manhole Roof Replacement - Hamilton | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 26-Aug-20 |  |  | 284160.86 | 298021.69 | 366155.42 | 284160.86 | Carr, Brad | B&M | 13-Nov-20 | 15-Jul-21 | 28-Sep-20 | 05-Oct-20 | 23-Dec-20 | Contractor | Materials |  | -81,994.56
452070 | HI-2 Removal | 820 - Nebo | 150269 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Nov-19 |  |  | 190761.63 | 187515.61 | 190761.63 | 190761.63 | Carr, Brad | K-Line | 30-Dec-19 | 14-Dec-20 | 25-Nov-19 | 06-Jan-20 | 31-Jan-20 | Contractor | Contractor |  | 0
452072 | Feeder Unshare-Juravinski Hospital | 820 - Nebo | 151009 | Active | 98 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 14-May-19 |  |  | 833434.39 | 943461.06 | 668604.11 | 833434.39 | Carr, Brad | K-Line | 06-Sep-19 | 26-Jul-23 | 10-Jun-19 | 10-Jun-19 | 09-Oct-20 | MC/PUCC Permit | MC/PUCC Permit |  | 164,830.28
452078 | 1926 Seventh St Louth, St. Catharines | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 08-Aug-19 |  |  | 96436.19 | 143589.04 | 96436.19 | 96436.19 | Frank Giancola |  | 03-Sep-20 | 26-Jul-23 | 24-Aug-20 | 17-Sep-19 | 27-Oct-20 | Customer | Customer |  | 0
452081 | 191 James St N, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 619.09 |  | 0 | Weaver, Thomas |  |  | 08-Apr-19
452082 | 1575 Main St W, Hamilton | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2019 | Kappheim, Adam | Alectra Utilities | 07-Oct-19 |  |  | 63171.19 | 49404.62 | 63171.19 | 63171.19 | Koeppe, Jeffrey |  | 02-Dec-19 | 26-Jul-23 | 25-Nov-19 | 02-Dec-19 | 27-Dec-19 | Locates | Customer |  | 0
452083 | 509 5th Concession Rd E, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1473.5 |  | 0 | Weaver, Thomas |  |  | 23-Apr-19
452085 | 8 Adams St, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 739.08 |  | 0 | Weaver, Thomas |  |  | 13-May-19
452086 | 138 Overdale Ave, Waterdown | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 92.74 |  | 0 | Weaver, Thomas |  |  | 13-May-19
452088 | 107 Florance Ave, Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1742.53 |  | 0 | Weaver, Thomas |  |  | 13-May-19
452093 | Jarvis St - King William to King | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 28-Aug-19 |  |  | 475059.02 | 488529.67 | 448232.08 | 475059.02 | Carr, Brad | B&M | 30-Dec-19 | 15-Sep-21 | 30-Sep-19 | 04-Nov-19 | 16-Mar-20 | MC/PUCC Permit | MC/PUCC Permit |  | 26,826.94
452094 | 5 Margaret St., Lynden | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Faisal | Alectra Utilities |  |  |  | 0 | 1360.49 |  | 0 | Weaver, Thomas |  |  | 18-Mar-19
452095 | 5 Empress Ave - Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 2018.75 |  | 0 | Weaver, Thomas |  |  | 18-Mar-19
452096 | 176 Queensdale Ave E - Hamilton | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 3266.59 |  | 0 | Weaver, Thomas |  |  | 18-Mar-19
452099 | 295 Dundas St East - Flamborough | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 25-Sep-19 |  |  | 70015.15 | 65134.1 | 70015.15 | 70015.15 | Koeppe, Jeffrey | Fairway | 22-Nov-19 | 25-Mar-21 | 11-Nov-19 | 14-Nov-19 | 06-Apr-20 | Customer | Customer |  | 0
452101 | Dennis Ave & Overdale Ave | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 09-Oct-19 |  |  | 33282.29 | 34455.32 | 33282.29 | 33282.29 | Koeppe, Jeffrey |  | 21-Nov-19 | 15-Jul-21 | 18-Nov-19 | 25-Dec-19 | 15-Jan-20 | Customer | Customer |  | 0
452104 | 30 Jerome Park Dr | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 1393.39 |  | 0 | Weaver, Thomas |  |  | 24-Jun-19
452110 | Stub Pole Relocate - Steel City Crt | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 03-May-19 |  |  | 7175.03 | 4884.63 | 7175.03 | 7175.03 | XPopiel, Joseph |  | 04-Jun-19 | 04-Dec-20 | 03-Jun-19 | 17-Jan-20 | 17-Jan-20 | Customer | Customer |  | 0
452113 | 1215 Barton St (STK) | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 24-Feb-20 |  |  | 55956.88 | 55821.24 | 55956.88 | 55956.88 | Koeppe, Jeffrey | Fairway | 30-Mar-20 | 07-Feb-22 | 23-Mar-20 | 13-Mar-20 | 09-Jul-20 |  | COVID19 |  | 0
452114 | 173 Rykert St | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 22-Jul-20 |  |  | 67568.69 | 55360.64 | 67568.69 | 67568.69 | Frank Giancola |  | 22-Sep-20 | 11-Jan-21 | 16-Sep-20 | 17-Aug-20 | 01-Oct-20 |  | Customer |  | 0
452115 | 690 Rennie 13kV Expansion | 820 - Nebo | 150665 | Active | 98 | COMPLETE | Medium | Infrast | 2020 | Jakubowski, Mark | Alectra Utilities | 01-Apr-20 |  |  | 688528.16 | 669092.54 | 638033.7 | 688528.16 | Carr, Brad | B&M | 17-Jul-20 | 26-Jul-23 | 04-May-20 | 20-Apr-20 | 28-Aug-20 |  | COVID19 |  | 50,494.46
452116 | 1212 Main St E 13kV Expansion - 7412X | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE | High | Comm | 2020 | Vande Kuyt, Greg | Alectra Utilities | 18-Sep-19 |  |  | 1250387.78 | 915586.75 | 1287867.09 | 1250387.78 | Carr, Brad | B&M | 13-Feb-20 | 19-Jan-22 | 07-Oct-19 | 09-Dec-19 | 23-Mar-20 | MC/PUCC Permit | MC/PUCC Permit |  | -37,479.31
452117 | Greenhill Pumping Station | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 15-Sep-21
452120 | Myst - Lakeview Dr (STK) | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | Gamboa, Henry | Alectra Utilities | 13-Dec-19 |  |  | 610434.13 | 567334.39 | 610434.13 | 610434.13 | Koeppe, Jeffrey |  | 23-Mar-20 | 29-Dec-20 | 13-Jan-20 | 13-Feb-20 | 15-Apr-20 | Customer | Customer |  | 0
452123 | OT-2 #6 CU Replacement | 820 - Nebo | 150333 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 285885.52 | 285475.33 | 325869.23 | 285885.52 | Carr, Brad | B&M | 30-Oct-20 | 01-Jul-21 | 14-Sep-20 | 31-Aug-20 | 05-Oct-20 |  |  |  | -39,983.71
452126 | #6 Replacement - WL2 | 820 - Nebo | 150350 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 30-Mar-20 |  |  | 421184.59 | 252757.87 | 421184.59 | 421184.59 | Scott Borer |  | 22-Dec-20 | 02-Jul-21 | 05-Oct-20 | 19-Oct-20 | 11-Dec-20 | Locates |  |  | 0
452128 | 9 Main St, St. Catharines | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE | High | Indust | 2020 | Jakubowski, Mark | Alectra Utilities | 28-May-20 |  |  | 16160.3 | 9154.84 | 16160.3 | 16160.3 | Frank Giancola |  | 26-Jun-20 | 26-Jul-23 | 23-Jun-20 | 25-Aug-20 | 27-Aug-20 | Customer | Customer |  | 0
452134 | Rymal Rd Widening - City of Hamilton | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Jakubowski, Mark | Alectra Utilities | 05-Mar-20 |  |  | 122736.24 | 82229 | 122736.24 | 122736.24 | Carr, Brad | K-Line | 15-May-20 | 20-Jul-20 | 04-May-20 | 04-May-20 | 14-May-20 |  |  |  | 0
452138 | Vanier Tower 3 | 820 - Nebo | 151452 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 505857.15 | 437793.47 | 505857.15 | 505857.15 | Andrew Mehlenbacher | Fairway | 16-Nov-20 | 02-Jul-21 | 17-Aug-20 | 01-Oct-20 | 14-Dec-20 | Lines | Lines |  | 0
452141 | MH70A & SB23 - Roof Replacement | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Sep-19 |  |  | 254278.19 | 237661.58 | 61340.96 | 254278.19 | Andrew Mehlenbacher | Fairway | 31-Dec-19 | 20-Sep-21 | 25-Nov-19 | 15-Jan-20 | 01-Dec-20 | Lines | Lines |  | 192,937.23
452145 | Rogers Make Ready - South Service Rd | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 26-Jun-20 |  |  | 6830.84 | 4443.34 | 6830.84 | 6830.84 | Hewitson, Trevor |  | 31-Jul-20 | 18-Jul-22 | 20-Jul-20 | 13-Aug-20 | 13-Aug-20 | Filler | Filler |  | 0
452148 | 480 Melvin Ave | 820 - Nebo | 150456 | Inactive | 99 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 21-Nov-19 |  |  | 23588.04 | 28984.12 | 23588.04 | 23588.04 | Koeppe, Jeffrey | N/A | 10-Jan-20 | 22-Sep-22 | 06-Jan-20 | 03-Jan-20 | 31-Jan-20 |  | Customer |  | 0
452151 | 1870 Burlington St E | 820 - Nebo | 150449 | Active | 98 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 21-Jan-20 |  |  | 314731.22 | 259972.81 | 302543.59 | 314731.22 | Roy Owen | B&M | 05-Mar-20 | 26-Jul-23 | 18-Feb-20 | 19-Feb-20 | 14-Sep-20 | Contractor | Customer |  | 12,187.63
452153 | 106 King St W, Stoney Creek | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-May-19
452159 | 106 King St W, Stoney Creek | 820 - Nebo |  | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 04-Aug-20
452163 | 29 West Ave., Stoney Creek | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Jun-19
452166 | Westchester & 406, St. Catharines | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Dec-20
452167 | 427 Geneva St. (SCH) | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 01-Jun-20 |  |  | 91710.37 | 85857.73 | 91710.37 | 91710.37 | Frank Giancola |  | 05-Aug-20 | 11-Jan-21 | 27-Jul-20 | 01-Dec-20 | 04-Dec-20 | Customer | Customer |  | 0
452168 | St. Davids Rd Pole Relocations | 830 - St. Catharines | 150653 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas | B&M |  | 30-Nov-20
452173 | 125 Rykert St. (SCH) | 830 - St. Catharines | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 12-Feb-20 |  |  | 107611.3 | 126503.26 | 107611.3 | 107611.3 | Frank Giancola | Wiens | 25-Mar-20 | 25-Mar-21 | 16-Mar-20 | 05-Mar-20 | 26-Jun-20 |  | COVID19 |  | 0
452175 | 340 Welland Ave | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 09-Jul-20 |  |  | 99083.89 | 84776.5 | 99083.89 | 99083.89 | Frank Giancola | Wiens | 10-Sep-20 | 08-Mar-21 | 24-Aug-20 | 18-Sep-20 | 03-Nov-20 | Customer | Customer |  | 0
452181 | Nikola Tesla Blvd, Hamilton | 820 - Nebo | 150644 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Dec-20
631387 | 100 CHARLTON AVE W | 820 - Nebo | 150456 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 04-Sep-19 |  |  | 42157.97 | 29348.76 | 26955.66 | 42157.97 | Carr, Brad |  | 17-Oct-19 | 15-Jul-21 | 14-Oct-19 | 24-Feb-20 | 24-Feb-20 | Customer | Customer |  | 15,202.31
631455 | PARKDALE | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631459 | 170 CONCESSION ST | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631461 | 1318 UPPER WELLINGTON ST | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631462 | 150 JAMES ST.S | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 01-Feb-21
631463 | 539 BARTON ST.E | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631464 | 2 OTTAWA ST.N | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631465 | 1344 HIGHWAY 8 | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631467 | 95 ROCKCLIFFE | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631468 | 30 GOLFWOOD DR | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631469 | 4 PENLAKE CRT - HAMILTON | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 3099.93 |  | 0 | Dre Danieli |  |  | 08-Jul-19
631470 | 201 HIGHWAY 5 WEST - FLAMBOROUGH | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | McAlpine, Robert | Alectra Utilities |  |  |  | 0 | 2418.33 |  | 0 | Dre Danieli |  |  | 15-Jul-19
631686 | MOFFATT ST, ST. CATHARINES | 830 - St. Catharines | 150653 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 16-Mar-20 |  |  | 76003.14 | 83557.92 | 76003.14 | 76003.14 | Dan Despres |  | 20-May-20 | 18-Jul-22 | 11-May-20 | 10-Jun-20 | 04-Sep-20 | COVID19 | N/A |  | 0
632710 | LUSH CONDOS (RED HILL) | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | Gamboa, Henry | Alectra Utilities | 02-Dec-19 |  |  | 505473.03 | 463428.56 | 505473.03 | 505473.03 | Roy Owen | Transpw | 16-Mar-20 | 15-Jul-21 | 13-Jan-20 | 27-Jan-20 | 19-Jun-20 | Contractor | Contractor |  | 0
632757 | NEBO - 3RD FEEDER | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 02-Dec-19 |  | 5 | 299927.56 | 333533.03 | 291466.51 | 299927.56 | Carr, Brad | B&M | 31-Jan-20 | 03-Aug-21 | 06-Jan-20 | 02-Dec-19 | 14-Feb-20 |  | Materials |  | 8,461.05
633037 | 550 FENNELL AVE.E - POWER CENTER UPGRADE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 04-Nov-19 |  |  | 86674.1 | 102246.94 | 86674.1 | 86674.1 | Roy Owen | Fairway | 14-Feb-20 | 02-Feb-23 | 05-Dec-19 | 05-Dec-19 | 17-Nov-20 |  | Customer |  | 0
633175 | HYDRO POLE RELOCATION - GENEVA ST & GUY RD | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 16-Mar-20 |  |  | 5217.46 | 2256.09 | 5217.46 | 5217.46 | Frank Giancola | N/A | 17-Jun-20 | 03-Aug-21 | 17-Jun-20 | 17-Jun-20 | 17-Jun-20 |  |  |  | 0
633189 | BELL MAKE READY - RESERVOIR RD & FIFTY RD | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 20-Jan-20 |  |  | 6149.96 | 3779.59 | 6149.96 | 6149.96 | Hewitson, Trevor |  | 24-Feb-20 | 22-Mar-21 | 24-Feb-20 | 24-Feb-20 | 22-Jun-20 | Filler | Filler |  | 0
633192 | ROGERS MAKE READY - MOHAWK RD E | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 5802.32 | 4626.35 | 5802.32 | 5802.32 | Hewitson, Trevor |  | 31-Aug-20 | 22-Nov-21 | 03-Aug-20 | 06-Jul-20 | 06-Jul-20 |  |  |  | 0
633220 | 2020 SWITCH REPLACEMENT PROGRAM - HAMILTON | 820 - Nebo | 150337 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 13-Jan-20 |  | 4 | 387778.19 | 330505.27 | 377022.19 | 387778.19 | Carr, Brad | K-Line | 27-Nov-20 | 04-Oct-21 | 02-Nov-20 | 20-Nov-20 | 23-Dec-20 | Contractor | Control/SCADA |  | 10,756.00
633222 | 2020 SWITCH REPLACEMENT PROGRAM - ST. CATHARINES | 830 - St. Catharines | 150337 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 13-Jan-20 |  |  | 211562.02 | 32824.78 | 211562.02 | 211562.02 | Dan Despres |  | 30-Sep-20 | 03-Aug-21 | 24-Aug-20 | 03-Sep-20 | 04-Dec-20 | Materials | Control/SCADA |  | 0
633225 | CENTRAL CONVERSION (2020 WORK) | 820 - Nebo | 150352 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 02-Sep-19 |  |  | 1867480.45 | 2076870 | 1710879.17 | 1867480.45 | Carr, Brad | K-Line | 10-Jul-20 | 15-Sep-21 | 03-Feb-20 | 27-Jan-20 | 23-Dec-20 |  | COVID19 |  | 156,601.28
633235 | POLE REPLACEMENT 2020- PH1 POLES - FLamingo Ave | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 117469.69 | 89083.11 | 117469.69 | 117469.69 | Dan Despres |  | 26-Mar-20 | 08-Mar-21 | 24-Feb-20 | 10-Feb-20 | 20-Jul-20 |  | COVID19 |  | 0
633236 | POLE REPLACEMENT 2020 - PH2 POLES - Silverdale Dr | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 14-Jan-20 |  |  | 150096.89 | 85078.49 | 150096.89 | 150096.89 | Dan Despres |  | 11-Jun-20 | 08-Mar-21 | 27-Apr-20 | 10-Jun-20 | 20-Jul-20 | COVID19 | COVID19 |  | 0
633237 | POLE REPLACEMENT 2020- PH3 POLES - Decew Pole Line | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 09-Jan-20 |  |  | 192677.96 | 123779.54 | 192677.96 | 192677.96 | Dan Despres |  | 29-May-20 | 08-Mar-21 | 20-Apr-20 | 04-Aug-20 | 18-Sep-20 | COVID19 | COVID19 |  | 0
633238 | U/G PEDESTAL REPLACEMENT 2020 - PH1 | 830 - St. Catharines | 151064 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 134736.46 | 92334.65 | 134736.46 | 134736.46 | Frank Giancola |  | 10-Dec-20 | 08-Mar-21 | 19-Oct-20 | 13-Oct-20 | 05-Nov-20 |  |  |  | 0
633376 | 176 OAKDALE AVE | 820 - Nebo | 150449 | Active | 95 | COMPLETE | High | Res-ICI | 2020 | Frigotto, Rodrigo | Alectra Utilities | 15-Jun-20 |  |  | 57475.75 | 38014.62 | 57202.5 | 57475.75 | Frank Giancola |  | 15-Sep-20 | 26-Jul-23 | 08-Sep-20 | 08-Sep-20 | 16-Oct-20 |  | Customer |  | 273.25
633391 | ROGERS MAKE READY - CENTRAL CONVERSION PHASE 3 | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 10610.15 | 6118.04 | 10610.15 | 10610.15 | Hewitson, Trevor |  | 31-Dec-20 | 23-Mar-22 | 19-Oct-20 | 26-Oct-20 | 26-Oct-20 | Filler |  |  | 0
633563 | 439 VINE ST - POLE & SERVICE RELOCATION | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 04-May-20 |  |  | 20663.11 | 13791.73 | 20663.11 | 20663.11 | Dan Despres |  | 02-Jul-20 | 21-Dec-20 | 29-Jun-20 | 04-Jun-20 | 05-Jun-20 |  |  |  | 0
633588 | 65 ROCKCLIFFE RD - RELOCATE SERVICE FOR ADDITION | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 01-Feb-21
633675 | 64 CURRIE ST | 830 - St. Catharines | 150665 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 28-May-20 |  |  | 0 | 0 |  | 0 | Dre Danieli |  | 28-May-20 | 24-Aug-20 | 28-May-20
633809 | 189 RIVERVIEW BLVD - ARIAL TRESPASS | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 26891.13 | 31812.11 | 26891.13 | 26891.13 | Carr, Brad | Wiens | 28-Feb-20 | 08-Mar-21 | 10-Feb-20 | 27-May-20 | 27-May-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
633825 | CENTRAL, HOLMESDALE, LUCERNE, HAMILTON | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jul-20 |  |  | 9189.73 | 8133.62 | 9189.73 | 9189.73 | Hewitson, Trevor |  | 30-Oct-20 | 04-Nov-21 | 01-Oct-20 | 26-Oct-20 | 26-Oct-20 | Filler |  |  | 0
634058 | JOINT USE PERMIT HW2019-104 - SEAPARK DR, ST CATH | 830 - St. Catharines | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 5247.4 | 5288.14 | 5247.4 | 5247.4 | Hewitson, Trevor |  | 30-Sep-20 | 22-Sep-22 | 01-Sep-20 | 21-Aug-20 | 21-Aug-20 |  |  |  | 0
634161 | ROGERS BONDS - THIRD BATCH - DUNDURN, WHITNEY, AND GOVERNORS | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 24-Feb-20 |  |  | 3491.77 | 7860.46 | 3491.77 | 3491.77 | Hewitson, Trevor |  | 30-Apr-20 | 22-Sep-22 | 30-Mar-20 | 24-Feb-20 | 22-Apr-20 |  |  |  | 0
634162 | 686 PARKDALE AVE N, HAMILTON | 820 - Nebo | 150449 | Active | 95 | COMPLETE | Low | Comm | 2020 | Frigotto, Rodrigo | Alectra Utilities | 07-Jul-20 |  |  | 199198.32 | 242217.79 | 199198.32 | 199198.32 | Roy Owen | Fairway | 29-Sep-20 | 26-Jul-23 | 31-Aug-20 | 17-Aug-20 | 20-Oct-20 |  | Customer |  | 0
634164 | 200 GLENDALE AVE N, HAMILTON | 820 - Nebo | 150449 | Active | 95 | COMPLETE |  |  | 2020 | Frigotto, Rodrigo | Alectra Utilities | 08-Jun-20 |  |  | 227949.92 | 257723.13 | 227949.92 | 227949.92 | Roy Owen | Fairway | 31-Aug-20 | 26-Jul-23 | 03-Aug-20 | 05-Oct-20 | 23-Nov-20 | Customer | Customer |  | 0
634171 | BELL BONDS - Y06557, ST CATH | 830 - St. Catharines |  | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 11-Mar-20 |  |  | 5561.47 | 1702.94 | 5561.47 | 5561.47 | Hewitson, Trevor |  | 30-Apr-20 | 25-May-21 | 30-Mar-20 | 01-Jun-20 | 01-Jun-20 | COVID19 | COVID19 |  | 0
634173 | THE TOWNS AT RED HILL | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 25-May-20 |  |  | 227198.04 | 219228.24 | 227198.04 | 227198.04 | Koeppe, Jeffrey |  | 15-Jul-20 | 25-Jan-21 | 06-Jul-20 | 06-Jul-20 | 31-Jul-20 |  | COVID19 |  | 0
634174 | BELL BONDS - X62208, DUNDAS | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 24-Feb-20 |  |  | 3101.68 | 2186.87 | 3101.68 | 3101.68 | Hewitson, Trevor |  | 30-Apr-20 | 25-May-21 | 30-Mar-20 | 24-Feb-20 | 22-Apr-20 |  |  |  | 0
634191 | HAMILTON 2019 URGENT POLE REPLACEMENT - PHASE 2 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 15-Oct-19 |  |  | 137553.65 | 112215.36 | 137553.65 | 137553.65 | Scott Borer | B&M | 28-Feb-20 | 16-Sep-21 | 10-Feb-20 | 28-Jan-20 | 10-Aug-20 |  | Lines |  | 0
634208 | Joint Use Permit HW2019-128 Make-Ready , HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 30-Apr-20 |  |  | 8751.55 | 5328.37 | 8751.55 | 8751.55 | Hewitson, Trevor |  | 31-Jul-20 | 30-Mar-22 | 29-Jun-20 | 14-Aug-20 | 14-Aug-20 | Filler | Filler |  | 0
634309 | COGECO BONDS - 2019 DUNDAS | 820 - Nebo |  | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 2845.99 | 1233.81 | 2845.99 | 2845.99 | Hewitson, Trevor |  | 30-Sep-20 | 08-Mar-21 | 01-Sep-20 | 28-Oct-20 | 28-Oct-20 | Filler | Filler |  | 0
634322 | COGECO BONDS - 2019 WEST HAMILTON | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 1981.11 | 2343.56 | 1981.11 | 1981.11 | Hewitson, Trevor |  | 30-Sep-20 | 21-Dec-20 | 01-Sep-20 | 21-Aug-20 | 21-Aug-20 |  |  |  | 0
634323 | COGECO BONDS - 2019 EAST HAM 1 | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 1412.89 | 1645.13 | 1412.89 | 1412.89 | Hewitson, Trevor |  | 30-Sep-20 | 25-Feb-21 | 01-Sep-20 | 26-Oct-20 | 26-Oct-20 | Filler | Filler |  | 0
634325 | COGECO BONDS - 2019 EAST HAM 2 | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 1412.89 | 1628.37 | 1412.89 | 1412.89 | Hewitson, Trevor |  | 30-Sep-20 | 25-Feb-21 | 01-Sep-20 | 26-Oct-20 | 26-Oct-20 | Filler | Filler |  | 0
634326 | COGECO BONDS - 2019 EAST HAM 3 | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 1412.89 | 3129.15 | 1412.89 | 1412.89 | Hewitson, Trevor |  | 30-Sep-20 | 29-Dec-21 | 01-Sep-20 | 09-Nov-20 | 09-Nov-20 | Filler | Filler |  | 0
634327 | COGECO BONDS - 2019 EAST HAM 4 | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 1412.89 | 1651.34 | 1412.89 | 1412.89 | Hewitson, Trevor |  | 30-Sep-20 | 25-Feb-21 | 01-Sep-20 | 26-Oct-20 | 26-Oct-20 | Filler | Filler |  | 0
634409 | 629 BARTON STREET EAST | 820 - Nebo | 150456 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 15-Nov-19 |  |  | 16091.2 | 8583.54 | 16091.2 | 16091.2 | Koeppe, Jeffrey |  | 19-Dec-19 | 15-Jul-21 | 16-Dec-19 | 06-Jan-20 | 06-Jan-20 | Locates | Locates |  | 0
634423 | CARDINAL HEIGHTS | 820 - Nebo | 150588 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 30-Jul-20 |  |  | 228162.94 | 217296.8 | 228162.94 | 228162.94 | Carr, Brad |  | 25-Sep-20 | 08-Mar-21 | 17-Aug-20 | 26-Oct-20 | 04-Nov-20 | Customer | Customer |  | 0
634448 | WILLOW LANE (SCH) - RELOCATE POLES IN SDWK CONFLICT | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | Gamboa, Henry | Alectra Utilities | 10-Jun-20 |  |  | 27309.26 | 25701.51 | 27309.26 | 27309.26 | Koeppe, Jeffrey |  | 20-Jul-20 | 16-Feb-21 | 13-Jul-20 | 07-Jul-20 | 20-Jul-20 |  |  |  | 0
634478 | 438 NEBO RD | 820 - Nebo | 150449 | Active | 98 | COMPLETE | VerHigh | Comm | 2020 | Kappheim, Adam | Alectra Utilities | 20-May-20 |  |  | 46702.53 | 60269.8 | 46702.53 | 46702.53 | Roy Owen |  | 26-Jun-20 | 26-Jul-23 | 22-Jun-20 | 31-Oct-20 | 02-Nov-20 | Customer | Customer |  | 0
634493 | HAMILTON 2020 POLE RESIDUALS PHASE 1 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 181226.01 | 172162.23 | 185428.92 | 181226.01 | Carr, Brad | B&M | 04-Sep-20 | 16-Sep-21 | 03-Aug-20 | 03-Aug-20 | 03-Nov-20 |  | Filler |  | -4,202.91
634495 | HAMILTON PCB TX'S OVERHEAD | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 72807.33 | 57269.53 | 72807.33 | 72807.33 | Koeppe, Jeffrey |  | 27-Nov-20 | 05-Oct-21 | 21-Sep-20 | 09-Oct-20 | 07-Dec-20 | Filler | Filler |  | 0
634497 | ST. CATHARINES PCB TX REPLACEMENT 2020 | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 25051.32 | 23459.36 | 25051.32 | 25051.32 | Dan Despres |  | 24-Feb-20 | 16-Feb-21 | 18-Feb-20 | 24-Feb-20 | 04-Mar-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
634531 | ROGERS MAKE READY - PARKSIDE DR - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 20-Jan-20 |  |  | 4577.33 | 3566.59 | 4577.33 | 4577.33 | Hewitson, Trevor |  | 28-Feb-20 | 29-Nov-21 | 28-Feb-20 | 24-Feb-20 | 03-May-20 | Filler | Filler |  | 0
634570 | HAMILTON 2020 POLE RESIDUALS PHASE 2 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 134760.83 | 117673.18 | 134760.83 | 134760.83 | Koeppe, Jeffrey |  | 31-Jul-20 | 16-Sep-21 | 02-Mar-20 | 21-Feb-20 | 17-Nov-20 |  | COVID19 |  | 0
634641 | CARDINAL HEIGHTS - POLE/PRIM REMOVALS & RE-LOCATIONS | 820 - Nebo | 151653 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 26-Aug-20 |  |  | 82800.66 | 62292.33 | 82800.66 | 82800.66 | Brad Carr | K-Line | 07-Oct-20 | 22-Mar-22 | 28-Sep-20 | 23-Nov-20 | 04-Dec-20 | Contractor | Contractor |  | 0
634664 | HAMILTON 2020 POLE RESIDUALS PHASE 3 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 16-Dec-19 |  |  | 145451 | 133056.76 | 158199.72 | 145451 | Carr, Brad | B&M | 11-Sep-20 | 16-Sep-21 | 17-Aug-20 | 02-Nov-20 | 17-Dec-20 | Contractor | Contractor |  | -12,748.72
634717 | JOINT USE PERMIT HW2019-109 - MAIN ST W, HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 04-May-20 |  |  | 4654.81 | 5058.04 | 4654.81 | 4654.81 | Hewitson, Trevor |  | 30-Sep-20 | 22-Mar-21 | 01-Sep-20 | 21-Aug-20 | 21-Aug-20 |  |  |  | 0
634758 | HAMILTON 2020 POLE RESIDUALS PHASE 4 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Dec-19 |  |  | 241792.56 | 213565.34 | 238095.82 | 241792.56 | Carr, Brad | B&M | 09-Oct-20 | 16-Sep-21 | 31-Aug-20 | 02-Nov-20 | 23-Dec-20 | Contractor | Contractor |  | 3,696.74
634826 | HAMILTON 2020 POLE RESIDUALS PHASE 5 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 06-Jul-20 |  |  | 175423.31 | 110231.09 | 164714.66 | 175423.31 | Carr, Brad | K-Line | 31-Jul-20 | 16-Sep-21 | 13-Jul-20 | 06-Jul-20 | 06-Aug-20 |  | Contractor |  | 10,708.65
634906 | ROAD RECONSTRUCTION - ST.DAVIDS RD | 830 - St. Catharines | 150653 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Jakubowski, Mark | Alectra Utilities | 11-May-20 |  |  | 563046 | 604052.41 | 457421.51 | 563046 | Carr, Brad | B&M | 07-Aug-20 | 15-Apr-21 | 08-Jun-20 | 08-Jun-20 | 10-Sep-20 |  | Contractor |  | 105,624.49
634916 | 156 5TH CONCESSION ROAD | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Kappheim, Adam | Alectra Utilities | 20-May-20 |  |  | 67073.64 | 68906.53 | 67073.64 | 67073.64 | Roy Owen | Fairway | 06-Jul-20 | 08-Mar-23 | 29-Jun-20 | 07-Sep-20 | 25-Sep-20 | Customer | Customer |  | 0
634970 | 391 VICTORIA AVENUE NORTH | 820 - Nebo | 150449 | Active | 98 | COMPLETE | High | Comm | 2020 | Kappheim, Adam | Alectra Utilities | 29-Jun-20 |  |  | 53751.43 | 46285.59 | 53751.43 | 53751.43 | Koeppe, Jeffrey | Fairway | 13-Aug-20 | 26-Jul-23 | 04-Aug-20 | 24-Aug-20 | 25-Sep-20 | Customer | Customer |  | 0
634975 | JOINT USE PERMIT HW2019-142 - MOUNTVILLE, INVERNESS E, E14, ETC - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 06-Jul-20 |  |  | 4779.64 | 7279.61 | 4779.64 | 4779.64 | Hewitson, Trevor |  | 30-Nov-20 | 29-Dec-21 | 02-Nov-20 | 02-Nov-20 | 02-Nov-20 |  |  |  | 0
634998 | JOINT USE PERMIT HW2019-145 - ARVIN AVE - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-May-20 |  |  | 11545.33 | 11119.13 | 11545.33 | 11545.33 | Hewitson, Trevor |  | 18-Dec-20 | 04-Oct-21 | 12-Oct-20 | 26-Oct-20 | 26-Oct-20 | Filler |  |  | 0
635029 | HUMMINGBIRD LANE DEVELOPMENT EXPANSION | 820 - Nebo | 152381 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | Jakubowski, Mark | Alectra Utilities | 10-Aug-20 |  |  | 327389.81 | 263240.19 | 327389.81 | 327389.81 | Carr, Brad | B&M | 16-Oct-20 | 22-Dec-20 | 07-Sep-20 | 07-Sep-20 | 03-Nov-20 |  |  |  | 0
635068 | 350 SCOTT ST PHASE 2 | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 86868.63 | 96860.27 | 86868.63 | 86868.63 | Dan Despres |  | 02-Oct-20 | 16-Sep-21 | 21-Sep-20 | 21-Sep-20 | 26-Oct-20 |  | Customer |  | 0
635184 | HAMILTON 2020 POLE RESIDUALS PHASE 7 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 26-Mar-20 |  |  | 378431.8 | 322233.14 | 394706.89 | 378431.8 | Carr, Brad | B&M | 30-Oct-20 | 16-Sep-21 | 14-Sep-20 | 12-Oct-20 | 23-Dec-20 | Contractor | Contractor |  | -16,275.09
635185 | HAMILTON 2020 POLE RESIDUALS PHASE 8 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 03-Aug-20 |  |  | 226029.38 | 221633.27 | 223670.49 | 226029.38 | Carr, Brad | B&M | 30-Nov-20 | 20-Sep-21 | 02-Nov-20 | 07-Sep-20 | 20-Nov-20 |  |  |  | 2,358.89
635377 | JOINT USE PERMIT HW2019-150 - SIMPSON RD - ST CATH | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 06-Jul-20 |  |  | 5633.97 | 4788.34 | 5633.97 | 5633.97 | Hewitson, Trevor |  | 30-Nov-20 | 11-Mar-21 | 02-Nov-20 | 11-Dec-20 | 11-Dec-20 | Filler | Filler |  | 0
635414 | SCH 2020 Bell Transfers | 830 - St. Catharines | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 28-Jan-20 |  |  | 28502.99 | 12812.81 | 28502.99 | 28502.99 | Frank Giancola | N/A | 12-Feb-20 | 20-Sep-21 | 08-Feb-20 | 22-Feb-20 | 23-Feb-20 | Customer | Customer |  | 0
635415 | HAMILTON 2020 URGENT POLE REPLACEMENTS | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 20-Jul-20 |  |  | 31143.65 | 58801.85 | 31143.65 | 31143.65 | Carr, Brad | K-Line | 31-Jul-20 | 20-Sep-21 | 21-Jul-20 | 20-Jul-20 | 31-Aug-20 |  | Contractor |  | 0
635429 | HAMILTON 2020 POLE RESIDUALS PHASE 9 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 28-Feb-20 |  |  | 145128.13 | 84406.63 | 143148.13 | 145128.13 | Carr, Brad | K-Line | 13-Nov-20 | 20-Sep-21 | 26-Oct-20 | 27-Jul-20 | 28-Aug-20 |  |  |  | 1,980.00
635453 | HAMILTON WATERFRONT TRUST TX RELOCATE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | High | Comm | 2020 | Kappheim, Adam | Alectra Utilities | 02-Mar-20 |  |  | 33950.57 | 25355.93 | 33950.57 | 33950.57 | Roy Owen |  | 07-Apr-20 | 08-Mar-22 | 30-Mar-20 | 27-Apr-20 | 03-Jun-20 | COVID19 | Customer |  | 0
635533 | HAMILTON 2020 POLE REDISDUALS PHASE 10 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 20-Jul-20 |  |  | 152539.75 | 91910.41 | 143093.75 | 152539.75 | Carr, Brad | K-Line | 16-Oct-20 | 20-Sep-21 | 28-Sep-20 | 07-Sep-20 | 23-Oct-20 |  | Contractor |  | 9,446.00
635544 | HAMILTON 2020 POLE RESIDUALS PHASE 11 | 820 - Nebo | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 28-Feb-20 |  |  | 220204.43 | 141881.29 | 218782.43 | 220204.43 | Carr, Brad | K-Line | 18-Sep-20 | 20-Sep-21 | 17-Aug-20 | 17-Aug-20 | 21-Sep-20 |  | Filler |  | 1,422.00
635616 | 205 NEBO ROAD | 820 - Nebo | 150449 | Active | 98 | COMPLETE | Medium | Comm | 2020 | Kappheim, Adam | Alectra Utilities | 15-May-20 |  |  | 66273.79 | 56779.18 | 66273.79 | 66273.79 | Roy Owen | Fairway | 21-Jul-20 | 26-Jul-23 | 13-Jul-20 | 21-Sep-20 | 03-Dec-20 | Customer | Customer |  | 0
635634 | TRENERGY INC. - OVERSIZE LOAD MOVE, ST. CATHARINES | 830 - St. Catharines | 150665 | Inactive | 99 | COMPLETE | High | Health | 2020 | Jakubowski, Mark | Alectra Utilities | 27-Apr-20 |  |  | 40230.35 | 29366.47 | 40230.35 | 40230.35 | Dan Despres |  | 25-May-20 | 03-Dec-20 | 18-May-20 | 23-May-20 | 24-May-20 | Customer |  |  | 0
635693 | 170 OGILVIE ST )ST.JOSEPHS VILLA) | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE | High | ICM | 2020 | Kappheim, Adam | Alectra Utilities | 03-Mar-20 |  |  | 77469.68 | 99990.76 | 77469.68 | 77469.68 | Roy Owen |  | 17-Apr-20 | 07-Mar-23 | 16-Mar-20 | 23-Mar-20 | 03-Apr-20 |  | Customer |  | 0
635714 | PEN CENTER - P10248 TX REPLACEMENT | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 03-Feb-20 |  |  | 27854.78 | 21617.8 | 27854.78 | 27854.78 | Brian Robinson |  | 12-Feb-20 | 08-Mar-21 | 08-Feb-20 | 08-Feb-20 | 09-Feb-20 |  |  |  | 0
635722 | 695 WOODWARD AVE N UPGRADE & 741 WOODWARD AVE N CONVERSION | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 18-Feb-20 |  |  | 91401.83 | 75084.46 | 91401.83 | 91401.83 | Koeppe, Jeffrey |  | 17-Apr-20 | 22-Sep-22 | 23-Mar-20 | 16-Mar-20 | 09-Jul-20 |  | COVID19 |  | 0
635726 | JOINT USE PERMIT HW2020-010 - QUIGLEY RD - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 30-Apr-20 |  |  | 4284.59 | 3337.95 | 4284.59 | 4284.59 | Hewitson, Trevor |  | 28-Aug-20 | 15-Nov-21 | 03-Aug-20 | 13-Aug-20 | 13-Aug-20 | Filler |  |  | 0
635743 | HAMILTON KICKER TX REPLACEMENT - TX 10117 | 820 - Nebo | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 28-Feb-20 |  |  | 3574.01 | 456.97 | 3574.01 | 3574.01 | Scott Borer |  | 01-Dec-20 | 20-Sep-21 | 01-Dec-20 | 01-Dec-20 | 01-Dec-20 | Lines | Lines |  | 0
635745 | HAMILTON KICKER TX REPLACEMENT - TX 7544 AND 2923 | 820 - Nebo | 150497 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 04-Nov-20 |  |  | 222046.19 | 177524.49 | 208264.43 | 222046.19 | Carr, Brad | B&M | 18-Dec-20 | 20-Sep-21 | 01-Dec-20 | 20-Nov-20 | 17-Dec-20 |  |  |  | 13,781.76
635757 | SC1474 - HEYWOOD GS | 830 - St. Catharines | 150334 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 12-Aug-20 |  |  | 127551.86 | 175554.49 | 127551.86 | 127551.86 | Frank Giancola | Wiens | 05-Oct-20 | 14-Feb-22 | 28-Sep-20 | 16-Oct-20 | 05-Nov-20 | Customer | Customer |  | 0
635758 | 2D13X - WATERDOWN AUTO SWITCH | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 12-Aug-20 |  | 1 | 419034.93 | 442565.57 | 384361.39 | 419034.93 | Carr, Brad | B&M | 27-Nov-20 | 15-Feb-22 | 19-Oct-20 | 03-Sep-20 | 03-Nov-20 |  |  |  | 34,673.54
635817 | BELL BONDS - X79674 AND Y41957 - ST CATH | 830 - St. Catharines | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 30-Apr-20 |  |  | 2428.84 | 774.88 | 2428.84 | 2428.84 | Hewitson, Trevor |  | 31-Jul-20 | 28-Jun-21 | 29-Jun-20 | 10-Jun-20 | 10-Jun-20 |  |  |  | 0
635827 | COGECO BONDS - 2020 FLAMBOROUGH | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 3614.82 | 2169.15 | 3614.82 | 3614.82 | Hewitson, Trevor |  | 31-Dec-20 | 25-Feb-21 | 19-Oct-20 | 12-Nov-20 | 12-Nov-20 | Filler |  |  | 0
635828 | COGECO BONDS - 2020 DUNDAS | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 10-Jun-20 |  |  | 2071.25 | 1239.89 | 2071.25 | 2071.25 | Hewitson, Trevor | N/A | 28-Aug-20 | 03-Dec-20 | 04-Aug-20 | 24-Jun-20 | 24-Jun-20 |  |  |  | 0
635829 | COGECO BONDS - 2020 AINSLIE WOOD NORTH - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 10-Jun-20 |  |  | 3614.82 | 3178.5 | 3614.82 | 3614.82 | Hewitson, Trevor | N/A | 28-Aug-20 | 25-Feb-21 | 04-Aug-20 | 09-Nov-20 | 09-Nov-20 | Filler | Filler |  | 0
635830 | COGECO BONDS - 2020 WESTDALE - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 10-Jun-20 |  |  | 2071.25 | 1799.85 | 2071.25 | 2071.25 | Hewitson, Trevor | N/A | 28-Aug-20 | 25-Feb-21 | 04-Aug-20 | 26-Oct-20 | 26-Oct-20 | Filler | Filler |  | 0
635831 | COGECO BONDS - 2020 KIRKENDALL NORTH - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Apr-20 |  |  | 2843.03 | 1928.05 | 2843.03 | 2843.03 | Hewitson, Trevor |  | 31-Dec-20 | 25-Feb-21 | 19-Oct-20 | 26-Oct-20 | 26-Oct-20 | Filler |  |  | 0
635832 | COGECO BONDS - 2020 HAMILTON EAST - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 10-Jun-20 |  |  | 3614.82 | 3986.32 | 3614.82 | 3614.82 | Hewitson, Trevor | N/A | 28-Aug-20 | 27-Jan-22 | 04-Aug-20 | 29-Dec-20 | 29-Dec-20 | Filler | Filler |  | 0
635833 | COGECO BONDS - 2020 GLENVIEW AND WINONA - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 10-Jun-20 |  |  | 2071.25 | 1535.8 | 2071.25 | 2071.25 | Hewitson, Trevor | N/A | 28-Aug-20 | 03-Dec-20 | 04-Aug-20 | 24-Jun-20 | 24-Jun-20 |  |  |  | 0
635942 | CENTRAL CONVERSION - PHASE 4 - 2021 WORK (FORMERLY S699225C DWG) | 820 - Nebo | 150352 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 24-Jul-20 |  |  | 1279307.64 | 1079305.66 | 1171457.64 | 1279307.64 | Carr, Brad | K-Line | 04-Dec-20 | 20-Sep-21 | 31-Aug-20 | 10-Aug-20 | 10-Nov-20 |  |  |  | 107,850.00
635968 | JOINT USE PERMIT HW2020-021 - ALBRIGHT - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 6308.91 | 3551.17 | 6308.91 | 6308.91 | Hewitson, Trevor |  | 30-Sep-20 | 15-Nov-21 | 01-Sep-20 | 21-Aug-20 | 21-Aug-20 |  |  |  | 0
636018 | ALTMAR COURT - CABLE REPLACEMENT | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 21-Aug-20 |  |  | 73878.23 | 58293.16 | 73878.23 | 73878.23 | Frank Giancola | Wiens | 06-Oct-20 | 08-Mar-21 | 28-Sep-20 | 14-Sep-20 | 01-Oct-20 |  |  |  | 0
636021 | 376 READ RD | 830 - St. Catharines | 150455 | Active | 98 | COMPLETE | Low | Comm | 2020 | Paesano, Andrew | Alectra Utilities | 04-May-20 |  |  | 61084.8 | 46202.08 | 61084.8 | 61084.8 | Frank Giancola | Wiens | 22-Jun-20 | 26-Jul-23 | 15-Jun-20 | 30-Jul-20 | 07-Aug-20 | Customer | Customer |  | 0
636056 | JOINT USE PERMIT HW2020-022 - SCOTT ST W - ST CATH | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 7178.34 | 3898.28 | 7178.34 | 7178.34 | Hewitson, Trevor |  | 30-Sep-20 | 25-Nov-21 | 01-Sep-20 | 20-Aug-20 | 20-Aug-20 |  |  |  | 0
636060 | MH 109C - ROOF REPLACEMENT | 820 - Nebo | 151065 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 26-Oct-20 |  |  | 99305.65 | 129297.39 | 99305.65 | 99305.65 | Andrew Mehlenbacher | Fairway | 13-Nov-20 | 04-Oct-21 | 02-Nov-20 | 02-Nov-20 | 04-Dec-20 |  | Lines |  | 0
636090 | MOUNTAIN BROW ROAD - 3- PH OVERHEAD WORK | 820 - Nebo | 150390 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 15-Jul-20 |  |  | 140565.35 | 117078.73 | 140565.35 | 140565.35 | Carr, Brad | K-Line | 09-Oct-20 | 22-Dec-20 | 28-Sep-20 | 31-Aug-20 | 05-Oct-20 |  |  |  | 0
636145 | 21 UPPER CENTENNIAL PKWY - BLDG B (GAS BAR) | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Paesano, Andrew | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  | 04-Jun-20 | 07-Mar-22 | 04-Jun-20 | 04-Jun-20 | 04-Jun-20
636150 | JOINT USE PERMIT HW2020-023 - RANDALL, SECOND N, AND BRANDOW - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 6395.3 | 5057.06 | 6395.3 | 6395.3 | Hewitson, Trevor |  | 30-Nov-20 | 25-Nov-21 | 02-Nov-20 | 21-Dec-20 | 21-Dec-20 | Filler | Filler |  | 0
636157 | 1290 ARVIN AVE - NEW SERVICE | 820 - Nebo | 150449 | Active | 98 | COMPLETE | Low | Comm | 2020 | Frigotto, Rodrigo | Alectra Utilities | 18-Sep-20 |  |  | 98549.57 | 95757.05 | 98549.57 | 98549.57 | Roy Owen |  | 11-Nov-20 | 26-Jul-23 | 02-Nov-20 | 02-Nov-20 | 30-Dec-20 |  | Customer |  | 0
636196 | JOINT USE PERMIT HW2020-026 - DELAWANA AND JEROME - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 6867.34 | 4565.09 | 6867.34 | 6867.34 | Hewitson, Trevor |  | 30-Oct-20 | 04-Nov-21 | 01-Oct-20 | 02-Nov-20 | 02-Nov-20 | Filler | Filler |  | 0
636248 | JOINT USE PERMIT HW2020-032 - UPPER WENTWORTH - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-May-20 |  |  | 5131.22 | 4462.3 | 5131.22 | 5131.22 | Hewitson, Trevor |  | 31-Dec-20 | 11-Mar-21 | 19-Oct-20 | 02-Nov-20 | 02-Nov-20 | Filler |  |  | 0
636277 | NEWTON M8 - 282X: RECONFIGURATION/FUSE CHANGES | 820 - Nebo | 151452 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 05-Jun-20 |  |  | 25303.01 | 17130.44 | 25303.01 | 25303.01 | Scott Borer |  | 20-Jul-20 | 12-Jul-21 | 13-Jul-20 | 14-Sep-20 | 23-Dec-20 | Filler | Filler |  | 0
636388 | KING & BAY EXPANSION - MCMASTER TOWER | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED |  |  | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault | B&M |  | 11-Dec-20
636440 | 514 QUEENSTON ST - LEAKING TX. REPLACEMENT | 830 - St. Catharines | 150335 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 18-Sep-20 |  |  | 48821.59 | 35723.65 | 48821.59 | 48821.59 | Dan Despres |  | 19-Nov-20 | 08-Mar-21 | 09-Nov-20 | 21-Oct-20 | 19-Nov-20 |  |  |  | 0
636460 | EA-8 FEEDER EXTENSION (UPPER KENILWORTH) HAMILTON | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 25-Aug-20 |  |  | 447205.97 | 564965.63 | 373041.88 | 447205.97 | Carr, Brad | K-Line | 27-Nov-20 | 05-Jul-21 | 28-Sep-20 | 20-Nov-20 | 23-Dec-20 | Contractor | Control/SCADA |  | 74,164.09
636493 | JOINT USE PERMIT HW2020-033 - LONGWOOD RD S - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 04-May-20 |  |  | 7110.16 | 5469.34 | 7110.16 | 7110.16 | Hewitson, Trevor |  | 28-Aug-20 | 04-Nov-21 | 03-Aug-20 | 12-Aug-20 | 12-Aug-20 | Filler |  |  | 0
636562 | JOINT USE PERMIT HW2020-038 - SEAMAN, DEWITT, AND MILLEN - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 13329.16 | 9543.09 | 13329.16 | 13329.16 | Hewitson, Trevor |  | 31-Dec-20 | 04-Oct-21 | 19-Oct-20 | 26-Oct-20 | 26-Oct-20 | Filler |  |  | 0
636590 | JOINT USE PERMIT HW2020-040 - WENTWORTH ESCARPMENT - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 7600.31 | 6684.07 | 7600.31 | 7600.31 | Hewitson, Trevor |  | 31-Dec-20 | 02-Jun-21 | 19-Oct-20 | 02-Nov-20 | 02-Nov-20 | Filler |  |  | 0
636595 | JOINT USE PERMIT HW2020-035 - YORK AND HOPKINS - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jul-20 |  |  | 9900.69 | 8737.68 | 9900.69 | 9900.69 | Hewitson, Trevor |  | 30-Nov-20 | 04-Oct-21 | 02-Nov-20 | 12-Nov-20 | 12-Nov-20 | Filler |  |  | 0
636598 | ANCHOR RELOCATE - 32 TRILLIUM AVE | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 16-Sep-20 |  |  | 19763.46 | 13864.65 | 19763.46 | 19763.46 | Koeppe, Jeffrey |  | 29-Oct-20 | 08-Mar-21 | 26-Oct-20 | 02-Nov-20 | 13-Nov-20 | MC/PUCC Permit |  |  | 0
636710 | JOINT USE PERMIT HW2020-042 - ROYAL AVE - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 6345.8 | 4719.96 | 6345.8 | 6345.8 | Hewitson, Trevor |  | 31-Dec-20 | 08-Mar-21 | 19-Oct-20 | 26-Oct-20 | 26-Oct-20 | Filler |  |  | 0
636774 | 67 DUNCOMBE DR | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault
636838 | JOINT USE PERMIT HW2020-048 - BELL AND MONTEREY - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-May-20 |  |  | 5585.32 | 4097.34 | 5585.32 | 5585.32 | Hewitson, Trevor |  | 30-Nov-20 | 11-Nov-21 | 02-Nov-20 | 26-Oct-20 | 26-Oct-20 |  |  |  | 0
636886 | JOINT USE PERMIT HW2020-057 - BEACH AND BEATTY - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jul-20 |  |  | 6087.6 | 5659.77 | 6087.6 | 6087.6 | Hewitson, Trevor |  | 30-Nov-20 | 12-Nov-21 | 02-Nov-20 | 26-Oct-20 | 26-Oct-20 |  |  |  | 0
636920 | 22 PATRICK STREET - OH SERVICE COMPAINT | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Sep-20 |  |  | 1776.19 | 12648.61 | 1776.19 | 1776.19 | Carr, Brad | K-Line | 10-Sep-20 | 22-Mar-21 | 10-Sep-20 | 10-Sep-20 | 10-Sep-20 |  |  |  | 0
636995 | 105 HIGH ST - PAVILLON DE LA JEUNESSE SCHOOL UPGRADE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 13-Aug-20 |  |  | 63385.12 | 50765.5 | 63385.12 | 63385.12 | Koeppe, Jeffrey | Fairway | 22-Sep-20 | 01-Dec-21 | 14-Sep-20 | 07-Sep-20 | 21-Sep-20 |  |  |  | 0
637043 | 8 AYLETT - ANCHOR RELOCATION | 820 - Nebo | 150828 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 18-Jun-20 |  |  | 15458.52 | 4060.98 | 15458.52 | 15458.52 | Carr, Brad | K-Line | 21-May-20 | 16-Feb-21 | 21-May-20 | 21-May-20 | 21-May-20 |  |  |  | 0
637146 | JOINT USE PERMIT HW2019-092 - SEAMAN - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 04-May-20 |  |  | 5296.8 | 1178.83 | 5296.8 | 5296.8 | Hewitson, Trevor |  | 30-Nov-20 | 25-Oct-21 | 02-Nov-20 | 26-Oct-20 | 26-Oct-20 |  |  |  | 0
637164 | ROGERS BONDS - 2020 BATCH 1 - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 10-Jun-20 |  |  | 3614.82 | 2499.51 | 3614.82 | 3614.82 | Hewitson, Trevor | N/A | 31-Jul-20 | 22-Mar-21 | 02-Jul-20 | 09-Nov-20 | 09-Nov-20 | Filler | Filler |  | 0
637264 | JOINT USE PERMIT HW2020-070 - TEAL AND SOUTH SERVICE - HAM | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 7110.91 | 3482.39 | 7110.91 | 7110.91 | Hewitson, Trevor |  | 30-Sep-20 | 12-Nov-21 | 01-Sep-20 | 17-Aug-20 | 17-Aug-20 | Filler |  |  | 0
637347 | JOINT USE PERMIT HW2020-078 - BUNTING AND DIEPPE - ST CATH | 830 - St. Catharines | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 15-Jun-20 |  |  | 9333.16 | 5323.25 | 9333.16 | 9333.16 | Hewitson, Trevor |  | 30-Sep-20 | 11-Nov-21 | 01-Sep-20 | 27-Aug-20 | 27-Aug-20 |  |  |  | 0
637355 | 2020 - OH AUTO SWITCH INSTALLS | 820 - Nebo | 150334 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 27-Aug-20 |  | 2 | 116952.2 | 116080.82 | 116952.2 | 116952.2 | Carr, Brad | K-Line | 30-Oct-20 | 03-Aug-21 | 26-Oct-20 | 02-Nov-20 | 23-Dec-20 | Contractor | Control/SCADA |  | 0
637362 | 38 WEST AVE S - UPGRADE | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 02-Jul-20 |  |  | 37881.06 | 28358.34 | 37881.06 | 37881.06 | Koeppe, Jeffrey |  | 07-Aug-20 | 15-Jul-21 | 04-Aug-20 | 13-Aug-20 | 14-Aug-20 | Customer | Customer |  | 0
637474 | POLE REPLACEMENT - EAST 25TH & FENNEL AVE E | 820 - Nebo | 150644 | Inactive | 99 | COMPLETE | Medium | Infrast | 2020 | Jakubowski, Mark | Alectra Utilities | 16-Sep-20 |  |  | 53730.16 | 51921.92 | 52269.16 | 53730.16 | Carr, Brad | K-Line | 23-Oct-20 | 22-Dec-20 | 19-Oct-20 | 13-Oct-20 | 15-Oct-20 |  |  |  | 1,461.00
637489 | 250 BUNTING ROAD - TX AND CABLE REPLACEMENT | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 08-Jul-20 |  |  | 113728.86 | 115940.01 | 113728.86 | 113728.86 | Frank Giancola | Wiens | 11-Aug-20 | 04-Oct-21 | 20-Jul-20 | 20-Jul-20 | 27-Jul-20 |  |  |  | 0
637551 | QUEEN ST - KING TO MAKET PRIMARY REMOVAL | 820 - Nebo | 150665 | Inactive | 99 | CANCELLED | Medium | Comm | 2020 | Jakubowski, Mark | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 11-Dec-20
637558 | 174 AND 190 NAPIER ST, HAM - DRILLING POLES 14698 AND 37611 | 820 - Nebo | 151536 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 1197.24 | 1010.4 | 1197.24 | 1197.24 | Hewitson, Trevor |  | 30-Nov-20 | 25-Feb-21 | 02-Nov-20 | 02-Nov-20 | 02-Nov-20 |  |  |  | 0
637570 | 202 CANADA ST - AERIAL TRESPASS | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 27-Jul-20 |  |  | 16083.95 | 16925.46 | 16083.95 | 16083.95 | Koeppe, Jeffrey |  | 03-Sep-20 | 22-Jan-21 | 31-Aug-20 | 06-Oct-20 | 06-Oct-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
637581 | LANG & REID / HAM / SR | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 20-Jul-20 |  |  | 27556.64 | 12872.83 | 27556.64 | 27556.64 | Roy Owen |  | 28-Aug-20 | 17-Jan-22 | 17-Aug-20 | 28-Jul-20 | 18-Sep-20 |  | Lines |  | 0
637590 | 80 GRANTHAM TX REPLACEMENT | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Sep-20 |  |  | 61921.16 | 62887.07 | 61921.16 | 61921.16 | Dan Despres | Wiens | 27-Oct-20 | 20-Oct-21 | 19-Oct-20 | 07-Oct-20 | 07-Dec-20 | MC/PUCC Permit | Customer |  | 0
637591 | 16 KEEFER ROAD - TX REPLACEMENT | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Sep-20 |  |  | 69143.08 | 46153.54 | 69143.08 | 69143.08 | Dan Despres | Wiens | 05-Nov-20 | 04-Oct-21 | 28-Oct-20 | 21-Oct-20 | 30-Nov-20 |  | Contractor |  | 0
637602 | 44 ROCHELLE DR AND 12 VILLAGE GATE PEDESTAL RELOCATE | 830 - St. Catharines | 150496 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 24-Aug-20 |  |  | 39878.5 | 23910.4 | 39878.5 | 39878.5 | Dan Despres |  | 13-Nov-20 | 08-Mar-21 | 09-Nov-20 | 19-Oct-20 | 19-Oct-20 |  |  |  | 0
637603 | 21 KEEFER ROAD - TX REPLACEMENT | 830 - St. Catharines | 150336 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Sep-20 |  |  | 73299.21 | 59452.66 | 73299.21 | 73299.21 | Dan Despres | Wiens | 17-Nov-20 | 04-Oct-21 | 09-Nov-20 | 21-Oct-20 | 30-Nov-20 |  |  |  | 0
637604 | HUNTINGTON ROAD - CABLE REPLACEMENT P9295-P9297 | 830 - St. Catharines | 151452 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Nov-20 |  |  | 26575.61 | 26490.6 | 26575.61 | 26575.61 | Dan Despres | Wiens | 08-Dec-20 | 01-Nov-21 | 07-Dec-20 | 04-Dec-20 | 08-Dec-20 |  |  |  | 0
637675 | 24 KENNARD ST | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 11-Aug-20 |  |  | 73100.19 | 57986.77 | 73100.19 | 73100.19 | Roy Owen | Fairway | 28-Aug-20 | 01-Dec-21 | 24-Aug-20 | 18-Sep-20 | 15-Oct-20 | Customer | Customer |  | 0
637703 | 1250 LAKESHORE RD W / SCH / NS00042061 / 1PH PAD | 830 - St. Catharines | 150455 | Inactive | 99 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 08-Sep-20 |  |  | 57884.1 | 37999.94 | 57884.1 | 57884.1 | Frank Giancola | Wiens | 03-Nov-20 | 21-Mar-22 | 26-Oct-20 | 16-Oct-20 | 04-Dec-20 |  | Materials |  | 0
637896 | 686 QUEENSTON ROAD - ELECTRIFY CANADA/HAM/NS00032030/3PHPAD | 820 - Nebo | 150455 | Inactive | 99 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 27-Oct-20 |  |  | 81015.83 | 62971.78 | 81015.83 | 81015.83 | Roy Owen | Fairway | 08-Dec-20 | 22-Sep-22 | 30-Nov-20 | 17-Dec-20 | 21-Dec-20 | Contractor | Contractor |  | 0
637909 | COSTCO - ST.CATHARINES - 2500A 347/600V UPGRADE | 820 - Nebo | 150455 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 3780.93 | 0 |  | 0 | Calvin Arsenault |  |  | 01-Dec-20
637922 | 925-979 MAIN ST W / HRZ. SR | 820 - Nebo | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Kappheim, Adam | Alectra Utilities | 18-Sep-20 |  |  | 9140.64 | 3475.23 | 9140.64 | 9140.64 | Roy Owen |  | 30-Oct-20 | 17-Jan-22 | 28-Oct-20 | 09-Oct-20 | 09-Oct-20 |  |  |  | 0
638009 | 70 NIAGARA ST / SCH / UP00055820 / 3PH PAD REPLACEMENT | 830 - St. Catharines | 150449 | Inactive | 99 | COMPLETE |  |  | 2020 | Paesano, Andrew | Alectra Utilities | 28-Sep-20 |  |  | 48425.95 | 30702.31 | 48425.95 | 48425.95 | Frank Giancola |  | 23-Oct-20 | 24-Nov-21 | 20-Oct-20 | 09-Oct-20 | 09-Oct-20 |  |  |  | 0
638144 | 75 DISCOVERY DR - TEMP SERVICE | 820 - Nebo | 150449 | Inactive | 99 | CANCELLED |  |  | 2020 | Kappheim, Adam | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 22-Jan-21
638198 | FOOTHILLS OF WINONA - PHASE 2B - SUBD RES EDS | 820 - Nebo | 150588 | Inactive | 99 | CANCELLED |  |  | 2020 | Gamboa, Henry | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Calvin Arsenault |  |  | 12-Feb-21
638396 | 107 MCNAB ST NORTH, LINE ISOLATION | 820 - Nebo | 150665 | Inactive | 99 | COMPLETE |  |  | 2020 | Jakubowski, Mark | Alectra Utilities | 16-Oct-20 |  |  | 6275.54 | 13349.95 | 6275.54 | 6275.54 | Scott Borer |  | 30-Oct-20 | 22-Sep-22 | 26-Oct-20 | 26-Oct-20 | 15-Dec-20 | Customer | Customer |  | 0
CN 2020 | Central North Region | [7 empty] | 2020 |  | Alectra Utilities |  |  | 4 | 18354172.43 | 18629980.67 |  | 0 | [5 empty] | 11-Jan-19 | 28-Dec-20
450067 | Various Locations Brampton 2019 - Part 1 - 1ph pad replacement | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Missing Converted Employee for WO | Alectra Utilities | 04-Dec-19 |  |  | 96993.43 | 68146.5 | 96993.43 | 96993.43 | John Costa | A&W | 20-Feb-20 | 19-Oct-21 | 03-Feb-20 | 11-Sep-20 | 11-Dec-20 | Filler | Filler |  | 0
450138 | ELIZABETH ST S AND ELLIOT ST | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2020 | Weaver, Thomas | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 15-Jul-21
450141 | MS10 S/G Shoppers World Area Backup | 805 - Sandalwood | 150416 | Inactive | 99 | COMPLETE |  |  | 2019 | Luimes, John | Alectra Utilities | 25-Apr-19 |  |  | 239015.65 | 263647.68 | 239015.65 | 239015.65 | Richard Cuddy | Transpw | 02-Aug-19 | 02-Mar-23 | 17-Jun-19 | 02-Aug-19 | 18-Dec-19 |  | MC/PUCC Permit |  | 0
450152 | C.V. Employment Ph 2 | 805 - Sandalwood | 151673 | Active | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 17-Dec-19 |  |  | 226721.18 | 939382.49 | 226721.18 | 226721.18 | Richard Cuddy |  | 17-Mar-20 | 26-Jul-23 | 23-Jan-20 | 27-Jan-20 | 24-Nov-20 | Customer | Customer |  | 0
450170 | 3389 STEELES AVENUE EAST | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 08-Oct-19 |  |  | 53782.62 | 46908.06 | 53782.62 | 53782.62 | Simon Evason |  | 22-Nov-19 | 26-Jul-23 | 18-Nov-19 | 10-Feb-20 | 10-Feb-20 | Customer | Customer |  | 0
450192 | 525 MAIN ST N - Senior Care | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2020 | Rao, Gaurav | Alectra Utilities | 22-Jan-20 |  |  | 95225.82 | 118757.5 | 95225.82 | 95225.82 | Simon Evason | Transpw | 17-Mar-20 | 30-May-23 | 02-Mar-20 | 12-Jun-20 | 16-Jun-20 | Customer | COVID19 |  | 0
450195 | QUEEN ST. E. & THE GORE RD. | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE | High | Subdiv | 2020 | Gamboa, Henry | Alectra Utilities | 24-Jun-19 |  |  | 282401.72 | 195994.57 | 282401.72 | 282401.72 | Richard Cuddy |  | 21-Oct-19 | 26-Jul-23 | 23-Sep-19 | 18-May-20 | 08-Jul-20 | Customer | Customer |  | 0
450199 | HWY 410, N OF VODDEN ST E - 2019 Viper #7 | 805 - Sandalwood | 150494 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 99849.75 | 110281.11 | 99849.75 | 99849.75 | John Costa |  | 17-Mar-20 | 21-Jun-21 | 02-Mar-20 | 11-Mar-20 | 31-Aug-20 | Filler | COVID19 |  | 0
450205 | KENVIEW BLVD, S OF CASTLEVIEW - 2019 Viper SW #8 | 805 - Sandalwood | 150494 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 99082.13 | 85526.35 | 99082.13 | 99082.13 | Reaburn, Jeff |  | 17-Jul-20 | 07-Sep-21 | 02-Jul-20 | 02-Nov-20 | 06-Nov-20 | COVID19 | COVID19 |  | 0
450268 | STATEVIEW HOMES - OOH LA LA RESIDENTIAL SUBDIVISION | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 13-Feb-20 |  |  | 114545.24 | 258019.55 | 114545.24 | 114545.24 | Nichol, Sandi |  | 24-Mar-20 | 02-Aug-22 | 16-Mar-20 | 13-Mar-20 | 08-Jul-20 |  | COVID19 |  | 0
450294 | CHURCH ST E - 2018 Pole Batch#8 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Dec-19 |  |  | 252763.35 | 205453.28 | 252763.35 | 252763.35 | John Costa | A&W | 18-Dec-20 | 18-Feb-21 | 28-Sep-20 | 28-Sep-20 | 10-Dec-20 |  | COVID19 |  | 0
450313 | 27 MORRIS CRT | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2019 | McAlpine, Robert | Alectra Utilities | 25-Apr-19 |  |  | 0 | 31258.74 | 0 | 0 | Brian Erskine |  | 25-Apr-19 | 09-Aug-22 | 25-Apr-19 | 27-Jun-19 | 27-Jun-19 |  | Customer |  | 0
450326 | Rosedale Village Phase 7A Stg1 - SP17-114.000 New Sub | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 24-Jun-19 |  |  | 285520.29 | 254694.92 | 285520.29 | 285520.29 | Richard Cuddy | Conelco | 24-Jun-19 | 26-Jul-23 | 24-Jun-19 | 11-Aug-20 | 30-Oct-20 | Customer | Customer |  | 0
450335 | HEARTLAKE RD & COUNTRYSIDE DR | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 04-Dec-19 |  |  | 126848.08 | 120155.86 | 115848.08 | 126848.08 | John Costa |  | 13-Feb-20 | 11-Jul-22 | 13-Jan-20 | 20-Jan-20 | 18-Feb-20 | Locates |  |  | 11,000.00
450368 | 2 AUCTION LANE | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 21-Aug-19 |  |  | 98434.81 | 101100.46 | 98434.81 | 98434.81 | Simon Evason | Transpw | 07-Oct-19 | 18-Jan-22 | 23-Sep-19 | 02-Dec-19 | 28-Apr-20 | Customer | Customer |  | 0
450421 | BRISDALE RD & MAYFIELD RD | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 21-Aug-19 |  |  | 32281.73 | 116335.79 | 32281.73 | 32281.73 | Richard Cuddy |  | 02-Oct-19 | 27-Jun-23 | 23-Sep-19 | 16-Dec-19 | 08-Jul-20 | Customer | Customer |  | 0
450433 | 7935 KENNEDY RD SOUTH | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 05-Feb-20 |  |  | 125394.84 | 122119.11 | 125394.84 | 125394.84 | Simon Evason | Somervl | 05-Aug-20 | 26-Jul-23 | 20-Jul-20 | 28-Aug-20 | 19-Jun-20 | Customer | Customer |  | 0
450595 | 31 HANSEN RD. S. | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2019 | Rao, Gaurav | Alectra Utilities | 08-Aug-19 |  |  | 44095.14 | 28722.89 | 44095.14 | 44095.14 | Simon Evason | Somervl | 18-Sep-19 | 26-Jul-23 | 09-Sep-19 | 13-Dec-19 | 13-Dec-19 |  | Customer |  | 0
450600 | N SANDALWOOD PKY W KENNEDY RD | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 21-Oct-19 |  |  | 412633.96 | 341592.98 | 412633.96 | 412633.96 | Richard Cuddy | Transpw | 09-Jan-20 | 29-Dec-21 | 18-Nov-19 | 27-Nov-19 | 29-Apr-20 | Customer | Customer |  | 0
450601 | W CHINGUACOUSY RD S QUEEN ST W | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE | High | Subdiv | 2020 | Gamboa, Henry | Alectra Utilities | 08-May-20 |  |  | 387088.59 | 313297.82 | 387088.59 | 387088.59 | Richard Cuddy |  | 26-Jun-20 | 26-Jul-23 | 15-Jun-20 | 18-Jun-20 | 30-Oct-20 | Customer | Customer |  | 0
450604 | 2460 QUEEN ST E | 805 - Sandalwood | 150386 | Active | 95 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 25-Jun-19 |  |  | 45001 | 35455 | 45001 | 45001 | Simon Evason |  | 06-Aug-19 | 26-Jul-23 | 29-Jul-19 | 16-Jun-20 | 12-Aug-20 | Customer | Customer |  | 0
450610 | 3425 CASTLEMORE DRIVE | 805 - Sandalwood | 150386 | Inactive | 99 | CANCELLED |  |  | 2020 | Rao, Gaurav | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 04-Jan-19 |  | 11-Dec-20
450611 | 11613 BRAMALEA ROAD | 805 - Sandalwood | 150389 | Active | 98 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 18-Dec-19 |  |  | 139151.6 | 86183.35 | 139151.6 | 139151.6 | Simon Evason | Somervl | 14-Feb-20 | 26-Jul-23 | 03-Feb-20 | 09-Apr-20 | 28-May-20 | Customer | COVID19 |  | 0
450621 | 5,9,15 BEAUMARIS DR. | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2019 | McAlpine, Robert | Alectra Utilities | 23-May-19 |  |  | 84091 | 66108.63 | 84091 | 84091 | Simon Evason | Somervl | 16-Jul-19 | 26-Jul-23 | 02-Jul-19 | 19-Dec-19 | 19-Dec-19 | Customer | Customer |  | 0
450632 | 7850 Heritage Rd. | 805 - Sandalwood | 150389 | Active | 98 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 11-Aug-20 |  |  | 115187.63 | 114060.48 | 115187.63 | 115187.63 | Simon Evason | Somervl | 29-Sep-20 | 26-Jul-23 | 14-Sep-20 | 19-Oct-20 | 17-Nov-20 | Customer | Customer |  | 0
450637 | 31 & 23 VODDEN ST W | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 10512.98 | 19572.87 | 10512.98 | 10512.98 | John Costa | A&W | 07-Jul-20 | 14-Feb-22 | 07-Jul-20 | 11-Sep-20 | 30-Oct-20 | COVID19 | COVID19 |  | 0
450663 | MCLAUGHLIN RD & WHITEPOPPY DR | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Gamboa, Henry | Alectra Utilities | 05-Feb-20 |  |  | 45584.82 | 50832.5 | 50650.08 | 45584.82 | Richard Cuddy | Somervl | 18-Mar-20 | 15-Jun-23 | 11-Mar-20 | 05-Nov-20 | 24-Nov-20 | Customer | Customer |  | -5,065.26
450736 | McMurchy Ave S and Steeles Ave W | 805 - Sandalwood | 151188 | Inactive | 99 | COMPLETE |  |  | 2019 | Agostini, Robert | Alectra Utilities | 24-Apr-19 |  |  | 192607.3 | 229611.63 | 192607.3 | 192607.3 | Richard Cuddy | Transpw | 23-Jul-19 | 12-Apr-23 | 17-Jun-19 | 02-Aug-19 | 12-Dec-19 |  | MC/PUCC Permit |  | 0
450744 | 2675 STEELES AVE. W. | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 08-Aug-19 |  |  | 159463.55 | 145922.24 | 159463.55 | 159463.55 | Simon Evason | Transpw | 16-Oct-19 | 26-Jul-23 | 23-Sep-19 | 20-Dec-19 | 29-Jan-20 | Customer | Customer |  | 0
450753 | WILLIAMS PKWY & MISSISSAUGA RD | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 06-Dec-19 |  |  | 149176.1 | 588027.14 | 149176.1 | 149176.1 | Richard Cuddy |  | 06-Feb-20 | 26-Jul-23 | 06-Jan-20 | 03-Jul-20 | 24-Nov-20 | Customer | Customer |  | 0
450773 | 130 RAILSIDE DR. | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2019 | Rao, Gaurav | Alectra Utilities | 04-Jun-19 |  |  | 167161 | 138296.82 | 167161 | 167161 | Simon Evason | Somervl | 23-Jul-19 | 26-Jul-23 | 08-Jul-19 | 23-Aug-19 | 17-Dec-19 |  | Customer |  | 0
450783 | DIXIE RD & WILLIAMS PKWY | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Pelleja, Emily | Alectra Utilities | 31-Jul-20 |  |  | 120711.91 | 113156.14 | 120711.91 | 120711.91 | Reaburn, Jeff | A&W | 25-Sep-20 | 18-Jul-23 | 24-Aug-20 | 10-Aug-20 | 09-Nov-20 | Customer | Customer |  | 0
450808 | MAYFIELD AND BRAMALEA RD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 14-Dec-18 |  |  | 16002 | 14207.52 | 16002 | 16002 | Simon Evason |  | 15-Jan-19 | 22-Sep-22 | 14-Jan-19 | 11-Jan-19 | 28-Apr-20 | Customer | Customer |  | 0
450815 | 475 CHRYSLER DR | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 25-Sep-19 |  |  | 82284.48 | 64684.12 | 82284.48 | 82284.48 | Simon Evason | Somervl | 08-Nov-19 | 27-Sep-22 | 28-Oct-19 | 28-Oct-19 | 30-Mar-20 | Customer | Customer |  | 0
450817 | 10254 HURONTARIO STREET | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 08-Jul-20 |  |  | 116956.52 | 106225.58 | 116956.52 | 116956.52 | Simon Evason | Transpw | 21-Aug-20 | 22-Sep-22 | 10-Aug-20 | 27-Oct-20 | 20-Nov-20 | Customer | Customer |  | 0
450835 | BRAMPTON DOWNNTOWN | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 19-Dec-18 |  |  | 1269132.42 | 1215520.34 | 1235399.92 | 1269132.42 | Nichol, Sandi |  | 18-Nov-19 | 30-Jan-23 | 08-Apr-19 | 01-Apr-19 | 10-Jan-20 |  |  |  | 33,732.50
450866 | 11025 TORBRAM RD | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 20-Sep-19 |  |  | 71096.05 | 92243.56 | 71096.05 | 71096.05 | Simon Evason | Transpw | 25-Oct-19 | 26-Jul-23 | 21-Oct-19 | 20-Dec-19 | 21-Jan-20 | Customer | Customer |  | 0
450890 | 80 MARY ST. | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE | Low | Indust | 2020 | Rao, Gaurav | Alectra Utilities | 01-Aug-19 |  |  | 37549.21 | 34454.77 | 37549.21 | 37549.21 | Simon Evason |  | 20-Sep-19 | 18-Feb-21 | 16-Sep-19 | 08-Jun-20 | 12-Jun-20 | Customer | Customer |  | 0
450894 | CHINGUACOUSY RD & WANLESS DR | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 14-Jun-19 |  |  | 1476984.69 | 1571725.22 | 1476984.69 | 1476984.69 | Richard Cuddy |  | 26-Nov-19 | 24-Oct-23 | 30-Sep-19 | 13-Dec-19 | 26-May-20 | Customer | Customer |  | 0
450915 | 223 Corporation Dr - 3ph - tx repl | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 04-Dec-19 |  |  | 27203.46 | 32792.86 | 27203.46 | 27203.46 | Reaburn, Jeff |  | 04-Sep-20 | 09-Aug-21 | 04-Sep-20 | 02-Oct-20 | 02-Oct-20 | COVID19 | COVID19 |  | 0
450929 | STEELES AVE AND SANDALWOOD PKW | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2020 | Lacombe, Joel | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 15-Jul-21
450930 | FINANCIAL DR & HERITAGE RD - Subdivision | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 13-Dec-19 |  |  | 647123.78 | 622554.34 | 647123.78 | 647123.78 | Nichol, Sandi | Transpw | 25-Mar-20 | 10-Jul-23 | 20-Jan-20 | 26-Nov-19 | 07-Jul-20 |  | Customer |  | 0
450931 | GREAT LAKE & SANDALWOOD PKY E | 805 - Sandalwood | 150630 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 21-Oct-19 |  |  | 140556.99 | 93661.36 | 140556.99 | 140556.99 | Richard Cuddy |  | 22-Nov-19 | 13-Apr-23 | 18-Nov-19 | 10-Feb-20 | 07-Jul-20 | Customer | Customer |  | 0
450936 | PROFESSOR LAKE PKY/PRINCETON - SG | 805 - Sandalwood | 150277 | Active | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 101638.31 | 4792.33 | 101638.31 | 101638.31 | Richard Cuddy |  | 21-Sep-20 | 26-Jul-23 | 07-Sep-20 | 08-Sep-20 | 30-Oct-20 |  | COVID19 |  | 0
450940 | 2020 POLE RENEWAL- MCCAUL ST- CENTRE ST N TO KENNEDY DR N - 12 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Dec-19 |  |  | 343351.83 | 302022.95 | 343351.83 | 343351.83 | Reaburn, Jeff | A&W | 18-Dec-20 | 14-Feb-22 | 08-Sep-20 | 08-Sep-20 | 20-Oct-20 |  |  |  | 0
450947 | 5 SANDALWOOD PKY W - 3ph tx. repl | 805 - Sandalwood | 150494 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 25077.89 | 20454.04 | 25077.89 | 25077.89 | Reaburn, Jeff |  | 04-Aug-20 | 12-Jul-21 | 04-Aug-20 | 23-Sep-20 | 23-Sep-20 | COVID19 | COVID19 |  | 0
450949 | 35 AUTOMATIC - 3ph - pad mount tx | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 36644.45 | 27938.16 | 36644.45 | 36644.45 | Reaburn, Jeff |  | 13-Jul-20 | 07-Sep-21 | 13-Jul-20 | 31-Oct-20 | 02-Nov-20 | COVID19 | COVID19 |  | 0
450950 | 25 REGAN RD - 3ph tx. repl | 805 - Sandalwood | 150494 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 26045.49 | 19996.72 | 26045.49 | 26045.49 | Reaburn, Jeff |  | 07-Aug-20 | 19-Oct-21 | 07-Aug-20 | 25-Sep-20 | 25-Sep-20 |  | COVID19 |  | 0
450960 | 7948 CHURCHVILLE RD | 805 - Sandalwood | 150645 | Inactive | 99 | CANCELLED |  |  | 2020 | Lacombe, Joel | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 15-Jul-21
450964 | 247 MCMURCHY AVE S | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2019 | Rao, Gaurav | Alectra Utilities | 11-Sep-19 |  |  | 78871.03 | 61159.37 | 78871.03 | 78871.03 | Simon Evason | Somervl | 19-Dec-19 | 15-Mar-23 | 09-Dec-19 | 24-Jan-20 | 20-Dec-19 | Customer | Customer |  | 0
450971 | MS-1 ELIZABETH ST 4KV CONV PH3 - Part A | 805 - Sandalwood | 151138 | Active | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 01-Nov-19 |  |  | 610046.23 | 683199.75 | 610046.23 | 610046.23 | Reaburn, Jeff |  | 03-Jul-20 | 26-Jul-23 | 06-Jan-20 | 03-Jan-20 | 03-Sep-20 |  | COVID19 |  | 0
631722 | 2020 INSULATOR REPLACEMENT PROGRAM | 805 - Sandalwood | 151021 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 02-Oct-19 |  |  | 333136.87 | 310895.38 | 333136.87 | 333136.87 | John Costa |  | 18-Dec-20 | 15-Nov-21 | 06-Jan-20 | 06-Jan-20 | 18-Dec-20 | Filler | Filler |  | 0
631757 | 27.6KV UNDERGROUND NEW SERVICE @ 50 COACHWORKS CRES | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 01-Oct-19 |  |  | 85110.12 | 62207.3 | 85110.12 | 85110.12 | Simon Evason | Somervl | 12-Nov-19 | 22-Sep-22 | 11-Nov-19 | 18-Nov-19 | 20-Jan-20 | Customer | Customer |  | 0
631934 | MATTAMY BOVAIRD CONDO (BLOCK 7) | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 13-Dec-19 |  |  | 313757.12 | 382885.19 | 313757.12 | 313757.12 | Richard Cuddy |  | 25-Feb-20 | 26-Jul-23 | 13-Jan-20 | 18-Sep-20 | 18-Sep-20 | Customer | Customer |  | 0
632351 | MS10 Brampton Design | 805 - Sandalwood | 150637 | Inactive | 99 | COMPLETE |  |  | 2020 | Dehaijle, Carlton | Alectra Utilities | 24-Sep-20 |  |  | 134163.07 | 184497.91 | 84736.07 | 134163.07 | Richard Cuddy | Somervl | 06-Nov-20 | 10-May-23 | 26-Oct-20 | 12-Oct-20 | 14-Dec-20 | Customer | Contractor |  | 49,427.00
632754 | 100 MARTIN BYRNE - 27.6KV SUPPLY TO 750 KVA TX | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 20-Sep-19 |  |  | 82227.21 | 83370.52 | 82227.21 | 82227.21 | Simon Evason | Somervl | 06-Nov-19 | 26-Jul-23 | 28-Oct-19 | 15-Jan-20 | 28-Apr-20 | Customer | Customer |  | 0
632823 | FEEDER CABLE REPLACEMENT GRID J4 | 805 - Sandalwood | 150572 | Active | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Jan-20 |  |  | 681177.58 | 716586.84 | 681177.58 | 681177.58 | Mark Bobanovic | Transpw | 04-Sep-20 | 26-Jul-23 | 13-Jul-20 | 27-Jul-20 | 14-Dec-20 | Locates |  |  | 0
632874 | PROFESSOR'S LAKE PKWY FEEDER CABLE REPLACEMENT -ELECTRICAL PHASE | 805 - Sandalwood | 150277 | Active | 99 | COMPLETE | High | Infrast | 2020 | Agostini, Robert | Alectra Utilities | 01-May-20 |  |  | 898331.81 | 808360.91 | 863252.97 | 898331.81 | Richard Cuddy | Transpw | 30-Nov-20 | 26-Jul-23 | 08-Jun-20 | 21-Apr-20 | 25-Sep-20 |  | COVID19 |  | 35,078.84
633119 | Tx Replacement Grid F3 - 7 min pads | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 20-Jan-20 |  |  | 80438.41 | 43193.7 | 80438.41 | 80438.41 | John Costa | A&W | 14-Feb-20 | 27-May-21 | 03-Feb-20 | 24-Jan-20 | 30-Oct-20 | COVID19 | Lines |  | 0
633120 | 2020 SWITCHGEAR RENEWAL - SITE# 213 - 1 MILKWEED | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 19-Dec-19 |  |  | 108274.98 | 95154.89 | 108274.98 | 108274.98 | Nichol, Sandi |  | 17-Jul-20 | 22-Sep-22 | 06-Jul-20 | 12-Mar-20 | 16-Mar-20 |  |  |  | 0
633122 | 2020 SWITCHGEAR REPLACEMENTS - SITE# 174 -223 CORPORATION DR | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 106353.53 | 97376.28 | 106353.53 | 106353.53 | Richard Cuddy |  | 27-Nov-20 | 07-Sep-21 | 16-Nov-20 | 02-Nov-20 | 06-Nov-20 |  |  |  | 0
633123 | 2020 SWITCHGEAR REPLACEMENTS - SITE# 221 - 30 PEDIGREE CRT | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 105763.07 | 85137.66 | 105763.07 | 105763.07 | Richard Cuddy |  | 15-May-20 | 07-Sep-21 | 04-May-20 | 06-Nov-20 | 17-Oct-20 | COVID19 | COVID19 |  | 0
633124 | 2020 SWITCHGEAR REPLACEMENTS - SITE# 270 - 2 GROUSE LANE | 805 - Sandalwood | 150282 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 105763.07 | 108735.54 | 105763.07 | 105763.07 | Richard Cuddy |  | 01-Jun-20 | 07-Sep-21 | 19-May-20 | 06-Jul-20 | 25-Sep-20 | COVID19 | COVID19 |  | 0
633147 | 2020 TRANSFORMER REPLACEMENTS-GRID H3 - 6 min pads | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 05-Feb-20 |  |  | 85460.92 | 57732.66 | 85460.92 | 85460.92 | John Costa | A&W | 25-Mar-20 | 02-Jun-21 | 02-Mar-20 | 16-Oct-20 | 24-Nov-20 | COVID19 | COVID19 |  | 0
633148 | 2020 TRANSFORMER REPLACEMENTS-GRID B3 - 1ph repl | 805 - Sandalwood | 150494 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 04-Dec-19 |  |  | 43104.11 | 35257.28 | 43104.11 | 43104.11 | John Costa | A&W | 11-Sep-20 | 02-Jun-21 | 17-Aug-20 | 09-Oct-20 | 30-Oct-20 | COVID19 | COVID19 |  | 0
633156 | JOINT USE PERMIT #HB2019-007 - RUTHERFORD ROAD SOUTH - BRAMPTON | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 06-Dec-19 |  |  | 6640.16 | 4213.72 | 6640.16 | 6640.16 | Brian Erskine |  | 17-Jan-20 | 22-Aug-22 | 13-Jan-20 | 06-Jan-20 | 14-Feb-20 | Customer | Customer |  | 0
633230 | TEMPORARILY REMOVE SPAN GUYS AND DOWN GUYS, COUNTRYSIDE DR | 805 - Sandalwood | 150674 | Inactive | 99 | CANCELLED |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 17-Jan-20 |  |  | 0 | 268.86 |  | 0 | Reaburn, Jeff |  | 03-Mar-20 | 11-Nov-19 | 24-Feb-20
633243 | Kennedy Dr N and Williams Pkwy - 2020 SWITCH REPLACEMENTS - SW# 20-1777 | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 07-Feb-20 |  | 1 | 128709.49 | 107650.68 | 128709.49 | 128709.49 | John Costa |  | 30-Sep-20 | 14-Feb-22 | 08-Sep-20 | 05-Oct-20 | 11-Dec-20 | COVID19 | COVID19 |  | 0
633244 | McLaughlin Rd and Kingknoll Dr. 2020 SWITCH REPLACEMENTS - SW# 20-396 | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 05-Feb-20 |  | 1 | 102804.04 | 102231.38 | 102804.04 | 102804.04 | John Costa |  | 29-Sep-20 | 15-Nov-21 | 08-Sep-20 | 02-Nov-20 | 18-Nov-20 | COVID19 | COVID19 |  | 0
633245 | 2020 SWITCH REPLACEMENTS - SW# 20-270 - Vodden and Main St | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  | 1 | 103057.22 | 118260.15 | 103057.22 | 103057.22 | John Costa |  | 31-Mar-20 | 07-Sep-21 | 16-Mar-20 | 26-Feb-20 | 27-Jul-20 |  | COVID19 |  | 0
633247 | 2020 SWITCH REPLACEMENTS - SW# 20-1414 - 144 Kennedy Rd S | 805 - Sandalwood | 151010 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  | 1 | 78719 | 64173.83 | 78719 | 78719 | Reaburn, Jeff |  | 29-Jul-20 | 15-Sep-21 | 20-Jul-20 | 20-Jul-20 | 12-Aug-20 | COVID19 | COVID19 |  | 0
633436 | POLE RELOCATION, HERITAGE ROAD | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2020 | Pelleja, Emily | Alectra Utilities | 20-Jan-20 |  |  | 31168.86 | 17582.77 | 31168.86 | 31168.86 | Nichol, Sandi |  | 03-Mar-20 | 22-Sep-22 | 24-Feb-20 | 14-Feb-20 | 14-Feb-20 |  |  |  | 0
633463 | COUNTRYSIDE DR - TEMPORARILY REMOVE SPAN GUYS AND DOWN GUYS | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 09-Sep-19 |  |  | 10378.99 | 3750.92 | 10378.99 | 10378.99 | John Costa |  | 03-Oct-19 | 15-Nov-21 | 30-Sep-19 | 13-Sep-19 | 18-Jun-20 | Customer | Customer |  | 0
633529 | MS-1 ELIZABETH ST 4KV CONV PH3 - Part B Laterals | 805 - Sandalwood | 151138 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 01-Nov-19 |  |  | 1006125.68 | 1021715.11 | 1119273.46 | 1006125.68 | Reaburn, Jeff |  | 15-Dec-20 | 22-Sep-22 | 06-Jan-20 | 03-Jan-20 | 20-Nov-20 |  |  |  | -113,147.78
633565 | 2020 TRANSFORMER REPLACEMENTS-GRID D2 | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 28472.72 | 32475.2 | 28472.72 | 28472.72 | John Costa | A&W | 07-Jul-20 | 27-May-21 | 03-Jul-20 | 11-Sep-20 | 30-Oct-20 | COVID19 | COVID19 |  | 0
633566 | 2020 TRANSFORMER REPLACEMENTS-GRID D3 | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 10352.76 | 13174.58 | 10352.76 | 10352.76 | John Costa | A&W | 02-Jul-20 | 27-May-21 | 02-Jul-20 | 11-Sep-20 | 30-Oct-20 | COVID19 | COVID19 |  | 0
633577 | 2020 TRANSFORMER REPLACEMENTS-GRID H2 - 2 mini pads | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 02-Dec-19 |  |  | 19829.16 | 11817.9 | 19829.16 | 19829.16 | John Costa | A&W | 27-Oct-20 | 27-May-21 | 26-Oct-20 | 12-Oct-20 | 30-Oct-20 |  | Customer |  | 0
633581 | 2020 TRANSFORMER REPLACEMENTS-GRID K3 - 3 min units | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 05-Feb-20 |  |  | 47535.21 | 22427.7 | 47535.21 | 47535.21 | John Costa | A&W | 10-Mar-20 | 02-Jun-21 | 02-Mar-20 | 31-Aug-20 | 30-Oct-20 | COVID19 | COVID19 |  | 0
633582 | 2020 TRANSFORMER REPLACEMENTS-GRID K4 | 805 - Sandalwood | 150285 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 2102.07 | ($0.27) | 2102.07 | 2102.07 | Dre Danieli |  |  | 16-Mar-22 | [6 empty] | 0
633583 | 2020 TRANSFORMER REPLACEMENTS-GRID O3 - 1 min pad | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 02-Dec-19 |  |  | 10178.11 | 56437.53 | 10178.11 | 10178.11 | John Costa | A&W | 30-Mar-20 | 27-May-21 | 30-Mar-20 | 31-Aug-20 | 30-Oct-20 | COVID19 | COVID19 |  | 0
633586 | Miss Rd and Lion Heead Golf Club Rd - 2020 DISTRIBUTION AUTOMATION- SW# 20-XXX | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 05-Feb-20 |  |  | 83933.26 | 82421.37 | 83933.26 | 83933.26 | John Costa |  | 09-Sep-20 | 17-Jan-22 | 24-Aug-20 | 29-Oct-20 | 01-Dec-20 | COVID19 | COVID19 |  | 0
633636 | 2020 EMERGING PROJECT - VAULT T3588 - kennedy Rd S | 805 - Sandalwood | 151449 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 04-Aug-20 |  |  | 386732.55 | 407470.58 | 386732.55 | 386732.55 | Reaburn, Jeff | Somervl | 28-Aug-20 | 07-Sep-21 | 10-Aug-20 | 10-Aug-20 | 18-Sep-20 |  | Customer |  | 0
633664 | POLE LINE RECOVERY | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 04-Dec-19 |  |  | 13294.84 | 11139.32 | 13294.84 | 13294.84 | John Costa |  | 08-Jan-20 | 10-Jul-22 | 06-Jan-20 | 06-Jan-20 | 08-Jan-20 |  |  |  | 0
633742 | 2020 DA- 7678 MAVIS RD | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 09-Dec-19 |  |  | 104494.85 | 108022.42 | 104494.85 | 104494.85 | John Costa |  | 21-Aug-20 | 25-Oct-21 | 04-Aug-20 | 27-Oct-20 | 04-Dec-20 | COVID19 | COVID19 |  | 0
633743 | 2020 DA- 7732 MCLAUGHLIN RD S | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 04-Dec-19 |  |  | 101206.86 | 63101.38 | 101206.86 | 101206.86 | Reaburn, Jeff |  | 17-Sep-20 | 07-Sep-21 | 01-Sep-20 | 01-Sep-20 | 17-Sep-20 |  |  |  | 0
633744 | 2020 DA- 7776 MISSISSAUGA RD | 805 - Sandalwood | 151104 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Dec-19 |  |  | 104778.25 | 110030.23 | 104778.25 | 104778.25 | Reaburn, Jeff |  | 16-Sep-20 | 07-Sep-21 | 31-Aug-20 | 09-Nov-20 | 27-Nov-20 | COVID19 | COVID19 |  | 0
634036 | 80 RIVERMONT - 27.6KV SUPPLY TO 500 KVA TX | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE | High | Comm | 2020 | Rao, Gaurav | Alectra Utilities | 24-Apr-20 |  |  | 76531.4 | 58472.3 | 76531.4 | 76531.4 | Simon Evason | Somervl | 19-Jun-20 | 26-Jul-23 | 08-Jun-20 | 26-May-20 | 12-Jun-20 |  |  |  | 0
634439 | 221 ADVANCE BLVD- UPGRADE FROM 200 AMP TO 600 AMP 347/600V | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 24-Aug-20
634524 | 201 WESTCREEK BLVD POLE RELOCATION | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE | VerHigh | Safety | 2020 | Pelleja, Emily | Alectra Utilities | 06-Apr-20 |  |  | 48926.05 | 40494.38 | 48926.05 | 48926.05 | Nichol, Sandi |  | 13-May-20 | 26-Jan-23 | 04-May-20 | 17-Apr-20 | 17-Apr-20 |  |  |  | 0
634642 | 2019 EMERGING - 3 SHADYWOOD- NEW SERVICE CONDUCTOR | 805 - Sandalwood | 151449 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 10-Jan-20 |  |  | 35001.71 | 27527.86 | 35001.71 | 35001.71 | Reaburn, Jeff | Somervl | 05-Feb-20 | 26-Apr-21 | 03-Feb-20 | 15-Jan-20 | 24-Jan-20 |  |  |  | 0
634662 | 9287 GOREWAY DR | 805 - Sandalwood | 150389 | Active | 95 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 08-Oct-20 |  |  | 99786.33 | 119921.84 | 99786.33 | 99786.33 | Simon Evason | Transpw | 10-Nov-20 | 26-Jul-23 | 02-Nov-20 | 23-Oct-20 | 28-Dec-20 | Customer | Customer |  | 0
634679 | 2020 TX RENEWAL-239 QUEEN ST E - VT7315 | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Nov-19 |  |  | 85712.54 | 88080.84 | 85712.54 | 85712.54 | Nichol, Sandi |  | 14-Feb-20 | 20-May-21 | 03-Feb-20 | 09-Jan-20 | 27-Jan-20 |  |  |  | 0
634915 | 9025 TORBRAM RD | 805 - Sandalwood | 150277 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 09-Dec-19 |  |  | 28208.7 | 47932.42 | 28208.7 | 28208.7 | Simon Evason |  | 06-Apr-20 | 27-May-21 | 06-Apr-20 | 02-Feb-20 | 05-Feb-20 | Customer | Customer |  | 0
634945 | 2020 POLE RENEWAL - CUMBERLAND DR AND MCCULLA AVE - 1 POLE | 805 - Sandalwood | 150284 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 15659.78 | 0 | 15659.78 | 15659.78 | Dre Danieli |  | 08-Oct-20 | 26-Oct-20 | 08-Oct-20 | 08-Oct-20 | 08-Oct-20 |  |  |  | 0
634969 | 2019 EMERGING-16 PALGRAVE CRES- SERVICE AND CABLE INSTALLATION | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 20-Jan-20 |  |  | 34823.41 | 36288.47 | 34823.41 | 34823.41 | Reaburn, Jeff | Somervl | 19-Feb-20 | 21-Jun-21 | 18-Feb-20 | 30-Jan-20 | 30-Jan-20 |  |  |  | 0
635041 | 2020 POLE RENEWAL - POLE #10315 AND #10333 KENNEDY & COCHRANE GRID H2 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 15-Jan-20 |  |  | 40940.4 | 53008.23 | 40940.4 | 40940.4 | Nichol, Sandi |  | 24-Jun-20 | 11-Jan-21 | 15-Jun-20 | 26-Feb-20 | 10-Mar-20 |  |  |  | 0
635042 | 2020 POLE RENEWAL - POLE #10315 KENNEDY RD N GRID H2 | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities | 03-Jul-20 |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 24-Aug-20 |  | 11-Dec-20 | 11-Dec-20
635043 | G3-91 - 71 CHURCH ST E - CITY OF BRAMPTON - 600A 120/208V | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 04-Dec-20 |  |  | 80365.96 | 59778.9 | 80365.96 | 80365.96 | Simon Evason | Somervl | 01-Feb-21 | 28-Mar-23 | 18-Jan-21 | 17-Dec-20 | 17-Dec-20 |  |  |  | 0
635106 | 2020 LEFT-BEHIND CABLE REPLACE | 805 - Sandalwood |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities | 03-Jul-20 |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 24-Aug-20 |  | 11-Dec-20 | 11-Dec-20
635491 | 2020 POLE RENEWAL - POLE #11477 AND #11249 KENNEDY RD N GRID H1 - 2 Poles | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Jul-20 |  |  | 29723.89 | 20164.58 | 29723.89 | 29723.89 | Reaburn, Jeff |  | 18-Dec-20 | 07-Sep-21 | 07-Dec-20 | 27-Nov-20 | 18-Dec-20 |  |  |  | 0
635563 | 2020 POLE RENEWAL - POLE #8670 BRAMALEA RD, S OF CLARK BLVD GRID J4 | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 05-Feb-20 |  |  | 15194.44 | 8903.54 | 15194.44 | 15194.44 | John Costa |  | 17-Apr-20 | 05-Aug-21 | 13-Apr-20 | 09-Nov-20 | 10-Nov-20 | COVID19 | COVID19 |  | 0
635795 | 21T-18007B FOUR X PHASE 3 | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 27-Aug-20 |  |  | 154111.34 | 150123.2 | 154111.34 | 154111.34 | Richard Cuddy |  | 29-Sep-20 | 26-Jul-23 | 28-Sep-20 | 05-Oct-20 | 17-Nov-20 | Customer | Control/SCADA |  | 0
635862 | 21T-19012B PARADISE HOMES NW PH3C | 805 - Sandalwood | 150630 | Active | 99 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 31-Jul-20 |  |  | 428021.84 | 333381.17 | 428021.84 | 428021.84 | Richard Cuddy | Transpw | 17-Nov-20 | 26-Jul-23 | 08-Sep-20 | 08-Sep-20 | 03-Dec-20 |  |  |  | 0
635948 | 7891 CHURCHVILLE RD / BRAM / NS / 1PH (LAYOUT) | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 13-Jul-20 |  |  | 31085.46 | 24707.73 | 31085.46 | 31085.46 | Reaburn, Jeff | Somervl | 20-Aug-20 | 26-Jun-22 | 12-Aug-20 | 05-Aug-20 | 05-Aug-20 |  |  |  | 0
635983 | 2020 POLE RENEWAL - VARIOUS-GRID G3 - 3 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Jul-20 |  |  | 80703.89 | 50134.24 | 80703.89 | 80703.89 | Reaburn, Jeff |  | 27-Nov-20 | 05-Aug-21 | 02-Nov-20 | 06-Nov-20 | 16-Dec-20 | COVID19 | COVID19 |  | 0
635986 | DIXIE RD - CLARK BLVD TO QUEEN ST E ANCHOR RELOCATION | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2020 | Watters, Maxwell | Alectra Utilities | 14-Sep-20 |  |  | 26777.59 | 22738.73 | 26777.59 | 26777.59 | Reaburn, Jeff | A&W | 16-Oct-20 | 04-May-23 | 14-Oct-20 | 14-Sep-20 | 09-Nov-20 |  | Customer |  | 0
636059 | 8 BRAMWIN CRT - SERVICE UPGRADE | 805 - Sandalwood | 150386 | Active | 98 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 12-Jun-20 |  |  | 60657.17 | 58792.88 | 60657.17 | 60657.17 | Simon Evason |  | 23-Jul-20 | 26-Jul-23 | 20-Jul-20 | 18-Sep-20 | 18-Sep-20 | Customer | Customer |  | 0
636061 | 2020 POLE RENEWAL-116 RUTHERFORD RD S - 1 Pole | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Jul-20 |  |  | 19675.09 | 14609.5 | 19675.09 | 19675.09 | Reaburn, Jeff |  | 30-Oct-20 | 07-Sep-21 | 26-Oct-20 | 29-Oct-20 | 06-Nov-20 | COVID19 | COVID19 |  | 0
636264 | 2020 EMERGING- 7891 CHURCHVILLE RD | 805 - Sandalwood | 150784 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 16-Jun-21
636335 | 2020 POLE RENEWAL-GRID F3-ARCHIBALD ST/MOORE ST, DAVID ST/MILL ST 3 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Jul-20 |  |  | 78963.81 | 62136.01 | 78963.81 | 78963.81 | Reaburn, Jeff |  | 04-Dec-20 | 22-Nov-21 | 16-Nov-20 | 06-Nov-20 | 20-Nov-20 |  |  |  | 0
636456 | 9287 GOREWAY DR | 805 - Sandalwood | 151449 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 26-Aug-20 |  |  | 82153.41 | 71483.04 | 82153.41 | 82153.41 | Richard Cuddy | Transpw | 05-Oct-20 | 01-Dec-21 | 28-Sep-20 | 07-Jul-20 | 30-Oct-20 |  | Customer |  | 0
636543 | 2020 CABLE REPLACEMENT - GRID: J3 | 805 - Sandalwood | 151181 | Active | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 03-Jul-20 |  |  | 484185 | 218944.03 | 484185 | 484185 | Richard Cuddy | Transpw | 02-Nov-20 | 26-Jul-23 | 28-Sep-20 | 28-Sep-20 | 12-Nov-20 |  | Contractor |  | 0
636766 | 465 DEERHURST DR | 805 - Sandalwood | 150386 | Active | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 22-Oct-20 |  |  | 77670.88 | 47758.78 | 77670.88 | 77670.88 | Simon Evason | Somervl | 01-Dec-20 | 04-Aug-23 | 23-Nov-20 | 14-Dec-20 | 17-Dec-20 | Customer | Customer |  | 0
636972 | OH FCI FILLER WORK | 805 - Sandalwood | 150784 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli
636999 | INSTALL UG FAULTED CIRCUIT INDICATORS W/LED | 805 - Sandalwood | 151449 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 11-Dec-20
637000 | INSTALL UG FAULTED CIRCUIT INDICATORS ACOUSTIC/LED | 805 - Sandalwood | 151449 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 11-Dec-20
637010 | 2020 - AUTOMATION ORDER - BW- VERTICAL | 805 - Sandalwood | 151010 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  |  |  | 11-Dec-20 | 11-Dec-20
637011 | 2020 - AUTOMATION ORDER - BW- VERTICAL | 805 - Sandalwood | 151010 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  |  |  | 11-Dec-20 | 11-Dec-20
637012 | 2020 - AUTOMATION ORDER - BW- VERTICAL | 805 - Sandalwood | 151010 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  |  |  | 11-Dec-20 | 11-Dec-20
637013 | 2020 - AUTOMATION ORDER - BW- HORIZONTAL | 805 - Sandalwood | 151010 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  |  |  | 11-Dec-20 | 11-Dec-20
637016 | 2020 - INSULATOR ORDER - BW | 805 - Sandalwood | 151021 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  |  |  | 11-Dec-20 | 11-Dec-20
637044 | ROAD CROSSING AND 1/0 CABLE RELOCATION-HURONTARIO ST AND HIGHWOOD RD. | 805 - Sandalwood | 150645 | Active | 99 | COMPLETE |  |  | 2020 | Pelleja, Emily | Alectra Utilities | 09-Jul-20 |  |  | 55063.16 | 72016.28 | 55063.16 | 55063.16 | Reaburn, Jeff | Somervl | 11-Aug-20 | 26-Jul-23 | 10-Aug-20 | 20-Jul-20 | 27-Jul-20 |  |  |  | 0
637065 | CENTRAL NORTH BRACKETS FILLER WORK | 805 - Sandalwood | 150784 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli
637066 | CENTRAL NORTH OH TRANSFORMERS FILLER WORK | 805 - Sandalwood | 150285 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  |  |  | 11-Dec-20 | 11-Dec-20
637067 | CENTRAL NORTH PADMOUNT TRANSFORMERS FILLER WORK | 805 - Sandalwood | 150285 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  |  |  | 11-Dec-20 | 11-Dec-20
637152 | 2020 POLE RENEWAL-GRID F3-MAIN ST- 2 POLES | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Jul-20 |  |  | 59595.04 | 30605.06 | 59595.04 | 59595.04 | Reaburn, Jeff |  | 11-Dec-20 | 22-Nov-21 | 07-Dec-20 | 20-Nov-20 | 27-Nov-20 |  |  |  | 0
637187 | 50 BROMLEY CRES - REAR LOT O/H SEC SERVICE AERIAL ENCROACHMENT | 805 - Sandalwood | 150784 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 05-Jun-20 |  |  | 9044.87 | 2555.34 | 9044.87 | 9044.87 | Brian Erskine |  | 10-Jul-20 | 27-Apr-23 | 10-Jul-20 | 22-Jun-20 | 22-Jun-20 |  |  |  | 0
637188 | 26 PINE TREE CRES / BRAM / NS / 1PH PAD | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 24-Jul-20 |  |  | 16857.77 | 11882.58 | 16857.77 | 16857.77 | Simon Evason | Somervl | 24-Aug-20 | 16-Jun-22 | 24-Aug-20 | 12-Aug-20 | 12-Aug-20 | Customer |  |  | 0
637271 | INSTALLATION OF PAD MOUNTED TRANSFORMER-HUMBERWEST PKWY & EXCHANGE DR | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2020 | Pelleja, Emily | Alectra Utilities | 10-Jul-20 |  |  | 44137.03 | 39638.47 | 44137.03 | 44137.03 | Richard Cuddy | Somervl | 14-Aug-20 | 07-Sep-21 | 11-Aug-20 | 08-Sep-20 | 18-Sep-20 | Lines | COVID19 |  | 0
637344 | 58 ABBEY RD - MP TX REPLACEMENT | 805 - Sandalwood | 150285 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Aug-20 |  |  | 34836.74 | 36710.84 | 34836.74 | 34836.74 | John Costa | Somervl | 02-Sep-20 | 04-Apr-23 | 01-Sep-20 | 11-Sep-20 | 11-Sep-20 | Customer | Customer |  | 0
637345 | 2020 POLE RENEWAL GRID E3 - POLE #15 & #24 CUMBRIAN CRT, POLE #32 PARKWAY AVE | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Jul-20 |  |  | 44949.32 | 61832.65 | 44949.32 | 44949.32 | Reaburn, Jeff |  | 11-Dec-20 | 22-Nov-21 | 07-Dec-20 | 20-Nov-20 | 21-Dec-20 |  | COVID19 |  | 0
637346 | 2020 POLE RENEWAL GRID M3 - POLE #37 & #38 WARD RD, POLE #11 EDVAC DR | 805 - Sandalwood | 150284 | Inactive | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 06-Jul-20 |  |  | 39076.58 | 50730.22 | 39076.58 | 39076.58 | Reaburn, Jeff |  | 04-Dec-20 | 25-Nov-21 | 30-Nov-20 | 31-Oct-20 | 11-Dec-20 |  | COVID19 |  | 0
637371 | 2020 POLE RENEWAL - GRID M2 (1POLE) | 805 - Sandalwood | 150284 | Inactive | 99 | CANCELLED |  |  | 2020 | Agostini, Robert | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Dre Danieli |  |  | 01-Dec-20
637638 | FEEDER 14F1 CABLE REPLACEMENT | 805 - Sandalwood | 151449 | Active | 99 | COMPLETE |  |  | 2020 | Agostini, Robert | Alectra Utilities | 27-Aug-20 |  |  | 899404.06 | 922978.17 | 896368.06 | 899404.06 | Richard Cuddy | Transpw | 09-Oct-20 | 26-Jul-23 | 08-Sep-20 | 08-Sep-20 | 02-Oct-20 |  |  |  | 3,036.00
637642 | ROGERS BOND CONNECTION- 286 RUTHERFORD ROAD SOUTH | 805 - Sandalwood | 151538 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 30-Jul-20 |  |  | 808.45 | 747.14 | 808.45 | 808.45 | Brian Erskine |  | 24-Aug-20 | 31-Aug-22 | 24-Aug-20 | 11-Aug-20 | 11-Aug-20 |  |  |  | 0
637744 | 11038 The Gore Rd - RELOCATION OF UNDERGROUND SECONDARY AND DOWN GUY WIRES | 805 - Sandalwood | 150645 | Inactive | 99 | COMPLETE |  |  | 2020 | Watters, Maxwell | Alectra Utilities | 29-Jul-20 |  |  | 9721.76 | 2087.25 | 9721.76 | 9721.76 | John Costa |  | 27-Aug-20 | 29-May-23 | 24-Aug-20 | 09-Jul-20 | 09-Jul-20 |  |  |  | 0
637808 | MCLAUGHLIN RD N (WANLESS TO MAYFIELD) / BRAM / NS / 1-PH (LAYOUT) | 805 - Sandalwood | 150389 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 16-Oct-20 |  |  | 27752.82 | 22480.61 | 27752.82 | 27752.82 | Reaburn, Jeff | K-Line | 13-Nov-20 | 27-Jun-22 | 26-Oct-20 | 23-Oct-20 | 23-Oct-20 |  |  |  | 0
638532 | HULRT OMSF - ANCHOR AND GUYING RELOCATION | 805 - Sandalwood | 150474 | Inactive | 99 | COMPLETE |  |  | 2020 | Tobin, Michael | Alectra Utilities | 28-Oct-20 |  |  | 13798.37 | 25972.29 | 13798.37 | 13798.37 | Reaburn, Jeff |  | 18-Nov-20 | 27-Jan-22 | 16-Nov-20 | 30-Oct-20 | 30-Oct-20 |  |  |  | 0
638565 | TEMPORARY ANCHOR REMOVAL- MAYFIELD RD POLE#1809 | 805 - Sandalwood | 150674 | Inactive | 99 | COMPLETE |  |  | 2020 | Pelleja, Emily | Alectra Utilities | 05-Oct-20 |  |  | 6116.39 | 5677.65 | 6116.39 | 6116.39 | John Costa |  | 13-Nov-20 | 22-Sep-22 | 02-Nov-20 | 02-Nov-20 | 15-Dec-20 | Customer | Customer |  | 0
638793 | 8850 MCLAUGHLIN RD S / BRAM / UP / 3PH | 805 - Sandalwood | 150386 | Inactive | 99 | COMPLETE |  |  | 2020 | Rao, Gaurav | Alectra Utilities | 27-Nov-20 |  |  | 26661.98 | 22670.58 | 26661.98 | 26661.98 | Simon Evason |  | 04-Jan-21 | 16-Jun-22 | 21-Dec-20 | 04-Dec-20 | 04-Dec-20 |  |  |  | 0
CS 2020 | Central South Region | [7 empty] | 2020 |  | Alectra Utilities |  | 1 | 4 | 49212715.29 | 48589563.24 |  | 0 | [5 empty] | 04-Dec-17 | 31-Dec-20
236291 | Galleria Plaza - 3055 Neilco Crt | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2020 | Mandic, Goran | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 09-Nov-20
251897 | QEW - Hurontario to Mississauga | 800 - Mavis | 150673 | Active | 99 | COMPLETE |  |  | 2020 | Carter, Gordon | Alectra Utilities | 09-May-19 |  |  | 6124038.78 | 6019747.78 | 5439615.83 | 6124038.27 | Mark Bobanovic | K-Line | 13-Sep-21 | 03-Nov-23 | 21-May-19 | 28-May-19 | 27-Apr-20 | Contractor |  |  | 684,422.44
274888 | 99 Lakeshore Rd. - Waterside Condominium | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2020 | Sta. Rita, Leovigildo | Alectra Utilities | 17-Jul-20 |  |  | 0 | 267.32 |  | 0 | Macdougall, Stephen |  |  | 26-Oct-20 |  |  |  | xBy-passed | xBy-passed
328145 | 1715 Audubon Blvd - 2015 OTC (INITIAL) - AUDUBON HOME | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2020 | Penner, Mitchell | Alectra Utilities | 07-Oct-19 |  |  | 160957.19 | 152339.65 | 139418.84 | 160957.19 | Paul Tremblay | Transpw | 05-Nov-19 | 22-Sep-22 | 14-Oct-19 | 11-Oct-19 | 03-Sep-20 |  | Customer |  | 21,538.35
345893 | Ninth Line & Argentia Feeder Installation | 800 - Mavis | 151176 | Inactive | 99 | COMPLETE |  |  | 2020 | Antonakos, Tony | Alectra Utilities | 10-Jul-19 |  |  | 286989.4 | 328638.98 | 152815.12 | 286989.4 | Paul Tremblay | Somervl | 18-Nov-19 | 09-Aug-22 | 07-Oct-19 | 25-Nov-19 | 24-Jan-20 | MC/PUCC Permit | Lines |  | 134,174.28
346941 | SUMMIT EGLINTON II BLOCK 45 | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 04-Oct-19 |  |  | 246639.98 | 236189.22 | 246639.98 | 246639.98 | Paul Tremblay | Transpw | 20-Nov-19 | 21-Apr-21 | 07-Nov-19 | 09-Oct-19 | 23-Jan-20 |  | Customer |  | 0
353105 | Reid Temporary Relocation Works - Carry over from 2017 | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 | Hotham, Matthew | Alectra Utilities | 04-Dec-17 |  |  | 171908.7 | 76440.49 | 171908.7 | 171908.7 | Rob Elliot |  | 28-Feb-18 | 15-Jul-21 | 04-Dec-17 | 04-Dec-17 | 17-Sep-20 | Customer | Customer |  | 0
355944 | Parkside Village Block 9 - 4055 Parkside Village Dr. | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Sta. Rita, Leovigildo | Alectra Utilities | 01-Jan-20 |  |  | 133266.38 | 189703.07 |  | 0 | Paul Tremblay |  | 23-Jan-20 | 24-Nov-20 | 23-Jan-20 | 23-Jan-20 | 23-Jan-20 | xBy-passed | xBy-passed
359161 | 6257 Airport Rd - Element Hotel by Westin | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Sidhu, Paul | Alectra Utilities | 05-Sep-18 |  |  | 108579.97 | 138341.24 | 121137.11 | 121137.11 | Peter Costantini |  | 29-Mar-19 | 11-Dec-20 | 04-Mar-19 | 09-Nov-19 | 12-Feb-20 | Customer | Customer |  | 0
363573 | Canada Post Gateway Substation - 4567 Dixie Rd. | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Sta. Rita, Leovigildo | Alectra Utilities | 07-May-18 |  |  | 100979.49 | 61633.3 | 100979.49 | 100979.49 | Rob Elliot |  | 31-May-18 | 06-Nov-20 | 07-May-18 | 12-Sep-18 | 29-Jan-20 | Customer | Customer |  | 0
367911 | QEW Improvements from Evans Ave. to Cawthra Rd. - P1 Bridge Section | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2020 | Antonakos, Tony | Alectra Utilities |  |  |  | 0 | 0 | 6500000 | 6500000 | Rob Elliot |  |  | 16-Nov-20 | [6 empty] | 0
368606 | Church Street Overhead rebuild | 800 - Mavis | 151183 | Inactive | 99 | COMPLETE |  |  | 2020 | Antonakos, Tony | Alectra Utilities | 14-Feb-19 |  |  | 1870560.64 | 1640182.42 | 1858560.64 | 1870560.64 | Rob Elliot |  | 25-Nov-19 | 23-Jun-22 | 18-Mar-19 | 14-Mar-19 | 19-Aug-20 | MC/PUCC Permit | MC/PUCC Permit |  | 12,000.00
373940 | Madigan's Lane | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2020 | Penner, Mitchell | Alectra Utilities | 10-Dec-19 |  |  | 55866.25 | 154261.2 | 55866.25 | 55866.25 | Paul Tremblay |  | 10-Dec-18 | 08-Jun-22 | 10-Dec-18 | 21-Jan-19 | 24-Jan-20 | Customer | Customer |  | 0
374088 | Blanefield Townhomes | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 04-Oct-19 |  |  | 169019.74 | 144616.17 | 169019.74 | 169019.74 | Paul Tremblay | Transpw | 14-Jan-20 | 15-Jul-21 | 06-Jan-20 | 22-Jan-20 | 28-May-20 | Customer | Customer |  | 0
375435 | JOHN STREET SOUTH & LAKE STREET - 2018 O/H REBUILD | 800 - Mavis | 151184 | Inactive | 99 | COMPLETE |  |  | 2020 | Antonakos, Tony | Alectra Utilities | 18-Oct-19 |  |  | 285536.6 | 284025.19 | 285536.6 | 285536.6 | Paul Murphy |  | 31-Dec-19 | 01-Sep-22 | 04-Nov-19 | 25-Nov-19 | 06-Mar-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
376032 | City of Mississauga Storm Water Pump - Black Walnut / Cactus Gate | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 | Sta. Rita, Leovigildo | Alectra Utilities | 04-Dec-17 |  |  | 2735.88 | 0 | 2735.88 | 2735.88 | Antonio Mina |  | 05-Feb-18 | 17-May-21 | 05-Feb-18 | 17-Nov-20 | 18-Nov-20 | Customer | Customer |  | 0
377764 | 5320 Ninth Line - Churchill Meadows Community Centre | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Mandic, Goran | Alectra Utilities | 18-Mar-19 |  |  | 167016.42 | 161284.59 | 167016.42 | 167016.42 | Peter Costantini |  | 02-May-19 | 04-Mar-21 | 01-Apr-19 | 19-Mar-19 | 27-Aug-20 | Customer | Customer |  | 0
379989 | Atwater Pole Replacement - Sie | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2020 | Lacombe, Joel | Alectra Utilities |  |  |  | 0 | 1617.86 | 40000 | 40000 | Antonakos, Tony |  |  | 02-Mar-20 | [6 empty] | 0
380322 | SIGSBEE 1/0 CABLE REPLACEMENT | 800 - Mavis | 151401 | Inactive | 99 | COMPLETE |  |  | 2020 | Lucic, Marko | Alectra Utilities | 12-Aug-19 |  |  | 891979.83 | 909458.67 | 598018.03 | 891979.83 | Paul Tremblay | Transpw | 20-Dec-19 | 21-Apr-22 | 23-Sep-19 | 11-Nov-19 | 03-Mar-20 | Contractor | Contractor |  | 293,961.80
382619 | Southdown - ROW to Lakeshore | 800 - Mavis | 151426 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Rob Elliot |  |  | 19-Apr-21
387516 | MTO Project - 401 West Expansion | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities | 02-Dec-19 |  |  | 1005093.26 | 1108824.65 | 919661.17 | 1107864.86 | Mark Bobanovic | K-Line | 16-Mar-20 | 18-Jul-23 | 03-Jan-20 | 18-Jan-20 | 27-Apr-20 | Customer | Customer |  | 188,203.69
389731 | 2475 Hurontario St - 6 Storey Building | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 08-Jun-20 |  |  | 293061.16 | 250696.01 | 293061.16 | 293061.16 | Peter Costantini |  |  | 26-Feb-21 |  | 01-Jul-20 | 11-Sep-20 | xBy-passed | xBy-passed |  | 0
390248 | WOODCHUCK LANE OH REBUILD | 800 - Mavis | 150495 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | ($54.86) |  | 0 | Weaver, Thomas |  |  | 14-Feb-22
391005 | 4572 Tomken Rd. - Dezen Tomken Plaza | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Sidhu, Paul | Alectra Utilities | 04-Sep-18 |  |  | 87315.88 | 136362.53 | 87315.88 | 87315.88 | Macdougall, Stephen |  | 19-Mar-19 | 01-Dec-20 | 04-Mar-19 | 02-Oct-19 | 04-Mar-20 | Customer | Customer |  | 0
391021 | 4699 Glen Erin Dr. - Mills Square Bldg D | 800 - Mavis | 150384 | Active | 99 | COMPLETE |  |  | 2020 | Sidhu, Paul | Alectra Utilities | 02-Oct-18 |  |  | 251006.52 | 261374.04 | 251006.52 | 251006.52 | Macdougall, Stephen |  | 18-Dec-18 | 24-Aug-23 | 13-Nov-18 | 15-Nov-18 | 20-Jan-20 |  | Customer |  | 0
392884 | 1775 Fifeshire Crt. - Region of Peel Fifeshire Sewage Pumping Station | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Sta. Rita, Leovigildo | Alectra Utilities |  |  |  | 25925.47 | 40558.22 | 25925.47 | 25925.47 | Macdougall, Stephen |  | 05-Jun-20 | 05-Nov-20 | 01-Jun-20 | 07-May-20 | 08-May-20 |  |  |  | 0
393895 | M-CITY TEMPORARY 2MVA SERVICE - 475 WEBB DRIVE - TEMP SERV | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 | Braletic, Bob | Alectra Utilities | 29-May-18 |  |  | 141735.8 | 90333.27 | 141735.8 | 141735.8 | Peter Costantini |  | 01-Aug-18 | 22-Sep-22 | 29-Jun-18 | 14-May-18 | 03-Aug-20 |  |  |  | 0
394097 | Chinguacousy Road Widening - W | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 10-Dec-20
394100 | TORBRAM ROAD WIDENING - QUEEN | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | ($83.46) |  | 0 | Weaver, Thomas |  |  | 24-Aug-20
394126 | STUB POLE TEMPORARY REMOVAL - | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | ($10.54) |  | 0 | Weaver, Thomas |  |  | 24-Aug-20
395401 | MISSISSAUGA SQUARE 2MVA SERVI | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 30-May-19 |  |  | 81669.79 | 82340.74 | 81669.79 | 81669.79 | Macdougall, Stephen |  | 29-Jul-19 | 30-Nov-20 | 15-Jul-19 | 19-Sep-19 | 07-May-20 | Customer | Customer |  | 0
395583 | 8 Nahani Way, Mississauga U/G | 800 - Mavis | 150652 | Active | 98 | COMPLETE |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities | 22-May-18 |  |  | 284693.48 | 288345.78 | 284693.48 | 284693.48 | Peter Costantini |  | 06-Jul-18 | 08-Aug-23 | 25-Jun-18 | 23-Jul-18 | 24-Aug-20 | Customer | Customer |  | 0
396201 | GO ELEC. - LWL - CONFLICT #LW21 - CAWTHRA ROAD | 800 - Mavis | 150594 | Inactive | 99 | COMPLETE | High | MLinx | 2020 | Tobin, Michael | Alectra Utilities | 13-Jul-20 |  |  | 2822879.77 | 3099985.82 | 2252430.2 | 2822879.77 | Rob Elliot | Transpw | 04-Jan-21 | 14-Oct-21 | 17-Aug-20 | 15-Jul-20 | 05-Nov-20 |  |  |  | 570,449.57
396228 | GO ELEC. - LWL - CONFLICT #LW23 - HURONTARIO ST. | 800 - Mavis | 150594 | Inactive | 99 | COMPLETE | High | MLinx | 2020 | Tobin, Michael | Alectra Utilities | 30-Sep-19 |  |  | 4564622.94 | 4452064.22 | 2408889.69 | 4564642.94 | Rob Elliot | Transpw | 02-Jul-20 | 13-Mar-22 | 02-Dec-19 | 23-Oct-19 | 17-Jul-20 |  | Contractor |  | 2,155,753.25
396439 | RER MX - KT CONFLICT #KT911 - MALTON GO CROSSING: EAST OF MALTON STATION 1 | 800 - Mavis | 150593 | Inactive | 99 | COMPLETE |  |  | 2020 | Tobin, Michael | Alectra Utilities | 23-Jul-20 |  |  | 47729.79 | 28946.53 | 42162.95 | 47729.79 | Rob Elliot |  | 28-Jul-20 | 21-Apr-21 | 23-Jul-20 | 23-Jul-20 | 23-Jul-20 |  |  |  | 5,566.84
397669 | MTO QEW Project- Mississauga R | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities | 30-Sep-19 |  |  | 50865.77 | 39561.68 | 50865.77 | 50865.77 | Rob Elliot |  |  | 22-Dec-20 |  | 13-Sep-19 | 27-Apr-20 | xBy-passed | xBy-passed |  | 0
398696 | 3045 Mavis Rd - Bldg C&D | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 04-Dec-17 |  |  | 49222.14 | 54840.66 | 40021.2 | 49222.14 | Macdougall, Stephen |  | 13-Jun-18 | 28-Jan-21 | 11-Jun-18 | 25-Jun-18 | 29-Jan-20 | Customer | Customer |  | 9,200.94
398733 | Clark Blvd - Road widening | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | ($89.17) |  | 0 | Weaver, Thomas |  |  | 24-Aug-20
402579 | 2210 & 2230 BROMSGROVE RD -Southdown Towns | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Sta. Rita, Leovigildo | Alectra Utilities | 07-Mar-19 |  |  | 109573.04 | 100669.47 | 109573.04 | 109573.04 | Macdougall, Stephen | Somervl | 14-May-19 | 03-Mar-21 | 01-May-19 | 14-Aug-19 | 01-May-20 | Customer | Customer |  | 0
402675 | 1996 LUSHES AVE - TOWNHOMES | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 02-Sep-20 |  |  | 112684.99 | 116298.86 | 112684.99 | 112684.99 | Paul Tremblay | Transpw | 22-Sep-20 | 19-Apr-21 | 08-Sep-20 | 15-Sep-20 | 22-Sep-20 | Customer |  |  | 0
404005 | SOUTHDOWN AND QEW POLE REPLACE | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2020 | Bobanovic, Mark | Alectra Utilities | 03-Apr-19 |  |  | 120146.77 | 165414.64 | 120146.77 | 120146.77 | Paul Murphy |  | 09-Apr-19 | 23-Jun-22 | 07-May-18 | 07-May-18 | 03-Feb-20 | Customer | Customer |  | 0
405121 | MTO PROJECT - 401 WEST & DERRY | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | ($39.20) |  | 0 | Weaver, Thomas |  |  | 24-Aug-20
405235 | 6825 MARITZ DRIVE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 10-Jul-18 |  |  | 87455.9 | 105900.01 | 87455.9 | 87455.9 | Macdougall, Stephen |  | 24-Aug-18 | 03-Mar-21 | 13-Aug-18 | 23-Dec-19 | 30-Jan-20 | Customer | Customer |  | 0
406596 | 3560 ODYSSEY DRIVE "BUILDING H | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Mandic, Goran | Alectra Utilities | 15-Aug-19 |  |  | 108524.08 | 76788.74 | 108524.08 | 108524.08 | Macdougall, Stephen | Somervl | 11-Nov-19 | 05-Mar-21 | 21-Oct-19 | 27-Sep-19 | 14-May-20 |  | Customer |  | 0
406609 | 3580 ODYSSEY DRIVE "BUILDING G | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 15-Aug-19 |  |  | 124179.32 | 94032.44 | 124179.32 | 124179.32 | Macdougall, Stephen | Somervl | 11-Nov-19 | 26-Feb-21 | 28-Oct-19 | 27-Sep-19 | 19-Feb-20 |  | Customer |  | 0
406617 | 3610 ODYSSEY DRIVE "BUILDING F | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 15-Aug-19 |  |  | 99576.06 | 71135.05 | 99576.06 | 99576.06 | Macdougall, Stephen | Somervl | 08-Oct-19 | 01-Mar-21 | 23-Sep-19 | 27-Sep-19 | 20-Jan-20 | Customer | Customer |  | 0
406625 | 3630 ODYSSEY DRIVE "BUILDING E | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 15-Aug-19 |  |  | 102621.43 | 68893.87 | 102621.43 | 102621.43 | Macdougall, Stephen | Somervl | 15-Oct-19 | 03-Mar-21 | 29-Sep-19 | 27-Sep-19 | 20-Jan-20 |  | Customer |  | 0
406941 | 2020 - WEBB M.S. EGRESS | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2020 | Antonakos, Tony | Alectra Utilities |  |  |  | 0 | 3033.13 |  | 0 | Weaver, Thomas |  |  | 19-Apr-21
407880 | 2021 44KV YORK-MEADOWPINE LOOP | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2020 | Antonakos, Tony | Alectra Utilities |  |  |  | 0 | ($39.24) |  | 0 | Weaver, Thomas |  |  | 19-Apr-21
408073 | 3320 ELMBANK RD - PARK N FLY 400A SERVICE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 08-Jul-19 |  |  | 105477.03 | 110977.03 | 105477.03 | 105477.03 | Macdougall, Stephen | Somervl | 28-Aug-19 | 12-Mar-21 | 05-Aug-19 | 01-Aug-19 | 21-Jan-20 |  | Customer |  | 0
408911 | 2023 - WALDEN CIRCLE VOLTAGE C | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2020 | Antonakos, Tony | Alectra Utilities |  |  |  | 0 | ($33.51) |  | 0 | Weaver, Thomas |  |  | 19-Nov-20
409720 | 2019 - SHAWSON MS EGRESS (FEED | 800 - Mavis | 150699 | Inactive | 99 | CANCELLED |  |  | 2020 | Antonakos, Tony | Alectra Utilities |  |  |  | 0 | 1622.03 |  | 0 | Paul Tremblay |  |  | 02-Jul-21
412048 | 6020 WINSTON CHURCHILL -DAYCAR | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2020 | Braletic, Bob | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Macdougall, Stephen |  |  | 05-Jan-22
413008 | 5809 SHAWSON DRIVE - TEMP SERV | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 04-Sep-18 |  |  | 20006.63 | 7499.63 | 20006.63 | 20006.63 | Bourgeois, Craig |  | 05-Oct-18 | 15-Jun-23 | 01-Oct-18 | 13-Sep-18 | 24-Feb-20 |  | Customer |  | 0
413163 | CYNARA RD. AND IRMA RD. - CABLE REPLACEMENT | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2020 | Antonakos, Tony | Alectra Utilities | 29-Jan-20 |  |  | 97054.41 | 104577.25 | 97054.41 | 97054.41 | Paul Tremblay | Somervl | 13-Mar-20 | 18-May-22 | 09-Mar-20 | 02-Mar-20 | 13-Mar-20 |  |  |  | 0
413876 | 2095&2105 MATHESON BLVD E - HOPEWELL FLEX OFFICE BUILDING | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | MacDougall, Stephen | Alectra Utilities | 20-Feb-20 |  |  | 349110.39 | 355233.08 | 349110.39 | 349110.39 | Peter Costantini | Somervl | 12-May-20 | 10-Jun-21 | 23-Mar-20 | 14-Mar-20 | 30-Oct-20 |  | Customer |  | 0
414140 | 3 QUEEN ST SOUTH, MISSISSAUGA, | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 17-Jul-20 |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 14-Mar-19 |  |  |  | xBy-passed | xBy-passed
415169 | POLE REPLACEMENT - BATCH #7 (4 POLES) | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2020 | Antonakos, Tony | Alectra Utilities | 12-Feb-19 |  |  | 80865.05 | 67626.97 | 80865.05 | 80865.05 | Rob Elliot |  | 23-Aug-19 | 08-Jun-22 | 01-May-19 | 20-Jan-20 | 13-Feb-20 | Filler | Filler |  | 0
415388 | MCVEAN DRIVE WIDENING - CASTLE | 800 - Mavis | 150673 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 18.99 | 0 | 18.99 | 18.99 | Weaver, Thomas |  |  | 24-May-22 | [6 empty] | 0
415425 | 5320 NINTH LINE - TEMP SERV | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 | Carter, Gordon | Alectra Utilities | 27-Sep-18 |  |  | 17315.15 | 11425.86 | 17315.15 | 17315.15 | Peter Costantini |  | 26-Oct-18 | 21-Jun-21 | 24-Oct-18 | 15-Nov-18 | 07-Sep-20 | Customer | Customer |  | 0
415724 | POLE REPLACEMENT - BATCH #10 (11 POLES) | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2020 | Antonakos, Tony | Alectra Utilities | 07-May-19 |  |  | 373775.82 | 342953.48 | 373775.82 | 373775.82 | Rob Elliot |  | 02-Oct-19 | 18-Nov-22 | 24-Jun-19 | 16-Dec-19 | 17-Dec-20 | Filler | Control/SCADA |  | 0
416268 | 170 Pinewood - Pole Reloc | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 24-Feb-20 |  |  | 37852.38 | 37015.29 | 37852.38 | 37852.38 | Paul Murphy |  | 09-Mar-20 | 09-Jun-21 | 02-Mar-20 | 16-Mar-20 | 17-Mar-20 | Customer | Customer |  | 0
416356 | 2300 HOGAN DRIVE - KUEHNE + NAGEL TX REPLACEMENT | 800 - Mavis | 150384 | Active | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 01-Jan-20 |  |  | 0 | 36726.45 |  | 0 | Macdougall, Stephen |  |  | 26-Jul-23 |  | 01-Jan-20 | 01-Jan-20 | xBy-passed | xBy-passed
416487 | 1610 KENMUIR | 800 - Mavis | 151063 | Inactive | 99 | CANCELLED |  |  | 2020 | Kafel, Krzysztof | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 27-Sep-18
418183 | RATHBURN RD W CABLE REPLACEMENT | 800 - Mavis | 151144 | Inactive | 99 | COMPLETE |  |  | 2020 | Lucic, Marko | Alectra Utilities | 22-Jul-19 |  |  | 2834889.75 | 3146031.9 | 2510648.07 | 2834889.75 | Paul Tremblay | Transpw | 20-Dec-19 | 09-Aug-22 | 05-Aug-19 | 15-Aug-19 | 16-Jul-20 | Contractor | Contractor |  | 324,241.68
418554 | BURNHAMTHORPE & CENTRAL P - VAN HORNE OUTDOOR BILLBOARD | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 17-Jul-20 |  |  | 0 | 0 |  | 0 | Peter Costantini |  |  | 05-Dec-18 |  |  |  | xBy-passed | xBy-passed
418781 | 6050 Millcreek Dr. - ORLANDO MILLCREEK BLDG | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 04-Feb-19 |  |  | 128858.71 | 127112.95 | 128858.71 | 128858.71 | Macdougall, Stephen |  | 26-Jun-19 | 18-Mar-21 | 20-May-19 | 14-Mar-19 | 08-Jun-20 |  | Customer |  | 0
419661 | 1940 CRESTVIEW TOWN HOMES | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 10-Dec-19 |  |  | 191905.6 | 192633.89 | 191905.6 | 191905.6 | Paul Tremblay | Transpw | 25-Feb-20 | 16-Apr-21 | 17-Feb-20 | 13-Jan-20 | 05-Oct-20 | Customer | Customer |  | 0
419670 | 25 CAPSTON ROAD - PEEL CHILDRE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 10-Dec-18 |  |  | 9904.58 | 149586.29 | 121071.45 | 130976.03 | Macdougall, Stephen |  | 29-Jan-19 | 03-Mar-21 | 07-Jan-19 | 07-Mar-19 | 22-Jan-20 | Customer | Customer |  | 9,904.58
420646 | 3110 Convair Dr - TEMP SERV | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 07-Feb-19 |  |  | 14937.45 | 11582.35 | 14937.45 | 14937.45 | Rob Elliot |  | 28-Feb-19 | 29-Nov-21 | 25-Feb-19 | 08-Mar-19 | 16-Jan-20 | Customer | Customer |  | 0
421139 | HOLBURNE SINGLE PHASE OH REBUI | 800 - Mavis | 151399 | Inactive | 99 | COMPLETE |  |  | 2020 | Carter, Gordon | Alectra Utilities | 01-Oct-19 |  |  | 495015.27 | 598931.55 | 495015.27 | 495015.27 | Paul Murphy |  | 02-Jun-20 | 08-Jun-22 | 06-Jan-20 | 02-Mar-20 | 22-Dec-20 | Locates | Lines |  | 0
422351 | 5250 SOLAR DRIVE - WAREHOUSE D | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 05-Aug-20 |  |  | 194500.33 | 170353.87 | 189482.81 | 194500.33 | Peter Costantini |  | 14-Oct-20 | 15-Mar-21 | 02-Sep-20 | 17-Aug-20 | 20-Nov-20 | Customer | Customer |  | 5,017.52
422810 | TANU CONDOS - TEMPORARY POLE L | 800 - Mavis | 150675 | Active | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 11-Oct-19 |  |  | 632819.2 | 420441.63 | 632819 | 632819 | Mark Bobanovic | A&W | 08-Jan-20 | 26-Jul-23 | 15-Oct-19 | 07-Oct-19 | 02-Jan-20 |  |  |  | 0
423986 | 3045 MAVIS ROAD - MIXED USE RE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 25-Feb-19 |  |  | 73528.24 | 90898.31 | 73528.24 | 73528.24 | Peter Costantini |  | 19-Oct-20 | 22-Sep-22 | 21-Sep-20 | 20-Oct-20 | 17-Dec-20 | Customer | Customer |  | 0
424031 | POLE REPLACEMENT - EGLINTON AV E & 403 | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2020 | Antonakos, Tony | Alectra Utilities | 01-Dec-19 |  |  | 0 | 428786 |  | 0 | Weaver, Thomas |  |  | 20-Jul-20 |  | 01-Apr-20 | 01-Aug-20 | xBy-passed | xBy-passed
424111 | THE WAY TOWNS-2277 SOUTH MILLW | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Sidhu, Paul | Alectra Utilities | 23-Sep-20 |  |  | 116106.68 | 78960.57 | 116106.68 | 116106.68 | Peter Costantini | Somervl | 01-Dec-20 | 18-Mar-21 | 26-Oct-20 | 25-Sep-20 | 08-Oct-20 |  |  |  | 0
425439 | ORLANDO 6065 MILLCREEK INDUSTR | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Mandic, Goran | Alectra Utilities | 09-Aug-19 |  |  | 115924.38 | 105954.4 | 115924.38 | 115924.38 | Macdougall, Stephen |  | 15-Oct-19 | 18-Mar-21 | 16-Sep-19 | 28-Oct-19 | 11-May-20 | Customer | Customer |  | 0
425463 | 1796 MATTAWA AVE | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2020 | Mandic, Goran | Alectra Utilities | 18-Mar-19 |  |  | 35993.34 | 0 | 29150.26 | 29150.26 | Macdougall, Stephen |  | 23-Apr-19 | 09-Apr-21 | 01-Apr-19 |  |  |  | Customer |  | 0
425640 | 350 MADILL BLVD - INDUSTRIAL SPEC. BLDG | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 11-Mar-19 |  |  | 107344.81 | 105538.05 | 107344.81 | 107344.81 | Peter Costantini | Somervl | 15-Oct-19 | 22-Sep-22 | 16-Sep-19 | 15-Nov-19 | 04-Feb-20 | Customer | Customer |  | 0
425720 | ORLANDO 6135 MILLCREEK INDUSTRIAL BLDG | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 30-Aug-19 |  |  | 0 | 126070.78 |  | 0 | Macdougall, Stephen |  | 22-Oct-19 | 12-Feb-21 | 14-Oct-19 | 09-Dec-19 | 05-Aug-20 | Customer | Customer
425754 | ROGERS MAKE READY - OLD MALTON VILLAGE - HULL & STUDLEY (MP18-0332) | 800 - Mavis | ROGERS | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 15-May-19 |  |  | 31206.08 | 11845.72 | 31206.08 | 31206.08 | Mark Bobanovic |  | 31-May-19 | 20-Dec-21 | 27-May-19 | 29-Jun-20 | 29-Jun-20 | Locates | Locates |  | 0
426159 | MTO CONT. NO. 2019-2014, HWY 4 | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Mandic, Goran | Alectra Utilities | 21-Jan-20 |  |  | 137926.88 | 75696.69 | 137926.88 | 137926.88 | Macdougall, Stephen |  | 19-May-20 | 18-Feb-22 | 24-Feb-20 | 05-Feb-20 | 07-May-20 |  |  |  | 0
426255 | 1850 MATHESON BLVD - ADDTIONAL | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 26-Mar-19 |  |  | 203195.34 | 200343.52 | 197827 | 203195.37 | Macdougall, Stephen |  | 12-Jul-19 | 16-Mar-21 | 03-Jun-19 | 03-Jun-19 | 06-Jan-20 |  | Customer |  | 5,368.37
426677 | OPP MODERNIZATION PH2 PROJECT | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | MacDougall, Stephen | Alectra Utilities | 17-Jan-20 |  |  | 209806.09 | 195471.37 | 209806.09 | 209806.09 | Macdougall, Stephen | Somervl | 21-Feb-20 | 23-Dec-20 | 27-Jan-20 | 23-Jan-20 | 30-Apr-20 |  | Customer |  | 0
426749 | VAN HORNE OUTDOOR BILLBOARD-CP | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 05-Feb-20 |  |  | 20232.62 | 15003.5 | 20232.62 | 20232.62 | Peter Costantini | Somervl | 12-Mar-20 | 22-Feb-21 | 10-Mar-20 | 11-Feb-20 | 11-Feb-20 |  |  |  | 0
426757 | KIPPER AVE OH REBUILD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2019 | Carter, Gordon | Alectra Utilities | 08-Jul-19 |  |  | 144062.2 | 126300.06 | 144062.2 | 144062.2 | Paul Murphy |  | 31-Dec-19 | 09-Aug-22 | 14-Oct-19 | 25-Oct-19 | 31-Dec-19 | Locates |  |  | 0
426888 | ROGERS MAKE READY - 2209 STANFIELD RD | 800 - Mavis | ROGERS | Inactive | 99 | CANCELLED |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 23-Jul-19 |  |  | 0 | 647.28 |  | 0 | Weaver, Thomas |  |  | 01-Feb-21
427151 | HEARTLAND CHURCH / 1100 CANADI | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Mandic, Goran | Alectra Utilities | 25-May-20 |  |  | 129753.9 | 106747.74 | 129753.9 | 129753.9 | Macdougall, Stephen | Somervl | 23-Jul-20 | 10-Dec-20 | 24-Jun-20 | 23-Jun-20 | 15-Jul-20 | Customer |  |  | 0
427784 | 4655 METCALFE AVE - ERIN SQUAR | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2020 | Mandic, Goran | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Weaver, Thomas |  |  | 29-Apr-19
428357 | TROPHY FOODS 3MVA UPGRADE | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE | High | Comm | 2020 | Mandic, Goran | Alectra Utilities | 25-Feb-20 |  |  | 80165.86 | 71556.89 | 80165.86 | 80165.86 | Macdougall, Stephen |  | 11-Jun-20 | 22-Feb-21 | 08-Jun-20 | 23-May-20 | 23-May-20 |  |  |  | 0
428390 | Rathburn Rd UG Rebuild - Phase 2 | 800 - Mavis | 151144 | Inactive | 99 | COMPLETE |  |  | 2020 | Lucic, Marko | Alectra Utilities | 25-Aug-19 |  |  | 761764.5 | 774214.55 | 727435.7 | 761764.5 | Paul Tremblay | Transpw | 21-Nov-19 | 09-Aug-22 | 10-Nov-19 | 16-Sep-19 | 11-Sep-20 |  | Contractor |  | 34,328.80
428613 | DESIGN HOME GIFT AND PAPER INC | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 24-Dec-19 |  |  | 89928.8 | 77702.29 | 89928.8 | 89928.8 | Paul Murphy |  | 17-Mar-20 | 26-Feb-21 | 02-Mar-20 | 10-Jan-20 | 01-Feb-20 |  |  |  | 0
428744 | STUB POLE RELOCATION FOR JOHN STREET EXPANSION | 800 - Mavis | 150594 | Inactive | 99 | COMPLETE |  |  | 2020 | Tobin, Michael | Alectra Utilities | 19-Aug-19 |  |  | 26170.68 | 17487.97 | 15719.2 | 25981.26 | Rob Elliot |  | 03-Oct-19 | 20-Aug-21 | 30-Sep-19 | 26-Sep-19 | 12-Mar-20 |  | MC/PUCC Permit |  | 10,262.06
428824 | 6685 CENTURY AVE - MOVATI FITNESS TEMP SERV | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 21-May-19 |  |  | 13828.74 | 14220.62 | 13828.74 | 13828.74 | Bourgeois, Craig |  | 18-Jun-19 | 22-Dec-20 | 17-Jun-19 | 18-Aug-19 | 03-Feb-20 | Customer | Customer |  | 0
429851 | FEEDER REPLACEMENT - L3359 TO L3321 - FAIRVIEW AND HURONTARIO | 800 - Mavis | 151107 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 20-Jul-20 |  |  | 655889.83 | 720052.35 | 647984.31 | 655889.83 | Paul Tremblay | Transpw | 10-Aug-20 | 21-Apr-22 | 27-Jul-20 | 19-Nov-20 | 18-Dec-20 | MC/PUCC Permit | MC/PUCC Permit |  | 7,905.52
429886 | BEEDIE PROPOSED WAREHOUSE FACILITY | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2020 | MacDougall, Stephen | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 10-Dec-20
429907 | 7481 Torbram Rd | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 24-Jul-19 |  |  | 33819.66 | 32509.15 | 33819.66 | 33819.66 | Macdougall, Stephen |  | 30-Aug-19 | 23-Feb-21 | 26-Aug-19 | 13-Mar-20 | 19-Mar-20 | Customer | Customer |  | 0
429940 | 270 LAKESHORE ROAD WEST - THE SHORES OF PORT CREDIT RETIREMENT HOMES | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 03-Sep-20 |  |  | 198696.58 | 205431.35 | 198696.58 | 198696.58 | Peter Costantini | Somervl | 27-Oct-20 | 10-Jun-21 | 29-Sep-20 | 10-Sep-20 | 15-Oct-20 |  |  |  | 0
430262 | VICTORIA STREET HOLDINGS | 800 - Mavis | 150652 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 11-May-20 |  |  | 122168.9 | 96920.89 | 122168.9 | 122168.9 | Paul Tremblay | Transpw | 23-Jun-20 | 26-Apr-21 | 08-Jun-20 | 22-May-20 | 18-Jun-20 |  |  |  | 0
430414 | CABLE REPLACEMENT - TX10375-W TO TX12371-W - FOLKWAY DR. | 800 - Mavis | 151146 | Inactive | 99 | COMPLETE |  |  | 2020 | Lucic, Marko | Alectra Utilities | 03-Feb-20 |  |  | 135143.96 | 114037.42 | 135143.96 | 135143.96 | Glenn Guile | Somervl | 18-Mar-20 | 15-Jul-21 | 12-Mar-20 | 05-Jun-20 | 16-Jun-20 | COVID19 | COVID19 |  | 0
430457 | Phase 3-Rathburn Rd W UG Cable Replacement | 800 - Mavis | 151144 | Inactive | 99 | COMPLETE |  |  | 2020 | Lucic, Marko | Alectra Utilities | 10-Feb-20 |  |  | 3650805.45 | 3615968.46 | 3584882.96 | 3650805.45 | Paul Tremblay | Transpw | 21-Aug-20 | 03-Jan-23 | 02-Mar-20 | 25-Oct-19 | 11-Sep-20 |  | Weather |  | 65,922.49
430537 | POLE RELOCATION - 588 CURZON AVE | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 25-Feb-20 |  |  | 21127.11 | 18829.16 | 21127.11 | 21127.11 | Rob Elliot |  | 10-Mar-20 | 24-Feb-21 | 02-Mar-20 | 04-Mar-20 | 19-Mar-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
631303 | UG CABLE REPLACEMENT - 71F3 | 800 - Mavis | 151107 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 24-Aug-20 |  |  | 1377469.38 | 1228537.5 | 1057400.3 | 1377469.38 | Paul Tremblay | Transpw | 17-Dec-20 | 11-Nov-21 | 14-Sep-20 | 02-Oct-20 | 16-Dec-20 | MC/PUCC Permit |  |  | 320,069.08
631304 | BOUGH BEECHES UG REBUILD - More info needed | 800 - Mavis | 151145 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Beaudrie, Scott | Alectra Utilities | 19-Jun-20 |  |  | 972419.3 | 928789.33 | 972419.3 | 972419.3 | Paul Tremblay | Transpw | 19-Oct-20 | 11-Nov-21 | 20-Jul-20 | 30-Jul-20 | 02-Oct-20 | MC/PUCC Permit |  |  | 0
631305 | 2020 UG REBUILD - FOLKWAY DRIVE | 800 - Mavis | 151146 | Active | 99 | COMPLETE | High | Reliab | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 3285570.1 | 3285484.68 | 3159684.07 | 3285570.1 | Paul Tremblay | Transpw | 13-Nov-20 | 26-Jul-23 | 01-Jun-20 | 15-Jun-20 | 20-Nov-20 | MC/PUCC Permit | MC/PUCC Permit |  | 125,886.03
631663 | Cogeco Middle Gate Pole Replacement | 800 - Mavis | Tedlo, Orwell, Middlegate | Active | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 18-Jul-19 |  |  | 24915.88 | 0 | 24915.88 | 24915.88 | K-Line Construction |  | 19-Aug-19 | 26-Jul-23 | 19-Aug-19 | 01-Jul-20 | 01-Jul-20 | Customer | Customer |  | 0
632210 | Inglewood Drive - Joint Use Permit | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 5749.52 | 3896.34 | 5749.52 | 5749.52 | Macdougall, Stephen |  | 27-Jul-20 | 15-Mar-21 | 27-Jul-20 | 09-Sep-20 | 09-Sep-20 | Lines | Lines |  | 0
632259 | UG Rebuld - Shelter Bay Road Area | 800 - Mavis | 151143 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 15-Jun-20 |  |  | 2075294.17 | 1746745.46 | 2049512.69 | 2075294.17 | Paul Tremblay | Transpw | 09-Dec-20 | 15-Aug-21 | 14-Jul-20 | 10-Aug-20 | 07-Oct-20 | MC/PUCC Permit |  |  | 25,781.48
632358 | Parkside Village Phase 3 | 800 - Mavis | 150652 | Active | 98 | COMPLETE |  |  | 2020 | Gamboa, Henry | Alectra Utilities | 16-Jan-20 |  |  | 212424.18 | 206281.1 | 212424.18 | 212424.18 | Mark Bobanovic | Transpw | 24-Feb-20 | 26-Jul-23 | 24-Feb-20 | 27-Apr-20 | 17-Aug-20 | Customer | Customer |  | 0
632392 | Britannie Rd and Brookhaven Way - Joint Use Permit | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 08-Jun-20 |  |  | 4127.59 | 8052.65 | 4127.59 | 4127.59 | Macdougall, Stephen |  | 28-Jul-20 | 22-Aug-22 | 28-Jul-20 | 16-Sep-20 | 16-Sep-20 | Lines | Lines |  | 0
632779 | 600 Arbor Rd - Bell Make Ready | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 16-Sep-19 |  |  | 5156.14 | 12878.43 | 5156.14 | 5156.14 | Macdougall, Stephen |  | 22-Oct-19 | 22-Sep-22 | 21-Oct-19 | 21-Sep-20 | 21-Sep-20 | Customer | Customer |  | 0
632842 | 550 Courtneypark Dr W - Switchgear Removal | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 17-Dec-19 | 1 | 1 | 104729.2 | 165242.2 | 104729.2 | 104729.2 | Glenn Guile | Somervl | 18-Feb-20 | 22-Sep-22 | 27-Jan-20 | 11-Feb-20 | 10-Mar-20 | Contractor | Customer |  | 0
632880 | Pole Relocation - Eglinton and Burgoyne | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 20-Jul-20 |  |  | 80792.42 | 65751.14 | 80792.42 | 80792.42 | Macdougall, Stephen |  | 21-Aug-20 | 13-Oct-22 | 20-Jul-20 | 21-Aug-20 | 21-Aug-20 | Lines |  |  | 0
633249 | TRANSFORMER UPGRADE - 345 SUPERIOR BLVD | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 02-Dec-19 |  |  | 60862.76 | 57358.89 | 60862.76 | 60862.76 | Macdougall, Stephen |  | 08-Jan-20 | 02-Nov-20 | 02-Jan-20 | 02-Jan-20 | 15-Jan-20 |  | Lines |  | 0
633452 | Erin Square Temporary 600A Service | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 30-Sep-19 |  |  | 50373.43 | 50021.08 | 50373.43 | 50373.43 | Macdougall, Stephen |  | 19-Nov-19 | 25-Nov-21 | 01-Nov-19 | 29-Nov-19 | 08-Jun-20 | Customer | Customer |  | 0
633483 | 2565 Rena Road | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 21-Sep-20 |  |  | 150048.2 | 122103.8 | 150048.2 | 150048.2 | Peter Costantini | Somervl | 26-Oct-20 | 03-Mar-21 | 12-Oct-20 | 06-Oct-20 | 10-Nov-20 |  | Customer |  | 0
633602 | Elm Dr - Guying Relocation | 800 - Mavis |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 27-Sep-19
633618 | 3 Storey Medical Office | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | MacDougall, Stephen | Alectra Utilities | 29-Jun-20 |  |  | 43701.86 | 56267.41 | 43701.86 | 43701.86 | Peter Costantini |  | 14-Aug-20 | 01-Mar-21 | 03-Aug-20 | 03-Jul-20 | 24-Aug-20 |  | Customer |  | 0
633637 | 425 Lakeshore Blvd - Guying Relocation | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 23-Jan-20 |  |  | 19357.44 | 16039.04 | 19357.44 | 19357.44 | Paul Murphy |  | 04-Mar-20 | 01-Jun-21 | 28-Feb-20 | 11-Feb-20 | 12-Feb-20 |  |  |  | 0
633727 | Arbor Rd - Joint Use Permit | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 08-Jun-20 |  |  | 10887.38 | 5956.77 | 10887.38 | 10887.38 | Macdougall, Stephen |  | 30-Jul-20 | 05-Jul-22 | 29-Jul-20 | 26-Aug-20 | 26-Aug-20 | Lines | Lines |  | 0
633792 | GREYPAN DIXIE EGLINTON | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 04-Feb-20 |  |  | 124013.82 | 144465.12 | 124013.82 | 124013.82 | Macdougall, Stephen | Somervl | 16-Mar-20 | 09-Mar-21 | 21-Feb-20 | 10-Mar-20 | 27-Mar-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
633793 | OH Transformer Replacements - Part 1 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 28-Feb-20 |  |  | 126530.83 | 121216.02 | 126530.83 | 126530.83 | Paul Murphy |  | 05-May-20 | 11-Nov-21 | 04-May-20 | 14-Oct-20 | 27-Oct-20 | COVID19 | COVID19 |  | 0
633865 | 2020 POLE REPLACEMENT BATCH 2 | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Oct-20 |  |  | 391915.11 | 352447.59 | 391915.11 | 391915.11 | Macdougall, Stephen |  | 23-Feb-21 | 05-Jan-22 | 12-Oct-20 | 12-Oct-20 | 17-Dec-20 | Lines | Lines |  | 0
633972 | 2020 Tx replacements batch 1 - 11 units | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 07-Jan-20 |  |  | 147870.58 | 203238.45 | 147870.58 | 147870.58 | Paul Tremblay |  | 12-Feb-20 | 06-Jul-21 | 15-Jan-20 | 20-Jan-20 | 28-Oct-20 | Filler | Filler |  | 0
633973 | 2020 tx replacements Batch 1 - 9 units | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-May-20 |  |  | 207948.94 | 179776.38 | 189945.88 | 207948.94 | Paul Tremblay |  | 30-Jun-20 | 08-Jun-22 | 22-Jun-20 | 06-Jul-20 | 31-Dec-20 | Filler | Filler |  | 18,003.06
633974 | 2020 tx replacements batch 3 - 11 units | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 07-Jan-20 |  |  | 101188.76 | 78110.55 | 101188.76 | 101188.76 | Glenn Guile |  | 24-Feb-20 | 30-Jun-21 | 15-Jan-20 | 20-Jan-20 | 29-Jun-20 | Filler | Filler |  | 0
633999 | QEW - Relocate Fuses @ P06143 on South Sheridan Way | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 19-Jun-20 |  |  | 51133.67 | 45034.8 | 51133.67 | 51133.67 | Rob Elliot |  | 31-Jul-20 | 26-Feb-21 | 20-Jul-20 | 20-Jul-20 | 13-Aug-20 |  | Locates |  | 0
634068 | Whites Studio Inc | 800 - Mavis |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities | 02-Dec-19 |  |  | 61205.38 | 7943.3 | 61205.38 | 61205.38 | XMoinuddin, Saad |  | 13-Dec-19 | 24-Aug-20 | 13-Dec-19 | 13-Dec-19 | 29-Jan-20 | xBy-passed | xBy-passed |  | 0
634106 | 2020 Tx replacements batch 4 - 15 units | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 07-Jan-20 |  |  | 149893.18 | 147012.45 | 149893.18 | 149893.18 | Peter Costantini |  | 18-Feb-20 | 22-Jun-21 | 15-Jan-20 | 21-Jan-20 | 03-Feb-20 | Filler | Filler |  | 0
634363 | 2020 Transformer Replacement Batch 5-10 Units | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 120088.59 | 101831.68 | 120088.59 | 120088.59 | K-Line Construction | K-Line | 20-Aug-20 | 29-Jun-21 | 27-Jul-20 | 07-Dec-20 | 17-Dec-20 | Filler | Filler |  | 0
634421 | PSN Bonds, HM2018-170, HM2019-006, HM2019-111 | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 5615.49 | 6430.33 | 5615.49 | 5615.49 | Macdougall, Stephen |  | 05-Aug-20 | 04-Jan-22 | 31-Jul-20 | 16-Sep-20 | 16-Sep-20 | Lines | Lines |  | 0
634427 | 320 Matheson Blvd - 3000KVA Tx Upgrade | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 19-Feb-20 |  |  | 81646.53 | 109575.54 | 81646.53 | 81646.53 | Peter Costantini | Somervl | 23-Apr-20 | 03-Mar-21 | 25-Mar-20 | 16-Mar-20 | 22-Aug-20 |  | Customer |  | 0
634509 | OH SW Replacement - LT41206 | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  | 1 | 147624.05 | 152477.4 | 147624.05 | 147624.05 | Paul Murphy |  | 21-Aug-20 | 15-Aug-21 | 27-Jul-20 | 26-Oct-20 | 10-Nov-20 | Filler | Filler |  | 0
634518 | Switch Replacement (LT41169) | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 20-Jan-20 |  | 1 | 121093.12 | 99145.42 | 121093.12 | 121093.12 | Paul Murphy |  | 17-Mar-20 | 15-Aug-21 | 02-Mar-20 | 06-Jul-20 | 14-Aug-20 | Filler | Filler |  | 0
634519 | Switch Replacement (LT41128) | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 20-Jan-20 |  | 1 | 117763.77 | 70381.36 | 117763.77 | 117763.77 | Paul Murphy |  | 02-Apr-20 | 15-Aug-21 | 18-Mar-20 | 24-Mar-20 | 14-Aug-20 | Filler | Filler |  | 0
634933 | QUEENSTON DR OH MINI REBUILD | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 13-Jan-20 |  |  | 108570.7 | 86084.47 | 108570.7 | 108570.7 | Paul Murphy |  | 11-Mar-20 | 15-Aug-21 | 03-Feb-20 | 09-Mar-20 | 12-Jun-20 | Locates | COVID19 |  | 0
634981 | JOINT USE PERMIT HM2019-113 AND HM2019-114 (REMOVALS) - 4000 NASHUA DR - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 22-Jun-20 |  |  | 5384.79 | 7525.49 | 5384.79 | 5384.79 | Macdougall, Stephen |  | 27-Jul-20 | 22-Sep-22 | 27-Jul-20 | 18-Sep-20 | 18-Sep-20 | Lines | Lines |  | 0
634996 | 126 CUMBERLAND DRIVE ANCHOR RELOCATION | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 27-Jan-20 |  |  | 4678.41 | 1501.24 | 4678.41 | 4678.41 | Paul Murphy |  | 15-Apr-20 | 16-Jul-21 | 13-Apr-20 | 13-Mar-20 | 13-Mar-20 |  |  |  | 0
635022 | JOINT USE PERMIT HM2019-115 - CAWTHRA RD - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 20-Oct-20 |  |  | 6611.62 | 5597.98 | 6611.62 | 6611.62 | Macdougall, Stephen |  | 16-Nov-20 | 10-Aug-22 | 16-Nov-20 | 10-Dec-20 | 10-Dec-20 | Lines |  |  | 0
635337 | ALEXANDRIA REBUILD | 800 - Mavis | 151063 | Active | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 28-Sep-20 |  |  | 351791.23 | 266766.81 | 350305.23 | 354177.23 | K-Line Construction | K-Line | 26-Nov-20 | 26-Jul-23 | 26-Oct-20 | 26-Oct-20 | 17-Dec-20 | MC/PUCC Permit | Contractor |  | 3,872.00
635340 | ROMETOWN REBUILD PHASE 1 | 800 - Mavis | 151148 | Active | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 14-Sep-20 |  |  | 365962.73 | 462996.3 | 358157.73 | 611083.09 | Mark Bobanovic | K-Line | 24-Nov-20 | 26-Jul-23 | 19-Oct-20 | 13-Oct-20 | 24-Nov-20 |  |  |  | 252,925.36
635341 | VICTORIA & BARRY ST | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 07-Jul-20 |  |  | 310518.69 | 212018.99 | 310518.69 | 310518.69 | Rob Elliot |  | 09-Nov-20 | 12-Nov-21 | 13-Jul-20 | 03-Aug-20 | 29-Oct-20 | MC/PUCC Permit |  |  | 0
635342 | JOYMAR DR - ANCHOR RELOCATE | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 12311.39 | 10089.48 | 12311.39 | 12311.39 | Paul Murphy |  | 05-Aug-20 | 15-Aug-21 | 03-Aug-20 | 23-Jul-20 | 23-Jul-20 |  |  |  | 0
635351 | 1180 BRITANNIA ROAD EAST | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2020 | Mandic, Goran | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 30-Nov-20
635352 | CREDITWOODLANDS (NORTH OF QUEENSTON DRIVE) | 800 - Mavis | 151063 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jul-20 |  |  | 111261.17 | 112346.6 | 111261.17 | 111261.17 | Rob Elliot |  | 15-Sep-20 | 02-Sep-21 | 10-Aug-20 | 15-Jul-20 | 10-Aug-20 | MC/PUCC Permit |  |  | 0
635476 | 68F2-ABANDON FEEDER FROM L34077 TO S6365 | 800 - Mavis | 151137 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 19529.28 | 8930.64 | 19529.28 | 19529.28 | Paul Tremblay |  | 26-Aug-20 | 28-Mar-22 | 17-Aug-20 | 21-Sep-20 | 23-Sep-20 | Filler | Filler |  | 0
635572 | SWGR REPLACEMENT - SG1457 | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 08-Jun-20 |  |  | 94714.62 | 86436.63 | 94714.62 | 94714.62 | Paul Tremblay |  | 22-Jul-20 | 12-Nov-21 | 06-Jul-20 | 27-Jul-20 | 30-Jul-20 | Filler | Filler |  | 0
635573 | SWGR REPLACEMENT - SG1636 | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 08-Jun-20 |  |  | 185501.83 | 160080.78 | 185501.83 | 185501.83 | Paul Tremblay |  | 10-Aug-20 | 12-Nov-21 | 06-Jul-20 | 18-Mar-20 | 18-Mar-20 | Filler | Filler |  | 0
635574 | SWGR REPLACEMENT - SG1448 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 08-Jun-20 |  |  | 94714.62 | 89256.26 | 94714.62 | 94714.62 | Paul Tremblay |  | 22-Jul-20 | 12-Nov-21 | 06-Jul-20 | 02-Jul-20 | 06-Jul-20 | Filler |  |  | 0
635575 | SWGR REPLACEMENT - SG1152 | 800 - Mavis | 151044 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 08-Jun-20 |  |  | 131559.72 | 92433.87 | 131559.72 | 131559.72 | Peter Costantini |  | 27-Jul-20 | 12-Nov-21 | 06-Jul-20 | 11-Nov-20 | 17-Nov-20 | Materials | Materials |  | 0
635729 | (SG1290) REMOVAL - REXWOOD RD. | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 88656.37 | 43908.46 | 88656.37 | 88656.37 | Glenn Guile |  | 02-Sep-20 | 12-Nov-21 | 27-Jul-20 | 28-Jul-20 | 04-Aug-20 | Filler | Filler |  | 0
635738 | (SG1690) REMOVAL - DILLINGWOOD DR. | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 221559.42 | 234695.28 | 221559.42 | 221559.42 | Glenn Guile | Transpw | 19-Oct-20 | 12-Nov-21 | 01-Oct-20 | 28-Sep-20 | 26-Oct-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
635750 | ENOLA AVE LOW SECONDARY SERVICES (MISSISSAUGA) | 800 - Mavis | 150823 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 25-May-20 |  |  | 22141.98 | 17639.61 | 22141.98 | 22141.98 | Macdougall, Stephen |  | 29-Jun-20 | 12-Nov-21 | 22-Jun-20 | 10-Aug-20 | 10-Aug-20 | Filler | Filler |  | 0
635763 | CENTRAL SOUTH TX REPLACEMENT - BATCH 19 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 12602.44 | 10800.52 | 12602.44 | 12602.44 | Paul Tremblay |  | 24-Jun-20 | 12-Nov-21 | 22-Jun-20 | 31-Aug-20 | 31-Aug-20 | Filler | Filler |  | 0
635765 | CENTRAL SOUTH TX REPLACEMENT - BATCH 21 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 30321.95 | 11128.6 | 30321.95 | 30321.95 | Glenn Guile |  | 26-Jun-20 | 12-Nov-21 | 22-Jun-20 | 24-Sep-20 | 24-Sep-20 | Filler | Filler |  | 0
635767 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #7 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Aug-20 |  |  | 22009.41 | 41979.91 | 22009.41 | 22009.41 | K-Line Construction | K-Line | 06-Nov-20 | 12-Nov-21 | 02-Nov-20 | 23-Nov-20 | 22-Dec-20 | Filler | Filler |  | 0
635768 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #8 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Aug-20 |  |  | 22009.41 | 24641.83 | 22009.41 | 22009.41 | K-Line Construction | K-Line | 09-Oct-20 | 12-Nov-21 | 05-Oct-20 | 30-Nov-20 | 03-Dec-20 | Filler |  |  | 0
635769 | CENTRAL SOUTH TX REPLACEMENT - BATCH 22 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Aug-20 |  |  | 33158.82 | 26561.47 | 33158.82 | 33158.82 | Paul Tremblay |  | 09-Nov-20 | 12-Nov-21 | 02-Nov-20 | 18-Dec-20 | 19-Dec-20 | Filler | Filler |  | 0
635770 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #9 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 10-Aug-20 |  |  | 23810.73 | 22383.74 | 23810.73 | 23810.73 | Paul Tremblay |  | 23-Oct-20 | 12-Nov-21 | 19-Oct-20 | 25-Nov-20 | 25-Nov-20 | Filler |  |  | 0
635773 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #10 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 22009.41 | 19943.78 | 22009.41 | 22009.41 | K-Line Construction | K-Line | 19-Oct-20 | 12-Nov-21 | 12-Oct-20 | 23-Nov-20 | 26-Nov-20 | Filler | Filler |  | 0
635774 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #11 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 46885.73 | 55141.63 | 46885.73 | 46885.73 | K-Line Construction | K-Line | 06-Nov-20 | 12-Nov-21 | 26-Oct-20 | 26-Nov-20 | 30-Nov-20 | Filler |  |  | 0
635775 | CENTRAL SOUTH TX REPLACMENT - BATCH 24 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Sep-20 |  |  | 74909.86 | 56236.01 | 74909.86 | 74909.86 | Peter Costantini |  | 05-Nov-20 | 12-Nov-21 | 19-Oct-20 | 19-Oct-20 | 05-Nov-20 |  |  |  | 0
635776 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #12 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 25404.95 | 27854.71 | 25404.95 | 25404.95 | K-Line Construction | K-Line | 30-Oct-20 | 12-Nov-21 | 26-Oct-20 | 23-Nov-20 | 22-Dec-20 | Filler | Filler |  | 0
635777 | CENTRAL SOUTH TX REPLACEMENT - BATCH 25 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 33033.69 | 15800.16 | 33033.69 | 33033.69 | K-Line Construction | K-Line | 20-Jul-20 | 12-Nov-21 | 13-Jul-20 | 09-Nov-20 | 21-Dec-20 | Filler | Filler |  | 0
635778 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #13 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 18491.87 | 26415.16 | 18491.87 | 18491.87 | Peter Costantini |  | 19-Oct-20 | 12-Nov-21 | 12-Oct-20 | 04-Nov-20 | 04-Nov-20 | Filler | Filler |  | 0
635779 | CENTRAL SOUTH TX REPLACEMENT - BATCH 26 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 47080.29 | 13539.16 | 47080.29 | 47080.29 | Glenn Guile |  | 23-Jul-20 | 12-Nov-21 | 13-Jul-20 | 29-Sep-20 | 29-Sep-20 | Filler | Filler |  | 0
635780 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #14 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 30028.98 | 31252.49 | 30028.98 | 30028.98 | K-Line Construction | K-Line | 10-Nov-20 | 12-Nov-21 | 02-Nov-20 | 07-Dec-20 | 09-Dec-20 | Filler | Filler |  | 0
635781 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #15 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 23833.34 | 23491.44 | 23833.34 | 23833.34 | Glenn Guile |  | 28-Oct-20 | 12-Nov-21 | 19-Oct-20 | 22-Oct-20 | 04-Nov-20 | Filler | Filler |  | 0
635783 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #16 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 17561.59 | 22396.11 | 17561.59 | 17561.59 | K-Line Construction | K-Line | 19-Oct-20 | 12-Nov-21 | 12-Oct-20 | 09-Nov-20 | 23-Dec-20 | Filler | Filler |  | 0
635784 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #17 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 41349.9 | 73541.26 | 41349.9 | 41349.9 | K-Line Construction | K-Line | 06-Nov-20 | 28-Mar-22 | 26-Oct-20 | 09-Nov-20 | 12-Nov-20 | Filler | Filler |  | 0
635785 | CENTRAL SOUTH TX REPLACEMENT - BATCH 27 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 25524.38 | 16675.9 | 25524.38 | 25524.38 | Peter Costantini |  | 29-Jul-20 | 12-Nov-21 | 23-Jul-20 | 23-Jul-20 | 11-Aug-20 |  | Filler |  | 0
635786 | CENTRAL SOUTH TX REPLACEMENT - BATCH 28 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 29673.18 | 15551.65 | 29673.18 | 29673.18 | Glenn Guile |  | 22-Oct-20 | 12-Nov-21 | 12-Oct-20 | 07-Oct-20 | 22-Oct-20 | Filler | Filler |  | 0
635788 | CENTRAL SOUTH TX REPLACEMENT - BATCH 30 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 23-Jun-20 |  |  | 17001.92 | 4073.31 | 17001.92 | 17001.92 | Peter Costantini |  | 05-Aug-20 | 12-Nov-21 | 31-Jul-20 | 14-Sep-20 | 14-Sep-20 | Filler | Filler |  | 0
635789 | CENTRAL SOUTH TX REPLACEMENT - BATCH 31 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 23-Jun-20 |  |  | 45908.81 | 44891.39 | 45908.81 | 45908.81 | Peter Costantini |  | 12-Aug-20 | 12-Nov-21 | 31-Jul-20 | 20-Jul-20 | 12-Aug-20 |  |  |  | 0
635790 | CENTRAL SOUTH TX REPLACMENT - BATCH 32 | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 29909.25 | 16025.81 | 29909.25 | 29909.25 | Peter Costantini |  | 31-Jul-20 | 12-Nov-21 | 23-Jul-20 | 13-Aug-20 | 14-Aug-20 | Filler | Filler |  | 0
635807 | 2020 REBUILD - TX8829 - TX8830 (RATHBURN AND WILCOX) | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 23-Jun-20 |  |  | 269842.91 | 281485.99 | 208929.19 | 269842.91 | Paul Tremblay | Somervl | 01-Sep-20 | 12-Nov-21 | 06-Aug-20 | 10-Aug-20 | 01-Sep-20 | Contractor |  |  | 60,913.72
635809 | BELL BONDS - Y59508 + Y10198 - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 15-Jun-20 |  |  | 2296.93 | 2831.97 | 2296.93 | 2296.93 | Macdougall, Stephen |  | 28-Jul-20 | 04-Jul-22 | 28-Jul-20 | 16-Sep-20 | 16-Sep-20 | Lines | Lines |  | 0
635875 | 3060 HURONTARIO ST. | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 01-Sep-20 |  |  | 78077.56 | 36207.84 | 78077.56 | 78077.56 | Peter Costantini |  | 23-Oct-20 | 23-Apr-21 | 23-Sep-20 | 04-Sep-20 | 15-Dec-20 |  | Customer |  | 0
635913 | (SG1757) REPLACEMENT - 217 STATESMAN DR. | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 89218.49 | 93615.76 | 89218.49 | 89218.49 | Glenn Guile |  | 07-Aug-20 | 21-Apr-22 | 22-Jul-20 | 16-Dec-20 | 18-Dec-20 | Materials | Materials |  | 0
635917 | (SG1280) REPLACEMENT - RATHBURN PARK | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 08-Jun-20 |  |  | 42846.88 | 42613.98 | 42846.88 | 42846.88 | Glenn Guile |  | 29-Jul-20 | 12-Nov-21 | 06-Jul-20 | 23-Sep-20 | 25-Sep-20 | Materials | Filler |  | 0
635921 | (SG1798) REPLACEMENT - 295 EGLINTON | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 08-Jun-20 |  |  | 87442.33 | 110902.03 | 87442.33 | 87442.33 | Glenn Guile |  | 20-Jul-20 | 12-Nov-21 | 06-Jul-20 | 30-Sep-20 | 02-Oct-20 | Materials | Lines |  | 0
635922 | (SG1561) REMOVAL - STRATHAVEN DR. | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 69064.67 | 82602.99 | 69064.67 | 69064.67 | Glenn Guile |  | 05-Aug-20 | 12-Nov-21 | 06-Jul-20 | 22-Jun-20 | 18-Oct-20 |  | Lines |  | 0
635923 | (SG1313) REMOVAL - SKYMARK AVE | 800 - Mavis | 151091 | Inactive | 99 | CANCELLED |  |  | 2020 | Beaudrie, Scott | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 21-Apr-22
635924 | (SG1787) REPLACEMENT - CANTAY RD. | 800 - Mavis | 151091 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 15-Jun-20 |  |  | 91617.05 | 103376.97 | 91617.05 | 91617.05 | Peter Costantini |  | 11-Aug-20 | 12-Nov-21 | 27-Jul-20 | 28-Nov-20 | 02-Dec-20 | Materials | Materials |  | 0
636007 | 1798 LANTERN FLY HOLLOW- TX60525 REPLACEMENT - O/H 50KVA 120/240V | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 13940.69 | 10186.21 | 13940.69 | 13940.69 | Rob Elliot |  | 15-Jul-20 | 28-Mar-22 | 13-Jul-20 | 12-Aug-20 | 12-Aug-20 | Filler | Filler |  | 0
636008 | 3930 NASHUA DR - TX11102 REPLACEMENT - O/H 500KVA 347/600V | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 29747.51 | 27734.97 | 29747.51 | 29747.51 | Paul Murphy |  | 20-Jul-20 | 12-Nov-21 | 16-Jul-20 | 16-Aug-20 | 16-Aug-20 | Filler | Filler |  | 0
636009 | 7252 WAINBROOK RD - TX6048 REPLACEMENT - O/H 50KVA 120/240V | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 12341.2 | 11927.24 | 12341.2 | 12341.2 | Rob Elliot |  | 23-Jul-20 | 12-Nov-21 | 21-Jul-20 | 19-Aug-20 | 20-Aug-20 | Filler | Filler |  | 0
636027 | DERRY ROAD & 401 DUCT BANK RELOCATIONS FOR WCC/MTO | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 09-Jul-20 |  |  | 181657.99 | 152910.34 | 181657.99 | 181657.99 | Glenn Guile | Somervl | 20-Aug-20 | 17-Mar-21 | 10-Aug-20 | 16-Jul-20 | 05-Aug-20 |  |  |  | 0
636057 | JOINT USE PERMIT HM2020-003 - GOREWAY DR - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 22-Jul-20 |  |  | 10105.78 | 7996.16 | 10105.78 | 10105.78 | Macdougall, Stephen |  | 24-Aug-20 | 10-Aug-22 | 24-Aug-20 | 24-Aug-20 | 24-Aug-20 |  |  |  | 0
636068 | 2260 MATHESON BLVD EAST | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 17-Aug-20 |  |  | 193614.63 | 145241.69 | 193614.63 | 193614.63 | Peter Costantini | Somervl | 06-Nov-20 | 05-Mar-21 | 30-Sep-20 | 02-Sep-20 | 06-Oct-20 |  |  |  | 0
636083 | 6688 VANGUARD DR - TX6086 REPLACEMENT - O/H 150KVA 120/208V | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 15682.95 | 16077.22 | 15682.95 | 15682.95 | Paul Murphy |  | 28-Jul-20 | 12-Nov-21 | 27-Jul-20 | 09-Aug-20 | 09-Aug-20 | Filler | Filler |  | 0
636084 | 522 GARDEN WALK - TX22683 REPLACEMENT - O/H 50KVA 120/240V | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 22-Jun-20 |  |  | 10101.36 | 16190.6 | 10101.36 | 10101.36 | Rob Elliot |  | 28-Jul-20 | 12-Nov-21 | 27-Jul-20 | 24-Aug-20 | 24-Aug-20 | Filler |  |  | 0
636085 | 1700 DERRY ROAD E - TX17101 REPLACEMENT - O/H 15KVA 120/240V | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 01-Jun-20 |  |  | 8800.51 | 8956.48 | 8800.51 | 8800.51 | Rob Elliot |  | 06-Aug-20 | 16-Nov-21 | 03-Aug-20 | 26-Aug-20 | 26-Aug-20 | Filler | Filler |  | 0
636114 | GUYING RELOCATION - SENECA AVE (P22419) | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 15-Jun-20 |  |  | 12965.78 | 3912.1 | 12965.78 | 12965.78 | Paul Murphy |  | 24-Jun-20 | 22-Feb-21 | 22-Jun-20 | 10-Aug-20 | 10-Aug-20 | Lines | Lines |  | 0
636173 | JOINT USE PERMIT HM2020-007 - DERRY RD E - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 08-Jun-20 |  |  | 3684.99 | 6955.37 | 3684.99 | 3684.99 | Paul Murphy |  | 22-Jun-20 | 04-Jul-22 | 22-Jun-20 | 17-Jun-20 | 17-Jun-20 |  |  |  | 0
636211 | DEER RUN CRT UG REBUILD | 800 - Mavis | 151451 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Beaudrie, Scott | Alectra Utilities | 31-Mar-20 |  |  | 234184.87 | 218338.47 | 234184.87 | 234184.87 | Paul Tremblay | Transpw | 16-Jun-20 | 12-Nov-21 | 25-May-20 | 25-Jun-20 | 11-Sep-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
636288 | JOINT USE PERMIT HM2020-011 - PARK ST EAST - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 08-Jun-20 |  |  | 5820.3 | 4603.42 | 5820.3 | 5820.3 | Macdougall, Stephen |  | 29-Jul-20 | 22-Aug-22 | 29-Jul-20 | 28-Sep-20 | 28-Sep-20 | Lines | Lines |  | 0
636436 | GUYING RELOCATIONS - MAVIS RD (P18017, P18018) | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 19-Aug-20 |  |  | 34804.03 | 23129.04 | 34804.03 | 34804.03 | Paul Murphy |  | 08-Oct-20 | 26-Feb-21 | 28-Sep-20 | 02-Sep-20 | 09-Sep-20 |  |  |  | 0
636687 | ERIN MILLS PARKWAY ROAD WORK BETWEEN CREDIT VALLEY ROAD AND BRITANNIA ROAD | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 17-Aug-20 |  |  | 32698.56 | 17027.09 | 32698.56 | 32698.56 | Macdougall, Stephen |  | 01-Oct-20 | 25-Feb-21 | 23-Sep-20 | 16-Oct-20 | 02-Nov-20 | Locates | Locates |  | 0
636708 | ANCHOR RELOCATION AT P07954 EGLINTON AVE | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE | Medium | Safety | 2020 | Lacombe, Joel | Alectra Utilities | 22-Jun-20 |  |  | 17524.96 | 6058.05 | 17524.96 | 17524.96 | Paul Murphy |  | 04-Aug-20 | 25-Feb-21 | 27-Jul-20 | 22-Jun-20 | 22-Jun-20 |  |  |  | 0
636733 | BELL BONDS - Y16415 - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Jun-20 |  |  | 1299.47 | 3587.87 | 1299.47 | 1299.47 | Macdougall, Stephen |  | 30-Jul-20 | 22-Sep-22 | 30-Jul-20 | 21-Sep-20 | 21-Sep-20 | Lines | Lines |  | 0
636790 | JOINT USE PERMIT HM2020-027 - CREEKBANK - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 01-Oct-20 |  |  | 5192.1 | 5796.5 | 5192.1 | 5192.1 | Macdougall, Stephen |  | 19-Oct-20 | 22-Sep-22 | 19-Oct-20 | 10-Dec-20 | 10-Dec-20 | Lines | Lines |  | 0
637090 | OH TRANSFORMERS - CENTRAL SOUTH | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2020 | Beaudrie, Scott | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 04-Oct-21
637092 | UG TRANSFORMERS - CENTRAL SOUTH | 800 - Mavis | 151043 | Inactive | 99 | CANCELLED |  |  | 2020 | Beaudrie, Scott | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad
637156 | 7415 TORBRAM ROAD ANCHOR/DG CONFLICT | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Lacombe, Joel | Alectra Utilities | 01-Jun-20 |  |  | 3131.06 | 7038.26 | 3131.06 | 3131.06 | Paul Murphy |  | 30-Jul-20 | 18-Feb-21 | 30-Jul-20 | 06-Aug-20 | 06-Aug-20 | Locates | Locates |  | 0
637174 | QUADREAL DEVELOPMENT - 1600 COURTNEYPARK DR. E. | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities |  |  |  | 101830.77 | 70634.25 | 101830.77 | 101830.77 | Peter Costantini |  | 02-Nov-20 | 11-Mar-21 | 02-Nov-20 | 13-Oct-20 | 05-Nov-20 | xBy-passed | xBy-passed |  | 0
637240 | CAWTHRA & NEEDHAM POLE REPLACEMENTS FOR ROGERS ATTACHMENTS | 800 - Mavis | 150675 | Inactive | 99 | CANCELLED |  |  | 2020 | Lacombe, Joel | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 11-Aug-21
637348 | BAYLIS MEDICAL | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | MacDougall, Stephen | Alectra Utilities | 22-Oct-20 |  |  | 98291.25 | 95321.32 | 98291.25 | 98291.25 | Peter Costantini | Somervl | 28-Oct-20 | 23-Feb-21 | 23-Oct-20 | 23-Oct-20 | 26-Oct-20 |  |  |  | 0
637549 | JOINT USE PERMIT HM2020-031 - DERRY W - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 22-Jul-20 |  |  | 7743.74 | 7057.54 | 7743.74 | 7743.74 | Macdougall, Stephen |  | 24-Aug-20 | 22-Aug-22 | 24-Aug-20 | 19-Aug-20 | 19-Aug-20 |  |  |  | 0
637552 | NEW OH BANK TRANSFORMER - 1020 CARDIFF BLVD | 800 - Mavis | 151043 | Inactive | 99 | COMPLETE |  |  | 2020 | Beaudrie, Scott | Alectra Utilities | 20-Aug-20 |  |  | 67795.62 | 63623.9 | 67795.62 | 67795.62 | Macdougall, Stephen |  | 23-Sep-20 | 04-Jul-21 | 14-Sep-20 | 12-Aug-20 | 12-Aug-20 | xBy-passed | xBy-passed |  | 0
637652 | CABLE REPLACEMENT - SIR JOHN'S HOMESTEAD - NBM | 800 - Mavis | 150495 | Inactive | 99 | CANCELLED |  |  | 2020 | Beaudrie, Scott | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 15-Jul-21
637674 | ARGENTIA ROAD AT SG1782 UNDERGROUND CABLE RELOCATIONS | 800 - Mavis | 150673 | Inactive | 99 | COMPLETE |  |  | 2020 | Lacombe, Joel | Alectra Utilities | 10-Nov-20 |  |  | 50439.51 | 52145.11 | 50439.51 | 50439.51 | Glenn Guile | Somervl | 23-Dec-20 | 02-Jun-21 | 07-Dec-20 | 18-Nov-20 | 07-Dec-20 |  |  |  | 0
637709 | BARBER HOUSE DEMO | 800 - Mavis | 150675 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 30-Jul-20 |  |  | 11929.42 | 4759.48 | 11929.42 | 11929.42 | Paul Tremblay |  | 31-Aug-20 | 12-Aug-21 | 24-Aug-20 | 01-Sep-20 | 02-Sep-20 | Customer | Customer |  | 0
637858 | JOINT USE PERMIT HM2020-040 - AVONHEAD - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 26-Nov-20 |  |  | 6252.75 | 3651.38 | 6252.75 | 6252.75 | Macdougall, Stephen |  | 04-Jan-21 | 22-Aug-22 | 04-Jan-21 | 11-Dec-20 | 11-Dec-20 |  |  |  | 0
637951 | JOB BELONGS TO BRAMPTON - BRAMPTON TERRITORY TO ADDRESS | 800 - Mavis | 150384 | Inactive | 99 | CANCELLED |  |  | 2020 | Mandic, Goran | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | XMoinuddin, Saad |  |  | 20-Jul-20
637965 | JOINT USE PERMIT HM2020-041 - ENTERPRISE - MISS | 800 - Mavis | 151537 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 26-Nov-20 |  |  | 7594 | 7115.32 | 7594 | 7594 | Macdougall, Stephen |  | 05-Jan-21 | 22-Sep-22 | 04-Jan-21 | 17-Dec-20 | 17-Dec-20 |  |  |  | 0
638803 | 3210 HURONTARIO ST- MISS - SR - 3PH SERVICE REMOVAL | 800 - Mavis | 150384 | Inactive | 99 | COMPLETE |  |  | 2020 | Mandic, Goran | Alectra Utilities | 26-Oct-20 |  |  | 10177.44 | 6499.07 | 10177.44 | 10177.44 | Peter Costantini |  | 30-Oct-20 | 19-Feb-21 | 30-Oct-20 | 30-Oct-20 | 30-Oct-20 | xBy-passed | xBy-passed |  | 0
EAST 2020 | East Region | [7 empty] | 2020 |  | Alectra Utilities |  | 134 | 186 | 95845172.19 | 92059274.44 |  | 0 | [5 empty] | 04-Feb-19 | 31-Dec-20
313357 | (WO 313357) 15-039 Guying Installation | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 29-Jun-20
313677 | (WO 313677) 15-056 Anchor Installation MAJOR MACKENZIE DR - GRAND TRUNK AVE TO ONTARIO ST | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 29-Jun-20
315381 | (WO 315381) Stub Pole and Guyung Reloc - NEW HUNGTINGTON RD | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 29-Jun-20
318487 | (WO 318487) BELL COMMUNICATION BONDS | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 11-May-20
318782 | (WO 318782) X95153 Bell Bonding | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 11-May-20
318942 | (WO 318942) Transfr cct HONI pole - Aurora | 815 - Addiscott | 101355 | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 14-Dec-18
319112 | (WO 319112) Rogers Bonds | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 11-May-20
452449 | (WO310192) Steeles Ave. west at Keele St. | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 2513.9 |  | 0 | Persaud, Ryan |  |  | 01-Feb-21
452504 | 452504 (WO 313019) A12 - Addison Hall Business Park | 815 - Addiscott | 101896 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 09-Oct-18 |  |  | 1479539.41 | 1561882.4 | 1479539.41 | 1479539.41 | Chris Hagan | Transpw | 01-Aug-19 | 02-Feb-22 | 29-Oct-18 | 01-Jul-19 | 14-Oct-20 | Customer | Customer |  | 0
452530 | (WO313541) 77 Woodstream Blvd | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Stephens, Barry N. | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Nov-20
452553 | 452553 (WO 314722) Vitlor Homes (Lots G - J) | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | Penner, Mitchell | Alectra Utilities | 10-May-19 |  |  | 149228.2 | 154424.73 | 149228.2 | 149228.2 | Steve Rumble | Transpw | 02-Jul-19 | 24-Aug-20 | 11-Jun-19 | 03-Oct-19 | 23-Feb-20 | Customer | Customer |  | 0
452559 | 452559 (WO 314876) Pole Relocation - Major Mackenzie Dr - Islington Ave To Pine Valley Dr (9 poles) | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Corriveau, Tom N | Alectra Utilities | 15-Jul-20 |  |  | 591973.48 | 499530.75 | 591973.48 | 591973.48 | Macdonald, Steve | K-Line | 18-Sep-20 | 08-Mar-21 | 27-Jul-20 | 14-Sep-20 | 11-Dec-20 | Customer |  |  | 0
452572 | 452572 - MCCOWAN RD. #8590 - PFAFF PORSCHE MARKHAM - Car dealership | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Dibratto, Susan | Alectra Utilities | 27-Nov-19 |  |  | 87264.14 | 76936.76 | 87264.14 | 87264.14 | Steve Rumble |  | 12-Feb-20 | 08-Mar-21 | 03-Feb-20 | 21-Aug-20 | 01-Sep-20 | Lines |  |  | 0
452604 | 452604 (WO 315353) Uptowns on Bayview | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 31-Oct-19 |  |  | 49325.95 | 64708.56 | 49325.95 | 49325.95 | Chris Hagan | Transpw | 09-Dec-19 | 18-Feb-21 | 02-Dec-19 | 15-Jul-20 | 29-Sep-20 | Customer | Customer |  | 0
452615 | (WO 452615 was 315474) Rebuild Pole Line on 19th Ave into 2 cct - From Leslie to Bayview | 815 - Addiscott | 101781 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 | 1202306 | 1202306 | Persaud, Ryan |  |  | 19-Oct-21 | [6 empty] | 0
452616 | 452616 (WO 315493) Sedgewick Dev Ph 1 (F) | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 12-Nov-19 |  |  | 1224733.97 | 1227188.17 | 1224733.97 | 1224733.97 | Chris Hagan | Conelco | 06-Dec-19 | 04-Mar-21 | 22-Nov-19 | 13-Jul-20 | 07-Dec-20 | Customer | Customer |  | 0
452618 | 452618 (WO 315508) - Corsica Pole Relocation - Bayview Drive & Hillsview Drive, Richmond Hill | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 18-Nov-19 |  |  | 71893.45 | 69185.29 | 71893.45 | 71893.45 | Chris Hagan | Transpw | 29-Nov-19 | 21-Jun-21 | 22-Nov-19 | 10-Dec-19 | 04-Nov-20 | Customer | Customer |  | 0
452622 | 452622 - RELOCATION FOR RD IMPROVEMENTS/RELOCATION FOR RD IMPROVEMENTS | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2020 | Pelleja, Emily | Alectra Utilities | 05-Nov-20 |  |  | 158674.13 | 92094.49 | 158674.13 | 158674.13 | Dan Kish | K-Line | 18-Dec-20 | 03-Oct-21 | 09-Dec-20 | 24-Nov-20 | 02-Dec-20 |  |  |  | 0
452629 | 452629 (WO 315590) Sedgewick Dev Ph 2 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 09-Sep-20 |  |  | 21835.06 | 66688.38 | 21835.06 | 21835.06 | Chris Hagan | Conelco | 30-Nov-20 | 02-Mar-21 | 09-Nov-20 | 17-Nov-20 | 07-Dec-20 | Customer | Customer |  | 0
452630 | 452630 (WO 315593) Centerfield Dev Ph 1 (F) | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 12-Nov-19 |  |  | 143602.51 | 135980.31 | 143602.51 | 143602.51 | Chris Hagan | Conelco | 06-Dec-19 | 09-Feb-21 | 25-Nov-19 | 13-Jul-20 | 07-Dec-20 | Customer | Customer |  | 0
452631 | 452631 (WO 315595) Dickson 48 Properties Inc. (F) | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 12-Nov-19 |  |  | 222505.33 | 217212.55 | 222505.33 | 222505.33 | Chris Hagan |  | 06-Dec-19 | 19-Feb-21 | 25-Nov-19 | 13-Jul-20 | 07-Dec-20 | Customer | Customer |  | 0
452638 | 452638 (WO 315620) Barker DC Buisness Park, Richmond Hill | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 27-Jul-18 |  |  | 1833422.13 | 2411175.66 | 1815193 | 1833422.13 | Chris Hagan | Transpw | 04-Apr-19 | 31-Aug-22 | 02-Jan-19 | 04-Feb-19 | 11-Nov-20 | Customer | Customer |  | 18,229.13
452644 | 452644 (WO 315718) Data Centre - Bldg. DC2 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 15-Oct-18 |  |  | 258851.74 | 240816.45 | 258851.74 | 258851.74 | Dave Lindsay | Transpw | 17-Jan-19 | 22-Apr-21 | 13-Nov-18 | 11-Jan-20 | 02-Nov-20 | Customer | Customer |  | 0
452646 | 452646 (WO 315759) Kings Landing | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE | Medium | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 18-Mar-20 |  |  | 34678.19 | 194872.95 | 34678.19 | 34678.19 | Steve Rumble |  | 10-Jul-20 | 05-Apr-22 | 01-Jun-20 | 20-May-20 | 23-Jun-20 |  |  |  | 0
452693 | 452693 (WO 316255) Cornell Ph 8 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 18-Oct-19 |  |  | 271380.16 | 233813.37 | 271380.16 | 271380.16 | Steve Rumble | Transpw | 17-Dec-19 | 25-Aug-20 | 16-Dec-19 | 13-Jan-20 | 12-May-20 | Customer | Customer |  | 0
452699 | 452699 (WO 316272) Highland Gate Phase One | 815 - Addiscott | 101887 | Active | 99 | COMPLETE | VerHigh | Subdiv | 2020 | Cranley, Stephen | Alectra Utilities | 01-Nov-17 |  |  | 410118.16 | 436249.35 | 410118.16 | 410118.16 | Cory Ruiter | Conelco | 01-May-19 | 03-Aug-23 | 23-Apr-19 | 08-May-19 | 16-Jun-20 | Contractor | Lines |  | 0
452722 | 452722 - UG Cable Replacement EPC - Steeles and Canadiana | 815 - Addiscott | 150141 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-Oct-19 |  |  | 1230570.13 | 1176859.39 | 843649.67 | 1230570.13 | Shane Christopher | Transpw | 19-Jun-20 | 06-Apr-22 | 11-May-20 | 11-May-20 | 22-Oct-20 | COVID19 | Materials |  | 386,920.46
452723 | 452723 (WO 316425) Steeles and Fairway Heights | 815 - Addiscott | 150141 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 17-Jul-20 |  |  | 2963096.23 | 2858665.9 | 2963096.23 | 2963096.23 | Shane Christopher | Transpw | 26-Mar-21 | 06-Apr-22 | 31-Aug-20 | 04-Aug-20 | 15-Dec-20 |  |  |  | 0
452736 | (WO316463) York University Campus Markham | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Stephens, Barry N. | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Nov-20
452799 | 452799 (WO 316617) Villagio (9891 Keele Street) | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE | VerHigh | Subdiv | 2020 | Penner, Mitchell | Alectra Utilities | 22-May-19 |  |  | 69087.38 | 67717.32 | 69087.38 | 69087.38 | Steve Rumble | Transpw | 16-Oct-19 | 08-Feb-21 | 16-Sep-19 | 02-Mar-20 | 15-Apr-20 | Customer | Customer |  | 0
452800 | (WO 316619) 180 Wellington, Aurora | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 | 53884.53 | 53884.53 | Persaud, Ryan |  |  | 20-Jun-18 | [6 empty] | 0
452801 | 452801 (WO 316633) Nashville Heights - Mizuno Lands | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 18-Oct-19 |  |  | 585953.16 | 544069.82 | 585953.16 | 585953.16 | Steve Rumble |  | 21-Jan-20 | 25-Jan-21 | 22-Nov-19 | 30-Sep-19 | 12-Feb-20 |  | Customer |  | 0
452810 | (WO316681) UG Design for City of Vaughan - HWY 7(E/O HWY 400-E/O CREDITSTONE RD), VAUGHAN | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 61254.02 | 0 | 0 | Steve Rumble |  |  | 22-Sep-22 | [6 empty] | 0
452820 | 452820 (WO 316698) 396, 404, 416 KING ROAD RICHMOND HILL | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | Penner, Mitchell | Alectra Utilities | 01-Nov-17 |  |  | 120722.09 | 112414.78 | 120722.09 | 120722.09 | Chris Hagan | Transpw | 03-Sep-19 | 01-Feb-21 | 12-Aug-19 | 01-Oct-20 | 10-Nov-20 | Customer | Customer |  | 0
452829 | 452829 (WO 316782) BUTTERMILL AVE #5 & PORTAGE PKWY #898 | 815 - Addiscott | 101791 | Active | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 26-Feb-19 |  |  | 99824.53 | 23622.15 | 99824.53 | 99824.53 | Dave Lindsay | Somervl | 23-May-19 | 26-Jul-23 | 23-Apr-19 | 10-Nov-20 | 10-Nov-20 | Customer | Customer |  | 0
452838 | (WO316794) Metrolinx Crossing Big Bay Point Rd - Dodson Rd to Grand Forest Dr | 825 - Patterson | 150591 | Inactive | 99 | CANCELLED |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Jul-21
452844 | 452844 (WO 316817) - Smart Reit VMC_Condo's_UG Cable Installation | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2019 | D'Onofrio, Tony | Alectra Utilities | 20-Nov-19 |  |  | 1509724.74 | 1503023.34 | 1509724.74 | 1509724.74 | Shane Christopher | Transpw | 16-Dec-19 | 26-Jul-23 | 27-Nov-19 | 09-Dec-19 | 20-Dec-19 |  | Customer |  | 0
452857 | 452857 (WO 316868) BG Aurora - Phase Two | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | Cranley, Stephen | Alectra Utilities | 09-Apr-19 |  |  | 921223.71 | 966729.42 | 921223.71 | 921223.71 | Steve Rumble | Transpw | 25-Sep-19 | 04-Sep-20 | 06-Jun-19 | 12-Nov-19 | 30-Apr-20 | Customer | Customer |  | 0
452867 | 452867 (WO 316891) PORTAGE PKWY - #950 | 815 - Addiscott | 101791 | Active | 99 | COMPLETE | VerHigh | Res-ICI | 2020 | Dibratto, Susan | Alectra Utilities | 26-Feb-19 |  |  | 51208.79 | 11606.59 | 51208.79 | 51208.79 | Cory Ruiter | Somervl | 29-Apr-19 | 16-Aug-23 | 05-Apr-19 | 18-Jun-19 | 20-May-20 | Customer | Customer |  | 0
452872 | 452872 (WO 316899) New Retirement Home. Aurora Meadows Phase 2 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 29-Oct-18 |  |  | 52663.55 | 52558.12 | 52663.55 | 52663.55 | Steve Rumble | Somervl | 01-Apr-19 | 21-Jan-21 | 19-Mar-19 | 04-Feb-20 | 05-Feb-20 | Customer | Customer |  | 0
452883 | 452883 (WO 316926) Leslie Elgin Phase 2 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 23-Apr-18 |  |  | 538659.91 | 545012.59 | 538659.91 | 538659.91 | Chris Hagan | Transpw | 22-Nov-18 | 12-Apr-21 | 01-Aug-18 | 22-Jun-20 | 06-Oct-20 | Customer | Customer |  | 0
452894 | (WO316997) Commercial Bldg | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 2688.57 |  | 0 | Persaud, Ryan |  |  | 01-Feb-21
452896 | 452896 (WO 317002) St. Magnus - Weston Road | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 26-May-20 |  |  | 21600.89 | 124899.29 | 21600.89 | 21600.89 | Chris Hagan | Conelco | 31-Aug-20 | 27-Jul-23 | 03-Aug-20 | 02-Sep-20 | 23-Sep-20 | Customer | Customer |  | 0
452903 | 452903 (WO 317048) 2020 Cable Replacement- Donald St. and Simcoe Terrace - Barrie | 825 - Patterson | 150139 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Bowman, Todd J | Alectra Utilities | 18-Nov-19 |  |  | 578423.03 | 556739.49 | 578423.03 | 578423.03 | Lotto, Jay | Transpw | 02-Oct-20 | 15-Jul-21 | 24-Jun-20 | 17-Jun-20 | 27-Jul-20 |  |  |  | 0
452904 | 452904 (WO 317049) Bradford - FNB Ph4 - Inspect and Connect | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 10-Oct-18 |  |  | 28327.04 | 262684.42 | 28327.04 | 28327.04 | Jeremy Wright | Conelco | 15-Apr-19 | 19-Nov-20 | 04-Mar-19 | 17-Sep-19 | 29-Jan-20 | Customer | Customer |  | 0
452921 | 452921 (WO 317189) WOODHAVEN BALLYMORE | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 17-Dec-18 |  |  | 231996.44 | 383418.15 | 231996.44 | 231996.44 | Steve Rumble | Transpw | 12-Jul-19 | 28-Aug-20 | 17-Jun-19 | 04-Oct-19 | 30-Apr-20 | Customer | Customer |  | 0
452950 | 452950 (WO 317313) Service Upgrade | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 16-Sep-19 |  |  | 24842.71 | 40639.59 | 24842.71 | 24842.71 | Jeremy Wright | HapAmp | 18-Oct-19 | 01-Nov-21 | 15-Oct-19 | 31-Aug-20 | 03-Sep-20 | Customer | Customer |  | 0
452952 | (WO317315) HIGHWAY NO. 7 WEST - #3201 AT INTERCHANGE WAY | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0.41 | 0 |  | 0 | Steve Rumble |  |  | 26-Oct-20
452955 | 452955 (WO 317323) Primont (Cornell 2) | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 12-Nov-19 |  |  | 331641.07 | 285189.45 | 331641.07 | 331641.07 | Steve Rumble |  | 17-Dec-19 | 31-Aug-20 | 16-Dec-19 | 18-Nov-19 | 12-May-20 | Customer | Customer |  | 0
452957 | 452957 (WO 317330) Union Midrise Residential Condo Bur Oak Ave. - #1735 at Markham Rd. | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 30-Apr-18 |  |  | 59283.83 | 50789.72 | 59283.83 | 59283.83 | Dave Lindsay | Transpw | 27-Sep-18 | 15-Mar-21 | 30-Jul-18 | 21-Aug-20 | 06-Oct-20 | Customer | Customer |  | 0
452959 | 452959 (WO 317337) UG Feeder on Cornell Rouge Blvd | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | Penner, Mitchell | Alectra Utilities | 29-Jul-19 |  |  | 390979 | 465983.62 | 390979 | 390979 | Steve Rumble | Transpw | 28-Nov-19 | 03-Nov-21 | 04-Nov-19 | 12-Dec-19 | 12-May-20 | Customer | Customer |  | 0
452969 | 452969 (WO 317408) Rutherford Rd - Jane to Westburne | 815 - Addiscott | 101762 | Active | 99 | COMPLETE | Medium | Infrast | 2020 | Corriveau, Tom N | Alectra Utilities | 11-Sep-19 |  |  | 4497116.68 | 5471939.05 | 4497116.68 | 4497116.68 | Shortt, Derek B. | Transpw | 01-Apr-20 | 26-Jul-23 | 22-Oct-19 | 10-Oct-19 | 12-Nov-20 |  |  |  | 0
453026 | 453026 (WO 317548) New Hotel | 815 - Addiscott | 101791 | Active | 99 | COMPLETE | Low | Hotel | 2020 | Cranley, Stephen | Alectra Utilities | 21-Feb-20 |  |  | 57753.79 | 60030.78 | 57753.79 | 57753.79 | Shane Christopher | Somervl | 24-Apr-20 | 28-Jul-23 | 14-Apr-20 | 26-Feb-20 | 25-Jun-20 |  |  |  | 0
453030 | 453030 (WO 317576) 18 Water Street Seniors Bldg | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 22-Jul-19 |  |  | 45628.37 | 61286.02 | 45628.37 | 45628.37 | Steve Rumble | N/A | 30-Sep-19 | 21-Jan-21 | 16-Sep-19 | 24-Oct-19 | 28-Jan-20 | Lines | Customer |  | 0
453038 | 453038 (WO 317598) I&C - 7803 & 7815 DUFFERIN ST. | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 25-Oct-19 |  |  | 249718.11 | 219680.6 | 249718.11 | 249718.11 | Steve Rumble | Transpw | 10-Dec-19 | 24-Aug-20 | 14-Nov-19 | 12-Dec-19 | 13-Jan-20 | Customer | Customer |  | 0
453050 | 453050 (WO 317676) Nashville North - East of Channel Ph. 4B | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 25-Oct-19 |  |  | 180868.93 | 168332.35 | 180868.93 | 180868.93 | Steve Rumble | Transpw | 13-Dec-19 | 24-Aug-20 | 09-Dec-19 | 24-Dec-19 | 12-Feb-20 | Customer | Customer |  | 0
453060 | (WO317737) Exist. Swgr Recovery & Splice | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 590.35 |  | 0 | Persaud, Ryan |  |  | 01-Feb-21
453061 | 453061 (WO 317741) Pole Line rebuild - AB-B1029 Dufferin St between MS431 and Albert St. Allisto | 825 - Patterson | 150362 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 28-Nov-19 |  |  | 609185.06 | 747804.32 | 609185.06 | 609185.06 | Jeremy Wright |  | 16-Apr-20 | 08-Mar-21 | 06-Jan-20 | 26-Jan-20 | 08-Aug-20 | Locates |  |  | 0
453084 | 453084 (WO 317841) Town Homes - U-Social | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 27-Sep-18 |  |  | 75885.64 | 65434 | 75885.64 | 75885.64 | Steve Rumble | Transpw | 28-Nov-18 | 22-Apr-22 | 08-Nov-18 | 16-Jun-20 | 31-Aug-20 | Customer | Customer |  | 0
453086 | (WO317853) Customer Secondary Relocate - 429 Champlain Rd - Penetang | 825 - Patterson |  | Inactive | 99 | CANCELLED |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 0 | 0 | 0 | 0 | Wong, Henry |  |  | 24-Aug-20 | [6 empty] | 0
453090 | 453090 - KING EAST SUBDIVISION PHASE 2 | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 22-Oct-20 |  |  | 115076.32 | 112747.37 | 115076.32 | 115076.32 | Chris Hagan | Transpw | 29-Dec-20 | 29-Dec-20 | 11-Dec-20 | 23-Oct-20 | 10-Nov-20 |  |  |  | 0
453098 | 453098 (WO 317901) McNaughton Rd & Eagle Rock - F (1840 Major Mackenzie Dr) | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 18-Aug-20 |  |  | 95178.95 | 103834.14 | 83046.95 | 95178.95 | Chris Hagan | Somervl | 23-Oct-20 | 25-Feb-21 | 05-Oct-20 | 03-Sep-20 | 04-Dec-20 | Customer | Customer |  | 12,132.00
453101 | 453101 (WO 317909) 8470 Keele St | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 26-Sep-19 |  |  | 69636.55 | 77489.03 | 69636.55 | 69636.55 | Steve Rumble |  | 27-Nov-19 | 26-Oct-20 | 11-Nov-19 | 11-Nov-19 | 24-Feb-20 |  | Lines |  | 0
453146 | 453146 (WO 318023) 9383 Islington Ave | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 28-Jan-19 |  |  | 62571.31 | 52862.36 | 62571.31 | 62571.31 | Steve Rumble | Somervl | 12-Apr-19 | 21-Jun-21 | 01-Apr-19 | 14-Mar-19 | 16-Apr-20 | Customer | Customer |  | 0
453167 | (WO318081) 28 Main St West Building | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 30-Nov-20
453170 | 453170 - PARENT W.O. FOR UNPLANNED/BELL 18-068 | 815 - Addiscott | 111116 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 29-Apr-20 |  |  | 12511.5 | 8748.64 | 12511.5 | 12511.5 | Macdonald, Larry |  | 11-Sep-20 | 27-Jan-21 | 13-Jul-20 | 07-Oct-20 | 07-Oct-20 | Filler | Filler |  | 0
453178 | 453178 (WO 318101) 329-343 Carrville Rd | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 30-Oct-19 |  |  | 184396.28 | 189600.33 | 184396.28 | 184396.28 | Macdonald, Larry | Conelco | 20-Jan-20 | 17-Aug-20 | 09-Dec-19 | 21-Nov-19 | 18-Feb-20 |  |  |  | 0
453190 | 453190 (WO 318134) National Homes Bradford Ph 2 | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 27-Sep-19 |  |  | 202003.83 | 124170.6 | 202003.83 | 202003.83 | Jeremy Wright |  | 28-Nov-19 | 29-Oct-20 | 25-Nov-19 | 23-Jun-20 | 08-Jul-20 | Customer | Customer |  | 0
453203 | 453203 (WO 318171) Dufferin & Langstaff Shell Station Development, Vaughan | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Corriveau, Tom N | Alectra Utilities | 27-Mar-20 |  |  | 281807.35 | 135848.81 | 281807.35 | 281807.35 | Macdonald, Steve | K-Line | 08-Sep-20 | 01-Nov-21 | 24-Aug-20 | 29-Sep-20 | 30-Oct-20 |  |  |  | 0
453211 | (WO 318186) Bollards for Switchgear on Zenway, Vaughan | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2020 | O'Gay, Brian | Alectra Utilities |  |  |  | 0 | 0 | 7000 | 7000 | Persaud, Ryan |  |  | 21-Jun-21 | [6 empty] | 0
453264 | 453264 (WO 318299) King Rd & McCachen St | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 06-May-20 |  |  | 29391.35 | 183238.38 | 29391.35 | 29391.35 | Chris Hagan |  | 31-Aug-20 | 02-Aug-23 | 24-Aug-20 | 15-Jul-20 | 04-Nov-20 |  | Lines |  | 0
453268 | 453268 (WO 318309) 7290 Major Mackenzie D | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 11-Dec-18 |  |  | 166037.98 | 182101.84 | 166037.98 | 166037.98 | Dave Lindsay | Transpw | 08-Mar-19 | 23-Aug-21 | 21-Feb-19 | 25-Apr-19 | 12-Nov-20 | Customer | Customer |  | 0
453276 | 453276 (WO 318356) Wycliffe the Promenade | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 31-Oct-19 |  |  | 315394.95 | 289736.2 | 315394.95 | 315394.95 | Steve Rumble |  | 07-Feb-20 | 26-Oct-20 | 16-Dec-19 | 09-Dec-19 | 28-May-20 | Customer | Customer |  | 0
453289 | 453289 (WO 318387) Industrial Bldg on Hillmount | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Cranley, Stephen | Alectra Utilities | 19-Feb-19 |  |  | 143476.78 | 146549.4 | 143476.78 | 143476.78 | Steve Rumble | Somervl | 11-Apr-19 | 28-Jan-21 | 04-Apr-19 | 03-Jun-19 | 29-May-20 | Customer | Customer |  | 0
453295 | 453295 (WO 318398) Barrie Recycling- Ser. Upgrade | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 14-Feb-19 |  |  | 59364.68 | 45290.43 | 59364.68 | 59364.68 | Lotto, Jay | HapAmp | 08-Apr-19 | 17-Jul-22 | 26-Mar-19 | 09-Jul-20 | 06-Oct-20 | Customer | Customer |  | 0
453297 | 453297 (WO 318400) - 948 FULLER AVE - HOSPICE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 08-Nov-19 |  |  | 75110.91 | 63533.61 | 75110.91 | 75110.91 | Jeremy Wright | HapAmp | 11-Dec-19 | 21-Jun-21 | 03-Dec-19 | 19-Dec-19 | 14-Jan-20 | Locates | Lines |  | 0
453305 | 453305 - 8399 KIPLING AVE. UNPLANNED/RELOCATE U/G PRIMARY CONDUCTOR | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 13-Oct-20 |  |  | 33834.07 | 29869.5 | 33834.07 | 33834.07 | Lamb, Tim | Transpw | 07-Dec-20 | 16-May-22 | 23-Nov-20 | 18-Nov-20 | 24-Nov-20 |  |  |  | 0
453333 | 453333 - PARENT W.O. FOR UNPLANNED/18-042 | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 14-Aug-20 |  |  | 24421.07 | 18498.25 | 24421.07 | 24421.07 | Macdonald, Larry |  | 08-Oct-20 | 17-Dec-21 | 05-Oct-20 | 10-Nov-20 | 11-Nov-20 | Filler | Filler |  | 0
453360 | 453360 (WO 318496) Relocate Poles (Hwy 50 @ Major Mac) | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE | VerHigh | Infrast | 2020 | Corriveau, Tom N | Alectra Utilities | 13-Feb-20 |  |  | 368095.12 | 473932.23 | 368095.12 | 368095.12 | Macdonald, Steve | K-Line | 17-Jul-20 | 27-Jan-22 | 15-Jun-20 | 25-May-20 | 13-Jun-20 |  |  |  | 0
453376 | 453376 (WO 318520) 11201 Keele St, Vaughan, ON | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Stephens, Barry N. | Alectra Utilities | 06-Feb-19 |  |  | 40930.01 | 42848.19 | 40930.01 | 40930.01 | Steve Rumble | Somervl | 31-Jul-19 | 06-Jun-21 | 18-Jul-19 | 09-Mar-20 | 01-Apr-20 | Customer | Customer |  | 0
453377 | (WO318521) 7700 Bayview Ave | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Nov-20
453387 | 453387 (WO 318536) Nashville Heights - Barons Property | 815 - Addiscott | 101887 | Active | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 24-Sep-20 |  |  | 925610.7 | 913635.53 | 925610.7 | 925610.7 | Chris Hagan | Transpw | 22-Jan-21 | 26-Jul-23 | 05-Oct-20 | 01-Oct-20 | 07-Dec-20 |  |  |  | 0
453389 | 453389 (WO 318541) 343,349,355 ELGIN MILLS RD | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | Penner, Mitchell | Alectra Utilities | 10-Jan-20 |  |  | 84558.25 | 85650.31 | 84558.25 | 84558.25 | Steve Rumble | Transpw | 07-Feb-20 | 24-Aug-20 | 27-Jan-20 | 12-Feb-20 | 24-Feb-20 | Contractor | Contractor |  | 0
453405 | (WO318591) 2 Canada's Wonderland Dr | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Stephens, Barry N. | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Nov-20
453416 | 453416 (WO 318604) 6220 Highway 7 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Stephens, Barry N. | Alectra Utilities | 29-Oct-18 |  |  | 59857.15 | 54378.88 | 59857.15 | 59857.15 | Steve Rumble | Somervl | 01-Feb-19 | 16-Feb-21 | 18-Jan-19 | 01-Nov-19 | 14-Jun-20 | Customer | Customer |  | 0
453420 | (WO318613) 7615 Keele Street | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Stephens, Barry N. | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Nov-20
453423 | 453423 (WO 318616) 2019 Pad TX Repl. - Batch 1 | 815 - Addiscott | 101508 | Active | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 07-Nov-19 |  |  | 345434.7 | 135622.02 | 351896.41 | 345434.7 | Chris Hagan | Somervl | 10-Mar-20 | 26-Jul-23 | 06-Jan-20 | 24-Jun-20 | 10-Dec-20 | Filler | Filler |  | -6,461.71
453450 | 453450 (WO 318677) 14314 YONGE ST - Retirement | 825 - Patterson | 101791 | Active | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 12-May-20 |  |  | 59909.88 | 63335.4 | 59909.88 | 59909.88 | Cory Ruiter | Somervl | 07-Aug-20 | 26-Jul-23 | 29-Jul-20 | 22-Jun-20 | 30-Jun-20 |  |  |  | 0
453460 | 453460 (WO 318688) Hydro Relocation,MTO INITIATED | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Lacombe, Joel | Alectra Utilities | 10-Apr-19 |  |  | 51913 | 52378.46 | 51913 | 51913 | Morrow, Joe |  | 27-Apr-20 | 06-Apr-22 | 14-Apr-20 | 03-Jun-20 | 10-Jun-20 | MC/PUCC Permit | MC/PUCC Permit |  | 0
453486 | 453486 (WO 318720) 2019 Cable Injection - (M37) - Woodbine & 14th | 815 - Addiscott | 150022 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 25-Jan-19 |  |  | 838173 | 726143.02 | 838173 | 838173 | Lamb, Tim | Nvinium | 31-Dec-20 | 06-May-21 | 12-Dec-19 | 12-Dec-19 | 31-Dec-20 | Customer | Contractor |  | 0
453488 | 453488 (WO 318722) 2019 Cable Injection - (V01) - Yonge, Steeles, Bathurst, Centre | 815 - Addiscott | 150014 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 25-Jan-19 |  |  | 828153 | 0 | 828153 | 828153 | Lamb, Tim | Nvinium | 31-Dec-20 | 31-Dec-20 | 02-Jan-20 |  |  | Contractor | Contractor |  | 0
453489 | 453489 (WO 318723) 2019 Cable Injection - (V36) - Steeles & Pinevalley | 815 - Addiscott | 150021 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 25-Jan-19 |  |  | 579193 | 84950.81 | 579193 | 579193 | Lamb, Tim | Nvinium | 02-Dec-19 | 19-Jul-21 | 22-Apr-19 | 22-Apr-19 | 14-Aug-20 |  | Contractor |  | 0
453490 | 453490 (WO 318724) 2019 Cable Injection - (V37) - Langstaff & Weston | 815 - Addiscott | 150134 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 25-Jan-19 |  |  | 1474888 | 1108537.68 | 1474888 | 1474888 | Lamb, Tim | Nvinium | 02-Dec-19 | 05-Aug-21 | 22-Apr-19 | 17-Jun-19 | 14-Aug-20 | Customer | Contractor |  | 0
453491 | 453491 (WO 318725) 2019 Cable Injection - (V18) - Major Mackenzie & Keele | 815 - Addiscott | 150025 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 03-Dec-18 |  |  | 1093542 | 861217.38 | 1093542 | 1093542 | Lamb, Tim | Nvinium | 02-Dec-19 | 25-Oct-21 | 22-Apr-19 | 08-Mar-19 | 14-Aug-20 |  | Contractor |  | 0
453514 | 453514 (WO 318759) Sandstorm Phase 7C | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 05-Feb-20 |  |  | 271575.21 | 230139.53 | 271575.21 | 271575.21 | Lotto, Jay | Transpw | 18-Sep-20 | 25-Nov-20 | 06-Aug-20 | 20-Jul-20 | 14-Aug-20 |  |  |  | 0
453521 | 453521 (WO 318769) 30 ERIC T SMITH WAY, AURORA | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 09-Jan-19 |  |  | 39662.3 | 28579.41 | 39662.3 | 39662.3 | Steve Rumble | Somervl | 02-Jul-19 | 19-Oct-20 | 19-Jun-19 | 08-Jan-20 | 17-Jan-20 | Customer | Customer |  | 0
453527 | 453527 (WO 318776) 6TH LINE AND SIMCOE RD, BRADFORD | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 05-Feb-20 |  |  | 266195.3 | 255158.4 | 266195.3 | 266195.3 | Lotto, Jay | Transpw | 24-Jul-20 | 09-Nov-20 | 10-Jun-20 | 08-Jul-20 | 07-Aug-20 |  |  |  | 0
453532 | (WO318784) 14 MILL STREET DEVELOPMENT IN TOTTENHAM ( Customer Driven) | 825 - Patterson | 101355 | Inactive | 99 | CANCELLED |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 0 | ($6,015.77) |  | 0 | Persaud, Ryan |  |  | 06-Jun-21
453544 | 453544 (WO 318798) Left-Behind Cable Replacement. V01 7200 YONGE ST | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-Mar-19 |  |  | 280060.19 | 292622.23 | 222856 | 280059.71 | Lamb, Tim | Transpw | 30-May-19 | 08-Mar-21 | 01-May-19 | 17-Aug-20 | 21-Oct-20 | Filler | Filler |  | 57,203.71
453545 | 453545 (WO 318799) Left-Behind Cable Replacement. V02 DORIAN PL AND FEE AV | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 04-May-20 |  |  | 231161.55 | 191990.2 | 231161.55 | 231161.55 | Lamb, Tim | Transpw | 11-Sep-20 | 08-Mar-21 | 04-Aug-20 | 13-Jul-20 | 21-Oct-20 |  | Lines |  | 0
453551 | 453551 (WO 318818) 60 & 70 QUEEN STREET SOUTH, TOTTENHAM | 825 - Patterson | 101828 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 11-Sep-19 |  |  | 42488.94 | 24128.98 | 42488.94 | 42488.94 | Jeremy Wright |  | 04-Oct-19 | 05-Jan-22 | 01-Oct-19 | 14-Dec-19 | 25-Aug-20 | Lines | Customer |  | 0
453571 | 453571 (WO 318861) I & C king's landing Phase II | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 16-Aug-19 |  |  | 63636.98 | 64386.38 | 63636.98 | 63636.98 | Chris Hagan | Transpw | 12-Nov-19 | 02-Feb-21 | 29-Oct-19 | 24-Sep-19 | 04-Nov-20 |  | Lines |  | 0
453575 | (WO318866) 2019 Distribution Automation. 370 NORTH RIVERMEDE RD, VAUGHAN | 815 - Addiscott | 2019 Distribution Automation | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Lamb, Tim |  |  | 13-Nov-18
453576 | (WO318867) 2019 Distribution Automation. 2 BRADWICK DR, VAUGHAN | 815 - Addiscott | 2019 Distribution Automation | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Lamb, Tim |  |  | 14-Nov-19
453577 | (WO318868) 2019 Distribution Automation. 70 TIGI CRT, VAUGHAN | 815 - Addiscott | 2020 Distribution Automation | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Lamb, Tim |  |  | 14-Nov-19
453578 | (WO318869) 2019 Distribution Automation. 51 WALTON DR, AURORA | 815 - Addiscott | 2020 Distribution Automation | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Lamb, Tim |  |  | 14-Nov-19
453579 | (WO318870) 2019 Distribution Automation. 33 BIRKSHIRE DR, AURORA | 815 - Addiscott | 2019 Distribution Automation | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Lamb, Tim |  |  | 14-Nov-19
453590 | 453590 (WO 318883) JU HE2018-147 Rogers | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 14-May-20 |  |  | 15944.57 | 12950.06 | 15944.57 | 15944.57 | Macdonald, Larry |  | 04-Sep-20 | 05-Jul-22 | 13-Jul-20 | 24-Sep-20 | 24-Sep-20 | Filler | Filler |  | 0
453596 | 453596 (WO 318889) MAJOR MACKENZIE DR E - MARKHAM RD TO NINTH LINE- METROLINX CROSSING #ST780 | 815 - Addiscott | 150591 | Active | 99 | COMPLETE | High | MLinx | 2020 | Vande Kuyt, Greg | Alectra Utilities | 21-Oct-19 |  |  | 1367668.26 | 1402414.12 | 1055185.8 | 1305794.26 | Shane Christopher | Transpw | 06-Mar-20 | 26-Jul-23 | 02-Dec-19 | 06-Apr-20 | 10-Nov-20 | Contractor | Contractor |  | 250,608.46
453605 | (WO 318899) TESTON RD & KEELE ST | 815 - Addiscott | 150591 | Inactive | 99 | CANCELLED |  |  | 2020 | Vande Kuyt, Greg | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Jul-21
453608 | 453608 (WO 318902) LANGSTAFF RD & KEELE ST RAILWAY- Metrolinx Electrical | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE | High | MLinx | 2020 | Vande Kuyt, Greg | Alectra Utilities | 09-Dec-19 |  |  | 1893137.89 | 2020043.89 | 1553581.89 | 1896346.09 | Shane Christopher | Transpw | 29-May-20 | 19-Apr-21 | 24-Feb-20 | 09-Apr-20 | 02-Oct-20 | COVID19 | MC/PUCC Permit |  | 342,764.20
453621 | 453621 - Riverwalk Meadows | 815 - Addiscott | 101887 | Active | 99 | COMPLETE | Medium | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 25-Nov-19 |  |  | 114427.74 | 120991.19 | 114427.74 | 114427.74 | Shane Christopher | Transpw | 15-Jul-20 | 26-Jul-23 | 29-May-20 | 11-May-20 | 14-Jul-20 | Customer | Customer |  | 0
453627 | 453627 (WO 318925) 8 Truman Road, Barrie | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 11-Oct-19 |  |  | 44390.45 | 55123.19 | 44390.45 | 44390.45 | Jeremy Wright |  | 13-Dec-19 | 31-Aug-22 | 15-Nov-19 | 25-Jan-20 | 31-Jan-20 | Customer | Customer |  | 0
453636 | 453636 (WO 318938) METROLINX CROSSIING #ST773 EUREKA STREET - HWY 7 TO PAVILLION STREET, MARKHAM | 815 - Addiscott | 150591 | Inactive | 99 | COMPLETE | High | MLinx | 2020 | Vande Kuyt, Greg | Alectra Utilities | 09-Dec-19 |  |  | 297476.26 | 311333.21 | 297476.26 | 297476.26 | Shane Christopher | Transpw | 03-Apr-20 | 25-Jan-21 | 24-Feb-20 | 11-Mar-20 | 09-Apr-20 |  | Contractor |  | 0
453637 | 453637 (WO 318939) JU HE2018-149 Rogers PINE VALLEY DR FROM LANGSTAFF RD. TO HWY 7 | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 27-Nov-19 |  |  | 29450.12 | 44442.04 | 29450.12 | 29450.12 | Macdonald, Larry |  | 17-Dec-19 | 01-Nov-21 | 13-Dec-19 | 18-Feb-20 | 25-Feb-20 | Filler | Filler |  | 0
453640 | 453640 (WO 318944) 57 & 59 Bridlefield Lane | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 23-Jun-20 |  |  | 89046.39 | 65747.38 | 89046.39 | 89046.39 | Steve Rumble | Transpw | 14-Jul-20 | 29-Oct-20 | 29-Jun-20 | 03-Jul-20 | 15-Jul-20 |  |  |  | 0
453657 | (WO318966) 81 McPherson St | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Stephens, Barry N. | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 02-Jan-19
453660 | (Wo 318970) TRCA Pole Relocation | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2020 | O'Gay, Brian | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 24-Aug-20
453687 | (WO319000) 60 VIA RENZO DR. - RICHMOND HILL | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2020 | O'Gay, Brian | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 24-Aug-20
453688 | 453688 (WO 319001) BELL FARM ROAD (ST. VINCENT TO DUCKWORTH ST), BARRIE | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  | Infrast | 2020 | Pelleja, Emily | Alectra Utilities | 16-Jul-20 |  |  | 197759.41 | 160715.15 | 197759.41 | 197759.41 | Dan Kish | K-Line | 14-Aug-20 | 22-Sep-22 | 27-Jul-20 | 23-Jul-20 | 20-Aug-20 |  | Customer |  | 0
453699 | 453699 (WO 319014) 221 CAMLAREN CRESCENT | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 11-Oct-19 |  |  | 65138.54 | 63792.15 | 65138.54 | 65138.54 | Macdonald, Larry | Transpw | 25-Nov-19 | 15-Dec-21 | 18-Nov-19 | 25-Nov-19 | 15-Jan-20 | Contractor | Lines |  | 0
453801 | 453801 - 2020 POLE REPLACEMENT - CN CROSSING - 14TH AVE/ALDEN RD, MARKHAM | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 15-Jun-20 |  |  | 114170.53 | 149827.54 | 162770.53 | 114170.53 | Macdonald, Steve | K-Line | 18-Dec-20 | 15-Mar-21 | 07-Dec-20 | 07-Dec-20 | 24-Dec-20 |  | Contractor |  | -48,600.00
453802 | 453802 (WO 319125) DA - AB‐B25 - 31 Poyntz Street - Air Break to Automated 44kV - Barrie | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 04-Sep-19 |  |  | 268709.59 | 349602.92 | 268709.59 | 268709.59 | Dan Kish |  | 18-Oct-19 | 16-Feb-21 | 09-Sep-19 | 11-Oct-19 | 17-Jan-20 | Locates | Locates |  | 0
453813 | 2020 POLE REPLACEMENT 4TH LINE AND CPP RAIL TOTTENHAM | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 21-Oct-20 |  |  | 90049.49 | 57320.2 | 90049.49 | 90049.49 | Dan Kish |  | 17-Dec-20 | 22-Feb-21 | 07-Dec-20 | 17-Nov-20 | 23-Nov-20 |  |  |  | 0
453833 | 453833 (WO 319169) 251 Rodinea Rd | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 25-Mar-19 |  |  | 47831.39 | 39915.28 | 47831.39 | 47831.39 | Dave Lindsay | Somervl | 06-May-19 | 23-Aug-21 | 26-Apr-19 | 23-Sep-19 | 20-Oct-20 | Customer | Customer |  | 0
453835 | (WO319174) STEELCASE RD WEST - 31 | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 1771.44 |  | 0 | Persaud, Ryan |  |  | 01-Feb-21
453875 | 453875 (WO 319217) 430 HOLLAND STREET WEST | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 14-Jun-19 |  |  | 39716.75 | 28081.15 | 39716.75 | 39716.75 | Jeremy Wright | HapAmp | 05-Jul-19 | 30-Mar-22 | 27-Jun-19 | 04-Sep-19 | 11-May-20 | Customer | Customer |  | 0
453888 | 453888 - 190 KENNEDY STREET WEST/INSPECT & CONNECT | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 25-Sep-19 |  |  | 91956.43 | 85314.44 | 91956.43 | 91956.43 | Steve Rumble |  | 21-Oct-19 | 17-Aug-20 | 15-Oct-19 | 22-Apr-20 | 22-Apr-20 | Customer | Customer |  | 0
453889 | 453889 (WO 319234) OH & UG RELOCATION. Phase 1.2 | 815 - Addiscott | 150343 | Inactive | 99 | COMPLETE | High | ICM | 2020 | Corriveau, Tom N | Alectra Utilities | 28-Nov-19 |  |  | 3964469.46 | 3947526.94 | 3913848.13 | 3964469.46 | Macdonald, Steve | K-Line | 04-Aug-20 | 03-Aug-21 | 06-Jan-20 | 17-Dec-19 | 30-Jun-20 | Contractor |  |  | 50,621.33
453891 | 453891 (WO 319236) - 8 North Village Way, Barrie | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 18-Nov-19 |  |  | 104160.42 | 98686.93 | 104160.42 | 104160.42 | Lotto, Jay | Transpw | 17-Dec-19 | 15-Aug-22 | 04-Dec-19 | 24-Feb-20 | 19-Mar-20 | Customer | Customer |  | 0
453906 | 453906 (WO 319263) HE2018-154 - Rogers DUFFERIN AND CENTRE STREET | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 26-Aug-19 |  |  | 5288.08 | 6061.73 | 5288.08 | 5288.08 | Macdonald, Larry |  | 10-Mar-20 | 14-Dec-21 | 10-Mar-20 | 06-Feb-20 | 06-Feb-20 |  |  |  | 0
453913 | 453913 (WO 319270) POLE RELOCATIONS JOHN STREET, BAYVIEW AVENUE TO RODDICK ROAD | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Corriveau, Tom N | Alectra Utilities | 04-Mar-20 |  |  | 94108.43 | 96104.45 | 94108.43 | 94108.43 | Macdonald, Steve | K-Line | 29-May-20 | 06-Apr-21 | 04-May-20 | 25-May-20 | 04-Jun-20 |  |  |  | 0
453921 | 453921 - M44 MINI-RUPTER REPLACEMENTS/CHILD WO - M44 2019 CABLE INJ | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Lamb, Tim |  | 13-Dec-19 | 14-Sep-20 | 13-Dec-19 | 24-Jan-20 | 24-Jan-20 | Lines | Lines
453925 | 453925 (WO 319284) 150 VIA RENZO DRIVE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | VerHigh | Indust | 2020 | Stephens, Barry N. | Alectra Utilities | 01-May-19 |  |  | 77726.56 | 68890.82 | 77726.56 | 77726.56 | Steve Rumble | Somervl | 30-Aug-19 | 17-Feb-21 | 15-Aug-19 | 17-Oct-19 | 02-Jun-20 | Contractor | Customer |  | 0
453934 | 453934 (WO 319294) MILL ST, TOTTENHAM | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE | VerHigh | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 27-Jan-20 |  |  | 229000.83 | 221381.2 | 229000.83 | 229000.83 | Lotto, Jay | Transpw | 19-Jun-20 | 22-Nov-21 | 10-Jun-20 | 01-Jun-20 | 15-Jun-20 |  |  |  | 0
453938 | 453938 (WO 319299) 50 Cityview | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 04-Mar-20 |  |  | 46545.94 | 35686.31 | 46545.94 | 46545.94 | Chris Hagan | Somervl | 13-Jul-20 | 10-Feb-21 | 06-Jul-20 | 26-Nov-20 | 10-Dec-20 | Customer | Customer |  | 0
453941 | 453941 (WO 319302) OH and UG, Bathurst St(N. of Rutherford Rd-N. of Lebovic Campus Dr), OH,UG Reloc | 815 - Addiscott | 150343 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 06-Jun-19 |  |  | 2188418 | 1620303.74 | 2188418 | 2188418 | Macdonald, Steve | K-Line | 25-Oct-19 | 03-Oct-21 | 09-Jul-19 | 22-Jun-19 | 14-Jan-20 |  |  |  | 0
453942 | 453942 - PHASE 2.2-OH&UG RELOC-BATHURST ST(N. OF LEBOVIC CAMPUS DR-N. OF VALLEY VISTA DR) | 815 - Addiscott | 150343 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 14-Aug-19 |  |  | 1709963.41 | 1719045.08 | 2140963.41 | 1709963.41 | Macdonald, Steve | K-Line | 27-Dec-19 | 15-Nov-21 | 27-Aug-19 | 03-Sep-19 | 14-Jan-20 |  |  |  | -431,000.00
453946 | 453946 (WO 319309) 9700 9th Line | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Corriveau, Tom N | Alectra Utilities | 04-Nov-19 |  |  | 131670.9 | 133199.09 | 131670.9 | 131670.9 | Ryan Walsh | Transpw | 17-Dec-19 | 14-Dec-21 | 03-Dec-19 | 10-Feb-20 | 10-Aug-20 | Locates | Locates |  | 0
453947 | 453947 (WO 319310) Portage pkway – Jane St | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 21-Aug-20 |  |  | 296860.44 | 252878.72 | 296860.44 | 296860.44 | Shane Christopher | Transpw | 23-Oct-20 | 04-Jul-21 | 12-Oct-20 | 05-Oct-20 | 30-Oct-20 |  | Contractor |  | 0
453950 | 453950 (WO 319313) - Dunlop St: Eccles to Toronto | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 08-Nov-19 |  |  | 128287.43 | 100576.21 | 128287.43 | 128287.43 | Dan Kish | HapAmp | 24-Jan-20 | 22-Sep-22 | 06-Jan-20 | 17-Jan-20 | 09-Feb-20 | Lines |  |  | 0
453954 | 453954 (WO 319318) Pole Relocation - Kennedy Road, Bur Oak Ave & Wilfred Murison Ave | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 03-Jun-19 |  |  | 130821 | 110069.54 | 130821 | 130821 | Morrow, Joe |  | 14-Nov-19 | 12-Oct-21 | 25-Sep-19 | 23-Nov-20 | 01-Dec-20 | Customer | Customer |  | 0
453955 | 453955 - HE2019-022 - BELL | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 21-Oct-20 |  |  | 29351.54 | 20519.51 | 29351.54 | 29351.54 | Macdonald, Larry |  | 27-Nov-20 | 16-Dec-21 | 25-Nov-20 | 18-Nov-20 | 18-Nov-20 |  |  |  | 0
453972 | 453972 (WO 319340) R20SA1001 - 12871 Yonge St | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 25-Oct-19 |  | 1 | 73047.05 | 100298.85 | 73047.05 | 73047.05 | Macdonald, Steve | K-Line | 10-Mar-20 | 16-Mar-21 | 02-Mar-20 | 07-Dec-20 | 21-Dec-20 | COVID19 | COVID19 |  | 0
453973 | 453973 (WO 319341) VTS4 Feeder Integration Part 2 - Egress to Kirby Rd | 815 - Addiscott | 102352 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 30-Oct-19 |  |  | 592712.48 | 641895.66 | 592712.48 | 592712.48 | Macdonald, Steve | K-Line | 03-Feb-20 | 11-Mar-21 | 06-Jan-20 | 30-Jan-20 | 03-Dec-20 | Contractor |  |  | 0
453974 | 453974 (WO 319342) VTS4 Feeder Integration Part 2 - Kirby Rd - VTS4 to Hwy 27 | 815 - Addiscott | 102352 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 532345.23 | 987529.02 | 532345.23 | 532345.23 | Macdonald, Steve | K-Line | 01-Apr-20 | 22-Mar-21 | 02-Jan-20 | 14-Jan-20 | 29-Sep-20 | Lines |  |  | 0
453975 | 453975 (WO 319343) VTS4 Feeder Integration Part 2 - Hwy 27 - Nashville to Major Mackenzie Drive | 815 - Addiscott | 102352 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 258811.53 | 376841.92 | 258811.53 | 258811.53 | Macdonald, Steve | K-Line | 02-Mar-20 | 12-Mar-21 | 04-Feb-20 | 25-Sep-20 | 31-Oct-20 | Lines |  |  | 0
453976 | 453976 (WO 319344) VTS4 Feeder Integration Part 2 - Major Mack Drive - Islington Ave to Weston Rd | 815 - Addiscott | 102352 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 1021475.77 | 1246740.9 | 1021475.77 | 1021475.77 | Macdonald, Steve | K-Line | 08-May-20 | 26-Mar-21 | 03-Mar-20 | 08-Jun-20 | 11-Dec-20 | COVID19 |  |  | 0
453985 | 453985 (WO 319354) PERFORMANCE DRIVE - #60 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 13-May-19 |  |  | 62903.8 | 54870.57 | 62903.8 | 62903.8 | Chris Hagan | Somervl | 02-Aug-19 | 10-Feb-21 | 22-Jul-19 | 18-Jun-20 | 19-Aug-20 | Customer | Customer |  | 0
453989 | 453989 (WO 319359) 75 MAPLEVIEW DRIVE - CHARG STN | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 25-Jan-20 |  |  | 81363.13 | 65285.4 | 81363.13 | 81363.13 | Lotto, Jay | HapAmp | 28-Feb-20 | 21-Jun-21 | 24-Feb-20 | 13-Mar-20 | 16-Nov-20 | COVID19 |  |  | 0
453990 | 453990 (WO 319360) 10 AND 20 GATINEAU DR | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities | 12-Nov-19 |  |  | 179208.95 | 167003.1 | 179208.95 | 179208.95 | Steve Rumble | El-Con | 02-Dec-19 | 24-Aug-20 | 25-Nov-19 | 03-Dec-19 | 25-Feb-20 | Customer | Customer |  | 0
453991 | 453991 (WO 319362) THOMPSONS RD W AT BELLISLE RD, PENETANGUISHENE | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE | VerHigh | Subdiv | 2020 | D'Onofrio, Tony | Alectra Utilities | 10-Oct-19 |  |  | 646498.81 | 618008.29 | 646498.81 | 646498.81 | Jeremy Wright |  | 22-Dec-19 | 17-Mar-21 | 25-Nov-19 | 24-Jan-20 | 12-Aug-20 | Customer | Customer |  | 0
453994 | 453994 - 2430 Teston Rd | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 19-Jul-19 |  |  | 75806.96 | 75504.92 | 75806.96 | 75806.96 | Steve Rumble | Somervl | 28-Aug-19 | 19-Oct-20 | 12-Aug-19 | 08-Aug-19 | 19-Feb-20 |  | Lines |  | 0
454021 | 454021 (WO 319408) Pole Installation 349 ELGIN MILLS | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 17-Jan-20 |  |  | 23041.37 | 30339.2 | 23041.37 | 23041.37 | Steve Rumble | Transpw | 06-Feb-20 | 31-Aug-21 | 27-Jan-20 | 25-Feb-20 | 10-Aug-20 | Locates |  |  | 0
454070 | 454070 (WO 319457) 105 REAGANS INDUSTRIAL PARKWAY | 825 - Patterson | 101919 | Inactive | 99 | CANCELLED |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 27-Sep-19 |  |  | 77348.36 | 0 | 77348.36 | 77348.36 | Jeremy Wright | HapAmp | 12-Nov-19 | 09-Feb-21 | 04-Nov-19 |  |  | Customer | Customer |  | 0
454078 | 454078 (WO 319466) Pole Relocations JANE STREET & MAJOR MACKENZIE | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE | VerHigh | Health | 2020 | Corriveau, Tom N | Alectra Utilities | 28-Jan-20 |  |  | 86624.6 | 70237.43 | 86624.6 | 86624.6 | Steve Rumble | K-Line | 28-Feb-20 | 04-Oct-22 | 10-Feb-20 | 11-May-20 | 10-Jun-20 | Lines | Lines |  | 0
454081 | 454081 (WO 319470) Road Widening JANE STREET TO HWY 400 | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE | VerHigh | Health | 2020 | Corriveau, Tom N | Alectra Utilities | 31-Jan-20 |  |  | 219462.36 | 242487.47 | 219462.36 | 219462.36 | Macdonald, Steve | K-Line | 23-Jul-20 | 10-May-21 | 08-Jul-20 | 25-May-20 | 03-Jul-20 |  |  |  | 0
454090 | 454090 (WO 454090) VICTORIA PARK AVE. #7200 AT TORBAY RD. | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 11-Jul-19 |  |  | 146438.99 | 125853.04 | 146438.99 | 146438.99 | Steve Rumble | Somervl | 20-Sep-19 | 01-Mar-21 | 28-Aug-19 | 22-Nov-19 | 16-Sep-20 | Customer | Customer |  | 0
454091 | 454091 (WO 319482). Pole line rebuild . Extend 153M10 to Transfer MS322. Bradford PHASE 1 | 825 - Patterson | 101781 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 14-Jul-20 |  |  | 1190447.54 | 775940.47 | 1190447.54 | 1190447.54 | Jeremy Wright | K-Line | 23-Oct-20 | 08-Mar-21 | 20-Jul-20 | 18-Aug-20 | 23-Nov-20 | Contractor |  |  | 0
454094 | (WO319486) BARONS STREET & MAJOR MACKENZIE DRIVE | 815 - Addiscott | PARENT W.O FOR UNPLANNED | Inactive | 99 | CANCELLED |  |  | 2020 | Penner, Mitchell | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 07-May-19
454101 | 454101 (WO 319493) 16TH AVENUE - Insulator Repl -2020 | 815 - Addiscott | 150009 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 06-Nov-19 |  |  | 206395.43 | 228212.33 | 206395.43 | 206395.43 | Morrow, Joe |  | 10-Mar-20 | 09-Dec-20 | 04-Feb-20 | 03-Jul-20 | 26-Aug-20 | COVID19 |  |  | 0
454102 | 454102 (WO 319494) HUNTINGTON RD - INSULATOR REPL - 2020 Project | 815 - Addiscott |  | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 06-Nov-19 |  |  | 44829.27 | 51308 | 44829.27 | 44829.27 | Morrow, Joe |  | 16-Mar-20 | 20-Jul-20 | 11-Mar-20 | 24-Jan-20 | 13-Mar-20 |  |  |  | 0
454106 | 454106 (WO 319498) Hydro Relocation RUTHERFORD RD AND MCGILLIVRAY ROAD, VAUGHAN | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 16-Dec-19 |  |  | 344136.58 | 255567.1 | 344136.58 | 344136.58 | Morrow, Joe |  | 05-Feb-20 | 03-Aug-21 | 06-Jan-20 | 13-Jan-20 | 25-Feb-20 | Lines |  |  | 0
454110 | 454110 (WO 319503) A02 Steeplechase Ave Cable Replacement ( Incremental Work) | 815 - Addiscott | 150254 | Active | 99 | COMPLETE | High | Reliab | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 08-Nov-19 |  |  | 2110904.21 | 2221843.98 | 2110904.21 | 2110904.21 | Lamb, Tim | Transpw | 25-Nov-20 | 26-Jul-23 | 18-May-20 | 19-May-20 | 28-Sep-20 |  |  |  | 0
454111 | 454111 (WO 319504) V15 Jardin Dr Cable Replacement ( Incremental Work) | 815 - Addiscott | 150257 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-Oct-19 |  |  | 1687606.24 | 1788665.77 | 1687606.24 | 1687606.24 | Lamb, Tim | Transpw | 08-Sep-20 | 08-Mar-21 | 02-Jun-20 | 19-May-20 | 07-Aug-20 |  |  |  | 0
454119 | 454119 (WO 319512) M41 - Woodbine and Elgin Mills (2020 Cable Injection) | 815 - Addiscott | 150019 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 113676.99 | 65593.76 | 113676.99 | 113676.99 | Lamb, Tim | Nvinium | 31-Dec-19 | 28-Jan-21 | 25-Nov-19 | 26-Feb-20 | 04-Dec-20 | Contractor | Contractor |  | 0
454120 | 454120 (WO 319513) M43 - John and Woodbine (2020 Cable Injection) | 815 - Addiscott | 150026 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 1029638.15 | 1075643.72 | 1029638.15 | 1029638.15 | Lamb, Tim | Nvinium | 30-Dec-20 | 16-Feb-21 | 06-Jan-20 | 08-Jun-20 | 04-Dec-20 | Contractor |  |  | 0
454121 | 454121 (WO 319514) V38 - Rutherford and Weston Rd (2020 Cable Injection) | 815 - Addiscott | 150261 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 1413868.92 | 809700.12 | 1413868.92 | 1413868.92 | Lamb, Tim | Nvinium | 31-Dec-20 | 16-Feb-21 | 25-Nov-19 | 20-Jan-20 | 31-Dec-20 | Contractor |  |  | 0
454124 | 454124 (WO 319517) V37 - Langstaff and Wesotn Rd (2020 Cable Injection) | 815 - Addiscott | 150134 | Active | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 1538880.95 | 1344425.82 | 1538880.95 | 1538880.95 | Lamb, Tim | Nvinium | 30-Dec-20 | 26-Jul-23 | 06-Jan-20 | 15-Jun-20 | 04-Dec-20 | Contractor |  |  | 0
454126 | 454126 (WO 319519) V43 - Hwy 7 and Pine Valley Dr (2020 Cable Injection) | 815 - Addiscott | 151121 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 1019464.22 | 868940.29 | 1019464.22 | 1019464.22 | Lamb, Tim | Nvinium | 30-Dec-20 | 16-Feb-21 | 06-Jan-20 | 20-Jan-20 | 04-Dec-20 | Contractor |  |  | 0
454127 | 454127 - ICI TX UPGRADE/700 CENTRE ST Ex. Walmart Upgrade | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | VerHigh | Grocery | 2020 | Dibratto, Susan | Alectra Utilities | 27-Feb-20 |  |  | 72010.4 | 75946.87 | 72010.4 | 72010.4 | Steve Rumble | Somervl | 15-May-20 | 24-Feb-21 | 04-May-20 | 19-Jun-20 | 03-Aug-20 | Customer | Customer |  | 0
454129 | 454129 - 141 NEW HUNTINGTON | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Dibratto, Susan | Alectra Utilities | 26-Jun-19 |  |  | 97149.13 | 81691.57 | 97149.13 | 97149.13 | Steve Rumble | Somervl | 18-Oct-19 | 10-Aug-20 | 07-Oct-19 | 30-Jan-20 | 05-Mar-20 | Customer | Customer |  | 0
454132 | 454132 - UNPLANNED/JOINT USE HE2019-043 | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 14-Feb-20 |  |  | 9760.73 | 6813.67 | 9760.73 | 9760.73 | Morrow, Joe |  | 29-May-20 | 24-Jan-22 | 30-Mar-20 | 03-Jun-20 | 10-Jun-20 |  |  |  | 0
454144 | 454144 - 41 KEYES COURT | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 26-Sep-19 |  |  | 92480.07 | 94949.99 | 92480.07 | 92480.07 | Steve Rumble | Somervl | 02-Dec-19 | 10-Aug-20 | 18-Nov-19 | 13-Dec-19 | 27-Jan-20 | Customer | Customer |  | 0
454145 | 454145 - 21 Keyes Court Vaughan | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 11-Jul-19 |  |  | 105660.6 | 85658.07 | 105660.6 | 105660.6 | Steve Rumble | Somervl | 25-Sep-19 | 19-Oct-20 | 06-Sep-19 | 02-Oct-19 | 05-Mar-20 | Contractor | Customer |  | 0
454148 | 454148 - 615 Bowes Rd, Vaughan | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | High | Comm | 2020 | Dibratto, Susan | Alectra Utilities | 10-Sep-19 |  |  | 162300.68 | 135114.3 | 162300.68 | 162300.68 | Steve Rumble | Somervl | 12-Nov-19 | 25-Feb-21 | 22-Oct-19 | 24-Oct-19 | 17-Jul-20 | Contractor | Customer |  | 0
454151 | 454151 (WO 319545) Remington Enterprise Temp | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 24-Jul-19 |  |  | 94739.66 | 97887.84 | 94739.66 | 94739.66 | Steve Rumble | Somervl | 31-Oct-19 | 19-Oct-20 | 21-Oct-19 | 20-Jan-20 | 05-Feb-20 | Customer | Customer |  | 0
454159 | 454159 (WO 319554)–Rear Lot Remediate–E/O Queen St. to Eastern Ave N/O of Greeenway St–Tott | 825 - Patterson | 150043 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 10-Jan-20 |  |  | 2565896.88 | 0 | 2565896.88 | 2565896.88 | Persaud, Ryan |  | 21-Dec-20 | 29-Nov-21 | 05-Oct-20 | 05-Oct-20 | 21-Dec-20 |  | Contractor |  | 0
454162 | (WO 319558) Joint Use Permit # HE2019-048 RUTHERFORD ROAD - WEST OF HWY 27 | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 03-Dec-19 |  |  | 6457.55 | 4175.25 | 6457.55 | 6457.55 | Macdonald, Larry |  | 10-Jan-20 | 15-Dec-21 | 06-Jan-20 | 13-Jan-20 | 13-Jan-20 | Filler | Filler |  | 0
454225 | 454225 (WO 319624) MCCACHEN ST & KING ROAD | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | Penner, Mitchell | Alectra Utilities | 23-Sep-20 |  |  | 89030.29 | 95669.33 | 89030.29 | 89030.29 | Dave Lindsay | Transpw | 23-Nov-20 | 04-May-23 | 09-Nov-20 | 16-Oct-20 | 16-Dec-20 |  | Customer |  | 0
454242 | 454242 (WO 319644) Stouffville Rd & Hwy 404 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 03-Sep-20 |  |  | 43331.61 | 34706.55 | 43331.61 | 43331.61 | Chris Hagan | Somervl | 13-Nov-20 | 03-Aug-21 | 02-Nov-20 | 28-Sep-20 | 07-Dec-20 |  | Customer |  | 0
454243 | (WO 319645) Residential Service Adjustment -31 MARK ST. AURORA | 815 - Addiscott | 101355 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 24-Aug-20
454244 | 454244 (WO 319646) 300 Gibraltar Road | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Low | Indust | 2020 | Dibratto, Susan | Alectra Utilities | 03-Oct-19 |  |  | 127510.38 | 119883.11 | 127510.38 | 127510.38 | Chris Hagan | Somervl | 09-Jan-20 | 09-Feb-21 | 19-Dec-19 | 03-Jun-20 | 15-Oct-20 | Customer | Customer |  | 0
454249 | 454249 (WO 319651) JU #HE2019-056 - NINTH LINE AND DONALD COUSENS PARKWAY | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 15-Oct-19 |  |  | 4475.12 | 5403.69 | 4475.12 | 4475.12 | Macdonald, Larry |  | 13-Mar-20 | 15-Dec-21 | 09-Mar-20 | 27-Feb-20 | 27-Feb-20 |  |  |  | 0
454250 | 454250 (WO 319654) VTS4 - MMD Pine Valley-Weston | 815 - Addiscott | 102352 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 |  |  | 438263.26 | 584463.08 | 438263.26 | 438263.26 | Macdonald, Steve | K-Line | 23-Oct-20 | 08-Mar-21 | 14-Sep-20 | 31-Oct-20 | 11-Dec-20 | Contractor |  |  | 0
631369 | 631369 - MX - RELOC - STEELES AVE - KENNEDY TO MIDLAND | 815 - Addiscott | 150451 | Inactive | 99 | COMPLETE | High | MLinx | 2020 | Vande Kuyt, Greg | Alectra Utilities | 13-Sep-19 |  |  | 4125168.39 | 5190266.02 | 4120206.39 | 4125168.39 | Shane Christopher | Transpw | 30-Jun-20 | 18-Feb-21 | 21-Oct-19 | 13-Jan-20 | 15-Sep-20 | Locates | Contractor |  | 4,962.00
631761 | 631761 - VTS4 FEEDER INTEGRATION PART 2 - EGRESS TO KIRBY RD | 815 - Addiscott | 102352 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 30-Oct-19 |  |  | 337009.27 | 598483.97 | 337009.27 | 337009.27 | Macdonald, Steve | K-Line | 04-Dec-20 | 16-Feb-21 | 26-Oct-20 | 12-Sep-20 | 24-Dec-20 |  | Contractor |  | 0
631836 | (WO631836) 78 BRADWICK DR UNIT B | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 758.37 |  | 0 | Persaud, Ryan |  |  | 01-Feb-21
632226 | 632226 (WO 632226) DUFFERIN ST & MAURIER BLVD PROP COM DEV | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Dibratto, Susan | Alectra Utilities | 20-Jan-20 |  |  | 42475.95 | 29903.1 | 42475.95 | 43183.95 | Chris Hagan | Somervl | 03-Apr-20 | 01-Mar-21 | 23-Mar-20 | 28-May-20 | 29-Oct-20 | Customer | Customer |  | 708
632287 | 632287 - JOINT USE PERMIT #HE2019-065 - TESTON ROAD - VAUGHAN | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 27-Nov-19 |  |  | 20852.35 | 18456.79 | 20852.35 | 20852.35 | Macdonald, Larry |  | 10-Dec-19 | 01-Nov-21 | 09-Dec-19 | 08-Jan-20 | 13-Jan-20 | Filler | Filler |  | 0
632335 | 632335 - 37,39,41 AUBURN CRT, INSPECT AND CONNECT | 825 - Patterson | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 11-Feb-20 |  |  | 11560.77 | 33774.95 | 11560.77 | 11560.77 | Jeremy Wright | HapAmp | 29-May-20 | 22-Nov-21 | 19-May-20 | 13-Mar-20 | 18-Mar-20 |  |  |  | 0
632377 | 632377 - 130 ST. JOHNS SIDEROAD | 815 - Addiscott | 101919 | Inactive | 99 | COMPLETE |  | Res-ICI | 2020 | Cranley, Stephen | Alectra Utilities | 25-Nov-19 |  |  | 61145.93 | 47843.3 | 61145.93 | 61145.93 | Steve Rumble | Somervl | 06-Jan-20 | 24-Feb-21 | 16-Dec-19 | 26-Dec-19 | 03-Apr-20 | Lines | Locates |  | 0
632468 | 632468 - 110 CITATION DR | 815 - Addiscott | PARENT WORK ORDER INDUST/COMM | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 12-Nov-19 |  |  | 40377.83 | 33787.43 | 40377.83 | 40377.83 | Steve Rumble |  | 02-Dec-19 | 18-Feb-21 | 25-Nov-19 | 05-Jan-20 | 08-Jan-20 | Customer | Customer |  | 0
632636 | 632636 - 700 APPLEWOOD CRES - Demolition | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 02-Aug-19 |  |  | 4722.69 | 1227.1 | 4722.69 | 4722.69 | Dave Lindsay | N/A | 16-Sep-19 | 01-Nov-21 | 16-Sep-19 | 15-Jul-20 | 04-Nov-20 | Customer | Customer |  | 0
632678 | 632678 - PHASE 3-OH&UG RELOC-BATHURST ST(N. OF VALLEY VISTA DR-N.OF MAJOR MACKENZIE DR) | 815 - Addiscott | 150343 | Inactive | 99 | COMPLETE | High | ICM | 2020 | Corriveau, Tom N | Alectra Utilities | 23-Jun-20 |  |  | 2692160.93 | 2094814.21 | 2692160.93 | 2692160.93 | Macdonald, Steve | K-Line | 27-Nov-20 | 16-Jun-22 | 29-Jun-20 | 06-Jul-20 | 26-Oct-20 |  |  |  | 0
632704 | 632704 - POLE REPLACEMENT SUBDIVISION INCON PROPERTY | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 10-Jan-20 |  |  | 23676.88 | 24674.63 | 23676.88 | 23676.88 | Steve Rumble |  | 03-Mar-20 | 14-Oct-21 | 24-Feb-20 | 19-Feb-20 | 05-Mar-20 |  |  |  | 0
632727 | 632727 - JOINT USE PERMIT #HE2019-074 - FAIRVIEW ROAD - BARRIE | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 29-Jul-20 |  |  | 11396.13 | 9791.25 | 11396.13 | 11396.13 | Dan Kish |  | 05-Oct-20 | 16-Feb-23 | 05-Oct-20 | 03-Sep-20 | 03-Sep-20 |  |  |  | 0
632803 | 632803 - POLE RELOCATE - E/O BAYVIEW AND GREE LANE (REFER TO ATTACHMENT TAB) | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities |  |  |  | 0 | 2193.99 |  | 0 | Macdonald, Larry |  | 25-Sep-20 | 24-Feb-22 | 24-Sep-20 | 24-Sep-20 | 24-Sep-20 |  | xBy-passed
632813 | 632813 - JOINT USE PERMIT #HE2019-079 - WESTON ROAD - VAUGHAN | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 03-Feb-20 |  |  | 7888.89 | 10307.53 | 7888.89 | 7888.89 | Macdonald, Larry |  | 09-Mar-20 | 22-Sep-22 | 09-Mar-20 | 13-Feb-20 | 13-Feb-20 |  |  |  | 0
632827 | 632827 - 100 MILL ST E | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | High | Comm | 2020 | Cranley, Stephen | Alectra Utilities | 11-Nov-19 |  |  | 79007.59 | 64716.6 | 79007.59 | 79007.59 | Lotto, Jay | HapAmp | 11-Dec-19 | 18-Feb-21 | 02-Dec-19 | 03-Mar-20 | 16-Apr-20 | Customer | Customer |  | 0
632839 | 632839 - 45 RODINEA RD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Medium | Indust | 2020 | Dibratto, Susan | Alectra Utilities | 25-Nov-19 |  |  | 83105.26 | 85790.5 | 83105.26 | 83105.26 | Dave Lindsay | Somervl | 13-Jan-20 | 23-Feb-21 | 06-Jan-20 | 26-Dec-19 | 26-Sep-20 |  | Customer |  | 0
632876 | (WO 632876) GUY WIRE RELOCATION - JANE ST & AUTO VAUGHAN DR | 815 - Addiscott | 101763 | Inactive | 99 | CANCELLED |  |  | 2020 | Corriveau, Tom N | Alectra Utilities |  |  |  | 0.23 | 0 |  | 0.23 | Persaud, Ryan |  |  | 05-Aug-21
632884 | 632884 - JOINT USE PERMIT #HE2019-086 - LESLIE STREET - RICHMOND HILL | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 28-Feb-20 |  |  | 6352.79 | 10527.37 | 6352.79 | 6352.79 | Macdonald, Larry |  | 06-Apr-20 | 22-Sep-22 | 06-Apr-20 | 21-Aug-20 | 21-Aug-20 | Filler | Filler |  | 0
632908 | 632908 - POLE REPLACEMENT 2020 BATCH 1 - AURORA - 12 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 31-Oct-19 | 13 | 13 | 157616.88 | 179669.02 | 157616.88 | 157616.88 | Morrow, Joe | K-Line | 03-Feb-20 | 25-Jan-21 | 06-Jan-20 | 23-Jun-20 | 14-Jul-20 | Filler |  |  | 0
632909 | 632909 - POLE REPLACEMENT 2020 BATCH 3 - MARKHAM - 22 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 20-Nov-19 | 18 | 18 | 158711.43 | 137411.81 | 158711.43 | 158711.43 | Morrow, Joe |  | 28-Aug-20 | 25-Jan-21 | 27-Jul-20 | 21-Jul-20 | 14-Aug-20 |  |  |  | 0
632912 | 632912 - 2020 Pole Replacement Batch 2 - Markham | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 23-Oct-19 | 16 | 16 | 240046.19 | 236552.1 | 240046.19 | 240046.19 | Morrow, Joe |  | 05-Jun-20 | 15-Mar-21 | 24-Feb-20 | 13-Oct-20 | 16-Dec-20 | COVID19 | COVID19 |  | 0
632929 | JOINT USE PERMIT #HE2019-089 - MULCASTER STREET & PENETANG STREET - BARRIE | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 09-Dec-19 |  |  | 9664.34 | 6791.2 | 9664.34 | 9664.34 | Aulis, John -x |  | 13-Mar-20 | 14-Dec-21 | 09-Mar-20 | 03-Feb-20 | 05-Feb-20 |  |  |  | 0
633011 | 633011 - 2020 Pole Replacement Batch 4 - Markham | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 23-Oct-19 | 12 | 12 | 149517.69 | 115704.61 | 149517.69 | 149517.69 | Macdonald, Steve |  | 03-Feb-20 | 25-Jan-21 | 06-Jan-20 | 29-Jan-20 | 17-Mar-20 | Lines |  |  | 0
633038 | 633038 - 2020 Padmount Transformer Replacement Batch 7 - Vaughan | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 12-Dec-19 |  |  | 156654.95 | 156385.09 | 156654.95 | 156654.95 | Chris Hagan | Somervl | 09-Apr-20 | 09-Dec-21 | 17-Feb-20 | 15-Jul-20 | 22-Dec-20 | Filler | Filler |  | 0
633056 | V38 2019 Pre-Work Only For 2020 Injection | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 13-Aug-19 |  |  | 184554.6 | ($467.71) | 184554.6 | 184554.6 | Lamb, Tim | N/A | 19-Dec-19 | 24-Feb-20 | 21-Oct-19 | [5 empty] | 0
633110 | 633110 - Replace 37TV143 & 37TV115 | 815 - Addiscott | 101027 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 22-Oct-19 |  |  | 51402.56 | 0 | 51402.56 | 51402.56 | Lamb, Tim |  | 20-May-20 | 08-Mar-21 | 20-Apr-20 |  |  | Lines | Lines |  | 0
633111 | 633111 - Replace 37TV133 & 37TV162 | 815 - Addiscott | 101027 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 22-Oct-19 |  | 2 | 96472.51 | 69473.3 | 79995.51 | 96472.51 | Lamb, Tim | Somervl | 20-May-20 | 08-Mar-21 | 20-Apr-20 | 17-Oct-20 | 17-Nov-20 | Contractor | Filler |  | 16,477.00
633112 | 633112 - 2020 Switch Replacements - Replace 25TV002 & 21TV010 | 815 - Addiscott | 101027 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 30-Jul-20 |  | 2 | 51391.5 | 28638.35 | 51391.5 | 51391.5 | Lamb, Tim |  | 21-Oct-20 | 08-Mar-21 | 21-Sep-20 | 26-Oct-20 | 03-Nov-20 | Lines | Lines |  | 0
633126 | 633126 - TRANSFORMER REPLACEMENT 2020 BATCH 9 - VAUGHAN - 11 UNITS | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 07-Nov-19 |  |  | 307708.34 | 253084.46 | 314680.7 | 307708.34 | Lamb, Tim | Somervl | 02-Mar-20 | 08-Jun-21 | 27-Jan-20 | 16-Jul-20 | 21-Oct-20 | Filler | Filler |  | -6,972.36
633128 | 633128 - TRANSFORMER REPLACEMENT 2020 BATCH 11 - VAUGHAN - 23 UNITS | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 07-Nov-19 |  |  | 395325.49 | 338473.99 | 413647.21 | 395325.49 | Chris Hagan | Somervl | 20-Mar-20 | 25-May-21 | 27-Jan-20 | 15-Aug-20 | 22-Dec-20 | Filler | Filler |  | -18,321.72
633135 | 633135 - DISTRIBUTION AUTOMATION 2020 - A06SL2046 - AURORA | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-Nov-19 |  | 1 | 118516.02 | 133873.25 | 118516.02 | 118516.02 | Macdonald, Steve | K-Line | 16-Apr-20 | 25-Mar-21 | 02-Apr-20 | 12-Aug-20 | 24-Aug-20 | COVID19 | COVID19 |  | 0
633137 | 633137 - DISTRIBUTION AUTOMATION 2020 - NEW SWITCH - MARKHAM | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 25-Oct-19 |  | 1 | 67280.61 | 93693.65 | 67280.61 | 67280.61 | Macdonald, Larry | K-Line | 03-Mar-20 | 03-Aug-21 | 24-Feb-20 | 29-Jun-20 | 29-Jun-20 |  |  |  | 0
633138 | 633138 - DISTRIBUTION AUTOMATION 2020 - V25SL3013 - VAUGHAN | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 22-Jan-20 |  | 1 | 86092.5 | 102625.22 | 86092.5 | 86092.5 | Macdonald, Steve | K-Line | 15-Jul-20 | 22-Mar-21 | 08-Jul-20 | 01-Aug-20 | 12-Sep-20 | COVID19 | COVID19 |  | 0
633139 | 633139 - DISTRIBUTION AUTOMATION 2020 - V25SL3025 - VAUGHAN | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 22-Jan-20 |  | 1 | 79535.23 | 99689.98 | 79535.23 | 79535.23 | Macdonald, Steve | K-Line | 22-Jul-20 | 19-Mar-21 | 16-Jul-20 | 16-Nov-20 | 27-Nov-20 | Contractor |  |  | 0
633144 | 633144 - 2021 Padmount Transformer Replacement Batch 12 - Vaughan - 11 units | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 07-Nov-19 |  |  | 288145.77 | 209074.61 | 297599.77 | 288145.77 | Steve Rumble | Somervl | 10-Feb-20 | 02-Jun-21 | 20-Jan-20 | 02-Mar-20 | 10-Sep-20 | Filler |  |  | -9,454.00
633145 | 633145 - DISTRIBUTION AUTOMATION 2020 - 66-L6 - VAUGHAN | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-Nov-19 |  | 1 | 83413.13 | 64231.03 | 83413.13 | 83413.13 | Macdonald, Larry |  | 20-Mar-20 | 26-Mar-21 | 11-Mar-20 | 19-Feb-20 | 24-Sep-20 |  |  |  | 0
633162 | (WO 633162) Replace 2 poles at Yonge and John St. Markham | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 15-Aug-19
633163 | (WO 633163) Replace P30260 at Yonge St and Morgan Ave. Markham | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 15-Aug-19
633166 | 633166 - 670 APPLEWOOD CRES | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | High | Grocery | 2020 | Dibratto, Susan | Alectra Utilities | 06-Feb-20 |  |  | 85268.08 | 70570.95 | 85268.08 | 85268.08 | Chris Hagan | Somervl | 21-Apr-20 | 25-Feb-21 | 13-Apr-20 | 17-Mar-20 | 04-Nov-20 |  | Lines |  | 0
633201 | ICI SERVICE REMOVAL/150 & 152 DUNLOP ST W | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities |  |  |  | 0 | 9917.15 |  | 0 | Lotto, Jay |  |  | 22-Nov-21 |  | 21-Aug-20 | 21-Aug-20 | xBy-passed | xBy-passed
633320 | 633320 - 2020 SWGR REPLACEMENTS - SC13305 - 53 WHITEHORN CRES - KABAR | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 04-Nov-19 |  | 1 | 6204.5 | 5363.47 | 6204.5 | 6204.5 | Lotto, Jay |  | 24-Apr-20 | 08-Mar-21 | 20-Apr-20 | 08-Jun-20 | 08-Jun-20 |  | Filler |  | 0
633321 | 633321 - 2020 SWGR REPLACEMENTS - SC13526 - 39 BUTTERNUT DR. - KABAR | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 04-Nov-19 |  | 1 | 6204.5 | 8100.14 | 6204.5 | 6204.5 | Lotto, Jay |  | 24-Apr-20 | 15-Nov-21 | 20-Apr-20 | 09-Jun-20 | 09-Jun-20 |  |  |  | 0
633322 | 633322 - 2020 SWGR REPLACEMENTS - SC13527 - 10 DYKSTRA DR - KABAR | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 12-Nov-19 |  | 1 | 6204.5 | 4842.07 | 6204.5 | 6204.5 | Lotto, Jay |  | 01-May-20 | 03-Aug-21 | 27-Apr-20 | 10-Jun-20 | 10-Jun-20 |  |  |  | 0
633323 | 633323 - 2020 SWGR REPLACEMENTS - SC13267 - 16 CHALMERS DR - KABAR | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 06-Nov-19 |  | 1 | 5881.2 | 6055.12 | 5881.2 | 5881.2 | Lotto, Jay |  | 01-May-20 | 07-Mar-22 | 27-Apr-20 | 18-Jun-20 | 18-Jun-20 |  | Filler |  | 0
633324 | 633324 - 2020 SWGR REPLACEMENTS - SC13649 - 141 MADELAINE DR - PMH-9 | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 06-Nov-19 |  | 1 | 26639 | 26287.9 | 26639 | 26639 | Lotto, Jay |  | 27-Jul-20 | 28-Nov-21 | 27-Jul-20 | 31-Aug-20 | 01-Sep-20 |  |  |  | 0
633325 | 633325 - 2020 SWGR REPLACEMENTS - SC13501 - 116 HOLLY MEADOW RD - PMH-3 | 825 - Patterson | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 06-Nov-19 |  | 1 | 13014.47 | 12619.1 | 13014.47 | 13014.47 | Lotto, Jay |  | 28-Jul-20 | 28-Nov-21 | 28-Jul-20 | 24-Aug-20 | 25-Aug-20 |  |  |  | 0
633330 | 633330 - SWITCHGEAR REPLACEMENT 2020 - BATCH 1 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 05-Nov-19 |  | 3 | 235551.64 | 279558.87 | 235551.64 | 235551.64 | Lamb, Tim | Somervl | 28-Feb-20 | 15-Jul-21 | 22-Jan-20 | 26-Jun-20 | 26-Jun-20 | Filler | Filler |  | 0
633331 | 633331 - SWITCHGEAR REPLACEMENT 2020 - BATCH 2 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 05-Nov-19 |  | 2 | 141719.64 | 141376.38 | 141719.64 | 141719.64 | Lamb, Tim |  | 28-Feb-20 | 15-Jul-21 | 27-Jan-20 | 19-Sep-20 | 03-Oct-20 | Filler | Filler |  | 0
633332 | 633332 - SWITCHGEAR REPLACEMENT 2020 - BATCH 4 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 05-Nov-19 |  | 5 | 476514.91 | 415346.82 | 476514.91 | 476514.91 | Lamb, Tim | Somervl | 17-Jul-20 | 15-Jul-21 | 10-Jul-20 | 14-Aug-20 | 08-Dec-20 | Filler | Filler |  | 0
633333 | 633333 - SWITCHGEAR REPLACEMENT 2020 - BATCH 5 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 06-Nov-19 |  | 2 | 66110.21 | 66758.4 | 66110.21 | 66110.21 | Lamb, Tim |  | 16-Jul-20 | 08-Mar-21 | 10-Jul-20 | 09-Jul-20 | 14-Jul-20 |  |  |  | 0
633334 | 633334 - SWITCHGEAR REPLACEMENT 2020 - BATCH 7 | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 05-Nov-19 |  | 5 | 383896.99 | 381490.52 | 391261.17 | 383896.99 | Lamb, Tim | Somervl | 30-Apr-20 | 08-Mar-21 | 03-Mar-20 | 25-Jun-20 | 30-Nov-20 | Filler | Filler |  | -7,364.18
633337 | 633337 - SWITCHGEAR REPLACEMENT 2020 - BATCH 3 - REPLACE 4 SWGS | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 23-Oct-19 |  | 4 | 277402.32 | 262438.19 | 277402.32 | 277402.32 | Lamb, Tim | Somervl | 28-Sep-20 | 08-Mar-21 | 27-Jul-20 | 25-Jun-20 | 25-Jun-20 |  |  |  | 0
633338 | 633338 - SWITCHGEAR REPLACEMENT 2020 - BATCH 6 - REPLACE 4 SWGS | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 09-Jan-20 |  | 3 | 307183.99 | 232568.79 | 307183.99 | 307183.99 | Lamb, Tim | Somervl | 28-Sep-20 | 06-Apr-22 | 27-Jul-20 | 25-Jun-20 | 25-Jun-20 |  |  |  | 0
633339 | 633339 - SWITCHGEAR REPLACEMENT 2020 - BATCH 8 - REPLACE 2 SWGS | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 07-Nov-19 |  | 2 | 141785.22 | 131094.6 | 141785.22 | 141785.22 | Lamb, Tim | Somervl | 28-Sep-20 | 08-Mar-21 | 27-Jul-20 | 23-Jun-20 | 30-Jun-20 |  |  |  | 0
633340 | 633340 - SWITCHGEAR REPLACEMENT 2020 - BATCH 9 - REPLACE 5 SWGS - DEFERRED UNITS | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 23-Oct-19 |  | 3 | 184388.12 | 185665.51 | 184388.12 | 184388.12 | Lamb, Tim |  | 05-Feb-20 | 08-Mar-21 | 20-Jan-20 | 25-Jun-20 | 25-Jun-20 | Filler |  |  | 0
633385 | 633385 - CABLE REPLACEMENT, M15 LARKIN - 15TP124 TO 15TP181 | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 19-May-20 |  |  | 223029.72 | 220533.69 | 223029.72 | 223029.72 | Lamb, Tim | Transpw | 22-Jul-20 | 04-Oct-21 | 06-Jul-20 | 22-Jun-20 | 21-Oct-20 |  | Lines |  | 0
633386 | 633386 - CABLE REPLACEMENT, V08 DUFFERIN ST - 8-P42 TO V08SP3021 | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 09-Apr-20 |  |  | 233159.83 | 247057.98 | 179692.78 | 233159.83 | Lamb, Tim | Transpw | 10-Jun-20 | 04-Oct-21 | 01-Jun-20 | 15-Jun-20 | 18-Dec-20 | Contractor | Contractor |  | 53,467.05
633387 | 633387 - CABLE REPLACEMENT, M20 WIGNALL CRES - 20SW012 TO 20SU001-5 | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 01-Apr-20 |  |  | 86502.08 | 86940.67 | 86502.08 | 86502.08 | Lamb, Tim | Transpw | 12-Jun-20 | 08-Mar-21 | 01-Jun-20 | 05-Jun-20 | 21-Oct-20 | Contractor | Contractor |  | 0
633388 | 633388 - CABLE REPLACEMENT, M33 CARLTON RD - 33TP002 TO 33TP003 | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE | High | Reliab | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 01-Apr-20 |  |  | 106494.3 | 97201.52 | 106494.3 | 106494.3 | Lamb, Tim | Transpw | 12-Jun-20 | 15-Jul-21 | 01-Jun-20 | 22-Jun-20 | 21-Oct-20 | Contractor | Contractor |  | 0
633389 | 633389 - CABLE REPLACEMENT, M51 DALMENY RD - SECONDARY CABLE REPLACEMENT | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 26-May-20 |  |  | 205695.16 | 163301.41 | 205695.16 | 205695.16 | Lamb, Tim | Transpw | 21-Oct-20 | 08-Mar-21 | 28-Sep-20 | 14-Jul-20 | 13-Nov-20 |  | Contractor |  | 0
633392 | 633392 - TRANSFORMER REPLACEMENT 2020 - REPLACE 2 PCB TXS ON M40 | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 13-Dec-19 |  |  | 29686.65 | 28095.83 | 29686.65 | 29686.65 | Lamb, Tim | Somervl | 28-Feb-20 | 25-May-21 | 17-Feb-20 | 07-Aug-20 | 07-Sep-20 | Contractor | Contractor |  | 0
633441 | 633441 - DISTRIBUTION AUTOMATION 2020 - A07SL2004 - AURORA | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-Nov-19 |  | 1 | 58157.31 | 96058.98 | 58157.31 | 58157.31 | Macdonald, Steve | K-Line | 01-Apr-20 | 24-Mar-21 | 23-Mar-20 | 21-Dec-20 | 24-Dec-20 | COVID19 | COVID19 |  | 0
633442 | 633442 - DISTRIBUTION AUTOMATION 2020 - A10SL2037 - AURORA | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 25-Oct-19 |  | 1 | 104020.34 | 120390.62 | 104020.34 | 104020.34 | Macdonald, Steve | K-Line | 21-Feb-20 | 25-Mar-21 | 10-Feb-20 | 15-Sep-20 | 30-Sep-20 | COVID19 | COVID19 |  | 0
633443 | 633443 - DISTRIBUTION AUTOMATION 2020 - V31SL3012 - VAUGHAN | 815 - Addiscott | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-Nov-19 |  | 1 | 84230.98 | 91576.65 | 84230.98 | 84230.98 | Macdonald, Steve | K-Line | 20-Nov-20 | 15-Mar-21 | 16-Nov-20 | 07-Dec-20 | 24-Dec-20 | Contractor | Contractor |  | 0
633481 | 633481 - POLE REPLACEMENT 2020 BATCH 11 - AURORA - 15 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 21-Nov-19 |  |  | 125166.55 | 158230.27 | 125166.55 | 125166.55 | Morrow, Joe |  | 02-Oct-20 | 15-May-23 | 08-Sep-20 | 14-Sep-20 | 02-Oct-20 |  |  |  | 0
633482 | 633482 - POLE REPLACEMENT 2020 BATCH 6 - MARKHAM - 26 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 06-Apr-20 |  |  | 247047.75 | 436814.51 | 247047.75 | 253772.41 | Ryan Walsh |  | 15-Sep-20 | 24-Feb-21 | 27-Jul-20 | 27-Jul-20 | 17-Sep-20 |  |  |  | 6,724.66
633492 | 633492 - 2020 POLE REPLACEMENTS BATCH 1 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 20-Dec-19 |  |  | 133472.62 | 151875.93 | 133472.62 | 133472.62 | Dan Kish |  | 26-Feb-20 | 21-Nov-21 | 03-Feb-20 | 04-Feb-20 | 07-Jul-20 | Filler |  |  | 0
633511 | 633511 - JOINT USE PERMIT HE2019-097- WESTON RD. MAJOR MACK TO DAVOS | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 12-Feb-20 |  |  | 10584.84 | 5942.21 | 10584.84 | 10584.84 | Macdonald, Larry |  | 31-Mar-20 | 01-Sep-22 | 30-Mar-20 | 01-Oct-20 | 01-Oct-20 | Filler | Filler |  | 0
633518 | 633518 - POLE REPLACEMENT 2020 - BATCH 7 - VAUGHAN - 17 POLES | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 16-Sep-19
633519 | 633519 - SWITCHGEAR REPLACEMENT 2020 - BATCH 10 - 2 DEFERRED UNITS | 815 - Addiscott | 100859 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 05-Nov-19 |  | 2 | 126919.39 | 130294.01 | 123304.39 | 126919.39 | Lamb, Tim |  | 05-Feb-20 | 08-Mar-21 | 27-Jan-20 | 25-Jun-20 | 07-Jul-20 | Filler |  |  | 3,615.00
633546 | 633546 - POLE REPLACEMENT 2020 BATCH 5 - MARKHAM - 14 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 07-Nov-19 | 12 | 12 | 224484.56 | 178113.33 | 251549.93 | 224484.56 | Ryan Walsh |  | 21-Aug-20 | 08-Apr-21 | 29-Jun-20 | 15-Jun-20 | 21-Jul-20 |  |  |  | -27,065.37
633547 | 633547 - POLE REPLACEMENT 2020 BATCH 9 - VAUGHAN - 12 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 05-Nov-19 | 9 | 9 | 160755.2 | 172353.5 | 160755.2 | 168787.88 | Ryan Walsh |  | 05-Mar-20 | 17-Feb-21 | 04-Feb-20 | 15-Jun-20 | 21-Jul-20 | Filler |  |  | 8,032.68
633607 | 633607 - POLE REPLACEMENT 2020 - BATCH 7 - VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 06-Nov-19 | 16 | 16 | 114154 | 138381.75 | 114154 | 114154 | Macdonald, Larry |  | 29-Jan-20 | 25-Feb-21 | 06-Jan-20 | 10-Feb-20 | 22-Dec-20 | Filler | Filler |  | 0
633608 | 633608 - POLE REPLACEMENT 2020 - BATCH 8 - VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 06-Nov-19 | 18 | 18 | 166986.64 | 254412.34 | 166986.64 | 166986.64 | Morrow, Joe |  | 23-Dec-20 | 04-Mar-21 | 01-Dec-20 | 14-Oct-20 | 20-Nov-20 |  |  |  | 0
633609 | 633609 - POLE REPLACEMENT 2020 - BATCH 10 - VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-Oct-19 | 11 | 11 | 292043.75 | 305096.29 | 292043.75 | 292043.75 | Macdonald, Steve | K-Line | 24-Aug-20 | 22-Mar-21 | 20-Jul-20 | 24-Oct-20 | 27-Nov-20 | Customer |  |  | 0
633610 | 633610 - TRANSFORMER REPLACEMENT 2020 - BATCH 13 - VAUGHAN | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 14-Nov-19 |  |  | 267170.54 | 178972.81 | 267170.54 | 267170.54 | Lamb, Tim | Somervl | 30-Mar-20 | 27-May-21 | 21-Feb-20 | 20-Feb-20 | 25-Jun-20 |  | Filler |  | 0
633611 | 633611 - TRANSFORMER REPLACEMENT 2020 - BATCH 14 - VAUGHAN | 815 - Addiscott | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 25-Nov-19 |  |  | 360970.61 | 261889.52 | 360970.61 | 360970.61 | Chris Hagan | K-Line | 30-Nov-20 | 27-May-21 | 02-Nov-20 | 06-Oct-20 | 03-Dec-20 |  | Contractor |  | 0
633612 | 633612 - 2020 POLE REPLACEMENTS BATCH 2 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 30-Dec-19 |  |  | 266013.93 | 289337.06 | 266013.93 | 266013.93 | Jeremy Wright |  | 27-Aug-20 | 08-Mar-21 | 30-Jun-20 | 20-Jul-20 | 07-Oct-20 |  |  |  | 0
633657 | BIG BAY POINT ROAD ANCHOR LOCATIONS | 825 - Patterson | 100959 | Active | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 11960.87 | 14284.91 | 11960.87 | 11960.87 | Dan Kish |  |  | 26-Jul-23 |  | 24-Nov-20 | 24-Nov-20 | xBy-passed | xBy-passed |  | 0
633668 | 633668 - 11 HANSON COURT / ICI PADMOUNT TX INSTALLATION | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 31-Oct-19 |  |  | 40255 | 32122.26 | 40255 | 40255 | Steve Rumble | Transpw | 29-Nov-19 | 18-Feb-21 | 25-Nov-19 | 02-Dec-19 | 07-Jan-20 | Contractor | Contractor |  | 0
633707 | 633707 - 681 YONGE STREET - RELOCATE POLES FOR PROPOSED DEVELOPMENT | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE | Medium | Infrast | 2020 | Pelleja, Emily | Alectra Utilities | 12-Jun-20 |  |  | 987396.47 | 729215.97 | 987396.47 | 987396.47 | Jeremy Wright | K-Line | 31-Jul-20 | 20-Sep-22 | 30-Jun-20 | 03-Jul-20 | 19-Sep-20 |  |  |  | 0
633807 | 633807 - 2020 TRANSFORMER RENEWAL - EAST - BARRIE BATCH 1 | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 20-Dec-19 |  |  | 115936.38 | 82027.96 | 115936.38 | 115936.38 | Lotto, Jay | HapAmp | 20-May-20 | 02-Jun-21 | 24-Feb-20 | 24-Jun-20 | 07-Aug-20 |  |  |  | 0
633810 | 633810 - 2020 TRANSFORMER RENEWAL - EAST - BARRIE BATCH 2 | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 20-Dec-19 |  |  | 169874.81 | 149992.52 | 169874.81 | 169874.81 | Lotto, Jay | HapAmp | 08-Sep-20 | 02-Jun-21 | 29-Jul-20 | 25-Jun-20 | 16-Nov-20 |  |  |  | 0
633811 | 633811 - 2020 TRANSFORMER RENEWAL - EAST - BARRIE BATCH 3 | 825 - Patterson | 101508 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 24-Jan-20 |  |  | 358557.79 | 302765.42 | 358557.79 | 358557.79 | Lotto, Jay | HapAmp | 14-Aug-20 | 27-May-21 | 27-Jul-20 | 26-Jun-20 | 03-Dec-20 |  | Filler |  | 0
633826 | 633826 - 10 GATINEAU DR - TEMPORARY POWER | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 23-Dec-19 |  |  | 59102.75 | 48351.59 | 59102.75 | 59102.75 | Steve Rumble | Somervl | 31-Jan-20 | 18-Feb-21 | 27-Jan-20 | 07-Feb-20 | 24-Mar-20 | Locates |  |  | 0
633869 | 633869 - POLE REPLACEMENT 2020 - MARKHAM - REPLACE 1 AND REMOVE 2 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 01-Apr-20 |  |  | 29044.28 | 67654.55 | 29044.28 | 29044.28 | Morrow, Joe |  | 12-Nov-20 | 19-Feb-21 | 09-Nov-20 | 26-Oct-20 | 21-Dec-20 | Filler | Filler |  | 0
633870 | 633870 - POLE REPLACEMENT 2020 - REPLACE P23368 - AHORN GROVE, MARKHAM | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 01-Apr-20 |  |  | 16827.45 | 21463.79 | 16827.45 | 16827.45 | Morrow, Joe |  | 04-Sep-20 | 25-Jan-21 | 01-Sep-20 | 21-Jul-20 | 21-Jul-20 |  |  |  | 0
633871 | 633871 - CABLE REPLACEMENT - 269 BAY THORN DR | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 08-Oct-19
633881 | 633881 - ICI PADMOUNT TX INSTALLATION/102 KING ST | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | High | Indust | 2020 | Cranley, Stephen | Alectra Utilities | 16-Mar-20 |  |  | 52933.27 | 46216.73 | 52933.27 | 52933.27 | Lotto, Jay | HapAmp | 10-Jul-20 | 18-Feb-21 | 22-Jun-20 | 01-Jun-20 | 03-Jun-20 |  |  |  | 0
633885 | 633885 - 919 CLARK AVE / ICI PAD TX INSTALLATION | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | High | Res-ICI | 2020 | Dibratto, Susan | Alectra Utilities | 04-May-20 |  |  | 68426.2 | 51226.29 | 68426.2 | 68426.2 | Chris Hagan | Somervl | 15-Jul-20 | 19-Feb-21 | 06-Jul-20 | 15-Oct-20 | 23-Nov-20 | Customer | Customer |  | 0
633892 | 633892 - 2020 DISTRIBUTION AUTOMATION - EAST - BARRIE - LT-B10043 - 250 ANNE ST. N | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 21-May-20 |  |  | 236983.6 | 162964.19 | 236983.6 | 236983.6 | Dan Kish |  | 08-Dec-20 | 03-Aug-21 | 30-Nov-20 | 11-Nov-20 | 21-Dec-20 | Materials | Materials |  | 0
633893 | 633893 - 2020 DISTRIBUTION AUTOMATION - EAST - BARRIE - LT-B35858 - 243 SAUNDERS RD. | 825 - Patterson | 100886 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 05-Mar-20 |  |  | 104360.81 | 108127.46 | 104360.81 | 104360.81 | Dan Kish | K-Line | 01-Dec-20 | 15-Mar-21 | 23-Nov-20 | 14-Dec-20 | 24-Dec-20 | Materials | Materials |  | 0
633896 | 633896 - 2020 SWITCH RENEWAL - EAST - BARRIE - 140 CUNDLES RD.W | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 11-May-20 |  | 1 | 218097.12 | 166634.16 | 218097.12 | 218097.12 | Dan Kish | K-Line | 22-Dec-20 | 03-Mar-21 | 07-Dec-20 | 14-Dec-20 | 21-Dec-20 | Materials |  |  | 0
633897 | 633897 - 2020 SWITCH RENEWAL - EAST - BARRIE - 124 VESPRA ST. | 825 - Patterson | 101027 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 31-Mar-20 |  | 1 | 190718.68 | 188385.99 | 190718.68 | 190718.68 | Dan Kish | K-Line | 14-Dec-20 | 06-May-21 | 01-Dec-20 | 12-Dec-20 | 21-Dec-20 | Materials | Materials |  | 0
633943 | (WO 633943) DUCT BANK LOWERING - JANE ST, NORTH OF BASS PRO MILLS DRIVE | 815 - Addiscott | 101761 | Inactive | 99 | CANCELLED |  |  | 2020 | Corriveau, Tom N | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 26-Oct-20
633950 | 633950 - POLE RELOCATION - HIGHWAY 50 SOUTH OF TRADE VALLEY DRIVE | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 06-Jan-20 |  |  | 34798.98 | 18323.95 | 34798.98 | 34798.98 | Macdonald, Larry |  | 03-Feb-20 | 24-Nov-21 | 27-Jan-20 | 18-Feb-20 | 26-Feb-20 | Locates |  |  | 0
633952 | 633952 - ICI NEW COMMERCIAL SERVICE/ 575 COCHRANE DR | 815 - Addiscott | 101791 | Active | 95 | COMPLETE |  |  | 2020 | Joshi, Namrata | Alectra Utilities | 30-Dec-20 |  |  | 87096.93 | 568599.95 | 87096.93 | 87096.93 | Steve Rumble | Somervl | 17-Mar-20 | 26-Jul-23 | 09-Mar-20 | 29-Jan-20 | 25-Feb-20 |  |  |  | 0
633975 | (WO 633975) 2020 SUNNIDALE AND ANNE CABLE REPLACEMENT | 815 - Addiscott | 151336 | Inactive | 99 | CANCELLED |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 21-Apr-22
633979 | 633979 - 196 BRADWICK DR / ICI PADMOUNT TRANSFORMER UPGRADE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 05-Dec-19 |  |  | 53753.19 | 53634.75 | 53753.19 | 53753.19 | Steve Rumble | Somervl | 05-Feb-20 | 18-Feb-21 | 27-Jan-20 | 04-Feb-20 | 10-Feb-20 | Customer |  |  | 0
633982 | (WO 633982) 3600 LANGSTAFF RD / ICI DUCTBANK RELOCATION | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 19-Oct-20
633993 | 633993 - HE2019-103, MAJOR MACK & KEELE AERIAL PERMIT | 815 - Addiscott | 101763 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 03-Feb-20 |  |  | 7784.84 | 6714.49 | 7784.84 | 7784.84 | Macdonald, Larry |  | 18-Feb-20 | 01-Nov-21 | 18-Feb-20 | 12-Feb-20 | 12-Feb-20 |  |  |  | 0
634040 | (WO 634040) REPLACE 31TP175, 7300 BIRCHMOUNT RD | 815 - Addiscott | 151450 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 13-Jan-20
634047 | 634047 - 115 CIDERMILL AVE. | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 06-Feb-20 |  |  | 56424.53 | 41063.52 | 56424.53 | 56424.53 | Chris Hagan |  | 06-May-20 | 18-Feb-21 | 30-Mar-20 | 27-Oct-20 | 30-Oct-20 | Customer | Customer |  | 0
634070 | 634070 - 2020 SUNNIDALE UG CABLE REPLACEMENT | 825 - Patterson | 151336 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 31-Jul-20 |  |  | 1081715.7 | 1190366.48 | 1081715.7 | 1081715.7 | Lotto, Jay | Transpw | 04-Dec-20 | 04-Oct-21 | 11-Sep-20 | 14-Sep-20 | 17-Nov-20 | Contractor |  |  | 0
634080 | 634080 - POLE REPLACEMENT 2020 - REPLACE P30260 AT YONGE ST AND MORGAN AVE, MARKHAM | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 26-Nov-19 |  |  | 37097.26 | 13764.47 | 37097.26 | 37097.26 | Morrow, Joe |  | 30-Sep-20 | 25-Jan-21 | 28-Sep-20 | 10-Aug-20 | 14-Aug-20 |  |  |  | 0
634081 | 634081 - 2020 POLE REPLACEMENT - REPLACE 2 POLES AT YONGE AND JOHN ST, MARKHAM | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 11-Dec-19 | 2 | 2 | 44003.5 | 29767.09 | 44003.5 | 44003.5 | Morrow, Joe |  | 20-Aug-20 | 18-Feb-21 | 17-Aug-20 | 14-Oct-20 | 14-Oct-20 |  |  |  | 0
634139 | 634139 - POLE REPLACEMENT 2020 - BATCH 17 - AURORA | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 22-Jan-20 |  |  | 245896.33 | 398020.47 | 309685.45 | 245896.33 | Macdonald, Steve | K-Line | 30-Nov-20 | 15-Mar-21 | 26-Oct-20 | 23-Nov-20 | 24-Dec-20 | Contractor | Contractor |  | -63,789.12
634166 | 634166 - HURST DRVE RELOCATE POLES AND ANCHORS FOR ROAD WIDENING | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE | Medium | Infrast | 2020 | Pelleja, Emily | Alectra Utilities | 08-Jul-20 |  |  | 249183.34 | 160322.76 | 249183.34 | 249183.34 | Jeremy Wright | K-Line | 14-Aug-20 | 22-Sep-22 | 17-Jul-20 | 11-Jul-20 | 25-Jul-20 |  |  |  | 0
634378 | 634378 - 2020 CABLE REPLACEMENT/YORK HILL PHASE 4B | 815 - Addiscott | 151114 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 13-Dec-19 |  |  | 440108.38 | 91977.67 | 440108.38 | 440108.38 | Lamb, Tim | Transpw | 08-May-20 | 06-May-21 | 30-Mar-20 | 23-Mar-20 | 16-Dec-20 |  | Contractor |  | 0
634389 | 634389 - POLE REPLACEMENT 2020 BATCH 13 - VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 27-Nov-19 |  |  | 47864.28 | 40593.77 | 47864.28 | 47864.28 | Morrow, Joe |  | 18-Sep-20 | 26-Feb-21 | 08-Sep-20 | 01-Dec-20 | 16-Dec-20 | Lines |  |  | 0
634390 | 634390 - POLE REPLACEMENT 2020 BATCH 14 - VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 09-Jan-20 |  |  | 144594.46 | 136861.64 | 144594.46 | 144594.46 | Morrow, Joe |  | 31-Jul-20 | 17-Feb-21 | 02-Jul-20 | 06-Jul-20 | 26-Aug-20 | Filler | Filler |  | 0
634391 | 634391 - POLE REPLACEMENT 2020 BATCH 15 - VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 02-Dec-19 | 5 | 5 | 72326.6 | 67756.58 | 72326.6 | 72326.6 | Morrow, Joe |  | 17-Jul-20 | 25-Jan-21 | 02-Jul-20 | 13-Jul-20 | 21-Jul-20 |  |  |  | 0
634392 | 634392 - POLE REPLACEMENT 2020 BATCH 16 - VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 08-Jan-20 |  |  | 69289.73 | 64898.22 | 69289.73 | 69289.73 | Morrow, Joe |  | 10-Sep-20 | 01-Mar-21 | 24-Aug-20 | 24-Aug-20 | 10-Sep-20 |  |  |  | 0
634469 | 634469 - 13029 BATHURST STREET | 815 - Addiscott | 101763 | Inactive | 99 | CANCELLED |  |  | 2020 | Corriveau, Tom N | Alectra Utilities |  |  |  | 1.3 | 0 |  | 0 | Persaud, Ryan |  |  | 24-Aug-20
634470 | 634470 - POLE REPLACEMENT 2020 - REPLACE 3 POLES AT HWY 407 AND PINE VALLEY DR, VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 26-Jun-20 |  |  | 84208.31 | 81618.6 | 84208.31 | 84208.31 | Macdonald, Steve | K-Line | 04-Sep-20 | 16-Feb-21 | 17-Aug-20 | 29-Aug-20 | 18-Sep-20 | COVID19 | COVID19 |  | 0
634471 | 634471 - POLE REPLACEMENT 2020 - REPLACE P46749 AT HWY 407 & ISLINGTON AVE, VAUGHAN | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 02-Apr-20 |  |  | 57871.99 | 79530.97 | 57871.99 | 73787.74 | Macdonald, Steve | K-Line | 23-Oct-20 | 16-Feb-21 | 19-Oct-20 | 18-Sep-20 | 18-Sep-20 |  |  |  | 15,915.75
634476 | 634476 - 2020 POLE REPLACEMENTS - VAUGHAN - BATCH 18 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 22-Apr-20 |  |  | 160199.54 | 137656.67 | 160199.54 | 160199.54 | Ryan Walsh |  | 15-Sep-20 | 12-Feb-21 | 24-Aug-20 | 29-Jul-20 | 14-Sep-20 |  |  |  | 0
634479 | 634479 - 2020 LEFT-BEHIND CABLE REPLACE/M37 14TH AVE | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-May-20 |  |  | 149290.99 | 144883.62 | 149290.99 | 149290.99 | Lamb, Tim | Somervl | 14-Sep-20 | 08-Mar-21 | 29-Jul-20 | 16-Aug-20 | 21-Oct-20 | Contractor | Contractor |  | 0
634480 | 634480 - 2020 LEFT-BEHIND CABLE REPLACE/V18 BARRHILL RD | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 19-Jun-20 |  |  | 720786.36 | 680631.91 | 720786.36 | 720786.36 | Lamb, Tim | Transpw | 25-Sep-20 | 21-Jul-21 | 04-Aug-20 | 14-Sep-20 | 03-Nov-20 | Contractor | Contractor |  | 0
634481 | 634481 - 2020 LEFT-BEHIND CABLE REPLACE/V36 SCHOLES RD | 815 - Addiscott | 150263 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-May-20 |  |  | 196761.53 | 185704.05 | 196761.53 | 196761.53 | Lamb, Tim | Transpw | 06-Oct-20 | 15-Jul-21 | 14-Sep-20 | 05-Oct-20 | 03-Nov-20 | Contractor | Contractor |  | 0
634487 | 634487 - 2020 POLE REPLACEMENTS - VAUGHAN - BATCH 19 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 04-May-20 |  |  | 131114.3 | 100916.19 | 131114.3 | 131114.3 | Morrow, Joe |  | 28-Aug-20 | 08-Feb-21 | 10-Aug-20 | 24-Aug-20 | 18-Sep-20 |  |  |  | 0
634488 | 634488 - 2020 POLE REPLACEMENT - P43709 | 815 - Addiscott | 100867 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 211.44 |  | 0 | Persaud, Ryan |  |  | 24-Feb-20
634494 | 634494 - 2020 POLE REPLACEMENT -P43706 | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 03-Jan-20 | 2 | 2 | 50374.01 | 51871.14 | 50374.01 | 50374.01 | Morrow, Joe |  | 03-Sep-20 | 25-Feb-21 | 24-Aug-20 | 23-Nov-20 | 23-Nov-20 | Lines | Lines |  | 0
634522 | 634522 - M43 - John and Woodbine (Mini Rupters) | 815 - Addiscott | 150026 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 27-Nov-19 |  |  | 277240.31 | 272472.6 | 277240.31 | 277240.31 | Lamb, Tim |  | 27-Mar-20 | 18-Feb-21 | 27-Jan-20 | 25-Jun-20 | 25-Jun-20 | Filler |  |  | 0
634525 | 634525 - 2020 POLE REPLACEMENTS - P41694 | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Persaud, Ryan |  |  | 20-Nov-19
634536 | 634536 - HE2019-112, BIG BAY POINT RD | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 08-Apr-20 |  |  | 8056.89 | 5197.04 | 8056.89 | 8056.89 | Aulis, John -x |  | 13-Oct-20 | 14-Dec-21 | 12-Oct-20 | 30-Sep-20 | 30-Sep-20 |  |  |  | 0
634572 | 634572 - POLE REPLACEMENT 2020 BATCH 20 - VAUGHAN - REPLACE 12 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 09-Jan-20 |  |  | 78247.11 | 52871.5 | 78247.11 | 78247.11 | Macdonald, Larry |  | 04-Dec-20 | 03-Mar-21 | 26-Oct-20 | 16-Oct-20 | 16-Dec-20 |  | Filler |  | 0
634595 | 634595 - 250 INTERCHANGE WAY - TEMPORARY | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 09-Dec-19 |  |  | 59853.75 | 71459.66 | 75533.46 | 75533.46 | Steve Rumble | Somervl | 24-Mar-20 | 18-Feb-21 | 16-Mar-20 | 18-Feb-20 | 09-Mar-20 |  |  |  | 0
634639 | 634639 - Main St. Markham North - #352 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 18-Feb-20 |  |  | 41252.53 | 25291.29 | 41252.53 | 41252.53 | Chris Hagan | Somervl | 07-May-20 | 01-Mar-21 | 27-Apr-20 | 08-Jun-20 | 10-Dec-20 | Customer | Customer |  | 0
634727 | 634727 - ICI DEMOLITION/ 200 ABERDEEN AVE | 815 - Addiscott | 452288 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 02-Jan-20 |  |  | 12237.67 | 3219.24 | 12237.67 | 12237.67 | Steve Rumble |  | 22-Jan-20 | 18-Feb-21 | 20-Jan-20 | 26-Nov-19 | 28-Feb-20 | Lines | Lines |  | 0
634926 | 634926 - BRADFORD STREET/HIGH STREET - RELOCATE POLES FOR ROAD WORKS | 825 - Patterson | 101764 | Inactive | 99 | COMPLETE | VerHigh | Infrast | 2020 | Pelleja, Emily | Alectra Utilities | 11-Mar-20 |  |  | 165671.03 | 188631.26 | 165671.03 | 165671.03 | Dan Kish | K-Line | 07-Apr-20 | 22-Sep-22 | 16-Mar-20 | 26-Mar-20 | 04-Jun-20 |  |  |  | 0
634943 | 634943 - FAIRTREE BLOCK 151 CONDO BLOCK SEMI DETACHED / INSPECT AND CONNECT WO | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 10-Jun-20 |  |  | 496942.86 | 488224.81 | 496942.86 | 496942.86 | Chris Hagan | Transpw | 02-Oct-20 | 24-Feb-21 | 17-Aug-20 | 16-Sep-20 | 05-Oct-20 | Customer | Customer |  | 0
634963 | 634963 - POLE REPLACEMENT 2020 BATCH 21 - VAUGHAN - REPLACE 3 POLES | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 09-Jan-20 |  |  | 84453.2 | 74877.37 | 84453.2 | 84453.2 | Macdonald, Larry |  | 04-Dec-20 | 23-Feb-21 | 26-Oct-20 | 16-Oct-20 | 03-Dec-20 |  |  |  | 0
634964 | 634964 - POLE REPLACEMENT 2020 - REPLACE P46320 AT ISLINGTON AVE & THISTLEWOOD AVE | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 28-Jul-20 |  |  | 55765.11 | 65378.01 | 55765.11 | 55765.11 | Macdonald, Larry |  | 18-Dec-20 | 17-Feb-21 | 02-Nov-20 | 09-Dec-20 | 17-Dec-20 | Filler | Filler |  | 0
635046 | 635046 - 2020 POLE REPLACEMENTS BATCH 3 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 06-Feb-20 |  |  | 144345.43 | 210666.92 | 144345.43 | 144345.43 | Dan Kish |  | 25-May-20 | 16-Sep-21 | 02-Mar-20 | 08-Jul-20 | 17-Sep-20 |  |  |  | 0
635047 | 635047 - 2020 POLE REPLACEMENTS BATCH 4 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 28-Feb-20 |  |  | 264247.28 | 177807.5 | 264247.28 | 264247.28 | Dan Kish |  | 29-Sep-20 | 16-Sep-21 | 10-Aug-20 | 16-Jul-20 | 02-Oct-20 |  |  |  | 0
635048 | 635048 - 2020 POLE REPLACEMENTS BATCH 5 | 825 - Patterson | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 12-Jun-20 |  |  | 294097.87 | 233286.78 | 294097.87 | 294097.87 | Dan Kish |  | 12-Nov-20 | 08-Mar-21 | 21-Sep-20 | 02-Oct-20 | 03-Dec-20 | Locates |  |  | 0
635317 | 635317 - 5467 19TH AVE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 22-May-20 |  |  | 44148.28 | 25537.57 | 44148.28 | 44148.28 | Chris Hagan | Somervl | 31-Jul-20 | 01-Mar-21 | 13-Jul-20 | 19-Jun-20 | 04-Nov-20 |  | Lines |  | 0
635346 | 635346 - 30 HANMER ST WEST, BARRIE - 3 PHASE SERVICE | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2020 | Cranley, Stephen | Alectra Utilities | 30-Apr-20 |  |  | 47230.58 | 34281.01 | 47230.58 | 47230.58 | Jeremy Wright | HapAmp | 06-Jul-20 | 15-Nov-21 | 29-Jun-20 | 01-Jun-20 | 17-Jul-20 |  |  |  | 0
635382 | 635382 - JOINT USE HE2019-132 | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | O'Gay, Brian | Alectra Utilities | 01-Apr-20 |  |  | 40963.25 | 76875.57 | 40963.25 | 40963.25 | Macdonald, Larry |  | 02-Jul-20 | 29-Mar-22 | 22-Jun-20 | 22-Jul-20 | 14-Aug-20 | Filler | Filler |  | 0
635570 | 635570 - 7 EAGLET CRT - KEELE LANDFILL / ICI 1PH PAD TX DEMO | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 04-Jun-20 |  |  | 7356.02 | 3929.6 | 7356.02 | 7356.02 | Steve Rumble |  | 30-Jun-20 | 26-Feb-21 | 26-Jun-20 | 28-Jul-20 | 28-Jul-20 | Customer | Customer |  | 0
635617 | 635617 - ICI CUSTOMER OWNED TRANSFORMER/25 REAGENS INDUSTRIAL PARKWAY | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | High | Health | 2020 | Cranley, Stephen | Alectra Utilities | 30-Mar-20 |  |  | 40963.25 | 33743.5 | 40963.25 | 40963.25 | Lotto, Jay | HapAmp | 10-Jun-20 | 15-Oct-21 | 04-Jun-20 | 07-May-20 | 14-May-20 |  |  |  | 0
635618 | 635618 - ICI PADMOUNT TX INSTALLATION/70A ELDERBERRY TRAIL | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | VerHigh | Res-ICI | 2020 | Cranley, Stephen | Alectra Utilities | 15-May-20 |  |  | 46227.79 | 44757.97 | 45592.79 | 46227.79 | Chris Hagan | Somervl | 22-Jun-20 | 08-Mar-23 | 15-Jun-20 | 08-Jun-20 | 02-Dec-20 |  | Customer |  | 635
635655 | 635655 - 2020 CABLE INJECTION/M40 CABLE INJECTION | 815 - Addiscott | 151342 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 27-Jan-20 |  |  | 214326.59 | 240414.1 | 214326.59 | 214326.59 | Lamb, Tim | Nvinium | 03-Apr-20 | 16-Feb-21 | 03-Feb-20 | 26-Feb-20 | 04-Dec-20 | Contractor | Contractor |  | 0
635680 | 635680 - CABLE REPLACEMENT - 269 BAY THORN DR | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 01-Apr-20 |  |  | 69747.37 | 54111.45 | 62090.28 | 69747.37 | Morrow, Joe | Somervl | 30-Oct-20 | 08-Mar-21 | 12-Oct-20 | 14-Dec-20 | 21-Dec-20 | Locates | Locates |  | 7,657.09
635692 | 5 PATTERSON RD, BEETON - TIM HORTONS | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE | High | Restaur | 2020 | Cranley, Stephen | Alectra Utilities | 25-Feb-20 |  |  | 48436.46 | 44434.47 | 48436.46 | 48436.46 | Lotto, Jay | HapAmp | 20-Apr-20 | 07-Jun-21 | 06-Apr-20 | 05-Mar-20 | 22-Apr-20 |  |  |  | 0
635761 | 635761 - 11408 YONGE STREET - STUB POLE INSTALLATION | 815 - Addiscott | 101762 | Inactive | 99 | COMPLETE | High | Infrast | 2020 | Lacombe, Joel | Alectra Utilities | 12-May-20 |  |  | 15379.58 | 5261.9 | 15379.58 | 15379.58 | Ryan Walsh |  | 15-Jul-20 | 28-Jan-21 | 13-Jul-20 | 22-Jun-20 | 22-Jun-20 |  |  |  | 0
635799 | 55 GRENCER ROAD | 815 - Addiscott | 101763 | Inactive | 99 | CANCELLED |  |  | 2020 | Corriveau, Tom N | Alectra Utilities |  |  |  | 0 | ($2,049.84) |  | 0 | Wong, Henry | K-Line |  | 24-Aug-20
635805 | 635805 - APPLEWOOD NORTH OF PORTAGE PARKWAY | 815 - Addiscott | 101761 | Inactive | 99 | COMPLETE | Medium | Infrast | 2020 | Corriveau, Tom N | Alectra Utilities | 22-Jun-20 |  |  | 168545.26 | 144217.15 | 168545.26 | 168545.26 | Steve Rumble | Transpw | 10-Jul-20 | 15-Sep-21 | 06-Jul-20 | 24-Jul-20 | 13-Aug-20 | Customer | Customer |  | 0
635808 | 635808 - CUSTOMER EMERGING PROJECT FOR HATPIN CONDO DEVELOPMENT - POLE INSTALLATION | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 01-Jun-20 |  |  | 22102.42 | 18205.91 | 22102.42 | 22102.42 | Macdonald, Larry |  | 05-Oct-20 | 19-Jul-21 | 04-Aug-20 | 19-Aug-20 | 03-Sep-20 |  |  |  | 0
635882 | 9113 AND 9125 BATHURST/INSPECT AND CONNECT | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities |  |  |  | 0 | 5311.6 |  | 0 | Wong, Henry |  |  | 11-Dec-20
635933 | 635933 - LESLIE STREET POLE REPLACEMENT (2 POLES) | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE | High | Subdiv | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 01-Apr-20 |  |  | 13739.21 | 21867.31 | 13739.21 | 13739.21 | Morrow, Joe |  | 11-Sep-20 | 17-Feb-21 | 10-Sep-20 | 30-Jul-20 | 26-Aug-20 |  |  |  | 0
636086 | 636086 - 2020 44KV INSULATOR REPLACEMENT PROGRAM | 825 - Patterson | 102537 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 31-Mar-20 |  |  | 3665.02 | 172094.75 | 3665.02 | 3665.02 | Jeremy Wright |  | 30-Dec-20 | 29-Dec-21 | 16-Nov-20 | 09-Nov-20 | 23-Nov-20 |  |  |  | 0
636130 | 636130 - ICI NEW COMMERCIAL / 8745 HIGHWAY 50 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 12-Aug-20 |  |  | 108118.58 | 79758.49 | 106856.58 | 108118.58 | Dave Lindsay | Somervl | 06-Nov-20 | 05-Mar-21 | 19-Oct-20 | 24-Sep-20 | 21-Dec-20 |  | Customer |  | 1,262.00
636148 | 636148 - BATHURST ST. - #12955 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  | Comm | 2020 | Dibratto, Susan | Alectra Utilities | 26-May-20 |  |  | 75811.88 | 66532.02 | 75811.88 | 75811.88 | Chris Hagan | Somervl | 21-Aug-20 | 26-Feb-21 | 10-Aug-20 | 16-Jul-20 | 14-Oct-20 |  | Customer |  | 0
636170 | 636170 - BAYVIEW DR 2020 STORM HARDENING 4CCT POLELINE | 825 - Patterson | 103659 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 31-Jul-20 |  |  | 441653.69 | 496043.99 | 441653.69 | 441653.69 | Jeremy Wright |  | 10-Nov-20 | 20-Aug-21 | 14-Sep-20 | 28-Sep-20 | 18-Dec-20 | Lines | Lines |  | 0
636201 | 636201 - 1100 RODICK RD / ICI PAD TX UPGRADE | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE | Low | Comm | 2020 | Dibratto, Susan | Alectra Utilities | 15-May-20 |  |  | 116651.07 | 99727.72 | 116651.07 | 116651.07 | Steve Rumble | Somervl | 08-Jul-20 | 20-Apr-22 | 22-Jun-20 | 17-Aug-20 | 20-Aug-20 | Customer | Customer |  | 0
636210 | 636210 - JOINT USE PERMIT HE2020-018, CHURCH STREET, RICHMOND HILL | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 04-May-20 |  |  | 5560.75 | 4596.36 | 5560.75 | 5560.75 | Macdonald, Larry |  | 11-Sep-20 | 22-Aug-22 | 13-Jul-20 | 17-Aug-20 | 17-Aug-20 | Filler |  |  | 0
636233 | 636233 - BELL BOND - BIG BAY POINT ROAD, BARRIE | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 22-Apr-20 |  |  | 0 | 1547.58 |  | 0 | Aulis, John -x |  | 07-Dec-20 | 17-Aug-22 | 07-Dec-20 | 22-May-20 | 22-May-20
636250 | 636250 - 45 FONTHILL - ESA EMERGING PROJECT - REAR LOT CONDUCTOR HEIGHT ADJUSTMENT | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 10-Jun-20 |  |  | 19403.83 | 19451.12 | 19403.83 | 19403.83 | Morrow, Joe |  | 06-Aug-20 | 08-Mar-21 | 04-Aug-20 | 15-Jul-20 | 21-Jul-20 |  |  |  | 0
636295 | 636295 - HUNTINGTON AND LANGSTAFF | 815 - Addiscott | 101763 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 29-Oct-20 |  |  | 25111.37 | 13474.65 | 25111.37 | 25111.37 | Macdonald, Larry |  | 17-Dec-20 | 21-Jun-21 | 14-Dec-20 | 07-Dec-20 | 10-Dec-20 |  |  |  | 0
636304 | 636304 - JOINT USE PERMIT #HE2020-024, HIGHWAY 27, VAUGHAN | 815 - Addiscott | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 21-Jul-20 |  |  | 6117.71 | 4439.49 | 6117.71 | 6117.71 | Macdonald, Larry |  | 14-Sep-20 | 22-Aug-22 | 14-Sep-20 | 14-Aug-20 | 14-Aug-20 |  |  |  | 0
636313 | 636313 - ICI PADMOUNT TX INSTALLATION/120 EAGLE ROCK WAY | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 18-Aug-20 |  |  | 110642.28 | 95711.25 | 110642.28 | 110642.28 | Chris Hagan | Somervl | 30-Oct-20 | 19-Feb-21 | 19-Oct-20 | 17-Sep-20 | 21-Dec-20 |  | Customer |  | 0
636314 | 636314 - PARENT W.O. FOR INSPECT/CONNECT/I&C - CP CAPITAL INVESTMENTS | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 16-Sep-20 |  |  | 329086.91 | 323259.24 | 329086.91 | 329086.91 | Chris Hagan | Transpw | 18-Dec-20 | 08-Mar-21 | 02-Nov-20 | 29-Sep-20 | 21-Dec-20 |  | Customer |  | 0
636408 | 19TH AVENUE, BAYVIEW TO LESLIE - ALECTRA FUNDED | 815 - Addiscott |  | Inactive | 99 | CANCELLED |  |  | 2020 | Corriveau, Tom N | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry
636469 | 1623 WELLINGTON ST, AURORA - NEW 3 PHASE SERVICE | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Cranley, Stephen | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 19-Apr-21
636529 | 636529 - POPLAR POLE REPLACE AND MAKE READY FOR SUBD | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 14-May-20 |  |  | 15700.1 | 13194.2 | 15700.1 | 15700.1 | Macdonald, Larry |  | 10-Aug-20 | 28-Jan-21 | 04-Aug-20 | 08-Jul-20 | 08-Jul-20 |  |  |  | 0
636541 | 636541 - VIA RENZO DR. - #60, PHASE 2 | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 30-Jun-20 |  |  | 18768.03 | 26411.85 | 18768.03 | 18768.03 | Chris Hagan |  | 20-Oct-20 | 19-Apr-21 | 05-Oct-20 | 09-Nov-20 | 23-Nov-20 | Customer | Customer |  | 0
636643 | 636643 - JOINT USE HE2020-029- BRADFORD ST. & HIGH ST. | 825 - Patterson | 151495 | Inactive | 99 | COMPLETE |  |  | 2020 | O'Gay, Brian | Alectra Utilities | 07-May-20 |  |  | 5563.47 | 4491.18 | 5563.47 | 5563.47 | Aulis, John -x |  | 05-Jun-20 | 07-Mar-22 | 04-Jun-20 | 09-Jun-20 | 09-Jun-20 |  |  |  | 0
636664 | 636664 - PARENT W.O. FOR INSPECT/CONNE/I&C CENTERFIELD 2A DEVELOPMENT | 815 - Addiscott | 101887 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 09-Sep-20 |  |  | 42845.41 | 371990.05 | 42845.41 | 42845.41 | Chris Hagan | Conelco | 30-Nov-20 | 08-Mar-21 | 12-Nov-20 | 30-Sep-20 | 07-Dec-20 |  |  |  | 0
636703 | 636703 - BAY MOORINGS - PERMANENT SERVICE REMOVAL | 825 - Patterson | 101761 | Inactive | 99 | COMPLETE |  |  | 2020 | Penner, Mitchell | Alectra Utilities | 27-May-20 |  |  | 4113.72 | 3141.31 | 4113.72 | 4113.72 | Lotto, Jay |  | 28-Jul-20 | 16-May-22 | 27-Jul-20 | 09-Jul-20 | 09-Jul-20 |  |  |  | 0
636734 | 636734 - POLE RELOCATION FOR BERCZY GLEN SUBDIVISION | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 25-Aug-20 |  |  | 13787.54 | 6980.46 | 13787.54 | 13787.54 | Macdonald, Larry |  | 20-Oct-20 | 27-Jul-23 | 19-Oct-20 | 18-Sep-20 | 18-Sep-20 |  |  |  | 0
636740 | 636740 - POLE REPLACEMENT 2020 - REPLACE P41431 AT YONGE ST & DUNLOP ST | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 22-Apr-20 |  |  | 38572.74 | 32146.58 | 38572.74 | 38572.74 | Macdonald, Larry |  | 04-Dec-20 | 12-Mar-21 | 26-Oct-20 | 17-Nov-20 | 20-Nov-20 | Filler |  |  | 0
636803 | 2020 VAULT LID RENEWAL PROGRAM - V2 - 37 DUNLOP ST.WEST | 825 - Patterson | 151526 | Inactive | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 79920 | 78119.56 | 79920 | 79920 | Wong, Henry |  |  | 16-Jun-21 |  |  |  | xBy-passed | xBy-passed |  | 0
636957 | 19TH AV - LESLIE TO WOODBINE/ HWY 404 CROSSING | 815 - Addiscott | 102545 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
636960 | HUNTINGTON - TEMPORARY CUSTOMER POLE INSTALLATION | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 29-May-20 |  |  | 11750.86 | 7038.23 | 11750.86 | 11750.86 | Macdonald, Steve |  | 22-Jun-20 | 16-Feb-21 | 05-Jun-20 | 10-Jun-20 | 10-Jun-20 |  |  |  | 0
637015 | 637015 - UG CABLE REPLACEMENT - A01 TAMARAC TRAIL - A01TP2105 TO A01TP2130 | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 27-Oct-20 |  |  | 109219.23 | 29290.43 | 109219.23 | 109219.23 | Lamb, Tim | Somervl | 28-Dec-20 | 05-Aug-21 | 10-Dec-20 | 24-Nov-20 | 08-Dec-20 |  |  |  | 0
637025 | 44KV AUTOMATED LIS - ADDITIONAL WORK - EAST - PATTERSON - CHILD W/O "CANCELLED" | 825 - Patterson | 101027 | Inactive | 99 | CANCELLED |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637031 | 44KV AUTOMATED LIS - ADDITIONAL WORK - EAST - PATTERSON - CHILD W/O 2 | 825 - Patterson | 101027 | Inactive | 99 | CANCELLED |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637039 | GUARDSMAN RD. EASTSIDE - #48 | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 30-Oct-20
637072 | 637072 - 7800 JANE ST / ICI PAD TX DEMO | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 15-Jun-20 |  |  | 15383.7 | 0 | 15383.7 | 15383.7 | Chris Hagan | Somervl | 20-Aug-20 | 12-Feb-21 | 17-Aug-20 |  |  | Customer | Customer |  | 0
637087 | 2020 TERMINATION BRACKETS -EAST - PATTERSON - CHILD W/O | 825 - Patterson | 101355 | Inactive | 99 | CANCELLED |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637105 | 637105 - LESLIE ST. AT EAST & WEST WILMOT RD. - N/E CORNER | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 09-Jul-20 |  |  | 34813.38 | 41873.99 | 34813.38 | 34813.38 | Chris Hagan | Somervl | 16-Oct-20 | 22-Apr-21 | 05-Oct-20 | 07-Sep-20 | 15-Sep-20 |  |  |  | 0
637107 | 2020 EXTRA POLE REPLACEMENTS - EAST - PATTERSON RD. - CHILD W/O | 825 - Patterson | 100867 | Inactive | 99 | CANCELLED |  |  | 2020 | Bowman, Todd J | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 18-Feb-21
637155 | 637155 - LESLIE ST AT EAST & WEST BEAVER CREEK RD - XXX CORNER / ICI 1PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 18-Sep-20 |  |  | 49785.26 | 51984.71 | 40933.26 | 49785.26 | Chris Hagan | Somervl | 11-Dec-20 | 22-Apr-21 | 23-Nov-20 | 30-Nov-20 | 21-Dec-20 | Contractor | Contractor |  | 8,852.00
637354 | 637354 - POLE REPLACEMENT KING AND BOND MINICIPAL SEMIS | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 23-Oct-20 |  |  | 43127.24 | 20845.66 | 43127.24 | 43127.24 | Macdonald, Larry |  | 11-Dec-20 | 05-Apr-22 | 30-Nov-20 | 19-Nov-20 | 24-Nov-20 |  |  |  | 0
637430 | 637430 - UNDERGROUND CROSSING SEWER REPAIR AT MCGAHEY STREET - TOTTENHAM | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2020 | Pelleja, Emily | Alectra Utilities | 21-Aug-20 |  |  | 88409.77 | 86553.75 | 88409.77 | 88409.77 | Lotto, Jay | Transpw | 27-Oct-20 | 19-Jul-21 | 12-Oct-20 | 22-Sep-20 | 02-Oct-20 |  |  |  | 0
637456 | 637456 - ANCHOR RELOCATION ULTRA TOWN INC. | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 27-Oct-20 |  |  | 10742.04 | 9016.6 | 10742.04 | 10742.04 | Macdonald, Larry |  | 07-Dec-20 | 22-Jul-21 | 07-Dec-20 | 07-Dec-20 | 10-Dec-20 |  |  |  | 0
637463 | 637463 - ISLINGTON AVE. - 10391 (KLEIMNBURG PUBLIC SCHOOL) | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 24-Aug-20
637509 | 637509 - UG CABLE REPLACEMENT - V40 GREENBROOKE DR - 40-37 TO 40-22 | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 03-Sep-20 |  |  | 56705.54 | 51198.87 | 56705.54 | 56705.54 | Lamb, Tim | Somervl | 23-Oct-20 | 08-Mar-21 | 12-Oct-20 | 21-Oct-20 | 02-Nov-20 | Contractor | Contractor |  | 0
637537 | 637537 - PORTAGE PKWY #898 - TEMPORARY RECOVERY | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 16-Jul-20 |  |  | 15206.34 | 19620.87 | 15206.34 | 15206.34 | Steve Rumble | Somervl | 21-Aug-20 | 23-Feb-21 | 17-Aug-20 | 10-Aug-20 | 17-Aug-20 |  |  |  | 0
637554 | 637554 - TX REMOVAL WOODEND PLACE DEVELOPMENT (PHASE) | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 26-Aug-20 |  |  | 25691.42 | 22932.72 | 25691.42 | 25691.42 | Chris Hagan | Transpw | 30-Oct-20 | 08-Apr-21 | 19-Oct-20 | 23-Oct-20 | 26-Oct-20 | Contractor |  |  | 0
637650 | 637650 - 700 APPLEWOOD CRES/ VAU/ SR/ 3PH PAD | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 21-Jul-20 |  |  | 7877.68 | 2759.84 | 7877.68 | 7877.68 | Steve Rumble |  | 02-Sep-20 | 02-Jun-21 | 02-Sep-20 | 25-Aug-20 | 25-Aug-20 |  |  |  | 0
637670 | 637670 - GRENCER ROAD RECONFIGURATION | 825 - Patterson | 101763 | Inactive | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities | 24-Aug-20 |  |  | 119690.49 | 94325.03 | 119690.49 | 119690.49 | Dan Kish | K-Line | 04-Sep-20 | 03-Aug-21 | 24-Aug-20 | 29-Aug-20 | 12-Sep-20 |  | Contractor |  | 0
637682 | 230 EDWARD ST, AUR/UP//3PH | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Cranley, Stephen | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 09-Feb-21
637746 | 138,142,148 GREY ALDER AVE - SUBD RES EDS | 815 - Addiscott | 101887 | Inactive | 99 | CANCELLED |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry
637805 | 637805 - CUSTOMER CAPTIAL TWO TRANSFOMER & ONE SWITCH REMOVAL FOR BERCZY MARKHAM JOB | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 25-Aug-20 |  |  | 7863.71 | 4045.67 | 7863.71 | 7863.71 | Macdonald, Larry |  | 14-Oct-20 | 19-Jul-21 | 12-Oct-20 | 11-Sep-20 | 11-Sep-20 |  |  |  | 0
637819 | 637819 - UG CABLE RELOCATION - 919 CLARK AVE WEST | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 02-Sep-20 |  |  | 71354.41 | 67932.72 | 71354.41 | 71354.41 | Lamb, Tim | Transpw | 23-Sep-20 | 15-Jul-21 | 14-Sep-20 | 23-Sep-20 | 21-Oct-20 | Contractor | MC/PUCC Permit |  | 0
637862 | 637862 - 2020 POLE REPLACEMENTS - LONGBRIDGE RD AND BUNKER RD | 815 - Addiscott | 100867 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 18-Aug-20 |  |  | 78789.36 | 58509.5 | 78789.36 | 78789.36 | Macdonald, Larry |  | 07-Oct-20 | 25-Feb-21 | 21-Sep-20 | 11-Sep-20 | 11-Sep-20 |  |  |  | 0
637869 | 637869 - BOND CRES MAKE READY FOR A SUBD 453133 | 815 - Addiscott | 151531 | Inactive | 99 | COMPLETE |  |  | 2020 | D'Onofrio, Tony | Alectra Utilities | 28-Oct-20 |  |  | 13847.08 | 7632.58 | 13847.08 | 13847.08 | Macdonald, Larry |  | 15-Dec-20 | 09-Mar-21 | 14-Dec-20 | 03-Dec-20 | 04-Dec-20 |  |  |  | 0
637945 | 637945 - 2020 REAR LOT EASTERN AVE IN TOTTENHAM | 825 - Patterson | 150043 | Active | 99 | COMPLETE |  |  | 2020 | Bowman, Todd J | Alectra Utilities | 31-Aug-20 |  |  | 2069851.85 | 2033846.8 | 2069851.85 | 2069851.85 | Dan Kish | Transpw | 18-Dec-20 | 26-Jul-23 | 05-Oct-20 | 05-Oct-20 | 21-Dec-20 |  | Contractor |  | 0
638133 | 638133 - WELLINGTON ST @ BAYVIEW AVE (AURORA) - HYDRO ONE RELOCATIONS | 815 - Addiscott | 101355 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 04-Sep-20 |  |  | 11251.98 | 22187.66 | 11251.98 | 11251.98 | Morrow, Joe |  | 03-Nov-20 | 17-Feb-21 | 02-Nov-20 | 26-Oct-20 | 26-Oct-20 |  |  |  | 0
638233 | 638233 - 1854 ADJALA TECUMSETH TOWNLINE / TOT / NS / 1PH PAD | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 25-Sep-20 |  |  | 26025.17 | 16513 | 26025.17 | 26025.17 | Lotto, Jay | HapAmp | 18-Dec-20 | 22-Jul-21 | 30-Nov-20 | 09-Nov-20 | 18-Dec-20 |  |  |  | 0
638392 | SWITCH REPLACEMENT - 37LIS017 | 815 - Addiscott | 101027 | Inactive | 99 | CANCELLED |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Wong, Henry |  |  | 20-Jul-20
638467 | 638467 - UG SECONDARY CABLE REPLACEMENTS, M52 ROMFIELD CIRCUIT | 815 - Addiscott | 151450 | Inactive | 99 | COMPLETE |  |  | 2020 | Tenorlas, Reynaldo | Alectra Utilities | 05-Oct-20 |  |  | 587076.39 | 585954.01 | 587076.39 | 587076.39 | Lamb, Tim | Transpw | 18-Dec-20 | 04-Oct-21 | 16-Nov-20 | 23-Oct-20 | 23-Nov-20 |  |  |  | 0
638626 | 638626 - 146 OLD KENNEDY RD / MAR / SR / VAULT DEMO | 815 - Addiscott | 101791 | Inactive | 99 | COMPLETE |  |  | 2020 | Dibratto, Susan | Alectra Utilities | 13-Nov-20 |  |  | 18367.6 | 12514.26 | 18367.6 | 18367.6 | Chris Hagan | Somervl | 23-Dec-20 | 02-Mar-21 | 18-Dec-20 | 23-Nov-20 | 26-Nov-20 |  |  |  | 0
638860 | 638860 - 50 ALLIANCE BLVD/BAR/UP/3PH PAD PHASE 1 | 825 - Patterson | 101919 | Inactive | 99 | COMPLETE |  |  | 2020 | Cranley, Stephen | Alectra Utilities | 12-Jan-21 |  |  | 99700.31 | 82727.16 | 99700.31 | 99700.31 | Lotto, Jay | HapAmp |  | 07-Jun-21 |  | 20-Dec-20 | 29-Dec-20 | xBy-passed | xBy-passed |  | 0
639012 | 4171 HWY 7 / MAR / UP / 3PH PAD TX | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | East Coordinator |  |  | 09-Feb-21
639404 | 639404 - ONEIDA CRESCENT - RICHMOND HILL | 815 - Addiscott | 101761 | Active | 99 | COMPLETE |  |  | 2020 | Corriveau, Tom N | Alectra Utilities |  |  |  | 7466.77 | 7611.04 | 7466.77 | 7466.77 | Chris Hagan |  |  | 26-Jul-23 |  | 04-Dec-20 | 07-Dec-20 | xBy-passed | xBy-passed |  | 0
639482 | 75 NEWKIRK RD / RHL / NS / 3PH VAULT DOWNGRADE | 815 - Addiscott | 101791 | Inactive | 99 | CANCELLED |  |  | 2020 | Dibratto, Susan | Alectra Utilities |  |  |  | 0 | 602.61 |  | 0 | East Coordinator |  |  | 02-Feb-21
SW 2020 | South West Region | [7 empty] | 2020 |  | Alectra Utilities |  |  |  | 5464159.67 | 5835986.02 |  | 0 | [5 empty] | 03-Jan-20 | 31-Dec-20
1000280 | Drew St - Rosewood Ave - Baqot St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 29579.27 |  | 0 | Manes, Bradley |  |  | 16-Dec-20 |  | 11-Mar-20 | 11-Mar-20
1027328 | 41 Conroy Cres | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 9201.45 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 | 18-Feb-20 | 18-Feb-20 | 18-Aug-20
1031531 | 561 York Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE | High | Comm | 2020 |  | Alectra Utilities |  |  |  | 0 | 48955.88 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 | 18-Feb-20 | 18-Feb-20 | 04-Jun-20
1045975 | 250 York Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE | High | Res-ICI | 2020 |  | Alectra Utilities |  |  |  | 0 | 29237.54 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 | 23-Mar-20 | 23-Mar-20 | 18-Aug-20 | Customer
1050258 | 943 Edinburgh Rd S | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 98152.72 |  | 0 | Stevens, Carl |  | 21-Apr-20 | 16-Dec-20 | 18-Feb-20 | 18-Feb-20 | 21-Apr-20
1061982 | 154 Milne Place | 840 - Southgate |  | Inactive | 99 | COMPLETE | VerHigh | Infrast | 2020 |  | Alectra Utilities |  |  |  | 0 | 17348.75 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 |  | 04-Jun-20 | 18-Aug-20
1075708 | 3 Stone Rd W | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 43021.07 |  | 0 | Manes, Bradley |  |  | 16-Dec-20 |  | 29-Jul-20 | 29-Jul-20
1075723 | Pole 154 Woodlawn Road West | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 75791.64 | 23078.09 | 75791.64 | 75791.64 | Lauryssen, John |  |  | 16-Dec-20 |  | 30-Oct-20 | 09-Nov-20 |  |  |  | 0
1077259 | 70 Kirby Crt | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 64605.46 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 | 18-Feb-20 | 18-Feb-20 | 12-Jun-20
1079167 | Alma Street North and Plymouth Court Phase 4 | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 282394.86 | 218563.62 | 282394.86 | 282394.86 | Lauryssen, John |  |  | 16-Dec-20 |  | 30-Oct-20 | 09-Nov-20 |  |  |  | 0
1079171 | Alma Street North and Julia Drive Phase 3 | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 270005.98 | 259896.33 | 270005.98 | 270005.98 | Lauryssen, John |  |  | 16-Dec-20 | 03-Jan-20 | 03-Jan-20 | 31-Jul-20 |  |  |  | 0
1082007 | 435 Stone Rd West | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 81302.79 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 | 18-Feb-20 | 18-Feb-20 | 14-Aug-20
1084158 | 731 Woolwich Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 32964.7 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 | 30-Mar-20 | 24-Aug-20 | 24-Aug-20 | Customer
1098347 | Main Street North, Rockwood | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 804378.53 | 274071 | 281456.8 | 281456.8 | Manes, Bradley |  |  | 16-Dec-20 | 13-Mar-20 | 13-Mar-20 | 30-Oct-20 |  |  |  | 0
1098489 | 995 Southgate Dr | 840 - Southgate |  | Inactive | 99 | COMPLETE | High | Health | 2020 |  | Alectra Utilities |  |  |  | 0 | 56327.21 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 |  | 17-Jul-20 | 20-Aug-20
1106965 | PMSG039 - 395 Southgate Dr - pad-switch replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 23534.86 | 26942.65 | 23534.86 | 23534.86 | Stevens, Carl |  |  | 16-Dec-20 |  | 05-Nov-20 | 05-Nov-20 |  |  |  | 0
1106972 | PMSG070 - 64 Fredrick Dr - pad switch replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 81782.55 | 971.3 | 81782.55 | 81782.55 | Stevens, Carl |  |  | 27-Jan-21 |  | 14-Dec-20 | 14-Dec-20 |  |  |  | 0
1109290 | 55 Quarterman Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE | Low | Indust | 2020 |  | Alectra Utilities |  |  |  | 0 | 39042.97 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 | 16-Mar-20 | 16-Mar-20 | 09-Jun-20
1110199 | Pleasant Road Reconstruction | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 384681.52 | 235188.44 | 384681.52 | 384681.52 | Manes, Bradley |  | 30-Sep-20 | 16-Dec-20 | 13-Jul-20 | 24-Aug-20 | 16-Oct-20 |  |  |  | 0
1110200 | Pleasant Rd - UG services to 4 & 55 Pleasant Dr | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 | 0 | 0 | Manes, Bradley |  |  | 16-Dec-20 |  | 23-Nov-20 | 27-Nov-20 |  |  |  | 0
1111303 | Metcalfe Steet & Balsam Drive Reconstruction | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 210595.54 | 213538.53 | 210595.54 | 210595.54 | Lauryssen, John |  | 24-Apr-20 | 16-Dec-20 | 10-Feb-20 | 10-Feb-20 | 21-Aug-20 |  |  |  | 0
1112601 | Kendrick Ave | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 90550.47 | 104177.62 | 90550.47 | 90550.47 | Lauryssen, John |  | 29-Sep-20 | 16-Dec-20 | 31-Aug-20 | 24-Aug-20 | 23-Sep-20 |  |  |  | 0
1115386 | 412 Laird Road - New Office Building | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 2289.41 | 2289.41 | 2289.41 | 2289.41 | Stevens, Carl |  |  | 16-Dec-20 |  | 17-Oct-20 | 17-Oct-20 |  |  |  | 0
1116951 | 119 Ingram Drive and 35 Wideman Boulevard On-Street Townhomes | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 188626.65 | 138396.58 | 188626.65 | 188626.65 | Stevens, Carl |  |  | 16-Dec-20 | 18-Feb-20 | 18-Feb-20 | 24-Aug-20 |  |  |  | 0
1118077 | Gladstone Avenue - Pole Line Reconstruction | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 107385.2 | 76168.52 | 107385.2 | 107385.2 | Manes, Bradley |  | 20-Feb-20 | 16-Dec-20 | 03-Feb-20 | 03-Feb-20 | 12-Feb-20 |  |  |  | 0
1119470 | 85 Queen St - New U/G Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 91.84 | 1172.84 | 91.84 | 91.84 | Stevens, Carl |  |  | 04-Jan-22 |  | 28-Dec-20 | 28-Dec-20 |  |  |  | 0
1122052 | Foresthill Drive and James Street West Reconstruction | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 144542.56 | 133151.08 | 144542.56 | 144542.56 | Lauryssen, John |  | 04-Jan-21 | 16-Dec-20 | 02-Nov-20 | 24-Sep-20 | 10-Nov-20 |  |  |  | 0
1122117 | King St, Havelock St & Spring St Reconstruction | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 190487.67 | 77015.99 | 190487.67 | 190487.67 | Lauryssen, John | K-Line | 12-Jan-21 | 04-Jan-22 | 09-Nov-20 | 23-Nov-20 | 31-Dec-20 |  |  |  | 0
1122118 | Johnston Street Reconstruction | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 170704.8 | 106177.82 | 170704.8 | 170704.8 | Lauryssen, John |  | 31-Aug-20 | 16-Feb-21 | 13-Jul-20 | 12-Nov-20 | 15-Dec-20 |  |  |  | 0
1123312 | Collingwood St & Shaftesbury Ave - Pole Line R/C | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 156141.07 | 138938.37 | 156141.07 | 156141.07 | Stevens, Carl |  |  | 16-Dec-20 |  | 30-Mar-20 | 30-Mar-20 |  |  |  | 0
1123811 | Pole 2 Chester Street | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 10599.84 | 8360.12 | 10599.84 | 10599.84 | Lauryssen, John |  |  | 16-Dec-20 |  | 20-Oct-20 | 25-Nov-20 |  |  |  | 0
1125108 | 226-274 Scottsdale Drive Townhomes - South of College Ave W | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 169274.83 | 315132.98 | 169274.83 | 169274.83 | Stevens, Carl |  | 19-Mar-20 | 22-Jan-21 | 18-Feb-20 | 18-Feb-20 | 19-Mar-20 |  |  |  | 0
1127158 | King St - OH Rebuild | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 147799.15 | 85480.48 | 147799.15 | 147799.15 | Manes, Bradley |  | 15-Oct-20 | 23-Feb-21 | 03-Aug-20 | 10-Nov-20 | 18-Dec-20 |  |  |  | 0
1127159 | Ferndale Ave - O/H Rebuild | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 251423.74 | 208156.86 | 251423.74 | 251423.74 | Lauryssen, John |  | 02-Oct-20 | 16-Dec-20 | 13-Jul-20 | 15-Jul-20 | 22-Sep-20 |  |  |  | 0
1129289 | Stevenson Street Townhomes - subdivision | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 23492.53 | 25201.5 | 23492.53 | 23492.53 | Stevens, Carl |  | 23-Jul-20 | 31-Dec-20 | 13-Jul-20 | 14-Aug-20 | 14-Sep-20 |  |  |  | 0
1129621 | 5M73 Feeder Cable | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 187649.39 |  | 0 | Stevens, Carl |  | 05-Feb-20 | 16-Dec-20 | 03-Feb-20 | 03-Feb-20 | 05-Feb-20
1129925 | Pole 7, 13 & 19 Westmount Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 39197.22 | 39377.49 | 39197.22 | 39197.22 | Lauryssen, John |  | 18-Nov-20 | 16-Dec-20 | 02-Nov-20 | 06-Jul-20 | 31-Jul-20 |  |  |  | 0
1131245 | Elizabeth & York | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 33198.38 | 55209.75 | 33198.38 | 33198.38 | Lauryssen, John |  |  | 16-Dec-20 |  | 24-Aug-20 | 24-Aug-20 |  |  |  | 0
1132251 | TH45 Gallery | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 15845.51 |  | 0 | Stevens, Carl |  |  | 31-Dec-21 | 18-Feb-20 | 28-Sep-20 | 28-Sep-20
1132375 | 149 Wellington St W - pole replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 46217.4 |  | 0 | Lauryssen, John |  |  | 16-Dec-20 | 18-Mar-20 | 18-Mar-20 | 19-Jun-20
1132511 | 120 Country Club Rebuild | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 466647.52 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 |  | 24-Aug-20 | 21-Sep-20 | Customer
1134205 | 190 Hanlon Creek | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 46503.52 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 | 09-Mar-20 | 09-Mar-20 | 20-Aug-20
1135255 | 590 Hanlon Creek Blvd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 6789.59 | 10788.11 | 6789.59 | 6789.59 | Stevens, Carl |  |  | 16-Dec-20 |  | 16-Oct-20 | 27-Oct-20 |  |  |  | 0
1145571 | Palmer St – OH Rebuild | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 105402.2 | 91362.54 | 105402.2 | 105402.2 | Manes, Bradley |  |  | 18-Jan-21 |  | 09-Nov-20 | 18-Dec-20 |  |  |  | 0
1145817 | Campbell TS 36M42 Feeder Egress Cable Replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 62364.77 | 70088.86 | 62364.77 | 62364.77 | Stevens, Carl |  |  | 16-Dec-20 | 23-Mar-20 | 14-Aug-20 | 14-Aug-20 |  |  |  | 0
1145818 | Campbell TS 36M61 Feeder Egress Cable Replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 66931.09 | 81731.23 | 66931.09 | 66931.09 | Stevens, Carl |  |  | 16-Dec-20 | 30-Mar-20 | 19-Aug-20 | 05-Sep-20 |  |  |  | 0
1146286 | PMSG017 - 33 Village Green - pad switch replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 83768.69 | 66288.75 | 282394.86 | 282394.86 | Stevens, Carl |  |  | 16-Dec-20 |  | 19-Oct-20 | 30-Oct-20 |  |  |  | 0
1146290 | PMSG073 - 8 Paisley St - pad switch replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 75449 | 75495.12 | 282394.86 | 282394.86 | Stevens, Carl |  |  | 18-Feb-21 |  | 30-Nov-20 | 30-Nov-20 |  |  |  | 0
1146291 | MJU-9 - 101 Lou's Blvd W - pad switch replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 22259.1 | 29579.27 | 282394.86 | 282394.86 | Stevens, Carl |  |  | 18-Feb-21 |  | 09-Sep-20 | 09-Sep-20 |  |  |  | 0
1146292 | MJU-10 - 129 Lou's Blvd W Fountain St - pad switch replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 22259.1 | 29130.14 | 282394.86 | 282394.86 | Stevens, Carl |  |  | 16-Dec-20 |  | 14-Aug-20 | 14-Aug-20 |  |  |  | 0
1150261 | 45 Marksham Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 495446.94 | 430341.66 | 495446.94 | 495446.94 | Stevens, Carl |  |  | 16-Dec-20 |  | 14-Sep-20 | 12-Nov-20 |  |  |  | 0
1151466 | Lee Street | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 23630 | 17151.64 | 23630 | 23630 | Stevens, Carl |  |  | 16-Dec-20 |  | 14-Aug-20 | 11-Sep-20 | Customer |  |  | 0
1151747 | Wyndham St S - Pole #22,26,28,30 | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 73759.78 |  | 0 | Lauryssen, John |  |  | 16-Dec-20 |  | 05-Oct-20 | 16-Oct-20
1152246 | L0738, Silvercreek Pkwy n/o Paisley. | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 88551.54 | 88679.68 | 88551.54 | 88551.54 | Manes, Bradley |  | 11-Sep-20 | 16-Dec-20 | 01-Sep-20 | 31-Jul-20 | 31-Jul-20 |  |  |  | 0
1152299 | L0003, College Ave E, at Powerhouse Lane | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 60333.8 | 53391.85 | 60333.8 | 60333.8 | Lauryssen, John |  | 02-Oct-20 | 22-Dec-20 | 28-Sep-20 | 05-Nov-20 | 05-Nov-20 |  |  |  | 0
1152311 | L1001, University e/o Gordon, | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 62749.78 | 55278.43 | 62749.78 | 62749.78 | Lauryssen, John |  | 25-Sep-20 | 22-Dec-20 | 21-Sep-20 | 05-Nov-20 | 05-Nov-20 |  |  |  | 0
1152312 | L0245, Martin Ave s/o Forbes. | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 60141.48 | 50061.71 | 60141.48 | 60141.48 | Lauryssen, John |  | 17-Sep-20 | 16-Dec-20 | 14-Sep-20 | 22-Sep-20 | 22-Sep-20 |  |  |  | 0
1152365 | L0123, York Rd, w/o Morris St | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 70261.97 |  | 0 | Lauryssen, John |  | 13-Oct-20 | 16-Dec-20 | 05-Oct-20 | 18-Sep-20 | 18-Sep-20
1154142 | Pole 10 Marlborough Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 11509.39 | 11509.39 | 11509.39 | 11509.39 | Lauryssen, John |  |  | 16-Dec-20 |  | 11-Dec-20 | 11-Dec-20 |  |  |  | 0
1154143 | 151 Metcalfe Street | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 7228.31 | 2125.61 | 7228.31 | 7228.31 | Lauryssen, John |  |  | 04-Jan-22 |  | 11-Dec-20 | 11-Dec-20 |  |  |  | 0
1154144 | Pole 18 Skov Cres | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 6385.4 | 6385.4 | 6385.4 | 6385.4 | Lauryssen, John |  |  | 16-Dec-20 |  | 11-Dec-20 | 11-Dec-20 |  |  |  | 0
1158656 | 245 Hanlon Blvd - Temp Service | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 0 | 0 |  | 0 | Stevens, Carl |  |  | 16-Dec-20 |  | 04-Jun-20 | 04-Jun-20
1159211 | Campbell TS 36M12 Feeder Egress | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 25864.08 | 23186.56 | 25864.08 | 25864.08 | Stevens, Carl |  |  | 16-Dec-20 |  | 30-Nov-20 | 11-Dec-20 |  |  |  | 0
1159216 | Campbell TS - 36M21 Feeder Egress Cable Replacment | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 27022.19 | 24568.87 | 27022.19 | 27022.19 | Stevens, Carl |  |  | 16-Dec-20 |  | 30-Nov-20 | 11-Dec-20 |  |  |  | 0
1159217 | Campbell TS - 36M52 Feeder Egress Cable Replacement | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 72863.33 | 77344.25 | 72863.33 | 72863.33 | Stevens, Carl |  |  | 16-Dec-20 |  | 23-Nov-20 | 27-Nov-20 |  |  |  | 0
1159282 | 28 Alma Street North | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 2464.07 | 2904.66 | 2464.07 | 2464.07 | Lauryssen, John |  |  | 16-Dec-20 |  | 08-Jun-20 | 08-Jun-20 |  |  |  | 0
1159965 | 355 Massey Rd - Linex - Linamar Cogen | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 31380.12 | 39261.37 | 31380.12 | 31380.12 | Stevens, Carl |  |  | 16-Dec-20 |  | 24-Oct-20 | 24-Oct-20 |  |  |  | 0
1160033 | 375 Massey Rd - Autocom - Linamar Cogen | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 36225.74 | 46313.47 | 36225.74 | 36225.74 | Stevens, Carl |  |  | 16-Dec-20 |  | 12-Sep-20 | 12-Sep-20 |  |  |  | 0
1160057 | 400 Massey Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 79182.57 | 64404.44 | 79182.57 | 79182.57 | Stevens, Carl |  |  | 16-Dec-20 |  | 05-Oct-20 | 12-Nov-20 |  |  |  | 0
1164226 | Pole 1 Winston Crescent | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 3567.43 | 7409.65 | 3567.43 | 3567.43 | Manes, Bradley |  |  | 16-Dec-20 |  | 20-Oct-20 | 20-Nov-20 |  |  |  | 0
1164230 | Pole 33 Lane Street | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 3317.63 | 6406.28 | 3317.63 | 3317.63 | Manes, Bradley |  |  | 16-Dec-20 |  | 20-Oct-20 | 02-Nov-20 |  |  |  | 0
1167063 | Menzie Ave (South of York Rd) | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 19625.67 | 94429.03 | 19625.67 | 19625.67 | Lauryssen, John |  |  | 16-Dec-20 |  | 19-Oct-20 | 20-Nov-20 |  |  |  | 0
1168926 | Carden St & Wyndham St N (MH#135) | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 413.29 | 10167.29 | 413.29 | 413.29 | Stevens, Carl |  |  | 16-Dec-20 |  | 24-Oct-20 | 24-Oct-20 |  |  |  | 0
1170919 | 242 Speedvale Avenue West | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 22547.58 | 22547.58 | 22547.58 | 22547.58 | Stevens, Carl |  |  | 16-Dec-20 |  | 04-Dec-20 | 04-Dec-20 |  |  |  | 0
1171192 | Pole 21 Vancouver Dr | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 3353.66 | 6938.41 | 3353.66 | 3353.66 | Manes, Bradley |  |  | 16-Dec-20 |  | 02-Nov-20 | 16-Nov-20 |  |  |  | 0
1171193 | Pole 31 Ottawa Crescent | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 13285.35 | 1942.15 | 13285.35 | 13285.35 | Lauryssen, John |  |  | 04-Jan-22 | 15-Dec-20 | 15-Dec-20 | 15-Dec-20 |  |  |  | 0
1171879 | Pole 222 York Rd | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 971.3 | 8805.25 | 971.3 | 971.3 | Lauryssen, John |  |  | 16-Dec-20 |  | 11-Dec-20 | 11-Dec-20 |  |  |  | 0
1171881 | Pole 13 Airpark Place | 840 - Southgate |  | Inactive | 99 | COMPLETE |  |  | 2020 |  | Alectra Utilities |  |  |  | 1904.64 | 6685.1 | 1904.64 | 1904.64 | Lauryssen, John |  |  | 16-Dec-20 |  | 11-Dec-20 | 11-Dec-20 |  |  |  | 0