## Template
Project Close Out
|  |  | Date: | 2023-08-02 | Something looks wrong with the RFC Report, Henry will get Maaz to look into it when he gets access to the Reports tab in P6
Project Details
Work Order Number | 646085
Project Name | YORKSHIRE ST N (LONDON RD W TO NORTHUMBERLAND ST) & LIVERPOOL ST
Design Tech | Alectra Utilities
Lines Supervisor | Lauryssen, John
Cost Breakdown
Project Estimate | 550228.89
Actual Cost | 715478.17
Difference | 165249.28
% Difference | 30.03%
| Planned Cost | Actual Cost | Difference | % Difference
Material | 239246.77 | 237308.35 | -1938.42 | -0.8102%
Personnel | 316727.06 | 263050.53 | -53676.53 | -16.95%
Tools/Facilities | 58303.69 | 118973.1 | 60669.41 | 104.1%
External: Other | 28000 | 96146.19 | 68146.19 | 243.4%
RFCs | 0
| Planned Hours | Actual Hours | Difference | % Difference
Labour Hours | 1772.9 | 2996.8 | 1223.9 | 69.03%
Lessons Learned/Mitigating Actions
People | Process |  | System

## CPI Report - June 6
Location | Year | Project ID | Project Name | Status | Sub-Status | Variance1 | Variance2 | Variance3 | Design Supervisor | Key Category? | Tech | Owner | Planned Total Costs | Actual Total Costs | Var$ | Var% | Planned Labour Costs | Actual Labour Costs | Var$ | Var% | Planned Material Costs | Actual Material Costs | Var$ | Var% | Planned Tool Costs | Actual Tool Costs | Var$ | Var% | Planned Ext Costs | Actual Ext Costs | Var$ | Var% | Planned Hours | Actual Hours | Var Hrs | Var% | Const Act Finish
Barrie | 2019 | 313976 | (WO313976) 30 KING ST. SOUTH, ALLISTON | 99 | COMPLETE | Engineering by-passed | N/A |  |  | No | Martin, Shane | Jeremy Wright | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 314240 | (WO 314240) Choice Properties- Commercial Development | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Martin, Shane | Jeremy Wright | 88392.79 | 72907.63 | -15485.16 | -17.52% | 13140.35 | 32105.32 | 18964.97 | 144.3% | 53650.94 | 35741.4 | -17909.54 | -33.38% | 2841.3 | 5060.91 | 2219.61 | 78.12% | 18760.2 | 0 | -18760.2 | -100% | 183 | 217 | 34 | 18.58% | 2019-01-08 01:00
Barrie | 2019 | 315241 | (WO315241) New 3 Ph. Service | 99 | CANCELLED | N/A |  |  |  | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 315290 | (WO315290) New 3 Ph. Service | 99 | COMPLETE | Engineering by-passed | N/A |  |  | No | Martin, Shane | Jeremy Wright | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 315453 | (WO315453) Zima Parkway Pole Line Upgrade | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Perks, Dan | Dan Kish | 130567 | 111400.88 | -19166.12 | -14.68% | 48912 | 0 | -48912 | -100% | 37759 | 0 | -37759 | -100% | 16293 | 0 | -16293 | -100% | 27603 | 0 | -27603 | -100% | 628 | 815.25 | 187.25 | 29.82% | 2019-04-13 01:00
Barrie | 2019 | 315984 | (WO 315984) 211 West Park Ave - Temp. UG, Bradford | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Perks, Dan | Jeremy Wright | 0 | 1683.36 | 1683.36 |  | 0 | 1455.36 | 1455.36 |  | 0 | 228 | 228 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 19 | 19 |  | 2019-07-26 01:00
Barrie | 2019 | 316180 | (WO316180) 39 BURKE ST, PENETANG | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Harris, Geoff L. | Jeremy Wright | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 316371 | (WO316371) New Retirement Home | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Martin, Shane | Jeremy Wright | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 316999 | (WO316999) New TX for Service Upgrade | 99 | CANCELLED | N/A |  |  |  | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 317310 | ( WO 317310) 2019 AB-B68 - P6579 - Collier St. - Air Break to manual 44kV LIS - Barrie | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A |  | No | Walters, Geoffrey D | Dan Kish | 182069 | 154941.53 | -27127.47 | -14.9% | 70070 | 66588.74 | -3481.26 | -4.968% | 51645 | 62762.83 | 11117.83 | 21.53% | 19404 | 6971.21 | -12432.79 | -64.07% | 40950 | 18618.75 | -22331.25 | -54.53% | 930 | 773.25 | -156.75 | -16.85% | 2019-02-24 01:00
Barrie | 2019 | 317779 | (317779) 122 Main Street- New Shoppers Drug Mart | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Martin, Shane | Jeremy Wright | 62903.23 | 57796.27 | -5106.96 | -8.119% | 14810.81 | 29431.73 | 14620.92 | 98.72% | 25223.15 | 22353.83 | -2869.32 | -11.38% | 2975.28 | 2870.37 | -104.91 | -3.526% | 19334.43 | 3140.34 | -16194.09 | -83.76% | 198.5 | 190.5 | -8 | -4.03% | 2019-02-02 01:00
Barrie | 2019 | 317781 | (WO317781) 2019 End of Life Automated Switch Replacements - AB-B1031 - Albert St. E & Douglas Dr. | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Walters, Geoffrey D | Dan Kish | 157545 | 139829.89 | -17715.11 | -11.24% | 42141 | 40393.18 | -1747.82 | -4.148% | 92349 | 86620.46 | -5728.54 | -6.203% | 11547 | 10734.75 | -812.25 | -7.034% | 11508 | 2081.5 | -9426.5 | -81.91% | 502 | 576 | 74 | 14.74% | 2019-01-12 01:00
Barrie | 2019 | 317917 | (WO317917) 1 Ph. Transformer Installation | 99 | CANCELLED | N/A |  |  |  | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 318169 | (WO318169) Edgehill Townhomes | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Perks, Dan | Jeremy Wright | 66009.8 | 58658.88 | -7350.92 | -11.14% | 10085.53 | 0 | -10085.53 | -100% | 2549.23 | 0 | -2549.23 | -100% | 1012.59 | 0 | -1012.59 | -100% | 52362.45 | 0 | -52362.45 | -100% | 134 | 71.5 | -62.5 | -46.64% | 2019-03-26 01:00
Barrie | 2019 | 318174 | (WO318174 ) McKenzie Pioneer | 99 | COMPLETE | Cont Est Over | N/A | N/A |  | No | Pollock, Kim | Jeremy Wright | 110099 | 118954.44 | 8855.44 | 8.043% | 48568 | 49142.94 | 574.94 | 1.184% | 26894 | 46131.06 | 19237.06 | 71.53% | 12587 | 4998.05 | -7588.95 | -60.29% | 22050 | 18682.39 | -3367.61 | -15.27% | 625 | 617 | -8 | -1.28% | 2019-02-09 01:00
Barrie | 2019 | 318188 | (WO318188) Tottenham Fire Hall Relocations | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Pollock, Kim | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 318210 | (WO318210) New 3 Phase Service | 99 | CANCELLED | N/A |  |  |  | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2019 | 318264 | (WO318264 ) Barrie - Bear Creek (Aspen Woods) - Inspect and Connect | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Perks, Dan | Jeremy Wright | 519756.33 | 513697.69 | -6058.64 | -1.166% | 29932.3 | 0 | -29932.3 | -100% | 4021.05 | 0 | -4021.05 | -100% | 6034.88 | 0 | -6034.88 | -100% | 479768.1 | 0 | -479768.1 | -100% | 400 | 310.25 | -89.75 | -22.44% | 2019-04-11 01:00
Barrie | 2019 | 318349 | (WO318349) Alliston - Briar Hill Vistas Ph 6 | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Perks, Dan | Jeremy Wright | 253208.82 | 254865.4 | 1656.58 | 0.6542% | 17016.18 | 0 | -17016.18 | -100% | 1433.35 | 0 | -1433.35 | -100% | 3008.54 | 0 | -3008.54 | -100% | 231750.75 | 0 | -231750.75 | -100% | 219 | 193 | -26 | -11.87% | 2019-01-16 01:00
Barrie | 2019 | 318632 | (WO318632 ) PMH-9 - BROWNING TRAIL SWITCHGEAR REPLACEMENT - Barrie | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Walters, Geoffrey D | Jeremy Wright | 24861 | 23524.19 | -1336.81 | -5.377% | 2548 | 761.52 | -1786.48 | -70.11% | 21759 | 19795.45 | -1963.55 | -9.024% | 554 | 2967.22 | 2413.22 | 435.6% | 0 | 0 | 0 |  | 34 | 13 | -21 | -61.76% | 2019-02-08 01:00
Barrie | 2019 | 318633 | (318633_ PMH-3 - 2 NEELANDS ST. SWITCHGEAR SLEEVE OUT - Barrie | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Walters, Geoffrey D | Jeremy Wright | 12356 | 7276.68 | -5079.32 | -41.11% | 2846 | 4561.37 | 1715.37 | 60.27% | 1408 | 2523.2 | 1115.2 | 79.2% | 647 | 192.11 | -454.89 | -70.31% | 7455 | 0 | -7455 | -100% | 38 | 68.5 | 30.5 | 80.26% | 2019-03-21 01:00
Barrie | 2019 | 318636 | (WO318636) 2019 PMH-3 - 141 HANMER ST. WEST SWITCHGEAR SLEEVE OUT - Barrie | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Walters, Geoffrey D | Jeremy Wright | 12356 | 5773.83 | -6582.17 | -53.27% | 2846 | 3766.77 | 920.77 | 32.35% | 1408 | 1823.2 | 415.2 | 29.49% | 647 | 183.86 | -463.14 | -71.58% | 7455 | 0 | -7455 | -100% | 38 | 51.5 | 13.5 | 35.53% | 2019-03-15 01:00
Barrie | 2019 | 318710 | (WO318710) LANGFORD BLVD AND HOLLAND STREET, BRADFORD. | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Harrington, James | Jeremy Wright | 134118 | 0 | -134118 | -100% | 11364 | 0 | -11364 | -100% | 14000 | 0 | -14000 | -100% | 1894 | 0 | -1894 | -100% | 106860 | 0 | -106860 | -100% | 147 | 108 | -39 | -26.53% | 2019-01-11 01:00
Barrie | 2021 | 452439 | (WO309672) 6857 & 7005 Industrial Parkway | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Perks, Dan | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-10 01:00
Barrie | 2022 | 452451 | (WO310348) 4 Don Hillock Drive. Best Western Hotel | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-10 01:00
Barrie | 2021 | 452454 | 452454 - 10TH SIDEROAD - BRADFORD/POLE LINE RELOCATION | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Harrington, James | Dan Kish | 1150873.03 | 932638.78 | -218234.25 | -18.96% | 98641.88 | 97266.11 | -1375.77 | -1.395% | 383268.79 | 328838.11 | -54430.68 | -14.2% | 3718 | 1088.14 | -2629.86 | -70.73% | 665244.36 | 481455.74 | -183788.62 | -27.63% | 321.5 | 238.5 | -83 | -25.82% | 2021-09-10 01:00
Barrie | 2019 | 452561 | 452561 (WO 314890) New Condo Development | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 145902.19 | 136921.94 | -8980.25 | -6.155% | 21652.52 | 17432.42 | -4220.1 | -19.49% | 27253.54 | 27925.51 | 671.97 | 2.466% | 1891.33 | 2136 | 244.67 | 12.94% | 95104.8 | 75185.85 | -19918.95 | -20.94% | 102 | 164 | 62 | 60.78% | 2019-12-14 01:00
Barrie | 2022 | 452576 | (WO315069) New 1 Phase Service. Bradford W.G. | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Persaud, Ryan | 0 | 145.82 | 145.82 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-08 01:00
Barrie | 2019 | 452577 | (WO315087) Summitpines Estates - Inspect and Connect | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Perks, Dan | Jeremy Wright | 437522.16 | 448648.87 | 11126.71 | 2.543% | 27534.89 | 33115.61 | 5580.72 | 20.27% | 5788.99 | 3453.89 | -2335.1 | -40.34% | 4312.08 | 1473 | -2839.08 | -65.84% | 399886.2 | 182575 | -217311.2 | -54.34% | 365 | 438.2 | 73.2 | 20.05% | 2019-10-08 01:00
Barrie | 2019 | 452589 | 452589 (WO 315223) Bradford East Developments Phase 1. CIVIL only | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Perks, Dan | Jeremy Wright | 809593.358 | 812100.44 | 2507.082 | 0.3097% | 46656.6692 | 48912.34 | 2255.6708 | 4.835% | 18493.2513 | 15318.33 | -3174.9213 | -17.17% | 9115.8375 | 2607 | -6508.8375 | -71.4% | 735327.6 | 166415.25 | -568912.35 | -77.37% | 0 | 354.5 | 354.5 |  | 2019-12-17 01:00
Barrie | 2022 | 452590 | 452590 - BRADFORD EAST DEVELOPMENTS PH2/INSPECT AND CONNECT | 99 | ANALYZE |  |  |  | Cranley, Stephen | No | Cranley, Stephen | Lotto, Jay | 560001.76 | 536549.45 | -23452.31 | -4.188% | 95020.18 | 71453.97 | -23566.21 | -24.8% | 4786.13 | 1148.83 | -3637.3 | -76% | 3858.45 | 2509 | -1349.45 | -34.97% | 456337 | 457665.45 | 1328.45 | 0.2911% | 252.03 | 133 | -119.03 | -47.23% | 2022-08-01 01:00
Barrie | 2021 | 452620 | 452620 (WO 315510) Mapleview Drive East Development | 99 | COMPLETE | Labour est. under |  |  | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 693394.07 | 734913.48 | 41519.41 | 5.988% | 35751.04 | 103094.32 | 67343.28 | 188.4% | 50943.59 | 44546.4 | -6397.19 | -12.56% | 10711.44 | 12146.72 | 1435.28 | 13.4% | 595988 | 567918.18 | -28069.82 | -4.71% | 865.78 | 509.75 | -356.03 | -41.12% | 2021-03-15 01:00
Barrie | 2020 | 452622 | 452622 - RELOCATION FOR RD IMPROVEMENTS/RELOCATION FOR RD IMPROVEMENTS | 99 | COMPLETE | Converted Project | N/A | N/A | Pelleja, Emily | No | Alectra Utilities | Dan Kish | 158674.13 | 92094.49 | -66579.64 | -41.96% | 19450.97 | 13721.93 | -5729.04 | -29.45% | 22820.79 | 19922.02 | -2898.77 | -12.7% | 306.26 | 0 | -306.26 | -100% | 116096.11 | 55631.05 | -60465.06 | -52.08% | 17.9 | 0.5 | -17.4 | -97.21% | 2020-12-02 01:00
Barrie | 2019 | 452647 | (WO 315764) Centre Street Riser Installation, Bradford ( Control Room Driven - Add'tl Spend Req'd) | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-11 01:00
Barrie | 2021 | 452679 | 452679 - EDGEHILL MANOR - SUBD RES EDS | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 117232.9 | 111093.01 | -6139.89 | -5.237% | 18998.95 | 14967.48 | -4031.47 | -21.22% | 1571.05 | 1952.21 | 381.16 | 24.26% | 1182.26 | 1030.55 | -151.71 | -12.83% | 95480.64 | 84976.7 | -10503.94 | -11% | 67.77 | 55.75 | -12.02 | -17.74% | 2021-03-03 01:00
Barrie | 2021 | 452728 | (WO316436) 21 MILL STREET | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Persaud, Ryan | 0 | 10634.28 | 10634.28 |  | 0 | 1030.67 | 1030.67 |  | 0 | 0 | 0 |  | 0 | 128 | 128 |  | 0 | 2078.34 | 2078.34 |  | 0 | 0 | 0 |  | 2019-12-18 01:00
Barrie | 2021 | 452737 | 452737 (WO 316470) Yonge - Go Village - Phase One | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 393878.45 | 378110.81 | -15767.64 | -4.003% | 34522.79 | 48337.68 | 13814.89 | 40.02% | 8886.4 | 2334.04 | -6552.36 | -73.73% | 2907.98 | 2847.24 | -60.74 | -2.089% | 347561.28 | 321816 | -25745.28 | -7.407% | 374.16 | 159.5 | -214.66 | -57.37% | 2021-07-13 01:00
Barrie | 2022 | 452738 | (WO316473) New Commercial Plaza | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Persaud, Ryan | 0 | 1293.52 | 1293.52 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-29 01:00
Barrie | 2021 | 452795 | 452795 (WO 316607) Belterra Phase 6 | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 1179528.19 | 1169723.7 | -9804.49 | -0.8312% | 76508.3 | 130475.21 | 53966.91 | 70.54% | 20265.11 | 17076.17 | -3188.94 | -15.74% | 7448.46 | 8603.33 | 1154.87 | 15.5% | 1075306.32 | 994191.6 | -81114.72 | -7.543% | 585.4 | 459.5 | -125.9 | -21.51% | 2021-10-07 01:00
Barrie | 2022 | 452798 | (WO316615) New Commercial Property | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Persaud, Ryan | 0 | 1217.94 | 1217.94 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-15 01:00
Barrie | 2021 | 452809 | 452809 - 35 Reid Drive - Warehouse | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 54555.75 | 43366.87 | -11188.88 | -20.51% | 16622.35 | 11373.21 | -5249.14 | -31.58% | 29635.75 | 22538.67 | -7097.08 | -23.95% | 1505.53 | 1740.47 | 234.94 | 15.61% | 6792.12 | 6288.5 | -503.62 | -7.415% | 81.64 | 64 | -17.64 | -21.61% | 2021-01-26 01:00
Barrie | 2019 | 452825 | 452825 (WO 316749) Water Pumping Station | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 32592.81 | 36001.59 | 3408.78 | 10.46% | 8275.15 | 5290.23 | -2984.92 | -36.07% | 22816.76 | 24554.02 | 1737.26 | 7.614% | 1500.9 | 3357 | 1856.1 | 123.7% | 0 | 0 | 0 |  | 65 | 78 | 13 | 20% | 2019-10-24 01:00
Barrie | 2022 | 452832 | 452832 - RER - MX - RELOC - GIVEN RD & BRIDGE ST - BARRIE LINE (1924) - RAILWAY CROSSINGS | 99 | COMPLETE | Under 10% | N/A | N/A | Vande Kuyt, Greg | No | Grahovac, John | Dan Kish | 210561.26 | 220527.7 | 9966.44 | 4.733% | 3626.31 | 9330.15 | 5703.84 | 157.3% | 60221.41 | 70213.78 | 9992.37 | 16.59% | 0 | 0 | 0 |  | 146713.54 | 137568.3 | -9145.24 | -6.233% | 0 | 0 | 0 |  | 2022-04-19
Barrie | 2022 | 452834 | 452834 - RER - MX - RELOC - DISSETTE ST - BARRIE LINE (66) - RAILWAY CROSSINGS | 99 | COMPLETE | Under 10% | N/A | N/A | Vande Kuyt, Greg | No | Grahovac, John | Dan Kish | 167798.71 | 189299.84 | 21501.13 | 12.81% | 11603.54 | 8274.32 | -3329.22 | -28.69% | 52234.77 | 54270.48 | 2035.71 | 3.897% | 0 | 0 | 0 |  | 103960.4 | 123234.92 | 19274.52 | 18.54% | 0 | 8.9 | 8.9 |  | 2022-03-25 01:00
Barrie | 2020 | 452838 | (WO316794) Metrolinx Crossing Big Bay Point Rd - Dodson Rd to Grand Forest Dr | 99 | CANCELLED | N/A |  |  | Vande Kuyt, Greg | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-21 01:00
Barrie | 2020 | 452903 | 452903 (WO 317048) 2020 Cable Replacement- Donald St. and Simcoe Terrace - Barrie | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | Yes | Alectra Utilities | Lotto, Jay | 578423.03 | 556739.49 | -21683.54 | -3.749% | 83532.69 | 72102.6 | -11430.09 | -13.68% | 9549.36 | 10500.62 | 951.26 | 9.962% | 6871.82 | 5478.94 | -1392.88 | -20.27% | 478469.16 | 468657.33 | -9811.83 | -2.051% | 872.25 | 318 | -554.25 | -63.54% | 2020-07-27 01:00
Barrie | 2020 | 452904 | 452904 (WO 317049) Bradford - FNB Ph4 - Inspect and Connect | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Jeremy Wright | 28327.04 | 262684.42 | 234357.38 | 827.3% | 21791.19 | 20469.35 | -1321.84 | -6.066% | 3029.27 | 1209.08 | -1820.19 | -60.09% | 3506.58 | 1644 | -1862.58 | -53.12% | 0 | 0 | 0 |  | 290 | 405 | 115 | 39.66% | 2020-01-30 01:00
Barrie | 2019 | 452913 | (WO 317116) Big Bay Point Urban Townhomes | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 89975.38 | 4762.5 | -85212.88 | -94.71% | 15344.66 | 4706.5 | -10638.16 | -69.33% | 38413.36 | 56 | -38357.36 | -99.85% | 3672.9 | 0 | -3672.9 | -100% | 32544.46 | 0 | -32544.46 | -100% | 0 | 0 | 0 |  | 2019-11-05 01:00
Barrie | 2019 | 452914 | 452914 (WO 317117) 70 Melbourne Drive | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Perks, Dan | Jeremy Wright | 59299.3 | 364536.63 | 305237.33 | 514.7% | 36792.92 | 17161.27 | -19631.65 | -53.36% | 14340.88 | 13400.93 | -939.95 | -6.554% | 8165.5 | 4048 | -4117.5 | -50.43% | 0 | 0 | 0 |  | 492 | 324.1 | -167.9 | -34.13% | 2019-11-05 01:00
Barrie | 2019 | 452948 | ( WO 317311) 2019 AB-B76 - P4491 - Huronia Rd. - Air Break to manual 44kV LIS - Barrie | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Walters, Geoffrey D | Jeremy Wright | 131177.48 | 104395.02 | -26782.46 | -20.42% | 46293.48 | 40012.81 | -6280.67 | -13.57% | 47835 | 48352.25 | 517.25 | 1.081% | 9162 | 5918.82 | -3243.18 | -35.4% | 27887 | 10111.14 | -17775.86 | -63.74% | 477 | 413.5 | -63.5 | -13.31% | 2019-02-13 01:00
Barrie | 2020 | 452950 | 452950 (WO 317313) Service Upgrade | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Jeremy Wright | 24842.71 | 40639.59 | 15796.88 | 63.59% | 4116.63 | 11132.24 | 7015.61 | 170.4% | 131.68 | 293.82 | 162.14 | 123.1% | 227.4 | 748.5 | 521.1 | 229.2% | 20367 | 20497.47 | 130.47 | 0.6406% | 21 | 105 | 84 | 400% | 2020-09-03 01:00
Barrie | 2019 | 452953 | ( WO 317321) Relocate Poles for Rd widening - HARVIE ROAD (HWY 400 TO ESSA ROAD), BARRIE | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Harrington, James | Dan Kish | 2348216 | 2256150.32 | -92065.68 | -3.921% | 45890 | 43010.85 | -2879.15 | -6.274% | 893341 | 659208.04 | -234132.96 | -26.21% | 6686 | 78024.63 | 71338.63 | 1067% | 1402299 | 2802.5 | -1399496.5 | -99.8% | 565 | 521 | -44 | -7.788% | 2019-05-25
Barrie | 2019 | 452958 | (WO317332) 8th Line and Langford Blvd, Bradford - Pole Relocations | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Harrington, James | Jeremy Wright | 201229 | 107418.31 | -93810.69 | -46.62% | 84842 | 401.85 | -84440.15 | -99.53% | 67143 | 72755.55 | 5612.55 | 8.359% | 30123 | 7359.66 | -22763.34 | -75.57% | 19121 | 26901.25 | 7780.25 | 40.69% | 1028 | 945.75 | -82.25 | -8.001% | 2019-04-11 01:00
Barrie | 2019 | 453014 | 453014 (WO 317528) 2018 Shirley Ave & Vine Cres. - Rear Lot O/H to U/G Conversion - Barrie | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 786533 | 747732.46 | -38800.54 | -4.933% | 109482 | 151402.79 | 41920.79 | 38.29% | 6833 | 18750.41 | 11917.41 | 174.4% | 39510 | 13503 | -26007 | -65.82% | 630708 | 564076.26 | -66631.74 | -10.56% | 1381.8 | 1439.45 | 57.65 | 4.172% | 2019-11-19 01:00
Barrie | 2019 | 453027 | 453027 (WO 317549) Medical Growing. 7163 3RD LINE TOTTENHAM | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Paterson, Greg | Jeremy Wright | 40688.26 | 35941.31 | -4746.95 | -11.67% | 15587.88 | 9539.72 | -6048.16 | -38.8% | 11191.39 | 9186.66 | -2004.73 | -17.91% | 1701.75 | 1306.5 | -395.25 | -23.23% | 12207.24 | 7342 | -4865.24 | -39.86% | 80 | 108 | 28 | 35% | 2019-11-14 01:00
Barrie | 2019 | 453044 | (WO317650) 136 BARRIE ST, BRADFORD - LOFT | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 54791.76 | 48612.03 | -6179.73 | -11.28% | 16941.71 | 492.68 | -16449.03 | -97.09% | 28215.18 | 21328.7 | -6886.48 | -24.41% | 4007.85 | 171 | -3836.85 | -95.73% | 4335.24 | 0 | -4335.24 | -100% | 242 | 220 | -22 | -9.091% | 2019-06-04
Barrie | 2019 | 453048 | (WO317660) Highway 89 and 10th SdRd, Pole Relocations | 98 | COMPLETE | Labour est. over | N/A | N/A | Corriveau, Tom N | No | Harrington, James | Jeremy Wright | 28969 | 37180.26 | 8211.26 | 28.34% | 15260 | 14811.73 | -448.27 | -2.938% | 6877 | 5494.88 | -1382.12 | -20.1% | 4500 | 824.23 | -3675.77 | -81.68% | 2332 | 495 | -1837 | -78.77% | 160 | 172.5 | 12.5 | 7.812% | 2019-05-11
Barrie | 2020 | 453061 | 453061 (WO 317741) Pole Line rebuild - AB-B1029 Dufferin St between MS431 and Albert St. Allisto | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Alectra Utilities | Jeremy Wright | 609185.06 | 747804.32 | 138619.26 | 22.75% | 230929.48 | 303542.97 | 72613.49 | 31.44% | 246535.93 | 237772.72 | -8763.21 | -3.555% | 47733.02 | 122449.1 | 74716.08 | 156.5% | 83986.63 | 84039.53 | 52.9 | 0.06299% | 3505.64 | 3402 | -103.64 | -2.956% | 2020-08-08 01:00
Barrie | 2019 | 453062 | (WO317742) 138M7 - AB-B1034 - Dufferin St - Air Break to Automated 44kV - Alliston | 99 | COMPLETE | Labour est. over |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 128040 | 128488.7 | 448.7 | 0.3504% | 36842 | 35273.22 | -1568.78 | -4.258% | 69812 | 74401.07 | 4589.07 | 6.573% | 10020 | 9989.87 | -30.13 | -0.3007% | 11366 | 8824.54 | -2541.46 | -22.36% | 494 | 458.5 | -35.5 | -7.186% | 2019-06-27 01:00
Barrie | 2020 | 453086 | (WO317853) Customer Secondary Relocate - 429 Champlain Rd - Penetang | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-10 01:00
Barrie | 2022 | 453113 | (WO317979) Changes to Metering | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Persaud, Ryan | 0 | 2001.75 | 2001.75 |  | 0 | 151.65 | 151.65 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2021-01-06 01:00
Barrie | 2019 | 453163 | (WO318075) 544&550 St. Vincent St | 99 | COMPLETE | Labour est. under |  |  | Cranley, Stephen | No | Perks, Dan | Jeremy Wright | 147230.9497 | 149116.53 | 1885.5803 | 1.281% | 14504.3039 | 3562.91 | -10941.3939 | -75.44% | 5309.8388 | 541.44 | -4768.3988 | -89.8% | 2228.457 | 848 | -1380.457 | -61.95% | 125188.35 | 0 | -125188.35 | -100% | 187 | 228.25 | 41.25 | 22.06% | 2019-07-03 01:00
Barrie | 2021 | 453171 | 453171 - INDUSTRIAL PKWY- RELOCATE POLE/RELOCATE POLE FOR INTERSECTION | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Corriveau, Tom N | No | Harrington, James | Dan Kish | 46489.49 | 17115.31 | -29374.18 | -63.18% | 26857.03 | 6612.44 | -20244.59 | -75.38% | 10120.91 | 5422.37 | -4698.54 | -46.42% | 4759.55 | 2140.5 | -2619.05 | -55.03% | 4752 | 2940 | -1812 | -38.13% | 169.6 | 58 | -111.6 | -65.8% | 2021-06-14 01:00
Barrie | 2019 | 453172 | (WO318090) 3 CONCERT WAY - PERMANENT | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 11358.67 | 13584.42 | 2225.75 | 19.6% | 5598.56 | 6369.63 | 771.07 | 13.77% | 624.28 | 624 | -0.28 | -0.04485% | 1605.45 | 275.79 | -1329.66 | -82.82% | 0 | 0 | 0 |  | 94 | 79.5 | -14.5 | -15.43% | 2019-05-16
Barrie | 2019 | 453183 | (WO318119) Pole Betterment Batch #1 – Yonge St and Big Bay Pt.Rd ( approx 22 poles) | 99 | COMPLETE | Labour est. over | N/A | N/A | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 742586 | 258748.18 | -483837.82 | -65.16% | 20534 | 13498.73 | -7035.27 | -34.26% | 208537 | 209104.34 | 567.34 | 0.2721% | 1155 | 31353.05 | 30198.05 | 2615% | 512360 | 4792.06 | -507567.94 | -99.06% | 260 | 167.75 | -92.25 | -35.48% | 2019-03-29 01:00
Barrie | 2019 | 453186 | (WO318123) 340 PENETANGUISHENE ROAD, BARRIE | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Perks, Dan | Jeremy Wright | 69661.23 | 71340.32 | 1679.09 | 2.41% | 9864.62 | 6678 | -3186.62 | -32.3% | 699.43 | 431.14 | -268.29 | -38.36% | 943.98 | 2334 | 1390.02 | 147.3% | 58153.2 | 27692 | -30461.2 | -52.38% | 132 | 135 | 3 | 2.273% | 2019-09-18 01:00
Barrie | 2019 | 453189 | (WO318133) New 3 Phase Service | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 53014.4241 | 50940.51 | -2073.9141 | -3.912% | 17976.9501 | 9391.8 | -8585.1501 | -47.76% | 26033.1225 | 22952.89 | -3080.2325 | -11.83% | 3851.4125 | 1977 | -1874.4125 | -48.67% | 4584.5 | 5336 | 751.5 | 16.39% | 230.5 | 241.5 | 11 | 4.772% | 2019-12-03 01:00
Barrie | 2020 | 453190 | 453190 (WO 318134) National Homes Bradford Ph 2 | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Jeremy Wright | 202003.83 | 124170.6 | -77833.23 | -38.53% | 15009.82 | 5983.07 | -9026.75 | -60.14% | 2092.73 | 986.7 | -1106.03 | -52.85% | 680.28 | 512 | -168.28 | -24.74% | 184221 | -17239.81 | -201460.81 | -109.4% | 55 | 74.5 | 19.5 | 35.45% | 2020-07-08 01:00
Barrie | 2019 | 453193 | (WO318147) Edgehill Drive - Make Ready Work to Raise Secondary Guards for Permit 18-086 | 99 | COMPLETE | Labour est. over | N/A | N/A | Corriveau, Tom N | No | Harrington, James | Aulis, John -x | 5589 | 4890.14 | -698.86 | -12.5% | 1262 | 0 | -1262 | -100% | 300 | 0 | -300 | -100% | 201 | 0 | -201 | -100% | 3826 | 0 | -3826 | -100% | 16 | 11 | -5 | -31.25% | 2019-05-08
Barrie | 2021 | 453197 | (WO318155) Harbour Pointe - Penetanguishene | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Harrington, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-11
Barrie | 2019 | 453199 | (WO318157) 357 Yonge St, Barrie | 99 | COMPLETE | Labour est. under | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 75111.89 | 117567.51 | 42455.62 | 56.52% | 13978.02 | 34943.15 | 20965.13 | 150% | 35333.09 | 30160.75 | -5172.34 | -14.64% | 2945.25 | 4682.87 | 1737.62 | 59% | 19277.95 | 2853.1 | -16424.85 | -85.2% | 202 | 252 | 50 | 24.75% | 2019-05-11
Barrie | 2019 | 453251 | (WO318257) 430 Holland St. West- Bradford Boston Pizza | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 72825.77 | 66787.29 | -6038.48 | -8.292% | 14547.04 | 400.48 | -14146.56 | -97.25% | 48783.83 | 38738.32 | -10045.51 | -20.59% | 3222.45 | 6036.97 | 2814.52 | 87.34% | 3733.8 | 820 | -2913.8 | -78.04% | 192 | 144.99 | -47.01 | -24.48% | 2019-06-11 01:00
Barrie | 2020 | 453295 | 453295 (WO 318398) Barrie Recycling- Ser. Upgrade | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 59364.68 | 45290.43 | -14074.25 | -23.71% | 12437.73 | 7585.93 | -4851.8 | -39.01% | 33393.9 | 26401.35 | -6992.55 | -20.94% | 4115.53 | 1698.05 | -2417.48 | -58.74% | 6821.52 | 6435.4 | -386.12 | -5.66% | 173 | 112 | -61 | -35.26% | 2020-10-06 01:00
Barrie | 2019 | 453296 | (WO318399) 120 ELLIS DRIVE, BARRIE | 99 | COMPLETE | Labour est. over |  |  | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 58359.74 | 50145.29 | -8214.45 | -14.08% | 10423.77 | 3700.05 | -6723.72 | -64.5% | 35539.1 | 26551.8 | -8987.3 | -25.29% | 3296.43 | 4723 | 1426.57 | 43.28% | 5936 | 5600 | -336 | -5.66% | 149.5 | 137 | -12.5 | -8.361% | 2019-07-12 01:00
Barrie | 2020 | 453297 | 453297 (WO 318400) - 948 FULLER AVE - HOSPICE | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Jeremy Wright | 75110.91 | 63533.61 | -11577.3 | -15.41% | 27357.43 | 20176.47 | -7180.96 | -26.25% | 29267.89 | 33388.61 | 4120.72 | 14.08% | 4663.21 | 4452.57 | -210.64 | -4.517% | 13822.38 | 4617 | -9205.38 | -66.6% | 322.09 | 177.5 | -144.59 | -44.89% | 2020-01-14 01:00
Barrie | 2022 | 453298 | 453298 - WEST ALLISTON 3 PHASE 1 - SUBD RES EDS | 99 | ANALYZE |  |  |  | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 488079.02 | 525571.06 | 37492.04 | 7.682% | 46101.05 | 26540.99 | -19560.06 | -42.43% | 9741.47 | 9973.58 | 232.11 | 2.383% | 5797.42 | 4564 | -1233.42 | -21.28% | 426439.08 | 131.35 | -426307.73 | -99.97% | 306.2 | 204.5 | -101.7 | -33.21% | 2022-06-12 01:00
Barrie | 2019 | 453396 | (WO318556) 322 KING STREET | 99 | COMPLETE | Labour est. over |  |  | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 61208.1682 | 42304.26 | -18903.9082 | -30.88% | 10584.462 | 1422.44 | -9162.022 | -86.56% | 29020.1977 | 21773.95 | -7246.2477 | -24.97% | 2864.4 | 768 | -2096.4 | -73.19% | 6428.8875 | 4452.75 | -1976.1375 | -30.74% | 174 | 125.5 | -48.5 | -27.87% | 2019-07-18 01:00
Barrie | 2021 | 453417 | (WO318607) Cauthers Crescent Extension | 99 | CANCELLED | N/A |  |  |  | No | Perks, Dan | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-08 01:00
Barrie | 2019 | 453422 | (WO318615) 2019 Pdmt TX Rep North Batch 1 | 99 | COMPLETE | Labour est. over | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 133204 | 99879.74 | -33324.26 | -25.02% | 17884 | 13905.34 | -3978.66 | -22.25% | 108634 | 75334.78 | -33299.22 | -30.65% | 6686 | 10639.62 | 3953.62 | 59.13% | 0 | 0 | 0 |  | 230 | 213.75 | -16.25 | -7.065% | 2019-05-23
Barrie | 2019 | 453433 | (WO318627) 2019 Pdmt TX Rep North Batch 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 112104 | 82545.16 | -29558.84 | -26.37% | 21815 | 9288.34 | -12526.66 | -57.42% | 82767 | 66269.82 | -16497.18 | -19.93% | 7522 | 6987 | -535 | -7.112% | 0 | 0 | 0 |  | 280 | 222.5 | -57.5 | -20.54% | 2019-08-08 01:00
Barrie | 2019 | 453434 | (WO318628) 2019 PDMT TX REP NORTH BATCH 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 130671 | 111244.03 | -19426.97 | -14.87% | 24149 | 4551.16 | -19597.84 | -81.15% | 98164 | 11107.92 | -87056.08 | -88.68% | 8358 | 4244 | -4114 | -49.22% | 0 | 0 | 0 |  | 310 | 282 | -28 | -9.032% | 2019-07-12 01:00
Barrie | 2019 | 453435 | (WO318629) 2019 Pdmt TX Rep North Batch 4 | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 129626 | 113881.85 | -15744.15 | -12.15% | 24149 | 8202.55 | -15946.45 | -66.03% | 97119 | 35058.07 | -62060.93 | -63.9% | 8358 | 6750 | -1608 | -19.24% | 0 | 0 | 0 |  | 310 | 321 | 11 | 3.548% | 2019-07-23 01:00
Barrie | 2019 | 453436 | 453436 (WO 318630) 2019 Pdmt TX Rep North Batch 5 | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 140676 | 158363.83 | 17687.83 | 12.57% | 14811 | 18281.58 | 3470.58 | 23.43% | 121653 | 110491.77 | -11161.23 | -9.175% | 4212 | 3441.33 | -770.67 | -18.3% | 0 | 26149.15 | 26149.15 |  | 161 | 232.25 | 71.25 | 44.25% | 2019-11-30 01:00
Barrie | 2019 | 453437 | 453437 (WO 318631) DA P4872 - Royal Parkside Dr. - Air Break to Automated 44kV | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Dan Kish | 174165 | 165369.89 | -8795.11 | -5.05% | 40924 | 48106.74 | 7182.74 | 17.55% | 101096 | 93896.15 | -7199.85 | -7.122% | 16114 | 19106 | 2992 | 18.57% | 16031 | 4261 | -11770 | -73.42% | 482 | 767 | 285 | 59.13% | 2019-09-10 01:00
Barrie | 2020 | 453450 | 453450 (WO 318677) 14314 YONGE ST - Retirement | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Cory Ruiter | 59909.88 | 63335.4 | 3425.52 | 5.718% | 11962.09 | 18369 | 6406.91 | 53.56% | 33138 | 32359.97 | -778.03 | -2.348% | 954.47 | 4103.81 | 3149.34 | 330% | 13855.32 | 6709.39 | -7145.93 | -51.58% | 95.45 | 161 | 65.55 | 68.67% | 2020-06-30 01:00
Barrie | 2019 | 453453 | (WO318681) BARRIE TS RECONSTRUCTION / UPGRADE FOR HYDRO ONE ( Cancelled) | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-11 01:00
Barrie | 2019 | 453454 | 453454 (WO 318682) 2019 STORM HARDENING - ANNE ST. FROM NEELANDS TO CUNDLES - Barrie | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Dan Kish | 416125 | 346735.51 | -69389.49 | -16.68% | 155760 | 36273.85 | -119486.15 | -76.71% | 118504 | 83076.89 | -35427.11 | -29.9% | 57591 | 11550 | -46041 | -79.94% | 84270 | 19796.67 | -64473.33 | -76.51% | 2002.6 | 1935.25 | -67.35 | -3.363% | 2019-09-11 01:00
Barrie | 2019 | 453497 | 453497 (WO 318736) Bell JU Permit 18-152. TOLLENDAL MILL ROAD, BARRIE | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Martin, Shane | Aulis, John -x | 11422.1 | 6606.4 | -4815.7 | -42.16% | 3782.41 | 3151.25 | -631.16 | -16.69% | 1595.71 | 739.68 | -856.03 | -53.65% | 391.8 | 859 | 467.2 | 119.2% | 5652.18 | 1856.47 | -3795.71 | -67.15% | 30.25 | 26 | -4.25 | -14.05% | 2019-11-14 01:00
Barrie | 2022 | 453505 | (WO318745) 430 FERNDALE RD, APARTMENT BUILDING | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 0 | 10975.99 | 10975.99 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-25 01:00
Barrie | 2022 | 453506 | (WO318746) 545 TIFFIN STREET | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 0 | 195.43 | 195.43 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-25 01:00
Barrie | 2020 | 453514 | 453514 (WO 318759) Sandstorm Phase 7C | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Lotto, Jay | 271575.21 | 230139.53 | -41435.68 | -15.26% | 22701.17 | 27742.49 | 5041.32 | 22.21% | 2542.08 | 2640.87 | 98.79 | 3.886% | 1176.28 | 301.5 | -874.78 | -74.37% | 245155.68 | 197870 | -47285.68 | -19.29% | 187.8 | 131.75 | -56.05 | -29.85% | 2020-08-14 01:00
Barrie | 2022 | 453519 | (WO318767) 162 ST. JOHN'S SIDEROAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-18 01:00
Barrie | 2022 | 453526 | (WO318775) Hydro One Scada Switch Install. FERNDALE DRIVE, BARRIE | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Harrington, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-07 01:00
Barrie | 2020 | 453527 | 453527 (WO 318776) 6TH LINE AND SIMCOE RD, BRADFORD | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Lotto, Jay | 266195.3 | 255158.4 | -11036.9 | -4.146% | 24416.47 | 29765.45 | 5348.98 | 21.91% | 7355.09 | 3736.52 | -3618.57 | -49.2% | 1934.3 | 1824 | -110.3 | -5.702% | 232489.44 | 215268 | -17221.44 | -7.407% | 226.23 | 124.5 | -101.73 | -44.97% | 2020-08-07 01:00
Barrie | 2019 | 453530 | (WO318780) 430 FERDALE DR, BARRIE - APARTMENTS | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 63580.96 | 47913 | -15667.96 | -24.64% | 14189.54 | 1285.78 | -12903.76 | -90.94% | 24883.09 | 21174.89 | -3708.2 | -14.9% | 4697.92 | 0 | -4697.92 | -100% | 16445.05 | 0 | -16445.05 | -100% | 152.5 | 96.5 | -56 | -36.72% | 2019-07-30 01:00
Barrie | 2020 | 453532 | (WO318784) 14 MILL STREET DEVELOPMENT IN TOTTENHAM ( Customer Driven) | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Alectra Utilities | Persaud, Ryan | 0 | -6015.77 | -6015.77 |  | 0 | 60.93 | 60.93 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 705.6 | 705.6 |  | 0 | 0 | 0 |  | 2019-08-14 01:00
Barrie | 2022 | 453533 | (WO318785) 25 ALBERT STREET WEST, ALLISTON | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Jeremy Wright | 0 | 273.59 | 273.59 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-14 01:00
Barrie | 2019 | 453534 | 453534 (WO 318786) Relocate Pole for Culvert. INNISFIL STREET N/O TIFFIN STREET, BARRIE | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Harrington, James | Dan Kish | 108545 | 102750.95 | -5794.05 | -5.338% | 28779 | 31735.22 | 2956.22 | 10.27% | 44731 | 18021.97 | -26709.03 | -59.71% | 9002 | 16889.92 | 7887.92 | 87.62% | 26033 | 27496.1 | 1463.1 | 5.62% | 364 | 646.27 | 282.27 | 77.55% | 2019-08-14 01:00
Barrie | 2019 | 453543 | (WO318795) MAPLEVIEW DRIVE AND STUNDEN LANE, BARRIE | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Harrington, James | Jeremy Wright | 10047.26 | 6264.06 | -3783.2 | -37.65% | 6456.04 | 4028.58 | -2427.46 | -37.6% | 1392.05 | 625.38 | -766.67 | -55.07% | 598.23 | 734 | 135.77 | 22.7% | 1600.94 | 876.1 | -724.84 | -45.28% | 34 | 42 | 8 | 23.53% | 2019-09-28 01:00
Barrie | 2020 | 453551 | 453551 (WO 318818) 60 & 70 QUEEN STREET SOUTH, TOTTENHAM | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Jeremy Wright | 42488.94 | 24128.98 | -18359.96 | -43.21% | 11325.14 | 9088.78 | -2236.36 | -19.75% | 14926.05 | 8193.66 | -6732.39 | -45.1% | 1387.75 | 2953.5 | 1565.75 | 112.8% | 14850 | 3893.04 | -10956.96 | -73.78% | 39 | 90.75 | 51.75 | 132.7% | 2020-08-25 01:00
Barrie | 2019 | 453562 | 453562 (WO 318829) 1588 ST. JOHN'S SIDE ROAD | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Fitz Randolph, Kim C | Steve Rumble | 10952 | 6110.09 | -4841.91 | -44.21% | 2409 | 565.69 | -1843.31 | -76.52% | 0 | 0 | 0 |  | 393 | 0 | -393 | -100% | 8150 | 5544.4 | -2605.6 | -31.97% | 32 | 0 | -32 | -100% | 2019-08-02 01:00
Barrie | 2019 | 453566 | (WO318854) ZAYO J/U permit HE2018-144. WELHAM ROAD, BARRIE | 99 | COMPLETE | Engineering by-passed | N/A | N/A | O'Gay, Brian | No | Harrington, James | Jeremy Wright | 0 | 5831.93 | 5831.93 |  | 0 | 2031.68 | 2031.68 |  | 0 | 1396.19 | 1396.19 |  | 0 | 183.1 | 183.1 |  | 0 | 2220.96 | 2220.96 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Barrie | 2021 | 453622 | 453622 - DYKIE SUBDIVISION - SUBD RES EDS | 98 | COMPLETE | Labour est. over | Cont Est Over | N/A | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 84256.53 | 74983.08 | -9273.45 | -11.01% | 18029.26 | 10045.83 | -7983.43 | -44.28% | 637.77 | 1524.94 | 887.17 | 139.1% | 817.58 | 712 | -105.58 | -12.91% | 64771.92 | 59974 | -4797.92 | -7.407% | 61.23 | 37 | -24.23 | -39.57% | 2021-07-13 01:00
Barrie | 2022 | 453624 | (WO318921) 558 HOLLAND STREET WEST | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Persaud, Ryan | 0 | 17119.44 | 17119.44 |  | 0 | 6166.08 | 6166.08 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2907.9 | 2907.9 |  | 0 | 1 | 1 |  | 2019-10-11 01:00
Barrie | 2021 | 453626 | 453626 - MAPLEVIEW DR. POLE RELOCATIONS/RELOCATE FOR RD WIDENING | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Pelleja, Emily | No | Battistella, Alexander | Jeremy Wright | 659610.37 | 439600.87 | -220009.5 | -33.35% | 217047.58 | 129244.4 | -87803.18 | -40.45% | 170191.38 | 162627.6 | -7563.78 | -4.444% | 60319.89 | 52661 | -7658.89 | -12.7% | 212051.52 | 94843.9 | -117207.62 | -55.27% | 1847.8 | 1438 | -409.8 | -22.18% | 2021-08-09 01:00
Barrie | 2020 | 453627 | 453627 (WO 318925) 8 Truman Road, Barrie | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Jeremy Wright | 44390.45 | 55123.19 | 10732.74 | 24.18% | 22185.33 | 23730.35 | 1545.02 | 6.964% | 15013.88 | 12773.18 | -2240.7 | -14.92% | 2995.76 | 9593.2 | 6597.44 | 220.2% | 4195.48 | 4659.5 | 464.02 | 11.06% | 223 | 253.5 | 30.5 | 13.68% | 2020-02-01 01:00
Barrie | 2021 | 453653 | 453653 - MAPLEVIEW DRIVE AND PRINCE WILLIAM WAY, BARRIE - RELOCATE POLES FOR RD WIDENING | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Harrington, James | Dan Kish | 716809.78 | 630978.51 | -85831.27 | -11.97% | 26553.62 | 56238.52 | 29684.9 | 111.8% | 214846.02 | 186000.8 | -28845.22 | -13.43% | 1056 | 1184.06 | 128.06 | 12.13% | 474354.14 | 386313.42 | -88040.72 | -18.56% | 71.25 | 65 | -6.25 | -8.772% | 2021-09-10 01:00
Barrie | 2019 | 453658 | 453658 (WO 318967) 71 Commerce Park Dr - New 3ph | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 69910.53 | 50404.35 | -19506.18 | -27.9% | 15760.43 | 8906.92 | -6853.51 | -43.49% | 24433.74 | 22555.12 | -1878.62 | -7.689% | 1555.36 | 1236 | -319.36 | -20.53% | 28161 | 7251.8 | -20909.2 | -74.25% | 89 | 70 | -19 | -21.35% | 2019-12-17 01:00
Barrie | 2022 | 453662 | Barrie TS Upgrade Feeders and Metering | 99 | CANCELLED | N/A |  |  |  | Yes | East | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-03 01:00
Barrie | 2019 | 453678 | 453678 (WO 318990) 2019 - 44KV INSULATOR REPLACEMENT PROGRAM - BARRIE | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 147000 | 116646.75 | -30353.25 | -20.65% | 64994 | 3425.75 | -61568.25 | -94.73% | 54057 | 7691.53 | -46365.47 | -85.77% | 27949 | 0 | -27949 | -100% | 0 | 39682.55 | 39682.55 |  | 839 | 571 | -268 | -31.94% | 2019-12-25 01:00
Barrie | 2020 | 453688 | 453688 (WO 319001) BELL FARM ROAD (ST. VINCENT TO DUCKWORTH ST), BARRIE | 99 | COMPLETE | Converted Project |  |  | Pelleja, Emily | No | Alectra Utilities | Dan Kish | 197759.41 | 160715.15 | -37044.26 | -18.73% | 24703.6 | 26272.01 | 1568.41 | 6.349% | 27308.65 | 26815.19 | -493.46 | -1.807% | 306.26 | 1109 | 802.74 | 262.1% | 145440.9 | 103301.59 | -42139.31 | -28.97% | 28.85 | 75 | 46.15 | 160% | 2020-08-20 01:00
Barrie | 2019 | 453718 | 453718 (WO 319035) Pole Betterment. Alliston. BATCH 1 (21 Poles) | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 258164.64 | 243301.9 | -14862.74 | -5.757% | 118935.64 | 26845.4 | -92090.24 | -77.43% | 75770 | 14217.01 | -61552.99 | -81.24% | 37489 | 12056.5 | -25432.5 | -67.84% | 25970 | 3448.6 | -22521.4 | -86.72% | 1281 | 1467.5 | 186.5 | 14.56% | 2019-09-28 01:00
Barrie | 2019 | 453797 | 453797 - SC13413 – PMH-9 change out to PVI-9 switch gear – 101 Marsellus – Barrie | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | Yes | Walters, Geoffrey D | Jeremy Wright | 28894 | 149208.15 | 120314.15 | 416.4% | 5248 | 19564.19 | 14316.19 | 272.8% | 21974 | 99666.65 | 77692.65 | 353.6% | 1672 | 1853.5 | 181.5 | 10.86% | 0 | 28123.81 | 28123.81 |  | 56 | 191.5 | 135.5 | 242% | 2019-11-27 01:00
Barrie | 2019 | 453799 | 453799 (WO 319122) S-B355846 – 555 Bayview - InLine switch to 44kV Automated – Barrie | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 170479 | 172343.28 | 1864.28 | 1.094% | 35670 | 46039.96 | 10369.96 | 29.07% | 113274 | 107565.3 | -5708.7 | -5.04% | 13055 | 15973.77 | 2918.77 | 22.36% | 8480 | 2764.25 | -5715.75 | -67.4% | 459 | 658 | 199 | 43.36% | 2019-10-12 01:00
Barrie | 2019 | 453800 | 453800 (WO 319123) DA - S‐B1019 - 62 Ardagh Road - InLine Switch to Automated 44kV - Barrie | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Dan Kish | 239514.29 | 224726.63 | -14787.66 | -6.174% | 70644.73 | 23586.85 | -47057.88 | -66.61% | 140502.47 | 108391.12 | -32111.35 | -22.85% | 14831.45 | 0 | -14831.45 | -100% | 13535.64 | 92748.66 | 79213.02 | 585.2% | 1023.84 | 87 | -936.84 | -91.5% | 2019-12-12 01:00
Barrie | 2020 | 453802 | 453802 (WO 319125) DA - AB‐B25 - 31 Poyntz Street - Air Break to Automated 44kV - Barrie | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | Yes | Alectra Utilities | Dan Kish | 268709.59 | 349602.92 | 80893.33 | 30.1% | 102728.26 | 143708.06 | 40979.8 | 39.89% | 124094.81 | 137759.45 | 13664.64 | 11.01% | 22326.64 | 41034.61 | 18707.97 | 83.79% | 19559.88 | 27100.8 | 7540.92 | 38.55% | 856 | 1666.5 | 810.5 | 94.68% | 2020-01-18 01:00
Barrie | 2019 | 453808 | 453808 (WO 319131) Pole Betterment. Alliston. BATCH 2 (18 Poles) | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 307716 | 262363.68 | -45352.32 | -14.74% | 143526 | 105230.01 | -38295.99 | -26.68% | 81249 | 74839.46 | -6409.54 | -7.889% | 56441 | 56193 | -248 | -0.4394% | 26500 | 26101.21 | -398.79 | -1.505% | 1447 | 1517.75 | 70.75 | 4.889% | 2019-11-23 01:00
Barrie | 2019 | 453809 | 453809 (WO 319132) Pole Betterment. Alliston. BATCH 3 (15 Poles) | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 192908 | 94675 | -98233 | -50.92% | 95310 | 43998 | -51312 | -53.84% | 34460 | 12489 | -21971 | -63.76% | 34942 | 28174 | -6768 | -19.37% | 28196 | 10014 | -18182 | -64.48% | 1216 | 1119.5 | -96.5 | -7.936% | 2019-11-19 01:00
Barrie | 2019 | 453810 | 453810 (WO 319133) Pole Betterment. Alliston. BATCH 4 (2 Poles) | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 85294.43 | 73222.83 | -12071.6 | -14.15% | 39451.19 | 35820.99 | -3630.2 | -9.202% | 15640.97 | 13193.6 | -2447.37 | -15.65% | 5361.1 | 8719 | 3357.9 | 62.63% | 24841.17 | 15489.24 | -9351.93 | -37.65% | 292 | 351.5 | 59.5 | 20.38% | 2019-12-21 01:00
Barrie | 2019 | 453811 | 453811 (WO 319134) Pole Betterment. Tottenham. BATCH 1 (21 Poles) | 99 | COMPLETE | Converted Project |  |  | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 275683 | 262585.69 | -13097.31 | -4.751% | 111093 | 104000.5 | -7092.5 | -6.384% | 73438 | 76462.05 | 3024.05 | 4.118% | 39689 | 39112.62 | -576.38 | -1.452% | 51463 | 42910.52 | -8552.48 | -16.62% | 240 | 1215 | 975 | 406.2% | 2019-12-07 01:00
Barrie | 2019 | 453812 | 453812 (WO 319135) Pole Betterment. Tottenham. BATCH 2 (16 Poles) | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 289426.6 | 329392.05 | 39965.45 | 13.81% | 101724.49 | 43487.47 | -58237.02 | -57.25% | 48409.47 | 55519.57 | 7110.1 | 14.69% | 15488.24 | 0 | -15488.24 | -100% | 123804.4 | 230285.01 | 106480.61 | 86.01% | 706.78 | 44.5 | -662.28 | -93.7% | 2019-12-20 01:00
Barrie | 2020 | 453813 | 2020 POLE REPLACEMENT 4TH LINE AND CPP RAIL TOTTENHAM | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 90049.49 | 57320.2 | -32729.29 | -36.35% | 35981.86 | 19919.43 | -16062.43 | -44.64% | 22203.78 | 13004.49 | -9199.29 | -41.43% | 6829.45 | 8063.78 | 1234.33 | 18.07% | 25034.4 | 16332.5 | -8701.9 | -34.76% | 273.82 | 175 | -98.82 | -36.09% | 2020-11-23 01:00
Barrie | 2019 | 453834 | (WO319171) Padmount Transformer replacement with O/H Transformer ( ESA Driven) - #6 Cumberland – Bar | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 91312 | 58357.44 | -32954.56 | -36.09% | 17259 | 11156.51 | -6102.49 | -35.36% | 13351 | 16149.94 | 2798.94 | 20.96% | 5608 | 2318 | -3290 | -58.67% | 55094 | 28732.99 | -26361.01 | -47.85% | 208 | 157.45 | -50.55 | -24.3% | 2019-08-28 01:00
Barrie | 2020 | 453875 | 453875 (WO 319217) 430 HOLLAND STREET WEST | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Jeremy Wright | 39716.7502 | 28081.15 | -11635.6002 | -29.3% | 9464.1268 | 5035.51 | -4428.6168 | -46.79% | 22550.8295 | 16285.66 | -6265.1695 | -27.78% | 2239.9708 | 960.15 | -1279.8208 | -57.14% | 4893.384 | 2745.5 | -2147.884 | -43.89% | 130.5 | 103 | -27.5 | -21.07% | 2020-05-11
Barrie | 2020 | 453891 | 453891 (WO 319236) - 8 North Village Way, Barrie | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 104160.42 | 98686.93 | -5473.49 | -5.255% | 19487.9 | 17317.31 | -2170.59 | -11.14% | 28897.33 | 29025.81 | 128.48 | 0.4446% | 1845.39 | 2068.5 | 223.11 | 12.09% | 53929.8 | 44207.62 | -9722.18 | -18.03% | 199.65 | 121.5 | -78.15 | -39.14% | 2020-03-20 01:00
Barrie | 2020 | 453934 | 453934 (WO 319294) MILL ST, TOTTENHAM | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Lotto, Jay | 229000.83 | 221381.2 | -7619.63 | -3.327% | 22275.07 | 28832.08 | 6557.01 | 29.44% | 4160.81 | 3339.34 | -821.47 | -19.74% | 1905.27 | 889 | -1016.27 | -53.34% | 200659.68 | 184611 | -16048.68 | -7.998% | 197.41 | 149.5 | -47.91 | -24.27% | 2020-06-15 01:00
Barrie | 2020 | 453950 | 453950 (WO 319313) - Dunlop St: Eccles to Toronto | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Dan Kish | 128287.43 | 100576.21 | -27711.22 | -21.6% | 66765.1 | 44093.46 | -22671.64 | -33.96% | 33837.58 | 21072.58 | -12765 | -37.72% | 10618.53 | 15636.32 | 5017.79 | 47.26% | 17066.22 | 15070.97 | -1995.25 | -11.69% | 764.52 | 456 | -308.52 | -40.35% | 2020-02-10 01:00
Barrie | 2022 | 453951 | 453951 - BRADFORD EAST DEV. BLK170/INSPECT AND CONNECT | 99 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 140869.22 | 142065.25 | 1196.03 | 0.849% | 31820.6 | 21582.71 | -10237.89 | -32.17% | 665.32 | 0 | -665.32 | -100% | 1741.3 | 1129 | -612.3 | -35.16% | 106642 | 116788 | 10146 | 9.514% | 131.02 | 62 | -69.02 | -52.68% | 2022-09-26 01:00
Barrie | 2022 | 453956 | 453956 - RA RELOCATIONS - CHATHAM ST PENETANG | 99 | COMPLETE | Cont Est Over | N/A | N/A | Lacombe, Joel | No | Corriveau, Tom N | Dan Kish | 452770.53 | 408031.44 | -44739.09 | -9.881% | 69246.14 | 62254 | -6992.14 | -10.1% | 82820.69 | 79758.86 | -3061.83 | -3.697% | 1452 | 475 | -977 | -67.29% | 299251.7 | 265543.58 | -33708.12 | -11.26% | 128.75 | 41.5 | -87.25 | -67.77% | 2022-02-28 01:00
Barrie | 2019 | 453979 | 453979 (WO 319348 ) 185 Cundles Road East, Barrie | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 49324.36 | 37534.1 | -11790.26 | -23.9% | 11626.92 | 7926.24 | -3700.68 | -31.83% | 29748.81 | 27526.51 | -2222.3 | -7.47% | 1030.15 | 1104 | 73.85 | 7.169% | 6918.48 | 0 | -6918.48 | -100% | 68 | 58 | -10 | -14.71% | 2019-12-12 01:00
Barrie | 2022 | 453986 | (WO319355) 8 TRUMAN ROAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2023-01-09 01:00
Barrie | 2022 | 453988 | 453988 - 110 YOUNG ST/ALLR/NS/3PH PAD | 99 | ANALYZE |  |  |  | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 98383.68 | 85447.93 | -12935.75 | -13.15% | 27271.36 | 18049.98 | -9221.38 | -33.81% | 57214.44 | 53109.67 | -4104.77 | -7.174% | 3385.88 | 2405.5 | -980.38 | -28.95% | 10512 | 10661.06 | 149.06 | 1.418% | 144.48 | 127.5 | -16.98 | -11.75% | 2023-01-09 01:00
Barrie | 2020 | 453989 | 453989 (WO 319359) 75 MAPLEVIEW DRIVE - CHARG STN | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 81363.13 | 65285.4 | -16077.73 | -19.76% | 16261.19 | 14402.6 | -1858.59 | -11.43% | 40544.95 | 32046.93 | -8498.02 | -20.96% | 1208.47 | 1595.93 | 387.46 | 32.06% | 23348.52 | 15488.85 | -7859.67 | -33.66% | 133.45 | 70.5 | -62.95 | -47.17% | 2020-11-16 01:00
Barrie | 2020 | 453991 | 453991 (WO 319362) THOMPSONS RD W AT BELLISLE RD, PENETANGUISHENE | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Jeremy Wright | 646498.81 | 618008.29 | -28490.52 | -4.407% | 46845.91 | 48633.77 | 1787.86 | 3.816% | 20524.16 | 26653.75 | 6129.59 | 29.87% | 6741.7 | 4243.5 | -2498.2 | -37.06% | 572387.04 | 67.2 | -572319.84 | -99.99% | 1013.9 | 591.5 | -422.4 | -41.66% | 2020-08-12 01:00
Barrie | 2022 | 454009 | EMERGING POLE REPLACEMENT/6735 5TH LINE | 99 | COMPLETE | Engineering by-passed |  |  | Bowman, Todd J | Yes | Pollock, Kim | Persaud, Ryan | 96871.01 | 83004.91 | -13866.1 | -14.31% | 40251.89 | 36235.24 | -4016.65 | -9.979% | 34809.75 | 20518.7 | -14291.05 | -41.05% | 8609.37 | 13240.61 | 4631.24 | 53.79% | 13200 | 5238.75 | -7961.25 | -60.31% | 297.85 | 315.5 | 17.65 | 5.926% | 2019-12-04 01:00
Barrie | 2020 | 454070 | 454070 (WO 319457) 105 REAGANS INDUSTRIAL PARKWAY | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Alectra Utilities | Jeremy Wright | 77348.36 | 0 | -77348.36 | -100% | 15922.7 | 0 | -15922.7 | -100% | 48636.05 | 0 | -48636.05 | -100% | 1606.21 | 0 | -1606.21 | -100% | 11183.4 | 0 | -11183.4 | -100% | 100 | 27 | -73 | -73% | 2019-11-18 01:00
Barrie | 2019 | 454072 | 454072 (WO 319459) FRED GRANT SQUARE TX UPGRADE | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 36511.91 | 30209.43 | -6302.48 | -17.26% | 8148.94 | 1547.75 | -6601.19 | -81.01% | 26083.07 | 26194.8 | 111.73 | 0.4284% | 821.9 | 390 | -431.9 | -52.55% | 1458 | 0 | -1458 | -100% | 62 | 15 | -47 | -75.81% | 2019-11-18 01:00
Barrie | 2020 | 454091 | 454091 (WO 319482). Pole line rebuild . Extend 153M10 to Transfer MS322. Bradford PHASE 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | Yes | Alectra Utilities | Jeremy Wright | 1190447.54 | 775940.47 | -414507.07 | -34.82% | 112079.58 | 84906.42 | -27173.16 | -24.24% | 295729.12 | 265485.13 | -30243.99 | -10.23% | 10798.48 | 0 | -10798.48 | -100% | 771840.36 | 425548.92 | -346291.44 | -44.87% | 0 | 43 | 43 |  | 2020-11-23 01:00
Barrie | 2021 | 454095 | 454095 - Anne St & Hwy 400 Pole Relocations for Bridge | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Pelleja, Emily | No | Harrington, James | Jeremy Wright | 3067584.03 | 2524182.79 | -543401.24 | -17.71% | 1187331.99 | 696887.88 | -490444.11 | -41.31% | 830309.57 | 600368.61 | -229940.96 | -27.69% | 235673.61 | 226395.28 | -9278.33 | -3.937% | 814268.86 | 998942.88 | 184674.02 | 22.68% | 7618.4 | 6719.5 | -898.9 | -11.8% | 2021-12-14 01:00
Barrie | 2019 | 454130 | 454130 (WO 319523) 81 & 91 King Street, Barrie | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 20599.75 | 15441.19 | -5158.56 | -25.04% | 9939.23 | 5268.37 | -4670.86 | -46.99% | 2519.23 | 2478.15 | -41.08 | -1.631% | 1074.58 | 1284 | 209.42 | 19.49% | 7066.71 | 2603.25 | -4463.46 | -63.16% | 43.2 | 42.5 | -0.7 | -1.62% | 2019-12-19 01:00
Barrie | 2020 | 454159 | 454159 (WO 319554)–Rear Lot Remediate–E/O Queen St. to Eastern Ave N/O of Greeenway St–Tott | 99 | COMPLETE | Converted Project | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Persaud, Ryan | 2565896.88 | 0 | -2565896.88 | -100% | 180450.25 | 0 | -180450.25 | -100% | 18379.64 | 0 | -18379.64 | -100% | 32706.39 | 0 | -32706.39 | -100% | 2334360.6 | 0 | -2334360.6 | -100% | 2675.43 | 35.75 | -2639.68 | -98.66% | 2020-12-21 01:00
Barrie | 2019 | 454196 | 454196 (WO 319593) - 131 Big Bay Point Road, Barrie | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 59797.68 | 49555.48 | -10242.2 | -17.13% | 14343.85 | 9735.31 | -4608.54 | -32.13% | 25040.24 | 23424.59 | -1615.65 | -6.452% | 1508.19 | 1575 | 66.81 | 4.43% | 18905.4 | 13884.03 | -5021.37 | -26.56% | 143.5 | 65 | -78.5 | -54.7% | 2019-12-25 01:00
Barrie | 2022 | 454228 | (WO319628) 6251 13th Line | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Paterson, Greg | Persaud, Ryan | 0 | 366.52 | 366.52 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-11 01:00
Barrie | 2020 | 632335 | 632335 - 37,39,41 AUBURN CRT, INSPECT AND CONNECT | 99 | COMPLETE | Estimate incorrect | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Jeremy Wright | 11560.77 | 33774.95 | 22214.18 | 192.2% | 11116.57 | 8821.75 | -2294.82 | -20.64% | 13.2 | 0 | -13.2 | -100% | 431 | 72 | -359 | -83.29% | 0 | 0 | 0 |  | 67 | 72 | 5 | 7.463% | 2020-03-19 01:00
Barrie | 2019 | 632359 | 632359 - PCB TRANSFORMER REPLACEMENTS BARRIE BATCH 1 | 99 | COMPLETE | Labour est. over |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 96516.91 | 71131.61 | -25385.3 | -26.3% | 30821.65 | 11706.37 | -19115.28 | -62.02% | 42128.87 | 38560.95 | -3567.92 | -8.469% | 7366.39 | 3516 | -3850.39 | -52.27% | 16200 | 17348.29 | 1148.29 | 7.088% | 265.61 | 100.5 | -165.11 | -62.16% | 2019-12-07 01:00
Barrie | 2019 | 632360 | 632360 - PCB Transformer Batch 2 | 99 | COMPLETE | Scope change - unforeseen |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Jeremy Wright | 191354.56 | 93851.19 | -97503.37 | -50.95% | 39322.8 | 18095.7 | -21227.1 | -53.98% | 118690.86 | 48929.32 | -69761.54 | -58.78% | 6340.9 | 2239 | -4101.9 | -64.69% | 27000 | 24587.17 | -2412.83 | -8.936% | 344.37 | 195 | -149.37 | -43.37% | 2019-12-10 01:00
Barrie | 2022 | 632362 | 17 CENTRE STREET RELOCATION | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | Yes | Pollock, Kim | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-03 01:00
Barrie | 2020 | 632727 | 632727 - JOINT USE PERMIT #HE2019-074 - FAIRVIEW ROAD - BARRIE | 99 | COMPLETE | Legal Fees | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Dan Kish | 11396.13 | 9791.25 | -1604.88 | -14.08% | 2441.64 | 1990.36 | -451.28 | -18.48% | 1019.34 | 830.89 | -188.45 | -18.49% | 157.8 | 195 | 37.2 | 23.57% | 7777.35 | 6775 | -1002.35 | -12.89% | 10.72 | 10 | -0.72 | -6.716% | 2020-09-03 01:00
Barrie | 2020 | 632827 | 632827 - 100 MILL ST E | 99 | COMPLETE | Cont Est Over | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 79007.59 | 64716.6 | -14290.99 | -18.09% | 13587.78 | 12535.49 | -1052.29 | -7.744% | 31914.64 | 29746.11 | -2168.53 | -6.795% | 1734.81 | 1398 | -336.81 | -19.41% | 31770.36 | 21037 | -10733.36 | -33.78% | 168.04 | 97 | -71.04 | -42.28% | 2020-04-17 01:00
Barrie | 2021 | 632843 | 632843 - 2021 Distribution Automation - DUCKWORTH & CUNDLES 44KV AUTOMATED LIS TIE SWITCH | 99 | COMPLETE | BOM cost variance | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 102794.32 | 175634.04 | 72839.72 | 70.86% | 44309.19 | 13645.78 | -30663.41 | -69.2% | 22943.93 | 95248.99 | 72305.06 | 315.1% | 10701.2 | 0 | -10701.2 | -100% | 24840 | 66739.27 | 41899.27 | 168.7% | 381.9 | 20 | -361.9 | -94.76% | 2021-10-15 01:00
Barrie | 2021 | 632864 | RELOCATION DESIGN FOR FUTURE DEVELOPMENT | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Pollock, Kim | Wong, Henry | 6949.22 | 701.82 | -6247.4 | -89.9% | 2949.22 | 701.82 | -2247.4 | -76.2% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4000 | 0 | -4000 | -100% | 0 | 0 | 0 |  | 2020-09-25 01:00
Barrie | 2020 | 632929 | JOINT USE PERMIT #HE2019-089 - MULCASTER STREET & PENETANG STREET - BARRIE | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Aulis, John -x | 9664.34 | 6791.2 | -2873.14 | -29.73% | 4619.09 | 1511.19 | -3107.9 | -67.28% | 1346.57 | 349.06 | -997.51 | -74.08% | 394.68 | 280.49 | -114.19 | -28.93% | 3304 | 4650.46 | 1346.46 | 40.75% | 28.32 | 10 | -18.32 | -64.69% | 2020-02-05 01:00
Barrie | 2019 | 633023 | 633023 - 141 & 151 KING ST, BARRIE - NEW 3 PHASE SERVICE | 99 | COMPLETE | Labour est. over |  |  | Cranley, Stephen | No | Harris, Geoff L. | Jeremy Wright | 50248.74 | 36458.86 | -13789.88 | -27.44% | 13800.7 | 7371.08 | -6429.62 | -46.59% | 24504.79 | 23673.78 | -831.01 | -3.391% | 1496.41 | 670 | -826.41 | -55.23% | 10446.84 | 4744 | -5702.84 | -54.59% | 80 | 74 | -6 | -7.5% | 2019-12-20 01:00
Barrie | 2021 | 633058 | 633058 - GO VILLAGE PH2 / INSPECT & CONNECT | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 671157.7 | 641730.06 | -29427.64 | -4.385% | 51338.49 | 75469.25 | 24130.76 | 47% | 10128.53 | 8911.31 | -1217.22 | -12.02% | 5881.04 | 3266.5 | -2614.54 | -44.46% | 603809.64 | 554083 | -49726.64 | -8.235% | 382.98 | 219.5 | -163.48 | -42.69% | 2021-10-01 01:00
Barrie | 2022 | 633199 | 633199 - 111 BRADFORD ST | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 77246.58 | 63291.82 | -13954.76 | -18.07% | 24947.9 | 20191.28 | -4756.62 | -19.07% | 32179.44 | 30729.99 | -1449.45 | -4.504% | 3285.82 | 4946.95 | 1661.13 | 50.55% | 16833.42 | 7423.6 | -9409.82 | -55.9% | 142.27 | 142.5 | 0.23 | 0.1617% | 2022-01-31 01:00
Barrie | 2020 | 633201 | ICI SERVICE REMOVAL/150 & 152 DUNLOP ST W | 99 | COMPLETE | Engineering by-passed |  |  | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 0 | 9917.15 | 9917.15 |  | 0 | 4187.15 | 4187.15 |  | 0 | 0 | 0 |  | 0 | 960 | 960 |  | 0 | 4770 | 4770 |  | 0 | 26 | 26 |  | 2020-08-21 01:00
Barrie | 2019 | 633214 | 633214 - JOINT USE PERMIT #HE2019-091 - CONDRINGTON STREET - BARRIE | 99 | COMPLETE | Engineering by-passed |  |  | O'Gay, Brian | No | Martin, Shane | Aulis, John -x | 5538.74 | 3772.65 | -1766.09 | -31.89% | 2172.33 | 800.06 | -1372.27 | -63.17% | 285.29 | 0 | -285.29 | -100% | 57.12 | 56.1 | -1.02 | -1.786% | 3024 | 2916.49 | -107.51 | -3.555% | 2.04 | 2 | -0.04 | -1.961% | 2019-11-21 01:00
Barrie | 2020 | 633320 | 633320 - 2020 SWGR REPLACEMENTS - SC13305 - 53 WHITEHORN CRES - KABAR | 99 | COMPLETE | Labour est. over | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 6204.5 | 5363.47 | -841.03 | -13.56% | 3023.11 | 2656.13 | -366.98 | -12.14% | 2779.5 | 2339.1 | -440.4 | -15.84% | 401.89 | 368.24 | -33.65 | -8.373% | 0 | 0 | 0 |  | 36.3 | 20 | -16.3 | -44.9% | 2020-06-08 01:00
Barrie | 2020 | 633321 | 633321 - 2020 SWGR REPLACEMENTS - SC13526 - 39 BUTTERNUT DR. - KABAR | 99 | COMPLETE | BOM not accurate | Labour est. over | N/A | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 6204.5 | 8100.14 | 1895.64 | 30.55% | 3023.11 | 2585.83 | -437.28 | -14.46% | 2779.5 | 5146.07 | 2366.57 | 85.14% | 401.89 | 368.24 | -33.65 | -8.373% | 0 | 0 | 0 |  | 36.3 | 20 | -16.3 | -44.9% | 2020-06-09 01:00
Barrie | 2020 | 633322 | 633322 - 2020 SWGR REPLACEMENTS - SC13527 - 10 DYKSTRA DR - KABAR | 99 | COMPLETE | BOM not accurate | Labour est. over | N/A | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 6204.5 | 4842.07 | -1362.43 | -21.96% | 3023.11 | 2134.73 | -888.38 | -29.39% | 2779.5 | 2339.1 | -440.4 | -15.84% | 401.89 | 368.24 | -33.65 | -8.373% | 0 | 0 | 0 |  | 36.3 | 20 | -16.3 | -44.9% | 2020-06-10 01:00
Barrie | 2020 | 633323 | 633323 - 2020 SWGR REPLACEMENTS - SC13267 - 16 CHALMERS DR - KABAR | 99 | COMPLETE | Under 10% |  |  | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 5881.2 | 6055.12 | 173.92 | 2.957% | 2998.2 | 2391.58 | -606.62 | -20.23% | 2300 | 3053.65 | 753.65 | 32.77% | 583 | 609.89 | 26.89 | 4.612% | 0 | 0 | 0 |  | 41 | 20 | -21 | -51.22% | 2020-06-18 01:00
Barrie | 2020 | 633324 | 633324 - 2020 SWGR REPLACEMENTS - SC13649 - 141 MADELAINE DR - PMH-9 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 26639 | 26287.9 | -351.1 | -1.318% | 5162 | 3883.38 | -1278.62 | -24.77% | 20742 | 21075.42 | 333.42 | 1.607% | 735 | 1329.1 | 594.1 | 80.83% | 0 | 0 | 0 |  | 35 | 36 | 1 | 2.857% | 2020-09-01 01:00
Barrie | 2020 | 633325 | 633325 - 2020 SWGR REPLACEMENTS - SC13501 - 116 HOLLY MEADOW RD - PMH-3 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 13014.47 | 12619.1 | -395.37 | -3.038% | 2998.2 | 2167.4 | -830.8 | -27.71% | 9433.27 | 9543.34 | 110.07 | 1.167% | 583 | 908.36 | 325.36 | 55.81% | 0 | 0 | 0 |  | 41 | 25 | -16 | -39.02% | 2020-08-25 01:00
Barrie | 2020 | 633492 | 633492 - 2020 POLE REPLACEMENTS BATCH 1 | 99 | COMPLETE | Labour est. under | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 133472.62 | 151875.93 | 18403.31 | 13.79% | 56723.2 | 69384.49 | 12661.29 | 22.32% | 42724.4 | 44813.76 | 2089.36 | 4.89% | 11691.7 | 27307.68 | 15615.98 | 133.6% | 22333.32 | 10370 | -11963.32 | -53.57% | 897.36 | 808 | -89.36 | -9.958% | 2020-07-07 01:00
Barrie | 2022 | 633502 | (WO 633502) SECONDARY ALLEY JUMPER REMOVAL AT 65 JOHN ST. - BRADFORD | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-11 01:00
Barrie | 2020 | 633612 | 633612 - 2020 POLE REPLACEMENTS BATCH 2 | 99 | COMPLETE | BOM not accurate | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Jeremy Wright | 266013.93 | 289337.06 | 23323.13 | 8.768% | 118511.03 | 117112.48 | -1398.55 | -1.18% | 74389.76 | 72279.68 | -2110.08 | -2.837% | 24785.3 | 60751.67 | 35966.37 | 145.1% | 48327.84 | 39193.23 | -9134.61 | -18.9% | 1849.05 | 1301 | -548.05 | -29.64% | 2020-10-07 01:00
Barrie | 2020 | 633657 | BIG BAY POINT ROAD ANCHOR LOCATIONS | 99 | COMPLETE | Engineering by-passed |  |  | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 11960.87 | 14284.91 | 2324.04 | 19.43% | 4342.46 | 3934.14 | -408.32 | -9.403% | 1989.57 | 1199.51 | -790.06 | -39.71% | 684.6 | 1757.01 | 1072.41 | 156.6% | 4944.24 | 7394.25 | 2450.01 | 49.55% | 40.92 | 34 | -6.92 | -16.91% | 2020-11-24 01:00
Barrie | 2022 | 633682 | PADMOUNT NORTH BATCH 1 - BARRIE | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-15 01:00
Barrie | 2020 | 633707 | 633707 - 681 YONGE STREET - RELOCATE POLES FOR PROPOSED DEVELOPMENT | 99 | COMPLETE | Cont Est Over | N/A | N/A | Pelleja, Emily | No | Alectra Utilities | Jeremy Wright | 987396.47 | 729215.97 | -258180.5 | -26.15% | 32326.97 | 67219.6 | 34892.63 | 107.9% | 198592.16 | 181316.34 | -17275.82 | -8.699% | 2761.44 | 1270 | -1491.44 | -54.01% | 753715.9 | 479410.03 | -274305.87 | -36.39% | 246.07 | 157.5 | -88.57 | -35.99% | 2020-09-19 01:00
Barrie | 2020 | 633807 | 633807 - 2020 TRANSFORMER RENEWAL - EAST - BARRIE BATCH 1 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 115936.38 | 82027.96 | -33908.42 | -29.25% | 23315.08 | 12997.25 | -10317.83 | -44.25% | 54468.38 | 47851.38 | -6617 | -12.15% | 5030.4 | 4722.33 | -308.07 | -6.124% | 33122.52 | 16457 | -16665.52 | -50.31% | 440.9 | 136 | -304.9 | -69.15% | 2020-08-07 01:00
Barrie | 2020 | 633810 | 633810 - 2020 TRANSFORMER RENEWAL - EAST - BARRIE BATCH 2 | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 169874.81 | 149992.52 | -19882.29 | -11.7% | 32738.63 | 19704.26 | -13034.37 | -39.81% | 76858.18 | 70686.84 | -6171.34 | -8.03% | 7282.4 | 7127.37 | -155.03 | -2.129% | 52995.6 | 52474.05 | -521.55 | -0.9841% | 623.4 | 173 | -450.4 | -72.25% | 2020-11-16 01:00
Barrie | 2020 | 633811 | 633811 - 2020 TRANSFORMER RENEWAL - EAST - BARRIE BATCH 3 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Lotto, Jay | 358557.79 | 302765.42 | -55792.37 | -15.56% | 47585.33 | 41517.18 | -6068.15 | -12.75% | 181812.08 | 191173.69 | 9361.61 | 5.149% | 9637.86 | 9915.75 | 277.89 | 2.883% | 119522.52 | 60158.8 | -59363.72 | -49.67% | 642.75 | 360.5 | -282.25 | -43.91% | 2020-12-03 01:00
Barrie | 2021 | 633851 | 633851 - 681 YONGE ST, BARRIE - NEW 3 PHASE SERVICE | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 94250.77 | 75690.34 | -18560.43 | -19.69% | 24456.49 | 17748.04 | -6708.45 | -27.43% | 48051.97 | 35621.33 | -12430.64 | -25.87% | 3124.19 | 3036.19 | -88 | -2.817% | 18618.12 | 19284.78 | 666.66 | 3.581% | 294.5 | 102 | -192.5 | -65.37% | 2021-03-05 01:00
Barrie | 2020 | 633881 | 633881 - ICI PADMOUNT TX INSTALLATION/102 KING ST | 99 | COMPLETE | Cont Est Over | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 52933.27 | 46216.73 | -6716.54 | -12.69% | 14163.77 | 13249.86 | -913.91 | -6.452% | 20496.01 | 19197.97 | -1298.04 | -6.333% | 1826.17 | 1960 | 133.83 | 7.328% | 16447.32 | 11808.9 | -4638.42 | -28.2% | 172.03 | 86 | -86.03 | -50.01% | 2020-06-03 01:00
Barrie | 2021 | 633889 | 633889 - 2021 DISTRIBUTION AUTOMATION - EAST - BRADFORD - LT-B1055 - 2620 8TH LINE, 1 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 218547.68 | 186922.13 | -31625.55 | -14.47% | 74322.07 | 10661.08 | -63660.99 | -85.66% | 94262.03 | 99159.5 | 4897.47 | 5.196% | 18129.5 | 16 | -18113.5 | -99.91% | 31834.08 | 77085.55 | 45251.47 | 142.1% | 646.85 | 18.5 | -628.35 | -97.14% | 2021-05-28 01:00
Barrie | 2021 | 633890 | 633890 - 2021 Vault Lid Renewal - V16 - 42 Maple Ave. | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 137860 | 72976.44 | -64883.56 | -47.06% | 32835 | 15403.02 | -17431.98 | -53.09% | 3848 | 4237.12 | 389.12 | 10.11% | 2996 | 391.25 | -2604.75 | -86.94% | 98181 | 52945.05 | -45235.95 | -46.07% | 421 | 22 | -399 | -94.77% | 2021-10-19 01:00
Barrie | 2021 | 633891 | 633891 - 2021 DISTRIBUTION AUTOMATION - EAST - BARRIE - LT-B40704 - BROCK ST | 99 | COMPLETE | BOM cost variance | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 137161.58 | 196979.73 | 59818.15 | 43.61% | 64897.63 | 52622.12 | -12275.51 | -18.92% | 45117.95 | 115333.43 | 70215.48 | 155.6% | 13106 | 14359.76 | 1253.76 | 9.566% | 14040 | 14664.42 | 624.42 | 4.447% | 480.32 | 407 | -73.32 | -15.26% | 2021-11-05 01:00
Barrie | 2020 | 633892 | 633892 - 2020 DISTRIBUTION AUTOMATION - EAST - BARRIE - LT-B10043 - 250 ANNE ST. N | 99 | COMPLETE | Labour est. over | N/A | N/A | Bowman, Todd J | yes | Alectra Utilities | Dan Kish | 236983.6 | 162964.19 | -74019.41 | -31.23% | 83936.37 | 33434.94 | -50501.43 | -60.17% | 103610.18 | 97448.67 | -6161.51 | -5.947% | 20419.61 | 16977.67 | -3441.94 | -16.86% | 29017.44 | 15102.91 | -13914.53 | -47.95% | 734.97 | 377.5 | -357.47 | -48.64% | 2020-12-21 01:00
Barrie | 2020 | 633893 | 633893 - 2020 DISTRIBUTION AUTOMATION - EAST - BARRIE - LT-B35858 - 243 SAUNDERS RD. | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Alectra Utilities | Dan Kish | 104360.81 | 108127.46 | 3766.65 | 3.609% | 24247.94 | 7788.44 | -16459.5 | -67.88% | 68073.51 | 69349.71 | 1276.2 | 1.875% | 5460 | 0 | -5460 | -100% | 6579.36 | 30989.31 | 24409.95 | 371% | 405.05 | 38.5 | -366.55 | -90.5% | 2020-12-24 01:00
Barrie | 2020 | 633896 | 633896 - 2020 SWITCH RENEWAL - EAST - BARRIE - 140 CUNDLES RD.W | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 218097.12 | 166634.16 | -51462.96 | -23.6% | 75630.2 | 13857.52 | -61772.68 | -81.68% | 99957.49 | 98625.63 | -1331.86 | -1.332% | 17902.71 | 0 | -17902.71 | -100% | 24606.72 | 54151.01 | 29544.29 | 120.1% | 651.67 | 55 | -596.67 | -91.56% | 2020-12-21 01:00
Barrie | 2020 | 633897 | 633897 - 2020 SWITCH RENEWAL - EAST - BARRIE - 124 VESPRA ST. | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 190718.68 | 188385.99 | -2332.69 | -1.223% | 52098.44 | 12090.64 | -40007.8 | -76.79% | 111984.92 | 108685.68 | -3299.24 | -2.946% | 11307.96 | 0 | -11307.96 | -100% | 15327.36 | 67609.67 | 52282.31 | 341.1% | 832.29 | 26 | -806.29 | -96.88% | 2020-12-21 01:00
Barrie | 2020 | 634070 | 634070 - 2020 SUNNIDALE UG CABLE REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Alectra Utilities | Lotto, Jay | 1081715.7 | 1190366.48 | 108650.78 | 10.04% | 47016.73 | 163140.3 | 116123.57 | 247% | 12013.42 | 19569.62 | 7556.2 | 62.9% | 7386.19 | 7333.07 | -53.12 | -0.7192% | 1015299.36 | 1000323.49 | -14975.87 | -1.475% | 694.72 | 484 | -210.72 | -30.33% | 2020-11-17 01:00
Barrie | 2020 | 634166 | 634166 - HURST DRVE RELOCATE POLES AND ANCHORS FOR ROAD WIDENING | 99 | COMPLETE | Cont Est Over | N/A | N/A | Pelleja, Emily | No | Alectra Utilities | Jeremy Wright | 249183.34 | 160322.76 | -88860.58 | -35.66% | 22549.6 | 23713.8 | 1164.2 | 5.163% | 39586.95 | 30816.08 | -8770.87 | -22.16% | 306.26 | 103.57 | -202.69 | -66.18% | 186740.53 | 105689.31 | -81051.22 | -43.4% | 84.6 | 0 | -84.6 | -100% | 2020-07-25 01:00
Barrie | 2021 | 634430 | 634430 - ICI PADMOUNT TX INSTALLATION/400 CROSSLAND BLVD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 27754.22 | 49375.5 | 21621.28 | 77.9% | 16765.59 | 18589.9 | 1824.31 | 10.88% | 28703.41 | 22171.4 | -6532.01 | -22.76% | 1490.26 | 2542 | 1051.74 | 70.57% | 3144.96 | 6072.2 | 2927.24 | 93.08% | 89.28 | 142.5 | 53.22 | 59.61% | 2021-11-18 01:00
Barrie | 2021 | 634431 | 634431 - ICI PADMOUNT TX INSTALLATION/100 MILL ST E | 99 | COMPLETE | Labour est. under | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 48556.2 | 53670.54 | 5114.34 | 10.53% | 8950.15 | 16958.26 | 8008.11 | 89.47% | 30526.61 | 27382 | -3144.61 | -10.3% | 726.72 | 2573.28 | 1846.56 | 254.1% | 8352.72 | 6757 | -1595.72 | -19.1% | 84.7 | 166 | 81.3 | 95.99% | 2021-11-15 01:00
Barrie | 2020 | 634536 | 634536 - HE2019-112, BIG BAY POINT RD | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | O'Gay, Brian | No | Alectra Utilities | Aulis, John -x | 8056.89 | 5197.04 | -2859.85 | -35.5% | 2437.09 | 1620.92 | -816.17 | -33.49% | 370.85 | 137.72 | -233.13 | -62.86% | 106.8 | 288.4 | 181.6 | 170% | 5142.15 | 3150 | -1992.15 | -38.74% | 9.73 | 9 | -0.73 | -7.503% | 2020-09-30 01:00
Barrie | 2022 | 634810 | 634810 - 25 ALBERT ST W/ALL/NS/3PH PAD | 99 | ANALYZE |  |  |  | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 76525.31 | 61073.31 | -15452 | -20.19% | 21064.58 | 8930.64 | -12133.94 | -57.6% | 43125.24 | 39838.17 | -3287.07 | -7.622% | 2394.49 | 1372.5 | -1021.99 | -42.68% | 9941 | 10932 | 991 | 9.969% | 128.01 | 44 | -84.01 | -65.63% | 2022-05-30 01:00
Barrie | 2021 | 634877 | 634877 - 342 KING ST, BARRIE - COMMERCIAL BUILDINGS | 99 | COMPLETE | BOM not accurate | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 87380.98 | 54581.87 | -32799.11 | -37.54% | 19254.93 | 16879.47 | -2375.46 | -12.34% | 60965.8 | 31094.82 | -29870.98 | -49% | 1977.33 | 1809 | -168.33 | -8.513% | 5182.92 | 4798.58 | -384.34 | -7.416% | 104.74 | 89 | -15.74 | -15.03% | 2021-12-17 01:00
Barrie | 2022 | 634895 | 634895 - 185 DUNLOP ST E, BARRIE - CONDO DEVELOPMENT | 95 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 276776.36 | 163548.09 | -113228.27 | -40.91% | 117510.23 | 60241.78 | -57268.45 | -48.73% | 105872.18 | 64734.98 | -41137.2 | -38.86% | 22942.83 | 13852.5 | -9090.33 | -39.62% | 30451.12 | 24718.83 | -5732.29 | -18.82% | 663.2 | 449 | -214.2 | -32.3% | 2022-10-25 01:00
Barrie | 2020 | 634926 | 634926 - BRADFORD STREET/HIGH STREET - RELOCATE POLES FOR ROAD WORKS | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Pelleja, Emily | No | Alectra Utilities | Dan Kish | 165671.03 | 188631.26 | 22960.23 | 13.86% | 74313.81 | 37162.1 | -37151.71 | -49.99% | 49674.13 | 47959.57 | -1714.56 | -3.452% | 13085.42 | 8607.51 | -4477.91 | -34.22% | 28597.67 | 94902.08 | 66304.41 | 231.9% | 919.1 | 225 | -694.1 | -75.52% | 2020-06-04 01:00
Barrie | 2021 | 634993 | 634993 - DISSETTE STREET, BRADFORD - RELOCATE POLES FOR NEW DEVELOPMENT | 99 | COMPLETE | Cont Est Over | N/A | N/A | Pelleja, Emily | No | Harrington, James | Dan Kish | 296929.42 | 231962.19 | -64967.23 | -21.88% | 27949.02 | 34042.18 | 6093.16 | 21.8% | 50633.13 | 41243.84 | -9389.29 | -18.54% | 0 | 0 | 0 |  | 218347.27 | 156676.17 | -61671.1 | -28.24% | 12 | 21 | 9 | 75% | 2021-05-15
Barrie | 2021 | 635021 | 635021 - 759 YONGE ST, BARRIE - PAINSWICK PARK | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 20948.97 | 15424.84 | -5524.13 | -26.37% | 14722.83 | 8663.07 | -6059.76 | -41.16% | 7139.14 | 6634.77 | -504.37 | -7.065% | 1087 | 127 | -960 | -88.32% | 0 | 0 | 0 |  | 54.41 | 3 | -51.41 | -94.49% | 2021-10-01 01:00
Barrie | 2020 | 635046 | 635046 - 2020 POLE REPLACEMENTS BATCH 3 | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 144345.43 | 210666.92 | 66321.49 | 45.95% | 59545.71 | 76202.28 | 16656.57 | 27.97% | 42951.34 | 66239.25 | 23287.91 | 54.22% | 11006.28 | 35536.89 | 24530.61 | 222.9% | 30842.1 | 32688.5 | 1846.4 | 5.987% | 890.53 | 810 | -80.53 | -9.043% | 2020-09-17 01:00
Barrie | 2020 | 635047 | 635047 - 2020 POLE REPLACEMENTS BATCH 4 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 264247.28 | 177807.5 | -86439.78 | -32.71% | 140791.36 | 68196.99 | -72594.37 | -51.56% | 54427.66 | 54644.41 | 216.75 | 0.3982% | 23668.26 | 30883.6 | 7215.34 | 30.49% | 45360 | 24082.5 | -21277.5 | -46.91% | 1880.96 | 707.5 | -1173.46 | -62.39% | 2020-10-02 01:00
Barrie | 2020 | 635048 | 635048 - 2020 POLE REPLACEMENTS BATCH 5 | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 294097.87 | 233286.78 | -60811.09 | -20.68% | 133436.83 | 98422.72 | -35014.11 | -26.24% | 58258.66 | 65585.31 | 7326.65 | 12.58% | 24210.38 | 38982.62 | 14772.24 | 61.02% | 78192 | 30296.13 | -47895.87 | -61.25% | 1957.45 | 890 | -1067.45 | -54.53% | 2020-12-03 01:00
Barrie | 2021 | 635176 | 635176 - 131 ELLIS DRIVE, BARRIE - 3 PHASE SERVICE | 99 | COMPLETE | Under 10% | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 64252.21 | 61761.48 | -2490.73 | -3.876% | 25121.53 | 15537.78 | -9583.75 | -38.15% | 41615.33 | 33334.84 | -8280.49 | -19.9% | 3372.67 | 2288 | -1084.67 | -32.16% | 16492.68 | 10600.86 | -5891.82 | -35.72% | 159.7 | 114.5 | -45.2 | -28.3% | 2021-10-06 01:00
Barrie | 2020 | 635346 | 635346 - 30 HANMER ST WEST, BARRIE - 3 PHASE SERVICE | 99 | COMPLETE | Labour est. over | Cont Est Over | BOM not accurate | Cranley, Stephen | No | Alectra Utilities | Jeremy Wright | 47230.58 | 34281.01 | -12949.57 | -27.42% | 11723.76 | 8139.94 | -3583.82 | -30.57% | 23660.84 | 19517.1 | -4143.74 | -17.51% | 733.86 | 1226.97 | 493.11 | 67.19% | 11112.12 | 5397 | -5715.12 | -51.43% | 96.25 | 48 | -48.25 | -50.13% | 2020-07-17 01:00
Barrie | 2020 | 635617 | 635617 - ICI CUSTOMER OWNED TRANSFORMER/25 REAGENS INDUSTRIAL PARKWAY | 99 | COMPLETE | Cont Est Over | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 40963.25 | 33743.5 | -7219.75 | -17.62% | 17221.36 | 18761.8 | 1540.44 | 8.945% | 8929.09 | 4494.11 | -4434.98 | -49.67% | 2102.28 | 3746 | 1643.72 | 78.19% | 12710.52 | 6741.59 | -5968.93 | -46.96% | 204.06 | 139 | -65.06 | -31.88% | 2020-05-14
Barrie | 2020 | 635692 | 5 PATTERSON RD, BEETON - TIM HORTONS | 99 | COMPLETE | Under 10% | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 48436.46 | 44434.47 | -4001.99 | -8.262% | 15695.54 | 15470.05 | -225.49 | -1.437% | 25853.91 | 23223.12 | -2630.79 | -10.18% | 2075.61 | 2330.24 | 254.63 | 12.27% | 4811.4 | 3411.06 | -1400.34 | -29.1% | 176.2 | 107 | -69.2 | -39.27% | 2020-04-22
Barrie | 2021 | 635720 | 635720 - 58 LAKESIDE TERRACE, BARRIE - TOWER A | 99 | COMPLETE | BOM not accurate | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 101800.61 | 90824.34 | -10976.27 | -10.78% | 18420.11 | 18487.56 | 67.45 | 0.3662% | 74083.49 | 60371.78 | -13711.71 | -18.51% | 1854.73 | 2139.5 | 284.77 | 15.35% | 7442.28 | 9825.5 | 2383.22 | 32.02% | 188.28 | 117 | -71.28 | -37.86% | 2021-08-04 01:00
Barrie | 2020 | 636086 | 636086 - 2020 44KV INSULATOR REPLACEMENT PROGRAM | 99 | COMPLETE | Est. Int. - Act. External | BOM not accurate | N/A | Bowman, Todd J | No | Alectra Utilities | Jeremy Wright | 3665.02 | 172094.75 | 168429.73 | 4596% | 2387.02 | 12352.92 | 9965.9 | 417.5% | 0 | 26289.68 | 26289.68 |  | 90 | 0 | -90 | -100% | 1188 | 133452.15 | 132264.15 | 11133% | 1531.35 | 5.5 | -1525.85 | -99.64% | 2020-11-23 01:00
Barrie | 2021 | 636088 | 636088 - 2021 VAULT REPLACEMENTS V25 - MULCASTER | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 154214.64 | 94729.68 | -59484.96 | -38.57% | 44640.3 | 29740.37 | -14899.93 | -33.38% | 7974.34 | 4589.95 | -3384.39 | -42.44% | 2996 | 5175.27 | 2179.27 | 72.74% | 98604 | 55224.09 | -43379.91 | -43.99% | 240 | 211 | -29 | -12.08% | 2021-12-09 01:00
Barrie | 2021 | 636103 | 636103 - JOINT USE PERMIT #HE2020-014, PENETANGUSHENE ROAD, BARRIE | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 6255.51 | 4521.63 | -1733.88 | -27.72% | 2490.31 | 1281.63 | -1208.68 | -48.54% | 251.6 | 0 | -251.6 | -100% | 111.6 | 90 | -21.6 | -19.35% | 3402 | 3150 | -252 | -7.407% | 7.2 | 4 | -3.2 | -44.44% | 2021-04-20
Barrie | 2020 | 636170 | 636170 - BAYVIEW DR 2020 STORM HARDENING 4CCT POLELINE | 99 | COMPLETE | Labour est. under | Cont Est Under | N/A | Bowman, Todd J | Yes | Alectra Utilities | Jeremy Wright | 441653.69 | 496043.99 | 54390.3 | 12.32% | 127340.66 | 141959.63 | 14618.97 | 11.48% | 196307.34 | 159013.41 | -37293.93 | -19% | 25166.19 | 66384.52 | 41218.33 | 163.8% | 92839.5 | 128686.43 | 35846.93 | 38.61% | 1786.29 | 1423 | -363.29 | -20.34% | 2020-12-18 01:00
Barrie | 2020 | 636233 | 636233 - BELL BOND - BIG BAY POINT ROAD, BARRIE | 99 | COMPLETE | Engineering by-passed |  |  | O'Gay, Brian | No | Alectra Utilities | Aulis, John -x | 0 | 1547.58 | 1547.58 |  | 0 | 1240.48 | 1240.48 |  | 0 | 0 | 0 |  | 0 | 307.1 | 307.1 |  | 0 | 0 | 0 |  | 4 | 11 | 7 | 175% | 2020-05-22
Barrie | 2021 | 636558 | 636558 - 2021 SUNNIDALE UG CABLE REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Lotto, Jay | 1898516.03 | 1932214.3 | 33698.27 | 1.775% | 35973 | 346209.91 | 310236.91 | 862.4% | 15073.53 | 42953.05 | 27879.52 | 185% | 6717.5 | 25982.22 | 19264.72 | 286.8% | 1840752 | 1517069.12 | -323682.88 | -17.58% | 346.4 | 988 | 641.6 | 185.2% | 2021-10-19 01:00
Barrie | 2021 | 636575 | 636575 - ICI PADMOUNT TX INSTALLATION/2 KING ST S | 99 | COMPLETE | Under 10% | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 45072.6 | 41667 | -3405.6 | -7.556% | 16503.87 | 12310.98 | -4192.89 | -25.41% | 23999.74 | 22640.79 | -1358.95 | -5.662% | 1549.31 | 1369.68 | -179.63 | -11.59% | 3019.68 | 5345.55 | 2325.87 | 77.02% | 83.85 | 47 | -36.85 | -43.95% | 2021-02-19 01:00
Barrie | 2020 | 636643 | 636643 - JOINT USE HE2020-029- BRADFORD ST. & HIGH ST. | 99 | COMPLETE | Legal Fees |  |  | O'Gay, Brian | No | Alectra Utilities | Aulis, John -x | 5563.47 | 4491.18 | -1072.29 | -19.27% | 1275.27 | 1186.58 | -88.69 | -6.955% | 251.6 | 42.4 | -209.2 | -83.15% | 86.6 | 112.2 | 25.6 | 29.56% | 3950 | 3150 | -800 | -20.25% | 7.4 | 4 | -3.4 | -45.95% | 2020-06-09 01:00
Barrie | 2020 | 636703 | 636703 - BAY MOORINGS - PERMANENT SERVICE REMOVAL | 99 | COMPLETE | Labour est. over | N/A | N/A | Penner, Mitchell | No | Alectra Utilities | Lotto, Jay | 4113.72 | 3141.31 | -972.41 | -23.64% | 3787.24 | 2613.31 | -1173.93 | -31% | 0 | 0 | 0 |  | 326.48 | 528 | 201.52 | 61.73% | 0 | 0 | 0 |  | 24.35 | 11 | -13.35 | -54.83% | 2020-07-09 01:00
Barrie | 2021 | 636780 | 636780 - 2021 DUNLOP BARRIE UG CABLE REPLACEMENT | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 797484.5 | 1078858.17 | 281373.67 | 35.28% | 111026.53 | 166446.74 | 55420.21 | 49.92% | 71123.31 | 85102.88 | 13979.57 | 19.66% | 25322.02 | 5170.47 | -20151.55 | -79.58% | 590012.64 | 822138.08 | 232125.44 | 39.34% | 895.74 | 225.5 | -670.24 | -74.83% | 2021-12-05 01:00
Barrie | 2021 | 636801 | 636801 - 2021 VAULT LID RENEWAL PROGRAM - V18 - 145 DUNLOP ST E | 99 | COMPLETE | Cont Est Over | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Lotto, Jay | 164770.16 | 164093.61 | -676.55 | -0.4106% | 29354.13 | 38442.95 | 9088.82 | 30.96% | 17258.43 | 19234.69 | 1976.26 | 11.45% | 6896 | 4367.33 | -2528.67 | -36.67% | 111261.6 | 102048.64 | -9212.96 | -8.28% | 275 | 199 | -76 | -27.64% | 2021-09-23 01:00
Barrie | 2021 | 636802 | 636802 - 2021 VAULT LID RENEWAL PROGRAM - V13 - 49 HIGH ST | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Lotto, Jay | 152462.13 | 172754.08 | 20291.95 | 13.31% | 41216.91 | 34614.31 | -6602.6 | -16.02% | 7467.22 | 3005.88 | -4461.34 | -59.75% | 6896 | 2052.98 | -4843.02 | -70.23% | 96882 | 133080.91 | 36198.91 | 37.36% | 240 | 77.5 | -162.5 | -67.71% | 2021-10-22 01:00
Barrie | 2020 | 636803 | 2020 VAULT LID RENEWAL PROGRAM - V2 - 37 DUNLOP ST.WEST | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Wong, Henry | 79920 | 78119.56 | -1800.44 | -2.253% | 0 | 13311.05 | 13311.05 |  | 0 | 669.56 | 669.56 |  | 0 | 1225.53 | 1225.53 |  | 79920 | 62913.42 | -17006.58 | -21.28% | 0 | 63.5 | 63.5 |  | 2021-11-03 01:00
Barrie | 2021 | 636804 | 636804 - 2021 VAULT LID RENEWAL PROGRAM - V49 - MAPLE AVE | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Lotto, Jay | 102833.48 | 60726.45 | -42107.03 | -40.95% | 38292.37 | 16245.29 | -22047.08 | -57.58% | 4663.11 | 1591.35 | -3071.76 | -65.87% | 6896 | 751.65 | -6144.35 | -89.1% | 52982 | 42138.16 | -10843.84 | -20.47% | 240 | 53 | -187 | -77.92% | 2021-11-03 01:00
Barrie | 2021 | 636861 | 636861 - 700 MAPLEVIEW DRIVE - BLOCK 6 EAST/INSPECT AND CONNECT | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 373504.76 | 361186.62 | -12318.14 | -3.298% | 26414.86 | 41221.65 | 14806.79 | 56.05% | 1730.42 | 0 | -1730.42 | -100% | 1778 | 2266.5 | 488.5 | 27.47% | 343581.48 | 315190.2 | -28391.28 | -8.263% | 168 | 143.75 | -24.25 | -14.43% | 2021-12-14 01:00
Barrie | 2022 | 636863 | 636863 - 700 MAPLEVIEW DRIVE - BLOCK 8/INSPECT AND CONNECT | 98 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 265373.3 | 261204.73 | -4168.57 | -1.571% | 30815.45 | 46488.22 | 15672.77 | 50.86% | 1609.52 | 310.01 | -1299.51 | -80.74% | 2213.89 | 2263.5 | 49.61 | 2.241% | 230734.44 | 212143 | -18591.44 | -8.058% | 210.58 | 137.5 | -73.08 | -34.7% | 2022-10-04 01:00
Barrie | 2021 | 636922 | 636922 - JOINT USE HE2020-037- SUNNIDALE RD.- FERNDALE DR. TO ANNE ST. | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 15495.42 | 16265.22 | 769.8 | 4.968% | 4633.44 | 5523.08 | 889.64 | 19.2% | 4440.36 | 928.39 | -3511.97 | -79.09% | 603.62 | 1824 | 1220.38 | 202.2% | 5818 | 7989.75 | 2171.75 | 37.33% | 20.42 | 48 | 27.58 | 135.1% | 2021-12-14 01:00
Barrie | 2020 | 637025 | 44KV AUTOMATED LIS - ADDITIONAL WORK - EAST - PATTERSON - CHILD W/O "CANCELLED" | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-19 01:00
Barrie | 2020 | 637031 | 44KV AUTOMATED LIS - ADDITIONAL WORK - EAST - PATTERSON - CHILD W/O 2 | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-17 01:00
Barrie | 2022 | 637033 | 637033 - ROAD AUTHORITY RELOCATION-ESSA ROAD AND FAIRVIEW ROAD | 99 | ANALYZE |  |  |  | Corriveau, Tom N | No | Zhang, Jiacheng | Dan Kish | 602865.93 | 542181.41 | -60684.52 | -10.07% | 257277.76 | 182338.16 | -74939.6 | -29.13% | 130675.47 | 129077.02 | -1598.45 | -1.223% | 44188.3 | 38678 | -5510.3 | -12.47% | 170724.4 | 192088.23 | 21363.83 | 12.51% | 1409.52 | 1374 | -35.52 | -2.52% | 2022-08-16 01:00
Barrie | 2022 | 637052 | 637052 - 40 THOMPSONS ROAD - RES SUBD EDS | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 50149.48 | 67225.62 | 17076.14 | 34.05% | 34568.83 | 36315.82 | 1746.99 | 5.054% | 4446.81 | 13599.55 | 9152.74 | 205.8% | 3997.2 | 8503 | 4505.8 | 112.7% | 7136.64 | 8807.25 | 1670.61 | 23.41% | 243.23 | 292 | 48.77 | 20.05% | 2022-08-29 01:00
Barrie | 2021 | 637073 | 637073 - JOINT USE HE2020-040- MAIN ST. PENETANGUISHENE | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 10106.58 | 5425.01 | -4681.57 | -46.32% | 3710.13 | 2095.01 | -1615.12 | -43.53% | 689.85 | 0 | -689.85 | -100% | 274.2 | 0 | -274.2 | -100% | 5432.4 | 3330 | -2102.4 | -38.7% | 16.2 | 0 | -16.2 | -100% | 2021-10-13 01:00
Barrie | 2020 | 637087 | 2020 TERMINATION BRACKETS -EAST - PATTERSON - CHILD W/O | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2023-01-10 01:00
Barrie | 2020 | 637107 | 2020 EXTRA POLE REPLACEMENTS - EAST - PATTERSON RD. - CHILD W/O | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-21 01:00
Barrie | 2022 | 637153 | 637153 - 430 ESSA ROAD, BARRIE | 95 | COMPLETE | BOM not accurate | Labour est. over | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 62038.82 | 53531.05 | -8507.77 | -13.71% | 17595.58 | 13578.82 | -4016.76 | -22.83% | 40434.03 | 32485.03 | -7949 | -19.66% | 1561.33 | 1731.55 | 170.22 | 10.9% | 2447.88 | 5735.65 | 3287.77 | 134.3% | 90.94 | 89 | -1.94 | -2.133% | 2022-02-07 01:00
Barrie | 2022 | 637194 | 637194 - LEAKING 3PH PADMOUNT TX REPLACEMENT AT 53 BAYFIELD ST. - BARRIE | 99 | COMPLETE | Cont Est Under | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Lotto, Jay | 82891.21 | 103700.93 | 20809.72 | 25.1% | 18235.76 | 21798.8 | 3563.04 | 19.54% | 21128.22 | 18415.97 | -2712.25 | -12.84% | 1423.23 | 2146.5 | 723.27 | 50.82% | 42104 | 61339.66 | 19235.66 | 45.69% | 0 | 66 | 66 |  | 2022-06-12 01:00
Barrie | 2022 | 637375 | 637375 - 700 MAPLEVIEW DRIVE - PHASE 2 - SUBD RES EDS | 95 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 331581.66 | 335833.29 | 4251.63 | 1.282% | 30499.08 | 50666.29 | 20167.21 | 66.12% | 3493.97 | 6331.24 | 2837.27 | 81.2% | 1910.53 | 5059.76 | 3149.23 | 164.8% | 295678.08 | 273776 | -21902.08 | -7.407% | 207 | 271.5 | 64.5 | 31.16% | 2022-03-22 01:00
Barrie | 2022 | 637378 | 637378 - 700 MAPLEVIEW DRIVE - BLOCK 17 - SUBD RES EDS | 95 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 448770.72 | 429715.09 | -19055.63 | -4.246% | 37013.21 | 53746.59 | 16733.38 | 45.21% | 3930.09 | 0 | -3930.09 | -100% | 2747.5 | 2394.5 | -353 | -12.85% | 405079.92 | 373574 | -31505.92 | -7.778% | 269.68 | 143 | -126.68 | -46.97% | 2022-03-22 01:00
Barrie | 2020 | 637430 | 637430 - UNDERGROUND CROSSING SEWER REPAIR AT MCGAHEY STREET - TOTTENHAM | 99 | COMPLETE | Under 10% | N/A | N/A | Pelleja, Emily | No | Alectra Utilities | Lotto, Jay | 88409.77 | 86553.75 | -1856.02 | -2.099% | 11123.65 | 18088.63 | 6964.98 | 62.61% | 1960.19 | 2554.22 | 594.03 | 30.3% | 458.17 | 955.11 | 496.94 | 108.5% | 74867.76 | 64955.79 | -9911.97 | -13.24% | 80.47 | 95 | 14.53 | 18.06% | 2020-10-02 01:00
Barrie | 2021 | 637473 | 49 COLLIER ST / BAR / NS / 3PH PAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-15 01:00
Barrie | 2022 | 637522 | 75 MELBOURNE ST / BRAD / SR / 1 PH PAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-15 01:00
Barrie | 2021 | 637543 | 637543 - 77 MELBOURNE ST / BRAD / NS / 3PH PAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 52174.44 | 60860.44 | 8686 | 16.65% | 16925.82 | 14847.22 | -2078.6 | -12.28% | 27953.51 | 18611.01 | -9342.5 | -33.42% | 1966.87 | 1775 | -191.87 | -9.755% | 27678.24 | 25627.21 | -2051.03 | -7.41% | 87.59 | 60 | -27.59 | -31.5% | 2021-03-18 01:00
Barrie | 2022 | 637657 | MORROW ROAD, BARRIE - REMOVE SECONDARY AND OLD POLES | 99 | COMPLETE | N/A | N/A | N/A | Pelleja, Emily | No | Harrington, James | Wong, Henry | 0 | 17596.66 | 17596.66 |  | 0 | 2708.9 | 2708.9 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14887.76 | 14887.76 |  | 0 | 0 | 0 |  | 2022-03-08 01:00
Barrie | 2022 | 637658 | 637658 - SANDSTORM PHASE 8A - SUBD RES EDS | 95 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 486734.69 | 464781.15 | -21953.54 | -4.51% | 51587.42 | 63226.31 | 11638.89 | 22.56% | 4173.07 | 3271.24 | -901.83 | -21.61% | 4210.04 | 4659.5 | 449.46 | 10.68% | 426764.16 | 392186.25 | -34577.91 | -8.102% | 387.74 | 251 | -136.74 | -35.27% | 2022-03-08 01:00
Barrie | 2020 | 637670 | 637670 - GRENCER ROAD RECONFIGURATION | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Dan Kish | 119690.49 | 94325.03 | -25365.46 | -21.19% | 11330.83 | 15121.08 | 3790.25 | 33.45% | 27947.78 | 28534.36 | 586.58 | 2.099% | 194.88 | 0 | -194.88 | -100% | 80217 | 50669.59 | -29547.41 | -36.83% | 6.93 | 16.75 | 9.82 | 141.7% | 2020-09-12 01:00
Barrie | 2021 | 637749 | 637749 - HONEYFIELD BLK 395 - SUBD RES EDS | 99 | COMPLETE | Estimate incorrect | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 297019.3 | 257218.02 | -39801.28 | -13.4% | 28450.77 | 14881.92 | -13568.85 | -47.69% | 3996.9 | 2281.15 | -1715.75 | -42.93% | 2707.27 | 2096 | -611.27 | -22.58% | 261864.36 | 46.8 | -261817.56 | -99.98% | 185.79 | 75.25 | -110.54 | -59.5% | 2021-05-31 01:00
Barrie | 2020 | 637945 | 637945 - 2020 REAR LOT EASTERN AVE IN TOTTENHAM | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | No | Alectra Utilities | Dan Kish | 2069851.85 | 2033846.8 | -36005.05 | -1.739% | 48719.93 | 214734.16 | 166014.23 | 340.8% | 9791.38 | 12749.59 | 2958.21 | 30.21% | 6021.38 | 3571.65 | -2449.73 | -40.68% | 2005319.16 | 1797278.91 | -208040.25 | -10.37% | 160 | 206.5 | 46.5 | 29.06% | 2020-12-21 01:00
Barrie | 2021 | 637972 | 637972 - 170 BURTON AVE/BAR/NS/3PH PAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 41106.46 | 56284.07 | 15177.61 | 36.92% | 17645.34 | 16542.83 | -1102.51 | -6.248% | 32614.29 | 26828.74 | -5785.55 | -17.74% | 1841.71 | 2854 | 1012.29 | 54.96% | 11355.12 | 10058.5 | -1296.62 | -11.42% | 94.25 | 108 | 13.75 | 14.59% | 2021-04-30
Barrie | 2022 | 638007 | JOINT USE PERMIT HE2020-061 | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Martin, Shane | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-09 01:00
Barrie | 2021 | 638115 | 638115 - 50 ALLIANCE BLVD/BAR/UP/3PH PAD PHASE 2 | 99 | COMPLETE | Under 10% | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 89024.77 | 93097.01 | 4072.24 | 4.574% | 13404.87 | 12476.53 | -928.34 | -6.925% | 74562.79 | 74928.69 | 365.9 | 0.4907% | 1057.11 | 952.5 | -104.61 | -9.896% | 0 | 4739.29 | 4739.29 |  | 62 | 22.5 | -39.5 | -63.71% | 2021-05-29 01:00
Barrie | 2022 | 638157 | 638157 - 2022 SUNNIDALE UG CABLE REPLACEMENT PHASE 3 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Lotto, Jay | 1586766.23 | 1715732.8 | 128966.57 | 8.128% | 181239.7 | 261535.06 | 80295.36 | 44.3% | 39562.38 | 114292 | 74729.62 | 188.9% | 13782.15 | 20509.5 | 6727.35 | 48.81% | 1352182 | 1319396.24 | -32785.76 | -2.425% | 719.07 | 926 | 206.93 | 28.78% | 2022-08-23 01:00
Barrie | 2021 | 638159 | 638159 - BRIAR HILL SUBDIVISION - HILLSIDE - SUBD RES EDS | 99 | COMPLETE | Cont Est Under | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 256566.06 | 280436.26 | 23870.2 | 9.304% | 33998.64 | 37242.31 | 3243.67 | 9.541% | 1691.48 | 653.94 | -1037.54 | -61.34% | 2681.38 | 1872.41 | -808.97 | -30.17% | 218194.56 | 240667.6 | 22473.04 | 10.3% | 245.53 | 112.75 | -132.78 | -54.08% | 2021-06-18 01:00
Barrie | 2020 | 638233 | 638233 - 1854 ADJALA TECUMSETH TOWNLINE / TOT / NS / 1PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 26025.17 | 16513 | -9512.17 | -36.55% | 13895.06 | 5618.29 | -8276.77 | -59.57% | 8574.42 | 4288.94 | -4285.48 | -49.98% | 1446.45 | 1444.17 | -2.28 | -0.1576% | 2109.24 | 5161.6 | 3052.36 | 144.7% | 68.2 | 35 | -33.2 | -48.68% | 2020-12-18 01:00
Barrie | 2022 | 638247 | 638247 - 233 DUNLOP ST W/BAR/NS/3PH PAD | 99 | COMPLETE | BOM not accurate | Labour est. under | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 72525.15 | 50695.1 | -21830.05 | -30.1% | 19942.64 | 10337.54 | -9605.1 | -48.16% | 43435.67 | 33040.06 | -10395.61 | -23.93% | 2403.84 | 574.5 | -1829.34 | -76.1% | 6743 | 6743 | 0 | 0% | 122.47 | 49 | -73.47 | -59.99% | 2022-07-21 01:00
Barrie | 2021 | 638389 | 21 LILY STREET, BEETON - RELOCATE POLES | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Lacombe, Joel | No | Lemire, Blake | Persaud, Ryan | 1704.38 | 6131.69 | 4427.31 | 259.8% | 1259.98 | 3047.69 | 1787.71 | 141.9% | 74.58 | 0 | -74.58 | -100% | 369.82 | 0 | -369.82 | -100% | 0 | 3084 | 3084 |  | 11.38 | 0 | -11.38 | -100% | 2021-12-31 01:00
Barrie | 2021 | 638465 | 638465 - 783 BAYVIEW DRIVE/BAR/UPGRADE | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 28009.26 | 42539.11 | 14529.85 | 51.88% | 14802.54 | 9698.99 | -5103.55 | -34.48% | 32878.25 | 28363.17 | -4515.08 | -13.73% | 1058.47 | 575.5 | -482.97 | -45.63% | 1620 | 3901.45 | 2281.45 | 140.8% | 58.4 | 32 | -26.4 | -45.21% | 2021-03-19 01:00
Barrie | 2021 | 638537 | 638537 - 2021 POLE REPLACEMENTS ALLISTON BATCH 1 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 400631.72 | 542027.77 | 141396.05 | 35.29% | 152690.72 | 54972.98 | -97717.74 | -64% | 132056.22 | 136166.28 | 4110.06 | 3.112% | 45684.78 | 0 | -45684.78 | -100% | 70200 | 350888.51 | 280688.51 | 399.8% | 1404.05 | 0 | -1404.05 | -100% | 2021-09-02 01:00
Barrie | 2021 | 638538 | 638538 - 2021 POLE REPLACEMENTS ALLISTON BATCH 2 | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 377617.05 | 321373.54 | -56243.51 | -14.89% | 132323.02 | 119058.36 | -13264.66 | -10.02% | 105171.06 | 60627.76 | -44543.3 | -42.35% | 38332.97 | 49018.04 | 10685.07 | 27.87% | 101790 | 92669.38 | -9120.62 | -8.96% | 1219.39 | 1077 | -142.39 | -11.68% | 2021-12-06 01:00
Barrie | 2021 | 638539 | 638539 - 2021 POLE REPLACEMENTS BARRIE BATCH 5 | 99 | COMPLETE | Labour est. over | BOM cost variance | N/A | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 162363.17 | 154659.95 | -7703.22 | -4.744% | 56394.86 | 55777.73 | -617.13 | -1.094% | 47032.48 | 36599.91 | -10432.57 | -22.18% | 16150.55 | 21838.25 | 5687.7 | 35.22% | 42785.28 | 40444.06 | -2341.22 | -5.472% | 520.26 | 482 | -38.26 | -7.354% | 2021-11-09 01:00
Barrie | 2021 | 638540 | 638540 - 2021 POLE REPLACEMENTS BARRIE BATCH 1 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 225171.56 | 210142.48 | -15029.08 | -6.675% | 71957.41 | 71297.44 | -659.97 | -0.9172% | 75862.39 | 72170.29 | -3692.1 | -4.867% | 19031.76 | 31510.69 | 12478.93 | 65.57% | 58320 | 35164.06 | -23155.94 | -39.7% | 676.56 | 645 | -31.56 | -4.665% | 2021-10-06 01:00
Barrie | 2021 | 638541 | 638541 - 2021 POLE REPLACEMENTS BARRIE BATCH 2 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 252098.51 | 264014.01 | 11915.5 | 4.727% | 73159.93 | 106311.09 | 33151.16 | 45.31% | 86708.31 | 73182.8 | -13525.51 | -15.6% | 18227.55 | 45067.33 | 26839.78 | 147.2% | 74002.72 | 39452.79 | -34549.93 | -46.69% | 690.86 | 1034.5 | 343.64 | 49.74% | 2021-10-26 01:00
Barrie | 2021 | 638542 | 638542 - 2021 POLE REPLACEMENTS BARRIE BATCH 3 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 234986.06 | 248204.14 | 13218.08 | 5.625% | 53053.72 | 89124.18 | 36070.46 | 67.99% | 119257.16 | 76470.91 | -42786.25 | -35.88% | 13911.78 | 42963.66 | 29051.88 | 208.8% | 48763.4 | 39645.39 | -9118.01 | -18.7% | 499.35 | 902.5 | 403.15 | 80.73% | 2021-10-06 01:00
Barrie | 2021 | 638543 | 638543 - 2021 POLE REPLACEMENTS BARRIE BATCH 4 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 220759.15 | 268220.3 | 47461.15 | 21.5% | 81353.26 | 101657.08 | 20303.82 | 24.96% | 78947.5 | 64680.31 | -14267.19 | -18.07% | 20498.39 | 42253.98 | 21755.59 | 106.1% | 39960 | 59628.93 | 19668.93 | 49.22% | 756.84 | 914 | 157.16 | 20.77% | 2021-10-22 01:00
Barrie | 2021 | 638544 | 638544 - 2021 POLE REPLACEMENTS BRADFORD BATCH 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 137782.23 | 151441.02 | 13658.79 | 9.913% | 51992.06 | 56234 | 4241.94 | 8.159% | 42602.81 | 44692.64 | 2089.83 | 4.905% | 14027.36 | 26840.01 | 12812.65 | 91.34% | 29160 | 23674.37 | -5485.63 | -18.81% | 442.94 | 546.5 | 103.56 | 23.38% | 2021-12-13 01:00
Barrie | 2021 | 638545 | 638545 - 2021 POLE REPLACEMENTS PENETANG BATCH 1 | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 36095.22 | 32296.14 | -3799.08 | -10.53% | 16139.47 | 14924.54 | -1214.93 | -7.528% | 5737.95 | 5150.64 | -587.31 | -10.24% | 3849.8 | 5520.55 | 1670.75 | 43.4% | 10368 | 6700.41 | -3667.59 | -35.37% | 131.41 | 113 | -18.41 | -14.01% | 2021-12-09 01:00
Barrie | 2021 | 638546 | 638546 - 2021 POLE REPLACEMENTS TOTTENHAM BATCH 1 | 99 | COMPLETE | BOM cost variance | Labour est. over | N/A | Bowman, Todd J | No | Pollock, Kim | Dan Kish | 84804.84 | 64849.96 | -19954.88 | -23.53% | 30701.67 | 28157.66 | -2544.01 | -8.286% | 17594.58 | 9686.53 | -7908.05 | -44.95% | 7348.59 | 5442.14 | -1906.45 | -25.94% | 29160 | 21563.63 | -7596.37 | -26.05% | 237.72 | 151 | -86.72 | -36.48% | 2021-12-01 01:00
Barrie | 2021 | 638557 | 638557 - JOINT USE PERMIT HE2020-068 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 7576.55 | 5538.26 | -2038.29 | -26.9% | 2410.55 | 1596.92 | -813.63 | -33.75% | 0 | 0 | 0 |  | 90 | 90 | 0 | 0% | 5076 | 3851.34 | -1224.66 | -24.13% | 4 | 7.5 | 3.5 | 87.5% | 2021-07-13 01:00
Barrie | 2021 | 638597 | 638597 - 2021 PADMOUNT TX REPLACEMENT BATCH 1 - BARRIE - 1X 3PH TX'S | 99 | COMPLETE | BOM cost variance | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 41851.29 | 48855.5 | 7004.21 | 16.74% | 5005.89 | 5465.95 | 460.06 | 9.19% | 36343.84 | 39069.41 | 2725.57 | 7.499% | 501.56 | 2395.14 | 1893.58 | 377.5% | 0 | 1925 | 1925 |  | 19.8 | 22 | 2.2 | 11.11% | 2021-12-30 01:00
Barrie | 2021 | 638598 | 638598 - 2021 PADMOUNT TX REPLACEMENT BATCH 2 - BARRIE - 4X 1PH TX'S | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 34164.66 | 25170.07 | -8994.59 | -26.33% | 14132.6 | 8697.06 | -5435.54 | -38.46% | 18133.15 | 14746.35 | -3386.8 | -18.68% | 1898.91 | 1726.66 | -172.25 | -9.071% | 0 | 0 | 0 |  | 74.96 | 32 | -42.96 | -57.31% | 2021-06-17 01:00
Barrie | 2021 | 638599 | 638599 - 2021 PADMOUNT TX REPLACEMENT BATCH 3 - BARRIE - 7X 1PH TX'S | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 52815.25 | 23826.94 | -28988.31 | -54.89% | 20163.03 | 8743.9 | -11419.13 | -56.63% | 29329.13 | 13495.78 | -15833.35 | -53.99% | 3323.09 | 1587.26 | -1735.83 | -52.24% | 0 | 0 | 0 |  | 131.17 | 32 | -99.17 | -75.6% | 2021-10-19 01:00
Barrie | 2021 | 638600 | 638600 - 2021 PADMOUNT TX REPLACEMENT BATCH 4 - BRADFORD - 1X 3PH & 1X 1PH TX'S | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 40815.11 | 8717.2 | -32097.91 | -78.64% | 7970.61 | 2484.04 | -5486.57 | -68.84% | 31405.98 | 5897.33 | -25508.65 | -81.22% | 1438.52 | 335.83 | -1102.69 | -76.65% | 0 | 0 | 0 |  | 47.56 | 10 | -37.56 | -78.97% | 2021-06-03 01:00
Barrie | 2021 | 638601 | 638601 - 2021 PADMOUNT TX REPLACEMENT BATCH 5 - BEETON - 1X 3PH & 2X 1PH | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 39658.48 | 37070.24 | -2588.24 | -6.526% | 10823.95 | 5106.91 | -5717.04 | -52.82% | 26459.04 | 29501.66 | 3042.62 | 11.5% | 2375.49 | 2461.67 | 86.18 | 3.628% | 0 | 0 | 0 |  | 75.32 | 36 | -39.32 | -52.2% | 2021-10-19 01:00
Barrie | 2022 | 638623 | 8TH LINE IN ALLISTON POLE RELOCATION | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated | N/A | Bowman, Todd J | No | Pollock, Kim | Jeremy Wright | 32794.63 | 36712.88 | 3918.25 | 11.95% | 13005.18 | 19116.87 | 6111.69 | 46.99% | 4770.2 | 3956.48 | -813.72 | -17.06% | 2419.25 | 6406.85 | 3987.6 | 164.8% | 12600 | 7232.68 | -5367.32 | -42.6% | 74.32 | 94.5 | 20.18 | 27.15% | 2022-01-26 01:00
Barrie | 2021 | 638627 | 638627 - 160 HOLLAND ST. - BRADFORD - 3PH PADMOUNT TRANSFORMER REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Lotto, Jay | 85362.06 | 92818.58 | 7456.52 | 8.735% | 24055.95 | 23751.95 | -304 | -1.264% | 10836.45 | 4378.22 | -6458.23 | -59.6% | 2914.02 | 3553.9 | 639.88 | 21.96% | 47555.64 | 61134.51 | 13578.87 | 28.55% | 134.41 | 64.5 | -69.91 | -52.01% | 2021-04-14
Barrie | 2021 | 638629 | 638629 - 2021 Distribution Automation -Bryne Dr & Commerce Park Dr-13.8kV Automated Intellirupter, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Jeremy Wright | 78503.75 | 82310.88 | 3807.13 | 4.85% | 38385.93 | 39557.53 | 1171.6 | 3.052% | 8380.92 | 18609.8 | 10228.88 | 122% | 6896.9 | 8946.14 | 2049.24 | 29.71% | 24840 | 15197.41 | -9642.59 | -38.82% | 229.45 | 388.5 | 159.05 | 69.32% | 2021-10-12 01:00
Barrie | 2021 | 638631 | 638631 - 2021 Distribution Automation - Essa & Beacon -13.8kV Automated Intellirupter, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Jeremy Wright | 75537.14 | 87172.52 | 11635.38 | 15.4% | 33652.39 | 39986.4 | 6334.01 | 18.82% | 10995.25 | 18680.18 | 7684.93 | 69.89% | 7129.5 | 9254.25 | 2124.75 | 29.8% | 23760 | 19251.69 | -4508.31 | -18.97% | 240.37 | 378 | 137.63 | 57.26% | 2021-10-06 01:00
Barrie | 2021 | 638632 | 638632 - 2021 - DISTRIBUTION AUTOMATION - BARRIE - TIFFIN & MILLER - 44KV AUTOMATED LIS | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 152705.61 | 176953.72 | 24248.11 | 15.88% | 35697.87 | 19052.41 | -16645.46 | -46.63% | 89595.77 | 94586.33 | 4990.56 | 5.57% | 9492.61 | 0 | -9492.61 | -100% | 17919.36 | 63314.98 | 45395.62 | 253.3% | 324.91 | 59.5 | -265.41 | -81.69% | 2021-10-25 01:00
Barrie | 2022 | 638652 | 2021 - SWITCHGEAR RENEWAL - BARRIE - SC13520 - 46 DEAN AVE | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Wong, Henry | 1130.97 | 0 | -1130.97 | -100% | 1130.97 | 0 | -1130.97 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-08 01:00
Barrie | 2022 | 638655 | 2021 - SWITCHGEAR RENEWAL - BARRIE - SC13649 - 141 MADELAINE DR | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | No | Walters, Geoffrey D | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-07 01:00
Barrie | 2021 | 638709 | 638709 - 1 BIG BAY POINT RD/BAR/NS/3PH PAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 62086.25 | 75133.32 | 13047.07 | 21.01% | 18719.54 | 15408.74 | -3310.8 | -17.69% | 57319.71 | 47855.33 | -9464.38 | -16.51% | 0 | 1938 | 1938 |  | 8397 | 9931.25 | 1534.25 | 18.27% | 112.85 | 73 | -39.85 | -35.31% | 2021-04-30
Barrie | 2021 | 638827 | 638827 - 233 DUNLOP ST W, BARRIE | 98 | COMPLETE | Labour est. over | Cont Est Over | N/A | Corriveau, Tom N | No | Battistella, Alexander | Jeremy Wright | 167046.76 | 133094.36 | -33952.4 | -20.33% | 73019.76 | 55716.76 | -17303 | -23.7% | 40692.63 | 40937.88 | 245.25 | 0.6027% | 14084.37 | 14420.5 | 336.13 | 2.387% | 39250 | 22019.22 | -17230.78 | -43.9% | 431.28 | 507.5 | 76.22 | 17.67% | 2021-12-15 01:00
Barrie | 2020 | 638860 | 638860 - 50 ALLIANCE BLVD/BAR/UP/3PH PAD PHASE 1 | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Lotto, Jay | 99700.31 | 82727.16 | -16973.15 | -17.02% | 38774.77 | 17161.09 | -21613.68 | -55.74% | 58878.41 | 48164.66 | -10713.75 | -18.2% | 4573.73 | 4538.82 | -34.91 | -0.7633% | 19823.4 | 12862.59 | -6960.81 | -35.11% | 202.14 | 125 | -77.14 | -38.16% | 2020-12-29 01:00
Barrie | 2021 | 638886 | 638886 - 25 GRENCER RD/BRAD/NS/3PH PAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 39033.58 | 47952.34 | 8918.76 | 22.85% | 16179.66 | 12183.29 | -3996.37 | -24.7% | 37690.39 | 29559.65 | -8130.74 | -21.57% | 1877.01 | 1591 | -286.01 | -15.24% | 5636.52 | 4618.4 | -1018.12 | -18.06% | 103.16 | 73 | -30.16 | -29.24% | 2021-03-23 01:00
Barrie | 2022 | 638959 | 638959 - LORMEL PHASE 3 - SUBD RES EDS | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 74426.59 | 2428.85 | -71997.74 | -96.74% | 46076.15 | 2372.85 | -43703.3 | -94.85% | 0 | 0 | 0 |  | 4004 | 56 | -3948 | -98.6% | 24346.44 | 0 | -24346.44 | -100% | 358 | 4 | -354 | -98.88% | 2022-05-02
Barrie | 2022 | 638999 | 5925 14TH LINE/ALL/NS/3 PH PAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | East Coordinator | 0 | 10000 | 10000 |  | 0 | 4062.6 | 4062.6 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5937.4 | 5937.4 |  | 0 | 0 | 0 |  | 2022-12-14 01:00
Barrie | 2021 | 639019 | 639019 - JOINT USE PERMIT #HE2020-075 - ADJALA TECHUMSETH TOWNLINE - TOTTENHAM | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 9247.53 | 6541.37 | -2706.16 | -29.26% | 3462.77 | 2041.37 | -1421.4 | -41.05% | 526.75 | 0 | -526.75 | -100% | 398.01 | 0 | -398.01 | -100% | 4860 | 4500 | -360 | -7.407% | 13.53 | 4 | -9.53 | -70.44% | 2021-06-29 01:00
Barrie | 2021 | 639059 | 639059 - 177 ROBERT ST E/PEN/NS/3PH PAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 48463.62 | 53488.25 | 5024.63 | 10.37% | 21963.16 | 13143.71 | -8819.45 | -40.16% | 37828.21 | 30812.64 | -7015.57 | -18.55% | 2324.25 | 2017.5 | -306.75 | -13.2% | 8698 | 7514.4 | -1183.6 | -13.61% | 125.06 | 69.5 | -55.56 | -44.43% | 2021-09-17 01:00
Barrie | 2022 | 639420 | 639420 - 204 MAPLEVIEW DR W/BAR/UP/3PH PAD | 99 | ANALYZE |  |  |  | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 106505.27 | 90483.65 | -16021.62 | -15.04% | 19216.94 | 10811.93 | -8405.01 | -43.74% | 82992.39 | 78797.72 | -4194.67 | -5.054% | 2195.94 | 874 | -1321.94 | -60.2% | 2100 | 0 | -2100 | -100% | 122.51 | 48 | -74.51 | -60.82% | 2022-07-06 01:00
Barrie | 2022 | 639464 | 639464 - 418 DUNLOP ST W/BAR/NS/3PH PAD | 95 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 97364.68 | 75794.77 | -21569.91 | -22.15% | 30228.79 | 19553.32 | -10675.47 | -35.32% | 49336.44 | 42860.17 | -6476.27 | -13.13% | 4366.45 | 2864 | -1502.45 | -34.41% | 13433 | 10517.28 | -2915.72 | -21.71% | 169.27 | 74 | -95.27 | -56.28% | 2022-10-14 01:00
Barrie | 2021 | 639475 | 639475 -122 QUEEN ST S/TOT/NS/1PH PAD | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 53242.66 | 36153.56 | -17089.1 | -32.1% | 22079.36 | 14948.02 | -7131.34 | -32.3% | 17816.38 | 12648.04 | -5168.34 | -29.01% | 3470.92 | 1944 | -1526.92 | -43.99% | 11876 | 6613.5 | -5262.5 | -44.31% | 137 | 90 | -47 | -34.31% | 2021-12-17 01:00
Barrie | 2021 | 639476 | 639476 - BEAR CREEK LANDING - REMOVALS | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 24449.29 | 19688.93 | -4760.36 | -19.47% | 12676.81 | 7577.21 | -5099.6 | -40.23% | 399.36 | 428.21 | 28.85 | 7.224% | 815.12 | 1126 | 310.88 | 38.14% | 10558 | 10557.51 | -0.49 | -0.004641% | 67.72 | 50 | -17.72 | -26.17% | 2021-11-15 01:00
Barrie | 2021 | 639556 | 639556 - BARRIE TS - TEMPORARY POLE RELOCATIONS | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 92326.54 | 57078.8 | -35247.74 | -38.18% | 45093.34 | 19245.56 | -25847.78 | -57.32% | 13286.57 | 13502.34 | 215.77 | 1.624% | 11266.63 | 4510.5 | -6756.13 | -59.97% | 22680 | 19820.4 | -2859.6 | -12.61% | 401.82 | 193 | -208.82 | -51.97% | 2021-01-15 01:00
Barrie | 2021 | 639657 | 639657 - 2021 BENSON BARRIE UG CABLE REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Lotto, Jay | 1261489.08 | 1299478.88 | 37989.8 | 3.012% | 35072.7 | 211329.68 | 176256.98 | 502.5% | 2294.54 | 32861.64 | 30567.1 | 1332% | 2860 | 10415.38 | 7555.38 | 264.2% | 1221261.84 | 1044872.18 | -176389.66 | -14.44% | 260 | 409 | 149 | 57.31% | 2021-09-07 01:00
Barrie | 2022 | 639735 | 639735 - TRANSFORMER RELOCATION AT 81 HOLT DRIVE - ALLISTON | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 53324.78 | 22031.87 | -31292.91 | -58.68% | 21157.73 | 6190.11 | -14967.62 | -70.74% | 1187.73 | 1368.26 | 180.53 | 15.2% | 2222.32 | 1268 | -954.32 | -42.94% | 28757 | 13205.5 | -15551.5 | -54.08% | 121.87 | 28 | -93.87 | -77.02% | 2022-10-03 01:00
Barrie | 2022 | 639787 | 639787 - 441 HURONIA RD/BAR/NS/3PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 69139.57 | 57218.29 | -11921.28 | -17.24% | 21370.62 | 15164.29 | -6206.33 | -29.04% | 35708.38 | 31138.05 | -4570.33 | -12.8% | 2772.57 | 2514.5 | -258.07 | -9.308% | 9288 | 8401.45 | -886.55 | -9.545% | 133.67 | 87 | -46.67 | -34.91% | 2022-11-28 01:00
Barrie | 2021 | 639788 | 639788 - 219 CHAMPLAIN RD/PEN/NS/1PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 38090.77 | 33709.66 | -4381.11 | -11.5% | 17419.59 | 11768.86 | -5650.73 | -32.44% | 15065.26 | 15643.4 | 578.14 | 3.838% | 2472.68 | 2244 | -228.68 | -9.248% | 4377.24 | 4053.4 | -323.84 | -7.398% | 112.37 | 82.5 | -29.87 | -26.58% | 2021-07-15 01:00
Barrie | 2022 | 640313 | 640313 - 1 REID DR/BAR/NS/3PH PAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 60497.78 | 70437.3 | 9939.52 | 16.43% | 18861.39 | 10847.65 | -8013.74 | -42.49% | 56952.7 | 52744.1 | -4208.6 | -7.39% | 2333.69 | 1323 | -1010.69 | -43.31% | 4700 | 5522.55 | 822.55 | 17.5% | 123.22 | 71 | -52.22 | -42.38% | 2022-09-15 01:00
Barrie | 2021 | 640320 | 640320 - 78 MAIN ST. PENETANG - ARIEL ENCROACHMENT SECONDARY SERVICE RELOCATION | 99 | COMPLETE | Labour est. over | N/A | N/A | Bowman, Todd J | No | Walters, Geoffrey D | Steve Rumble | 28615.42 | 24179.85 | -4435.57 | -15.5% | 13946.32 | 10794.42 | -3151.9 | -22.6% | 1473.94 | 1099.89 | -374.05 | -25.38% | 2100.16 | 1140.54 | -959.62 | -45.69% | 11095 | 11145 | 50 | 0.4507% | 66.23 | 22 | -44.23 | -66.78% | 2021-10-13 01:00
Barrie | 2021 | 640458 | 640458 - 21 PATTERSON RD/BAR/NS/CUSTOMER OWNED STN | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 17785.32 | 11051.06 | -6734.26 | -37.86% | 12194.26 | 10837.56 | -1356.7 | -11.13% | 9271.06 | 0 | -9271.06 | -100% | 1320 | 213.5 | -1106.5 | -83.83% | 0 | 0 | 0 |  | 0 | 38 | 38 |  | 2021-05-14
Barrie | 2021 | 640498 | 640498 - BELL BOND CONNECTIONS- MAPLEVIEW DRIVE WEST, BARRIE | 99 | COMPLETE | Labour est. under | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 748.96 | 1348.74 | 599.78 | 80.08% | 703.96 | 1168.74 | 464.78 | 66.02% | 0 | 0 | 0 |  | 45 | 180 | 135 | 300% | 0 | 0 | 0 |  | 2 | 8 | 6 | 300% | 2021-03-09 01:00
Barrie | 2021 | 640544 | 640544 - 36 WHITE OAKS RD/BAR/NS/1PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 40442.3 | 33613.28 | -6829.02 | -16.89% | 18080.9 | 14694.9 | -3386 | -18.73% | 14333.87 | 12703.87 | -1630 | -11.37% | 2308.53 | 1664 | -644.53 | -27.92% | 5719 | 4550.51 | -1168.49 | -20.43% | 105.05 | 94 | -11.05 | -10.52% | 2021-12-01 01:00
Barrie | 2022 | 640618 | 640618 - 541 ESSA ROAD - SUBD RES EDS | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 97825.69 | 90366.33 | -7459.36 | -7.625% | 24728.93 | 21700.63 | -3028.3 | -12.25% | 2423.11 | 2454.7 | 31.59 | 1.304% | 1929.65 | 967 | -962.65 | -49.89% | 68744 | 65244 | -3500 | -5.091% | 85.58 | 53 | -32.58 | -38.07% | 2022-11-04 01:00
Barrie | 2022 | 640636 | 2021 VAULT LID RENEWAL PROGRAM - V16 - 42 MAPLE AVE. - EXTRA LOCATION | 99 | COMPLETE | Engineering by-passed |  |  | Bowman, Todd J | No | Walters, Geoffrey D | East Coordinator | 0 | 52489.6 | 52489.6 |  | 0 | 13558.85 | 13558.85 |  | 0 | 4772.88 | 4772.88 |  | 0 | 1506.47 | 1506.47 |  | 0 | 32651.4 | 32651.4 |  | 0 | 99 | 99 |  | 2022-11-14 01:00
Barrie | 2022 | 640638 | 2021 VAULT LID RENEWAL PROGRAM - V25 - 41 MULCASTER ST | 99 | COMPLETE | Engineering by-passed |  |  | Bowman, Todd J | No | Walters, Geoffrey D | East Coordinator | 0 | 7769.85 | 7769.85 |  | 0 | 3636.62 | 3636.62 |  | 0 | 0 | 0 |  | 0 | 187.5 | 187.5 |  | 0 | 3945.73 | 3945.73 |  | 0 | 31 | 31 |  | 2022-11-14 01:00
Barrie | 2021 | 640665 | 640665 - BIG BAY POINT ROAD - HYDRO CROSSING RELOCATION | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Lotto, Jay | 134246.56 | 138541.21 | 4294.65 | 3.199% | 8443.08 | 13321.01 | 4877.93 | 57.77% | 0 | 588.51 | 588.51 |  | 1011.64 | 1675 | 663.36 | 65.57% | 124791.84 | 122956.69 | -1835.15 | -1.471% | 80.51 | 43 | -37.51 | -46.59% | 2021-06-01 01:00
Barrie | 2022 | 640732 | 640732 - 2021 PADMOUNT TX REPLACEMENT EXTRA BATCH 1 - BARRIE 1PH TX'S | 99 | COMPLETE | Inaccurate design | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 84698.81 | 60022.58 | -24676.23 | -29.13% | 24064.95 | 16400.14 | -7664.81 | -31.85% | 55761 | 40066.44 | -15694.56 | -28.15% | 4872.86 | 3556 | -1316.86 | -27.02% | 0 | 0 | 0 |  | 144.86 | 90 | -54.86 | -37.87% | 2022-05-06
Barrie | 2022 | 640733 | 640733 - 2021 PADMOUNT TX REPLACEMENT EXTRA BATCH 7 - BARRIE | 99 | COMPLETE | Inaccurate design | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 41895.23 | 32848.03 | -9047.2 | -21.59% | 8560.81 | 4650.81 | -3910 | -45.67% | 31518.94 | 26541.22 | -4977.72 | -15.79% | 1815.48 | 1656 | -159.48 | -8.784% | 0 | 0 | 0 |  | 51.6 | 32 | -19.6 | -37.98% | 2022-08-25 01:00
Barrie | 2021 | 640805 | 640805 - JOINT USE PERMIT HE2020-076 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 8324.03 | 5632.86 | -2691.17 | -32.33% | 3479.55 | 1860.26 | -1619.29 | -46.54% | 929.36 | 217.6 | -711.76 | -76.59% | 415.92 | 315 | -100.92 | -24.26% | 3499.2 | 3240 | -259.2 | -7.407% | 14.08 | 16 | 1.92 | 13.64% | 2021-08-18 01:00
Barrie | 2021 | 640861 | 640861 - JOINT USE PERMIT HE2021-026 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 8141.79 | 5032.25 | -3109.54 | -38.19% | 3308.08 | 878.87 | -2429.21 | -73.43% | 755.43 | 198.94 | -556.49 | -73.67% | 278.28 | 45 | -233.28 | -83.83% | 3800 | 3909.44 | 109.44 | 2.88% | 9.72 | 2 | -7.72 | -79.42% | 2021-09-21 01:00
Barrie | 2021 | 640912 | 640912 - JOINT USE PERMIT HE2021-027 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 6197.41 | 5118.93 | -1078.48 | -17.4% | 2853.44 | 1476.72 | -1376.72 | -48.25% | 58.97 | 292.71 | 233.74 | 396.4% | 135 | 199.5 | 64.5 | 47.78% | 3150 | 3150 | 0 | 0% | 6 | 7 | 1 | 16.67% | 2021-09-08 01:00
Barrie | 2021 | 640913 | 640913 - JOINT USE PERMIT HE2021-028 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 3665 | 2145.1 | -1519.9 | -41.47% | 2387 | 1065.43 | -1321.57 | -55.37% | 0 | 0 | 0 |  | 90 | 0 | -90 | -100% | 1188 | 1079.67 | -108.33 | -9.119% | 6 | 6 | 0 | 0% | 2021-07-21 01:00
Barrie | 2021 | 640916 | 640916 - JOINT USE PERMIT HE2021-030 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 6922.61 | 3790.73 | -3131.88 | -45.24% | 3274.84 | 1310.44 | -1964.4 | -59.98% | 852.58 | 0 | -852.58 | -100% | 295.19 | 135 | -160.19 | -54.27% | 2500 | 2345.29 | -154.71 | -6.188% | 10.35 | 6 | -4.35 | -42.03% | 2021-08-12 01:00
Barrie | 2021 | 640949 | 640949 - 2021 EMERG. UG CABLE REPLACEMENT BRADFORD | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | No | Pollock, Kim | Lotto, Jay | 487912.02 | 481165.07 | -6746.95 | -1.383% | 36767.98 | 48506.86 | 11738.88 | 31.93% | 58706.24 | 52301.28 | -6404.96 | -10.91% | 3637.8 | 1024 | -2613.8 | -71.85% | 388800 | 379332.93 | -9467.07 | -2.435% | 271.67 | 64 | -207.67 | -76.44% | 2021-05-31 01:00
Barrie | 2021 | 640958 | 640958 - 299 ANNE ST N - SUBD CAP | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Perks, Dan | Lotto, Jay | 30180.11 | 24607.57 | -5572.54 | -18.46% | 11122.65 | 7678.01 | -3444.64 | -30.97% | 4378.42 | 3988.74 | -389.68 | -8.9% | 2045.2 | 1242.5 | -802.7 | -39.25% | 12633.84 | 11698.32 | -935.52 | -7.405% | 75.2 | 53 | -22.2 | -29.52% | 2021-06-22 01:00
Barrie | 2022 | 640976 | 640976 - HARBOUR POINTE PHASE IV - SUBD RES EDS | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 209045.73 | 205471.94 | -3573.79 | -1.71% | 49290.62 | 35443.13 | -13847.49 | -28.09% | 4186.5 | 2750.81 | -1435.69 | -34.29% | 3336.61 | 1921 | -1415.61 | -42.43% | 152232 | 165357 | 13125 | 8.622% | 185.84 | 97 | -88.84 | -47.8% | 2022-12-13 01:00
Barrie | 2021 | 641031 | 641031 - 38 POYNTZ ST, PENETANGUISHENE - 400A 120/240V SERVICE | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 31967.77 | 24619.58 | -7348.19 | -22.99% | 16944.18 | 10436.72 | -6507.46 | -38.41% | 8828.38 | 8694.26 | -134.12 | -1.519% | 2088.21 | 1382 | -706.21 | -33.82% | 4107 | 4106.6 | -0.4 | -0.009739% | 92.27 | 68 | -24.27 | -26.3% | 2021-11-17 01:00
Barrie | 2022 | 641116 | 641116 - 130 VESPRA ST/BAR/UP/3PH PAD | 95 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 80022.67 | 71633.97 | -8388.7 | -10.48% | 22314.78 | 17566.34 | -4748.44 | -21.28% | 42490.66 | 39578.53 | -2912.13 | -6.854% | 3653.23 | 2797.5 | -855.73 | -23.42% | 11564 | 11691.6 | 127.6 | 1.103% | 136 | 80.5 | -55.5 | -40.81% | 2022-09-16 01:00
Barrie | 2022 | 641204 | 311 SAUNDERS RD/BAR/SR/3 PHASE PAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-31 01:00
Barrie | 2022 | 641296 | 641296 - HWY 400 CROSSING, SUNNIDALE ROAD | 99 | COMPLETE | Estimate incorrect | Material Req incorrectly | Estimate incorrect | Corriveau, Tom N | No | Battistella, Alexander | Dan Kish | 105555.46 | 51711.25 | -53844.21 | -51.01% | 54914.03 | 28023.74 | -26890.29 | -48.97% | 12494.75 | 7410.52 | -5084.23 | -40.69% | 9728.68 | 5706.5 | -4022.18 | -41.34% | 28418 | 10570.49 | -17847.51 | -62.8% | 160.24 | 186 | 25.76 | 16.08% | 2022-07-22 01:00
Barrie | 2021 | 641345 | 641345 - 400 HURONIA RD/BAR/UP/CUSTOMER OWNED STATION | 99 | COMPLETE | BOM not accurate | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 12773.59 | 8837.18 | -3936.41 | -30.82% | 10632 | 8517.68 | -2114.32 | -19.89% | 6409.59 | 0 | -6409.59 | -100% | 732 | 319.5 | -412.5 | -56.35% | 0 | 0 | 0 |  | 24 | 20.5 | -3.5 | -14.58% | 2021-11-03 01:00
Barrie | 2022 | 641366 | 641366 - 4795 CW LEACH RD/ALL/NS/3PH PAD | 99 | COMPLETE | BOM not accurate | Labour est. under | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 81441.49 | 104839.71 | 23398.22 | 28.73% | 19270.49 | 14663.56 | -4606.93 | -23.91% | 33195.55 | 56782.39 | 23586.84 | 71.05% | 2103.45 | 1734.5 | -368.95 | -17.54% | 26872 | 31659.26 | 4787.26 | 17.82% | 110.26 | 67.5 | -42.76 | -38.78% | 2022-08-26 01:00
Barrie | 2021 | 641406 | 641406 - JOINT USE PERMIT HE2021-050 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 5801.62 | 2885.37 | -2916.25 | -50.27% | 2686.54 | 987.07 | -1699.47 | -63.26% | 899.8 | 48.3 | -851.5 | -94.63% | 217.28 | 0 | -217.28 | -100% | 1998 | 1850 | -148 | -7.407% | 6.72 | 0 | -6.72 | -100% | 2021-12-01 01:00
Barrie | 2022 | 641469 | 641469 - JOINT USE PERMIT HE2021-049 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 9407.64 | 5701.92 | -3705.72 | -39.39% | 4273.14 | 2432.34 | -1840.8 | -43.08% | 1092.57 | 295.58 | -796.99 | -72.95% | 491.93 | 424 | -67.93 | -13.81% | 3550 | 2550 | -1000 | -28.17% | 15.97 | 16 | 0.03 | 0.1879% | 2022-02-15 01:00
Barrie | 2022 | 641533 | 641533 - JOINT USE PERMIT HE2021-054- CHURCHILL DR. & ELLIS DR. | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Dan Kish | 11211.32 | 8606.97 | -2604.35 | -23.23% | 3453.04 | 2101.9 | -1351.14 | -39.13% | 721.67 | 171.07 | -550.6 | -76.3% | 246.61 | 394 | 147.39 | 59.77% | 6790 | 5940 | -850 | -12.52% | 8.81 | 12 | 3.19 | 36.21% | 2022-03-30
Barrie | 2022 | 641562 | 641562 - 317 SAUNDERS RD/BAR/NS/3 PHASE PAD | 95 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 75438.84 | 95191.4 | 19752.56 | 26.18% | 22596.61 | 15194.23 | -7402.38 | -32.76% | 47038.94 | 52594.74 | 5555.8 | 11.81% | 2334.29 | 2158.5 | -175.79 | -7.531% | 25819 | 25243.93 | -575.07 | -2.227% | 120.62 | 122.5 | 1.88 | 1.559% | 2022-12-02 01:00
Barrie | 2022 | 641639 | 641639 - GUNN STREET/PEEL STREET POLE RELOCATION - ROAD WIDENING | 99 | COMPLETE | Labour est. over | N/A | N/A | Corriveau, Tom N | No | Harrington, James | Jeremy Wright | 63898.08 | 48882.15 | -15015.93 | -23.5% | 38254.19 | 27707.03 | -10547.16 | -27.57% | 11925.26 | 10214.13 | -1711.13 | -14.35% | 7778.63 | 7430.5 | -348.13 | -4.475% | 5940 | 3530.49 | -2409.51 | -40.56% | 211.31 | 216.5 | 5.19 | 2.456% | 2022-02-07 01:00
Barrie | 2021 | 641673 | 641673 - JOINT USE PERMIT HE2021-056 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 6662.69 | 4328.68 | -2334.01 | -35.03% | 3003.2 | 1024.68 | -1978.52 | -65.88% | 310.85 | 0 | -310.85 | -100% | 198.64 | 154 | -44.64 | -22.47% | 3150 | 3150 | 0 | 0% | 7.36 | 5 | -2.36 | -32.07% | 2021-10-13 01:00
Barrie | 2021 | 641884 | 641884 - JOINT USE PERMIT HE2021-063 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 6662.69 | 4240.98 | -2421.71 | -36.35% | 3003.2 | 1000.98 | -2002.22 | -66.67% | 310.85 | 0 | -310.85 | -100% | 198.64 | 90 | -108.64 | -54.69% | 3150 | 3150 | 0 | 0% | 7.36 | 4 | -3.36 | -45.65% | 2021-10-14 01:00
Barrie | 2022 | 641920 | 641920 - 2022 SWGR REPLACEMENT - SC4627 - BARRIE - 2 VICTORIA ST. | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 26398.56 | 24470.05 | -1928.51 | -7.305% | 5098.68 | 3149.25 | -1949.43 | -38.23% | 20500.08 | 20321.82 | -178.26 | -0.8696% | 799.8 | 596 | -203.8 | -25.48% | 0 | 402.98 | 402.98 |  | 23.48 | 16 | -7.48 | -31.86% | 2022-01-14 01:00
Barrie | 2022 | 641921 | 641921 - 2022 SWGR REPLACEMENT - SC13220 - BARRIE - 33 CLOUGHLEY DR. | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 27427.67 | 29039.21 | 1611.54 | 5.876% | 5881.94 | 5865.22 | -16.72 | -0.2843% | 20745.93 | 22612.99 | 1867.06 | 9% | 799.8 | 561 | -238.8 | -29.86% | 0 | 0 | 0 |  | 23.48 | 29 | 5.52 | 23.51% | 2022-09-02 01:00
Barrie | 2022 | 641924 | 641924 - 2022 SWGR REPLACEMENT - SC4450 - BARRIE - 160 BURNS CIRCLE | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 31361.74 | 29807.47 | -1554.27 | -4.956% | 10875.37 | 7449.54 | -3425.83 | -31.5% | 19686.57 | 21541.93 | 1855.36 | 9.424% | 799.8 | 816 | 16.2 | 2.026% | 0 | 0 | 0 |  | 23.48 | 24 | 0.52 | 2.215% | 2022-09-23 01:00
Barrie | 2022 | 641925 | 641925 - 2022 SWGR REPLACEMENT - SC13536 - BARRIE - 75 HANMER ST. EAST | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 143155.91 | 147144.73 | 3988.82 | 2.786% | 23781.69 | 16504.18 | -7277.51 | -30.6% | 105148.84 | 106610.82 | 1461.98 | 1.39% | 4200.38 | 2830 | -1370.38 | -32.63% | 10025 | 21199.73 | 11174.73 | 111.5% | 176.66 | 121.5 | -55.16 | -31.22% | 2022-06-29 01:00
Barrie | 2022 | 641938 | 641938 - 2022 DISTRIBUTION AUTOMATION - BARRIE - FAIRVIEW RD. | 99 | COMPLETE | BOM not accurate | Labour est. over | Cont Est Over | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 194179.67 | 140880.44 | -53299.23 | -27.45% | 51992.63 | 31051.39 | -20941.24 | -40.28% | 105718.02 | 86136.52 | -19581.5 | -18.52% | 11969.02 | 6814.5 | -5154.52 | -43.07% | 24500 | 16878.03 | -7621.97 | -31.11% | 400.25 | 316 | -84.25 | -21.05% | 2022-03-30
Barrie | 2022 | 641939 | 641939 - 2022 DISTRIBUTION AUTOMATION - BARRIE - WELLINGTON ST. EAST OF BAYFIELD | 99 | COMPLETE | Labour est. over | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 249636.46 | 178571.88 | -71064.58 | -28.47% | 94187.11 | 46705.18 | -47481.93 | -50.41% | 96142.8 | 93392.27 | -2750.53 | -2.861% | 22806.55 | 14751.5 | -8055.05 | -35.32% | 36500 | 23722.93 | -12777.07 | -35.01% | 732.74 | 482.5 | -250.24 | -34.15% | 2022-06-21 01:00
Barrie | 2022 | 641940 | 641940 - 2022 DISTRIBUTION AUTOMATION - BARRIE - BAYVIEW & BALDWIN | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 226073.89 | 192131.55 | -33942.34 | -15.01% | 80088.17 | 47228.48 | -32859.69 | -41.03% | 95667.1 | 96786.4 | 1119.3 | 1.17% | 19818.62 | 15728.5 | -4090.12 | -20.64% | 30500 | 32388.17 | 1888.17 | 6.191% | 633.18 | 539 | -94.18 | -14.87% | 2022-03-30
Barrie | 2021 | 642039 | 642039 - 20 ST. PAUL'S CRESCENT/BAR/NS/3PH | 99 | COMPLETE | BOM not accurate | Labour est. over | N/A | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 17321.01 | 6067.46 | -11253.55 | -64.97% | 11101.85 | 4703.68 | -6398.17 | -57.63% | 6996.33 | 902.28 | -6094.05 | -87.1% | 1222.83 | 461.5 | -761.33 | -62.26% | 0 | 0 | 0 |  | 59.02 | 34 | -25.02 | -42.39% | 2021-09-07 01:00
Barrie | 2021 | 642057 | 642057 - JOINT USE PERMIT HE2021-071 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Steve Rumble | 8067.47 | 6215.05 | -1852.42 | -22.96% | 2364.75 | 2216.05 | -148.7 | -6.288% | 271.09 | 0 | -271.09 | -100% | 121.63 | 189 | 67.37 | 55.39% | 5310 | 3810 | -1500 | -28.25% | 4.37 | 6 | 1.63 | 37.3% | 2021-10-20 01:00
Barrie | 2022 | 642073 | 642073 - 829 ESSA RD - SUBD RES EDS - NET ZERO SUBDIVISION | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 131739.8 | 130130.82 | -1608.98 | -1.221% | 26757.08 | 25162.91 | -1594.17 | -5.958% | 1074.14 | 2940.11 | 1865.97 | 173.7% | 1271.58 | 1569.5 | 297.92 | 23.43% | 102637 | 99464.65 | -3172.35 | -3.091% | 84.66 | 77.5 | -7.16 | -8.457% | 2022-05-05
Barrie | 2021 | 642083 | 642083 - 55 DUNLOP ST W/BAR/SR/3PH PAD | 99 | COMPLETE | BOM not accurate | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 19311.71 | 9003.83 | -10307.88 | -53.38% | 8798.29 | 5335.33 | -3462.96 | -39.36% | 6409.59 | 0 | -6409.59 | -100% | 551.71 | 379.5 | -172.21 | -31.21% | 3552.12 | 3289 | -263.12 | -7.407% | 16 | 13 | -3 | -18.75% | 2021-09-20 01:00
Barrie | 2021 | 642098 | 642098 - 65 WELHAM RD/BAR/SR/3PH PAD | 99 | COMPLETE | BOM not accurate | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 17632.41 | 9251.14 | -8381.27 | -47.53% | 6542.14 | 5348.64 | -1193.5 | -18.24% | 6409.59 | 0 | -6409.59 | -100% | 527 | 499.5 | -27.5 | -5.218% | 4153.68 | 3403 | -750.68 | -18.07% | 18.2 | 9 | -9.2 | -50.55% | 2021-08-09 01:00
Barrie | 2022 | 642099 | 642099 - QUEEN'S PARK (WELLINGTON D1 CITY PROJECT), BARRIE - RELOCATE POLES FOR RD WORKS | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Pelleja, Emily | No | Harrington, James | Dan Kish | 241527.09 | 138791.88 | -102735.21 | -42.54% | 129177.17 | 70698.5 | -58478.67 | -45.27% | 43705.89 | 31989.69 | -11716.2 | -26.81% | 26926.53 | 17151 | -9775.53 | -36.3% | 41717.5 | 18952.69 | -22764.81 | -54.57% | 767.59 | 561 | -206.59 | -26.91% | 2022-05-25 01:00
Barrie | 2022 | 642116 | 642116 - 65 WELHAM RD/BAR/NS/3PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 68656.59 | 55172.22 | -13484.37 | -19.64% | 22943.7 | 13909.36 | -9034.34 | -39.38% | 26405.91 | 24584.61 | -1821.3 | -6.897% | 3192.98 | 2434 | -758.98 | -23.77% | 16114 | 14244.25 | -1869.75 | -11.6% | 128.87 | 64 | -64.87 | -50.34% | 2022-09-19 01:00
Barrie | 2022 | 642232 | 642232 - 2022 PDMT TX REPLACEMENT BATCH 1 - BARRIE - 18X 1PH TX'S | 99 | COMPLETE | Cont Est Under | BOM not accurate | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 145935.49 | 240815.3 | 94879.81 | 65.01% | 40621.79 | 43193.33 | 2571.54 | 6.33% | 97893.53 | 111744.56 | 13851.03 | 14.15% | 7420.17 | 9016.53 | 1596.36 | 21.51% | 0 | 76860.88 | 76860.88 |  | 216.12 | 301.5 | 85.38 | 39.51% | 2022-09-27 01:00
Barrie | 2022 | 642238 | 642238 - 2022 PDMT TX REPLACEMENT BATCH 2 - NEW TECH - 19X 1PH TX'S | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 190598.24 | 182353.63 | -8244.61 | -4.326% | 51787.21 | 32324.28 | -19462.93 | -37.58% | 103446.8 | 117587.99 | 14141.19 | 13.67% | 9364.23 | 9273.56 | -90.67 | -0.9683% | 26000 | 23167.8 | -2832.2 | -10.89% | 276.63 | 265 | -11.63 | -4.204% | 2022-10-24 01:00
Barrie | 2022 | 642239 | 642239 - 2022 PDMT TX REPLACEMENT BATCH 3 - BARRIE - 5X 3PH TX'S | 99 | COMPLETE | BOM not accurate | Labour est. over | Cont Est Over | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 138687.22 | 76775 | -61912.22 | -44.64% | 26186.82 | 10851.12 | -15335.7 | -58.56% | 88371.98 | 57009.21 | -31362.77 | -35.49% | 4128.42 | 1192.07 | -2936.35 | -71.13% | 20000 | 7722.6 | -12277.4 | -61.39% | 120.21 | 64 | -56.21 | -46.76% | 2022-10-19 01:00
Barrie | 2022 | 642240 | 642240 - 2022 PDMT TX REPLACEMENT BATCH 4 - BARRIE - 19X 1PH TX'S | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 186527.08 | 180389.05 | -6138.03 | -3.291% | 44161.21 | 29567.37 | -14593.84 | -33.05% | 107001.64 | 110240.52 | 3238.88 | 3.027% | 9364.23 | 8334.76 | -1029.47 | -10.99% | 26000 | 32246.4 | 6246.4 | 24.02% | 276.63 | 254 | -22.63 | -8.181% | 2022-09-29 01:00
Barrie | 2022 | 642242 | 642242 - 2022 PDMT TX REPLACEMENT BATCH 5 - BARRIE - 17X 1PH TX'S | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 127955.6 | 117819.68 | -10135.92 | -7.921% | 32576.84 | 19181.34 | -13395.5 | -41.12% | 88506.42 | 92644.73 | 4138.31 | 4.676% | 6872.34 | 5993.61 | -878.73 | -12.79% | 0 | 0 | 0 |  | 200.13 | 196.5 | -3.63 | -1.814% | 2022-07-15 01:00
Barrie | 2022 | 642269 | 642269 - DIXON COURT - SUBD CAP | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Perks, Dan | Lotto, Jay | 55099.9 | 52853.03 | -2246.87 | -4.078% | 11975.9 | 9668.96 | -2306.94 | -19.26% | 0 | 0 | 0 |  | 576 | 636 | 60 | 10.42% | 42548 | 42548.07 | 0.07 | 0.0001645% | 36 | 38 | 2 | 5.556% | 2022-04-28
Barrie | 2022 | 642278 | 642278 - 61 THOMPSON RD W/PEN/NS/1 PHASE PAD | 95 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 36772.26 | 31894.14 | -4878.12 | -13.27% | 16963.22 | 14027.31 | -2935.91 | -17.31% | 10780.72 | 6845.48 | -3935.24 | -36.5% | 1649.32 | 1874 | 224.68 | 13.62% | 7379 | 9147.35 | 1768.35 | 23.96% | 81.33 | 96 | 14.67 | 18.04% | 2022-12-20 01:00
Barrie | 2022 | 642308 | 642308 - 2022 POLE REPLACEMENTS BARRIE BATCH 1 EUGENIA | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated | N/A | Bowman, Todd J | Yes | Pollock, Kim | Jeremy Wright | 160512.81 | 232324.46 | 71811.65 | 44.74% | 57402.09 | 104191.59 | 46789.5 | 81.51% | 42427.13 | 41365.23 | -1061.9 | -2.503% | 16083.59 | 40369.5 | 24285.91 | 151% | 44600 | 46398.14 | 1798.14 | 4.032% | 496.05 | 1012 | 515.95 | 104% | 2022-04-20
Barrie | 2022 | 642309 | 642309 - 2022 POLE REPLACEMENTS BARRIE BATCH 2 CLAPPERTON ST | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated | Cont Est Under | Bowman, Todd J | Yes | Pollock, Kim | Jeremy Wright | 217138.44 | 256185.14 | 39046.7 | 17.98% | 89542.36 | 103922.28 | 14379.92 | 16.06% | 53357.93 | 52952.58 | -405.35 | -0.7597% | 25238.15 | 41770.5 | 16532.35 | 65.51% | 49000 | 57539.78 | 8539.78 | 17.43% | 788.33 | 1183.5 | 395.17 | 50.13% | 2022-04-20
Barrie | 2022 | 642371 | 468 SIMCOE ROAD, BRADFORD | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | East Coordinator | 0 | 603.46 | 603.46 |  | 0 | 603.46 | 603.46 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-24 01:00
Barrie | 2021 | 642413 | 642413 - HIGH ST POLE RELOCATION - POLE RELOCATION FOR CITY SIDEWALK, CITY INITIATED | 99 | COMPLETE | Labour est. over | N/A | N/A | Corriveau, Tom N | No | Harrington, James | Dan Kish | 41219.67 | 21196.72 | -20022.95 | -48.58% | 27738.2 | 11401.75 | -16336.45 | -58.9% | 3579.15 | 2562.97 | -1016.18 | -28.39% | 5062.32 | 3632 | -1430.32 | -28.25% | 4840 | 3600 | -1240 | -25.62% | 208.98 | 102.5 | -106.48 | -50.95% | 2021-10-22 01:00
Barrie | 2021 | 642414 | ECCLES ST N, BARRIE - STUB POLE INSTALLATION FOR CITY OF BARRIE INITIATED WORK | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Harrington, James | East Coordinator | 0 | 1920.23 | 1920.23 |  | 0 | 1920.23 | 1920.23 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-29 01:00
Barrie | 2022 | 642472 | 642472 - 447 BAYVIEW DRIVE/BAR/NS/3PH PAD | 95 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 72562.49 | 49994.22 | -22568.27 | -31.1% | 22299.28 | 10360.85 | -11938.43 | -53.54% | 42271.77 | 32851.07 | -9420.7 | -22.29% | 2468.44 | 1259.5 | -1208.94 | -48.98% | 5523 | 5522.8 | -0.2 | -0.003621% | 123.87 | 64 | -59.87 | -48.33% | 2022-06-08 01:00
Barrie | 2022 | 642474 | 642474 - 2022 SWITCH RENEWAL - ALLISTON - 44KV AUTOMATED LIS - AB-B1027 | 99 | COMPLETE | Labour est. over | Cont Est Over |  | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 224612.2 | 191566.3 | -33045.9 | -14.71% | 76722.8 | 59418.64 | -17304.16 | -22.55% | 103957.03 | 103648.63 | -308.4 | -0.2967% | 18657.37 | 16112.94 | -2544.43 | -13.64% | 25275 | 12386.09 | -12888.91 | -50.99% | 501.23 | 502 | 0.77 | 0.1536% | 2023-01-05 01:00
Barrie | 2022 | 642475 | 642475 - 2022 SWITCH RENEWAL - BRADFORD- 194 SIMCOE RD. - 13.8KV AUTOMATED LIS - AB-13800 | 99 | COMPLETE | Estimate incorrect | Cont Est Over |  | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 164111.95 | 152368.46 | -11743.49 | -7.156% | 69870.56 | 58819.46 | -11051.1 | -15.82% | 67598.36 | 69034.64 | 1436.28 | 2.125% | 14643.03 | 18653.28 | 4010.25 | 27.39% | 12000 | 5861.08 | -6138.92 | -51.16% | 400.19 | 447 | 46.81 | 11.7% | 2022-08-03 01:00
Barrie | 2022 | 642477 | 642477 - 2022 SWITCH RENEWAL -BRADFORD- 226 BARRIE ST.- 13.8KV AUTOMATED LIS - AB-13743 | 99 | COMPLETE | Under 10% |  |  | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 142588.15 | 135197.4 | -7390.75 | -5.183% | 44817.42 | 35350.28 | -9467.14 | -21.12% | 57502.38 | 60666.37 | 3163.99 | 5.502% | 10698.35 | 9969.17 | -729.18 | -6.816% | 29570 | 29211.58 | -358.42 | -1.212% | 300.11 | 296.5 | -3.61 | -1.203% | 2022-09-16 01:00
Barrie | 2022 | 642481 | 642481 - 2022 SWITCH RENEWAL -BRADFORD- 43 CHURCH ST. - 13.8KV AUTOMATED LIS - AB-13747 | 99 | COMPLETE | Labour est. over | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 144064.79 | 104026.51 | -40038.28 | -27.79% | 55739.46 | 28445.3 | -27294.16 | -48.97% | 59221.66 | 60550.72 | 1329.06 | 2.244% | 14534.67 | 6563 | -7971.67 | -54.85% | 14569 | 8467.49 | -6101.51 | -41.88% | 400.96 | 280 | -120.96 | -30.17% | 2022-10-26 01:00
Barrie | 2022 | 642483 | 642483 - 2022 SWITCH RENEWAL - BRADFORD- 380 WALKER RD. - 13.8KV AUTOMATED LIS - AB-13804 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 105226.1 | 104831.71 | -394.39 | -0.3748% | 36767.71 | 35291.35 | -1476.36 | -4.015% | 57434.15 | 58862.36 | 1428.21 | 2.487% | 7024.24 | 8594.5 | 1570.26 | 22.35% | 4000 | 2083.5 | -1916.5 | -47.91% | 200.4 | 309.5 | 109.1 | 54.44% | 2022-09-12 01:00
Barrie | 2022 | 642484 | 642484 - 2022 SWITCH RENEWAL - BRADFORD- EDWARD ST.- 13.8KV AUTOMATED LIS - AB-13783 | 99 | COMPLETE | Labour est. over | N/A | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 181886.48 | 140474.47 | -41412.01 | -22.77% | 83339.22 | 49238.54 | -34100.68 | -40.92% | 72098.63 | 70513.68 | -1584.95 | -2.198% | 18448.63 | 13629.5 | -4819.13 | -26.12% | 8000 | 7092.75 | -907.25 | -11.34% | 501.46 | 389.5 | -111.96 | -22.33% | 2022-10-07 01:00
Barrie | 2022 | 642486 | 642486 - 2022 SWITCH RENEWAL -BRADFORD- 305 BARRIE ST- 13.8KV AUTOMATED LIS - AB-13744 | 99 | COMPLETE | Labour est. over | Cont Est Over |  | Bowman, Todd J | Yes | Walters, Geoffrey D | Dan Kish | 129844.31 | 96390.22 | -33454.09 | -25.76% | 44626.94 | 30081.68 | -14545.26 | -32.59% | 56066.12 | 51496.45 | -4569.67 | -8.151% | 11581.25 | 8839.18 | -2742.07 | -23.68% | 17570 | 5972.91 | -11597.09 | -66.01% | 300.23 | 243 | -57.23 | -19.06% | 2022-11-04 01:00
Barrie | 2021 | 642489 | 642489 - 25 ALBERT ST W/ALL/SR/3PH PAD | 99 | COMPLETE | BOM not accurate | Labour est. over | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 16721.83 | 1859.81 | -14862.02 | -88.88% | 6902.14 | 1731.81 | -5170.33 | -74.91% | 4792.69 | 0 | -4792.69 | -100% | 527 | 128 | -399 | -75.71% | 4500 | 0 | -4500 | -100% | 18.2 | 24 | 5.8 | 31.87% | 2021-10-22 01:00
Barrie | 2022 | 642506 | 642506 - 2022 POLE REPLACEMENTS ALLISTON BATCH 1 EAST AVE | 99 | COMPLETE | Cont Est Under | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 64102.57 | 91922.39 | 27819.82 | 43.4% | 32191.63 | 32285.53 | 93.9 | 0.2917% | 11932.72 | 13442.08 | 1509.36 | 12.65% | 8978.22 | 9925 | 946.78 | 10.55% | 11000 | 36269.78 | 25269.78 | 229.7% | 288.85 | 252 | -36.85 | -12.76% | 2022-01-18 01:00
Barrie | 2022 | 642507 | 642507 - 2022 POLE REPLACEMENTS ALLISTON BATCH 2 ALBERT | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 81377.4 | 78840.05 | -2537.35 | -3.118% | 26742.32 | 39549.24 | 12806.92 | 47.89% | 29840.59 | 16643.81 | -13196.78 | -44.22% | 7594.49 | 8394 | 799.51 | 10.53% | 17200 | 14253 | -2947 | -17.13% | 233.3 | 338 | 104.7 | 44.88% | 2022-02-01 01:00
Barrie | 2022 | 642508 | 642508 - 2022 POLE REPLACEMENTS TOTTENHAM BATCH 1 | 99 | COMPLETE | BOM not accurate | Cont Est Over | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 66983.69 | 48634 | -18349.69 | -27.39% | 22982.07 | 23485.8 | 503.73 | 2.192% | 17108.34 | 9259.02 | -7849.32 | -45.88% | 6393.28 | 4490 | -1903.28 | -29.77% | 20500 | 11399.18 | -9100.82 | -44.39% | 196.19 | 176 | -20.19 | -10.29% | 2022-03-11 01:00
Barrie | 2022 | 642509 | 642509 - 2022 POLE REPLACEMENTS BEETON BATCH 1 | 99 | COMPLETE | Estimate incorrect | Estimate incorrect | Material Under Estimated | Obeng, Nana | Yes | Pollock, Kim | Dan Kish | 371425.91 | 331819.87 | -39606.04 | -10.66% | 99802.18 | 52445.12 | -47357.06 | -47.45% | 60445.94 | 73316.35 | 12870.41 | 21.29% | 24901.79 | 42.85 | -24858.94 | -99.83% | 186276 | 206015.55 | 19739.55 | 10.6% | 658.94 | 8 | -650.94 | -98.79% | 2022-12-23 01:00
Barrie | 2022 | 642510 | 642510 - 2022 POLE REPLACEMENTS THORNTON BATCH 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Bowman, Todd J | Yes | Pollock, Kim | Dan Kish | 506909.12 | 467400.87 | -39508.25 | -7.794% | 185156.25 | 158821.21 | -26335.04 | -14.22% | 103935.05 | 114058.1 | 10123.05 | 9.74% | 50637.82 | 52883 | 2245.18 | 4.434% | 167180 | 141638.56 | -25541.44 | -15.28% | 1417.27 | 1750 | 332.73 | 23.48% | 2022-09-27 01:00
Barrie | 2022 | 642511 | 642511 - 2022 POLE REPLACEMENTS BRADFORD BATCH 1 | 99 | COMPLETE | Labour est. under | Cont Est Over |  | Obeng, Nana | Yes | Pollock, Kim | Dan Kish | 205359.91 | 186111.34 | -19248.57 | -9.373% | 84197.86 | 79237.4 | -4960.46 | -5.891% | 51927.52 | 48613.03 | -3314.49 | -6.383% | 25626.53 | 29341.94 | 3715.41 | 14.5% | 43608 | 28918.97 | -14689.03 | -33.68% | 671.06 | 804.5 | 133.44 | 19.88% | 2022-12-21 01:00
Barrie | 2021 | 642758 | 47 GEORGE STREET HYDRO RELOCATION - NEW TECUMSETH | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Murray, Jake R | East Coordinator | 97.91 | 0 | -97.91 | -100% | 97.91 | 0 | -97.91 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-01 01:00
Barrie | 2022 | 642996 | 642996 - 6870 13TH LINE/ALL/NS/3PH PAD | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 66429.1 | 46139.53 | -20289.57 | -30.54% | 19361.53 | 10331.56 | -9029.97 | -46.64% | 36705.06 | 28247.97 | -8457.09 | -23.04% | 2572.51 | 1468.5 | -1104.01 | -42.92% | 7790 | 6091.5 | -1698.5 | -21.8% | 111.22 | 49.5 | -61.72 | -55.49% | 2022-09-05 01:00
Barrie | 2022 | 643084 | 643084 - 691 SIMCOE RD/BRAD/NS/3PH PAD | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 52635.63 | 42604.25 | -10031.38 | -19.06% | 14955.98 | 10181.07 | -4774.91 | -31.93% | 34979.39 | 29892.18 | -5087.21 | -14.54% | 1490.26 | 1321 | -169.26 | -11.36% | 1210 | 1210 | 0 | 0% | 89.28 | 68 | -21.28 | -23.84% | 2022-02-07 01:00
Barrie | 2021 | 643122 | 643122 - 259 INNISFIL ST/BAR/SR/3PH PAD | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 14003.53 | 6684.25 | -7319.28 | -52.27% | 7225.95 | 3530.25 | -3695.7 | -51.14% | 3761.22 | 0 | -3761.22 | -100% | 616.36 | 756 | 139.64 | 22.66% | 2400 | 2398 | -2 | -0.08333% | 22.85 | 17 | -5.85 | -25.6% | 2021-10-19 01:00
Barrie | 2022 | 643356 | 643356 - 2022 EAST NORTH PCB UG TX REPLACEMENT BARRIE | 99 | COMPLETE | Under 10% | N/A | N/A | Obeng, Nana | No | Pollock, Kim | Lotto, Jay | 30769.72 | 31682.44 | 912.72 | 2.966% | 10799.26 | 9361.58 | -1437.68 | -13.31% | 7751.17 | 9404.21 | 1653.04 | 21.33% | 1219.29 | 1173 | -46.29 | -3.796% | 11000 | 11743.65 | 743.65 | 6.76% | 58.81 | 26.5 | -32.31 | -54.94% | 2022-10-27 01:00
Barrie | 2022 | 643359 | 643359 - 2022 EAST NORTH PCB UG TX REPLACEMENT TOTTENHAM | 99 | COMPLETE | Scope change - unforeseen | Labour est. under | Estimate incorrect | Obeng, Nana | No | Pollock, Kim | Lotto, Jay | 21856.19 | 37180.56 | 15324.37 | 70.11% | 4425.38 | 12394.77 | 7969.39 | 180.1% | 7674.02 | 9347.97 | 1673.95 | 21.81% | 656.79 | 1484.1 | 827.31 | 126% | 9100 | 13953.72 | 4853.72 | 53.34% | 29.31 | 36 | 6.69 | 22.82% | 2022-11-17 01:00
Barrie | 2022 | 643414 | 643414 - 10 STEEL ST, BARRIE - POLE RELOCATION - | 98 | COMPLETE | N/A |  | N/A | Corriveau, Tom N | No | Silcock, Jordan | Dan Kish | 49122.57 | 12182.95 | -36939.62 | -75.2% | 15324.34 | 4017.52 | -11306.82 | -73.78% | 10634.15 | 0 | -10634.15 | -100% | 3425.08 | 0 | -3425.08 | -100% | 19739 | 8165.43 | -11573.57 | -58.63% | 78.52 | 3 | -75.52 | -96.18% | 2022-12-19 01:00
Barrie | 2022 | 643512 | 643512 - 100 WILLOUGHBY WAY/ALL/NS/3PH PAD | 99 | ANALYZE |  |  |  | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 54748.82 | 45670.73 | -9078.09 | -16.58% | 16038.46 | 11090.11 | -4948.35 | -30.85% | 35440.02 | 31837.52 | -3602.5 | -10.17% | 1760.34 | 1345 | -415.34 | -23.59% | 1510 | 1398.1 | -111.9 | -7.411% | 89.28 | 65 | -24.28 | -27.2% | 2022-06-17 01:00
Barrie | 2022 | 643513 | 643513 - 118 ST. VINCENT/BAR/UP/1PH PAD | 95 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 45764.25 | 41180.96 | -4583.29 | -10.02% | 15463.41 | 13154.78 | -2308.63 | -14.93% | 14936.43 | 11851.28 | -3085.15 | -20.66% | 1411.41 | 1372 | -39.41 | -2.792% | 13953 | 14802.9 | 849.9 | 6.091% | 58.11 | 44 | -14.11 | -24.28% | 2022-10-17 01:00
Barrie | 2022 | 643532 | 643532 - 783 HURONIA RD/BAR/NS/3 PHASE PAD | 95 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Lotto, Jay | 83014.33 | 59090.34 | -23923.99 | -28.82% | 23635.6 | 12723.19 | -10912.41 | -46.17% | 50388.02 | 38713.25 | -11674.77 | -23.17% | 2899.71 | 1563 | -1336.71 | -46.1% | 6091 | 6090.9 | -0.1 | -0.001642% | 129.42 | 78 | -51.42 | -39.73% | 2022-11-04 01:00
Barrie | 2022 | 643549 | 20 ROSE ST/BAR/SR/3 PHASE SERVICE REMOVAL | 99 | COMPLETE | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | East Coordinator | 11058.76 | 6523.2 | -4535.56 | -41.01% | 8491.39 | 4246.5 | -4244.89 | -49.99% | 255.06 | 0 | -255.06 | -100% | 775.31 | 740 | -35.31 | -4.554% | 1537 | 1536.7 | -0.3 | -0.01952% | 37.41 | 25 | -12.41 | -33.17% | 2021-08-31 01:00
Barrie | 2022 | 643550 | 643550 - 2022 POLE REPLACEMENTS BARRIE BATCH 3 | 99 | COMPLETE | Labour est. over | Cont Est Over |  | Obeng, Nana | Yes | Pollock, Kim | Dan Kish | 522169.89 | 456542.92 | -65626.97 | -12.57% | 223583.73 | 155496.23 | -68087.5 | -30.45% | 142636.18 | 150017.29 | 7381.11 | 5.175% | 60549.98 | 56448.71 | -4101.27 | -6.773% | 95400 | 94580.69 | -819.31 | -0.8588% | 1669.76 | 1505.5 | -164.26 | -9.837% | 2022-12-21 01:00
Barrie | 2022 | 643582 | 236 DUNLOP ST, W/BAR/UP/1 PHASE PAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-04-22
Barrie | 2022 | 644771 | 644771 - 304 DUNLOP ST W/BAR/SR/3PH PAD | 99 | COMPLETE | BOM not accurate | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 17562.93 | 9546.74 | -8016.19 | -45.64% | 7280.44 | 7773.74 | 493.3 | 6.776% | 6778.33 | 0 | -6778.33 | -100% | 618.16 | 585 | -33.16 | -5.364% | 2886 | 1188 | -1698 | -58.84% | 18.2 | 9 | -9.2 | -50.55% | 2022-07-23 01:00
Barrie | 2022 | 645488 | 645488 - 2022 VAULT LID RENEWAL PROGRAM - V23 - 37 MULCASTER ST | 95 | ANALYZE |  |  |  | Bowman, Todd J | Yes | Walters, Geoffrey D | Lotto, Jay | 251816.67 | 273345.78 | 21529.11 | 8.55% | 57105.39 | 45583.32 | -11522.07 | -20.18% | 8861.28 | 14831.82 | 5970.54 | 67.38% | 4260 | 2726.86 | -1533.14 | -35.99% | 181590 | 210203.78 | 28613.78 | 15.76% | 240 | 107.5 | -132.5 | -55.21% | 2022-11-25 01:00
Barrie | 2022 | 647541 | 647541 - 2023 SWGR REPLACEMENT - SC13530 - 52 CUMMING DR. - BARRIE | 95 | ANALYZE |  |  |  | Obeng, Nana | No | Walters, Geoffrey D | Lotto, Jay | 20242.09 | 17454.82 | -2787.27 | -13.77% | 5552.51 | 4591.65 | -960.86 | -17.3% | 3769.81 | 1622.2 | -2147.61 | -56.97% | 598.77 | 920.23 | 321.46 | 53.69% | 10321 | 10320.74 | -0.26 | -0.002519% | 24.22 | 30 | 5.78 | 23.86% | 2022-10-26 01:00
Barrie | 2022 | 648303 | 93 BRADFORD ST/BAR/SR/3PH PAD | 98 | ANALYZE |  |  |  | Cranley, Stephen | No | Paterson, Greg | Lotto, Jay | 11808.28 | 10469.5 | -1338.78 | -11.34% | 7390.12 | 6284.8 | -1105.32 | -14.96% | 0 | 0 | 0 |  | 618.16 | 384 | -234.16 | -37.88% | 3800 | 3800.7 | 0.7 | 0.01842% | 18.2 | 16 | -2.2 | -12.09% | 2022-12-29 01:00
Brampton | 2020 | 450067 | Various Locations Brampton 2019 - Part 1 - 1ph pad replacement | 99 | COMPLETE | Est. Int. - Act. External | Scope change - unforeseen | N/A | Missing Converted Employee for WO | Yes tx. | Alectra Utilities | John Costa | 96993.43 | 68146.5 | -28846.93 | -29.74% | 39536.99 | 2064.92 | -37472.07 | -94.78% | 51216.44 | 46469.08 | -4747.36 | -9.269% | 6240 | 0 | -6240 | -100% | 0 | 15364.42 | 15364.42 |  | 16 | 2 | -14 | -87.5% | 2020-12-11 01:00
Brampton | 2019 | 450072 | Chinguacousy Park Primary Dist Loop | 99 | COMPLETE | Converted Project | N/A | N/A | Luimes, John | No | Miller, Michael | Richard Cuddy | 314723.25 | 315549.35 | 826.1 | 0.2625% | 55479.1 | 23431.53 | -32047.57 | -57.77% | 23605 | 25403.59 | 1798.59 | 7.62% | 7777 | 0 | -7777 | -100% | 227862.15 | 203895.7 | -23966.45 | -10.52% | 629 | 601.25 | -27.75 | -4.412% | 2019-07-06 01:00
Brampton | 2022 | 450081 | ETR 407- TORBRAM RD | 99 | CANCELLED | N/A |  |  | Tobin, Michael | No | Chopra, Rabinder | Weaver, Thomas | 0 | 32450.27 | 32450.27 |  | 0 | 13671.91 | 13671.91 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6724 | 6724 |  | 0 | 16 | 16 |  | 2019-10-01 01:00
Brampton | 2021 | 450082 | THE GORE RD & COUNTRYSIDE DR | 99 | CANCELLED | N/A |  |  | Norman, Greg | No | Erzek, Ryan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-01 01:00
Brampton | 2022 | 450083 | STEELES AVE E-ADVANCE BLVD | 99 | CANCELLED | N/A |  |  | Tobin, Michael | No | Chopra, Rabinder | Weaver, Thomas | 0 | 33967.48 | 33967.48 |  | 0 | 6069.06 | 6069.06 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14000.18 | 14000.18 |  | 0 | 38.5 | 38.5 |  | 2019-10-01 01:00
Brampton | 2019 | 450086 | 71 Orenda Rd - Switch Replacement - #3 | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Casey, Ryan | Reaburn, Jeff | 127297.59 | 91249.2 | -36048.39 | -28.32% | 37832.76 | 20842.69 | -16990.07 | -44.91% | 78130.83 | 56337.34 | -21793.49 | -27.89% | 7934 | 4397 | -3537 | -44.58% | 3400 | 2275 | -1125 | -33.09% | 398.5 | 351 | -47.5 | -11.92% | 2019-10-01 01:00
Brampton | 2019 | 450088 | SW WILLIAMS PKY W MCLAUGHLIN - Switch Replacement #4 | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Casey, Ryan | Reaburn, Jeff | 132124.12 | 125951.45 | -6172.67 | -4.672% | 39050 | 39192.93 | 142.93 | 0.366% | 81452.12 | 52411.94 | -29040.18 | -35.65% | 8222 | 5996 | -2226 | -27.07% | 3400 | 13267.3 | 9867.3 | 290.2% | 390.5 | 642.25 | 251.75 | 64.47% | 2019-10-01 01:00
Brampton | 2019 | 450094 | 339 QUEEN ST W Switch Replacement #1 | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Casey, Ryan | Reaburn, Jeff | 146575.11 | 124960.66 | -21614.45 | -14.75% | 58187.01 | 42596.98 | -15590.03 | -26.79% | 73500 | 54070.95 | -19429.05 | -26.43% | 8666.6 | 14346 | 5679.4 | 65.53% | 6221.5 | 3725 | -2496.5 | -40.13% | 436 | 662.25 | 226.25 | 51.89% | 2019-11-15 01:00
Brampton | 2022 | 450097 | Highway 410 & Williams Pkwy | 99 | CANCELLED | N/A |  |  | Weaver, Thomas | No | Robinson, David | Weaver, Thomas | 0 | 19536.16 | 19536.16 |  | 0 | 487.38 | 487.38 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13598.93 | 13598.93 |  | 0 | 1.5 | 1.5 |  | 2019-10-01 01:00
Brampton | 2019 | 450102 | MAYFIELD RD | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Robinson, David | Nichol, Sandi | 38000 | 52825.6 | 14825.6 | 39.01% | 4000 | 3142.42 | -857.58 | -21.44% | 6000 | 5628.69 | -371.31 | -6.189% | 3000 | 0 | -3000 | -100% | 25000 | 28938.45 | 3938.45 | 15.75% | 0 | 58.5 | 58.5 |  | 2019-10-01 01:00
Brampton | 2019 | 450108 | INSULATOR REPLACMENT 2019 | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Casey, Ryan | John Costa | 317091.7 | 265119.11 | -51972.59 | -16.39% | 258315.54 | 111392.74 | -146922.8 | -56.88% | 58733.16 | 64874.87 | 6141.71 | 10.46% | 43 | 36016 | 35973 | 83658% | 0 | 408 | 408 |  | 2075 | 1653.65 | -421.35 | -20.31% | 2019-12-21 01:00
Brampton | 2022 | 450115 | 7995 KENNEDY RD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-20 01:00
Brampton | 2021 | 450136 | EMERY BRAM. HEARTLAKE - SUBD ICI EDS | 99 | COMPLETE | Labour est. over | Vac truck |  | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 185954.33 | 552531.45 | 366577.12 | 197.1% | 105667.82 | 47762.87 | -57904.95 | -54.8% | 49554.51 | 53831.17 | 4276.66 | 8.63% | 30732 | 12888 | -17844 | -58.06% | 0 | 7202.15 | 7202.15 |  | 830 | 536.25 | -293.75 | -35.39% | 2021-08-20 01:00
Brampton | 2020 | 450138 | ELIZABETH ST S AND ELLIOT ST | 99 | CANCELLED | N/A |  |  | Weaver, Thomas | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-19 01:00
Brampton | 2019 | 450141 | MS10 S/G Shoppers World Area Backup | 99 | COMPLETE | Converted Project | N/A | N/A | Luimes, John | No | Alectra Utilities | Richard Cuddy | 239015.65 | 263647.68 | 24632.03 | 10.31% | 24373.16 | 57856.91 | 33483.75 | 137.4% | 116978.4 | 119127.28 | 2148.88 | 1.837% | 1693.5 | 6623 | 4929.5 | 291.1% | 95970.59 | 46129.66 | -49840.93 | -51.93% | 666 | 799.75 | 133.75 | 20.08% | 2019-12-19 01:00
Brampton | 2020 | 450152 | C.V. Employment Ph 2 | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 226721.18 | 939382.49 | 712661.31 | 314.3% | 120591.59 | 61989.73 | -58601.86 | -48.6% | 45389.59 | 49801.95 | 4412.36 | 9.721% | 60740 | 23632.71 | -37107.29 | -61.09% | 0 | 5721.57 | 5721.57 |  | 926 | 695.25 | -230.75 | -24.92% | 2020-11-24 01:00
Brampton | 2019 | 450164 | 200 EDGEWARE RD | 95 | COMPLETE | Converted Project | N/A | N/A | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 89810 | 82610.27 | -7199.73 | -8.017% | 30000 | 16718.49 | -13281.51 | -44.27% | 33993 | 40550.49 | 6557.49 | 19.29% | 5610 | 1047 | -4563 | -81.34% | 20207 | 20304.52 | 97.52 | 0.4826% | 296 | 210 | -86 | -29.05% | 2019-12-10 01:00
Brampton | 2022 | 450165 | BRAMALEA RD-ETR 407 | 99 | CANCELLED | N/A |  |  | Tobin, Michael | No | Chopra, Rabinder | Weaver, Thomas | 0 | 30874.93 | 30874.93 |  | 0 | 3062.39 | 3062.39 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12342.16 | 12342.16 |  | 0 | 0 | 0 |  | 2020-02-11 00:59
Brampton | 2020 | 450170 | 3389 STEELES AVENUE EAST | 98 | COMPLETE | Converted Project | N/A | N/A | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 53782.62 | 46908.06 | -6874.56 | -12.78% | 19246.84 | 6250.46 | -12996.38 | -67.52% | 31259.78 | 35006.33 | 3746.55 | 11.99% | 3276 | 2146.12 | -1129.88 | -34.49% | 0 | 2552.84 | 2552.84 |  | 138 | 80 | -58 | -42.03% | 2020-02-11 00:59
Brampton | 2022 | 450186 | SUN PAC BLVD BLOCK 1, 2 & 3 | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 1327.43 | 1327.43 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-16 01:00
Brampton | 2020 | 450192 | 525 MAIN ST N - Senior Care | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 95225.82 | 118757.5 | 23531.68 | 24.71% | 23650.16 | 34551.55 | 10901.39 | 46.09% | 35995.06 | 38852.11 | 2857.05 | 7.937% | 0 | 6140.57 | 6140.57 |  | 35580.6 | 34744.18 | -836.42 | -2.351% | 174 | 381 | 207 | 119% | 2020-06-16 01:00
Brampton | 2019 | 450193 | VARIOUS LOCATIONS-BRAMPTON - Phase 2 UG Portion | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Nichol, Sandi | 150698.11 | 155720.32 | 5022.21 | 3.333% | 87479.32 | 16063 | -71416.32 | -81.64% | 38277.14 | 39690.96 | 1413.82 | 3.694% | 14441 | 513 | -13928 | -96.45% | 10500.65 | 73679.12 | 63178.47 | 601.7% | 876 | 82.5 | -793.5 | -90.58% | 2019-11-27 01:00
Brampton | 2019 | 450194 | Torbram Rd - 2019 OH Portion | 99 | COMPLETE | Cont Est Over | BOM not accurate | N/A |  | CC | Miller, Michael | Nichol, Sandi | 635143 | 1001525.96 | 366382.96 | 57.69% | 10650.8 | 23.49 | -10627.31 | -99.78% | 153593.8 | 177366.13 | 23772.33 | 15.48% | 2500 | 529 | -1971 | -78.84% | 468398.4 | 405005.25 | -63393.15 | -13.53% | 119 | 118.75 | -0.25 | -0.2101% | 2019-04-06 01:00
Brampton | 2020 | 450195 | QUEEN ST. E. & THE GORE RD. | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 282401.72 | 195994.57 | -86407.15 | -30.6% | 36096.96 | 20700.33 | -15396.63 | -42.65% | 11412.68 | 11992.23 | 579.55 | 5.078% | 1638 | 3695.3 | 2057.3 | 125.6% | 233254.08 | 135.8 | -233118.28 | -99.94% | 305 | 218.75 | -86.25 | -28.28% | 2020-07-08 01:00
Brampton | 2019 | 450196 | BOVAIRD DR & HWY 410 - 2019 Viper SW #5 | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | D'Ermes, Michael | Reaburn, Jeff | 95000 | 132265.6 | 37265.6 | 39.23% | 45000 | 11002.43 | -33997.57 | -75.55% | 50000 | 61575.26 | 11575.26 | 23.15% | 0 | 636 | 636 |  | 0 | 53691.62 | 53691.62 |  | 408 | 87.5 | -320.5 | -78.55% | 2019-12-05 01:00
Brampton | 2019 | 450198 | KENNEDY RD N, S OF BOVAIRD DR - 2019 Viper SW #6 | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | D'Ermes, Michael | Reaburn, Jeff | 95000 | 101327 | 6327 | 6.66% | 45000 | 26654 | -18346 | -40.77% | 50000 | 57291 | 7291 | 14.58% | 0 | 9144 | 9144 |  | 0 | 2650 | 2650 |  | 408 | 389.25 | -18.75 | -4.596% | 2019-10-19 01:00
Brampton | 2020 | 450199 | HWY 410, N OF VODDEN ST E - 2019 Viper #7 | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | OH SW | Alectra Utilities | John Costa | 99849.75 | 110281.11 | 10431.36 | 10.45% | 43166.63 | 37989.57 | -5177.06 | -11.99% | 52807.03 | 51145.13 | -1661.9 | -3.147% | 2832 | 12389.11 | 9557.11 | 337.5% | 1044.09 | 6785.7 | 5741.61 | 549.9% | 360 | 437 | 77 | 21.39% | 2020-08-31 01:00
Brampton | 2020 | 450205 | KENVIEW BLVD, S OF CASTLEVIEW - 2019 Viper SW #8 | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes OH SW | Alectra Utilities | Reaburn, Jeff | 99082.13 | 85526.35 | -13555.78 | -13.68% | 43060.71 | 13324.14 | -29736.57 | -69.06% | 50330.39 | 52683.82 | 2353.43 | 4.676% | 5343 | 1129.61 | -4213.39 | -78.86% | 348.03 | 16093.44 | 15745.41 | 4524% | 384 | 147.5 | -236.5 | -61.59% | 2020-11-06 01:00
Brampton | 2019 | 450206 | 2019 Pole Replacement - Batch #5 | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Casey, Ryan | John Costa | 206050.6 | 182153.24 | -23897.36 | -11.6% | 138628.5 | 74920.33 | -63708.17 | -45.96% | 36050 | 50868.03 | 14818.03 | 41.1% | 18786.5 | 23385.5 | 4599 | 24.48% | 12585.6 | 544 | -12041.6 | -95.68% | 1297 | 1262 | -35 | -2.699% | 2019-11-27 00:59
Brampton | 2019 | 450207 | 45 Railroad St | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Gaurav | No | Ferry, Rodnne | Simon Evason | 123323.16 | 112272.08 | -11051.08 | -8.961% | 28600 | 19846.51 | -8753.49 | -30.61% | 72056 | 68303.06 | -3752.94 | -5.208% | 5472 | 7139.13 | 1667.13 | 30.47% | 5984 | 10590.34 | 4606.34 | 76.98% | 280 | 297.5 | 17.5 | 6.25% | 2019-11-23 01:00
Brampton | 2019 | 450209 | 2019 Pole Replacement - Batch #6 | 99 | COMPLETE | Labour est. under | Labour est. under | Labour est. under |  | No | Casey, Ryan | Reaburn, Jeff | 24807.69 | 70765.72 | 45958.03 | 185.3% | 17933.3 | 38123.63 | 20190.33 | 112.6% | 3609.79 | 2747.82 | -861.97 | -23.88% | 3264.6 | 9052 | 5787.4 | 177.3% | 0 | 5075 | 5075 |  | 190 | 423.5 | 233.5 | 122.9% | 2019-02-06 01:00
Brampton | 2021 | 450210 | BRAMPTON (ZAYO - SENTREX) | 99 | CANCELLED | N/A |  |  |  | No | Martin, Shane | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-21 01:00
Brampton | 2019 | 450212 | BOVAIRD - QUEEN, MAIN - KENNDY Cable injectoin G3 - 2019 | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Simon Evason | 200146.09 | 201876.56 | 1730.47 | 0.8646% | 9589.44 | 17296.01 | 7706.57 | 80.37% | 17930.4 | 2956.84 | -14973.56 | -83.51% | 2064 | 0 | -2064 | -100% | 170562.25 | 124599.19 | -45963.06 | -26.95% | 95 | 152 | 57 | 60% | 2019-12-21 01:00
Brampton | 2019 | 450213 | Cable Injection - Brampton H3 - 2019 | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Simon Evason | 1093100.86 | 417621.3 | -675479.56 | -61.79% | 35960.4 | 47867.57 | 11907.17 | 33.11% | 77633.21 | 5221.41 | -72411.8 | -93.27% | 7740 | 0 | -7740 | -100% | 971767.25 | 309884.81 | -661882.44 | -68.11% | 263 | 302 | 39 | 14.83% | 2019-12-21 01:00
Brampton | 2021 | 450215 | 100 Sandalwood Pky W | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-01-18 01:00
Brampton | 2021 | 450226 | DENISION AVE & HAGGERT AVE | 99 | COMPLETE | Under 10% |  |  | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 87247.39 | 88096.71 | 849.32 | 0.9735% | 14679.96 | 16346.18 | 1666.22 | 11.35% | 2230.75 | 313.9 | -1916.85 | -85.93% | 546 | 992.51 | 446.51 | 81.78% | 69790.68 | 920 | -68870.68 | -98.68% | 66 | 99.5 | 33.5 | 50.76% | 2021-01-18 01:00
Brampton | 2019 | 450233 | 71 Orenda Rd | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Ferry, Rodnne | Simon Evason | 50915 | 56886.07 | 5971.07 | 11.73% | 31962 | 363.04 | -31598.96 | -98.86% | 8625 | 15355.5 | 6730.5 | 78.03% | 5700 | 0 | -5700 | -100% | 0 | 0 | 0 |  | 358 | 343.5 | -14.5 | -4.05% | 2019-08-27 01:00
Brampton | 2019 | 450237 | 4.16KV-27.6KV PH2 CONV(2019) | 99 | COMPLETE | RFC not approved in time | Scope – Eng | Estimate incorrect |  | Yes | Miller, Michael | Nichol, Sandi | 546377.83 | 1538894.8 | 992516.97 | 181.7% | 335635.14 | 574132.01 | 238496.87 | 71.06% | 137984.69 | 83417.96 | -54566.73 | -39.55% | 58145 | 138173.99 | 80028.99 | 137.6% | 14613 | 15432.42 | 819.42 | 5.607% | 3439 | 6450.25 | 3011.25 | 87.56% | 2019-05-14
Brampton | 2022 | 450243 | BOVAIRD DR W & LAGERFELD DR | 95 | COMPLETE | Cont Est Under | Material Over Estimated | Labour est. over | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 112794.39 | 143296.39 | 30502 | 27.04% | 38625.73 | 31213.24 | -7412.49 | -19.19% | 59037.06 | 44511.15 | -14525.91 | -24.6% | 0 | 6628.25 | 6628.25 |  | 15131.6 | 59163.32 | 44031.72 | 291% | 176 | 273.75 | 97.75 | 55.54% | 2022-10-11 01:00
Brampton | 2020 | 450268 | STATEVIEW HOMES - OOH LA LA RESIDENTIAL SUBDIVISION | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Nichol, Sandi | 114545.24 | 258019.55 | 143474.31 | 125.3% | 11672.05 | 24455.74 | 12783.69 | 109.5% | 11433.3 | 11058.03 | -375.27 | -3.282% | 2081 | 2819.3 | 738.3 | 35.48% | 1.08 | 382.65 | 381.57 | 35331% | 110 | 248 | 138 | 125.5% | 2020-07-08 01:00
Brampton | 2019 | 450269 | Goreway Grade Separation | 99 | COMPLETE | Labour est. under | Estimate incorrect | N/A | Agostini, Robert | No | Robinson, David | Reaburn, Jeff | 398190.77 | 1357111 | 958920.23 | 240.8% | 219801 | 264295.12 | 44494.12 | 20.24% | 68089.77 | 74302.39 | 6212.62 | 9.124% | 67711 | 69898.49 | 2187.49 | 3.231% | 42589 | 69323.67 | 26734.67 | 62.77% | 935 | 2663.25 | 1728.25 | 184.8% | 2019-01-19 01:00
Brampton | 2021 | 450271 | 7900 McLaughlin Rd | 99 | COMPLETE | Estimate incorrect | Labour est. under | Vac truck | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 35821.93 | 89395.52 | 53573.59 | 149.6% | 30517.93 | 27022.96 | -3494.97 | -11.45% | 0 | 51934.13 | 51934.13 |  | 5304 | 4940.25 | -363.75 | -6.858% | 0 | 1423 | 1423 |  | 228 | 375.6 | 147.6 | 64.74% | 2021-01-26 01:00
Brampton | 2019 | 450274 | Heritage Road Pole relocation – six poles | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Erzek, Ryan | Reaburn, Jeff | 183575.09 | 375793.04 | 192217.95 | 104.7% | 106457.35 | 0 | -106457.35 | -100% | 28803.86 | 28803.86 | 0 | 0% | 28603.5 | 0 | -28603.5 | -100% | 19710.38 | 0 | -19710.38 | -100% | 1382.3 | 1324.75 | -57.55 | -4.163% | 2019-04-02 01:00
Brampton | 2019 | 450277 | 2019 Pole Batch #9 - EDGEMONT DR/CHURCH ST E | 99 | COMPLETE | Estimate incorrect | N/A | N/A |  | No | Miller, Michael | John Costa | 51277.27 | 144836.59 | 93559.32 | 182.5% | 32942.81 | 52314.75 | 19371.94 | 58.8% | 11075.46 | 10358.89 | -716.57 | -6.47% | 7259 | 10769 | 3510 | 48.35% | 0 | 4155.1 | 4155.1 |  | 578 | 576.5 | -1.5 | -0.2595% | 2019-04-05 01:00
Brampton | 2021 | 450280 | CUMBERLAND DR/BRISCO ST - 2019 Pole Batch #20 | 99 | COMPLETE | Cont Est Over | Labour est. under | N/A | Agostini, Robert | Yes OH Mini Rebuild | Casey, Ryan | Reaburn, Jeff | 665148.01 | 534030.36 | -131117.65 | -19.71% | 26940.86 | 56270.56 | 29329.7 | 108.9% | 84151.19 | 87403.49 | 3252.3 | 3.865% | 840 | 0 | -840 | -100% | 553215.96 | 386914.78 | -166301.18 | -30.06% | 65 | 30 | -35 | -53.85% | 2021-01-28 01:00
Brampton | 2022 | 450282 | 176 MAIN ST S | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 2929.6 | 2929.6 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-19 01:00
Brampton | 2019 | 450287 | 2239 Bovaird Dr W | 99 | COMPLETE | Labour est. under | Vac truck | Estimate incorrect |  | No | Ferry, Rodnne | Simon Evason | 7403 | 21820.95 | 14417.95 | 194.8% | 5100 | 239.55 | -4860.45 | -95.3% | 1219 | 913.22 | -305.78 | -25.08% | 1084 | 2390.5 | 1306.5 | 120.5% | 0 | 1125.85 | 1125.85 |  | 50 | 124.5 | 74.5 | 149% | 2019-01-19 01:00
Brampton | 2020 | 450294 | CHURCH ST E - 2018 Pole Batch#8 | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes OH Mini Rebuild | Alectra Utilities | John Costa | 252763.35 | 205453.28 | -47310.07 | -18.72% | 16503.98 | 19451.38 | 2947.4 | 17.86% | 26289.25 | 29896.72 | 3607.47 | 13.72% | 840 | 168.3 | -671.7 | -79.96% | 209130.12 | 154084.9 | -55045.22 | -26.32% | 128 | 26 | -102 | -79.69% | 2020-12-10 01:00
Brampton | 2019 | 450298 | DIXIE RD & MAYFIELD RD - Subdivision | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 253144.23 | 975911.73 | 722767.5 | 285.5% | 147537.53 | 97830.55 | -49706.98 | -33.69% | 86256.7 | 95793.78 | 9537.08 | 11.06% | 19350 | 14343.98 | -5006.02 | -25.87% | 0 | 7964.95 | 7964.95 |  | 1477 | 2274 | 797 | 53.96% | 2019-08-07 00:59
Brampton | 2021 | 450301 | #1 HWY 7 & CREDITVIEW RD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-28 01:00
Brampton | 2021 | 450307 | 329 BALMORAL DR | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Casey, Ryan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-28 01:00
Brampton | 2021 | 450308 | 20 BELMONT DR | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Casey, Ryan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-28 01:00
Brampton | 2021 | 450309 | 18 AINTREE CRES | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Casey, Ryan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-28 01:00
Brampton | 2022 | 450310 | 65 CATHCART CRES | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Casey, Ryan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-28 01:00
Brampton | 2022 | 450312 | SNDLWOOD PKWY-MCLAU TO HRTLKE | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Robinson, David | Weaver, Thomas | 0 | 20490.43 | 20490.43 |  | 0 | 868.02 | 868.02 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-28 01:00
Brampton | 2019 | 450313 | 27 MORRIS CRT | 99 | COMPLETE | Converted Project | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Brian Erskine | 0 | 31258.74 | 31258.74 |  | 0 | 1981.21 | 1981.21 |  | 0 | 3598.08 | 3598.08 |  | 0 | 0 | 0 |  | 0 | 21687.93 | 21687.93 |  | 0 | 23.5 | 23.5 |  | 2019-06-28 01:00
Brampton | 2019 | 450315 | 24 MORRIS CRT | 99 | COMPLETE | Converted Project | N/A | N/A | McAlpine, Robert | No | Cavanaugh, Danny | Simon Evason | 37409 | 38327.5 | 918.5 | 2.455% | 9200 | 5030.16 | -4169.84 | -45.32% | 20280 | 23177.51 | 2897.51 | 14.29% | 1616 | 1055.08 | -560.92 | -34.71% | 6313 | 6228.06 | -84.94 | -1.345% | 104 | 81 | -23 | -22.12% | 2019-07-20 01:00
Brampton | 2021 | 450318 | 237B ADVANCE BOULEVARD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Hotham, Matthew | 78862.91 | 0 | -78862.91 | -100% | 27443.9 | 0 | -27443.9 | -100% | 46427.01 | 0 | -46427.01 | -100% | 4992 | 0 | -4992 | -100% | 0 | 0 | 0 |  | 212 | 0 | -212 | -100% | 2020-10-30 01:00
Brampton | 2020 | 450326 | Rosedale Village Phase 7A Stg1 - SP17-114.000 New Sub | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 285520.29 | 254694.92 | -30825.37 | -10.8% | 41978.76 | 30353.34 | -11625.42 | -27.69% | 12459.81 | 2173.99 | -10285.82 | -82.55% | 2301 | 4405.16 | 2104.16 | 91.45% | 228780.72 | 1675.2 | -227105.52 | -99.27% | 338 | 359.5 | 21.5 | 6.361% | 2020-10-30 01:00
Brampton | 2021 | 450327 | ROSEDALE VILLAGE PH7A STG2 - SUBD RES EDS | 99 | COMPLETE | N/A | N/A | N/A | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 26109.65 | 263266.35 | 237156.7 | 908.3% | 21038.53 | 20311.06 | -727.47 | -3.458% | 751.12 | 2885.2 | 2134.08 | 284.1% | 4320 | 2572 | -1748 | -40.46% | 0 | 375 | 375 |  | 134 | 247 | 113 | 84.33% | 2021-07-26 01:00
Brampton | 2020 | 450335 | HEARTLAKE RD & COUNTRYSIDE DR | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | John Costa | 126848.08 | 120155.86 | -6692.22 | -5.276% | 76247.54 | 68125.23 | -8122.31 | -10.65% | 31484.54 | 19719.48 | -11765.06 | -37.37% | 5616 | 11561 | 5945 | 105.9% | 13500 | 12950.29 | -549.71 | -4.072% | 598 | 764.5 | 166.5 | 27.84% | 2020-02-19 01:00
Brampton | 2019 | 450339 | MS 14 - 14F3 FEEDER EGRESS REPLACEMENT - substation work | 99 | COMPLETE | Converted Project |  |  |  | No | Zaghloul, Sam | Richard Cuddy | 173930 | 194651.08 | 20721.08 | 11.91% | 33595 | 5222.01 | -28372.99 | -84.46% | 35300 | 38626.35 | 3326.35 | 9.423% | 7594 | 0 | -7594 | -100% | 97441 | 61459.49 | -35981.51 | -36.93% | 386 | 1051.5 | 665.5 | 172.4% | 2019-06-07
Brampton | 2021 | 450345 | UTILITY CORRIDOR ON VALLEYWAY DR - SUBD CAP PROJ | 99 | COMPLETE | BOM not accurate | N/A | N/A | Gamboa, Henry | No | Erzek, Ryan | Reaburn, Jeff | 335568.48 | 352101.05 | 16532.57 | 4.927% | 18174.62 | 28231 | 10056.38 | 55.33% | 100906.86 | 114589.04 | 13682.18 | 13.56% | 180 | 88 | -92 | -51.11% | 216307 | 202076.56 | -14230.44 | -6.579% | 22.16 | 60.5 | 38.34 | 173% | 2021-12-23 01:00
Brampton | 2019 | 450348 | BOVAIRD DR W & HERITAGE RD - PCB TX. | 99 | COMPLETE | Converted Project |  |  |  | No | D'Ermes, Michael | John Costa | 45215.19 | 43537.97 | -1677.22 | -3.709% | 29567.44 | 19736.22 | -9831.22 | -33.25% | 13649.2 | 16432.06 | 2782.86 | 20.39% | 1998.55 | 1394.25 | -604.3 | -30.24% | 0 | 0 | 0 |  | 356 | 408.25 | 52.25 | 14.68% | 2019-08-22 01:00
Brampton | 2019 | 450349 | WINSTON CHURCHILL & BOVAIRD - PCB Tx. | 99 | COMPLETE | Converted Project |  |  |  | No | D'Ermes, Michael | John Costa | 14637.44 | 20773.72 | 6136.28 | 41.92% | 7991.2 | 9741.26 | 1750.06 | 21.9% | 4275.38 | 4426.16 | 150.78 | 3.527% | 2370.86 | 2396.5 | 25.64 | 1.081% | 0 | 0 | 0 |  | 172 | 170.25 | -1.75 | -1.017% | 2019-08-03 01:00
Brampton | 2019 | 450350 | 10 & 20 LIGHTBEAM TERRACE | 92 | COMPLETE | Converted Project | N/A | N/A | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 108338.77 | 97176.28 | -11162.49 | -10.3% | 27443.9 | 16480 | -10963.9 | -39.95% | 67636.55 | 64490.52 | -3146.03 | -4.651% | 4992 | 2730 | -2262 | -45.31% | 8266.32 | 13392.95 | 5126.63 | 62.02% | 212 | 187.5 | -24.5 | -11.56% | 2019-12-13 01:00
Brampton | 2021 | 450352 | POLICE LANDS BLK 51-1 - SUBD RES EDS | 99 | COMPLETE | Labour est. over | Scope – Eng | N/A | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 37587.48 | 155435.94 | 117848.46 | 313.5% | 29877.52 | 17763.77 | -12113.75 | -40.54% | 509.96 | 1186.21 | 676.25 | 132.6% | 7200 | 1972 | -5228 | -72.61% | 0 | 490.45 | 490.45 |  | 188 | 129.5 | -58.5 | -31.12% | 2021-11-18 01:00
Brampton | 2020 | 450368 | 2 AUCTION LANE | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 98434.81 | 101100.46 | 2665.65 | 2.708% | 29783.25 | 25627.88 | -4155.37 | -13.95% | 29915.44 | 36033.61 | 6118.17 | 20.45% | 5187 | 3618 | -1569 | -30.25% | 33549.12 | 33252.83 | -296.29 | -0.8832% | 225 | 231 | 6 | 2.667% | 2020-04-28
Brampton | 2021 | 450370 | 10 & 20 LIGHTBEAM TERRACE | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-10 01:00
Brampton | 2019 | 450392 | 5 PRECIDIO CRT | 95 | COMPLETE | Converted Project | N/A | N/A | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 105660.602 | 38419.3 | -67241.302 | -63.64% | 15551.1588 | 4377.15 | -11174.0088 | -71.85% | 57094.2786 | 30944.2 | -26150.0786 | -45.8% | 6134.8454 | 516 | -5618.8454 | -91.59% | 15387.6066 | 0 | -15387.6066 | -100% | 202 | 45.25 | -156.75 | -77.6% | 2019-09-10 01:00
Brampton | 2019 | 450394 | 22 Bowman Ave | 99 | COMPLETE | Converted Project |  |  |  | No | D'Ermes, Michael | Richard Cuddy | 15000 | 7491.72 | -7508.28 | -50.06% | 1598.24 | 0 | -1598.24 | -100% | 10350.83 | 789.2 | -9561.63 | -92.38% | 344 | 0 | -344 | -100% | 0 | 0 | 0 |  | 36 | 71 | 35 | 97.22% | 2019-05-31
Brampton | 2019 | 450401 | 2755 WANLESS - Dr. - OH PCB Tx. Replacement | 99 | COMPLETE | Converted Project |  |  |  | No | Miller, Michael | John Costa | 15218.52 | 21903.81 | 6685.29 | 43.93% | 8390.76 | 10859.5 | 2468.74 | 29.42% | 4327.91 | 4427.12 | 99.21 | 2.292% | 2064 | 1373 | -691 | -33.48% | 435.85 | 818.8 | 382.95 | 87.86% | 160 | 174 | 14 | 8.75% | 2019-09-14 01:00
Brampton | 2019 | 450402 | 9353 Winston Churchill Blvd - OH PCB Tx. Replacement | 99 | COMPLETE | Converted Project |  |  |  | No | Miller, Michael | John Costa | 49391.71 | 28590.82 | -20800.89 | -42.11% | 28768.3 | 12108.91 | -16659.39 | -57.91% | 14429.36 | 11371.12 | -3058.24 | -21.19% | 4300 | 1756 | -2544 | -59.16% | 1894.05 | 0 | -1894.05 | -100% | 388 | 206.25 | -181.75 | -46.84% | 2019-08-03 01:00
Brampton | 2020 | 450421 | BRISDALE RD & MAYFIELD RD | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 32281.73 | 116335.79 | 84054.06 | 260.4% | 24889.08 | 14181.46 | -10707.62 | -43.02% | 5715.65 | 5196.25 | -519.4 | -9.087% | 1677 | 1617 | -60 | -3.578% | 0 | 1907.18 | 1907.18 |  | 240 | 142 | -98 | -40.83% | 2020-07-08 01:00
Brampton | 2021 | 450425 | 9715 WINSTON CHURCHILL | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 85433.1 | 89942.93 | 4509.83 | 5.279% | 22482.03 | 18875.95 | -3606.08 | -16.04% | 8691.75 | 11251.37 | 2559.62 | 29.45% | 3522 | 922.46 | -2599.54 | -73.81% | 50737.32 | 58893.15 | 8155.83 | 16.07% | 154 | 173.5 | 19.5 | 12.66% | 2021-06-10 01:00
Brampton | 2021 | 450430 | 25 PEEL CENTRE DR. | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Cavanaugh, Danny | Hotham, Matthew | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-19 01:00
Brampton | 2020 | 450433 | 7935 KENNEDY RD SOUTH | 95 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 125394.84 | 122119.11 | -3275.73 | -2.612% | 37084.35 | 30489.51 | -6594.84 | -17.78% | 46338.81 | 54960.26 | 8621.45 | 18.61% | 7605 | 12062.59 | 4457.59 | 58.61% | 34366.68 | 22876.06 | -11490.62 | -33.44% | 242 | 334.75 | 92.75 | 38.33% | 2020-06-19 01:00
Brampton | 2019 | 450442 | 8733 HERITAGE RD | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Robinson, David | Nichol, Sandi | 6500 | 9303.94 | 2803.94 | 43.14% | 2000 | 107.91 | -1892.09 | -94.6% | 3500 | 780.5 | -2719.5 | -77.7% | 1000 | 0 | -1000 | -100% | 0 | 0 | 0 |  | 65 | 63 | -2 | -3.077% | 2019-07-09 01:00
Brampton | 2019 | 450476 | COUNTRYSIDE DR | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Robinson, David | Reaburn, Jeff | 0 | 17377.97 | 17377.97 |  | 0 | 3084.54 | 3084.54 |  | 0 | 181.08 | 181.08 |  | 0 | 0 | 0 |  | 0 | 11650.75 | 11650.75 |  | 0 | 1.5 | 1.5 |  | 2019-10-08 01:00
Brampton | 2019 | 450480 | 8 GRAFTON CRES | 99 | COMPLETE | Converted Project | N/A | N/A | McAlpine, Robert | No | Cavanaugh, Danny | Brian Erskine | 4176 | 7631.61 | 3455.61 | 82.75% | 3800 | 1366.35 | -2433.65 | -64.04% | 104 | 0 | -104 | -100% | 272 | 0 | -272 | -100% | 0 | 4811.27 | 4811.27 |  | 0 | 21 | 21 |  | 2019-07-03 00:59
Brampton | 2021 | 450489 | 81 STAFFORD DRIVE | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 20719.41 | 11643.42 | -9075.99 | -43.8% | 9718.01 | 5344.37 | -4373.64 | -45.01% | 4776.4 | 0 | -4776.4 | -100% | 1950 | 0 | -1950 | -100% | 4275 | 4549.1 | 274.1 | 6.412% | 98 | 53.5 | -44.5 | -45.41% | 2021-11-18 01:00
Brampton | 2021 | 450494 | ASHLEY OAKS KINGSHOTT TOWNHOMES - SUBD RES EDS | 99 | COMPLETE | Labour est. over | N/A | N/A | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 27222.88 | 166039.6 | 138816.72 | 509.9% | 18999.95 | 15438.07 | -3561.88 | -18.75% | 810.93 | 1542.6 | 731.67 | 90.23% | 3200 | 560 | -2640 | -82.5% | 4212 | 4228.8 | 16.8 | 0.3989% | 84 | 76 | -8 | -9.524% | 2021-11-18 01:00
Brampton | 2021 | 450528 | 209 QUEEN ST E | 95 | COMPLETE | Estimate incorrect | Labour est. under | Cont Est Over | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 478353.35 | 541980.43 | 63627.08 | 13.3% | 37351.51 | 445801.93 | 408450.42 | 1094% | 60867.1 | 61101 | 233.9 | 0.3843% | 10296 | 6249.81 | -4046.19 | -39.3% | 369838.74 | 28827.69 | -341011.05 | -92.21% | 455 | 370.5 | -84.5 | -18.57% | 2021-04-24
Brampton | 2019 | 450532 | The Gore Rd and Beamish Crt - Pole Relocate | 99 | COMPLETE | Converted Project | N/A | N/A |  | CC | Robinson, David | Nichol, Sandi | 47623.71 | 44444.02 | -3179.69 | -6.677% | 0 | 8474.81 | 8474.81 |  | 2846.91 | 3893.24 | 1046.33 | 36.75% | 0 | 0 | 0 |  | 44776.8 | 30296.18 | -14480.62 | -32.34% | 10 | 27.5 | 17.5 | 175% | 2019-11-05 01:00
Brampton | 2022 | 450583 | 200 FIRST GULF BLVD. | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 3556.54 | 3556.54 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-14 01:00
Brampton | 2019 | 450595 | 31 HANSEN RD. S. | 98 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 44095.14 | 28722.89 | -15372.25 | -34.86% | 27625.71 | 11694.72 | -15930.99 | -57.67% | 7431.03 | 4418.76 | -3012.27 | -40.54% | 4524 | 1651.5 | -2872.5 | -63.49% | 4514.4 | 6096.9 | 1582.5 | 35.05% | 176 | 108 | -68 | -38.64% | 2019-12-14 01:00
Brampton | 2020 | 450600 | N SANDALWOOD PKY W KENNEDY RD | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 412633.96 | 341592.98 | -71040.98 | -17.22% | 55621.31 | 41933.25 | -13688.06 | -24.61% | 24443.81 | 20354.5 | -4089.31 | -16.73% | 4602 | 1749.47 | -2852.53 | -61.98% | 327966.84 | 275125.69 | -52841.15 | -16.11% | 457 | 162 | -295 | -64.55% | 2020-04-29
Brampton | 2020 | 450601 | W CHINGUACOUSY RD S QUEEN ST W | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 387088.59 | 313297.82 | -73790.77 | -19.06% | 54607.25 | 21971.25 | -32636 | -59.76% | 29757.34 | 7406.75 | -22350.59 | -75.11% | 1404 | 2838 | 1434 | 102.1% | 301320 | 527.2 | -300792.8 | -99.83% | 260 | 204.1 | -55.9 | -21.5% | 2020-10-30 01:00
Brampton | 2021 | 450602 | GORE (MOSAIK) INC - SUBD RES EDS | 99 | COMPLETE | BOM not accurate | N/A | N/A | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 49480.98 | 504861.2 | 455380.22 | 920.3% | 20845.59 | 21913.6 | 1068.01 | 5.123% | 2109.39 | 4504.6 | 2395.21 | 113.5% | 2496 | 5714 | 3218 | 128.9% | 24030 | 23260.8 | -769.2 | -3.201% | 141 | 164.75 | 23.75 | 16.84% | 2021-10-15 01:00
Brampton | 2020 | 450604 | 2460 QUEEN ST E | 95 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 45001 | 35455 | -9546 | -21.21% | 21400 | 7197.91 | -14202.09 | -66.36% | 15710 | 16441.74 | 731.74 | 4.658% | 3800 | 2183.52 | -1616.48 | -42.54% | 0 | 7642.38 | 7642.38 |  | 208 | 85 | -123 | -59.13% | 2020-08-12 01:00
Brampton | 2019 | 450605 | 7 BLAIR DR | 99 | COMPLETE | Under 10% | N/A | N/A |  | No | Bojanic, Dusan | Simon Evason | 31012.33 | 32815.33 | 1803 | 5.814% | 18800 | 0 | -18800 | -100% | 6286 | 1777.53 | -4508.47 | -71.72% | 3107 | 0 | -3107 | -100% | 0 | 0 | 0 |  | 0 | 89 | 89 |  | 2019-03-12 01:00
Brampton | 2020 | 450610 | 3425 CASTLEMORE DRIVE | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-05-28
Brampton | 2020 | 450611 | 11613 BRAMALEA ROAD | 98 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 139151.6 | 86183.35 | -52968.25 | -38.07% | 27946.91 | 23992.66 | -3954.25 | -14.15% | 39622.05 | 38770.7 | -851.35 | -2.149% | 4992 | 7005.11 | 2013.11 | 40.33% | 66590.64 | 12690.67 | -53899.97 | -80.94% | 212 | 283.5 | 71.5 | 33.73% | 2020-05-28
Brampton | 2019 | 450614 | HERITAGE RD AND FINANCIAL DR | 99 | COMPLETE | Labour est. over | Scope change - unforeseen | N/A |  | No | Lemire, Blake | Brian Erskine | 3200 | 5783.6 | 2583.6 | 80.74% | 3200 | 820.49 | -2379.51 | -74.36% | 0 | 0 | 0 |  | 0 | 195 | 195 |  | 0 | 917.8 | 917.8 |  | 30 | 11 | -19 | -63.33% | 2019-03-05 01:00
Brampton | 2019 | 450620 | 209 Steeles Ave. W. (200 MALTA AVE) | 98 | COMPLETE | Labour est. over | BOM not accurate | N/A | 0 | No | Cavanaugh, Danny | Simon Evason | 58579 | 54034.1 | -4544.9 | -7.759% | 30153 | 14604.66 | -15548.34 | -51.56% | 23375 | 21808.78 | -1566.22 | -6.7% | 5051 | 1508 | -3543 | -70.14% | 0 | 0 | 0 |  | 264 | 143.5 | -120.5 | -45.64% | 2019-06-07
Brampton | 2019 | 450621 | 5,9,15 BEAUMARIS DR. | 98 | COMPLETE | Converted Project |  |  | McAlpine, Robert | No | Alectra Utilities | Simon Evason | 84091 | 66108.63 | -17982.37 | -21.38% | 29300 | 13599.16 | -15700.84 | -53.59% | 31308 | 36827.26 | 5519.26 | 17.63% | 5670 | 463.57 | -5206.43 | -91.82% | 17813 | 12683.63 | -5129.37 | -28.8% | 243 | 174.5 | -68.5 | -28.19% | 2019-12-20 01:00
Brampton | 2019 | 450629 | 9025 Torbram Rd - ICI | 99 | COMPLETE | BOM not accurate | Labour est. over | Cont Est Over |  | No | Bojanic, Dusan | Simon Evason | 98804.23 | 62154.08 | -36650.15 | -37.09% | 30300 | 1646.35 | -28653.65 | -94.57% | 30929 | 21855.61 | -9073.39 | -29.34% | 5722 | 1406 | -4316 | -75.43% | 22871 | 13843.18 | -9027.82 | -39.47% | 257 | 206.5 | -50.5 | -19.65% | 2019-06-18 01:00
Brampton | 2019 | 450631 | CASTLEMORE AND EVERGREEN | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Lemire, Blake | John Costa | 2760 | 5765.85 | 3005.85 | 108.9% | 2500 | 0 | -2500 | -100% | 260 | 205.08 | -54.92 | -21.12% | 0 | 768 | 768 |  | 0 | 0 | 0 |  | 34 | 21 | -13 | -38.24% | 2019-05-16
Brampton | 2020 | 450632 | 7850 Heritage Rd. | 98 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 115187.63 | 114060.48 | -1127.15 | -0.9785% | 34163.88 | 30379.65 | -3784.23 | -11.08% | 46067.15 | 53325.69 | 7258.54 | 15.76% | 6396 | 9263.42 | 2867.42 | 44.83% | 28560.6 | 20700.08 | -7860.52 | -27.52% | 256 | 336.35 | 80.35 | 31.39% | 2020-11-17 01:00
Brampton | 2019 | 450633 | Creditview - Dist Automation 2019 | 99 | COMPLETE | Converted Project | N/A | N/A |  | Yes | D'Ermes, Michael | Richard Cuddy | 95000 | 79818.78 | -15181.22 | -15.98% | 45000 | 18440.9 | -26559.1 | -59.02% | 50000 | 50243.39 | 243.39 | 0.4868% | 0 | 798 | 798 |  | 0 | 0 | 0 |  | 392 | 387.5 | -4.5 | -1.148% | 2019-08-03 01:00
Brampton | 2020 | 450637 | 31 & 23 VODDEN ST W | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes Tx | Alectra Utilities | John Costa | 10512.98 | 19572.87 | 9059.89 | 86.18% | 4131.61 | 543.44 | -3588.17 | -86.85% | 5977.37 | 16574.37 | 10597 | 177.3% | 404 | 0 | -404 | -100% | 0 | 1742.45 | 1742.45 |  | 22 | 2 | -20 | -90.91% | 2020-10-30 01:00
Brampton | 2021 | 450638 | 15 LYNCH ST | 98 | COMPLETE | Under 10% | Labour est. over | BOM not accurate | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 93756.4 | 98813.55 | 5057.15 | 5.394% | 22181.03 | 19073.41 | -3107.62 | -14.01% | 29014.13 | 33517.43 | 4503.3 | 15.52% | 4056 | 2112 | -1944 | -47.93% | 38505.24 | 38670.47 | 165.23 | 0.4291% | 160 | 231.9 | 71.9 | 44.94% | 2021-01-25 01:00
Brampton | 2019 | 450641 | 30 LOAFERS LAKE LANE | 99 | COMPLETE | Estimate incorrect | BOM not used | N/A |  | No | Bojanic, Dusan | Simon Evason | 59978.64 | 85105.38 | 25126.74 | 41.89% | 24736 | 53 | -24683 | -99.79% | 24942 | 28797.66 | 3855.66 | 15.46% | 4848 | 2362 | -2486 | -51.28% | 0 | 662.48 | 662.48 |  | 208 | 200 | -8 | -3.846% | 2019-05-24
Brampton | 2021 | 450646 | 0 SUN PAC BLVD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-02 01:00
Brampton | 2019 | 450661 | STEELES AND MALTA AVE | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Erzek, Ryan | Richard Cuddy | 51585.31 | 131250.26 | 79664.95 | 154.4% | 33962.6 | 0 | -33962.6 | -100% | 14354.71 | 14229.14 | -125.57 | -0.8748% | 3268 | 162 | -3106 | -95.04% | 0 | 0 | 0 |  | 340 | 432 | 92 | 27.06% | 2019-03-02 01:00
Brampton | 2019 | 450662 | 200 RIVERMONT RD | 98 | COMPLETE | Converted Project |  |  |  | No | Bojanic, Dusan | Simon Evason | 70326.54 | 72793.3 | 2466.76 | 3.508% | 26212.54 | 4397.07 | -21815.47 | -83.23% | 31103 | 30477.24 | -625.76 | -2.012% | 6311 | 1804 | -4507 | -71.41% | 6700 | 2169.05 | -4530.95 | -67.63% | 262 | 283 | 21 | 8.015% | 2019-06-15 01:00
Brampton | 2020 | 450663 | MCLAUGHLIN RD & WHITEPOPPY DR | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 45584.82 | 50832.5 | 5247.68 | 11.51% | 27484.77 | 29379.17 | 1894.4 | 6.893% | 5536.87 | 5536.01 | -0.86 | -0.01553% | 3444 | 5705.64 | 2261.64 | 65.67% | 9119.18 | 4672.5 | -4446.68 | -48.76% | 180 | 181 | 1 | 0.5556% | 2020-11-24 01:00
Brampton | 2019 | 450664 | VARIOUS LOCATIONS | 99 | COMPLETE | BOM not accurate | N/A | N/A | Agostini, Robert | No | Casey, Ryan | Brian Erskine | 13924.5 | 23872.89 | 9948.39 | 71.45% | 8488.94 | 8420.89 | -68.05 | -0.8016% | 4747.56 | 5339 | 591.44 | 12.46% | 688 | 846 | 158 | 22.97% | 0 | 0 | 0 |  | 85 | 94.5 | 9.5 | 11.18% | 2019-04-16 01:00
Brampton | 2019 | 450665 | HWY 410 @ VODDEN ST.EAST | 99 | COMPLETE | Labour est. under | Cont Est Over | N/A | Agostini, Robert | No | Robinson, David | Richard Cuddy | 425000 | 953200.02 | 528200.02 | 124.3% | 30000 | 7947.82 | -22052.18 | -73.51% | 13000 | 14472.34 | 1472.34 | 11.33% | 18000 | 0 | -18000 | -100% | 364000 | 95031.9 | -268968.1 | -73.89% | 320 | 828.5 | 508.5 | 158.9% | 2019-06-07
Brampton | 2019 | 450668 | LAGERFELD DR & CREDITVIEW RD | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Erzek, Ryan | Richard Cuddy | 69356.74 | 52042.48 | -17314.26 | -24.96% | 39556.44 | 13773.95 | -25782.49 | -65.18% | 22952.6 | 2435.47 | -20517.13 | -89.39% | 5332 | 285 | -5047 | -94.65% | 1515.7 | 5315.78 | 3800.08 | 250.7% | 396 | 336.75 | -59.25 | -14.96% | 2019-09-14 01:00
Brampton | 2019 | 450681 | 5 NEVETS RD | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A |  | No | Bojanic, Dusan | Simon Evason | 59638 | 90892.62 | 31254.62 | 52.41% | 19392 | 13187.13 | -6204.87 | -32% | 24064 | 25278.06 | 1214.06 | 5.045% | 7760 | 2101.5 | -5658.5 | -72.92% | 3000 | 17635.79 | 14635.79 | 487.9% | 170 | 156 | -14 | -8.235% | 2019-01-11 01:00
Brampton | 2019 | 450687 | 180 Veterans Dr | 98 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 54002.28 | 149164.55 | 95162.27 | 176.2% | 19392 | 4264.81 | -15127.19 | -78.01% | 22853 | 24002.61 | 1149.61 | 5.03% | 4848 | 1372.25 | -3475.75 | -71.69% | 2000 | 2531.77 | 531.77 | 26.59% | 214 | 261 | 47 | 21.96% | 2019-04-13 01:00
Brampton | 2021 | 450688 | 3455 Queen Street E | 95 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 142528.63 | 129181.89 | -13346.74 | -9.364% | 40910.08 | 24799.02 | -16111.06 | -39.38% | 65418.75 | 63458.38 | -1960.37 | -2.997% | 6786 | 5251.36 | -1534.64 | -22.61% | 29413.8 | 31205.91 | 1792.11 | 6.093% | 250 | 277.8 | 27.8 | 11.12% | 2021-03-05 01:00
Brampton | 2019 | 450690 | 5907 Steeles Ave E | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Ferry, Rodnne | Simon Evason | 84832.45 | 74037.56 | -10794.89 | -12.72% | 8755.33 | 2203.42 | -6551.91 | -74.83% | 0 | 36430.37 | 36430.37 |  | 1139 | 0 | -1139 | -100% | 3243.6 | 5776.1 | 2532.5 | 78.08% | 280 | 255 | -25 | -8.929% | 2019-08-09 01:00
Brampton | 2021 | 450714 | 1713 STEELES AVE E - PERMANENT SERVICE | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 87674.98 | 93067.86 | 5392.88 | 6.151% | 32147.86 | 20333.69 | -11814.17 | -36.75% | 37011.71 | 45220.94 | 8209.23 | 22.18% | 4301.85 | 5534.5 | 1232.65 | 28.65% | 14213.56 | 17829.94 | 3616.38 | 25.44% | 226 | 228.25 | 2.25 | 0.9956% | 2021-03-26 01:00
Brampton | 2019 | 450719 | 5227 MAYFIELD DR | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A |  | No | Bojanic, Dusan | Simon Evason | 5876.72 | 2665.32 | -3211.4 | -54.65% | 4704 | 1164.1 | -3539.9 | -75.25% | 428.72 | 281.64 | -147.08 | -34.31% | 744 | 352 | -392 | -52.69% | 0 | 867.58 | 867.58 |  | 51 | 44 | -7 | -13.73% | 2019-05-23 23:59
Brampton | 2022 | 450728 | WILLIAMS PKWY-MCLAUGHLN /NORTH | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Lemire, Blake | Weaver, Thomas | 0 | 209376.08 | 209376.08 |  | 0 | 3182.39 | 3182.39 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13291.97 | 13291.97 |  | 0 | 9.5 | 9.5 |  | 2019-12-05 01:00
Brampton | 2019 | 450730 | CHINGUACOUSY & WANLESS - Road Widening - COB | 99 | COMPLETE | Converted Project |  |  | Kafel, Krzysztof | No | Watters, Maxwell | Reaburn, Jeff | 920764.85 | 920106.54 | -658.31 | -0.0715% | 39037.72 | 47121.32 | 8083.6 | 20.71% | 242741.45 | 235541.96 | -7199.49 | -2.966% | 0 | 417 | 417 |  | 638985.68 | 77629.62 | -561356.06 | -87.85% | 230 | 242.5 | 12.5 | 5.435% | 2019-12-05 01:00
Brampton | 2022 | 450731 | TORBRAM ROAD & QUEEN STREET | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Lemire, Blake | Weaver, Thomas | 0 | 77009.93 | 77009.93 |  | 0 | 28982.8 | 28982.8 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-13 01:00
Brampton | 2019 | 450736 | McMurchy Ave S and Steeles Ave W | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Alectra Utilities | Richard Cuddy | 192607.3 | 237989.13 | 45381.83 | 23.56% | 40000 | 45203.95 | 5203.95 | 13.01% | 5684.11 | 17005.79 | 11321.68 | 199.2% | 860 | 4011 | 3151 | 366.4% | 146063.19 | 111163.07 | -34900.12 | -23.89% | 504 | 558.75 | 54.75 | 10.86% | 2019-12-13 01:00
Brampton | 2020 | 450744 | 2675 STEELES AVE. W. | 98 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 159463.55 | 145922.24 | -13541.31 | -8.492% | 43195.85 | 27856.52 | -15339.33 | -35.51% | 64303.98 | 66182.39 | 1878.41 | 2.921% | 3705 | 5219.5 | 1514.5 | 40.88% | 48258.72 | 39938.01 | -8320.71 | -17.24% | 286 | 277.5 | -8.5 | -2.972% | 2020-01-30 01:00
Brampton | 2021 | 450748 | 10300 HEART LAKE RD.N. | 98 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 122142.9 | 117491.74 | -4651.16 | -3.808% | 40650.35 | 29235.15 | -11415.2 | -28.08% | 51253.75 | 52882.12 | 1628.37 | 3.177% | 4799.4 | 4629.5 | -169.9 | -3.54% | 25439.4 | 27135.52 | 1696.12 | 6.667% | 314.8 | 314.5 | -0.3 | -0.0953% | 2021-11-03 01:00
Brampton | 2020 | 450753 | WILLIAMS PKWY & MISSISSAUGA RD | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 149176.1 | 588027.14 | 438851.04 | 294.2% | 89874.83 | 41737.88 | -48136.95 | -53.56% | 40255.27 | 59642.23 | 19386.96 | 48.16% | 19046 | 5179.11 | -13866.89 | -72.81% | 0 | 1032.13 | 1032.13 |  | 534 | 485.5 | -48.5 | -9.082% | 2020-11-24 01:00
Brampton | 2019 | 450760 | MAYFIELD RD & CREDITVIEW RD | 99 | COMPLETE | Scope change - unforeseen | Estimate incorrect | N/A |  | No | Erzek, Ryan | Richard Cuddy | 353790.43 | 369662.93 | 15872.5 | 4.486% | 173009.48 | 65506.25 | -107503.23 | -62.14% | 148272.95 | 649.42 | -147623.53 | -99.56% | 32508 | 9586 | -22922 | -70.51% | 0 | 3010.96 | 3010.96 |  | 2243 | 1838 | -405 | -18.06% | 2019-01-29 01:00
Brampton | 2019 | 450762 | DIXIE RD & MAYFIELD RD - Feeder for the Subdivision | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Erzek, Ryan | Richard Cuddy | 47482.08 | 44828.85 | -2653.23 | -5.588% | 23274.37 | 13588.33 | -9686.04 | -41.62% | 22226.26 | 15314.16 | -6912.1 | -31.1% | 1978 | 753 | -1225 | -61.93% | 3.45 | 0 | -3.45 | -100% | 265 | 340 | 75 | 28.3% | 2019-07-30 01:00
Brampton | 2022 | 450763 | MAIN ST S & CLARENCE ST | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Erzek, Ryan | Dre Danieli | 0 | 2307.25 | 2307.25 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-30 01:00
Brampton | 2022 | 450764 | WILLIAMS PKY HWY 10 - KENNEDY | 99 | CANCELLED | N/A |  |  | Casciato, Adam J | No | Lemire, Blake | Weaver, Thomas | 0 | 20211.7 | 20211.7 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-30 01:00
Brampton | 2019 | 450769 | 28 TRURO CIR | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Erzek, Ryan | Richard Cuddy | 265616.22 | 246397.71 | -19218.51 | -7.235% | 25671.73 | 3630.17 | -22041.56 | -85.86% | 32956.49 | 8902.19 | -24054.3 | -72.99% | 4988 | 0 | -4988 | -100% | 202000 | 0 | -202000 | -100% | 257 | 222.5 | -34.5 | -13.42% | 2019-11-30 01:00
Brampton | 2021 | 450771 | CV PATILDA PH5 ST1 - SUBD RES EDS | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 78654.36 | 718772.3 | 640117.94 | 813.8% | 47399.28 | 38405.64 | -8993.64 | -18.97% | 14481.08 | 21839.11 | 7358.03 | 50.81% | 11266 | 7755 | -3511 | -31.16% | 5508 | 5100 | -408 | -7.407% | 364 | 418.5 | 54.5 | 14.97% | 2021-05-25 01:00
Brampton | 2019 | 450773 | 130 RAILSIDE DR. | 98 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 167161 | 138296.82 | -28864.18 | -17.27% | 62644 | 22362.51 | -40281.49 | -64.3% | 65453 | 67246.32 | 1793.32 | 2.74% | 5020 | 1774.13 | -3245.87 | -64.66% | 34044 | 39672.52 | 5628.52 | 16.53% | 252 | 277 | 25 | 9.921% | 2019-12-18 01:00
Brampton | 2019 | 450776 | BOVAIRD DR-CREDITVIEW/WORTNGTN | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | No | Robinson, David | Reaburn, Jeff | 340000 | 338941.86 | -1058.14 | -0.3112% | 20000 | 5136.52 | -14863.48 | -74.32% | 37000 | 41088 | 4088 | 11.05% | 6000 | 0 | -6000 | -100% | 270000 | 1548.75 | -268451.25 | -99.43% | 309 | 291.5 | -17.5 | -5.663% | 2019-08-07 01:00
Brampton | 2021 | 450782 | WALLSEND STAGE 1 - SUBD RES EDS | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 50974.25 | 472501.37 | 421527.12 | 826.9% | 31736.03 | 18498.09 | -13237.94 | -41.71% | 6634.22 | 10340.85 | 3706.63 | 55.87% | 7096 | 3234 | -3862 | -54.43% | 5508 | 5560 | 52 | 0.9441% | 197 | 148 | -49 | -24.87% | 2021-05-25 01:00
Brampton | 2020 | 450783 | DIXIE RD & WILLIAMS PKWY | 98 | COMPLETE | Converted Project |  |  | Pelleja, Emily | CC | Alectra Utilities | Reaburn, Jeff | 120711.91 | 113156.14 | -7555.77 | -6.259% | 2345.09 | 17726.2 | 15381.11 | 655.9% | 28006.78 | 29129.36 | 1122.58 | 4.008% | 112 | 0 | -112 | -100% | 90248.04 | 63759.53 | -26488.51 | -29.35% | 8 | 49 | 41 | 512.5% | 2020-11-09 01:00
Brampton | 2019 | 450785 | COUNTRYSIDE DR/MCVEAN DR | 99 | COMPLETE | Estimate incorrect | Labour est. over | BOM not accurate |  | No | Robinson, David | Reaburn, Jeff | 33000 | 33846.48 | 846.48 | 2.565% | 18000 | 0 | -18000 | -100% | 6000 | 1385.8 | -4614.2 | -76.9% | 9000 | 0 | -9000 | -100% | 0 | 0 | 0 |  | 36 | 129.5 | 93.5 | 259.7% | 2019-01-03 01:00
Brampton | 2019 | 450786 | BRAMALEA RD @ BRAMALEA GO | 99 | COMPLETE | Estimate incorrect | Cont Est Over | BOM not accurate |  | No | Robinson, David | Reaburn, Jeff | 358032.47 | 468291.42 | 110258.95 | 30.8% | 70000 | 2927.54 | -67072.46 | -95.82% | 45000 | 62070.7 | 17070.7 | 37.93% | 35000 | 288 | -34712 | -99.18% | 165000 | 13269 | -151731 | -91.96% | 231 | 247 | 16 | 6.926% | 2019-02-09 01:00
Brampton | 2019 | 450802 | MAYFIELD RD AND BRAMALEA RD | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 96705.33 | 90470.93 | -6234.4 | -6.447% | 45000 | 21831.16 | -23168.84 | -51.49% | 51705.33 | 55109.57 | 3404.24 | 6.584% | 0 | 54 | 54 |  | 0 | 0 | 0 |  | 392 | 410.75 | 18.75 | 4.783% | 2019-10-01 01:00
Brampton | 2019 | 450804 | WINSTON CHURCHILL/EMBELTON | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Casey, Ryan | Richard Cuddy | 100337.39 | 91348.42 | -8988.97 | -8.959% | 44406.46 | 24671.04 | -19735.42 | -44.44% | 49245.93 | 58015.11 | 8769.18 | 17.81% | 6685 | 2853 | -3832 | -57.32% | 0 | 0 | 0 |  | 370 | 384.75 | 14.75 | 3.986% | 2019-09-11 01:00
Brampton | 2019 | 450806 | QUEEN ST E & GATEWAY BLVD | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 99632 | 105214.24 | 5582.24 | 5.603% | 44000 | 35813.97 | -8186.03 | -18.6% | 48610 | 51800.65 | 3190.65 | 6.564% | 7022 | 10701.5 | 3679.5 | 52.4% | 0 | 0 | 0 |  | 363 | 456 | 93 | 25.62% | 2019-11-28 01:00
Brampton | 2020 | 450808 | MAYFIELD AND BRAMALEA RD | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 16002 | 14207.52 | -1794.48 | -11.21% | 5300 | 0 | -5300 | -100% | 5618 | 7053.69 | 1435.69 | 25.56% | 1084 | 0 | -1084 | -100% | 4000 | 0 | -4000 | -100% | 52 | 48 | -4 | -7.692% | 2020-04-28
Brampton | 2022 | 450814 | ELIZABETH ST N 7 NELSON ST | 99 | CANCELLED | N/A |  |  | Newitt, Andrew | No | Lemire, Blake | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-03-31 01:00
Brampton | 2020 | 450815 | 475 CHRYSLER DR | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 82284.48 | 64684.12 | -17600.36 | -21.39% | 24707.28 | 16637.88 | -8069.4 | -32.66% | 29836.08 | 29341.07 | -495.01 | -1.659% | 3858 | 1706.78 | -2151.22 | -55.76% | 23883.12 | 15103.05 | -8780.07 | -36.76% | 160 | 188.75 | 28.75 | 17.97% | 2020-03-31 01:00
Brampton | 2019 | 450816 | 3 St.Patrick Rd | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A |  | No | Bojanic, Dusan | Simon Evason | 16528.38 | 24219.47 | 7691.09 | 46.53% | 9892 | 4385.24 | -5506.76 | -55.67% | 638 | 567.93 | -70.07 | -10.98% | 1614 | 281 | -1333 | -82.59% | 2869.95 | 7159.53 | 4289.58 | 149.5% | 100 | 75.5 | -24.5 | -24.5% | 2019-02-20 01:00
Brampton | 2020 | 450817 | 10254 HURONTARIO STREET | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 116956.52 | 106225.58 | -10730.94 | -9.175% | 35641.09 | 15578.82 | -20062.27 | -56.29% | 17711.89 | 19938.81 | 2226.92 | 12.57% | 5148 | 2905.61 | -2242.39 | -43.56% | 58455.54 | 67162.47 | 8706.93 | 14.89% | 236 | 166 | -70 | -29.66% | 2020-11-20 01:00
Brampton | 2021 | 450821 | 6401 MAYFIELD ROAD | 98 | COMPLETE | Estimate incorrect | Labour est. over |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 91204.55 | 82018.11 | -9186.44 | -10.07% | 29405.73 | 11315.59 | -18090.14 | -61.52% | 47160.55 | 47459.08 | 298.53 | 0.633% | 5319.6 | 3187 | -2132.6 | -40.09% | 9318.67 | 16105.45 | 6786.78 | 72.83% | 164 | 121 | -43 | -26.22% | 2021-10-08 01:00
Brampton | 2019 | 450828 | 2700 NORTH PARK DR. | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 58915 | 44814.9 | -14100.1 | -23.93% | 0 | 6333.48 | 6333.48 |  | 0 | 26865.32 | 26865.32 |  | 0 | 228 | 228 |  | 0 | 0 | 0 |  | 242 | 262.5 | 20.5 | 8.471% | 2019-07-23 00:59
Brampton | 2019 | 450831 | 45 RAILROAD | 99 | CANCELLED | Converted Project |  |  |  | No | Ferry, Rodnne | Simon Evason | 8135 | 7225.85 | -909.15 | -11.18% | 7616 | 2858.97 | -4757.03 | -62.46% | 200 | 115.25 | -84.75 | -42.38% | 319 | 14 | -305 | -95.61% | 0 | 682.33 | 682.33 |  | 49 | 40.5 | -8.5 | -17.35% | 2019-03-20 01:00
Brampton | 2019 | 450834 | FINANCIAL DR N.SEAPINES/MINER | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Robinson, David | Reaburn, Jeff | 0 | 18656.15 | 18656.15 |  | 0 | 5667.11 | 5667.11 |  | 0 | 4112.72 | 4112.72 |  | 0 | 912 | 912 |  | 0 | 7964.32 | 7964.32 |  | 0 | 58 | 58 |  | 2019-04-03 00:59
Brampton | 2020 | 450835 | BRAMPTON DOWNNTOWN | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | Yes | Alectra Utilities | Nichol, Sandi | 1269132.42 | 1215520.34 | -53612.08 | -4.224% | 767166.47 | 343239.34 | -423927.13 | -55.26% | 123394.72 | 168249.45 | 44854.73 | 36.35% | 178921 | 92478.25 | -86442.75 | -48.31% | 199650.23 | 91407.11 | -108243.12 | -54.22% | 7977 | 7220.75 | -756.25 | -9.48% | 2020-01-11 01:00
Brampton | 2019 | 450841 | 275 GARDEN BROOK TRAIL | 99 | COMPLETE | Estimate incorrect | Labour est. over | N/A |  | No | Bojanic, Dusan | Simon Evason | 106379.9 | 141245.72 | 34865.82 | 32.77% | 22816 | 16767.93 | -6048.07 | -26.51% | 34938 | 33373.82 | -1564.18 | -4.477% | 4224 | 2895 | -1329 | -31.46% | 34731 | 34273.02 | -457.98 | -1.319% | 186 | 177.5 | -8.5 | -4.57% | 2019-02-27 00:59
Brampton | 2019 | 450842 | Churchville Rd - 27.6kV Pole Line Rebuild | 99 | COMPLETE | Cont Est Under | Estimate incorrect | Estimate incorrect |  | No | D'Ermes, Michael | Reaburn, Jeff | 422510.38 | 878561.92 | 456051.54 | 107.9% | 0 | 319.37 | 319.37 |  | 61147.19 | 62103.29 | 956.1 | 1.564% | 29628.1 | 2805 | -26823.1 | -90.53% | 331735.09 | 376255.42 | 44520.33 | 13.42% | 223.8 | 264.75 | 40.95 | 18.3% | 2019-02-23 01:00
Brampton | 2021 | 450844 | TACC HOLBORN - SUBD RES EDS | 99 | COMPLETE | Cont Est Over | N/A | N/A | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 939810.5 | 787018.95 | -152791.55 | -16.26% | 78703.76 | 99385.43 | 20681.67 | 26.28% | 2615.42 | 2643.34 | 27.92 | 1.068% | 11740 | 3857 | -7883 | -67.15% | 846751.32 | 674889 | -171862.32 | -20.3% | 490 | 375 | -115 | -23.47% | 2021-05-12
Brampton | 2021 | 450846 | WALNESS (EAST) 21T-11011B - SUBD RES EDS | 99 | COMPLETE | Labour est. over | Inaccurate design | N/A | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 76860.09 | 691540.5 | 614680.41 | 799.7% | 56333.95 | 30909.79 | -25424.16 | -45.13% | 8114.14 | 11081.52 | 2967.38 | 36.57% | 12412 | 1792 | -10620 | -85.56% | 0 | 15424.35 | 15424.35 |  | 377 | 226.75 | -150.25 | -39.85% | 2021-12-10 01:00
Brampton | 2021 | 450847 | ALLOA GREEN (WEST) 21T-17001B - SUBD RES EDS | 99 | COMPLETE | Labour est. over | Inaccurate design | N/A | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 35823.04 | 185195.54 | 149372.5 | 417% | 28723.01 | 14940.29 | -13782.72 | -47.98% | 1892.03 | 1548.3 | -343.73 | -18.17% | 5208 | 0 | -5208 | -100% | 0 | 7136.35 | 7136.35 |  | 137 | 58 | -79 | -57.66% | 2021-12-08 01:00
Brampton | 2022 | 450848 | SE CRNR OF MAYFIELD & KENNEDY | 99 | CANCELLED | N/A |  |  |  | No | Lemire, Blake | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-10 01:00
Brampton | 2019 | 450849 | Forestside Block 5 Townhomes | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 210918.79 | 128743.76 | -82175.03 | -38.96% | 19452.09 | 15955 | -3497.09 | -17.98% | 4482.46 | 4633.55 | 151.09 | 3.371% | 195 | 1905 | 1710 | 876.9% | 186789.24 | 2812.5 | -183976.74 | -98.49% | 154 | 167 | 13 | 8.442% | 2019-09-10 01:00
Brampton | 2019 | 450852 | AIRPORT RD & COUNTRYSIDE DR | 99 | COMPLETE | Est. Int. - Act. External | Est. Int. - Act. External | N/A |  | No | Erzek, Ryan | Reaburn, Jeff | 63748.18 | 72762.42 | 9014.24 | 14.14% | 48762.82 | 0 | -48762.82 | -100% | 9537.26 | 8667.47 | -869.79 | -9.12% | 3569 | 0 | -3569 | -100% | 1879.1 | 0 | -1879.1 | -100% | 346 | 266.5 | -79.5 | -22.98% | 2019-03-05 01:00
Brampton | 2019 | 450855 | 20 WESTWYN COURT | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Ferry, Rodnne | Simon Evason | 94332.63 | 63757.26 | -30575.37 | -32.41% | 38000 | 4328 | -33672 | -88.61% | 34951 | 29712.7 | -5238.3 | -14.99% | 7850 | 900 | -6950 | -88.54% | 4956 | 5310.87 | 354.87 | 7.16% | 376 | 254 | -122 | -32.45% | 2019-10-08 01:00
Brampton | 2019 | 450862 | ICELAND POPPY TRAIL | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 16345.26 | 78843.28 | 62498.02 | 382.4% | 11886.91 | 7142.95 | -4743.96 | -39.91% | 3469.35 | 3277.86 | -191.49 | -5.519% | 989 | 788.37 | -200.63 | -20.29% | 0 | 2325 | 2325 |  | 119 | 124.5 | 5.5 | 4.622% | 2019-08-03 01:00
Brampton | 2020 | 450866 | 11025 TORBRAM RD | 98 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 71096.05 | 92243.56 | 21147.51 | 29.74% | 20023.34 | 11052.33 | -8971.01 | -44.8% | 21587.08 | 53465.73 | 31878.65 | 147.7% | 3214.2 | 1224 | -1990.2 | -61.92% | 26271.43 | 2730.53 | -23540.9 | -89.61% | 132 | 139.5 | 7.5 | 5.682% | 2020-01-22 01:00
Brampton | 2021 | 450880 | NEAMSBY STAGE 1 - SUBD RES EDS | 99 | COMPLETE | Labour est. over | Inaccurate design | N/A | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 34999.39 | 284741.41 | 249742.02 | 713.6% | 24883.39 | 12855.76 | -12027.63 | -48.34% | 0 | 2687.24 | 2687.24 |  | 5904 | 1908 | -3996 | -67.68% | 4212 | 3978.1 | -233.9 | -5.553% | 140 | 102.75 | -37.25 | -26.61% | 2021-05-25 01:00
Brampton | 2020 | 450890 | 80 MARY ST. | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 37549.21 | 34454.77 | -3094.44 | -8.241% | 18400.6 | 4896.6 | -13504 | -73.39% | 16691.61 | 17326.03 | 634.42 | 3.801% | 2457 | 732 | -1725 | -70.21% | 0 | 5681.8 | 5681.8 |  | 103 | 39.75 | -63.25 | -61.41% | 2020-06-12 01:00
Brampton | 2021 | 450891 | SE OF MAYFIELD & GORDON RANDLE | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Armstrong, Colby | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-05-26
Brampton | 2020 | 450894 | CHINGUACOUSY RD & WANLESS DR | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 1476984.69 | 1571725.22 | 94740.53 | 6.414% | 110917.4 | 146637.43 | 35720.03 | 32.2% | 114936.2 | 115637.77 | 701.57 | 0.6104% | 6942 | 29172.22 | 22230.22 | 320.2% | 0 | 36088.71 | 36088.71 |  | 967 | 1590.25 | 623.25 | 64.45% | 2020-05-26
Brampton | 2019 | 450897 | 2019 SWITCHGEAR REPLACEMENTS - Union St and Nelson | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | D'Ermes, Michael | Richard Cuddy | 95405.12 | 100125.86 | 4720.74 | 4.948% | 19978 | 459.47 | -19518.53 | -97.7% | 74395.12 | 73489.72 | -905.4 | -1.217% | 1032 | 228 | -804 | -77.91% | 0 | 0 | 0 |  | 238.5 | 245.5 | 7 | 2.935% | 2019-02-08 01:00
Brampton | 2019 | 450904 | CREDITVIEW RD & VETERANS DR | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Erzek, Ryan | Richard Cuddy | 330719.28 | 317826.13 | -12893.15 | -3.899% | 21376.46 | 225 | -21151.46 | -98.95% | 5232.16 | 3495.92 | -1736.24 | -33.18% | 258 | 0 | -258 | -100% | 303852.66 | 301 | -303551.66 | -99.9% | 214 | 140.75 | -73.25 | -34.23% | 2019-10-08 00:59
Brampton | 2022 | 450905 | GO ELEC RER-CONFLICT KT#30 | 99 | CANCELLED | N/A |  |  | Khuu, Philander | No | Chopra, Rabinder | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-13 01:00
Brampton | 2021 | 450913 | 2021 TX RENEWAL- GRID G4-2 TX | 99 | COMPLETE | Cont Est Under | Labour est. under | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 34337.21 | 48784.26 | 14447.05 | 42.07% | 8848.64 | 8988.65 | 140.01 | 1.582% | 11803.41 | 12185.25 | 381.84 | 3.235% | 1560 | 2728.99 | 1168.99 | 74.94% | 12125.16 | 16163.01 | 4037.85 | 33.3% | 45 | 64 | 19 | 42.22% | 2021-08-13 01:00
Brampton | 2020 | 450915 | 223 Corporation Dr - 3ph - tx repl | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes Tx. | Alectra Utilities | Reaburn, Jeff | 27203.46 | 32792.86 | 5589.4 | 20.55% | 5226.5 | 4922.46 | -304.04 | -5.817% | 21274.96 | 22496.13 | 1221.17 | 5.74% | 702 | 1599.52 | 897.52 | 127.9% | 0 | 524.18 | 524.18 |  | 32 | 40 | 8 | 25% | 2020-10-02 01:00
Brampton | 2019 | 450916 | 2019 - VARIOUS LOCATIONS BRAMPTON - tx | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Casey, Ryan | Reaburn, Jeff | 87362.65 | 84793.27 | -2569.38 | -2.941% | 44012.53 | 19330.9 | -24681.63 | -56.08% | 40570.62 | 39034.67 | -1535.95 | -3.786% | 2779.5 | 2427 | -352.5 | -12.68% | 0 | 622 | 622 |  | 124 | 159.5 | 35.5 | 28.63% | 2019-03-26 01:00
Brampton | 2021 | 450918 | HERITAGE RD, S OF EMBLETON | 99 | COMPLETE | Under 10% | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Reaburn, Jeff | 549100.91 | 597433 | 48332.09 | 8.802% | 235270.1 | 251046.82 | 15776.72 | 6.706% | 180650.59 | 175439.98 | -5210.61 | -2.884% | 80754.1 | 105096.67 | 24342.57 | 30.14% | 52426.12 | 52426.38 | 0.26 | 0.0004959% | 2790 | 2706.5 | -83.5 | -2.993% | 2021-03-22 01:00
Brampton | 2019 | 450919 | VAN KIRK DR AND BOVAIRD DR W | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Lemire, Blake | John Costa | 3500 | 7420.46 | 3920.46 | 112% | 3500 | 0 | -3500 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 27 | 47 | 20 | 74.07% | 2019-05-01 01:00
Brampton | 2019 | 450920 | 860 AND 870 NORTH PARK DR. | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Cavanaugh, Danny | Simon Evason | 69497 | 70706.36 | 1209.36 | 1.74% | 25018 | 19443.52 | -5574.48 | -22.28% | 41251 | 44684.74 | 3433.74 | 8.324% | 3228 | 3096 | -132 | -4.089% | 0 | 501 | 501 |  | 155 | 242 | 87 | 56.13% | 2019-11-26 01:00
Brampton | 2020 | 450929 | STEELES AVE AND SANDALWOOD PKW | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-07 01:00
Brampton | 2020 | 450930 | FINANCIAL DR & HERITAGE RD - Subdivision | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Nichol, Sandi | 647123.78 | 622554.34 | -24569.44 | -3.797% | 79678.11 | 91352.59 | 11674.48 | 14.65% | 40852.67 | 38175.46 | -2677.21 | -6.553% | 7644 | 11643.37 | 3999.37 | 52.32% | 518949 | 472254.64 | -46694.36 | -8.998% | 642 | 574 | -68 | -10.59% | 2020-07-07 01:00
Brampton | 2020 | 450931 | GREAT LAKE & SANDALWOOD PKY E | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 140556.99 | 93661.36 | -46895.63 | -33.36% | 17135.56 | 10385.14 | -6750.42 | -39.39% | 3485.27 | 3687.75 | 202.48 | 5.81% | 0 | 655.92 | 655.92 |  | 119936.16 | 1204.25 | -118731.91 | -99% | 119 | 62.75 | -56.25 | -47.27% | 2020-07-07 01:00
Brampton | 2020 | 450936 | PROFESSOR LAKE PKY/PRINCETON - SG | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes SG | Alectra Utilities | Richard Cuddy | 101638.31 | 4792.33 | -96845.98 | -95.28% | 21926.12 | 2916.58 | -19009.54 | -86.7% | 75032.19 | 0 | -75032.19 | -100% | 4680 | 0 | -4680 | -100% | 0 | 0 | 0 |  | 212 | 16 | -196 | -92.45% | 2020-10-30 01:00
Brampton | 2019 | 450937 | 25 VAN KIRK DR AND REGAN RD - tx | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A |  | No | Casey, Ryan | Simon Evason | 73670.79 | 51581.46 | -22089.33 | -29.98% | 45295.72 | 12659.24 | -32636.48 | -72.05% | 26098.07 | 23702.98 | -2395.09 | -9.177% | 2277 | 1280 | -997 | -43.79% | 0 | 0 | 0 |  | 128 | 98 | -30 | -23.44% | 2019-04-22 01:00
Brampton | 2019 | 450939 | 239 QUEEN ST E -tx | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Casey, Ryan | Simon Evason | 79182.91 | 15754.22 | -63428.69 | -80.1% | 46372.05 | 1016.37 | -45355.68 | -97.81% | 29152.86 | 0 | -29152.86 | -100% | 1933 | 0 | -1933 | -100% | 1725 | 0 | -1725 | -100% | 150 | 157.5 | 7.5 | 5% | 2019-12-21 01:00
Brampton | 2020 | 450940 | 2020 POLE RENEWAL- MCCAUL ST- CENTRE ST N TO KENNEDY DR N - 12 POLES | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes OH Mini Rebuild | Alectra Utilities | Reaburn, Jeff | 343351.83 | 302022.95 | -41328.88 | -12.04% | 18059.95 | 25924.97 | 7865.02 | 43.55% | 36665.36 | 45082.36 | 8417 | 22.96% | 840 | 72 | -768 | -91.43% | 287786.52 | 223633.8 | -64152.72 | -22.29% | 166 | 28.5 | -137.5 | -82.83% | 2020-10-20 01:00
Brampton | 2019 | 450941 | VARIOUS LOCATIONS BRAMPTON - Batch 2 - WP Replacement 2019 | 99 | COMPLETE | Estimate incorrect | Labour est. over | N/A |  | No | D'Ermes, Michael | Reaburn, Jeff | 157986.12 | 250023.06 | 92036.94 | 58.26% | 107912 | 33588.33 | -74323.67 | -68.87% | 18224.32 | 18322.24 | 97.92 | 0.5373% | 24247.9 | 24883 | 635.1 | 2.619% | 7601.9 | 16458 | 8856.1 | 116.5% | 1151 | 1247 | 96 | 8.341% | 2019-04-26 01:00
Brampton | 2019 | 450942 | VARIOUS LOCATIONS BRAMPTON - Batch 3 - WP Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | No | Casey, Ryan | John Costa | 79162.99 | 53304.76 | -25858.23 | -32.66% | 58000 | 348.43 | -57651.57 | -99.4% | 8602.49 | 9100.62 | 498.13 | 5.791% | 6268.5 | 0 | -6268.5 | -100% | 6292 | 0 | -6292 | -100% | 580 | 378.25 | -201.75 | -34.78% | 2019-07-12 01:00
Brampton | 2019 | 450944 | 10F6 Extension - MS-1 Elizabeth St 4.16kV Voltage Conversion - Ph5 - OH Portion | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 706774.86 | 650698.99 | -56075.87 | -7.934% | 37100 | 42553.75 | 5453.75 | 14.7% | 144301.53 | 149270.22 | 4968.69 | 3.443% | 0 | 18 | 18 |  | 525373.33 | 398176.22 | -127197.11 | -24.21% | 371 | 357 | -14 | -3.774% | 2019-12-05 01:00
Brampton | 2019 | 450945 | BOVAIRD,BRAMALEA TO TORBRAM - OH Portion | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 409445.62 | 402470.51 | -6975.11 | -1.704% | 24000 | 26068.67 | 2068.67 | 8.619% | 135445.62 | 97956.9 | -37488.72 | -27.68% | 0 | 144 | 144 |  | 250000 | 265715.9 | 15715.9 | 6.286% | 268 | 249 | -19 | -7.09% | 2019-12-05 01:00
Brampton | 2020 | 450947 | 5 SANDALWOOD PKY W - 3ph tx. repl | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes Tx | Alectra Utilities | Reaburn, Jeff | 25077.89 | 20454.04 | -4623.85 | -18.44% | 7410.78 | 3271.25 | -4139.53 | -55.86% | 16692.11 | 14404.1 | -2288.01 | -13.71% | 975 | 236.62 | -738.38 | -75.73% | 0 | 0 | 0 |  | 53 | 25 | -28 | -52.83% | 2020-09-23 01:00
Brampton | 2019 | 450948 | 9025 TORBRAM RD - tx - Capital | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Miller, Michael | Simon Evason | 25870.9 | 3015.54 | -22855.36 | -88.34% | 9380.6 | 486.64 | -8893.96 | -94.81% | 15157.3 | 0 | -15157.3 | -100% | 1333 | 0 | -1333 | -100% | 0 | 0 | 0 |  | 55 | 23.75 | -31.25 | -56.82% | 2019-12-21 01:00
Brampton | 2020 | 450949 | 35 AUTOMATIC - 3ph - pad mount tx | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes Tx | Alectra Utilities | Reaburn, Jeff | 36644.45 | 27938.16 | -8706.29 | -23.76% | 9178.32 | 4096.1 | -5082.22 | -55.37% | 26101.13 | 21589.87 | -4511.26 | -17.28% | 1365 | 933.53 | -431.47 | -31.61% | 0 | 0 | 0 |  | 44 | 39 | -5 | -11.36% | 2020-11-02 01:00
Brampton | 2020 | 450950 | 25 REGAN RD - 3ph tx. repl | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes Tx | Alectra Utilities | Reaburn, Jeff | 26045.49 | 19996.72 | -6048.77 | -23.22% | 7410.78 | 3237.93 | -4172.85 | -56.31% | 17659.71 | 15094.21 | -2565.5 | -14.53% | 975 | 338.03 | -636.97 | -65.33% | 0 | 0 | 0 |  | 53 | 26 | -27 | -50.94% | 2020-09-25 01:00
Brampton | 2019 | 450953 | 500 DEERHURST DRIVE | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Ferry, Rodnne | Simon Evason | 79719 | 70286.94 | -9432.06 | -11.83% | 31300 | 7800.73 | -23499.27 | -75.08% | 31347 | 27896.06 | -3450.94 | -11.01% | 5562 | 793 | -4769 | -85.74% | 11510 | 0 | -11510 | -100% | 276 | 259.5 | -16.5 | -5.978% | 2019-10-25 00:59
Brampton | 2019 | 450954 | Switchgear - 5 - County Court and Havelock | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | D'Ermes, Michael | Richard Cuddy | 95321.17 | 137693.28 | 42372.11 | 44.45% | 19978 | 33480.41 | 13502.41 | 67.59% | 74311.17 | 75463.32 | 1152.15 | 1.55% | 1032 | 3474 | 2442 | 236.6% | 0 | 272 | 272 |  | 233.5 | 241 | 7.5 | 3.212% | 2019-03-23 01:00
Brampton | 2019 | 450955 | Pole Replacement 2019 Batch #4 | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Casey, Ryan | Reaburn, Jeff | 32895.3 | 76868.37 | 43973.07 | 133.7% | 17987.43 | 27506.91 | 9519.48 | 52.92% | 4416.42 | 4207.55 | -208.87 | -4.729% | 4931.45 | 4587 | -344.45 | -6.985% | 5560 | 4236.5 | -1323.5 | -23.8% | 218 | 288.5 | 70.5 | 32.34% | 2019-02-06 01:00
Brampton | 2019 | 450956 | 20 BISCAYNE CRES | 99 | COMPLETE | Converted Project | BOM not accurate | Estimate incorrect |  | No | Bojanic, Dusan | Simon Evason | 48064.55 | 70213.01 | 22148.46 | 46.08% | 17200 | 140.91 | -17059.09 | -99.18% | 23003 | 25620.57 | 2617.57 | 11.38% | 3492 | 0 | -3492 | -100% | 4369.55 | 786.7 | -3582.85 | -82% | 174 | 59 | -115 | -66.09% | 2019-05-25
Brampton | 2019 | 450959 | PROFESSOR LK & FAIRWAY HEIGHTS | 99 | COMPLETE | Converted Project | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Mark Bobanovic | 1443064.91 | 1545985.56 | 102920.65 | 7.132% | 61204.16 | 158397.05 | 97192.89 | 158.8% | 0 | 474.05 | 474.05 |  | 2430 | 1675.5 | -754.5 | -31.05% | 1379430.75 | 1325920.65 | -53510.1 | -3.879% | 419 | 381.5 | -37.5 | -8.95% | 2019-12-21 01:00
Brampton | 2020 | 450960 | 7948 CHURCHVILLE RD | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-20 01:00
Brampton | 2022 | 450961 | GOREWAY DR | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | D'Ermes, Michael | Dre Danieli | 17.08 | 0 | -17.08 | -100% | 17.08 | 0 | -17.08 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-20 01:00
Brampton | 2021 | 450962 | BOVAIRD DR W AND BRISDALE DR | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Martin, Shane | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-20 01:00
Brampton | 2019 | 450964 | 247 MCMURCHY AVE S | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 78871.03 | 61159.37 | -17711.66 | -22.46% | 33218.01 | 14194.93 | -19023.08 | -57.27% | 32019.72 | 29513.78 | -2505.94 | -7.826% | 6009.9 | 5524.97 | -484.93 | -8.069% | 7623.4 | 9471.93 | 1848.53 | 24.25% | 214 | 157 | -57 | -26.64% | 2019-12-20 01:00
Brampton | 2019 | 450966 | BALMORAL DR/APPLEBY DR - SG | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Miller, Michael | Richard Cuddy | 106050.7 | 125767.32 | 19716.62 | 18.59% | 19976.2 | 21111.32 | 1135.12 | 5.682% | 78624 | 75396.64 | -3227.36 | -4.105% | 7450.5 | 4007 | -3443.5 | -46.22% | 0 | 272 | 272 |  | 222 | 210.25 | -11.75 | -5.293% | 2019-02-28 01:00
Brampton | 2019 | 450969 | Cable Injection - Brampton (F3-G3-H3) - 2019 | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Simon Evason | 1343485.79 | 1057639.71 | -285846.08 | -21.28% | 47947.2 | 119808.73 | 71861.53 | 149.9% | 98339.24 | 34520.68 | -63818.56 | -64.9% | 10320 | 872.45 | -9447.55 | -91.55% | 1186879.35 | 793055.99 | -393823.36 | -33.18% | 163 | 439.75 | 276.75 | 169.8% | 2019-12-21 01:00
Brampton | 2020 | 450971 | MS-1 ELIZABETH ST 4KV CONV PH3 - Part A | 99 | COMPLETE | Converted Project |  |  | Agostini, Robert | Yes | Alectra Utilities | Reaburn, Jeff | 610046.23 | 683199.75 | 73153.52 | 11.99% | 423668.85 | 359940.6 | -63728.25 | -15.04% | 117347.78 | 127363.9 | 10016.12 | 8.535% | 42251 | 121363.81 | 79112.81 | 187.2% | 26778.6 | 74531.44 | 47752.84 | 178.3% | 5000 | 4362.25 | -637.75 | -12.75% | 2020-09-03 01:00
Brampton | 2019 | 631720 | The Gore Rd and Queen St - STUB POLE INSTALLATION / D/G RELOCATION | 99 | COMPLETE | Cont Est Over | BOM not accurate | Estimate incorrect | Lacombe, Joel | CC | Robinson, David | John Costa | 46377.67 | 37161.57 | -9216.1 | -19.87% | 2393.12 | 5471.82 | 3078.7 | 128.6% | 1322.39 | 2673.05 | 1350.66 | 102.1% | 0 | 0 | 0 |  | 42662.16 | 29016.7 | -13645.46 | -31.98% | 10 | 23.5 | 13.5 | 135% | 2019-11-27 00:59
Brampton | 2020 | 631722 | 2020 INSULATOR REPLACEMENT PROGRAM | 99 | COMPLETE | Filler work | Filler work | Filler work | Agostini, Robert | Yes | Alectra Utilities | John Costa | 333136.87 | 310895.38 | -22241.49 | -6.676% | 168175.48 | 129440.22 | -38735.26 | -23.03% | 132396.39 | 127123.99 | -5272.4 | -3.982% | 32565 | 45745.01 | 13180.01 | 40.47% | 0 | 8586.16 | 8586.16 |  | 1543 | 1398.75 | -144.25 | -9.349% | 2020-12-18 01:00
Brampton | 2022 | 631755 | 2020 CABLE INJECTION PROJECT - GRIDS N2 | 95 | ANALYZE |  |  |  | Agostini, Robert | Yes | Casey, Ryan | Simon Evason | 857817.57 | 2733988.71 | 1876171.14 | 218.7% | 79170.45 | 348767.23 | 269596.78 | 340.5% | 66411.08 | 63111.84 | -3299.24 | -4.968% | 1960 | 19474.05 | 17514.05 | 893.6% | 710276.04 | 2302635.59 | 1592359.55 | 224.2% | 840 | 539.5 | -300.5 | -35.77% | 2023-01-04 01:00
Brampton | 2020 | 631757 | 27.6KV UNDERGROUND NEW SERVICE @ 50 COACHWORKS CRES | 99 | COMPLETE | Labour est. over | Estimate incorrect | Cont Est Under | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 85110.12 | 62207.3 | -22902.82 | -26.91% | 32022.2 | 15940.96 | -16081.24 | -50.22% | 31951.29 | 30706.66 | -1244.63 | -3.895% | 5319.6 | 1725 | -3594.6 | -67.57% | 15817.03 | 13834.68 | -1982.35 | -12.53% | 214 | 151.5 | -62.5 | -29.21% | 2020-01-21 01:00
Brampton | 2020 | 631934 | MATTAMY BOVAIRD CONDO (BLOCK 7) | 99 | COMPLETE | Estimate incorrect | BOM not accurate | Cont Est Under | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 313757.12 | 382885.19 | 69128.07 | 22.03% | 55164.02 | 25905.47 | -29258.55 | -53.04% | 21147.1 | 43453.22 | 22306.12 | 105.5% | 14075 | 3263.06 | -10811.94 | -76.82% | 223371 | 2435.36 | -220935.64 | -98.91% | 431 | 205.75 | -225.25 | -52.26% | 2020-09-18 01:00
Brampton | 2020 | 632351 | MS10 Brampton Design | 99 | COMPLETE | Scope – Const | Cont Est Under | Labour est. under | Dehaijle, Carlton | No | Alectra Utilities | Richard Cuddy | 134163.07 | 184497.91 | 50334.84 | 37.52% | 61637.43 | 82396.87 | 20759.44 | 33.68% | 24752.5 | 24076.79 | -675.71 | -2.73% | 9973.14 | 23243.79 | 13270.65 | 133.1% | 37800 | 54780.46 | 16980.46 | 44.92% | 490 | 901.25 | 411.25 | 83.93% | 2020-12-14 01:00
Brampton | 2021 | 632681 | 200 Largerfeld Dr and Creditview Rd - Block 7 | 95 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 67181.83 | 66679.83 | -502 | -0.7472% | 23984.49 | 15887.22 | -8097.27 | -33.76% | 35434.53 | 37321.77 | 1887.24 | 5.326% | 5068 | 5529.29 | 461.29 | 9.102% | 23424.12 | 7941.55 | -15482.57 | -66.1% | 172 | 186.5 | 14.5 | 8.43% | 2021-04-30
Brampton | 2020 | 632754 | 100 MARTIN BYRNE - 27.6KV SUPPLY TO 750 KVA TX | 98 | COMPLETE | Cont Est Under | Estimate incorrect | Cont Est Under | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 82227.21 | 83370.52 | 1143.31 | 1.39% | 33692.07 | 25739.73 | -7952.34 | -23.6% | 24387.06 | 25739.77 | 1352.71 | 5.547% | 6048.9 | 4476 | -1572.9 | -26% | 18099.18 | 27415.02 | 9315.84 | 51.47% | 222 | 255.5 | 33.5 | 15.09% | 2020-04-28
Brampton | 2021 | 632755 | #10 PEEL CENTRE DR-FEEDER CABLE ENCROACHMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 155732.34 | 141178.82 | -14553.52 | -9.345% | 19271.1 | 35984.32 | 16713.22 | 86.73% | 0 | 0 | 0 |  | 5400 | 5294.02 | -105.98 | -1.963% | 131061.24 | 99900.48 | -31160.76 | -23.78% | 160 | 156.5 | -3.5 | -2.188% | 2021-11-19 01:00
Brampton | 2022 | 632768 | 2020 CABLE INJECTION PROJECT - GRID J3 | 95 | ANALYZE |  |  |  | Agostini, Robert | Yes | Casey, Ryan | Simon Evason | 723893.72 | 2035134.37 | 1311240.65 | 181.1% | 68869.96 | 262506.89 | 193636.93 | 281.2% | 71366.52 | 48057.74 | -23308.78 | -32.66% | 1750 | 15677.9 | 13927.9 | 795.9% | 581907.24 | 1708891.84 | 1126984.6 | 193.7% | 708 | 431.5 | -276.5 | -39.05% | 2023-01-04 01:00
Brampton | 2021 | 632769 | 2020 CABLE INJECTION PROJECT - GRID K3 | 99 | COMPLETE | N/A |  |  | Agostini, Robert | Yes | Casey, Ryan | Simon Evason | 327812.53 | 551318.34 | 223505.81 | 68.18% | 33170.97 | 93022.67 | 59851.7 | 180.4% | 33043.52 | 16037.32 | -17006.2 | -51.47% | 980 | 9035.64 | 8055.64 | 822% | 260618.04 | 433222.71 | 172604.67 | 66.23% | 334 | 218.5 | -115.5 | -34.58% | 2021-12-06 01:00
Brampton | 2022 | 632771 | 2020 CABLE INJECTION PROJECT - GRID I3 | 99 | COMPLETE | N/A |  |  | Agostini, Robert | Yes | Casey, Ryan | Simon Evason | 516721.51 | 822858.35 | 306136.84 | 59.25% | 49518.63 | 134731.33 | 85212.7 | 172.1% | 43008.28 | 89689.65 | 46681.37 | 108.5% | 840 | 4741.54 | 3901.54 | 464.5% | 423354.6 | 593695.83 | 170341.23 | 40.24% | 746 | 724 | -22 | -2.949% | 2022-05-30 01:00
Brampton | 2022 | 632772 | 4KV CONVERSION - PHASE 8 | 99 | COMPLETE | Cont Est Over | Labour est. under | Material Under Estimated | Agostini, Robert | Yes | Casey, Ryan | AW Group | 1942931.54 | 1974477.68 | 31546.14 | 1.624% | 35111.74 | 259286.6 | 224174.86 | 638.5% | 207086.77 | 306534.83 | 99448.06 | 48.02% | 3200 | 2114.55 | -1085.45 | -33.92% | 1697533.03 | 1406541.7 | -290991.33 | -17.14% | 200 | 230.5 | 30.5 | 15.25% | 2022-11-21 01:00
Brampton | 2021 | 632773 | 4KV CONVERSION - PHASE 2B | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 514493.35 | 471806.61 | -42686.74 | -8.297% | 192432.63 | 178296.1 | -14136.53 | -7.346% | 57081.28 | 61103.15 | 4021.87 | 7.046% | 57762 | 75278.27 | 17516.27 | 30.32% | 207217.44 | 157129.09 | -50088.35 | -24.17% | 1558 | 1561 | 3 | 0.1926% | 2021-09-15 01:00
Brampton | 2021 | 632799 | 4KV CONVERSION PH7-BRAMPTON - 2021 | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Miller, Michael | Reaburn, Jeff | 1129992.47 | 1143521.75 | 13529.28 | 1.197% | 338340.06 | 452551.36 | 114211.3 | 33.76% | 106964.5 | 83757.01 | -23207.49 | -21.7% | 96420 | 121935.51 | 25515.51 | 26.46% | 588267.91 | 485277.87 | -102990.04 | -17.51% | 3628 | 3978.25 | 350.25 | 9.654% | 2021-08-23 01:00
Brampton | 2019 | 632815 | THE GORE RD- UNDERGROUND CABLE RELOCATION | 99 | COMPLETE | Cont Est Over | Estimate incorrect | BOM not accurate |  | CC | Lemire, Blake | Nichol, Sandi | 45305.73 | 47281.75 | 1976.02 | 4.362% | 1897.28 | 4189.54 | 2292.26 | 120.8% | 6441.13 | 10445.55 | 4004.42 | 62.17% | 0 | 0 | 0 |  | 36967.32 | 32646.66 | -4320.66 | -11.69% | 12 | 0 | -12 | -100% | 2019-11-05 00:59
Brampton | 2020 | 632823 | FEEDER CABLE REPLACEMENT GRID J4 | 99 | COMPLETE | Cont Est Under | N/A | N/A | Agostini, Robert | Yes | Alectra Utilities | Mark Bobanovic | 681177.58 | 716586.84 | 35409.26 | 5.198% | 44612.5 | 100921.44 | 56308.94 | 126.2% | 0 | 0 | 0 |  | 390 | 1450.01 | 1060.01 | 271.8% | 636175.08 | 614215.39 | -21959.69 | -3.452% | 170 | 241.5 | 71.5 | 42.06% | 2020-12-14 01:00
Brampton | 2020 | 632874 | PROFESSOR'S LAKE PKWY FEEDER CABLE REPLACEMENT -ELECTRICAL PHASE | 99 | COMPLETE | Estimate incorrect | Cont Est Over | Material Req incorrectly | Agostini, Robert | Yes | Alectra Utilities | Richard Cuddy | 898331.81 | 808360.91 | -89970.9 | -10.02% | 194766.44 | 133523.68 | -61242.76 | -31.44% | 44904.61 | 126072.59 | 81167.98 | 180.8% | 23400 | 38553.99 | 15153.99 | 64.76% | 635260.76 | 510210.65 | -125050.11 | -19.68% | 1815 | 902.75 | -912.25 | -50.26% | 2020-09-25 01:00
Brampton | 2022 | 632899 | 4KV CONVERSION - PHASE 6 | 99 | COMPLETE | Vehicle Under Estimated | Labour est. over | Material Under Estimated | Agostini, Robert | Yes | D'Ermes, Michael | Reaburn, Jeff | 1468555.34 | 1586515.44 | 117960.1 | 8.032% | 635301.77 | 614787.33 | -20514.44 | -3.229% | 140619.57 | 157573.75 | 16954.18 | 12.06% | 117372 | 238186.61 | 120814.61 | 102.9% | 575262 | 575967.75 | 705.75 | 0.1227% | 5272 | 6100.5 | 828.5 | 15.72% | 2022-12-28 01:00
Brampton | 2021 | 632971 | JOINT USE PERMIT #HB2019-001 - BOVAIRD DRIVE WEST - BRAMPTON | 99 | COMPLETE | Labour est. over | BOM not accurate | Cont Est Over | O'Gay, Brian | No | Martin, Shane | John Costa | 18704.55 | 15392.42 | -3312.13 | -17.71% | 6490.15 | 4720.84 | -1769.31 | -27.26% | 1257.7 | 2282.2 | 1024.5 | 81.46% | 1523.2 | 1192 | -331.2 | -21.74% | 9433.5 | 7197.38 | -2236.12 | -23.7% | 79.8 | 44.5 | -35.3 | -44.24% | 2021-04-01 01:00
Brampton | 2021 | 632972 | JOINT USE PERMIT #HB2019-002 - GOREWAY DRIVE - BRAMPTON | 99 | COMPLETE | Scope – Eng | Labour est. over |  | O'Gay, Brian | No | Martin, Shane | John Costa | 24103.48 | 19154.6 | -4948.88 | -20.53% | 11339.6 | 9876.14 | -1463.46 | -12.91% | 1466.38 | 2255.25 | 788.87 | 53.8% | 3021.5 | 3168 | 146.5 | 4.849% | 8276 | 3855.21 | -4420.79 | -53.42% | 158.8 | 112 | -46.8 | -29.47% | 2021-06-04 01:00
Brampton | 2021 | 632973 | JOINT USE PERMIT #HB2019-003 - HWY 50 - BRAMPTON | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Martin, Shane | John Costa | 37990.03 | 37143.04 | -846.99 | -2.23% | 11491.55 | 17800.5 | 6308.95 | 54.9% | 8850 | 4120.41 | -4729.59 | -53.44% | 2181.8 | 6495 | 4313.2 | 197.7% | 15466.68 | 8727.13 | -6739.55 | -43.57% | 83.02 | 225.75 | 142.73 | 171.9% | 2021-04-26
Brampton | 2020 | 633119 | Tx Replacement Grid F3 - 7 min pads | 99 | COMPLETE | Est. Int. - Act. External | Scope change - unforeseen | Scope – Const | Agostini, Robert | Yes Tx. | Alectra Utilities | John Costa | 80438.41 | 43193.7 | -37244.71 | -46.3% | 25415.74 | 8201.46 | -17214.28 | -67.73% | 43430.47 | 24708.53 | -18721.94 | -43.11% | 2828 | 181.24 | -2646.76 | -93.59% | 8764.2 | 10102.47 | 1338.27 | 15.27% | 16 | 111 | 95 | 593.8% | 2020-10-30 01:00
Brampton | 2020 | 633120 | 2020 SWITCHGEAR RENEWAL - SITE# 213 - 1 MILKWEED | 99 | COMPLETE | Labour est. over |  |  | Agostini, Robert | No | Alectra Utilities | Nichol, Sandi | 108274.98 | 95154.89 | -13120.09 | -12.12% | 24263.21 | 14207.12 | -10056.09 | -41.45% | 80083.77 | 77371.86 | -2711.91 | -3.386% | 3928 | 3575.91 | -352.09 | -8.964% | 0 | 0 | 0 |  | 212 | 149 | -63 | -29.72% | 2020-03-17 01:00
Brampton | 2020 | 633122 | 2020 SWITCHGEAR REPLACEMENTS - SITE# 174 -223 CORPORATION DR | 99 | COMPLETE | Cont Est Over | N/A | N/A | Agostini, Robert | Yes SG | Alectra Utilities | Richard Cuddy | 106353.53 | 97376.28 | -8977.25 | -8.441% | 25332.26 | 15392.86 | -9939.4 | -39.24% | 76341.27 | 75716.86 | -624.41 | -0.8179% | 4680 | 5950.74 | 1270.74 | 27.15% | 0 | 315.82 | 315.82 |  | 160 | 149.5 | -10.5 | -6.562% | 2020-11-06 01:00
Brampton | 2020 | 633123 | 2020 SWITCHGEAR REPLACEMENTS - SITE# 221 - 30 PEDIGREE CRT | 99 | COMPLETE | Cont Est Over | Cont Est Over | N/A | Agostini, Robert | Yes SG | Alectra Utilities | Richard Cuddy | 105763.07 | 85137.66 | -20625.41 | -19.5% | 25687.68 | 7109.89 | -18577.79 | -72.32% | 75395.39 | 76355.61 | 960.22 | 1.274% | 4680 | 1672.16 | -3007.84 | -64.27% | 0 | 0 | 0 |  | 212 | 48.5 | -163.5 | -77.12% | 2020-10-17 01:00
Brampton | 2020 | 633124 | 2020 SWITCHGEAR REPLACEMENTS - SITE# 270 - 2 GROUSE LANE | 99 | COMPLETE | Cont Est Over | BOM not accurate | N/A | Agostini, Robert | Yes SG | Alectra Utilities | Richard Cuddy | 105763.07 | 108735.54 | 2972.47 | 2.81% | 25687.68 | 17752.88 | -7934.8 | -30.89% | 75395.39 | 84447.92 | 9052.53 | 12.01% | 4680 | 6534.74 | 1854.74 | 39.63% | 0 | 0 | 0 |  | 212 | 183.5 | -28.5 | -13.44% | 2020-09-25 01:00
Brampton | 2020 | 633147 | 2020 TRANSFORMER REPLACEMENTS-GRID H3 - 6 min pads | 99 | COMPLETE | Est. Int. - Act. External | Est. Int. - Act. External | N/A | Agostini, Robert | Yes Tx. | Alectra Utilities | John Costa | 85460.92 | 57732.66 | -27728.26 | -32.45% | 31524.84 | 4605.83 | -26919.01 | -85.39% | 48944.08 | 41013.94 | -7930.14 | -16.2% | 4992 | 0 | -4992 | -100% | 0 | 12112.89 | 12112.89 |  | 13 | 2 | -11 | -84.62% | 2020-11-24 01:00
Brampton | 2020 | 633148 | 2020 TRANSFORMER REPLACEMENTS-GRID B3 - 1ph repl | 99 | COMPLETE | Est. Int. - Act. External | Est. Int. - Act. External | N/A | Agostini, Robert | Yes Tx | Alectra Utilities | John Costa | 43104.11 | 35257.28 | -7846.83 | -18.2% | 18868.09 | 5084.02 | -13784.07 | -73.05% | 21628.02 | 23122.81 | 1494.79 | 6.911% | 2608 | 0 | -2608 | -100% | 0 | 7050.45 | 7050.45 |  | 142 | 10.5 | -131.5 | -92.61% | 2020-10-30 01:00
Brampton | 2020 | 633156 | JOINT USE PERMIT #HB2019-007 - RUTHERFORD ROAD SOUTH - BRAMPTON | 99 | COMPLETE | Scope change - unforeseen | Scope change - unforeseen | Scope change - unforeseen | O'Gay, Brian | No | Alectra Utilities | Brian Erskine | 6640.16 | 4213.72 | -2426.44 | -36.54% | 3843.48 | 1849 | -1994.48 | -51.89% | 64.69 | 0 | -64.69 | -100% | 355.99 | 224.39 | -131.6 | -36.97% | 2376 | 2140.33 | -235.67 | -9.919% | 36 | 12 | -24 | -66.67% | 2020-02-15 00:59
Brampton | 2020 | 633230 | TEMPORARILY REMOVE SPAN GUYS AND DOWN GUYS, COUNTRYSIDE DR | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Alectra Utilities | Reaburn, Jeff | 0 | 268.86 | 268.86 |  | 0 | 250.86 | 250.86 |  | 0 | 0 | 0 |  | 0 | 18 | 18 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2022-10-28 01:00
Brampton | 2020 | 633243 | Kennedy Dr N and Williams Pkwy - 2020 SWITCH REPLACEMENTS - SW# 20-1777 | 99 | COMPLETE | Est. Ext. - Act. Internal | Scope – Const | N/A | Agostini, Robert | Yes OH SW | Alectra Utilities | John Costa | 128709.49 | 107650.68 | -21058.81 | -16.36% | 56929.97 | 14839.76 | -42090.21 | -73.93% | 55081.04 | 58345.51 | 3264.47 | 5.927% | 11130 | 2779.03 | -8350.97 | -75.03% | 5568.48 | 31686.38 | 26117.9 | 469% | 540 | 98.5 | -441.5 | -81.76% | 2020-12-11 01:00
Brampton | 2020 | 633244 | McLaughlin Rd and Kingknoll Dr. 2020 SWITCH REPLACEMENTS - SW# 20-396 | 99 | COMPLETE | Estimate incorrect | Cont Est Under | N/A | Agostini, Robert | Yes OH SW | Alectra Utilities | John Costa | 102804.04 | 102231.38 | -572.66 | -0.557% | 42391.18 | 30421.83 | -11969.35 | -28.24% | 53656.8 | 58098.35 | 4441.55 | 8.278% | 6060 | 11254.2 | 5194.2 | 85.71% | 696.06 | 2457 | 1760.94 | 253% | 374 | 348 | -26 | -6.952% | 2020-11-18 01:00
Brampton | 2020 | 633245 | 2020 SWITCH REPLACEMENTS - SW# 20-270 - Vodden and Main St | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Agostini, Robert | Yes OH SW | Alectra Utilities | John Costa | 103057.22 | 118260.15 | 15202.93 | 14.75% | 42473.26 | 45305.83 | 2832.57 | 6.669% | 50122.9 | 55605.28 | 5482.38 | 10.94% | 9765 | 15299.04 | 5534.04 | 56.67% | 696.06 | 2050 | 1353.94 | 194.5% | 370 | 524.5 | 154.5 | 41.76% | 2020-07-27 01:00
Brampton | 2020 | 633247 | 2020 SWITCH REPLACEMENTS - SW# 20-1414 - 144 Kennedy Rd S | 99 | COMPLETE | Cont Est Over | Cont Est Over | N/A | Agostini, Robert | No | Alectra Utilities | Reaburn, Jeff | 78719 | 64173.83 | -14545.17 | -18.48% | 25507.44 | 18522.21 | -6985.23 | -27.39% | 44491.56 | 42223.5 | -2268.06 | -5.098% | 8720 | 3428.12 | -5291.88 | -60.69% | 0 | 0 | 0 |  | 260 | 199.5 | -60.5 | -23.27% | 2020-08-12 01:00
Brampton | 2021 | 633375 | C1-6 - 1465 MAYFIELD RD - 27.6KV U/G RADIAL 750KVA | 95 | COMPLETE | Labour est. over | Cont Est Over |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 84130.88 | 62418.22 | -21712.66 | -25.81% | 33838.61 | 16520.26 | -17318.35 | -51.18% | 37581.07 | 36319.64 | -1261.43 | -3.357% | 5662.8 | 1702 | -3960.8 | -69.94% | 7048.4 | 7876.32 | 827.92 | 11.75% | 220 | 137 | -83 | -37.73% | 2021-08-20 01:00
Brampton | 2020 | 633436 | POLE RELOCATION, HERITAGE ROAD | 99 | COMPLETE | Labour est. over | Labour est. over | No Feedback from Const | Pelleja, Emily | No | Alectra Utilities | Nichol, Sandi | 31168.86 | 17582.77 | -13586.09 | -43.59% | 19714.19 | 10500.39 | -9213.8 | -46.74% | 3566.43 | 3340.26 | -226.17 | -6.342% | 5104 | 3007.74 | -2096.26 | -41.07% | 2784.24 | 734.38 | -2049.86 | -73.62% | 179.2 | 101 | -78.2 | -43.64% | 2020-02-15 01:00
Brampton | 2021 | 633438 | 2300 NORTH PARK DRIVE | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 94477.61 | 88568.14 | -5909.47 | -6.255% | 30313.4 | 12970.37 | -17343.03 | -57.21% | 54057.89 | 58686.42 | 4628.53 | 8.562% | 0 | 2016 | 2016 |  | 10106.32 | 14895.35 | 4789.03 | 47.39% | 176 | 177.5 | 1.5 | 0.8523% | 2021-03-05 01:00
Brampton | 2020 | 633463 | COUNTRYSIDE DR - TEMPORARILY REMOVE SPAN GUYS AND DOWN GUYS | 99 | COMPLETE | Cont Est Over | Cont Est Over | Estimate incorrect | Lacombe, Joel | No | Alectra Utilities | John Costa | 10378.99 | 3750.92 | -6628.07 | -63.86% | 9472.65 | 2606.69 | -6865.96 | -72.48% | 138.76 | 281.73 | 142.97 | 103% | 0 | 862.5 | 862.5 |  | 767.58 | 0 | -767.58 | -100% | 86 | 32.5 | -53.5 | -62.21% | 2020-06-18 01:00
Brampton | 2019 | 633484 | POLE RELOCATION AT 6401 MAYFIELD RD | 99 | COMPLETE | Estimate incorrect | Vehicle Under Estimated | Estimate incorrect | Lacombe, Joel | No | Robinson, David | John Costa | 21090.04 | 21703.95 | 613.91 | 2.911% | 13975.77 | 10102.96 | -3872.81 | -27.71% | 4162.15 | 4182.99 | 20.84 | 0.5007% | 1560 | 5268 | 3708 | 237.7% | 1392.12 | 2150 | 757.88 | 54.44% | 129.5 | 124 | -5.5 | -4.247% | 2019-11-08 01:00
Brampton | 2021 | 633498 | 633498 - JOINT USE PERMIT HB2019-009 | 99 | COMPLETE | Labour est. over | BOM not accurate | Scope change - unforeseen | O'Gay, Brian | No | Martin, Shane | Richard Cuddy | 14141.92 | 10341.42 | -3800.5 | -26.87% | 8884.95 | 3236.61 | -5648.34 | -63.57% | 660.43 | 1742.38 | 1081.95 | 163.8% | 1207.5 | 664 | -543.5 | -45.01% | 3389.04 | 4698.43 | 1309.39 | 38.64% | 64.66 | 16.5 | -48.16 | -74.48% | 2021-02-12 01:00
Brampton | 2022 | 633501 | JOINT USE PERMIT HB2019-010- THE GORE ROAD- KELWAYS CIRCLE TO HWY 50 | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Under Estimated | O'Gay, Brian | No | Martin, Shane | Justin Gregoris | 34070.14 | 18887.97 | -15182.17 | -44.56% | 18086.29 | 4437.61 | -13648.68 | -75.46% | 1996.71 | 3192.22 | 1195.51 | 59.87% | 3387.14 | 0 | -3387.14 | -100% | 10600 | 11258.14 | 658.14 | 6.209% | 0 | 9 | 9 |  | 2022-04-29
Brampton | 2022 | 633513 | 26.6 KV SUPPLY TO 750 KVA TX AT 100 MANETT CRES. - FILE# F3-100, REF# NS00905810 | 95 | COMPLETE | Cont Est Over | N/A | N/A | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 89923.66 | 76674.59 | -13249.07 | -14.73% | 32220.24 | 19972.7 | -12247.54 | -38.01% | 35765.56 | 41270.78 | 5505.22 | 15.39% | 5733 | 4516.39 | -1216.61 | -21.22% | 16204.86 | 10912.74 | -5292.12 | -32.66% | 216 | 210 | -6 | -2.778% | 2022-01-10 01:00
Brampton | 2020 | 633529 | MS-1 ELIZABETH ST 4KV CONV PH3 - Part B Laterals | 99 | COMPLETE | Estimate incorrect | Scope change - unforeseen | BOM not accurate | Agostini, Robert | Yes | Alectra Utilities | Reaburn, Jeff | 1006125.68 | 1021715.11 | 15589.43 | 1.549% | 703221.54 | 513496.66 | -189724.88 | -26.98% | 166605.24 | 184750.95 | 18145.71 | 10.89% | 52103 | 194407.08 | 142304.08 | 273.1% | 84195.9 | 129060.42 | 44864.52 | 53.29% | 6053 | 6158.75 | 105.75 | 1.747% | 2020-11-20 01:00
Brampton | 2021 | 633530 | 4KV CONV PH3C - APARTMENTS | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Reaburn, Jeff | 885776.78 | 881604.5 | -4172.28 | -0.471% | 145103.84 | 171663.13 | 26559.29 | 18.3% | 49830.91 | 54199.7 | 4368.79 | 8.767% | 21768 | 25920.44 | 4152.44 | 19.08% | 669074.03 | 629821.23 | -39252.8 | -5.867% | 1140 | 622 | -518 | -45.44% | 2021-12-17 01:00
Brampton | 2021 | 633564 | 2021 TX RENEWAL-GRID J2-5 TX | 99 | COMPLETE | Scope change - unforeseen | Cont Est Under | Vehicle Under Estimated | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 53931.06 | 70292.99 | 16361.93 | 30.34% | 13663.36 | 12157.76 | -1505.6 | -11.02% | 33885.7 | 30773.57 | -3112.13 | -9.184% | 2062 | 3953.89 | 1891.89 | 91.75% | 4320 | 23407.77 | 19087.77 | 441.8% | 108 | 114 | 6 | 5.556% | 2021-12-16 01:00
Brampton | 2020 | 633565 | 2020 TRANSFORMER REPLACEMENTS-GRID D2 | 99 | COMPLETE | Est. Int. - Act. External | Scope change - unforeseen | N/A | Agostini, Robert | Yes Tx | Alectra Utilities | John Costa | 28472.72 | 32475.2 | 4002.48 | 14.06% | 9327.43 | 1574.49 | -7752.94 | -83.12% | 17933.29 | 17092.44 | -840.85 | -4.689% | 1212 | 0 | -1212 | -100% | 0 | 13808.27 | 13808.27 |  | 66 | 0 | -66 | -100% | 2020-10-30 01:00
Brampton | 2020 | 633566 | 2020 TRANSFORMER REPLACEMENTS-GRID D3 | 99 | COMPLETE | Scope change - unforeseen | Est. Int. - Act. External | BOM not accurate | Agostini, Robert | Yes Tx | Alectra Utilities | John Costa | 10352.76 | 13174.58 | 2821.82 | 27.26% | 3693.4 | 1085.8 | -2607.6 | -70.6% | 6255.36 | 5990.2 | -265.16 | -4.239% | 404 | 0 | -404 | -100% | 0 | 6098.58 | 6098.58 |  | 22 | 0 | -22 | -100% | 2020-10-30 01:00
Brampton | 2021 | 633567 | 2021 TX RENEWAL-GRID E3-3 TX | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 33965.6 | 32448.47 | -1517.13 | -4.467% | 8257.04 | 7408.55 | -848.49 | -10.28% | 20218.56 | 18241.82 | -1976.74 | -9.777% | 1170 | 2775.32 | 1605.32 | 137.2% | 4320 | 4022.78 | -297.22 | -6.88% | 60 | 70 | 10 | 16.67% | 2021-09-02 01:00
Brampton | 2021 | 633568 | 2021 TX RENEWAL-GRID I2-2 TX | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 24953.29 | 22400.05 | -2553.24 | -10.23% | 6317.82 | 5792.71 | -525.11 | -8.312% | 13535.47 | 11175.97 | -2359.5 | -17.43% | 780 | 1069.26 | 289.26 | 37.08% | 4320 | 4362.11 | 42.11 | 0.9748% | 40 | 39 | -1 | -2.5% | 2021-09-09 01:00
Brampton | 2021 | 633570 | 2021 TX RENEWAL-GRID I3-1 TX | 99 | COMPLETE | Under 10% | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 13281.61 | 11964.31 | -1317.3 | -9.918% | 4048.52 | 3316.76 | -731.76 | -18.07% | 6683.09 | 6074.89 | -608.2 | -9.101% | 390 | 570.27 | 180.27 | 46.22% | 2160 | 2002.39 | -157.61 | -7.297% | 20 | 26 | 6 | 30% | 2021-08-31 01:00
Brampton | 2021 | 633571 | 2021 TX RENEWAL-GRID J3-2 TX | 99 | COMPLETE | Labour est. under | Scope change - unforeseen | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 17460.3 | 23611.62 | 6151.32 | 35.23% | 3675.5 | 6923.31 | 3247.81 | 88.36% | 13004.8 | 13434.41 | 429.61 | 3.303% | 780 | 244.74 | -535.26 | -68.62% | 0 | 3009.16 | 3009.16 |  | 40 | 68.5 | 28.5 | 71.25% | 2021-10-21 01:00
Brampton | 2021 | 633572 | 2021 TX RENEWAL-GRID F4-1 TX | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 11631.69 | 12342.07 | 710.38 | 6.107% | 4333.55 | 4466.19 | 132.64 | 3.061% | 6504.14 | 6586.24 | 82.1 | 1.262% | 794 | 0 | -794 | -100% | 0 | 1289.64 | 1289.64 |  | 45 | 50 | 5 | 11.11% | 2021-10-22 01:00
Brampton | 2021 | 633573 | 2021 TX RENEWAL-GRID F5- 1 TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 11424.74 | 9603.98 | -1820.76 | -15.94% | 4333.55 | 3101.71 | -1231.84 | -28.43% | 6297.19 | 5932 | -365.19 | -5.799% | 794 | 570.27 | -223.73 | -28.18% | 0 | 0 | 0 |  | 41 | 26 | -15 | -36.59% | 2021-10-19 01:00
Brampton | 2021 | 633574 | 2021 TX RENEWAL-GRID G2-7 TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 74363.84 | 62236.55 | -12127.29 | -16.31% | 23427.51 | 13043.79 | -10383.72 | -44.32% | 45378.33 | 41148.76 | -4229.57 | -9.321% | 5558 | 8044 | 2486 | 44.73% | 0 | 0 | 0 |  | 147 | 166 | 19 | 12.93% | 2021-08-31 01:00
Brampton | 2021 | 633576 | 2021 TX RENEWAL-GRID G5-1 TX | 99 | COMPLETE | Labour est. under | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 11976.85 | 9598.54 | -2378.31 | -19.86% | 4299.81 | 3463.78 | -836.03 | -19.44% | 6761.04 | 5932 | -829.04 | -12.26% | 916 | 202.76 | -713.24 | -77.86% | 0 | 0 | 0 |  | 21 | 27.5 | 6.5 | 30.95% | 2021-10-18 01:00
Brampton | 2020 | 633577 | 2020 TRANSFORMER REPLACEMENTS-GRID H2 - 2 mini pads | 99 | COMPLETE | Est. Int. - Act. External | Scope change - unforeseen | N/A | Agostini, Robert | Yes Tx. | Alectra Utilities | John Costa | 19829.16 | 11817.9 | -8011.26 | -40.4% | 6510.43 | 3180.08 | -3330.35 | -51.15% | 12510.73 | 6074.72 | -6436.01 | -51.44% | 808 | 740 | -68 | -8.416% | 0 | 1823.1 | 1823.1 |  | 4 | 23.5 | 19.5 | 487.5% | 2020-10-30 01:00
Brampton | 2021 | 633578 | 2020 TX RENEWAL-GRID I3-2 TX | 99 | COMPLETE | Est. Ext. - Act. Internal | Scope – Const | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 37195.32 | 55370.2 | 18174.88 | 48.86% | 10594.69 | 8876.87 | -1717.82 | -16.21% | 13472.63 | 14585.25 | 1112.62 | 8.258% | 1248 | 0 | -1248 | -100% | 11880 | 31908.08 | 20028.08 | 168.6% | 80 | 8.5 | -71.5 | -89.38% | 2021-12-16 01:00
Brampton | 2021 | 633579 | 2021 TX RENEWAL-GRID J3-4 TX | 99 | COMPLETE | Labour est. over | Cont Est Under | BOM not accurate | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 61149.95 | 50180.9 | -10969.05 | -17.94% | 20517.93 | 14050.77 | -6467.16 | -31.52% | 25752.02 | 22841.88 | -2910.14 | -11.3% | 6240 | 3057.29 | -3182.71 | -51% | 8640 | 10230.96 | 1590.96 | 18.41% | 160 | 113 | -47 | -29.38% | 2021-08-04 01:00
Brampton | 2020 | 633581 | 2020 TRANSFORMER REPLACEMENTS-GRID K3 - 3 min units | 99 | COMPLETE | Material Req incorrectly | Scope change - unforeseen | Scope change - unforeseen | Agostini, Robert | Yes Tx. | Alectra Utilities | John Costa | 47535.21 | 22427.7 | -25107.51 | -52.82% | 11831.13 | 2141.05 | -9690.08 | -81.9% | 33832.08 | 16562.89 | -17269.19 | -51.04% | 1872 | 0 | -1872 | -100% | 0 | 3723.76 | 3723.76 |  | 101 | 0 | -101 | -100% | 2020-10-30 01:00
Brampton | 2020 | 633582 | 2020 TRANSFORMER REPLACEMENTS-GRID K4 | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 2102.07 | -0.27 | -2102.34 | -100% | 2102.07 | -0.27 | -2102.34 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2020-10-30 01:00
Brampton | 2020 | 633583 | 2020 TRANSFORMER REPLACEMENTS-GRID O3 - 1 min pad | 99 | COMPLETE | Material Req incorrectly | Scope change - unforeseen | Scope change - unforeseen | Agostini, Robert | Yes Tx. | Alectra Utilities | John Costa | 10178.11 | 56437.53 | 46259.42 | 454.5% | 3693.4 | 1207.53 | -2485.87 | -67.31% | 6080.71 | 53487.55 | 47406.84 | 779.6% | 404 | 0 | -404 | -100% | 0 | 1742.45 | 1742.45 |  | 22 | 0 | -22 | -100% | 2020-10-30 01:00
Brampton | 2020 | 633586 | Miss Rd and Lion Heead Golf Club Rd - 2020 DISTRIBUTION AUTOMATION- SW# 20-XXX | 99 | COMPLETE | Labour est. over | BOM not accurate | Labour est. over | Agostini, Robert | Yes OH SW | Alectra Utilities | John Costa | 83933.26 | 82421.37 | -1511.89 | -1.801% | 30903.88 | 23369.55 | -7534.33 | -24.38% | 49059.38 | 52492.62 | 3433.24 | 6.998% | 3970 | 6559.2 | 2589.2 | 65.22% | 0 | 0 | 0 |  | 254 | 260.5 | 6.5 | 2.559% | 2020-12-01 01:00
Brampton | 2020 | 633636 | 2020 EMERGING PROJECT - VAULT T3588 - kennedy Rd S | 99 | COMPLETE | Scope change - unforeseen | Labour est. under | N/A | Agostini, Robert | No | Alectra Utilities | Reaburn, Jeff | 386732.55 | 407470.58 | 20738.03 | 5.362% | 57864.05 | 81947.86 | 24083.81 | 41.62% | 29767.74 | 28267.17 | -1500.57 | -5.041% | 5614 | 6192.5 | 578.5 | 10.3% | 293486.76 | 291063.05 | -2423.71 | -0.8258% | 270.5 | 470 | 199.5 | 73.75% | 2020-09-18 01:00
Brampton | 2020 | 633664 | POLE LINE RECOVERY | 99 | COMPLETE | Labour est. over | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | John Costa | 13294.84 | 11139.32 | -2155.52 | -16.21% | 12670.84 | 9980.11 | -2690.73 | -21.24% | 0 | 295.21 | 295.21 |  | 624 | 864 | 240 | 38.46% | 0 | 0 | 0 |  | 70 | 71.5 | 1.5 | 2.143% | 2020-01-09 01:00
Brampton | 2020 | 633742 | 2020 DA- 7678 MAVIS RD | 99 | COMPLETE | Labour est. over | BOM not accurate | Vac truck | Agostini, Robert | Yes OH SW | Alectra Utilities | John Costa | 104494.85 | 108022.42 | 3527.57 | 3.376% | 42473.26 | 29336.84 | -13136.42 | -30.93% | 51908.56 | 63304.36 | 11395.8 | 21.95% | 9765 | 10506.22 | 741.22 | 7.591% | 348.03 | 4875 | 4526.97 | 1301% | 370 | 340 | -30 | -8.108% | 2020-12-04 01:00
Brampton | 2020 | 633743 | 2020 DA- 7732 MCLAUGHLIN RD S | 99 | COMPLETE | Labour est. over | BOM not accurate | Labour est. over | Agostini, Robert | Yes OH SW | Alectra Utilities | Reaburn, Jeff | 101206.86 | 63101.38 | -38105.48 | -37.65% | 42473.26 | 14842.95 | -27630.31 | -65.05% | 48968.6 | 42778.05 | -6190.55 | -12.64% | 9765 | 5480.38 | -4284.62 | -43.88% | 0 | 0 | 0 |  | 370 | 178 | -192 | -51.89% | 2020-09-17 01:00
Brampton | 2020 | 633744 | 2020 DA- 7776 MISSISSAUGA RD | 99 | COMPLETE | Scope – Const | BOM not accurate | N/A | Agostini, Robert | Yes OH SW | Alectra Utilities | Reaburn, Jeff | 104778.25 | 110030.23 | 5251.98 | 5.012% | 42473.26 | 9200.05 | -33273.21 | -78.34% | 52539.99 | 59467.83 | 6927.84 | 13.19% | 9765 | 155.35 | -9609.65 | -98.41% | 0 | 41207 | 41207 |  | 370 | 50.5 | -319.5 | -86.35% | 2020-11-27 01:00
Brampton | 2019 | 633764 | COUNTRYSIDE DR STUB POLE RE-INSTALLATION | 99 | COMPLETE | BOM not used | Cont Est Over | Labour est. under | Lacombe, Joel | CC | Robinson, David | John Costa | 23300.43 | 18418.27 | -4882.16 | -20.95% | 752.43 | 2252.76 | 1500.33 | 199.4% | 3202.08 | 612.24 | -2589.84 | -80.88% | 42 | 0 | -42 | -100% | 19303.92 | 15553.27 | -3750.65 | -19.43% | 4 | 18.5 | 14.5 | 362.5% | 2019-11-27 00:59
Brampton | 2020 | 634036 | 80 RIVERMONT - 27.6KV SUPPLY TO 500 KVA TX | 98 | COMPLETE | Labour est. over | Cont Est Over | BOM not accurate | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 76531.4 | 58472.3 | -18059.1 | -23.6% | 30396.28 | 20393.2 | -10003.08 | -32.91% | 30004.35 | 27359.95 | -2644.4 | -8.813% | 5405.4 | 3590 | -1815.4 | -33.58% | 10725.37 | 7129.15 | -3596.22 | -33.53% | 205 | 215 | 10 | 4.878% | 2020-06-12 01:00
Brampton | 2022 | 634227 | COUNTRYSIDE VILLAGES 2 (21T-12019B) - SUBD RES EDS | 99 | COMPLETE | Cont Est Over | Labour est. over | Material Under Estimated | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 331972.14 | 275685.36 | -56286.78 | -16.96% | 75693.11 | 60720.46 | -14972.65 | -19.78% | 6006.67 | 14115.9 | 8109.23 | 135% | 11520 | 3632 | -7888 | -68.47% | 238752.36 | 197217 | -41535.36 | -17.4% | 296 | 235.5 | -60.5 | -20.44% | 2022-02-11 01:00
Brampton | 2020 | 634439 | 221 ADVANCE BLVD- UPGRADE FROM 200 AMP TO 600 AMP 347/600V | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 |  | 2021-01-29 01:00
Brampton | 2021 | 634443 | TANYAVILLE PHASE 2 - SUBD RES EDS | 99 | COMPLETE | Labour est. over |  |  | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 37077.72 | 190529.16 | 153451.44 | 413.9% | 32798.85 | 24010.24 | -8788.61 | -26.8% | 534.87 | 605.98 | 71.11 | 13.29% | 3744 | 1471.5 | -2272.5 | -60.7% | 0 | 159.4 | 159.4 |  | 126 | 96.92 | -29.08 | -23.08% | 2021-01-29 01:00
Brampton | 2022 | 634450 | C4-22 - 58 SKY HARBOUR DR - 27.6KV 800KVA | 95 | COMPLETE | Labour est. under | Cont Est Over | Vehicle Under Estimated | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 175253.01 | 221676.8 | 46423.79 | 26.49% | 44390.74 | 145870.11 | 101479.37 | 228.6% | 43011.65 | 46320.59 | 3308.94 | 7.693% | 8236.8 | 13009.5 | 4772.7 | 57.94% | 79613.82 | 16476.6 | -63137.22 | -79.3% | 314.6 | 441 | 126.4 | 40.18% | 2022-01-24 01:00
Brampton | 2021 | 634502 | HB2018-017, BELL - THE GORE RD | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Martin, Shane | John Costa | 50376.04 | 50008.66 | -367.38 | -0.7293% | 1188.45 | 7034.32 | 5845.87 | 491.9% | 1229.59 | 0 | -1229.59 | -100% | 0 | 0 | 0 |  | 47958 | 42974.34 | -4983.66 | -10.39% | 0.4 | 2 | 1.6 | 400% | 2021-08-10 01:00
Brampton | 2020 | 634524 | 201 WESTCREEK BLVD POLE RELOCATION | 99 | COMPLETE | Cont Est Over | BOM not accurate | Estimate incorrect | Pelleja, Emily | No | Alectra Utilities | Nichol, Sandi | 48926.05 | 40494.38 | -8431.67 | -17.23% | 25443.17 | 17211.14 | -8232.03 | -32.35% | 19331.68 | 11378.42 | -7953.26 | -41.14% | 112 | 8319.82 | 8207.82 | 7328% | 4039.2 | 3585 | -454.2 | -11.24% | 216 | 173.5 | -42.5 | -19.68% | 2020-04-17 01:00
Brampton | 2020 | 634642 | 2019 EMERGING - 3 SHADYWOOD- NEW SERVICE CONDUCTOR | 99 | COMPLETE | Cont Est Over | Scope change - unforeseen | N/A | Agostini, Robert | No | Alectra Utilities | Reaburn, Jeff | 35001.71 | 27527.86 | -7473.85 | -21.35% | 5111.36 | 7028.21 | 1916.85 | 37.5% | 225.59 | 743.47 | 517.88 | 229.6% | 184 | 252 | 68 | 36.96% | 29480.76 | 19504.18 | -9976.58 | -33.84% | 11 | 26.5 | 15.5 | 140.9% | 2020-01-25 01:00
Brampton | 2020 | 634662 | 9287 GOREWAY DR | 95 | COMPLETE | BOM not accurate | Cont Est Under | Estimate incorrect | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 99786.33 | 119921.84 | 20135.51 | 20.18% | 28142.49 | 22081.7 | -6060.79 | -21.54% | 29327.28 | 29041.82 | -285.46 | -0.9734% | 0 | 4554.04 | 4554.04 |  | 42316.56 | 64244.28 | 21927.72 | 51.82% | 176 | 219.5 | 43.5 | 24.72% | 2020-12-28 01:00
Brampton | 2020 | 634679 | 2020 TX RENEWAL-239 QUEEN ST E - VT7315 | 99 | COMPLETE | Estimate incorrect | Civil contractor | Estimate incorrect | Agostini, Robert | No | Alectra Utilities | Nichol, Sandi | 85712.54 | 88080.84 | 2368.3 | 2.763% | 46321.67 | 10657.11 | -35664.56 | -76.99% | 33302.87 | 31426.76 | -1876.11 | -5.633% | 6088 | 855.86 | -5232.14 | -85.94% | 0 | 30403.26 | 30403.26 |  | 317 | 39.5 | -277.5 | -87.54% | 2020-01-28 01:00
Brampton | 2021 | 634901 | HODERO MAYFIELD RD - SUBD RES EDS | 99 | COMPLETE | Under 10% |  |  | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 289792.44 | 280916 | -8876.44 | -3.063% | 34383.51 | 49557.92 | 15174.41 | 44.13% | 9642.33 | 8390.15 | -1252.18 | -12.99% | 6390 | 4548 | -1842 | -28.83% | 239376.6 | 218419.93 | -20956.67 | -8.755% | 185 | 183.5 | -1.5 | -0.8108% | 2021-03-19 01:00
Brampton | 2020 | 634915 | 9025 TORBRAM RD | 99 | COMPLETE | Estimate incorrect | Labour est. under | Scope change - unforeseen | Agostini, Robert | No | Alectra Utilities | Simon Evason | 28208.7 | 47932.42 | 19723.72 | 69.92% | 5233.17 | 13514 | 8280.83 | 158.2% | 22273.53 | 25685.89 | 3412.36 | 15.32% | 702 | 4010.32 | 3308.32 | 471.3% | 0 | 2193.31 | 2193.31 |  | 32 | 155 | 123 | 384.4% | 2020-02-06 01:00
Brampton | 2020 | 634945 | 2020 POLE RENEWAL - CUMBERLAND DR AND MCCULLA AVE - 1 POLE | 99 | CANCELLED | N/A | N/A | N/A | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 15659.78 | 0 | -15659.78 | -100% | 12630.18 | 0 | -12630.18 | -100% | 767.57 | 0 | -767.57 | -100% | 1914 | 0 | -1914 | -100% | 348.03 | 0 | -348.03 | -100% | 0 | 0 | 0 |  | 2020-10-08 01:00
Brampton | 2020 | 634969 | 2019 EMERGING-16 PALGRAVE CRES- SERVICE AND CABLE INSTALLATION | 99 | COMPLETE | Labour est. over | Cont Est Over | BOM not accurate | Agostini, Robert | No | Alectra Utilities | Reaburn, Jeff | 34823.41 | 36288.47 | 1465.06 | 4.207% | 5735.71 | 7549.75 | 1814.04 | 31.63% | 195.78 | 460.55 | 264.77 | 135.2% | 354 | 234 | -120 | -33.9% | 28537.92 | 28044.17 | -493.75 | -1.73% | 21 | 36.5 | 15.5 | 73.81% | 2020-01-31 01:00
Brampton | 2020 | 635041 | 2020 POLE RENEWAL - POLE #10315 AND #10333 KENNEDY & COCHRANE GRID H2 | 99 | COMPLETE | Labour est. under | Estimate incorrect | Estimate incorrect | Agostini, Robert | Pole | Alectra Utilities | Nichol, Sandi | 40940.4 | 53008.23 | 12067.83 | 29.48% | 26428.33 | 28656.66 | 2228.33 | 8.432% | 11202.07 | 12060.19 | 858.12 | 7.66% | 3310 | 6867 | 3557 | 107.5% | 0 | 5424.38 | 5424.38 |  | 180 | 291.5 | 111.5 | 61.94% | 2020-03-11 01:00
Brampton | 2020 | 635042 | 2020 POLE RENEWAL - POLE #10315 KENNEDY RD N GRID H2 | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2020 | 635043 | G3-91 - 71 CHURCH ST E - CITY OF BRAMPTON - 600A 120/208V | 99 | COMPLETE | Cont Est Under | Labour est. over | Labour est. over | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 80365.96 | 59783.49 | -20582.47 | -25.61% | 37377.4 | 11867.18 | -25510.22 | -68.25% | 25599.72 | 25278.84 | -320.88 | -1.253% | 6240 | 686.13 | -5553.87 | -89% | 11148.84 | 21946.75 | 10797.91 | 96.85% | 278 | 106.75 | -171.25 | -61.6% | 2020-12-17 01:00
Brampton | 2021 | 635052 | 295 QUEEN ST.E. - 27.6KV SUPPLY TO 750 KVA TX | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-09-17 01:00
Brampton | 2020 | 635106 | 2020 LEFT-BEHIND CABLE REPLACE | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2021 | 635369 | NATIONAL HOMES GOREWAY (MUNICIPAL) - SUBD RES EDS | 99 | COMPLETE | Cont Est Over |  |  | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 123057.71 | 105852.96 | -17204.75 | -13.98% | 11564.87 | 16391.89 | 4827.02 | 41.74% | 0 | 592.37 | 592.37 |  | 876 | 112.5 | -763.5 | -87.16% | 110616.84 | 87573 | -23043.84 | -20.83% | 34 | 42.75 | 8.75 | 25.74% | 2021-10-14 01:00
Brampton | 2022 | 635371 | NATIONAL HOMES GOREWAY (CONDO) - SUBD RES EDS | 99 | COMPLETE | Labour est. under | Cont Est Over | N/A | Gamboa, Henry | No | Erzek, Ryan | Zenon Lipinski | 342538.74 | 359630.66 | 17091.92 | 4.99% | 31657.85 | 71277.03 | 39619.18 | 125.1% | 7064.33 | 6054.06 | -1010.27 | -14.3% | 7160 | 6259.33 | -900.67 | -12.58% | 296656.56 | 274729.4 | -21927.16 | -7.391% | 201 | 341 | 140 | 69.65% | 2022-08-26 01:00
Brampton | 2020 | 635491 | 2020 POLE RENEWAL - POLE #11477 AND #11249 KENNEDY RD N GRID H1 - 2 Poles | 99 | COMPLETE | Cont Est Over | Scope – Const | Estimate incorrect | Agostini, Robert | Yes Pole | Alectra Utilities | Reaburn, Jeff | 29723.89 | 20164.58 | -9559.31 | -32.16% | 20838.07 | 7721.44 | -13116.63 | -62.95% | 2873.82 | 4430.16 | 1556.34 | 54.16% | 2340 | 1016.24 | -1323.76 | -56.57% | 3672 | 6996.74 | 3324.74 | 90.54% | 152 | 64 | -88 | -57.89% | 2020-12-18 01:00
Brampton | 2020 | 635563 | 2020 POLE RENEWAL - POLE #8670 BRAMALEA RD, S OF CLARK BLVD GRID J4 | 99 | COMPLETE | Cont Est Over | Vac truck | N/A | Agostini, Robert | Yes Pole | Alectra Utilities | John Costa | 15194.44 | 8903.54 | -6290.9 | -41.4% | 12746.8 | 4550.87 | -8195.93 | -64.3% | 792.64 | 978.09 | 185.45 | 23.4% | 1655 | 1294.58 | -360.42 | -21.78% | 0 | 2080 | 2080 |  | 87 | 28 | -59 | -67.82% | 2020-11-10 01:00
Brampton | 2021 | 635642 | 134 KENNEDY RD. S. - SERVICE UPGRADE | 95 | COMPLETE | Cont Est Over | Labour est. over | N/A | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 194797.85 | 139047.9 | -55749.95 | -28.62% | 48579.21 | 33850.03 | -14729.18 | -30.32% | 71022.2 | 73090.72 | 2068.52 | 2.912% | 7488 | 7712.09 | 224.09 | 2.993% | 67708.44 | 24384.72 | -43323.72 | -63.99% | 346 | 344.5 | -1.5 | -0.4335% | 2021-10-20 01:00
Brampton | 2021 | 635659 | 160 SALVATION RD | 95 | COMPLETE | Labour est. over | Cont Est Under | N/A | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 72599.37 | 60193.49 | -12405.88 | -17.09% | 31936.47 | 16178.17 | -15758.3 | -49.34% | 16687.08 | 15827.87 | -859.21 | -5.149% | 4118.4 | 4116.76 | -1.64 | -0.03982% | 19857.42 | 24070.69 | 4213.27 | 21.22% | 195 | 202 | 7 | 3.59% | 2021-02-23 01:00
Brampton | 2022 | 635711 | MISSISSAUGA RD @ LAGERFELD RD. POLE RELOCATION (LAGERFELD RD EXT. | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Robinson, David | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-26 01:00
Brampton | 2020 | 635795 | 21T-18007B FOUR X PHASE 3 | 99 | COMPLETE | Labour est. under | Estimate incorrect | Estimate incorrect | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 154111.34 | 150123.2 | -3988.14 | -2.588% | 15757.18 | 11525.01 | -4232.17 | -26.86% | 420.12 | 509.15 | 89.03 | 21.19% | 760 | 1215 | 455 | 59.87% | 137174.04 | 3750 | -133424.04 | -97.27% | 60 | 86.5 | 26.5 | 44.17% | 2020-11-17 01:00
Brampton | 2020 | 635862 | 21T-19012B PARADISE HOMES NW PH3C | 99 | COMPLETE | Cont Est Over | Labour est. over | Estimate incorrect | Gamboa, Henry | No | Alectra Utilities | Richard Cuddy | 428021.84 | 333381.17 | -94640.67 | -22.11% | 50785.45 | 51694.54 | 909.09 | 1.79% | 5684.47 | 5812.08 | 127.61 | 2.245% | 6918 | 7651.15 | 733.15 | 10.6% | 364633.92 | 268223.4 | -96410.52 | -26.44% | 381 | 255.5 | -125.5 | -32.94% | 2020-12-03 01:00
Brampton | 2020 | 635948 | 7891 CHURCHVILLE RD / BRAM / NS / 1PH (LAYOUT) | 99 | COMPLETE | Estimate incorrect | BOM not accurate | Estimate incorrect | Rao, Gaurav | No | Alectra Utilities | Reaburn, Jeff | 31085.46 | 24411.38 | -6674.08 | -21.47% | 21098.49 | 13267.57 | -7830.92 | -37.12% | 7646.97 | 5335.47 | -2311.5 | -30.23% | 2340 | 5808.34 | 3468.34 | 148.2% | 0 | 0 | 0 |  | 170 | 167 | -3 | -1.765% | 2020-08-05 01:00
Brampton | 2021 | 635954 | 625 REMEMBRANCE RD | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 143361.86 | 137753.04 | -5608.82 | -3.912% | 24568.45 | 21082.68 | -3485.77 | -14.19% | 28278.24 | 35326.31 | 7048.07 | 24.92% | 5491.2 | 1757 | -3734.2 | -68% | 85023.97 | 79587.05 | -5436.92 | -6.395% | 162.3 | 174 | 11.7 | 7.209% | 2021-02-11 01:00
Brampton | 2020 | 635983 | 2020 POLE RENEWAL - VARIOUS-GRID G3 - 3 POLES | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A | Agostini, Robert | Yes Pole | Alectra Utilities | Reaburn, Jeff | 80703.89 | 50134.24 | -30569.65 | -37.88% | 51017.74 | 26546.74 | -24471 | -47.97% | 8454.46 | 9291.16 | 836.7 | 9.897% | 10527 | 9661.15 | -865.85 | -8.225% | 10704.69 | 4635.19 | -6069.5 | -56.7% | 436 | 295 | -141 | -32.34% | 2020-12-16 01:00
Brampton | 2020 | 635986 | DIXIE RD - CLARK BLVD TO QUEEN ST E ANCHOR RELOCATION | 99 | COMPLETE | Cont Est Over | BOM not accurate | N/A | Watters, Maxwell | No | Alectra Utilities | Reaburn, Jeff | 26777.59 | 22738.73 | -4038.86 | -15.08% | 4628.84 | 5808.4 | 1179.56 | 25.48% | 1663.43 | 806.03 | -857.4 | -51.54% | 42 | 0 | -42 | -100% | 20443.32 | 16124.3 | -4319.02 | -21.13% | 7.94 | 3 | -4.94 | -62.22% | 2020-11-09 01:00
Brampton | 2021 | 636024 | 21T-06024B SCOTTISH HEATHER PHASE 4B | 99 | COMPLETE | Under 10% |  |  | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 716924.76 | 718328.01 | 1403.25 | 0.1957% | 43637.99 | 93474.41 | 49836.42 | 114.2% | 11160.53 | 11849.15 | 688.62 | 6.17% | 9884 | 8997.4 | -886.6 | -8.97% | 652242.24 | 604007.05 | -48235.19 | -7.395% | 306 | 421.25 | 115.25 | 37.66% | 2021-01-27 01:00
Brampton | 2021 | 636033 | 797 MAYFIELD RD / BRAM / NS / 1PH | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Tan, Seefon | Justin Gregoris | 22229.62 | 21205.64 | -1023.98 | -4.606% | 14087.06 | 10003.98 | -4083.08 | -28.98% | 7332.56 | 7112.14 | -220.42 | -3.006% | 810 | 2370 | 1560 | 192.6% | 0 | 1719.52 | 1719.52 |  | 95 | 139 | 44 | 46.32% | 2021-04-28
Brampton | 2022 | 636041 | CAL-GORE DEVELOPMENT INC. - SUBD RES EDS | 99 | COMPLETE | Cont Est Over | Labour est. over | Material Under Estimated | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 204570.53 | 144135.82 | -60434.71 | -29.54% | 29559.87 | 17877.16 | -11682.71 | -39.52% | 6392.58 | 13377.4 | 6984.82 | 109.3% | 6158 | 3507.59 | -2650.41 | -43.04% | 162460.08 | 105517 | -56943.08 | -35.05% | 257 | 112.27 | -144.73 | -56.32% | 2022-02-11 01:00
Brampton | 2020 | 636059 | 8 BRAMWIN CRT - SERVICE UPGRADE | 98 | COMPLETE | Labour est. over | BOM not accurate | N/A | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 60657.17 | 58792.88 | -1864.29 | -3.073% | 15531.14 | 10395.39 | -5135.75 | -33.07% | 43449.03 | 46385.89 | 2936.86 | 6.759% | 1677 | 1974 | 297 | 17.71% | 0 | 37.6 | 37.6 |  | 74 | 112 | 38 | 51.35% | 2020-09-18 01:00
Brampton | 2020 | 636061 | 2020 POLE RENEWAL-116 RUTHERFORD RD S - 1 Pole | 99 | COMPLETE | Labour est. over | Vac truck | N/A | Agostini, Robert | Yes Pole | Alectra Utilities | Reaburn, Jeff | 19675.09 | 14609.5 | -5065.59 | -25.75% | 12731.39 | 7555.83 | -5175.56 | -40.65% | 1287.7 | 1389.68 | 101.98 | 7.92% | 1984 | 2991.91 | 1007.91 | 50.8% | 3672 | 2672.08 | -999.92 | -27.23% | 8 | 71.5 | 63.5 | 793.8% | 2020-11-06 01:00
Brampton | 2021 | 636179 | 2021 POLE RENEWAL-CN PROPERTY-POLE REMOVAL- 1 POLE | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | John Costa | 9383.89 | 2929.08 | -6454.81 | -68.79% | 7494.61 | 2536.23 | -4958.38 | -66.16% | 0 | 0 | 0 |  | 1872 | 392.85 | -1479.15 | -79.01% | 17.28 | 0 | -17.28 | -100% | 49.36 | 20.5 | -28.86 | -58.47% | 2021-05-06
Brampton | 2022 | 636232 | 85 DEVON RD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-05-22
Brampton | 2020 | 636264 | 2020 EMERGING- 7891 CHURCHVILLE RD | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-08 01:00
Brampton | 2020 | 636335 | 2020 POLE RENEWAL-GRID F3-ARCHIBALD ST/MOORE ST, DAVID ST/MILL ST 3 POLES | 99 | COMPLETE | Labour est. over | Scope change - unforeseen | N/A | Agostini, Robert | Yes Pole | Alectra Utilities | Reaburn, Jeff | 78963.81 | 62136.01 | -16827.8 | -21.31% | 42227.86 | 30172.18 | -12055.68 | -28.55% | 18240.11 | 16605.47 | -1634.64 | -8.962% | 11424 | 12488.36 | 1064.36 | 9.317% | 7071.84 | 2870 | -4201.84 | -59.42% | 536 | 280.75 | -255.25 | -47.62% | 2020-11-20 01:00
Brampton | 2021 | 636337 | 2021 POLE RENEWAL-GRID F2- 9 POLES | 99 | COMPLETE | Labour est. over | Scope – Const | Cont Est Over | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 308036.36 | 210173.23 | -97863.13 | -31.77% | 152910.79 | 88600.89 | -64309.9 | -42.06% | 46601.57 | 48505.32 | 1903.75 | 4.085% | 46424 | 33753.76 | -12670.24 | -27.29% | 62100 | 39313.26 | -22786.74 | -36.69% | 1122.32 | 784.5 | -337.82 | -30.1% | 2021-04-23
Brampton | 2021 | 636416 | 65 ATTMAR DR. - 27.6KV SUPPLY TO 2000 KVA TX | 95 | COMPLETE | Estimate incorrect | Cont Est Over | Labour est. over | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 123489.61 | 98059.03 | -25430.58 | -20.59% | 41884.27 | 25300.4 | -16583.87 | -39.59% | 52020.42 | 59350.89 | 7330.47 | 14.09% | 7878 | 3696 | -4182 | -53.08% | 21706.92 | 9711.74 | -11995.18 | -55.26% | 300 | 291.75 | -8.25 | -2.75% | 2021-05-18 01:00
Brampton | 2021 | 636431 | 2020 SWITCHGEAR RENEWAL-SITE# 484(FORMERLY 98)-SANDALWOOD PKWY AND ROSEDALE | 99 | COMPLETE | Commodity Price | Cont Est Under | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 162125.08 | 222622.31 | 60497.23 | 37.32% | 7301.54 | 17797.53 | 10495.99 | 143.8% | 130803.54 | 163667.6 | 32864.06 | 25.12% | 1020 | 1819.33 | 799.33 | 78.37% | 23000 | 39337.85 | 16337.85 | 71.03% | 58 | 99 | 41 | 70.69% | 2021-12-22 01:00
Brampton | 2021 | 636432 | 2020 SWITCHGEAR RENEWAL - SITE# 480 (FORMERLY 149)- PETER ROBINSON EAST OF DIXIE | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 162125.08 | 172738.43 | 10613.35 | 6.546% | 7301.54 | 17126.2 | 9824.66 | 134.6% | 130803.54 | 154327.69 | 23524.15 | 17.98% | 1020 | 532.25 | -487.75 | -47.82% | 23000 | 752.29 | -22247.71 | -96.73% | 58 | 153 | 95 | 163.8% | 2021-10-29 01:00
Brampton | 2021 | 636433 | 2020 SWITCHGEAR RENEWAL-SITE# 478 (FORMERLY 181)-GURU NANAK ST W OF DIXIE | 99 | COMPLETE | Commodity Price | Cont Est Under | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 162125.08 | 199778.73 | 37653.65 | 23.23% | 7301.54 | 15492.85 | 8191.31 | 112.2% | 130803.54 | 158160.97 | 27357.43 | 20.91% | 1020 | 377.06 | -642.94 | -63.03% | 23000 | 25747.85 | 2747.85 | 11.95% | 58 | 100.5 | 42.5 | 73.28% | 2021-11-15 01:00
Brampton | 2021 | 636447 | 2021 SWITCHGEAR RENEWAL - SITE# 116 | 99 | COMPLETE | Labour est. under | Scope change - unforeseen | Commodity Price | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 160908.66 | 194543.3 | 33634.64 | 20.9% | 24809.39 | 33235.76 | 8426.37 | 33.96% | 128909.27 | 148264.95 | 19355.68 | 15.01% | 7190 | 13042.59 | 5852.59 | 81.4% | 0 | 0 | 0 |  | 185 | 306 | 121 | 65.41% | 2021-10-25 01:00
Brampton | 2020 | 636456 | 9287 GOREWAY DR | 99 | COMPLETE | Labour est. over | Cont Est Over | Scope change - unforeseen | Agostini, Robert | No | Alectra Utilities | Richard Cuddy | 82153.41 | 71483.04 | -10670.37 | -12.99% | 31371.73 | 24476.86 | -6894.87 | -21.98% | 2383.96 | 1300.71 | -1083.25 | -45.44% | 3568 | 2163.25 | -1404.75 | -39.37% | 44829.72 | 43542.22 | -1287.5 | -2.872% | 112 | 128.7 | 16.7 | 14.91% | 2020-10-30 01:00
Brampton | 2021 | 636527 | 2021 SWITCHGEAR RENEWAL - SITE# 118 - FERNFOREST DR, S OF SANDALWOOD | 99 | COMPLETE | Commodity Price | Labour est. over | Estimate incorrect | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 163535.67 | 205033.15 | 41497.48 | 25.38% | 37000.96 | 33224.29 | -3776.67 | -10.21% | 11846.71 | 163649.22 | 151802.51 | 1281% | 6688 | 8159.64 | 1471.64 | 22% | 108000 | 0 | -108000 | -100% | 258 | 293.5 | 35.5 | 13.76% | 2021-12-10 01:00
Brampton | 2022 | 636531 | 425 CHRYSLER DR | 95 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 256331.76 | 128318.37 | -128013.39 | -49.94% | 87514.71 | 30995.86 | -56518.85 | -64.58% | 61516.89 | 42021.64 | -19495.25 | -31.69% | 18532.8 | 10445.94 | -8086.86 | -43.64% | 88767.36 | 44854.93 | -43912.43 | -49.47% | 633.6 | 392 | -241.6 | -38.13% | 2022-01-27 01:00
Brampton | 2020 | 636543 | 2020 CABLE REPLACEMENT - GRID: J3 | 99 | COMPLETE | Estimate incorrect | Labour est. over | Estimate incorrect | Agostini, Robert | No | Alectra Utilities | Richard Cuddy | 484185 | 218944.03 | -265240.97 | -54.78% | 43599.17 | 29624.78 | -13974.39 | -32.05% | 6601.99 | 801.03 | -5800.96 | -87.87% | 9492 | 0 | -9492 | -100% | 424491.84 | 188518.22 | -235973.62 | -55.59% | 334 | 33.5 | -300.5 | -89.97% | 2020-11-12 01:00
Brampton | 2021 | 636586 | 7324 KENNEDY RD S / BRAM / NS / 3PH PAD (TEMPORARY) | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 76306.82 | 78737.11 | 2430.29 | 3.185% | 27884.39 | 15505.13 | -12379.26 | -44.39% | 36533.79 | 36604.33 | 70.54 | 0.1931% | 2106 | 3952 | 1846 | 87.65% | 9782.64 | 22675.65 | 12893.01 | 131.8% | 190 | 169.5 | -20.5 | -10.79% | 2021-03-31 01:00
Brampton | 2020 | 636766 | 465 DEERHURST DR | 99 | COMPLETE | BOM not accurate | Labour est. over | Cont Est Over | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 77670.88 | 47758.78 | -29912.1 | -38.51% | 27083.58 | 17054.74 | -10028.84 | -37.03% | 23226.08 | 5449.53 | -17776.55 | -76.54% | 5148 | 3849.21 | -1298.79 | -25.23% | 22213.22 | 21405.3 | -807.92 | -3.637% | 175 | 216.5 | 41.5 | 23.71% | 2020-12-17 01:00
Brampton | 2021 | 636837 | JOINT USE PERMIT HB2020-015- NORTH PARK DR. S/O LETHBRIDGE DR. | 99 | COMPLETE | Labour est. over | Scope change - unforeseen | N/A | O'Gay, Brian | No | Martin, Shane | John Costa | 13691.13 | 9113.78 | -4577.35 | -33.43% | 6389.48 | 4185.39 | -2204.09 | -34.5% | 246.24 | 114.39 | -131.85 | -53.55% | 888.61 | 844 | -44.61 | -5.02% | 6166.8 | 3970 | -2196.8 | -35.62% | 40.81 | 35.5 | -5.31 | -13.01% | 2021-04-29
Brampton | 2021 | 636840 | 4KV CONV PH3D - (MAIN ST S & GUEST ST) | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Reaburn, Jeff | 238888.89 | 225949.94 | -12938.95 | -5.416% | 41867.68 | 39549.78 | -2317.9 | -5.536% | 16081.21 | 8701.86 | -7379.35 | -45.89% | 5980 | 4046 | -1934 | -32.34% | 174960 | 173652.3 | -1307.7 | -0.7474% | 314 | 225.25 | -88.75 | -28.26% | 2021-05-25 01:00
Brampton | 2022 | 636869 | 136M1 O/H FEEDER EGRESS - GOREWAY RD (HUMBERWEST PKWY TO YORKLAND BLVD) | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | D'Ermes, Michael | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-05-11
Brampton | 2022 | 636871 | STEELES AVE AND HURONTARIO ST GTT | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Lemire, Blake | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-05-11
Brampton | 2021 | 636894 | 9280 AND 9300 GOREWAY DR - 27.6KV TO 1500 KVA TX | 95 | COMPLETE | Estimate incorrect | Labour est. over | Cont Est Over | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 117764.1 | 100914.95 | -16849.15 | -14.31% | 51922.67 | 31032.97 | -20889.7 | -40.23% | 45725.83 | 47627.01 | 1901.18 | 4.158% | 8268 | 11742.44 | 3474.44 | 42.02% | 11847.6 | 10499.69 | -1347.91 | -11.38% | 370 | 393.3 | 23.3 | 6.297% | 2021-04-15
Brampton | 2021 | 636898 | ATTMAR DR AND THE GORE RD - FEEDER EXTENSION | 98 | COMPLETE | Under 10% |  |  | Watters, Maxwell | No | Lemire, Blake | Richard Cuddy | 226345.13 | 234073.63 | 7728.5 | 3.414% | 38166.61 | 45052.82 | 6886.21 | 18.04% | 34588.88 | 33882 | -706.88 | -2.044% | 560 | 7203.75 | 6643.75 | 1186% | 153029.64 | 147935.06 | -5094.58 | -3.329% | 468 | 297 | -171 | -36.54% | 2021-12-10 01:00
Brampton | 2020 | 636972 | OH FCI FILLER WORK | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-31 01:00
Brampton | 2020 | 636999 | INSTALL UG FAULTED CIRCUIT INDICATORS W/LED | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-11 01:00
Brampton | 2020 | 637000 | INSTALL UG FAULTED CIRCUIT INDICATORS ACOUSTIC/LED | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-11 01:00
Brampton | 2020 | 637010 | 2020 - AUTOMATION ORDER - BW- VERTICAL | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2020 | 637011 | 2020 - AUTOMATION ORDER - BW- VERTICAL | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2020 | 637012 | 2020 - AUTOMATION ORDER - BW- VERTICAL | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2020 | 637013 | 2020 - AUTOMATION ORDER - BW- HORIZONTAL | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2020 | 637016 | 2020 - INSULATOR ORDER - BW | 99 | CANCELLED | N/A |  |  | Agostini, Robert | Yes | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2020 | 637044 | ROAD CROSSING AND 1/0 CABLE RELOCATION-HURONTARIO ST AND HIGHWOOD RD. | 99 | COMPLETE | Labour est. over | Estimate incorrect | BOM not accurate | Pelleja, Emily | No | Alectra Utilities | Reaburn, Jeff | 55063.16 | 72016.28 | 16953.12 | 30.79% | 6018.84 | 19373.97 | 13355.13 | 221.9% | 6945.92 | 4124.19 | -2821.73 | -40.62% | 0 | 2528.74 | 2528.74 |  | 42098.4 | 45989.38 | 3890.98 | 9.243% | 37 | 118.75 | 81.75 | 220.9% | 2020-07-27 01:00
Brampton | 2021 | 637046 | 45 WEST DR - 27.6KV SUPPLY TO 1500 KVA TX | 95 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 156206.57 | 169999.99 | 13793.42 | 8.83% | 36417.42 | 106293.87 | 69876.45 | 191.9% | 52868.75 | 56755.55 | 3886.8 | 7.352% | 6786 | 6105 | -681 | -10.04% | 60134.4 | 825.1 | -59309.3 | -98.63% | 418 | 414.45 | -3.55 | -0.8493% | 2021-04-15
Brampton | 2020 | 637065 | CENTRAL NORTH BRACKETS FILLER WORK | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2020 | 637066 | CENTRAL NORTH OH TRANSFORMERS FILLER WORK | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2020 | 637067 | CENTRAL NORTH PADMOUNT TRANSFORMERS FILLER WORK | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-11 01:00
Brampton | 2021 | 637068 | 2021 EMERGING PROJECT - 7835 HWY 50 | 99 | COMPLETE | BOM not accurate | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 183598.18 | 180709.79 | -2888.39 | -1.573% | 12506.28 | 18533.51 | 6027.23 | 48.19% | 6475.38 | 16400.24 | 9924.86 | 153.3% | 1840 | 286 | -1554 | -84.46% | 162776.52 | 145490.04 | -17286.48 | -10.62% | 116 | 39.5 | -76.5 | -65.95% | 2021-07-29 01:00
Brampton | 2022 | 637088 | 4KV CONVERSION - PHASE 10 | 95 | ANALYZE |  |  |  | Agostini, Robert | Yes | Casey, Ryan | AW Group | 1143817.27 | 1196720.1 | 52902.83 | 4.625% | 47840.07 | 143809.32 | 95969.25 | 200.6% | 191631.68 | 292430.87 | 100799.19 | 52.6% | 3200 | 0 | -3200 | -100% | 901145.52 | 760479.91 | -140665.61 | -15.61% | 0 | 133.5 | 133.5 |  | 2023-01-10 01:00
Brampton | 2021 | 637109 | CONCRETE POLES -CENTRAL NORTH | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Miller, Michael | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-21 01:00
Brampton | 2021 | 637110 | WOOD POLES - CENTRAL NORTH | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Miller, Michael | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-21 01:00
Brampton | 2021 | 637141 | 2021 POLE RENEWAL-GRID M3- 7 POLES | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 228515.29 | 247753.86 | 19238.57 | 8.419% | 107328.71 | 104114.84 | -3213.87 | -2.994% | 75520.58 | 73751.71 | -1768.87 | -2.342% | 30816 | 56805.42 | 25989.42 | 84.34% | 14850 | 13081.89 | -1768.11 | -11.91% | 884 | 978 | 94 | 10.63% | 2021-08-23 01:00
Brampton | 2021 | 637142 | 2021 POLE RENEWAL-GRID N5- 4 POLES | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | John Costa | 84299.73 | 81411.8 | -2887.93 | -3.426% | 41150.59 | 33476.72 | -7673.87 | -18.65% | 18657.14 | 16015.98 | -2641.16 | -14.16% | 13368 | 18934.61 | 5566.61 | 41.64% | 11124 | 12984.49 | 1860.49 | 16.73% | 328 | 326.75 | -1.25 | -0.3811% | 2021-12-31 01:00
Brampton | 2021 | 637148 | HERITAGE ROAD DEVELOPMENT ENTRANCE POLE RELOCATION | 98 | COMPLETE | Under 10% | N/A | N/A | Pelleja, Emily | No | Lemire, Blake | Justin Gregoris | 92349.81 | 92654.83 | 305.02 | 0.3303% | 47989.35 | 48294.37 | 305.02 | 0.6356% | 21343 | 21343 | 0 | 0% | 15196.72 | 15196.72 | 0 | 0% | 7820.74 | 7820.74 | 0 | 0% | 552 | 551.25 | -0.75 | -0.1359% | 2021-03-22 01:00
Brampton | 2020 | 637152 | 2020 POLE RENEWAL-GRID F3-MAIN ST- 2 POLES | 99 | COMPLETE | Scope change - unforeseen | Cont Est Under | Estimate incorrect | Agostini, Robert | Pole | Alectra Utilities | Reaburn, Jeff | 59595.04 | 30605.06 | -28989.98 | -48.64% | 31826.87 | 13362.74 | -18464.13 | -58.01% | 14046.28 | 8740 | -5306.28 | -37.78% | 8860 | 5867.32 | -2992.68 | -33.78% | 4861.89 | 2635 | -2226.89 | -45.8% | 20 | 156 | 136 | 680% | 2020-11-27 01:00
Brampton | 2021 | 637170 | COMMUTER DR. - 27.6KV SUPPLY TO ELECTRIC BUS STATION | 95 | COMPLETE | Scope – Const | Estimate incorrect | N/A | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 171545.44 | 206173.92 | 34628.48 | 20.19% | 33983.77 | 166062.79 | 132079.02 | 388.7% | 32051.58 | 36113.14 | 4061.56 | 12.67% | 5850 | 2336 | -3514 | -60.07% | 99660.09 | 700 | -98960.09 | -99.3% | 311 | 281.5 | -29.5 | -9.486% | 2021-03-29 01:00
Brampton | 2021 | 637171 | 1478 QUEEN ST. E.- 27.6KV SUPPLY TO ELECTRIC BUS CHARGING STATION | 95 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 107007.93 | 99534.89 | -7473.04 | -6.984% | 50018.03 | 36704.36 | -13313.67 | -26.62% | 40523.62 | 42359.98 | 1836.36 | 4.532% | 5460 | 11389.8 | 5929.8 | 108.6% | 11006.28 | 8238.48 | -2767.8 | -25.15% | 458 | 493.25 | 35.25 | 7.697% | 2021-04-15
Brampton | 2020 | 637187 | 50 BROMLEY CRES - REAR LOT O/H SEC SERVICE AERIAL ENCROACHMENT | 99 | COMPLETE | Cont Est Over | N/A | N/A | Agostini, Robert | No | Alectra Utilities | Brian Erskine | 9044.87 | 2555.34 | -6489.53 | -71.75% | 8201.26 | 2449.34 | -5751.92 | -70.13% | 7.61 | 0 | -7.61 | -100% | 836 | 106 | -730 | -87.32% | 0 | 0 | 0 |  | 44 | 4 | -40 | -90.91% | 2020-06-22 01:00
Brampton | 2020 | 637188 | 26 PINE TREE CRES / BRAM / NS / 1PH PAD | 99 | COMPLETE | Estimate incorrect | Estimate incorrect | N/A | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 16857.77 | 11882.58 | -4975.19 | -29.51% | 4128.81 | 3380.53 | -748.28 | -18.12% | 6966.2 | 6610.54 | -355.66 | -5.106% | 312 | 1311.84 | 999.84 | 320.5% | 5450.76 | 579.67 | -4871.09 | -89.37% | 26 | 39 | 13 | 50% | 2020-08-12 01:00
Brampton | 2021 | 637202 | RELOCATION OF UNDERGROUND 1000 KCMIL CABLE- HUMBERWEST PKWY | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Pelleja, Emily | No | Robinson, David | Richard Cuddy | 526870.21 | 303489.85 | -223380.36 | -42.4% | 77145.89 | 70671.56 | -6474.33 | -8.392% | 131006.6 | 80827.52 | -50179.08 | -38.3% | 0 | 4224 | 4224 |  | 318717.72 | 147766.77 | -170950.95 | -53.64% | 660 | 260 | -400 | -60.61% | 2021-03-10 01:00
Brampton | 2021 | 637216 | 2021 POLE RENEWAL - P#14 & P#4660 - GRID P1 - 2 POLES | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | No | Miller, Michael | John Costa | 41178.45 | 39641.71 | -1536.74 | -3.732% | 24975.26 | 18220.35 | -6754.91 | -27.05% | 3051.19 | 2862.14 | -189.05 | -6.196% | 6240 | 8729.91 | 2489.91 | 39.9% | 6912 | 9829.31 | 2917.31 | 42.21% | 200 | 140 | -60 | -30% | 2021-12-15 01:00
Brampton | 2021 | 637218 | POLE LINE ENCROACHMENT- #8406 CREDITVIEW RD - | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | yes | Miller, Michael | Reaburn, Jeff | 115000.65 | 126963.23 | 11962.58 | 10.4% | 31382.74 | 49598.41 | 18215.67 | 58.04% | 15589.07 | 13184.31 | -2404.76 | -15.43% | 0 | 0 | 0 |  | 68028.84 | 64180.51 | -3848.33 | -5.657% | 33.5 | 73.5 | 40 | 119.4% | 2021-10-01 01:00
Brampton | 2021 | 637233 | 2020 POLE RENEWAL-GRID G2- 1 POLE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 20274.11 | 14835.06 | -5439.05 | -26.83% | 6344.02 | 4764.96 | -1579.06 | -24.89% | 2677.09 | 2562.06 | -115.03 | -4.297% | 320 | 0 | -320 | -100% | 10933 | 7508.04 | -3424.96 | -31.33% | 20 | 0 | -20 | -100% | 2021-12-23 01:00
Brampton | 2021 | 637234 | 2021 POLE RENEWAL-GRID Q2- 1 POLE | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | John Costa | 22829.99 | 15922.18 | -6907.81 | -30.26% | 12141.72 | 6529.92 | -5611.8 | -46.22% | 5114.27 | 5074.83 | -39.44 | -0.7712% | 3792 | 2597.91 | -1194.09 | -31.49% | 1782 | 1719.52 | -62.48 | -3.506% | 92 | 55 | -37 | -40.22% | 2021-11-05 01:00
Brampton | 2022 | 637235 | 2020 POLE RENEWAL-GRID I5- 1 POLE | 99 | COMPLETE | Cont Est Under | Labour est. over | Vehicle Over Estimated- | Agostini, Robert | Yes | Casey, Ryan | K-Line Construction | 29011.81 | 30378.7 | 1366.89 | 4.711% | 16904.54 | 6952.08 | -9952.46 | -58.87% | 6522.27 | 8924.95 | 2402.68 | 36.84% | 5585 | 0 | -5585 | -100% | 0 | 14501.67 | 14501.67 |  | 115 | 3.5 | -111.5 | -96.96% | 2022-09-30 01:00
Brampton | 2021 | 637257 | LOST CANYON WAY - SUBD RES EDS | 99 | COMPLETE | Cont Est Over |  |  | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 119297.79 | 100704.23 | -18593.56 | -15.59% | 21208.41 | 19027.77 | -2180.64 | -10.28% | 482.22 | 543.64 | 61.42 | 12.74% | 4320 | 1311 | -3009 | -69.65% | 93287.16 | 79821.82 | -13465.34 | -14.43% | 105 | 96.25 | -8.75 | -8.333% | 2021-08-20 01:00
Brampton | 2020 | 637271 | INSTALLATION OF PAD MOUNTED TRANSFORMER-HUMBERWEST PKWY & EXCHANGE DR | 99 | COMPLETE | Estimate incorrect | Cont Est Over | Labour est. over | Pelleja, Emily | No | Alectra Utilities | Richard Cuddy | 44137.03 | 39638.47 | -4498.56 | -10.19% | 16875.91 | 14853.55 | -2022.36 | -11.98% | 6214.08 | 5142.93 | -1071.15 | -17.24% | 0 | 3317.72 | 3317.72 |  | 21047.04 | 16324.27 | -4722.77 | -22.44% | 120 | 111 | -9 | -7.5% | 2020-09-18 01:00
Brampton | 2020 | 637344 | 58 ABBEY RD - MP TX REPLACEMENT | 99 | COMPLETE | Scope – Const | Cont Est Under | N/A | Agostini, Robert | No | Alectra Utilities | John Costa | 34836.74 | 36710.84 | 1874.1 | 5.38% | 7927.35 | 7955.37 | 28.02 | 0.3535% | 5096.71 | 4318.94 | -777.77 | -15.26% | 892 | 1728 | 836 | 93.72% | 20920.68 | 22708.53 | 1787.85 | 8.546% | 48 | 56 | 8 | 16.67% | 2020-09-11 01:00
Brampton | 2020 | 637345 | 2020 POLE RENEWAL GRID E3 - POLE #15 & #24 CUMBRIAN CRT, POLE #32 PARKWAY AVE | 99 | COMPLETE | Estimate incorrect | Estimate incorrect | Labour est. under | Agostini, Robert | Yes Pole | Alectra Utilities | Reaburn, Jeff | 44949.32 | 61832.65 | 16883.33 | 37.56% | 26100.4 | 30591.37 | 4490.97 | 17.21% | 15616.92 | 14147.58 | -1469.34 | -9.409% | 3232 | 12036.7 | 8804.7 | 272.4% | 0 | 5057 | 5057 |  | 168 | 325.5 | 157.5 | 93.75% | 2020-12-21 01:00
Brampton | 2020 | 637346 | 2020 POLE RENEWAL GRID M3 - POLE #37 & #38 WARD RD, POLE #11 EDVAC DR | 99 | COMPLETE | Scope – Eng | Estimate incorrect | Estimate incorrect | Agostini, Robert | Yes Pole | Alectra Utilities | Reaburn, Jeff | 39076.58 | 50730.22 | 11653.64 | 29.82% | 26100.4 | 18614.33 | -7486.07 | -28.68% | 9744.18 | 16808.68 | 7064.5 | 72.5% | 3232 | 6999.35 | 3767.35 | 116.6% | 0 | 8307.86 | 8307.86 |  | 178 | 182 | 4 | 2.247% | 2020-12-11 01:00
Brampton | 2021 | 637351 | BOVAIRD DR W & LAGERFELD DR / BRAM / NS / 3PH PAD | 95 | COMPLETE | Estimate incorrect | Labour est. over | Cont Est Under | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 115135.18 | 66870.92 | -48264.26 | -41.92% | 37688.49 | 16297.62 | -21390.87 | -56.76% | 31911.37 | 795.19 | -31116.18 | -97.51% | 3276 | 1693 | -1583 | -48.32% | 42259.32 | 48085.11 | 5825.79 | 13.79% | 290 | 179 | -111 | -38.28% | 2021-02-12 01:00
Brampton | 2021 | 637353 | FEEDER CABLE REPLACEMENT GRID I3 - 2021 PHASE 1 | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | Mark Bobanovic | 740782.02 | 762747.7 | 21965.68 | 2.965% | 16982.02 | 117313.25 | 100331.23 | 590.8% | 0 | 0 | 0 |  | 1280 | 2206.73 | 926.73 | 72.4% | 722520 | 643227.72 | -79292.28 | -10.97% | 160 | 178.5 | 18.5 | 11.56% | 2021-08-20 01:00
Brampton | 2021 | 637365 | FEEDER CABLE REPLACEMENT GRID J4 - PH2A (ELECTRICAL) | 99 | COMPLETE | Cont Est Over | Labour est. over | Vehicle Not Charged | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 330823.1 | 255941.46 | -74881.64 | -22.63% | 58932.96 | 44890.32 | -14042.64 | -23.83% | 6479.18 | 4705.69 | -1773.49 | -27.37% | 13650 | 4445.5 | -9204.5 | -67.43% | 251760.96 | 201899.95 | -49861.01 | -19.8% | 366 | 353.5 | -12.5 | -3.415% | 2021-07-23 01:00
Brampton | 2021 | 637366 | FEEDER CABLE REPLACEMENT GRID J4 - PH2B (ELECTRICAL&CIVIL) | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 2303983.13 | 2257204.01 | -46779.12 | -2.03% | 218809.09 | 418190.11 | 199381.02 | 91.12% | 91062.56 | 119904.44 | 28841.88 | 31.67% | 64496 | 37674.38 | -26821.62 | -41.59% | 1929615.48 | 1681435.08 | -248180.4 | -12.86% | 1572 | 1607.5 | 35.5 | 2.258% | 2021-12-10 01:00
Brampton | 2020 | 637371 | 2020 POLE RENEWAL - GRID M2 (1POLE) | 99 | CANCELLED | N/A |  |  | Agostini, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-13 01:00
Brampton | 2021 | 637374 | 2020 POLE RENEWAL GRID O2- 1 POLE | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Agostini, Robert | Yes | Miller, Michael | John Costa | 31083.54 | 17213.75 | -13869.79 | -44.62% | 16594.85 | 8878.19 | -7716.66 | -46.5% | 5458.69 | 3778.79 | -1679.9 | -30.77% | 3900 | 1725.07 | -2174.93 | -55.77% | 5130 | 2831.7 | -2298.3 | -44.8% | 124 | 56 | -68 | -54.84% | 2021-12-13 01:00
Brampton | 2022 | 637390 | 1403 QUEEN ST W TOWNHOME DEVT – SUBD RES EDS | 98 | COMPLETE | Material Under Estimated | Labour est. over | N/A | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 36225.17 | 45950.22 | 9725.05 | 26.85% | 22037.85 | 21659.14 | -378.71 | -1.718% | 5349.32 | 10226.4 | 4877.08 | 91.17% | 5088 | 5864 | 776 | 15.25% | 3750 | 6511.38 | 2761.38 | 73.64% | 123 | 145 | 22 | 17.89% | 2022-12-20 01:00
Brampton | 2022 | 637512 | CABLE INJECTION 2021-GRID I3 (CAPITAL BUDGET PROJECT_151318) | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Miller, Michael | Simon Evason | 611048.54 | 591428.51 | -19620.03 | -3.211% | 35445.56 | 90217.76 | 54772.2 | 154.5% | 58691.62 | 5270.39 | -53421.23 | -91.02% | 3110 | 3497.24 | 387.24 | 12.45% | 513801.36 | 492443.12 | -21358.24 | -4.157% | 280 | 153 | -127 | -45.36% | 2022-05-30 01:00
Brampton | 2022 | 637513 | CABLE INJECTION 2021-GRID G2 (CAPITAL BUDGET PROJECT_151314) | 95 | ANALYZE |  |  |  | Agostini, Robert | Yes | Miller, Michael | Simon Evason | 461887.84 | 517713.91 | 55826.07 | 12.09% | 27116.41 | 71830.6 | 44714.19 | 164.9% | 33438.35 | 13723.69 | -19714.66 | -58.96% | 2380 | 592.06 | -1787.94 | -75.12% | 398953.08 | 431567.56 | 32614.48 | 8.175% | 215 | 57 | -158 | -73.49% | 2023-01-04 01:00
Brampton | 2022 | 637516 | CABLE INJECTION 2021-GRID H2 (CAPITAL BUDGET PROJECT_151316) | 95 | ANALYZE |  |  |  | Agostini, Robert | Yes | Miller, Michael | Simon Evason | 464304.38 | 578901.03 | 114596.65 | 24.68% | 34911.88 | 87830.76 | 52918.88 | 151.6% | 30134.1 | 22412.49 | -7721.61 | -25.62% | 2380 | 2860.86 | 480.86 | 20.2% | 396878.4 | 465796.92 | 68918.52 | 17.37% | 215 | 134 | -81 | -37.67% | 2023-01-04 01:00
Brampton | 2022 | 637517 | CABLE INJECTION 2021-GRID E4 (CAPITAL BUDGET PROJECT_151310) | 95 | ANALYZE |  |  |  | Agostini, Robert | Yes | Miller, Michael | Simon Evason | 469121.8 | 323826.46 | -145295.34 | -30.97% | 27516.09 | 53957.7 | 26441.61 | 96.1% | 33593.95 | 16901.64 | -16692.31 | -49.69% | 2394 | 570.27 | -1823.73 | -76.18% | 405617.76 | 252396.85 | -153220.91 | -37.77% | 216 | 103.5 | -112.5 | -52.08% | 2023-01-04 01:00
Brampton | 2022 | 637518 | CABLE INJECTION 2021-GRID G1 (CAPITAL BUDGET PROJECT_151462) | 95 | ANALYZE |  |  |  | Agostini, Robert | Yes | Miller, Michael | Simon Evason | 458964.37 | 241221.37 | -217743 | -47.44% | 27012.76 | 44595.05 | 17582.29 | 65.09% | 29834.41 | 20158.84 | -9675.57 | -32.43% | 2366 | 4059.84 | 1693.84 | 71.59% | 399751.2 | 172407.64 | -227343.56 | -56.87% | 214 | 172 | -42 | -19.63% | 2023-01-04 01:00
Brampton | 2021 | 637520 | BROOKVALLEY PHASE 2A SUBDIVISION - SUBD RES EDS | 99 | COMPLETE | Labour est. over |  |  | Gamboa, Henry | No | Armstrong, Colby | Richard Cuddy | 26018.22 | 59172.43 | 33154.21 | 127.4% | 18550.2 | 7356.85 | -11193.35 | -60.34% | 610.02 | 499.62 | -110.4 | -18.1% | 2808 | 303 | -2505 | -89.21% | 4050 | 3750 | -300 | -7.407% | 103 | 39 | -64 | -62.14% | 2021-12-22 01:00
Brampton | 2021 | 637637 | 180 DELTA PARK BLVD / BRAM / NS / 3PH | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 66416.56 | 60613.19 | -5803.37 | -8.738% | 25880.74 | 14293.95 | -11586.79 | -44.77% | 19444.38 | 22867.79 | 3423.41 | 17.61% | 2496 | 3309 | 813 | 32.57% | 18595.44 | 20142.45 | 1547.01 | 8.319% | 170 | 185 | 15 | 8.824% | 2021-01-13 01:00
Brampton | 2020 | 637638 | FEEDER 14F1 CABLE REPLACEMENT | 99 | COMPLETE | BOM not accurate | Estimate incorrect | Cont Est Over | Agostini, Robert | Yes | Alectra Utilities | Richard Cuddy | 899404.06 | 922978.17 | 23574.11 | 2.621% | 22895.63 | 84691.09 | 61795.46 | 269.9% | 116974.07 | 135584.26 | 18610.19 | 15.91% | 1248 | 759.49 | -488.51 | -39.14% | 758286.36 | 701943.33 | -56343.03 | -7.43% | 131 | 110.5 | -20.5 | -15.65% | 2020-10-02 01:00
Brampton | 2020 | 637642 | ROGERS BOND CONNECTION- 286 RUTHERFORD ROAD SOUTH | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Brian Erskine | 808.45 | 747.14 | -61.31 | -7.584% | 730.45 | 691.04 | -39.41 | -5.395% | 0 | 0 | 0 |  | 78 | 56.1 | -21.9 | -28.08% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0% | 2020-08-11 01:00
Brampton | 2022 | 637705 | 24 VODDEN ST. E../ BRAM/ NS00048091/ 3 PH PAD | 95 | COMPLETE | Labour est. under | Material Over Estimated | Cont Est Over | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 62528.46 | 90622.7 | 28094.24 | 44.93% | 31287.48 | 39449.24 | 8161.76 | 26.09% | 36859.26 | 35065.26 | -1794 | -4.867% | 6300 | 6904.5 | 604.5 | 9.595% | 10431.72 | 9203.7 | -1228.02 | -11.77% | 149.3333 | 343.25 | 193.9167 | 129.9% | 2022-10-28 01:00
Brampton | 2021 | 637739 | 2021 INSULATOR REPLACEMENT PROGRAM | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | John Costa | 353177.94 | 333437.48 | -19740.46 | -5.589% | 175991.77 | 142836.24 | -33155.53 | -18.84% | 146026.17 | 118693.42 | -27332.75 | -18.72% | 31160 | 66696.47 | 35536.47 | 114% | 0 | 5211.35 | 5211.35 |  | 1575 | 1394.5 | -180.5 | -11.46% | 2021-12-24 01:00
Brampton | 2020 | 637744 | 11038 The Gore Rd - RELOCATION OF UNDERGROUND SECONDARY AND DOWN GUY WIRES | 99 | COMPLETE | Scope change - unforeseen | Labour est. over | BOM not used | Watters, Maxwell | No | Alectra Utilities | John Costa | 9721.76 | 2087.25 | -7634.51 | -78.53% | 8943.65 | 1567.25 | -7376.4 | -82.48% | 767.31 | 0 | -767.31 | -100% | 0 | 0 | 0 |  | 10.8 | 520 | 509.2 | 4715% | 80 | 10 | -70 | -87.5% | 2020-07-09 01:00
Brampton | 2020 | 637808 | MCLAUGHLIN RD N (WANLESS TO MAYFIELD) / BRAM / NS / 1-PH (LAYOUT) | 99 | COMPLETE | Cont Est Over | Scope change - unforeseen | N/A | Rao, Gaurav | No | Alectra Utilities | Reaburn, Jeff | 27752.82 | 22480.61 | -5272.21 | -19% | 2960.31 | 1889.1 | -1071.21 | -36.19% | 7004.91 | 6539.27 | -465.64 | -6.647% | 0 | 0 | 0 |  | 17787.6 | 14052.24 | -3735.36 | -21% | 0 | 0 | 0 |  | 2020-10-23 01:00
Brampton | 2022 | 637817 | GOREWAY DR PH2.1 COTTRELLE BLVD TO CASTLEMORE RD | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Lemire, Blake | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-21 01:00
Brampton | 2021 | 637833 | JOINT USE PERMIT HB2020-026- MAYFIELD ROAD | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Martin, Shane | John Costa | 8318.87 | 7875.09 | -443.78 | -5.335% | 2678.87 | 2657.25 | -21.62 | -0.8071% | 0 | 110.8 | 110.8 |  | 540 | 0 | -540 | -100% | 5100 | 5107.04 | 7.04 | 0.138% | 24 | 25.5 | 1.5 | 6.25% | 2021-05-03
Brampton | 2022 | 637868 | HUMBERWEST PKWY AND CASTLEMORE TOWN CENTRE PLAZA ENTRANCE / BRAM / NS / 1-PH | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Tan, Seefon | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-04 01:00
Brampton | 2021 | 637881 | 44 WESTWYN CRT | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 132377.46 | 139491.55 | 7114.09 | 5.374% | 35092.25 | 18764.49 | -16327.76 | -46.53% | 50820.68 | 50059.15 | -761.53 | -1.498% | 7128 | 4703 | -2425 | -34.02% | 63921.53 | 65964.91 | 2043.38 | 3.197% | 233.2 | 188 | -45.2 | -19.38% | 2021-10-05 01:00
Brampton | 2021 | 637944 | 150 DELTA PARK BLVD / BRAM / UP / 3PH | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 48230.73 | 60411.69 | 12180.96 | 25.26% | 25685.22 | 10742.55 | -14942.67 | -58.18% | 43023.51 | 39792.95 | -3230.56 | -7.509% | 1872 | 2884.5 | 1012.5 | 54.09% | 0 | 6991.69 | 6991.69 |  | 354 | 119.5 | -234.5 | -66.24% | 2021-04-22
Brampton | 2021 | 637946 | 2021 EMERGING PROJECT - 45 WEST DR | 99 | COMPLETE | Scope – Const | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | John Costa | 35349.92 | 55421.6 | 20071.68 | 56.78% | 14470.54 | 10737.05 | -3733.49 | -25.8% | 8414.38 | 8350.13 | -64.25 | -0.7636% | 3717 | 964.71 | -2752.29 | -74.05% | 8748 | 35369.71 | 26621.71 | 304.3% | 103 | 27.5 | -75.5 | -73.3% | 2021-04-26
Brampton | 2022 | 637991 | CNTRYSD VL PH5 ST2 - RES SUBD EDS | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Over Estimated | Gamboa, Henry | No | Erzek, Ryan | Zenon Lipinski | 115123.43 | 571790.98 | 456667.55 | 396.7% | 92303.07 | 13031.46 | -79271.61 | -85.88% | 4749.16 | 96.72 | -4652.44 | -97.96% | 12971.2 | 200 | -12771.2 | -98.46% | 5100 | 5134.8 | 34.8 | 0.6824% | 723.28 | 56.67 | -666.61 | -92.16% | 2022-08-17 01:00
Brampton | 2021 | 638029 | 2021 EMERGING PROJECT - 41/43 ASHWOOD CRES | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 46100.78 | 47086.34 | 985.56 | 2.138% | 8058.68 | 12376.28 | 4317.6 | 53.58% | 23.82 | 0 | -23.82 | -100% | 768 | 0 | -768 | -100% | 37250.28 | 34710.06 | -2540.22 | -6.819% | 23 | 28 | 5 | 21.74% | 2021-08-23 01:00
Brampton | 2021 | 638046 | CABLE INJECTION 2021-GRID E3 (CAPITAL BUDGET PROJECT_151309) | 99 | COMPLETE | N/A |  |  | Agostini, Robert | Yes | Miller, Michael | Simon Evason | 170589.27 | 86902.79 | -83686.48 | -49.06% | 12506.17 | 15170.87 | 2664.7 | 21.31% | 33131.1 | 2932.6 | -30198.5 | -91.15% | 1130 | 1571.42 | 441.42 | 39.06% | 123822 | 67227.9 | -56594.1 | -45.71% | 100 | 26 | -74 | -74% | 2021-11-02 01:00
Brampton | 2022 | 638076 | 7900 HURONTARIO ST / BRAM / NS / 3PH PAD | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Tan, Seefon | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-07 01:00
Brampton | 2022 | 638077 | 7685 HURONTARIO ST / BRAM / NS / 3PH PAD | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Tan, Seefon | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-07 01:00
Brampton | 2021 | 638118 | 2021 POLE RENEWAL -GRID E2- 1 POLE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Reaburn, Jeff | 17379.49 | 9722.91 | -7656.58 | -44.06% | 6303.09 | 4763.75 | -1539.34 | -24.42% | 3566.4 | 2577.38 | -989.02 | -27.73% | 128 | 0 | -128 | -100% | 7382 | 2381.78 | -5000.22 | -67.74% | 8 | 6.5 | -1.5 | -18.75% | 2021-12-23 01:00
Brampton | 2022 | 638119 | 2021 POLE RENEWAL -GRID E4- 4 POLE | 99 | COMPLETE | Cont Est Under | BOM not accurate |  | Agostini, Robert | Yes | Casey, Ryan | K-Line Construction | 127416.58 | 93194.05 | -34222.53 | -26.86% | 13952.19 | 16212.17 | 2259.98 | 16.2% | 58609.39 | 44051.26 | -14558.13 | -24.84% | 896 | 632.05 | -263.95 | -29.46% | 53959 | 32298.57 | -21660.43 | -40.14% | 56 | 49.5 | -6.5 | -11.61% | 2021-12-31 01:00
Brampton | 2021 | 638120 | 2021 POLE RENEWAL -GRID E3- 3 POLES | 99 | COMPLETE | Scope – Eng | BOM not accurate | Vac truck | Agostini, Robert | Yes | Casey, Ryan | John Costa | 110033.32 | 125350.62 | 15317.3 | 13.92% | 53299.19 | 52137.22 | -1161.97 | -2.18% | 34096.13 | 39875.9 | 5779.77 | 16.95% | 16104 | 24144.68 | 8040.68 | 49.93% | 6534 | 9192.82 | 2658.82 | 40.69% | 444 | 576.5 | 132.5 | 29.84% | 2021-05-07
Brampton | 2021 | 638121 | POLE RELOCATIONS (#9079, #9095, #9111) | 99 | COMPLETE | Scope – Eng | Scope – Eng |  | Gamboa, Henry | No | Erzek, Ryan | Richard Cuddy | 129223.25 | 108541.13 | -20682.12 | -16% | 82234.95 | 54919.9 | -27315.05 | -33.22% | 26108.3 | 26447.73 | 339.43 | 1.3% | 20880 | 14704 | -6176 | -29.58% | 0 | 12469.5 | 12469.5 |  | 664 | 501.5 | -162.5 | -24.47% | 2021-06-04 01:00
Brampton | 2021 | 638122 | 238 STEELWELL RD / BRAM / UP / 3PH PAD | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 46509.11 | 44086.58 | -2422.53 | -5.209% | 27371.76 | 4730.23 | -22641.53 | -82.72% | 40805.15 | 36073.29 | -4731.86 | -11.6% | 2917.2 | 775.5 | -2141.7 | -73.42% | 0 | 2507.56 | 2507.56 |  | 181.5 | 63 | -118.5 | -65.29% | 2021-05-03
Brampton | 2021 | 638167 | 215 VETERANS DR / BRAM / NS / 3PH PAD | 95 | COMPLETE | Estimate incorrect | Labour est. over | Material Req incorrectly | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 90732.48 | 91353.12 | 620.64 | 0.684% | 42003.3 | 20957.09 | -21046.21 | -50.11% | 45383.46 | 38881.37 | -6502.09 | -14.33% | 3060 | 5551 | 2491 | 81.41% | 22635.72 | 25963.66 | 3327.94 | 14.7% | 330 | 222.5 | -107.5 | -32.58% | 2021-06-11 01:00
Brampton | 2021 | 638170 | 2021 DISTRIBUTION AUTOMATION 44-496 (44-362), 1 | 99 | COMPLETE | Labour est. under | BOM not accurate |  | Agostini, Robert | Yes | Casey, Ryan | John Costa | 97685.52 | 125853.37 | 28167.85 | 28.84% | 34116.41 | 41210.75 | 7094.34 | 20.79% | 52513.11 | 68982.32 | 16469.21 | 31.36% | 11056 | 15660.3 | 4604.3 | 41.65% | 0 | 0 | 0 |  | 272 | 462 | 190 | 69.85% | 2021-09-27 01:00
Brampton | 2021 | 638171 | 2021 DISTRIBUTION AUTOMATION 44-498 (44-373), 1 | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated | BOM not accurate | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 151680.9 | 239320.19 | 87639.29 | 57.78% | 66404.31 | 91101.58 | 24697.27 | 37.19% | 64356.59 | 84373.82 | 20017.23 | 31.1% | 20920 | 56753.54 | 35833.54 | 171.3% | 0 | 7091.25 | 7091.25 |  | 580 | 1005.25 | 425.25 | 73.32% | 2021-06-25 01:00
Brampton | 2021 | 638172 | 2021 DISTRIBUTION AUTOMATION 44-499 (44-377), 1 | 99 | COMPLETE | Scope – Const | BOM not accurate | N/A | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 130233.65 | 159817.83 | 29584.18 | 22.72% | 53722.09 | 21062.83 | -32659.26 | -60.79% | 59005.56 | 75312.16 | 16306.6 | 27.64% | 17506 | 3340.84 | -14165.16 | -80.92% | 0 | 60102 | 60102 |  | 447 | 99 | -348 | -77.85% | 2021-04-16
Brampton | 2021 | 638173 | 2021 DISTRIBUTION AUTOMATION 44-497 (44-396), 1 | 99 | COMPLETE | Est. Ext. - Act. Internal | BOM not accurate | N/A | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 91551.94 | 149711.35 | 58159.41 | 63.53% | 29603.66 | 15536.92 | -14066.74 | -47.52% | 52452.28 | 66114.42 | 13662.14 | 26.05% | 9496 | 282.76 | -9213.24 | -97.02% | 0 | 67777.25 | 67777.25 |  | 0 | 30.5 | 30.5 |  | 2021-10-29 01:00
Brampton | 2022 | 638269 | 20 DAVISELM DR / BRAM / NS / 3PH | 99 | COMPLETE | Labour est. under | Cont Est Over | Material Under Estimated | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 84155.16 | 136290.32 | 52135.16 | 61.95% | 25338.98 | 85271.52 | 59932.54 | 236.5% | 32448.1 | 37882.47 | 5434.37 | 16.75% | 3060 | 3105 | 45 | 1.471% | 45658.08 | 7269.65 | -38388.43 | -84.08% | 170 | 178.5 | 8.5 | 5% | 2022-07-14 01:00
Brampton | 2021 | 638280 | 2021 SWITCH REPLACEMENT - 44-218, 1 | 99 | COMPLETE | BOM not accurate | Estimate incorrect | Vehicle Under Estimated | Agostini, Robert | Yes | D'Ermes, Michael | John Costa | 123743.86 | 106317.33 | -17426.53 | -14.08% | 28636.61 | 28623.17 | -13.44 | -0.04693% | 82659.77 | 62068.61 | -20591.16 | -24.91% | 9012 | 12782.8 | 3770.8 | 41.84% | 3435.48 | 2842.75 | -592.73 | -17.25% | 242 | 309 | 67 | 27.69% | 2021-09-15 01:00
Brampton | 2021 | 638281 | 2021 SWITCH REPLACEMENT - 44-220, 1 | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | John Costa | 123743.86 | 111436.72 | -12307.14 | -9.946% | 28636.61 | 26696.7 | -1939.91 | -6.774% | 82659.77 | 73682.53 | -8977.24 | -10.86% | 9012 | 7910.94 | -1101.06 | -12.22% | 3435.48 | 3146.55 | -288.93 | -8.41% | 242 | 300 | 58 | 23.97% | 2021-09-15 01:00
Brampton | 2021 | 638282 | 2021 SWITCH REPLACEMENT - 44-236, 1 | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | John Costa | 123977.65 | 117402.57 | -6575.08 | -5.303% | 29518.58 | 32512.13 | 2993.55 | 10.14% | 82011.59 | 61741.59 | -20270 | -24.72% | 9012 | 20046.64 | 11034.64 | 122.4% | 3435.48 | 3102.21 | -333.27 | -9.701% | 242 | 364 | 122 | 50.41% | 2021-10-29 01:00
Brampton | 2021 | 638315 | 2021 SWITCH REPLACEMENT- 44-237, 1 | 99 | COMPLETE | BOM not accurate | Estimate incorrect |  | Agostini, Robert | Yes | Miller, Michael | John Costa | 89137.04 | 113832.7 | 24695.66 | 27.71% | 29334.09 | 27392.72 | -1941.37 | -6.618% | 49199.47 | 73590.48 | 24391.01 | 49.58% | 8248 | 10399.5 | 2151.5 | 26.09% | 2355.48 | 2450 | 94.52 | 4.013% | 264 | 333.5 | 69.5 | 26.33% | 2021-07-08 01:00
Brampton | 2021 | 638316 | 2021 SWITCH REPLACEMENT- 44-275, 1 | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Miller, Michael | John Costa | 127921.43 | 127944.5 | 23.07 | 0.01803% | 54279.58 | 31090.63 | -23188.95 | -42.72% | 54698.37 | 80007.74 | 25309.37 | 46.27% | 16048 | 11715 | -4333 | -27% | 2895.48 | 5131.13 | 2235.65 | 77.21% | 496 | 405.5 | -90.5 | -18.25% | 2021-07-23 01:00
Brampton | 2021 | 638317 | 2021 SWITCH REPLACEMENT- 44-243, 1 | 99 | COMPLETE | BOM not accurate | Estimate incorrect | N/A | Agostini, Robert | Yes | Miller, Michael | John Costa | 89137.04 | 105343.16 | 16206.12 | 18.18% | 29334.09 | 25440.89 | -3893.2 | -13.27% | 49199.47 | 64404.11 | 15204.64 | 30.9% | 8248 | 12646.97 | 4398.97 | 53.33% | 2355.48 | 2851.19 | 495.71 | 21.04% | 232 | 275.25 | 43.25 | 18.64% | 2021-11-16 01:00
Brampton | 2021 | 638328 | 85 COTTRELLE BLVD / BRAM / NS / 1PH (TEMPORARY - LAYOUT) | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Tan, Seefon | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-30 01:00
Brampton | 2022 | 638347 | 2022 SWITCHGEAR RENEWAL-SITE 261 - BRISDALE DR | 99 | COMPLETE | Under 10% | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Zenon Lipinski | 112741.25 | 107662.91 | -5078.34 | -4.504% | 27625.2 | 19531.16 | -8094.04 | -29.3% | 76692.05 | 82959.75 | 6267.7 | 8.173% | 8424 | 5172 | -3252 | -38.6% | 0 | 0 | 0 |  | 216 | 220 | 4 | 1.852% | 2022-05-13 01:00
Brampton | 2021 | 638364 | 2021 TX RENEWAL-GRID P3-1 TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 10648.43 | 8713.32 | -1935.11 | -18.17% | 3346.79 | 2355.48 | -991.31 | -29.62% | 6507.64 | 5787.57 | -720.07 | -11.06% | 794 | 570.27 | -223.73 | -28.18% | 0 | 0 | 0 |  | 21 | 26 | 5 | 23.81% | 2021-09-28 01:00
Brampton | 2021 | 638365 | 2021 TX RENEWAL-GRID G3-10 TX | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 172943.46 | 169941.6 | -3001.86 | -1.736% | 5606.95 | 17069.49 | 11462.54 | 204.4% | 65266.79 | 65592.47 | 325.68 | 0.499% | 220 | 0 | -220 | -100% | 101849.72 | 87279.64 | -14570.08 | -14.31% | 40 | 19 | -21 | -52.5% | 2021-12-16 01:00
Brampton | 2021 | 638367 | 2021 TX RENEWAL- 3PH TX- 75 QUARRY EDGE DR | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 26479.96 | 20196.78 | -6283.18 | -23.73% | 7473.05 | 4590.78 | -2882.27 | -38.57% | 17446.91 | 14221.51 | -3225.4 | -18.49% | 1560 | 1384.49 | -175.51 | -11.25% | 0 | 0 | 0 |  | 40 | 36 | -4 | -10% | 2021-11-18 01:00
Brampton | 2021 | 638403 | 2021 FEEDER CABLE REPLACEMENT GRID J4 - PH1 (ELECTRICAL&CIVIL) | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 575586.88 | 532425.07 | -43161.81 | -7.499% | 43182.68 | 102530.15 | 59347.47 | 137.4% | 8234.84 | 7047.12 | -1187.72 | -14.42% | 0 | 7391.3 | 7391.3 |  | 524169.36 | 415456.5 | -108712.86 | -20.74% | 332 | 340.25 | 8.25 | 2.485% | 2021-07-23 01:00
Brampton | 2021 | 638416 | 2021 POLE RENEWAL -4 MARKET ST- 1 POLE | 99 | COMPLETE | Scope – Const | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | John Costa | 22597.18 | 19447.66 | -3149.52 | -13.94% | 14047.88 | 5944.18 | -8103.7 | -57.69% | 2261.3 | 1904.25 | -357.05 | -15.79% | 3912 | 893.43 | -3018.57 | -77.16% | 2376 | 10705.8 | 8329.8 | 350.6% | 108 | 34 | -74 | -68.52% | 2021-03-22 01:00
Brampton | 2021 | 638470 | 2021 TX RENEWAL-GRID C3- 3 TXS | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | No | Miller, Michael | Richard Cuddy | 35786.22 | 32147.02 | -3639.2 | -10.17% | 12804.15 | 10601.66 | -2202.49 | -17.2% | 19238.07 | 16772.4 | -2465.67 | -12.82% | 3744 | 4080.61 | 336.61 | 8.991% | 0 | 692.35 | 692.35 |  | 96 | 92.5 | -3.5 | -3.646% | 2021-03-02 01:00
Brampton | 2021 | 638471 | 2021 TX RENEWAL-GRID D2- 1TX | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 12525.4 | 8579.62 | -3945.78 | -31.5% | 5090.34 | 2056.84 | -3033.5 | -59.59% | 6187.06 | 6166.36 | -20.7 | -0.3346% | 1248 | 356.42 | -891.58 | -71.44% | 0 | 0 | 0 |  | 32 | 17.5 | -14.5 | -45.31% | 2021-11-27 01:00
Brampton | 2021 | 638472 | 2021 TX RENEWAL-GRID D3 - 1TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 12525.4 | 10458.23 | -2067.17 | -16.5% | 5090.34 | 2558.16 | -2532.18 | -49.74% | 6187.06 | 6166.36 | -20.7 | -0.3346% | 1248 | 579.78 | -668.22 | -53.54% | 0 | 1153.93 | 1153.93 |  | 32 | 17 | -15 | -46.88% | 2021-11-28 01:00
Brampton | 2021 | 638473 | 2021 TX RENEWAL-GRID E4 - 1TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 12525.4 | 9831.76 | -2693.64 | -21.51% | 5090.34 | 3291.22 | -1799.12 | -35.34% | 6187.06 | 6357.58 | 170.52 | 2.756% | 1248 | 182.96 | -1065.04 | -85.34% | 0 | 0 | 0 |  | 32 | 17.5 | -14.5 | -45.31% | 2021-11-27 01:00
Brampton | 2021 | 638474 | 2021 TX RENEWAL-GRID F3 - 2 TXS | 99 | COMPLETE | Labour est. over | BOM cost variance | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 24247.6 | 18385.88 | -5861.72 | -24.17% | 8700.56 | 4409.5 | -4291.06 | -49.32% | 13051.04 | 11552.72 | -1498.32 | -11.48% | 2496 | 2423.66 | -72.34 | -2.898% | 0 | 0 | 0 |  | 64 | 30 | -34 | -53.12% | 2021-08-20 01:00
Brampton | 2021 | 638475 | 2021 TX RENEWAL-GRID H3 - 5 TXS | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 82806.24 | 85641.99 | 2835.75 | 3.425% | 25030.68 | 17858.89 | -7171.79 | -28.65% | 32155.56 | 29095.89 | -3059.67 | -9.515% | 7800 | 2661.27 | -5138.73 | -65.88% | 17820 | 36025.94 | 18205.94 | 102.2% | 200 | 141.5 | -58.5 | -29.25% | 2021-08-11 01:00
Brampton | 2021 | 638476 | 2021 TX RENEWAL-GRID O3 - 2 TXS | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 24247.6 | 18869.06 | -5378.54 | -22.18% | 8700.56 | 5223.18 | -3477.38 | -39.97% | 13051.04 | 11668.94 | -1382.1 | -10.59% | 2496 | 1976.94 | -519.06 | -20.8% | 0 | 0 | 0 |  | 64 | 50 | -14 | -21.88% | 2021-10-15 01:00
Brampton | 2020 | 638532 | HULRT OMSF - ANCHOR AND GUYING RELOCATION | 99 | COMPLETE | Converted Project |  |  | Tobin, Michael | No | Alectra Utilities | Reaburn, Jeff | 13798.37 | 25972.29 | 12173.92 | 88.23% | 9025.51 | 10922.38 | 1896.87 | 21.02% | 1652.86 | 2589.7 | 936.84 | 56.68% | 3120 | 4020.45 | 900.45 | 28.86% | 0 | 8439.76 | 8439.76 |  | 80 | 64 | -16 | -20% | 2020-10-30 01:00
Brampton | 2020 | 638565 | TEMPORARY ANCHOR REMOVAL- MAYFIELD RD POLE#1809 | 99 | COMPLETE | Estimate incorrect | Estimate incorrect | N/A | Pelleja, Emily | No | Alectra Utilities | John Costa | 6116.39 | 5677.65 | -438.74 | -7.173% | 5295.45 | 2827.42 | -2468.03 | -46.61% | 284.94 | 362.22 | 77.28 | 27.12% | 536 | 700.51 | 164.51 | 30.69% | 0 | 1787.5 | 1787.5 |  | 40 | 31.5 | -8.5 | -21.25% | 2020-12-15 01:00
Brampton | 2021 | 638566 | 2021 MINI-POLE REBUILDS - REBUILD 3 CLUSTER ID 21 - 5 | 99 | COMPLETE | Cont Est Over | BOM cost variance | N/A | Agostini, Robert | Yes | D'Ermes, Michael | John Costa | 218944.81 | 205942.47 | -13002.34 | -5.939% | 5226.22 | 25526.03 | 20299.81 | 388.4% | 27975.79 | 33204.76 | 5228.97 | 18.69% | 512 | 0 | -512 | -100% | 185230.8 | 147211.68 | -38019.12 | -20.53% | 32 | 13.5 | -18.5 | -57.81% | 2021-07-19 01:00
Brampton | 2021 | 638567 | 2021 MINI-POLE REBUILDS - REBUILD 6 CLUSTER ID 25 - 5 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | John Costa | 169953.5 | 148965.24 | -20988.26 | -12.35% | 5226.22 | 18634.82 | 13408.6 | 256.6% | 28841.6 | 28122.18 | -719.42 | -2.494% | 512 | 0 | -512 | -100% | 135373.68 | 102208.24 | -33165.44 | -24.5% | 32 | 15 | -17 | -53.12% | 2021-07-08 01:00
Brampton | 2021 | 638568 | 2021 MINI-POLE REBUILDS - REBUILD 9 CLUSTER ID 78 - 5 | 99 | COMPLETE | Cont Est Over |  |  | Agostini, Robert | Yes | D'Ermes, Michael | John Costa | 215705.52 | 207753.11 | -7952.41 | -3.687% | 5226.22 | 28401.8 | 23175.58 | 443.4% | 45976.86 | 43834.76 | -2142.1 | -4.659% | 512 | 0 | -512 | -100% | 163990.44 | 135516.55 | -28473.89 | -17.36% | 32 | 74 | 42 | 131.2% | 2021-12-07 01:00
Brampton | 2021 | 638569 | 2021 MINI-POLE REBUILDS - REBUILD 12 CLUSTER ID 14 - 5 | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | John Costa | 282853.45 | 324535.06 | 41681.61 | 14.74% | 7184.44 | 39545.49 | 32361.05 | 450.4% | 44574.85 | 56153.42 | 11578.57 | 25.98% | 512 | 0 | -512 | -100% | 230582.16 | 228836.15 | -1746.01 | -0.7572% | 32 | 24 | -8 | -25% | 2021-12-07 01:00
Brampton | 2021 | 638624 | 2021 TX RENEWAL-GRID M3 - 2 TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 19688.71 | 16837.35 | -2851.36 | -14.48% | 6317.82 | 3960.35 | -2357.47 | -37.31% | 12590.89 | 11989 | -601.89 | -4.78% | 780 | 888 | 108 | 13.85% | 0 | 0 | 0 |  | 40 | 50 | 10 | 25% | 2021-09-15 01:00
Brampton | 2021 | 638625 | 2021 TX RENEWAL-GRID N3 - 1TX | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 8813.55 | 8655.43 | -158.12 | -1.794% | 2128.11 | 2664.69 | 536.58 | 25.21% | 6295.44 | 5630.74 | -664.7 | -10.56% | 390 | 360 | -30 | -7.692% | 0 | 0 | 0 |  | 20 | 25.25 | 5.25 | 26.25% | 2021-09-29 01:00
Brampton | 2021 | 638664 | 2021 SWITCHGEAR RENEWAL-SITE 253 - VALLEY CREEK DR | 99 | COMPLETE | BOM not accurate | Labour est. over |  | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 138310.92 | 101592.58 | -36718.34 | -26.55% | 29047.99 | 15754.38 | -13293.61 | -45.76% | 100986.93 | 80868.91 | -20118.02 | -19.92% | 8276 | 4969.29 | -3306.71 | -39.96% | 0 | 0 | 0 |  | 206 | 176 | -30 | -14.56% | 2021-12-16 01:00
Brampton | 2021 | 638666 | 2021 SWITCHGEAR RENEWAL-SITE 229- 121 DON MINAKER DR | 99 | COMPLETE | BOM not accurate | Labour est. over | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 135158.54 | 98966.58 | -36191.96 | -26.78% | 26145.91 | 15580.83 | -10565.08 | -40.41% | 101128.63 | 77846.19 | -23282.44 | -23.02% | 7884 | 5539.56 | -2344.44 | -29.74% | 0 | 0 | 0 |  | 206 | 147 | -59 | -28.64% | 2021-08-13 01:00
Brampton | 2021 | 638704 | 80 HALE RD | 99 | COMPLETE | Converted Project |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 98038.68 | 115550.7 | 17512.02 | 17.86% | 38949.86 | 24175.67 | -14774.19 | -37.93% | 63223.59 | 68673.72 | 5450.13 | 8.62% | 8316 | 5947 | -2369 | -28.49% | 12134.23 | 16754.31 | 4620.08 | 38.07% | 273.4 | 289.5 | 16.1 | 5.889% | 2021-06-14 01:00
Brampton | 2021 | 638705 | 46 HALE RD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-04-30
Brampton | 2021 | 638731 | 2021 LEFT BEHIND CABLE SEGMENTS - GRID J3 | 99 | COMPLETE | Under 10% |  | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 664696.79 | 685286.47 | 20589.68 | 3.098% | 48026.96 | 128825.52 | 80798.56 | 168.2% | 18087.39 | 30524.18 | 12436.79 | 68.76% | 10152 | 9011.88 | -1140.12 | -11.23% | 588430.44 | 516924.89 | -71505.55 | -12.15% | 315 | 395.25 | 80.25 | 25.48% | 2021-08-13 01:00
Brampton | 2021 | 638748 | 150 HOWDEN BLVD / BRAM / SR / 3PH | 99 | COMPLETE | Estimate incorrect | Labour est. over | BOM not accurate | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 37353.38 | 32470.83 | -4882.55 | -13.07% | 15398.66 | 11691.85 | -3706.81 | -24.07% | 1383.6 | 1063.19 | -320.41 | -23.16% | 1872 | 2819.5 | 947.5 | 50.61% | 18699.12 | 16896.29 | -1802.83 | -9.641% | 120 | 135 | 15 | 12.5% | 2021-03-09 01:00
Brampton | 2020 | 638793 | 8850 MCLAUGHLIN RD S / BRAM / UP / 3PH | 99 | COMPLETE | Estimate incorrect | Cont Est Over | BOM not accurate | Rao, Gaurav | No | Alectra Utilities | Simon Evason | 26661.98 | 22670.58 | -3991.4 | -14.97% | 25170.14 | 3186.16 | -21983.98 | -87.34% | 21189.84 | 16476.51 | -4713.33 | -22.24% | 2652 | 1393.11 | -1258.89 | -47.47% | 0 | 1614.8 | 1614.8 |  | 160 | 33 | -127 | -79.38% | 2020-12-04 01:00
Brampton | 2022 | 638794 | 292 CONESTOGA DR / BRAM / NS / 3PH | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Tan, Seefon | Dre Danieli | 46261.37 | 0 | -46261.37 | -100% | 25745.96 | 0 | -25745.96 | -100% | 18643.41 | 0 | -18643.41 | -100% | 1872 | 0 | -1872 | -100% | 0 | 0 | 0 |  | 170 | 0 | -170 | -100% | 2020-10-30 01:00
Brampton | 2021 | 638830 | JOINT USE PERMIT #HB2020-036 - RUTHERFORD ROAD SOUTH, BRAMPTON | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Martin, Shane | John Costa | 6166.07 | 5434.03 | -732.04 | -11.87% | 2629.07 | 1913.56 | -715.51 | -27.22% | 0 | 122.47 | 122.47 |  | 135 | 248 | 113 | 83.7% | 3402 | 3150 | -252 | -7.407% | 6 | 17.5 | 11.5 | 191.7% | 2021-05-04
Brampton | 2022 | 638849 | 175 VETERANS DR./ BRAM/ NS00078910/ 500 KVA PAD | 95 | COMPLETE | Material Under Estimated | N/A | N/A | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 84661.74 | 131521.41 | 46859.67 | 55.35% | 26497.36 | 27325.22 | 827.86 | 3.124% | 38578.34 | 62479.87 | 23901.53 | 61.96% | 4446 | 3944 | -502 | -11.29% | 37490.04 | 37772.32 | 282.28 | 0.7529% | 172 | 212.75 | 40.75 | 23.69% | 2022-09-20 01:00
Brampton | 2022 | 639000 | KENDALWOOD LAND - SUBD RES EDS | 95 | COMPLETE | Labour est. over | Cont Est Under | Vehicle Over Estimated- | Gamboa, Henry | No | Ferry, Rodnne | Zenon Lipinski | 809661.75 | 803323.93 | -6337.82 | -0.7828% | 139716.66 | 128506.67 | -11209.99 | -8.023% | 19882.49 | 23698.03 | 3815.54 | 19.19% | 18813 | 10953 | -7860 | -41.78% | 631249.6 | 638015.43 | 6765.83 | 1.072% | 723 | 346.5 | -376.5 | -52.07% | 2022-12-14 01:00
Brampton | 2021 | 639086 | DOWN GUYS WIRES AND ANCHORS RELOCATION - HUMBERWEST PKWY | 99 | COMPLETE | Scope change - unforeseen | RFC not approved in time |  | Watters, Maxwell | No | Robinson, David | Reaburn, Jeff | 13148.11 | 28719.92 | 15571.81 | 118.4% | 9312.55 | 12399.85 | 3087.3 | 33.15% | 3835.56 | 6386.5 | 2550.94 | 66.51% | 0 | 2732 | 2732 |  | 0 | 7201.57 | 7201.57 |  | 86 | 115.25 | 29.25 | 34.01% | 2021-05-06
Brampton | 2022 | 639113 | 2022 SWITCHGEAR RENEWAL - SITE# 247 - BRISDALE DR, S OF RANCHERO DR | 99 | COMPLETE | Labour est. over | Material Under Estimated | Vehicle Under Estimated | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 118475.29 | 116672.13 | -1803.16 | -1.522% | 31650.31 | 23833.37 | -7816.94 | -24.7% | 82215.98 | 85860.34 | 3644.36 | 4.433% | 4609 | 6978.42 | 2369.42 | 51.41% | 0 | 0 | 0 |  | 204 | 209 | 5 | 2.451% | 2022-04-28
Brampton | 2021 | 639184 | JOINT USE PERMIT #HB2020-041, INNIS LAKE ROAD, BRAMPTON | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | John Costa | 5415.5 | 2945.77 | -2469.73 | -45.6% | 3720.94 | 1303.51 | -2417.43 | -64.97% | 183.47 | 304.14 | 120.67 | 65.77% | 431.09 | 249 | -182.09 | -42.24% | 1080 | 1089.12 | 9.12 | 0.8444% | 15.97 | 3 | -12.97 | -81.21% | 2021-07-16 01:00
Brampton | 2022 | 639485 | 563 BOVAIRD DR E / UP / BRAM / 1PH PAD | 99 | COMPLETE | Material Under Estimated | Labour est. under | N/A | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 30446.96 | 30543.93 | 96.97 | 0.3185% | 8943.25 | 7818.28 | -1124.97 | -12.58% | 6739.75 | 8011.26 | 1271.51 | 18.87% | 900 | 1520 | 620 | 68.89% | 13863.96 | 13194.39 | -669.57 | -4.83% | 58 | 68.5 | 10.5 | 18.1% | 2022-03-30
Brampton | 2022 | 639489 | MAYFIELD DEVELOPMENT (21T-18003B) - SUBD RES EDS | 98 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Over Estimated | Gamboa, Henry | No | Armstrong, Colby | Zenon Lipinski | 65291.22 | 41956.66 | -23334.56 | -35.74% | 39887.94 | 28011 | -11876.94 | -29.78% | 10127.28 | 5247.66 | -4879.62 | -48.18% | 10176 | 3598 | -6578 | -64.64% | 5100 | 5100 | 0 | 0% | 236 | 211 | -25 | -10.59% | 2022-05-11 01:00
Brampton | 2021 | 639711 | 465 DEERHURST DR - SERVICE UPGRADE | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 28683.1 | 31083.94 | 2400.84 | 8.37% | 19661.89 | 3586 | -16075.89 | -81.76% | 31230.21 | 22145.23 | -9084.98 | -29.09% | 2376 | 702 | -1674 | -70.45% | 0 | 4650.71 | 4650.71 |  | 92.4 | 36 | -56.4 | -61.04% | 2021-05-20 01:00
Brampton | 2022 | 639715 | ASHLEY FAMILY HOMES - SUBD RES EDS | 99 | COMPLETE | Labour est. over | Material Under Estimated | Vehicle Over Estimated- | Gamboa, Henry | No | Erzek, Ryan | Zenon Lipinski | 71586.41 | 276252.74 | 204666.33 | 285.9% | 50949.65 | 36705.5 | -14244.15 | -27.96% | 3624.76 | 5322.83 | 1698.07 | 46.85% | 11504 | 10204 | -1300 | -11.3% | 5508 | 5258.85 | -249.15 | -4.523% | 284 | 391 | 107 | 37.68% | 2022-05-10 01:00
Brampton | 2021 | 639739 | BELL SECONDARY TRANSFER POLE 48-0 - 48 DUNBARTON CRES | 99 | COMPLETE | Labour est. under | N/A | N/A | Agostini, Robert | No | Casey, Ryan | Brian Erskine | 2731.24 | 3413.24 | 682 | 24.97% | 2342.6 | 2914.25 | 571.65 | 24.4% | 28.64 | 0 | -28.64 | -100% | 360 | 498.99 | 138.99 | 38.61% | 0 | 0 | 0 |  | 8 | 24 | 16 | 200% | 2021-02-09 01:00
Brampton | 2021 | 639748 | 2021 4KV CONV PH3E - (ETOBICOKE DR) | 99 | COMPLETE | Scope change - unforeseen |  |  | Agostini, Robert | No | D'Ermes, Michael | Reaburn, Jeff | 156969.74 | 148783.51 | -8186.23 | -5.215% | 57423.76 | 54035.23 | -3388.53 | -5.901% | 15557.98 | 13946.58 | -1611.4 | -10.36% | 13788 | 23583.91 | 9795.91 | 71.05% | 70200 | 57217.79 | -12982.21 | -18.49% | 418 | 421.5 | 3.5 | 0.8373% | 2021-12-17 01:00
Brampton | 2021 | 639838 | 215 VETERANS DR / BRAM / NS / 3PH PAD (TEMP) | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Tan, Seefon | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-05 01:00
Brampton | 2021 | 639849 | 7850 HERITAGE RD/BRA/UP00103588/4.5 MVA C.O. TX'S | 99 | COMPLETE | Estimate incorrect | Labour est. over | Material Req incorrectly | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 50902.39 | 43945.37 | -6957.02 | -13.67% | 23308.78 | 18466.31 | -4842.47 | -20.78% | 7884.29 | 1413.51 | -6470.78 | -82.07% | 3240 | 2396 | -844 | -26.05% | 21469.32 | 21669.55 | 200.23 | 0.9326% | 132 | 154 | 22 | 16.67% | 2021-12-07 01:00
Brampton | 2021 | 639857 | 6 ANGELBLUFF CRT / BRAM / NS / 1PH PAD | 99 | COMPLETE | Estimate incorrect | Labour est. over | Cont Est Over | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 35830.54 | 31603.07 | -4227.47 | -11.8% | 13022.23 | 7057.48 | -5964.75 | -45.8% | 11187.31 | 9269.86 | -1917.45 | -17.14% | 900 | 1188 | 288 | 32% | 11965 | 14087.73 | 2122.73 | 17.74% | 90 | 77.5 | -12.5 | -13.89% | 2021-10-15 01:00
Brampton | 2021 | 640122 | JOINT USE PERMIT HB2021-001- TILBURY COURT | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Martin, Shane | John Costa | 5954.2 | 5583.4 | -370.8 | -6.228% | 1958.2 | 1736.96 | -221.24 | -11.3% | 0 | 0 | 0 |  | 0 | 90 | 90 |  | 3996 | 3756.44 | -239.56 | -5.995% | 0 | 6 | 6 |  | 2021-07-30 01:00
Brampton | 2021 | 640180 | 10 HEDGEDALE RD | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 57414.57 | 51083.12 | -6331.45 | -11.03% | 31058.58 | 10559.87 | -20498.71 | -66% | 30572.73 | 20029.36 | -10543.37 | -34.49% | 3564 | 2087 | -1477 | -41.44% | 16804.26 | 18406.89 | 1602.63 | 9.537% | 137.6 | 110.5 | -27.1 | -19.69% | 2021-07-07 01:00
Brampton | 2021 | 640246 | 2021 EMERGING PROJECT - MS10 F3 CABLE REPLACEMENT | 99 | COMPLETE | Scope change - unforeseen | BOM not accurate | Labour est. over | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 151179.61 | 111371.58 | -39808.03 | -26.33% | 40988.71 | 25434.41 | -15554.3 | -37.95% | 110.46 | 4311.81 | 4201.35 | 3804% | 14400 | 4436 | -9964 | -69.19% | 95680.44 | 77189.36 | -18491.08 | -19.33% | 336 | 216 | -120 | -35.71% | 2021-06-11 01:00
Brampton | 2021 | 640287 | 10950 GOREWAY DR/BRA/NS00100404/1500 KVA PAD | 99 | COMPLETE | Estimate incorrect | Labour est. over | Cont Est Over | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 94583.22 | 74676.07 | -19907.15 | -21.05% | 27317.31 | 21222.54 | -6094.77 | -22.31% | 77409.75 | 42925.18 | -34484.57 | -44.55% | 5130 | 4614 | -516 | -10.06% | 7076.16 | 5914.35 | -1161.81 | -16.42% | 172 | 240.75 | 68.75 | 39.97% | 2021-10-18 01:00
Brampton | 2022 | 640292 | 215 WILKINSON RD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-28
Brampton | 2022 | 640311 | 917 BOVAIRD DR.W./BRA/NS00097122/150 KVA PAD | 95 | COMPLETE | Labour est. under | Cont Est Over | Material Over Estimated | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 157887.88 | 212206.32 | 54318.44 | 34.4% | 37663.35 | 178760.26 | 141096.91 | 374.6% | 33731.53 | 29118.81 | -4612.72 | -13.67% | 6660 | 4239 | -2421 | -36.35% | 79833 | 88.25 | -79744.75 | -99.89% | 206 | 214.5 | 8.5 | 4.126% | 2022-09-19 01:00
Brampton | 2021 | 640494 | 2021 DA- AIRPORT RD S OF WILLIAMS PKWY, 1 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 119273.97 | 69880.26 | -49393.71 | -41.41% | 10640.48 | 14769.77 | 4129.29 | 38.81% | 52143.49 | 17294.69 | -34848.8 | -66.83% | 0 | 632.05 | 632.05 |  | 56490 | 37183.75 | -19306.25 | -34.18% | 30 | 48.5 | 18.5 | 61.67% | 2021-08-26 01:00
Brampton | 2021 | 640496 | 2021-44KV D/A SWITCH REPLACEMENT(44-137) - ITD2021-43, 1 | 99 | COMPLETE | BOM not accurate | Cont Est Under |  | Agostini, Robert | Yes | Miller, Michael | Reaburn, Jeff | 185234.9 | 227022.27 | 41787.37 | 22.56% | 16593.15 | 28802.55 | 12209.4 | 73.58% | 84257.27 | 99824.16 | 15566.89 | 18.48% | 0 | 898.18 | 898.18 |  | 84384.48 | 97497.38 | 13112.9 | 15.54% | 48 | 64 | 16 | 33.33% | 2021-09-03 01:00
Brampton | 2021 | 640527 | 225 MALTA AVE/ BRAM/ NS/00108870/ X 1500 KVA PAD | 95 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 77965.8 | 79084.07 | 1118.27 | 1.434% | 32348.15 | 20891.67 | -11456.48 | -35.42% | 47103.85 | 42127.69 | -4976.16 | -10.56% | 6300 | 3284 | -3016 | -47.87% | 14563.8 | 12780.71 | -1783.09 | -12.24% | 212 | 217.5 | 5.5 | 2.594% | 2021-12-16 01:00
Brampton | 2021 | 640645 | 2021 DA- STEELES E OF WINSTON CHURCHILL, 1 | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Reaburn, Jeff | 94358.88 | 98428.05 | 4069.17 | 4.312% | 30753.32 | 13902.5 | -16850.82 | -54.79% | 52478.08 | 55354.37 | 2876.29 | 5.481% | 10392 | 532.25 | -9859.75 | -94.88% | 735.48 | 28638.93 | 27903.45 | 3794% | 44 | 50 | 6 | 13.64% | 2021-10-22 01:00
Brampton | 2022 | 640646 | 305 FOGAL ROAD | 95 | COMPLETE | Labour est. over | Cont Est Under | Vehicle Under Estimated | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 94863.39 | 92925.64 | -1937.75 | -2.043% | 39050.79 | 21976.91 | -17073.88 | -43.72% | 39590.9 | 42655.17 | 3064.27 | 7.74% | 7128 | 9507.5 | 2379.5 | 33.38% | 9093.7 | 18786.06 | 9692.36 | 106.6% | 233.2 | 251 | 17.8 | 7.633% | 2022-07-26 01:00
Brampton | 2022 | 640658 | 2021 TX RENEWAL-GRID J3- 4TX | 99 | COMPLETE | Cont Est Under | Vac truck |  | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 41129.87 | 51028.98 | 9899.11 | 24.07% | 11018.33 | 13778.5 | 2760.17 | 25.05% | 26495.54 | 26456.19 | -39.35 | -0.1485% | 3616 | 4460 | 844 | 23.34% | 0 | 6334.29 | 6334.29 |  | 81 | 103 | 22 | 27.16% | 2022-03-22 01:00
Brampton | 2022 | 640659 | 2021 TX RENEWAL-GRID F4- 1TX | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 11787.97 | 12855.52 | 1067.55 | 9.056% | 4299.81 | 4029.67 | -270.14 | -6.283% | 6572.16 | 5963.89 | -608.27 | -9.255% | 916 | 624 | -292 | -31.88% | 0 | 2237.96 | 2237.96 |  | 41 | 51 | 10 | 24.39% | 2022-01-07 01:00
Brampton | 2022 | 640660 | 2021 TX RENEWAL-GRID H2- 2TX | 99 | COMPLETE | Estimate incorrect | Cont Est Under |  | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 21913.55 | 29557.26 | 7643.71 | 34.88% | 6539.33 | 6748.36 | 209.03 | 3.197% | 13558.22 | 13407.73 | -150.49 | -1.11% | 1816 | 1936 | 120 | 6.608% | 0 | 7465.17 | 7465.17 |  | 81 | 49 | -32 | -39.51% | 2022-01-06 01:00
Brampton | 2021 | 640681 | 2021 POLE RENEWAL -GRID C4- 4 POLES | 99 | COMPLETE | Cont Est Under | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | John Costa | 53947.91 | 72485.98 | 18538.07 | 34.36% | 9436.06 | 15222.06 | 5786 | 61.32% | 7775.65 | 8201.65 | 426 | 5.479% | 0 | 0 | 0 |  | 36736.2 | 49062.27 | 12326.07 | 33.55% | 48 | 10 | -38 | -79.17% | 2021-12-16 01:00
Brampton | 2022 | 640682 | 2022 POLE RENEWAL GRID I4 - 4 POLES | 99 | COMPLETE | Labour est. over | Cont Est Under | Vehicle Over Estimated- | Agostini, Robert | No | Casey, Ryan | K-Line Construction | 70830.08 | 59343.33 | -11486.75 | -16.22% | 42481.69 | 8118.56 | -34363.13 | -80.89% | 10580.39 | 11427.88 | 847.49 | 8.01% | 13368 | 0 | -13368 | -100% | 4400 | 39796.89 | 35396.89 | 804.5% | 328 | 8 | -320 | -97.56% | 2022-09-23 01:00
Brampton | 2021 | 640683 | 2021 POLE RENEWAL -GRID I5- 3 POLES | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Casey, Ryan | John Costa | 62760.58 | 56076.55 | -6684.03 | -10.65% | 11517.17 | 10119.02 | -1398.15 | -12.14% | 6216.41 | 9392.27 | 3175.86 | 51.09% | 448 | 0 | -448 | -100% | 44579 | 36565.26 | -8013.74 | -17.98% | 28 | 8 | -20 | -71.43% | 2021-12-23 01:00
Brampton | 2021 | 640688 | 2021 POLE RENEWAL GRID G2- 3 POLES | 99 | COMPLETE | Cont Est Under | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Reaburn, Jeff | 69178.32 | 104163.07 | 34984.75 | 50.57% | 8376.81 | 20761.78 | 12384.97 | 147.8% | 17514.51 | 17438.93 | -75.58 | -0.4315% | 0 | 0 | 0 |  | 43287 | 65962.36 | 22675.36 | 52.38% | 24 | 16 | -8 | -33.33% | 2021-12-23 01:00
Brampton | 2022 | 640692 | 2022 POLE RENEWAL GRID J4 PH1- 6 POLES | 95 | ANALYZE |  |  |  | Agostini, Robert | Yes | Miller, Michael | AW Group | 377928.87 | 449374.61 | 71445.74 | 18.9% | 43273.92 | 87095.51 | 43821.59 | 101.3% | 68523.95 | 96761.67 | 28237.72 | 41.21% | 0 | 0 | 0 |  | 266131 | 265517.43 | -613.57 | -0.2306% | 40 | 49 | 9 | 22.5% | 2023-01-03 01:00
Brampton | 2022 | 640745 | 2022 TX RENEWAL(BATCH#2)2021 CARRY OVER-GRID N2 - 4 TXS | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Under Estimated | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 49042.66 | 46939.98 | -2102.68 | -4.287% | 16780.57 | 13817.01 | -2963.56 | -17.66% | 26502.09 | 29846.34 | 3344.25 | 12.62% | 5760 | 3276.63 | -2483.37 | -43.11% | 0 | 0 | 0 |  | 128 | 95.5 | -32.5 | -25.39% | 2022-11-15 01:00
Brampton | 2021 | 640817 | 370 MAIN ST.N./ BRAM/ UP00115791/ PRIMARY CABLE RELOCATION | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 161145.42 | 153776.08 | -7369.34 | -4.573% | 35878.6 | 35302.67 | -575.93 | -1.605% | 30270.02 | 29791.1 | -478.92 | -1.582% | 7020 | 7060.5 | 40.5 | 0.5769% | 87976.8 | 81621.81 | -6354.99 | -7.223% | 200 | 314 | 114 | 57% | 2021-05-15
Brampton | 2022 | 640856 | 75 COTTRELLE BLVD / NS / BRAM / 3PH PAD | 95 | COMPLETE | Cont Est Under | Material Over Estimated | Labour est. over | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 68507.36 | 91312.47 | 22805.11 | 33.29% | 26359.86 | 14822.21 | -11537.65 | -43.77% | 50621.5 | 32409.7 | -18211.8 | -35.98% | 2160 | 2564 | 404 | 18.7% | 11716 | 41516.56 | 29800.56 | 254.4% | 170 | 121.5 | -48.5 | -28.53% | 2022-08-03 01:00
Brampton | 2022 | 640880 | FEEDER CABLE REPLACEMENT GRID I3 - 2022 PHASE 2 | 99 | COMPLETE | Cont Est Over | Labour est. over | Vehicle Over Estimated- | Agostini, Robert | Yes | Casey, Ryan | Transpower Group | 830457.17 | 728827.72 | -101629.45 | -12.24% | 130569.6 | 142760.53 | 12190.93 | 9.337% | 10268.57 | 16644.3 | 6375.73 | 62.09% | 18000 | 11937.06 | -6062.94 | -33.68% | 671619 | 557485.83 | -114133.17 | -16.99% | 700 | 554.5 | -145.5 | -20.79% | 2022-06-30 01:00
Brampton | 2021 | 640886 | 2021 POLE RENEWAL PH1 GRID I5 - 4 POLES | 99 | COMPLETE | Cont Est Under | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Reaburn, Jeff | 129920.96 | 188799.23 | 58878.27 | 45.32% | 12264.07 | 27808.14 | 15544.07 | 126.7% | 42989.89 | 43292.97 | 303.08 | 0.705% | 0 | 0 | 0 |  | 74667 | 117698.12 | 43031.12 | 57.63% | 32 | 17 | -15 | -46.88% | 2021-12-23 01:00
Brampton | 2022 | 640893 | 2022 TX RENEWAL(OH)BATCH#2-GRID D4-1TX | 99 | COMPLETE | N/A | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Zenon Lipinski | 12576.79 | 13676.77 | 1099.98 | 8.746% | 6926.48 | 7664.02 | 737.54 | 10.65% | 3530.31 | 4089.96 | 559.65 | 15.85% | 2120 | 1922.79 | -197.21 | -9.302% | 0 | 0 | 0 |  | 40 | 56 | 16 | 40% | 2022-11-02 01:00
Brampton | 2022 | 640904 | 90 COLLINGWOOD AVE | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Under | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 125610.6 | 96680.68 | -28929.92 | -23.03% | 39055.07 | 13038.56 | -26016.51 | -66.61% | 30067.23 | 24879.28 | -5187.95 | -17.25% | 4752 | 3578 | -1174 | -24.71% | 51736.3 | 55184.84 | 3448.54 | 6.666% | 162.8 | 163.5 | 0.7 | 0.43% | 2022-01-10 01:00
Brampton | 2022 | 641014 | 286 RUTHERFORD RD SOUTH | 99 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 160222.58 | 96628.98 | -63593.6 | -39.69% | 45955.88 | 12295.55 | -33660.33 | -73.24% | 85688.7 | 58453.41 | -27235.29 | -31.78% | 8316 | 4250.5 | -4065.5 | -48.89% | 20262 | 21629.52 | 1367.52 | 6.749% | 246 | 128.5 | -117.5 | -47.76% | 2022-02-14 01:00
Brampton | 2022 | 641039 | SABERWOOD HOMES - SUBD RES EDS | 99 | COMPLETE | Labour est. over | N/A | N/A | Gamboa, Henry | No | Armstrong, Colby | Zenon Lipinski | 131268.17 | 126308.1 | -4960.07 | -3.779% | 32053.72 | 27075.56 | -4978.16 | -15.53% | 523.45 | 541.54 | 18.09 | 3.456% | 1224 | 1224 | 0 | 0% | 97467 | 97467 | 0 | 0% | 93 | 98.5 | 5.5 | 5.914% | 2022-09-02 01:00
Brampton | 2021 | 641162 | 2300 NORTH PARK DRIVE DOWN GUY WIRE AND ANCHOR RELOCATION | 98 | COMPLETE | Estimate incorrect | N/A | N/A | Watters, Maxwell | No | Robinson, David | Reaburn, Jeff | 2653.16 | 9061.21 | 6408.05 | 241.5% | 2030.65 | 4479.83 | 2449.18 | 120.6% | 622.51 | 809.38 | 186.87 | 30.02% | 0 | 1632 | 1632 |  | 0 | 2140 | 2140 |  | 16 | 61.5 | 45.5 | 284.4% | 2021-09-03 01:00
Brampton | 2022 | 641166 | 11801 BRAMALEA RD / BRAM / NS00119574 / 3PH PAD | 95 | COMPLETE | Material Under Estimated | Labour est. over | Vehicle Under Estimated | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 54835.13 | 78508.43 | 23673.3 | 43.17% | 25897.56 | 16400.46 | -9497.1 | -36.67% | 20246.57 | 47928.46 | 27681.89 | 136.7% | 1800 | 5192 | 3392 | 188.4% | 6891 | 8987.51 | 2096.51 | 30.42% | 170 | 174 | 4 | 2.353% | 2022-10-14 01:00
Brampton | 2022 | 641230 | CREDITVIEW WOODS - SUBD RES EDS | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Under Estimated | Gamboa, Henry | No | Paesano, Chelsea | Zenon Lipinski | 266594.85 | 235286.55 | -31308.3 | -11.74% | 64526.67 | 40726.46 | -23800.21 | -36.88% | 2707.18 | 5601.44 | 2894.26 | 106.9% | 12480 | 1568 | -10912 | -87.44% | 186881 | 187390.65 | 509.65 | 0.2727% | 256 | 94.75 | -161.25 | -62.99% | 2022-12-02 01:00
Brampton | 2022 | 641416 | 4 EDVAC/ BRAM/ UP00127303/ 1500 KVA TX | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Under | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 44122.75 | 46667.71 | 2544.96 | 5.768% | 19938.14 | 9757.79 | -10180.35 | -51.06% | 43344.29 | 34198.57 | -9145.72 | -21.1% | 2700 | 1968.5 | -731.5 | -27.09% | 490.32 | 742.85 | 252.53 | 51.5% | 88 | 75 | -13 | -14.77% | 2022-01-06 01:00
Brampton | 2022 | 641442 | 709 QUEEN ST W / BRAM / NS00114490 / 3PH PAD | 95 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Over Estimated- | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 88462.16 | 73854.32 | -14607.84 | -16.51% | 32246.13 | 21311.31 | -10934.82 | -33.91% | 25324.03 | 26275.89 | 951.86 | 3.759% | 5400 | 4235.25 | -1164.75 | -21.57% | 25492 | 22031.87 | -3460.13 | -13.57% | 210 | 202.25 | -7.75 | -3.69% | 2022-10-13 01:00
Brampton | 2021 | 641472 | 50 WENTWORTH CRT/ BRAM/ UP00095664/ 150KVA TX | 99 | COMPLETE | Estimate incorrect | Cont Est Over | Labour est. over | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 47228.41 | 50644.61 | 3416.2 | 7.233% | 26352.08 | 13194.91 | -13157.17 | -49.93% | 20168.33 | 16499.22 | -3669.11 | -18.19% | 4680 | 2706.5 | -1973.5 | -42.17% | 18378 | 18243.98 | -134.02 | -0.7292% | 158 | 128.5 | -29.5 | -18.67% | 2021-10-18 01:00
Brampton | 2022 | 641501 | 350 DEERHURST DR / BRAM / NS00133739 / 3PH PAD | 95 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Cont Est Under | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 58433.79 | 59933.64 | 1499.85 | 2.567% | 31195.25 | 9563.44 | -21631.81 | -69.34% | 31832.54 | 34084.16 | 2251.62 | 7.073% | 5400 | 2322 | -3078 | -57% | 12356 | 13964.04 | 1608.04 | 13.01% | 210 | 91.5 | -118.5 | -56.43% | 2022-09-28 01:00
Brampton | 2022 | 641605 | 2022 CABLE INJECTION -GRID I3 (CAPITAL BUDGET PROJECT_151318) | 99 | COMPLETE | N/A |  |  | Agostini, Robert | Yes | Casey, Ryan | Simon Evason | 377284.84 | 624305.87 | 247021.03 | 65.47% | 37215.42 | 87049.8 | 49834.38 | 133.9% | 36549.42 | 0 | -36549.42 | -100% | 1120 | 0 | -1120 | -100% | 302400 | 537256.07 | 234856.07 | 77.66% | 70 | 9 | -61 | -87.14% | 2022-05-30 01:00
Brampton | 2022 | 641633 | ROSEDALE VILLAGE PH7B STG1 - SUBD RES EDS | 99 | COMPLETE | Labour est. over | N/A | N/A | Gamboa, Henry | No | Armstrong, Colby | Zenon Lipinski | 26688.76 | 471669.89 | 444981.13 | 1667% | 24410.12 | 13356.56 | -11053.56 | -45.28% | 809.84 | 831.05 | 21.21 | 2.619% | 1468.8 | 1557 | 88.2 | 6.005% | 0 | 7046.28 | 7046.28 |  | 138 | 86 | -52 | -37.68% | 2022-09-22 01:00
Brampton | 2021 | 641824 | CUSTOMER INITIATED RELOCATION - 225 BALMORAL DR | 95 | COMPLETE | Under 10% |  |  | Lacombe, Joel | No | Robinson, David | Richard Cuddy | 35636.41 | 38118.26 | 2481.85 | 6.964% | 6483.97 | 10151.17 | 3667.2 | 56.56% | 1068.12 | 1255.31 | 187.19 | 17.53% | 0 | 64 | 64 |  | 28084.32 | 26647.78 | -1436.54 | -5.115% | 48 | 24 | -24 | -50% | 2021-11-18 01:00
Brampton | 2022 | 641826 | 0 ACE DR | 95 | ANALYZE |  |  |  | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 141256.49 | 135041.39 | -6215.1 | -4.4% | 40363.22 | 18383.48 | -21979.74 | -54.45% | 68266.17 | 87532.77 | 19266.6 | 28.22% | 7128 | 5091.25 | -2036.75 | -28.57% | 25499.1 | 24033.89 | -1465.21 | -5.746% | 233.2 | 174.5 | -58.7 | -25.17% | 2022-12-02 01:00
Brampton | 2022 | 641857 | ROAD AUTHORITY RELOCATION - CHINGUACOUSY RD - MAYFIELD RD TO WANLESS DR - PHASE2 | 99 | COMPLETE | Labour est. under | Cont Est Over | Material Under Estimated | Lacombe, Joel | No | Robinson, David | AW Group | 366634.51 | 466110.9 | 99476.39 | 27.13% | 31718.95 | 157224.92 | 125505.97 | 395.7% | 99046.56 | 113288.28 | 14241.72 | 14.38% | 0 | 3350 | 3350 |  | 235869 | 192247.7 | -43621.3 | -18.49% | 140 | 160 | 20 | 14.29% | 2022-02-18 01:00
Brampton | 2022 | 641927 | 2022 SWITCHGEAR RENEWAL - SITE# 555 - McLaughlin Rd & Steeles Ave. W | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | No | D'Ermes, Michael | Zenon Lipinski | 225239.36 | 235277.54 | 10038.18 | 4.457% | 37422.64 | 43121.38 | 5698.74 | 15.23% | 169575.49 | 174430.09 | 4854.6 | 2.863% | 6688 | 7299.82 | 611.82 | 9.148% | 11553.23 | 10426.25 | -1126.98 | -9.755% | 258 | 296 | 38 | 14.73% | 2022-12-15 01:00
Brampton | 2022 | 641984 | 2022 TX RENEWAL-GRID B3- 1TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 15516.28 | 13089.69 | -2426.59 | -15.64% | 8257.92 | 4979.93 | -3277.99 | -39.7% | 6522.36 | 7235.77 | 713.41 | 10.94% | 736 | 873.99 | 137.99 | 18.75% | 0 | 0 | 0 |  | 17 | 16 | -1 | -5.882% | 2022-11-30 01:00
Brampton | 2022 | 641991 | 2022 TX RENEWAL-GRID F3- 2TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 24708.01 | 24940.39 | 232.38 | 0.9405% | 9457.8 | 8551.33 | -906.47 | -9.584% | 13810.21 | 14638.82 | 828.61 | 6% | 1440 | 1750.24 | 310.24 | 21.54% | 0 | 0 | 0 |  | 32 | 52 | 20 | 62.5% | 2022-09-30 01:00
Brampton | 2022 | 642001 | 2022 SWITCH RENEWAL - SW44-415 TORBRAM RD | 99 | COMPLETE | Vehicle Under Estimated | Labour est. under | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Zenon Lipinski | 113346.41 | 129029.36 | 15682.95 | 13.84% | 30807.8 | 38869.54 | 8061.74 | 26.17% | 71465.61 | 72243.24 | 777.63 | 1.088% | 10392 | 16538.21 | 6146.21 | 59.14% | 681 | 1378.37 | 697.37 | 102.4% | 242 | 384.75 | 142.75 | 58.99% | 2022-09-08 01:00
Brampton | 2022 | 642002 | 2022 SWITCH RENEWAL - SW44-403 HEART LAKE RD S | 99 | COMPLETE | Material Over Estimated | Labour est. over | Vehicle Over Estimated- | Agostini, Robert | Yes | Casey, Ryan | Zenon Lipinski | 154054.56 | 110505.14 | -43549.42 | -28.27% | 40577.97 | 27127.74 | -13450.23 | -33.15% | 95027.59 | 75186.11 | -19841.48 | -20.88% | 13368 | 8191.29 | -5176.71 | -38.72% | 5081 | 0 | -5081 | -100% | 328 | 262 | -66 | -20.12% | 2022-09-22 01:00
Brampton | 2022 | 642003 | 2022 SWITCH RENEWAL - SW44-378 PEEL RGNL RD 4 | 99 | COMPLETE | Labour est. over | BOM not accurate | Vehicle Over Estimated- | Agostini, Robert | Yes | Miller, Michael | Zenon Lipinski | 183743.41 | 114863.36 | -68880.05 | -37.49% | 62945.16 | 26698.39 | -36246.77 | -57.58% | 98005.25 | 78429.81 | -19575.44 | -19.97% | 22112 | 9735.16 | -12376.84 | -55.97% | 681 | 0 | -681 | -100% | 512 | 258 | -254 | -49.61% | 2022-06-02 01:00
Brampton | 2022 | 642006 | 2022 SWITCHGEAR RENEWAL-SITE 516 SANDALWOOD PKWY (FORMERLY SITE 214) | 99 | COMPLETE | N/A | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Zenon Lipinski | 114804.79 | 119498.92 | 4694.13 | 4.089% | 21859.67 | 24966.73 | 3107.06 | 14.21% | 85404.62 | 87526.71 | 2122.09 | 2.485% | 7200 | 7005.48 | -194.52 | -2.702% | 340.5 | 0 | -340.5 | -100% | 216 | 270 | 54 | 25% | 2022-10-21 01:00
Brampton | 2022 | 642062 | 685 REMEMBRANCE RD / BRAM / NS00094732 / 3PH PAD | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | N/A | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 148610.87 | 127600.42 | -21010.45 | -14.14% | 39820.83 | 20751.75 | -19069.08 | -47.89% | 49082.04 | 46818.13 | -2263.91 | -4.613% | 6830 | 4339 | -2491 | -36.47% | 52878 | 55691.54 | 2813.54 | 5.321% | 255 | 251 | -4 | -1.569% | 2022-01-06 01:00
Brampton | 2021 | 642097 | 1 BLAIR DR/ BRAM/UP00118596/ 750 KVA TX | 99 | COMPLETE | Under 10% |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 64927.98 | 70359.91 | 5431.93 | 8.366% | 33747.65 | 23215.78 | -10531.87 | -31.21% | 40659.33 | 35045.04 | -5614.29 | -13.81% | 6300 | 5760 | -540 | -8.571% | 6571 | 6339.09 | -231.91 | -3.529% | 232 | 232 | 0 | 0% | 2021-12-08 01:00
Brampton | 2021 | 642110 | 2021 POLE RENEWAL GRID J4 PH2- 2 POLES | 99 | COMPLETE | Cont Est Over | BOM not accurate | N/A | Agostini, Robert | Yes | Miller, Michael | Reaburn, Jeff | 23262.77 | 19803.27 | -3459.5 | -14.87% | 4643.07 | 5214.48 | 571.41 | 12.31% | 4793.7 | 3817.62 | -976.08 | -20.36% | 0 | 0 | 0 |  | 13826 | 10771.17 | -3054.83 | -22.09% | 16 | 9 | -7 | -43.75% | 2021-12-23 01:00
Brampton | 2022 | 642115 | 2022 D/A SWITCHGEAR INSTALLATION-SITE 339 -WILLIAMS PKY W WEST OF ELBERN MARKELL | 99 | COMPLETE | Material Over Estimated | Vehicle Over Estimated- | Cont Est Under | Agostini, Robert | Yes | Miller, Michael | Zenon Lipinski | 236364.36 | 227296.42 | -9067.94 | -3.836% | 40052.07 | 40201.97 | 149.9 | 0.3743% | 174816.29 | 168230.58 | -6585.71 | -3.767% | 10796 | 6431.5 | -4364.5 | -40.43% | 10700 | 12432.37 | 1732.37 | 16.19% | 316 | 322 | 6 | 1.899% | 2022-08-18 01:00
Brampton | 2022 | 642118 | 2022 DA- HWY 50 N/O COTTRELLE | 99 | COMPLETE | BOM not accurate | Vehicle Under Estimated | Labour est. under | Agostini, Robert | Yes | Casey, Ryan | Justin Gregoris | 96507.22 | 127045.15 | 30537.93 | 31.64% | 33988.69 | 43116.35 | 9127.66 | 26.85% | 52622.53 | 65008.24 | 12385.71 | 23.54% | 9896 | 16211.74 | 6315.74 | 63.82% | 0 | 2708.82 | 2708.82 |  | 256 | 470.5 | 214.5 | 83.79% | 2022-04-06
Brampton | 2022 | 642119 | 2022 DA- SW 44-436 AIRPORT/NEVETS | 99 | COMPLETE | Cont Est Over | Labour est. over | Vehicle Over Estimated- | Agostini, Robert | Yes | Casey, Ryan | AW Group | 132151.2 | 112357.01 | -19794.19 | -14.98% | 3533.26 | 10864.71 | 7331.45 | 207.5% | 83819.94 | 87341.68 | 3521.74 | 4.202% | 0 | 1417.21 | 1417.21 |  | 44798 | 12733.41 | -32064.59 | -71.58% | 240 | 38 | -202 | -84.17% | 2022-10-18 01:00
Brampton | 2022 | 642133 | 151104 2022 DISTRIBUTION AUTOMATION - SWGR 340 | 99 | COMPLETE | Cont Est Over | Vehicle Over Estimated- | Material Over Estimated | Agostini, Robert | No | D'Ermes, Michael | Zenon Lipinski | 248628.19 | 238186.27 | -10441.92 | -4.2% | 44803.11 | 46488.14 | 1685.03 | 3.761% | 159570.08 | 159004.18 | -565.9 | -0.3546% | 13700 | 9952.81 | -3747.19 | -27.35% | 30555 | 22741.14 | -7813.86 | -25.57% | 316 | 358 | 42 | 13.29% | 2022-08-02 01:00
Brampton | 2022 | 642134 | NEAMSBY STAGE 2 - SUBD RES EDS | 99 | COMPLETE | Labour est. over | Material Under Estimated | N/A | Gamboa, Henry | No | Erzek, Ryan | Zenon Lipinski | 76391.9 | 978465.97 | 902074.07 | 1181% | 54278.08 | 37159.58 | -17118.5 | -31.54% | 1838.82 | 11465.64 | 9626.82 | 523.5% | 9125 | 9825.75 | 700.75 | 7.679% | 11150 | 11150 | 0 | 0% | 231 | 351.75 | 120.75 | 52.27% | 2022-08-17 01:00
Brampton | 2022 | 642135 | WALLSEND STAGE 2 - SUBD RES EDS | 99 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Gamboa, Henry | No | Erzek, Ryan | Zenon Lipinski | 54022.14 | 299149.62 | 245127.48 | 453.8% | 37853.15 | 18642.23 | -19210.92 | -50.75% | 7171.59 | 5863.39 | -1308.2 | -18.24% | 3897.4 | 2735 | -1162.4 | -29.83% | 5100 | 5925 | 825 | 16.18% | 239 | 122.5 | -116.5 | -48.74% | 2022-08-17 01:00
Brampton | 2021 | 642199 | 73 PARKHURST SQ / BRAM / SR00151185 / 3PH VAULT | 99 | COMPLETE | Estimate incorrect | Cont Est Over | Labour est. over | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 28406.33 | 23624.21 | -4782.12 | -16.83% | 14567.57 | 9219.49 | -5348.08 | -36.71% | 1366.76 | 2515.39 | 1148.63 | 84.04% | 3240 | 1831 | -1409 | -43.49% | 9232 | 10058.33 | 826.33 | 8.951% | 101 | 101.5 | 0.5 | 0.495% | 2021-10-06 01:00
Brampton | 2022 | 642226 | 2022-44KV D/A SWITCH INSTALLATION(44-325) - ITD2022-19 | 99 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Agostini, Robert | Yes | Miller, Michael | AW Group | 162263.07 | 147925 | -14338.07 | -8.836% | 5272.64 | 17154.04 | 11881.4 | 225.3% | 102659.64 | 81576.31 | -21083.33 | -20.54% | 0 | 676.64 | 676.64 |  | 54330.79 | 48518.01 | -5812.78 | -10.7% | 536 | 45 | -491 | -91.6% | 2022-10-07 01:00
Brampton | 2021 | 642248 | 2021 EMERGING PROJECT - SECONDARY SERVICE RENEWAL -10 BELMONT DR | 99 | COMPLETE | Labour est. over | N/A | N/A | Agostini, Robert | Yes | Casey, Ryan | Reaburn, Jeff | 40232.48 | 32853.68 | -7378.8 | -18.34% | 14774.18 | 12426.39 | -2347.79 | -15.89% | 1169.3 | 1325.06 | 155.76 | 13.32% | 9000 | 2255.74 | -6744.26 | -74.94% | 15289 | 16846.49 | 1557.49 | 10.19% | 206 | 101 | -105 | -50.97% | 2021-12-06 01:00
Brampton | 2022 | 642326 | 2022 DA SW20-1485 - HWY 407 HONI ROW E/O HURONTARIO ST | 98 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Over Estimated- | Agostini, Robert | Yes | D'Ermes, Michael | AW Group | 96342.31 | 108852.15 | 12509.84 | 12.98% | 2003.67 | 23374.13 | 21370.46 | 1067% | 58969.64 | 58279.33 | -690.31 | -1.171% | -2664 | 2593.79 | 5257.79 | -197.4% | 38033 | 24604.9 | -13428.1 | -35.31% | 336 | 119.5 | -216.5 | -64.43% | 2022-07-08 01:00
Brampton | 2022 | 642342 | 2022 DA- SW 20-1239 | 99 | COMPLETE | Vehicle Over Estimated | Labour est. over | Material Under Estimated | Agostini, Robert | Yes | Casey, Ryan | AW Group | 130873.84 | 151297.76 | 20423.92 | 15.61% | 3097.2 | 19809.64 | 16712.44 | 539.6% | 53504.49 | 63403.72 | 9899.23 | 18.5% | 0 | 986.77 | 986.77 |  | 74272.15 | 67097.63 | -7174.52 | -9.66% | 396 | 63 | -333 | -84.09% | 2022-11-07 01:00
Brampton | 2022 | 642348 | 2022-44KV LIS SWITCH INSTALLATION(44-434) | 99 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Agostini, Robert | Yes | Miller, Michael | Justin Gregoris | 155614.41 | 114573.89 | -41040.52 | -26.37% | 5272.64 | 15487.3 | 10214.66 | 193.7% | 95048.07 | 59448.28 | -35599.79 | -37.45% | 0 | 817.61 | 817.61 |  | 55293.7 | 38820.7 | -16473 | -29.79% | 528 | 66.5 | -461.5 | -87.41% | 2022-10-10 01:00
Brampton | 2022 | 642351 | 2022 DA SW INSTALLATION - 20-1756 (ITD 2022-19) | 99 | COMPLETE | Under 10% | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Justin Gregoris | 138839.74 | 127155.77 | -11683.97 | -8.415% | 54033.82 | 42143.18 | -11890.64 | -22.01% | 66044.92 | 65490.09 | -554.83 | -0.8401% | 18080 | 17322.5 | -757.5 | -4.19% | 681 | 2200 | 1519 | 223.1% | 434 | 487 | 53 | 12.21% | 2022-04-06
Brampton | 2022 | 642354 | 2022 DA SW20-1184 - INTERMODAL DR E/O DEVON RD | 99 | COMPLETE | Labour est. over | Material Under Estimated | Vehicle Over Estimated- | Agostini, Robert | Yes | D'Ermes, Michael | AW Group | 132848.94 | 176132.26 | 43283.32 | 32.58% | 5506.78 | 21571.45 | 16064.67 | 291.7% | 60949.73 | 92278.33 | 31328.6 | 51.4% | 0 | 676.64 | 676.64 |  | 66392.43 | 61605.84 | -4786.59 | -7.21% | 456 | 56.5 | -399.5 | -87.61% | 2022-10-28 01:00
Brampton | 2022 | 642415 | THE PAVILION PH 3 - SUBD CAP PROJ | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Armstrong, Colby | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6 | 6 |  | 2021-09-29 01:00
Brampton | 2022 | 642451 | 2022 POLE RENEWAL GRID H4 - 17 POLES (HALE RD) | 99 | COMPLETE | Cont Est Under | Labour est. over | Vehicle Over Estimated- | Agostini, Robert | Yes | Miller, Michael | Black and McDonald Group | 522588.4 | 659516.16 | 136927.76 | 26.2% | 238801.8 | 93511.76 | -145290.04 | -60.84% | 155772.6 | 213432.84 | 57660.24 | 37.02% | 86964 | 8426.43 | -78537.57 | -90.31% | 41050 | 344145.13 | 303095.13 | 738.4% | 1584 | 323 | -1261 | -79.61% | 2022-12-14 01:00
Brampton | 2022 | 642454 | 2022 MINI-POLE REBUILD - GLIDDEN RD - 28 Poles | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | K-Line Construction | 726729.82 | 804907.45 | 78177.63 | 10.76% | 359621.01 | 120038.87 | -239582.14 | -66.62% | 154112.2 | 236413.23 | 82301.03 | 53.4% | 127024 | 13320.23 | -113703.77 | -89.51% | 85972.61 | 435135.12 | 349162.51 | 406.1% | 2864 | 413.5 | -2450.5 | -85.56% | 2022-12-18 01:00
Brampton | 2022 | 642529 | 2022 TX RENEWAL-GRID D3 - 5 TX | 99 | COMPLETE | Labour est. over | Material Under Estimated | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 53107.69 | 50603.55 | -2504.14 | -4.715% | 15424.3 | 10801.5 | -4622.8 | -29.97% | 34067.39 | 36204.62 | 2137.23 | 6.274% | 3616 | 3193.74 | -422.26 | -11.68% | 0 | 403.69 | 403.69 |  | 81 | 93 | 12 | 14.81% | 2022-11-25 01:00
Brampton | 2022 | 642530 | 2022 TX RENEWAL-GRID F1 - 4TX | 99 | COMPLETE | Material Over Estimated | Labour est. over | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 43782.59 | 33485.88 | -10296.71 | -23.52% | 13632.69 | 8795.07 | -4837.62 | -35.49% | 27253.9 | 21898.54 | -5355.36 | -19.65% | 2896 | 2792.27 | -103.73 | -3.582% | 0 | 0 | 0 |  | 65 | 89 | 24 | 36.92% | 2022-10-13 01:00
Brampton | 2022 | 642532 | 2022 TX RENEWAL-GRID G2 - 3TX | 99 | COMPLETE | Labour est. over | Vehicle Under Estimated | N/A | Agostini, Robert | Yes | Casey, Ryan | Richard Cuddy | 28490.59 | 30522.8 | 2032.21 | 7.133% | 10372.44 | 9225.94 | -1146.5 | -11.05% | 15942.15 | 16876.14 | 933.99 | 5.859% | 2176 | 4420.72 | 2244.72 | 103.2% | 0 | 0 | 0 |  | 49 | 82 | 33 | 67.35% | 2022-10-28 01:00
Brampton | 2022 | 642542 | 2022 TX RENEWAL - 3PH TX STEELWELL RD | 99 | Upload Completed | BOM not accurate |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Zenon Lipinski | 30958.43 | 27458.87 | -3499.56 | -11.3% | 8297.62 | 7830.06 | -467.56 | -5.635% | 21535.81 | 18744.67 | -2791.14 | -12.96% | 1125 | 884.14 | -240.86 | -21.41% | 0 | 0 | 0 |  | 50 | 48.25 | -1.75 | -3.5% | 2022-10-30 01:00
Brampton | 2022 | 642543 | 2022 TX RENEWAL - 1PH TX CHAPEL ST - 2 TX | 99 | COMPLETE | Material Over Estimated | Labour est. over | Cont Est Under | Agostini, Robert | No | D'Ermes, Michael | Richard Cuddy | 25359.6 | 19861.23 | -5498.37 | -21.68% | 10590.84 | 8280.59 | -2310.25 | -21.81% | 13072.76 | 8836.59 | -4236.17 | -32.4% | 1696 | 1398.39 | -297.61 | -17.55% | 0 | 1345.66 | 1345.66 |  | 32 | 41.5 | 9.5 | 29.69% | 2022-04-14
Brampton | 2022 | 642544 | 2022 TX RENEWAL - 1PH TX GRID D2 - 1 TX | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 11542.57 | 12901.53 | 1358.96 | 11.77% | 5708.03 | 4564.04 | -1143.99 | -20.04% | 5114.54 | 6294.49 | 1179.95 | 23.07% | 720 | 1218 | 498 | 69.17% | 0 | 825 | 825 |  | 16 | 36 | 20 | 125% | 2022-03-15 01:00
Brampton | 2022 | 642545 | 2022 TX RENEWAL - 1PH TX GRID I3 - 5 TX | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 41009.21 | 42039.14 | 1029.93 | 2.511% | 13853.53 | 16076.84 | 2223.31 | 16.05% | 23555.68 | 19522.3 | -4033.38 | -17.12% | 3600 | 6440 | 2840 | 78.89% | 0 | 0 | 0 |  | 80 | 161 | 81 | 101.2% | 2022-04-12
Brampton | 2022 | 642546 | 2022 TX RENEWAL - 1PH TX GRID E3 - 8 TX | 99 | COMPLETE | Cont Est Under | Material Under Estimated | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 64115.99 | 82558.7 | 18442.71 | 28.76% | 22165.64 | 21317.67 | -847.97 | -3.826% | 36190.35 | 44932.04 | 8741.69 | 24.15% | 5760 | 5873.24 | 113.24 | 1.966% | 0 | 10435.75 | 10435.75 |  | 128 | 158 | 30 | 23.44% | 2022-12-20 01:00
Brampton | 2022 | 642547 | 2022 TX RENEWAL - 1PH TX GRID E2 - 1 TX | 99 | COMPLETE | Material Under Estimated | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Richard Cuddy | 8970.71 | 11158.03 | 2187.32 | 24.38% | 3749.81 | 4506.82 | 757.01 | 20.19% | 4500.9 | 5631.74 | 1130.84 | 25.12% | 720 | 1019.47 | 299.47 | 41.59% | 0 | 0 | 0 |  | 16 | 25 | 9 | 56.25% | 2022-08-16 01:00
Brampton | 2022 | 642549 | DOWN GUY AND ANCHORS RELOCATION -BOVAIRD DR WEST OF CREDITVIEW RD | 99 | COMPLETE | Vehicle Under Estimated | Cont Est Under | N/A | Watters, Maxwell | No | Robinson, David | Richard Cuddy | 10931.5 | 18538.02 | 7606.52 | 69.58% | 9761.88 | 10367.31 | 605.43 | 6.202% | 1165.62 | 1868.6 | 702.98 | 60.31% | 0 | 4905 | 4905 |  | 4 | 1397.11 | 1393.11 | 34828% | 80 | 117 | 37 | 46.25% | 2022-01-07 01:00
Brampton | 2022 | 642611 | 2022 TX RENEWAL-GRID I2 - 1 TX (1PH MP) | 99 | COMPLETE | Labour est. over |  |  | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 9777.81 | 8640.4 | -1137.41 | -11.63% | 3749.81 | 3582.41 | -167.4 | -4.464% | 5308 | 4241.99 | -1066.01 | -20.08% | 720 | 816 | 96 | 13.33% | 0 | 0 | 0 |  | 16 | 25 | 9 | 56.25% | 2022-04-14
Brampton | 2022 | 642612 | 2022 TX RENEWAL-GRID H4 - 1 TX(3PH PAD) | 99 | COMPLETE | Under 10% |  |  | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 28003.74 | 30357.49 | 2353.75 | 8.405% | 6575 | 6113.74 | -461.26 | -7.015% | 19307.74 | 22691.75 | 3384.01 | 17.53% | 1440 | 1552 | 112 | 7.778% | 681 | 0 | -681 | -100% | 32 | 33 | 1 | 3.125% | 2022-04-28
Brampton | 2022 | 642619 | 2022 TX RENEWAL-GRID H3 - 4 TXS (1PH MP) | 99 | COMPLETE | Cont Est Under | Labour est. under | Material Over Estimated | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 34249.04 | 56313.82 | 22064.78 | 64.42% | 9516.25 | 23270.35 | 13754.1 | 144.5% | 21852.79 | 20004.68 | -1848.11 | -8.457% | 2880 | 5528.71 | 2648.71 | 91.97% | 0 | 7510.08 | 7510.08 |  | 64 | 215 | 151 | 235.9% | 2022-07-18 01:00
Brampton | 2021 | 642620 | 152278 2022 CABLE REPLACEMENT - GRID G1 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 537718.73 | 467551.75 | -70166.98 | -13.05% | 62847.45 | 79795.05 | 16947.6 | 26.97% | 1111.28 | 919.39 | -191.89 | -17.27% | 5760 | 3667.17 | -2092.83 | -36.33% | 468000 | 383170.14 | -84829.86 | -18.13% | 173 | 179 | 6 | 3.468% | 2021-12-06 01:00
Brampton | 2022 | 642621 | 2022 TX RENEWAL-GRID G3 - 1 TX (1PH MP) | 99 | COMPLETE | N/A | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 9777.81 | 11613 | 1835.19 | 18.77% | 3749.81 | 4795.92 | 1046.11 | 27.9% | 5308 | 5459.29 | 151.29 | 2.85% | 720 | 1357.79 | 637.79 | 88.58% | 0 | 0 | 0 |  | 16 | 37 | 21 | 131.2% | 2022-08-17 01:00
Brampton | 2022 | 642622 | 2022 TX RENEWAL-GRID J3 - 1 TX(3PH PAD) | 99 | COMPLETE | Material Under Estimated | Labour est. over | N/A | Agostini, Robert | Yes | Miller, Michael | Zenon Lipinski | 29947.75 | 40708.67 | 10760.92 | 35.93% | 6575 | 5538.99 | -1036.01 | -15.76% | 21251.75 | 34123.14 | 12871.39 | 60.57% | 1440 | 1046.54 | -393.46 | -27.32% | 681 | 0 | -681 | -100% | 32 | 25.5 | -6.5 | -20.31% | 2022-05-20 01:00
Brampton | 2022 | 642625 | 2022 TX RENEWAL-GRID N3 - 2TXS (1PH MP) | 99 | COMPLETE | Material Under Estimated | Labour est. over | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 17988.98 | 20427.45 | 2438.47 | 13.56% | 5933.04 | 4701.12 | -1231.92 | -20.76% | 10615.94 | 14578.3 | 3962.36 | 37.32% | 1440 | 1148.03 | -291.97 | -20.28% | 0 | 0 | 0 |  | 32 | 22 | -10 | -31.25% | 2022-11-29 01:00
Brampton | 2022 | 642626 | 2022 TX RENEWAL-GRID H3 - 1 TX (3PH PAD) | 99 | COMPLETE | Material Under Estimated | Labour est. under | N/A | Agostini, Robert | Yes | Miller, Michael | Zenon Lipinski | 22177.77 | 41482.71 | 19304.94 | 87.05% | 6575 | 8824.79 | 2249.79 | 34.22% | 13481.77 | 30146.57 | 16664.8 | 123.6% | 1440 | 1578.83 | 138.83 | 9.641% | 681 | 932.52 | 251.52 | 36.93% | 32 | 33 | 1 | 3.125% | 2022-08-26 01:00
Brampton | 2022 | 642648 | 15 BRAMALEA RD / BRAM / NS00143382 / CUSTOMER-OWNED SUBSTATION | 99 | COMPLETE | Material Over Estimated | Vehicle Under Estimated | Labour est. under | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 30292.95 | 23978.13 | -6314.82 | -20.85% | 7665.64 | 10484.63 | 2818.99 | 36.77% | 13875.31 | 2923.02 | -10952.29 | -78.93% | 1272 | 5033 | 3761 | 295.7% | 7480 | 5537.48 | -1942.52 | -25.97% | 50 | 109.5 | 59.5 | 119% | 2022-04-14
Brampton | 2021 | 642718 | 4395 CASTLEMORE RD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-30 01:00
Brampton | 2022 | 642725 | FEEDER EXPANSION -FINANCIAL DRIVE /SOUTH OF LEGENDARY CIR | 95 | COMPLETE | Labour est. under | Cont Est Over | Material Over Estimated | Watters, Maxwell | No | Robinson, David | Zenon Lipinski | 67112.27 | 69333.68 | 2221.41 | 3.31% | 8328.29 | 21043.4 | 12715.11 | 152.7% | 12783.98 | 9397.56 | -3386.42 | -26.49% | 0 | 1378 | 1378 |  | 46000 | 37514.72 | -8485.28 | -18.45% | 160 | 103.5 | -56.5 | -35.31% | 2022-06-30 01:00
Brampton | 2022 | 642757 | 12 HENDERSON AVE / BRAM / NS00154354 / 3PH PAD | 99 | COMPLETE | Material Over Estimated | Labour est. under | Vehicle Under Estimated | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 153311.88 | 125852.67 | -27459.21 | -17.91% | 20322.89 | 25439.54 | 5116.65 | 25.18% | 84550.66 | 46349.83 | -38200.83 | -45.18% | 3347.33 | 4693.5 | 1346.17 | 40.22% | 45091 | 49369.8 | 4278.8 | 9.489% | 132.99 | 213.5 | 80.51 | 60.54% | 2022-05-08
Brampton | 2021 | 642781 | TRANSFORMER RELOCATION 6 GERMAIN CIRCLE LOT 217 | 99 | COMPLETE | Under 10% | N/A | N/A | Pelleja, Emily | No | Robinson, David | Richard Cuddy | 17907.55 | 16370.92 | -1536.63 | -8.581% | 3501.91 | 5069.27 | 1567.36 | 44.76% | 244.46 | 418.75 | 174.29 | 71.3% | 0 | 837 | 837 |  | 14161.18 | 10045.9 | -4115.28 | -29.06% | 18 | 32 | 14 | 77.78% | 2021-12-08 01:00
Brampton | 2022 | 642948 | 70 COACHWORKS CRES | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Under | Rao, Gaurav | No | Bojanic, Dusan | Simon Evason | 90753.11 | 68599.51 | -22153.6 | -24.41% | 32410.26 | 18273.26 | -14137 | -43.62% | 32457.65 | 22760.98 | -9696.67 | -29.87% | 5596.8 | 4593 | -1003.8 | -17.94% | 20288.4 | 22972.27 | 2683.87 | 13.23% | 162.8 | 199 | 36.2 | 22.24% | 2022-05-18 01:00
Brampton | 2022 | 643027 | 2022 POLE RENEWAL GRID L4 - 2 POLES (VARIOUS LOCATIONS) | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Over Estimated | Agostini, Robert | Yes | Miller, Michael | K-Line Construction | 68859.68 | 27438.2 | -41421.48 | -60.15% | 34146.03 | 8634.27 | -25511.76 | -74.71% | 11817.65 | 10190.01 | -1627.64 | -13.77% | 12720 | 0 | -12720 | -100% | 10176 | 8613.92 | -1562.08 | -15.35% | 240 | 4.5 | -235.5 | -98.12% | 2022-09-16 01:00
Brampton | 2022 | 643028 | 2022 POLE RENEWAL GRID L3 - 1 POLE (NORTH PARK DR) | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Over Estimated | Agostini, Robert | Yes | Miller, Michael | K-Line Construction | 27105.26 | 14351.4 | -12753.86 | -47.05% | 13473.42 | 5874.96 | -7598.46 | -56.4% | 5691.84 | 3353.72 | -2338.12 | -41.08% | 4240 | 0 | -4240 | -100% | 3700 | 5122.72 | 1422.72 | 38.45% | 96 | 5.5 | -90.5 | -94.27% | 2022-09-15 01:00
Brampton | 2022 | 643030 | 2022 POLE RENEWAL GRID J5 - 3 POLES (VARIOUS LOCATIONS) | 99 | COMPLETE | Cont Est Under | Labour est. over | Vehicle Over Estimated- | Agostini, Robert | Yes | Miller, Michael | K-Line Construction | 136771.87 | 126924.37 | -9847.5 | -7.2% | 75638.85 | 23044.93 | -52593.92 | -69.53% | 18153.02 | 16961.11 | -1191.91 | -6.566% | 29680 | 0 | -29680 | -100% | 13300 | 86918.33 | 73618.33 | 553.5% | 590 | 9 | -581 | -98.47% | 2022-09-30 01:00
Brampton | 2022 | 643077 | 2022 POLE RENEWAL -GRID A3- 1 POLE | 99 | COMPLETE | Vehicle Over Estimated | Labour est. over | N/A | Agostini, Robert | Yes | Casey, Ryan | K-Line Construction | 21240.29 | 10842.49 | -10397.8 | -48.95% | 9754.02 | 4871.25 | -4882.77 | -50.06% | 5958.27 | 5971.24 | 12.97 | 0.2177% | 5528 | 0 | -5528 | -100% | 0 | 0 | 0 |  | 112 | 14.5 | -97.5 | -87.05% | 2022-10-07 01:00
Brampton | 2022 | 643078 | 2022 POLE RENEWAL -GRID A2- 2 POLES HERITAGE | 99 | COMPLETE | Vac truck | Labour est. under |  | Agostini, Robert | Yes | Casey, Ryan | Justin Gregoris | 20406.94 | 30185.64 | 9778.7 | 47.92% | 10970.3 | 17056.96 | 6086.66 | 55.48% | 3844.64 | 5854.79 | 2010.15 | 52.28% | 5592 | 4565.07 | -1026.93 | -18.36% | 0 | 2708.82 | 2708.82 |  | 132 | 192 | 60 | 45.45% | 2022-03-11 01:00
Brampton | 2022 | 643079 | 2022 POLE RENEWAL -GRID C4- 1 POLE MISSISSAUGA | 99 | COMPLETE | Vac truck | Labour est. under |  | Agostini, Robert | Yes | Casey, Ryan | Justin Gregoris | 10633.28 | 18304.52 | 7671.24 | 72.14% | 6136.89 | 9982.99 | 3846.1 | 62.67% | 1604.39 | 1608.32 | 3.93 | 0.245% | 2892 | 3271.56 | 379.56 | 13.12% | 0 | 3441.65 | 3441.65 |  | 72 | 80 | 8 | 11.11% | 2022-06-20 01:00
Brampton | 2022 | 643080 | 2022 POLE RENEWAL -GRID F3- 4 POLES | 99 | COMPLETE | Cont Est Under | Labour est. over | Vehicle Over Estimated- | Agostini, Robert | Yes | Casey, Ryan | K-Line Construction | 56068.97 | 92069.39 | 36000.42 | 64.21% | 24582.14 | 12204.1 | -12378.04 | -50.35% | 15924.83 | 21778.12 | 5853.29 | 36.76% | 12984 | 0 | -12984 | -100% | 2578 | 58087.17 | 55509.17 | 2153% | 304 | 7 | -297 | -97.7% | 2022-09-23 01:00
Brampton | 2022 | 643081 | 2022 POLE RENEWAL -GRID F2- 1 POLES | 99 | COMPLETE | BOM not accurate |  |  | Agostini, Robert | Yes | Casey, Ryan | Justin Gregoris | 14942.15 | 20723.29 | 5781.14 | 38.69% | 7928.72 | 8509.84 | 581.12 | 7.329% | 2528.93 | 8830.25 | 6301.32 | 249.2% | 3840 | 3383.2 | -456.8 | -11.9% | 644.5 | 0 | -644.5 | -100% | 95 | 98.5 | 3.5 | 3.684% | 2022-03-14 01:00
Brampton | 2022 | 643097 | STEELES AVE W AND MCLAUGHLIN RD STRUT GUY | 99 | COMPLETE | Labour est. over | BOM not accurate | Vehicle Under Estimated | Pelleja, Emily | No | Mckeen, Brant | Justin Gregoris | 9259.5 | 3001 | -6258.5 | -67.59% | 8579.82 | 2669.1 | -5910.72 | -68.89% | 655.98 | 148.9 | -507.08 | -77.3% | 19.7 | 183 | 163.3 | 828.9% | 4 | 0 | -4 | -100% | 64.6 | 20.5 | -44.1 | -68.27% | 2022-01-31 01:00
Brampton | 2022 | 643099 | 2022 POLE RENEWAL GRID D5 - 1 POLE | 99 | COMPLETE | Labour est. over | Vehicle Not Charged | Cont Est Under | Agostini, Robert | Yes | D'Ermes, Michael | K-Line Construction | 26037.58 | 13946.54 | -12091.04 | -46.44% | 17426.54 | 6061.41 | -11365.13 | -65.22% | 1252.04 | 1191.03 | -61.01 | -4.873% | 4259 | 0 | -4259 | -100% | 3100 | 6694.1 | 3594.1 | 115.9% | 81 | 5.5 | -75.5 | -93.21% | 2022-09-23 01:00
Brampton | 2022 | 643102 | 2022 POLE RENEWAL GRID F5 - 1 POLE | 99 | COMPLETE | Labour est. over | Vehicle Not Charged |  | Agostini, Robert | Yes | D'Ermes, Michael | K-Line Construction | 34626.36 | 11325.91 | -23300.45 | -67.29% | 21261.4 | 4750.48 | -16510.92 | -77.66% | 3885.96 | 4385.36 | 499.4 | 12.85% | 6379 | 0 | -6379 | -100% | 3100 | 2190.07 | -909.93 | -29.35% | 121 | 4 | -117 | -96.69% | 2022-10-07 01:00
Brampton | 2022 | 643103 | 2022 POLE RENEWAL GRID G1 - 1 POLE | 99 | COMPLETE | Labour est. over | Vehicle Not Charged |  | Agostini, Robert | Yes | D'Ermes, Michael | K-Line Construction | 48764.39 | 31325.66 | -17438.73 | -35.76% | 22616.65 | 7286.16 | -15330.49 | -67.78% | 9668.74 | 10521.36 | 852.62 | 8.818% | 6379 | 0 | -6379 | -100% | 10100 | 13518.14 | 3418.14 | 33.84% | 121 | 2.5 | -118.5 | -97.93% | 2022-10-07 01:00
Brampton | 2022 | 643113 | 2022 POLE RENEWAL -GRID H4- 1 POLES | 99 | COMPLETE | Cont Est Under | Labour est. over | Vehicle Over Estimated- | Agostini, Robert | Yes | Casey, Ryan | K-Line Construction | 20721.9 | 23365.34 | 2643.44 | 12.76% | 11276.61 | 4177.35 | -7099.26 | -62.96% | 2800.29 | 4450.38 | 1650.09 | 58.93% | 6645 | 0 | -6645 | -100% | 0 | 14737.61 | 14737.61 |  | 135 | 2.5 | -132.5 | -98.15% | 2022-09-23 01:00
Brampton | 2022 | 643128 | 100 WHYBANK DR / BRAM / NS00142521 / 3PH PAD | 95 | COMPLETE | Cont Est Over | Labour est. over | Material Over Estimated | Rao, Gaurav | No | Wigley, Graham | Simon Evason | 138811.47 | 109848.01 | -28963.46 | -20.87% | 26598.59 | 19443.86 | -7154.73 | -26.9% | 49483.08 | 42205.08 | -7278 | -14.71% | 2786.8 | 3280 | 493.2 | 17.7% | 59943 | 44919.07 | -15023.93 | -25.06% | 158 | 141.5 | -16.5 | -10.44% | 2022-10-13 01:00
Brampton | 2022 | 643130 | 398 RAILSIDE DR / BRAM / NS00142639 / 3PH PAD | 95 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Cont Est Over | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 105185.83 | 72949.14 | -32236.69 | -30.65% | 29375.32 | 9988.1 | -19387.22 | -66% | 48310.51 | 45992.33 | -2318.18 | -4.799% | 8480 | 2681.5 | -5798.5 | -68.38% | 19020 | 14287.21 | -4732.79 | -24.88% | 210 | 102 | -108 | -51.43% | 2022-09-21 01:00
Brampton | 2022 | 643135 | 425 RAILSIDE DR FEEDER EXTENSION | 95 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Watters, Maxwell | No | Mckeen, Brant | Reaburn, Jeff | 54453.56 | 38213.7 | -16239.86 | -29.82% | 26668.36 | 19648.57 | -7019.79 | -26.32% | 10744 | 7604.38 | -3139.62 | -29.22% | 6177.2 | 7163 | 985.8 | 15.96% | 10864 | 3797.75 | -7066.25 | -65.04% | 160 | 205.5 | 45.5 | 28.44% | 2022-08-29 01:00
Brampton | 2021 | 643189 | 25 FREDERICK ST SECONDARY SERVICE RELOCATION | 99 | COMPLETE | Cont Est Over | Labour est. over |  | Pelleja, Emily | No | Mckeen, Brant | Justin Gregoris | 6490.82 | 1347.96 | -5142.86 | -79.23% | 2636.21 | 1101.02 | -1535.19 | -58.23% | 354.61 | 94.44 | -260.17 | -73.37% | 0 | 152.5 | 152.5 |  | 3500 | 0 | -3500 | -100% | 32 | 8.5 | -23.5 | -73.44% | 2021-11-30 01:00
Brampton | 2022 | 643190 | 277 VODDEN ST SWITCHGEAR RELOCATION | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Mckeen, Brant | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-01 01:00
Brampton | 2022 | 643228 | 11619 HURONTARIO ST SIDEWALK STRUT | 99 | COMPLETE | Under 10% |  |  | Pelleja, Emily | No | Mckeen, Brant | Reaburn, Jeff | 9944.83 | 5188.97 | -4755.86 | -47.82% | 6928.06 | 3969.86 | -2958.2 | -42.7% | 1103.77 | 352.86 | -750.91 | -68.03% | 0 | 0 | 0 |  | 1913 | 866.25 | -1046.75 | -54.72% | 0 | 24.5 | 24.5 |  | 2022-09-16 01:00
Brampton | 2022 | 643260 | 95 WALKER DR POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Mckeen, Brant | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-04-06
Brampton | 2022 | 643296 | 7500 FINANCIAL DR / BRAM / NS00157470 / 1PH PAD (TEMPORARY) | 99 | COMPLETE | Labour est. under | Cont Est Over | Material Under Estimated | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 46824.34 | 52749.74 | 5925.4 | 12.65% | 6378.86 | 14240.37 | 7861.51 | 123.2% | 5055.48 | 6273.27 | 1217.79 | 24.09% | 2700 | 3216 | 516 | 19.11% | 32690 | 29020.1 | -3669.9 | -11.23% | 100 | 132.5 | 32.5 | 32.5% | 2022-03-03 01:00
Brampton | 2022 | 643495 | 8 ATLAS CRT / BRAM / UP00159523 / CUSTOMER OWNED SUBSTATION | 95 | COMPLETE | Material Over Estimated | N/A | N/A | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 19982.21 | 14742.02 | -5240.19 | -26.22% | 7557.92 | 7066.18 | -491.74 | -6.506% | 7909.29 | 3136.5 | -4772.79 | -60.34% | 2025 | 1790.75 | -234.25 | -11.57% | 2490 | 2748.59 | 258.59 | 10.39% | 60 | 65 | 5 | 8.333% | 2022-12-03 01:00
Brampton | 2022 | 643504 | 2022 SWITCHGEAR REPLACEMENT SITE 207 (GRID K2) - SANDALWOOD PKY E | 99 | COMPLETE | Under 10% | N/A | N/A | Agostini, Robert | Yes | Miller, Michael | Richard Cuddy | 115345.48 | 105587.34 | -9758.14 | -8.46% | 21859.67 | 17580.9 | -4278.77 | -19.57% | 85945.31 | 83706.44 | -2238.87 | -2.605% | 7200 | 4300 | -2900 | -40.28% | 340.5 | 0 | -340.5 | -100% | 216 | 183 | -33 | -15.28% | 2022-04-11
Brampton | 2019 | R468 | 2074/2084 Steeles Ave. E. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-19 01:00
Brampton | 2019 | T372 | 9659 Winston Churchill Blvd | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A |  | No | Cavanaugh, Danny | Simon Evason | 16750 | 10346.27 | -6403.73 | -38.23% | 15000 | 7719.52 | -7280.48 | -48.54% | 1150 | 871.25 | -278.75 | -24.24% | 301 | 1211.5 | 910.5 | 302.5% | 299 | 544 | 245 | 81.94% | 80 | 79.5 | -0.5 | -0.625% | 2019-01-19 01:00
Brampton | 2019 | T538 | CREDITVIEW RD & WANLESS DR | 99 | CANCELLED | N/A |  |  |  | No | Armstrong, Colby | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-17 01:00
Brampton | 2019 | T543 | 5203 OLD CASTLEMORE RD | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-17 01:00
Brampton | 2019 | T883 | 25 PEEL CENTRE DR | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-17 01:00
Brampton | 2021 | 643516 | 52 DENISON AVE PRIMARY CIRCUIT ISOLATION | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Mckeen, Brant | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-02
Brampton | 2022 | 643585 | 2022 EMERGING PROJECT - UG SECONDARY SERVICE RELOCATE | 99 | COMPLETE | Estimate incorrect | Cont Est Under |  | Agostini, Robert | No | Casey, Ryan | Zenon Lipinski | 27790.14 | 35180.39 | 7390.25 | 26.59% | 10073.01 | 10444.04 | 371.03 | 3.683% | 1395.13 | 1715.73 | 320.6 | 22.98% | 580 | 624 | 44 | 7.586% | 15742 | 22396.62 | 6654.62 | 42.27% | 36 | 42 | 6 | 16.67% | 2022-04-22
Brampton | 2022 | 643608 | EDGEMONT DRIVE - KENNEDY RD TIE FOR PHASE 10 | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Cont Est Over | Agostini, Robert | No | Casey, Ryan | Reaburn, Jeff | 28425.8 | 10369.04 | -18056.76 | -63.52% | 15360.34 | 2829.04 | -12531.3 | -81.58% | 4485.46 | 6155 | 1669.54 | 37.22% | 4692 | 0 | -4692 | -100% | 3888 | 1385 | -2503 | -64.38% | 0 | 8 | 8 |  | 2022-11-08 01:00
Brampton | 2022 | 643816 | RAISE NEUTRAL AT 7850 HERITAGE RD | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Mckeen, Brant | Dre Danieli | 10000 | 1137.41 | -8862.59 | -88.63% | 0 | 1137.41 | 1137.41 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10000 | 0 | -10000 | -100% | 0 | 17.5 | 17.5 |  | 2022-02-16 01:00
Brampton | 2022 | 644788 | 2022 EMERGING PROJECT - STORM DRAIN REPLACEMENT 136M52FEEDER CABLE RELOCATION | 99 | COMPLETE | Cont Est Over | Labour est. over | Material Over Estimated | Agostini, Robert | No | Casey, Ryan | Zenon Lipinski | 316330.97 | 306902.19 | -9428.78 | -2.981% | 44877.41 | 48919.07 | 4041.66 | 9.006% | 4997.76 | 0 | -4997.76 | -100% | 1702.8 | 1795.35 | 92.55 | 5.435% | 264753 | 256187.77 | -8565.23 | -3.235% | 70.32 | 80 | 9.68 | 13.77% | 2022-12-22 01:00
Brampton | 2022 | 645026 | LAGERFELD TO BOVAIRD DR W / BRAM / NS00202707 / 1PH PAD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Tan, Seefon | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-14 01:00
Brampton | 2022 | 644260 | RIVERSTONE SUBDIVISION - SUBD RES EDS | 98 | COMPLETE | Labour est. over | Cont Est Over | N/A | Gamboa, Henry | No | Armstrong, Colby | Zenon Lipinski | 114564.77 | 106569.37 | -7995.4 | -6.979% | 32455.83 | 28261.82 | -4194.01 | -12.92% | 518.54 | 651.55 | 133.01 | 25.65% | 1958.4 | 1924 | -34.4 | -1.757% | 79632 | 75732 | -3900 | -4.898% | 137 | 151 | 14 | 10.22% | 2022-11-18 01:00
Brampton | 2022 | 644451 | 255 ORENDA RD / BRAM / UP00195213 / CUSTOMER OWNED SUBSTATION | 99 | COMPLETE | Material Over Estimated | Labour est. over | Vehicle Over Estimated- | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 27140.86 | 9082.85 | -18058.01 | -66.53% | 7430.34 | 4592.08 | -2838.26 | -38.2% | 14579.52 | 1352.46 | -13227.06 | -90.72% | 2226 | 654 | -1572 | -70.62% | 2905 | 2484.31 | -420.69 | -14.48% | 60 | 40.5 | -19.5 | -32.5% | 2022-05-08
Brampton | 2022 | 644476 | 4 AUCTION LN / BRAM / NS00204490 / 3PH PAD | 95 | COMPLETE | Cont Est Over | Labour est. over | N/A | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 80284.83 | 66578.73 | -13706.1 | -17.07% | 13628.73 | 10854.25 | -2774.48 | -20.36% | 39258.11 | 38503.03 | -755.08 | -1.923% | 1695.99 | 1086 | -609.99 | -35.97% | 25702 | 16135.45 | -9566.55 | -37.22% | 94.39 | 125 | 30.61 | 32.43% | 2022-12-02 01:00
Brampton | 2022 | 644526 | 760 WANLESS DR/ BRAM/ NS00202620/ 500 KVA PAD | 99 | COMPLETE | Material Over Estimated | Labour est. over | N/A | Rao, Gaurav | No | Cavanaugh, Danny | Simon Evason | 177910.04 | 151743.71 | -26166.33 | -14.71% | 42927.91 | 34527.4 | -8400.51 | -19.57% | 38789.13 | 20708.99 | -18080.14 | -46.61% | 5596 | 5910 | 314 | 5.611% | 90597 | 90597.32 | 0.32 | 0.0003532% | 228 | 187.5 | -40.5 | -17.76% | 2022-10-13 01:00
Brampton | 2022 | 644594 | 2022 TX RENEWAL - 1PH TX GRID G2 - 1 TX | 99 | COMPLETE | N/A | N/A | N/A | Agostini, Robert | No | D'Ermes, Michael | Zenon Lipinski | 11870.27 | 11685.5 | -184.77 | -1.557% | 6068.33 | 5913.01 | -155.32 | -2.56% | 4953.94 | 4545.52 | -408.42 | -8.244% | 848 | 1226.97 | 378.97 | 44.69% | 0 | 0 | 0 |  | 16 | 40 | 24 | 150% | 2022-07-07 01:00
Brampton | 2022 | 644596 | 2022 TX RENEWAL - 1PH TX GRID J2 - 1 TX | 99 | COMPLETE | N/A | N/A | N/A | Agostini, Robert | Yes | D'Ermes, Michael | Zenon Lipinski | 12356.91 | 12731.36 | 374.45 | 3.03% | 6068.33 | 5747.02 | -321.31 | -5.295% | 5440.58 | 5401 | -39.58 | -0.7275% | 848 | 1583.34 | 735.34 | 86.71% | 0 | 0 | 0 |  | 16 | 44 | 28 | 175% | 2022-08-15 01:00
Brampton | 2022 | 644616 | 190 BOVAIRD DR W / BRAM / SR00206666 / 3PH VAULT ROOM | 95 | COMPLETE | Labour est. over | Material Under Estimated | N/A | Rao, Gaurav | No | Tan, Seefon | Simon Evason | 26643.33 | 15431.7 | -11211.63 | -42.08% | 20967.99 | 5637.7 | -15330.29 | -73.11% | 422.54 | 4992.72 | 4570.18 | 1082% | 3052.8 | 2431 | -621.8 | -20.37% | 2200 | 2370.28 | 170.28 | 7.74% | 160 | 69.5 | -90.5 | -56.56% | 2022-07-22 01:00
Brampton | 2022 | 644701 | 2001 WHARTON WAY UNIT B | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Bojanic, Dusan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-08-31 01:00
Brampton | 2022 | 644702 | 6140 OSPREY BLVD | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Bojanic, Dusan | Dre Danieli | 0 | 252.49 | 252.49 |  | 0 | 252.49 | 252.49 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 | 4 |  | 2022-08-31 01:00
Brampton | 2022 | 646347 | POLE RELOCATION -HERITAGE ROAD ( COB PROPOSED SATELLITE YARD) | 95 | COMPLETE | Cont Est Over | Labour est. under | Material Under Estimated | Watters, Maxwell | No | Robinson, David | AW Group | 24147.76 | 25352.13 | 1204.37 | 4.988% | 3767.34 | 10250.67 | 6483.33 | 172.1% | 2726.42 | 4047.06 | 1320.64 | 48.44% | 0 | 0 | 0 |  | 17654 | 11054.4 | -6599.6 | -37.38% | 0 | 11 | 11 |  | 2022-11-07 01:00
Brampton | 2022 | 646774 | KENNEDY RD N AND MAYFIELD RD TEMPORARY ANCHOR RELOCATION | 95 | COMPLETE | Cont Est Over | Labour est. over | N/A | Watters, Maxwell | No | Boivin, Cameron | AW Group | 44694.82 | 11283.77 | -33411.05 | -74.75% | 9300.33 | 7614.92 | -1685.41 | -18.12% | 2215.49 | 1788.7 | -426.79 | -19.26% | 0 | 0 | 0 |  | 33179 | 1880.15 | -31298.85 | -94.33% | 0 | 7.5 | 7.5 |  | 2022-10-03 01:00
Brampton | 2022 | 646881 | S&C FACEPLATE UPGRADES SW44-425 | 98 | COMPLETE | Cont Est Under | Labour est. under | Material Under Estimated | Agostini, Robert | No | Casey, Ryan | K-Line Construction | 71564.06 | 102809.6 | 31245.54 | 43.66% | 9193.15 | 10538.35 | 1345.2 | 14.63% | 48827.91 | 56597.53 | 7769.62 | 15.91% | 608 | 563.87 | -44.13 | -7.258% | 12935 | 35109.85 | 22174.85 | 171.4% | 32 | 29 | -3 | -9.375% | 2022-11-24 01:00
Brampton | 2022 | 646882 | 2022 - S&C FACEPLATE UPGRADES - DA 44-427 | 98 | COMPLETE | Material Under Estimated | Labour est. over | Cont Est Over | Agostini, Robert | No | Casey, Ryan | K-Line Construction | 94998.42 | 73912 | -21086.42 | -22.2% | 9193.15 | 4598.26 | -4594.89 | -49.98% | 48827.91 | 56482.07 | 7654.16 | 15.68% | 608 | 324.22 | -283.78 | -46.67% | 36369.36 | 12507.45 | -23861.91 | -65.61% | 32 | 22.5 | -9.5 | -29.69% | 2022-11-30 01:00
Brampton | 2022 | 646916 | S&C FACEPLATE UPGRADES SW44-448 | 98 | COMPLETE | Labour est. over | Material Under Estimated | Cont Est Under | Agostini, Robert | No | Casey, Ryan | K-Line Construction | 74499.56 | 79484.65 | 4985.09 | 6.691% | 9193.15 | 6490.17 | -2702.98 | -29.4% | 51763.41 | 56957.97 | 5194.56 | 10.04% | 608 | 281.93 | -326.07 | -53.63% | 12935 | 15754.58 | 2819.58 | 21.8% | 32 | 22 | -10 | -31.25% | 2022-12-14 01:00
Brampton | 2022 | 646917 | S&C FACEPLATE UPGRADES SW44-432 | 99 | COMPLETE | Cont Est Over | Material Under Estimated | Labour est. over | Agostini, Robert | No | Casey, Ryan | K-Line Construction | 74499.56 | 75384.15 | 884.59 | 1.187% | 9193.15 | 5632.63 | -3560.52 | -38.73% | 51763.41 | 57006.46 | 5243.05 | 10.13% | 608 | 366.51 | -241.49 | -39.72% | 12935 | 12378.55 | -556.45 | -4.302% | 32 | 22 | -10 | -31.25% | 2022-12-14 01:00
Brampton | 2022 | 646918 | S&C FACEPLATE UPGRADES SW44-50 | 99 | COMPLETE | Cont Est Over | Material Under Estimated | Labour est. over | Agostini, Robert | No | Casey, Ryan | K-Line Construction | 74499.56 | 78518.43 | 4018.87 | 5.394% | 9193.15 | 7966.43 | -1226.72 | -13.34% | 51763.41 | 57332.12 | 5568.71 | 10.76% | 608 | 859.9 | 251.9 | 41.43% | 12935 | 12359.98 | -575.02 | -4.445% | 32 | 39.5 | 7.5 | 23.44% | 2022-12-14 01:00
Brampton | 2022 | 645210 | 1555 CLARK BLVD / BRAM / UP00204207 / 3PH PAD | 95 | COMPLETE | Cont Est Over | Material Over Estimated | Labour est. over | Rao, Gaurav | No | Wigley, Graham | Simon Evason | 176454.44 | 59740.97 | -116713.47 | -66.14% | 34784.33 | 21291 | -13493.33 | -38.79% | 68780.11 | 7127.06 | -61653.05 | -89.64% | 2376 | 3779 | 1403 | 59.05% | 70514 | 27543.91 | -42970.09 | -60.94% | 180 | 169 | -11 | -6.111% | 2022-10-01 01:00
Brampton | 2022 | 645319 | SCADA AMATE SWITCHES INSTALLATION ON EAST DRIVE AND COVENTRY ROAD | 98 | COMPLETE | Material Under Estimated | Labour est. under | Cont Est Over | Watters, Maxwell | No | Robinson, David | AW Group | 222733.96 | 306660.78 | 83926.82 | 37.68% | 4446.24 | 36658.88 | 32212.64 | 724.5% | 109218.86 | 175211.82 | 65992.96 | 60.42% | 1122.14 | 1750 | 627.86 | 55.95% | 107946.72 | 93040.08 | -14906.64 | -13.81% | 24 | 154 | 130 | 541.7% | 2022-12-22 01:00
Brampton | 2022 | 645341 | POLE # 7339 RELOCATION- MAYFIELD RD. AND MARTINBRYNE | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Watters, Maxwell | No | Robinson, David | AW Group | 33473.94 | 25056.94 | -8417 | -25.14% | 5595.75 | 3307.88 | -2287.87 | -40.89% | 5366.19 | 6002.04 | 635.85 | 11.85% | 0 | 0 | 0 |  | 22512 | 15747.02 | -6764.98 | -30.05% | 45 | 6.5 | -38.5 | -85.56% | 2022-06-27 01:00
Brampton | 2022 | 645479 | POLE INSTALLATION -HEART LAKE RD | 95 | COMPLETE | Material Under Estimated | Labour est. under | Cont Est Over | Watters, Maxwell | No | Robinson, David | AW Group | 80001.77 | 92224.3 | 12222.53 | 15.28% | 9104.97 | 17044.41 | 7939.44 | 87.2% | 15632.8 | 23551.15 | 7918.35 | 50.65% | 0 | 0 | 0 |  | 55264 | 51628.74 | -3635.26 | -6.578% | 0 | 20.5 | 20.5 |  | 2022-09-19 01:00
Brampton | 2022 | 645586 | TFP MAYCHING - SUBD CAP PROJ | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Cont Est Under | Gamboa, Henry | No | Erzek, Ryan | Zenon Lipinski | 19310.86 | 10266.43 | -9044.43 | -46.84% | 14873.37 | 6913.93 | -7959.44 | -53.51% | 0 | 0 | 0 |  | 3110.49 | 720 | -2390.49 | -76.85% | 1327 | 2632.5 | 1305.5 | 98.38% | 80 | 18 | -62 | -77.5% | 2022-08-22 01:00
Brampton | 2022 | 645728 | DIXIE RD NOISE WALL ISOLATIONS | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Mckeen, Brant | Dre Danieli | 0 | 495.91 | 495.91 |  | 0 | 495.91 | 495.91 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-13 01:00
Brampton | 2022 | 645832 | GOREWAY DRIVE ANCHOR RELOCATION | 95 | COMPLETE | Cont Est Over | N/A | N/A | Watters, Maxwell | No | Robinson, David | AW Group | 15202.87 | 11655.33 | -3547.54 | -23.33% | 2446.55 | 2324.63 | -121.92 | -4.983% | 956.32 | 447.05 | -509.27 | -53.25% | 0 | 0 | 0 |  | 11800 | 8883.65 | -2916.35 | -24.71% | 0 | 0 | 0 |  | 2023-01-05 01:00
Brampton | 2022 | 647189 | 160 SUN PAC BLVD/BRAM/NS00269176/ 150 KVA | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Cavanaugh, Danny | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-21 01:00
Brampton | 2022 | 648846 | 237 B ADVANCE BLVD. / BRAM / UP00313938 / 3PH PAD | 99 | CANCELLED | N/A |  |  | Rao, Gaurav | No | Central North | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-05 00:59
Brampton | 2019 | W116 | Mayfield Rd | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Robinson, David | Reaburn, Jeff | 0 | 1743.95 | 1743.95 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4.5 | 4.5 |  | 2019-04-05 00:59
Brampton | 2019 | W938 | 59 MCLAUGHLIN ROAD NORTH | 99 | COMPLETE | Estimate incorrect | N/A | N/A |  | No | Bojanic, Dusan | Simon Evason | 5810 | 6565.44 | 755.44 | 13% | 5448 | 3519.08 | -1928.92 | -35.41% | 362 | 859.03 | 497.03 | 137.3% | 0 | 1024 | 1024 |  | 0 | 1163.33 | 1163.33 |  | 53 | 41 | -12 | -22.64% | 2019-05-24
Brampton | 2019 | X103 | SANDALWOOD PKY W & VETERANS DR | 99 | CANCELLED | N/A |  |  |  | No | Armstrong, Colby | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-20 01:00
Brampton | 2019 | Y155 | TOMKEN RD. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-20 01:00
Brampton | 2019 | Y891 | FERNFOREST DR AND KALAHARI RD - SG | 99 | COMPLETE | N/A | N/A | N/A |  | No | Casey, Ryan | Richard Cuddy | 106348.71 | 100185 | -6163.71 | -5.796% | 25375.54 | 22017.96 | -3357.58 | -13.23% | 78626.17 | 74235.25 | -4390.92 | -5.585% | 2347 | 3600 | 1253 | 53.39% | 0 | 0 | 0 |  | 222 | 233 | 11 | 4.955% | 2019-02-20 01:00
Brampton | 2019 | Z704 | NE corner Steeles and Chinguacousy Rd | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-02
Brampton | 2019 | B136 | Remembrance Rdr | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Hotham, Matthew | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | B287 | 66A Main St.S. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | B363 | WILLIAMS PKWY & ROYAL WEST DR | 99 | CANCELLED | N/A |  |  |  | No | Central North | Simon Evason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | B872 | MAYFIELD RD AND DIXIE ROAD | 99 | CANCELLED | N/A |  |  |  | No | Gamboa, Henry | Simon Evason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | B878 | Geddes lane n of Demaris Dr | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | C335 | 56A Wellington St. W. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | C922 | 2001 North Park Dr | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | C948 | sw corner Queen St. & CreditviewRd. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | D062 | Queen Street west – Chinguacousy Road to Mississauga Road- pull old poles | 99 | CANCELLED | N/A |  |  |  | No | Central North | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | -25 | -100% | 2019-04-28 01:00
Brampton | 2019 | D285 | VARIOUS LOCATIONS-KENVIEW BLD | 99 | CANCELLED | N/A |  |  |  | No | Casey, Ryan | Hotham, Matthew | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | F193 | WILLIAMS PKWY & ROYAL WEST DR | 99 | CANCELLED | N/A |  |  |  | No | Erzek, Ryan | Simon Evason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | F194 | WILLIAMS PKWY & ROYAL WEST DR | 99 | CANCELLED | N/A |  |  |  | No | Erzek, Ryan | Simon Evason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | G841 | RICHMOND DR & BARTLEY BULL PKY | 99 | CANCELLED | N/A |  |  |  | No | Casey, Ryan | Hotham, Matthew | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | H145 | H145 | 99 | CANCELLED | N/A |  |  |  | No | Central North | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | I917 | BONNIE BRAE & CHINGUACOUSY | 99 | CANCELLED | N/A |  |  |  | No | Erzek, Ryan | Simon Evason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | J185 | 10916 Coleraine Dr. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | L737 | Queen St and The Gore Road -Two Stub poles | 99 | CANCELLED | N/A |  |  |  | No | Central North | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | M598 | 4864 Castlemore Rd | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | M806 | Rivermont Rd and Fiancial Dr. (M173) | 99 | CANCELLED | N/A |  |  |  | No | Erzek, Ryan | Richard Cuddy | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | M894 | 22 NEOPOLITAN RD | 99 | CANCELLED | N/A |  |  |  | No | Erzek, Ryan | Simon Evason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | M895 | 23 Avondale Blvd | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | M966 | Dist Cable Rehab 42M46 & 42M476 - Electrical Work | 99 | CANCELLED | N/A |  |  |  | No | Gamboa, Henry | Simon Evason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N194 | SE corner Bovaird Dr. and Hurontario St. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N215 | DIXIE RD & SANDALWOOD PKY E | 99 | CANCELLED | N/A |  |  |  | No | D'Ermes, Michael | Hotham, Matthew | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N359 | 1105 Queen St E | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N479 | Hwy 407 and Airport Rd | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N482 | Intermodal and CN Rail | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N623 | 200 STEELWELL RD | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N649 | 200 STEELWEL RD (TEMP SERVICE ) | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N672 | 10639 Heartlake Rd | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | N771 | 31 Hansen Rd.S. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-28 01:00
Brampton | 2019 | NA37 | 296 ORENDA RD. | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A |  | No | Cavanaugh, Danny | Simon Evason | 11724 | 9397.87 | -2326.13 | -19.84% | 8000 | 5532.04 | -2467.96 | -30.85% | 2162 | 3379.29 | 1217.29 | 56.3% | 1562 | 461.75 | -1100.25 | -70.44% | 0 | 0 | 0 |  | 91 | 45.5 | -45.5 | -50% | 2019-04-28 01:00
Brampton | 2019 | NB21 | 10254 Hurontario St. | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Cavanaugh, Danny | Simon Evason | 7000 | 3592.32 | -3407.68 | -48.68% | 5000 | 2407.47 | -2592.53 | -51.85% | 0 | 0 | 0 |  | 1000 | 554 | -446 | -44.6% | 1000 | 628.19 | -371.81 | -37.18% | 40 | 27.75 | -12.25 | -30.63% | 2019-05-03 01:00
Brampton | 2019 | O842 | 58 church St E | 99 | CANCELLED | N/A |  |  |  | No | Erzek, Ryan | Nichol, Sandi | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Brampton | 2019 | P198 | 1685 Queen St E | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Brampton | 2019 | P491 | 130 SANDALWOOD PKWY WEST | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Brampton | 2019 | P616 | 1100 CENTRAL PARK DR. | 99 | CANCELLED | N/A |  |  |  | No | Bojanic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Brampton | 2019 | P745 | 11613 Bramalea Rd | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Brampton | 2019 | P748 | 7625 Finch Ave. W. | 99 | CANCELLED | N/A |  |  |  | No | Cavanaugh, Danny | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Brampton | 2019 | Q188 | 101 West Drive | 99 | CANCELLED | N/A |  |  |  | No | Ferry, Rodnne | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Guelph | 2020 | 1115386 | 412 Laird Road - New Office Building | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 2289.41 | 2289.41 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11 | 11 |  | 2020-10-17 01:00
Guelph | 2020 | 1116951 | 119 Ingram Drive and 35 Wideman Boulevard On-Street Townhomes | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 188626.65 | 138396.58 | -50230.07 | -26.63% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 176 | 215 | 39 | 22.16% | 2020-08-24 01:00
Guelph | 2020 | 1118077 | Gladstone Avenue - Pole Line Reconstruction | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Manes, Bradley | 107385.2 | 76168.52 | -31216.68 | -29.07% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 570.5 | 368.5 | -202 | -35.41% | 2020-02-13 01:00
Guelph | 2020 | 1119470 | 85 Queen St - New U/G Service | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 91.84 | 1172.84 | 1081 | 1177% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-28 01:00
Guelph | 2020 | 1122052 | Foresthill Drive and James Street West Reconstruction | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 144542.56 | 133151.08 | -11391.48 | -7.881% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1000 | 582.9 | -417.1 | -41.71% | 2020-11-10 01:00
Guelph | 2020 | 1122117 | King St, Havelock St & Spring St Reconstruction | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 190487.67 | 77015.99 | -113471.68 | -59.57% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1092 | 0 | -1092 | -100% | 2020-12-31 01:00
Guelph | 2020 | 1122118 | Johnston Street Reconstruction | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 170704.8 | 106177.82 | -64526.98 | -37.8% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1000 | 400.6 | -599.4 | -59.94% | 2020-12-15 01:00
Guelph | 2020 | 1123312 | Collingwood St & Shaftesbury Ave - Pole Line R/C | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 156141.07 | 138938.37 | -17202.7 | -11.02% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 810 | 615.8 | -194.2 | -23.98% | 2020-03-30 01:00
Guelph | 2020 | 1123811 | Pole 2 Chester Street | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 10599.84 | 8360.12 | -2239.72 | -21.13% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 64 | 39.5 | -24.5 | -38.28% | 2020-11-25 01:00
Guelph | 2020 | 1125108 | 226-274 Scottsdale Drive Townhomes - South of College Ave W | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 169274.83 | 315132.98 | 145858.15 | 86.17% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 182 | 422 | 240 | 131.9% | 2020-03-20 01:00
Guelph | 2021 | 1126105 | 164 and 168 Deerpath Drive Townhomes | 99 | COMPLETE | N/A |  |  |  | No | Kingswell, Dean J | Stevens, Carl | 337987.33 | 43263.12 | -294724.21 | -87.2% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 366.3 | 310 | -56.3 | -15.37% | 2021-03-01 01:00
Guelph | 2020 | 1127158 | King St - OH Rebuild | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Manes, Bradley | 147799.15 | 85480.48 | -62318.67 | -42.16% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 900 | 310.5 | -589.5 | -65.5% | 2020-12-18 01:00
Guelph | 2020 | 1127159 | Ferndale Ave - O/H Rebuild | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 251423.74 | 208156.86 | -43266.88 | -17.21% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1448 | 868 | -580 | -40.06% | 2020-09-22 01:00
Guelph | 2020 | 1129289 | Stevenson Street Townhomes - subdivision | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 23492.53 | 25201.5 | 1708.97 | 7.275% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 130 | 118 | -12 | -9.231% | 2020-09-14 01:00
Guelph | 2020 | 1129621 | 5M73 Feeder Cable | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 187649.39 | 187649.39 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 806.3 | 806.3 |  | 2020-02-06 01:00
Guelph | 2020 | 1129925 | Pole 7, 13 & 19 Westmount Rd | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 39197.22 | 39377.49 | 180.27 | 0.4599% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 195 | 196.5 | 1.5 | 0.7692% | 2020-07-31 01:00
Guelph | 2020 | 1131245 | Elizabeth & York | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 33198.38 | 55209.75 | 22011.37 | 66.3% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 148.75 | 260 | 111.25 | 74.79% | 2020-08-24 01:00
Guelph | 2020 | 1132251 | TH45 Gallery | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 15845.51 | 15845.51 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 40.5 | 40.5 |  | 2020-09-28 01:00
Guelph | 2020 | 1132375 | 149 Wellington St W - pole replacement | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 0 | 46217.4 | 46217.4 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 188.5 | 188.5 |  | 2020-06-19 01:00
Guelph | 2022 | 1132376 | Z6003 Pole 208 Woodlawn Rd W | 99 | COMPLETE | N/A |  |  |  | Yes | Patenaude, Mélanie | Manes, Bradley | 42654.81 | 35930.5 | -6724.31 | -15.76% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 78.75 | 72.75 | 1212% | 2022-01-19 01:00
Guelph | 2020 | 1132511 | 120 Country Club Rebuild | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 466647.52 | 466647.52 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 400.6 | 400.6 |  | 2020-09-21 01:00
Guelph | 2020 | 1134205 | 190 Hanlon Creek | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 46503.52 | 46503.52 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 71.5 | 71.5 |  | 2020-08-20 01:00
Guelph | 2020 | 1135255 | 590 Hanlon Creek Blvd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 6789.59 | 10788.11 | 3998.52 | 58.89% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 36 | 36 |  | 2020-10-27 01:00
Guelph | 2021 | 1135276 | 140 Huron Street Townhomes | 99 | COMPLETE | N/A |  |  |  | No | Kingswell, Dean J | Stevens, Carl | 183.68 | 65205.79 | 65022.11 | 35400% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 222.5 | 222.5 |  | 2021-04-22
Guelph | 2021 | 1136109 | 19 Elmira Rd S - Costs TX Swap | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 8752.43 | 2341.98 | -6410.45 | -73.24% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 51 | 18 | -33 | -64.71% | 2021-11-01 01:00
Guelph | 2020 | 1145571 | Palmer St – OH Rebuild | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Manes, Bradley | 105402.2 | 91362.54 | -14039.66 | -13.32% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 876.75 | 400.2 | -476.55 | -54.35% | 2020-12-18 01:00
Guelph | 2020 | 1145817 | Campbell TS 36M42 Feeder Egress Cable Replacement | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 62364.77 | 70088.86 | 7724.09 | 12.39% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 288 | 316.5 | 28.5 | 9.896% | 2020-08-14 01:00
Guelph | 2020 | 1145818 | Campbell TS 36M61 Feeder Egress Cable Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 66931.09 | 81731.23 | 14800.14 | 22.11% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 296.4 | 383 | 86.6 | 29.22% | 2020-09-05 01:00
Guelph | 2021 | 1146109 | 245 Hanlon Creek Blvd - Per Service | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 60800.01 | 32620.56 | -28179.45 | -46.35% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 140.6 | 56.5 | -84.1 | -59.82% | 2021-02-10 01:00
Guelph | 2021 | 1146282 | PMSG005 - 130 Stone Rd West - pad switch replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Jamkodjian, Cassandra | Stevens, Carl | 83283.01 | 85103.73 | 1820.72 | 2.186% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 114 | 52.5 | -61.5 | -53.95% | 2021-11-18 01:00
Guelph | 2021 | 1146285 | PMG - 110 Stone Road West | 99 | COMPLETE | N/A |  |  |  | No | Jamkodjian, Cassandra | Stevens, Carl | 83357.7 | 96137.86 | 12780.16 | 15.33% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 114 | 88.4 | -25.6 | -22.46% | 2021-05-28 01:00
Guelph | 2020 | 1146286 | PMSG017 - 33 Village Green - pad switch replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 83768.69 | 66288.75 | -17479.94 | -20.87% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 114 | 111 | -3 | -2.632% | 2020-10-30 01:00
Guelph | 2021 | 1146287 | PMS - Teal Drive | 99 | COMPLETE | N/A |  |  |  | No | Jamkodjian, Cassandra | Stevens, Carl | 81742.15 | 82720.84 | 978.69 | 1.197% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 91 | 92.2 | 1.2 | 1.319% | 2021-03-31 01:00
Guelph | 2021 | 1146288 | PMSG031 - Edinburgh Rd S @ Terraview Cres - pad switch replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Jamkodjian, Cassandra | Stevens, Carl | 81742.15 | 83359.52 | 1617.37 | 1.979% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 91 | 99.5 | 8.5 | 9.341% | 2021-04-30
Guelph | 2021 | 1146289 | PMS - 52 Beaver Meadow Drive | 99 | COMPLETE | N/A |  |  |  | No | Jamkodjian, Cassandra | Stevens, Carl | 84652.96 | 83630.05 | -1022.91 | -1.208% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 114 | 94 | -20 | -17.54% | 2021-03-16 01:00
Guelph | 2020 | 1146290 | PMSG073 - 8 Paisley St - pad switch replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 75449 | 75495.12 | 46.12 | 0.06113% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 50.5 | 41 | -9.5 | -18.81% | 2020-11-30 01:00
Guelph | 2020 | 1146291 | MJU-9 - 101 Lou's Blvd W - pad switch replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 22259.1 | 29579.27 | 7320.17 | 32.89% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 880 | 874 | 14567% | 2020-09-09 01:00
Guelph | 2020 | 1146292 | MJU-10 - 129 Lou's Blvd W Fountain St - pad switch replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 22259.1 | 29130.14 | 6871.04 | 30.87% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 864 | 858 | 14300% | 2020-08-14 01:00
Guelph | 2020 | 1150261 | 45 Marksham Rd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 495446.94 | 430341.66 | -65105.28 | -13.14% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 592 | 525.3 | -66.7 | -11.27% | 2020-11-12 01:00
Guelph | 2020 | 1151466 | Lee Street | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 23630 | 17151.64 | -6478.36 | -27.42% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 30 | 38.5 | 8.5 | 28.33% | 2020-09-11 01:00
Guelph | 2020 | 1151747 | Wyndham St S - Pole #22,26,28,30 | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 0 | 73759.78 | 73759.78 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 278.2 | 278.2 |  | 2020-10-16 01:00
Guelph | 2020 | 1152246 | L0738, Silvercreek Pkwy n/o Paisley. | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Manes, Bradley | 88551.54 | 88679.68 | 128.14 | 0.1447% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 195 | 262.3 | 67.3 | 34.51% | 2020-07-31 01:00
Guelph | 2020 | 1152299 | L0003, College Ave E, at Powerhouse Lane | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 60333.8 | 53391.85 | -6941.95 | -11.51% | 7956 | 0 | -7956 | -100% | 48510.4 | 0 | -48510.4 | -100% | 2298.4 | 0 | -2298.4 | -100% | 1569 | 0 | -1569 | -100% | 113 | 88 | -25 | -22.12% | 2020-11-05 01:00
Guelph | 2020 | 1152311 | L1001, University e/o Gordon, | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 62749.78 | 55278.43 | -7471.35 | -11.91% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 101 | 88.9 | -12.1 | -11.98% | 2020-11-05 01:00
Guelph | 2020 | 1152312 | L0245, Martin Ave s/o Forbes. | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 60141.48 | 50061.71 | -10079.77 | -16.76% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 95 | 67.3 | -27.7 | -29.16% | 2020-09-22 01:00
Guelph | 2020 | 1152365 | L0123, York Rd, w/o Morris St | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 0 | 70261.97 | 70261.97 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 140 | 147.9 | 7.9 | 5.643% | 2020-09-18 01:00
Guelph | 2021 | 1152570 | Beechwood Ave - North of Waterloo Ave - Customer Capital Work | 99 | COMPLETE | N/A |  |  |  | No | Harrison, Eric | Stevens, Carl | 8025.75 | 17432.45 | 9406.7 | 117.2% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 90.1 | 92.5 | 2.4 | 2.664% | 2021-04-23
Guelph | 2022 | 1152590 | 395 Edinburgh Rd N - temp | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 69945.73 | 3190.4 | -66755.33 | -95.44% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 226.2 | 18.5 | -207.7 | -91.82% | 2022-01-03 01:00
Guelph | 2020 | 1154142 | Pole 10 Marlborough Rd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 11509.39 | 11509.39 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 48.5 | 48.5 |  | 2020-12-11 01:00
Guelph | 2020 | 1154143 | 151 Metcalfe Street | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 7228.31 | 2125.61 | -5102.7 | -70.59% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 44 | -2 | -46 | -104.5% | 2020-12-11 01:00
Guelph | 2020 | 1154144 | Pole 18 Skov Cres | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 6385.4 | 6385.4 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 31.5 | 31.5 |  | 2020-12-11 01:00
Guelph | 2021 | 1155218 | Norwich Street Pedestrian Bridge - Line Isolation | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Manes, Bradley | 9500 | 5637.75 | -3862.25 | -40.66% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 45.5 | 45.5 |  | 2021-05-28 01:00
Guelph | 2021 | 1155355 | 89 Beechwood Avenue Townhomes | 99 | COMPLETE | N/A |  |  |  | No | Kingswell, Dean J | Stevens, Carl | 48928.45 | 59850.74 | 10922.29 | 22.32% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 78.25 | 73 | -5.25 | -6.709% | 2021-05-03
Guelph | 2021 | 1157566 | 389 Speedvale Ave W – Transite - Royal Rd - Pole 5 to BK01275 | 99 | COMPLETE | N/A |  |  |  | No | Patenaude, Mélanie | Stevens, Carl | 104928.47 | 76035.16 | -28893.31 | -27.54% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 208.85 | 174.3 | -34.55 | -16.54% | 2021-02-10 01:00
Guelph | 2021 | 1158579 | Lowes Road - Subivision | 99 | COMPLETE | N/A |  |  |  | No | Kingswell, Dean J | Stevens, Carl | 189348.8 | 154932.35 | -34416.45 | -18.18% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 219 | 202 | -17 | -7.763% | 2021-11-18 01:00
Guelph | 2020 | 1158656 | 245 Hanlon Blvd - Temp Service | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-04 01:00
Guelph | 2021 | 1158768 | BrightonSt, Liac Pl,Sumac Pl Pole Line Rebuild | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Manes, Bradley | 164424.48 | 122267.2 | -42157.28 | -25.64% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 957.5 | 499 | -458.5 | -47.89% | 2021-04-23
Guelph | 2021 | 1159146 | 353 & 355 Victoria Rd N - Transite | 99 | COMPLETE | N/A |  |  |  | No | Patenaude, Mélanie | Lauryssen, John | 90090.1 | 58889.29 | -31200.81 | -34.63% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 82.3 | 47.7 | -34.6 | -42.04% | 2021-06-03 01:00
Guelph | 2021 | 1159210 | Ptarmigan Drive and Merganser Drive | 99 | COMPLETE | N/A |  |  |  | yes | Jamkodjian, Cassandra | Stevens, Carl | 25636.84 | 33079.52 | 7442.68 | 29.03% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 119.4 | 139.5 | 20.1 | 16.83% | 2021-09-03 01:00
Guelph | 2020 | 1159211 | Campbell TS 36M12 Feeder Egress | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 25864.08 | 23186.56 | -2677.52 | -10.35% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 119.6 | 72.5 | -47.1 | -39.38% | 2020-12-11 01:00
Guelph | 2020 | 1159216 | Campbell TS - 36M21 Feeder Egress Cable Replacment | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 27022.19 | 24568.87 | -2453.32 | -9.079% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 119.4 | 68.8 | -50.6 | -42.38% | 2020-12-11 01:00
Guelph | 2020 | 1159217 | Campbell TS - 36M52 Feeder Egress Cable Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 72863.33 | 77344.25 | 4480.92 | 6.15% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 359.4 | 304.5 | -54.9 | -15.28% | 2020-11-27 01:00
Guelph | 2020 | 1159282 | 28 Alma Street North | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 2464.07 | 2904.66 | 440.59 | 17.88% | 1442.03 | 0 | -1442.03 | -100% | 328.31 | 0 | -328.31 | -100% | 416.59 | 0 | -416.59 | -100% | 185.3 | 0 | -185.3 | -100% | 14.5 | 15.5 | 1 | 6.897% | 2020-06-08 01:00
Guelph | 2021 | 1159314 | Gladstone Avenue, Phase 2 | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Manes, Bradley | 81292.69 | 83712.67 | 2419.98 | 2.977% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 528.25 | 375 | -153.25 | -29.01% | 2021-04-23
Guelph | 2020 | 1159965 | 355 Massey Rd - Linex - Linamar Cogen | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 31380.12 | 39261.37 | 7881.25 | 25.12% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 150.2 | 57 | -93.2 | -62.05% | 2020-10-24 01:00
Guelph | 2020 | 1160033 | 375 Massey Rd - Autocom - Linamar Cogen | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 36225.74 | 46313.47 | 10087.73 | 27.85% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 170 | 90.2 | -79.8 | -46.94% | 2020-09-12 01:00
Guelph | 2020 | 1160057 | 400 Massey Rd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 79182.57 | 64404.44 | -14778.13 | -18.66% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 238 | 156.3 | -81.7 | -34.33% | 2020-11-12 01:00
Guelph | 2021 | 1161145 | Sackville St, Morris St, Harris St & Johnston St - Pole Line Rebuild | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 128808.83 | 129086.43 | 277.6 | 0.2155% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 776.95 | 501 | -275.95 | -35.52% | 2021-05-14
Guelph | 2021 | 1162545 | Temp U/G Service - 166 Deerpath Dr Townhomes | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 500.72 | 500.72 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8 | 8 |  | 2021-03-19 01:00
Guelph | 2021 | 1162819 | Queen Street - Derry St to Eramosa Rd) | 99 | COMPLETE | N/A |  |  |  | Yes | Patenaude, Mélanie | Lauryssen, John | 1339.76 | 69441.45 | 68101.69 | 5083% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 100 | 342.7 | 242.7 | 242.7% | 2021-02-25 01:00
Guelph | 2021 | 1163908 | Lowes Road West | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 12969.09 | 53411.23 | 40442.14 | 311.8% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 275.9 | 275.9 |  | 2021-02-25 01:00
Guelph | 2020 | 1164226 | Pole 1 Winston Crescent | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Manes, Bradley | 3567.43 | 7409.65 | 3842.22 | 107.7% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 38 | 38 |  | 2020-11-20 01:00
Guelph | 2021 | 1164227 | Pole 2 Kitchener Ave | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 6071.48 | 2459.27 | -3612.21 | -59.49% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 36 | 1.6 | -34.4 | -95.56% | 2021-01-08 01:00
Guelph | 2021 | 1164228 | Pole 4 Riverview Dr. | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 12715.45 | 6077.29 | -6638.16 | -52.21% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 62.5 | 26.5 | -36 | -57.6% | 2021-01-08 01:00
Guelph | 2020 | 1164230 | Pole 33 Lane Street | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Manes, Bradley | 3317.63 | 6406.28 | 3088.65 | 93.1% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 31 | 31 |  | 2020-11-02 01:00
Guelph | 2021 | 1165751 | Golds Court - Pole Line Extension | 99 | COMPLETE | N/A |  |  |  | No | South-West | Lauryssen, John | 27361.04 | 41104.42 | 13743.38 | 50.23% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 28 | 118.9 | 90.9 | 324.6% | 2021-11-30 01:00
Guelph | 2021 | 1165997 | 65 & 75 Quarterman Road | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 158076.18 | 145930.78 | -12145.4 | -7.683% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 301.4 | 227.5 | -73.9 | -24.52% | 2021-08-13 01:00
Guelph | 2022 | 1166443 | 71 Wyndham St - temp | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 85916.47 | 1308.08 | -84608.39 | -98.48% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 146.4 | 47.5 | -98.9 | -67.55% | 2022-01-27 01:00
Guelph | 2020 | 1167063 | Menzie Ave (South of York Rd) | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 19625.67 | 94429.03 | 74803.36 | 381.2% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 421.5 | 421.5 |  | 2020-11-20 01:00
Guelph | 2021 | 1168011 | Arthur Street North (from Palmer St to Rose St) & New St | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 214021.51 | 277817.62 | 63796.11 | 29.81% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 953.5 | 1258.5 | 305 | 31.99% | 2021-10-08 01:00
Guelph | 2020 | 1168926 | Carden St & Wyndham St N (MH#135) | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 413.29 | 10167.29 | 9754 | 2360% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5.5 | 5.5 |  | 2020-10-24 01:00
Guelph | 2021 | 1169016 | Pole A2 Inverness Drive (N1316) & Pole 33 Balmoral Drive (N1317) | 99 | COMPLETE | N/A |  |  |  | No | Patenaude, Mélanie | Manes, Bradley | 4707.83 | 0 | -4707.83 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 16 | 0 | -16 | -100% | 2021-06-03 01:00
Guelph | 2022 | 1169159 | 425 Watson Pky N | 99 | COMPLETE | N/A |  |  |  | No | Dyce, Stephen A | Calvin Arsenault | 47100.83 | 30648.95 | -16451.88 | -34.93% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 120.2 | 53 | -67.2 | -55.91% | 2020-12-04 01:00
Guelph | 2020 | 1170919 | 242 Speedvale Avenue West | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 22547.58 | 22547.58 | 0 | 0% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5 | 5 |  | 2020-12-04 01:00
Guelph | 2020 | 1171192 | Pole 21 Vancouver Dr | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Manes, Bradley | 3353.66 | 6938.41 | 3584.75 | 106.9% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 32 | 32 |  | 2020-11-16 01:00
Guelph | 2020 | 1171193 | Pole 31 Ottawa Crescent | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 13285.35 | 1942.15 | -11343.2 | -85.38% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 59 | -2 | -61 | -103.4% | 2020-12-15 01:00
Guelph | 2021 | 1171873 | Pole 91 Stevenson St N | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 380.59 | 8685.92 | 8305.33 | 2182% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 40 | 40 |  | 2021-02-15 01:00
Guelph | 2020 | 1171879 | Pole 222 York Rd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 971.3 | 8805.25 | 7833.95 | 806.5% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 34 | 34 |  | 2020-12-11 01:00
Guelph | 2020 | 1171881 | Pole 13 Airpark Place | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 1904.64 | 6685.1 | 4780.46 | 251% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 29 | 29 |  | 2020-12-11 01:00
Guelph | 2021 | 1171912 | Pole 44 Watson Parkway South | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 11989.19 | 13410.5 | 1421.31 | 11.85% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 58.5 | 48 | -10.5 | -17.95% | 2021-01-08 01:00
Guelph | 2022 | 1171984 | Temp O/H Service - 299 York Rd | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Manes, Bradley | 6174 | 0 | -6174 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-27 01:00
Guelph | 2021 | 1173656 | Pole 3 Sloan Ave | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 11087.48 | 8776.01 | -2311.47 | -20.85% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 53 | 32 | -21 | -39.62% | 2021-02-09 01:00
Guelph | 2021 | 1173657 | Pole 9 Hayes Ave | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 0 | 19226.79 | 19226.79 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 73 | 101 | 28 | 38.36% | 2021-02-08 01:00
Guelph | 2021 | 1173658 | Pole 26 Windsor St | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 6885.87 | 4208.62 | -2677.25 | -38.88% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 42 | 15 | -27 | -64.29% | 2021-01-08 01:00
Guelph | 2021 | 1173659 | Pole 18 Windsor St | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 18072.1 | 20314.79 | 2242.69 | 12.41% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 82.5 | 100 | 17.5 | 21.21% | 2021-06-03 01:00
Guelph | 2022 | 1175332 | 1 Wilbert Street - Temp O/H Service | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Manes, Bradley | 2228 | 0 | -2228 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8 | 8 |  | 2022-01-03 01:00
Guelph | 2022 | 1175473 | 117 Guelph Street, Rockwood | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 16597.65 | 2340.95 | -14256.7 | -85.9% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 61 | 54 | -7 | -11.48% | 2022-02-04 01:00
Guelph | 2021 | 1176661 | Pole 3 Fair Road - w/o Arrow Road | 99 | COMPLETE | N/A |  |  |  | No | Patenaude, Mélanie | Manes, Bradley | 25709.35 | 19556.49 | -6152.86 | -23.93% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 42 | 32 | -10 | -23.81% | 2021-01-18 01:00
Guelph | 2021 | 1177661 | Bagot St Phase 1, London Rd W and Mercer St | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 271420 | 286882.2 | 15462.2 | 5.697% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1517.2 | 1468.3 | -48.9 | -3.223% | 2021-05-25 01:00
Guelph | 2021 | 1177677 | Bagot St Phase 2 , Suffolk St W and Merion St | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 241674.3 | 349997.08 | 108322.78 | 44.82% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1097.2 | 1596.5 | 499.3 | 45.51% | 2021-10-15 01:00
Guelph | 2021 | 1177691 | Islington Dr, Inverness Dr and Glenbrook Ave | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 297189.86 | 315020.46 | 17830.6 | 6% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1636.5 | 1618.2 | -18.3 | -1.118% | 2021-05-26 01:00
Guelph | 2021 | 1179565 | Pole 3 Algoma Drive | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 11516.09 | 12292.4 | 776.31 | 6.741% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 68.5 | 60 | -8.5 | -12.41% | 2021-02-05 01:00
Guelph | 2022 | 1179566 | Pole 10 Hamel Ave Dist OH | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 8514.07 | 3242.97 | -5271.1 | -61.91% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 67.2 | 43.1 | -24.1 | -35.86% | 2022-01-27 01:00
Guelph | 2021 | 1179567 | Pole 52 Waverly Drive | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 10172.21 | 13499.74 | 3327.53 | 32.71% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 58.5 | 63.5 | 5 | 8.547% | 2021-01-18 01:00
Guelph | 2021 | 1179568 | Pole 62 Waverly Dr | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 6259.03 | 15938.33 | 9679.3 | 154.6% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 64.5 | 39.5 | 158% | 2021-01-22 01:00
Guelph | 2021 | 1180585 | Hanlon Road - Overhead Switch Replacement Poles | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 18587.4 | 19450 | 862.6 | 4.641% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 120.5 | 113 | -7.5 | -6.224% | 2021-01-18 01:00
Guelph | 2021 | 1180645 | 2 Worton Avenue | 99 | COMPLETE | N/A |  |  |  | Yes | South-West | Stevens, Carl | 164744.1 | 211447.01 | 46702.91 | 28.35% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 165 | 228 | 63 | 38.18% | 2021-10-15 01:00
Guelph | 2022 | 1181382 | Pole 7 Duke Street | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Calvin Arsenault | 8271.64 | 17483.39 | 9211.75 | 111.4% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 66.5 | 104.3 | 37.8 | 56.84% | 2022-01-27 01:00
Guelph | 2021 | 1181388 | Pole R11 Dunlop Drive | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 5972.18 | 21987.3 | 16015.12 | 268.2% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 33 | 24.9 | -8.1 | -24.55% | 2021-04-01 01:00
Guelph | 2022 | 1181396 | Pole 23 Dunlop Drive | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Calvin Arsenault | 0 | 17703.29 | 17703.29 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 41.5 | 73 | 31.5 | 75.9% | 2022-01-27 01:00
Guelph | 2021 | 1181397 | Pole 132 College Ave E | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 6255.4 | 12105.44 | 5850.04 | 93.52% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 33 | 60 | 27 | 81.82% | 2021-01-18 01:00
Guelph | 2021 | 1181670 | Hanlon Road - LIS L0181 Replacement Dist OH Poles | 99 | COMPLETE | N/A |  |  |  | Yes | Consultant, NBM | Manes, Bradley | 24453.43 | 16576.27 | -7877.16 | -32.21% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 113 | 108.5 | -4.5 | -3.982% | 2022-03-01 01:00
Guelph | 2021 | 1182109 | Replacement of Polymer Insulators - Various Locations | 99 | COMPLETE | N/A |  |  |  | Yes | Patenaude, Mélanie | Lauryssen, John | 0 | 91059.03 | 91059.03 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 495 | 571 | 76 | 15.35% | 2021-12-24 01:00
Guelph | 2021 | 1182189 | Block 25 Longfellow Ave - NiMa Trails Pumping Station | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 38666.69 | 36703.12 | -1963.57 | -5.078% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 132.4 | 96.5 | -35.9 | -27.11% | 2021-05-14
Guelph | 2021 | 1182711 | Montana Road - J0356Y Switch Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 16452.97 | 13540.78 | -2912.19 | -17.7% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 42 | 20 | -22 | -52.38% | 2021-06-11 01:00
Guelph | 2021 | 1182716 | Pleasant Rd - J0382R Switch Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 16452.97 | 15186.74 | -1266.23 | -7.696% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 42 | 32 | -10 | -23.81% | 2021-06-14 01:00
Guelph | 2021 | 1182717 | Western Avenue - 0253R Switch Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 16452.97 | 15343.59 | -1109.38 | -6.743% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 42 | 32 | -10 | -23.81% | 2021-06-15 01:00
Guelph | 2021 | 1183092 | Metcalfe Street - 0272Y Switch Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 23363.21 | 21481.9 | -1881.31 | -8.052% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 75.5 | 60 | -15.5 | -20.53% | 2021-07-23 01:00
Guelph | 2021 | 1183098 | Highview Place - 0336B Switch Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 20858.57 | 18278.91 | -2579.66 | -12.37% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 64 | 39 | -25 | -39.06% | 2021-06-21 01:00
Guelph | 2021 | 1183101 | Ridgewood Ave - 0254B Switch Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 0 | 26178.12 | 26178.12 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 78 | 78 |  | 2021-10-18 01:00
Guelph | 2021 | 1183103 | Glenburnie Drive - 0317Y Switch Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 0 | 26197.41 | 26197.41 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 75 | 75 |  | 2021-09-10 01:00
Guelph | 2021 | 1183104 | Kerr Street - 0347R Switch Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 0 | 23811.16 | 23811.16 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 79.7 | 79.7 |  | 2021-07-14 01:00
Guelph | 2021 | 1184128 | 25 Wellington St W | 99 | COMPLETE | N/A |  |  |  | No | Dyce, Stephen A | Stevens, Carl | 51195.17 | 10943.58 | -40251.59 | -78.62% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 79 | 72 | -7 | -8.861% | 2021-08-13 01:00
Guelph | 2021 | 1184255 | 415 Elizabeth Street | 99 | COMPLETE | N/A |  |  |  | No | Dyce, Stephen A | Stevens, Carl | 15766.15 | 20283.99 | 4517.84 | 28.66% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 57.64 | 59.5 | 1.86 | 3.227% | 2021-04-22
Guelph | 2022 | 1184336 | 27 Crestwood Place | 99 | COMPLETE | N/A |  |  |  | No | Dyce, Stephen A | Stevens, Carl | 3147.99 | 1853.19 | -1294.8 | -41.13% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 18 | 6 | -12 | -66.67% | 2022-01-27 01:00
Guelph | 2022 | 1185676 | Gosling Gardens 304 - 2021 Rogers Power Supply Connections | 99 | COMPLETE | N/A |  |  |  | No | South-West | Calvin Arsenault | 965.67 | 0 | -965.67 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6 | 6 |  | 2021-11-18 01:00
Guelph | 2021 | 1186551 | 350 Hanlon Creek Boulevard | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 64397.5 | 16972.88 | -47424.62 | -73.64% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 102.2 | 80 | -22.2 | -21.72% | 2021-11-18 01:00
Guelph | 2021 | 1186556 | 50 Golds Court | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 87550 | 111787.26 | 24237.26 | 27.68% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 104.5 | 104.5 |  | 2021-11-01 01:00
Guelph | 2021 | 1187356 | 49 Rhonda Road Townhome Rehab | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Stevens, Carl | 583504.65 | 660013.44 | 76508.79 | 13.11% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 597 | 1008.1 | 411.1 | 68.86% | 2021-12-06 01:00
Guelph | 2022 | 1187448 | 1533 Gordon Street | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 0 | 24198.86 | 24198.86 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 70.5 | 70.5 |  | 2022-01-10 01:00
Guelph | 2022 | 1187673 | 87 Cassino Ave | 99 | COMPLETE | N/A |  |  |  | No | Harrison, Eric | Calvin Arsenault | 7125.65 | 3778.85 | -3346.8 | -46.97% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 32 | 12.2 | -19.8 | -61.88% | 2022-01-27 01:00
Guelph | 2021 | 1187903 | Pole 73 Elmira Rd N - East of Independence Pl - Scadamate Switch | 99 | COMPLETE | N/A |  |  |  | No | Harrison, Eric | Manes, Bradley | 69395.46 | 70349.29 | 953.83 | 1.374% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 151 | 148.2 | -2.8 | -1.854% | 2021-07-30 01:00
Guelph | 2021 | 1187911 | 332 Gosling Gardens - South Mills Condo Bldg | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 12399.18 | 11588.72 | -810.46 | -6.536% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 24 | 18 | -6 | -25% | 2021-02-17 01:00
Guelph | 2021 | 1188012 | Pole 23 Mackenzie Street | 99 | COMPLETE | N/A |  |  |  | Yes | Consultant, NBM | Manes, Bradley | 5622.74 | 6514.42 | 891.68 | 15.86% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 37 | 21 | -16 | -43.24% | 2021-03-26 01:00
Guelph | 2021 | 1188014 | pole 6 Hanlon Road | 99 | COMPLETE | N/A |  |  |  | Yes | Consultant, NBM | Manes, Bradley | 13283.03 | 11111.65 | -2171.38 | -16.35% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 67 | 46 | -21 | -31.34% | 2021-04-30
Guelph | 2021 | 1188015 | Pole 12 Dennis St, Rockwood | 99 | COMPLETE | N/A |  |  |  | Yes | Consultant, NBM | Manes, Bradley | 11537.12 | 15983.81 | 4446.69 | 38.54% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 62.5 | 59 | -3.5 | -5.6% | 2021-10-18 01:00
Guelph | 2021 | 1188019 | Pole 1 Bridge Street, Roockwood | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 7245.14 | 7775.39 | 530.25 | 7.319% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 46.5 | 38 | -8.5 | -18.28% | 2021-08-26 01:00
Guelph | 2021 | 1189028 | Forest Street - LIS L0850 Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Lauryssen, John | 78661.94 | 104588.26 | 25926.32 | 32.96% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 337 | 305.5 | -31.5 | -9.347% | 2021-07-30 01:00
Guelph | 2021 | 1190278 | Pole 4 Heather Ave | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 10166.47 | 6310.84 | -3855.63 | -37.92% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 61 | 23 | -38 | -62.3% | 2021-06-01 01:00
Guelph | 2021 | 1190839 | Third Party Transfer - Rogers - 73 Elmira Road North | 99 | COMPLETE | N/A |  |  |  | No | Harrison, Eric | Manes, Bradley | 5167.18 | 2612.1 | -2555.08 | -49.45% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 14 | 8 | -6 | -42.86% | 2021-06-25 01:00
Guelph | 2022 | 1193004 | 990 York Road | 99 | COMPLETE | N/A |  |  |  | No | Danieli, Andrea | Stevens, Carl | 0 | 11449.33 | 11449.33 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 31 | 39 | 8 | 25.81% | 2022-01-27 01:00
Guelph | 2021 | 1193314 | P-Algoma Drive (off Monana Road) | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 144689 | 162764.04 | 18075.04 | 12.49% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 733 | 649.9 | -83.1 | -11.34% | 2021-11-29 01:00
Guelph | 2022 | 1193333 | P-Riverview Drive and Wolseley Road | 99 | COMPLETE | N/A |  |  |  | Yes | Consultant, NBM | Manes, Bradley | 170346.64 | 1035.04 | -169311.6 | -99.39% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 778.5 | 1278.8 | 500.3 | 64.26% | 2021-10-04 01:00
Guelph | 2021 | 1193519 | P-601 /ekmira Road North/GUE/NS/1Ph UG SEC SERVICE | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 5931.11 | 6785.44 | 854.33 | 14.4% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 34 | 17.5 | -16.5 | -48.53% | 2021-10-04 01:00
Guelph | 2022 | 1193576 | 576 Woolwich Street | 99 | CANCELLED | N/A |  |  |  | No | Dyce, Stephen A | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-10-04 01:00
Guelph | 2022 | 1193782 | 18 Industrial Street/GUE/NS/3PH SEC SERVICE | 99 | COMPLETE | N/A |  |  |  | No | Danieli, Andrea | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-10-04 01:00
Guelph | 2021 | 1194148 | 65 Lemon St | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 6000 | 4867.24 | -1132.76 | -18.88% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7.5 | 7.5 |  | 2021-10-04 01:00
Guelph | 2021 | 1194611 | Governors Rd & Malcolm Rd | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Lauryssen, John | 21385.51 | 27470.51 | 6085 | 28.45% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 125.5 | 91.1 | -34.4 | -27.41% | 2021-08-20 01:00
Guelph | 2022 | 1194613 | 19 Dormie Lane | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 7391.92 | 4613.78 | -2778.14 | -37.58% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 0 | -9 | -100% | 2021-12-31 01:00
Guelph | 2022 | 1195678 | P-100 Victoria Road South / GUE / NS | 99 | COMPLETE | N/A |  |  |  | No | Danieli, Andrea | Stevens, Carl | 370.5 | 0 | -370.5 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 47 | 27.7 | -19.3 | -41.06% | 2021-08-20 01:00
Guelph | 2022 | 1196115 | P-27 Vanier Drive / GUE / NS / 1PH UG Service | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-20 01:00
Guelph | 2021 | 1196263 | Pole 15 Arthur St S - anchor relocation only - customer capital work | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Manes, Bradley | 3990.4 | 4385.81 | 395.41 | 9.909% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 23.5 | 23 | -0.5 | -2.128% | 2021-08-20 01:00
Guelph | 2021 | 1196963 | P-207 Metcalfe Street / GUE / UP / 1PH Pole Mounted Tranformer | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Manes, Bradley | 4376.45 | 2468.95 | -1907.5 | -43.59% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 20 | 8 | -12 | -60% | 2021-10-08 01:00
Guelph | 2021 | 1197821 | P-27 Norwich Street East / GUE / NS / 1PH UG SEC SERVICE | 99 | COMPLETE | N/A |  |  |  | Yes | McIntyre, Max | Stevens, Carl | 11833.2 | 10717.91 | -1115.29 | -9.425% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 22 | 27 | 5 | 22.73% | 2021-11-01 01:00
Guelph | 2022 | 1198303 | P-Temp OH Service - 15 Harcourt Dr / GUE / NS / 1PH OH TEMP SEC SERVICE | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1198393 | P-505 Kortright Road West / GUE / NS | 99 | COMPLETE | N/A |  |  |  | No | Joshi, Namrata | Stevens, Carl | 2210 | 5754.91 | 3544.91 | 160.4% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 11 | 42 | 31 | 281.8% | 2021-12-31 01:00
Guelph | 2022 | 1198394 | P-505 Kortright Road West / GUE /NS | 99 | COMPLETE | N/A |  |  |  | No | Joshi, Namrata | Stevens, Carl | 2259.85 | 0 | -2259.85 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 12 | 0 | -12 | -100% | 2021-12-31 01:00
Guelph | 2021 | 1199111 | Harts Lane West (off Gordon Street) | 99 | COMPLETE | N/A |  |  |  | Yes | Consultant, NBM | Lauryssen, John | 9553 | 17690 | 8137 | 85.18% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 155 | 134 | -21 | -13.55% | 2021-09-09 01:00
Guelph | 2021 | 1199375 | P-Pole 308 Edinburgh Rd S | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 4544 | 6370 | 1826 | 40.18% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 49 | 31 | -18 | -36.73% | 2021-06-01 01:00
Guelph | 2021 | 1199395 | P-Pole 121 College Ave | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 14999.62 | 10221 | -4778.62 | -31.86% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 66 | 79 | 13 | 19.7% | 2021-09-13 01:00
Guelph | 2021 | 1200968 | P-82 Creighton Ave/GUE/NS/1PH UG SEC Relocation | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 1286 | 2059 | 773 | 60.11% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 9 | 1 | 12.5% | 2021-06-09 01:00
Guelph | 2021 | 1201533 | P-120 Gzowski St / ROC / NS / 1PH UG Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 3183.37 | 1500 | -1683.37 | -52.88% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10 | 8 | -2 | -20% | 2021-10-04 01:00
Guelph | 2022 | 1201695 | 41 Richardson St / GUE / UP / 1PH Polemounted TX Upgrade | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Manes, Bradley | 1868 | 0 | -1868 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 20 | 0 | -20 | -100% | 2021-12-31 01:00
Guelph | 2022 | 1202625 | P-Temp OH Service - 10 Winston Cres/GUE/NS/1PH SEC Temp Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2021 | 1202771 | P-Golfview Rd - 0293B Switch Replacement Project | 99 | COMPLETE | N/A |  |  |  | No | Harrison, Eric | Lauryssen, John | 22401 | 16033 | -6368 | -28.43% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 71 | 60 | -11 | -15.49% | 2021-07-30 01:00
Guelph | 2021 | 1203593 | P-Pole 94 Downey Road | 99 | COMPLETE | N/A |  |  |  | Yes | South-West | Manes, Bradley | 6059.48 | 3280 | -2779.48 | -45.87% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 33 | 25 | -8 | -24.24% | 2021-08-05 01:00
Guelph | 2021 | 1203921 | Ironwood Rd 311 - BK0203 TX Replacement | 99 | COMPLETE | N/A |  |  |  | No | Jamkodjian, Cassandra | Stevens, Carl | 6843.54 | 5311 | -1532.54 | -22.39% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 16 | 16 | 0 | 0% | 2021-11-19 01:00
Guelph | 2022 | 1203952 | P-188 Niska Rd / GUE / NS / 1PH UG Secondary Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 2999.96 | 287.48 | -2712.48 | -90.42% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 1 | -8 | -88.89% | 2021-11-30 01:00
Guelph | 2022 | 1203959 | P-523 Kortright Rd W / GUE / NS / 1PH Sec Temp Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 1773.72 | 0 | -1773.72 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | -8 | -100% | 2021-11-30 01:00
Guelph | 2021 | 1204022 | Ptarmigan Dr 60 Unit 8 - BK04730 TX Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Jamkodjian, Cassandra | Stevens, Carl | 6843.54 | 6694.59 | -148.95 | -2.177% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 16 | 16 | 0 | 0% | 2021-11-19 01:00
Guelph | 2022 | 1204023 | P-Nima Trails Blk 122 - Shakespeare Dr / GUE / NS | 99 | CANCELLED | N/A |  |  |  | No | Joshi, Namrata | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-10 01:00
Guelph | 2021 | 1204762 | P-171 Lou's Blvd Rockwood - BK80294 TX Replacement | 99 | COMPLETE | N/A |  |  |  | No | Jamkodjian, Cassandra | Stevens, Carl | 6179 | 5550.44 | -628.56 | -10.17% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 16 | 12 | -4 | -25% | 2021-12-10 01:00
Guelph | 2021 | 1205068 | P-Gryphon Place Cable Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Harrison, Eric | Stevens, Carl | 0 | 29569.77 | 29569.77 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 47.5 | 47.5 |  | 2021-10-04 01:00
Guelph | 2022 | 1205160 | Stevenson St. N.- Pole Hold | 99 | COMPLETE | N/A |  |  |  | No | South-West | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1205239 | P-Temp OH Service - 54 Phelan Crt / GUE / NS / OH Temp | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Manes, Bradley | 4851.65 | 0 | -4851.65 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 16.3 | 0 | -16.3 | -100% | 2022-01-03 01:00
Guelph | 2022 | 1205242 | P-Temp OH Service - 100 Victoria Rd S / GUE / NS / OH Temp | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1205333 | P-1657 Gordon St / GUE / NS / 1PH SEC Temp Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 1983.12 | 0 | -1983.12 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 12.6 | 0 | -12.6 | -100% | 2021-12-31 01:00
Guelph | 2022 | 1205793 | P-25 Poppy Dr / GUE / UP | 99 | COMPLETE | N/A |  |  |  | No | Joshi, Namrata | Stevens, Carl | 13357.78 | -14632.18 | -27989.96 | -209.5% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 35 | 18 | -17 | -48.57% | 2022-02-11 01:00
Guelph | 2022 | 1205794 | 1219 Edinburgh Rd S-Resupply Rogers Box from Secondary Bus | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Lauryssen, John | 6170.6 | 0 | -6170.6 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 41 | 32 | -9 | -21.95% | 2021-12-13 01:00
Guelph | 2022 | 1205876 | P-24 Corporate Crt-PMSG024 Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Jamkodjian, Cassandra | Stevens, Carl | 85124.09 | 97979.53 | 12855.44 | 15.1% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 85.5 | 109 | 23.5 | 27.49% | 2022-01-31 01:00
Guelph | 2022 | 1205880 | P-44 Corporate Crt-PMSG025 Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Jamkodjian, Cassandra | Stevens, Carl | 88807.7 | 104272.7 | 15465 | 17.41% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 114 | 91 | -23 | -20.18% | 2022-01-31 01:00
Guelph | 2022 | 1206187 | Main St N, Rockwood | 99 | COMPLETE | N/A |  |  |  | No | Jamkodjian, Cassandra | Calvin Arsenault | 0 | 10187.07 | 10187.07 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 53.2 | 53.2 |  | 2022-01-27 01:00
Guelph | 2022 | 1206278 | P-145 Speedvale Ave W/GUE/UP | 99 | CANCELLED | N/A |  |  |  | No | Joshi, Namrata | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-28
Guelph | 2022 | 1206587 | P-Dormie Lane to Pole R23 | 99 | COMPLETE | N/A |  |  | Bolton, Ian | No | Consultant, NBM | Lauryssen, John | 175324.78 | 206067.39 | 30742.61 | 17.53% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 754 | 957.75 | 203.75 | 27.02% | 2022-03-28
Guelph | 2022 | 1206826 | Arthur St S and Elizabeth St/GUE/NS/1PH Sec Temp Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 1815.71 | 0 | -1815.71 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 11.4 | 0 | -11.4 | -100% | 2021-12-31 01:00
Guelph | 2021 | 1206827 | P-6 Mayfield Ave/GUE/UP/1 PH UG Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 6068.34 | 4741.56 | -1326.78 | -21.86% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 11 | 6 | -5 | -45.45% | 2021-10-04 01:00
Guelph | 2022 | 1207266 | York Rd.- Pole Hold | 99 | COMPLETE | N/A |  |  |  | No | South-West | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-10-15 01:00
Guelph | 2021 | 1207371 | P-Pole 12 Powell St W | 99 | COMPLETE | N/A |  |  |  | No | Consultant, NBM | Manes, Bradley | 0 | 17135.79 | 17135.79 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 87.5 | 87.5 |  | 2021-10-15 01:00
Guelph | 2021 | 1208145 | P-Lowes Rd Pole 11 | 99 | COMPLETE | N/A |  |  |  | No | South-West | Manes, Bradley | 275 | 2809.51 | 2534.51 | 921.6% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 20 | 32 | 12 | 60% | 2021-07-28 01:00
Guelph | 2021 | 1208535 | 101 Cooper Drive Temp / GUE / NS | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Manes, Bradley | 43838.39 | 0 | -43838.39 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 87.84 | 62 | -25.84 | -29.42% | 2021-12-31 01:00
Guelph | 2021 | 1208975 | P-Pole 8 Maltby Rd E | 99 | COMPLETE | N/A |  |  |  | Yes | South-West | Manes, Bradley | 6061.87 | 8100.58 | 2038.71 | 33.63% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 33 | 44.5 | 11.5 | 34.85% | 2021-08-06 01:00
Guelph | 2021 | 1208982 | P-Pole 111 Victoria Rd S | 99 | COMPLETE | N/A |  |  |  | No | South-West | Manes, Bradley | 6331.87 | 6128.94 | -202.93 | -3.205% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 34.5 | 30 | -4.5 | -13.04% | 2021-08-20 01:00
Guelph | 2021 | 1209366 | P-70 Division St - BK01431 Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Jamkodjian, Cassandra | Stevens, Carl | 83412.39 | 84397.53 | 985.14 | 1.181% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 133.5 | 193.5 | 60 | 44.94% | 2021-12-31 01:00
Guelph | 2022 | 1211397 | P-370 Stone Rd W/GUE/UP | 99 | COMPLETE | N/A |  |  |  | No | Dyce, Stephen A | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 35 | 0 | -35 | -100% | 2022-01-27 01:00
Guelph | 2022 | 1211706 | 313 Metcalfe St/GUE/UP/1ph TX Upgrade | 99 | COMPLETE | N/A |  |  |  | No | South-West | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | -8 | -100% | 2022-01-27 01:00
Guelph | 2022 | 1211855 | 7 Stevenson St N/GUE/NS/1 PH UG Temp Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 1559.14 | 339.82 | -1219.32 | -78.2% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 3.5 | -4.5 | -56.25% | 2022-01-27 01:00
Guelph | 2021 | 1213533 | 68 Cheltonwood Ave/GUE/UP/1 PH TX Upgrade | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 3623.91 | 7385.98 | 3762.07 | 103.8% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 14 | 23.5 | 9.5 | 67.86% | 2021-09-14 01:00
Guelph | 2021 | 1213536 | P-Pole 86 Waverley Dr | 99 | COMPLETE | N/A |  |  |  | Yes | Consultant, NBM | Manes, Bradley | 8887.67 | 13915.15 | 5027.48 | 56.57% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 51 | 81 | 30 | 58.82% | 2021-10-15 01:00
Guelph | 2021 | 1214056 | P-In Front of 28 Crane St - UD284 Vault Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Patenaude, Mélanie | Stevens, Carl | 31158 | 46973.3 | 15815.3 | 50.76% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 67 | 93.5 | 26.5 | 39.55% | 2021-11-19 01:00
Guelph | 2021 | 1214058 | Across the road from 97 Gosling Dr (Right beside bus stop) - UD276 Vault Replacement | 99 | COMPLETE | N/A |  |  |  | yes | Patenaude, Mélanie | Stevens, Carl | 5771.99 | 3053.2 | -2718.79 | -47.1% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2 | 2.5 | 0.5 | 25% | 2021-12-31 01:00
Guelph | 2022 | 1214059 | P-In Front of 288 Starwood Dr - UD598 Vault Replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Patenaude, Mélanie | Stevens, Carl | 37242.61 | 74625.21 | 37382.6 | 100.4% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 163.4 | 242.5 | 79.1 | 48.41% | 2022-01-14 01:00
Guelph | 2022 | 1214061 | P-165 Emma St/GUE/UP/1 PH Service Upgrade | 99 | COMPLETE | N/A |  |  |  | No | South-West | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-12 01:00
Guelph | 2022 | 1214242 | P-262 Main St S/ROC/UP/1PH Commercial Isolation | 99 | COMPLETE | N/A |  |  |  | No | South-West | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 | 4 |  | 2021-11-12 01:00
Guelph | 2021 | 1214243 | Pole 13 Maltby Rd W | 99 | COMPLETE | N/A |  |  |  | yes | Dyce, Stephen A | Manes, Bradley | 0 | 3950 | 3950 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 38 | 29 | -9 | -23.68% | 2021-11-12 01:00
Guelph | 2021 | 1215073 | 32 Pondview Cres/GUE/UP/1PH TX Upgrade | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 3046.49 | 5806.91 | 2760.42 | 90.61% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 11.5 | 3.5 | 43.75% | 2021-09-17 01:00
Guelph | 2022 | 1216254 | 166 College Ave W/GUE/SR/3PH Primary Service Removal | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 1605.9 | 4414.5 | 2808.6 | 174.9% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4 | 32 | 28 | 700% | 2022-01-27 01:00
Guelph | 2022 | 1216257 | 176 College Ave W/GUE/SR/1 PH Service Removal | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 2006.82 | 2315.82 | 309 | 15.4% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4 | 12 | 8 | 200% | 2022-02-11 01:00
Guelph | 2022 | 1218544 | P-12 Shallmar Crt/GUE/UP/1 PH Pad TX Upgrade | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 2935.21 | 6603.01 | 3667.8 | 125% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 34 | 12 | -22 | -64.71% | 2022-01-27 01:00
Guelph | 2022 | 1218546 | P-200 Hanlon Creek Blvd | 99 | CANCELLED | N/A |  |  |  | No | South-West | Stevens, Carl | 73924.31 | 586.64 | -73337.67 | -99.21% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3201.99 | 6 | -3195.99 | -99.81% | 2022-02-25 01:00
Guelph | 2022 | 1226277 | 67 Vancouver Dr/GUE/UP/1PH TX Upgrade | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 3102.1 | 792.05 | -2310.05 | -74.47% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 6 | -2 | -25% | 2022-01-03 01:00
Guelph | 2021 | 1227763 | P-9 King Edward Pl | 99 | COMPLETE | N/A |  |  |  | Yes | Jamkodjian, Cassandra | Stevens, Carl | 6344.77 | 31530.83 | 25186.06 | 397% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 15.5 | 7.5 | 93.75% | 2021-11-30 01:00
Guelph | 2022 | 1228452 | P-2071 Gordon St/GUE/UP/1 PH Secondary UG Conversion | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-02-28 01:00
Guelph | 2022 | 1230395 | 14 Jane St/GUE/NS/1 PH OH Temp Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | -72.94 | -72.94 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | -1 | -1 |  | 2022-02-28 01:00
Guelph | 2022 | 1230398 | Downey Rd & Woodland Glen Dr/GUE/NS/NEW OH Sec Span | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Manes, Bradley | 0 | 2440.89 | 2440.89 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 10.5 | 10.5 |  | 2022-02-28 01:00
Guelph | 2022 | 1231368 | Heath Rd - Replacement of Existing UG Services | 99 | COMPLETE | N/A |  |  |  | No | South-West | Stevens, Carl | 90916.33 | 45662.35 | -45253.98 | -49.78% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 49 | 168.5 | 119.5 | 243.9% | 2022-03-11 01:00
Guelph | 2022 | 1231743 | Lewis Rd SCADAMate R0780 Installation | 99 | COMPLETE | N/A |  |  |  | Yes | South-West | Lauryssen, John | 57559.65 | 56336.22 | -1223.43 | -2.125% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 88 | 73.5 | -14.5 | -16.48% | 2022-01-31 01:00
Guelph | 2022 | 1231744 | Lewis Rd SCADAMate R0781 Installation | 99 | COMPLETE | N/A |  |  |  | Yes | South-West | Manes, Bradley | 57559.65 | 53293.23 | -4266.42 | -7.412% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 88 | 50 | -38 | -43.18% | 2022-04-08
Guelph | 2022 | 1231875 | P-51 Woodlawn Rd W/GUE/UP/1PH Meter Relocation | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1232849 | P-138 College Ave W/GUE/UP/Commercial Isolation | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 0 | 1188.03 | 1188.03 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 | 4 |  | 2021-12-31 01:00
Guelph | 2022 | 1233085 | P-675 Victoria Rd N/GUE/NS/1PH Temp Service | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1234019 | 18 Vista Terrace/GUE/UP/1PH TX Upgrade | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 4045.44 | 4662.4 | 616.96 | 15.25% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 12 | 3 | 33.33% | 2021-12-31 01:00
Guelph | 2022 | 1234692 | Young St Pole 3 | 99 | COMPLETE | N/A |  |  |  | yes | Consultant, NBM | Manes, Bradley | 2201.85 | 2056.31 | -145.54 | -6.61% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 13.5 | 8.5 | -5 | -37.04% | 2021-12-31 01:00
Guelph | 2022 | 1234837 | P-Joint Use Transfer-Bell-Inkerman,Hearn,Chadwick,Allan,St Arnaud | 99 | COMPLETE | N/A |  |  |  | No | South-West | Stevens, Carl | 0 | 6566.19 | 6566.19 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 26 | 26 |  | 2021-12-31 01:00
Guelph | 2022 | 1236307 | 35 Miller St/GUE/UP/1PH Pad TX Upgrade | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 8604.68 | 0 | -8604.68 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | -25 | -100% | 2021-12-31 01:00
Guelph | 2022 | 1236937 | 6 Mayfield Ave/GUE/UP/1 PH UG Service Additional Charges | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | 501.37 | 501.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1236938 | P-363 Elizabeth St/GUE/UP/Commercial Service Isolation | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 0 | 525.88 | 525.88 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 | 4 |  | 2021-12-31 01:00
Guelph | 2022 | 1237738 | 120 Country Club Drive Townhomes Rehab | 99 | COMPLETE | N/A |  |  |  | No | Harrison, Eric | Calvin Arsenault | 0 | 1647.81 | 1647.81 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1237757 | 82 Creighton Ave/GUE/NS/1PH UG SEC Relocation 2022 Charges | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | 556.28 | 556.28 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1238253 | 415 Elmira Rd - Emergency PMSG063 Replacement | 99 | COMPLETE | N/A |  |  |  | No | Jamkodjian, Cassandra | Calvin Arsenault | 0 | 35603.39 | 35603.39 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 80.5 | 80.5 |  | 2021-12-31 01:00
Guelph | 2022 | 1239939 | 55 Baker St/GUE/NS/1 PH OH Temp Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Manes, Bradley | 0 | 250.85 | 250.85 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2021-12-31 01:00
Guelph | 2022 | 1240661 | Hammond Manufacturing - 394 Edinburgh Rd N | 99 | COMPLETE | N/A |  |  |  | No | South-West | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1241767 | 735 Woolwich Street - New Office Building | 99 | COMPLETE | N/A |  |  |  | No | Dyce, Stephen A | Stevens, Carl | 0 | 3213.87 | 3213.87 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1242267 | 265 Woodlawn Rd W/GUE/NS/1PH OH Temp Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-31 01:00
Guelph | 2022 | 1244430 | Secondary Cable Replacement - 14 Mountford Dr | 99 | COMPLETE | N/A |  |  |  | No | South-West | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-02
Guelph | 2022 | 1244493 | 710 Woolwich St/GUE/NS/1PH OH TEMP Service | 99 | COMPLETE | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-02
Guelph | 2022 | 1246619 | 731 Woolwich St. | 99 | COMPLETE | N/A |  |  |  | No | Dyce, Stephen A | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-02
Guelph | 2022 | 1246632 | 98 Farley Drive - Urban Lofts | 99 | CANCELLED | N/A |  |  |  | No | Dyce, Stephen A | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-23 01:00
Guelph | 2022 | 1247456 | P- 142 Brant Ave / GUE / UP / 1PH Rogers Power supply connection | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-23 01:00
Guelph | 2022 | 1247865 | 39 Oak St. / GUE / NS / 1PH OH Temp Service | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Stevens, Carl | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-23 01:00
Guelph | 2022 | 1247897 | P-12 Wyndham St N / GUE / UP / Commercial Service Isolation | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-23 01:00
Guelph | 2022 | 1247913 | P- 20 Stevenson St S / GUE / UP / Commercial Service Isolation | 99 | CANCELLED | N/A |  |  |  | No | McIntyre, Max | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-23 01:00
Guelph | 2022 | 646230 | P-455 Watson Parkway North / GUE / NS | 95 | COMPLETE | N/A |  |  | McGregor, Brendan | No | Dyce, Stephen A | Stevens, Carl | 99076.28 | 77555.76 | -21520.52 | -21.72% | 0 | 17650.66 | 17650.66 |  | 0 | 52769.43 | 52769.43 |  | 0 | 3811.59 | 3811.59 |  | 0 | 3324.08 | 3324.08 |  | 259.6 | 202 | -57.6 | -22.19% | 2021-12-31 01:00
Guelph | 2022 | 646232 | P-Maple St (from Forest St to L0199) | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Chris McDonald | Lauryssen, John | 45706.17 | 194283.11 | 148576.94 | 325.1% | 0 | 84506.57 | 84506.57 |  | 0 | 46645.19 | 46645.19 |  | 0 | 23231.47 | 23231.47 |  | 0 | 39899.88 | 39899.88 |  | 477.5 | 900.5 | 423 | 88.59% | 2022-03-28
Guelph | 2022 | 646234 | 396-398 Silvercreek Pkwy N / GUE / UP | 95 | COMPLETE | N/A |  |  | McAlpine, Robert | No | Dyce, Stephen A | Stevens, Carl | 63584.93 | 52489.21 | -11095.72 | -17.45% | 0 | 6456.23 | 6456.23 |  | 0 | 32792.42 | 32792.42 |  | 0 | 1913.42 | 1913.42 |  | 0 | 11327.14 | 11327.14 |  | 160.28 | 72.5 | -87.78 | -54.77% | 2022-05-13 01:00
Guelph | 2022 | 646235 | P-Dawson Rd - SCADAMate R0155 | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Harrison, Eric | Lauryssen, John | 68274.89 | 75587.57 | 7312.68 | 10.71% | 0 | 10388.48 | 10388.48 |  | 0 | 58692.3 | 58692.3 |  | 0 | 5200.54 | 5200.54 |  | 0 | 1306.25 | 1306.25 |  | 144.25 | 105.25 | -39 | -27.04% | 2022-07-26 01:00
Guelph | 2022 | 646236 | P-Pole 9 Manor Park Cres | 95 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | South-West | Manes, Bradley | 17078 | 20823.58 | 3745.58 | 21.93% | 0 | 7833.38 | 7833.38 |  | 0 | 5350.28 | 5350.28 |  | 0 | 3734.02 | 3734.02 |  | 0 | 3905.9 | 3905.9 |  | 84.9 | 76 | -8.9 | -10.48% | 2022-06-27 01:00
Guelph | 2022 | 646239 | P-Hayes Ave (South of York Rd) | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Chris McDonald | Lauryssen, John | 88276.01 | 121172.48 | 32896.47 | 37.27% | 0 | 47756.65 | 47756.65 |  | 0 | 31325.4 | 31325.4 |  | 0 | 21983.48 | 21983.48 |  | 0 | 20106.95 | 20106.95 |  | 488 | 495 | 7 | 1.434% | 2022-10-31 01:00
Guelph | 2022 | 646242 | P-1 Mont St/GUE/NS | 95 | COMPLETE | N/A |  |  | McAlpine, Robert | No | South-West | Stevens, Carl | 39904.1 | 42556.68 | 2652.58 | 6.647% | 0 | 7387.51 | 7387.51 |  | 0 | 10752.47 | 10752.47 |  | 0 | 1773.58 | 1773.58 |  | 0 | 22643.12 | 22643.12 |  | 87.08 | 58 | -29.08 | -33.39% | 2022-05-19 01:00
Guelph | 2022 | 646243 | P-In Front of 110 Municipal St - UD558 Vault Replacement | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Patenaude, Mélanie | Stevens, Carl | 5945 | 11012.84 | 5067.84 | 85.25% | 0 | 2067.01 | 2067.01 |  | 0 | 1805.66 | 1805.66 |  | 0 | 264.39 | 264.39 |  | 0 | 6875.78 | 6875.78 |  | 2 | 11 | 9 | 450% | 2022-07-18 01:00
Guelph | 2022 | 646244 | P-In Front of 150 Woolwich St- UD169 Vault Replacement | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Patenaude, Mélanie | Stevens, Carl | 8993 | 10642.33 | 1649.33 | 18.34% | 0 | 1492.47 | 1492.47 |  | 0 | 1755.65 | 1755.65 |  | 0 | 143.09 | 143.09 |  | 0 | 7251.12 | 7251.12 |  | 8 | 4 | -4 | -50% | 2022-05-25 01:00
Guelph | 2022 | 646245 | P-In Front of 215 Woolwich St - UD172 Sidewalk Vault Repair | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Patenaude, Mélanie | Stevens, Carl | 9362.91 | 9656.06 | 293.15 | 3.131% | 0 | 1040.51 | 1040.51 |  | 0 | 1680.96 | 1680.96 |  | 0 | 0 | 0 |  | 0 | 6934.59 | 6934.59 |  | 8 | 0 | -8 | -100% | 2022-04-11
Guelph | 2022 | 646247 | 203 Main St S, Rockwood - BK 80282 Replacement | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Jamkodjian, Cassandra | Stevens, Carl | 3770.87 | 5080 | 1309.13 | 34.72% | 0 | 1639.05 | 1639.05 |  | 0 | 2558.91 | 2558.91 |  | 0 | 299.64 | 299.64 |  | 0 | 582.4 | 582.4 |  | 16 | 13 | -3 | -18.75% | 2022-07-19 01:00
Guelph | 2022 | 646248 | 121 Bagot St - Townhomes Rehab | 99 | ANALYZE |  |  |  | Bolton, Ian J | Yes | Harrison, Eric | Stevens, Carl | 671843.48 | 713898.28 | 42054.8 | 6.26% | 0 | 119565.73 | 119565.73 |  | 0 | 113884.39 | 113884.39 |  | 0 | 42278.17 | 42278.17 |  | 0 | 438169.99 | 438169.99 |  | 888.75 | 1167.75 | 279 | 31.39% | 2022-12-12 01:00
Guelph | 2022 | 646250 | Forest St, Foreshill Dr & Wolfond Cres Rebuild | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Chris McDonald | Manes, Bradley | 194590.04 | 330325.43 | 135735.39 | 69.75% | 0 | 137538.95 | 137538.95 |  | 0 | 96638.45 | 96638.45 |  | 0 | 49682.3 | 49682.3 |  | 0 | 46465.73 | 46465.73 |  | 955.5 | 1416.5 | 461 | 48.25% | 2022-06-09 01:00
Guelph | 2022 | 646251 | Beverley St (Morris St to Johnston St) & Harris St | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Chris McDonald | Lauryssen, John | 93961.89 | 103215.7 | 9253.81 | 9.848% | 0 | 41688.91 | 41688.91 |  | 0 | 28092.11 | 28092.11 |  | 0 | 10995.49 | 10995.49 |  | 0 | 22439.19 | 22439.19 |  | 1419 | 452.25 | -966.75 | -68.13% | 2022-04-01
Guelph | 2022 | 646253 | Stevenson St N & Kensington St Rebuild | 95 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | South-West | Lauryssen, John | 208595.22 | 327941.68 | 119346.46 | 57.21% | 0 | 129067.02 | 129067.02 |  | 0 | 92341.53 | 92341.53 |  | 0 | 71227.38 | 71227.38 |  | 0 | 35305.75 | 35305.75 |  | 1019.8 | 1347.25 | 327.45 | 32.11% | 2022-10-19 01:00
Guelph | 2022 | 646255 | 505 Southgate Dr - BK06334 Replacement | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Jamkodjian, Cassandra | Stevens, Carl | 22173.71 | 20841.5 | -1332.21 | -6.008% | 0 | 1564.57 | 1564.57 |  | 0 | 18749.15 | 18749.15 |  | 0 | 527.78 | 527.78 |  | 0 | 0 | 0 |  | 40 | 15 | -25 | -62.5% | 2022-10-31 01:00
Guelph | 2022 | 646256 | 1030 Gordon St - BK05073 Replacement | 99 | COMPLETE | Under 10% |  |  | Bolton, Ian J | Yes | Jamkodjian, Cassandra | Stevens, Carl | 22173.71 | 21892.16 | -281.55 | -1.27% | 0 | 1508.62 | 1508.62 |  | 0 | 19490.37 | 19490.37 |  | 0 | 893.17 | 893.17 |  | 0 | 0 | 0 |  | 40 | 18 | -22 | -55% | 2022-11-21 01:00
Guelph | 2022 | 646257 | 247 Eramosa Rd - BK05054 Replacement | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Jamkodjian, Cassandra | Stevens, Carl | 18850.91 | 16587.47 | -2263.44 | -12.01% | 0 | 1465.49 | 1465.49 |  | 0 | 14497.98 | 14497.98 |  | 0 | 624 | 624 |  | 0 | 0 | 0 |  | 40 | 17.5 | -22.5 | -56.25% | 2022-10-18 01:00
Guelph | 2022 | 646260 | P-7 Quebec St - Manhole Lid Replacement (MHS10010) | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Patenaude, Mélanie | Stevens, Carl | 9036.23 | 12352.19 | 3315.96 | 36.7% | 0 | 2505.07 | 2505.07 |  | 0 | 0 | 0 |  | 0 | 246.41 | 246.41 |  | 0 | 9600.71 | 9600.71 |  | 4 | 11.5 | 7.5 | 187.5% | 2022-12-12 01:00
Guelph | 2022 | 646261 | P-75 Walnut Dr-UD Vault Lid Replacement (UD303) | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Patenaude, Mélanie | Stevens, Carl | 8548.39 | 11641.6 | 3093.21 | 36.18% | 0 | 1622.85 | 1622.85 |  | 0 | 1755.65 | 1755.65 |  | 0 | 143.09 | 143.09 |  | 0 | 8120.01 | 8120.01 |  | 6 | 4 | -2 | -33.33% | 2022-05-25 01:00
Guelph | 2022 | 646262 | P-200 Woolwich St - UD Vault Lid Replacement (UD171) | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Patenaude, Mélanie | Stevens, Carl | 8548.39 | 6512.52 | -2035.87 | -23.82% | 0 | 946.15 | 946.15 |  | 0 | 1680.96 | 1680.96 |  | 0 | 143.09 | 143.09 |  | 0 | 3742.32 | 3742.32 |  | 6 | 4 | -2 | -33.33% | 2022-04-11
Guelph | 2022 | 646263 | P-Vancouver Dr & Edmonton Dr - Pole Line RC | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Harrison, Eric | Manes, Bradley | 319000 | 321534.79 | 2534.79 | 0.7946% | 0 | 139909.07 | 139909.07 |  | 0 | 107275.4 | 107275.4 |  | 0 | 48894.26 | 48894.26 |  | 319000 | 25456.06 | -293543.94 | -92.02% | 1000 | 1515.5 | 515.5 | 51.55% | 2022-07-08 01:00
Guelph | 2022 | 646264 | 30 Hanlon Creek Blvd/GUE/NS | 95 | COMPLETE | N/A |  |  | McAlpine, Robert | No | South-West | Stevens, Carl | 101522.21 | 96225.9 | -5296.31 | -5.217% | 0 | 7444.67 | 7444.67 |  | 0 | 75296.27 | 75296.27 |  | 0 | 3822.03 | 3822.03 |  | 0 | 9662.93 | 9662.93 |  | 135.4 | 67 | -68.4 | -50.52% | 2022-12-05 01:00
Guelph | 2022 | 646267 | Pole 153 & 155 Speedvale Ave W Replacement | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | No | South-West | Manes, Bradley | 22740 | 59429.64 | 36689.64 | 161.3% | 0 | 12781.16 | 12781.16 |  | 0 | 15410.55 | 15410.55 |  | 0 | 4406.22 | 4406.22 |  | 0 | 26831.71 | 26831.71 |  | 66 | 137.5 | 71.5 | 108.3% | 2022-04-14
Guelph | 2022 | 646268 | Speedvale Ave W SCADAMate R0110 Installation | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | South-West | Manes, Bradley | 57559.65 | 56190.22 | -1369.43 | -2.379% | 0 | 5873.56 | 5873.56 |  | 0 | 48762.82 | 48762.82 |  | 0 | 1553.84 | 1553.84 |  | 0 | 0 | 0 |  | 88 | 64 | -24 | -27.27% | 2022-03-28
Guelph | 2022 | 646269 | P-Imperial Rd N LIS L0817 Replacement | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Harrison, Eric | Lauryssen, John | 1504.8 | 32028.5 | 30523.7 | 2028% | 0 | 10041.85 | 10041.85 |  | 0 | 16219.91 | 16219.91 |  | 0 | 4319.22 | 4319.22 |  | 0 | 1447.52 | 1447.52 |  | 0 | 102.5 | 102.5 |  | 2022-07-29 01:00
Guelph | 2022 | 646271 | P-Wellington St W-SCADAMate R0132 Installation | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Harrison, Eric | Lauryssen, John | 57575.85 | 52064.72 | -5511.13 | -9.572% | 0 | 3396.22 | 3396.22 |  | 0 | 47770.03 | 47770.03 |  | 0 | 898.47 | 898.47 |  | 0 | 0 | 0 |  | 88 | 35 | -53 | -60.23% | 2022-03-28
Guelph | 2022 | 646273 | P-Willow Rd - SCADAMate R0459 Installation | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Harrison, Eric | Lauryssen, John | 58103.17 | 54876.42 | -3226.75 | -5.553% | 0 | 5295.12 | 5295.12 |  | 0 | 48180.49 | 48180.49 |  | 0 | 1400.81 | 1400.81 |  | 0 | 0 | 0 |  | 91 | 58.5 | -32.5 | -35.71% | 2022-04-04
Guelph | 2022 | 646274 | P-Exhibition St - LIS L0575 Replacement | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Harrison, Eric | Manes, Bradley | 26873.4 | 29170.33 | 2296.93 | 8.547% | 0 | 13506.63 | 13506.63 |  | 0 | 11320.55 | 11320.55 |  | 0 | 3573.15 | 3573.15 |  | 0 | 770 | 770 |  | 119 | 144.25 | 25.25 | 21.22% | 2022-04-08
Guelph | 2022 | 646284 | 100 Victoria Rd S/GUE/NS | 95 | COMPLETE | N/A |  |  | McAlpine, Robert | No | McGregor, Brendan | Stevens, Carl | 58623.49 | 53718.92 | -4904.57 | -8.366% | 0 | 6709.92 | 6709.92 |  | 0 | 33323.12 | 33323.12 |  | 0 | 1993.29 | 1993.29 |  | 0 | 11692.59 | 11692.59 |  | 118.04 | 71 | -47.04 | -39.85% | 2022-05-05
Guelph | 2022 | 646285 | P-201 Elmira Rd S/GUE/NS/Temp Service | 95 | COMPLETE | N/A |  |  | McGregor, Brendan | No | McIntyre, Max | Stevens, Carl | 0 | 4705.94 | 4705.94 |  | 0 | 1542.79 | 1542.79 |  | 0 | 1732.15 | 1732.15 |  | 0 | 606 | 606 |  | 0 | 825 | 825 |  | 0 | 21 | 21 |  | 2022-12-26 01:00
Guelph | 2022 | 646288 | 78 Starwood Drive/GUE/NS/1PH Overhead Temp Service | 95 | COMPLETE | N/A |  |  | McGregor, Brendan | No | McIntyre, Max | Stevens, Carl | 3896.8 | 841.04 | -3055.76 | -78.42% | 0 | 697.04 | 697.04 |  | 0 | 0 | 0 |  | 0 | 144 | 144 |  | 0 | 0 | 0 |  | 22 | 13 | -9 | -40.91% | 2022-07-19 01:00
Guelph | 2022 | 645910 | WESTWOOD RD - OVERPASS REPLACEMENT AT HANLON EXPWY (POLE LINE R/C PORT | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | No | Harrison, Eric | Manes, Bradley | 154003.38 | 114707.34 | -39296.04 | -25.52% | 74734.7 | 46715.81 | -28018.89 | -37.49% | 41013.89 | 37378.63 | -3635.26 | -8.863% | 24494.79 | 11297.5 | -13197.29 | -53.88% | 13760 | 19315.4 | 5555.4 | 40.37% | 618.12 | 494.5 | -123.62 | -20% | 2022-11-16 01:00
Guelph | 2022 | 645962 | RIDGEWOOD AVE BK00277 | 95 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Jamkodjian, Cassandra | Manes, Bradley | 21525.23 | 17717.43 | -3807.8 | -17.69% | 11080.08 | 9291.12 | -1788.96 | -16.15% | 5809.79 | 5382.18 | -427.61 | -7.36% | 2435.36 | 2229.53 | -205.83 | -8.452% | 2200 | 814.6 | -1385.4 | -62.97% | 63.71 | 72.5 | 8.79 | 13.8% | 2022-12-29 01:00
Guelph | 2022 | 646013 | P-755 Stone Rd E/GUE/NS-Site Servicing | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | South-West | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-24 01:00
Guelph | 2022 | 646030 | 140 DENNIS ST, ROCKWOOD - BK 80199 DECOMMISSION | 99 | COMPLETE | Labour est. over |  |  | Bolton, Ian J | No | Jamkodjian, Cassandra | Manes, Bradley | 7733.09 | 4256.91 | -3476.18 | -44.95% | 6223.83 | 3203.52 | -3020.31 | -48.53% | 612.98 | 596.09 | -16.89 | -2.755% | 896.28 | 104.5 | -791.78 | -88.34% | 0 | 352.8 | 352.8 |  | 32.84 | 11 | -21.84 | -66.5% | 2022-10-24 01:00
Guelph | 2022 | 646053 | P-20 Dunkirk Ave - BK00085 Replacement | 99 | CANCELLED | N/A |  |  | Bolton, Ian J | No | Jamkodjian, Cassandra | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-14 01:00
Guelph | 2022 | 646080 | POLE 8 STARWOOD DRIVE RELOCATION | 99 | COMPLETE | Labour est. over | Vehicle Under Estimated | N/A | Jakubowski, Mark | No | Fisher, Cody | Manes, Bradley | 17793.76 | 38112.87 | 20319.11 | 114.2% | 7242.18 | 13354.21 | 6112.03 | 84.39% | 7482.71 | 8072.16 | 589.45 | 7.877% | 2452.87 | 6307 | 3854.13 | 157.1% | 616 | 10379.5 | 9763.5 | 1585% | 64 | 148 | 84 | 131.2% | 2022-10-14 01:00
Guelph | 2022 | 646143 | 905 WOODLAWN RD W | 95 | COMPLETE | N/A |  |  | Jakubowski, Mark | No | Fisher, Cody | Lauryssen, John | 100594.39 | 69302.97 | -31291.42 | -31.11% | 40038.48 | 24587.43 | -15451.05 | -38.59% | 44737.88 | 13393.61 | -31344.27 | -70.06% | 13068.03 | 11421 | -1647.03 | -12.6% | 2750 | 19900.93 | 17150.93 | 623.7% | 336.66 | 250 | -86.66 | -25.74% | 2022-12-23 01:00
Guelph | 2022 | 646177 | P-Victoria Rd S and Florence Ln / GUE / NS / 1PH OH Temp Service | 99 | CANCELLED | N/A |  |  | McGregor, Brendan | No | McIntyre, Max | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-09-09 01:00
Guelph | 2022 | 646199 | 100 Victoria Road South / GUE / NS | 99 | CANCELLED | N/A |  |  | Bolton, Ian J | No | Jamkodjian, Cassandra | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-09-09 01:00
Guelph | 2022 | 646220 | Silver Maple - 120 Westmount Road | 95 | COMPLETE | N/A |  |  | Velickovski, Goran | No | Kingswell, Dean J | Stevens, Carl | 197590.07 | 184857.82 | -12732.25 | -6.444% | 0 | 19048.7 | 19048.7 |  | 0 | 157943.3 | 157943.3 |  | 0 | 4292.4 | 4292.4 |  | 0 | 3573.42 | 3573.42 |  | 253.75 | 216.5 | -37.25 | -14.68% | 2022-09-09 01:00
Guelph | 2022 | 646221 | Guelph West Reinforcement, Phase 3 - Edinburgh Road North | 99 | ANALYZE |  |  |  | Bolton, Ian J | Yes | Harrison, Eric | Manes, Bradley | 648023.9 | 592902.74 | -55121.16 | -8.506% | 0 | 230244.52 | 230244.52 |  | 0 | 244497.53 | 244497.53 |  | 0 | 57082.21 | 57082.21 |  | 0 | 61078.48 | 61078.48 |  | 3109.5 | 2641.95 | -467.55 | -15.04% | 2022-04-29
Guelph | 2022 | 646222 | 20 Gosling Gardens - Apartment Buildings | 95 | COMPLETE | N/A |  |  | McGregor, Brendan | No | McGregor, Brendan | Stevens, Carl | 56684.77 | 54974.97 | -1709.8 | -3.016% | 0 | 7713.26 | 7713.26 |  | 0 | 39518.81 | 39518.81 |  | 0 | 2212.69 | 2212.69 |  | 0 | 5530.21 | 5530.21 |  | 28 | 81 | 53 | 189.3% | 2022-04-14
Guelph | 2022 | 646223 | Silvercreek Parkway North at Curtis Drive - OH primary H1 crossing installation - | 99 | COMPLETE | Labour est. over |  |  | Bolton, Ian J | No | Jamkodjian, Cassandra | Lauryssen, John | 35517.43 | 25705.68 | -9811.75 | -27.63% | 0 | 10076.85 | 10076.85 |  | 0 | 11157.68 | 11157.68 |  | 0 | 3877.15 | 3877.15 |  | 0 | 594 | 594 |  | 179.2 | 104.5 | -74.7 | -41.69% | 2022-12-02 01:00
Guelph | 2022 | 646224 | Edinburgh Road South at College Avenue West | 99 | COMPLETE | N/A |  |  | Bolton, Ian J | Yes | Jamkodjian, Cassandra | Stevens, Carl | 34059.81 | 41646.31 | 7586.5 | 22.27% | 0 | 19203 | 19203 |  | 0 | 16279.68 | 16279.68 |  | 0 | 6163.63 | 6163.63 |  | 0 | 0 | 0 |  | 120 | 208.5 | 88.5 | 73.75% | 2022-06-30 01:00
Guelph | 2022 | 646225 | 131 Malcolm Road - New CEVA Bld - New U/G Service | 95 | COMPLETE | N/A |  |  | McGregor, Brendan | No | Dyce, Stephen A | Stevens, Carl | 81928 | 89358.21 | 7430.21 | 9.069% | 0 | 11731.54 | 11731.54 |  | 0 | 59107.95 | 59107.95 |  | 0 | 2368.34 | 2368.34 |  | 0 | 16150.38 | 16150.38 |  | 162 | 137 | -25 | -15.43% | 2022-01-10 01:00
Guelph | 2022 | 646226 | 54 Phelan Court - Commercial Servicing | 98 | COMPLETE | N/A |  |  | McGregor, Brendan | No | McGregor, Brendan | Stevens, Carl | 83153.62 | 85203.39 | 2049.77 | 2.465% | 0 | 8948.58 | 8948.58 |  | 0 | 68597.52 | 68597.52 |  | 0 | 2381.53 | 2381.53 |  | 0 | 5275.76 | 5275.76 |  | 141 | 96.5 | -44.5 | -31.56% | 2022-04-28
Guelph | 2022 | 646227 | Queen St (548) - Eramosa Rd to Grange St | 95 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | South-West | Lauryssen, John | 120793.59 | 157549.88 | 36756.29 | 30.43% | 0 | 61790.64 | 61790.64 |  | 0 | 49195.55 | 49195.55 |  | 0 | 16667.55 | 16667.55 |  | 0 | 29896.14 | 29896.14 |  | 16 | 699.5 | 683.5 | 4272% | 2022-03-17 01:00
Guelph | 2022 | 646228 | P-Pasmore Street and Clara Street, Rockwood | 95 | COMPLETE | Labour est. under |  |  | Bolton, Ian J | Yes | Chris McDonald | Manes, Bradley | 94445.41 | 178842.75 | 84397.34 | 89.36% | 0 | 60440.44 | 60440.44 |  | 0 | 37689.89 | 37689.89 |  | 0 | 26242.57 | 26242.57 |  | 0 | 54469.85 | 54469.85 |  | 420 | 613.75 | 193.75 | 46.13% | 2022-12-12 01:00
Guelph | 2022 | 647149 | 65 MALTBY RD / GUE / NS / 1PH POLE | 95 | COMPLETE | N/A |  |  | McGregor, Brendan | No | Shereefdeen, Zuhair | Manes, Bradley | 20469.24 | 10560.65 | -9908.59 | -48.41% | 5889.4 | 2835.45 | -3053.95 | -51.86% | 4479.94 | 750.19 | -3729.75 | -83.25% | 1191.9 | 350.5 | -841.4 | -70.59% | 8908 | 6624.51 | -2283.49 | -25.63% | 58.3633 | 17.5 | -40.8633 | -70.02% | 2022-11-28 01:00
Guelph | 2022 | 647209 | 54 CAMPBELL ROAD /GUE/NS/ SINGLE PHASE TEMP SERVICE | 95 | COMPLETE | N/A |  |  | McGregor, Brendan | No | Dyce, Stephen A | Manes, Bradley | 8867.73 | 7536.37 | -1331.36 | -15.01% | 4591.46 | 4082.47 | -508.99 | -11.09% | 3091.74 | 3082.9 | -8.84 | -0.2859% | 1184.53 | 371 | -813.53 | -68.68% | 0 | 0 | 0 |  | 15.01 | 42 | 26.99 | 179.8% | 2022-12-21 01:00
Guelph | 2022 | 647232 | 20 ARMSTRONG AVE - BK01861 REPLACEMENT | 99 | CANCELLED | N/A |  |  | Bolton, Ian J | No | Jamkodjian, Cassandra | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-18 01:00
Guelph | 2022 | 647237 | 351 ERAMOSA RD - BK00537 REPLACEMENT | 99 | CANCELLED | N/A |  |  | Bolton, Ian J | No | Jamkodjian, Cassandra | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-18 01:00
Guelph | 2022 | 647238 | 102 WYNDHAM ST N - BK06503 REPLACEMENT | 99 | CANCELLED | N/A |  |  | Bolton, Ian J | No | Jamkodjian, Cassandra | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-18 01:00
Guelph | 2022 | 647323 | 21-009 METCALFE RECONSTRUCTION - HYDRO CONFLICTS TEMP RELOCATION | 99 | COMPLETE | Engineering by-passed |  |  | Bolton, Ian J | No | Chris McDonald | Stevens, Carl | 35312.04 | 20534.12 | -14777.92 | -41.85% | 12295.05 | 8734.05 | -3561 | -28.96% | 14243.79 | 6874.68 | -7369.11 | -51.74% | 2629.2 | 3512 | 882.8 | 33.58% | 6144 | 1413.39 | -4730.61 | -77% | 100 | 94 | -6 | -6% | 2022-08-15 01:00
Guelph | 2022 | 647503 | P107 EDINBURGH RD S ROTTEN POLE REPLACEMENT | 95 | COMPLETE | Under 10% |  |  | Bolton, Ian J | No | Chris McDonald | Manes, Bradley | 47532.57 | 52334.97 | 4802.4 | 10.1% | 19814.29 | 21655.31 | 1841.02 | 9.291% | 15254.68 | 15489.91 | 235.23 | 1.542% | 5813.6 | 10769.86 | 4956.26 | 85.25% | 6650 | 4419.89 | -2230.11 | -33.54% | 162.0833 | 222 | 59.9167 | 36.97% | 2022-11-16 01:00
Guelph | 2022 | 859455 | Joint Use Transfer - Rogers - Willow Rd Reconstruction | 99 | COMPLETE | N/A |  |  |  | No | South-West | Stevens, Carl | 8288 | 0 | -8288 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 59 | 0 | -59 | -100% | 2022-05-02
Guelph | 2022 | 935908 | Paisley St & Dublin St N | 99 | COMPLETE | N/A |  |  |  | No | McGregor, Brendan | Stevens, Carl | 0 | 2866.7 | 2866.7 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-02
Guelph | 2020 | 1000280 | Drew St - Rosewood Ave - Baqot St | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Manes, Bradley | 0 | 29579.27 | 29579.27 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-03-11 01:00
Guelph | 2022 | 1018695 | NiMa Trails, Phase 1B Subdivision | 99 | COMPLETE | N/A |  |  |  | No | Kingswell, Dean J | Stevens, Carl | 394748 | 0 | -394748 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 399 | 172.5 | -226.5 | -56.77% | 2022-03-01 01:00
Guelph | 2020 | 1027328 | 41 Conroy Cres | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 9201.45 | 9201.45 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 28 | 28 |  | 2020-08-18 01:00
Guelph | 2020 | 1031531 | 561 York Rd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 48955.88 | 48955.88 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 100.9 | 100.9 |  | 2020-06-04 01:00
Guelph | 2020 | 1045975 | 250 York Rd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 29237.54 | 29237.54 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 42 | 42 |  | 2020-08-18 01:00
Guelph | 2020 | 1050258 | 943 Edinburgh Rd S | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 98152.72 | 98152.72 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 30 | 30 |  | 2020-04-22
Guelph | 2020 | 1061982 | 154 Milne Place | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 17348.75 | 17348.75 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 38.5 | 38.5 |  | 2020-08-18 01:00
Guelph | 2020 | 1075708 | 3 Stone Rd W | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Manes, Bradley | 0 | 43021.07 | 43021.07 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 196.5 | 196.5 |  | 2020-07-29 01:00
Guelph | 2020 | 1075723 | Pole 154 Woodlawn Road West | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Lauryssen, John | 75791.64 | 23078.09 | -52713.55 | -69.55% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 179 | 105.6 | -73.4 | -41.01% | 2020-11-09 01:00
Guelph | 2020 | 1077259 | 70 Kirby Crt | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 64605.46 | 64605.46 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 94.5 | 94.5 |  | 2020-06-12 01:00
Guelph | 2020 | 1079167 | Alma Street North and Plymouth Court Phase 4 | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 282394.86 | 218563.62 | -63831.24 | -22.6% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 951 | 981 | 30 | 3.155% | 2020-11-09 01:00
Guelph | 2020 | 1079171 | Alma Street North and Julia Drive Phase 3 | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 270005.98 | 259896.33 | -10109.65 | -3.744% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1185.3 | 892.5 | -292.8 | -24.7% | 2020-07-31 01:00
Guelph | 2021 | 1081608 | Delhi St pole #76 | 99 | COMPLETE | N/A |  |  |  | No | Harrison, Eric | Manes, Bradley | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1321.5 | 1321.5 |  | 2021-01-29 01:00
Guelph | 2020 | 1082007 | 435 Stone Rd West | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 81302.79 | 81302.79 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 161.3 | 161.3 |  | 2020-08-14 01:00
Guelph | 2021 | 1082576 | 73 & 93 Arthur St S | 99 | COMPLETE | N/A |  |  |  | No | South-West | Stevens, Carl | 0 | 528.03 | 528.03 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 | 4 |  | 2021-05-14
Guelph | 2022 | 1084146 | 735 Woolwich St | 99 | COMPLETE | N/A |  |  |  | No | Dyce, Stephen A | Manes, Bradley | 85045.18 | 36381.67 | -48663.51 | -57.22% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 117 | 91 | -26 | -22.22% | 2020-08-24 01:00
Guelph | 2020 | 1084158 | 731 Woolwich Rd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 32964.7 | 32964.7 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 58 | 58 |  | 2020-08-24 01:00
Guelph | 2021 | 1085690 | 1131 Gordon Street Townhomes | 99 | COMPLETE | N/A |  |  |  | No | Kingswell, Dean J | Stevens, Carl | 37162.62 | 19112.88 | -18049.74 | -48.57% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 59.75 | 26 | -33.75 | -56.49% | 2021-11-01 01:00
Guelph | 2020 | 1098347 | Main Street North, Rockwood | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Manes, Bradley | 804378.53 | 274071 | -530307.53 | -65.93% | 0 | 0 | 0 |  | 422921.73 | 0 | -422921.73 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1564.5 | 1487.5 | -77 | -4.922% | 2020-10-30 01:00
Guelph | 2020 | 1098489 | 995 Southgate Dr | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 56327.21 | 56327.21 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 117 | 117 |  | 2020-08-20 01:00
Guelph | 2020 | 1106965 | PMSG039 - 395 Southgate Dr - pad-switch replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 23534.86 | 26942.65 | 3407.79 | 14.48% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 24 | 40 | 16 | 66.67% | 2020-11-05 01:00
Guelph | 2020 | 1106972 | PMSG070 - 64 Fredrick Dr - pad switch replacement | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Stevens, Carl | 81782.55 | 971.3 | -80811.25 | -98.81% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 514 | 0 | -514 | -100% | 2020-12-14 01:00
Guelph | 2022 | 1107154 | Harts Village, Phase 2 Subdivision | 99 | COMPLETE | N/A |  |  |  | No | Kingswell, Dean J | Stevens, Carl | 408091.46 | 25522.52 | -382568.94 | -93.75% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 440.4 | 156 | -284.4 | -64.58% | 2022-01-27 01:00
Guelph | 2020 | 1109290 | 55 Quarterman Rd | 99 | COMPLETE | N/A |  |  |  | No | Alectra Utilities | Stevens, Carl | 0 | 39042.97 | 39042.97 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 69.5 | 69.5 |  | 2020-06-09 01:00
Guelph | 2020 | 1110199 | Pleasant Road Reconstruction | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Manes, Bradley | 384681.52 | 235188.44 | -149493.08 | -38.86% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1388 | 872 | -516 | -37.18% | 2020-10-16 01:00
Guelph | 2020 | 1110200 | Pleasant Rd - UG services to 4 & 55 Pleasant Dr | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Manes, Bradley | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-27 01:00
Guelph | 2020 | 1111303 | Metcalfe Steet & Balsam Drive Reconstruction | 99 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 210595.54 | 213538.53 | 2942.99 | 1.397% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1155.8 | 1152.7 | -3.1 | -0.2682% | 2020-08-21 01:00
Guelph | 2023 | 646085 | YORKSHIRE ST N (LONDON RD W TO NORTHUMBERLAND ST) & LIVERPOOL ST | 94 | COMPLETE | N/A |  |  |  | Yes | Alectra Utilities | Lauryssen, John | 550228.89 | 715478.17 | -165249.28 | 15.05% | 316727.06 | 263050.53 | 53676.53 |  | 239246.77 | 237308.35 | -1938.42 |  | 58303.69 | 118973.1 | 60669.41 |  | 28000 | 96146.19 | 68146.19 |  | 1772.9 | 2996.8 | 1223.9 | -11.94% | 2023-05-08
Hamilton | 2019 | 12696 | 2 Witherspoon St - Trouble Call | 99 | COMPLETE | N/A | N/A | N/A |  | No | Johnson, William | Hotham, Matthew | 0 | 61389.58 | 61389.58 |  | 0 | 35843.39 | 35843.39 |  | 0 | 17192.09 | 17192.09 |  | 0 | 1747.77 | 1747.77 |  | 0 | 5473.42 | 5473.42 |  | 0 | 161.75 | 161.75 |  | 2019-05-29
Hamilton | 2019 | 13011A | 36 Queenston St(SCH) | 99 | COMPLETE | N/A | N/A | N/A |  | No | Alectra Utilities | Weaver, Thomas | 0 | 10141.7 | 10141.7 |  | 0 | 0 | 0 |  | 0 | 5537.19 | 5537.19 |  | 0 | 0 | 0 |  | 0 | 805 | 805 |  | 0 | 0 | 0 |  | 2019-05-17
Hamilton | 2019 | 13225 | Ottawa/Campbell Rear Alley Rebuild | 99 | COMPLETE | N/A | N/A | N/A |  | No | Webb-Murre, Paige | Destefano, Nick | 134647.48 | 144945.22 | 10297.74 | 7.648% | 18513.72 | 14427.52 | -4086.2 | -22.07% | 10730.4 | 21770.87 | 11040.47 | 102.9% | 1076.8 | 0 | -1076.8 | -100% | 104326.56 | 104335.56 | 9 | 0.008627% | 248 | 242.25 | -5.75 | -2.319% | 2019-01-04 01:00
Hamilton | 2019 | 13256 | 2017 Pole Residual | 99 | COMPLETE | BOM not accurate | N/A | N/A |  | No | Celic, Dusan | XPopiel, Joseph | 26811.88 | 26264.08 | -547.8 | -2.043% | 14808.12 | 15789.79 | 981.67 | 6.629% | 5671.26 | 2543.2 | -3128.06 | -55.16% | 3332.5 | 544.32 | -2788.18 | -83.67% | 3000 | 4969.82 | 1969.82 | 65.66% | 212 | 257.65 | 45.65 | 21.53% | 2019-03-14 01:00
Hamilton | 2019 | 14800 | Cameron Drive Deficiencies | 99 | COMPLETE | N/A | N/A | N/A |  | No | Wardell, Paul | Jakubowski, Mark | 0 | 61068.27 | 61068.27 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 61068.27 | 61068.27 |  | 0 | 0 | 0 |  | 2019-05-08
Hamilton | 2019 | 15353 | 16 Astra Street - Pad Relocation | 99 | COMPLETE | N/A | N/A | N/A |  | No | Webb-Murre, Paige | Andrew Mehlenbacher | 20910.64 | 2977.24 | -17933.4 | -85.76% | 9909.61 | 2423.54 | -7486.07 | -75.54% | 7429.03 | 0 | -7429.03 | -100% | 618.3 | 0 | -618.3 | -100% | 2953.7 | 553.7 | -2400 | -81.25% | 149 | 41.5 | -107.5 | -72.15% | 2019-04-03 01:00
Hamilton | 2019 | 15448 | 257 Main St. E HAM | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 684.92 | 684.92 |  | 0 | 684.92 | 684.92 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 10.5 | 10.5 |  | 2019-05-07
Hamilton | 2019 | 15469 | 52 Brydale Crt. DUN | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 746.49 | 746.49 |  | 0 | 746.49 | 746.49 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14 | 14 |  | 2019-05-07
Hamilton | 2019 | 15474 | 97 5th Concession Rd. E FLA | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 904.17 | 904.17 |  | 0 | 904.17 | 904.17 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14.5 | 14.5 |  | 2019-05-07
Hamilton | 2019 | 15477 | 460 Dundas St. E | 99 | COMPLETE | Labour est. under | Vac truck | N/A |  | No | Montgomery, Michael | Koeppe, Jeffrey | 29578.22 | 38415.96 | 8837.74 | 29.88% | 11173.97 | 15672.08 | 4498.11 | 40.26% | 15506.85 | 14487.72 | -1019.13 | -6.572% | 2897.4 | 832.96 | -2064.44 | -71.25% | 0 | 937.5 | 937.5 |  | 157.5 | 236.5 | 79 | 50.16% | 2019-02-20 01:00
Hamilton | 2019 | 15502 | Horning TS - Switch Gear Rebuild | 99 | COMPLETE | Scope change - unforeseen | BOM not accurate | Labour est. under |  | Yes | Billone, Justin | Roy Owen | 1144881.53 | 1299172.71 | 154291.18 | 13.48% | 136663.71 | 182416.96 | 45753.25 | 33.48% | 334696.02 | 340776.19 | 6080.17 | 1.817% | 20831.8 | 5350.86 | -15480.94 | -74.31% | 652690 | 670880 | 18190 | 2.787% | 2098.5 | 2663 | 564.5 | 26.9% | 2019-02-26 01:00
Hamilton | 2019 | 15566B | HUC43 | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 10371.07 | 10371.07 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
Hamilton | 2019 | 15567B | HUC91 | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 7292.34 | 7292.34 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
Hamilton | 2019 | 15568B | HUC185 | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 6695.02 | 6695.02 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
Hamilton | 2019 | 15569B | HUC190 | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 8280.92 | 8280.92 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
Hamilton | 2019 | 15571B | HUC345 | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 8163.75 | 8163.75 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
Hamilton | 2019 | 15572B | HUC600 | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 5908.95 | 5908.95 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
Hamilton | 2019 | 15573B | HUC601 | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 6801.12 | 6801.12 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
Hamilton | 2019 | 15575B | HUC1361 | 99 | COMPLETE | N/A |  |  |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 1164 | 1164 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
Hamilton | 2019 | 15717 | 289 Winona Rd, Stoney Creek | 99 | COMPLETE | Civil contractor | N/A | N/A |  | No | Laus, Tomislav | Carr, Brad | 2454.53 | 1304.26 | -1150.27 | -46.86% | 1396.11 | 1304.26 | -91.85 | -6.579% | 0 | 0 | 0 |  | 134 | 0 | -134 | -100% | 924.42 | 0 | -924.42 | -100% | 24 | 20.5 | -3.5 | -14.58% | 2019-03-22 01:00
Hamilton | 2019 | 15767 | 659 Parkdale - Temp Upgrade | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 559 | 50 | -509 | -91.06% | 2019-06-07
Hamilton | 2019 | 15771 | 170 Concession St | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 15772 | 1318 Upper Wellington St | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 15776 | 150 James St.po\S | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 15857 | 265, 275 Sherman Ave N, Hamilton | 99 | COMPLETE | BOM not accurate | N/A | N/A |  | No | Bennett, Aaron | Andrew Mehlenbacher | 25882.02 | 30116.36 | 4234.34 | 16.36% | 19700.69 | 22042.88 | 2342.19 | 11.89% | 3574.13 | 5172.16 | 1598.03 | 44.71% | 2607.2 | 549.82 | -2057.38 | -78.91% | 0 | 0 | 0 |  | 299.5 | 315.25 | 15.75 | 5.259% | 2019-01-17 01:00
Hamilton | 2019 | 16033 | 391 Highland Rd E, Stoney Creek | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A |  | No | Laus, Tomislav | Koeppe, Jeffrey | 18031.36 | 19941.29 | 1909.93 | 10.59% | 3878.03 | 4497.35 | 619.32 | 15.97% | 4908.8 | 5524.7 | 615.9 | 12.55% | 1010 | 143.44 | -866.56 | -85.8% | 8234.53 | 8234.53 | 0 | 0% | 53 | 71 | 18 | 33.96% | 2019-01-26 01:00
Hamilton | 2019 | 16160 | 539 Barton St.E | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 16161 | 2 Ottawa St.N | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 16164 | 1344 Highway 8 | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 16165 | 2411 Barton St.E (Rear) | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 16171 | 95 Rockcliffe | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 16175 | 460 Sanatorium Rd | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Oosterlinck, David | Roy Owen | 14248.15 | 17116.21 | 2868.06 | 20.13% | 11353.36 | 14061.85 | 2708.49 | 23.86% | 893.79 | 977.92 | 84.13 | 9.413% | 2001 | 610.93 | -1390.07 | -69.47% | 0 | 0 | 0 |  | 173 | 207.25 | 34.25 | 19.8% | 2019-01-31 01:00
Hamilton | 2019 | 16274 | 113-123 Emerald St. S | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 1416.53 | 1416.53 |  | 0 | 1416.53 | 1416.53 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 21 | 21 |  | 2019-05-07
Hamilton | 2019 | 16278 | 80 Queen St. S | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 2442.12 | 2442.12 |  | 0 | 2442.12 | 2442.12 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 37 | 37 |  | 2019-05-07
Hamilton | 2019 | 16283 | 2 Hillyard St. HAM | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-07
Hamilton | 2019 | 16284 | 30 John St. N | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 1875.65 | 1875.65 |  | 0 | 1875.65 | 1875.65 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 28 | 28 |  | 2019-05-07
Hamilton | 2019 | 16288 | 1457 Main St. W Ham | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 1234.3 | 1234.3 |  | 0 | 1234.3 | 1234.3 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 17.5 | 17.5 |  | 2019-05-07
Hamilton | 2019 | 16317 | Cogeco Make Ready - Mountain Ave | 99 | COMPLETE | Labour est. over | BOM – truck stock | N/A |  | No | Celic, Dusan | XPopiel, Joseph | 4416.88 | 2332.07 | -2084.81 | -47.2% | 2602.58 | 0 | -2602.58 | -100% | 734.8 | 0 | -734.8 | -100% | 280 | 0 | -280 | -100% | 799.5 | 0 | -799.5 | -100% | 36 | 24.25 | -11.75 | -32.64% | 2019-01-11 01:00
Hamilton | 2019 | 16323 | East 8th St Pole Replacement | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Webb-Murre, Paige | XPopiel, Joseph | 27345.6 | 24203.24 | -3142.36 | -11.49% | 10842.51 | 10153.5 | -689.01 | -6.355% | 8968.69 | 6445.22 | -2523.47 | -28.14% | 3334.4 | 627.62 | -2706.78 | -81.18% | 4200 | 2636.49 | -1563.51 | -37.23% | 194 | 161 | -33 | -17.01% | 2019-01-26 01:00
Hamilton | 2019 | 16340 | 542 Upper Sherman Ave - Hamilton | 99 | COMPLETE | Vac truck | N/A | N/A |  | No | Djuric, Zdravko | Koeppe, Jeffrey | 9962.68 | 8113.45 | -1849.23 | -18.56% | 4652.94 | 4398.88 | -254.06 | -5.46% | 1043.77 | 632 | -411.77 | -39.45% | 1701.2 | 185.08 | -1516.12 | -89.12% | 2564.77 | 1839.77 | -725 | -28.27% | 65.5 | 65 | -0.5 | -0.7634% | 2019-01-26 01:00
Hamilton | 2019 | 16346 | 30 Golfwood Dr | 99 | CANCELLED | N/A | N/A | N/A |  | No | Djuric, Zdravko | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-06
Hamilton | 2019 | 16354 | 4 Penlake Crt - Hamilton | 99 | CANCELLED | N/A | N/A | N/A |  | No | Djuric, Zdravko | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-06
Hamilton | 2019 | 16358 | 201 Highway 5 West - Flamborough | 99 | CANCELLED | N/A | N/A | N/A |  | No | Djuric, Zdravko | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-06
Hamilton | 2019 | 16403 | Cogeco Make Ready - Broadway Ave | 99 | COMPLETE | N/A | N/A | N/A |  | No | Celic, Dusan | Frank Giancola | 2451.12 | 2825.65 | 374.53 | 15.28% | 1276.27 | 0 | -1276.27 | -100% | 0 | 0 | 0 |  | 135.5 | 0 | -135.5 | -100% | 1039.35 | 0 | -1039.35 | -100% | 17 | 20 | 3 | 17.65% | 2019-01-04 01:00
Hamilton | 2019 | 16443 | Cogeco Make Ready - Bond St N | 99 | COMPLETE | N/A | N/A | N/A |  | No | Celic, Dusan | Carr, Brad | 2207.97 | 1930.35 | -277.62 | -12.57% | 522.52 | 0 | -522.52 | -100% | 0 | 0 | 0 |  | 42.45 | 0 | -42.45 | -100% | 1643 | 0 | -1643 | -100% | 7 | 4.5 | -2.5 | -35.71% | 2019-01-30 01:00
Hamilton | 2019 | 16538 | Cogeco Make Ready - John St N | 99 | CANCELLED | N/A | N/A | N/A |  | No | Celic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-13 01:00
Hamilton | 2020 | 451016 | Parkside Drive - HWY 6 to Main St. | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Caucci, Jason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-14 01:00
Hamilton | 2020 | 451043 | Transfer of Hydro One Cust. - Rymal | 99 | COMPLETE | Converted Project | N/A | N/A | Newitt, Andrew | No | Alectra Utilities | Koeppe, Jeffrey | 159886.86 | 105989.08 | -53897.78 | -33.71% | 23999.73 | 12414.87 | -11584.86 | -48.27% | 35011.8 | 25053.86 | -9957.94 | -28.44% | 5415.6 | 3314.29 | -2101.31 | -38.8% | 95403.77 | 28033.44 | -67370.33 | -70.62% | 356 | 436 | 80 | 22.47% | 2020-01-14 01:00
Hamilton | 2020 | 451058 | Salerno Dairy (Parkdale and Rennie) | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 53207.94 | 59913.08 | 6705.14 | 12.6% | 27640.77 | 981.15 | -26659.62 | -96.45% | 18825.22 | 24806.12 | 5980.9 | 31.77% | 5341.95 | 54 | -5287.95 | -98.99% | 1400 | 2260.06 | 860.06 | 61.43% | 408.5 | 385 | -23.5 | -5.753% | 2020-08-14 01:00
Hamilton | 2019 | 451062 | 120 Cannon St.E | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Oosterlinck, David | Tony Ierace | 43459.43 | 53746.48 | 10287.05 | 23.67% | 16582.54 | 3705.38 | -12877.16 | -77.65% | 18452.21 | 22064.15 | 3611.94 | 19.57% | 740.28 | 982 | 241.72 | 32.65% | 7684.4 | 0 | -7684.4 | -100% | 182 | 266.75 | 84.75 | 46.57% | 2019-08-31 01:00
Hamilton | 2022 | 451070 | Fairleigh Ave Rebuild | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Paesano, Andrew | Koeppe, Jeffrey | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-03 01:00
Hamilton | 2019 | 451075 | Barton St - Delta To WYE Conversion | 99 | COMPLETE | Cont Est Under | N/A | N/A |  | No | Celic, Dusan | Carr, Brad | 134009.54 | 131565.78 | -2443.76 | -1.824% | 15600.14 | 8250.2 | -7349.94 | -47.11% | 40031.72 | 40878.43 | 846.71 | 2.115% | 2143.1 | 17.5 | -2125.6 | -99.18% | 76234.58 | 81999.58 | 5765 | 7.562% | 203 | 149.25 | -53.75 | -26.48% | 2019-05-03 01:00
Hamilton | 2019 | 451076 | DART Pole Rplmnts - Homeside Ave | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 9066.59 | 9066.59 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2020 | 451080 | King & Dundurn, Shoppers Plaza | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Roy Owen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-14 01:00
Hamilton | 2019 | 13420 | Paramount Sub- Additional Tx's | 99 | COMPLETE | N/A |  |  |  | No | Billone, Justin | Destefano, Nick | 0 | 383.76 | 383.76 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-27 01:00
Hamilton | 2022 | 451084 | James St | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Oosterlinck, David | Destefano, Nick | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2022 | 451086 | 2016 Pole Residual Melody Crt | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | Yes | Paesano, Andrew | Koeppe, Jeffrey | 18450.13 | 0 | -18450.13 | -100% | 14442.46 | 0 | -14442.46 | -100% | 2728.46 | 0 | -2728.46 | -100% | 757.48 | 0 | -757.48 | -100% | 521.73 | 0 | -521.73 | -100% | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 14098 | HCE Fiber Installations 2015 | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jolie, Chris | Hewitson, Trevor | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 14420 | 197 King Wm - Steel Lounge | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 14655 | Elgin TS Bus Relocations | 99 | COMPLETE | N/A | N/A | N/A |  | No | Jolie, Chris | Jakubowski, Mark | 0 | 2324701.67 | 2324701.67 |  | 0 | 10351.97 | 10351.97 |  | 0 | 843.42 | 843.42 |  | 0 | 34.39 | 34.39 |  | 0 | 2275195.09 | 2275195.09 |  | 0 | 156.35 | 156.35 |  | 2019-04-24 01:00
Hamilton | 2019 | 14683 | 1040 Main St E (Gage Park) | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 3702.04 | 3702.04 |  | 0 | 3702.04 | 3702.04 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 65.5 | 65.5 |  | 2019-05-07
Hamilton | 2019 | 451093 | 27 Bold St, Hamilton | 99 | COMPLETE | BOM cost variance | Cont Est Over | N/A |  | No | Laus, Tomislav | Koeppe, Jeffrey | 52766.58 | 62354.9 | 9588.32 | 18.17% | 20556.39 | 18887.26 | -1669.13 | -8.12% | 10879.69 | 16421.24 | 5541.55 | 50.93% | 4946 | 1125.44 | -3820.56 | -77.25% | 16384.5 | 13143.6 | -3240.9 | -19.78% | 322.5 | 317.5 | -5 | -1.55% | 2019-03-09 01:00
Hamilton | 2020 | 451095 | SuperCrawl-James St N-King-Murray | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Brian Robinson | 3792.42 | 0 | -3792.42 | -100% | 3232.35 | 0 | -3232.35 | -100% | 397.47 | 0 | -397.47 | -100% | 162.6 | 0 | -162.6 | -100% | 0 | 0 | 0 |  | 61 | 25 | -36 | -59.02% | 2019-05-29
Hamilton | 2019 | 451100 | York to 290 Barton St W Large Move | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Johnson, William | Jakubowski, Mark | 5408.36 | 6298.12 | 889.76 | 16.45% | 5280.75 | 0 | -5280.75 | -100% | 0 | 0 | 0 |  | 127.61 | 0 | -127.61 | -100% | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 |  | 2019-05-29
Hamilton | 2019 | 451101 | Buchanan St. Pole Replacements | 99 | COMPLETE | Converted Project | N/A | N/A | McAlpine, Robert | No | Webb-Murre, Paige | Scott Borer | 61354.16 | 45502.46 | -15851.7 | -25.84% | 28553.65 | 0 | -28553.65 | -100% | 14908.74 | 17140.41 | 2231.67 | 14.97% | 9594.8 | 0 | -9594.8 | -100% | 8296.97 | 0 | -8296.97 | -100% | 421 | 315 | -106 | -25.18% | 2019-06-18 01:00
Hamilton | 2019 | 451102 | 30 Milton Ave Large Load Move | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Johnson, William | Jakubowski, Mark | 0 | 3920.26 | 3920.26 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 |  | 2019-05-29
Hamilton | 2019 | 451103 | Milton Ave to Hwy 6 N Large Move | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Johnson, William | Jakubowski, Mark | 0 | 1198.5 | 1198.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2.5 | 2.5 |  | 2019-05-29
Hamilton | 2022 | 451104 | future 867 cannon e | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-09 01:00
Hamilton | 2019 | 451106 | Centennial Go Station, Park & Ride | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Andrew Mehlenbacher | 14347.49 | 16976.54 | 2629.05 | 18.32% | 6558.69 | 2995.09 | -3563.6 | -54.33% | 619.55 | 602.98 | -16.57 | -2.675% | 606.4 | 858 | 251.6 | 41.49% | 6562.85 | 0 | -6562.85 | -100% | 107 | 113.5 | 6.5 | 6.075% | 2019-09-14 01:00
Hamilton | 2020 | 451112 | First Rd and Green Mountain | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 1339825.79 | 1249426.02 | -90399.77 | -6.747% | 35719.12 | 98606.03 | 62886.91 | 176.1% | 308068.47 | 253889.55 | -54178.92 | -17.59% | 0 | 2280 | 2280 |  | 996038.2 | 862808.65 | -133229.55 | -13.38% | 192 | 269 | 77 | 40.1% | 2020-05-27
Hamilton | 2022 | 451113 | Green Millen Shores - East (Rec) | 99 | CANCELLED | N/A |  |  | Newitt, Andrew | No | Vandekuyt, Greg | Destefano, Nick | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-15 01:00
Hamilton | 2021 | 451115 | 2021 TX RENEWAL - KICKER TX OH - 1 | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Brad Carr | 43055.45 | 44792.59 | 1737.14 | 4.035% | 3453.69 | 8281.69 | 4828 | 139.8% | 1087.26 | 0 | -1087.26 | -100% | 0 | 139.4 | 139.4 |  | 38514.5 | 34040.25 | -4474.25 | -11.62% | 16 | 12 | -4 | -25% | 2021-06-15 01:00
Hamilton | 2020 | 451123 | 111 Brockley Dr | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | XPopiel, Joseph | 85563.24 | 77608.58 | -7954.66 | -9.297% | 26732.1 | 5813.06 | -20919.04 | -78.25% | 32800.51 | 33562.26 | 761.75 | 2.322% | 4482.05 | 334 | -4148.05 | -92.55% | 21548.58 | 0 | -21548.58 | -100% | 376 | 291.55 | -84.45 | -22.46% | 2020-04-24
Hamilton | 2022 | 451129 | 2015 Pole removals Hamilton | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451130 | Fontana Gardens Phase 3 | 99 | CANCELLED | N/A |  |  |  | No | Johnson, William | Tony Ierace | 0 | 250.68 | 250.68 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2021 | 451132 | Residual Poles - East Downtown 2016 | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Karan, Andjelo | Koeppe, Jeffrey | 60999.92 | 99090.27 | 38090.35 | 62.44% | 31475.54 | 43685.48 | 12209.94 | 38.79% | 18854.91 | 23288.72 | 4433.81 | 23.52% | 2018.92 | 15895.35 | 13876.43 | 687.3% | 8607.43 | 8743.69 | 136.26 | 1.583% | 0 | 597 | 597 |  | 2021-01-15 01:00
Hamilton | 2022 | 451135 | Waste Water Treatment Plant | 98 | COMPLETE | Converted Project |  | Labour est. under | Jakubowski, Mark | No | Patel, Ketan | Tony Ierace | 500103.92 | 936804.26 | 436700.34 | 87.32% | 119495.44 | 151618.79 | 32123.35 | 26.88% | 286450.11 | 417446.27 | 130996.16 | 45.73% | 15811.76 | 21720.76 | 5909 | 37.37% | 78346.61 | 78955.31 | 608.7 | 0.7769% | 2261.5 | 3050.25 | 788.75 | 34.88% | 2022-02-04 01:00
Hamilton | 2020 | 451136 | Highland F3 4kV Feeder Removal | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 203350.62 | 141702.5 | -61648.12 | -30.32% | 3934.14 | 10921.65 | 6987.51 | 177.6% | 26426.44 | 45722.25 | 19295.81 | 73.02% | 543.2 | 161.5 | -381.7 | -70.27% | 172446.84 | 79200.14 | -93246.7 | -54.07% | 42 | 24.5 | -17.5 | -41.67% | 2020-02-26 01:00
Hamilton | 2022 | 451140 | Bell Canada Third Party Transfers | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-30 01:00
Hamilton | 2022 | 451143 | Rogers Third Party Transfers | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-30 01:00
Hamilton | 2022 | 451144 | Cogeco Third Party Transfers | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-30 01:00
Hamilton | 2022 | 451145 | City of Hamilton 3rdParty Transfers | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-30 01:00
Hamilton | 2019 | 451150 | Dundas St Subdivision | 99 | COMPLETE | Scope change - unforeseen | Cont Est Under | BOM not accurate | Beaudrie, Scott | No | Webb-Murre, Paige | Brian Robinson | 81793.87 | 226345.99 | 144552.12 | 176.7% | 30135.49 | 0 | -30135.49 | -100% | 10166.63 | 12983.18 | 2816.55 | 27.7% | 1066.98 | 0 | -1066.98 | -100% | 33946.15 | 0 | -33946.15 | -100% | 433 | 493.5 | 60.5 | 13.97% | 2019-01-30 01:00
Hamilton | 2019 | 451151 | Rymal Rd East & Hwy 20 | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Brian Robinson | 18408.38 | 12992.62 | -5415.76 | -29.42% | 12498.6 | 150.69 | -12347.91 | -98.79% | 4088.27 | 3740.04 | -348.23 | -8.518% | 699.78 | 0 | -699.78 | -100% | 1121.73 | 0 | -1121.73 | -100% | 191 | 117 | -74 | -38.74% | 2019-09-28 01:00
Hamilton | 2021 | 451156 | 1365 Baseline Rd - Pole Conflicts | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Johnson, William | Jakubowski, Mark | 0 | 7572.58 | 7572.58 |  | 0 | 348.43 | 348.43 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3 | 3 |  | 2019-05-29
Hamilton | 2019 | 451157 | 300 Mohawk Rd E - Trans Rm Removal | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 674.02 | 674.02 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2022 | 451158 | 27 Proctor- Service Relocation | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Paesano, Andrew | Koeppe, Jeffrey | 2963.13 | 0 | -2963.13 | -100% | 1572.63 | 0 | -1572.63 | -100% | 0 | 0 | 0 |  | 26.84 | 0 | -26.84 | -100% | 1363.66 | 0 | -1363.66 | -100% | 0 | 0 | 0 |  | 2020-02-21 01:00
Hamilton | 2020 | 451163 | 85 Mary St | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 135541.28 | 178993.31 | 43452.03 | 32.06% | 39293.59 | 11550.12 | -27743.47 | -70.61% | 32376.15 | 32038.48 | -337.67 | -1.043% | 6903.8 | 2515.85 | -4387.95 | -63.56% | 56967.74 | 2786.65 | -54181.09 | -95.11% | 473.5 | 513 | 39.5 | 8.342% | 2020-02-21 01:00
Hamilton | 2022 | 451167 | Fletcher Square - Sw and Tx Rework | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-14 01:00
Hamilton | 2020 | 451169 | 225 Ray St N | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 12196.92 | 12032.63 | -164.29 | -1.347% | 6235.15 | 0 | -6235.15 | -100% | 3232.14 | 4314.2 | 1082.06 | 33.48% | 316.14 | 0 | -316.14 | -100% | 1193.1 | 0 | -1193.1 | -100% | 92 | 76 | -16 | -17.39% | 2020-11-23 01:00
Hamilton | 2021 | 451172 | DUNDAS AND SPRING CREEK CONDO | 98 | COMPLETE | Labour est. under |  |  | Kappheim, Adam | No | Oosterlinck, David | Macdougall, Stephen | 62175.96 | 91778.98 | 29603.02 | 47.61% | 14380.47 | 32770.52 | 18390.05 | 127.9% | 36732.52 | 40796.97 | 4064.45 | 11.06% | 4339.97 | 5495.5 | 1155.53 | 26.63% | 6723 | 7453.91 | 730.91 | 10.87% | 174 | 300.25 | 126.25 | 72.56% | 2021-11-03 01:00
Hamilton | 2022 | 451174 | 154 Main St.E (Condo Temp) | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Oosterlinck, David | Macdougall, Stephen | 126353.75 | 109176.03 | -17177.72 | -13.59% | 33286.8 | 104.94 | -33181.86 | -99.68% | 16357.91 | 11662.92 | -4694.99 | -28.7% | 8274 | 0 | -8274 | -100% | 68435.04 | 874.53 | -67560.51 | -98.72% | 347 | 299.75 | -47.25 | -13.62% | 2022-11-04 01:00
Hamilton | 2019 | 451187 | 360 Beach Rd | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 583.13 | 583.13 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451188 | 215 Ottawa St N | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 970.73 | 970.73 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451196 | Lynden Rd Large Load Move | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 692.84 | 692.84 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451198 | Beach TS Pole Brace | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Jolie, Chris | Brian Robinson | 0 | 13735.87 | 13735.87 |  | 0 | 2235.87 | 2235.87 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 11500 | 11500 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451201 | Pole Residual – 2017 Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 90767.74 | 77233.2 | -13534.54 | -14.91% | 34761.77 | 0 | -34761.77 | -100% | 32183.36 | 18038.44 | -14144.92 | -43.95% | 10670.1 | 0 | -10670.1 | -100% | 13152.51 | 0 | -13152.51 | -100% | 505 | 627.5 | 122.5 | 24.26% | 2019-05-25
Hamilton | 2020 | 451208 | Kicker Can Removal – 49 Gage Ave N | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Brian Robinson | 0 | 3924.25 | 3924.25 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-16 01:00
Hamilton | 2022 | 451209 | 461 King St. E - Service Relocation | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Paesano, Andrew | Koeppe, Jeffrey | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-16 01:00
Hamilton | 2019 | 451210 | 2017 Pole Residuals Contracted - P1 | 99 | COMPLETE | BOM not accurate | Cont Est Under | N/A |  | No | Celic, Dusan | XPopiel, Joseph | 49623.56 | 53324.39 | 3700.83 | 7.458% | 29578.75 | 28476 | -1102.75 | -3.728% | 7484.53 | 5609.91 | -1874.62 | -25.05% | 6483.88 | 8221.5 | 1737.62 | 26.8% | 6076.4 | 10928.67 | 4852.27 | 79.85% | 423 | 477.55 | 54.55 | 12.9% | 2019-04-16 01:00
Hamilton | 2019 | 451211 | 2016 Pole Residuals Contracted - P2 | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 52494.47 | 80572.69 | 28078.22 | 53.49% | 28685.07 | 200.92 | -28484.15 | -99.3% | 8288.95 | 9926.77 | 1637.82 | 19.76% | 9466.75 | 0 | -9466.75 | -100% | 6053.7 | 0 | -6053.7 | -100% | 452.5 | 396.5 | -56 | -12.38% | 2019-08-22 01:00
Hamilton | 2019 | 451212 | East 36th Kicker Can Removal | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 518.12 | 518.12 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451215 | 125 Rifle Range Rd, Hamilton | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 451217 | 24 Ditton Dr, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Andrew Mehlenbacher | 6292.33 | 0 | -6292.33 | -100% | 2279.59 | 0 | -2279.59 | -100% | 564.9 | 0 | -564.9 | -100% | 93.24 | 0 | -93.24 | -100% | 3354.6 | 0 | -3354.6 | -100% | 33.5 | 17.5 | -16 | -47.76% | 2019-11-06 01:00
Hamilton | 2020 | 451218 | 135 Trenholme Cres, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2020 | 451219 | 12 West Ave, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1.5 | 1.5 |  | 2019-05-29
Hamilton | 2022 | 451220 | 2016 Hamilton Pole Residual | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | Yes | Paesano, Andrew | Koeppe, Jeffrey | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451224 | 385 McNeilly Rd - CN Rail | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 2335.96 | 2335.96 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451227 | 793 Beach Blvd | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451228 | 500 James St N | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451231 | 29 Linden St | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 402.74 | 402.74 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451242 | Park and Cross Guy Move | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2022 | 451243 | Hamilton LBDS Replacements - 2016 | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | Yes | Paesano, Andrew | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2022 | 451244 | RFC template | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Morris, Mark | Caucci, Jason | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451245 | 140 Kenilworth Ave N Parkette | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451246 | 129 Rebecca St | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 586.74 | 586.74 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451248 | V3578 | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jolie, Chris | Hewitson, Trevor | 0 | 522.17 | 522.17 |  | 0 | 261.59 | 261.59 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451249 | 224 James St S Temp Disc OT | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Johnson, William | Jakubowski, Mark | 0 | 6250.99 | 6250.99 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451250 | Re-banding 491X and 492X | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 10565.39 | 10565.39 |  | 0 | 10154.31 | 10154.31 |  | 0 | 131.94 | 131.94 |  | 0 | 279.14 | 279.14 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2020 | 451253 | Victora Ave N Pole Move - CN | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 120876.21 | 151400.95 | 30524.74 | 25.25% | 11053.83 | 16776.84 | 5723.01 | 51.77% | 11428.19 | 18615.68 | 7187.49 | 62.89% | 0 | 380 | 380 |  | 98394.19 | 94994.69 | -3399.5 | -3.455% | 24 | 41.5 | 17.5 | 72.92% | 2020-02-25 01:00
Hamilton | 2019 | 451254 | 300 King St W, Ham | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 2502 | 2502 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2502 | 2502 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451255 | 2017 Ham LBDS Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Billone, Justin | Carr, Brad | 57889.5 | 58801.71 | 912.21 | 1.576% | 7817.66 | 2676.63 | -5141.03 | -65.76% | 23315.26 | 20039.79 | -3275.47 | -14.05% | 283 | 0 | -283 | -100% | 26473.58 | 29207.32 | 2733.74 | 10.33% | 105 | 89 | -16 | -15.24% | 2019-09-25 01:00
Hamilton | 2020 | 451258 | Stryker Development | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451259 | Manhole Lid Replacements - 2018 | 99 | CANCELLED | N/A | N/A | N/A |  | Yes | Johnson, William | Jakubowski, Mark | 0 | 1552.87 | 1552.87 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451260 | 43 Woodbine Cres | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Koeppe, Jeffrey | 3487.86 | 2342.91 | -1144.95 | -32.83% | 2762.92 | 0 | -2762.92 | -100% | 248.24 | 0 | -248.24 | -100% | 476.7 | 0 | -476.7 | -100% | 0 | 0 | 0 |  | 63 | 14 | -49 | -77.78% | 2019-06-06
Hamilton | 2019 | 451262 | Hamilton Port Authority Pole Moves | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Weaver, Thomas | 0 | 52536.01 | 52536.01 |  | 0 | 5767.74 | 5767.74 |  | 0 | 44825.7 | 44825.7 |  | 0 | 1351 | 1351 |  | 0 | 0 | 0 |  | 0 | 65 | 65 |  | 2019-05-29
Hamilton | 2019 | 451263 | 725 Limeridge Road East | 99 | COMPLETE | Labour est. under | N/A | N/A | Jakubowski, Mark | No | Johnson, William | Koeppe, Jeffrey | 20766.05 | 27280.07 | 6514.02 | 31.37% | 10294.98 | 0 | -10294.98 | -100% | 3630.4 | 5717.82 | 2087.42 | 57.5% | 3275.9 | 0 | -3275.9 | -100% | 3564.77 | 0 | -3564.77 | -100% | 144 | 186 | 42 | 29.17% | 2019-05-06
Hamilton | 2020 | 451281 | John Substation Conversion | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 1506387.16 | 1549365.23 | 42978.07 | 2.853% | 91339.52 | 85530.62 | -5808.9 | -6.36% | 302091.31 | 325999.33 | 23908.02 | 7.914% | 3056.4 | 1068.75 | -1987.65 | -65.03% | 1109899.93 | 922332.71 | -187567.22 | -16.9% | 1203 | 1058.25 | -144.75 | -12.03% | 2020-02-25 01:00
Hamilton | 2019 | 451284 | Victory Subdivision - Phase 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Andrew Mehlenbacher | 15514.66 | 99243.67 | 83729.01 | 539.7% | 11730.79 | 348.43 | -11382.36 | -97.03% | 1911.27 | 2741.92 | 830.65 | 43.46% | 1872.6 | 0 | -1872.6 | -100% | 0 | 0 | 0 |  | 168.5 | 185 | 16.5 | 9.792% | 2019-04-16 01:00
Hamilton | 2020 | 451286 | Stoneycreek Mountain URD | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | Yes | Alectra Utilities | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-09 01:00
Hamilton | 2022 | 451294 | ROAD AUTHORITY - MOUNTAINBROW RD AND WATERDOWN RD WIDENING | 99 | COMPLETE | Under 10% | BOM not accurate |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 307077.65 | 301192.79 | -5884.86 | -1.916% | 28630.97 | 32507.7 | 3876.73 | 13.54% | 45710.65 | 64406.99 | 18696.34 | 40.9% | 384 | 0 | -384 | -100% | 232352.03 | 186563.81 | -45788.22 | -19.71% | 24 | 8 | -16 | -66.67% | 2022-04-22
Hamilton | 2022 | 451300 | TX Move Ottawa St -Constellation Dr | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Paesano, Andrew | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-31 01:00
Hamilton | 2021 | 451310 | 1361 Upper Sherman Ave, Hamilton | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Laus, Tomislav | Andrew Mehlenbacher | 2685.52 | 0 | -2685.52 | -100% | 2554.22 | 0 | -2554.22 | -100% | 0 | 0 | 0 |  | 115.84 | 0 | -115.84 | -100% | 0 | 0 | 0 |  | 43 | 16 | -27 | -62.79% | 2021-06-03 01:00
Hamilton | 2019 | 451311 | 36 Ditton Dr, Hamilton | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Laus, Tomislav | Tony Ierace | 64174.97 | 57555.82 | -6619.15 | -10.31% | 9044.5 | 5926.87 | -3117.63 | -34.47% | 28715.51 | 22350.36 | -6365.15 | -22.17% | 1551.4 | 468 | -1083.4 | -69.83% | 24863.56 | 0 | -24863.56 | -100% | 139 | 136 | -3 | -2.158% | 2019-11-21 01:00
Hamilton | 2021 | 451312 | 78 Philomena Dr, Hamilton | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Laus, Tomislav | Brad Carr | 1268.79 | 0 | -1268.79 | -100% | 1218.15 | 0 | -1218.15 | -100% | 0 | 0 | 0 |  | 50.64 | 0 | -50.64 | -100% | 0 | 0 | 0 |  | 17 | 12 | -5 | -29.41% | 2021-06-03 01:00
Hamilton | 2021 | 451313 | Upper Wentworth & Rymal Rd E, Ham | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Laus, Tomislav | Brad Carr | 1826.42 | 0 | -1826.42 | -100% | 1374.28 | 0 | -1374.28 | -100% | 0 | 0 | 0 |  | 274 | 0 | -274 | -100% | 0 | 0 | 0 |  | 37 | 20.5 | -16.5 | -44.59% | 2021-06-03 01:00
Hamilton | 2019 | 451318 | 1670 Garth St, Hamilton | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Laus, Tomislav | Roy Owen | 60457.21 | 69250.83 | 8793.62 | 14.55% | 11140.32 | 2389.77 | -8750.55 | -78.55% | 41097.65 | 45645.62 | 4547.97 | 11.07% | 1664.04 | 585 | -1079.04 | -64.84% | 6555.2 | 0 | -6555.2 | -100% | 172.5 | 213.75 | 41.25 | 23.91% | 2019-11-09 01:00
Hamilton | 2019 | 451320 | 652 Lawerence Rd, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Laus, Tomislav | Koeppe, Jeffrey | 45277.69 | 0 | -45277.69 | -100% | 14416.12 | 0 | -14416.12 | -100% | 16005.47 | 0 | -16005.47 | -100% | 5017.4 | 0 | -5017.4 | -100% | 9838.7 | 0 | -9838.7 | -100% | 213 | 30 | -183 | -85.92% | 2019-11-07 01:00
Hamilton | 2019 | 451321 | 26 Upper Mount Albion Rd, Hamilton | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Laus, Tomislav | Roy Owen | 60313.51 | 61596.1 | 1282.59 | 2.127% | 11581.94 | 3138.45 | -8443.49 | -72.9% | 31420.17 | 36841.42 | 5421.25 | 17.25% | 2246.2 | 714 | -1532.2 | -68.21% | 15065.2 | 0 | -15065.2 | -100% | 181.5 | 195 | 13.5 | 7.438% | 2019-09-26 01:00
Hamilton | 2020 | 451330 | 120 Springvally Cres, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1292.56 | 1292.56 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-29 01:00
Hamilton | 2020 | 451331 | 1342 Stone Church Rd E, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1752.87 | 1752.87 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-29 01:00
Hamilton | 2022 | 451332 | 47 Wentworth St S, Hamilton | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-29 01:00
Hamilton | 2020 | 451333 | 191 James St N, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 3332.02 | 3332.02 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-29 01:00
Hamilton | 2020 | 451334 | 685 Robson Rd, Waterdown | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1290.99 | 1290.99 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-29 01:00
Hamilton | 2019 | 451336 | 30 Hamilton St S, Waterdown | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 63228.04 | 74817.77 | 11589.73 | 18.33% | 10945.18 | 830.12 | -10115.06 | -92.42% | 34107.52 | 43141.09 | 9033.57 | 26.49% | 2965.8 | 0 | -2965.8 | -100% | 15209.54 | 0 | -15209.54 | -100% | 170 | 215 | 45 | 26.47% | 2019-06-29 01:00
Hamilton | 2021 | 451337 | 212 KING WILLIAM ST, HAMILTON | 95 | COMPLETE | Converted Project | BOM – truck stock |  | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 21546.59 | 26042.21 | 4495.62 | 20.86% | 5681.34 | 11728.82 | 6047.48 | 106.4% | 14548.43 | 6499.64 | -8048.79 | -55.32% | 1316.82 | 946 | -370.82 | -28.16% | 0 | 1166.36 | 1166.36 |  | 88.17 | 93.5 | 5.33 | 6.045% | 2021-11-05 01:00
Hamilton | 2020 | 451338 | 111 Church St, st catharines | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Frank Giancola | 67288.03 | 56224.67 | -11063.36 | -16.44% | 9800 | 12742.41 | 2942.41 | 30.02% | 2765.4 | 30917.06 | 28151.66 | 1018% | 33760.88 | 1839 | -31921.88 | -94.55% | 20961.75 | 2844.25 | -18117.5 | -86.43% | 289 | 263.25 | -25.75 | -8.91% | 2020-01-08 01:00
Hamilton | 2022 | 451339 | 1070 Main St W - Padmount Tx | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Wardell, Paul | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-03 01:00
Hamilton | 2020 | 451340 | 2017 Pole Residual - Stirton St | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Jakubowski, Mark | 0 | 1839.75 | 1839.75 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-03 01:00
Hamilton | 2019 | 451342 | 101 Shoreview Place, Stoney Creek | 99 | COMPLETE | Labour est. under | Cont Est Over | N/A | Jakubowski, Mark | No | Patel, Ketan | Andrew Mehlenbacher | 121554.13 | 128657.73 | 7103.6 | 5.844% | 14772.82 | 0 | -14772.82 | -100% | 100071.61 | 106138.18 | 6066.57 | 6.062% | 2509.7 | 0 | -2509.7 | -100% | 4200 | 0 | -4200 | -100% | 226 | 269 | 43 | 19.03% | 2019-05-03 01:00
Hamilton | 2019 | 451343 | Stroud Lane 4 Conversion (2018) | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Wardell, Paul | Andrew Mehlenbacher | 124400.98 | 145666.4 | 21265.42 | 17.09% | 53275.3 | 20174.87 | -33100.43 | -62.13% | 28793.88 | 31166.48 | 2372.6 | 8.24% | 5048.1 | 3847 | -1201.1 | -23.79% | 37283.7 | 10521.4 | -26762.3 | -71.78% | 711 | 725.05 | 14.05 | 1.976% | 2019-08-16 01:00
Hamilton | 2022 | 451345 | Huxley Ave South - Pole Replacement | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | Yes | Paesano, Andrew | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-07
Hamilton | 2019 | 451349 | 367 5th Concession Rd East | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 1756.59 | 1756.59 |  | 0 | 1756.59 | 1756.59 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 30.5 | 30.5 |  | 2019-05-07
Hamilton | 2019 | 451350 | V3326 Replacement | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jolie, Chris | Jakubowski, Mark | 0 | 352.03 | 352.03 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451351 | 1040 Main St E (Gage Pk. Greenhse) | 98 | COMPLETE | Converted Project |  |  | Rao, Faisal | No | Montgomery, Michael | Koeppe, Jeffrey | 75541.87 | 78774.88 | 3233.01 | 4.28% | 15354.74 | 0 | -15354.74 | -100% | 49311.73 | 42134.5 | -7177.23 | -14.55% | 5898 | 0 | -5898 | -100% | 4977.4 | 0 | -4977.4 | -100% | 321 | 372.5 | 51.5 | 16.04% | 2019-05-14
Hamilton | 2019 | 451358 | 2017 Rogers Work | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jolie, Chris | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451362 | 5272x - 0622x tie - CE conversion | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Wardell, Paul | Roy Owen | 363827.32 | 400143.74 | 36316.42 | 9.982% | 64113 | 15116.54 | -48996.46 | -76.42% | 218032.8 | 256524.83 | 38492.03 | 17.65% | 5978.2 | 4536 | -1442.2 | -24.12% | 75703.32 | 19965.48 | -55737.84 | -73.63% | 804 | 1162.4 | 358.4 | 44.58% | 2019-08-10 01:00
Hamilton | 2019 | 451369 | Upper Mount Albion - Overhead | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 442266.72 | 420024.65 | -22242.07 | -5.029% | 200050.36 | 43460.71 | -156589.65 | -78.28% | 127576.18 | 109777.5 | -17798.68 | -13.95% | 59205.44 | 13193 | -46012.44 | -77.72% | 55434.74 | 23880.84 | -31553.9 | -56.92% | 2805 | 2335.5 | -469.5 | -16.74% | 2019-09-27 01:00
Hamilton | 2020 | 451370 | York Rd Bridge Alterations | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451371 | 2017 HCE Telecomm Work | 99 | CANCELLED | N/A |  |  | Vande Kuyt, Greg | No | Jolie, Chris | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2020 | 451374 | TX Structure Removal – Melvin Ave | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Jakubowski, Mark | 0 | 1749.31 | 1749.31 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-21 01:00
Hamilton | 2019 | 451379 | Branthaven Dakota Phase 2 | 99 | COMPLETE | Converted Project |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Tony Ierace | 21196.76 | 477737.27 | 456540.51 | 2154% | 18799.75 | 1530.85 | -17268.9 | -91.86% | 0 | 1547.44 | 1547.44 |  | 2397.01 | 0 | -2397.01 | -100% | 0 | 532.26 | 532.26 |  | 383.25 | 245.5 | -137.75 | -35.94% | 2019-08-21 01:00
Hamilton | 2022 | 451380 | 64 Main St East, Hamilton | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-16
Hamilton | 2019 | 451382 | 2 Oriole Cres | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Dragojevic, Igor | Andrew Mehlenbacher | 18277.66 | 22941.13 | 4663.47 | 25.51% | 5978.48 | 602.48 | -5376 | -89.92% | 3209.92 | 0 | -3209.92 | -100% | 409.7 | 0 | -409.7 | -100% | 8649.2 | 7531 | -1118.2 | -12.93% | 90 | 83.75 | -6.25 | -6.944% | 2019-07-05 01:00
Hamilton | 2019 | 451383 | 419 Dewitt Rd | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Dragojevic, Igor | Koeppe, Jeffrey | 69717.05 | 68603.03 | -1114.02 | -1.598% | 18653.37 | 11453.37 | -7200 | -38.6% | 31208.61 | 27863.15 | -3345.46 | -10.72% | 3530.3 | 2380 | -1150.3 | -32.58% | 16324.77 | 11810 | -4514.77 | -27.66% | 262 | 303.5 | 41.5 | 15.84% | 2019-12-07 01:00
Hamilton | 2020 | 451388 | 108 James St N, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-17 01:00
Hamilton | 2021 | 451392 | Celtic Dr. - 8kV Conversion | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 1550275.51 | 1573258.45 | 22982.94 | 1.483% | 27936.45 | 141936.7 | 114000.25 | 408.1% | 196102.74 | 221598.16 | 25495.42 | 13% | 1050 | 1937.52 | 887.52 | 84.53% | 1325186.32 | 1169901.3 | -155285.02 | -11.72% | 80 | 93.5 | 13.5 | 16.88% | 2021-06-17 01:00
Hamilton | 2020 | 451398 | 500 James St N, Hamilton | 98 | COMPLETE | Converted Project |  |  | Frigotto, Rodrigo | No | Alectra Utilities | Roy Owen | 105937.24 | 93560.91 | -12376.33 | -11.68% | 11792.7 | 11187.11 | -605.59 | -5.135% | 35565.5 | 35841.55 | 276.05 | 0.7762% | 1609.5 | 1736.43 | 126.93 | 7.886% | 56969.54 | 41263.39 | -15706.15 | -27.57% | 172 | 133 | -39 | -22.67% | 2020-04-09 01:00
Hamilton | 2020 | 451399 | 202 Valley Rd, Waterdown | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 484.14 | 484.14 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-26 01:00
Hamilton | 2020 | 451400 | 581 Barton St E, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-26 01:00
Hamilton | 2019 | 451401 | 18 West Ave S, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Koeppe, Jeffrey | 28426.09 | 26964.81 | -1461.28 | -5.141% | 7614.58 | 2713.05 | -4901.53 | -64.37% | 8803.87 | 9953.74 | 1149.87 | 13.06% | 2241.1 | 498 | -1743.1 | -77.78% | 9766.54 | 6754 | -3012.54 | -30.85% | 113 | 105.75 | -7.25 | -6.416% | 2019-10-26 01:00
Hamilton | 2020 | 451402 | 823 Highway 6 N, Waterdown | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-26 01:00
Hamilton | 2022 | 451403 | 470 Upper Sherman Ave, Hamilton | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-26 01:00
Hamilton | 2020 | 451404 | 823 Highway 6 N, Waterdown | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 9994.68 | 0 | -9994.68 | -100% | 2767.92 | 0 | -2767.92 | -100% | 1038.41 | 0 | -1038.41 | -100% | 763.3 | 0 | -763.3 | -100% | 5425.05 | 0 | -5425.05 | -100% | 0 | 0 | 0 |  | 2019-01-26 01:00
Hamilton | 2020 | 451405 | 81 Skylark Dr, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-26 01:00
Hamilton | 2020 | 451406 | 470 Upper Sherman Ave, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 7027.54 | 0 | -7027.54 | -100% | 1424.84 | 0 | -1424.84 | -100% | 0 | 0 | 0 |  | 378.3 | 0 | -378.3 | -100% | 5224.4 | 0 | -5224.4 | -100% | 0 | 0 | 0 |  | 2019-01-26 01:00
Hamilton | 2022 | 451407 | 488 Rymal Rd E, Hamilton | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-26 01:00
Hamilton | 2019 | 451408 | 110 Bellagio Ave, stoney creek | 99 | COMPLETE | Labour est. over | Scope change - unforeseen | BOM not used | Paesano, Andrew | No | Laus, Tomislav | Andrew Mehlenbacher | 42962.92 | 37436.77 | -5526.15 | -12.86% | 7767.37 | 0 | -7767.37 | -100% | 33603.55 | 0 | -33603.55 | -100% | 1592 | 0 | -1592 | -100% | 0 | 0 | 0 |  | 112 | 111 | -1 | -0.8929% | 2019-01-26 01:00
Hamilton | 2019 | 451410 | York Conversion Phase 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Karan, Andjelo | Carr, Brad | 1724800.52 | 2201341.19 | 476540.67 | 27.63% | 52356.49 | 35960.93 | -16395.56 | -31.32% | 271718.1 | 309079.36 | 37361.26 | 13.75% | 6678.8 | 0 | -6678.8 | -100% | 1394047.13 | 440563.43 | -953483.7 | -68.4% | 471 | 472.75 | 1.75 | 0.3715% | 2019-06-21 01:00
Hamilton | 2020 | 451411 | Main / Hess Apartments | 99 | CANCELLED | N/A | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Jakubowski, Mark | 0 | 30311.74 | 30311.74 |  | 0 | 0 | 0 |  | 0 | 43.11 | 43.11 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-30 01:00
Hamilton | 2021 | 451413 | HALSON SS CLEANUP | 99 | CANCELLED | N/A |  |  | Newitt, Andrew | No | Vandekuyt, Greg | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-30 01:00
Hamilton | 2020 | 451419 | 357 Wilson St E | 98 | COMPLETE | Converted Project |  |  | Frigotto, Rodrigo | No | Alectra Utilities | Koeppe, Jeffrey | 139201.23 | 158113.91 | 18912.68 | 13.59% | 27603.83 | 28573.66 | 969.83 | 3.513% | 42439.26 | 44719.17 | 2279.91 | 5.372% | 5045.6 | 7669.93 | 2624.33 | 52.01% | 64112.54 | 62960 | -1152.54 | -1.798% | 378 | 480.5 | 102.5 | 27.12% | 2020-01-30 01:00
Hamilton | 2019 | 451420 | 2 Bulls Lane | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Montgomery, Michael | Roy Owen | 72246.76 | 137909.32 | 65662.56 | 90.89% | 17782.25 | 23779.5 | 5997.25 | 33.73% | 11314.31 | 9927.85 | -1386.46 | -12.25% | 2427.2 | 3681 | 1253.8 | 51.66% | 40723 | 86283.98 | 45560.98 | 111.9% | 274 | 319.75 | 45.75 | 16.7% | 2019-10-02 01:00
Hamilton | 2020 | 451421 | 130 Osler Dr. DUN | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 23929.97 | 21892.79 | -2037.18 | -8.513% | 9048.03 | 271.18 | -8776.85 | -97% | 11961.44 | 11639.31 | -322.13 | -2.693% | 1160.5 | 0 | -1160.5 | -100% | 1760 | 492.76 | -1267.24 | -72% | 115 | 111.25 | -3.75 | -3.261% | 2020-01-07 01:00
Hamilton | 2020 | 451422 | 375 Wilson St. East | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 181057.6 | 293344.59 | 112286.99 | 62.02% | 33147.13 | 55071.9 | 21924.77 | 66.14% | 30873.58 | 52091.39 | 21217.81 | 68.72% | 5164.2 | 16426.38 | 11262.18 | 218.1% | 111872.69 | 163168.38 | 51295.69 | 45.85% | 494 | 634 | 140 | 28.34% | 2020-07-14 01:00
Hamilton | 2020 | 451423 | 153 Nash Rd. S HAM | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-15 01:00
Hamilton | 2020 | 451424 | 1 Redfern Ave. (Scenic Woods Dev) (Temp) | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 94642.19 | 91490.6 | -3151.59 | -3.33% | 14122.75 | 920.72 | -13202.03 | -93.48% | 52623.7 | 47023.84 | -5599.86 | -10.64% | 1956.2 | 0 | -1956.2 | -100% | 25939.54 | 0 | -25939.54 | -100% | 207 | 223.25 | 16.25 | 7.85% | 2020-01-15 01:00
Hamilton | 2019 | 451425 | 1615 Upper Wellington St. | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 1463.79 | 1463.79 |  | 0 | 1463.79 | 1463.79 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 23 | 23 |  | 2019-05-07
Hamilton | 2020 | 451426 | 428 Main St. W HAM | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-16 01:00
Hamilton | 2019 | 451427 | 177 Sherman Ave. N | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Montgomery, Michael | Koeppe, Jeffrey | 27794.52 | 34773.48 | 6978.96 | 25.11% | 14061.04 | 16253.99 | 2192.95 | 15.6% | 10807.78 | 11503.25 | 695.47 | 6.435% | 2925.7 | 868.48 | -2057.22 | -70.32% | 0 | 0 | 0 |  | 192.5 | 251.5 | 59 | 30.65% | 2019-04-16 01:00
Hamilton | 2020 | 451428 | 1 Redfern Ave. HAM | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-31 01:00
Hamilton | 2020 | 451429 | 440 Victoria Ave. N HAM | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 51618.37 | 63212.81 | 11594.44 | 22.46% | 21370.36 | 16629.6 | -4740.76 | -22.18% | 26993.2 | 36782.62 | 9789.42 | 36.27% | 3254.81 | 6493.75 | 3238.94 | 99.51% | 0 | 0 | 0 |  | 160 | 212.25 | 52.25 | 32.66% | 2020-01-31 01:00
Hamilton | 2019 | 451430 | 5th Concession - Phase 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Billone, Justin | Carr, Brad | 1586081 | 1724943.96 | 138862.96 | 8.755% | 76885.87 | 12626.68 | -64259.19 | -83.58% | 310923.06 | 446486.44 | 135563.38 | 43.6% | 5660 | 380 | -5280 | -93.29% | 1192612.07 | 122887.74 | -1069724.33 | -89.7% | 1059 | 943.55 | -115.45 | -10.9% | 2019-11-27 01:00
Hamilton | 2019 | 451431 | 2017 Cogeco Permit Review | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-23 01:00
Hamilton | 2019 | 451447 | York Conversion - OH Removals | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Karan, Andjelo | Carr, Brad | 47777.36 | 36810.71 | -10966.65 | -22.95% | 45450 | 4528.71 | -40921.29 | -90.04% | 169.8 | 0 | -169.8 | -100% | 0 | 456 | 456 |  | 2157.56 | 31307.36 | 29149.8 | 1351% | 30 | 41.5 | 11.5 | 38.33% | 2019-07-19 01:00
Hamilton | 2019 | 451450 | Upper Sherman / Rymal | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Jolie, Chris | Koeppe, Jeffrey | 125845.46 | 111832.8 | -14012.66 | -11.13% | 31555.16 | 5450.37 | -26104.79 | -82.73% | 78357.4 | 55328.62 | -23028.78 | -29.39% | 10879.2 | 0 | -10879.2 | -100% | 5053.7 | 0 | -5053.7 | -100% | 467 | 508.5 | 41.5 | 8.887% | 2019-06-03
Hamilton | 2019 | 451458 | HUC250 | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 1280.07 | 1280.07 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-30 01:00
Hamilton | 2019 | 451463 | HUC1045 - FIT - 1045 Upper Paradise Road | 99 | COMPLETE | N/A | N/A | N/A |  | No | Lustrinelli, Mark | Weaver, Thomas | 0 | 272 | 272 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-30 01:00
Hamilton | 2019 | 451467 | 81 Robinson St, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Roy Owen | 51234.09 | 50628.1 | -605.99 | -1.183% | 12556.1 | 0 | -12556.1 | -100% | 37286.99 | 37801.41 | 514.42 | 1.38% | 1391 | 0 | -1391 | -100% | 0 | 0 | 0 |  | 185 | 163.25 | -21.75 | -11.76% | 2019-06-07
Hamilton | 2020 | 451468 | Gibson Ave - Development | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Koeppe, Jeffrey | 32426.75 | 96197.66 | 63770.91 | 196.7% | 18546.8 | 25563.25 | 7016.45 | 37.83% | 10232.38 | 11773.71 | 1541.33 | 15.06% | 3325.32 | 8282.66 | 4957.34 | 149.1% | 322.25 | 1119.03 | 796.78 | 247.3% | 161 | 302 | 141 | 87.58% | 2020-02-01 01:00
Hamilton | 2021 | 451469 | Elgin TS Rebuild Phase 2 | 99 | COMPLETE | Converted Project | 3rd party plant | Labour est. under | Vande Kuyt, Greg | No | Lustrinelli, Mark | Andrew Mehlenbacher | 1327490.81 | 1548300.4 | 220809.59 | 16.63% | 443235.25 | 505938.74 | 62703.49 | 14.15% | 816688.86 | 826835.65 | 10146.79 | 1.242% | 67566.7 | 65451.84 | -2114.86 | -3.13% | 0 | 10258.68 | 10258.68 |  | 6973 | 7945.25 | 972.25 | 13.94% | 2021-10-18 01:00
Hamilton | 2022 | 451477 | SILVERWOOD HOMES PHASE 1C - SUBD RES EDS | 99 | COMPLETE | Inaccurate design |  |  | Velickovski, Goran | No | Morris, Mark | Roy Owen | 9008.43 | 12193.23 | 3184.8 | 35.35% | 8285.3 | 5797.62 | -2487.68 | -30.03% | 70.87 | 70.79 | -0.08 | -0.1129% | 652.26 | 702 | 49.74 | 7.626% | 0 | 3750 | 3750 |  | 34.39 | 66 | 31.61 | 91.92% | 2022-05-17 01:00
Hamilton | 2020 | 451488 | 807 Alexander Rd, Ancaster | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-25 01:00
Hamilton | 2020 | 451490 | 297 Ottawa St N , Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Hotham, Matthew | 17606.93 | 0 | -17606.93 | -100% | 2797.26 | 0 | -2797.26 | -100% | 516.87 | 0 | -516.87 | -100% | 804.4 | 0 | -804.4 | -100% | 13488.4 | 0 | -13488.4 | -100% | 0 | 0 | 0 |  | 2021-08-25 01:00
Hamilton | 2020 | 451491 | 272 Park St S, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-25 01:00
Hamilton | 2022 | 451492 | 95 Jerome Park Dr, Hamilton | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-25 01:00
Hamilton | 2020 | 451493 | 64 Munroe St, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-25 01:00
Hamilton | 2020 | 451494 | 360 Beach Rd, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-25 01:00
Hamilton | 2022 | 451495 | 6 Lesterwood St | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-25 01:00
Hamilton | 2021 | 451497 | 592 Old Dundas Rd, Ancaster - S.T.P | 98 | COMPLETE | Labour est. over |  |  | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 80929.15 | 72274.05 | -8655.1 | -10.69% | 34483.59 | 16793.69 | -17689.9 | -51.3% | 23990.36 | 29151.16 | 5160.8 | 21.51% | 1753.2 | 5274.41 | 3521.21 | 200.8% | 20702 | 18245.07 | -2456.93 | -11.87% | 96 | 213 | 117 | 121.9% | 2021-08-25 01:00
Hamilton | 2019 | 451510 | Eringate Court - Development | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Gamboa, Henry | No | Morris, Mark | Andrew Mehlenbacher | 13387.75 | 8463.59 | -4924.16 | -36.78% | 11583.99 | 0 | -11583.99 | -100% | 132.16 | 0 | -132.16 | -100% | 0 | 0 | 0 |  | 1671.6 | 0 | -1671.6 | -100% | 173 | 104.25 | -68.75 | -39.74% | 2019-02-28 01:00
Hamilton | 2022 | 451513 | 1911 Barton St E | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Dragojevic, Igor | Hotham, Matthew | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-19 01:00
Hamilton | 2020 | 451514 | 467 Charlton Ave E | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Koeppe, Jeffrey | 170170.03 | 176332.4 | 6162.37 | 3.621% | 32370.22 | 14924.6 | -17445.62 | -53.89% | 90493.31 | 89434.05 | -1059.26 | -1.171% | 5856.5 | 3123 | -2733.5 | -46.67% | 41450 | 44083.25 | 2633.25 | 6.353% | 459 | 464.5 | 5.5 | 1.198% | 2020-06-19 01:00
Hamilton | 2019 | 451516 | 4th Concession Road Upgrade | 99 | COMPLETE | Converted Project | N/A | N/A | McAlpine, Robert | No | Paesano, Andrew | Weaver, Thomas | 0 | 1150.1 | 1150.1 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 | 4 |  | 2019-05-07
Hamilton | 2020 | 451525 | TX Room Decommission-28 Rebecca ST | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-03 01:00
Hamilton | 2020 | 451526 | Central Park - Development | 99 | COMPLETE | Converted Project |  |  | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 35755.48 | 729978.51 | 694223.03 | 1942% | 21548.4 | 6229.81 | -15318.59 | -71.09% | 10365.28 | 13641.15 | 3275.87 | 31.6% | 3841.8 | 1284.89 | -2556.91 | -66.56% | 0 | 0 | 0 |  | 331 | 315 | -16 | -4.834% | 2020-02-03 01:00
Hamilton | 2019 | 451528 | ABERDEEN 2 - 2nd Phase Conversion | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Anderson, Dean | Carr, Brad | 2027116.39 | 2161806.35 | 134689.96 | 6.644% | 52396.26 | 20661.58 | -31734.68 | -60.57% | 396061.38 | 504510.66 | 108449.28 | 27.38% | 4334 | 76 | -4258 | -98.25% | 1574324.75 | 252149.81 | -1322174.94 | -83.98% | 730 | 627.75 | -102.25 | -14.01% | 2019-07-11 01:00
Hamilton | 2019 | 451533 | 2120 Rymal Rd E | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Paesano, Andrew | No | Laus, Tomislav | Andrew Mehlenbacher | 89224.85 | 91231.38 | 2006.53 | 2.249% | 15154.39 | 0 | -15154.39 | -100% | 44241.89 | 0 | -44241.89 | -100% | 3138.8 | 0 | -3138.8 | -100% | 26689.77 | 0 | -26689.77 | -100% | 230 | 193.5 | -36.5 | -15.87% | 2019-01-08 01:00
Hamilton | 2020 | 451537 | Confederation Beach Sports Park | 98 | COMPLETE | Labour est. over |  |  | Paesano, Andrew | No | Alectra Utilities | Roy Owen | 54489 | 52769.08 | -1719.92 | -3.156% | 21409.68 | 12823.82 | -8585.86 | -40.1% | 23602.32 | 25797.53 | 2195.21 | 9.301% | 2878.2 | 4551.16 | 1672.96 | 58.13% | 6598.8 | 6139.35 | -459.45 | -6.963% | 173 | 138 | -35 | -20.23% | 2020-09-25 01:00
Hamilton | 2020 | 451538 | 124 Balsam Ave S, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-29 01:00
Hamilton | 2022 | 451539 | 52 Ottawa St N, Hamilton - Temp | 95 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Laus, Tomislav | Macdougall, Stephen | 118948.7 | 113919.95 | -5028.75 | -4.228% | 60112.39 | 33348.33 | -26764.06 | -44.52% | 42294.77 | 45778.88 | 3484.11 | 8.238% | 5312 | 11138.01 | 5826.01 | 109.7% | 11229.54 | 9500.36 | -1729.18 | -15.4% | 573 | 596 | 23 | 4.014% | 2022-12-29 01:00
Hamilton | 2021 | 451540 | 155 Ontario St | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Morris, Mark | Weaver, Thomas | 0 | 752.24 | 752.24 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-08
Hamilton | 2019 | 451541 | 19 Page St | 99 | COMPLETE | N/A | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-08
Hamilton | 2022 | 451543 | 7 Everton Crt | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-08
Hamilton | 2019 | 451548 | 112 King St W, Dundas | 99 | COMPLETE | Under 10% | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Roy Owen | 11538.66 | 10605.46 | -933.2 | -8.088% | 4451.73 | 0 | -4451.73 | -100% | 481.09 | 500.95 | 19.86 | 4.128% | 405.3 | 0 | -405.3 | -100% | 6200.54 | 0 | -6200.54 | -100% | 61 | 58.25 | -2.75 | -4.508% | 2019-05-08
Hamilton | 2019 | 451549 | 8 Kingsborough Dr | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Dragojevic, Igor | Koeppe, Jeffrey | 25142.36 | 15441.23 | -9701.13 | -38.58% | 11783.2 | 450.1 | -11333.1 | -96.18% | 3244 | 5714 | 2470 | 76.14% | 2519.1 | 493.83 | -2025.27 | -80.4% | 7596.06 | 5626.29 | -1969.77 | -25.93% | 165.5 | 194.25 | 28.75 | 17.37% | 2019-04-16 01:00
Hamilton | 2020 | 451550 | 600 Tenth Rd E | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2020 | 451551 | 31 Ditton Dr | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2020 | 451552 | 1851 Brampton St | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2019 | 451558 | Longwood Rd Frid - Aberdeen | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jolie, Chris | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
Hamilton | 2020 | 451559 | Stroud Lane SS feeder removals | 99 | COMPLETE | Converted Project |  |  | Beaudrie, Scott | yes | Alectra Utilities | Andrew Mehlenbacher | 39722.27 | 24317 | -15405.27 | -38.78% | 31021.07 | 13755.08 | -17265.99 | -55.66% | 0 | 3493.93 | 3493.93 |  | 7701.2 | 1855.5 | -5845.7 | -75.91% | 1000 | 0 | -1000 | -100% | 508 | 258 | -250 | -49.21% | 2020-05-04
Hamilton | 2019 | 451560 | AB-2 Substation & Newton TS work | 99 | COMPLETE | BOM not accurate | N/A | N/A |  | No | Anderson, Dean | Roy Owen | 173802.73 | 178014.3 | 4211.57 | 2.423% | 33962.53 | 14395.02 | -19567.51 | -57.61% | 132855.19 | 140645.16 | 7789.97 | 5.864% | 5775.01 | 643.99 | -5131.02 | -88.85% | 1210 | 0 | -1210 | -100% | 557.11 | 150.75 | -406.36 | -72.94% | 2019-05-03 01:00
Hamilton | 2020 | 451561 | Juravinski Hosptial Back-up Feeder | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 1589878.05 | 1551290.28 | -38587.77 | -2.427% | 36955.16 | 76537.29 | 39582.13 | 107.1% | 298356.24 | 473875.15 | 175518.91 | 58.83% | 3305.8 | 741 | -2564.8 | -77.58% | 1251260.85 | 852019.55 | -399241.3 | -31.91% | 509.5 | 378.5 | -131 | -25.71% | 2020-02-15 01:00
Hamilton | 2021 | 451563 | 49 WALNUT ST.S (CONDO) | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Oosterlinck, David | Roy Owen | 15759.62 | 21264.75 | 5505.13 | 34.93% | 10868.61 | 13633.73 | 2765.12 | 25.44% | 3435.27 | 1308.47 | -2126.8 | -61.91% | 1455.74 | 1078 | -377.74 | -25.95% | 0 | 605.3 | 605.3 |  | 81.68 | 93.5 | 11.82 | 14.47% | 2021-04-26
Hamilton | 2020 | 451564 | Bell Pole - Winona Crossing | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 637.62 | 637.62 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2020 | 451567 | 659 Parkdale Ave | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 451569 | 158 Herkimer St | 99 | CANCELLED | N/A | N/A | N/A |  | No | Oosterlinck, David | Weaver, Thomas | 0 | 5785.46 | 5785.46 |  | 0 | 843.64 | 843.64 |  | 0 | 0 | 0 |  | 0 | 99 | 99 |  | 0 | 1129.54 | 1129.54 |  | 0 | 11 | 11 |  | 2019-06-07
Hamilton | 2022 | 451570 | 1280 RYMAL RD E | 98 | COMPLETE | Material Under Estimated | Labour est. under |  | Kappheim, Adam | No | Oosterlinck, David | Roy Owen | 321452.7 | 446616.27 | 125163.57 | 38.94% | 27477.1 | 82249.73 | 54772.63 | 199.3% | 265359.3 | 318672.94 | 53313.64 | 20.09% | 5380.3 | 15198.5 | 9818.2 | 182.5% | 23236 | 25020.95 | 1784.95 | 7.682% | 340.35 | 892.25 | 551.9 | 162.2% | 2022-02-18 01:00
Hamilton | 2019 | 451571 | 1318 Rymal Rd.E | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Roy Owen | 85121.86 | 77101.6 | -8020.26 | -9.422% | 34027.07 | 251.41 | -33775.66 | -99.26% | 47012.59 | 37278.8 | -9733.79 | -20.7% | 4082.2 | 0 | -4082.2 | -100% | 0 | 0 | 0 |  | 494 | 509.5 | 15.5 | 3.138% | 2019-04-06 01:00
Hamilton | 2021 | 451573 | WALNUT/JACKSON FEEDER EXPANSION | 98 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Jolie, Chris | Brad Carr | 659790.45 | 690508.9 | 30718.45 | 4.656% | 56202.63 | 49123.32 | -7079.31 | -12.6% | 292574.34 | 344872.11 | 52297.77 | 17.88% | 4602.04 | 3047.83 | -1554.21 | -33.77% | 306411.44 | 290255.32 | -16156.12 | -5.273% | 445.64 | 206 | -239.64 | -53.77% | 2021-06-10 01:00
Hamilton | 2020 | 451576 | 8 Emming Crt, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-30 01:00
Hamilton | 2019 | 451578 | 959 Upper James St, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Koeppe, Jeffrey | 34842.07 | 28801.85 | -6040.22 | -17.34% | 18039.49 | 12397.1 | -5642.39 | -31.28% | 9206.44 | 8752.46 | -453.98 | -4.931% | 4718.6 | 3577.5 | -1141.1 | -24.18% | 2877.54 | 0 | -2877.54 | -100% | 257.5 | 223.25 | -34.25 | -13.3% | 2019-08-30 01:00
Hamilton | 2019 | 451579 | 287 Old Guelph Rd, Dundas | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 1348.73 | 1348.73 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2020 | 451581 | 204 Hillyard St, Hamilton | 95 | COMPLETE | Converted Project |  |  | Frigotto, Rodrigo | No | Alectra Utilities | Koeppe, Jeffrey | 79124.5 | 82178.09 | 3053.59 | 3.859% | 23202.29 | 15278.27 | -7924.02 | -34.15% | 44286.64 | 45685.6 | 1398.96 | 3.159% | 5225.8 | 3671.47 | -1554.33 | -29.74% | 6409.77 | 3445 | -2964.77 | -46.25% | 338.5 | 337.5 | -1 | -0.2954% | 2020-08-11 01:00
Hamilton | 2019 | 451583 | 675-681 Mohawk Rd E, Hamilton | 99 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Bennett, Aaron | Koeppe, Jeffrey | 89049.21 | 95696.67 | 6647.46 | 7.465% | 36723.59 | 847.34 | -35876.25 | -97.69% | 31700.16 | 34878.56 | 3178.4 | 10.03% | 8899.92 | 0 | -8899.92 | -100% | 11725.54 | 6236.37 | -5489.17 | -46.81% | 517.5 | 527.25 | 9.75 | 1.884% | 2019-06-18 01:00
Hamilton | 2019 | 451584 | 141 Park St N, Hamilton | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 1028.14 | 1028.14 |  | 0 | 514.07 | 514.07 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 451585 | 107 MacNab St N, Hamilton | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Bennett, Aaron | Brian Robinson | 101256.83 | 118628.57 | 17371.74 | 17.16% | 30517.67 | 1741 | -28776.67 | -94.3% | 47705.52 | 51505.88 | 3800.36 | 7.966% | 7415.6 | 0 | -7415.6 | -100% | 15618.04 | 21762.54 | 6144.5 | 39.34% | 437.5 | 478.25 | 40.75 | 9.314% | 2019-09-28 01:00
Hamilton | 2019 | 451586 | John SS PH 1, Part 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Karan, Andjelo | Carr, Brad | 1146595.91 | 1053251.41 | -93344.5 | -8.141% | 30787.5 | 15877.66 | -14909.84 | -48.43% | 216735.56 | 273961.14 | 57225.58 | 26.4% | 3846 | 304 | -3542 | -92.1% | 895226.85 | 145937.25 | -749289.6 | -83.7% | 436 | 379.5 | -56.5 | -12.96% | 2019-11-02 01:00
Hamilton | 2020 | 451587 | John SS PH 1, Part 2 | 99 | COMPLETE | Converted Project | Labour est. under | N/A | Beaudrie, Scott | No | Alectra Utilities | Scott Borer | 1324302.44 | 1668243.83 | 343941.39 | 25.97% | 510214.27 | 481086.21 | -29128.06 | -5.709% | 392914.45 | 444647.35 | 51732.9 | 13.17% | 190094.6 | 189662.03 | -432.57 | -0.2276% | 231079.12 | 205894.89 | -25184.23 | -10.9% | 7120 | 9082.5 | 1962.5 | 27.56% | 2020-11-13 01:00
Hamilton | 2019 | 451589 | Skinner Road Housing | 99 | COMPLETE | Converted Project |  |  | Velickovski, Goran | No | Morris, Mark | Tony Ierace | 11100.62 | 109538.26 | 98437.64 | 886.8% | 10569.17 | 356.93 | -10212.24 | -96.62% | 66.65 | 711.13 | 644.48 | 967% | 464.8 | 38 | -426.8 | -91.82% | 0 | 148.6 | 148.6 |  | 127 | 96.25 | -30.75 | -24.21% | 2019-10-12 01:00
Hamilton | 2019 | 451594 | Parkdale Data Center | 99 | CANCELLED | N/A | N/A | N/A | Vande Kuyt, Greg | No | Jolie, Chris | Weaver, Thomas | 0 | 145241.33 | 145241.33 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 306.75 | 306.75 |  | 2019-05-08
Hamilton | 2021 | 451595 | 690 SOUTH SERVICE RD | 99 | COMPLETE | Under 10% |  |  | Frigotto, Rodrigo | No | Dragojevic, Igor | Macdougall, Stephen | 172120.45 | 175442.28 | 3321.83 | 1.93% | 51982.9 | 57849.94 | 5867.04 | 11.29% | 103720.02 | 101566.91 | -2153.11 | -2.076% | 10937.53 | 11520.5 | 582.97 | 5.33% | 5480 | 2191.25 | -3288.75 | -60.01% | 367.12 | 646 | 278.88 | 75.96% | 2021-10-21 01:00
Hamilton | 2021 | 451600 | Mountain URD - Phase 2 - (South) | 99 | COMPLETE | Converted Project | Covid-19 | Cont Est Over | Beaudrie, Scott | Yes | Billone, Justin | Andrew Mehlenbacher | 516979.71 | 671204.05 | 154224.34 | 29.83% | 64071.9 | 112785.05 | 48713.15 | 76.03% | 303353.29 | 312796.78 | 9443.49 | 3.113% | 9754 | 21181.52 | 11427.52 | 117.2% | 139800.52 | 176455.3 | 36654.78 | 26.22% | 1511.75 | 1819 | 307.25 | 20.32% | 2021-04-26
Hamilton | 2020 | 451608 | John Sub. Conv. 2019 - PH 2, PART 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 2253286.94 | 2668550.09 | 415263.15 | 18.43% | 38412.2 | 180319.76 | 141907.56 | 369.4% | 447633.34 | 541790.71 | 94157.37 | 21.03% | 3396 | 4168.47 | 772.47 | 22.75% | 1763845.4 | 1769525.94 | 5680.54 | 0.3221% | 526 | 689.25 | 163.25 | 31.04% | 2020-07-16 01:00
Hamilton | 2020 | 451609 | Salerno Dairy | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Roy Owen | 410021.9 | 432939.11 | 22917.21 | 5.589% | 38862.86 | 464.57 | -38398.29 | -98.8% | 210107.7 | 274357.17 | 64249.47 | 30.58% | 6654.8 | 0 | -6654.8 | -100% | 154396.54 | 0 | -154396.54 | -100% | 592.5 | 621.5 | 29 | 4.895% | 2020-01-15 01:00
Hamilton | 2021 | 451615 | Hamilton 2018 Pole Residuals - 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Brian Robinson | 103102.77 | 96089.26 | -7013.51 | -6.802% | 23608.89 | 9710.52 | -13898.37 | -58.87% | 19648.98 | 15852.38 | -3796.6 | -19.32% | 14564.77 | 2443.5 | -12121.27 | -83.22% | 45280.13 | 19333.15 | -25946.98 | -57.3% | 592.5 | 581.5 | -11 | -1.857% | 2021-04-30
Hamilton | 2019 | 451616 | Hamilton 2018 Pole Residuals | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Koeppe, Jeffrey | 61107.04 | 76848.63 | 15741.59 | 25.76% | 27583.51 | 265.76 | -27317.75 | -99.04% | 14612.76 | 13046.08 | -1566.68 | -10.72% | 8846 | 56 | -8790 | -99.37% | 10064.77 | 0 | -10064.77 | -100% | 618 | 551 | -67 | -10.84% | 2019-12-17 01:00
Hamilton | 2019 | 451617 | Hamilton 2018 Pole Residuals | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Koeppe, Jeffrey | 63908.61 | 87267.06 | 23358.45 | 36.55% | 29170.75 | 21390.53 | -7780.22 | -26.67% | 14327.09 | 14997.78 | 670.69 | 4.681% | 8846 | 7469 | -1377 | -15.57% | 11564.77 | 9617.75 | -1947.02 | -16.84% | 412 | 572 | 160 | 38.83% | 2019-12-13 01:00
Hamilton | 2020 | 451618 | Hamilton 2018 Pole Residuals | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 108187.77 | 102395.08 | -5792.69 | -5.354% | 1946.73 | 8617.97 | 6671.24 | 342.7% | 0 | 21632.39 | 21632.39 |  | 252 | 0 | -252 | -100% | 105989.04 | 69154.06 | -36834.98 | -34.75% | 23 | 18 | -5 | -21.74% | 2020-02-25 01:00
Hamilton | 2019 | 451620 | 2018 Bell Permit Reviews | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 22463.4 | 22463.4 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 15 | 15 | 0 | 0% | 2019-04-10 01:00
Hamilton | 2022 | 451622 | Lake 121X circuit - Cond. Upgrade | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Anderson, Dean | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-08
Hamilton | 2019 | 451623 | 9281x Reroute from Kenilworth | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Jolie, Chris | Weaver, Thomas | 0 | 97870.24 | 97870.24 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 167 | 167 |  | 2019-05-08
Hamilton | 2020 | 451624 | Baldwin #1 2018 URD Phase 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Andrew Mehlenbacher | 137494.75 | 151504.38 | 14009.63 | 10.19% | 21981.16 | 37360.85 | 15379.69 | 69.97% | 84630.09 | 83605.23 | -1024.86 | -1.211% | 3633.5 | 5622.19 | 1988.69 | 54.73% | 27250 | 18191.51 | -9058.49 | -33.24% | 393 | 506.5 | 113.5 | 28.88% | 2020-09-24 01:00
Hamilton | 2021 | 451628 | 1212 MAIN ST - MAPLE AVE UPGRADE | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Jolie, Chris | Carr, Brad | 999618.35 | 834947.45 | -164670.9 | -16.47% | 38404.55 | 61281.19 | 22876.64 | 59.57% | 156066.8 | 233604.42 | 77537.62 | 49.68% | 2800 | 27.33 | -2772.67 | -99.02% | 802347 | 540034.51 | -262312.49 | -32.69% | 250 | 67.5 | -182.5 | -73% | 2021-01-13 01:00
Hamilton | 2020 | 451629 | 49 Dunbar Ave | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 15.5 | 15.5 |  | 2020-01-12 01:00
Hamilton | 2020 | 451630 | 600 Second Rd. E. | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Carr, Brad | 15126.18 | 25744.31 | 10618.13 | 70.2% | 5870.43 | 6120.98 | 250.55 | 4.268% | 843.93 | 883.51 | 39.58 | 4.69% | 1140.18 | 1604.44 | 464.26 | 40.72% | 3464.77 | 15244.23 | 11779.46 | 340% | 70.5 | 85.5 | 15 | 21.28% | 2020-01-12 01:00
Hamilton | 2020 | 451632 | 23 Royce Ave | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Koeppe, Jeffrey | 66727.16 | 63393.08 | -3334.08 | -4.997% | 18363.84 | 11220.85 | -7142.99 | -38.9% | 27368.99 | 28837.4 | 1468.41 | 5.365% | 2570.89 | 3604.68 | 1033.79 | 40.21% | -6396.04 | 16584.96 | 22981 | -359.3% | 120 | 123 | 3 | 2.5% | 2020-08-17 01:00
Hamilton | 2020 | 451633 | 1224 Stone Church Rd E | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2020-10-05 01:00
Hamilton | 2020 | 451636 | 72 Sherman Ave S, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-05 01:00
Hamilton | 2020 | 451637 | Wentworth St Railway Crossing - Juravinski | 99 | COMPLETE | 3rd party plant | Cont Est Under | Labour est. under | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 447710.36 | 401125.52 | -46584.84 | -10.41% | 7158.41 | 36218.56 | 29060.15 | 406% | 78758.78 | 60141.08 | -18617.7 | -23.64% | 448 | 0 | -448 | -100% | 322161.17 | 300880.97 | -21280.2 | -6.605% | 42 | 63.5 | 21.5 | 51.19% | 2020-10-05 01:00
Hamilton | 2020 | 451638 | Baldwin #2 Overhead Conversion Ph 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 2166145.73 | 2303892.34 | 137746.61 | 6.359% | 1495404.09 | 142366.38 | -1353037.71 | -90.48% | 405651.12 | 493306.56 | 87655.44 | 21.61% | 7425.92 | 503.78 | -6922.14 | -93.22% | 257664.6 | 1565250.98 | 1307586.38 | 507.5% | 1240 | 734.25 | -505.75 | -40.79% | 2020-11-20 01:00
Hamilton | 2020 | 451639 | Rear Alley-Btwn John & Hughson St S | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 882857.79 | 929624.13 | 46766.34 | 5.297% | 726531.79 | 74355.08 | -652176.71 | -89.77% | 14197.8 | 143008.63 | 128810.83 | 907.3% | 119477.79 | 3437 | -116040.79 | -97.12% | 22650.41 | 700720.64 | 678070.23 | 2994% | 309 | 342 | 33 | 10.68% | 2020-02-25 01:00
Hamilton | 2019 | 451640 | Upper Sherman & Rymal Rd, Hamilton | 99 | COMPLETE | Labour est. over | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Koeppe, Jeffrey | 74477.79 | 73288.32 | -1189.47 | -1.597% | 20054.38 | 32.1 | -20022.28 | -99.84% | 42206.82 | 0 | -42206.82 | -100% | 3765.8 | 0 | -3765.8 | -100% | 8450.79 | 401.25 | -8049.54 | -95.25% | 293 | 249.75 | -43.25 | -14.76% | 2019-01-16 01:00
Hamilton | 2021 | 451643 | Mountain URD - Phase 2 - (North) | 99 | COMPLETE | Scope – Eng | Labour est. under |  | Beaudrie, Scott | Yes | Billone, Justin | Andrew Mehlenbacher | 1087289.31 | 1479882.47 | 392593.16 | 36.11% | 121057.42 | 257666.79 | 136609.37 | 112.8% | 569763.16 | 732724.88 | 162961.72 | 28.6% | 26092.41 | 67574.18 | 41481.77 | 159% | 370376.32 | 412554.31 | 42177.99 | 11.39% | 1255.5 | 2746 | 1490.5 | 118.7% | 2021-09-03 01:00
Hamilton | 2020 | 451644 | Central Conversion 2019 - Phase 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 1939267.23 | 1384542.2 | -554725.03 | -28.6% | 1474069.48 | 95211.94 | -1378857.54 | -93.54% | 2978.8 | 359200.07 | 356221.27 | 11959% | 329797.98 | 2728.6 | -327069.38 | -99.17% | 132420.97 | 837186.63 | 704765.66 | 532.2% | 1032.5 | 1071.5 | 39 | 3.777% | 2020-02-25 01:00
Hamilton | 2019 | 451645 | Upp. Sherman Ave-Bell Pole Relocate | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Carr, Brad | 125661.29 | 331868.94 | 206207.65 | 164.1% | 6036.99 | 0 | -6036.99 | -100% | 38779.19 | 79652.78 | 40873.59 | 105.4% | 283 | 0 | -283 | -100% | 80562.11 | 0 | -80562.11 | -100% | 82 | 94.5 | 12.5 | 15.24% | 2019-03-30 01:00
Hamilton | 2021 | 451646 | ROAD AUTHORITY - POLE RELOCATION - REGION OF PEEL - DIXIE RD - LOCATION 1 | 99 | CANCELLED | N/A |  |  | Pelleja, Emily | No | Celic, Dusan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-17 01:00
Hamilton | 2021 | 451647 | Celtic Dr - 8 kV Conv. - Phase 2 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 1632511.31 | 1831021.15 | 198509.84 | 12.16% | 14282.65 | 178115.58 | 163832.93 | 1147% | 198360.66 | 219300.25 | 20939.59 | 10.56% | 1120 | 3551.47 | 2431.47 | 217.1% | 1418748 | 1427298.87 | 8550.87 | 0.6027% | 80 | 182.5 | 102.5 | 128.1% | 2021-06-17 01:00
Hamilton | 2020 | 451648 | Upper Sherman Extension | 99 | COMPLETE | Converted Project |  |  | Velickovski, Goran | No | Alectra Utilities | Carr, Brad | 358775.82 | 407087.05 | 48311.23 | 13.47% | 16912.35 | 50712.13 | 33799.78 | 199.9% | 4755.87 | 10092.25 | 5336.38 | 112.2% | 2809.6 | 7387.1 | 4577.5 | 162.9% | 334298 | 334298 | 0 | 0% | 237 | 311 | 74 | 31.22% | 2020-02-15 01:00
Hamilton | 2019 | 451649 | 2018 Cogeco Permit Review | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 9963.7 | 9963.7 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 108 | 108 |  | 0 | 0 | 0 |  | 38 | 19 | -19 | -50% | 2019-02-23 01:00
Hamilton | 2020 | 451651 | 634 Upper Sherman Ave, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-16 01:00
Hamilton | 2020 | 451652 | 227 Templemead Dr, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 37 | 37 |  | 2019-11-16 01:00
Hamilton | 2020 | 451655 | Explore Townhomes - Albright Road | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Andrew Mehlenbacher | 213115.06 | 1154813.07 | 941698.01 | 441.9% | 56511.68 | 57541.04 | 1029.36 | 1.821% | 36265.64 | 35671.26 | -594.38 | -1.639% | 6059.2 | 10690.55 | 4631.35 | 76.44% | 114278.54 | 107268.53 | -7010.01 | -6.134% | 789 | 1000.75 | 211.75 | 26.84% | 2020-02-15 01:00
Hamilton | 2020 | 451658 | 125 Wilson St, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-19 01:00
Hamilton | 2019 | 451659 | Smart Grid Fund - Miles (Capital) | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Karan, Andjelo | Dan Despres | 98875.24 | 107595.27 | 8720.03 | 8.819% | 4588.63 | 11556.47 | 6967.84 | 151.9% | 0 | 0 | 0 |  | 1786.61 | 2462.45 | 675.84 | 37.83% | 92500 | 13000 | -79500 | -85.95% | 64 | 211 | 147 | 229.7% | 2019-04-19 01:00
Hamilton | 2019 | 451662 | 2018 Rogers Permit Reviews | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 35192.18 | 35192.18 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 43 | 22 | -21 | -48.84% | 2019-05-30
Hamilton | 2019 | 451667 | Rymal Rd W - Road Work Deficiencies | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Jolie, Chris | Weaver, Thomas | 0 | 15701.38 | 15701.38 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-29 01:00
Hamilton | 2019 | 451668 | OH Recloser Replacement Project | 99 | COMPLETE | Scope change - unforeseen | BOM not accurate | N/A |  | No | Billone, Justin | Brian Robinson | 134039.37 | 190076.51 | 56037.14 | 41.81% | 55186.25 | 34297.54 | -20888.71 | -37.85% | 69460.92 | 15567.66 | -53893.26 | -77.59% | 9392.2 | 4032.58 | -5359.62 | -57.06% | 0 | 720 | 720 |  | 748.5 | 1744.75 | 996.25 | 133.1% | 2019-04-18 01:00
Hamilton | 2020 | 451672 | Urban Core Developments - Victoria Ave | 98 | COMPLETE | Converted Project |  |  | Velickovski, Goran | No | Alectra Utilities | Koeppe, Jeffrey | 72348.16 | 67534.87 | -4813.29 | -6.653% | 31155.13 | 3598.27 | -27556.86 | -88.45% | 18775.89 | 18385.62 | -390.27 | -2.079% | 7287.6 | 556.67 | -6730.93 | -92.36% | 15129.54 | 18726.79 | 3597.25 | 23.78% | 392 | 319.75 | -72.25 | -18.43% | 2020-01-14 01:00
Hamilton | 2020 | 451673 | Flamborough Power Center | 95 | COMPLETE | Converted Project |  |  | Velickovski, Goran | No | Alectra Utilities | Roy Owen | 57168.93 | 79606.73 | 22437.8 | 39.25% | 28839.19 | 15899.72 | -12939.47 | -44.87% | 19249.77 | 21521.14 | 2271.37 | 11.8% | 5815.2 | 2999.11 | -2816.09 | -48.43% | 3264.77 | 2234.43 | -1030.34 | -31.56% | 418 | 505.75 | 87.75 | 20.99% | 2020-01-15 01:00
Hamilton | 2020 | 451677 | Waterdown Bay - Hydro Supply | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 3691.59 | 3818.72 | 127.13 | 3.444% | 3238.79 | 1841.61 | -1397.18 | -43.14% | 0 | 0 | 0 |  | 452.8 | 294.5 | -158.3 | -34.96% | 0 | 0 | 0 |  | 38 | 46 | 8 | 21.05% | 2020-11-03 01:00
Hamilton | 2022 | 451680 | Brampton LRT | 99 | CANCELLED | N/A |  |  | Tobin, Michael | No | Jolie, Chris | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-08
Hamilton | 2019 | 451681 | Stations Facility Upgrades | 99 | COMPLETE | N/A | N/A | N/A |  | No | Billone, Justin | Weaver, Thomas | 0 | 33077.48 | 33077.48 |  | 0 | 616.79 | 616.79 |  | 0 | 0 | 0 |  | 0 | 59.8 | 59.8 |  | 0 | 32236.69 | 32236.69 |  | 0 | 9.5 | 9.5 |  | 2019-05-08
Hamilton | 2019 | 451684 | 281 Barton St. STC - Gas Station | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Lustrinelli, Mark | Carr, Brad | 20165.17 | 20003.38 | -161.79 | -0.8023% | 4284.83 | 5074.44 | 789.61 | 18.43% | 1032.5 | 0 | -1032.5 | -100% | 0 | 311 | 311 |  | 14847.84 | 12693.57 | -2154.27 | -14.51% | 10 | 14.5 | 4.5 | 45% | 2019-10-29 01:00
Hamilton | 2019 | 451686 | 40 Centennial Pkwy N - OH to UG | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Lustrinelli, Mark | Koeppe, Jeffrey | 16422.01 | 16526.65 | 104.64 | 0.6372% | 11041.95 | 1749.28 | -9292.67 | -84.16% | 1144.92 | 2106.66 | 961.74 | 84% | 1722 | 786 | -936 | -54.36% | 1729.54 | 1281.25 | -448.29 | -25.92% | 162 | 151 | -11 | -6.79% | 2019-07-24 01:00
Hamilton | 2019 | 451690 | 71 Innovation Dr, Flamborough | 99 | COMPLETE | Under 10% | N/A | N/A | Paesano, Andrew | No | Laus, Tomislav | Roy Owen | 40426.67 | 43699.17 | 3272.5 | 8.095% | 10854 | 2268.35 | -8585.65 | -79.1% | 20668.87 | 0 | -20668.87 | -100% | 1508.8 | 328 | -1180.8 | -78.26% | 7395 | 2657.17 | -4737.83 | -64.07% | 163 | 190 | 27 | 16.56% | 2019-01-17 01:00
Hamilton | 2020 | 451691 | 85 Holton Ave. S | 99 | CANCELLED | N/A | N/A | N/A |  | No | Alectra Utilities | Weaver, Thomas | 0 | 335.88 | 335.88 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-14 01:00
Hamilton | 2020 | 451692 | 56 Third Rd E | 99 | CANCELLED | N/A | N/A | N/A |  | No | Alectra Utilities | Weaver, Thomas | 0 | 49.3 | 49.3 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-14 01:00
Hamilton | 2020 | 451693 | 37 Henley Dr, St.Catharines | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-14 01:00
Hamilton | 2020 | 451694 | 565 Seaman St, Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-14 01:00
Hamilton | 2019 | 451695 | 693 Beach Blvd. Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Laus, Tomislav | Koeppe, Jeffrey | 23983.84 | 29175.69 | 5191.85 | 21.65% | 6270.38 | 4567.42 | -1702.96 | -27.16% | 4751.72 | 5223.23 | 471.51 | 9.923% | 1722.2 | 1603 | -119.2 | -6.921% | 11239.54 | 11005 | -234.54 | -2.087% | 97 | 115.5 | 18.5 | 19.07% | 2019-09-14 01:00
Hamilton | 2020 | 451696 | 2070 Rymal Rd E, Hamilton | 98 | COMPLETE | Cont Est Over | BOM not accurate |  | Paesano, Andrew | No | Alectra Utilities | Roy Owen | 71006.63 | 76849.46 | 5842.83 | 8.229% | 15505.06 | 11821.7 | -3683.36 | -23.76% | 35692.33 | 45080.74 | 9388.41 | 26.3% | 798 | 1811.69 | 1013.69 | 127% | 19011.24 | 14991.29 | -4019.95 | -21.15% | 106 | 110.75 | 4.75 | 4.481% | 2020-09-25 01:00
Hamilton | 2020 | 451697 | 462 & 464 Mary St, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-30 01:00
Hamilton | 2020 | 451699 | 54-42 Lakeshore Rd, Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-18 01:00
Hamilton | 2019 | 451700 | 60/68 Centennial Pkwy S, Stny Crk | 95 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Laus, Tomislav | Roy Owen | 62699.64 | 64586.48 | 1886.84 | 3.009% | 17678.55 | 12961.37 | -4717.18 | -26.68% | 29563.6 | 30829.84 | 1266.24 | 4.283% | 2685 | 2504 | -181 | -6.741% | 12772.49 | 0 | -12772.49 | -100% | 214 | 310.5 | 96.5 | 45.09% | 2019-09-18 01:00
Hamilton | 2019 | 451702 | 724 Queenston Rd, Stoney Creek | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A |  | No | Laus, Tomislav | Koeppe, Jeffrey | 30897.29 | 36444.6 | 5547.31 | 17.95% | 10400.41 | 13010.54 | 2610.13 | 25.1% | 9731.94 | 10844.79 | 1112.85 | 11.44% | 3289.4 | 4662 | 1372.6 | 41.73% | 7475.54 | 7927.27 | 451.73 | 6.043% | 146 | 183.5 | 37.5 | 25.68% | 2019-02-11 01:00
Hamilton | 2020 | 451703 | 44 Leckie Ave | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-30 01:00
Hamilton | 2020 | 451704 | Lower Davis Creek Flood Control | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-30 01:00
Hamilton | 2019 | 451708 | 665 Starthearne Ave, Hamilton | 99 | COMPLETE | Under 10% | N/A | N/A |  | No | Laus, Tomislav | Koeppe, Jeffrey | 14927.15 | 14733 | -194.15 | -1.301% | 5026.82 | 5053.19 | 26.37 | 0.5246% | 8611.73 | 7366.14 | -1245.59 | -14.46% | 1288.6 | 197.08 | -1091.52 | -84.71% | 0 | 0 | 0 |  | 68 | 73.75 | 5.75 | 8.456% | 2019-02-21 01:00
Hamilton | 2020 | 451709 | 738 Mud St E, Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-15 01:00
Hamilton | 2020 | 451710 | 7 Gertrude St, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-15 01:00
Hamilton | 2019 | 451711 | 1721 Strathearne Ave, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Laus, Tomislav | Koeppe, Jeffrey | 11948.43 | 7649.21 | -4299.22 | -35.98% | 1564.77 | 770.96 | -793.81 | -50.73% | 1211.59 | 638.23 | -573.36 | -47.32% | 7079.07 | 135 | -6944.07 | -98.09% | 2093 | 0 | -2093 | -100% | 103.5 | 85 | -18.5 | -17.87% | 2019-06-15 01:00
Hamilton | 2022 | 451712 | 45 King St E, Hamilton - Temp Crane | 98 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Laus, Tomislav | Roy Owen | 47218.03 | 48235.45 | 1017.42 | 2.155% | 7778.14 | 4324.56 | -3453.58 | -44.4% | 38818.15 | 41301.39 | 2483.24 | 6.397% | 621.74 | 1129.88 | 508.14 | 81.73% | 0 | 890.5 | 890.5 |  | 50.5 | 51 | 0.5 | 0.9901% | 2022-11-14 01:00
Hamilton | 2020 | 451714 | 31 John St N, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-19 01:00
Hamilton | 2020 | 451715 | 117 Park St S, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-19 01:00
Hamilton | 2019 | 451716 | 1053 Barton St, Stoney Creek | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Laus, Tomislav | Koeppe, Jeffrey | 67936.23 | 70750.24 | 2814.01 | 4.142% | 20340.02 | 9562.52 | -10777.5 | -52.99% | 36957.86 | 41123.42 | 4165.56 | 11.27% | 4626.8 | 2976.5 | -1650.3 | -35.67% | 6011.55 | 3632.01 | -2379.54 | -39.58% | 294 | 262 | -32 | -10.88% | 2019-09-19 01:00
Hamilton | 2019 | 451717 | 99 Lincoln Rd, Stoney Creek | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Laus, Tomislav | Koeppe, Jeffrey | 73624.34 | 85078.39 | 11454.05 | 15.56% | 26883.44 | 27441.7 | 558.26 | 2.077% | 34435.75 | 38716.76 | 4281.01 | 12.43% | 6183.6 | 6589.5 | 405.9 | 6.564% | 6121.55 | 5769.28 | -352.27 | -5.755% | 382.5 | 478 | 95.5 | 24.97% | 2019-11-23 01:00
Hamilton | 2020 | 451718 | 7 Gertrude St, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-08 01:00
Hamilton | 2020 | 451719 | 82 Parkside Dr, Flamborough | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-08 01:00
Hamilton | 2020 | 451720 | 2750 King St E, Stoney Creek | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Roy Owen | 224281.34 | 223917.55 | -363.79 | -0.1622% | 42922.28 | 27685.87 | -15236.41 | -35.5% | 109626.75 | 126746.93 | 17120.18 | 15.62% | 4841.43 | 5637.89 | 796.46 | 16.45% | 66890.88 | 60814.02 | -6076.86 | -9.085% | 366.02 | 248.25 | -117.77 | -32.18% | 2020-06-08 01:00
Hamilton | 2020 | 451721 | 1212 Main St. E - Bell Station | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Roy Owen | 95727.37 | 83535.2 | -12192.17 | -12.74% | 26766.41 | 16848.72 | -9917.69 | -37.05% | 33302.88 | 39171.61 | 5868.73 | 17.62% | 5207.48 | 4947.45 | -260.03 | -4.993% | 30450.6 | 20436.1 | -10014.5 | -32.89% | 280 | 143.5 | -136.5 | -48.75% | 2020-06-30 01:00
Hamilton | 2020 | 451723 | 212 Natinal Dr. | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-10 01:00
Hamilton | 2020 | 451724 | 121 Hwy 8, Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-10 01:00
Hamilton | 2020 | 451725 | 198 Welland Ave. St. Kitts | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 40398.04 | 45463.51 | 5065.47 | 12.54% | 17717.18 | 12604.47 | -5112.71 | -28.86% | 18285.01 | 18266.39 | -18.62 | -0.1018% | 2208.85 | 3275.05 | 1066.2 | 48.27% | 2187 | 8153.75 | 5966.75 | 272.8% | 137 | 56 | -81 | -59.12% | 2020-08-10 01:00
Hamilton | 2021 | 451728 | 49 COLLEGIATE AVE, STONEY CREEK | 99 | COMPLETE | Vac truck |  |  | Paesano, Andrew | No | Laus, Tomislav | Macdougall, Stephen | 105171.62 | 99571.59 | -5600.03 | -5.325% | 33817.49 | 34440.94 | 623.45 | 1.844% | 39090.21 | 37431.26 | -1658.95 | -4.244% | 6743.52 | 11155.46 | 4411.94 | 65.42% | 25520.4 | 16543.93 | -8976.47 | -35.17% | 268.24 | 411 | 142.76 | 53.22% | 2021-06-11 01:00
Hamilton | 2020 | 451730 | 10 Newman Rd, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3 | 3 |  | 2019-07-26 01:00
Hamilton | 2020 | 451732 | CHH Demo - James St N & MacNab St N | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6 | 6 |  | 2020-02-15 01:00
Hamilton | 2020 | 451733 | 23 Southmeadow Cres. | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-15 01:00
Hamilton | 2020 | 451734 | 284 Winona Rd, Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-15 01:00
Hamilton | 2020 | 451736 | Effort Square T75 - 140 King St E | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 396215.6 | 537801.76 | 141586.16 | 35.73% | 30959.64 | 68234.6 | 37274.96 | 120.4% | 14534.75 | 81330.41 | 66795.66 | 459.6% | 3545.6 | 34333.89 | 30788.29 | 868.4% | 347175.61 | 346363.96 | -811.65 | -0.2338% | 443 | 361 | -82 | -18.51% | 2020-02-15 01:00
Hamilton | 2020 | 451739 | Concession & U Gage Pole Replacment - Juravinski | 99 | CANCELLED | N/A | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Weaver, Thomas | 94552.5 | 12079.99 | -82472.51 | -87.22% | 10804.77 | 0 | -10804.77 | -100% | 24100.37 | 10801.97 | -13298.4 | -55.18% | 16096.5 | 0 | -16096.5 | -100% | 43550.86 | 0 | -43550.86 | -100% | 0 | 0 | 0 |  | 2020-02-06 01:00
Hamilton | 2020 | 451742 | 38 West Ave N, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-04 01:00
Hamilton | 2020 | 451743 | Humphrey Street Townhomes Sub | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Andrew Mehlenbacher | 16995.44 | 236763.36 | 219767.92 | 1293% | 16411.44 | 86.22 | -16325.22 | -99.47% | 0 | 0 | 0 |  | 584 | 0 | -584 | -100% | 0 | 0 | 0 |  | 198 | 141 | -57 | -28.79% | 2020-12-04 01:00
Hamilton | 2020 | 451745 | Royce Ave Expansion - Stoneycreek | 98 | COMPLETE | Converted Project | Labour est. over |  | Jakubowski, Mark | No | Alectra Utilities | Scott Borer | 340377.92 | 377444.64 | 37066.72 | 10.89% | 126487.87 | 144503.15 | 18015.28 | 14.24% | 98012.67 | 94148.61 | -3864.06 | -3.942% | 32249.03 | 74792.2 | 42543.17 | 131.9% | 83628.35 | 61210.73 | -22417.62 | -26.81% | 2190 | 1735 | -455 | -20.78% | 2020-10-06 01:00
Hamilton | 2021 | 451746 | Project Estimating 2018 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-08 01:00
Hamilton | 2019 | 451747 | 408 Cumberland Ave, Hamilton | 99 | COMPLETE | BOM not accurate | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Koeppe, Jeffrey | 85610.63 | 90449.59 | 4838.96 | 5.652% | 24785.84 | 199.48 | -24586.36 | -99.2% | 27934.05 | 0 | -27934.05 | -100% | 5735.2 | 0 | -5735.2 | -100% | 27155.54 | 2493.52 | -24662.02 | -90.82% | 362.5 | 346.5 | -16 | -4.414% | 2019-01-08 01:00
Hamilton | 2019 | 451748 | 905 Upper Ottawa St, Hamilton | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 451749 | Cross of Lorraine, Hamilton | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 2927.56 | 2927.56 |  | 0 | 1463.78 | 1463.78 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2020 | 451750 | 43 Farmer Crt, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1769.09 | 1769.09 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2020 | 451751 | 729 Centre Rd, Flamborough | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1591.28 | 1591.28 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 451752 | 97 Lakeview Dr, Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2020 | 451753 | 1911 Barton St E, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 616.83 | 616.83 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 451754 | 34 Malton Dr, Hamilton | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 2581.07 | 2581.07 |  | 0 | 1618.9 | 1618.9 |  | 0 | 0 | 0 |  | 0 | 770 | 770 |  | 0 | 0 | 0 |  | 0 | 16.5 | 16.5 |  | 2019-06-07
Hamilton | 2019 | 451755 | 97 Lakeview Dr, Hamilton | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 3981.2 | 3981.2 |  | 0 | 1990.6 | 1990.6 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 451765 | Aberdeen #1 Feeder | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Anderson, Dean | Carr, Brad | 682823.42 | 734293.66 | 51470.24 | 7.538% | 57996.79 | 5972.52 | -52024.27 | -89.7% | 193038.37 | 220810.64 | 27772.27 | 14.39% | 4449.88 | 0 | -4449.88 | -100% | 427338.38 | 74656.5 | -352681.88 | -82.53% | 841.4 | 510.5 | -330.9 | -39.33% | 2019-05-30
Hamilton | 2022 | 451770 | RIVERVIEW DRIVE REAR LOT CONVERSION | 99 | COMPLETE | N/A |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Brad Carr | 0 | 3666.44 | 3666.44 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2023-01-04 01:00
Hamilton | 2022 | 451772 | RAVENSCLIFFE U/G & REAR LOT CONVERSION | 92 | ACTIVE |  |  |  | Beaudrie, Scott | Yes | Anderson, Dean | Brad Carr | 2183520.46 | 2132667.19 | -50853.27 | -2.329% | 250666.67 | 322011.41 | 71344.74 | 28.46% | 108976.64 | 69173.69 | -39802.95 | -36.52% | 8812.27 | 0 | -8812.27 | -100% | 1815064.88 | 1739463.5 | -75601.38 | -4.165% | 493.46 | 113.5 | -379.96 | -77% | 2022-12-28 01:00
Hamilton | 2020 | 451776 | 85 Holton Ave S, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-05-01
Hamilton | 2019 | 451779 | Kinrade UG Service Install | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 36424.73 | 35038.99 | -1385.74 | -3.804% | 11690.23 | 0 | -11690.23 | -100% | 2110.76 | 3640.19 | 1529.43 | 72.46% | 1634.2 | 0 | -1634.2 | -100% | 20989.54 | 0 | -20989.54 | -100% | 213.5 | 151.5 | -62 | -29.04% | 2019-05-04 01:00
Hamilton | 2020 | 451780 | 480 King William St, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-01
Hamilton | 2019 | 451781 | Life-288 Glover Rd | 99 | COMPLETE | N/A | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Koeppe, Jeffrey | 56321.81 | 51724.33 | -4597.48 | -8.163% | 28622.59 | 0 | -28622.59 | -100% | 11134.55 | 0 | -11134.55 | -100% | 5394.4 | 0 | -5394.4 | -100% | 11170.27 | 0 | -11170.27 | -100% | 427.5 | 354 | -73.5 | -17.19% | 2019-06-01
Hamilton | 2020 | 451784 | Empire-Red Hill Ph. 3 & 4 | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Carr, Brad | 52564.51 | 907174.2 | 854609.69 | 1626% | 40172.78 | 18341.64 | -21831.14 | -54.34% | 7033.9 | 10131.24 | 3097.34 | 44.03% | 634.64 | 4446.32 | 3811.68 | 600.6% | 1129.54 | 0 | -1129.54 | -100% | 564 | 484.25 | -79.75 | -14.14% | 2020-02-25 01:00
Hamilton | 2020 | 451785 | 90 Beach Rd 12MVA Expansion | 99 | CANCELLED | N/A |  |  | Vande Kuyt, Greg | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-29 01:00
Hamilton | 2020 | 451786 | 63 Worsley Rd | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-29 01:00
Hamilton | 2020 | 451787 | 856 Barton St.E | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 38277 | 25732.04 | -12544.96 | -32.77% | 10763.31 | 8465.93 | -2297.38 | -21.34% | 16015.89 | 9752.24 | -6263.65 | -39.11% | 1999.2 | 1896 | -103.2 | -5.162% | 9498.6 | 3740.84 | -5757.76 | -60.62% | 81 | 75 | -6 | -7.407% | 2020-01-29 01:00
Hamilton | 2021 | 451788 | Winona Crossing - Site A (Temp) | 98 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Oosterlinck, David | Tony Ierace | 38749.18 | 42131.26 | 3382.08 | 8.728% | 8379.65 | 984.08 | -7395.57 | -88.26% | 29738.53 | 34782.87 | 5044.34 | 16.96% | 631 | 153 | -478 | -75.75% | 0 | 0 | 0 |  | 115.5 | 85 | -30.5 | -26.41% | 2021-06-25 01:00
Hamilton | 2019 | 451789 | Juravinski Hospital Main Service | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Oosterlinck, David | Roy Owen | 509902.25 | 421599.53 | -88302.72 | -17.32% | 46107.29 | 31438.43 | -14668.86 | -31.81% | 172641.62 | 166708.44 | -5933.18 | -3.437% | 7629.6 | 4264 | -3365.6 | -44.11% | 283523.74 | 125029.29 | -158494.45 | -55.9% | 666 | 623.25 | -42.75 | -6.419% | 2019-11-27 01:00
Hamilton | 2020 | 451790 | 479 King St.E | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 21227.62 | 2140.68 | -19086.94 | -89.92% | 10277.13 | 106.16 | -10170.97 | -98.97% | 8805.49 | 0 | -8805.49 | -100% | 2145 | 0 | -2145 | -100% | 0 | 0 | 0 |  | 141.5 | 27.5 | -114 | -80.57% | 2019-11-13 01:00
Hamilton | 2019 | 451791 | 20 George St - CCRA Project | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Oosterlinck, David | Roy Owen | 7776.26 | 9559.4 | 1783.14 | 22.93% | 7002.5 | 6188.83 | -813.67 | -11.62% | 163.86 | 608.13 | 444.27 | 271.1% | 609.9 | 646.5 | 36.6 | 6.001% | 0 | 0 | 0 |  | 57 | 64.5 | 7.5 | 13.16% | 2019-11-13 01:00
Hamilton | 2022 | 451792 | 695 James St.N (Temp) | 99 | COMPLETE | N/A | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Macdougall, Stephen | 11062.49 | 8719.73 | -2342.76 | -21.18% | 5299.8 | 151.58 | -5148.22 | -97.14% | 3690.49 | 4351.03 | 660.54 | 17.9% | 2072.2 | 0 | -2072.2 | -100% | 0 | 0 | 0 |  | 73 | 46.5 | -26.5 | -36.3% | 2022-08-17 01:00
Hamilton | 2020 | 451793 | 154 Main St.E(Temp Service) | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 42972.57 | 50326 | 7353.43 | 17.11% | 8482.9 | 8268 | -214.9 | -2.533% | 19560.33 | 22881 | 3320.67 | 16.98% | 1301.8 | 1663 | 361.2 | 27.75% | 13627.54 | 12498 | -1129.54 | -8.289% | 122 | 150 | 28 | 22.95% | 2020-01-15 01:00
Hamilton | 2019 | 451794 | 45 Wellington St.N | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Koeppe, Jeffrey | 22137.93 | 35822.85 | 13684.92 | 61.82% | 8869.02 | 1499.84 | -7369.18 | -83.09% | 2773.2 | 8655.17 | 5881.97 | 212.1% | 0 | 0 | 0 |  | 10495.71 | 15331.75 | 4836.04 | 46.08% | 124 | 124 | 0 | 0% | 2019-08-03 01:00
Hamilton | 2019 | 451795 | 966 Beach Blvd | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Carr, Brad | 35159.72 | 20071.47 | -15088.25 | -42.91% | 4164.99 | 2492.58 | -1672.41 | -40.15% | 4813.18 | 0 | -4813.18 | -100% | 2505.2 | 171 | -2334.2 | -93.17% | 23676.35 | 13781.04 | -9895.31 | -41.79% | 3 | 48.5 | 45.5 | 1517% | 2019-10-29 01:00
Hamilton | 2019 | 451797 | 399 Kenora Ave | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Koeppe, Jeffrey | 10242.77 | 13158.36 | 2915.59 | 28.46% | 5710.27 | 0 | -5710.27 | -100% | 1679.13 | 1643.92 | -35.21 | -2.097% | 1288.6 | 0 | -1288.6 | -100% | 1564.77 | 0 | -1564.77 | -100% | 78.5 | 97 | 18.5 | 23.57% | 2019-06-13 01:00
Hamilton | 2019 | 451802 | 50 Colquhoun Cres | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Scott Borer | 8272.97 | 11370.51 | 3097.54 | 37.44% | 4449.86 | 3392.79 | -1057.07 | -23.76% | 577.94 | 1024.07 | 446.13 | 77.19% | 1680.4 | 1278 | -402.4 | -23.95% | 0 | 3770.25 | 3770.25 |  | 61 | 92.5 | 31.5 | 51.64% | 2019-07-24 01:00
Hamilton | 2019 | 451804 | 1675 Burlington St.E | 99 | COMPLETE | FTE OTP | BOM not accurate | N/A | Kappheim, Adam | No | Oosterlinck, David | Andrew Mehlenbacher | 37873.71 | 54418.87 | 16545.16 | 43.69% | 11658.57 | 0 | -11658.57 | -100% | 24351.54 | 0 | -24351.54 | -100% | 1863.6 | 0 | -1863.6 | -100% | 0 | 0 | 0 |  | 173 | 125.75 | -47.25 | -27.31% | 2019-04-18 01:00
Hamilton | 2020 | 451805 | 87 Kennedy Ave | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-23
Hamilton | 2022 | 451806 | Empire Redhill - Temp Temp Pole | 99 | COMPLETE | Material Under Estimated |  |  | Kappheim, Adam | No | Oosterlinck, David | Macdougall, Stephen | 16634.05 | 15198.12 | -1435.93 | -8.632% | 10888.72 | 7984.55 | -2904.17 | -26.67% | 889.53 | 2543.97 | 1654.44 | 186% | 2855.8 | 2599 | -256.8 | -8.992% | 2000 | 875 | -1125 | -56.25% | 150.5 | 135.5 | -15 | -9.967% | 2022-08-22 01:00
Hamilton | 2020 | 451808 | Biggar St Wire Removal | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-14 01:00
Hamilton | 2022 | 451812 | 354 King St.W - Temp | 99 | COMPLETE | Safety |  |  | Kappheim, Adam | No | Oosterlinck, David | Roy Owen | 46893.94 | 56390.46 | 9496.52 | 20.25% | 15226.33 | 17348.31 | 2121.98 | 13.94% | 29618.96 | 34586.71 | 4967.75 | 16.77% | 1409.29 | 3022.84 | 1613.55 | 114.5% | 639.36 | 0 | -639.36 | -100% | 102 | 159.25 | 57.25 | 56.13% | 2022-11-14 01:00
Hamilton | 2019 | 451813 | 810 Beeforth Rd | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Koeppe, Jeffrey | 9553.98 | 11539.98 | 1986 | 20.79% | 5999.95 | 4753.12 | -1246.83 | -20.78% | 1033.91 | 1305.75 | 271.84 | 26.29% | 1128 | 1382 | 254 | 22.52% | 1392.12 | 2851.07 | 1458.95 | 104.8% | 49 | 51.5 | 2.5 | 5.102% | 2019-11-12 01:00
Hamilton | 2020 | 451814 | Nora Frances School | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 53381.95 | 45899.9 | -7482.05 | -14.02% | 10689.23 | 7708.33 | -2980.9 | -27.89% | 39795.89 | 37228.55 | -2567.34 | -6.451% | 2896.83 | 489.78 | -2407.05 | -83.09% | 0 | 0 | 0 |  | 52 | 55.5 | 3.5 | 6.731% | 2020-02-15 01:00
Hamilton | 2020 | 451815 | 623 Upper James St | 95 | COMPLETE | Converted Project |  |  | Frigotto, Rodrigo | No | Alectra Utilities | Koeppe, Jeffrey | 94853.08 | 90950.62 | -3902.46 | -4.114% | 23189.26 | 19512.99 | -3676.27 | -15.85% | 23248.83 | 27253.31 | 4004.48 | 17.22% | 3565.83 | 4411.52 | 845.69 | 23.72% | 44849.16 | 38925 | -5924.16 | -13.21% | 160 | 164 | 4 | 2.5% | 2020-07-31 01:00
Hamilton | 2020 | 451816 | 954 Concession St | 99 | COMPLETE | Converted Project | Labour est. under | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 36499.18 | 54955.62 | 18456.44 | 50.57% | 12314.07 | 24284.63 | 11970.56 | 97.21% | 19752.61 | 11442.61 | -8310 | -42.07% | 4432.5 | 5637 | 1204.5 | 27.17% | 0 | 13157.64 | 13157.64 |  | 156 | 256 | 100 | 64.1% | 2020-10-07 01:00
Hamilton | 2020 | 451817 | 806 Beeforth Rd | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 4 | 4 |  | 2021-04-01 01:00
Hamilton | 2021 | 451818 | 50 LEAVITT BLVD(FORMERLY 36-42 DUNDAS ST.E) - WESCAM BUILDING | 99 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Oosterlinck, David | Roy Owen | 19590.69 | 22237.11 | 2646.42 | 13.51% | 12195.33 | 16362 | 4166.67 | 34.17% | 5161.62 | 4263.03 | -898.59 | -17.41% | 2233.74 | 1408.97 | -824.77 | -36.92% | 0 | 104.55 | 104.55 |  | 101.4 | 114 | 12.6 | 12.43% | 2021-04-01 01:00
Hamilton | 2020 | 451820 | 92 Barton St.E | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 127.73 | 127.73 |  | 0 | 127.73 | 127.73 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 |  | 2019-02-11 01:00
Hamilton | 2019 | 451825 | Bell Make Ready - Pelham Rd | 99 | COMPLETE | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Dan Despres | 7745.38 | 15216.22 | 7470.84 | 96.46% | 1354.33 | 0 | -1354.33 | -100% | 0 | 0 | 0 |  | 135.5 | 0 | -135.5 | -100% | 6255.55 | 0 | -6255.55 | -100% | 18 | 14.5 | -3.5 | -19.44% | 2019-02-11 01:00
Hamilton | 2020 | 451826 | 620 King St. EAST HAM | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-19 01:00
Hamilton | 2019 | 451827 | 1096 Barton St. East | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Faisal | No | Montgomery, Michael | Koeppe, Jeffrey | 46499.68 | 45508.23 | -991.45 | -2.132% | 21173.41 | 46.09 | -21127.32 | -99.78% | 11142.53 | 10800.99 | -341.54 | -3.065% | 4729.2 | 0 | -4729.2 | -100% | 9454.54 | 576.07 | -8878.47 | -93.91% | 288.5 | 252.5 | -36 | -12.48% | 2019-06-19 01:00
Hamilton | 2020 | 451828 | 390 Rymal Rd W HAM | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 12 | 12 |  | 2019-05-07
Hamilton | 2019 | 451829 | 75 Blake St. HAM | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 933.11 | 933.11 |  | 0 | 933.11 | 933.11 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14 | 14 |  | 2019-05-07
Hamilton | 2020 | 451830 | Riverwalk Condos FLA | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-03 01:00
Hamilton | 2019 | 451831 | 95 Howard St. Lynden | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Faisal | No | Montgomery, Michael | Koeppe, Jeffrey | 24052.43 | 35241.49 | 11189.06 | 46.52% | 13257.39 | 9112.99 | -4144.4 | -31.26% | 6717.17 | 7160.38 | 443.21 | 6.598% | 2513.1 | 5564 | 3050.9 | 121.4% | 1564.77 | 4132.75 | 2567.98 | 164.1% | 178.5 | 248.5 | 70 | 39.22% | 2019-08-03 01:00
Hamilton | 2019 | 451832 | 56 Price Ave | 99 | COMPLETE | FTE OTP | N/A | N/A |  | No | Montgomery, Michael | Koeppe, Jeffrey | 23158.62 | 21073.52 | -2085.1 | -9.004% | 10962.85 | 7431.03 | -3531.82 | -32.22% | 6342.4 | 6309.32 | -33.08 | -0.5216% | 2520.6 | 372.95 | -2147.65 | -85.2% | 3332.77 | 4232.77 | 900 | 27% | 151 | 113.25 | -37.75 | -25% | 2019-01-26 01:00
Hamilton | 2019 | 451833 | 477 Dundas St. East | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Faisal | No | Montgomery, Michael | Koeppe, Jeffrey | 72381.63 | 77720.93 | 5339.3 | 7.377% | 18298.49 | 0 | -18298.49 | -100% | 24373.68 | 28418.43 | 4044.75 | 16.59% | 4393.4 | 0 | -4393.4 | -100% | 25316.06 | 0 | -25316.06 | -100% | 265 | 267 | 2 | 0.7547% | 2019-04-19 01:00
Hamilton | 2019 | 451834 | 205 Lovers Lane | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Faisal | No | Montgomery, Michael | Carr, Brad | 17075.7 | 32281.44 | 15205.74 | 89.05% | 2582.66 | 1953.61 | -629.05 | -24.36% | 277.63 | 0 | -277.63 | -100% | 28.3 | 0 | -28.3 | -100% | 14187.11 | 14187.11 | 0 | 0% | 35.5 | 33 | -2.5 | -7.042% | 2019-05-07
Hamilton | 2021 | 451835 | 89 Megna Crt. HAM | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Faisal | No | Montgomery, Michael | Roy Owen | 10337.35 | 10538.52 | 201.17 | 1.946% | 5877.36 | 1139.39 | -4737.97 | -80.61% | 3878.89 | 4654.67 | 775.78 | 20% | 581.1 | 256.5 | -324.6 | -55.86% | 0 | 0 | 0 |  | 83.5 | 78.5 | -5 | -5.988% | 2021-01-19 01:00
Hamilton | 2020 | 451836 | 21 John St. S | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-21 01:00
Hamilton | 2019 | 451838 | 20 Jerseyville Rd. W ANC | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Montgomery, Michael | Carr, Brad | 8251.09 | 7492.35 | -758.74 | -9.196% | 2126.4 | 1791.58 | -334.82 | -15.75% | 395.62 | 0 | -395.62 | -100% | 28.3 | 0 | -28.3 | -100% | 5700.77 | 5700.77 | 0 | 0% | 29 | 28.5 | -0.5 | -1.724% | 2019-02-21 01:00
Hamilton | 2020 | 451839 | 858 Burlington St. E, HAM | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1.5 | 1.5 |  | 2021-07-12 01:00
Hamilton | 2021 | 451840 | 372 DUNDAS ST. E | 98 | COMPLETE | Cont Est Over |  |  | Kappheim, Adam | No | Sabbah, Amir | Macdougall, Stephen | 61586.69 | 54377.34 | -7209.35 | -11.71% | 19020.31 | 13252.69 | -5767.62 | -30.32% | 26728.96 | 27255.4 | 526.44 | 1.97% | 2894.7 | 3042.32 | 147.62 | 5.1% | 12942.72 | 6972.02 | -5970.7 | -46.13% | 146 | 159.5 | 13.5 | 9.247% | 2021-07-12 01:00
Hamilton | 2020 | 451841 | 195 James St. S. | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-11 01:00
Hamilton | 2019 | 451842 | 46 King St. E HAM | 99 | COMPLETE | Converted Project | N/A | N/A | Rao, Faisal | No | Montgomery, Michael | Roy Owen | 7581.76 | 11871.8 | 4290.04 | 56.58% | 6393.16 | 0 | -6393.16 | -100% | 0 | 0 | 0 |  | 1188.6 | 0 | -1188.6 | -100% | 0 | 0 | 0 |  | 93 | 74 | -19 | -20.43% | 2019-04-11 01:00
Hamilton | 2020 | 451843 | 156 5th Conc Rd. E WTD | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-05-07
Hamilton | 2021 | 451844 | 1041 West 5th St. HAM | 95 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Sabbah, Amir | Roy Owen | 80859.66 | 77894.01 | -2965.65 | -3.668% | 19423.69 | 14364.79 | -5058.9 | -26.04% | 41893.28 | 42812.65 | 919.37 | 2.195% | 2542.41 | 4584.07 | 2041.66 | 80.3% | 17000.28 | 14610.82 | -2389.46 | -14.06% | 134 | 149 | 15 | 11.19% | 2021-05-07
Hamilton | 2020 | 451845 | 560 - 580 Highland Rd W, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-03 01:00
Hamilton | 2020 | 451846 | 323 Aberdeen Ave, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-03 01:00
Hamilton | 2020 | 451848 | Rymal and Nebo 27kV Expansion | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Carr, Brad | 1090260.92 | 1381019.54 | 290758.62 | 26.67% | 44977.58 | 11698.03 | -33279.55 | -73.99% | 271423.2 | 475316.6 | 203893.4 | 75.12% | 5239.6 | 1579 | -3660.6 | -69.86% | 768620.54 | 1600 | -767020.54 | -99.79% | 643 | 936.25 | 293.25 | 45.61% | 2020-06-03 01:00
Hamilton | 2020 | 451850 | Main / Broadway MH Install for LRT | 99 | CANCELLED | N/A | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-25 01:00
Hamilton | 2019 | 451852 | 869 Barton St | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Dragojevic, Igor | Koeppe, Jeffrey | 85638.12 | 89589.28 | 3951.16 | 4.614% | 18060.93 | 5818.97 | -12241.96 | -67.78% | 51081.9 | 50458.28 | -623.62 | -1.221% | 3734.5 | 1945 | -1789.5 | -47.92% | 12760.79 | 11244.25 | -1516.54 | -11.88% | 257.5 | 299.25 | 41.75 | 16.21% | 2019-07-13 01:00
Hamilton | 2019 | 451855 | Rogers Make Ready - Nash Rd | 99 | COMPLETE | Labour est. over | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 8666.43 | 16412.66 | 7746.23 | 89.38% | 2844.62 | 0 | -2844.62 | -100% | 952.63 | 0 | -952.63 | -100% | 840.2 | 0 | -840.2 | -100% | 4028.98 | 0 | -4028.98 | -100% | 39 | 34.5 | -4.5 | -11.54% | 2019-05-30
Hamilton | 2019 | 451856 | Rogers Make Ready - Chatham St | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 7252.05 | 13856.8 | 6604.75 | 91.07% | 2788.93 | 0 | -2788.93 | -100% | 381.06 | 0 | -381.06 | -100% | 840.2 | 0 | -840.2 | -100% | 3241.86 | 0 | -3241.86 | -100% | 38 | 39.75 | 1.75 | 4.605% | 2019-04-26 01:00
Hamilton | 2019 | 451859 | Cogeco Make Ready - Lodor St | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Celic, Dusan | Weaver, Thomas | 0 | 770.95 | 770.95 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3 | 3 |  | 2019-01-12 01:00
Hamilton | 2019 | 451863 | 2018 Automated Switches - Part 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Billone, Justin | Carr, Brad | 469409.92 | 514373.21 | 44963.29 | 9.579% | 22095.97 | 12080.73 | -10015.24 | -45.33% | 190869.63 | 225779.99 | 34910.36 | 18.29% | 1965.4 | 95 | -1870.4 | -95.17% | 254478.92 | 82415.9 | -172063.02 | -67.61% | 323 | 395.75 | 72.75 | 22.52% | 2019-10-29 01:00
Hamilton | 2020 | 451865 | 2018 Manhole & Vault Lid Repairs | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 0 | 57330.28 | 57330.28 |  | 0 | 1639.61 | 1639.61 |  | 0 | 1622.62 | 1622.62 |  | 0 | 0 | 0 |  | 0 | 15718.29 | 15718.29 |  | 0 | 0 | 0 |  | 2020-11-04 01:00
Hamilton | 2019 | 451867 | Madison Condos | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Carr, Brad | 28129.68 | 1314689.74 | 1286560.06 | 4574% | 26984.06 | 1460.69 | -25523.37 | -94.59% | 204.02 | 3099.55 | 2895.53 | 1419% | 941.6 | 152 | -789.6 | -83.86% | 0 | 239.2 | 239.2 |  | 380 | 230.25 | -149.75 | -39.41% | 2019-07-05 01:00
Hamilton | 2020 | 451869 | Wentworth -10 #6 Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | yes | Alectra Utilities | Scott Borer | 298365.93 | 495178.61 | 196812.68 | 65.96% | 29380 | 220219.67 | 190839.67 | 649.6% | 36660.3 | 110861.72 | 74201.42 | 202.4% | 104643.61 | 104139.3 | -504.31 | -0.4819% | 127682.02 | 34421.92 | -93260.1 | -73.04% | 2116 | 3140 | 1024 | 48.39% | 2020-11-13 01:00
Hamilton | 2020 | 451870 | 201 Concession 5th E, Flamborough | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-15
Hamilton | 2019 | 451871 | Bell Make Ready - Millen Overpass | 99 | COMPLETE | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 4684.6 | 4684.6 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 0 | 0% | 2019-05-15
Hamilton | 2021 | 451873 | 11 Hillgarden Rd, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-17 01:00
Hamilton | 2020 | 451875 | Skinner Rd. Re work | 99 | CANCELLED | N/A | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-17 01:00
Hamilton | 2019 | 451878 | Baldwin #2 Overhead Conversion Ph 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Carr, Brad | 692773.31 | 715966.38 | 23193.07 | 3.348% | 21224.22 | 9397.32 | -11826.9 | -55.72% | 162472.39 | 183177.85 | 20705.46 | 12.74% | 1698 | 190 | -1508 | -88.81% | 507378.7 | 93905.21 | -413473.49 | -81.49% | 300 | 252.75 | -47.25 | -15.75% | 2019-07-19 01:00
Hamilton | 2019 | 451881 | 89 Osler Dr - Dundas | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Djuric, Zdravko | Roy Owen | 12863.55 | 11679.47 | -1184.08 | -9.205% | 4347.36 | 0 | -4347.36 | -100% | 819.32 | 0 | -819.32 | -100% | 332.1 | 0 | -332.1 | -100% | 7364.77 | 0 | -7364.77 | -100% | 70.5 | 59.75 | -10.75 | -15.25% | 2019-06-07
Hamilton | 2020 | 451882 | 11 Morningstar Crt | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 2821.6 | 2821.6 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-10 01:00
Hamilton | 2019 | 451883 | 11 Oriole Ave - Stoney Creek | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Djuric, Zdravko | Koeppe, Jeffrey | 40433.59 | 41024.84 | 591.25 | 1.462% | 13736.78 | 0 | -13736.78 | -100% | 21881.44 | 17705.88 | -4175.56 | -19.08% | 2750.6 | 0 | -2750.6 | -100% | 2064.77 | 0 | -2064.77 | -100% | 197.5 | 218.5 | 21 | 10.63% | 2019-12-10 01:00
Hamilton | 2020 | 451884 | 41 Hopkins Crt - Dundas | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 2093.86 | 2093.86 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-30
Hamilton | 2019 | 451885 | 68 Turnbull Rd - Dundas | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Djuric, Zdravko | Roy Owen | 5355.7 | 3900.67 | -1455.03 | -27.17% | 4838.55 | 3608.24 | -1230.31 | -25.43% | 242.92 | 221.24 | -21.68 | -8.925% | 274.23 | 7.64 | -266.59 | -97.21% | 0 | 0 | 0 |  | 68.5 | 55.5 | -13 | -18.98% | 2019-05-30
Hamilton | 2019 | 451886 | 114 Overdale Ave - Flamborough | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Djuric, Zdravko | Carr, Brad | 7051.19 | 7336.31 | 285.12 | 4.044% | 2419.79 | 455.47 | -1964.32 | -81.18% | 242.93 | 0 | -242.93 | -100% | 38.7 | 38 | -0.7 | -1.809% | 4349.77 | 3785 | -564.77 | -12.98% | 40.5 | 42.5 | 2 | 4.938% | 2019-07-26 01:00
Hamilton | 2019 | 451887 | 16 Murray St - Hamilton | 99 | COMPLETE | Vehicle Not Charged | Cont Est Over | Estimate incorrect |  | No | Djuric, Zdravko | Koeppe, Jeffrey | 8842.39 | 6195.54 | -2646.85 | -29.93% | 5792.84 | 4775.23 | -1017.61 | -17.57% | 556.78 | 376.03 | -180.75 | -32.46% | 928 | 0 | -928 | -100% | 1564.77 | 987.88 | -576.89 | -36.87% | 81 | 73.5 | -7.5 | -9.259% | 2019-03-23 01:00
Hamilton | 2020 | 451888 | 15 Tevere Pl - Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 2297 | 2297 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-02 01:00
Hamilton | 2020 | 451889 | 137 Peter St - Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 2693.16 | 2693.16 |  | 0 | 165.3 | 165.3 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2019-08-02 01:00
Hamilton | 2020 | 451890 | 530 Scenic Dr - Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 2454.16 | 2454.16 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-02 01:00
Hamilton | 2019 | 451891 | 305 East 37th St - Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Djuric, Zdravko | Koeppe, Jeffrey | 26310.46 | 21929.32 | -4381.14 | -16.65% | 11070.92 | 6205.87 | -4865.05 | -43.94% | 9836.47 | 8581.03 | -1255.44 | -12.76% | 3338.3 | 1955 | -1383.3 | -41.44% | 2064.77 | 1337.5 | -727.27 | -35.22% | 160.5 | 142 | -18.5 | -11.53% | 2019-08-02 01:00
Hamilton | 2020 | 451892 | 26 Berry Hill Ave - Flamborough | 99 | CANCELLED | N/A | N/A | N/A |  | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-03 01:00
Hamilton | 2019 | 451893 | 14 Sullivans Lane, Dundas | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Bennett, Aaron | Carr, Brad | 7257.58 | 8373.53 | 1115.95 | 15.38% | 225.66 | 1619.76 | 1394.1 | 617.8% | 229.05 | 0 | -229.05 | -100% | 49.1 | 0 | -49.1 | -100% | 6753.77 | 6753.77 | 0 | 0% | 33.5 | 26.75 | -6.75 | -20.15% | 2019-05-03 01:00
Hamilton | 2021 | 451894 | 100 Hamilton St N, Waterdown | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Bennett, Aaron | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-01 01:00
Hamilton | 2020 | 451895 | 85 Coreslab Dr, Waterdown | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 5319.27 | 5319.27 |  | 0 | 890.31 | 890.31 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 10 | 10 |  | 2020-04-01 01:00
Hamilton | 2020 | 451896 | 45 Ewen Rd, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1369.34 | 1369.34 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-01 01:00
Hamilton | 2020 | 451897 | 77 Leland St, Hamilton | 98 | CANCELLED |  |  |  | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 14541.67 | 14541.67 |  | 0 | 962.45 | 962.45 |  | 0 | 1548.61 | 1548.61 |  | 0 | 0 | 0 |  | 0 | 12030.61 | 12030.61 |  | 0 | 2 | 2 |  | 2020-04-01 01:00
Hamilton | 2019 | 451898 | 171 Appleford Crt, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 17509.56 | 23062.46 | 5552.9 | 31.71% | 3791.42 | 1317.89 | -2473.53 | -65.24% | 423.4 | 0 | -423.4 | -100% | 253.2 | 0 | -253.2 | -100% | 13041.54 | 16473.65 | 3432.11 | 26.32% | 57 | 61.5 | 4.5 | 7.895% | 2019-06-15 01:00
Hamilton | 2019 | 451899 | Supercrawl, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Koeppe, Jeffrey | 32539.17 | 36617.3 | 4078.13 | 12.53% | 20454.75 | 11887.81 | -8566.94 | -41.88% | 9161.62 | 10388.46 | 1226.84 | 13.39% | 2922.8 | 4816 | 1893.2 | 64.77% | 0 | 4199.03 | 4199.03 |  | 159 | 142 | -17 | -10.69% | 2019-11-23 01:00
Hamilton | 2020 | 451900 | 90 Beach Rd, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1410.8 | 1410.8 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-08 01:00
Hamilton | 2020 | 451901 | 77 Leland St, Hamilton | 99 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 45597.1 | 50032.02 | 4434.92 | 9.726% | 13036.84 | 10647.99 | -2388.85 | -18.32% | 29475.98 | 32654.89 | 3178.91 | 10.78% | 3084.28 | 3534.92 | 450.64 | 14.61% | 0 | 593.35 | 593.35 |  | 140 | 85.5 | -54.5 | -38.93% | 2020-06-08 01:00
Hamilton | 2020 | 451903 | 33 Stoneridge Crt, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1012.7 | 1012.7 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2020 | 451904 | 10 Sherman Rise, Dundas | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1069.38 | 1069.38 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2020 | 451905 | 200 Sherman Ave S, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1613.51 | 1613.51 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2019 | 451906 | 396 Acadia Dr, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Weaver, Thomas | 0 | 1566.12 | 1566.12 |  | 0 | 783.06 | 783.06 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
Hamilton | 2021 | 451907 | 15 Queen St S, Hamilton | 98 | COMPLETE | Estimate incorrect |  |  | Kappheim, Adam | No | Bennett, Aaron | Macdougall, Stephen | 97457.61 | 142636.96 | 45179.35 | 46.36% | 44673.89 | 38210.74 | -6463.15 | -14.47% | 43436.46 | 47622.21 | 4185.75 | 9.636% | 9347.26 | 8564.16 | -783.1 | -8.378% | 0 | 42656.74 | 42656.74 |  | 356.5 | 400.5 | 44 | 12.34% | 2021-01-29 01:00
Hamilton | 2019 | 451908 | 107 MacNab St N, Hamilton | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Bennett, Aaron | Brian Robinson | 20651.33 | 10112.79 | -10538.54 | -51.03% | 7407.31 | 0 | -7407.31 | -100% | 4368.76 | 1532.72 | -2836.04 | -64.92% | 1623.8 | 0 | -1623.8 | -100% | 7251.46 | 0 | -7251.46 | -100% | 99.5 | 111 | 11.5 | 11.56% | 2019-09-28 01:00
Hamilton | 2020 | 451909 | 119 Hwy 5, Waterdown | 95 | COMPLETE | Converted Project |  |  | Frigotto, Rodrigo | No | Alectra Utilities | Roy Owen | 77960.94 | 66918.22 | -11042.72 | -14.16% | 25532.35 | 14180.9 | -11351.45 | -44.46% | 29132.14 | 32296.29 | 3164.15 | 10.86% | 4076.77 | 4504.41 | 427.64 | 10.49% | 19219.68 | 15521.43 | -3698.25 | -19.24% | 168 | 80 | -88 | -52.38% | 2020-06-17 01:00
Hamilton | 2019 | 451910 | 214 Park St W, Dundas | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Carr, Brad | 8061.02 | 3145.22 | -4915.8 | -60.98% | 6083.54 | 305.33 | -5778.21 | -94.98% | 59.5 | 167.19 | 107.69 | 181% | 159.64 | 152 | -7.64 | -4.786% | 1758.34 | 0 | -1758.34 | -100% | 30 | 30.75 | 0.75 | 2.5% | 2019-09-14 01:00
Hamilton | 2019 | 451911 | 43 Woodbine Cres, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Weaver, Thomas | 0 | 1770.25 | 1770.25 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 16.75 | 16.75 |  | 2019-06-01
Hamilton | 2019 | 451913 | Rogers Make Ready - Barton St | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Brian Robinson | 15528.95 | 11711.39 | -3817.56 | -24.58% | 7817.87 | 4768.45 | -3049.42 | -39.01% | 1517.26 | 627.73 | -889.53 | -58.63% | 1387.68 | 943 | -444.68 | -32.04% | 4806.14 | 0 | -4806.14 | -100% | 50 | 59.5 | 9.5 | 19% | 2019-12-21 01:00
Hamilton | 2021 | 451914 | Zayo Make Ready - Escarpment Climb | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 38911.24 | 38911.24 |  | 0 | 5434.95 | 5434.95 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 13128.34 | 13128.34 |  | 0 | 0 | 0 |  | 2020-08-13 01:00
Hamilton | 2019 | 451916 | Highland Rd W - Underground Civil | 99 | COMPLETE | Cont Est Over | BOM not accurate | Estimate incorrect |  | No | Celic, Dusan | Carr, Brad | 388842.33 | 326960.07 | -61882.26 | -15.91% | 7677.97 | 0 | -7677.97 | -100% | 0 | 0 | 0 |  | 907.09 | 0 | -907.09 | -100% | 380257.27 | 0 | -380257.27 | -100% | 109.5 | 122.1 | 12.6 | 11.51% | 2019-04-07 01:00
Hamilton | 2019 | 451920 | Cogeco Make Ready - Central PH1 | 99 | COMPLETE | Cont Est Over | N/A | N/A |  | No | Celic, Dusan | Carr, Brad | 6646.12 | 6707.27 | 61.15 | 0.9201% | 477.78 | 0 | -477.78 | -100% | 191.85 | 0 | -191.85 | -100% | 42.45 | 0 | -42.45 | -100% | 5934.04 | 0 | -5934.04 | -100% | 6.5 | 4 | -2.5 | -38.46% | 2019-02-13 01:00
Hamilton | 2019 | 451922 | 110 Gordon Drummond Ave TX Relocate | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Karan, Andjelo | Andrew Mehlenbacher | 47352.74 | 57858.47 | 10505.73 | 22.19% | 13085.39 | 1233.2 | -11852.19 | -90.58% | 11663.38 | 15064.46 | 3401.08 | 29.16% | 1529.2 | 0 | -1529.2 | -100% | 21074.77 | 9662.82 | -11411.95 | -54.15% | 189 | 159.75 | -29.25 | -15.48% | 2019-05-28
Hamilton | 2019 | 451924 | 2350 Third St. Louth | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Laus, Tomislav | Frank Giancola | 26994.3 | 22842.28 | -4152.02 | -15.38% | 9695.01 | 7483.54 | -2211.47 | -22.81% | 7267.69 | 7058.9 | -208.79 | -2.873% | 3381.6 | 326.52 | -3055.08 | -90.34% | 6650 | 5425 | -1225 | -18.42% | 150 | 121.25 | -28.75 | -19.17% | 2019-03-19 01:00
Hamilton | 2021 | 451927 | Skinner Rd - pad re-location | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 118712.87 | 62747.8 | -55965.07 | -47.14% | 6914.56 | 7237.7 | 323.14 | 4.673% | 14257.64 | 0 | -14257.64 | -100% | 367.9 | 165.5 | -202.4 | -55.01% | 97172.77 | 26443.69 | -70729.08 | -72.79% | 101 | 109.1 | 8.1 | 8.02% | 2021-02-25 01:00
Hamilton | 2019 | 451928 | 2 Reservoir Road - Stoney Creek | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A |  | No | Anderson, Dean | XPopiel, Joseph | 170418.57 | 36400.84 | -134017.73 | -78.64% | 85568.4 | -5.93 | -85574.33 | -100% | 20663.2 | 20286.73 | -376.47 | -1.822% | 29762.2 | 16194.25 | -13567.95 | -45.59% | 34424.77 | -74.21 | -34498.98 | -100.2% | 947 | 768.5 | -178.5 | -18.85% | 2019-03-20 01:00
Hamilton | 2019 | 451930 | 97 Third Rd E | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Dragojevic, Igor | Koeppe, Jeffrey | 22100.52 | 40292.81 | 18192.29 | 82.32% | 8130.7 | 7256.91 | -873.79 | -10.75% | 7080.33 | 6844.28 | -236.05 | -3.334% | 1757.8 | 287.06 | -1470.74 | -83.67% | 5131.69 | 7241.74 | 2110.05 | 41.12% | 115.5 | 113.5 | -2 | -1.732% | 2019-04-20 01:00
Hamilton | 2020 | 451931 | 240 Margaret Ave | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-12 01:00
Hamilton | 2019 | 451932 | 34 Windemere Rd | 99 | COMPLETE | BOM not accurate | N/A | N/A |  | No | Dragojevic, Igor | Koeppe, Jeffrey | 5886.27 | 7971.05 | 2084.78 | 35.42% | 4689.87 | 461.84 | -4228.03 | -90.15% | 299.6 | 1114.27 | 814.67 | 271.9% | 896.8 | 76.2 | -820.6 | -91.5% | 0 | 5773.05 | 5773.05 |  | 69.5 | 69.5 | 0 | 0% | 2019-04-12 01:00
Hamilton | 2020 | 451933 | 991 Main St E | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-17 01:00
Hamilton | 2019 | 451934 | 3 Green Mountain Rd W | 95 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Dragojevic, Igor | Koeppe, Jeffrey | 46796.12 | 52419.82 | 5623.7 | 12.02% | 4833.09 | 14079.38 | 9246.29 | 191.3% | 2887.2 | 27372.44 | 24485.24 | 848.1% | 23812.66 | 3604 | -20208.66 | -84.87% | 15263.17 | 3370.69 | -11892.48 | -77.92% | 221.5 | 263.5 | 42 | 18.96% | 2019-09-17 01:00
Hamilton | 2019 | 451935 | 1439 Main St E | 99 | COMPLETE | Estimate incorrect | N/A | N/A |  | No | Dragojevic, Igor | Koeppe, Jeffrey | 24758.49 | 16174.54 | -8583.95 | -34.67% | 11630.27 | 516.38 | -11113.89 | -95.56% | 7444.72 | 6542.05 | -902.67 | -12.12% | 910.1 | 284.89 | -625.21 | -68.7% | 4773.4 | 6454.8 | 1681.4 | 35.22% | 106.5 | 102.5 | -4 | -3.756% | 2019-03-18 01:00
Hamilton | 2020 | 451936 | 37 & 39 Galbraith Dr | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-03 01:00
Hamilton | 2020 | 451937 | Waterdown Bay - Pond 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Carr, Brad | 11591.47 | 137371.58 | 125780.11 | 1085% | 10298.68 | 3691.16 | -6607.52 | -64.16% | 67.99 | 0 | -67.99 | -100% | 1224.8 | 576.03 | -648.77 | -52.97% | 0 | 0 | 0 |  | 148 | 60.75 | -87.25 | -58.95% | 2020-11-03 01:00
Hamilton | 2020 | 451939 | Hamilton 2019 Pole Residuals Phase1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 157978.01 | 221031.51 | 63053.5 | 39.91% | 12831.52 | 23116.5 | 10284.98 | 80.15% | 33675.73 | 50728.63 | 17052.9 | 50.64% | 2123.36 | 0 | -2123.36 | -100% | 109347.4 | 142420.63 | 33073.23 | 30.25% | 46 | 110.5 | 64.5 | 140.2% | 2020-09-09 01:00
Hamilton | 2019 | 451940 | Ottawa 8 - #6 Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Anderson, Dean | Carr, Brad | 566274.91 | 539686.38 | -26588.53 | -4.695% | 37570.67 | 35927.93 | -1642.74 | -4.372% | 136584.21 | 136338.43 | -245.78 | -0.1799% | 0 | 57 | 57 |  | 392120.03 | 353058.08 | -39061.95 | -9.962% | 457 | 73 | -384 | -84.03% | 2019-11-28 01:00
Hamilton | 2022 | 451944 | FONTAINBLEU - HOUSES PLANNED CAP B&M COSTS | 99 | COMPLETE | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Brad Carr | 0 | 12745.58 | 12745.58 |  | 0 | 6432.73 | 6432.73 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5959.53 | 5959.53 |  | 0 | 0 | 0 |  | 2023-01-03 01:00
Hamilton | 2019 | 451945 | Lantern Lane URD | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Carr, Brad | 115418.17 | 106084.91 | -9333.26 | -8.086% | 4765.65 | 3636.04 | -1129.61 | -23.7% | 12822.12 | 7328.07 | -5494.05 | -42.85% | 0 | 0 | 0 |  | 97830.4 | 25156.38 | -72674.02 | -74.29% | 73 | 107.6 | 34.6 | 47.4% | 2019-07-27 01:00
Hamilton | 2019 | 451946 | Rogers Make Ready - Mohawk Rd W | 99 | COMPLETE | Vac truck | N/A | N/A |  | No | Celic, Dusan | XPopiel, Joseph | 9299.4 | 7949.64 | -1349.76 | -14.51% | 5144.2 | 0 | -5144.2 | -100% | 1015.4 | 0 | -1015.4 | -100% | 1680.4 | 0 | -1680.4 | -100% | 1459.4 | 0 | -1459.4 | -100% | 71 | 68 | -3 | -4.225% | 2019-01-15 01:00
Hamilton | 2019 | 451951 | 331X_Part 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Billone, Justin | Andrew Mehlenbacher | 592399.49 | 694339.2 | 101939.71 | 17.21% | 48189.23 | 69200.51 | 21011.28 | 43.6% | 210611.71 | 228472.71 | 17861 | 8.481% | 9410.4 | 9898 | 487.6 | 5.182% | 324188.15 | 194211.02 | -129977.13 | -40.09% | 729.5 | 906.25 | 176.75 | 24.23% | 2019-12-10 01:00
Hamilton | 2020 | 451952 | 331X_Part 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Andrew Mehlenbacher | 919724.95 | 1100808.87 | 181083.92 | 19.69% | 51583.39 | 93717.26 | 42133.87 | 81.68% | 107829.28 | 76298.34 | -31530.94 | -29.24% | 5410.34 | 7203.68 | 1793.34 | 33.15% | 754901.94 | 751620.88 | -3281.06 | -0.4346% | 529.8 | 563.75 | 33.95 | 6.408% | 2020-10-19 01:00
Hamilton | 2020 | 451953 | 331X_Part 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Andrew Mehlenbacher | 774665.54 | 1129746.95 | 355081.41 | 45.84% | 44764.64 | 111094.65 | 66330.01 | 148.2% | 67786.53 | 90840.02 | 23053.49 | 34.01% | 5386.5 | 7143.37 | 1756.87 | 32.62% | 656727.87 | 841623.83 | 184895.96 | 28.15% | 519 | 619.75 | 100.75 | 19.41% | 2020-11-30 01:00
Hamilton | 2020 | 451954 | Fontainbleu Reliability | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 605492.82 | 85120.05 | -520372.77 | -85.94% | 18557.14 | 18974.23 | 417.09 | 2.248% | 9688.9 | 43479.79 | 33790.89 | 348.8% | 2085.27 | 4051.23 | 1965.96 | 94.28% | 575161.51 | 7985.79 | -567175.72 | -98.61% | 213 | 205 | -8 | -3.756% | 2020-09-29 01:00
Hamilton | 2019 | 451955 | 70 Bobolink | 99 | COMPLETE | N/A | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-13 01:00
Hamilton | 2019 | 451956 | Cogeco Make Ready - Mulberry St | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Celic, Dusan | Weaver, Thomas | 0 | 1165.77 | 1165.77 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 |  | 2019-02-13 01:00
Hamilton | 2020 | 451959 | Juravinski - Gage St Escarpment | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 774954.39 | 603664.28 | -171290.11 | -22.1% | 15725.27 | 48004.89 | 32279.62 | 205.3% | 28151.59 | 101693.79 | 73542.2 | 261.2% | 560 | 0 | -560 | -100% | 730517.53 | 426944.97 | -303572.56 | -41.56% | 53 | 63.25 | 10.25 | 19.34% | 2020-04-20
Hamilton | 2020 | 451960 | Juravinski - Cannon/Gage Upgrades | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 3910321.52 | 4087233.3 | 176911.78 | 4.524% | 62998.4 | 228124.28 | 165125.88 | 262.1% | 849176.63 | 1138988.93 | 289812.3 | 34.13% | 8714 | 5215.5 | -3498.5 | -40.15% | 2989432.49 | 2506432.09 | -483000.4 | -16.16% | 988 | 625.25 | -362.75 | -36.72% | 2020-04-17 01:00
Hamilton | 2020 | 451963 | Bell Pole Relocation - GM & Upp Cen | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2019-12-13 01:00
Hamilton | 2019 | 451964 | 2019 Ridley Heights ( U/G Portion) | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Rolfe, Eric | Carr, Brad | 1773610.41 | 1715022.65 | -58587.76 | -3.303% | 21529.82 | 144535.53 | 123005.71 | 571.3% | 76051.89 | 7306.45 | -68745.44 | -90.39% | 2264 | 4522 | 2258 | 99.73% | 1673764.7 | 1547652.48 | -126112.22 | -7.535% | 385 | 409 | 24 | 6.234% | 2019-12-13 01:00
Hamilton | 2020 | 451966 | U. Gage & Loconder Dr - cable | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 2997686.94 | 3466392.1 | 468705.16 | 15.64% | 252671.75 | 310500.4 | 57828.65 | 22.89% | 593693.02 | 720628.27 | 126935.25 | 21.38% | 35458.1 | 9219.16 | -26238.94 | -74% | 2115864.07 | 2412371.8 | 296507.73 | 14.01% | 2032 | 810 | -1222 | -60.14% | 2020-12-23 01:00
Hamilton | 2019 | 451970 | Rogers Make Ready - Sanatorium Rd | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 11356.26 | 18588.02 | 7231.76 | 63.68% | 4886.81 | 0 | -4886.81 | -100% | 2361.62 | 0 | -2361.62 | -100% | 1623.8 | 0 | -1623.8 | -100% | 2484.03 | 0 | -2484.03 | -100% | 67 | 46.25 | -20.75 | -30.97% | 2019-03-23 01:00
Hamilton | 2020 | 451971 | Hamilton Mountain URD 2019 Part 4 | 99 | CANCELLED | N/A | N/A | N/A |  | No | Alectra Utilities | Weaver, Thomas | 0 | 4328.3 | 4328.3 |  | 0 | 2164.15 | 2164.15 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-05-07
Hamilton | 2020 | 451972 | 60 Vola Court - Rotten Poles | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 148253.75 | 136276.5 | -11977.25 | -8.079% | 1351.16 | 10605.43 | 9254.27 | 684.9% | 0 | 24606.04 | 24606.04 |  | 0 | 0 | 0 |  | 146902.59 | 98556.87 | -48345.72 | -32.91% | 39 | 8.5 | -30.5 | -78.21% | 2020-05-07
Hamilton | 2019 | 451974 | Rogers Make Ready - Frid St | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 7436.31 | 12177.06 | 4740.75 | 63.75% | 3801.36 | 0 | -3801.36 | -100% | 793.5 | 0 | -793.5 | -100% | 1232 | 0 | -1232 | -100% | 1609.45 | 0 | -1609.45 | -100% | 52 | 34 | -18 | -34.62% | 2019-04-22 01:00
Hamilton | 2020 | 451976 | Ottawa 4 - #6 Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | yes | Alectra Utilities | Carr, Brad | 1213776.8 | 968986.02 | -244790.78 | -20.17% | 83391.34 | 76371.57 | -7019.77 | -8.418% | 221350.16 | 247530.45 | 26180.29 | 11.83% | 10703.04 | 0 | -10703.04 | -100% | 898332.26 | 639661.52 | -258670.74 | -28.79% | 120 | 53.75 | -66.25 | -55.21% | 2020-12-23 01:00
Hamilton | 2020 | 451977 | Eleanor & Stonechurch PMH (16458) | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 411787.76 | 442336.28 | 30548.52 | 7.419% | 204764.54 | 28173.79 | -176590.75 | -86.24% | 881.68 | 193328.81 | 192447.13 | 21827% | 183260.16 | 741 | -182519.16 | -99.6% | 22881.38 | 209431.46 | 186550.08 | 815.3% | 210 | 122.5 | -87.5 | -41.67% | 2020-02-15 01:00
Hamilton | 2020 | 451979 | Wentworth St Escarpment Climb - Juravinski | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 406655.25 | 437299.29 | 30644.04 | 7.536% | 276517.35 | 35687.43 | -240829.92 | -87.09% | 1024.46 | 54565.11 | 53540.65 | 5226% | 26532.11 | 28.5 | -26503.61 | -99.89% | 102581.33 | 317087.84 | 214506.51 | 209.1% | 181.5 | 148.5 | -33 | -18.18% | 2020-02-25 01:00
Hamilton | 2020 | 451980 | URD-Limeridge W & Kendale Switches | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 1441315.33 | 1422134.8 | -19180.53 | -1.331% | 24824.59 | 119388.48 | 94563.89 | 380.9% | 408384.46 | 335102.28 | -73282.18 | -17.94% | 1681.36 | 4187.24 | 2505.88 | 149% | 1006424.92 | 936875.22 | -69549.7 | -6.911% | 256 | 309.25 | 53.25 | 20.8% | 2020-11-17 01:00
Hamilton | 2019 | 451981 | Baldwin Conversion - Civil Work | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Karan, Andjelo | Scott Borer | 1106417.99 | 1618119.41 | 511701.42 | 46.25% | 148678.21 | 121601.48 | -27076.73 | -18.21% | 26013.62 | 134633.56 | 108619.94 | 417.6% | 53189.2 | 23727.5 | -29461.7 | -55.39% | 878536.96 | 465771.68 | -412765.28 | -46.98% | 4248 | 4039.75 | -208.25 | -4.902% | 2019-12-19 01:00
Hamilton | 2020 | 451982 | Pole Relocate-Birch Ave & Barton St | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 28991.48 | 25740.56 | -3250.92 | -11.21% | 2156.52 | 3908.88 | 1752.36 | 81.26% | 2675.52 | 1541.47 | -1134.05 | -42.39% | 56 | 0 | -56 | -100% | 24103.44 | 20067.11 | -4036.33 | -16.75% | 6 | 2 | -4 | -66.67% | 2020-06-30 01:00
Hamilton | 2019 | 451983 | Rogers Make Ready - Dundas St E | 99 | COMPLETE | Labour est. over | BOM cost variance | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 9858.08 | 10966.9 | 1108.82 | 11.25% | 5901.76 | 0 | -5901.76 | -100% | 947 | 0 | -947 | -100% | 2015.6 | 0 | -2015.6 | -100% | 993.72 | 0 | -993.72 | -100% | 81 | 43.5 | -37.5 | -46.3% | 2019-04-27 01:00
Hamilton | 2019 | 451984 | Cogeco Make Ready - Macklin St S | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 5315.52 | 9017.08 | 3701.56 | 69.64% | 2790.83 | 0 | -2790.83 | -100% | 190.77 | 0 | -190.77 | -100% | 840.2 | 0 | -840.2 | -100% | 1493.72 | 0 | -1493.72 | -100% | 38 | 14.25 | -23.75 | -62.5% | 2019-03-19 01:00
Hamilton | 2019 | 451985 | Rogers Make Ready - Upp. Ottawa | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 3672.91 | 7587.88 | 3914.97 | 106.6% | 1923.03 | 507.36 | -1415.67 | -73.62% | 59.33 | 0 | -59.33 | -100% | 448.4 | 124 | -324.4 | -72.35% | 1242.15 | 0 | -1242.15 | -100% | 26 | 37 | 11 | 42.31% | 2019-03-22 01:00
Hamilton | 2020 | 451988 | Beach Blvd - Rear Alley Relocation | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | XPopiel, Joseph | 41115.29 | 27975.46 | -13139.83 | -31.96% | 22670.97 | 13040.86 | -9630.11 | -42.48% | 2322.23 | 3260.98 | 938.75 | 40.42% | 4745.37 | 5008 | 262.63 | 5.534% | 11376.72 | 5320 | -6056.72 | -53.24% | 178 | 134 | -44 | -24.72% | 2020-02-22 01:00
Hamilton | 2019 | 451990 | Cogeco Make Ready - Highland Rd W | 99 | COMPLETE | Labour est. over | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Carr, Brad | 3639.39 | 5546.68 | 1907.29 | 52.41% | 684.17 | 0 | -684.17 | -100% | 0 | 0 | 0 |  | 28.3 | 0 | -28.3 | -100% | 2926.92 | 0 | -2926.92 | -100% | 9 | 2.5 | -6.5 | -72.22% | 2019-01-30 01:00
Hamilton | 2019 | 451991 | Rogers Make Ready - Upper Ottawa | 99 | COMPLETE | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 6600.95 | 13553.88 | 6952.93 | 105.3% | 2861.95 | 0 | -2861.95 | -100% | 1156.65 | 0 | -1156.65 | -100% | 840.2 | 0 | -840.2 | -100% | 1742.15 | 0 | -1742.15 | -100% | 39 | 37.25 | -1.75 | -4.487% | 2019-03-14 01:00
Hamilton | 2020 | 451992 | Life - recoverable re-locations | 99 | CANCELLED | N/A | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-07 01:00
Hamilton | 2019 | 451993 | Cogeco Make Ready - Centennial Pkwy | 99 | COMPLETE | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 3166.11 | 5482.4 | 2316.29 | 73.16% | 1921.14 | 0 | -1921.14 | -100% | 79.58 | 0 | -79.58 | -100% | 420.1 | 0 | -420.1 | -100% | 745.29 | 0 | -745.29 | -100% | 26 | 25.75 | -0.25 | -0.9615% | 2019-02-07 01:00
Hamilton | 2019 | 451995 | Wilson St - Duct Structure | 99 | COMPLETE | Scope change - unforeseen | Cont Est Over | Labour est. over |  | No | Billone, Justin | Carr, Brad | 193993.31 | 112097.46 | -81895.85 | -42.22% | 7844.71 | 112097.46 | 104252.75 | 1329% | 0 | 0 | 0 |  | 1188.6 | 0 | -1188.6 | -100% | 184960 | 0 | -184960 | -100% | 112 | 67 | -45 | -40.18% | 2019-02-14 01:00
Hamilton | 2021 | 452001 | 50 Secord Dr | 95 | COMPLETE | Covid-19 |  |  | Paesano, Andrew | No | Dragojevic, Igor | Macdougall, Stephen | 89231.17 | 97992.88 | 8761.71 | 9.819% | 33603.7 | 29013.14 | -4590.56 | -13.66% | 31673.58 | 36974.46 | 5300.88 | 16.74% | 5367.18 | 11354.86 | 5987.68 | 111.6% | -9169.29 | 17289.42 | 26458.71 | -288.6% | 252 | 372.5 | 120.5 | 47.82% | 2021-08-13 01:00
Hamilton | 2021 | 452008 | 690 Rennie St | 98 | COMPLETE | Commodity Price | Cont Est Under |  | Paesano, Andrew | No | Dragojevic, Igor | Macdougall, Stephen | 60683.38 | 72232.38 | 11549 | 19.03% | 13128.25 | 17232.9 | 4104.65 | 31.27% | 44231.19 | 49115.56 | 4884.37 | 11.04% | 3323.94 | 2959 | -364.94 | -10.98% | 0 | 2185.72 | 2185.72 |  | 131.5 | 140 | 8.5 | 6.464% | 2021-12-13 01:00
Hamilton | 2019 | 452010 | Bell Make Ready - West Ave | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Koeppe, Jeffrey | 14360.34 | 14238.86 | -121.48 | -0.8459% | 7307.62 | 0 | -7307.62 | -100% | 1673.6 | 1405.64 | -267.96 | -16.01% | 2072.2 | 0 | -2072.2 | -100% | 3306.92 | 0 | -3306.92 | -100% | 99 | 107.5 | 8.5 | 8.586% | 2019-06-27 01:00
Hamilton | 2019 | 452011 | Stroud #3 Phase 6 Completion | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Carr, Brad | 578330.16 | 531550.3 | -46779.86 | -8.089% | 469004.16 | 26305.2 | -442698.96 | -94.39% | 962.2 | 37065.01 | 36102.81 | 3752% | 43495.68 | 465.5 | -43030.18 | -98.93% | 64868.12 | 278292.66 | 213424.54 | 329% | 138 | 118 | -20 | -14.49% | 2019-09-25 01:00
Hamilton | 2020 | 452012 | Hamilton 2019 Pole Removals | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Brian Robinson | 0 | 297979.83 | 297979.83 |  | 0 | 70918.65 | 70918.65 |  | 0 | 58177.59 | 58177.59 |  | 0 | 0 | 0 |  | 0 | -1668.8 | -1668.8 |  | 0 | 325.75 | 325.75 |  | 2020-02-04 01:00
Hamilton | 2020 | 452016 | Juravinski - Circuit 8621 X Install - Part 2 | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Tony Ierace | 400974.9 | 544144.27 | 143169.37 | 35.71% | 44605.83 | 67489.42 | 22883.59 | 51.3% | 230282.7 | 275848.32 | 45565.62 | 19.79% | 7665.2 | 8057.5 | 392.3 | 5.118% | 118421.17 | 190389.33 | 71968.16 | 60.77% | 680.5 | 606 | -74.5 | -10.95% | 2020-10-16 01:00
Hamilton | 2020 | 452018 | 391X - Feeder Extension | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Andrew Mehlenbacher | 403943.15 | 383581.67 | -20361.48 | -5.041% | 37038.5 | 84677.17 | 47638.67 | 128.6% | 324891.71 | 257742.07 | -67149.64 | -20.67% | 6693.4 | 24977.57 | 18284.17 | 273.2% | 35319.54 | 10814.57 | -24504.97 | -69.38% | 556.5 | 1142.75 | 586.25 | 105.3% | 2020-09-10 01:00
Hamilton | 2020 | 452019 | York and Willowglen Pole Replace | 99 | COMPLETE | Engineering by-passed | Engineering by-passed | Engineering by-passed | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 76389.28 | 33751.81 | -42637.47 | -55.82% | 0 | 2488.02 | 2488.02 |  | 64532.16 | 7940.19 | -56591.97 | -87.7% | 0 | 0 | 0 |  | 11857.12 | 21477.55 | 9620.43 | 81.14% | 0 | 0 | 0 |  | 2020-02-19 01:00
Hamilton | 2019 | 452021 | Rogers Make Ready - Highway 8 | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 7108.89 | 5971.18 | -1137.71 | -16% | 2790.83 | 0 | -2790.83 | -100% | 714.7 | 502.41 | -212.29 | -29.7% | 811.9 | 0 | -811.9 | -100% | 2791.46 | 0 | -2791.46 | -100% | 38 | 26 | -12 | -31.58% | 2019-07-13 01:00
Hamilton | 2019 | 452022 | OH Prim Relocate - North Service Rd | 99 | COMPLETE | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Carr, Brad | 55544.19 | 90894.46 | 35350.27 | 63.64% | 3374.39 | 830.97 | -2543.42 | -75.37% | 0 | 508.93 | 508.93 |  | 169.8 | 0 | -169.8 | -100% | 52000 | 10387.11 | -41612.89 | -80.02% | 44 | 24.5 | -19.5 | -44.32% | 2019-01-29 01:00
Hamilton | 2022 | 452028 | SS VARIOUS IMPROVEMENTS 2019 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-27 01:00
Hamilton | 2019 | 452029 | Central 3 conv (2018 carry-over) | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Wardell, Paul | Carr, Brad | 46396.2 | 318707.41 | 272311.21 | 586.9% | 0 | 733.25 | 733.25 |  | 0 | 22959.76 | 22959.76 |  | 0 | 0 | 0 |  | 46396.2 | 9165.64 | -37230.56 | -80.24% | 123 | 74.25 | -48.75 | -39.63% | 2019-04-27 01:00
Hamilton | 2019 | 452030 | Relocate Hydro Pole - Baldwin St | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Carr, Brad | 47261.22 | 48823.22 | 1562 | 3.305% | 3475.75 | 3980.7 | 504.95 | 14.53% | 5962.79 | 10755.08 | 4792.29 | 80.37% | 0 | 0 | 0 |  | 0 | 32228.69 | 32228.69 |  | 9 | 9 | 0 | 0% | 2019-11-27 01:00
Hamilton | 2020 | 452031 | #6 Replacement - WL4-WL1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | yes | Alectra Utilities | Scott Borer | 1215547.33 | 829740.42 | -385806.91 | -31.74% | 863763.13 | 373704.32 | -490058.81 | -56.74% | 213295.2 | 205258.14 | -8037.06 | -3.768% | 138489 | 133122.9 | -5366.1 | -3.875% | 0 | 113781 | 113781 |  | 7996 | 4509.5 | -3486.5 | -43.6% | 2020-11-13 01:00
Hamilton | 2019 | 452033 | 21 Rivercrest Dr | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Carr, Brad | 19491.69 | 19328.04 | -163.65 | -0.8396% | 10530.21 | 0 | -10530.21 | -100% | 56.6 | 5256.79 | 5200.19 | 9188% | 5166.93 | 0 | -5166.93 | -100% | 3737.95 | 0 | -3737.95 | -100% | 49 | 39 | -10 | -20.41% | 2019-05-14
Hamilton | 2019 | 452041 | Primary Cable Isolation - S.Service | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 555.42 | 555.42 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 27 | 12 | -15 | -55.56% | 2019-03-08 01:00
Hamilton | 2020 | 452042 | Cogeco Make Ready - Queendale Ave E | 99 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Scott Borer | 13335.83 | 9654.24 | -3681.59 | -27.61% | 6056.11 | 4146.83 | -1909.28 | -31.53% | 1943.8 | 1021.31 | -922.49 | -47.46% | 2043.9 | 1792.92 | -250.98 | -12.28% | 3292.02 | 2163.98 | -1128.04 | -34.27% | 78 | 98 | 20 | 25.64% | 2020-02-01 01:00
Hamilton | 2019 | 452044 | 2019 Bell Bonds | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Hewitson, Trevor | 2567.58 | 2553.3 | -14.28 | -0.5562% | 2174.76 | 0 | -2174.76 | -100% | 68.22 | 57.8 | -10.42 | -15.27% | 324.6 | 0 | -324.6 | -100% | 0 | 0 | 0 |  | 29 | 33 | 4 | 13.79% | 2019-11-29 01:00
Hamilton | 2020 | 452045 | Hydro Pole Relocates - Dundas St E | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 501411.18 | 408091.73 | -93319.45 | -18.61% | 13208.23 | 34225.09 | 21016.86 | 159.1% | 62855.95 | 105123.71 | 42267.76 | 67.25% | 677 | 228 | -449 | -66.32% | 424670 | 268514.93 | -156155.07 | -36.77% | 47 | 54.5 | 7.5 | 15.96% | 2020-08-06 01:00
Hamilton | 2020 | 452058 | Wentworth - 12 # 6 Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | XPopiel, Joseph | 211153.31 | 340295.84 | 129142.53 | 61.16% | 0 | 132644.15 | 132644.15 |  | 24565 | 89486.07 | 64921.07 | 264.3% | 90835.98 | 68494 | -22341.98 | -24.6% | 95752.33 | 28806.5 | -66945.83 | -69.92% | 1344 | 1662.5 | 318.5 | 23.7% | 2020-01-18 01:00
Hamilton | 2020 | 452059 | U/G Pedestal Replacement-St cath | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Frank Giancola | 106904.43 | 93867.39 | -13037.04 | -12.2% | 49711.78 | 41621.25 | -8090.53 | -16.27% | 31745.85 | 24195.11 | -7550.74 | -23.78% | 9446.8 | 9048 | -398.8 | -4.222% | 16000 | 13764 | -2236 | -13.98% | 448 | 643 | 195 | 43.53% | 2020-02-29 01:00
Hamilton | 2020 | 452061 | 65 Guise St Structure Conversion | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 396377.49 | 399816.17 | 3438.68 | 0.8675% | 8118.89 | 33003.47 | 24884.58 | 306.5% | 66889.25 | 89710.34 | 22821.09 | 34.12% | 570 | 608 | 38 | 6.667% | 320799.35 | 276321.88 | -44477.47 | -13.86% | 73 | 53 | -20 | -27.4% | 2020-08-20 01:00
Hamilton | 2020 | 452062 | Discovery Dr. Structure Relocation | 99 | CANCELLED | N/A | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-08 01:00
Hamilton | 2019 | 452068 | Cogeco Make Ready - Park St | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Carr, Brad | 3175.68 | 2377.57 | -798.11 | -25.13% | 692.45 | 0 | -692.45 | -100% | 327.59 | 0 | -327.59 | -100% | 28.3 | 0 | -28.3 | -100% | 2127.34 | 0 | -2127.34 | -100% | 9 | 3.5 | -5.5 | -61.11% | 2019-03-22 01:00
Hamilton | 2020 | 452069 | Manhole Roof Replacement - Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 284160.86 | 298021.69 | 13860.83 | 4.878% | 15271.38 | 32885.74 | 17614.36 | 115.3% | 0 | 13757.13 | 13757.13 |  | 896 | 1101.21 | 205.21 | 22.9% | 267993.48 | 247355.26 | -20638.22 | -7.701% | 80 | 58.5 | -21.5 | -26.88% | 2020-12-23 01:00
Hamilton | 2020 | 452070 | HI-2 Removal | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 190761.63 | 187515.61 | -3246.02 | -1.702% | 10674.25 | 11839.78 | 1165.53 | 10.92% | 39615.06 | 69814.28 | 30199.22 | 76.23% | 392 | 209 | -183 | -46.68% | 140080.32 | 104495.14 | -35585.18 | -25.4% | 37 | 25 | -12 | -32.43% | 2020-02-01 01:00
Hamilton | 2019 | 452071 | Cogeco Make Ready - John St N | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Hewitson, Trevor | 4741.48 | 3880.29 | -861.19 | -18.16% | 2508.63 | 1594.95 | -913.68 | -36.42% | 529 | 740.02 | 211.02 | 39.89% | 627.32 | 0 | -627.32 | -100% | 1076.53 | 0 | -1076.53 | -100% | 34 | 41 | 7 | 20.59% | 2019-09-10 01:00
Hamilton | 2020 | 452072 | Feeder Unshare-Juravinski Hospital | 98 | COMPLETE | Converted Project | Material reused |  | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 833434.39 | 943461.06 | 110026.67 | 13.2% | 14077.1 | 46673.25 | 32596.15 | 231.6% | 160866 | 249898.01 | 89032.01 | 55.35% | 1132 | 0 | -1132 | -100% | 657359.29 | 480700.01 | -176659.28 | -26.87% | 194 | 95 | -99 | -51.03% | 2020-10-09 01:00
Hamilton | 2019 | 452073 | 2019 Rogers Bonds | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Hewitson, Trevor | 1065.05 | 4189.11 | 3124.06 | 293.3% | 905.47 | 195.98 | -709.49 | -78.36% | 24.08 | 0 | -24.08 | -100% | 135.5 | 0 | -135.5 | -100% | 0 | 0 | 0 |  | 40 | 44.25 | 4.25 | 10.62% | 2019-11-29 01:00
Hamilton | 2019 | 452074 | Cogeco Make Ready - Burlington St | 99 | COMPLETE | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 1090.96 | 1090.96 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 |  | 2019-03-30 01:00
Hamilton | 2019 | 452075 | Cogeco Make Ready - Cosby Rd | 99 | COMPLETE | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 2207.17 | 2207.17 |  | 0 | 0 | 0 |  | 0 | 41.25 | 41.25 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2 | 1 | -1 | -50% | 2019-04-13 01:00
Hamilton | 2019 | 452079 | Cogeco Make Ready - Glover Rd | 99 | COMPLETE | Labour est. over | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 2218.38 | 2580.76 | 362.38 | 16.34% | 1363.3 | 0 | -1363.3 | -100% | 57.1 | 0 | -57.1 | -100% | 135.5 | 0 | -135.5 | -100% | 662.48 | 0 | -662.48 | -100% | 18 | 8 | -10 | -55.56% | 2019-05-03 01:00
Hamilton | 2020 | 452081 | 191 James St N, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 619.09 | 619.09 |  | 0 | 600.09 | 600.09 |  | 0 | 0 | 0 |  | 0 | 19 | 19 |  | 0 | 0 | 0 |  | 0 | 8 | 8 |  | 2019-12-28 01:00
Hamilton | 2019 | 452082 | 1575 Main St W, Hamilton | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 63171.19 | 49404.62 | -13766.57 | -21.79% | 35879.71 | 11204.54 | -24675.17 | -68.77% | 21278.16 | 28652.5 | 7374.34 | 34.66% | 6013.32 | 2324 | -3689.32 | -61.35% | 0 | 6647.8 | 6647.8 |  | 272 | 100.5 | -171.5 | -63.05% | 2019-12-28 01:00
Hamilton | 2020 | 452083 | 509 5th Concession Rd E, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1473.5 | 1473.5 |  | 0 | 19.4 | 19.4 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 |  | 2019-07-31 01:00
Hamilton | 2019 | 452084 | 15 Queen St S, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Bennett, Aaron | Koeppe, Jeffrey | 6206.17 | 4701.41 | -1504.76 | -24.25% | 4318.93 | 2364.75 | -1954.18 | -45.25% | 945.94 | 0 | -945.94 | -100% | 941.3 | 633 | -308.3 | -32.75% | 0 | 0 | 0 |  | 68.5 | 63.5 | -5 | -7.299% | 2019-07-31 01:00
Hamilton | 2020 | 452085 | 8 Adams St, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 739.08 | 739.08 |  | 0 | 193.02 | 193.02 |  | 0 | 0 | 0 |  | 0 | 47.5 | 47.5 |  | 0 | 0 | 0 |  | 0 | 2.5 | 2.5 |  | 2021-02-04 01:00
Hamilton | 2020 | 452086 | 138 Overdale Ave, Waterdown | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 92.74 | 92.74 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-02-04 01:00
Hamilton | 2021 | 452087 | 115 Hamilton St N, Waterdown | 98 | COMPLETE | Converted Project |  |  | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 56292.94 | 49128.64 | -7164.3 | -12.73% | 15768.91 | 12305.45 | -3463.46 | -21.96% | 39282.05 | 33900.16 | -5381.89 | -13.7% | 1241.98 | 2386.14 | 1144.16 | 92.12% | 0 | 29.61 | 29.61 |  | 83 | 142.75 | 59.75 | 71.99% | 2021-02-04 01:00
Hamilton | 2020 | 452088 | 107 Florance Ave, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1742.53 | 1742.53 |  | 0 | 584.2 | 584.2 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-26 01:00
Hamilton | 2019 | 452090 | Bell Make Ready - Winchester Blvd | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 8343.42 | 8136.58 | -206.84 | -2.479% | 2871.54 | 538.79 | -2332.75 | -81.24% | 1425.19 | 224.05 | -1201.14 | -84.28% | 840.2 | 0 | -840.2 | -100% | 3206.49 | 1025 | -2181.49 | -68.03% | 39 | 36 | -3 | -7.692% | 2019-07-13 01:00
Hamilton | 2021 | 452091 | Duke St, Wellington St & Lake St | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 6896.35 | 28892.33 | 21995.98 | 319% | 1862.56 | 3941.83 | 2079.27 | 111.6% | 405.55 | 0 | -405.55 | -100% | 179.4 | 371 | 191.6 | 106.8% | 4448.84 | 19483.76 | 15034.92 | 338% | 12 | 28 | 16 | 133.3% | 2021-01-02 01:00
Hamilton | 2020 | 452093 | Jarvis St - King William to King | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 475059.02 | 488529.67 | 13470.65 | 2.836% | 15394.75 | 42661.39 | 27266.64 | 177.1% | 77496.77 | 86233.08 | 8736.31 | 11.27% | 1120 | 1216 | 96 | 8.571% | 381047.5 | 356573.83 | -24473.67 | -6.423% | 101.6 | 115 | 13.4 | 13.19% | 2020-03-17 01:00
Hamilton | 2020 | 452094 | 5 Margaret St., Lynden | 99 | CANCELLED | N/A | N/A | N/A | Rao, Faisal | No | Alectra Utilities | Weaver, Thomas | 0 | 1360.49 | 1360.49 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-07 01:00
Hamilton | 2020 | 452095 | 5 Empress Ave - Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 2018.75 | 2018.75 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-07 01:00
Hamilton | 2020 | 452096 | 176 Queensdale Ave E - Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 3266.59 | 3266.59 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-07 01:00
Hamilton | 2020 | 452099 | 295 Dundas St East - Flamborough | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 70015.15 | 65134.1 | -4881.05 | -6.971% | 22277.07 | 16018.57 | -6258.5 | -28.09% | 18751.11 | 15246.74 | -3504.37 | -18.69% | 4437.49 | 4957 | 519.51 | 11.71% | 24549.48 | 26567.02 | 2017.54 | 8.218% | 170 | 188 | 18 | 10.59% | 2020-04-07 01:00
Hamilton | 2019 | 452100 | 2, 6 & 10 Dennis Ave - Flamborough | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Djuric, Zdravko | Carr, Brad | 27833.67 | 27911.63 | 77.96 | 0.2801% | 21053.54 | 2322.26 | -18731.28 | -88.97% | 59.5 | 0 | -59.5 | -100% | 1054.03 | 133 | -921.03 | -87.38% | 5666.6 | 23177 | 17510.4 | 309% | 40.5 | 27.5 | -13 | -32.1% | 2019-07-31 01:00
Hamilton | 2020 | 452101 | Dennis Ave & Overdale Ave | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 33282.29 | 34455.32 | 1173.03 | 3.524% | 21184.96 | 14602.96 | -6582 | -31.07% | 5801.11 | 9184.74 | 3383.63 | 58.33% | 4293.9 | 4339 | 45.1 | 1.05% | 2002.32 | 3525.34 | 1523.02 | 76.06% | 162 | 182 | 20 | 12.35% | 2020-01-16 01:00
Hamilton | 2020 | 452104 | 30 Jerome Park Dr | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 1393.39 | 1393.39 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-19 01:00
Hamilton | 2019 | 452107 | 154 Main St E Structure Upgrade | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Jolie, Chris | Carr, Brad | 465589.07 | 456303.74 | -9285.33 | -1.994% | 8234.3 | 19012.35 | 10778.05 | 130.9% | 0 | 1812.34 | 1812.34 |  | 1245.2 | 152 | -1093.2 | -87.79% | 456109.57 | 242989.85 | -213119.72 | -46.73% | 119 | 122 | 3 | 2.521% | 2019-11-08 01:00
Hamilton | 2019 | 452108 | Pole Relocation - 41 Oak Ave | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 14980.28 | 12387.21 | -2593.07 | -17.31% | 6833.45 | 336.26 | -6497.19 | -95.08% | 2043.9 | 1999.4 | -44.5 | -2.177% | 1564.77 | 460 | -1104.77 | -70.6% | 4538.16 | 0 | -4538.16 | -100% | 94 | 102.75 | 8.75 | 9.309% | 2019-06-29 01:00
Hamilton | 2019 | 452109 | Pole Relocation - 20 Winona Park Dr | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 8160.03 | 6803.28 | -1356.75 | -16.63% | 1000 | 0 | -1000 | -100% | 1260.3 | 734.83 | -525.47 | -41.69% | 775.65 | 0 | -775.65 | -100% | 5124.08 | 0 | -5124.08 | -100% | 70 | 62 | -8 | -11.43% | 2019-06-05
Hamilton | 2020 | 452110 | Stub Pole Relocate - Steel City Crt | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | XPopiel, Joseph | 7175.03 | 4884.63 | -2290.4 | -31.92% | 5095.2 | 644.01 | -4451.19 | -87.36% | 1232 | 0 | -1232 | -100% | 500 | 0 | -500 | -100% | 347.83 | 1880 | 1532.17 | 440.5% | 70.5 | 1 | -69.5 | -98.58% | 2020-01-18 01:00
Hamilton | 2020 | 452113 | 1215 Barton St (STK) | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Koeppe, Jeffrey | 55956.88 | 55821.24 | -135.64 | -0.2424% | 15708.59 | 12546.67 | -3161.92 | -20.13% | 7254.09 | 10278.77 | 3024.68 | 41.7% | 1415 | 1360.75 | -54.25 | -3.834% | 31579.2 | 30013.62 | -1565.58 | -4.958% | 84.35 | 59.5 | -24.85 | -29.46% | 2020-07-09 01:00
Hamilton | 2020 | 452115 | 690 Rennie 13kV Expansion | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 688528.16 | 669092.54 | -19435.62 | -2.823% | 17109.11 | 41535.21 | 24426.1 | 142.8% | 206010.59 | 240044.08 | 34033.49 | 16.52% | 1864 | 258.5 | -1605.5 | -86.13% | 463544.46 | 386835.87 | -76708.59 | -16.55% | 400 | 273.5 | -126.5 | -31.62% | 2020-08-28 01:00
Hamilton | 2020 | 452116 | 1212 Main St E 13kV Expansion - 7412X | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Carr, Brad | 1250387.78 | 915586.75 | -334801.03 | -26.78% | 57564.9 | 50239.76 | -7325.14 | -12.73% | 655079.15 | 622440.66 | -32638.49 | -4.982% | 11800 | 2984.25 | -8815.75 | -74.71% | 525943.73 | 238739.36 | -287204.37 | -54.61% | 480 | 333 | -147 | -30.63% | 2020-03-24 01:00
Hamilton | 2020 | 452117 | Greenhill Pumping Station | 99 | CANCELLED | N/A | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2019-11-01 01:00
Hamilton | 2019 | 452119 | MH206 - Roof Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Billone, Justin | Carr, Brad | 72786.37 | 84735.2 | 11948.83 | 16.42% | 4632.73 | 3419.55 | -1213.18 | -26.19% | 1693.35 | 9920.15 | 8226.8 | 485.8% | 396.2 | 0 | -396.2 | -100% | 66064.09 | 42744.38 | -23319.71 | -35.3% | 63.5 | 214.5 | 151 | 237.8% | 2019-07-20 01:00
Hamilton | 2020 | 452120 | Myst - Lakeview Dr (STK) | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Koeppe, Jeffrey | 610434.13 | 567334.39 | -43099.74 | -7.061% | 37491.14 | 23032.77 | -14458.37 | -38.56% | 4031.39 | 3471.48 | -559.91 | -13.89% | 5371.92 | 4032 | -1339.92 | -24.94% | 563539.68 | 6479.72 | -557059.96 | -98.85% | 270 | 271 | 1 | 0.3704% | 2020-04-16 01:00
Hamilton | 2021 | 452122 | CENTRAL CONVERSION - MARKLAND ST | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Wardell, Paul | Brad Carr | 1352318.74 | 1408639.48 | 56320.74 | 4.165% | 49132.81 | 196846.82 | 147714.01 | 300.6% | 243643.13 | 234784.51 | -8858.62 | -3.636% | 10614.04 | 3342.43 | -7271.61 | -68.51% | 1048928.76 | 967384.3 | -81544.46 | -7.774% | 470.17 | 188.5 | -281.67 | -59.91% | 2021-10-01 01:00
Hamilton | 2020 | 452123 | OT-2 #6 CU Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | yes | Alectra Utilities | Carr, Brad | 285885.52 | 285475.33 | -410.19 | -0.1435% | 11516.6 | 22815.47 | 11298.87 | 98.11% | 91486.79 | 78069.53 | -13417.26 | -14.67% | 3235.84 | 587.59 | -2648.25 | -81.84% | 179646.29 | 181189.57 | 1543.28 | 0.8591% | 50 | 39 | -11 | -22% | 2020-10-05 01:00
Hamilton | 2019 | 452124 | Bell Make Ready - Kenilworth Ave | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 4970.07 | 2160.55 | -2809.52 | -56.53% | 2871.54 | 521.98 | -2349.56 | -81.82% | 678.66 | 501.66 | -177 | -26.08% | 840.2 | 468 | -372.2 | -44.3% | 579.67 | 0 | -579.67 | -100% | 39 | 13 | -26 | -66.67% | 2019-07-30 01:00
Hamilton | 2020 | 452126 | #6 Replacement - WL2 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Scott Borer | 421184.59 | 252757.87 | -168426.72 | -39.99% | 308416.01 | 100895.47 | -207520.54 | -67.29% | 63319.58 | 81615.09 | 18295.51 | 28.89% | 49449 | 48567.25 | -881.75 | -1.783% | 0 | 18251.26 | 18251.26 |  | 2856 | 1255 | -1601 | -56.06% | 2020-12-11 01:00
Hamilton | 2019 | 452131 | 24 King St West | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | XPopiel, Joseph | 4832.55 | 1225.62 | -3606.93 | -74.64% | 0 | 936 | 936 |  | 868.5 | 0 | -868.5 | -100% | 336.65 | 53 | -283.65 | -84.26% | 3627.4 | 0 | -3627.4 | -100% | 50 | 14 | -36 | -72% | 2019-08-10 01:00
Hamilton | 2020 | 452134 | Rymal Rd Widening - City of Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 122736.24 | 82229 | -40507.24 | -33% | 6738.19 | 13081 | 6342.81 | 94.13% | 28222.05 | 30756 | 2533.95 | 8.979% | 196 | 0 | -196 | -100% | 87580 | 37366 | -50214 | -57.34% | 20 | 31 | 11 | 55% | 2020-05-14
Hamilton | 2019 | 452135 | Pole Relocate - Kimberly Drive | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 13033.86 | 19518 | 6484.14 | 49.75% | 6629.15 | 5267 | -1362.15 | -20.55% | 727.11 | 1103 | 375.89 | 51.7% | 1191.28 | 986 | -205.28 | -17.23% | 4486.32 | 11850 | 7363.68 | 164.1% | 47 | 46.5 | -0.5 | -1.064% | 2019-11-28 01:00
Hamilton | 2019 | 452136 | Pole Line Relocate - Mountain Brow | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Carr, Brad | 381826.9 | 422111.61 | 40284.71 | 10.55% | 9536.3 | 25935.3 | 16399 | 172% | 73031.23 | 157135.94 | 84104.71 | 115.2% | 0 | 0 | 0 |  | 299259.37 | 232481.1 | -66778.27 | -22.31% | 50 | 48 | -2 | -4% | 2019-11-27 01:00
Hamilton | 2020 | 452138 | Vanier Tower 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Andrew Mehlenbacher | 505857.15 | 437793.47 | -68063.68 | -13.46% | 84866.43 | 77361.05 | -7505.38 | -8.844% | 84213.15 | 25079.16 | -59133.99 | -70.22% | 10343.25 | 7452.8 | -2890.45 | -27.95% | 326434.32 | 326372.35 | -61.97 | -0.01898% | 569 | 610 | 41 | 7.206% | 2020-12-14 01:00
Hamilton | 2021 | 452140 | CENTRAL - ST JAMES PL- 16664 (2020) | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Wardell, Paul | Brad Carr | 1000752.3 | 1058346.96 | 57594.66 | 5.755% | 33340.68 | 162490.35 | 129149.67 | 387.4% | 34402.72 | 46463.21 | 12060.49 | 35.06% | 1853.6 | 0 | -1853.6 | -100% | 931155.3 | 848293.4 | -82861.9 | -8.899% | 130 | 28 | -102 | -78.46% | 2021-10-01 01:00
Hamilton | 2020 | 452141 | MH70A & SB23 - Roof Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Andrew Mehlenbacher | 254278.19 | 237661.58 | -16616.61 | -6.535% | 19889.96 | 33218.6 | 13328.64 | 67.01% | 0 | 6340.87 | 6340.87 |  | 3840 | 887.58 | -2952.42 | -76.89% | 230548.23 | 196165.6 | -34382.63 | -14.91% | 152 | 143 | -9 | -5.921% | 2020-12-01 01:00
Hamilton | 2022 | 452142 | SC752 - Removal | 99 | COMPLETE | Labour est. under | Scope change - unforeseen |  | Beaudrie, Scott | Yes | Billone, Justin | Tony Ierace | 15599.63 | 25102.27 | 9502.64 | 60.92% | 9434.71 | 13683.78 | 4249.07 | 45.04% | 5306.92 | 6654.77 | 1347.85 | 25.4% | 858 | 2171 | 1313 | 153% | 0 | 1986 | 1986 |  | 92 | 167 | 75 | 81.52% | 2022-01-25 01:00
Hamilton | 2020 | 452145 | Rogers Make Ready - South Service Rd | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 6830.84 | 4443.34 | -2387.5 | -34.95% | 2394.24 | 1271.32 | -1122.92 | -46.9% | 227.6 | 0 | -227.6 | -100% | 358.8 | 307.82 | -50.98 | -14.21% | 3850.2 | 1242.15 | -2608.05 | -67.74% | 4 | 8 | 4 | 100% | 2020-08-13 01:00
Hamilton | 2021 | 452146 | CLAPPISON 5/6 PROPERTIES - SUBD ICI EDS | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Gamboa, Henry | No | Morris, Mark | Brad Carr | 507325.11 | 523881.15 | 16556.04 | 3.263% | 31710.43 | 67286.9 | 35576.47 | 112.2% | 10538.76 | 23697.29 | 13158.53 | 124.9% | 3689.12 | 5686.96 | 1997.84 | 54.15% | 461386.8 | 427210 | -34176.8 | -7.407% | 212.99 | 333.5 | 120.51 | 56.58% | 2021-04-13
Hamilton | 2020 | 452148 | 480 Melvin Ave | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Koeppe, Jeffrey | 23588.04 | 0 | -23588.04 | -100% | 15492.49 | 0 | -15492.49 | -100% | 2404.67 | 0 | -2404.67 | -100% | 2992.5 | 0 | -2992.5 | -100% | 2698.38 | 0 | -2698.38 | -100% | 117 | 0 | -117 | -100% | 2020-02-01 01:00
Hamilton | 2020 | 452151 | 1870 Burlington St E | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Roy Owen | 314731.22 | 259972.81 | -54758.41 | -17.4% | 65032.3 | 53392.22 | -11640.08 | -17.9% | 178293.2 | 145017.95 | -33275.25 | -18.66% | 9418.89 | 8850 | -568.89 | -6.04% | 52350.84 | 51666.59 | -684.25 | -1.307% | 286.5 | 528.25 | 241.75 | 84.38% | 2020-09-14 01:00
Hamilton | 2020 | 452153 | 106 King St W, Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-05-06
Hamilton | 2021 | 452154 | 1119 BARTON ST, STONEY CREEK | 99 | COMPLETE | Cont Est Over | Labour est. under |  | Paesano, Andrew | No | Laus, Tomislav | Macdougall, Stephen | 96724.02 | 95882.58 | -841.44 | -0.8699% | 26011.39 | 23482.03 | -2529.36 | -9.724% | 48167.27 | 52979.99 | 4812.72 | 9.992% | 4349.52 | 7677.53 | 3328.01 | 76.51% | 18195.84 | 10579.65 | -7616.19 | -41.86% | 184.23 | 320 | 135.77 | 73.7% | 2021-05-06
Hamilton | 2022 | 452155 | 98 James St S, Hamilton | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Laus, Tomislav | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-22 01:00
Hamilton | 2022 | 452156 | 100 JAMES ST S, HAMILTON | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Laus, Tomislav | Weaver, Thomas | 0 | 15039.38 | 15039.38 |  | 0 | 8210.86 | 8210.86 |  | 0 | 0 | 0 |  | 0 | 69.04 | 69.04 |  | 0 | 6209.5 | 6209.5 |  | 0 | 23.25 | 23.25 |  | 2019-10-22 01:00
Hamilton | 2019 | 452157 | 2 Gage Ave S, Hamilton | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Laus, Tomislav | Koeppe, Jeffrey | 43027.89 | 23186.79 | -19841.1 | -46.11% | 18849.4 | 9703.33 | -9146.07 | -48.52% | 21404.97 | 9718.34 | -11686.63 | -54.6% | 2773.52 | 3658 | 884.48 | 31.89% | 0 | 0 | 0 |  | 159.94 | 121 | -38.94 | -24.35% | 2019-10-22 01:00
Hamilton | 2019 | 452158 | 12 Dundana Ave, Dundas | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Laus, Tomislav | Koeppe, Jeffrey | 8617.83 | 10480.54 | 1862.71 | 21.61% | 6226.2 | 3522.72 | -2703.48 | -43.42% | 375.51 | 3636.2 | 3260.69 | 868.3% | 624 | 546 | -78 | -12.5% | 1392.12 | 2465 | 1072.88 | 77.07% | 70 | 40 | -30 | -42.86% | 2019-08-15 01:00
Hamilton | 2020 | 452159 | 106 King St W, Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-04 01:00
Hamilton | 2022 | 452160 | 110 Bellagio Ave, Hamilton | 99 | CANCELLED | N/A |  |  |  | No | Laus, Tomislav | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-04 01:00
Hamilton | 2020 | 452163 | 29 West Ave., Stoney Creek | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-04 01:00
Hamilton | 2019 | 452178 | Bell Make Ready - Lovers Lane | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Brian Robinson | 5521.78 | 4367.6 | -1154.18 | -20.9% | 4010.66 | 1727.8 | -2282.86 | -56.92% | 232 | 0 | -232 | -100% | 594.72 | 428 | -166.72 | -28.03% | 684.4 | 579.67 | -104.73 | -15.3% | 24 | 12 | -12 | -50% | 2019-10-30 01:00
Hamilton | 2020 | 452181 | Nikola Tesla Blvd, Hamilton | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-05
Hamilton | 2019 | 631350 | Cogeco Make Ready - Birch Ave | 99 | COMPLETE | Filler work | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Brian Robinson | 6364.3 | 2292.03 | -4072.27 | -63.99% | 4010.66 | 589.57 | -3421.09 | -85.3% | 977.76 | 1039.98 | 62.22 | 6.364% | 594.72 | 0 | -594.72 | -100% | 781.16 | 662.48 | -118.68 | -15.19% | 22 | 0 | -22 | -100% | 2019-12-20 01:00
Hamilton | 2020 | 631387 | 100 CHARLTON AVE W | 99 | COMPLETE | Scope – Eng | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Carr, Brad | 42157.97 | 29348.76 | -12809.21 | -30.38% | 9854.45 | 3459.52 | -6394.93 | -64.89% | 25861.07 | 25889.24 | 28.17 | 0.1089% | 1200.32 | 0 | -1200.32 | -100% | 5242.13 | 0 | -5242.13 | -100% | 68 | 19 | -49 | -72.06% | 2020-02-24 01:00
Hamilton | 2020 | 631455 | PARKDALE | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631459 | 170 CONCESSION ST | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631461 | 1318 UPPER WELLINGTON ST | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631462 | 150 JAMES ST.S | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631463 | 539 BARTON ST.E | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631464 | 2 OTTAWA ST.N | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631465 | 1344 HIGHWAY 8 | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631467 | 95 ROCKCLIFFE | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631468 | 30 GOLFWOOD DR | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631469 | 4 PENLAKE CRT - HAMILTON | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 3099.93 | 3099.93 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2020 | 631470 | 201 HIGHWAY 5 WEST - FLAMBOROUGH | 99 | CANCELLED | N/A | N/A | N/A | McAlpine, Robert | No | Alectra Utilities | Dre Danieli | 0 | 2418.33 | 2418.33 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-01 01:00
Hamilton | 2022 | 632381 | 291 LODOR ST - SERVICE UPGRADE | 99 | COMPLETE | Labour est. over |  |  | Kappheim, Adam | No | Sabbah, Amir | Macdougall, Stephen | 52498.39 | 43282.45 | -9215.94 | -17.55% | 25611.8 | 16429.11 | -9182.69 | -35.85% | 19232.35 | 18941.08 | -291.27 | -1.514% | 6499.24 | 5532 | -967.24 | -14.88% | 1155 | 2380.26 | 1225.26 | 106.1% | 204.71 | 184 | -20.71 | -10.12% | 2022-03-28
Hamilton | 2021 | 632672 | 27 CLAREMONT DRIVE | 99 | COMPLETE | Cont Est Under |  |  | Beaudrie, Scott | No | Wardell, Paul | Macdougall, Stephen | 13376.76 | 19553.51 | 6176.75 | 46.18% | 10524.15 | 10702.3 | 178.15 | 1.693% | 1198.69 | 1102.41 | -96.28 | -8.032% | 1653.92 | 1809.65 | 155.73 | 9.416% | 0 | 5939.15 | 5939.15 |  | 52 | 93.5 | 41.5 | 79.81% | 2021-05-28 01:00
Hamilton | 2020 | 632710 | LUSH CONDOS (RED HILL) | 99 | COMPLETE | Labour est. under | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Roy Owen | 505473.03 | 463428.56 | -42044.47 | -8.318% | 28490.85 | 49775.43 | 21284.58 | 74.71% | 2235.14 | 2488.79 | 253.65 | 11.35% | 2164.96 | 2635.19 | 470.23 | 21.72% | 472582.08 | 407946.15 | -64635.93 | -13.68% | 192 | 146 | -46 | -23.96% | 2020-06-19 01:00
Hamilton | 2019 | 632730 | HIGHLAND DUCT STRUCTURE INSTALL | 99 | COMPLETE | Engineering by-passed |  |  | Jakubowski, Mark | No | Celic, Dusan | Carr, Brad | 0 | 82167.78 | 82167.78 |  | 0 | 6229.28 | 6229.28 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 75938.5 | 75938.5 |  | 0 | 0 | 0 |  | 2019-09-12 01:00
Hamilton | 2020 | 632757 | NEBO - 3RD FEEDER | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 299927.56 | 333533.03 | 33605.47 | 11.2% | 8261.28 | 33159.5 | 24898.22 | 301.4% | 191448.63 | 206120.86 | 14672.23 | 7.664% | 394 | 1295.18 | 901.18 | 228.7% | 99823.65 | 92957.49 | -6866.16 | -6.878% | 38 | 255.5 | 217.5 | 572.4% | 2020-02-15 01:00
Hamilton | 2021 | 632760 | CABLE INJECTION INVESTIGATION | 99 | COMPLETE | Scope – Const |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 390385.43 | 262048 | -128337.43 | -32.87% | 6134.84 | 33728.58 | 27593.74 | 449.8% | 0 | 129.67 | 129.67 |  | 0 | 762.24 | 762.24 |  | 384250.59 | 227427.51 | -156823.08 | -40.81% | 72 | 85.5 | 13.5 | 18.75% | 2021-12-10 01:00
Hamilton | 2019 | 632820 | POLE RELOCATION - FEEDER UPGRADE - CHARLTON AVE | 99 | COMPLETE | Engineering by-passed |  |  | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 0 | 36614.16 | 36614.16 |  | 0 | 2854.94 | 2854.94 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 33759.22 | 33759.22 |  | 0 | 0 | 0 |  | 2019-09-12 01:00
Hamilton | 2019 | 632821 | BELL POLE RELOCATE - TRANSFER PRIMARY - NEW INTERSECTION INSTALL | 99 | COMPLETE | Engineering by-passed |  |  | Jakubowski, Mark | No | Celic, Dusan | Scott Borer | 0 | 39579.05 | 39579.05 |  | 0 | 2931.78 | 2931.78 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 36647.27 | 36647.27 |  | 0 | 0 | 0 |  | 2019-09-12 01:00
Hamilton | 2019 | 632831 | COGECO MAKE READY - GREEN MOUNTAIN RD | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Dre Danieli | 3582.7 | 1052.99 | -2529.71 | -70.61% | 2459.66 | 390.51 | -2069.15 | -84.12% | 44.52 | 0 | -44.52 | -100% | 297.36 | 0 | -297.36 | -100% | 781.16 | 662.48 | -118.68 | -15.19% | 0 | 0 | 0 |  | 2019-09-19 01:00
Hamilton | 2021 | 632836 | BELL MAKE READY - MANSFIELD DR | 99 | COMPLETE | BOM – truck stock |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 8002.9 | 4791.81 | -3211.09 | -40.12% | 1654.82 | 1907.98 | 253.16 | 15.3% | 1062.54 | 0 | -1062.54 | -100% | 334.79 | 123 | -211.79 | -63.26% | 4950.75 | 2760.83 | -2189.92 | -44.23% | 22 | 14 | -8 | -36.36% | 2021-03-01 01:00
Hamilton | 2019 | 632837 | 1527 UPPER JAMES ST MAIN SERVICE REMOVAL | 99 | COMPLETE | Estimate incorrect | BOM – truck stock |  | Kappheim, Adam | No | Sabbah, Amir | Roy Owen | 6233.1 | 3343.11 | -2889.99 | -46.37% | 4027.15 | 2992.11 | -1035.04 | -25.7% | 1746.27 | 0 | -1746.27 | -100% | 459.68 | 351 | -108.68 | -23.64% | 0 | 0 | 0 |  | 26 | 22.5 | -3.5 | -13.46% | 2019-10-31 01:00
Hamilton | 2019 | 632838 | 51 Sulphur Springs Rd | 99 | COMPLETE | Estimate incorrect |  |  |  | No | Sabbah, Amir | Koeppe, Jeffrey | 5310.16 | 3690.21 | -1619.95 | -30.51% | 4390.82 | 2784.94 | -1605.88 | -36.57% | 629.54 | 445.27 | -184.27 | -29.27% | 289.8 | 460 | 170.2 | 58.73% | 0 | 0 | 0 |  | 26 | 22 | -4 | -15.38% | 2019-09-18 01:00
Hamilton | 2021 | 632888 | WATERDOWN BAY - PHASE 3 (POND 4) | 99 | COMPLETE | Under 10% | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Roy Owen | 2945070.32 | 2910507.03 | -34563.29 | -1.174% | 139781.75 | 340245.78 | 200464.03 | 143.4% | 54136.17 | 56745.88 | 2609.71 | 4.821% | 13172.04 | 31083.64 | 17911.6 | 136% | 2737980.36 | 2482431.73 | -255548.63 | -9.333% | 1208 | 1332.5 | 124.5 | 10.31% | 2021-02-01 01:00
Hamilton | 2021 | 632889 | WATERDOWN BAY - PHASE 3 (POND 5) | 99 | COMPLETE | Under 10% | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Roy Owen | 1163726.02 | 1169088.25 | 5362.23 | 0.4608% | 38748.84 | 300702.13 | 261953.29 | 676% | 15537.1 | 23901.73 | 8364.63 | 53.84% | 4613.04 | 12895.19 | 8282.15 | 179.5% | 1104827.04 | 831589.2 | -273237.84 | -24.73% | 542.51 | 815 | 272.49 | 50.23% | 2021-09-21 01:00
Hamilton | 2019 | 632897 | 245 JAMES ST N | 99 | COMPLETE | Estimate incorrect |  |  | Kappheim, Adam | No | Sabbah, Amir | Koeppe, Jeffrey | 9650.67 | 6534.87 | -3115.8 | -32.29% | 8531.57 | 5633.87 | -2897.7 | -33.96% | 544.9 | 0 | -544.9 | -100% | 574.2 | 901 | 326.8 | 56.91% | 0 | 0 | 0 |  | 48 | 55 | 7 | 14.58% | 2019-08-30 01:00
Hamilton | 2022 | 632932 | JOINT USE PERMIT HW2019-022 - WHITNEY AND EMERSON - HAM | 99 | COMPLETE | Engineering by-passed |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 13358.64 | 3024.98 | -10333.66 | -77.36% | 7616.55 | 976.22 | -6640.33 | -87.18% | 463.95 | 61.32 | -402.63 | -86.78% | 1412.46 | 0 | -1412.46 | -100% | 3865.68 | 1987.44 | -1878.24 | -48.59% | 46 | 0 | -46 | -100% | 2022-01-25 01:00
Hamilton | 2020 | 633037 | 550 FENNELL AVE.E - POWER CENTER UPGRADE | 99 | COMPLETE | BOM – truck stock |  |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 86674.1 | 102246.94 | 15572.84 | 17.97% | 32726.68 | 28331.3 | -4395.38 | -13.43% | 43287.74 | 61320.73 | 18032.99 | 41.66% | 2360.96 | 5476.21 | 3115.25 | 131.9% | 8298.72 | 7118.7 | -1180.02 | -14.22% | 227 | 286.75 | 59.75 | 26.32% | 2020-11-17 01:00
Hamilton | 2019 | 633041 | POLE RELOCATION - GRADING CHANGE - CN BRIDGE | 99 | COMPLETE | Est. Int. - Act. External | BOM not used | N/A | Jakubowski, Mark | No | Celic, Dusan | Carr, Brad | 21272.28 | 13937.51 | -7334.77 | -34.48% | 12901.12 | 1881.54 | -11019.58 | -85.42% | 2950.24 | 0 | -2950.24 | -100% | 2378.88 | 113.45 | -2265.43 | -95.23% | 3042.04 | 11942.52 | 8900.48 | 292.6% | 82 | 10 | -72 | -87.8% | 2019-11-27 01:00
Hamilton | 2019 | 633160 | 80 AUBREY AVE, HAMILTON - NEW 200A U/G SERVICE | 99 | COMPLETE | Labour est. over |  |  | Paesano, Andrew | No | Bharosi, Mohindra | Koeppe, Jeffrey | 30597.25 | 25977.95 | -4619.3 | -15.1% | 14958.98 | 9202.67 | -5756.31 | -38.48% | 4299.95 | 4353.82 | 53.87 | 1.253% | 1749 | 1751 | 2 | 0.1144% | 9589.32 | 10670.46 | 1081.14 | 11.27% | 115 | 54 | -61 | -53.04% | 2019-11-12 01:00
Hamilton | 2020 | 633189 | BELL MAKE READY - RESERVOIR RD & FIFTY RD | 99 | COMPLETE | Scope change - unforeseen | Labour est. over | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 6149.96 | 3779.59 | -2370.37 | -38.54% | 2991.24 | 914.92 | -2076.32 | -69.41% | 0 | 0 | 0 |  | 465.07 | 51.78 | -413.29 | -88.87% | 2693.65 | 2812.89 | 119.24 | 4.427% | 14 | 4 | -10 | -71.43% | 2020-06-22 01:00
Hamilton | 2020 | 633192 | ROGERS MAKE READY - MOHAWK RD E | 99 | COMPLETE | BOM not used | Cont Est Over | Scope change - unforeseen | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 5802.32 | 4626.35 | -1175.97 | -20.27% | 1414.47 | 1296.79 | -117.68 | -8.32% | 447.95 | 0 | -447.95 | -100% | 89.7 | 293.44 | 203.74 | 227.1% | 3850.2 | 3036.12 | -814.08 | -21.14% | 9 | 9 | 0 | 0% | 2020-07-06 01:00
Hamilton | 2019 | 633198 | ROGERS MAKE READY - CONCESSION ST | 99 | COMPLETE | Labour est. over |  |  | Jakubowski, Mark | No | Celic, Dusan | Hewitson, Trevor | 6250.32 | 1328.65 | -4921.67 | -78.74% | 3019.94 | 588.48 | -2431.46 | -80.51% | 232 | 0 | -232 | -100% | 396.48 | 160.5 | -235.98 | -59.52% | 2601.9 | 579.67 | -2022.23 | -77.72% | 15 | 4.5 | -10.5 | -70% | 2019-10-30 01:00
Hamilton | 2022 | 633200 | 446 DUNDAS ST.E - TEMP | 99 | COMPLETE | Labour est. over |  |  | Kappheim, Adam | No | Oosterlinck, David | Macdougall, Stephen | 70605.73 | 52274.02 | -18331.71 | -25.96% | 29328.62 | 15898.8 | -13429.82 | -45.79% | 28793.83 | 24638.33 | -4155.5 | -14.43% | 5392 | 3273.39 | -2118.61 | -39.29% | 7091.28 | 8463.5 | 1372.22 | 19.35% | 214.02 | 168 | -46.02 | -21.5% | 2022-03-11 01:00
Hamilton | 2020 | 633220 | 2020 SWITCH REPLACEMENT PROGRAM - HAMILTON | 99 | COMPLETE | Est. Ext. - Act. Internal | BOM not accurate | Estimate incorrect | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 387778.19 | 330505.27 | -57272.92 | -14.77% | 77493.66 | 21250.64 | -56243.02 | -72.58% | 169104.77 | 200074.75 | 30969.98 | 18.31% | 11902.4 | 1175.19 | -10727.21 | -90.13% | 129277.36 | 108004.69 | -21272.67 | -16.46% | 693 | 94.5 | -598.5 | -86.36% | 2020-12-23 01:00
Hamilton | 2020 | 633225 | CENTRAL CONVERSION (2020 WORK) | 99 | COMPLETE | Cont Est Under | Scope change - unforeseen | Labour est. under | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 1867480.45 | 2076870 | 209389.55 | 11.21% | 30118.6 | 169398.12 | 139279.52 | 462.4% | 419625.48 | 438079.79 | 18454.31 | 4.398% | 2324 | 4473.09 | 2149.09 | 92.47% | 1415412.37 | 1464919 | 49506.63 | 3.498% | 207 | 304.75 | 97.75 | 47.22% | 2020-12-23 01:00
Hamilton | 2022 | 633227 | KENILWORTH TS - STATION UPGRADE | 99 | COMPLETE | Under 10% |  |  | Braletic, Bob | No | Lustrinelli, Mark | Tony Ierace | 1287508.79 | 1324793.21 | 37284.42 | 2.896% | 251892.84 | 219672.04 | -32220.8 | -12.79% | 913429.88 | 913427.88 | -2 | -0.000219% | 46376.3 | 46378.3 | 2 | 0.004313% | 75809.77 | 144534.08 | 68724.31 | 90.65% | 1400 | 2650.5 | 1250.5 | 89.32% | 2022-02-04 01:00
Hamilton | 2021 | 633256 | 258 BEACH BLVD - NEW UNDERGROUND SERVICE | 99 | COMPLETE | Under 10% | N/A | N/A | Paesano, Andrew | No | Bharosi, Mohindra | Roy Owen | 23731.4 | 24343.75 | 612.35 | 2.58% | 10433.05 | 13480.56 | 3047.51 | 29.21% | 5096.95 | 5563.34 | 466.39 | 9.15% | 2527.4 | 3956.5 | 1429.1 | 56.54% | 5674 | 1343.35 | -4330.65 | -76.32% | 134.4 | 165.5 | 31.1 | 23.14% | 2021-03-04 01:00
Hamilton | 2020 | 633376 | 176 OAKDALE AVE | 95 | COMPLETE | Vac truck | Cont Est Over | Labour est. over | Frigotto, Rodrigo | No | Alectra Utilities | Frank Giancola | 57475.75 | 38014.62 | -19461.13 | -33.86% | 22102.08 | 12650.83 | -9451.25 | -42.76% | 18676.1 | 20627.64 | 1951.54 | 10.45% | 4257.04 | 1987.9 | -2269.14 | -53.3% | 12440.53 | 2748.25 | -9692.28 | -77.91% | 158 | 88 | -70 | -44.3% | 2020-10-16 01:00
Hamilton | 2020 | 633391 | ROGERS MAKE READY - CENTRAL CONVERSION PHASE 3 | 99 | COMPLETE | Scope change - unforeseen | Scope change - unforeseen | Labour est. over | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 10610.15 | 6118.04 | -4492.11 | -42.34% | 3525.24 | 3631.85 | 106.61 | 3.024% | 1530.39 | 63.25 | -1467.14 | -95.87% | 366.71 | 376 | 9.29 | 2.533% | 5187.81 | 2046.94 | -3140.87 | -60.54% | 12 | 37 | 25 | 208.3% | 2020-10-26 01:00
Hamilton | 2019 | 633453 | 476 BEACH ROAD | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Bharosi, Mohindra | Koeppe, Jeffrey | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-22 01:00
Hamilton | 2022 | 633500 | ST. MARY'S CHURCH - PARK ST & SHEAFFE ST | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-04-29
Hamilton | 2021 | 633562 | REBUILD: W 34TH & W 33RD STREET, N OF LESLIE AVE (HAMILTON) - 16 | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 341580.3 | 320776.97 | -20803.33 | -6.09% | 14202.56 | 46905.36 | 32702.8 | 230.3% | 53782.72 | 66309.4 | 12526.68 | 23.29% | 1904.69 | 1245.31 | -659.38 | -34.62% | 271690.33 | 206316.9 | -65373.43 | -24.06% | 40 | 41 | 1 | 2.5% | 2021-06-17 01:00
Hamilton | 2020 | 633588 | 65 ROCKCLIFFE RD - RELOCATE SERVICE FOR ADDITION | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-22 01:00
Hamilton | 2022 | 633651 | 2 BOLD ST, HAMILTON | 98 | COMPLETE | Estimate incorrect | Material Over Estimated |  | Jakubowski, Mark | No | Patel, Ketan | Brian Robinson | 12473.1 | 9428.74 | -3044.36 | -24.41% | 8559.91 | 6288.47 | -2271.44 | -26.54% | 2793.19 | 1825.55 | -967.64 | -34.64% | 1120 | 1314.72 | 194.72 | 17.39% | 0 | 0 | 0 |  | 50 | 55 | 5 | 10% | 2022-12-20 01:00
Hamilton | 2019 | 633822 | NEWTON TS - T2 REPLACEMENT WORK | 99 | COMPLETE | BOM not accurate | N/A | N/A | Braletic, Bob | No | Lustrinelli, Mark | Roy Owen | 53204.35 | 34146.63 | -19057.72 | -35.82% | 18739.06 | 15942.08 | -2796.98 | -14.93% | 33227.29 | 16060.05 | -17167.24 | -51.67% | 1238 | 2144.5 | 906.5 | 73.22% | 0 | 0 | 0 |  | 147 | 148 | 1 | 0.6803% | 2019-11-27 01:00
Hamilton | 2020 | 633825 | CENTRAL, HOLMESDALE, LUCERNE, HAMILTON | 99 | COMPLETE | Labour est. over | BOM not used | BOM – truck stock | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 9189.73 | 8133.62 | -1056.11 | -11.49% | 1495.86 | 969.79 | -526.07 | -35.17% | 415.34 | 0 | -415.34 | -100% | 134.55 | 0 | -134.55 | -100% | 7143.98 | 7163.83 | 19.85 | 0.2779% | 9 | 0 | -9 | -100% | 2020-10-26 01:00
Hamilton | 2021 | 633827 | 970 PARAMOUNT DR - VALLEY PARK LIBRARY UPGRADE | 95 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Bharosi, Mohindra | Roy Owen | 62909.72 | 61541.5 | -1368.22 | -2.175% | 20556.12 | 17847.6 | -2708.52 | -13.18% | 31100.23 | 35613.77 | 4513.54 | 14.51% | 4175.05 | 1550.16 | -2624.89 | -62.87% | 7078.32 | 6529.97 | -548.35 | -7.747% | 164.8 | 121 | -43.8 | -26.58% | 2021-04-26
Hamilton | 2019 | 633878 | 50 GREEN MOUNTAIN ROAD WEST - REMOVAL / DEMOLITION | 99 | COMPLETE | Estimate incorrect |  |  | Paesano, Andrew | No | Bharosi, Mohindra | Koeppe, Jeffrey | 9356.13 | 6358.57 | -2997.56 | -32.04% | 7381.8 | 5534.57 | -1847.23 | -25.02% | 0 | 0 | 0 |  | 753.93 | 824 | 70.07 | 9.294% | 1220.4 | 0 | -1220.4 | -100% | 52 | 42 | -10 | -19.23% | 2019-11-19 01:00
Hamilton | 2021 | 633938 | CHEGWIN STREET POLE RELOCATION - 3 | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 37627.2 | 26634.22 | -10992.98 | -29.22% | 23315.21 | 13390.72 | -9924.49 | -42.57% | 2772.29 | 4056.15 | 1283.86 | 46.31% | 4740.52 | 4176.28 | -564.24 | -11.9% | 6799.18 | 5011.07 | -1788.11 | -26.3% | 170 | 171 | 1 | 0.5882% | 2021-02-19 01:00
Hamilton | 2021 | 633939 | LAGUNA VILLAGE | 99 | COMPLETE | Labour est. over | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Roy Owen | 922362.25 | 830333.33 | -92028.92 | -9.978% | 43643.69 | 16882.96 | -26760.73 | -61.32% | 86.6 | 0 | -86.6 | -100% | 3360 | 2938.64 | -421.36 | -12.54% | 875271.96 | 74.6 | -875197.36 | -99.99% | 330 | 173.75 | -156.25 | -47.35% | 2021-02-25 01:00
Hamilton | 2021 | 633989 | PEARL ST S, JACKSON ST, AND CANADA ST, HAMILTON | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 7279.88 | 7694.19 | 414.31 | 5.691% | 1081.65 | 1100.3 | 18.65 | 1.724% | 223.98 | 156.98 | -67 | -29.91% | 179.4 | 0 | -179.4 | -100% | 5794.85 | 6436.91 | 642.06 | 11.08% | 12 | 0 | -12 | -100% | 2021-02-22 01:00
Hamilton | 2021 | 634017 | JOINT USE PERMIT HW2019-094 - ANDERSON DR, HAMILTON | 99 | COMPLETE | Est. Ext. - Act. Internal | N/A | N/A | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 11619.94 | 12063.74 | 443.8 | 3.819% | 4377.51 | 1294.08 | -3083.43 | -70.44% | 1480.79 | 1693.32 | 212.53 | 14.35% | 514.19 | 0 | -514.19 | -100% | 5247.45 | 9076.34 | 3828.89 | 72.97% | 32.04 | 2 | -30.04 | -93.76% | 2021-03-24 01:00
Hamilton | 2021 | 634022 | JOINT USE PERMIT HW2019-107 - CENTRE RD, HAMILTON | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | Yes | Johnson, William | Brad Carr | 7721.02 | 1430.9 | -6290.12 | -81.47% | 2830.76 | 518.42 | -2312.34 | -81.69% | 0 | 0 | 0 |  | 585.81 | 0 | -585.81 | -100% | 4304.45 | 912.48 | -3391.97 | -78.8% | 36 | 1 | -35 | -97.22% | 2021-10-20 01:00
Hamilton | 2021 | 634032 | JOINT USE PERMIT HW2019-120 - JOHN S, CHARLTON E, ST JOSEPHS, ETC, HAMILTON | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | West | Brad Carr | 12579.79 | 720.04 | -11859.75 | -94.28% | 965.45 | 0 | -965.45 | -100% | 455.95 | 0 | -455.95 | -100% | 135.45 | 0 | -135.45 | -100% | 11022.94 | 720.04 | -10302.9 | -93.47% | 3.15 | 0 | -3.15 | -100% | 2021-04-08 01:00
Hamilton | 2021 | 634056 | LOVERS LN, HAMILTON | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 10364.72 | 7730.2 | -2634.52 | -25.42% | 3281.84 | 1499.96 | -1781.88 | -54.3% | 2584.26 | 1411.71 | -1172.55 | -45.37% | 818.62 | 492 | -326.62 | -39.9% | 3680 | 4326.53 | 646.53 | 17.57% | 38 | 16 | -22 | -57.89% | 2021-02-04 01:00
Hamilton | 2022 | 634123 | 417-423 HIGHWAY 8, STONEY CREEK | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-17 01:00
Hamilton | 2020 | 634161 | ROGERS BONDS - THIRD BATCH - DUNDURN, WHITNEY, AND GOVERNORS | 99 | COMPLETE | Scope change - unforeseen | Scope change - unforeseen |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 3491.77 | 7860.46 | 4368.69 | 125.1% | 3121.31 | 6259.36 | 3138.05 | 100.5% | 0 | 0 | 0 |  | 370.46 | 1601.1 | 1230.64 | 332.2% | 0 | 0 | 0 |  | 17 | 70 | 53 | 311.8% | 2020-04-23
Hamilton | 2020 | 634162 | 686 PARKDALE AVE N, HAMILTON | 95 | COMPLETE | BOM not accurate | Labour est. under |  | Frigotto, Rodrigo | No | Alectra Utilities | Roy Owen | 199198.32 | 242217.79 | 43019.47 | 21.6% | 49074.28 | 54689.24 | 5614.96 | 11.44% | 86277.86 | 114415.45 | 28137.59 | 32.61% | 6068.34 | 15017.1 | 8948.76 | 147.5% | 57777.84 | 58096 | 318.16 | 0.5507% | 424 | 593.17 | 169.17 | 39.9% | 2020-10-20 01:00
Hamilton | 2021 | 634163 | 121 HIGHWAY #8, STONEY CREEK | 98 | COMPLETE | Cont Est Under | Covid-19 | Scope – Const | Paesano, Andrew | No | Laus, Tomislav | Macdougall, Stephen | 107162.76 | 107969.42 | 806.66 | 0.7527% | 44828.15 | 31540.58 | -13287.57 | -29.64% | 41021.55 | 48662.07 | 7640.52 | 18.63% | 8754.82 | 11734.53 | 2979.71 | 34.04% | 12558.24 | 16032.24 | 3474 | 27.66% | 378.5 | 385.5 | 7 | 1.849% | 2021-01-25 01:00
Hamilton | 2020 | 634164 | 200 GLENDALE AVE N, HAMILTON | 95 | COMPLETE | Labour est. under | Vac truck | Cont Est Over | Frigotto, Rodrigo | No | Alectra Utilities | Roy Owen | 227949.92 | 257723.13 | 29773.21 | 13.06% | 37373.93 | 43235.45 | 5861.52 | 15.68% | 141032.49 | 165300.46 | 24267.97 | 17.21% | 3453.42 | 12015.12 | 8561.7 | 247.9% | 46090.08 | 37172.1 | -8917.98 | -19.35% | 281 | 494.75 | 213.75 | 76.07% | 2020-11-23 01:00
Hamilton | 2020 | 634173 | THE TOWNS AT RED HILL | 99 | COMPLETE | Under 10% | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Koeppe, Jeffrey | 227198.04 | 219228.24 | -7969.8 | -3.508% | 42803.65 | 29567.69 | -13235.96 | -30.92% | 10198.29 | 12438.06 | 2239.77 | 21.96% | 5423.42 | 11528.94 | 6105.52 | 112.6% | 168772.68 | 909.9 | -167862.78 | -99.46% | 219 | 346.75 | 127.75 | 58.33% | 2020-07-31 01:00
Hamilton | 2020 | 634174 | BELL BONDS - X62208, DUNDAS | 99 | COMPLETE | Labour est. over | Scope change - unforeseen | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 3101.68 | 2186.87 | -914.81 | -29.49% | 2784.14 | 1979.74 | -804.4 | -28.89% | 0 | 0 | 0 |  | 317.54 | 207.13 | -110.41 | -34.77% | 0 | 0 | 0 |  | 15 | 16 | 1 | 6.667% | 2020-04-23
Hamilton | 2020 | 634191 | HAMILTON 2019 URGENT POLE REPLACEMENT - PHASE 2 | 99 | COMPLETE | BOM not accurate | Material reused | N/A | Beaudrie, Scott | No | Alectra Utilities | Scott Borer | 137553.65 | 112215.36 | -25338.29 | -18.42% | 41358.57 | 31149.73 | -10208.84 | -24.68% | 39509.55 | 20588.57 | -18920.98 | -47.89% | 9567.02 | 14295.02 | 4728 | 49.42% | 47118.51 | 46182.04 | -936.47 | -1.987% | 369 | 309.5 | -59.5 | -16.12% | 2020-08-10 01:00
Hamilton | 2021 | 634207 | GLOVER, BARTON, AND MCNEILLY, HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 17095.67 | 14463.22 | -2632.45 | -15.4% | 4811.83 | 1618.55 | -3193.28 | -66.36% | 2680.28 | 2325.3 | -354.98 | -13.24% | 687.24 | 0 | -687.24 | -100% | 8916.32 | 10519.37 | 1603.05 | 17.98% | 24 | 0 | -24 | -100% | 2021-02-22 01:00
Hamilton | 2020 | 634208 | Joint Use Permit HW2019-128 Make-Ready , HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 8751.55 | 5328.37 | -3423.18 | -39.12% | 2387.75 | 828.37 | -1559.38 | -65.31% | 529.71 | 0 | -529.71 | -100% | 245.09 | 0 | -245.09 | -100% | 5589 | 4500 | -1089 | -19.48% | 15 | 0 | -15 | -100% | 2020-08-14 01:00
Hamilton | 2021 | 634277 | UPGRADE SC1355 TO A PMH11 WITH SCADA - 1 | 99 | COMPLETE | Labour est. under | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Roy Owen | 127139.08 | 156056.13 | 28917.05 | 22.74% | 7160.91 | 9608.59 | 2447.68 | 34.18% | 118343.17 | 131983.09 | 13639.92 | 11.53% | 1635 | 2225.74 | 590.74 | 36.13% | 0 | 0 | 0 |  | 56 | 122.5 | 66.5 | 118.8% | 2021-01-06 01:00
Hamilton | 2021 | 634308 | COGECO BONDS - 2019 FLAMBOROUGH | 99 | COMPLETE | Cont Est Under |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 1223.48 | 1481.15 | 257.67 | 21.06% | 1044.08 | 295.54 | -748.54 | -71.69% | 0 | 0 | 0 |  | 179.4 | 0 | -179.4 | -100% | 0 | 1185.61 | 1185.61 |  | 8 | 0 | -8 | -100% | 2021-02-22 01:00
Hamilton | 2020 | 634309 | COGECO BONDS - 2019 DUNDAS | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 2845.99 | 1233.81 | -1612.18 | -56.65% | 2581.37 | 147.93 | -2433.44 | -94.27% | 0 | 0 | 0 |  | 264.62 | 0 | -264.62 | -100% | 0 | 1085.88 | 1085.88 |  | 10 | 0 | -10 | -100% | 2020-10-28 01:00
Hamilton | 2020 | 634322 | COGECO BONDS - 2019 WEST HAMILTON | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 1981.11 | 2343.56 | 362.45 | 18.3% | 1622.31 | 1719.56 | 97.25 | 5.995% | 0 | 0 | 0 |  | 358.8 | 624 | 265.2 | 73.91% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0% | 2020-08-21 01:00
Hamilton | 2020 | 634323 | COGECO BONDS - 2019 EAST HAM 1 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 1412.89 | 1645.13 | 232.24 | 16.44% | 1188.64 | 345.1 | -843.54 | -70.97% | 0 | 81.19 | 81.19 |  | 224.25 | 0 | -224.25 | -100% | 0 | 1218.84 | 1218.84 |  | 10 | 0 | -10 | -100% | 2020-10-26 01:00
Hamilton | 2020 | 634325 | COGECO BONDS - 2019 EAST HAM 2 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 1412.89 | 1628.37 | 215.48 | 15.25% | 1188.64 | 295.79 | -892.85 | -75.12% | 0 | 113.74 | 113.74 |  | 224.25 | 0 | -224.25 | -100% | 0 | 1218.84 | 1218.84 |  | 10 | 0 | -10 | -100% | 2020-10-26 01:00
Hamilton | 2020 | 634326 | COGECO BONDS - 2019 EAST HAM 3 | 99 | COMPLETE | Labour est. under | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 1412.89 | 3129.15 | 1716.26 | 121.5% | 1188.64 | 2628.58 | 1439.94 | 121.1% | 0 | 0 | 0 |  | 224.25 | 500.57 | 276.32 | 123.2% | 0 | 0 | 0 |  | 10 | 25 | 15 | 150% | 2020-11-09 01:00
Hamilton | 2020 | 634327 | COGECO BONDS - 2019 EAST HAM 4 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 1412.89 | 1651.34 | 238.45 | 16.88% | 1188.64 | 345.04 | -843.6 | -70.97% | 0 | 0 | 0 |  | 224.25 | 0 | -224.25 | -100% | 0 | 1306.3 | 1306.3 |  | 10 | 0 | -10 | -100% | 2020-10-26 01:00
Hamilton | 2021 | 634365 | WATERDOWN 3RD FEEDER - Deep Dive | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | yes | Anderson, Dean | Brad Carr | 2328847.76 | 2119956.7 | -208891.06 | -8.97% | 99845.84 | 178097.89 | 78252.05 | 78.37% | 402522.86 | 444193.87 | 41671.01 | 10.35% | 11490.18 | 0 | -11490.18 | -100% | 1814988.88 | 1497664.94 | -317323.94 | -17.48% | 48 | 137.5 | 89.5 | 186.5% | 2021-02-10 01:00
Hamilton | 2022 | 634382 | JOINT USE PERMIT 20170719-1474-005 - MILL, WELLINGTON S, MCNAB - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 8892.28 | 5839.56 | -3052.72 | -34.33% | 1680.51 | 1301.84 | -378.67 | -22.53% | 524.57 | 0 | -524.57 | -100% | 0 | 0 | 0 |  | 6687.2 | 4537.72 | -2149.48 | -32.14% | 0 | 0 | 0 |  | 2022-01-24 01:00
Hamilton | 2020 | 634409 | 629 BARTON STREET EAST | 99 | COMPLETE | Labour est. over | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 16091.2 | 8583.54 | -7507.66 | -46.66% | 12112.6 | 3625.51 | -8487.09 | -70.07% | 1711.08 | 1702.53 | -8.55 | -0.4997% | 2267.52 | 968 | -1299.52 | -57.31% | 0 | 2287.5 | 2287.5 |  | 94 | 39 | -55 | -58.51% | 2020-01-07 01:00
Hamilton | 2020 | 634423 | CARDINAL HEIGHTS | 99 | COMPLETE | Labour est. over | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Carr, Brad | 228162.94 | 217296.8 | -10866.14 | -4.762% | 23852.32 | 12583.79 | -11268.53 | -47.24% | 0 | 0 | 0 |  | 499.5 | 901.89 | 402.39 | 80.56% | 203811.12 | 0 | -203811.12 | -100% | 45 | 83.5 | 38.5 | 85.56% | 2020-11-04 01:00
Hamilton | 2020 | 634448 | WILLOW LANE (SCH) - RELOCATE POLES IN SDWK CONFLICT | 99 | COMPLETE | Under 10% | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Koeppe, Jeffrey | 27309.26 | 25701.51 | -1607.75 | -5.887% | 15239.88 | 8081 | -7158.88 | -46.97% | 1669.18 | 6863.3 | 5194.12 | 311.2% | 2894.2 | 3557.21 | 663.01 | 22.91% | 7506 | 7200 | -306 | -4.077% | 108 | 85.5 | -22.5 | -20.83% | 2020-07-20 01:00
Hamilton | 2020 | 634478 | 438 NEBO RD | 98 | COMPLETE | Cont Est Under |  |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 46702.53 | 60269.8 | 13567.27 | 29.05% | 15353.77 | 10108.03 | -5245.74 | -34.17% | 30172.37 | 35688.14 | 5515.77 | 18.28% | 1176.39 | 1468.63 | 292.24 | 24.84% | 0 | 13005 | 13005 |  | 98 | 77 | -21 | -21.43% | 2020-11-02 01:00
Hamilton | 2021 | 634490 | DANBURY ST REBUILD (HAMILTON) - 4 | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | No | Karan, Andjelo | Koeppe, Jeffrey | 51423.32 | 32267.03 | -19156.29 | -37.25% | 36485.09 | 18020.24 | -18464.85 | -50.61% | 3062.66 | 6898.46 | 3835.8 | 125.2% | 9091.33 | 4207.55 | -4883.78 | -53.72% | 2784.24 | 3140.78 | 356.54 | 12.81% | 330 | 203.5 | -126.5 | -38.33% | 2021-01-15 01:00
Hamilton | 2021 | 634492 | KAREN CRES REBUILD (HAMILTON) - 7 | 99 | COMPLETE | Safety |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 115827.63 | 99391.61 | -16436.02 | -14.19% | 73155.83 | 51875.24 | -21280.59 | -29.09% | 14700.24 | 23307.08 | 8606.84 | 58.55% | 18226.72 | 15672.41 | -2554.31 | -14.01% | 9744.84 | 8536.88 | -1207.96 | -12.4% | 644 | 659.5 | 15.5 | 2.407% | 2021-02-26 01:00
Hamilton | 2020 | 634493 | HAMILTON 2020 POLE RESIDUALS PHASE 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 181226.01 | 172162.23 | -9063.78 | -5.001% | 12946.57 | 15760.11 | 2813.54 | 21.73% | 35877.59 | 34364.57 | -1513.02 | -4.217% | 1176 | 0 | -1176 | -100% | 131225.85 | 122037.55 | -9188.3 | -7.002% | 30 | 29.5 | -0.5 | -1.667% | 2020-11-03 01:00
Hamilton | 2020 | 634495 | HAMILTON PCB TX'S OVERHEAD | 99 | COMPLETE | BOM not accurate | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Koeppe, Jeffrey | 72807.33 | 57269.53 | -15537.8 | -21.34% | 36707.6 | 26889.06 | -9818.54 | -26.75% | 26435.11 | 13821.21 | -12613.9 | -47.72% | 8620.53 | 12724.26 | 4103.73 | 47.6% | 1044.09 | 3835 | 2790.91 | 267.3% | 316 | 343 | 27 | 8.544% | 2020-12-07 01:00
Hamilton | 2021 | 634496 | HAMILTON PCB TX'S UNDERGROUND - 1 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Andrew Mehlenbacher | 54676.3 | 43106.98 | -11569.32 | -21.16% | 28246.3 | 14670.02 | -13576.28 | -48.06% | 6411.1 | 7646.32 | 1235.22 | 19.27% | 5514.5 | 2967.79 | -2546.71 | -46.18% | 14504.4 | 17822.85 | 3318.45 | 22.88% | 235 | 127 | -108 | -45.96% | 2021-07-07 01:00
Hamilton | 2021 | 634503 | ST. PETERS HOSPITAL UPGRADE - CUMBERLAND AVE | 99 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Jolie, Chris | Brad Carr | 759207.45 | 722719.01 | -36488.44 | -4.806% | 27176.73 | 57914.63 | 30737.9 | 113.1% | 202616.29 | 211282.88 | 8666.59 | 4.277% | 2016 | 44 | -1972 | -97.82% | 527398.43 | 453477.5 | -73920.93 | -14.02% | 149.28 | 121 | -28.28 | -18.94% | 2021-06-10 01:00
Hamilton | 2021 | 634528 | JOINT USE PERMIT HW2019-087 - CENTRAL, HOLMESDALE, LUCERNE, SUMMERHILL, ETC - HA | 99 | COMPLETE | Material Req incorrectly | N/A | N/A | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 20301.69 | 10320.95 | -9980.74 | -49.16% | 5339.09 | 1373 | -3966.09 | -74.28% | 5739.37 | 753.64 | -4985.73 | -86.87% | 653.43 | 0 | -653.43 | -100% | 8569.8 | 8194.31 | -375.49 | -4.382% | 37.95 | 0 | -37.95 | -100% | 2021-03-24 01:00
Hamilton | 2020 | 634531 | ROGERS MAKE READY - PARKSIDE DR - HAM | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 4577.33 | 3566.59 | -1010.74 | -22.08% | 2186.59 | 620.8 | -1565.79 | -71.61% | 224.14 | 0 | -224.14 | -100% | 179.4 | 56.1 | -123.3 | -68.73% | 1987.2 | 2889.69 | 902.49 | 45.42% | 15 | 2 | -13 | -86.67% | 2020-05-03
Hamilton | 2020 | 634570 | HAMILTON 2020 POLE RESIDUALS PHASE 2 | 99 | COMPLETE | Cont Est Under | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Koeppe, Jeffrey | 134760.83 | 117673.18 | -17087.65 | -12.68% | 81442.76 | 54922.82 | -26519.94 | -32.56% | 30450.71 | 29894.64 | -556.07 | -1.826% | 19735.09 | 24455.3 | 4720.21 | 23.92% | 3132.27 | 8400.42 | 5268.15 | 168.2% | 720 | 702.5 | -17.5 | -2.431% | 2020-11-17 01:00
Hamilton | 2020 | 634641 | CARDINAL HEIGHTS - POLE/PRIM REMOVALS & RE-LOCATIONS | 99 | COMPLETE | Cont Est Over | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Brad Carr | 82800.66 | 62292.33 | -20508.33 | -24.77% | 10974.98 | 10377.8 | -597.18 | -5.441% | 5682.16 | 8914.49 | 3232.33 | 56.89% | 0 | 0 | 0 |  | 66143.52 | 43000.04 | -23143.48 | -34.99% | 14 | 14 | 0 | 0% | 2020-12-04 01:00
Hamilton | 2020 | 634664 | HAMILTON 2020 POLE RESIDUALS PHASE 3 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 145451 | 133056.76 | -12394.24 | -8.521% | 11507.28 | 10933.2 | -574.08 | -4.989% | 21979.29 | 20163.18 | -1816.11 | -8.263% | 1467.87 | 0 | -1467.87 | -100% | 110496.56 | 101960.38 | -8536.18 | -7.725% | 30 | 11 | -19 | -63.33% | 2020-12-17 01:00
Hamilton | 2020 | 634717 | JOINT USE PERMIT HW2019-109 - MAIN ST W, HAM | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 4654.81 | 5058.04 | 403.23 | 8.663% | 1505.21 | 1511.13 | 5.92 | 0.3933% | 0 | 0 | 0 |  | 105.85 | 293.44 | 187.59 | 177.2% | 3043.75 | 3253.47 | 209.72 | 6.89% | 6 | 9 | 3 | 50% | 2020-08-21 01:00
Hamilton | 2022 | 634744 | 1324 RYMAL ROAD EAST | 95 | COMPLETE | Labour est. over | Labour est. over |  | Kappheim, Adam | No | Djuric, Zdravko | Roy Owen | 64354.68 | 46285.25 | -18069.43 | -28.08% | 26460.37 | 11375.79 | -15084.58 | -57.01% | 24469.64 | 25055.11 | 585.47 | 2.393% | 5159.43 | 2738 | -2421.43 | -46.93% | 8265.24 | 7116.35 | -1148.89 | -13.9% | 230 | 119 | -111 | -48.26% | 2022-09-21 01:00
Hamilton | 2020 | 634758 | HAMILTON 2020 POLE RESIDUALS PHASE 4 | 99 | COMPLETE | Material reused | BOM – truck stock | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 241792.56 | 213565.34 | -28227.22 | -11.67% | 13457.29 | 19259.91 | 5802.62 | 43.12% | 57561.61 | 36489.18 | -21072.43 | -36.61% | 1568 | 0 | -1568 | -100% | 169205.66 | 157816.25 | -11389.41 | -6.731% | 70.44 | 4 | -66.44 | -94.32% | 2020-12-23 01:00
Hamilton | 2020 | 634826 | HAMILTON 2020 POLE RESIDUALS PHASE 5 | 99 | COMPLETE | BOM not accurate | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 175423.31 | 110231.09 | -65192.22 | -37.16% | 14230.59 | 9927.01 | -4303.58 | -30.24% | 40673.95 | 23772.25 | -16901.7 | -41.55% | 2126.56 | 0 | -2126.56 | -100% | 118392.21 | 76531.83 | -41860.38 | -35.36% | 20 | 11 | -9 | -45% | 2020-08-06 01:00
Hamilton | 2021 | 634827 | HAMILTON 2020 POLE RESIDUALS PHASE 6 - 8 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Macdougall, Stephen | 161821.39 | 155133.87 | -6687.52 | -4.133% | 79428.73 | 59434.01 | -19994.72 | -25.17% | 19954.28 | 24265.98 | 4311.7 | 21.61% | 22402.5 | 19674 | -2728.5 | -12.18% | 40035.88 | 51759.88 | 11724 | 29.28% | 770 | 757.5 | -12.5 | -1.623% | 2021-05-28 01:00
Hamilton | 2020 | 634916 | 156 5TH CONCESSION ROAD | 99 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 67073.64 | 68906.53 | 1832.89 | 2.733% | 13431.96 | 14350.44 | 918.48 | 6.838% | 31861.34 | 32641.11 | 779.77 | 2.447% | 2464.54 | 4333.24 | 1868.7 | 75.82% | 19315.8 | 15671.06 | -3644.74 | -18.87% | 102 | 164 | 62 | 60.78% | 2020-09-25 01:00
Hamilton | 2020 | 634970 | 391 VICTORIA AVENUE NORTH | 98 | COMPLETE | Labour est. over |  |  | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 53751.43 | 46285.59 | -7465.84 | -13.89% | 18102.84 | 11818.14 | -6284.7 | -34.72% | 23015.32 | 24042.52 | 1027.2 | 4.463% | 3724.35 | 3306.21 | -418.14 | -11.23% | 8908.92 | 7118.72 | -1790.2 | -20.09% | 152 | 104 | -48 | -31.58% | 2020-09-25 01:00
Hamilton | 2021 | 634973 | JOINT USE PERMIT HW2019-140 - PARKSIDE, YORK, MELVILLE, SYDENHAM | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 11181.88 | 10306.93 | -874.95 | -7.825% | 2358.57 | 1678.15 | -680.42 | -28.85% | 447.95 | 460.22 | 12.27 | 2.739% | 179.4 | 0 | -179.4 | -100% | 8195.96 | 8168.56 | -27.4 | -0.3343% | 15 | 2 | -13 | -86.67% | 2021-02-22 01:00
Hamilton | 2021 | 634974 | JOINT USE PERMIT HW2019-141 - INVERNESS, E 13, QUEENSDALE | 99 | COMPLETE | Cont Est Under |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 24941.79 | 31245.71 | 6303.92 | 25.27% | 680.87 | 3591.26 | 2910.39 | 427.5% | 5342.78 | 0 | -5342.78 | -100% | 0 | 44 | 44 |  | 18918.14 | 27610.45 | 8692.31 | 45.95% | 0 | 2 | 2 |  | 2021-06-08 01:00
Hamilton | 2020 | 634975 | JOINT USE PERMIT HW2019-142 - MOUNTVILLE, INVERNESS E, E14, ETC - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 4779.64 | 7279.61 | 2499.97 | 52.3% | 1397.48 | 1016 | -381.48 | -27.3% | 187.46 | 0 | -187.46 | -100% | 89.7 | 0 | -89.7 | -100% | 3105 | 6263.61 | 3158.61 | 101.7% | 6 | 0 | -6 | -100% | 2020-11-02 01:00
Hamilton | 2022 | 634976 | JOINT USE PERMIT HW2019-143 - BARTON E, MONS, AND CAVELL - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 9266 | 9715.9 | 449.9 | 4.855% | 400.7 | 1872.76 | 1472.06 | 367.4% | 474.9 | 732.3 | 257.4 | 54.2% | 0 | 44 | 44 |  | 8390.4 | 7066.84 | -1323.56 | -15.77% | 0 | 2 | 2 |  | 2022-04-07
Hamilton | 2020 | 634998 | JOINT USE PERMIT HW2019-145 - ARVIN AVE - HAM | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 11545.33 | 11119.13 | -426.2 | -3.692% | 5110.85 | 1529.32 | -3581.53 | -70.08% | 1481.11 | 352.67 | -1128.44 | -76.19% | 603.89 | 0 | -603.89 | -100% | 4349.48 | 9237.14 | 4887.66 | 112.4% | 38.04 | 0 | -38.04 | -100% | 2020-10-26 01:00
Hamilton | 2022 | 635013 | CABLE INJECT - MILLEN/BARTON/FRUITLAND | 95 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 245280.09 | 849268.67 | 603988.58 | 246.2% | 5385.07 | 110279.63 | 104894.56 | 1948% | 7695.02 | 36359.92 | 28664.9 | 372.5% | 0 | 802.73 | 802.73 |  | 232200 | 701826.39 | 469626.39 | 202.3% | 0 | 29.5 | 29.5 |  | 2022-07-26 01:00
Hamilton | 2022 | 635015 | CABLE INJECT - BOLGER/ELMA/DOROTHY | 99 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 143796.48 | 35858.57 | -107937.91 | -75.06% | 3453.69 | 4843.25 | 1389.56 | 40.23% | 2961.39 | 603.65 | -2357.74 | -79.62% | 0 | 69.7 | 69.7 |  | 137381.4 | 30341.97 | -107039.43 | -77.91% | 0 | 6.5 | 6.5 |  | 2022-06-30 01:00
Hamilton | 2020 | 635029 | HUMMINGBIRD LANE DEVELOPMENT EXPANSION | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 327389.81 | 263240.19 | -64149.62 | -19.59% | 14007.81 | 23104.93 | 9097.12 | 64.94% | 71712 | 70895.11 | -816.89 | -1.139% | 560 | 698 | 138 | 24.64% | 241110 | 168542.15 | -72567.85 | -30.1% | 80 | 66 | -14 | -17.5% | 2020-11-03 01:00
Hamilton | 2020 | 635184 | HAMILTON 2020 POLE RESIDUALS PHASE 7 | 99 | COMPLETE | Material reused | BOM – truck stock | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 378431.8 | 322233.14 | -56198.66 | -14.85% | 21869.7 | 25100.11 | 3230.41 | 14.77% | 112070.39 | 69950.21 | -42120.18 | -37.58% | 3061.52 | 0 | -3061.52 | -100% | 241430.19 | 227182.82 | -14247.37 | -5.901% | 55 | 48 | -7 | -12.73% | 2020-12-23 01:00
Hamilton | 2020 | 635185 | HAMILTON 2020 POLE RESIDUALS PHASE 8 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 226029.38 | 221633.27 | -4396.11 | -1.945% | 7666.46 | 17470.64 | 9804.18 | 127.9% | 50008.15 | 42609.7 | -7398.45 | -14.79% | 420 | 0 | -420 | -100% | 167934.77 | 161552.93 | -6381.84 | -3.8% | 30 | 20 | -10 | -33.33% | 2020-11-20 01:00
Hamilton | 2021 | 635366 | 324 PARKDALE AVE NORTH - HYUNDAI DEALERSHIP | 98 | COMPLETE | Vac truck |  |  | Paesano, Andrew | No | Bharosi, Mohindra | Macdougall, Stephen | 120153.02 | 105931.12 | -14221.9 | -11.84% | 44680.87 | 46964.55 | 2283.68 | 5.111% | 39991.7 | 39854.92 | -136.78 | -0.342% | 16687.45 | 13685.61 | -3001.84 | -17.99% | 18793 | 5426.04 | -13366.96 | -71.13% | 620 | 452.5 | -167.5 | -27.02% | 2021-04-01 01:00
Hamilton | 2020 | 635377 | JOINT USE PERMIT HW2019-150 - SIMPSON RD - ST CATH | 99 | COMPLETE | Labour est. under |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 5633.97 | 4788.34 | -845.63 | -15.01% | 895.46 | 1106.25 | 210.79 | 23.54% | 0 | 0 | 0 |  | 89.7 | 152.47 | 62.77 | 69.98% | 4648.81 | 3529.62 | -1119.19 | -24.07% | 4 | 8 | 4 | 100% | 2020-12-11 01:00
Hamilton | 2021 | 635378 | JOINT USE PERMIT HW2019-151 - MITCHELL AND BERRYMAN - ST CATH | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 5895.82 | 4018.68 | -1877.14 | -31.84% | 1495.86 | 1942.47 | 446.61 | 29.86% | 415.21 | 0 | -415.21 | -100% | 134.55 | 371 | 236.45 | 175.7% | 3850.2 | 1705.21 | -2144.99 | -55.71% | 9 | 28 | 19 | 211.1% | 2021-01-03 01:00
Hamilton | 2022 | 635385 | CENTRAL CONVERSION - CE-10 & CE-2 REMOVALS | 99 | COMPLETE | Labour est. over | Vac truck |  | Beaudrie, Scott | Yes | Wardell, Paul | Tony Ierace | 44122.8 | 19100.81 | -25021.99 | -56.71% | 36630.3 | 14469.13 | -22161.17 | -60.5% | 0 | 396.75 | 396.75 |  | 7492.5 | 3793.93 | -3698.57 | -49.36% | 0 | 441 | 441 |  | 192 | 161 | -31 | -16.15% | 2022-01-14 01:00
Hamilton | 2020 | 635415 | HAMILTON 2020 URGENT POLE REPLACEMENTS | 99 | COMPLETE | Cont Est Under | BOM not accurate | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 31143.65 | 58801.85 | 27658.2 | 88.81% | 2570.19 | 6319.21 | 3749.02 | 145.9% | 28025.14 | 4170.03 | -23855.11 | -85.12% | 548.32 | 0 | -548.32 | -100% | 0 | 48312.61 | 48312.61 |  | 8 | 1.5 | -6.5 | -81.25% | 2020-08-31 01:00
Hamilton | 2020 | 635429 | HAMILTON 2020 POLE RESIDUALS PHASE 9 | 99 | COMPLETE | Cont Est Over | BOM not accurate | BOM – truck stock | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 145128.13 | 84406.63 | -60721.5 | -41.84% | 8897.94 | 8975.45 | 77.51 | 0.8711% | 20098.27 | 10042.05 | -10056.22 | -50.04% | 728.16 | 0 | -728.16 | -100% | 115403.76 | 65389.13 | -50014.63 | -43.34% | 8 | 15 | 7 | 87.5% | 2020-08-28 01:00
Hamilton | 2020 | 635453 | HAMILTON WATERFRONT TRUST TX RELOCATE | 99 | COMPLETE | Labour est. over | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 33950.57 | 25355.93 | -8594.64 | -25.32% | 18424.92 | 14769.1 | -3655.82 | -19.84% | 8604.07 | 6853.41 | -1750.66 | -20.35% | 2601.58 | 3733.42 | 1131.84 | 43.51% | 4320 | 0 | -4320 | -100% | 130 | 81.5 | -48.5 | -37.31% | 2020-06-03 01:00
Hamilton | 2021 | 635455 | JOINT USE PERMIT HW2020-001 - BONAVENTURE DR - HAM | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 9739.28 | 11050.32 | 1311.04 | 13.46% | 680.87 | 1371.85 | 690.98 | 101.5% | 561.89 | 2513.27 | 1951.38 | 347.3% | 0 | 0 | 0 |  | 8496.52 | 7165.2 | -1331.32 | -15.67% | 0 | 0 | 0 |  | 2021-06-08 01:00
Hamilton | 2020 | 635533 | HAMILTON 2020 POLE REDISDUALS PHASE 10 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 152539.75 | 91910.41 | -60629.34 | -39.75% | 12131.57 | 7582.51 | -4549.06 | -37.5% | 20332.79 | 18260.2 | -2072.59 | -10.19% | 1577.47 | 0 | -1577.47 | -100% | 6203 | 66067.7 | 59864.7 | 965.1% | 20 | 3 | -17 | -85% | 2020-10-23 01:00
Hamilton | 2021 | 635534 | JOINT USE PERMIT HW2020-002 - CROCKETT, E24, QUEENSDALE E - HAM | 99 | COMPLETE | RFC not approved in time |  |  | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 20856.28 | 54238.85 | 33382.57 | 160.1% | 6658.42 | 19440.78 | 12782.36 | 192% | 3497.06 | 4975.64 | 1478.58 | 42.28% | 717.6 | 9562 | 8844.4 | 1232% | 9983.2 | 20260.43 | 10277.23 | 102.9% | 298 | 262 | -36 | -12.08% | 2021-04-19
Hamilton | 2020 | 635544 | HAMILTON 2020 POLE RESIDUALS PHASE 11 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 220204.43 | 141881.29 | -78323.14 | -35.57% | 12826.4 | 15169.2 | 2342.8 | 18.27% | 13866.67 | 12228.16 | -1638.51 | -11.82% | 711.2 | 0 | -711.2 | -100% | 192800.16 | 114483.93 | -78316.23 | -40.62% | 40 | 28 | -12 | -30% | 2020-09-21 01:00
Hamilton | 2022 | 635593 | JOINT USE PERMIT HW2020-003 - DUNKIRK, ROSEDALE, MONTROSE, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 22943.29 | 27781.01 | 4837.72 | 21.09% | 3263.17 | 2754.97 | -508.2 | -15.57% | 2772.98 | 3174.07 | 401.09 | 14.46% | 260.74 | 0 | -260.74 | -100% | 16646.4 | 21851.97 | 5205.57 | 31.27% | 6.72 | 0 | -6.72 | -100% | 2022-01-24 01:00
Hamilton | 2022 | 635601 | REBUILD: W 31ST, BTWN ANGELA AVE & LESLIE AVE (HAMILTON) - 9 | 99 | COMPLETE | Vac truck | Labour est. under | Vehicle Under Estimated | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 117533.97 | 150356.25 | 32822.28 | 27.93% | 61417.09 | 71076.67 | 9659.58 | 15.73% | 30016.88 | 30499.6 | 482.72 | 1.608% | 17100 | 26873.28 | 9773.28 | 57.15% | 9000 | 21906.7 | 12906.7 | 143.4% | 600 | 865.5 | 265.5 | 44.25% | 2022-02-01 01:00
Hamilton | 2021 | 635602 | REBUILD: LESLIE & W 32ND, N OF BENDAMERE (HAMILTON) -18 | 99 | COMPLETE | BOM not accurate | Vac truck | N/A | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 136045.92 | 228320.81 | 92274.89 | 67.83% | 89391.09 | 100903.26 | 11512.17 | 12.88% | 0 | 51691.43 | 51691.43 |  | 26654.83 | 48983.99 | 22329.16 | 83.77% | 20000 | 26742.13 | 6742.13 | 33.71% | 920 | 1330 | 410 | 44.57% | 2021-04-16
Hamilton | 2021 | 635603 | REBUILD: W 31ST, N OF BENDAMERE (HAMILTON) - 7 | 99 | COMPLETE | Material reused | Labour est. under | Vac truck | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 127427.67 | 150279.73 | 22852.06 | 17.93% | 61417.09 | 66107.39 | 4690.3 | 7.637% | 41410.58 | 37881.55 | -3529.03 | -8.522% | 17100 | 35924.76 | 18824.76 | 110.1% | 7500 | 10366.03 | 2866.03 | 38.21% | 600 | 897 | 297 | 49.5% | 2021-06-04 01:00
Hamilton | 2022 | 635604 | REBUILD: W 33RD, N OF SANATORIUM (HAMILTON) - 7 | 95 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 132815.54 | 153475.93 | 20660.39 | 15.56% | 81070.54 | 75480.4 | -5590.14 | -6.895% | 21173 | 35401.91 | 14228.91 | 67.2% | 22572 | 28551.4 | 5979.4 | 26.49% | 8000 | 14015.22 | 6015.22 | 75.19% | 792 | 884 | 92 | 11.62% | 2022-10-28 01:00
Hamilton | 2021 | 635605 | REBUILD: W 31ST, N OF SANATORIUM (HAMILTON) - 6 | 99 | COMPLETE | Labour est. under | Safety |  | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 155333.54 | 188794.06 | 33460.52 | 21.54% | 88440.6 | 87175.13 | -1265.47 | -1.431% | 34268.94 | 46227.73 | 11958.79 | 34.9% | 24624 | 43827.78 | 19203.78 | 77.99% | 8000 | 11563.42 | 3563.42 | 44.54% | 864 | 1137.5 | 273.5 | 31.66% | 2021-09-17 01:00
Hamilton | 2022 | 635606 | REBUILD: LESLIE, W28TH TO W27TH (HAMILTON) - 5 | 95 | COMPLETE | Under 10% | Estimate incorrect |  | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 30067.68 | 31756.58 | 1688.9 | 5.617% | 20390.48 | 18290.18 | -2100.3 | -10.3% | 0 | 5967.07 | 5967.07 |  | 5677.2 | 4095.93 | -1581.27 | -27.85% | 4000 | 3403.4 | -596.6 | -14.92% | 200 | 187.5 | -12.5 | -6.25% | 2022-11-09 01:00
Hamilton | 2021 | 635607 | REBUILD: ELMWOOD & W 25TH (HAMILTON) - 2 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 20140.35 | 21173.22 | 1032.87 | 5.128% | 12283.42 | 11425.82 | -857.6 | -6.982% | 2436.93 | 2563.73 | 126.8 | 5.203% | 3420 | 4321.39 | 901.39 | 26.36% | 2000 | 2862.28 | 862.28 | 43.11% | 120 | 140.5 | 20.5 | 17.08% | 2021-06-14 01:00
Hamilton | 2021 | 635608 | REBUILD: DENLOW & GARTH (HAMILTON) - 3 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Koeppe, Jeffrey | 52975.38 | 67249.29 | 14273.91 | 26.94% | 29480.2 | 30340.76 | 860.56 | 2.919% | 12287.18 | 19299 | 7011.82 | 57.07% | 8208 | 11928.98 | 3720.98 | 45.33% | 3000 | 5680.55 | 2680.55 | 89.35% | 288 | 379.5 | 91.5 | 31.77% | 2021-07-22 01:00
Hamilton | 2021 | 635609 | REBUILD: AUCHMAR & GARTH (HAMILTON) - 3 | 99 | COMPLETE | Material reused | Cont Est Over |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 80157.63 | 64364.55 | -15793.08 | -19.7% | 5919.76 | 10899.85 | 4980.09 | 84.13% | 14161.88 | 10777.22 | -3384.66 | -23.9% | 305.55 | 69.7 | -235.85 | -77.19% | 59770.44 | 42617.78 | -17152.66 | -28.7% | 10 | 40 | 30 | 300% | 2021-11-18 01:00
Hamilton | 2020 | 635616 | 205 NEBO ROAD | 98 | COMPLETE | BOM not accurate | Labour est. over |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 66273.79 | 56779.18 | -9494.61 | -14.33% | 26781.94 | 10699.54 | -16082.4 | -60.05% | 27210.31 | 36271.3 | 9060.99 | 33.3% | 3738.74 | 1869.99 | -1868.75 | -49.98% | 8542.8 | 7938.35 | -604.45 | -7.076% | 116 | 102 | -14 | -12.07% | 2020-12-03 01:00
Hamilton | 2022 | 635639 | 223 EAST AVE N | 99 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Bennett, Aaron | Macdougall, Stephen | 81484.79 | 79915.16 | -1569.63 | -1.926% | 29480.78 | 15350.63 | -14130.15 | -47.93% | 42006.43 | 54487.53 | 12481.1 | 29.71% | 3934.58 | 2821.5 | -1113.08 | -28.29% | 6063 | 7255.5 | 1192.5 | 19.67% | 154.54 | 136 | -18.54 | -12% | 2022-03-12 01:00
Hamilton | 2022 | 635658 | Fruitland Rd & Lakeview Dr - DESANTIS ROSE JOINT VENTURE INC. - TEMP | 95 | COMPLETE | Scope change - unforeseen | Commodity Price |  | Paesano, Andrew | No | Bharosi, Mohindra | Macdougall, Stephen | 106779.85 | 89911.44 | -16868.41 | -15.8% | 33517.31 | 26591.41 | -6925.9 | -20.66% | 35643.73 | 51719.4 | 16075.67 | 45.1% | 7295.65 | 5191.07 | -2104.58 | -28.85% | 30323.16 | 6409.56 | -23913.6 | -78.86% | 280 | 227.5 | -52.5 | -18.75% | 2022-11-22 01:00
Hamilton | 2020 | 635693 | 170 OGILVIE ST )ST.JOSEPHS VILLA) | 99 | COMPLETE | BOM not accurate | Labour est. under |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 77469.68 | 99990.76 | 22521.08 | 29.07% | 38445.39 | 32980.79 | -5464.6 | -14.21% | 31783.25 | 51627.28 | 19844.03 | 62.44% | 7241.04 | 15173.89 | 7932.85 | 109.6% | 0 | 208.8 | 208.8 |  | 322 | 393 | 71 | 22.05% | 2020-04-04 01:00
Hamilton | 2021 | 635715 | MH2163 SEWERING | 99 | COMPLETE | Cont Est Over |  |  | Biggs, Scott | No | Jolie, Chris | Brad Carr | 66450.31 | 56242.99 | -10207.32 | -15.36% | 13845.41 | 8472.33 | -5373.08 | -38.81% | 0 | 1862.52 | 1862.52 |  | 224 | 1655.03 | 1431.03 | 638.9% | 52380.9 | 44253.11 | -8127.79 | -15.52% | 16 | 10 | -6 | -37.5% | 2021-08-26 01:00
Hamilton | 2020 | 635722 | 695 WOODWARD AVE N UPGRADE & 741 WOODWARD AVE N CONVERSION | 99 | COMPLETE | Vac truck |  |  | Paesano, Andrew | No | Alectra Utilities | Koeppe, Jeffrey | 91401.83 | 0 | -91401.83 | -100% | 54665.83 | 0 | -54665.83 | -100% | 22478.59 | 0 | -22478.59 | -100% | 12379.29 | 0 | -12379.29 | -100% | 1878.12 | 0 | -1878.12 | -100% | 470 | 0 | -470 | -100% | 2020-07-09 01:00
Hamilton | 2020 | 635726 | JOINT USE PERMIT HW2020-010 - QUIGLEY RD - HAM | 99 | COMPLETE | BOM – truck stock |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 4284.59 | 3337.95 | -946.64 | -22.09% | 1486.91 | 1185.48 | -301.43 | -20.27% | 223.98 | 0 | -223.98 | -100% | 89.7 | 152.47 | 62.77 | 69.98% | 2484 | 2000 | -484 | -19.48% | 10 | 6 | -4 | -40% | 2020-08-13 01:00
Hamilton | 2021 | 635727 | JOINT USE PERMIT HW2020-011 - HIGHLAND AND UPR MT ALBION - HAM | 99 | COMPLETE | BOM – truck stock |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 7443.22 | 6716.98 | -726.24 | -9.757% | 1654.41 | 1201.02 | -453.39 | -27.4% | 379.76 | 0 | -379.76 | -100% | 155.39 | 0 | -155.39 | -100% | 5253.66 | 5515.96 | 262.3 | 4.993% | 6 | 0 | -6 | -100% | 2021-02-22 01:00
Hamilton | 2021 | 635739 | 212 KING WILLIAM ST - TEMP SERVICE | 99 | COMPLETE | Vehicle Under Estimated |  |  | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 38901.77 | 44684.78 | 5783.01 | 14.87% | 7999.11 | 9577.98 | 1578.87 | 19.74% | 30222.89 | 32976.66 | 2753.77 | 9.112% | 679.77 | 2130.14 | 1450.37 | 213.4% | 0 | 0 | 0 |  | 59 | 78 | 19 | 32.2% | 2021-11-24 01:00
Hamilton | 2020 | 635743 | HAMILTON KICKER TX REPLACEMENT - TX 10117 | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Scott Borer | 3574.01 | 456.97 | -3117.04 | -87.21% | 3010.01 | 456.97 | -2553.04 | -84.82% | 0 | 0 | 0 |  | 564 | 0 | -564 | -100% | 0 | 0 | 0 |  | 21.5 | 0.5 | -21 | -97.67% | 2020-12-01 01:00
Hamilton | 2021 | 635744 | HAMILTON KICKER TX REPLACEMENT - TX # 6592 - 1 | 99 | COMPLETE | BOM not accurate |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 58787.47 | 44830.5 | -13956.97 | -23.74% | 21350.42 | 19217.22 | -2133.2 | -9.991% | 21497.78 | 4948.92 | -16548.86 | -76.98% | 4808.52 | 8982.01 | 4173.49 | 86.79% | 11130.75 | 11682.35 | 551.6 | 4.956% | 181 | 176.5 | -4.5 | -2.486% | 2021-12-31 01:00
Hamilton | 2020 | 635745 | HAMILTON KICKER TX REPLACEMENT - TX 7544 AND 2923 | 99 | COMPLETE | Cont Est Over | Labour est. under | BOM not accurate | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 222046.19 | 177524.49 | -44521.7 | -20.05% | 4966.46 | 19520.88 | 14554.42 | 293.1% | 64754.57 | 37266.7 | -27487.87 | -42.45% | 421.12 | 683.25 | 262.13 | 62.25% | 151904.04 | 120053.66 | -31850.38 | -20.97% | 29 | 50 | 21 | 72.41% | 2020-12-17 01:00
Hamilton | 2021 | 635747 | 2021 POLE RENEWAL - BATCH 1 - 5 POLES | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Brad Carr | 92761.37 | 66873.39 | -25887.98 | -27.91% | 8299.59 | 11921.17 | 3621.58 | 43.64% | 15360.22 | 14872.22 | -488 | -3.177% | 1108 | 1496.96 | 388.96 | 35.1% | 67993.56 | 38583.04 | -29410.52 | -43.25% | 14 | 30 | 16 | 114.3% | 2021-11-04 01:00
Hamilton | 2022 | 635749 | HAMILTON KICKER TX REPLACEMENT - TX 7675 AND 8050 - 2 | 99 | COMPLETE | Labour est. under | Scope change - unforeseen |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 35125.53 | 48392.54 | 13267.01 | 37.77% | 10480.97 | 18358.63 | 7877.66 | 75.16% | 1363.92 | 4801.62 | 3437.7 | 252% | 2298 | 5240.29 | 2942.29 | 128% | 20982.64 | 19992 | -990.64 | -4.721% | 82 | 156.5 | 74.5 | 90.85% | 2022-03-25 01:00
Hamilton | 2021 | 635756 | HAMILTON KICKER TX REPLACEMENT - TX 13000 - 1 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 8511.02 | 9587.03 | 1076.01 | 12.64% | 4060.33 | 4392.45 | 332.12 | 8.18% | 233.43 | 0 | -233.43 | -100% | 564 | 1541.32 | 977.32 | 173.3% | 3653.26 | 3653.26 | 0 | 0% | 21.5 | 36.5 | 15 | 69.77% | 2021-06-04 01:00
Hamilton | 2020 | 635758 | 2D13X - WATERDOWN AUTO SWITCH | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 419034.93 | 442565.57 | 23530.64 | 5.615% | 12481.67 | 35079.69 | 22598.02 | 181% | 151969.04 | 179953.71 | 27984.67 | 18.41% | 756 | 1052.2 | 296.2 | 39.18% | 253828.22 | 226479.97 | -27348.25 | -10.77% | 54 | 118 | 64 | 118.5% | 2020-11-03 01:00
Hamilton | 2021 | 635822 | DUNDAS ST E & HAMILTON ST PMH AUTOMATION - Deep dive | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | yes | Anderson, Dean | Brad Carr | 324895.11 | 326093.87 | 1198.76 | 0.369% | 18262.35 | 19331.62 | 1069.27 | 5.855% | 305283.64 | 306200.06 | 916.42 | 0.3002% | 1336.16 | 562.19 | -773.97 | -57.92% | 12.96 | 0 | -12.96 | -100% | 64 | 121 | 57 | 89.06% | 2021-02-10 01:00
Hamilton | 2021 | 635826 | COGECO BONDS - 2020 ANCASTER | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 3614.82 | 2418.81 | -1196.01 | -33.09% | 3191.44 | 343 | -2848.44 | -89.25% | 0 | 0 | 0 |  | 423.38 | 0 | -423.38 | -100% | 0 | 2075.81 | 2075.81 |  | 16 | 0 | -16 | -100% | 2021-02-22 01:00
Hamilton | 2020 | 635827 | COGECO BONDS - 2020 FLAMBOROUGH | 99 | COMPLETE | Estimate incorrect |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 3614.82 | 2169.15 | -1445.67 | -39.99% | 3191.44 | 244.57 | -2946.87 | -92.34% | 0 | 0 | 0 |  | 423.38 | 0 | -423.38 | -100% | 0 | 1924.58 | 1924.58 |  | 0 | 0 | 0 |  | 2020-11-12 01:00
Hamilton | 2020 | 635828 | COGECO BONDS - 2020 DUNDAS | 99 | COMPLETE | Estimate incorrect |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 2071.25 | 1239.89 | -831.36 | -40.14% | 1859.56 | 927.89 | -931.67 | -50.1% | 0 | 0 | 0 |  | 211.69 | 312 | 100.31 | 47.39% | 0 | 0 | 0 |  | 8 | 8 | 0 | 0% | 2020-06-24 01:00
Hamilton | 2020 | 635829 | COGECO BONDS - 2020 AINSLIE WOOD NORTH - HAM | 99 | COMPLETE | Labour est. under |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 3614.82 | 3178.5 | -436.32 | -12.07% | 3191.44 | 2661.39 | -530.05 | -16.61% | 0 | 0 | 0 |  | 423.38 | 517.11 | 93.73 | 22.14% | 0 | 0 | 0 |  | 16 | 29 | 13 | 81.25% | 2020-11-09 01:00
Hamilton | 2020 | 635830 | COGECO BONDS - 2020 WESTDALE - HAM | 99 | COMPLETE | Labour est. over |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 2071.25 | 1799.85 | -271.4 | -13.1% | 1859.56 | 522.81 | -1336.75 | -71.89% | 0 | 0 | 0 |  | 211.69 | 140.25 | -71.44 | -33.75% | 0 | 1136.79 | 1136.79 |  | 8 | 2.5 | -5.5 | -68.75% | 2020-10-26 01:00
Hamilton | 2020 | 635831 | COGECO BONDS - 2020 KIRKENDALL NORTH - HAM | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 2843.03 | 1928.05 | -914.98 | -32.18% | 2525.49 | 244.69 | -2280.8 | -90.31% | 0 | 0 | 0 |  | 317.54 | 0 | -317.54 | -100% | 0 | 1683.36 | 1683.36 |  | 12 | 0 | -12 | -100% | 2020-10-26 01:00
Hamilton | 2020 | 635832 | COGECO BONDS - 2020 HAMILTON EAST - HAM | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 3614.82 | 3986.32 | 371.5 | 10.28% | 3191.44 | 3282.93 | 91.49 | 2.867% | 0 | 0 | 0 |  | 423.38 | 703.39 | 280.01 | 66.14% | 0 | 0 | 0 |  | 16 | 37.5 | 21.5 | 134.4% | 2020-12-29 01:00
Hamilton | 2020 | 635833 | COGECO BONDS - 2020 GLENVIEW AND WINONA - HAM | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 2071.25 | 1535.8 | -535.45 | -25.85% | 1859.56 | 1481.8 | -377.76 | -20.31% | 0 | 0 | 0 |  | 211.69 | 54 | -157.69 | -74.49% | 0 | 0 | 0 |  | 8 | 14 | 6 | 75% | 2020-06-24 01:00
Hamilton | 2022 | 635835 | ROAD AUTHORITY - PARKIDE DR ROAD WIDENING - WATERDOWN | 99 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 2271588.88 | 2234118.46 | -37470.42 | -1.65% | 191102.74 | 237487.79 | 46385.05 | 24.27% | 344266.79 | 405713.81 | 61447.02 | 17.85% | 1920 | 0 | -1920 | -100% | 1734299.35 | 1590571.78 | -143727.57 | -8.287% | 120 | 20 | -100 | -83.33% | 2022-10-31 01:00
Hamilton | 2022 | 635840 | ROAD AUTHORITY - GRINDSTONE BRIDGE OVERHEAD WIRE RELOCATION | 99 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 321701.44 | 305659.74 | -16041.7 | -4.987% | 45576.59 | 49183.5 | 3606.91 | 7.914% | 58115.81 | 51156.77 | -6959.04 | -11.97% | 384 | 42 | -342 | -89.06% | 217625.04 | 202803.44 | -14821.6 | -6.811% | 24 | 8 | -16 | -66.67% | 2022-04-21
Hamilton | 2022 | 635932 | RYMAL RD WIDENING - CITY OF HAMILTON - PHASE 2 | 99 | COMPLETE | Material Over Estimated |  |  | Jakubowski, Mark | No | Celic, Dusan | Koeppe, Jeffrey | 880044.16 | 885834.81 | 5790.65 | 0.658% | 163168.09 | 154275.57 | -8892.52 | -5.45% | 185584.25 | 178036.23 | -7548.02 | -4.067% | 32411 | 31291 | -1120 | -3.456% | 498880.82 | 522232.01 | 23351.19 | 4.681% | 80 | 1144.5 | 1064.5 | 1331% | 2022-05-18 01:00
Hamilton | 2021 | 635938 | WATERDOWN - 3RD FEEDER SUBDIVISION WORK | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | yes | Anderson, Dean | Brad Carr | 501879.07 | 509573.07 | 7694 | 1.533% | 19910.97 | 72725.09 | 52814.12 | 265.3% | 130069.3 | 148452.03 | 18382.73 | 14.13% | 456 | 5289.37 | 4833.37 | 1060% | 351442.8 | 283106.58 | -68336.22 | -19.44% | 48 | 518.5 | 470.5 | 980.2% | 2021-04-19
Hamilton | 2020 | 635942 | CENTRAL CONVERSION - PHASE 4 - 2021 WORK (FORMERLY S699225C DWG) | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 1279307.64 | 1079305.66 | -200001.98 | -15.63% | 60450.71 | 81531.23 | 21080.52 | 34.87% | 188441.42 | 208059.89 | 19618.47 | 10.41% | 11745.35 | 1254.3 | -10491.05 | -89.32% | 1018670.16 | 788460.24 | -230209.92 | -22.6% | 100 | 58 | -42 | -42% | 2020-11-10 01:00
Hamilton | 2021 | 635945 | HAMILTON - URGENT POLE # 55818 REPLACEMENT - 1 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Brian Robinson | 40403.8 | 39947.62 | -456.18 | -1.129% | 15974.62 | 2863.09 | -13111.53 | -82.08% | 20108.85 | 11381.09 | -8727.76 | -43.4% | 3849.72 | 0 | -3849.72 | -100% | 470.61 | 25703.44 | 25232.83 | 5362% | 140 | 2 | -138 | -98.57% | 2021-05-09
Hamilton | 2020 | 635968 | JOINT USE PERMIT HW2020-021 - ALBRIGHT - HAM | 99 | COMPLETE | Vac truck | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 6308.91 | 3551.17 | -2757.74 | -43.71% | 1386.14 | 1067.86 | -318.28 | -22.96% | 917.18 | 0 | -917.18 | -100% | 155.39 | 195.63 | 40.24 | 25.9% | 3850.2 | 2287.68 | -1562.52 | -40.58% | 8 | 6 | -2 | -25% | 2020-08-21 01:00
Hamilton | 2021 | 636003 | GLENDALE TS - POLE RELOCATION | 99 | COMPLETE | N/A | N/A | N/A | Braletic, Bob | No | Lustrinelli, Mark | Frank Giancola | 65670.74 | 0 | -65670.74 | -100% | 44357.35 | 0 | -44357.35 | -100% | 8758.28 | 0 | -8758.28 | -100% | 10079.75 | 0 | -10079.75 | -100% | 2475.36 | 0 | -2475.36 | -100% | 380 | 0 | -380 | -100% | 2021-04-16
Hamilton | 2022 | 636032 | 3 STUDEBAKER PLACE | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Sabbah, Amir | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-04-28
Hamilton | 2021 | 636039 | 383 DUNDAS ST. E. - WATERDOWN | 99 | COMPLETE | Labour est. over | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Brad Carr | 517745.59 | 499499.08 | -18246.51 | -3.524% | 34223 | 18776.88 | -15446.12 | -45.13% | 4206.97 | 4280.19 | 73.22 | 1.74% | 5778.82 | 2905.21 | -2873.61 | -49.73% | 473536.8 | 0 | -473536.8 | -100% | 246.14 | 197.75 | -48.39 | -19.66% | 2021-03-15 01:00
Hamilton | 2021 | 636043 | CHEDOKE HEIGHTS - PHASE 1 - SUBD RES EDS | 99 | COMPLETE | N/A |  |  | Gamboa, Henry | No | Morris, Mark | Brad Carr | 256796.42 | 686697.17 | 429900.75 | 167.4% | 43680.76 | 39128.69 | -4552.07 | -10.42% | 99595 | 100600.47 | 1005.47 | 1.01% | 4185.85 | 4259.51 | 73.66 | 1.76% | 109334.81 | 102306.1 | -7028.71 | -6.429% | 232.39 | 287.75 | 55.36 | 23.82% | 2021-08-25 01:00
Hamilton | 2020 | 636056 | JOINT USE PERMIT HW2020-022 - SCOTT ST W - ST CATH | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 7178.34 | 3898.28 | -3280.06 | -45.69% | 2009.74 | 748.28 | -1261.46 | -62.77% | 990.37 | 0 | -990.37 | -100% | 265.93 | 0 | -265.93 | -100% | 3912.3 | 3150 | -762.3 | -19.48% | 13 | 0 | -13 | -100% | 2020-08-20 01:00
Hamilton | 2020 | 636060 | MH 109C - ROOF REPLACEMENT | 99 | COMPLETE | Cont Est Under |  |  | Beaudrie, Scott | No | Alectra Utilities | Andrew Mehlenbacher | 99305.65 | 129297.39 | 29991.74 | 30.2% | 13945.65 | 78420.15 | 64474.5 | 462.3% | 0 | 9597.51 | 9597.51 |  | 364 | 735.03 | 371.03 | 101.9% | 84996 | 40544.7 | -44451.3 | -52.3% | 58 | 36 | -22 | -37.93% | 2020-12-04 01:00
Hamilton | 2020 | 636090 | MOUNTAIN BROW ROAD - 3- PH OVERHEAD WORK | 99 | COMPLETE | Cont Est Over | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 140565.35 | 117078.73 | -23486.62 | -16.71% | 11948.56 | 11185.66 | -762.9 | -6.385% | 36918.87 | 40681.8 | 3762.93 | 10.19% | 1583.8 | 0 | -1583.8 | -100% | 90114.12 | 65211.27 | -24902.85 | -27.63% | 12 | 17 | 5 | 41.67% | 2020-10-05 01:00
Hamilton | 2020 | 636145 | 21 UPPER CENTENNIAL PKWY - BLDG B (GAS BAR) | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-04 01:00
Hamilton | 2020 | 636150 | JOINT USE PERMIT HW2020-023 - RANDALL, SECOND N, AND BRANDOW - HAM | 99 | COMPLETE | Legal Fees | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 6395.3 | 5057.06 | -1338.24 | -20.93% | 1163.72 | 917.06 | -246.66 | -21.2% | 0 | 0 | 0 |  | 89.7 | 0 | -89.7 | -100% | 5141.88 | 4140 | -1001.88 | -19.48% | 4 | 0 | -4 | -100% | 2020-12-21 01:00
Hamilton | 2020 | 636157 | 1290 ARVIN AVE - NEW SERVICE | 98 | COMPLETE | Estimate incorrect |  |  | Frigotto, Rodrigo | No | Alectra Utilities | Roy Owen | 98549.57 | 68028.11 | -30521.46 | -30.97% | 19956.6 | 13610.11 | -6346.49 | -31.8% | 48662.47 | 49153.94 | 491.47 | 1.01% | 3208.06 | 4244.06 | 1036 | 32.29% | 26722.44 | 1020 | -25702.44 | -96.18% | 138.6 | 152 | 13.4 | 9.668% | 2020-12-30 01:00
Hamilton | 2020 | 636196 | JOINT USE PERMIT HW2020-026 - DELAWANA AND JEROME - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 6867.34 | 4565.09 | -2302.25 | -33.52% | 1386.14 | 641.03 | -745.11 | -53.75% | 1413.51 | 0 | -1413.51 | -100% | 155.39 | 0 | -155.39 | -100% | 3912.3 | 3924.06 | 11.76 | 0.3006% | 0 | 0 | 0 |  | 2020-11-02 01:00
Hamilton | 2021 | 636230 | VICTORY RIDGE - PHASE 4 | 99 | COMPLETE | Labour est. over |  |  | Gamboa, Henry | No | Morris, Mark | Brad Carr | 115956.91 | 98461.7 | -17495.21 | -15.09% | 13625.73 | 12049.36 | -1576.37 | -11.57% | 43.3 | 198.6 | 155.3 | 358.7% | 1998 | 264 | -1734 | -86.79% | 100289.88 | 85949.74 | -14340.14 | -14.3% | 79.2 | 51 | -28.2 | -35.61% | 2021-09-15 01:00
Hamilton | 2020 | 636248 | JOINT USE PERMIT HW2020-032 - UPPER WENTWORTH - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 5131.22 | 4462.3 | -668.92 | -13.04% | 1129.22 | 538.24 | -590.98 | -52.34% | 0 | 0 | 0 |  | 89.7 | 0 | -89.7 | -100% | 3912.3 | 3924.06 | 11.76 | 0.3006% | 6 | 0 | -6 | -100% | 2020-11-02 01:00
Hamilton | 2020 | 636277 | NEWTON M8 - 282X: RECONFIGURATION/FUSE CHANGES | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Scott Borer | 25303.01 | 17130.44 | -8172.57 | -32.3% | 17090.5 | 10229.49 | -6861.01 | -40.15% | 4566.91 | 3251.68 | -1315.23 | -28.8% | 3645.6 | 3649.27 | 3.67 | 0.1007% | 0 | 0 | 0 |  | 130 | 112 | -18 | -13.85% | 2020-12-23 01:00
Hamilton | 2022 | 636296 | MH20 JAMES STREET SOUTH RAISE LID | 99 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Weaver, Thomas | 11835.92 | 13896.37 | 2060.45 | 17.41% | 239.92 | 2356.37 | 2116.45 | 882.1% | 0 | 0 | 0 |  | 56 | 0 | -56 | -100% | 11540 | 11540 | 0 | 0% | 4 | 8 | 4 | 100% | 2022-12-21 01:00
Hamilton | 2021 | 636315 | 535 UPPER KENILWORTH AVE - BERNIE ARBOUR STADIUM | 99 | COMPLETE | Scope – Const |  |  | Jakubowski, Mark | No | Patel, Ketan | Roy Owen | 20720.76 | 21980.17 | 1259.41 | 6.078% | 14790.12 | 12057.34 | -2732.78 | -18.48% | 4882.7 | 8409.83 | 3527.13 | 72.24% | 1047.94 | 1513 | 465.06 | 44.38% | 0 | 0 | 0 |  | 68 | 121.5 | 53.5 | 78.68% | 2021-05-25 01:00
Hamilton | 2020 | 636388 | KING & BAY EXPANSION - MCMASTER TOWER | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-06 01:00
Hamilton | 2022 | 636451 | FOOTHILLS OF WINONA - SERVICE ADDITIONS/RE-LOCATIONS | 95 | COMPLETE | Labour est. over |  |  | Gamboa, Henry | No | Morris, Mark | Roy Owen | 58541.53 | 51813.95 | -6727.58 | -11.49% | 15321.81 | 11788.95 | -3532.86 | -23.06% | 0 | 0 | 0 |  | 496 | 466 | -30 | -6.048% | 42723.72 | 39559 | -3164.72 | -7.407% | 73 | 40 | -33 | -45.21% | 2022-01-21 01:00
Hamilton | 2020 | 636460 | EA-8 FEEDER EXTENSION (UPPER KENILWORTH) HAMILTON | 99 | COMPLETE | BOM not accurate | Labour est. under | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 447205.97 | 564965.63 | 117759.66 | 26.33% | 0 | 45797.03 | 45797.03 |  | 10830.4 | 154893.57 | 144063.17 | 1330% | 0 | 0 | 0 |  | 436375.57 | 364275.03 | -72100.54 | -16.52% | 0 | 40 | 40 |  | 2020-12-23 01:00
Hamilton | 2020 | 636493 | JOINT USE PERMIT HW2020-033 - LONGWOOD RD S - HAM | 99 | COMPLETE | BOM – truck stock |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 7110.16 | 5469.34 | -1640.82 | -23.08% | 2119.49 | 1928.09 | -191.4 | -9.03% | 833.28 | 0 | -833.28 | -100% | 245.09 | 391.25 | 146.16 | 59.64% | 3912.3 | 3150 | -762.3 | -19.48% | 14 | 16 | 2 | 14.29% | 2020-08-12 01:00
Hamilton | 2021 | 636495 | 10 AINTREE CRT - GUY REMOVAL | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 907.12 | 0 | -907.12 | -100% | 829.12 | 0 | -829.12 | -100% | 0 | 0 | 0 |  | 78 | 0 | -78 | -100% | 0 | 0 | 0 |  | 4 | 0 | -4 | -100% | 2021-06-08 01:00
Hamilton | 2020 | 636562 | JOINT USE PERMIT HW2020-038 - SEAMAN, DEWITT, AND MILLEN - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 13329.16 | 9543.09 | -3786.07 | -28.4% | 4870.82 | 1152.47 | -3718.35 | -76.34% | 1843.17 | 1058.02 | -785.15 | -42.6% | 752.93 | 0 | -752.93 | -100% | 5862.24 | 7332.6 | 1470.36 | 25.08% | 24 | 0 | -24 | -100% | 2020-10-26 01:00
Hamilton | 2021 | 636574 | SC1032 UPGRADE - 1 | 99 | COMPLETE | BOM not accurate |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Andrew Mehlenbacher | 74735.56 | 83925.73 | 9190.17 | 12.3% | 8873.23 | 8824.22 | -49.01 | -0.5523% | 64824.41 | 72113.16 | 7288.75 | 11.24% | 1037.92 | 1691.81 | 653.89 | 63% | 0 | 1296.54 | 1296.54 |  | 83.52 | 75.25 | -8.27 | -9.902% | 2021-06-24 01:00
Hamilton | 2020 | 636590 | JOINT USE PERMIT HW2020-040 - WENTWORTH ESCARPMENT - HAM | 99 | COMPLETE | Cont Est Under |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 7600.31 | 6684.07 | -916.24 | -12.06% | 3329.21 | 638.39 | -2690.82 | -80.82% | 0 | 0 | 0 |  | 358.8 | 0 | -358.8 | -100% | 3912.3 | 6045.68 | 2133.38 | 54.53% | 24 | 0 | -24 | -100% | 2020-11-02 01:00
Hamilton | 2020 | 636595 | JOINT USE PERMIT HW2020-035 - YORK AND HOPKINS - HAM | 99 | COMPLETE | Cont Est Under |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 9900.69 | 8737.68 | -1163.01 | -11.75% | 3843.09 | 2295.01 | -1548.08 | -40.28% | 1217.94 | 635.11 | -582.83 | -47.85% | 490.18 | 0 | -490.18 | -100% | 4349.48 | 5807.56 | 1458.08 | 33.52% | 24 | 24 | 0 | 0% | 2020-11-12 01:00
Hamilton | 2021 | 636596 | JOINT USE PERMIT HW2020-036 - YORK AND HOPKINS - HAM | 99 | COMPLETE | Cont Est Under |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 15020.62 | 18957.36 | 3936.74 | 26.21% | 868.37 | 1830.38 | 962.01 | 110.8% | 1203.05 | 3258.72 | 2055.67 | 170.9% | 0 | 0 | 0 |  | 12949.2 | 13868.26 | 919.06 | 7.097% | 0 | 0 | 0 |  | 2021-10-20 01:00
Hamilton | 2020 | 636598 | ANCHOR RELOCATE - 32 TRILLIUM AVE | 99 | COMPLETE | Labour est. over | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Koeppe, Jeffrey | 19763.46 | 13864.65 | -5898.81 | -29.85% | 11654.49 | 7005.23 | -4649.26 | -39.89% | 2179.05 | 1589.34 | -589.71 | -27.06% | 2394 | 2002.28 | -391.72 | -16.36% | 3535.92 | 3267.8 | -268.12 | -7.583% | 84 | 52 | -32 | -38.1% | 2020-11-13 01:00
Hamilton | 2022 | 636620 | 6 ACORN STREET - Temp | 99 | COMPLETE | BOM cost variance | Metering under |  | Kappheim, Adam | No | Djuric, Zdravko | Macdougall, Stephen | 38324.85 | 49102.62 | 10777.77 | 28.12% | 18077.61 | 10405.23 | -7672.38 | -42.44% | 4129.28 | 30334.04 | 26204.76 | 634.6% | 3496 | 2379 | -1117 | -31.95% | 12621.96 | 5984.35 | -6637.61 | -52.59% | 132 | 124 | -8 | -6.061% | 2021-11-08 01:00
Hamilton | 2022 | 636685 | EMERGING OH INSULATOR REPLACEMENT 2022 - LAKE M81 | 99 | COMPLETE | Labour est. under |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Macdougall, Stephen | 34623.2 | 42552.62 | 7929.42 | 22.9% | 21476.98 | 28272.82 | 6795.84 | 31.64% | 6186.52 | 8983.96 | 2797.44 | 45.22% | 6959.7 | 5295.84 | -1663.86 | -23.91% | 0 | 0 | 0 |  | 183.15 | 280 | 96.85 | 52.88% | 2022-12-02 01:00
Hamilton | 2022 | 636688 | 121 KING ST E - GORE PARK LOFTS | 99 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Sabbah, Amir | Roy Owen | 44461.24 | 0 | -44461.24 | -100% | 3760.92 | 0 | -3760.92 | -100% | 38078.24 | 0 | -38078.24 | -100% | 704 | 0 | -704 | -100% | 1918.08 | 0 | -1918.08 | -100% | 24 | 0 | -24 | -100% | 2022-11-14 01:00
Hamilton | 2020 | 636710 | JOINT USE PERMIT HW2020-042 - ROYAL AVE - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 6345.8 | 4719.96 | -1625.84 | -25.62% | 1859.56 | 587.67 | -1271.89 | -68.4% | 0 | 59.81 | 59.81 |  | 211.69 | 0 | -211.69 | -100% | 4274.55 | 4072.48 | -202.07 | -4.727% | 4 | 0 | -4 | -100% | 2020-10-26 01:00
Hamilton | 2021 | 636732 | 2021 POLE REPLACEMENTS - UPPER SHERMAN - 2 | 99 | COMPLETE | Covid-19 |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Macdougall, Stephen | 34589.3 | 53071.86 | 18482.56 | 53.43% | 19419.21 | 25107.17 | 5687.96 | 29.29% | 5527.27 | 5908.82 | 381.55 | 6.903% | 4890.82 | 16286.81 | 11395.99 | 233% | 4752 | 5769.06 | 1017.06 | 21.4% | 164.72 | 336.5 | 171.78 | 104.3% | 2021-06-04 01:00
Hamilton | 2020 | 636774 | 67 DUNCOMBE DR | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-12 01:00
Hamilton | 2021 | 636810 | JOINT USE PERMIT HW2020-046 - MACNAB - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Johnson, William | Brad Carr | 8114.44 | 6103.09 | -2011.35 | -24.79% | 2067.76 | 1060.07 | -1007.69 | -48.73% | 1868.45 | 270.25 | -1598.2 | -85.54% | 265.93 | 0 | -265.93 | -100% | 3912.3 | 4772.77 | 860.47 | 21.99% | 13.08 | 0 | -13.08 | -100% | 2021-03-31 01:00
Hamilton | 2021 | 636811 | JOINT USE PERMIT HW2020-047 - ROYAL, BOWMAN, WILMONT, STROUD - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 9010.16 | 7223.21 | -1786.95 | -19.83% | 831.41 | 1300.63 | 469.22 | 56.44% | 305.17 | 0 | -305.17 | -100% | 119.5 | 0 | -119.5 | -100% | 7754.08 | 5922.58 | -1831.5 | -23.62% | 3.36 | 0 | -3.36 | -100% | 2021-05-10
Hamilton | 2021 | 636812 | 50 KING ST E | 99 | COMPLETE | Labour est. under | BOM not accurate |  | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 122794.82 | 109167.59 | -13627.23 | -11.1% | 17435.17 | 29798.5 | 12363.33 | 70.91% | 79859.25 | 52903.04 | -26956.21 | -33.75% | 3298.4 | 3767.25 | 468.85 | 14.21% | 22202 | 22698.8 | 496.8 | 2.238% | 161.95 | 246 | 84.05 | 51.9% | 2021-05-07
Hamilton | 2020 | 636838 | JOINT USE PERMIT HW2020-048 - BELL AND MONTEREY - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 5585.32 | 4097.34 | -1487.98 | -26.64% | 1145.25 | 741.85 | -403.4 | -35.22% | 455.32 | 251.18 | -204.14 | -44.83% | 134.55 | 40.28 | -94.27 | -70.06% | 3850.2 | 3064.03 | -786.17 | -20.42% | 6 | 0 | -6 | -100% | 2020-10-26 01:00
Hamilton | 2021 | 636881 | JOINT USE PERMIT HW2020-052 - CENTRAL PARK AND KEMP - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 14341.04 | 10646.73 | -3694.31 | -25.76% | 680.87 | 1438.39 | 757.52 | 111.3% | 1145.78 | 842.94 | -302.84 | -26.43% | 0 | 0 | 0 |  | 12514.39 | 8365.4 | -4148.99 | -33.15% | 0 | 0 | 0 |  | 2021-06-08 01:00
Hamilton | 2021 | 636885 | JOINT USE PERMIT HW2020-056 - HIGHLAND - HAM | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 7765.89 | 6553.44 | -1212.45 | -15.61% | 3329.21 | 778.17 | -2551.04 | -76.63% | 227.68 | 588.61 | 360.93 | 158.5% | 358.8 | 0 | -358.8 | -100% | 3850.2 | 5186.66 | 1336.46 | 34.71% | 18 | 0 | -18 | -100% | 2021-02-22 01:00
Hamilton | 2020 | 636886 | JOINT USE PERMIT HW2020-057 - BEACH AND BEATTY - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 6087.6 | 5659.77 | -427.83 | -7.028% | 1187.24 | 917.14 | -270.1 | -22.75% | 227.68 | 227.38 | -0.3 | -0.1318% | 89.7 | 0 | -89.7 | -100% | 4582.98 | 4515.25 | -67.73 | -1.478% | 6 | 0 | -6 | -100% | 2020-10-26 01:00
Hamilton | 2020 | 636920 | 22 PATRICK STREET - OH SERVICE COMPAINT | 99 | COMPLETE | Engineering by-passed |  |  | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 1776.19 | 12648.61 | 10872.42 | 612.1% | 1776.19 | 2548.55 | 772.36 | 43.48% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 10100.06 | 10100.06 |  | 1 | 0 | -1 | -100% | 2020-09-10 01:00
Hamilton | 2021 | 636962 | 575 WOODWARD AVE - SUBD RES EDS | 99 | COMPLETE | Cont Est Over |  |  | Gamboa, Henry | No | Morris, Mark | Brad Carr | 478780.43 | 415056.76 | -63723.67 | -13.31% | 24357.67 | 46526.69 | 22169.02 | 91.01% | 141.76 | 102.4 | -39.36 | -27.77% | 924 | 2652.67 | 1728.67 | 187.1% | 453357 | 365775 | -87582 | -19.32% | 156 | 181.5 | 25.5 | 16.35% | 2021-08-25 01:00
Hamilton | 2022 | 636967 | 27 RACHAEL DRIVE - SUBD RES EDS | 95 | COMPLETE | Cont Est Over |  |  | Gamboa, Henry | No | Morris, Mark | Brad Carr | 335532.6 | 286612.4 | -48920.2 | -14.58% | 18557.31 | 34047.46 | 15490.15 | 83.47% | 8470.91 | 11561.34 | 3090.43 | 36.48% | 2190.46 | 3680 | 1489.54 | 68% | 306313.92 | 236337.15 | -69976.77 | -22.84% | 139.41 | 167.5 | 28.09 | 20.15% | 2022-02-11 01:00
Hamilton | 2021 | 636974 | JOINT USE PERMIT HW2020-059 - ARGYLE, FRASER, EDINBURGH, ETC - HAM | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 9642.13 | 7318.18 | -2323.95 | -24.1% | 2653.9 | 1086.1 | -1567.8 | -59.08% | 683.01 | 148.36 | -534.65 | -78.28% | 269.1 | 0 | -269.1 | -100% | 6036.12 | 6083.72 | 47.6 | 0.7886% | 18 | 0 | -18 | -100% | 2021-03-31 01:00
Hamilton | 2021 | 636975 | JOINT USE PERMIT HW2020-060 - RYMAL W AND ALFRIN - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 6577.74 | 5523.58 | -1054.16 | -16.03% | 704.95 | 938.02 | 233.07 | 33.06% | 241.67 | 0 | -241.67 | -100% | 0 | 0 | 0 |  | 5631.12 | 4585.56 | -1045.56 | -18.57% | 0 | 0 | 0 |  | 2021-08-13 01:00
Hamilton | 2020 | 636995 | 105 HIGH ST - PAVILLON DE LA JEUNESSE SCHOOL UPGRADE | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 63385.12 | 50765.5 | -12619.62 | -19.91% | 18615.04 | 12363.36 | -6251.68 | -33.58% | 19144.28 | 21841.29 | 2697.01 | 14.09% | 2757.88 | 2248.25 | -509.63 | -18.48% | 22867.92 | 14312.6 | -8555.32 | -37.41% | 136 | 109.5 | -26.5 | -19.49% | 2020-09-21 01:00
Hamilton | 2022 | 636996 | 981 BARTON ST STONEY CREEK UPGRADE | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Jolie, Chris | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-11 01:00
Hamilton | 2022 | 637022 | INSULATORS - WEST - NEBO | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-19 01:00
Hamilton | 2020 | 637043 | 8 AYLETT - ANCHOR RELOCATION | 99 | COMPLETE | Cont Est Over | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 15458.52 | 4060.98 | -11397.54 | -73.73% | 207.28 | 261.46 | 54.18 | 26.14% | 1074.16 | 531.32 | -542.84 | -50.54% | 28 | 0 | -28 | -100% | 14149.08 | 3268.2 | -10880.88 | -76.9% | 2 | 0 | -2 | -100% | 2020-05-21
Hamilton | 2022 | 637117 | SISTER VARGA | 95 | COMPLETE | Engineering by-passed |  |  | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 74030.22 | 50362.73 | -23667.49 | -31.97% | 17240.95 | 12555.53 | -4685.42 | -27.18% | 51101 | 35575.91 | -15525.09 | -30.38% | 1657.27 | 1691.29 | 34.02 | 2.053% | 4031 | 540 | -3491 | -86.6% | 77.52 | 97 | 19.48 | 25.13% | 2022-01-21 01:00
Hamilton | 2020 | 637146 | JOINT USE PERMIT HW2019-092 - SEAMAN - HAM | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 5296.8 | 1178.83 | -4117.97 | -77.74% | 1129.22 | 362.56 | -766.66 | -67.89% | 227.68 | 163.12 | -64.56 | -28.36% | 89.7 | 0 | -89.7 | -100% | 3850.2 | 653.15 | -3197.05 | -83.04% | 6 | 0 | -6 | -100% | 2020-10-26 01:00
Hamilton | 2021 | 637150 | ROAD AUTHORITY - POLE RELOCATION - CENTRE RD - WATERDOWN | 99 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 210889.1 | 194762.48 | -16126.62 | -7.647% | 11629.29 | 24342.81 | 12713.52 | 109.3% | 28547.81 | 26663.77 | -1884.04 | -6.6% | 288 | 308 | 20 | 6.944% | 170424 | 143447.9 | -26976.1 | -15.83% | 18 | 20 | 2 | 11.11% | 2021-06-21 01:00
Hamilton | 2022 | 637163 | 40 MALLARD TRAIL | 99 | COMPLETE | Metering under |  |  | Kappheim, Adam | No | Djuric, Zdravko | Macdougall, Stephen | 82891.04 | 78658.12 | -4232.92 | -5.107% | 18417.76 | 18766.4 | 348.64 | 1.893% | 24145.52 | 26457.44 | 2311.92 | 9.575% | 3584 | 5348.28 | 1764.28 | 49.23% | 36743.76 | 28086 | -8657.76 | -23.56% | 140 | 205 | 65 | 46.43% | 2022-01-26 01:00
Hamilton | 2020 | 637164 | ROGERS BONDS - 2020 BATCH 1 - HAM | 99 | COMPLETE | Estimate incorrect |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 3614.82 | 2499.51 | -1115.31 | -30.85% | 3191.44 | 1781.74 | -1409.7 | -44.17% | 0 | 0 | 0 |  | 423.38 | 717.77 | 294.39 | 69.53% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0% | 2020-11-09 01:00
Hamilton | 2021 | 637183 | JOINT USE PERMIT HW2020-065 - GOVERNORS RD - HAM | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 11100.69 | 8670.68 | -2430.01 | -21.89% | 3247.53 | 1339.88 | -1907.65 | -58.74% | 910.66 | 1744.57 | 833.91 | 91.57% | 313.95 | 0 | -313.95 | -100% | 6628.55 | 5586.23 | -1042.32 | -15.72% | 21 | 0 | -21 | -100% | 2021-05-14
Hamilton | 2021 | 637210 | 157 MILL STREET NORTH | 99 | COMPLETE | Cont Est Over |  |  | Kappheim, Adam | No | Djuric, Zdravko | Macdougall, Stephen | 58426.98 | 37307.42 | -21119.56 | -36.15% | 18417.97 | 8713.85 | -9704.12 | -52.69% | 20835.12 | 26785.57 | 5950.45 | 28.56% | 3584.09 | 1808 | -1776.09 | -49.55% | 15589.8 | 0 | -15589.8 | -100% | 140 | 95 | -45 | -32.14% | 2021-08-04 01:00
Hamilton | 2022 | 637228 | WINONA HILLS SUBDIVISION - SUBD RES EDS | 95 | COMPLETE | Labour est. under | BOM not accurate |  | Velickovski, Goran | No | Morris, Mark | Macdougall, Stephen | 49723.91 | 67803.45 | 18079.54 | 36.36% | 28547.25 | 31392.78 | 2845.53 | 9.968% | 11487.27 | 15721.26 | 4233.99 | 36.86% | 5289.39 | 7845 | 2555.61 | 48.32% | 4400 | 6377.25 | 1977.25 | 44.94% | 189.95 | 306.5 | 116.55 | 61.36% | 2023-01-04 01:00
Hamilton | 2020 | 637264 | JOINT USE PERMIT HW2020-070 - TEAL AND SOUTH SERVICE - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 7110.91 | 3482.39 | -3628.52 | -51.03% | 2177.51 | 1335.76 | -841.75 | -38.66% | 838.11 | 0 | -838.11 | -100% | 245.09 | 0 | -245.09 | -100% | 3850.2 | 2146.63 | -1703.57 | -44.25% | 12 | 9 | -3 | -25% | 2020-08-17 01:00
Hamilton | 2021 | 637292 | 1565 UPPER JAMES STREET - CULVER PROPERTIES LTD. | 99 | COMPLETE | Labour est. under |  |  | Kappheim, Adam | No | Bharosi, Mohindra | Roy Owen | 117490.14 | 115246.12 | -2244.02 | -1.91% | 16211.65 | 24128.03 | 7916.38 | 48.83% | 68978.53 | 64950.08 | -4028.45 | -5.84% | 2868.88 | 3599.21 | 730.33 | 25.46% | 29431.08 | 22568.8 | -6862.28 | -23.32% | 112 | 152.5 | 40.5 | 36.16% | 2021-09-07 01:00
Hamilton | 2021 | 637332 | JOINT USE PERMIT HW2020-075 - ROXBOROUGH, ARCHIBALD, ETC - HAM | 99 | COMPLETE | Under 10% |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 33738.84 | 36617.54 | 2878.7 | 8.532% | 939.93 | 2393.76 | 1453.83 | 154.7% | 11026.11 | 9261.34 | -1764.77 | -16.01% | 0 | 0 | 0 |  | 21772.8 | 24962.44 | 3189.64 | 14.65% | 0 | 0 | 0 |  | 2021-08-13 01:00
Hamilton | 2021 | 637338 | SECOND FEED INTO SC1390 @ SALERNO DAIRY - 20 MORLEY STREET | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Karan, Andjelo | Roy Owen | 21701.31 | 19949.12 | -1752.19 | -8.074% | 12860.57 | 12911.86 | 51.29 | 0.3988% | 7504.24 | 5612.84 | -1891.4 | -25.2% | 1336.5 | 1424.42 | 87.92 | 6.578% | 0 | 0 | 0 |  | 120 | 124 | 4 | 3.333% | 2021-01-18 01:00
Hamilton | 2020 | 637355 | 2020 - OH AUTO SWITCH INSTALLS | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Carr, Brad | 116952.2 | 116080.82 | -871.38 | -0.7451% | 3868.27 | 7898.73 | 4030.46 | 104.2% | 72075.41 | 76622.94 | 4547.53 | 6.309% | 56 | 300.63 | 244.63 | 436.8% | 40952.52 | 31258.52 | -9694 | -23.67% | 4 | 31 | 27 | 675% | 2020-12-23 01:00
Hamilton | 2020 | 637362 | 38 WEST AVE S - UPGRADE | 99 | COMPLETE | Labour est. over |  |  | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 37881.06 | 28358.34 | -9522.72 | -25.14% | 17831.26 | 8829.69 | -9001.57 | -50.48% | 14632.16 | 16459.65 | 1827.49 | 12.49% | 3384 | 3069 | -315 | -9.309% | 2033.64 | 0 | -2033.64 | -100% | 100 | 110 | 10 | 10% | 2020-08-14 01:00
Hamilton | 2021 | 637395 | 256 LIME KILN ROAD ANCASTER - FAULTY TRANSFORMER | 99 | COMPLETE | BOM – truck stock |  |  | Beaudrie, Scott | No | Wardell, Paul | Koeppe, Jeffrey | 49418.77 | 55671.64 | 6252.87 | 12.65% | 16282.79 | 19386.97 | 3104.18 | 19.06% | 16598.71 | 13170.36 | -3428.35 | -20.65% | 3782.47 | 8690.31 | 4907.84 | 129.8% | 12754.8 | 14424 | 1669.2 | 13.09% | 120 | 167 | 47 | 39.17% | 2021-06-21 01:00
Hamilton | 2022 | 637419 | HAM - NS - TEMP SERVICE - LONGWOOD S | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Oosterlinck, David | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-02 01:00
Hamilton | 2022 | 637452 | TURNER AVE - UG REAR LOT CONVERSION | 92 | ACTIVE |  |  |  | Beaudrie, Scott | Yes | Anderson, Dean | Brad Carr | 663135.92 | 596080.48 | -67055.44 | -10.11% | 95262.04 | 107404.3 | 12142.26 | 12.75% | 15172.71 | 12474.47 | -2698.24 | -17.78% | 1356.93 | 0 | -1356.93 | -100% | 551344.24 | 476201.71 | -75142.53 | -13.63% | 84.35 | 4.5 | -79.85 | -94.67% | 2022-12-28 01:00
Hamilton | 2021 | 637453 | INGLEWOOD & UNDERCLIFFE CONVERSION | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | Yes | Anderson, Dean | Brad Carr | 641525.11 | 559012.29 | -82512.82 | -12.86% | 41981.99 | 84364.94 | 42382.95 | 101% | 30826.78 | 35038.82 | 4212.04 | 13.66% | 2699.73 | 0 | -2699.73 | -100% | 566016.61 | 439608.53 | -126408.08 | -22.33% | 184 | 0 | -184 | -100% | 2021-12-10 01:00
Hamilton | 2020 | 637474 | POLE REPLACEMENT - EAST 25TH & FENNEL AVE E | 99 | COMPLETE | Under 10% | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 53730.16 | 51921.92 | -1808.24 | -3.365% | 5457.02 | 6805.11 | 1348.09 | 24.7% | 13082.9 | 17739 | 4656.1 | 35.59% | 84 | 0 | -84 | -100% | 35106.24 | 27377.81 | -7728.43 | -22.01% | 6 | 6 | 0 | 0% | 2020-10-15 01:00
Hamilton | 2021 | 637490 | 2021 POLE RENEWAL - EAST 21ST ST - 6 | 99 | COMPLETE | Under 10% | BOM not used |  | Beaudrie, Scott | No | Webb-Murre, Paige | Koeppe, Jeffrey | 96560.17 | 121502.88 | 24942.71 | 25.83% | 50548.66 | 61643.33 | 11094.67 | 21.95% | 19919.17 | 22307.44 | 2388.27 | 11.99% | 11836.34 | 25174.34 | 13338 | 112.7% | 14256 | 12377.77 | -1878.23 | -13.18% | 566 | 646 | 80 | 14.13% | 2021-11-19 01:00
Hamilton | 2021 | 637546 | JOINT USE PERMIT HW2020-080 - DUNDURN N AND TOM - HAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Johnson, William | Brad Carr | 14322.7 | 6674.78 | -7647.92 | -53.4% | 3215.32 | 1012.68 | -2202.64 | -68.5% | 3305.07 | 364.17 | -2940.9 | -88.98% | 528.38 | 0 | -528.38 | -100% | 7273.93 | 5297.93 | -1976 | -27.17% | 18.72 | 0 | -18.72 | -100% | 2021-04-16
Hamilton | 2020 | 637551 | QUEEN ST - KING TO MAKET PRIMARY REMOVAL | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-12 01:00
Hamilton | 2020 | 637558 | 174 AND 190 NAPIER ST, HAM - DRILLING POLES 14698 AND 37611 | 99 | COMPLETE | Labour est. over |  |  | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 1197.24 | 1010.4 | -186.84 | -15.61% | 1105.2 | 494.36 | -610.84 | -55.27% | 0 | 0 | 0 |  | 92.04 | 0 | -92.04 | -100% | 0 | 516.04 | 516.04 |  | 4 | 0 | -4 | -100% | 2020-11-02 01:00
Hamilton | 2020 | 637570 | 202 CANADA ST - AERIAL TRESPASS | 99 | COMPLETE | Under 10% | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Koeppe, Jeffrey | 16083.95 | 16925.46 | 841.51 | 5.232% | 9879.88 | 9303.76 | -576.12 | -5.831% | 1403.73 | 3534.12 | 2130.39 | 151.8% | 1500.4 | 2423 | 922.6 | 61.49% | 3299.94 | 1664.58 | -1635.36 | -49.56% | 80 | 110 | 30 | 37.5% | 2020-10-06 01:00
Hamilton | 2020 | 637581 | LANG & REID / HAM / SR | 99 | COMPLETE | Labour est. over | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 27556.64 | 12872.83 | -14683.81 | -53.29% | 19072.65 | 8845.21 | -10227.44 | -53.62% | 1281.83 | 136.28 | -1145.55 | -89.37% | 2448 | 1936.5 | -511.5 | -20.89% | 4754.16 | 1954.84 | -2799.32 | -58.88% | 160 | 103.5 | -56.5 | -35.31% | 2020-09-18 01:00
Hamilton | 2021 | 637667 | MH 90 - LID/ROOF ADJUSTMENTS | 99 | COMPLETE | Cont Est Under | N/A | N/A | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 21386.27 | 27312.64 | 5926.37 | 27.71% | 4776.24 | 4252.54 | -523.7 | -10.96% | 652.27 | 4328.16 | 3675.89 | 563.6% | 112 | 0 | -112 | -100% | 15845.76 | 18731.94 | 2886.18 | 18.21% | 8 | 0 | -8 | -100% | 2021-01-27 01:00
Hamilton | 2020 | 637675 | 24 KENNARD ST | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Paesano, Andrew | No | Alectra Utilities | Roy Owen | 73100.19 | 57986.77 | -15113.42 | -20.67% | 15759.67 | 11169.49 | -4590.18 | -29.13% | 26627.15 | 26136.45 | -490.7 | -1.843% | 2217.57 | 1936.11 | -281.46 | -12.69% | 28495.8 | 18744.72 | -9751.08 | -34.22% | 100 | 66.5 | -33.5 | -33.5% | 2020-10-15 01:00
Hamilton | 2021 | 637710 | V1061 RELOCATON | 99 | COMPLETE | BOM not accurate | N/A | N/A | Jakubowski, Mark | Yes | Jolie, Chris | Brad Carr | 182201.3 | 177247.81 | -4953.49 | -2.719% | 6434.57 | 15766.16 | 9331.59 | 145% | 33250.17 | 41047.8 | 7797.63 | 23.45% | 336 | 306 | -30 | -8.929% | 142180.56 | 120127.85 | -22052.71 | -15.51% | 24 | 34 | 10 | 41.67% | 2021-03-12 01:00
Hamilton | 2021 | 637719 | JOINT USE PERMIT HW2020-089 - BOBOLINK - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 5945.74 | 3184.74 | -2761 | -46.44% | 1106.19 | 897.06 | -209.13 | -18.91% | 267.01 | 0 | -267.01 | -100% | 119.7 | 0 | -119.7 | -100% | 4452.84 | 2287.68 | -2165.16 | -48.62% | 4 | 0 | -4 | -100% | 2021-05-17 01:00
Hamilton | 2022 | 637720 | JOINT USE PERMIT HW2020-091 - PARK, BROCK N, MARKET N, ETC - HAM | 99 | COMPLETE | Engineering by-passed |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 9782.71 | 6884.88 | -2897.83 | -29.62% | 1572.6 | 1062.9 | -509.7 | -32.41% | 455.95 | 0 | -455.95 | -100% | 117.3 | 0 | -117.3 | -100% | 7636.86 | 5821.98 | -1814.88 | -23.76% | 3.15 | 0 | -3.15 | -100% | 2022-01-04 01:00
Hamilton | 2021 | 637726 | JOINT USE PERMIT HW2020-095 - HATT, NAPIER S, MATILDA S - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 11239.41 | 7461.75 | -3777.66 | -33.61% | 683.95 | 1117.18 | 433.23 | 63.34% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10555.46 | 6344.57 | -4210.89 | -39.89% | 0 | 0 | 0 |  | 2021-06-08 01:00
Hamilton | 2021 | 637728 | JOINT USE PERMIT HW2020-094 - JAMES, BROCK S, HATT, BOND S - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 8155.22 | 6017.25 | -2137.97 | -26.22% | 517.18 | 1178.27 | 661.09 | 127.8% | 265 | 0 | -265 | -100% | 0 | 44 | 44 |  | 7373.04 | 4794.98 | -2578.06 | -34.97% | 0 | 2 | 2 |  | 2021-04-16
Hamilton | 2021 | 637761 | JOINT USE PERMIT HW2020-098 - CREIGHTON, MAYFAIR, GOVERNORS - HAM | 99 | COMPLETE | Legal Fees |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 8910.95 | 7086.99 | -1823.96 | -20.47% | 1026.25 | 1144.92 | 118.67 | 11.56% | 260.98 | 330.02 | 69.04 | 26.45% | 0 | 0 | 0 |  | 7623.72 | 5612.05 | -2011.67 | -26.39% | 0 | 0 | 0 |  | 2021-10-20 01:00
Hamilton | 2020 | 637896 | 686 QUEENSTON ROAD - ELECTRIFY CANADA/HAM/NS00032030/3PHPAD | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Paesano, Andrew | No | Alectra Utilities | Roy Owen | 81015.83 | 62971.78 | -18044.05 | -22.27% | 30405.84 | 17924.08 | -12481.76 | -41.05% | 34397.16 | 41144.55 | 6747.39 | 19.62% | 5333.99 | 3309.8 | -2024.19 | -37.95% | 10878.84 | 593.35 | -10285.49 | -94.55% | 225 | 179 | -46 | -20.44% | 2020-12-21 01:00
Hamilton | 2020 | 637909 | COSTCO - ST.CATHARINES - 2500A 347/600V UPGRADE | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Calvin Arsenault | 3780.93 | 0 | -3780.93 | -100% | 3780.93 | 0 | -3780.93 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-22 01:00
Hamilton | 2022 | 637917 | POLE 41797 - REPLACE FUSES ON POLE | 95 | COMPLETE | Material Req incorrectly | Labour est. over |  | Beaudrie, Scott | No | Billone, Justin | Koeppe, Jeffrey | 30246.21 | 15267.96 | -14978.25 | -49.52% | 10385.84 | 6580.89 | -3804.95 | -36.64% | 15426.47 | 6659.47 | -8767 | -56.83% | 2433.9 | 1488.61 | -945.29 | -38.84% | 2000 | 538.99 | -1461.01 | -73.05% | 43.92 | 62 | 18.08 | 41.17% | 2022-12-20 01:00
Hamilton | 2021 | 637920 | TX RENEWAL PROGRAM 2021 PHASE 1 - STONEY CREEK - 3 | 99 | COMPLETE | Labour est. under | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Macdougall, Stephen | 63109.85 | 57336.57 | -5773.28 | -9.148% | 34693.82 | 26952.47 | -7741.35 | -22.31% | 14541.55 | 14278.52 | -263.03 | -1.809% | 6746.48 | 9190.83 | 2444.35 | 36.23% | 7128 | 6914.75 | -213.25 | -2.992% | 239.36 | 366.5 | 127.14 | 53.12% | 2021-05-28 01:00
Hamilton | 2021 | 637921 | TX RENEWAL PROGRAM 2021 - PHASE 2 - HAMILTON - 4 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Macdougall, Stephen | 92236.57 | 98723.88 | 6487.31 | 7.033% | 39265.03 | 45210.49 | 5945.46 | 15.14% | 36787.26 | 31741.07 | -5046.19 | -13.72% | 9056.28 | 19494.47 | 10438.19 | 115.3% | 7128 | 2277.85 | -4850.15 | -68.04% | 320 | 511 | 191 | 59.69% | 2021-12-23 01:00
Hamilton | 2020 | 637922 | 925-979 MAIN ST W / HRZ. SR | 99 | COMPLETE | Estimate incorrect |  |  | Kappheim, Adam | No | Alectra Utilities | Roy Owen | 9140.64 | 3475.23 | -5665.41 | -61.98% | 6330.43 | 3475.23 | -2855.2 | -45.1% | 1580 | 0 | -1580 | -100% | 1013.13 | 0 | -1013.13 | -100% | 217.08 | 0 | -217.08 | -100% | 39.99 | 42 | 2.01 | 5.026% | 2020-10-09 01:00
Hamilton | 2022 | 637929 | 202 DUNDURN STREET SOUTH / HAM / UP / 3PH PAD | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Djuric, Zdravko | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-22 01:00
Hamilton | 2021 | 638019 | JOINT USE PERMIT HW2020-099 - LOCKE S, GEORGE, NELSON, PEARL S - HAM | 99 | COMPLETE | Labour est. over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 8828.79 | 7765.76 | -1063.03 | -12.04% | 1522.18 | 611.58 | -910.6 | -59.82% | 392.8 | 276.94 | -115.86 | -29.5% | 153.83 | 0 | -153.83 | -100% | 6759.98 | 6877.24 | 117.26 | 1.735% | 3.36 | 0 | -3.36 | -100% | 2021-08-13 01:00
Hamilton | 2021 | 638021 | JOINT USE PERMIT HW2020-101 - REGENT, ANGELINA, OTTAVIANO, ETC - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 10337.1 | 7975.89 | -2361.21 | -22.84% | 995.35 | 1078.48 | 83.13 | 8.352% | 453.9 | 373.36 | -80.54 | -17.74% | 144.49 | 0 | -144.49 | -100% | 8743.36 | 6524.05 | -2219.31 | -25.38% | 3.36 | 0 | -3.36 | -100% | 2021-04-16
Hamilton | 2021 | 638083 | 857 WOODWARD AVE | 99 | COMPLETE | Estimate incorrect |  |  | Paesano, Andrew | No | Dragojevic, Igor | Macdougall, Stephen | 65963.9 | 56050.6 | -9913.3 | -15.03% | 29515.5 | 20945.23 | -8570.27 | -29.04% | 11781.58 | 15016.74 | 3235.16 | 27.46% | 6240.94 | 4834 | -1406.94 | -22.54% | 18425.88 | 15254.63 | -3171.25 | -17.21% | 221.92 | 210.75 | -11.17 | -5.033% | 2021-11-12 01:00
Hamilton | 2021 | 638110 | JOINT USE PERMIT HW2020-109 - MORGAN, CAROGA, BONAVENTURE, ETC - HAM | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 10955.14 | 7833.67 | -3121.47 | -28.49% | 1329.52 | 928.15 | -401.37 | -30.19% | 819.06 | 591.68 | -227.38 | -27.76% | 260.74 | 0 | -260.74 | -100% | 8545.82 | 6313.84 | -2231.98 | -26.12% | 6.72 | 0 | -6.72 | -100% | 2021-04-16
Hamilton | 2021 | 638124 | 161 BROCKLEY DR | 99 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Dragojevic, Igor | Macdougall, Stephen | 49939.9 | 46697.56 | -3242.34 | -6.492% | 21319.33 | 15199.47 | -6119.86 | -28.71% | 24733.95 | 27320.14 | 2586.19 | 10.46% | 3276.42 | 3547 | 270.58 | 8.258% | 610.2 | 630.95 | 20.75 | 3.401% | 143.02 | 149 | 5.98 | 4.181% | 2021-07-02 01:00
Hamilton | 2020 | 638144 | 75 DISCOVERY DR - TEMP SERVICE | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-08-23 01:00
Hamilton | 2021 | 638197 | FOOTHILLS OF WINONA PHASE 1B & 2 - SUBD RES EDS | 99 | COMPLETE | Labour est. under |  |  | Gamboa, Henry | No | Morris, Mark | Roy Owen | 22429.2 | 195847.87 | 173418.67 | 773.2% | 19325.97 | 24068.45 | 4742.48 | 24.54% | 1602.24 | 429.66 | -1172.58 | -73.18% | 1500.99 | 3762 | 2261.01 | 150.6% | 0 | 236.9 | 236.9 |  | 111.26 | 240 | 128.74 | 115.7% | 2021-12-10 01:00
Hamilton | 2020 | 638198 | FOOTHILLS OF WINONA - PHASE 2B - SUBD RES EDS | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Alectra Utilities | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-16 01:00
Hamilton | 2021 | 638226 | JOINT USE PERMIT HW2020-115 - KILBOURN AND HWY 8 - HAM | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Johnson, William | Brad Carr | 5421.23 | 5575.61 | 154.38 | 2.848% | 466.62 | 915.17 | 448.55 | 96.13% | 0 | 0 | 0 |  | 0 | 564 | 564 |  | 4954.61 | 4096.44 | -858.17 | -17.32% | 0 | 0 | 0 |  | 2021-04-16
Hamilton | 2022 | 638270 | JOINT USE PERMIT HW2020-120 - SOUTH W, WOODWARD, HILLSIDE N, ETC - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 10651.8 | 10156.3 | -495.5 | -4.652% | 680.87 | 1679.89 | 999.02 | 146.7% | 231.17 | 693.94 | 462.77 | 200.2% | 0 | 0 | 0 |  | 9739.76 | 7782.47 | -1957.29 | -20.1% | 0 | 0 | 0 |  | 2022-04-26
Hamilton | 2022 | 638271 | JOINT USE PERMIT HW2020-121 - HILLSIDE S AND ROGERS - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 16322 | 16613.02 | 291.02 | 1.783% | 3061.19 | 2300.1 | -761.09 | -24.86% | 1206.85 | 2932.07 | 1725.22 | 143% | 282.46 | 0 | -282.46 | -100% | 11771.5 | 11380.85 | -390.65 | -3.319% | 6.72 | 0 | -6.72 | -100% | 2022-01-24 01:00
Hamilton | 2021 | 638272 | JOINT USE PERMIT HW2020-122 - GOVERNORS - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 39651.75 | 7094.66 | -32557.09 | -82.11% | 1716.68 | 1089.36 | -627.32 | -36.54% | 3348.5 | 0 | -3348.5 | -100% | 132.41 | 0 | -132.41 | -100% | 34454.16 | 6005.3 | -28448.86 | -82.57% | 3.15 | 0 | -3.15 | -100% | 2021-10-20 01:00
Hamilton | 2022 | 638288 | PIER 8 PUMPING STATION - TEMP SERVICE | 99 | COMPLETE | N/A |  |  | Kappheim, Adam | No | Jolie, Chris | Macdougall, Stephen | 98165.84 | 87921.56 | -10244.28 | -10.44% | 45276.6 | 34114.38 | -11162.22 | -24.65% | 33809.11 | 32911.99 | -897.12 | -2.653% | 9990.85 | 8814 | -1176.85 | -11.78% | 9089.28 | 12081.19 | 2991.91 | 32.92% | 392.86 | 417.5 | 24.64 | 6.272% | 2022-11-14 01:00
Hamilton | 2021 | 638310 | LANG & REID - PHASE 2 / HAM / SR | 99 | COMPLETE | Labour est. over | BOM not used |  | Kappheim, Adam | No | Sabbah, Amir | Roy Owen | 52238.97 | 0 | -52238.97 | -100% | 35488.36 | 0 | -35488.36 | -100% | 2825.21 | 0 | -2825.21 | -100% | 5496 | 0 | -5496 | -100% | 8429.4 | 0 | -8429.4 | -100% | 312 | 0 | -312 | -100% | 2021-10-20 01:00
Hamilton | 2021 | 638323 | ABERDEEN #4 O/H -BAY TO MTN ACCESS | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Anderson, Dean | Koeppe, Jeffrey | 658514 | 774592.06 | 116078.06 | 17.63% | 223662.21 | 310526.94 | 86864.73 | 38.84% | 198053.05 | 189332.78 | -8720.27 | -4.403% | 40813.74 | 112542.38 | 71728.64 | 175.7% | 195985 | 162189.96 | -33795.04 | -17.24% | 3375.5 | 3393.5 | 18 | 0.5333% | 2021-05-21 01:00
Hamilton | 2020 | 638396 | 107 MCNAB ST NORTH, LINE ISOLATION | 99 | COMPLETE | Labour est. under |  |  | Jakubowski, Mark | No | Alectra Utilities | Scott Borer | 6275.54 | 13349.95 | 7074.41 | 112.7% | 4929.54 | 11642.45 | 6712.91 | 136.2% | 337.99 | 0 | -337.99 | -100% | 1008.01 | 1707.5 | 699.49 | 69.39% | 0 | 0 | 0 |  | 36 | 123.5 | 87.5 | 243.1% | 2020-12-15 01:00
Hamilton | 2021 | 638408 | 254 SOUTH SERVICE ROAD / HAM / UP | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Sabbah, Amir | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-10-20 01:00
Hamilton | 2021 | 638412 | JOINT USE PERMIT HW2020-126 - DUNDAS EAST - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 14145.44 | 9629.17 | -4516.27 | -31.93% | 1489.6 | 1110.07 | -379.53 | -25.48% | 1004.94 | 2802.7 | 1797.76 | 178.9% | 288.98 | 0 | -288.98 | -100% | 11361.92 | 5716.4 | -5645.52 | -49.69% | 6.72 | 0 | -6.72 | -100% | 2021-10-20 01:00
Hamilton | 2021 | 638413 | JOINT USE PERMIT HW2020-127 - RAINBOW - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 11449.14 | 5759.59 | -5689.55 | -49.69% | 1707.48 | 931.07 | -776.41 | -45.47% | 819.17 | 520.93 | -298.24 | -36.41% | 144.49 | 0 | -144.49 | -100% | 8778 | 4307.59 | -4470.41 | -50.93% | 3.36 | 0 | -3.36 | -100% | 2021-08-30 01:00
Hamilton | 2022 | 638415 | 631 SOUTH TOWN LINE RD / HAM / UP | 99 | CANCELLED | N/A |  |  | Kappheim, Adam | No | Sabbah, Amir | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-22 01:00
Hamilton | 2022 | 638419 | TX RENEWAL PROGRAM 2021 - PHASE 3 - HAMILTON - 3 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 57206.18 | 55530.61 | -1675.57 | -2.929% | 29142.23 | 21459.52 | -7682.71 | -26.36% | 16977.19 | 18805.18 | 1827.99 | 10.77% | 6334.76 | 9396.69 | 3061.93 | 48.34% | 4752 | 5869.22 | 1117.22 | 23.51% | 244 | 285 | 41 | 16.8% | 2022-05-02
Hamilton | 2022 | 638424 | 237 ARVIN AVE - TK PLASTICS LTD/HAM/UP00070769 /3PHPAD | 99 | COMPLETE | Labour est. over |  |  | Frigotto, Rodrigo | No | Bharosi, Mohindra | Macdougall, Stephen | 140711.36 | 128710.29 | -12001.07 | -8.529% | 44912.09 | 28872.1 | -16039.99 | -35.71% | 67242.8 | 76017.84 | 8775.04 | 13.05% | 8608.65 | 6714 | -1894.65 | -22.01% | 19947.82 | 17106.35 | -2841.47 | -14.24% | 388.8 | 281.5 | -107.3 | -27.6% | 2022-01-24 01:00
Hamilton | 2021 | 638426 | 2 MEDICORUM PLACE - VICANO CONSTRUCTION LTD/HAM/NS00046555/3PHPAD | 99 | COMPLETE | Labour est. under |  |  | Paesano, Andrew | No | Bharosi, Mohindra | Roy Owen | 86740.31 | 74671.79 | -12068.52 | -13.91% | 18571.19 | 16322.77 | -2248.42 | -12.11% | 50070.04 | 47612.24 | -2457.8 | -4.909% | 2242.52 | 2180 | -62.52 | -2.788% | 15856.56 | 8556.78 | -7299.78 | -46.04% | 117.72 | 168.5 | 50.78 | 43.14% | 2021-07-29 01:00
Hamilton | 2021 | 638427 | 432 HIGHLAND RD -HIGHLAND PACKERS/HAM/UP00056773/3PHPAD | 99 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Bharosi, Mohindra | Macdougall, Stephen | 150406.32 | 141617.13 | -8789.19 | -5.844% | 71405.12 | 48082.91 | -23322.21 | -32.66% | 63820.05 | 64144.77 | 324.72 | 0.5088% | 16750.87 | 17146.5 | 395.63 | 2.362% | 20780.28 | 12242.95 | -8537.33 | -41.08% | 608 | 614 | 6 | 0.9868% | 2021-08-16 01:00
Hamilton | 2021 | 638468 | SC869 - SWITCH REPLACEMENT - GATESTONE DRIVE - 1 | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | Yes | Billone, Justin | Roy Owen | 88108.77 | 79042.68 | -9066.09 | -10.29% | 14680.57 | 8645.65 | -6034.92 | -41.11% | 70014.2 | 69708.03 | -306.17 | -0.4373% | 3414 | 689 | -2725 | -79.82% | 0 | 0 | 0 |  | 106 | 86.5 | -19.5 | -18.4% | 2021-04-19
Hamilton | 2021 | 638484 | 2021 TX RENEWAL - 21 JONES ST STONEY CREEK - 1 | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Roy Owen | 30309.88 | 32754.2 | 2444.32 | 8.064% | 10739.03 | 12219.78 | 1480.75 | 13.79% | 1191.8 | 1905.14 | 713.34 | 59.85% | 479.05 | 926.2 | 447.15 | 93.34% | 17900 | 17703.08 | -196.92 | -1.1% | 33.89 | 72 | 38.11 | 112.5% | 2021-12-24 01:00
Hamilton | 2021 | 638523 | AUTO SWITCH INSTALLS - DUNDAS TS FEEDERS, 2 | 99 | COMPLETE | BOM not accurate | Flagging | N/A | Beaudrie, Scott | Yes | Billone, Justin | Koeppe, Jeffrey | 140234.97 | 152399.04 | 12164.07 | 8.674% | 38891.78 | 30296.89 | -8594.89 | -22.1% | 92991.19 | 106005.35 | 13014.16 | 14% | 8352 | 12747.16 | 4395.16 | 52.62% | 0 | 3349.64 | 3349.64 |  | 320 | 352.5 | 32.5 | 10.16% | 2021-06-04 01:00
Hamilton | 2021 | 638547 | TX RENEWAL PROGRAM 2021 - PHASE 6 - WATERDOWN - 3 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Macdougall, Stephen | 61574.74 | 69539.41 | 7964.67 | 12.93% | 30139.12 | 27833.56 | -2305.56 | -7.65% | 17590.46 | 20795.86 | 3205.4 | 18.22% | 6717.16 | 16172.64 | 9455.48 | 140.8% | 7128 | 4737.35 | -2390.65 | -33.54% | 240 | 318.5 | 78.5 | 32.71% | 2021-07-12 01:00
Hamilton | 2021 | 638548 | TX RENEWAL PROGRAM 2021 PHASE 7 - HAMILTON EAST - 3 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Macdougall, Stephen | 68278.15 | 64001.63 | -4276.52 | -6.263% | 35297.42 | 24954.37 | -10343.05 | -29.3% | 17811.77 | 20244.32 | 2432.55 | 13.66% | 8040.96 | 13332.37 | 5291.41 | 65.81% | 7128 | 5470.57 | -1657.43 | -23.25% | 360 | 291.5 | -68.5 | -19.03% | 2021-11-22 01:00
Hamilton | 2021 | 638668 | MOHAWK & UPPER JAMES SWITCH, 1 | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Anderson, Dean | Brad Carr | 777016.73 | 649019.37 | -127997.36 | -16.47% | 75241.36 | 87910.39 | 12669.03 | 16.84% | 155756.3 | 166987.92 | 11231.62 | 7.211% | 8352.8 | 2946.41 | -5406.39 | -64.73% | 537666.27 | 391174.65 | -146491.62 | -27.25% | 169.84 | 189.5 | 19.66 | 11.58% | 2021-11-11 01:00
Hamilton | 2022 | 638721 | JOINT USE PERMIT HW2020-135 - MAIN SOUTH - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 4683.83 | 5538.46 | 854.63 | 18.25% | 704.95 | 1110.89 | 405.94 | 57.58% | 241.22 | 0 | -241.22 | -100% | 0 | 0 | 0 |  | 3737.66 | 4427.57 | 689.91 | 18.46% | 0 | 0 | 0 |  | 2022-01-12 01:00
Hamilton | 2021 | 638727 | 41 REID AVE / HAM / NS | 99 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Sabbah, Amir | Roy Owen | 80765.48 | 64984.5 | -15780.98 | -19.54% | 23792.96 | 20033.16 | -3759.8 | -15.8% | 34421.15 | 4732.54 | -29688.61 | -86.25% | 3390.49 | 2388.5 | -1001.99 | -29.55% | 41510.88 | 37830.3 | -3680.58 | -8.867% | 166 | 185.5 | 19.5 | 11.75% | 2021-07-02 01:00
Hamilton | 2022 | 638760 | 1831X RELIABILITY PROJECT | 99 | COMPLETE | Scope – Eng |  |  | Beaudrie, Scott | No | Billone, Justin | Macdougall, Stephen | 56835.09 | 28308.91 | -28526.18 | -50.19% | 21061.29 | 15601 | -5460.29 | -25.93% | 30603.62 | 6465.91 | -24137.71 | -78.87% | 5170.18 | 5172 | 1.82 | 0.0352% | 0 | 1070 | 1070 |  | 156.67 | 128 | -28.67 | -18.3% | 2022-01-24 01:00
Hamilton | 2021 | 638774 | JOINT USE PERMIT HW2020-137 - GRAYS AND HWY 8 - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 6694.25 | 5365.1 | -1329.15 | -19.86% | 509.12 | 1163.12 | 654 | 128.5% | 260.25 | 0 | -260.25 | -100% | 0 | 0 | 0 |  | 5924.88 | 4201.98 | -1722.9 | -29.08% | 0 | 0 | 0 |  | 2021-03-29 01:00
Hamilton | 2022 | 638887 | 223 EAST AVE - EXPANSION | 95 | COMPLETE | Estimate incorrect | Cont Est Under |  | Kappheim, Adam | No | Bennett, Aaron | Macdougall, Stephen | 61468.89 | 54868.94 | -6599.95 | -10.74% | 43235.12 | 32270.42 | -10964.7 | -25.36% | 6947.9 | 5271.52 | -1676.38 | -24.13% | 10185.87 | 10547 | 361.13 | 3.545% | 1100 | 6780 | 5680 | 516.4% | 360.92 | 368 | 7.08 | 1.962% | 2022-01-21 01:00
Hamilton | 2022 | 638929 | 270 MELVIN AVE - SUBD RES EDS | 99 | COMPLETE | Estimate incorrect |  |  | Velickovski, Goran | No | Morris, Mark | Roy Owen | 31211.95 | 234462.62 | 203250.67 | 651.2% | 20129.08 | 17523.87 | -2605.21 | -12.94% | 70.87 | 24098.43 | 24027.56 | 33904% | 1400 | 2546 | 1146 | 81.86% | 9612 | 3950.45 | -5661.55 | -58.9% | 100 | 150.5 | 50.5 | 50.5% | 2022-05-24 01:00
Hamilton | 2021 | 638952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 1) | 99 | COMPLETE | Scope – Eng |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 1973542.16 | 2176427.82 | 202885.66 | 10.28% | 20629.45 | 251743.31 | 231113.86 | 1120% | 506776.61 | 506452.53 | -324.08 | -0.06395% | 3232 | 249.57 | -2982.43 | -92.28% | 1442904.1 | 1417982.41 | -24921.69 | -1.727% | 202 | 85 | -117 | -57.92% | 2021-12-23 01:00
Hamilton | 2022 | 638954 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (EAST OF UPPER PARADISE) (3A) | 92 | ACTIVE |  |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 905115.08 | 960616.65 | 55501.57 | 6.132% | 145584.04 | 137231.45 | -8352.59 | -5.737% | 131736.42 | 166217.5 | 34481.08 | 26.17% | 3745 | 216.21 | -3528.79 | -94.23% | 624049.62 | 656951.49 | 32901.87 | 5.272% | 199 | 22 | -177 | -88.94% | 2022-12-15 01:00
Hamilton | 2021 | 638967 | MAUNAL SWITCH RENEWAL - HAMILTON 2021 - 2 | 99 | COMPLETE | Labour est. under |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 48479.72 | 53497.16 | 5017.44 | 10.35% | 22235.29 | 27236.03 | 5000.74 | 22.49% | 20026.56 | 15195.75 | -4830.81 | -24.12% | 3665.87 | 4728.5 | 1062.63 | 28.99% | 2552 | 6336.88 | 3784.88 | 148.3% | 246 | 324 | 78 | 31.71% | 2021-10-27 01:00
Hamilton | 2021 | 638968 | AUTOMATE SWITCH RENEWAL - HAMILTON 2021, 4 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Brad Carr | 363415.38 | 379462.21 | 16046.83 | 4.416% | 41929.49 | 35029.07 | -6900.42 | -16.46% | 193830.14 | 223710.24 | 29880.1 | 15.42% | 921.24 | 1807.45 | 886.21 | 96.2% | 126734.51 | 118915.45 | -7819.06 | -6.17% | 267.64 | 181.5 | -86.14 | -32.19% | 2021-06-18 01:00
Hamilton | 2021 | 638970 | 2021 EMERGING OH - EAST 25TH ST - BELL POLES | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Brad Carr | 115586.37 | 122667.69 | 7081.32 | 6.126% | 4487.66 | 12994.75 | 8507.09 | 189.6% | 29699.18 | 34571.62 | 4872.44 | 16.41% | 0 | 0 | 0 |  | 81399.53 | 75101.32 | -6298.21 | -7.737% | 20 | 0 | -20 | -100% | 2021-06-24 01:00
Hamilton | 2021 | 639007 | INSULATOR RENEWAL - HAMILTON 2021 - PHASE 1 | 99 | COMPLETE | Estimate incorrect |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 163763.67 | 149176.6 | -14587.07 | -8.907% | 94782.07 | 76910.46 | -17871.61 | -18.86% | 39948.36 | 39813.71 | -134.65 | -0.3371% | 29033.24 | 32452.43 | 3419.19 | 11.78% | 0 | 0 | 0 |  | 991.19 | 958 | -33.19 | -3.349% | 2021-10-08 01:00
Hamilton | 2022 | 639010 | EMERGING OH INSULATOR REPLACEMENT 2022 - LAKE M4 | 99 | COMPLETE | Under 10% | Safety |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 106174.68 | 100409.5 | -5765.18 | -5.43% | 68010.08 | 53585.77 | -14424.31 | -21.21% | 16618.6 | 26861.73 | 10243.13 | 61.64% | 21546 | 19962 | -1584 | -7.352% | 0 | 0 | 0 |  | 567 | 655 | 88 | 15.52% | 2022-10-24 01:00
Hamilton | 2021 | 639013 | TX RENWAL PROGRAM - PHASE 12 - EAST 43RD ST - 1 | 99 | COMPLETE | Labour est. under | Cont Est Under |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 34416.16 | 46895.55 | 12479.39 | 36.26% | 18858.59 | 22634.85 | 3776.26 | 20.02% | 8855.05 | 7013.87 | -1841.18 | -20.79% | 4326.52 | 12164.33 | 7837.81 | 181.2% | 2376 | 5082.5 | 2706.5 | 113.9% | 160 | 271.5 | 111.5 | 69.69% | 2021-12-14 01:00
Hamilton | 2022 | 639014 | TX RENWAL PROGRAM 2021 - PHASE 13 - ORGAN CRES - 1 | 99 | COMPLETE | Vac truck |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 28606.15 | 24098.25 | -4507.9 | -15.76% | 15135.72 | 9248.74 | -5886.98 | -38.89% | 7723.31 | 6593.9 | -1129.41 | -14.62% | 3371.12 | 1616 | -1755.12 | -52.06% | 2376 | 6639.61 | 4263.61 | 179.4% | 120 | 108 | -12 | -10% | 2022-05-10 01:00
Hamilton | 2021 | 639015 | TX RENWAL PROGRAM 2021 - PHASE 14 - FERNWOOD CRES - 1 | 99 | COMPLETE | Estimate incorrect |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 30676.28 | 25596.72 | -5079.56 | -16.56% | 15874.37 | 12670.86 | -3203.51 | -20.18% | 8868.59 | 6529.49 | -2339.1 | -26.38% | 3557.32 | 5000.52 | 1443.2 | 40.57% | 2376 | 1395.85 | -980.15 | -41.25% | 120 | 128 | 8 | 6.667% | 2021-11-05 01:00
Hamilton | 2022 | 639016 | TX RENEWAL PROGRAM 2021 - PHASE 15 - EAST 45TH STREET - 1 | 99 | COMPLETE | Commodity Price | Estimate incorrect |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 34177.17 | 21200.61 | -12976.56 | -37.97% | 18684.72 | 12450.21 | -6234.51 | -33.37% | 8633.34 | 3036.32 | -5597.02 | -64.83% | 4483.11 | 3846.21 | -636.9 | -14.21% | 2376 | 1867.87 | -508.13 | -21.39% | 160 | 165.5 | 5.5 | 3.438% | 2022-05-04
Hamilton | 2022 | 639017 | TX RENEWAL PROGRAM 2021 - PHASE 16 - GRANDFIELD ST - 1 | 99 | COMPLETE | Labour est. under |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 25878.96 | 32407.96 | 6529 | 25.23% | 12869.89 | 16051.31 | 3181.42 | 24.72% | 7739.95 | 10824.27 | 3084.32 | 39.85% | 2893.12 | 4569 | 1675.88 | 57.93% | 2376 | 963.38 | -1412.62 | -59.45% | 100 | 186 | 86 | 86% | 2022-05-04
Hamilton | 2021 | 639022 | BALDWIN CARRY-OVER WORK 2021 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Karan, Andjelo | Brad Carr | 554071.86 | 609366.87 | 55295.01 | 9.98% | 2961.65 | 74701.18 | 71739.53 | 2422% | 61426.04 | 128675.02 | 67248.98 | 109.5% | 464 | 1558.61 | 1094.61 | 235.9% | 489220.17 | 404432.06 | -84788.11 | -17.33% | 29 | 74 | 45 | 155.2% | 2021-12-23 01:00
Hamilton | 2022 | 639064 | 90 GLOVER ROAD | 95 | COMPLETE | Commodity Price | Metering under | Labour est. under | Kappheim, Adam | No | Djuric, Zdravko | Roy Owen | 53095.47 | 62391.81 | 9296.34 | 17.51% | 17191.9 | 21176.97 | 3985.07 | 23.18% | 32221.53 | 41816.24 | 9594.71 | 29.78% | 2272.04 | 3154 | 881.96 | 38.82% | 6410 | 1244.6 | -5165.4 | -80.58% | 128 | 239 | 111 | 86.72% | 2022-04-20
Hamilton | 2021 | 639079 | 30 LOTTRIDGE ST / HAM / UP / 1PH SERV | 99 | COMPLETE | Labour est. under | N/A | N/A | Paesano, Andrew | No | Dragojevic, Igor | Macdougall, Stephen | 31657.69 | 30162.82 | -1494.87 | -4.722% | 18581.09 | 17382.72 | -1198.37 | -6.449% | 2600.34 | 3559.55 | 959.21 | 36.89% | 3963.86 | 5683 | 1719.14 | 43.37% | 6512.4 | 3537.55 | -2974.85 | -45.68% | 140 | 251.5 | 111.5 | 79.64% | 2021-02-26 01:00
Hamilton | 2022 | 639130 | 89 SUSSEX ST, HAMILTON - POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-08 01:00
Hamilton | 2021 | 639338 | HP95614 RELOCATE - WEST 5TH | 99 | COMPLETE | Cont Est Over |  |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 22931.86 | 18629.21 | -4302.65 | -18.76% | 4567.88 | 3322.8 | -1245.08 | -27.26% | 278.12 | 0 | -278.12 | -100% | 0 | 66 | 66 |  | 18085.86 | 15240.41 | -2845.45 | -15.73% | 0 | 3 | 3 |  | 2021-04-19
Hamilton | 2021 | 639360 | STREETLIGHT CONDUCTOR INSTALL - FIRST RD W | 99 | COMPLETE | Labour est. over |  |  | Jakubowski, Mark | No | Celic, Dusan | Koeppe, Jeffrey | 10883.85 | 4013.65 | -6870.2 | -63.12% | 8810.3 | 3521.65 | -5288.65 | -60.03% | 202.12 | 0 | -202.12 | -100% | 1871.43 | 492 | -1379.43 | -73.71% | 0 | 0 | 0 |  | 49.05 | 24 | -25.05 | -51.07% | 2021-03-11 01:00
Hamilton | 2021 | 639433 | MAPLE AVE / KENILWORTH TERM POLE | 98 | COMPLETE | Cont Est Over |  |  | Jakubowski, Mark | No | Jolie, Chris | Brad Carr | 148213.95 | 133212.08 | -15001.87 | -10.12% | 7346.55 | 10605.03 | 3258.48 | 44.35% | 21424.57 | 24609.51 | 3184.94 | 14.87% | 384 | 0 | -384 | -100% | 119058.83 | 97997.54 | -21061.29 | -17.69% | 24 | 2 | -22 | -91.67% | 2021-12-02 01:00
Hamilton | 2021 | 639492 | 83 CENTENNIAL PARKWAY SOUTH / STC / NS / 3PH PAD | 99 | COMPLETE | Cont Est Over |  |  | Kappheim, Adam | No | Djuric, Zdravko | Macdougall, Stephen | 66132.97 | 56890.3 | -9242.67 | -13.98% | 15018.44 | 11312.73 | -3705.71 | -24.67% | 39404.55 | 42259.62 | 2855.07 | 7.246% | 2413.34 | 2675 | 261.66 | 10.84% | 9296.64 | 642.95 | -8653.69 | -93.08% | 112 | 140.5 | 28.5 | 25.45% | 2021-08-13 01:00
Hamilton | 2021 | 639494 | JOINT USE PERMIT HW2020-149 - WOODWARD AND BRAMPTON - HAM | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Johnson, William | Brad Carr | 5345.12 | 5165.5 | -179.62 | -3.36% | 1369.67 | 1017.86 | -351.81 | -25.69% | 998.69 | 376.25 | -622.44 | -62.33% | 130.36 | 0 | -130.36 | -100% | 2846.4 | 3771.39 | 924.99 | 32.5% | 3.36 | 0 | -3.36 | -100% | 2021-08-30 01:00
Hamilton | 2021 | 639525 | 2021 EMERGING OH - EAST 16TH - BELL POLES | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Brad Carr | 86461.18 | 26084.92 | -60376.26 | -69.83% | 5867.41 | 1808.46 | -4058.95 | -69.18% | 12859.06 | 12543.35 | -315.71 | -2.455% | 523.02 | 88 | -435.02 | -83.17% | 67211.69 | 11645.11 | -55566.58 | -82.67% | 18.62 | 6 | -12.62 | -67.78% | 2021-03-03 01:00
Hamilton | 2021 | 639563 | ROGERS BONDS - 2020 BATCH 2 - HAM | 99 | COMPLETE | Estimate incorrect |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 4363.79 | 1482.64 | -2881.15 | -66.02% | 3798.81 | 1177.64 | -2621.17 | -69% | 0 | 0 | 0 |  | 564.98 | 305 | -259.98 | -46.02% | 0 | 0 | 0 |  | 16 | 16 | 0 | 0% | 2021-06-02 01:00
Hamilton | 2021 | 639581 | UPPER JAMES & LINC PMH SWITCH, 1 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Anderson, Dean | Brad Carr | 604557.24 | 605600.73 | 1043.49 | 0.1726% | 66329.96 | 59942.95 | -6387.01 | -9.629% | 302317.41 | 337646.86 | 35329.45 | 11.69% | 6866.56 | 2871.95 | -3994.61 | -58.17% | 229043.31 | 205138.97 | -23904.34 | -10.44% | 176 | 173 | -3 | -1.705% | 2021-11-02 01:00
Hamilton | 2021 | 639656 | 56 DUNDAS ST E PRIVATE LINE BURIAL | 99 | COMPLETE | Under 10% | N/A | N/A | Jakubowski, Mark | No | Jolie, Chris | Brad Carr | 68244.02 | 65545.36 | -2698.66 | -3.954% | 4448.12 | 7610.06 | 3161.94 | 71.08% | 14777.41 | 13633.07 | -1144.34 | -7.744% | 160 | 286 | 126 | 78.75% | 48858.49 | 44016.23 | -4842.26 | -9.911% | 10 | 15 | 5 | 50% | 2021-03-18 01:00
Hamilton | 2021 | 639670 | SC775 - MANUAL PMH 9 - 1 | 99 | COMPLETE | BOM not used |  |  | Beaudrie, Scott | No | Billone, Justin | Tony Ierace | 88668.39 | 88108.44 | -559.95 | -0.6315% | 15703.64 | 8870.88 | -6832.76 | -43.51% | 69972.75 | 77070.53 | 7097.78 | 10.14% | 2992 | 2167.03 | -824.97 | -27.57% | 0 | 0 | 0 |  | 112 | 97.5 | -14.5 | -12.95% | 2021-10-15 01:00
Hamilton | 2022 | 639714 | 90 GLOVER RD EXPANSION | 95 | COMPLETE | Estimate incorrect |  |  | Jakubowski, Mark | No | Jolie, Chris | Brad Carr | 620553.94 | 561999.48 | -58554.46 | -9.436% | 19390.87 | 47816.95 | 28426.08 | 146.6% | 110697.78 | 115501.44 | 4803.66 | 4.339% | 1504 | 1484 | -20 | -1.33% | 488961.29 | 397197.09 | -91764.2 | -18.77% | 94 | 69 | -25 | -26.6% | 2022-02-04 01:00
Hamilton | 2022 | 639719 | JOINT USE PERMIT HW2020-154 - RAMSEY, OFIELD, LWR HORNING, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 15297.27 | 8719.67 | -6577.6 | -43% | 2267.67 | 1094.02 | -1173.65 | -51.76% | 1048.45 | 262.21 | -786.24 | -74.99% | 367.24 | 0 | -367.24 | -100% | 11613.91 | 7363.44 | -4250.47 | -36.6% | 0 | 0 | 0 |  | 2022-01-31 01:00
Hamilton | 2021 | 639751 | 1 JARVIS - LINE RELOCATION | 99 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Jolie, Chris | Brad Carr | 167495.48 | 153500.22 | -13995.26 | -8.356% | 9917.5 | 16247.69 | 6330.19 | 63.83% | 31291.84 | 32746.39 | 1454.55 | 4.648% | 480 | 451 | -29 | -6.042% | 125806.14 | 104055.14 | -21751 | -17.29% | 30 | 32.5 | 2.5 | 8.333% | 2021-05-21 01:00
Hamilton | 2022 | 639786 | 2 BROCK ST SOUTH, DUNDAS - OH LINE ISOLATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-28 01:00
Hamilton | 2021 | 639859 | 139 PARKDALE AVE-PARKDALE ELEMENTARY UPGRADE/HAM/UP00087734/3PHPAD | 99 | COMPLETE | BOM not accurate | Cont Est Over |  | Frigotto, Rodrigo | No | Bharosi, Mohindra | Roy Owen | 77083.97 | 80756.12 | 3672.15 | 4.764% | 22408.56 | 22684.68 | 276.12 | 1.232% | 32976.9 | 26294.99 | -6681.91 | -20.26% | 2486.87 | 1377.5 | -1109.37 | -44.61% | 41561.64 | 30398.95 | -11162.69 | -26.86% | 112 | 134 | 22 | 19.64% | 2021-12-20 01:00
Hamilton | 2021 | 640051 | ROXBOROUGH PARK POLE LINE REMOVAL (HAMILTON) | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Karan, Andjelo | Brad Carr | 121464.67 | 127137.42 | 5672.75 | 4.67% | 1838.27 | 23561.87 | 21723.6 | 1182% | 16880.96 | 19678.58 | 2797.62 | 16.57% | 288 | 468.89 | 180.89 | 62.81% | 102457.44 | 83428.08 | -19029.36 | -18.57% | 18 | 14 | -4 | -22.22% | 2021-07-15 01:00
Hamilton | 2022 | 640102 | JOINT USE PERMIT HW2020-156 - MAIN N, HAMILTON N, WESLEY, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 11349.44 | 10172.96 | -1176.48 | -10.37% | 1859.8 | 1659.1 | -200.7 | -10.79% | 561.24 | 358.42 | -202.82 | -36.14% | 0 | 0 | 0 |  | 8928.4 | 8155.44 | -772.96 | -8.657% | 0 | 0 | 0 |  | 2022-02-07 01:00
Hamilton | 2021 | 640202 | 2021 - VOICE RADIO INTGR -TRANSITION/VOICE RADIO INTGR - DEWITT TOWER SERVICE | 95 | COMPLETE | N/A |  |  | Haid, Philip G. | No | Lustrinelli, Mark | Macdougall, Stephen | 11390.63 | 5935.55 | -5455.08 | -47.89% | 2710.52 | 2377.62 | -332.9 | -12.28% | 7803.18 | 1999.19 | -5803.99 | -74.38% | 876.93 | 1558.74 | 681.81 | 77.75% | 0 | 0 | 0 |  | 32 | 28 | -4 | -12.5% | 2021-05-28 01:00
Hamilton | 2022 | 640203 | 71 MAIN STREET/DUN/NS00101750/3PHPAD | 99 | COMPLETE | Under 10% |  |  | Frigotto, Rodrigo | No | Bharosi, Mohindra | Roy Owen | 81664.04 | 87120.46 | 5456.42 | 6.682% | 20052.63 | 25939.95 | 5887.32 | 29.36% | 41775.58 | 48668.21 | 6892.63 | 16.5% | 2529.83 | 2987 | 457.17 | 18.07% | 17306 | 9525.3 | -7780.7 | -44.96% | 102.48 | 142 | 39.52 | 38.56% | 2022-11-09 01:00
Hamilton | 2021 | 640253 | CUSTOMER INITIATED SERVICE UPGRADE - 8 TISDALE AVE S - HAMILTON | 99 | COMPLETE | BOM cost variance | BOM not accurate |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 111951.96 | 77762.88 | -34189.08 | -30.54% | 14524.44 | 17424.24 | 2899.8 | 19.96% | 40577.92 | 17682.25 | -22895.67 | -56.42% | 128 | 55 | -73 | -57.03% | 56721.6 | 42601.39 | -14120.21 | -24.89% | 8 | 2.5 | -5.5 | -68.75% | 2021-12-10 01:00
Hamilton | 2022 | 640268 | JOINT USE PERMIT HW2021-003 - YORK, WILMAR, SLEEPY HOLLOW, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 15536.54 | 10275.47 | -5261.07 | -33.86% | 1526.96 | 1352.76 | -174.2 | -11.41% | 662.25 | 443.19 | -219.06 | -33.08% | 0 | 0 | 0 |  | 13347.33 | 8479.52 | -4867.81 | -36.47% | 0 | 0 | 0 |  | 2022-01-31 01:00
Hamilton | 2022 | 640315 | JOINT USE PERMIT HW2021-004 - NAPIER N, HATT, MATILDA N, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 12571.18 | 9712.58 | -2858.6 | -22.74% | 1617.55 | 1459.97 | -157.58 | -9.742% | 280.63 | 72.61 | -208.02 | -74.13% | 0 | 0 | 0 |  | 10673 | 8180 | -2493 | -23.36% | 0 | 0 | 0 |  | 2022-01-31 01:00
Hamilton | 2022 | 640316 | JOINT USE PERMIT HW2021-005 - BOND N, BOND S, JAMES, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 14286.52 | 10637.96 | -3648.56 | -25.54% | 2091.86 | 1523.97 | -567.89 | -27.15% | 1008.35 | 610.99 | -397.36 | -39.41% | 132.41 | 0 | -132.41 | -100% | 11053.9 | 8503 | -2550.9 | -23.08% | 3.15 | 0 | -3.15 | -100% | 2022-01-31 01:00
Hamilton | 2021 | 640444 | GAGE & BEECHWOOD TX RELOCATION | 99 | COMPLETE | Commodity Price |  |  | Beaudrie, Scott | No | Karan, Andjelo | Koeppe, Jeffrey | 11318.58 | 7007.68 | -4310.9 | -38.09% | 5019.99 | 4945.23 | -74.76 | -1.489% | 4794.94 | 598.75 | -4196.19 | -87.51% | 1503.65 | 1463.7 | -39.95 | -2.657% | 0 | 0 | 0 |  | 46.15 | 31 | -15.15 | -32.83% | 2021-11-19 01:00
Hamilton | 2021 | 640459 | CITY OF HAMILTON - GRANT BLVD, TX UPGRADE | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7.5 | 7.5 |  | 2022-04-07
Hamilton | 2022 | 640559 | FOOTHILLS OF WINONA PHASE 3 - SUBD RES EDS | 99 | COMPLETE | Under 10% |  |  | Velickovski, Goran | No | Morris, Mark | Roy Owen | 396133.41 | 395689.5 | -443.91 | -0.1121% | 70719.5 | 63423.91 | -7295.59 | -10.32% | 4777.62 | 5828.18 | 1050.56 | 21.99% | 5271.29 | 4592 | -679.29 | -12.89% | 315365 | 321845.41 | 6480.41 | 2.055% | 197.99 | 278 | 80.01 | 40.41% | 2022-11-23 01:00
Hamilton | 2021 | 640629 | AUTO SWITCH INSTALLS - DUNDAS TS - PHASE 2, 3 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Brad Carr | 219274.41 | 241656.74 | 22382.33 | 10.21% | 19601.67 | 35620.46 | 16018.79 | 81.72% | 129916.84 | 142468.71 | 12551.87 | 9.661% | 2304 | 5908.65 | 3604.65 | 156.5% | 67451.9 | 57658.92 | -9792.98 | -14.52% | 144 | 233.5 | 89.5 | 62.15% | 2021-11-26 01:00
Hamilton | 2022 | 640639 | 191 KING STREET WEST - TEMP SERVICE | 99 | COMPLETE | Labour est. under |  |  | Kappheim, Adam | No | Sabbah, Amir | Roy Owen | 27679.74 | 41212.21 | 13532.47 | 48.89% | 6394.94 | 15772.85 | 9377.91 | 146.6% | 11549.71 | 13367.56 | 1817.85 | 15.74% | 1040.01 | 4020.5 | 2980.49 | 286.6% | 8695.08 | 8051.3 | -643.78 | -7.404% | 58 | 215.5 | 157.5 | 271.6% | 2022-11-14 01:00
Hamilton | 2021 | 640725 | JOINT USE PERMIT HW2021-017 - TEAL, FRANCES, AND CHURCH - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 8000.55 | 5824.52 | -2176.03 | -27.2% | 1114.65 | 862.83 | -251.82 | -22.59% | 653.04 | 272.79 | -380.25 | -58.23% | 122.22 | 0 | -122.22 | -100% | 6110.64 | 4688.9 | -1421.74 | -23.27% | 3.15 | 0 | -3.15 | -100% | 2021-08-13 01:00
Hamilton | 2021 | 640742 | ROAD AUTHORITY RELOCATION - STRACHAN ST E - ANCHOR RELOCATE | 99 | COMPLETE | Vac truck |  |  | Jakubowski, Mark | No | Celic, Dusan | Koeppe, Jeffrey | 13218.56 | 8860.49 | -4358.07 | -32.97% | 7713.84 | 5034.88 | -2678.96 | -34.73% | 738.92 | 1129.63 | 390.71 | 52.88% | 1687.8 | 984 | -703.8 | -41.7% | 3078 | 1711.98 | -1366.02 | -44.38% | 52.2 | 48 | -4.2 | -8.046% | 2021-07-02 01:00
Hamilton | 2021 | 640772 | 2021 - MH 39A - MANHOLE ROOF REPLACEMENT | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Brad Carr | 158562.63 | 191440.49 | 32877.86 | 20.73% | 26049.92 | 36383.06 | 10333.14 | 39.67% | 0 | 0 | 0 |  | 576 | 839.57 | 263.57 | 45.76% | 131936.71 | 154217.86 | 22281.15 | 16.89% | 36 | 26 | -10 | -27.78% | 2021-12-10 01:00
Hamilton | 2022 | 640795 | CHAMBER LID REPLACEMENTS- 2022- PHASE 1 | 95 | COMPLETE | Cont Est Under |  |  | Beaudrie, Scott | No | Wardell, Paul | Brad Carr | 93617.17 | 123634.55 | 30017.38 | 32.06% | 21962.56 | 27193.98 | 5231.42 | 23.82% | 1597.38 | 2568.71 | 971.33 | 60.81% | 0 | 278.8 | 278.8 |  | 70057.23 | 93593.06 | 23535.83 | 33.6% | 26 | 14 | -12 | -46.15% | 2022-12-14 01:00
Hamilton | 2022 | 640808 | JOINT USE PERMIT HW2021-025 - MARION N AND DROMORE - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 10997.16 | 8070.51 | -2926.65 | -26.61% | 1889.79 | 1306.87 | -582.92 | -30.85% | 446.96 | 203.64 | -243.32 | -54.44% | 132.41 | 0 | -132.41 | -100% | 8528 | 6560 | -1968 | -23.08% | 3.15 | 0 | -3.15 | -100% | 2022-01-31 01:00
Hamilton | 2022 | 640834 | 380 MCNEILLY RD/HAM/NS/NS00106348/3PHPAD | 95 | ANALYZE |  |  |  | Frigotto, Rodrigo | No | Bharosi, Mohindra | Roy Owen | 243989.2 | 223474.43 | -20514.77 | -8.408% | 59509.25 | 62206.87 | 2697.62 | 4.533% | 125549.09 | 103183.33 | -22365.76 | -17.81% | 11896.86 | 15113 | 3216.14 | 27.03% | 47034 | 42971.23 | -4062.77 | -8.638% | 424.8 | 560 | 135.2 | 31.83% | 2022-08-26 01:00
Hamilton | 2022 | 640847 | 40 ZINFANDAL DR - SUBD RES EDS | 95 | ANALYZE |  |  |  | Velickovski, Goran | No | Morris, Mark | Roy Owen | 197634 | 199355.74 | 1721.74 | 0.8712% | 34924.9 | 31963.1 | -2961.8 | -8.48% | 85.84 | 285.64 | 199.8 | 232.8% | 2565.26 | 1949 | -616.26 | -24.02% | 160058 | 165158 | 5100 | 3.186% | 102.78 | 116.5 | 13.72 | 13.35% | 2023-02-02 01:00
Hamilton | 2021 | 640868 | 2021 POLE REPLACMENT - BATCH 1 - 6 | 99 | COMPLETE | Estimate incorrect | Cont Est Over |  | Beaudrie, Scott | No | Webb-Murre, Paige | Koeppe, Jeffrey | 65240.37 | 43735 | -21505.37 | -32.96% | 32253.68 | 22807.88 | -9445.8 | -29.29% | 6567.29 | 5096.98 | -1470.31 | -22.39% | 8599.4 | 9458.59 | 859.19 | 9.991% | 17820 | 6371.55 | -11448.45 | -64.24% | 264.28 | 227.5 | -36.78 | -13.92% | 2021-11-10 01:00
Hamilton | 2022 | 640884 | CUSTOMER INITIATED EXPANSION - ROXBOROUGH PARK INC. DEVELOPMENT - QUEENSTON RD | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Celic, Dusan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-23 01:00
Hamilton | 2021 | 640898 | JOINT USE PERMIT HW2021-031 - CLAPHAM RD - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 8671.86 | 6637.1 | -2034.76 | -23.46% | 1578.97 | 1394.36 | -184.61 | -11.69% | 665.78 | 553.84 | -111.94 | -16.81% | 260.74 | 0 | -260.74 | -100% | 6166.37 | 4688.9 | -1477.47 | -23.96% | 6.72 | 2 | -4.72 | -70.24% | 2021-08-13 01:00
Hamilton | 2022 | 640903 | 280 EASTPORT DR - BELL MOBILITY COMM TOWER | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Jolie, Chris | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-10 01:00
Hamilton | 2022 | 640926 | 1 JARVIS ST - TEMP | 99 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Bennett, Aaron | Roy Owen | 46593.51 | 43542.92 | -3050.59 | -6.547% | 11482.98 | 10801.99 | -680.99 | -5.93% | 33606.09 | 31416.93 | -2189.16 | -6.514% | 1504.44 | 1324 | -180.44 | -11.99% | 0 | 0 | 0 |  | 90.89 | 107 | 16.11 | 17.72% | 2022-11-14 01:00
Hamilton | 2021 | 640984 | 60 WOODLEY'S LANE - BELL POLE REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Brad Carr | 20803.14 | 21899.19 | 1096.05 | 5.269% | 1863.36 | -11608.35 | -13471.71 | -723% | 2212.74 | 2674.98 | 462.24 | 20.89% | 0 | 44 | 44 |  | 16727.04 | 30788.56 | 14061.52 | 84.06% | 4 | 2 | -2 | -50% | 2021-04-01 01:00
Hamilton | 2021 | 641032 | SC752 AREA - NEW AB TRANSFORMERS | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Tony Ierace | 87999.9 | 79554.53 | -8445.37 | -9.597% | 28147.81 | 22109.54 | -6038.27 | -21.45% | 21157.41 | 17463.4 | -3694.01 | -17.46% | 14549.68 | 5596.59 | -8953.09 | -61.53% | 24145 | 13010 | -11135 | -46.12% | 188 | 167 | -21 | -11.17% | 2021-12-20 01:00
Hamilton | 2022 | 641067 | MIDTOWN - SUBD RES EDS | 95 | COMPLETE | Under 10% |  |  | Velickovski, Goran | No | Morris, Mark | Roy Owen | 778884.16 | 779928.67 | 1044.51 | 0.1341% | 113003.19 | 103422.54 | -9580.65 | -8.478% | 85.84 | 4259.13 | 4173.29 | 4862% | 4616.13 | 4436 | -180.13 | -3.902% | 661179 | 667811 | 6632 | 1.003% | 219.7733 | 222.75 | 2.9767 | 1.354% | 2022-12-20 01:00
Hamilton | 2021 | 641096 | ROAD AUTHORITY RELOCATION - ANCHOR RELOCATE - KESWICK CRT | 99 | COMPLETE | Labour est. over |  |  | Jakubowski, Mark | No | Celic, Dusan | Koeppe, Jeffrey | 25297.85 | 12594.03 | -12703.82 | -50.22% | 15235.68 | 7060.8 | -8174.88 | -53.66% | 2519.54 | 2269.48 | -250.06 | -9.925% | 3142.63 | 0 | -3142.63 | -100% | 4400 | 3263.75 | -1136.25 | -25.82% | 96.21 | 40 | -56.21 | -58.42% | 2021-09-27 01:00
Hamilton | 2022 | 641138 | JOINT USE PERMIT HW2021-044 - BEACH - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 7843.61 | 7561.33 | -282.28 | -3.599% | 1689.33 | 1197.2 | -492.13 | -29.13% | 360.64 | 278.68 | -81.96 | -22.73% | 141.24 | 0 | -141.24 | -100% | 5652.4 | 6085.45 | 433.05 | 7.661% | 3.36 | 0 | -3.36 | -100% | 2021-11-08 01:00
Hamilton | 2022 | 641159 | V63 & V64 VAULT LID REPLACEMENT | 99 | COMPLETE | Material Req incorrectly |  |  | Jakubowski, Mark | Yes | Celic, Dusan | Brad Carr | 29763.85 | 36620.47 | 6856.62 | 23.04% | 783.28 | 5547.22 | 4763.94 | 608.2% | 13288.17 | 10060.25 | -3227.92 | -24.29% | 0 | 0 | 0 |  | 15692.4 | 21013 | 5320.6 | 33.91% | 0 | 0 | 0 |  | 2022-03-28
Hamilton | 2022 | 641164 | CHERYL AVE MINI REBUILD (HAMILTON - 11 | 95 | COMPLETE | Under 10% | Material Under Estimated |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 200588.56 | 192675.76 | -7912.8 | -3.945% | 4637.43 | 22699.96 | 18062.53 | 389.5% | 33654.17 | 52611.91 | 18957.74 | 56.33% | 0 | 381.17 | 381.17 |  | 162296.96 | 116982.72 | -45314.24 | -27.92% | 20 | 21 | 1 | 5% | 2022-10-25 01:00
Hamilton | 2022 | 641174 | JOINT USE PERMIT HW2021-046 - SCENIC, LESLIE, W28, PRICE - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 16433.33 | 12029 | -4404.33 | -26.8% | 2236.39 | 1898.17 | -338.22 | -15.12% | 561.24 | 291.83 | -269.41 | -48% | 0 | 0 | 0 |  | 13635.7 | 9839 | -3796.7 | -27.84% | 0 | 0 | 0 |  | 2022-01-31 01:00
Hamilton | 2021 | 641175 | 90 RIDGE STREET - SERVICE TO BE MOVED AWAY FROM FUTURE POOL | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Wardell, Paul | Macdougall, Stephen | 20616.93 | 16270.4 | -4346.53 | -21.08% | 7760.47 | 5371.77 | -2388.7 | -30.78% | 851.77 | 306.28 | -545.49 | -64.04% | 778.09 | 405.53 | -372.56 | -47.88% | 11226.6 | 10186.82 | -1039.78 | -9.262% | 28.05 | 12 | -16.05 | -57.22% | 2021-07-26 01:00
Hamilton | 2021 | 641176 | 352 INVERNESS - REPLACE EXISTING ANCHORS | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Wardell, Paul | Brad Carr | 7453.43 | 6960.52 | -492.91 | -6.613% | 2873.82 | 3785.78 | 911.96 | 31.73% | 222.61 | 220.44 | -2.17 | -0.9748% | 0 | 202.76 | 202.76 |  | 4357 | 2751.54 | -1605.46 | -36.85% | 1 | 8 | 7 | 700% | 2021-09-13 01:00
Hamilton | 2022 | 641177 | 173 CLINE - ANCHOR REPLACEMENT | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Wardell, Paul | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-29 01:00
Hamilton | 2022 | 641224 | JOINT USE PERMIT HW2021-053 - NARDI, POTTRUFF S, CHERRY, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 8551.51 | 6821.8 | -1729.71 | -20.23% | 1321.15 | 1227.23 | -93.92 | -7.109% | 262.36 | 234.57 | -27.79 | -10.59% | 0 | 0 | 0 |  | 6968 | 5360 | -1608 | -23.08% | 0 | 0 | 0 |  | 2022-01-31 01:00
Hamilton | 2021 | 641256 | 2021 - TX RENEWAL - WENTWORTH ST - 1 TX | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Brad Carr | 56074.97 | 38198.93 | -17876.04 | -31.88% | 1778.72 | 3915.95 | 2137.23 | 120.2% | 6275.13 | 3539.36 | -2735.77 | -43.6% | 0 | 0 | 0 |  | 48021.12 | 30743.62 | -17277.5 | -35.98% | 4 | 0 | -4 | -100% | 2021-08-20 01:00
Hamilton | 2021 | 641275 | 259 MAGNOLIA DRIVE - MANHOLE LID REPAIR | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Anderson, Dean | Brad Carr | 65055.91 | 49971.08 | -15084.83 | -23.19% | 5151.43 | 7367.8 | 2216.37 | 43.02% | 3472.76 | 3446.41 | -26.35 | -0.7588% | 586 | 418.2 | -167.8 | -28.63% | 55845.72 | 38738.67 | -17107.05 | -30.63% | 41 | 16 | -25 | -60.98% | 2021-10-29 01:00
Hamilton | 2022 | 641298 | 85 POULETTE ST - SUBD RES EDS | 99 | COMPLETE | Labour est. over | BOM – truck stock |  | Velickovski, Goran | No | Morris, Mark | Macdougall, Stephen | 50239.11 | 140717.43 | 90478.32 | 180.1% | 33092.94 | 12108.81 | -20984.13 | -63.41% | 4331.37 | 1407.31 | -2924.06 | -67.51% | 2814.8 | 2310 | -504.8 | -17.93% | 10000 | 57.65 | -9942.35 | -99.42% | 120.04 | 90.25 | -29.79 | -24.82% | 2022-09-24 01:00
Hamilton | 2021 | 641328 | 41 GREAT FALLS BLVD - SUBD CAP PROJ | 99 | COMPLETE | Cont Est Over |  |  | Gamboa, Henry | No | Morris, Mark | Roy Owen | 29863.15 | 23787.08 | -6076.07 | -20.35% | 10734.3 | 8919.44 | -1814.86 | -16.91% | 70.87 | 212.64 | 141.77 | 200% | 1485.3 | 634 | -851.3 | -57.32% | 17572.68 | 14021 | -3551.68 | -20.21% | 64 | 68 | 4 | 6.25% | 2021-09-01 01:00
Hamilton | 2021 | 641379 | 55 1/2 ROCKCLIFFE ROAD - UG SERVICE TO BE RELOCATED | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Wardell, Paul | Roy Owen | 28327.65 | 30407.32 | 2079.67 | 7.341% | 4968.58 | 8923.23 | 3954.65 | 79.59% | 1350.6 | 290.88 | -1059.72 | -78.46% | 601.55 | 796.8 | 195.25 | 32.46% | 21406.92 | 20396.41 | -1010.51 | -4.72% | 29.45 | 26 | -3.45 | -11.71% | 2021-06-11 01:00
Hamilton | 2022 | 641401 | JOINT USE PERMIT HW2021-056 - TROY, DUNN, GRACE, GLOW, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 16611.59 | 11919.35 | -4692.24 | -28.25% | 2338.81 | 1438.53 | -900.28 | -38.49% | 360.64 | 278.68 | -81.96 | -22.73% | 141.24 | 0 | -141.24 | -100% | 13770.9 | 10202.14 | -3568.76 | -25.92% | 3.36 | 0 | -3.36 | -100% | 2022-01-31 01:00
Hamilton | 2021 | 641446 | 20 EAST AVENUE SOUTH - REMOVAL | 99 | COMPLETE | Labour est. over |  |  | Kappheim, Adam | No | Djuric, Zdravko | Roy Owen | 7964.18 | 5848.06 | -2116.12 | -26.57% | 6538.73 | 4296.98 | -2241.75 | -34.28% | 529.45 | 1037.58 | 508.13 | 95.97% | 896 | 513.5 | -382.5 | -42.69% | 0 | 0 | 0 |  | 56 | 43 | -13 | -23.21% | 2021-05-31 01:00
Hamilton | 2022 | 641473 | SUMMIT PARK PHASE 11A - SUBD RES EDS | 95 | COMPLETE | Estimate incorrect | Cont Est Over | Labour est. over | Gamboa, Henry | No | Morris, Mark | Roy Owen | 548339 | 614613.53 | 66274.53 | 12.09% | 14499.68 | 73665.09 | 59165.41 | 408% | 0 | 724.94 | 724.94 |  | 3304.32 | 2438.5 | -865.82 | -26.2% | 530535 | 537785 | 7250 | 1.367% | 139.92 | 125 | -14.92 | -10.66% | 2022-09-21 01:00
Hamilton | 2022 | 641479 | JOINT USE PERMIT HW2021-062 - GARSIDE S, NORMANDY, BARON S - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 11756.79 | 8826.25 | -2930.54 | -24.93% | 1910.76 | 1642.01 | -268.75 | -14.07% | 280.63 | 308.25 | 27.62 | 9.842% | 0 | 0 | 0 |  | 9565.4 | 6875.99 | -2689.41 | -28.12% | 0 | 0 | 0 |  | 2022-04-11
Hamilton | 2022 | 641480 | JOINT USE PERMIT HW2021-063 - ALMA, PARKSIDE, AND SYDENHAM - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 8700.87 | 7969.63 | -731.24 | -8.404% | 1924.54 | 1474.71 | -449.83 | -23.37% | 471.89 | 224.49 | -247.4 | -52.43% | 143.64 | 0 | -143.64 | -100% | 6160.8 | 6270.43 | 109.63 | 1.779% | 3.15 | 2 | -1.15 | -36.51% | 2022-03-14 01:00
Hamilton | 2021 | 641523 | 672 ARVIN AVE / HAM / NS / 3PH PAD | 99 | COMPLETE | Estimate incorrect |  |  | Frigotto, Rodrigo | No | Dragojevic, Igor | Macdougall, Stephen | 73029.83 | 65179.67 | -7850.16 | -10.75% | 29279.7 | 23068.05 | -6211.65 | -21.21% | 29853.46 | 29405.62 | -447.84 | -1.5% | 5855.67 | 5330 | -525.67 | -8.977% | 8041 | 7376 | -665 | -8.27% | 208.07 | 220 | 11.93 | 5.734% | 2021-11-05 01:00
Hamilton | 2021 | 641526 | 124 ELEANOR AVE - AERIAL TRESPASS | 99 | COMPLETE | BOM – truck stock |  |  | Beaudrie, Scott | No | Anderson, Dean | Koeppe, Jeffrey | 11649.11 | 7672.32 | -3976.79 | -34.14% | 5840.56 | 3544.04 | -2296.52 | -39.32% | 2145.66 | 1334 | -811.66 | -37.83% | 1286.89 | 595.62 | -691.27 | -53.72% | 2376 | 2198.66 | -177.34 | -7.464% | 39.11 | 40 | 0.89 | 2.276% | 2021-07-06 01:00
Hamilton | 2021 | 641597 | AUTO SW - HWY 5_WEST OF HWY 6, 1 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Koeppe, Jeffrey | 66096.68 | 68772.2 | 2675.52 | 4.048% | 19202.25 | 20510.85 | 1308.6 | 6.815% | 42624.45 | 40043.1 | -2581.35 | -6.056% | 4269.98 | 8218.25 | 3948.27 | 92.47% | 0 | 0 | 0 |  | 156.02 | 215.5 | 59.48 | 38.12% | 2021-07-23 01:00
Hamilton | 2021 | 641611 | 75 JAMES ST S & 44 HUGHSON ST S/ HAM / UP00118548 / 3PH CUST OWNED SUB TEMP SRVC | 99 | COMPLETE | Labour est. under | Cont Est Over |  | Frigotto, Rodrigo | No | Laus, Tomislav | Roy Owen | 36219.61 | 40853.65 | 4634.04 | 12.79% | 13139.58 | 23138.17 | 9998.59 | 76.1% | 10193.57 | 7402.12 | -2791.45 | -27.38% | 1387.7 | 4570 | 3182.3 | 229.3% | 11498.76 | 5743.36 | -5755.4 | -50.05% | 64.45 | 292 | 227.55 | 353.1% | 2021-12-22 01:00
Hamilton | 2022 | 641621 | JOINT USE PERMIT HW2021-067 - ST JOSEPHS, ARKLEDUN, KINGSWAY - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 9408.14 | 7856.22 | -1551.92 | -16.5% | 1404.04 | 1319.7 | -84.34 | -6.007% | 0 | 379.52 | 379.52 |  | 0 | 0 | 0 |  | 8004.1 | 6157 | -1847.1 | -23.08% | 0 | 0 | 0 |  | 2022-04-11
Hamilton | 2022 | 641652 | JOINT USE PERMIT HW2021-071 - HEAD, MILL, MERCER, ETC - HAM | 95 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 12116.75 | 8916.41 | -3200.34 | -26.41% | 1934.89 | 1697.27 | -237.62 | -12.28% | 314.86 | 279.14 | -35.72 | -11.34% | 0 | 0 | 0 |  | 9867 | 6940 | -2927 | -29.66% | 0 | 0 | 0 |  | 2022-04-11
Hamilton | 2022 | 641653 | JOINT USE PERMIT HW2021-072 - BARTON EAST - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 7843.61 | 5115.35 | -2728.26 | -34.78% | 1689.33 | 934.53 | -754.8 | -44.68% | 360.64 | 278.68 | -81.96 | -22.73% | 141.24 | 0 | -141.24 | -100% | 5652.4 | 3902.14 | -1750.26 | -30.96% | 3.36 | 0 | -3.36 | -100% | 2021-11-08 01:00
Hamilton | 2022 | 641690 | BARNABY ST - POLE RENEWAL - 7 | 99 | COMPLETE | Vac truck | BOM cost variance |  | Beaudrie, Scott | Yes | Billone, Justin | Koeppe, Jeffrey | 110165.12 | 117122.49 | 6957.37 | 6.315% | 72996.76 | 62964.27 | -10032.49 | -13.74% | 10237.41 | 17641.01 | 7403.6 | 72.32% | 19430.95 | 22343.79 | 2912.84 | 14.99% | 7500 | 14173.42 | 6673.42 | 88.98% | 599.54 | 681 | 81.46 | 13.59% | 2022-12-09 01:00
Hamilton | 2022 | 641699 | 31 SUNRISE CRES (DUNDAS) NEW SEC DUCT | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Karan, Andjelo | Brad Carr | 31531.35 | 31782.28 | 250.93 | 0.7958% | 6533.78 | 7163.72 | 629.94 | 9.641% | 847.57 | 0 | -847.57 | -100% | 0 | 468.89 | 468.89 |  | 24150 | 24149.67 | -0.33 | -0.001366% | 0 | 32 | 32 |  | 2022-07-11 01:00
Hamilton | 2021 | 641723 | 360 WENTWORTH STREET NORTH - GUY WIRE RELOCATION | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Wardell, Paul | Brad Carr | 152910.75 | 132129.86 | -20780.89 | -13.59% | 22347.68 | 28092.84 | 5745.16 | 25.71% | 30006.07 | 30205.69 | 199.62 | 0.6653% | 0 | 0 | 0 |  | 100557 | 73831.33 | -26725.67 | -26.58% | 14 | 0 | -14 | -100% | 2021-12-10 01:00
Hamilton | 2021 | 641724 | 743 GREEN MOUNTAIN ROAD POLE REPLACEMENT | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Karan, Andjelo | Koeppe, Jeffrey | 7632.5 | 9386.12 | 1753.62 | 22.98% | 5226.46 | 4255.69 | -970.77 | -18.57% | 829.96 | 775.7 | -54.26 | -6.538% | 1576.08 | 1609.43 | 33.35 | 2.116% | 0 | 2745.3 | 2745.3 |  | 47.76 | 32 | -15.76 | -33% | 2021-11-05 01:00
Hamilton | 2022 | 641735 | JOINT USE PERMIT HW2021-074 - RED OAK AND MARGARET - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 8962.64 | 6014.03 | -2948.61 | -32.9% | 2282.4 | 1307.66 | -974.74 | -42.71% | 943.76 | 235.74 | -708.02 | -75.02% | 287.28 | 0 | -287.28 | -100% | 5449.2 | 4470.63 | -978.57 | -17.96% | 6.3 | 0 | -6.3 | -100% | 2022-03-14 01:00
Hamilton | 2022 | 641736 | JOINT USE PERMIT HW2021-075 - BUCKINGHAM, SANDRINGHAM, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 24252.22 | 19904.64 | -4347.58 | -17.93% | 3644.67 | 2603.54 | -1041.13 | -28.57% | 1003.08 | 700.65 | -302.43 | -30.15% | 331.97 | 0 | -331.97 | -100% | 19272.5 | 16600.45 | -2672.05 | -13.86% | 6.72 | 0 | -6.72 | -100% | 2022-01-31 01:00
Hamilton | 2021 | 641771 | 281 WINONA ROAD POLE REPLACEMENT | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Karan, Andjelo | Koeppe, Jeffrey | 17641.02 | 11141.26 | -6499.76 | -36.84% | 10628.92 | 4891.66 | -5737.26 | -53.98% | 1659.94 | 1596.37 | -63.57 | -3.83% | 3152.16 | 2458.51 | -693.65 | -22.01% | 2200 | 2194.72 | -5.28 | -0.24% | 95.52 | 40 | -55.52 | -58.12% | 2021-11-19 01:00
Hamilton | 2022 | 641834 | 20 EAST AVENUE SOUTH / HAM / NS / 3PH PAD | 95 | ANALYZE |  |  |  | Kappheim, Adam | No | Djuric, Zdravko | Roy Owen | 54007.01 | 86680.91 | 32673.9 | 60.5% | 25981.9 | 28127.24 | 2145.34 | 8.257% | 11519.11 | 19786.69 | 8267.58 | 71.77% | 4092 | 2717 | -1375 | -33.6% | 12414 | 36049.98 | 23635.98 | 190.4% | 188 | 226.5 | 38.5 | 20.48% | 2023-01-12 01:00
Hamilton | 2022 | 641844 | 10 MULBERRY ST POLE REPLACEMENT | 99 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Jolie, Chris | Macdougall, Stephen | 35947.8 | 34243.39 | -1704.41 | -4.741% | 22098.96 | 18130.74 | -3968.22 | -17.96% | 5509.62 | 7767.6 | 2257.98 | 40.98% | 6017.22 | 6914 | 896.78 | 14.9% | 2322 | 1431.05 | -890.95 | -38.37% | 183.89 | 200 | 16.11 | 8.761% | 2022-05-31 01:00
Hamilton | 2022 | 641963 | JOINT USE PERMIT HW2021-083 - MILANO, GUILDWOOD, ADIS, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 26472.65 | 18150.4 | -8322.25 | -31.44% | 4818.05 | 2299.99 | -2518.06 | -52.26% | 2460.5 | 551.41 | -1909.09 | -77.59% | 919.3 | 0 | -919.3 | -100% | 18274.8 | 15299 | -2975.8 | -16.28% | 20.16 | 0 | -20.16 | -100% | 2022-03-14 01:00
Hamilton | 2022 | 641988 | JOINT USE PERMIT HW2019-061 - LOWDEN AVE - BELL:Y77217 - HAM | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 24441.92 | 15277.66 | -9164.26 | -37.49% | 3214.23 | 2268.96 | -945.27 | -29.41% | 1594.59 | 2589.87 | 995.28 | 62.42% | 166.66 | 0 | -166.66 | -100% | 19466.44 | 10418.83 | -9047.61 | -46.48% | 3.36 | 0 | -3.36 | -100% | 2022-02-12 01:00
Hamilton | 2021 | 641999 | 290 GREEN MOUNTAIN RD E | 99 | COMPLETE | BOM not accurate | BOM – truck stock |  | Frigotto, Rodrigo | No | Bennett, Aaron | Roy Owen | 47524.32 | 44679.58 | -2844.74 | -5.986% | 15351.04 | 15556.55 | 205.51 | 1.339% | 15235.03 | 12210.53 | -3024.5 | -19.85% | 2627.25 | 3286 | 658.75 | 25.07% | 14311 | 13626.5 | -684.5 | -4.783% | 111.73 | 160.5 | 48.77 | 43.65% | 2021-11-30 01:00
Hamilton | 2021 | 642033 | WINONA RD POLE RELOCATIONS (SOUTH OF BASELINE ROAD) HAMILTON | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Karan, Andjelo | Brad Carr | 152110.56 | 129194.98 | -22915.58 | -15.07% | 16064.57 | 17436.21 | 1371.64 | 8.538% | 26083.15 | 29373.87 | 3290.72 | 12.62% | 288 | 0 | -288 | -100% | 109674.84 | 82384.9 | -27289.94 | -24.88% | 18 | 2 | -16 | -88.89% | 2021-12-10 01:00
Hamilton | 2022 | 642054 | 18 AUGUSTA ST / HAM / NS00131456 / 1500KVA 3PH COMMERCIAL SERVICE | 99 | COMPLETE | Under 10% |  |  | Frigotto, Rodrigo | No | Laus, Tomislav | Roy Owen | 93781.2 | 91445.9 | -2335.3 | -2.49% | 18021.78 | 17998.14 | -23.64 | -0.1312% | 50060.72 | 46123.2 | -3937.52 | -7.865% | 1387.7 | 2424 | 1036.3 | 74.68% | 24311 | 24900.56 | 589.56 | 2.425% | 107.45 | 122 | 14.55 | 13.54% | 2022-03-21 01:00
Hamilton | 2022 | 642060 | OH AUTO SWITCHES (DA) 2022 - PART 1 - 6 | 99 | COMPLETE | Vac truck |  |  | Beaudrie, Scott | Yes | Billone, Justin | Koeppe, Jeffrey | 439669.2 | 500067.35 | 60398.15 | 13.74% | 107891.05 | 120531.06 | 12640.01 | 11.72% | 302504.82 | 320621.86 | 18117.04 | 5.989% | 29273.33 | 46138.5 | 16865.17 | 57.61% | 0 | 12775.93 | 12775.93 |  | 935.67 | 1477 | 541.33 | 57.85% | 2022-05-31 01:00
Hamilton | 2022 | 642061 | OH AUTO SWITCHES (DA) 2022 - PART 2 - 4 | 98 | COMPLETE | Under 10% | Vac truck |  | Beaudrie, Scott | Yes | Billone, Justin | Koeppe, Jeffrey | 406574.77 | 391909.04 | -14665.73 | -3.607% | 113521.08 | 97272.36 | -16248.72 | -14.31% | 266142.27 | 253961.93 | -12180.34 | -4.577% | 26911.42 | 22953.89 | -3957.53 | -14.71% | 0 | 17720.86 | 17720.86 |  | 950.59 | 946.5 | -4.09 | -0.4303% | 2022-12-09 01:00
Hamilton | 2022 | 642168 | CUSTOMER INITIATED EXPANSION - ROXBOROUGH PARK, REID AVE NORTH - HAMILTON | 92 | ACTIVE |  |  |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 534472.53 | 523884.6 | -10587.93 | -1.981% | 61335.67 | 64892.74 | 3557.07 | 5.799% | 116075.95 | 147441.49 | 31365.54 | 27.02% | 1026 | 1014 | -12 | -1.17% | 356034.91 | 310536.37 | -45498.54 | -12.78% | 54 | 43 | -11 | -20.37% | 2022-11-08 01:00
Hamilton | 2021 | 642173 | WILD LIFE MITIGATION (HAMILTON) | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Karan, Andjelo | Koeppe, Jeffrey | 91116.79 | 51684.33 | -39432.46 | -43.28% | 61751.12 | 21888.03 | -39863.09 | -64.55% | 11528.34 | 6182.21 | -5346.13 | -46.37% | 17837.33 | 6757.72 | -11079.61 | -62.11% | 0 | 16856.37 | 16856.37 |  | 551.67 | 194.5 | -357.17 | -64.74% | 2021-12-10 01:00
Hamilton | 2022 | 642177 | JOINT USE PERMIT HW2021-090 - GREENCEDAR, VENETIAN, ANTHONY, ETC - HAM | 99 | COMPLETE | Estimate incorrect | Cont Est Over |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 21875.79 | 11261.43 | -10614.36 | -48.52% | 5965.03 | 1594.57 | -4370.46 | -73.27% | 3251.2 | 1077.86 | -2173.34 | -66.85% | 1493.86 | 0 | -1493.86 | -100% | 11165.7 | 8589 | -2576.7 | -23.08% | 30.24 | 0 | -30.24 | -100% | 2022-03-14 01:00
Hamilton | 2022 | 642303 | 2022 - TX RENEWAL HAM BATCH 1 - 5 TX'S | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Macdougall, Stephen | 168274.47 | 112585.24 | -55689.23 | -33.09% | 78821.59 | 46355.31 | -32466.28 | -41.19% | 52454.32 | 39243.72 | -13210.6 | -25.18% | 22093.56 | 14762 | -7331.56 | -33.18% | 14905 | 12224.21 | -2680.79 | -17.99% | 677.28 | 562 | -115.28 | -17.02% | 2022-08-16 01:00
Hamilton | 2022 | 642319 | 620 RYMAL RD EAST/ HAM / UP | 99 | COMPLETE | Labour est. under | Cont Est Over | N/A | Kappheim, Adam | No | Sabbah, Amir | Macdougall, Stephen | 74775.85 | 64653.74 | -10122.11 | -13.54% | 24854.33 | 19582.62 | -5271.71 | -21.21% | 36292.18 | 35417.71 | -874.47 | -2.41% | 5957.34 | 3707 | -2250.34 | -37.77% | 7672 | 5946.41 | -1725.59 | -22.49% | 160 | 223 | 63 | 39.38% | 2022-12-22 01:00
Hamilton | 2022 | 642398 | 2022 - SWITCH RENEWAL - WEST - HORIZONTAL UNITS - 2 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 185715.53 | 169824.03 | -15891.5 | -8.557% | 51457.28 | 47508.72 | -3948.56 | -7.673% | 114028.74 | 100357.68 | -13671.06 | -11.99% | 12429.51 | 15815 | 3385.49 | 27.24% | 7800 | 6142.63 | -1657.37 | -21.25% | 432.8 | 546 | 113.2 | 26.16% | 2022-10-07 01:00
Hamilton | 2022 | 642399 | 2022 - SWITCH RENEWAL - WEST - VERTICAL UNITS - 2 | 99 | COMPLETE | Under 10% | Cont Est Over |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Brad Carr | 226457.41 | 213227.75 | -13229.66 | -5.842% | 14888.92 | 24840.71 | 9951.79 | 66.84% | 102727.85 | 112308.44 | 9580.59 | 9.326% | 1520 | 871 | -649 | -42.7% | 107320.64 | 75207.6 | -32113.04 | -29.92% | 98 | 122.5 | 24.5 | 25% | 2022-09-14 01:00
Hamilton | 2022 | 642500 | 1040 QUEENSDALE AVENUE EAST / HAM / UP / 3PH PAD | 99 | COMPLETE | Cont Est Under | Labour est. under | Vac truck | Kappheim, Adam | No | Djuric, Zdravko | Macdougall, Stephen | 63925.94 | 86580.96 | 22655.02 | 35.44% | 21813.26 | 29874.24 | 8060.98 | 36.95% | 26497.19 | 30962.4 | 4465.21 | 16.85% | 4490.49 | 6971 | 2480.51 | 55.24% | 11125 | 18773.32 | 7648.32 | 68.75% | 164 | 301 | 137 | 83.54% | 2022-05-30 01:00
Hamilton | 2022 | 642502 | 30 LAURIER AVENUE / HAM / UP / 3PH PAD | 99 | COMPLETE | Labour est. under |  |  | Kappheim, Adam | No | Djuric, Zdravko | Roy Owen | 47913.52 | 51043.26 | 3129.74 | 6.532% | 10405.02 | 16462.51 | 6057.49 | 58.22% | 21581.54 | 18245.8 | -3335.74 | -15.46% | 951.96 | 2534 | 1582.04 | 166.2% | 14975 | 13800.95 | -1174.05 | -7.84% | 56 | 160.5 | 104.5 | 186.6% | 2022-05-13 01:00
Hamilton | 2022 | 642503 | 86 CAMERON AVENUE / DUN / UP / 3PH PAD | 99 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Djuric, Zdravko | Macdougall, Stephen | 65558.41 | 68011.68 | 2453.27 | 3.742% | 22011.81 | 23624.79 | 1612.98 | 7.328% | 25625.88 | 24618.42 | -1007.46 | -3.931% | 4490.72 | 5807 | 1316.28 | 29.31% | 13430 | 13961.47 | 531.47 | 3.957% | 164 | 257 | 93 | 56.71% | 2022-03-18 01:00
Hamilton | 2022 | 642505 | OH AUTO SWITCHES (DA) 2022 - PART 3 - 4 | 99 | COMPLETE | Under 10% | Cont Est Under |  | Beaudrie, Scott | Yes | Billone, Justin | Koeppe, Jeffrey | 365294.42 | 360586.5 | -4707.92 | -1.289% | 103694.59 | 93171.06 | -10523.53 | -10.15% | 231131.99 | 222820.55 | -8311.44 | -3.596% | 24541.58 | 25340.74 | 799.16 | 3.256% | 5926.26 | 19254.15 | 13327.89 | 224.9% | 892 | 965 | 73 | 8.184% | 2022-07-22 01:00
Hamilton | 2022 | 642516 | UG AUTO SWITCHES (DA) 2022 - MH764 - 1 | 98 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 365807.78 | 391115.45 | 25307.67 | 6.918% | 48956.05 | 43770.9 | -5185.15 | -10.59% | 199101.73 | 233805.41 | 34703.68 | 17.43% | 3351 | 2815.95 | -535.05 | -15.97% | 114399 | 110723.19 | -3675.81 | -3.213% | 201 | 279 | 78 | 38.81% | 2022-09-07 01:00
Hamilton | 2022 | 642518 | UG AUTO SWITCHES (DA) 2022 - CLAPPISON - 1 | 99 | COMPLETE | BOM cost variance |  |  | Beaudrie, Scott | Yes | Wardell, Paul | Tony Ierace | 447750.27 | 501441.55 | 53691.28 | 11.99% | 99252.88 | 93458.93 | -5793.95 | -5.838% | 200675.52 | 264622.59 | 63947.07 | 31.87% | 16424.18 | 16524.68 | 100.5 | 0.6119% | 131397.69 | 126835.35 | -4562.34 | -3.472% | 660.29 | 664 | 3.71 | 0.5619% | 2022-12-09 01:00
Hamilton | 2022 | 642567 | 2022 - BELAND AVE N - 1 WP, 1OH TX | 99 | COMPLETE | Vac truck |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Macdougall, Stephen | 24299.58 | 22846.44 | -1453.14 | -5.98% | 12360.22 | 9357.51 | -3002.71 | -24.29% | 6508 | 6513.1 | 5.1 | 0.07837% | 3231.36 | 4664.5 | 1433.14 | 44.35% | 2200 | 2311.33 | 111.33 | 5.06% | 97.92 | 115 | 17.08 | 17.44% | 2022-10-21 01:00
Hamilton | 2022 | 642637 | 85 CORESLAB DR | 99 | COMPLETE | Estimate incorrect | Labour est. over |  | Frigotto, Rodrigo | No | Bennett, Aaron | Macdougall, Stephen | 79020.31 | 64739.11 | -14281.2 | -18.07% | 25141.06 | 16806.38 | -8334.68 | -33.15% | 34377.3 | 36251.72 | 1874.42 | 5.452% | 4584.95 | 3416 | -1168.95 | -25.5% | 14917 | 8265.01 | -6651.99 | -44.59% | 172.62 | 139 | -33.62 | -19.48% | 2022-09-21 01:00
Hamilton | 2021 | 642660 | OVERHEAD LINE ISOLATION/REMOVAL, 14-18 AUGUSTA ST | 99 | COMPLETE | Labour est. over |  |  | Jakubowski, Mark | No | Patel, Ketan | Macdougall, Stephen | 71448.3 | 35611.56 | -35836.74 | -50.16% | 47996.64 | 18632.95 | -29363.69 | -61.18% | 10604.36 | 6855.39 | -3748.97 | -35.35% | 11722.3 | 4350 | -7372.3 | -62.89% | 1125 | 5773.22 | 4648.22 | 413.2% | 280.05 | 171 | -109.05 | -38.94% | 2021-11-26 01:00
Hamilton | 2022 | 642683 | CUSTOMER INITIATED RELOCATIONS - AYR AVE/BINGHAM DR | 95 | COMPLETE | Under 10% | Material Under Estimated |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 321437.76 | 301452.74 | -19985.02 | -6.217% | 46891.67 | 40300.73 | -6590.94 | -14.06% | 27888.87 | 50786.54 | 22897.67 | 82.1% | 950 | 156 | -794 | -83.58% | 245707.22 | 210209.47 | -35497.75 | -14.45% | 50 | 24 | -26 | -52% | 2023-01-13 01:00
Hamilton | 2022 | 642736 | 406 PRITCHARD RD / HAM / NS | 95 | COMPLETE | Commodity Price | BOM not accurate | Labour est. over | Kappheim, Adam | No | Sabbah, Amir | Roy Owen | 145201.07 | 145878.34 | 677.27 | 0.4664% | 37924.93 | 27928.53 | -9996.4 | -26.36% | 48697.4 | 63071.16 | 14373.76 | 29.52% | 4818.74 | 2524 | -2294.74 | -47.62% | 53760 | 52354.65 | -1405.35 | -2.614% | 158.08 | 160.5 | 2.42 | 1.531% | 2022-11-09 01:00
Hamilton | 2022 | 642745 | 87 KENNEDY AVE - REROUTING SERVICE FOR AERIAL TRESPASS | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Wardell, Paul | Brad Carr | 15152.82 | 15092.06 | -60.76 | -0.401% | 4170.65 | 6653.68 | 2483.03 | 59.54% | 684.47 | 14.82 | -669.65 | -97.83% | 203.7 | 530 | 326.3 | 160.2% | 10094 | 7893.56 | -2200.44 | -21.8% | 9.3 | 23 | 13.7 | 147.3% | 2022-04-28
Hamilton | 2022 | 642748 | 2021 EMERGING OH - HAM - BATCH 3 - 1 TX | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-08
Hamilton | 2022 | 642829 | QUEENSTON RD BURIAL - NASH TO CENTENNIAL | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Jolie, Chris | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-28
Hamilton | 2022 | 642832 | HYDRO VAULT LID REPLACEMENT-V77-CHAMPLAIN AVE | 99 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Celic, Dusan | Brad Carr | 22390.09 | 22496.17 | 106.08 | 0.4738% | 2385.71 | 3311.92 | 926.21 | 38.82% | 3457.19 | 3534 | 76.81 | 2.222% | 32 | 0 | -32 | -100% | 16515.19 | 15650.25 | -864.94 | -5.237% | 2 | 0 | -2 | -100% | 2022-03-28
Hamilton | 2022 | 642862 | 2022 - TX RENEWAL HAM - BATCH 3 (UG) - 5 TX | 99 | COMPLETE | Commodity Price | Labour est. under |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Tony Ierace | 43994.99 | 30814.93 | -13180.06 | -29.96% | 14679.41 | 10240.14 | -4439.27 | -30.24% | 25799.1 | 18767.79 | -7031.31 | -27.25% | 3516.48 | 1807 | -1709.48 | -48.61% | 0 | 0 | 0 |  | 119.88 | 140.5 | 20.62 | 17.2% | 2022-03-25 01:00
Hamilton | 2022 | 642909 | JOINT USE PERMIT HW2021-118 - WILSON E - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 10790.35 | 8431.75 | -2358.6 | -21.86% | 1478.92 | 1400.82 | -78.1 | -5.281% | 371.33 | 153.93 | -217.4 | -58.55% | 0 | 0 | 0 |  | 8940.1 | 6877 | -2063.1 | -23.08% | 0 | 0 | 0 |  | 2022-03-14 01:00
Hamilton | 2022 | 642910 | JOINT USE PERMIT HW2021-119 - BARTON - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 10823.88 | 9621.69 | -1202.19 | -11.11% | 2191.42 | 1583.17 | -608.25 | -27.76% | 791.23 | 1759.52 | 968.29 | 122.4% | 306.43 | 0 | -306.43 | -100% | 7534.8 | 6279 | -1255.8 | -16.67% | 6.72 | 0 | -6.72 | -100% | 2022-03-14 01:00
Hamilton | 2022 | 642915 | JOINT USE PERMIT HW2021-123 - MOUNTAIN N - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 6136.81 | 5005.51 | -1131.3 | -18.43% | 1320.01 | 1136.78 | -183.23 | -13.88% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4816.8 | 3868.73 | -948.07 | -19.68% | 0 | 0 | 0 |  | 2022-03-14 01:00
Hamilton | 2022 | 642916 | JOINT USE PERMIT HW2021-124 - GRAY, BRITANNIA, ROXBOROUGH, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 7928.36 | 6676.75 | -1251.61 | -15.79% | 1511.96 | 1339.75 | -172.21 | -11.39% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6416.4 | 5337 | -1079.4 | -16.82% | 0 | 0 | 0 |  | 2022-03-14 01:00
Hamilton | 2022 | 642919 | JOINT USE PERMIT HW2021-127 - CHERRYWOOD, NEW MTN, ETC - HAM | 99 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 6963.6 | 5577.44 | -1386.16 | -19.91% | 1202.17 | 1250.64 | 48.47 | 4.032% | 280.63 | 110.8 | -169.83 | -60.52% | 0 | 0 | 0 |  | 5480.8 | 4216 | -1264.8 | -23.08% | 0 | 0 | 0 |  | 2022-03-14 01:00
Hamilton | 2022 | 642970 | 2022 TX RENEWAL HAM - BATCH 4 - 5 TX | 99 | COMPLETE | Material Req incorrectly | Vac truck |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Macdougall, Stephen | 118392.51 | 150510.83 | 32118.32 | 27.13% | 61249.05 | 61008.57 | -240.48 | -0.3926% | 38860.17 | 50286.37 | 11426.2 | 29.4% | 18283.29 | 16604 | -1679.29 | -9.185% | 0 | 22611.89 | 22611.89 |  | 564.79 | 753.5 | 188.71 | 33.41% | 2022-10-14 01:00
Hamilton | 2022 | 643004 | 2021 - 50 MAIN STREET (DUNDAS) - TRANSFORMER REPLACEMENT | 99 | COMPLETE | Cont Est Over | BOM not accurate |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 44522.26 | 33387.23 | -11135.03 | -25.01% | 2566.55 | 2385.91 | -180.64 | -7.038% | 23540.71 | 15907.24 | -7633.47 | -32.43% | 0 | 0 | 0 |  | 18415 | 15094.08 | -3320.92 | -18.03% | 4 | 0 | -4 | -100% | 2022-03-15 01:00
Hamilton | 2022 | 643082 | ROXBOROUGH PARK - PHASE 3 - SUBD RES EDS | 99 | CANCELLED | N/A |  |  | Velickovski, Goran | No | Morris, Mark | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-02-07 01:00
Hamilton | 2022 | 643111 | 2022 - WEST CABLE REPLACEMENTS - STONEY CREEK - NORTH OF HWY 8 (PART 2) | 92 | ACTIVE |  |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 1999586.86 | 2115536.77 | 115949.91 | 5.799% | 144035.12 | 278241.53 | 134206.41 | 93.18% | 141969.63 | 194257.74 | 52288.11 | 36.83% | 0 | 5535.04 | 5535.04 |  | 1713582.11 | 1631103.18 | -82478.93 | -4.813% | 240 | 201 | -39 | -16.25% | 2022-12-15 01:00
Hamilton | 2022 | 643209 | 82 PARKSIDE DR / HAM / NS | 99 | COMPLETE | Under 10% |  |  | Frigotto, Rodrigo | No | Sabbah, Amir | Roy Owen | 56811.48 | 63987.8 | 7176.32 | 12.63% | 15755.41 | 17163.53 | 1408.12 | 8.937% | 31757.36 | 36564.86 | 4807.5 | 15.14% | 2090.71 | 4189 | 2098.29 | 100.4% | 7208 | 6070.41 | -1137.59 | -15.78% | 77.06 | 139.5 | 62.44 | 81.03% | 2022-11-09 01:00
Hamilton | 2022 | 643363 | 51 RALEIGH ST / HAM / UP / 1PH | 99 | COMPLETE | Material Req incorrectly | Labour est. over |  | Frigotto, Rodrigo | No | Dragojevic, Igor | Roy Owen | 7591.7 | 0 | -7591.7 | -100% | 3372.08 | 0 | -3372.08 | -100% | 3514.86 | 0 | -3514.86 | -100% | 704.76 | 0 | -704.76 | -100% | 0 | 0 | 0 |  | 24.03 | 0 | -24.03 | -100% | 2022-02-17 01:00
Hamilton | 2022 | 643389 | 21 RANDALL AVE - OVERHEAD TRESPASS - INGROUND POOL | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Wardell, Paul | Koeppe, Jeffrey | 9724.51 | 10412.83 | 688.32 | 7.078% | 6391.2 | 6079.22 | -311.98 | -4.881% | 1420.82 | 771.73 | -649.09 | -45.68% | 1162.49 | 2048 | 885.51 | 76.17% | 750 | 1513.88 | 763.88 | 101.9% | 35.72 | 44 | 8.28 | 23.18% | 2022-03-01 01:00
Hamilton | 2022 | 643519 | 2022 SWITCH RENEWAL HAM - BATCH 2 - 1 VIPER | 99 | COMPLETE | Vac truck | Material Req incorrectly |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 124582.64 | 99552.83 | -25029.81 | -20.09% | 44772.95 | 35223.46 | -9549.49 | -21.33% | 61053.21 | 49619.47 | -11433.74 | -18.73% | 11551.48 | 14584 | 3032.52 | 26.25% | 7205 | 125.9 | -7079.1 | -98.25% | 386.23 | 405 | 18.77 | 4.86% | 2022-05-02
Hamilton | 2022 | 643536 | 2022 SWITCH RENEAL HAM - 2 MAUNAL LIS | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Koeppe, Jeffrey | 100379.31 | 107294.32 | 6915.01 | 6.889% | 51264.48 | 41498.77 | -9765.71 | -19.05% | 27323.1 | 32139.8 | 4816.7 | 17.63% | 14191.73 | 15766.5 | 1574.77 | 11.1% | 7600 | 17889.25 | 10289.25 | 135.4% | 448.86 | 516.5 | 67.64 | 15.07% | 2022-10-07 01:00
Hamilton | 2022 | 643652 | 66 INNOVATION DRIVE / HAM / UP / 3PH PAD | 95 | COMPLETE | Under 10% |  |  | Frigotto, Rodrigo | No | Dragojevic, Igor | Roy Owen | 46124.73 | 45721.63 | -403.1 | -0.8739% | 13455.88 | 14871.17 | 1415.29 | 10.52% | 32188.89 | 27984.81 | -4204.08 | -13.06% | 479.96 | 1109 | 629.04 | 131.1% | 0 | 1756.65 | 1756.65 |  | 32 | 59 | 27 | 84.38% | 2022-08-24 01:00
Hamilton | 2022 | 643944 | 2022 EMERGING OH - STROUD SC RELOCATION | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Wardell, Paul | Koeppe, Jeffrey | 207214.19 | 189373.37 | -17840.82 | -8.61% | 67411.06 | 60609.14 | -6801.92 | -10.09% | 97750.07 | 88578.31 | -9171.76 | -9.383% | 14913.06 | 17230 | 2316.94 | 15.54% | 27140 | 22955.92 | -4184.08 | -15.42% | 522.62 | 699.5 | 176.88 | 33.84% | 2022-04-29
Hamilton | 2022 | 643952 | CUSTOMER INITIATED RELOCATIONS - POLE RELOCATION AYR AVE | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Celic, Dusan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-08-12 01:00
Hamilton | 2022 | 644004 | HWY 8 & GRAY - AUTOMATE INTERSECTION - 3 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Billone, Justin | Koeppe, Jeffrey | 232049.69 | 232251.19 | 201.5 | 0.08683% | 63560.44 | 51025.13 | -12535.31 | -19.72% | 151161.25 | 161942.2 | 10780.95 | 7.132% | 17328 | 16806.61 | -521.39 | -3.009% | 0 | 2477.25 | 2477.25 |  | 526 | 525 | -1 | -0.1901% | 2022-08-12 01:00
Hamilton | 2022 | 644075 | 415 MAIN ST W / HAM / NS00186002 / 750KVA 3PH TEMP SERVICE | 99 | COMPLETE | Under 10% |  |  | Frigotto, Rodrigo | No | Laus, Tomislav | Roy Owen | 79900.8 | 74820.87 | -5079.93 | -6.358% | 18076.51 | 16220.72 | -1855.79 | -10.27% | 36201.54 | 30184.6 | -6016.94 | -16.62% | 1567.75 | 1838.5 | 270.75 | 17.27% | 24055 | 26577.05 | 2522.05 | 10.48% | 103.45 | 104.5 | 1.05 | 1.015% | 2022-11-14 01:00
Hamilton | 2022 | 644148 | CUSTOMER INITIATED DE-ENERGIZE PRIMARY - 324 DUNDAS ST E - WATERDOWN | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Celic, Dusan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-08 01:00
Hamilton | 2022 | 645002 | 367 BARTON ST/ STC / UP00192515 / 500KVA - 400A 347/600V 3PH PAD SERVICE | 99 | CANCELLED | N/A |  |  | Frigotto, Rodrigo | No | Laus, Tomislav | Calvin Arsenault | 2493.65 | 0 | -2493.65 | -100% | 2493.65 | 0 | -2493.65 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-14 01:00
Hamilton | 2022 | 645079 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 WEST OF DEWITT (PART 2) | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-14 01:00
Hamilton | 2022 | 645080 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 WEST OF DEWITT (PART 3) | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-14 01:00
Hamilton | 2022 | 645081 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 EAST OF DEWITT (PART 2) | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-14 01:00
Hamilton | 2022 | 645082 | WEST CABLE REPLACEMENTS - STONEY CREEK - SOUTH OF HWY 8 EAST OF DEWITT (PART 3) | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-14 01:00
Hamilton | 2022 | 645101 | 41 REID AVE / HAM / NS00280013 / RELOCATE 3PH PAD | 95 | COMPLETE | Scope – Eng | Scope – Eng |  | Frigotto, Rodrigo | No | Laus, Tomislav | Roy Owen | 36617.26 | 22236.49 | -14380.77 | -39.27% | 13746.46 | 14230.18 | 483.72 | 3.519% | 25863.07 | 4218.9 | -21644.17 | -83.69% | 1759.09 | 3170 | 1410.91 | 80.21% | -4751.36 | 617.41 | 5368.77 | -113% | 103.33 | 125 | 21.67 | 20.97% | 2022-10-14 01:00
Hamilton | 2022 | 644427 | 2022 BELL TRANSFERS - AUCHMAR ROAD | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Brad Carr | 19286.36 | 19780.9 | 494.54 | 2.564% | 6921.98 | 6004.5 | -917.48 | -13.25% | 1914.38 | 2311.4 | 397.02 | 20.74% | 0 | 1015 | 1015 |  | 10450 | 10450 | 0 | 0% | 0 | 31 | 31 |  | 2022-07-11 01:00
Hamilton | 2022 | 644535 | PEIR 14 PORT AUTH - HAM - NS - 3PH - 600A | 99 | CANCELLED | N/A |  |  | Frigotto, Rodrigo | No | Pellerin, Patrick | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-13 01:00
Hamilton | 2022 | 644638 | 158 JAMES STREET SOUTH - SERVICE RELOCATION | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Wardell, Paul | Brad Carr | 21600.07 | 21537.8 | -62.27 | -0.2883% | 5596.96 | 6131.62 | 534.66 | 9.553% | 777.41 | 0 | -777.41 | -100% | 119.7 | 299 | 179.3 | 149.8% | 15106 | 15107.18 | 1.18 | 0.007811% | 7.15 | 11.5 | 4.35 | 60.84% | 2022-08-22 01:00
Hamilton | 2022 | 644737 | 1 JAMES ST SOUTH - VAULT LID REPLACEMENT | 99 | COMPLETE | Labour est. over |  |  | Carr, Brad | No | Billone, Justin | Brad Carr | 11574.47 | 8995.16 | -2579.31 | -22.28% | 3947.47 | 1989.16 | -1958.31 | -49.61% | 3534 | 3534 | 0 | 0% | 228 | 52 | -176 | -77.19% | 3865 | 3420 | -445 | -11.51% | 12 | 2 | -10 | -83.33% | 2022-08-31 01:00
Hamilton | 2022 | 644750 | QUEEN VICTORIA DR - VAULT LID | 95 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Billone, Justin | Brad Carr | 13155.56 | 11174.04 | -1981.52 | -15.06% | 4176.75 | 2543.44 | -1633.31 | -39.1% | 3756.81 | 4118.96 | 362.15 | 9.64% | 190 | 58.64 | -131.36 | -69.14% | 5032 | 4453 | -579 | -11.51% | 10 | 2 | -8 | -80% | 2022-12-19 01:00
Hamilton | 2022 | 646349 | 35 SUNNYHURST AVE STONEY CREEK | 99 | COMPLETE | Engineering by-passed |  |  | Beaudrie, Scott | No | Karan, Andjelo | Brad Carr | 0 | 50550.16 | 50550.16 |  | 0 | 6763.11 | 6763.11 |  | 0 | 14533.23 | 14533.23 |  | 0 | 0 | 0 |  | 0 | 29253.82 | 29253.82 |  | 0 | 0 | 0 |  | 2022-12-29 01:00
Hamilton | 2022 | 646569 | 600 FERGUSON AVE N PIER 10 - HAM - UP - 400A 347/600V | 99 | CANCELLED | N/A |  |  | Frigotto, Rodrigo | No | Pellerin, Patrick | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-28 01:00
Hamilton | 2022 | 646611 | 2022 TX RENEWAL - POLE TRAN P7676 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-03 01:00
Hamilton | 2022 | 645371 | 400 JONES RD N / HAM / NS00200340 / 3PH PAD (CANCELLED) | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Bharosi, Mohindra | Calvin Arsenault | 124749.99 | 4240.26 | -120509.73 | -96.6% | 37837.98 | 4240.26 | -33597.72 | -88.79% | 56847.2 | 0 | -56847.2 | -100% | 8824.81 | 0 | -8824.81 | -100% | 21240 | 0 | -21240 | -100% | 256 | 2 | -254 | -99.22% | 2022-11-07 01:00
Hamilton | 2022 | 645400 | AUTO SWITCH - SC1012 - 1 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Tony Ierace | 157290.17 | 163215.43 | 5925.26 | 3.767% | 25462.64 | 20783.5 | -4679.14 | -18.38% | 128783.47 | 138902.12 | 10118.65 | 7.857% | 3044.06 | 3529.81 | 485.75 | 15.96% | 0 | 0 | 0 |  | 172.64 | 214 | 41.36 | 23.96% | 2022-06-17 01:00
Hamilton | 2022 | 645576 | 1831X - LBDS INSTALL | 99 | COMPLETE | Vac truck |  |  | Beaudrie, Scott | No | Billone, Justin | Koeppe, Jeffrey | 42423.87 | 34861.38 | -7562.49 | -17.83% | 22758.31 | 15541.87 | -7216.44 | -31.71% | 13793.42 | 13118.7 | -674.72 | -4.892% | 5872.14 | 4655.28 | -1216.86 | -20.72% | 0 | 1545.53 | 1545.53 |  | 154.53 | 141 | -13.53 | -8.756% | 2022-11-11 01:00
Hamilton | 2022 | 645669 | CUSTOMER INTITIATED POLE HEIGHT INCREASE - LAKESHORE RD - ST. CATHARINES | 99 | COMPLETE | N/A |  |  | Jakubowski, Mark | No | Celic, Dusan | Frank Giancola | 48477.58 | 0 | -48477.58 | -100% | 27696.12 | 0 | -27696.12 | -100% | 7092.06 | 0 | -7092.06 | -100% | 6188.4 | 0 | -6188.4 | -100% | 7501 | 0 | -7501 | -100% | 162 | 0 | -162 | -100% | 2022-08-25 01:00
Hamilton | 2022 | 647155 | CENTRAL VOLTAGE CONVERSION FUSING | 95 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Wardell, Paul | Brad Carr | 57231.61 | 60434.85 | 3203.24 | 5.597% | 5824.92 | 10599.33 | 4774.41 | 81.97% | 7172.76 | 6823.87 | -348.89 | -4.864% | 0 | 0 | 0 |  | 44233.93 | 43011.65 | -1222.28 | -2.763% | 6 | 8 | 2 | 33.33% | 2022-12-01 01:00
Hamilton | 2022 | 647157 | CUSTOMER INTITIATED SERVICE RELOCATION / ANCHOR INSTALL - STONECHURC RD W - HAM | 99 | COMPLETE | Vac truck |  |  | Jakubowski, Mark | No | Celic, Dusan | Koeppe, Jeffrey | 9756.56 | 4467.58 | -5288.98 | -54.21% | 5843.02 | 3151.08 | -2691.94 | -46.07% | 573.54 | 201.99 | -371.55 | -64.78% | 1140 | 693 | -447 | -39.21% | 2200 | 421.51 | -1778.49 | -80.84% | 30 | 22 | -8 | -26.67% | 2022-10-27 01:00
Hamilton | 2022 | 647432 | CUSTOMER INITIATED POLE RELOCATION - ST.MARKS CENTRE - HUNTER ST W & BAY ST S | 99 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Celic, Dusan | Koeppe, Jeffrey | 9280.42 | 11197.91 | 1917.49 | 20.66% | 5479.97 | 7333.87 | 1853.9 | 33.83% | 0 | 0 | 0 |  | 1000.45 | 1616 | 615.55 | 61.53% | 2800 | 2248.04 | -551.96 | -19.71% | 24.55 | 32 | 7.45 | 30.35% | 2022-10-07 01:00
Hamilton | 2022 | 648333 | 1557 RYMAL RD E - HAM / NS | 95 | COMPLETE | Under 10% |  |  | Frigotto, Rodrigo | No | Sabbah, Amir | Roy Owen | 37196.76 | 34906.98 | -2289.78 | -6.156% | 11636.43 | 6700.8 | -4935.63 | -42.42% | 23044.05 | 26293.18 | 3249.13 | 14.1% | 2516.28 | 1913 | -603.28 | -23.98% | 0 | 0 | 0 |  | 102.36 | 86 | -16.36 | -15.98% | 2022-12-07 01:00
Hamilton | 2022 | 648785 | 82 FERGUSON AVE N / HAM / NS00287202 / 200A 347/600 | 99 | CANCELLED | N/A |  |  | Frigotto, Rodrigo | No | Ogilvie, Jordan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-05 00:59
Markham | 2019 | 310640 | ( WO 310640) THE GRAND CHATEAUS ON BAYVIEW PH2 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Perks, Dan | Steve Rumble | 0 | 8472.79 | 8472.79 |  | 0 | 6089.98 | 6089.98 |  | 0 | 2227.03 | 2227.03 |  | 0 | 155.78 | 155.78 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 310939 | ( WO 310939) CENTRO 7777 WESTON (RETAIL AND OFFICE) | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Yuen, Paul | Steve Rumble | 249656.34 | 205439.5 | -44216.84 | -17.71% | 48787.83 | 60390.11 | 11602.28 | 23.78% | 142547.07 | 101174.75 | -41372.32 | -29.02% | 10410.57 | 8346.16 | -2064.41 | -19.83% | 47910.87 | 35528.48 | -12382.39 | -25.84% | 657.5 | 458.5 | -199 | -30.27% | 2019-04-23 01:00
Markham | 2019 | 311826 | ( WO 311826) KLEINDOR DEVELOPMENT INC. PH#2 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Kinsella, William P | Steve Rumble | 0 | 67063.65 | 67063.65 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 49 | 49 |  | 2019-07-26 01:00
Markham | 2019 | 312191 | (WO312191) 3150 Major Mackenzie Dr | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Dibratto, Susan | Lyle, Sedore | 182388.34 | 199171.1 | 16782.76 | 9.202% | 43457.39 | 73662.69 | 30205.3 | 69.51% | 120631.86 | 109272.34 | -11359.52 | -9.417% | 9941.09 | 14112.05 | 4170.96 | 41.96% | 8358 | 2124.02 | -6233.98 | -74.59% | 580.4 | 367.5 | -212.9 | -36.68% | 2019-02-13 01:00
Markham | 2019 | 312306 | (WO 312306) 20 Brodie Dr | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 313166 | ( WO 313166) 3940 HIGHWAY 8 - PEAK GARDENS SUBDIVION | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Alarcon, Alejandro | Steve Rumble | 119613.76 | 118613.27 | -1000.49 | -0.8364% | 22045.97 | 9635.75 | -12410.22 | -56.29% | 11898.32 | 14711 | 2812.68 | 23.64% | 4773.27 | 28 | -4745.27 | -99.41% | 80896.2 | 0 | -80896.2 | -100% | 301 | 107.75 | -193.25 | -64.2% | 2019-02-21 01:00
Markham | 2019 | 313234 | (WO313234) S/W corner Yonge & Elderberry | 99 | COMPLETE | Engineering by-passed |  |  |  | No | Harris, Geoff L. | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 313235 | (WO313235) 300 EARL STEWART DR, AURORA | 99 | COMPLETE | Engineering by-passed |  |  |  | No | Harris, Geoff L. | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2020 | 313357 | (WO 313357) 15-039 Guying Installation | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 313385 | (WO313385) 9750 YONGE STREET | 99 | CANCELLED | Engineering by-passed |  |  |  | No | Dibratto, Susan | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2020 | 313677 | (WO 313677) 15-056 Anchor Installation MAJOR MACKENZIE DR - GRAND TRUNK AVE TO ONTARIO ST | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 313887 | (WO 313887) Brownstones Phase 2 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Dibratto, Susan | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 313906 | ( WO 313906) MADISON LEGACY BLOCK 11 SUBDIVISION | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 0 | 515968.81 | 515968.81 |  | 0 | 111099.06 | 111099.06 |  | 0 | 139729.84 | 139729.84 |  | 0 | 393.37 | 393.37 |  | 0 | 6175.25 | 6175.25 |  | 0 | 220.5 | 220.5 |  | 2019-07-26 01:00
Markham | 2019 | 314091 | ( WO 314091) 251 Langstaff Rd | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 314247 | ( WO 314247) LESILE ELGIN PHASE 1 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Alarcon, Alejandro | Steve Rumble | 0 | 1512377.97 | 1512377.97 |  | 0 | 558915.94 | 558915.94 |  | 0 | 925920.07 | 925920.07 |  | 0 | 3541.96 | 3541.96 |  | 0 | 24000 | 24000 |  | 0 | 133.5 | 133.5 |  | 2019-07-26 01:00
Markham | 2019 | 314351 | ( WO 314351) VILLAGES OF FAIRTREE - EAST VILLAGE | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Alarcon, Alejandro | Steve Rumble | 786406.31 | 12026.17 | -774380.14 | -98.47% | 23081.72 | 1970.17 | -21111.55 | -91.46% | 6346.16 | 28 | -6318.16 | -99.56% | 6716.9 | 28 | -6688.9 | -99.58% | 750261.53 | 10000 | -740261.53 | -98.67% | 472.32 | 0 | -472.32 | -100% | 2019-07-26 01:00
Markham | 2019 | 314652 | (WO 314652) Aurora Go station Pole Relocation | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 314669 | ( WO 314669) 7818 DUFFERIN BUILDING A | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 314729 | ( WO 314729) Corsica Ph 1 subdivision | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 0 | 64426.45 | 64426.45 |  | 0 | 36341.78 | 36341.78 |  | 0 | 15785.89 | 15785.89 |  | 0 | 2059.38 | 2059.38 |  | 0 | 10239.4 | 10239.4 |  | 401 | 249.75 | -151.25 | -37.72% | 2019-07-26 01:00
Markham | 2019 | 314731 | (WO 314731) Corsica Residential Development PH2 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 31267.46 | 16079.86 | -15187.6 | -48.57% | 14041.23 | 8371.4 | -5669.83 | -40.38% | 5917.66 | 889.74 | -5027.92 | -84.96% | 4086.07 | 68.72 | -4017.35 | -98.32% | 7222.5 | 6750 | -472.5 | -6.542% | 344.03 | 117.48 | -226.55 | -65.85% | 2019-07-26 01:00
Markham | 2019 | 314733 | ( WO 314733) CORSICA RESIDENTIAL PHASE 3 SUBDIVISION | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 0 | 18224.7 | 18224.7 |  | 0 | 7949.79 | 7949.79 |  | 0 | 2770.31 | 2770.31 |  | 0 | 754.6 | 754.6 |  | 0 | 6750 | 6750 |  | 0 | 74 | 74 |  | 2019-07-26 01:00
Markham | 2019 | 314813 | ( WO 314813) MATTAMY HOMES PHASE 1B (AURORA) (SERVICES ONLY) | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Fitz Randolph, Kim C | Steve Rumble | 0 | 4443.92 | 4443.92 |  | 0 | 4016.92 | 4016.92 |  | 0 | 213.5 | 213.5 |  | 0 | 213.5 | 213.5 |  | 0 | 0 | 0 |  | 0 | 19.5 | 19.5 |  | 2019-07-26 01:00
Markham | 2019 | 315020 | ( WO 315020) 77 EAGLEVIEW HEIGHTS PH 1 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 0 | 384650.32 | 384650.32 |  | 0 | 142949.99 | 142949.99 |  | 0 | 230688.85 | 230688.85 |  | 0 | 915.73 | 915.73 |  | 0 | 10095.75 | 10095.75 |  | 0 | 252.25 | 252.25 |  | 2019-07-26 01:00
Markham | 2019 | 315057 | ( WO 315057) BG AURORA PHASE 1 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Fitz Randolph, Kim C | Steve Rumble | 0 | 685742.26 | 685742.26 |  | 0 | 256144.98 | 256144.98 |  | 0 | 223197.69 | 223197.69 |  | 0 | 875.59 | 875.59 |  | 0 | 205524 | 205524 |  | 0 | 39 | 39 |  | 2019-07-26 01:00
Markham | 2019 | 315084 | ( WO 315084) GLEN RIDGES ESTATES SUBDIVISION | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Fitz Randolph, Kim C | Steve Rumble | 0 | 245418.7 | 245418.7 |  | 0 | 104192.28 | 104192.28 |  | 0 | 69782.02 | 69782.02 |  | 0 | 437.4 | 437.4 |  | 0 | 71007 | 71007 |  | 0 | 16.5 | 16.5 |  | 2019-07-26 01:00
Markham | 2019 | 315355 | (WO 315355) HW 50 - CASTLEMORE TO MAYFIELD | 99 | CANCELLED | N/A |  |  |  | No | Lacombe, Joel | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 315364 | (WO 315364) 9225 Bathurst St | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 315376 | (WO315376) S/G Pole Relocate at Kevi Subdivision | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Graham, Bruce W. | Macdonald, Larry | 17787 | 8829.47 | -8957.53 | -50.36% | 3053 | 6572.98 | 3519.98 | 115.3% | 753 | 1479.66 | 726.66 | 96.5% | 0 | 141.4 | 141.4 |  | 13981 | 635.43 | -13345.57 | -95.46% | 40 | 86 | 46 | 115% | 2019-01-18 01:00
Markham | 2020 | 315381 | (WO 315381) Stub Pole and Guyung Reloc - NEW HUNGTINGTON RD | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-13 01:00
Markham | 2019 | 315521 | (WO315521) 8451 & 8457 Islington Avenue | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 155679.89 | 159444.74 | 3764.85 | 2.418% | 13379.32 | 88921.18 | 75541.86 | 564.6% | 4473.96 | 66453.5 | 61979.54 | 1385% | 2368.21 | 319.76 | -2048.45 | -86.5% | 135458.4 | 3750.3 | -131708.1 | -97.23% | 171 | 167.25 | -3.75 | -2.193% | 2019-03-30 01:00
Markham | 2019 | 315692 | ( WO 315692) GERMANA PLACE DEVELOPMENT | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Alarcon, Alejandro | Steve Rumble | 60794.02 | 54574.58 | -6219.44 | -10.23% | 8886.32 | 0 | -8886.32 | -100% | 687.84 | 0 | -687.84 | -100% | 548.94 | 0 | -548.94 | -100% | 50670.92 | 0 | -50670.92 | -100% | 126.5 | 67 | -59.5 | -47.04% | 2019-07-26 01:00
Markham | 2019 | 315723 | (WO 315723) 275 Woodbridge Avenue | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Dibratto, Susan | Steve Rumble | 79356.23 | 36961.63 | -42394.6 | -53.42% | 17710.16 | 27822.08 | 10111.92 | 57.1% | 10405.02 | 8419.13 | -1985.89 | -19.09% | 3130.05 | 680.57 | -2449.48 | -78.26% | 48111 | 39.85 | -48071.15 | -99.92% | 236 | 292 | 56 | 23.73% | 2019-02-02 01:00
Markham | 2019 | 315906 | (WO315906) Prima Vista Estates - Phase 1. Teston Road & Pine Valley Drive | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 59373.48 | 39661.36 | -19712.12 | -33.2% | 34981.95 | 0 | -34981.95 | -100% | 9863.98 | 0 | -9863.98 | -100% | 7440.05 | 0 | -7440.05 | -100% | 7087.5 | 0 | -7087.5 | -100% | 467 | 254.25 | -212.75 | -45.56% | 2019-02-08 01:00
Markham | 2019 | 315929 | (WO315929) Mosaik Phase 3 - Block 40/47 | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 29388.56 | 20587.59 | -8800.97 | -29.95% | 14405.68 | 0 | -14405.68 | -100% | 8464.5 | 0 | -8464.5 | -100% | 2843.38 | 0 | -2843.38 | -100% | 3675 | 0 | -3675 | -100% | 193 | 120.25 | -72.75 | -37.69% | 2019-02-08 01:00
Markham | 2019 | 316139 | ( WO 316139) Proposed Townhouse Development | 99 | COMPLETE | Converted Project |  |  |  | No | Dibratto, Susan | Steve Rumble | 73111.48 | 0 | -73111.48 | -100% | 14510.29 | 0 | -14510.29 | -100% | 20530.29 | 0 | -20530.29 | -100% | 2610.3 | 0 | -2610.3 | -100% | 35460.6 | 0 | -35460.6 | -100% | 193 | 129.5 | -63.5 | -32.9% | 2019-09-13 01:00
Markham | 2019 | 316185 | (WO 316185) Vaughan Mills (Tesla) | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 316191 | (WO 316191) Pole Relocation Leslie St Stouffville Rd to Bloomington Rd | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 316270 | (WO 316270) 161 Milani Blvd | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 316300 | (WO316300) 2381423 Ontario Inc | 99 | CANCELLED | N/A |  |  |  | No | Graham, Bruce W. | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 316314 | ( WO 316314) 77 EAGLEVIEW HEIGHTS PH 2 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 0 | 322679.59 | 322679.59 |  | 0 | 115361.24 | 115361.24 |  | 0 | 199677.33 | 199677.33 |  | 0 | 141.02 | 141.02 |  | 0 | 7500 | 7500 |  | 0 | 137 | 137 |  | 2019-07-26 01:00
Markham | 2019 | 316318 | (WO 316318) PEAK GARDENS PHASE 2 - 3947 HWY 7 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Alarcon, Alejandro | Steve Rumble | 84116.13 | 0 | -84116.13 | -100% | 13818.32 | 0 | -13818.32 | -100% | 2041.93 | 0 | -2041.93 | -100% | 2109.03 | 0 | -2109.03 | -100% | 66146.85 | 0 | -66146.85 | -100% | 186 | 0 | -186 | -100% | 2019-07-26 01:00
Markham | 2019 | 316392 | (WO316392 ) 100 Lawford Rd | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 34735.3 | 28784.87 | -5950.43 | -17.13% | 8617.56 | 10957.67 | 2340.11 | 27.16% | 14490 | 15563.09 | 1073.09 | 7.406% | 2217.6 | 2234.56 | 16.96 | 0.7648% | 5250 | 29.55 | -5220.45 | -99.44% | 136 | 115 | -21 | -15.44% | 2019-02-01 01:00
Markham | 2019 | 316428 | ( WO 316428) Steeles and New Westminister - Phase 3 | 99 | COMPLETE | Labour est. over | Civil contractor | N/A |  | No | Chiuco, Joseph-x | Cory Ruiter | 974628 | 838310.25 | -136317.75 | -13.99% | 21059 | 48939.98 | 27880.98 | 132.4% | 0 | 109703.2 | 109703.2 |  | 3696 | 0 | -3696 | -100% | 949873 | 679667.07 | -270205.93 | -28.45% | 280 | 102.5 | -177.5 | -63.39% | 2019-01-03 01:00
Markham | 2019 | 316464 | (WO 316464) 1600 Major Mackenzie Dr E | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 316511 | ( WO 316511) ADENA VIEWS SUBDIVISION | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Perks, Dan | Steve Rumble | 311187.56 | 269384.73 | -41802.83 | -13.43% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3499.76 | 0 | -3499.76 | -100% | 307687.8 | 0 | -307687.8 | -100% | 368.7 | 241 | -127.7 | -34.64% | 2019-07-26 01:00
Markham | 2019 | 316549 | (WO 316549) Joint Use 17-054 Make Ready | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Battistella, Alexander | Macdonald, Larry | 14646 | 9943.48 | -4702.52 | -32.11% | 4370 | 2742.05 | -1627.95 | -37.25% | 2983 | 2382.58 | -600.42 | -20.13% | 883 | 303.99 | -579.01 | -65.57% | 6410 | 4514.86 | -1895.14 | -29.57% | 58.23 | 39.4 | -18.83 | -32.34% | 2019-03-21 01:00
Markham | 2019 | 316581 | (WO316581) Regent St. Development | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Graham, Bruce W. | Steve Rumble | 96870.93 | 98966.52 | 2095.59 | 2.163% | 12280.1 | 66004.97 | 53724.87 | 437.5% | 2131.28 | 30147.34 | 28016.06 | 1315% | 1893.05 | 204.21 | -1688.84 | -89.21% | 80566.5 | 2610 | -77956.5 | -96.76% | 162 | 172.5 | 10.5 | 6.481% | 2019-03-26 01:00
Markham | 2019 | 316686 | (WO 316686) 7875 Hwy 50 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 316717 | (WO 316717) 150 NEW HUNTINGTON RD | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 316806 | (WO316806) 32 WELLINGTON ST. AURORA | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Harris, Geoff L. | Steve Rumble | 44901.84 | 45862.65 | 960.81 | 2.14% | 12101.08 | 22348.06 | 10246.98 | 84.68% | 21223.36 | 20770.29 | -453.07 | -2.135% | 2252.25 | 2744.3 | 492.05 | 21.85% | 9074.71 | 0 | -9074.71 | -100% | 162.5 | 196 | 33.5 | 20.62% | 2019-01-15 01:00
Markham | 2019 | 316841 | (WO 316841) JU 17-094 Bullock Drive | 99 | COMPLETE | Labour est. under | No Feedback from Const | N/A |  | No | Battistella, Alexander | Macdonald, Larry | 13940 | 16727.82 | 2787.82 | 20% | 5528 | 8371.52 | 2843.52 | 51.44% | 314 | 2003 | 1689 | 537.9% | 1063 | 0 | -1063 | -100% | 7035 | 6353.3 | -681.7 | -9.69% | 66 | 120 | 54 | 81.82% | 2019-01-17 01:00
Markham | 2019 | 316894 | (WO316894) Pavilia Park Towns. Highway 7 & Saddlecreek Dr | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 181666.76 | 192616.68 | 10949.92 | 6.027% | 23104.8 | 0 | -23104.8 | -100% | 2271.06 | 0 | -2271.06 | -100% | 2779.85 | 0 | -2779.85 | -100% | 153511.05 | 0 | -153511.05 | -100% | 299 | 406 | 107 | 35.79% | 2019-02-12 01:00
Markham | 2019 | 316911 | (WO316911) 7200 Victoria Park Ave | 99 | CANCELLED | Engineering by-passed | N/A |  |  | No | Yuen, Paul | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 316918 | (WO316918) 388 Spinnaker Way | 99 | COMPLETE | Converted Project |  |  |  | No | Paterson, Greg | Steve Rumble | 32681.25 | 0 | -32681.25 | -100% | 7722.75 | 0 | -7722.75 | -100% | 24150 | 0 | -24150 | -100% | 808.5 | 0 | -808.5 | -100% | 0 | 0 | 0 |  | 93 | 67.5 | -25.5 | -27.42% | 2019-09-13 01:00
Markham | 2019 | 316922 | (WO316922) S/GEAR RELOCATION - CANADA DRIVE & VEDETTE WAY - CANADA DR - S/GEAR RELOCATI | 99 | COMPLETE | Scope – Eng | Weather | Labour est. under |  | No | Zhang, Jiacheng | Lamb, Tim | 143810 | 151770.2 | 7960.2 | 5.535% | 71640 | 23271.38 | -48368.62 | -67.52% | 1886 | 57364.82 | 55478.82 | 2942% | 4066 | 6865.22 | 2799.22 | 68.84% | 66218 | 64268.78 | -1949.22 | -2.944% | 226 | 281.5 | 55.5 | 24.56% | 2019-02-12 01:00
Markham | 2019 | 316942 | ( WO 316942) Larkin Ave, M15 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Alectra Utilities | Lamb, Tim | 113970 | 166260.5 | 52290.5 | 45.88% | 9737 | 14083 | 4346 | 44.63% | 412 | 25246.17 | 24834.17 | 6028% | 1386 | 385.45 | -1000.55 | -72.19% | 0 | 126545.88 | 126545.88 |  | 135 | 221.5 | 86.5 | 64.07% | 2019-07-26 01:00
Markham | 2019 | 316993 | (WO316993) Main Monarch Castlepoint N Ph2. S/O KIRBY RD. & W/O KIPLING AVE. | 99 | COMPLETE | Engineering by-passed | N/A |  |  | No | Estrada, Michael | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 317008 | (WO 317008) JU 17-126 Pole Replacement and Down guy replacement | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Battistella, Alexander | Macdonald, Larry | 33900 | 27332.65 | -6567.35 | -19.37% | 12750 | 10738.99 | -2011.01 | -15.77% | 9238 | 8432.85 | -805.15 | -8.716% | 3486 | 816.05 | -2669.95 | -76.59% | 8426 | 7344.76 | -1081.24 | -12.83% | 170.9 | 121.15 | -49.75 | -29.11% | 2019-02-20 01:00
Markham | 2019 | 317040 | ( WO 317040) Transformer Relocation - LOT 104 STARKWEATHER STREET | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Fitz Randolph, Kim C | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 317075 | (WO 317075) Joint Use 17-130 Rivermede & Bowes RD | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Battistella, Alexander | Macdonald, Larry | 7965 | 7821.24 | -143.76 | -1.805% | 2226 | 2063.65 | -162.35 | -7.293% | 236 | 340 | 104 | 44.07% | 336 | 0 | -336 | -100% | 5167 | 5417.59 | 250.59 | 4.85% | 29.53 | 31.9 | 2.37 | 8.026% | 2019-02-01 01:00
Markham | 2019 | 317081 | (WO317081) Snidercroft Rd. - #211 | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Yuen, Paul | Steve Rumble | 72576.62 | 38602.58 | -33974.04 | -46.81% | 18489.08 | 17463.79 | -1025.29 | -5.545% | 41524.39 | 18504.16 | -23020.23 | -55.44% | 3361.05 | 2634.63 | -726.42 | -21.61% | 0 | 0 | 0 |  | 227.5 | 102.25 | -125.25 | -55.05% | 2019-01-16 01:00
Markham | 2019 | 317115 | ( WO 317115) Pole Installation future riser - LENNOX AVE - PARENT W.O. FOR UNPLANNED | 99 | COMPLETE |  | N/A | N/A |  | No | Alarcon, Alejandro | Steve Rumble | 0 | 31577.27 | 31577.27 |  | 0 | 30881.27 | 30881.27 |  | 0 | 696 | 696 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 317228 | ( WO 317228) REPLACE 8 SWITCHGEARS IN V31 | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Gonzales, Leonard | Lamb, Tim | 460856 | 495824.57 | 34968.57 | 7.588% | 44841 | 63206.3 | 18365.3 | 40.96% | 390255 | 377190.82 | -13064.18 | -3.348% | 11002 | 55427.45 | 44425.45 | 403.8% | 14758 | 0 | -14758 | -100% | 521.65 | 477.5 | -44.15 | -8.464% | 2019-07-26 01:00
Markham | 2019 | 317235 | ( WO 317235) REPLACE A05SP2011 | 99 | COMPLETE | Labour est. over | Filler work | N/A |  | No | Gonzales, Leonard | Lamb, Tim | 23641.25 | 8238.66 | -15402.59 | -65.15% | 2200 | 5198.82 | 2998.82 | 136.3% | 20341.25 | 2718.99 | -17622.26 | -86.63% | 1100 | 320.85 | -779.15 | -70.83% | 0 | 0 | 0 |  | 83 | 66 | -17 | -20.48% | 2019-01-24 01:00
Markham | 2019 | 317237 | (WO 317237) REPLACE A05SP2008 | 99 | COMPLETE | Labour est. over | Filler work | N/A |  | No | Roy, James | Lamb, Tim | 41962 | 30551.27 | -11410.73 | -27.19% | 7105 | 6338.39 | -766.61 | -10.79% | 24796 | 21254.9 | -3541.1 | -14.28% | 1733 | 2957.98 | 1224.98 | 70.69% | 8328 | 0 | -8328 | -100% | 95 | 87.25 | -7.75 | -8.158% | 2019-02-01 01:00
Markham | 2019 | 317273 | (WO 317273) Replace 12 Transformers in V53 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Gonzales, Leonard | Steve Rumble | 208349 | 206704.49 | -1644.51 | -0.7893% | 44995 | 33919.71 | -11075.29 | -24.61% | 101453 | 81902.06 | -19550.94 | -19.27% | 12679 | 11613.91 | -1065.09 | -8.4% | 49222 | 79268.81 | 30046.81 | 61.04% | 597.86 | 295.5 | -302.36 | -50.57% | 2019-07-26 01:00
Markham | 2019 | 317286 | ( WO 317286) Replace 11 Transformers in V26 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Roy, James | Steve Rumble | 132132 | 91802.92 | -40329.08 | -30.52% | 48204 | 33332.52 | -14871.48 | -30.85% | 68741 | 46358.41 | -22382.59 | -32.56% | 11365 | 6908.91 | -4456.09 | -39.21% | 3822 | 5203.08 | 1381.08 | 36.14% | 657 | 114 | -543 | -82.65% | 2019-07-26 01:00
Markham | 2019 | 317296 | ( WO 317296) Replace V39TP1001 | 99 | COMPLETE | Labour est. over | Filler work | N/A |  | No | Roy, James | Steve Rumble | 10707 | 8264.96 | -2442.04 | -22.81% | 4551 | 3548.99 | -1002.01 | -22.02% | 5036 | 4138.01 | -897.99 | -17.83% | 1120 | 577.96 | -542.04 | -48.4% | 0 | 0 | 0 |  | 49 | 47.65 | -1.35 | -2.755% | 2019-01-31 01:00
Markham | 2019 | 317334 | (WO 317334) Toronto Montessori School - Vault to Pad Conversion | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Dibratto, Susan | Steve Rumble | 83851 | 63338.3 | -20512.7 | -24.46% | 14324.52 | 46795.91 | 32471.39 | 226.7% | 35201.98 | 14693.16 | -20508.82 | -58.26% | 3696 | 1849.23 | -1846.77 | -49.97% | 30628.5 | 0 | -30628.5 | -100% | 200 | 167.5 | -32.5 | -16.25% | 2019-07-26 01:00
Markham | 2019 | 317375 | (WO317375) Expo Condos Ph 3 & 4 | 99 | CANCELLED | Engineering by-passed | N/A |  |  | No | Dibratto, Susan | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 317380 | (WO 317380) 22 Esna Park Dr | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 317403 | (WO 317403) Esso Gas Station | 99 | COMPLETE | Converted Project |  |  |  | No | Paterson, Greg | Steve Rumble | 56053.79 | 0 | -56053.79 | -100% | 12648.1 | 0 | -12648.1 | -100% | 24397.54 | 0 | -24397.54 | -100% | 3153.15 | 0 | -3153.15 | -100% | 15855 | 0 | -15855 | -100% | 176.5 | 141 | -35.5 | -20.11% | 2019-09-13 01:00
Markham | 2019 | 317404 | (WO 317404) 7233 Hwy 27 | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 317442 | ( WO 317442) (M44) - Konrad Cr (690m) | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Alectra Utilities | Lamb, Tim | 199300 | 166282.82 | -33017.18 | -16.57% | 22193 | 16109.3 | -6083.7 | -27.41% | 953 | 19888 | 18935 | 1987% | 4481 | 0 | -4481 | -100% | 171673 | 130285.52 | -41387.48 | -24.11% | 274 | 106 | -168 | -61.31% | 2019-07-26 01:00
Markham | 2019 | 317663 | (WO317663) Royal Richmond - 305 Bloomington Rd | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Estrada, Michael | Steve Rumble | 263476.56 | 259896.61 | -3579.95 | -1.359% | 17008.15 | 0 | -17008.15 | -100% | 5872.11 | 0 | -5872.11 | -100% | 3141.95 | 0 | -3141.95 | -100% | 237454.35 | 0 | -237454.35 | -100% | 230 | 219.5 | -10.5 | -4.565% | 2019-02-15 01:00
Markham | 2019 | 317709 | (WO 317709) 407 and Woodbine Ave | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-02 01:00
Markham | 2019 | 317789 | (WO317789) 10483 Islington Ave | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 317825 | (WO 317825) UG Secondary Service Relocation - 54 Sanderson cr | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Alectra Utilities | Lamb, Tim | 17719 | 585.51 | -17133.49 | -96.7% | 3984 | 585.51 | -3398.49 | -85.3% | 53 | 0 | -53 | -100% | 583 | 0 | -583 | -100% | 13099 | 0 | -13099 | -100% | 55.25 | 0 | -55.25 | -100% | 2019-07-26 01:00
Markham | 2019 | 318091 | (WO 318091) 16th Avenue - Pole Repl. | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-06 01:00
Markham | 2019 | 318093 | (WO 318093) Huntington Road- Pole Repl | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-06 01:00
Markham | 2019 | 318109 | (WO318109) Redstone Townhomes | 99 | CANCELLED | N/A |  |  |  | No | Yuen, Paul | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-06 01:00
Markham | 2019 | 318149 | (WO 318149) JU 18-065 | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Battistella, Alexander | Macdonald, Larry | 11976 | 14586.32 | 2610.32 | 21.8% | 4687 | 10911 | 6224 | 132.8% | 1184 | 287.82 | -896.18 | -75.69% | 832 | 41.07 | -790.93 | -95.06% | 5273 | 3346.43 | -1926.57 | -36.54% | 56 | 14.5 | -41.5 | -74.11% | 2019-04-06 01:00
Markham | 2019 | 318214 | (WO318214) 201 Staffern Dr | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 12089.7 | 5910.6 | -6179.1 | -51.11% | 7312.2 | 4468.28 | -2843.92 | -38.89% | 3622.5 | 1279.63 | -2342.87 | -64.68% | 1155 | 162.69 | -992.31 | -85.91% | 0 | 0 | 0 |  | 90 | 62 | -28 | -31.11% | 2019-07-26 01:00
Markham | 2019 | 318221 | (WO 318221) Relocations for Vaughan Sidewalks | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Barry, Kenneth | Macdonald, Larry | 18883 | 14619.95 | -4263.05 | -22.58% | 10486 | 10962.56 | 476.56 | 4.545% | 2570 | 3341.56 | 771.56 | 30.02% | 2117 | 315.83 | -1801.17 | -85.08% | 3710 | 0 | -3710 | -100% | 133.31 | 115 | -18.31 | -13.73% | 2019-04-13 01:00
Markham | 2019 | 318222 | (WO 318222) Relocations for Markham Sidwalks | 99 | COMPLETE | Converted Project |  |  |  | No | Battistella, Alexander | Macdonald, Larry | 22239 | 32165.42 | 9926.42 | 44.64% | 10678 | 21906.56 | 11228.56 | 105.2% | 3977 | 6670.49 | 2693.49 | 67.73% | 1894 | 828.37 | -1065.63 | -56.26% | 5690 | 2760 | -2930 | -51.49% | 60 | 68 | 8 | 13.33% | 2019-03-08 01:00
Markham | 2019 | 318291 | (WO 318291) - Primary Service Fitness center. 325 Woodbridge Ave | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Yuen, Paul | Steve Rumble | 113578.97 | 129519.68 | 15940.71 | 14.03% | 14137.41 | 89435.9 | 75298.49 | 532.6% | 21164.83 | 35304.5 | 14139.67 | 66.81% | 3418.8 | 4779.28 | 1360.48 | 39.79% | 20359.56 | 0 | -20359.56 | -100% | 299 | 290.75 | -8.25 | -2.759% | 2019-03-07 01:00
Markham | 2019 | 318305 | (WO318305) Pole Relocation - Victoria Square Blvd | 99 | COMPLETE | Converted Project |  |  |  | No | Alarcon, Alejandro | Macdonald, Larry | 31267 | 20574.12 | -10692.88 | -34.2% | 13847 | 10848.27 | -2998.73 | -21.66% | 9453 | 8096.97 | -1356.03 | -14.34% | 3912 | 808.05 | -3103.95 | -79.34% | 4055 | 820.83 | -3234.17 | -79.76% | 177 | 125.5 | -51.5 | -29.1% | 2019-03-15 01:00
Markham | 2019 | 318440 | (WO 318440) JU 17-156 | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Battistella, Alexander | Macdonald, Larry | 11752 | 7487.73 | -4264.27 | -36.29% | 4947 | 4400.91 | -546.09 | -11.04% | 933 | 1483.22 | 550.22 | 58.97% | 912 | 124.46 | -787.54 | -86.35% | 4960 | 1479.14 | -3480.86 | -70.18% | 59.5 | 47 | -12.5 | -21.01% | 2019-03-22 01:00
Markham | 2019 | 318447 | (WO 318447) Pole Relocation - 4671 14th Avenue, Markham | 99 | CANCELLED | N/A |  |  |  | No | Barry, Kenneth | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2020 | 318487 | (WO 318487) BELL COMMUNICATION BONDS | 99 | COMPLETE | Converted Project |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 318503 | (WO318503) George Kirby and Ilan Ramon | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Graham, Bruce W. | Cory Ruiter | 0 | 14304.89 | 14304.89 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 318511 | (WO 318511) Road Widening - Elgin Mills Road W, Bathurst to Yonge, Richmond Hill | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-19 01:00
Markham | 2019 | 318587 | (WO 318587) 145 GIBRALTAR ROAD | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Dibratto, Susan | Steve Rumble | 123526.87 | 104357.87 | -19169 | -15.52% | 10453.57 | 14138.52 | 3684.95 | 35.25% | 93637.97 | 78637.95 | -15000.02 | -16.02% | 2621.85 | 11511.75 | 8889.9 | 339.1% | 12874.13 | 69.65 | -12804.48 | -99.46% | 154 | 183.5 | 29.5 | 19.16% | 2019-02-19 01:00
Markham | 2019 | 318600 | (WO 318600) 2019 Pole Replacement Batch 01 | 99 | COMPLETE | Converted Project |  |  |  | No | Roy, James | Shortt, Derek B. | 185386 | 110881.47 | -74504.53 | -40.19% | 94743 | 70055.16 | -24687.84 | -26.06% | 35707 | 37814.99 | 2107.99 | 5.904% | 27636 | 3011.32 | -24624.68 | -89.1% | 27300 | 0 | -27300 | -100% | 1086.35 | 887.5 | -198.85 | -18.3% | 2019-03-15 01:00
Markham | 2019 | 318605 | (WO 318605) Westwood Gardens Pole Relocation | 99 | COMPLETE | Converted Project |  |  |  | No | Barry, Kenneth | Macdonald, Larry | 16035 | 17879.04 | 1844.04 | 11.5% | 6419 | 14010.19 | 7591.19 | 118.3% | 6611 | 3066.04 | -3544.96 | -53.62% | 1283 | 457.81 | -825.19 | -64.32% | 1722 | 345 | -1377 | -79.97% | 85.52 | 27.25 | -58.27 | -68.14% | 2019-01-15 01:00
Markham | 2019 | 318609 | 318609 - 20 Baif Blvd. Cable replacement | 99 | COMPLETE | Converted Project |  |  |  | No | Chiuco, Joseph-x | Lamb, Tim | 89952 | 1951.28 | -88000.72 | -97.83% | 7995 | 1797.28 | -6197.72 | -77.52% | 617 | 154 | -463 | -75.04% | 1582 | 0 | -1582 | -100% | 79758 | 0 | -79758 | -100% | 106.5 | 23.5 | -83 | -77.93% | 2019-01-16 01:00
Markham | 2019 | 318612 | (WO 318612) 8125 Highway 50 | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Dibratto, Susan | Steve Rumble | 78259.4 | 56057.15 | -22202.25 | -28.37% | 10453.57 | 13773.41 | 3319.84 | 31.76% | 43730.88 | 36919.84 | -6811.04 | -15.57% | 2945.25 | 5363.9 | 2418.65 | 82.12% | 14217 | 0 | -14217 | -100% | 167.5 | 179.5 | 12 | 7.164% | 2019-01-16 01:00
Markham | 2019 | 318640 | (WO318640) 2019 - Pdmt TX Rep. Batch 7 | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Steve Rumble | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-03 01:00
Markham | 2019 | 318691 | (WO318691) Repl. Switchgear - Batch 1 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A |  | No | Handy, James | Steve Rumble | 96374 | 106230.78 | 9856.78 | 10.23% | 16758 | 34416.62 | 17658.62 | 105.4% | 75597 | 62447.1 | -13149.9 | -17.39% | 4019 | 9367.06 | 5348.06 | 133.1% | 0 | 0 | 0 |  | 224 | 0 | -224 | -100% | 2019-04-03 01:00
Markham | 2019 | 318702 | (WO 318702) JU 18-045 Anchor and Down Guy Installation | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Battistella, Alexander | Macdonald, Larry | 6909 | 3357.42 | -3551.58 | -51.41% | 2379 | 453.26 | -1925.74 | -80.95% | 839 | 359.83 | -479.17 | -57.11% | 383 | 51.87 | -331.13 | -86.46% | 3308 | 2492.46 | -815.54 | -24.65% | 31.59 | 12.4 | -19.19 | -60.75% | 2019-02-07 01:00
Markham | 2019 | 318704 | (WO 318704) 18-120 Rogers JU Application | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-11 01:00
Markham | 2019 | 318706 | (WO 318706) Hydro Relocation- STEELES AV E - KENNEDY TO MIDLAND | 99 | CANCELLED | N/A |  |  |  | No | Chiuco, Joseph-x | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-11 01:00
Markham | 2019 | 318727 | (WO 318727) 18-106 Rogers JU Application | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-20 01:00
Markham | 2019 | 318728 | (WO 318728) 18-103 Rogers JU Application | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-20 01:00
Markham | 2019 | 318729 | (WO 318729) 18-137 Rogers JU Application | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-20 01:00
Markham | 2019 | 318730 | (WO 318730) 18-131 Rogers JU Application | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-20 01:00
Markham | 2019 | 318732 | (WO 318732) 18-097 Rogers JU Application | 99 | COMPLETE | Labour est. over | No Feedback from Const | N/A |  | No | Battistella, Alexander | Macdonald, Larry | 4525 | 2413.56 | -2111.44 | -46.66% | 2679 | 2057.56 | -621.44 | -23.2% | 371 | 356 | -15 | -4.043% | 468 | 0 | -468 | -100% | 1007 | 0 | -1007 | -100% | 34 | 31.25 | -2.75 | -8.088% | 2019-03-20 01:00
Markham | 2019 | 318754 | (WO 318754) Span Pole Removal 63 Larmont St | 99 | COMPLETE | Converted Project |  |  |  | No | Battistella, Alexander | Macdonald, Larry | 18781 | 15694.71 | -3086.29 | -16.43% | 11539 | 5508.69 | -6030.31 | -52.26% | 1597 | 7138.71 | 5541.71 | 347% | 3260 | 862.31 | -2397.69 | -73.55% | 2385 | 2185 | -200 | -8.386% | 147.5 | 81.25 | -66.25 | -44.92% | 2019-03-29 01:00
Markham | 2019 | 318764 | (WO 318764) Remove Pole P25069 | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-18 01:00
Markham | 2020 | 318782 | (WO 318782) X95153 Bell Bonding | 99 | COMPLETE | Converted Project |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-18 01:00
Markham | 2019 | 318816 | (WO 318816) Replace Pole P23136 - Markham | 99 | COMPLETE | Converted Project |  |  |  | No | Canale, Alfred | Macdonald, Steve | 21894 | 24539.59 | 2645.59 | 12.08% | 10119 | 16840.23 | 6721.23 | 66.42% | 2230 | 5245.07 | 3015.07 | 135.2% | 2195 | 786.77 | -1408.23 | -64.16% | 7350 | 1667.52 | -5682.48 | -77.31% | 135 | 37.5 | -97.5 | -72.22% | 2019-03-18 01:00
Markham | 2019 | 318817 | (WO 318817) Replace Pole P50098 - Markham | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A |  | No | Canale, Alfred | Macdonald, Steve | 15906 | 19505.82 | 3599.82 | 22.63% | 7059 | 17632.89 | 10573.89 | 149.8% | 1448 | -60.9 | -1508.9 | -104.2% | 2014 | -11.24 | -2025.24 | -100.6% | 5385 | 1945.07 | -3439.93 | -63.88% | 90.3 | 31 | -59.3 | -65.67% | 2019-03-20 01:00
Markham | 2019 | 318833 | (WO 318833) 2019 3 Rpl Pole - Markham | 99 | CANCELLED | N/A |  |  |  | No | Canale, Alfred | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-04 01:00
Markham | 2019 | 318835 | (WO 318835) 2019 5 Rpl Pole - Markham | 99 | CANCELLED | N/A |  |  |  | No | Canale, Alfred | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-04 01:00
Markham | 2019 | 318874 | (WO318874) 2019 Distribution Automation. RUTHERFORD RD E/O JANE ST | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-04 01:00
Markham | 2019 | 318941 | (WO 318941) Transfer cct HONI pole - Yonge | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Shortt, Derek B. | 5789 | 146.79 | -5642.21 | -97.46% | 4120 | 146.79 | -3973.21 | -96.44% | 745 | 0 | -745 | -100% | 924 | 0 | -924 | -100% | 0 | 0 | 0 |  | 40 | 6.75 | -33.25 | -83.12% | 2019-03-04 01:00
Markham | 2020 | 318942 | (WO 318942) Transfr cct HONI pole - Aurora | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-04 01:00
Markham | 2019 | 318950 | (WO 318950) Transfr cct HONI pole - Aurora | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Shortt, Derek B. | 8221 | 146.79 | -8074.21 | -98.21% | 6203 | 146.79 | -6056.21 | -97.63% | 447 | 0 | -447 | -100% | 1571 | 0 | -1571 | -100% | 0 | 0 | 0 |  | 83 | 6.75 | -76.25 | -91.87% | 2019-03-04 01:00
Markham | 2019 | 318985 | (WO 318985) Batch 14 - Replace 9 Poles | 99 | CANCELLED | N/A |  |  |  | No | Canale, Alfred | Shortt, Derek B. | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-04 01:00
Markham | 2019 | 319010 | (WO 319010) Batch 16 - Replace 11 Poles | 99 | CANCELLED | N/A |  |  |  | No | Canale, Alfred | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-04 01:00
Markham | 2019 | 319026 | (WO319026) 241 Hanlan Rd | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Paterson, Greg | Steve Rumble | 27271.9344 | 27859.13 | 587.1956 | 2.153% | 6051.4764 | 9277.01 | 3225.5336 | 53.3% | 18285 | 16264.21 | -2020.79 | -11.05% | 1504.458 | 2317.91 | 813.452 | 54.07% | 0 | 0 | 0 |  | 85 | 145.5 | 60.5 | 71.18% | 2019-03-04 01:00
Markham | 2020 | 319112 | (WO 319112) Rogers Bonds | 99 | COMPLETE | Converted Project |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-05 01:00
Markham | 2019 | 319173 | (WO 319173) Pole Relocation- 13200 YONGE STREET, RICHMOND HILL | 99 | COMPLETE | Converted Project |  |  |  | No | Battistella, Alexander | Macdonald, Steve | 15607 | 8324.89 | -7282.11 | -46.66% | 8534 | 4446.29 | -4087.71 | -47.9% | 2769 | 3540.96 | 771.96 | 27.88% | 2608 | 337.64 | -2270.36 | -87.05% | 1696 | 0 | -1696 | -100% | 103 | 52.5 | -50.5 | -49.03% | 2019-04-05 01:00
Markham | 2019 | 319216 | (WO 319216) Batch 18 - Replace 4 Poles | 99 | CANCELLED | N/A |  |  |  | No | Canale, Alfred | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-09
Markham | 2019 | 319345 | (WO 319345) Replace P27562 - 341 Steelcase Rd W., Markham | 99 | CANCELLED | N/A |  |  |  | No | Canale, Alfred | Shortt, Derek B. | 58795 | 0 | -58795 | -100% | 19604 | 0 | -19604 | -100% | 7296 | 0 | -7296 | -100% | 6655 | 0 | -6655 | -100% | 25240 | 0 | -25240 | -100% | 0 | 0 | 0 |  | 2019-05-09
Markham | 2019 | 319500 | (WO 319500) Transfer cct HONI pole - RHYONGE & REGATTA - RICHMOND HILL | 99 | CANCELLED | N/A |  |  |  | No | Roy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-09
Markham | 2022 | 452428 | 452428 - 1623 Wellington Street Developments | 99 | ANALYZE |  |  |  | Penner, Mitchell | No | Swales, Mathew | Dave Lindsay | 221288.4 | 218589.61 | -2698.79 | -1.22% | 28375.35 | 37193.1 | 8817.75 | 31.08% | 11721.94 | 12100.01 | 378.07 | 3.225% | 2726.51 | 4051.5 | 1324.99 | 48.6% | 178464.6 | 165245 | -13219.6 | -7.407% | 119.32 | 152 | 32.68 | 27.39% | 2022-05-05
Markham | 2020 | 452449 | (WO310192) Steeles Ave. west at Keele St. | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Persaud, Ryan | 0 | 2513.9 | 2513.9 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-10 01:00
Markham | 2022 | 452457 | (WO310938) The Remington Centre | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Yuen, Paul | Persaud, Ryan | 0 | 1168.82 | 1168.82 |  | 0 | 1168.82 | 1168.82 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 |  | 2019-07-26 01:00
Markham | 2019 | 452476 | ( WO 312394) CORNELL ROUGE PH 4D | 99 | COMPLETE | Engineering by-passed | N/A | N/A | D'Onofrio, Tony | No | Kinsella, William P | Cory Ruiter | 0 | 1706182.89 | 1706182.89 |  | 0 | 459 | 459 |  | 0 | 7289.79 | 7289.79 |  | 0 | 810.31 | 810.31 |  | 0 | 30356.25 | 30356.25 |  | 0 | 547.5 | 547.5 |  | 2019-07-26 01:00
Markham | 2021 | 452482 | 452482 (WO 312575) JANE ST. #9075 & #9085 AT RIVERROCK GATE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 371556.59 | 284602.69 | -86953.9 | -23.4% | 28129.85 | 31038.1 | 2908.25 | 10.34% | 121666.69 | 125397.11 | 3730.42 | 3.066% | 2970.41 | 1905.35 | -1065.06 | -35.86% | 218789.64 | 121172.83 | -97616.81 | -44.62% | 345.8 | 210.6 | -135.2 | -39.1% | 2021-02-08 01:00
Markham | 2020 | 452504 | 452504 (WO 313019) A12 - Addison Hall Business Park | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 1479539.41 | 1561882.4 | 82342.99 | 5.565% | 28413.74 | 102884.57 | 74470.83 | 262.1% | 25478.36 | 34825.66 | 9347.3 | 36.69% | 6548.16 | 4828.06 | -1720.1 | -26.27% | 1419099.15 | 667336.4 | -751762.75 | -52.97% | 373 | 462.05 | 89.05 | 23.87% | 2020-10-14 01:00
Markham | 2019 | 452509 | (WO 313222) WyView Subdivision | 99 | COMPLETE | Engineering by-passed |  |  | D'Onofrio, Tony | No | Alarcon, Alejandro | Steve Rumble | 213896.9621 | 195891.48 | -18005.4821 | -8.418% | 34787.979 | 7953.44 | -26834.539 | -77.14% | 15327.8279 | 0 | -15327.8279 | -100% | 10212.5952 | 738 | -9474.5952 | -92.77% | 153568.56 | 12544.79 | -141023.77 | -91.83% | 0 | 50 | 50 |  | 2019-07-26 01:00
Markham | 2019 | 452520 | 452520 (WO 313379) Highway No. 7 East - #3972 | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 78437.46 | 17121.1 | -61316.36 | -78.17% | 15403.82 | 432.27 | -14971.55 | -97.19% | 40736.63 | 2905.36 | -37831.27 | -92.87% | 0 | 0 | 0 |  | 18939.25 | 0 | -18939.25 | -100% | 182 | 172.25 | -9.75 | -5.357% | 2019-10-09 01:00
Markham | 2021 | 452521 | 452521 - UG RELOCATION/GLEN SHIELDS AVE BRIDGE, VAUGH | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Horlings, Jake | 520225.58 | 508041.98 | -12183.6 | -2.342% | 40702.42 | 63682.04 | 22979.62 | 56.46% | 3995.2 | 5671.17 | 1675.97 | 41.95% | 3640.32 | 5429 | 1788.68 | 49.14% | 471887.64 | 391286.85 | -80600.79 | -17.08% | 294.12 | 275.5 | -18.62 | -6.331% | 2021-06-23 01:00
Markham | 2021 | 452528 | 452528 (WO 313534) St. John's Sideroad- Bayview Ave To Hwy 404 | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Barry, Kenneth | Macdonald, Steve | 1092760.45 | 1194078.91 | 101318.46 | 9.272% | 40619.64 | 99687.33 | 59067.69 | 145.4% | 370441.57 | 412986.8 | 42545.23 | 11.49% | 0 | 0 | 0 |  | 681699.24 | 681404.78 | -294.46 | -0.0432% | 8 | 34 | 26 | 325% | 2021-03-08 01:00
Markham | 2020 | 452530 | (WO313541) 77 Woodstream Blvd | 99 | CANCELLED | N/A |  |  | Stephens, Barry N. | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 452532 | ( WO 313699) TOWN HOME BLOCK (16TH & MARKHAM RD) | 99 | COMPLETE | Engineering by-passed | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Cory Ruiter | 0 | 88420.11 | 88420.11 |  | 0 | 948.68 | 948.68 |  | 0 | 1569.3 | 1569.3 |  | 0 | 235.4 | 235.4 |  | 0 | 59.4 | 59.4 |  | 0 | 165.25 | 165.25 |  | 2019-07-26 01:00
Markham | 2019 | 452543 | ( WO 314095) BLOOMINGTON GO STATION | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 287532.42 | 463287.61 | 175755.19 | 61.13% | 10757.67 | 69001.95 | 58244.28 | 541.4% | 53733.75 | 41866.31 | -11867.44 | -22.09% | 2541 | 6425.77 | 3884.77 | 152.9% | 220500 | 109358.88 | -111141.12 | -50.4% | 150 | 164 | 14 | 9.333% | 2019-05-14
Markham | 2019 | 452545 | (WO 314304) 568 RIVERLANDS AVENUE | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 56880.47 | 58451.98 | 1571.51 | 2.763% | 8184.92 | 232.88 | -7952.04 | -97.15% | 22474.15 | 18260.25 | -4213.9 | -18.75% | 1917.3 | 0 | -1917.3 | -100% | 21330.75 | 2911.02 | -18419.73 | -86.35% | 274 | 229 | -45 | -16.42% | 2019-07-04 01:00
Markham | 2019 | 452546 | (WO 314306) 8600 Woodbine Ave N. of Hwy 7 | 99 | COMPLETE | Engineering by-passed | N/A | N/A | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 0 | 112314.13 | 112314.13 |  | 0 | 7348.38 | 7348.38 |  | 0 | 44821.06 | 44821.06 |  | 0 | 535 | 535 |  | 0 | 23177.15 | 23177.15 |  | 0 | 267.75 | 267.75 |  | 2019-07-26 01:00
Markham | 2020 | 452553 | 452553 (WO 314722) Vitlor Homes (Lots G - J) | 99 | COMPLETE | Converted Project |  |  | Penner, Mitchell | No | Alectra Utilities | Steve Rumble | 149228.1972 | 154424.73 | 5196.5328 | 3.482% | 139534.5 | 16914.8 | -122619.7 | -87.88% | 413.1256 | 464.36 | 51.2344 | 12.4% | 8698.6826 | 140 | -8558.6826 | -98.39% | 581.889 | 132890 | 132308.111 | 22738% | 144 | 195 | 51 | 35.42% | 2020-02-24 01:00
Markham | 2020 | 452559 | 452559 (WO 314876) Pole Relocation - Major Mackenzie Dr - Islington Ave To Pine Valley Dr (9 poles) | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 591973.48 | 499530.75 | -92442.73 | -15.62% | 29603.04 | 59692.96 | 30089.92 | 101.6% | 142164.04 | 150298.26 | 8134.22 | 5.722% | 0 | 3070 | 3070 |  | 420206.4 | 286469.53 | -133736.87 | -31.83% | 100 | 102.5 | 2.5 | 2.5% | 2020-12-11 01:00
Markham | 2019 | 452563 | ( WO 314953) WOODBRIDGE PARK RESIDENTIAL | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alarcon, Alejandro | Steve Rumble | 90563.9447 | 314238.01 | 223674.0653 | 247% | 59946.3372 | 4171.96 | -55774.3772 | -93.04% | 14807.7598 | 10842.44 | -3965.3198 | -26.78% | 15809.8476 | 0 | -15809.8476 | -100% | 0 | 7649.93 | 7649.93 |  | 759 | 283 | -476 | -62.71% | 2019-10-24 01:00
Markham | 2019 | 452567 | (WO315030) 8,10,18 Rouge Valley | 99 | COMPLETE | Labour est. under |  |  | Dibratto, Susan | No | Paterson, Greg | Steve Rumble | 97785.83 | 90543.74 | -7242.09 | -7.406% | 13504.68 | 96.1 | -13408.58 | -99.29% | 58225.65 | 48384.9 | -9840.75 | -16.9% | 3095.4 | 0 | -3095.4 | -100% | 18900 | 1201.3 | -17698.7 | -93.64% | 194 | 261 | 67 | 34.54% | 2019-06-15 01:00
Markham | 2021 | 452569 | 452569 (WO 315040) 9000 Jane St. Carisma Condo | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 91700.32 | 61666.84 | -30033.48 | -32.75% | 6823.23 | 15304.55 | 8481.32 | 124.3% | 3200.92 | 1275.94 | -1924.98 | -60.14% | 636.17 | 1872.97 | 1236.8 | 194.4% | 81040 | 41012.37 | -40027.63 | -49.39% | 96.4 | 100 | 3.6 | 3.734% | 2021-06-30 01:00
Markham | 2020 | 452572 | 452572 - MCCOWAN RD. #8590 - PFAFF PORSCHE MARKHAM - Car dealership | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 87264.14 | 76936.76 | -10327.38 | -11.83% | 19939.5 | 13598.33 | -6341.17 | -31.8% | 44586.23 | 42542.83 | -2043.4 | -4.583% | 2082.28 | 1927.48 | -154.8 | -7.434% | 20656.13 | 18380.5 | -2275.63 | -11.02% | 196.68 | 104 | -92.68 | -47.12% | 2020-09-01 01:00
Markham | 2021 | 452573 | 452573 (WO 315062) GO Transit Station | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 107734.88 | 89283.86 | -18451.02 | -17.13% | 32113.88 | 16834.78 | -15279.1 | -47.58% | 41853.16 | 49175.05 | 7321.89 | 17.49% | 5077.96 | 3343 | -1734.96 | -34.17% | 28689.88 | 17287.66 | -11402.22 | -39.74% | 394.33 | 138.5 | -255.83 | -64.88% | 2021-04-27
Markham | 2022 | 452586 | 452586 - 210 EDWARD ST, AURORA | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Dave Lindsay | 61133.39 | 70069.29 | 8935.9 | 14.62% | 30236.1 | 17831.18 | -12404.92 | -41.03% | 27695.8 | 19253.25 | -8442.55 | -30.48% | 3313.49 | 4744 | 1430.51 | 43.17% | 22238 | 24472.62 | 2234.62 | 10.05% | 167.82 | 147 | -20.82 | -12.41% | 2022-10-07 01:00
Markham | 2019 | 452594 | 452594 (WO 315264) M43 Steelcase and Idema - 10 Steelcase | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 186523 | 197955 | 11432 | 6.129% | 9548 | 20242 | 10694 | 112% | 0 | 12837 | 12837 |  | 2207 | 0 | -2207 | -100% | 174768 | 164876 | -9892 | -5.66% | 116 | 115.5 | -0.5 | -0.431% | 2019-11-16 01:00
Markham | 2019 | 452595 | 452595 (WO 315265) M43 Steelcase and Idema - 76 Steelcase | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 205912 | 210204 | 4292 | 2.084% | 9548 | 19970 | 10422 | 109.2% | 0 | 7067 | 7067 |  | 2207 | 0 | -2207 | -100% | 194157 | 183167 | -10990 | -5.66% | 116 | 92.5 | -23.5 | -20.26% | 2019-11-16 01:00
Markham | 2019 | 452596 | 452596 (WO 315266) M43 Steelcase and Idema - 77 Steelcase | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 161194 | 160773 | -421 | -0.2612% | 9548 | 16917 | 7369 | 77.18% | 0 | 2876 | 2876 |  | 2207 | 0 | -2207 | -100% | 149439 | 140980 | -8459 | -5.661% | 116 | 101.75 | -14.25 | -12.28% | 2019-11-16 01:00
Markham | 2019 | 452597 | 452597 (WO 315267) M43 Steelcase and Idema - 57 and 67 Steelcase | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 259909 | 271995 | 12086 | 4.65% | 9548 | 29298 | 19750 | 206.8% | 0 | 4910 | 4910 |  | 2207 | 0 | -2207 | -100% | 248154 | 237787 | -10367 | -4.178% | 116 | 144.25 | 28.25 | 24.35% | 2019-11-16 01:00
Markham | 2019 | 452598 | 452598 (WO 315268) M43 Steelcase and Idema - 207-297 Idema | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 819879.52 | 850772 | 30892.48 | 3.768% | 18194.52 | 88954 | 70759.48 | 388.9% | 0 | 5655 | 5655 |  | 2207 | 0 | -2207 | -100% | 799478 | 756163 | -43315 | -5.418% | 181 | 350.25 | 169.25 | 93.51% | 2019-12-19 01:00
Markham | 2019 | 452599 | 452599 (WO 315269) M43 Steelcase and Idema - 161-183 Idema | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 268491 | 178721 | -89770 | -33.44% | 9548 | 21428 | 11880 | 124.4% | 0 | 6450 | 6450 |  | 2207 | 0 | -2207 | -100% | 256736 | 150843 | -105893 | -41.25% | 116 | 138.5 | 22.5 | 19.4% | 2019-11-16 01:00
Markham | 2019 | 452600 | 452600 (WO 315270) M43 Idema OH Pole Line Extension | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 250660 | 250425 | -235 | -0.09375% | 9548 | 24107 | 14559 | 152.5% | 0 | 0 | 0 |  | 2207 | 936 | -1271 | -57.59% | 238905 | 225382 | -13523 | -5.66% | 116 | 102 | -14 | -12.07% | 2019-11-16 01:00
Markham | 2020 | 452604 | 452604 (WO 315353) Uptowns on Bayview | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 49325.95 | 64708.56 | 15382.61 | 31.19% | 3218.16 | 10336.46 | 7118.3 | 221.2% | 809.15 | 935.67 | 126.52 | 15.64% | 231.64 | 710 | 478.36 | 206.5% | 45067 | 43299.15 | -1767.85 | -3.923% | 37.4 | 51.5 | 14.1 | 37.7% | 2020-09-29 01:00
Markham | 2019 | 452608 | ( WO 315393) YRRTC - Y2.1 - Stage 4 - Baif Blvd. to Major Mac W | 99 | COMPLETE | Converted Project |  |  | Lacombe, Joel | No | Lacombe, Joel | Steve Rumble | 7243670 | 10649358.93 | 3405688.93 | 47.02% | 289661 | 146420.03 | -143240.97 | -49.45% | 670299 | 709731.5 | 39432.5 | 5.883% | 90419 | 66.5 | -90352.5 | -99.93% | 6193291 | 1816853.98 | -4376437.02 | -70.66% | 1174 | 1313 | 139 | 11.84% | 2019-08-23 01:00
Markham | 2019 | 452609 | (WO315396) YRRTC-Y2.1-STAGE 7 | 99 | COMPLETE | Converted Project |  |  | Lacombe, Joel | No | Lacombe, Joel | Steve Rumble | 4222556.44 | 5298630.22 | 1076073.78 | 25.48% | 223806 | 75289.07 | -148516.93 | -66.36% | 357628 | 184528.61 | -173099.39 | -48.4% | 40967.44 | 0 | -40967.44 | -100% | 3600155 | 868787.25 | -2731367.75 | -75.87% | 0 | 952.5 | 952.5 |  | 2019-08-23 01:00
Markham | 2019 | 452610 | (WO315397) YRRTC - Y2.1 - Stage 8 Yonge St - Weldrick to Elmwood | 99 | COMPLETE | Converted Project |  |  | Lacombe, Joel | No | Lacombe, Joel | Steve Rumble | 6466282.22 | 7698977.14 | 1232694.92 | 19.06% | 0 | 5891.94 | 5891.94 |  | 522036 | 475224.68 | -46811.32 | -8.967% | 961.22 | 0 | -961.22 | -100% | 5943285 | 0 | -5943285 | -100% | 468 | 1014.5 | 546.5 | 116.8% | 2019-08-23 01:00
Markham | 2019 | 452614 | 452614 (WO 315445) 13200 Yonge St School | 99 | COMPLETE | Converted Project | N/A | N/A | Stephens, Barry N. | No | Dibratto, Susan | Steve Rumble | 65044.67 | 56583.09 | -8461.58 | -13.01% | 15643.16 | 5588.16 | -10055 | -64.28% | 33421.28 | 23063.71 | -10357.57 | -30.99% | 3759.53 | 2295.5 | -1464.03 | -38.94% | 8281.35 | 13328.09 | 5046.74 | 60.94% | 223 | 218.75 | -4.25 | -1.906% | 2019-09-13 01:00
Markham | 2020 | 452615 | (WO 452615 was 315474) Rebuild Pole Line on 19th Ave into 2 cct - From Leslie to Bayview | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-07 01:00
Markham | 2020 | 452616 | 452616 (WO 315493) Sedgewick Dev Ph 1 (F) | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 1224733.97 | 1227188.17 | 2454.2 | 0.2004% | 22999.84 | 19522.25 | -3477.59 | -15.12% | 8860.07 | 3879.82 | -4980.25 | -56.21% | 3862.06 | 3450.5 | -411.56 | -10.66% | 1189012 | 3901.94 | -1185110.06 | -99.67% | 588.03 | 277.49 | -310.54 | -52.81% | 2020-12-07 01:00
Markham | 2019 | 452617 | (WO315501) Yorkton Limited Phase 2. Royal Aberdeen Rd/ Yorkton Blvd | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Estrada, Michael | Steve Rumble | 583231.35 | 610178.59 | 26947.24 | 4.62% | 39756.3 | 26847.5 | -12908.8 | -32.47% | 4322.38 | 1093.66 | -3228.72 | -74.7% | 6853.67 | 78 | -6775.67 | -98.86% | 532299 | 175296.5 | -357002.5 | -67.07% | 450 | 494.75 | 44.75 | 9.944% | 2019-10-22 01:00
Markham | 2020 | 452618 | 452618 (WO 315508) - Corsica Pole Relocation - Bayview Drive & Hillsview Drive, Richmond Hill | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 71893.45 | 69185.29 | -2708.16 | -3.767% | 13082.67 | 12034.08 | -1048.59 | -8.015% | 7130.94 | 5559.25 | -1571.69 | -22.04% | 1967.84 | 2324 | 356.16 | 18.1% | 49712 | 44001.61 | -5710.39 | -11.49% | 204.2 | 113.5 | -90.7 | -44.42% | 2020-11-04 01:00
Markham | 2019 | 452626 | 452626 (WO 315551) 7089 Yonge Street | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 84546.88 | 94924.85 | 10377.97 | 12.27% | 10083.59 | 21687.45 | 11603.86 | 115.1% | 53280.07 | 45062.91 | -8217.16 | -15.42% | 1380.22 | 5195 | 3814.78 | 276.4% | 19803 | 15398.83 | -4404.17 | -22.24% | 124 | 378.24 | 254.24 | 205% | 2019-11-21 01:00
Markham | 2021 | 452628 | 452628 (WO 315584) Mackenzie Creek Condo Dev | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 0 | 654206.89 | 654206.89 |  | 0 | 53130.43 | 53130.43 |  | 0 | 13767.32 | 13767.32 |  | 0 | 4280.28 | 4280.28 |  | 0 | 364949.85 | 364949.85 |  | 0 | 206 | 206 |  | 2021-12-07 01:00
Markham | 2020 | 452629 | 452629 (WO 315590) Sedgewick Dev Ph 2 | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 21835.06 | 66688.38 | 44853.32 | 205.4% | 13764.84 | 3368.05 | -10396.79 | -75.53% | 295.83 | 0 | -295.83 | -100% | 1024.39 | 120.83 | -903.56 | -88.2% | 6750 | 0 | -6750 | -100% | 170.08 | 7.5 | -162.58 | -95.59% | 2020-12-07 01:00
Markham | 2020 | 452630 | 452630 (WO 315593) Centerfield Dev Ph 1 (F) | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 143602.51 | 135980.31 | -7622.2 | -5.308% | 7368.86 | 5727.49 | -1641.37 | -22.27% | 5064.59 | 5133.04 | 68.45 | 1.352% | 1171.06 | 747.98 | -423.08 | -36.13% | 129998 | 6212.4 | -123785.6 | -95.22% | 155.03 | 52 | -103.03 | -66.46% | 2020-12-07 01:00
Markham | 2020 | 452631 | 452631 (WO 315595) Dickson 48 Properties Inc. (F) | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 222505.33 | 217212.55 | -5292.78 | -2.379% | 3795.77 | 5318.16 | 1522.39 | 40.11% | 778.56 | 0 | -778.56 | -100% | 152 | 0 | -152 | -100% | 217779 | 0 | -217779 | -100% | 25 | 50 | 25 | 100% | 2020-12-07 01:00
Markham | 2020 | 452638 | 452638 (WO 315620) Barker DC Buisness Park, Richmond Hill | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Chris Hagan | 1833422.13 | 2411175.66 | 577753.53 | 31.51% | 56979.13 | 262172.28 | 205193.15 | 360.1% | 44204 | 71346.36 | 27142.36 | 61.4% | 9664 | 13663.5 | 3999.5 | 41.39% | 1722575 | 1995026.03 | 272451.03 | 15.82% | 705 | 1416.25 | 711.25 | 100.9% | 2020-11-11 01:00
Markham | 2019 | 452640 | 452640 (WO 315625) Extension of Duct Banks on Leslie St | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Lamb, Tim | 246407.61 | 220316.48 | -26091.13 | -10.59% | 35704.95 | 31697.74 | -4007.21 | -11.22% | 23681.06 | 5029.65 | -18651.41 | -78.76% | 2155.84 | 3369.5 | 1213.66 | 56.3% | 184865.76 | 170828.45 | -14037.31 | -7.593% | 186 | 233 | 47 | 25.27% | 2019-11-05 01:00
Markham | 2019 | 452642 | 452642 (WO 315651) Rutherford Road (Westburne Drive to Confederation PKWY), Vaughan | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Barry, Kenneth | Morrow, Joe | 2041325.4 | 2619815.25 | 578489.85 | 28.34% | 158963.4 | 263768.35 | 104804.95 | 65.93% | 329807 | 36109.03 | -293697.97 | -89.05% | 125486 | 33050 | -92436 | -73.66% | 1427069 | 2286887.87 | 859818.87 | 60.25% | 360 | 4360.5 | 4000.5 | 1111% | 2019-10-02 01:00
Markham | 2020 | 452644 | 452644 (WO 315718) Data Centre - Bldg. DC2 | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Dave Lindsay | 258851.74 | 240816.45 | -18035.29 | -6.967% | 42136.59 | 23759.29 | -18377.3 | -43.61% | 209083.27 | 206653.24 | -2430.03 | -1.162% | 0 | 4611.57 | 4611.57 |  | 6300 | 64.3 | -6235.7 | -98.98% | 467 | 376.75 | -90.25 | -19.33% | 2020-11-02 01:00
Markham | 2020 | 452646 | 452646 (WO 315759) Kings Landing | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 34678.19 | 194872.95 | 160194.76 | 461.9% | 23248.62 | 14805.78 | -8442.84 | -36.32% | 5632.74 | 4178.54 | -1454.2 | -25.82% | 2015.75 | 2081 | 65.25 | 3.237% | 3781.08 | 0 | -3781.08 | -100% | 220.02 | 148.5 | -71.52 | -32.51% | 2020-06-23 01:00
Markham | 2019 | 452672 | 452672 (WO 315938) ICI Padmount Transformer Installation | 99 | COMPLETE | Converted Project |  |  | Stephens, Barry N. | No | Dibratto, Susan | Steve Rumble | 223027.94 | 197868.48 | -25159.46 | -11.28% | 29419.47 | 5340.83 | -24078.64 | -81.85% | 124351.52 | 108766.86 | -15584.66 | -12.53% | 7877.1 | 150 | -7727.1 | -98.1% | 61379.85 | 50696.36 | -10683.49 | -17.41% | 411 | 235.5 | -175.5 | -42.7% | 2019-11-11 01:00
Markham | 2021 | 452692 | 452692 (WO 316252) 1756 ST. JOHNS SD RD | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Perks, Dan | Dave Lindsay | 391252.34 | 462766.89 | 71514.55 | 18.28% | 25932.25 | 16676.39 | -9255.86 | -35.69% | 7936.13 | 2552.97 | -5383.16 | -67.83% | 3821.66 | 0 | -3821.66 | -100% | 353562.3 | 61660.43 | -291901.87 | -82.56% | 192 | 76.9 | -115.1 | -59.95% | 2021-04-27
Markham | 2020 | 452693 | 452693 (WO 316255) Cornell Ph 8 | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 271380.16 | 233813.37 | -37566.79 | -13.84% | 10478.62 | 29505.21 | 19026.59 | 181.6% | 1504.19 | 1192.99 | -311.2 | -20.69% | 396.71 | 1315 | 918.29 | 231.5% | 259000.64 | 194148 | -64852.64 | -25.04% | 123.47 | 178 | 54.53 | 44.16% | 2020-05-12
Markham | 2019 | 452696 | 452696 (WO 316261) Rutherford GO Station | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Diefenbaker, Trevor A | Steve Rumble | 19361.59 | 31417.64 | 12056.05 | 62.27% | 7334.36 | 3356.17 | -3978.19 | -54.24% | 0 | 25266.82 | 25266.82 |  | 523.07 | 535 | 11.93 | 2.281% | 11504.16 | 0 | -11504.16 | -100% | 29 | 33 | 4 | 13.79% | 2019-12-11 01:00
Markham | 2019 | 452698 | ( WO 316266) NINE TEN WEST CARVILLE DISTRICT | 99 | COMPLETE | Engineering by-passed | N/A | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Steve Rumble | 303660.09 | 186172.47 | -117487.62 | -38.69% | 17410.07 | 0 | -17410.07 | -100% | 2529.96 | 0 | -2529.96 | -100% | 3427.81 | 0 | -3427.81 | -100% | 280292.25 | 0 | -280292.25 | -100% | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2020 | 452699 | 452699 (WO 316272) Highland Gate Phase One | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Cory Ruiter | 410118.16 | 436249.35 | 26131.19 | 6.372% | 19704.61 | 8608.74 | -11095.87 | -56.31% | 5711.76 | 3083.41 | -2628.35 | -46.02% | 2980.59 | 594 | -2386.59 | -80.07% | 381721.2 | 0 | -381721.2 | -100% | 273.65 | 312 | 38.35 | 14.01% | 2020-06-16 01:00
Markham | 2019 | 452713 | 452713 (WO 316366) Medical Offices. 1 Eaglet Court Offices | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 70554.46 | 98113.96 | 27559.5 | 39.06% | 10527.95 | 16728.11 | 6200.16 | 58.89% | 26783.64 | 22370.74 | -4412.9 | -16.48% | 3060.75 | 1878 | -1182.75 | -38.64% | 22657.95 | 53678.01 | 31020.06 | 136.9% | 172.5 | 219.5 | 47 | 27.25% | 2019-11-13 01:00
Markham | 2019 | 452716 | ( WO 316370) Rebuild Pole Line on Warden Ave into 4 cct - From 16th Ave to Major Mackenzie Drive | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Tempra, Troylan | Shortt, Derek B. | 1789407 | 1924453 | 135046 | 7.547% | 622507 | 54597 | -567910 | -91.23% | 714594 | 608653 | -105941 | -14.83% | 220626 | 17823 | -202803 | -91.92% | 231680 | 19293 | -212387 | -91.67% | 9716 | 11036.5 | 1320.5 | 13.59% | 2019-07-16 01:00
Markham | 2019 | 452718 | 452718 (WO 316390) M43 Steelcase and Idema - 8 Steelcase | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 105908 | 115666 | 9758 | 9.214% | 8309 | 13845 | 5536 | 66.63% | 0 | 11324 | 11324 |  | 1672 | 0 | -1672 | -100% | 95927 | 90497 | -5430 | -5.661% | 100 | 101.5 | 1.5 | 1.5% | 2019-11-16 01:00
Markham | 2021 | 452719 | 452719 - RAISE NEUTRAL HEIGHT AND INSTALL BOLLARDS, VAUGHAN | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Larry | 55486.38 | 27032.56 | -28453.82 | -51.28% | 14231.25 | 6295.34 | -7935.91 | -55.76% | 1630.65 | 62.79 | -1567.86 | -96.15% | 308.7 | 353 | 44.3 | 14.35% | 39315.78 | 20321.43 | -18994.35 | -48.31% | 37.8 | 20 | -17.8 | -47.09% | 2021-02-12 01:00
Markham | 2020 | 452722 | 452722 - UG Cable Replacement EPC - Steeles and Canadiana | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Shane Christopher | 1230570.13 | 1176859.39 | -53710.74 | -4.365% | 16746.27 | 98095.31 | 81349.04 | 485.8% | 307257.13 | 0 | -307257.13 | -100% | 1400 | 28 | -1372 | -98% | 905166.73 | 1078736.08 | 173569.35 | 19.18% | 224 | 137 | -87 | -38.84% | 2020-10-22 01:00
Markham | 2020 | 452723 | 452723 (WO 316425) Steeles and Fairway Heights | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Shane Christopher | 2963096.23 | 2858665.9 | -104430.33 | -3.524% | 47080.67 | 244618.15 | 197537.48 | 419.6% | 0 | 8931.99 | 8931.99 |  | 4760 | 765.24 | -3994.76 | -83.92% | 2911255.56 | 2593920.22 | -317335.34 | -10.9% | 680 | 166 | -514 | -75.59% | 2020-12-15 01:00
Markham | 2022 | 452725 | (WO 452725 was 316430) Cable Replacement - V22 - 251 Doney Cres | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Handy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-16 01:00
Markham | 2019 | 452726 | 452726 (WO 316431) M43 Steelcase and Idema - 87 Steelcase | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 168626 | 172691 | 4065 | 2.411% | 9548 | 18880 | 9332 | 97.74% | 0 | 5820 | 5820 |  | 2207 | 0 | -2207 | -100% | 156871 | 147991 | -8880 | -5.661% | 116 | 103.25 | -12.75 | -10.99% | 2019-11-16 01:00
Markham | 2019 | 452732 | 452732 (WO 316450) Union Condominium Development | 99 | COMPLETE | Converted Project |  |  |  | No | Alarcon, Alejandro | Steve Rumble | 18947.27 | 213059.44 | 194112.17 | 1024% | 13331.8 | 21299.74 | 7967.94 | 59.77% | 3663.98 | 0 | -3663.98 | -100% | 1951.49 | 1351 | -600.49 | -30.77% | 0 | 0 | 0 |  | 178.28 | 320.5 | 142.22 | 79.77% | 2019-12-18 01:00
Markham | 2020 | 452736 | (WO316463) York University Campus Markham | 99 | CANCELLED | N/A |  |  | Stephens, Barry N. | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-13 01:00
Markham | 2019 | 452751 | 452751 (WO 316490) Hwy 404 and Hwy 7 Crossing | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Steve | 363086 | 458807.41 | 95721.41 | 26.36% | 115661 | 25535.91 | -90125.09 | -77.92% | 137059 | 169967.59 | 32908.59 | 24.01% | 42762 | 0 | -42762 | -100% | 67604 | 263303.91 | 195699.91 | 289.5% | 899 | 139.5 | -759.5 | -84.48% | 2019-11-29 01:00
Markham | 2021 | 452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Grahovac, John | Shane Christopher | 1554201.75 | 1738111.65 | 183909.9 | 11.83% | 7756.92 | 128083.81 | 120326.89 | 1551% | 85878.6 | 99344.97 | 13466.37 | 15.68% | 0 | 543.72 | 543.72 |  | 1460566.23 | 1487990.76 | 27424.53 | 1.878% | 57 | 59 | 2 | 3.509% | 2021-01-22 01:00
Markham | 2022 | 452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | 95 | ANALYZE |  |  |  | Khuu, Philander | No | Grahovac, John | Shane Christopher | 3438125.12 | 2964956.94 | -473168.18 | -13.76% | 290958.48 | 43775 | -247183.48 | -84.95% | 116779 | 118112.8 | 1333.8 | 1.142% | 0 | 774 | 774 |  | 3030387.64 | 2778197.45 | -252190.19 | -8.322% | 45 | 111.5 | 66.5 | 147.8% | 2022-09-29 01:00
Markham | 2019 | 452784 | 452784 (WO 316550) Lindvest Pine Valley Phase 1 | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Estrada, Michael | Steve Rumble | 79565.9054 | 724123.16 | 644557.2546 | 810.1% | 42417.6553 | 11250.07 | -31167.5853 | -73.48% | 16489.235 | 17398.16 | 908.925 | 5.512% | 13504.015 | 1246 | -12258.015 | -90.77% | 7155 | 14642.64 | 7487.64 | 104.6% | 553 | 284 | -269 | -48.64% | 2019-10-17 01:00
Markham | 2021 | 452785 | 452785 - LINDVEST ZZEN P.VAL. PH2 | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 438619.23 | 478139.77 | 39520.54 | 9.01% | 39782.54 | 28895.6 | -10886.94 | -27.37% | 5179.32 | 5628.02 | 448.7 | 8.663% | 3282.73 | 5992 | 2709.27 | 82.53% | 390374.64 | 3870 | -386504.64 | -99.01% | 286.38 | 301 | 14.62 | 5.105% | 2021-09-15 01:00
Markham | 2022 | 452796 | 452796 - PRIMA VISTA ESTATES PH 2 | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Estrada, Michael | Dave Lindsay | 589000.93 | 48532.45 | -540468.48 | -91.76% | 76366.39 | 29592.34 | -46774.05 | -61.25% | 14346.1 | 4554.31 | -9791.79 | -68.25% | 5003.44 | 3630 | -1373.44 | -27.45% | 493285 | 0 | -493285 | -100% | 279.64 | 295 | 15.36 | 5.493% | 2022-07-18 01:00
Markham | 2020 | 452799 | 452799 (WO 316617) Villagio (9891 Keele Street) | 99 | COMPLETE | Converted Project |  |  | Penner, Mitchell | No | Alectra Utilities | Steve Rumble | 69087.3813 | 67717.32 | -1370.0613 | -1.983% | 20653.0208 | 19439.73 | -1213.2908 | -5.875% | 8678.3048 | 7004.2 | -1674.1048 | -19.29% | 5713.0957 | 2445 | -3268.0957 | -57.2% | 34042.96 | 21446.64 | -12596.32 | -37% | 257 | 180 | -77 | -29.96% | 2020-04-15 01:00
Markham | 2020 | 452800 | (WO 316619) 180 Wellington, Aurora | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-13 01:00
Markham | 2020 | 452801 | 452801 (WO 316633) Nashville Heights - Mizuno Lands | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 585953.16 | 544069.82 | -41883.34 | -7.148% | 12764.04 | 65406 | 52641.96 | 412.4% | 4200.04 | 6985.11 | 2785.07 | 66.31% | 2463.08 | 2616 | 152.92 | 6.208% | 566526 | 456893 | -109633 | -19.35% | 415 | 321.5 | -93.5 | -22.53% | 2020-02-13 01:00
Markham | 2020 | 452810 | (WO316681) UG Design for City of Vaughan - HWY 7(E/O HWY 400-E/O CREDITSTONE RD), VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Steve Rumble | 0 | 61254.02 | 61254.02 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 836.19 | 836.19 |  | 0 | 0 | 0 |  | 2019-08-17 01:00
Markham | 2019 | 452812 | (WO 316688) Fire Station No. 7 - 4 | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Yuen, Paul | Steve Rumble | 66336.09 | 65857.24 | -478.85 | -0.7219% | 26672.04 | 7341.46 | -19330.58 | -72.48% | 27504.17 | 24099.54 | -3404.63 | -12.38% | 0 | 3075 | 3075 |  | 10006.13 | 7249.12 | -2757.01 | -27.55% | 301 | 228.5 | -72.5 | -24.09% | 2019-08-17 01:00
Markham | 2019 | 452814 | ( WO 316692) OH Relocation - HWY 427 AND STEELES AVE, VAUGHAN - OH Reloc due to HWY 427 | 99 | CANCELLED | N/A | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 452815 | ( WO 316693) Hydro Relocation - HWY 427 AND HWY 7, VAUGHAN - Hydro Reloc due to HWY 427 | 99 | COMPLETE | No Feedback from Const | N/A | N/A | Tenorlas, Reynaldo | No | Zhang, Jiacheng | Macdonald, Steve | 200000 | 136544.9 | -63455.1 | -31.73% | 0 | 29067.02 | 29067.02 |  | 0 | 334.48 | 334.48 |  | 0 | 50.17 | 50.17 |  | 0 | 38208.02 | 38208.02 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2019 | 452816 | ( WO 316694) UG Relocation - HWY 427 AND ZENWAY BLVD, VAUGHAN - UG Reloc due to HWY 427 | 99 | COMPLETE | No Feedback from Const | N/A | N/A | Tenorlas, Reynaldo | No | Zhang, Jiacheng | Macdonald, Steve | 39067 | 35771.7 | -3295.3 | -8.435% | 2289 | 6154.46 | 3865.46 | 168.9% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 36778 | 10951.39 | -25826.61 | -70.22% | 0 | 0 | 0 |  | 2019-07-26 01:00
Markham | 2022 | 452817 | 452817 (WO 316695) OH Relocation - HWY 427 EXTENSION, LANGSTAFF RD, EAST OF HUNTINGTON RD, VAUGHAN | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 156850.14 | 104260.43 | -52589.71 | -33.53% | 9153.66 | 7880.59 | -1273.07 | -13.91% | 0 | 937.11 | 937.11 |  | 0 | 0 | 0 |  | 147696.48 | 28085.31 | -119611.17 | -80.98% | 5 | 33 | 28 | 560% | 2021-06-07 01:00
Markham | 2019 | 452818 | 452818 (WO 316696) Hydro Relocation - HWY 427 EXTENSION, RUTHERFORD RD, EAST OF HUNTINGTON RD, VGN | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 2981400 | 249592.12 | -2731807.88 | -91.63% | 0 | 2060.86 | 2060.86 |  | 0 | 2993.08 | 2993.08 |  | 0 | 0 | 0 |  | 2981400 | 9175.08 | -2972224.92 | -99.69% | 428 | 340 | -88 | -20.56% | 2019-10-02 01:00
Markham | 2022 | 452819 | 452819 (WO 316697) Hydro Relocation - HWY 427 EXTENSION, HUNTINGTON Rr, MAJOR MACK DR, VAUGHAN | 98 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 213879 | 172973.47 | -40905.53 | -19.13% | 15947 | 8405.4 | -7541.6 | -47.29% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 197932 | 16625.98 | -181306.02 | -91.6% | 0 | 57.5 | 57.5 |  | 2021-06-07 01:00
Markham | 2020 | 452820 | 452820 (WO 316698) 396, 404, 416 KING ROAD RICHMOND HILL | 99 | COMPLETE | Converted Project | N/A | N/A | Penner, Mitchell | No | Alectra Utilities | Chris Hagan | 120722.0925 | 112414.78 | -8307.3125 | -6.881% | 12304.8434 | 8983.2 | -3321.6434 | -26.99% | 1485.7172 | 1658.69 | 172.9728 | 11.64% | 2337.0919 | 294 | -2043.0919 | -87.42% | 104594.44 | 77102 | -27492.44 | -26.28% | 156.3 | 22.5 | -133.8 | -85.6% | 2020-11-10 01:00
Markham | 2020 | 452829 | 452829 (WO 316782) BUTTERMILL AVE #5 & PORTAGE PKWY #898 | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Dave Lindsay | 99824.53 | 23622.15 | -76202.38 | -76.34% | 30256.09 | 2203.59 | -28052.5 | -92.72% | 33358.12 | 2919.06 | -30439.06 | -91.25% | 5336.1 | 0 | -5336.1 | -100% | 18018 | 0 | -18018 | -100% | 453 | 178 | -275 | -60.71% | 2020-11-10 01:00
Markham | 2019 | 452844 | 452844 (WO 316817) - Smart Reit VMC_Condo's_UG Cable Installation | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Shane Christopher | 1509724.74 | 1503023.34 | -6701.4 | -0.4439% | 245232.13 | 164323.57 | -80908.56 | -32.99% | 4000 | 96027.48 | 92027.48 | 2301% | 11011.04 | 10070.04 | -941 | -8.546% | 1162908 | 950196.68 | -212711.32 | -18.29% | 1196.37 | 799.75 | -396.62 | -33.15% | 2019-12-21 01:00
Markham | 2022 | 452850 | ( WO 316842) Hydro Relocation - PROCTOR AVE AND HENDERSON AVE, MARKHAM | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Zhang, Jiacheng | Persaud, Ryan | 74.82 | 0 | -74.82 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-27
Markham | 2019 | 452854 | (WO316864) 70 Leek Cres | 99 | COMPLETE | Labour est. under | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 41770.1586 | 28498.44 | -13271.7186 | -31.77% | 10508.2146 | 12977.22 | 2469.0054 | 23.5% | 29256 | 1272 | -27984 | -95.65% | 2005.944 | 0 | -2005.944 | -100% | 0 | 0 | 0 |  | 120 | 149 | 29 | 24.17% | 2019-05-27
Markham | 2020 | 452857 | 452857 (WO 316868) BG Aurora - Phase Two | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Steve Rumble | 921223.71 | 966729.42 | 45505.71 | 4.94% | 32342.3 | 86243.52 | 53901.22 | 166.7% | 10169.32 | 12470.05 | 2300.73 | 22.62% | 5648.64 | 1234 | -4414.64 | -78.15% | 873063.45 | 844008.9 | -29054.55 | -3.328% | 424 | 426 | 2 | 0.4717% | 2020-04-30
Markham | 2019 | 452861 | (WO 316877) 168/176 Elgin Mills Rd | 99 | COMPLETE | Engineering by-passed | N/A | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Steve Rumble | 54863.1539 | 45945.51 | -8917.6439 | -16.25% | 19251.3816 | 0 | -19251.3816 | -100% | 3393.8179 | 0 | -3393.8179 | -100% | 5108.1364 | 0 | -5108.1364 | -100% | 27109.818 | 0 | -27109.818 | -100% | 112.54 | 0 | -112.54 | -100% | 2019-07-26 01:00
Markham | 2019 | 452862 | ( WO 316880) 100 GIBRALTAR RD (HWY 50 & HWY7) | 99 | COMPLETE | BOM not used | N/A | N/A | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 114002.05 | 99743.06 | -14258.99 | -12.51% | 17912.52 | 8391.16 | -9521.36 | -53.15% | 58811.15 | 62223.94 | 3412.79 | 5.803% | 5976.04 | 1973.5 | -4002.54 | -66.98% | 20497.16 | 20439.06 | -58.1 | -0.2835% | 264 | 170.5 | -93.5 | -35.42% | 2019-08-20 01:00
Markham | 2019 | 452864 | (WO 316883) YRRTC related-H2W-Hwy 400 Crossing at Hwy 7 | 99 | COMPLETE | Inaccurate design | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Steve Rumble | 3176161.33 | 3248365.89 | 72204.56 | 2.273% | 82370 | 7640.62 | -74729.38 | -90.72% | 23106.33 | 5125.1 | -17981.23 | -77.82% | 22026 | 768.77 | -21257.23 | -96.51% | 3048659 | 85736.41 | -2962922.59 | -97.19% | 1103.5 | 519.5 | -584 | -52.92% | 2019-02-13 01:00
Markham | 2019 | 452866 | (WO316888) Gandhi Lane #12 & #32 | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 124725.28 | 90467.27 | -34258.01 | -27.47% | 14547.96 | 16008.52 | 1460.56 | 10.04% | 80738.71 | 65009.51 | -15729.2 | -19.48% | 3742.2 | 9402.44 | 5660.24 | 151.3% | 17599.43 | 46.8 | -17552.63 | -99.73% | 223 | 164 | -59 | -26.46% | 2019-03-13 01:00
Markham | 2020 | 452867 | 452867 (WO 316891) PORTAGE PKWY - #950 | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Cory Ruiter | 51208.79 | 11606.59 | -39602.2 | -77.33% | 16224.94 | 1382.62 | -14842.32 | -91.48% | 12300.77 | 782.29 | -11518.48 | -93.64% | 3441.9 | 0 | -3441.9 | -100% | 9137.1 | 0 | -9137.1 | -100% | 149 | 134.75 | -14.25 | -9.564% | 2020-05-20
Markham | 2020 | 452872 | 452872 (WO 316899) New Retirement Home. Aurora Meadows Phase 2 | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Steve Rumble | 52663.55 | 52558.12 | -105.43 | -0.2002% | 9416.66 | 7814.37 | -1602.29 | -17.02% | 35241.46 | 34372.67 | -868.79 | -2.465% | 2097.48 | 1669 | -428.48 | -20.43% | 2021.25 | 4987.72 | 2966.47 | 146.8% | 140.5 | 148 | 7.5 | 5.338% | 2020-02-06 01:00
Markham | 2020 | 452883 | 452883 (WO 316926) Leslie Elgin Phase 2 | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 538659.91 | 545012.59 | 6352.68 | 1.179% | 36456.32 | 64358.36 | 27902.04 | 76.54% | 7091.67 | 6639.02 | -452.65 | -6.383% | 9523.67 | 4700 | -4823.67 | -50.65% | 485588.25 | 365474 | -120114.25 | -24.74% | 509.28 | 442.5 | -66.78 | -13.11% | 2020-10-06 01:00
Markham | 2021 | 452884 | 452884 (WO 316940) Uptown Phase 3 - Verdale | 99 | COMPLETE | Under 10% | N/A | N/A | Stephens, Barry N. | No | Dibratto, Susan | Dave Lindsay | 131915 | 129234.67 | -2680.33 | -2.032% | 12500.52 | 17632.62 | 5132.1 | 41.06% | 92850.75 | 91949.23 | -901.52 | -0.9709% | 3106.95 | 3039.64 | -67.31 | -2.166% | 16544.08 | 12324.64 | -4219.44 | -25.5% | 195 | 247.5 | 52.5 | 26.92% | 2021-10-27 01:00
Markham | 2019 | 452890 | (WO316986) 155 Snivley St | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alarcon, Alejandro | Steve Rumble | 13606.9777 | 111738.29 | 98131.3123 | 721.2% | 10651.8464 | 7581.22 | -3070.6264 | -28.83% | 1331.4869 | 494.78 | -836.7069 | -62.84% | 1623.6445 | 0 | -1623.6445 | -100% | 0 | 5382 | 5382 |  | 135 | 175.75 | 40.75 | 30.19% | 2019-07-30 01:00
Markham | 2019 | 452891 | (WO316990) Monarch Castlepoint Kipling South Development Ph. 2 | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Steve Rumble | 584280.72 | 41975 | -542305.72 | -92.82% | 32890.06 | 0 | -32890.06 | -100% | 7525.86 | 0 | -7525.86 | -100% | 6464.3 | 0 | -6464.3 | -100% | 537400.5 | 0 | -537400.5 | -100% | 447 | 406 | -41 | -9.172% | 2019-04-06 01:00
Markham | 2019 | 452892 | (WO 316992) Monarch Castlepoint Kipling North Development Ph. 2 | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Steve Rumble | 613947.8 | 44006.92 | -569940.88 | -92.83% | 36277.42 | 0 | -36277.42 | -100% | 5712.95 | 0 | -5712.95 | -100% | 7516.28 | 0 | -7516.28 | -100% | 564441.15 | 0 | -564441.15 | -100% | 483.5 | 367.25 | -116.25 | -24.04% | 2019-04-06 01:00
Markham | 2020 | 452894 | (WO316997) Commercial Bldg | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Persaud, Ryan | 0 | 2688.57 | 2688.57 |  | 0 | 128.68 | 128.68 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 |  | 2020-09-23 01:00
Markham | 2020 | 452896 | 452896 (WO 317002) St. Magnus - Weston Road | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 21600.89 | 124899.29 | 103298.4 | 478.2% | 20380.32 | 13001.55 | -7378.77 | -36.21% | 283.79 | 1361.07 | 1077.28 | 379.6% | 936.78 | 2923.59 | 1986.81 | 212.1% | 0 | 0 | 0 |  | 101.16 | 123 | 21.84 | 21.59% | 2020-09-23 01:00
Markham | 2019 | 452901 | (WO 317039) - O/H - 16th Ave & McCowan Rd Pole installation | 99 | COMPLETE | Switching | Inaccurate design | N/A | Tenorlas, Reynaldo | No | Battistella, Alexander | Shortt, Derek B. | 50753 | 186878.03 | 136125.03 | 268.2% | 21747 | 93044.48 | 71297.48 | 327.8% | 19922 | 6531.76 | -13390.24 | -67.21% | 4558 | 4744.74 | 186.74 | 4.097% | 4526 | 14655.39 | 10129.39 | 223.8% | 277.3 | 1093.75 | 816.45 | 294.4% | 2019-01-25 00:59
Markham | 2019 | 452915 | 452915 (WO 317132) V36SP1006 - 17 Vinyl Crt | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | Yes | Handy, James | Steve Rumble | 239613 | 140704.31 | -98908.69 | -41.28% | 33915 | 26986.85 | -6928.15 | -20.43% | 106863 | 24640.9 | -82222.1 | -76.94% | 8755 | 4625 | -4130 | -47.17% | 90080 | 84451.56 | -5628.44 | -6.248% | 454 | 322 | -132 | -29.07% | 2019-11-26 01:00
Markham | 2019 | 452916 | (WO 317135) A10SL2010 - Bayview n-o Wellington | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Tempra, Troylan | Macdonald, Steve | 90565 | 65974.48 | -24590.52 | -27.15% | 27215 | 1326.85 | -25888.15 | -95.12% | 56304 | 45615.08 | -10688.92 | -18.98% | 7046 | 6802.35 | -243.65 | -3.458% | 0 | 12230.2 | 12230.2 |  | 380 | 56 | -324 | -85.26% | 2019-06-06
Markham | 2019 | 452917 | ( WO 317139) V17SL3010 - Rutherford w-o Dufferin | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Macdonald, Steve | 78609 | 67181.77 | -11427.23 | -14.54% | 25003 | 3021.92 | -21981.08 | -87.91% | 44439 | 45794.15 | 1355.15 | 3.049% | 6329 | 0 | -6329 | -100% | 2838 | 18365.7 | 15527.7 | 547.1% | 314 | 45.5 | -268.5 | -85.51% | 2019-09-11 01:00
Markham | 2019 | 452918 | ( WO 317140) V17SL3013 - Dufferin St s-o Rutherford | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Macdonald, Steve | 75556 | 73853.59 | -1702.41 | -2.253% | 22364 | 3200.01 | -19163.99 | -85.69% | 45617 | 50085.28 | 4468.28 | 9.795% | 5475 | 0 | -5475 | -100% | 2100 | 20568.3 | 18468.3 | 879.4% | 312 | 50 | -262 | -83.97% | 2019-09-11 01:00
Markham | 2021 | 452920 | 452920 - INSPECT/CONNE/I&C 1335 ELGIN MILLS ROAD EAST | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Dave Lindsay | 78402.68 | 72705.87 | -5696.81 | -7.266% | 14502.04 | 16171.67 | 1669.63 | 11.51% | 1521.77 | 0 | -1521.77 | -100% | 524.03 | 562.42 | 38.39 | 7.326% | 61854.84 | 53854.2 | -8000.64 | -12.93% | 44.32 | 50.5 | 6.18 | 13.94% | 2021-01-13 01:00
Markham | 2020 | 452921 | 452921 (WO 317189) WOODHAVEN BALLYMORE | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 231996.4377 | 383418.15 | 151421.7123 | 65.27% | 14528.85 | 21676.68 | 7147.83 | 49.2% | 3153.5577 | 31.08 | -3122.4777 | -99.01% | 2236.08 | 807 | -1429.08 | -63.91% | 212077.95 | 71964 | -140113.95 | -66.07% | 186 | 323.25 | 137.25 | 73.79% | 2020-04-30
Markham | 2021 | 452929 | 452929 - AURORA GLEN SHIMVEST SUBD - BLK 161 SCRIVNER DRIVE | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 5506.49 | 108500.41 | 102993.92 | 1870% | 3814.63 | 6273.1 | 2458.47 | 64.45% | 1406.43 | 1873.18 | 466.75 | 33.19% | 253.03 | 1196.77 | 943.74 | 373% | 32.4 | 3704.98 | 3672.58 | 11335% | 36.32 | 46 | 9.68 | 26.65% | 2021-01-13 01:00
Markham | 2019 | 452932 | (WO 317239) REPLACE SWGRS 31-L22 & 31-L20 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Lamb, Tim | 145146 | 65287.72 | -79858.28 | -55.02% | 16512 | -137.6 | -16649.6 | -100.8% | 111125 | 47277.52 | -63847.48 | -57.46% | 3696 | 6791.25 | 3095.25 | 83.75% | 13813 | -10299 | -24112 | -174.6% | 35 | 140 | 105 | 300% | 2019-09-03 01:00
Markham | 2019 | 452933 | ( WO 317244) REPLACE 16-L30 | 99 | COMPLETE | Labour est. under | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Lamb, Tim | 79171 | 72311.38 | -6859.62 | -8.664% | 6730 | 7691.1 | 961.1 | 14.28% | 64102 | 244.38 | -63857.62 | -99.62% | 1432 | 8293.75 | 6861.75 | 479.2% | 6907 | 0 | -6907 | -100% | 77 | 95 | 18 | 23.38% | 2019-04-05 01:00
Markham | 2019 | 452934 | ( WO 317245) REPLACE 29-L12 | 99 | COMPLETE | Labour est. over | Filler work | N/A | Tenorlas, Reynaldo | No | Roy, James | Lamb, Tim | 71892 | 103518.62 | 31626.62 | 43.99% | 6822 | 1532.51 | -5289.49 | -77.54% | 55287 | 91503.55 | 36216.55 | 65.51% | 1455 | 13652.41 | 12197.41 | 838.3% | 8328 | -5023.42 | -13351.42 | -160.3% | 78 | 30 | -48 | -61.54% | 2019-03-24 01:00
Markham | 2019 | 452935 | ( WO 317246) REPLACE 3 SWITCHGEARS | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Lamb, Tim | 232554 | 189608.32 | -42945.68 | -18.47% | 19135 | 105.87 | -19029.13 | -99.45% | 184116 | 152625.46 | -31490.54 | -17.1% | 4320 | 22569.82 | 18249.82 | 422.4% | 24983 | 0 | -24983 | -100% | 187 | 182.5 | -4.5 | -2.406% | 2019-06-11 01:00
Markham | 2019 | 452936 | ( WO 317247) REPLACE 43-L34 | 99 | COMPLETE | Labour est. over | Filler work | N/A | Tenorlas, Reynaldo | No | Roy, James | Lamb, Tim | 84241 | 61455.98 | -22785.02 | -27.05% | 8879 | -401.87 | -9280.87 | -104.5% | 64415 | 53812.84 | -10602.16 | -16.46% | 1779 | 7945.1 | 6166.1 | 346.6% | 9168 | -5023.42 | -14191.42 | -154.8% | 102 | 67.75 | -34.25 | -33.58% | 2019-02-24 01:00
Markham | 2019 | 452939 | ( WO 317278) Replace 23 Transformers in V53 V54 | 99 | COMPLETE | Labour est. over | Filler work | N/A | Tenorlas, Reynaldo | No | Handy, James | Steve Rumble | 191912 | 147762.62 | -44149.38 | -23.01% | 60915 | 42238.06 | -18676.94 | -30.66% | 113857 | 92093.75 | -21763.25 | -19.11% | 17140 | 13430.81 | -3709.19 | -21.64% | 0 | 0 | 0 |  | 817 | 191.5 | -625.5 | -76.56% | 2019-03-22 01:00
Markham | 2019 | 452940 | ( WO 317279) Replace 4 Transformers in V58 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Steve Rumble | 98306 | 73058.07 | -25247.93 | -25.68% | 30865 | 18890.55 | -11974.45 | -38.8% | 59633 | 47448.49 | -12184.51 | -20.43% | 7808 | 6719.03 | -1088.97 | -13.95% | 0 | 0 | 0 |  | 413 | 140 | -273 | -66.1% | 2019-04-17 01:00
Markham | 2019 | 452941 | ( WO 317280) Replace 11 Transformers in V43 | 99 | COMPLETE | Labour est. over | Filler work | N/A | Tenorlas, Reynaldo | No | Handy, James | Steve Rumble | 187126 | 106942.42 | -80183.58 | -42.85% | 34733 | 1080.99 | -33652.01 | -96.89% | 74706 | 15269.91 | -59436.09 | -79.56% | 9009 | 8491.91 | -517.09 | -5.74% | 68678 | 2772.2 | -65905.8 | -95.96% | 465 | 253 | -212 | -45.59% | 2019-02-19 01:00
Markham | 2019 | 452942 | ( WO 317284) Replace 10 Transformers in V30 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 279476 | 142188.22 | -137287.78 | -49.12% | 46070 | 22092.5 | -23977.5 | -52.05% | 132558 | 101500.78 | -31057.22 | -23.43% | 9540 | 7774.5 | -1765.5 | -18.51% | 91308 | 10820.44 | -80487.56 | -88.15% | 553 | 409.8 | -143.2 | -25.9% | 2019-10-16 01:00
Markham | 2019 | 452943 | 452943 (WO 317292) Replace 2 Transformers in V15 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 34205 | 18362.62 | -15842.38 | -46.32% | 8230 | 3563.69 | -4666.31 | -56.7% | 12450 | 14353.93 | 1903.93 | 15.29% | 1964 | 445 | -1519 | -77.34% | 11561 | 0 | -11561 | -100% | 110 | 69.65 | -40.35 | -36.68% | 2019-11-15 01:00
Markham | 2019 | 452944 | 452944 (WO 317293) Replace 2 Transformers in V16 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 63215 | 21067.18 | -42147.82 | -66.67% | 12434 | 2828.19 | -9605.81 | -77.25% | 31353 | 16458.99 | -14894.01 | -47.5% | 2772 | 1780 | -992 | -35.79% | 16656 | 0 | -16656 | -100% | 140 | 35.5 | -104.5 | -74.64% | 2019-10-01 01:00
Markham | 2019 | 452945 | 452945 (WO 317298) Replace 24-73 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 0 | 20637.69 | 20637.69 |  | 0 | 2854.81 | 2854.81 |  | 0 | 17482.88 | 17482.88 |  | 0 | 300 | 300 |  | 0 | 0 | 0 |  | 68 | 27.5 | -40.5 | -59.56% | 2019-09-24 01:00
Markham | 2019 | 452946 | ( WO 317299) Replace 13-22 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 17683 | 8778.55 | -8904.45 | -50.36% | 4604 | 507.84 | -4096.16 | -88.97% | 6225 | 5498.51 | -726.49 | -11.67% | 1074 | 0 | -1074 | -100% | 5780 | 2772.2 | -3007.8 | -52.04% | 62 | 6 | -56 | -90.32% | 2019-10-10 01:00
Markham | 2019 | 452947 | 452947 (WO 317300) Replace Tx 31-114 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 36690 | 19805.24 | -16884.76 | -46.02% | 6360 | 1872.36 | -4487.64 | -70.56% | 20662 | 17482.88 | -3179.12 | -15.39% | 1340 | 450 | -890 | -66.42% | 8328 | 0 | -8328 | -100% | 73 | 24 | -49 | -67.12% | 2019-09-28 01:00
Markham | 2020 | 452952 | (WO317315) HIGHWAY NO. 7 WEST - #3201 AT INTERCHANGE WAY | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 0.41 | 0 | -0.41 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-25
Markham | 2019 | 452954 | 452954 (WO 317322) JU 17-140 | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 17508.58 | 14100.05 | -3408.53 | -19.47% | 3484.15 | 1700.08 | -1784.07 | -51.21% | 1821.75 | 2040.55 | 218.8 | 12.01% | 384.24 | 0 | -384.24 | -100% | 11818.44 | 10359.42 | -1459.02 | -12.35% | 26.53 | 6.5 | -20.03 | -75.5% | 2019-11-05 01:00
Markham | 2020 | 452955 | 452955 (WO 317323) Primont (Cornell 2) | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 331641.07 | 285189.45 | -46451.62 | -14.01% | 23873.11 | 39535.25 | 15662.14 | 65.61% | 2067.05 | 1192.99 | -874.06 | -42.29% | 1291.03 | 778 | -513.03 | -39.74% | 304409.88 | 236680.05 | -67729.83 | -22.25% | 214.2 | 216 | 1.8 | 0.8403% | 2020-05-12
Markham | 2021 | 452956 | 452956 (WO 317326) Yonge St. - #8868 at Westwood | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 49234.29 | 40338.67 | -8895.62 | -18.07% | 13432.23 | 13229.36 | -202.87 | -1.51% | 11049.13 | 9095.03 | -1954.1 | -17.69% | 3395.7 | 3570 | 174.3 | 5.133% | 14257.52 | 6985.67 | -7271.85 | -51% | 203 | 228.26 | 25.26 | 12.44% | 2021-06-30 01:00
Markham | 2020 | 452957 | 452957 (WO 317330) Union Midrise Residential Condo Bur Oak Ave. - #1735 at Markham Rd. | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Dave Lindsay | 59283.83 | 50789.72 | -8494.11 | -14.33% | 11573.79 | 8675.91 | -2897.88 | -25.04% | 43848.14 | 35316.04 | -8532.1 | -19.46% | 2286.9 | 1933.96 | -352.94 | -15.43% | 1575 | 0 | -1575 | -100% | 161 | 151 | -10 | -6.211% | 2020-10-06 01:00
Markham | 2020 | 452959 | 452959 (WO 317337) UG Feeder on Cornell Rouge Blvd | 99 | COMPLETE | Converted Project | N/A | N/A | Penner, Mitchell | No | Alectra Utilities | Steve Rumble | 390979 | 465983.62 | 75004.62 | 19.18% | 19447 | 97310.94 | 77863.94 | 400.4% | 68958 | 71093 | 2135 | 3.096% | 5984 | 8946 | 2962 | 49.5% | 296590 | 286822.43 | -9767.57 | -3.293% | 249 | 681.01 | 432.01 | 173.5% | 2020-05-12
Markham | 2019 | 452962 | (WO317363) Pole Relocate at Elgin Mills Road East | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Morrow, Joe | 252416 | 99639.12 | -152776.88 | -60.53% | 12632 | 7449.11 | -5182.89 | -41.03% | 48256 | 1248.18 | -47007.82 | -97.41% | 323 | 0 | -323 | -100% | 191205 | 90941.83 | -100263.17 | -52.44% | 501 | 770.5 | 269.5 | 53.79% | 2019-06-07
Markham | 2019 | 452965 | 452965 (WO 317382) Bishop's Gate Ph. 3 | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alarcon, Alejandro | Cory Ruiter | 123283.8 | 57949.37 | -65334.43 | -53% | 13378.44 | 1325.64 | -12052.8 | -90.09% | 1833.12 | 0 | -1833.12 | -100% | 2800.46 | 0 | -2800.46 | -100% | 105271.78 | 0 | -105271.78 | -100% | 170 | 65 | -105 | -61.76% | 2019-11-26 01:00
Markham | 2020 | 452969 | 452969 (WO 317408) Rutherford Rd - Jane to Westburne | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Shortt, Derek B. | 4497116.68 | 5471939.05 | 974822.37 | 21.68% | 1126254.39 | 763423.17 | -362831.22 | -32.22% | 1195316.92 | 1371417.81 | 176100.89 | 14.73% | 251650.89 | 119602 | -132048.89 | -52.47% | 1923894.48 | 3019915.76 | 1096021.28 | 56.97% | 18664.61 | 6270.4 | -12394.21 | -66.4% | 2020-11-12 01:00
Markham | 2021 | 452970 | 452970 - DIGRAM DEVELOPMENTS MARKHAM 2 | 99 | COMPLETE | Estimate incorrect | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Dave Lindsay | 17493.82 | 152706.34 | 135212.52 | 772.9% | 15840.38 | 9780.23 | -6060.15 | -38.26% | 951.4 | 0 | -951.4 | -100% | 702.04 | 1108 | 405.96 | 57.83% | 0 | 0 | 0 |  | 60.37 | 71 | 10.63 | 17.61% | 2021-12-08 01:00
Markham | 2019 | 452973 | (WO 317452) 201 Romina Drive | 99 | COMPLETE | Labour est. over |  |  | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 38564.55 | 40331.94 | 1767.39 | 4.583% | 9711.24 | 10353.02 | 641.78 | 6.609% | 22577.9 | 21054.45 | -1523.45 | -6.748% | 1944.68 | 6336 | 4391.32 | 225.8% | 4330.73 | 0 | -4330.73 | -100% | 114.5 | 177 | 62.5 | 54.59% | 2019-07-20 01:00
Markham | 2019 | 452975 | (WO 317472) Commercial Building - Service Shop | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Steve Rumble | 50884.06 | 30062.96 | -20821.1 | -40.92% | 13278.77 | 11506.55 | -1772.22 | -13.35% | 19660.24 | 16232.79 | -3427.45 | -17.43% | 3060.75 | 2197.67 | -863.08 | -28.2% | 14884.3 | 125.95 | -14758.35 | -99.15% | 214.5 | 159.5 | -55 | -25.64% | 2019-06-07
Markham | 2021 | 452976 | 452976 - MARKHAMONE POLE RELOCATION | 99 | COMPLETE | Scope – Eng | BOM cost variance | N/A | D'Onofrio, Tony | No | Estrada, Michael | Macdonald, Larry | 133095.77 | 66307.85 | -66787.92 | -50.18% | 50769.11 | 4904.04 | -45865.07 | -90.34% | 65235.72 | 17448.74 | -47786.98 | -73.25% | 7490.94 | 0 | -7490.94 | -100% | 9600 | 43955.07 | 34355.07 | 357.9% | 353.13 | 0 | -353.13 | -100% | 2021-09-24 01:00
Markham | 2022 | 453023 | 453023 (WO 317545) OH Relocation - HWY 427 EXTN, LANGSTAFF RD, EAST OF HUNTINGTON RD, VAUGHAN-Temp | 99 | COMPLETE | Material Over Estimated | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 26745 | 35323.15 | 8578.15 | 32.07% | 1993 | 149.91 | -1843.09 | -92.48% | 0 | 33398.29 | 33398.29 |  | 0 | 0 | 0 |  | 24752 | 1774.95 | -22977.05 | -92.83% | 0 | 0 | 0 |  | 2021-06-07 01:00
Markham | 2019 | 453024 | (WO317546) Hydro Relocation - HWY 427 EXTENSION, HUNTINGTON RD AND MAJOR MACKENZIE DR, VAUGHAN - Tem | 99 | COMPLETE | No Feedback from Const | N/A | N/A | O'Gay, Brian | No | Zhang, Jiacheng | Macdonald, Steve | 120000 | 31245.95 | -88754.05 | -73.96% | 0 | 80.85 | 80.85 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1010.64 | 1010.64 |  | 0 | 27 | 27 |  | 2019-07-26 01:00
Markham | 2020 | 453026 | 453026 (WO 317548) New Hotel | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Shane Christopher | 57753.79 | 60030.78 | 2276.99 | 3.943% | 10876.04 | 16973.88 | 6097.84 | 56.07% | 25543.52 | 24723.81 | -819.71 | -3.209% | 924.39 | 2375 | 1450.61 | 156.9% | 20409.84 | 12019.69 | -8390.15 | -41.11% | 114.65 | 131.5 | 16.85 | 14.7% | 2020-06-25 01:00
Markham | 2020 | 453030 | 453030 (WO 317576) 18 Water Street Seniors Bldg | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 45628.371 | 61286.02 | 15657.649 | 34.32% | 10646.1312 | 13087.67 | 2441.5388 | 22.93% | 28339.5192 | 44173.37 | 15833.8508 | 55.87% | 3410.1048 | 1460.5 | -1949.6048 | -57.17% | 0 | 911.85 | 911.85 |  | 151 | 171.5 | 20.5 | 13.58% | 2020-01-29 01:00
Markham | 2019 | 453031 | 453031 (WO 317577) 180 VIA RENZO @ ULTIMATE DR | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 82589.6604 | 59711.15 | -22878.5104 | -27.7% | 12120.1486 | 10201.16 | -1918.9886 | -15.83% | 43239.4294 | 41289.88 | -1949.5494 | -4.509% | 3978.4556 | 2229.5 | -1748.9556 | -43.96% | 19241.5864 | 3836.7 | -15404.8864 | -80.06% | 169 | 165.75 | -3.25 | -1.923% | 2019-09-24 01:00
Markham | 2021 | 453034 | 453034 (WO 317586) Pine Valley Enclave II Dev | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Dave Lindsay | 185360.82 | 178350.68 | -7010.14 | -3.782% | 20691.84 | 20962.84 | 271 | 1.31% | 5319.2 | 3909.85 | -1409.35 | -26.5% | 2067.22 | 1754.69 | -312.53 | -15.12% | 157282.56 | 145632 | -11650.56 | -7.407% | 193.95 | 76 | -117.95 | -60.81% | 2021-02-17 01:00
Markham | 2019 | 453037 | (WO317591) 150 Gibraltar | 99 | COMPLETE | Converted Project |  |  | Stephens, Barry N. | No | Dibratto, Susan | Steve Rumble | 157367.38 | 148863.35 | -8504.03 | -5.404% | 9412.22 | 3020.86 | -6391.36 | -67.9% | 101899.43 | 75317.22 | -26582.21 | -26.09% | 2321.55 | 0 | -2321.55 | -100% | 39406.5 | 0 | -39406.5 | -100% | 140.5 | 132.75 | -7.75 | -5.516% | 2019-03-27 01:00
Markham | 2020 | 453038 | 453038 (WO 317598) I&C - 7803 & 7815 DUFFERIN ST. | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 249718.11 | 219680.6 | -30037.51 | -12.03% | 28594.46 | 26552.2 | -2042.26 | -7.142% | 7124.86 | 4219.86 | -2905 | -40.77% | 2884.71 | 0 | -2884.71 | -100% | 211114.08 | 186013.85 | -25100.23 | -11.89% | 313.16 | 173.99 | -139.17 | -44.44% | 2020-01-14 01:00
Markham | 2020 | 453050 | 453050 (WO 317676) Nashville North - East of Channel Ph. 4B | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 180868.93 | 168332.35 | -12536.58 | -6.931% | 21403.4 | 26191.55 | 4788.15 | 22.37% | 1989.28 | 1308.2 | -681.08 | -34.24% | 1136.53 | 1317 | 180.47 | 15.88% | 156339.72 | 134900 | -21439.72 | -13.71% | 189.05 | 203.5 | 14.45 | 7.643% | 2020-02-13 01:00
Markham | 2020 | 453060 | (WO317737) Exist. Swgr Recovery & Splice | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Persaud, Ryan | 0 | 590.35 | 590.35 |  | 0 | 386.73 | 386.73 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-08 01:00
Markham | 2019 | 453082 | 453082 (WO 317837) 81 Performance Drive | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 61808.2 | 46732.04 | -15076.16 | -24.39% | 29385.24 | 17638.92 | -11746.32 | -39.97% | 25769.37 | 24658.78 | -1110.59 | -4.31% | 2714.24 | 2131 | -583.24 | -21.49% | 0 | 0 | 0 |  | 168 | 271 | 103 | 61.31% | 2019-11-26 01:00
Markham | 2020 | 453084 | 453084 (WO 317841) Town Homes - U-Social | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 75885.64 | 65434 | -10451.64 | -13.77% | 20235.19 | 7851.06 | -12384.13 | -61.2% | 41467.35 | 37933.12 | -3534.23 | -8.523% | 0 | 1503.15 | 1503.15 |  | 11134.66 | 13984.17 | 2849.51 | 25.59% | 228.5 | 133.25 | -95.25 | -41.68% | 2020-08-31 01:00
Markham | 2020 | 453090 | 453090 - KING EAST SUBDIVISION PHASE 2 | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 115076.32 | 112747.37 | -2328.95 | -2.024% | 11987.32 | 16161.09 | 4173.77 | 34.82% | 1871.36 | 0 | -1871.36 | -100% | 554.64 | 1247 | 692.36 | 124.8% | 100663 | 91704 | -8959 | -8.9% | 54.24 | 57.5 | 3.26 | 6.01% | 2020-11-10 01:00
Markham | 2019 | 453097 | (WO 317896) OH Relocation - 7089 YONGE STREET, MARKHAM, ON | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Zhang, Jiacheng | Macdonald, Steve | 208546 | 98978.55 | -109567.45 | -52.54% | 48924 | 1172.71 | -47751.29 | -97.6% | 52310 | 80668.88 | 28358.88 | 54.21% | 17674 | 4673.31 | -13000.69 | -73.56% | 89638 | 12463.65 | -77174.35 | -86.1% | 594 | 122.5 | -471.5 | -79.38% | 2019-06-07
Markham | 2020 | 453098 | 453098 (WO 317901) McNaughton Rd & Eagle Rock - F (1840 Major Mackenzie Dr) | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 95178.95 | 103834.14 | 8655.19 | 9.094% | 17081.33 | 22656.13 | 5574.8 | 32.64% | 39178.75 | 39583.44 | 404.69 | 1.033% | 1130.39 | 3067.5 | 1937.11 | 171.4% | 37788.48 | 35932.73 | -1855.75 | -4.911% | 277.65 | 207.98 | -69.67 | -25.09% | 2020-12-04 01:00
Markham | 2020 | 453101 | 453101 (WO 317909) 8470 Keele St | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 69636.55 | 77489.03 | 7852.48 | 11.28% | 23731.42 | 17222.88 | -6508.54 | -27.43% | 17635.21 | 23232.7 | 5597.49 | 31.74% | 4423.52 | 5986 | 1562.48 | 35.32% | 23846.4 | 22678.39 | -1168.01 | -4.898% | 216 | 207 | -9 | -4.167% | 2020-02-25 01:00
Markham | 2019 | 453111 | (WO 317977) Add 1x 27.6kV CCT - ELGIN MILLS RD-BAYVIEW TO LESLIE | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Morrow, Joe | 315977 | 317340.38 | 1363.38 | 0.4315% | 99850 | 70909.37 | -28940.63 | -28.98% | 141423 | 106567.17 | -34855.83 | -24.65% | 27454 | 36430 | 8976 | 32.69% | 47250 | 17004.12 | -30245.88 | -64.01% | 1338.5 | 1771 | 432.5 | 32.31% | 2019-07-30 01:00
Markham | 2019 | 453112 | (WO 317978) Add 1x 27.6kV CCT - ELGIN MILLS RD-LESLIE TO WOODBINE | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Morrow, Joe | 458505 | 560607.57 | 102102.57 | 22.27% | 158895 | 9227.35 | -149667.65 | -94.19% | 176254 | 186770.53 | 10516.53 | 5.967% | 44606 | 0 | -44606 | -100% | 78750 | 9658.5 | -69091.5 | -87.74% | 2131 | 2773 | 642 | 30.13% | 2019-06-07
Markham | 2021 | 453114 | 453114 (WO 317980) M48/R05 19th Av - Leslie to Woodbine - New 27.6kV Pole Line | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Ryan Walsh | 1488597.52 | 1527118.06 | 38520.54 | 2.588% | 550318.12 | 408906.37 | -141411.75 | -25.7% | 381981.86 | 416995.83 | 35013.97 | 9.166% | 68213.17 | 174060.65 | 105847.48 | 155.2% | 488084.37 | 480893.33 | -7191.04 | -1.473% | 2837.46 | 4304 | 1466.54 | 51.68% | 2021-01-06 01:00
Markham | 2022 | 453115 | 15132-15136 YONGE ST, AURORA/15132-15136 YONGE ST, AURORA | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Cranley, Stephen | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-09 01:00
Markham | 2019 | 453142 | (WO318014) 16th & McCowan Dev | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alarcon, Alejandro | Steve Rumble | 42135.3659 | 306736.55 | 264601.1841 | 628% | 30644.5204 | 10691.17 | -19953.3504 | -65.11% | 4439.1165 | 1810.19 | -2628.9265 | -59.22% | 7051.729 | 0 | -7051.729 | -100% | 0 | 6396.23 | 6396.23 |  | 384 | 213.5 | -170.5 | -44.4% | 2019-10-09 01:00
Markham | 2021 | 453143 | 453143 - INSPECT/CONNE/I&C - 1696913 ONTARIO INC. | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | D'Onofrio, Tony | Dave Lindsay | 179630.14 | 182131.28 | 2501.14 | 1.392% | 18410.35 | 29463.31 | 11052.96 | 60.04% | 1479.9 | 1236.42 | -243.48 | -16.45% | 948.57 | 1668 | 719.43 | 75.84% | 158791.32 | 147029 | -11762.32 | -7.407% | 117.68 | 136.5 | 18.82 | 15.99% | 2021-12-02 01:00
Markham | 2019 | 453145 | 453145 (WO 318021) J, K, L McNaughton & EagleRock | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 90075.28 | 57992.65 | -32082.63 | -35.62% | 10981.02 | 16364.28 | 5383.26 | 49.02% | 33156.8 | 33254.56 | 97.76 | 0.2948% | 3343.24 | 2436.5 | -906.74 | -27.12% | 37144.22 | 2218.74 | -34925.48 | -94.03% | 160 | 254 | 94 | 58.75% | 2019-12-04 01:00
Markham | 2020 | 453146 | 453146 (WO 318023) 9383 Islington Ave | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Steve Rumble | 62571.31 | 52862.36 | -9708.95 | -15.52% | 11718.06 | 12305.63 | 587.57 | 5.014% | 28678.13 | 25130.91 | -3547.22 | -12.37% | 3014.55 | 3219.53 | 204.98 | 6.8% | 15100.47 | 8465.24 | -6635.23 | -43.94% | 171 | 206.15 | 35.15 | 20.56% | 2020-04-16 01:00
Markham | 2020 | 453167 | (WO318081) 28 Main St West Building | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-07 01:00
Markham | 2020 | 453170 | 453170 - PARENT W.O. FOR UNPLANNED/BELL 18-068 | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 12511.5 | 8748.64 | -3762.86 | -30.08% | 4071.48 | 4212.07 | 140.59 | 3.453% | 1667.93 | 165.57 | -1502.36 | -90.07% | 1338.59 | 1052 | -286.59 | -21.41% | 5433.5 | 3319 | -2114.5 | -38.92% | 100.6 | 32 | -68.6 | -68.19% | 2020-10-07 01:00
Markham | 2019 | 453173 | 453173 (WO 318092) Langstaff Road - Pole Repl. | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Larry | 274429 | 172817 | -101612 | -37.03% | 114311 | 59730 | -54581 | -47.75% | 52259 | 66027 | 13768 | 26.35% | 47823 | 25749 | -22074 | -46.16% | 60036 | 21311 | -38725 | -64.5% | 1329.89 | 1227.5 | -102.39 | -7.699% | 2019-11-26 01:00
Markham | 2022 | 453175 | 453175 - JOINT USE PERMIT 18-079 | 99 | COMPLETE | Cont Est Over | Labour est. over | Material Over Estimated | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 55033.59 | 31794.11 | -23239.48 | -42.23% | 20998.76 | 14170.27 | -6828.49 | -32.52% | 9864.36 | 4601.33 | -5263.03 | -53.35% | 4596.47 | 5580 | 983.53 | 21.4% | 19574 | 7442.51 | -12131.49 | -61.98% | 161.7 | 145 | -16.7 | -10.33% | 2022-01-27 01:00
Markham | 2020 | 453178 | 453178 (WO 318101) 329-343 Carrville Rd | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 184396.28 | 189600.33 | 5204.05 | 2.822% | 13064.37 | 8409.08 | -4655.29 | -35.63% | 8760.95 | 7964.89 | -796.06 | -9.086% | 2252.52 | 371 | -1881.52 | -83.53% | 160318.44 | 18915.54 | -141402.9 | -88.2% | 188.66 | 83 | -105.66 | -56.01% | 2020-02-19 01:00
Markham | 2019 | 453181 | (WO318108) 707 Creditstone Road | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 61625.46 | 40763.23 | -20862.23 | -33.85% | 10081.66 | 7717.67 | -2363.99 | -23.45% | 27198.79 | 28708.57 | 1509.78 | 5.551% | 2506.35 | 4235.94 | 1729.59 | 69.01% | 18865.31 | 101.05 | -18764.26 | -99.46% | 149 | 100 | -49 | -32.89% | 2019-05-17
Markham | 2021 | 453182 | 453182 (WO 318114 ) A02 - Princeton Heights | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Fitz Randolph, Kim C | Dave Lindsay | 23013.1231 | 145563.48 | 122550.3569 | 532.5% | 14802.4695 | 6419.22 | -8383.2495 | -56.63% | 5733.1786 | 1938.57 | -3794.6086 | -66.19% | 2477.475 | 1657 | -820.475 | -33.12% | 0 | 0 | 0 |  | 197 | 142.5 | -54.5 | -27.66% | 2021-04-27
Markham | 2019 | 453195 | (WO 318150) JU 18-087 New anchor and down guy | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Battistella, Alexander | Macdonald, Larry | 14209 | 12161.7 | -2047.3 | -14.41% | 4126 | 3382.05 | -743.95 | -18.03% | 845 | 2279.7 | 1434.7 | 169.8% | 808 | 235.75 | -572.25 | -70.82% | 8430 | 6264.2 | -2165.8 | -25.69% | 64.96 | 54.65 | -10.31 | -15.87% | 2019-08-27 01:00
Markham | 2021 | 453196 | 453196 - PRIMA VISTA PH4 | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 383354.35 | 360299.82 | -23054.53 | -6.014% | 38119.55 | 6199.01 | -31920.54 | -83.74% | 2306.52 | 0 | -2306.52 | -100% | 363.28 | 992 | 628.72 | 173.1% | 342565 | 60.35 | -342504.65 | -99.98% | 48.48 | 38.5 | -9.98 | -20.59% | 2021-11-11 01:00
Markham | 2021 | 453202 | 453202 (WO 318166) Incon Property Holdings (Maple Grove) Ltd. | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Dave Lindsay | 30067.72 | 147742.56 | 117674.84 | 391.4% | 22001.7 | 12376.56 | -9625.14 | -43.75% | 5592.51 | 5253.06 | -339.45 | -6.07% | 2473.51 | 2051.52 | -421.99 | -17.06% | 0 | 0 | 0 |  | 226.86 | 64 | -162.86 | -71.79% | 2021-07-21 01:00
Markham | 2020 | 453203 | 453203 (WO 318171) Dufferin & Langstaff Shell Station Development, Vaughan | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 281807.35 | 135848.81 | -145958.54 | -51.79% | 131796.52 | 11709.9 | -120086.62 | -91.12% | 70607.65 | 30014.38 | -40593.27 | -57.49% | 26080.88 | 0 | -26080.88 | -100% | 53322.3 | 94124.53 | 40802.23 | 76.52% | 1715.48 | 19 | -1696.48 | -98.89% | 2020-10-30 01:00
Markham | 2020 | 453211 | (WO 318186) Bollards for Switchgear on Zenway, Vaughan | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-07 01:00
Markham | 2022 | 453212 | 453212 (WO 318189) Hydro Relocation - HWY 427 EXTN, MAJOR MACK DR, Wes of HUNTINGTON RD, VAUGHAN - | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 57507 | 33078.41 | -24428.59 | -42.48% | 4386 | 2463.41 | -1922.59 | -43.83% | 0 | 369.02 | 369.02 |  | 0 | 0 | 0 |  | 53121 | 1756.87 | -51364.13 | -96.69% | 0 | 20 | 20 |  | 2021-06-07 01:00
Markham | 2019 | 453213 | 453213 (WO 318191) REPLACEMENT OF POLE P40762 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 42095 | 73300.57 | 31205.57 | 74.13% | 25226 | 39022.11 | 13796.11 | 54.69% | 5582 | 15453.96 | 9871.96 | 176.9% | 9167 | 15574.5 | 6407.5 | 69.9% | 2120 | 3250 | 1130 | 53.3% | 324 | 515.5 | 191.5 | 59.1% | 2019-11-06 01:00
Markham | 2021 | 453214 | 453214 - INSPECT/CONNE/OAK KNOLLSUBDIVISION PHASE 4 | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 167379.41 | 178857.04 | 11477.63 | 6.857% | 7556.56 | 20450.25 | 12893.69 | 170.6% | 1184.08 | 995.73 | -188.35 | -15.91% | 586.17 | 1060.9 | 474.73 | 80.99% | 158052.6 | 147430.8 | -10621.8 | -6.72% | 53.24 | 51.5 | -1.74 | -3.268% | 2021-01-13 01:00
Markham | 2019 | 453215 | (WO 318194) Pine Valley pole relocations, Vaughan | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Battistella, Alexander | Macdonald, Steve | 130566 | 45512.88 | -85053.12 | -65.14% | 65624 | 1371.6 | -64252.4 | -97.91% | 35866 | 23475.02 | -12390.98 | -34.55% | 15951 | 3521.26 | -12429.74 | -77.92% | 13125 | 17145 | 4020 | 30.63% | 690.5 | 37.5 | -653 | -94.57% | 2019-05-03 01:00
Markham | 2019 | 453225 | (WO318215) 7200 Martin Grove | 99 | COMPLETE | Labour est. over |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 118742.8006 | 100439.27 | -18303.5306 | -15.41% | 17952.4197 | 1351.2 | -16601.2197 | -92.47% | 67532.6 | 53654.54 | -13878.06 | -20.55% | 6686.48 | 0 | -6686.48 | -100% | 21200 | 16890.04 | -4309.96 | -20.33% | 260 | 267.5 | 7.5 | 2.885% | 2019-06-22 01:00
Markham | 2019 | 453233 | (WO318234) Trans Canada Pipe Line-Phase 2 | 99 | COMPLETE | Labour est. under |  |  | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 110638.62 | 102164.18 | -8474.44 | -7.66% | 19187.13 | 1896.31 | -17290.82 | -90.12% | 79784.46 | 63960.84 | -15823.62 | -19.83% | 4346.21 | 90 | -4256.21 | -97.93% | 5781.8 | 0 | -5781.8 | -100% | 256 | 309 | 53 | 20.7% | 2019-06-18 01:00
Markham | 2019 | 453237 | 453237 (WO 318240) M43 Steeles and Quail Valley | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 819759.31 | 833871 | 14111.69 | 1.721% | 20750 | 79528 | 58778 | 283.3% | 7692.31 | 1566 | -6126.31 | -79.64% | 2073 | 0 | -2073 | -100% | 789244 | 752777 | -36467 | -4.62% | 262 | 209.5 | -52.5 | -20.04% | 2019-12-19 01:00
Markham | 2019 | 453252 | 453252 (WO 318259) Pole relocation Hwy 27 and CPR | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Barry, Kenneth | Macdonald, Steve | 461049.93 | 399073.91 | -61976.02 | -13.44% | 16055.8 | 29370.98 | 13315.18 | 82.93% | 127314.29 | 139761.22 | 12446.93 | 9.777% | 0 | 0 | 0 |  | 317679.84 | 226173.06 | -91506.78 | -28.8% | 3.6 | 82 | 78.4 | 2178% | 2019-11-05 01:00
Markham | 2019 | 453255 | (WO 318266) Leslie Street - Elgin Mills to 19th Avenue | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Battistella, Alexander | Shortt, Derek B. | 536819.83 | 530521.63 | -6298.2 | -1.173% | 148832.5 | 18352.68 | -130479.82 | -87.67% | 125035.91 | 71454.39 | -53581.52 | -42.85% | 70071.42 | 0 | -70071.42 | -100% | 192880 | 157763.63 | -35116.37 | -18.21% | 1655 | 2038.5 | 383.5 | 23.17% | 2019-07-01 01:00
Markham | 2019 | 453259 | (WO318292) Highway No. 50 - #8865 | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Yuen, Paul | Steve Rumble | 101488.12 | 68247.12 | -33241 | -32.75% | 13021.68 | 432.27 | -12589.41 | -96.68% | 55746.01 | 44743.81 | -11002.2 | -19.74% | 3776.85 | 0 | -3776.85 | -100% | 21422.98 | 0 | -21422.98 | -100% | 174 | 189.5 | 15.5 | 8.908% | 2019-04-11 01:00
Markham | 2021 | 453263 | 453263 - CITYVIEW BLVD AT TESTON RD/SPLIT 1/0 LOOP | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Horlings, Jake | 236553.52 | 231658.92 | -4894.6 | -2.069% | 45766.26 | 29748.26 | -16018 | -35% | 27297.38 | 40791.78 | 13494.4 | 49.43% | 4093.76 | 2401.5 | -1692.26 | -41.34% | 159396.12 | 133702.38 | -25693.74 | -16.12% | 205.48 | 148 | -57.48 | -27.97% | 2021-06-04 01:00
Markham | 2020 | 453264 | 453264 (WO 318299) King Rd & McCachen St | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 29391.35 | 183238.38 | 153847.03 | 523.4% | 15786.57 | 11896.28 | -3890.29 | -24.64% | 7788.83 | 4241.37 | -3547.46 | -45.55% | 2315.95 | 3134.32 | 818.37 | 35.34% | 3500 | 288.4 | -3211.6 | -91.76% | 239.82 | 100.5 | -139.32 | -58.09% | 2020-11-04 01:00
Markham | 2019 | 453266 | (WO 318306) 62 Sherwood Forest Dr. Pole Relocation, Markham | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Barry, Kenneth | Macdonald, Larry | 18403.89 | 13155.39 | -5248.5 | -28.52% | 9978.94 | 4360.98 | -5617.96 | -56.3% | 5086.57 | 5070.41 | -16.16 | -0.3177% | 1808.29 | 2004 | 195.71 | 10.82% | 1530.09 | 1720 | 189.91 | 12.41% | 88.25 | 67 | -21.25 | -24.08% | 2019-08-23 01:00
Markham | 2019 | 453267 | 453267 (WO 318308) 100 Eagle Rock Way | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 109478.51 | 123531.84 | 14053.33 | 12.84% | 12573.46 | 11091.73 | -1481.73 | -11.78% | 72450 | 65649.84 | -6800.16 | -9.386% | 3603.6 | 2901.29 | -702.31 | -19.49% | 15750 | 911.85 | -14838.15 | -94.21% | 188 | 226.25 | 38.25 | 20.35% | 2019-12-04 01:00
Markham | 2020 | 453268 | 453268 (WO 318309) 7290 Major Mackenzie D | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Dave Lindsay | 166037.98 | 182101.84 | 16063.86 | 9.675% | 11273.22 | 13979.31 | 2706.09 | 24% | 95875.5 | 91080.9 | -4794.6 | -5.001% | 2402.4 | 914.84 | -1487.56 | -61.92% | 52426.76 | 61282.65 | 8855.89 | 16.89% | 164 | 184.25 | 20.25 | 12.35% | 2020-11-12 01:00
Markham | 2019 | 453275 | (WO318353) Lowering of Duct Bank - Glen Meadows & Bayview Ave | 99 | COMPLETE | Labour est. under | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Steve Rumble | 20016 | 18973.61 | -1042.39 | -5.208% | 6142 | 5124.28 | -1017.72 | -16.57% | 881 | 433 | -448 | -50.85% | 1386 | 0 | -1386 | -100% | 11607 | 0 | -11607 | -100% | 82 | 95.75 | 13.75 | 16.77% | 2019-05-14
Markham | 2020 | 453276 | 453276 (WO 318356) Wycliffe the Promenade | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 315394.95 | 289736.2 | -25658.75 | -8.135% | 23217.51 | 15302.21 | -7915.3 | -34.09% | 1955.13 | 1517.01 | -438.12 | -22.41% | 1440.03 | 0 | -1440.03 | -100% | 288782.28 | 48.45 | -288733.83 | -99.98% | 199.2 | 176 | -23.2 | -11.65% | 2020-05-28
Markham | 2019 | 453277 | 453277 - JU Permit 18-134 | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 23262.98 | 25173 | 1910.02 | 8.211% | 3455.49 | 3818 | 362.51 | 10.49% | 3982.73 | 1847 | -2135.73 | -53.62% | 510.36 | 357 | -153.36 | -30.05% | 15314.4 | 19151 | 3836.6 | 25.05% | 34 | 20.5 | -13.5 | -39.71% | 2019-10-18 01:00
Markham | 2019 | 453284 | 453284 (WO 318378) 30 Sims Crescent | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 134527 | 145668.38 | 11141.38 | 8.282% | 13169 | 9176.56 | -3992.44 | -30.32% | 95098 | 93128 | -1970 | -2.072% | 3511 | 1800 | -1711 | -48.73% | 18661 | 30663.27 | 12002.27 | 64.32% | 192 | 194.25 | 2.25 | 1.172% | 2019-08-22 01:00
Markham | 2020 | 453289 | 453289 (WO 318387) Industrial Bldg on Hillmount | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Steve Rumble | 143476.78 | 146549.4 | 3072.62 | 2.142% | 12468.72 | 18475.01 | 6006.29 | 48.17% | 97444.79 | 94088.04 | -3356.75 | -3.445% | 4128.9 | 2269.5 | -1859.4 | -45.03% | 25424.33 | 27575.49 | 2151.16 | 8.461% | 174 | 255.5 | 81.5 | 46.84% | 2020-05-29
Markham | 2019 | 453290 | (WO 318388) 25 Farrell Rd. | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 65970.3 | 65172.05 | -798.25 | -1.21% | 9970.09 | 0 | -9970.09 | -100% | 26323.26 | 20353.13 | -5970.13 | -22.68% | 2471.7 | 0 | -2471.7 | -100% | 24231.9 | 0 | -24231.9 | -100% | 247 | 240 | -7 | -2.834% | 2019-10-10 01:00
Markham | 2019 | 453291 | 453291 (WO 318390) Phase 1.1 BATHURST STREET(N. OF SUMMERIDGE DR TO N. OF NER ISRAEL DR), VAUGHAN | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 1372052 | 1410743.45 | 38691.45 | 2.82% | 12867 | 64096.83 | 51229.83 | 398.1% | 201343 | 159323.37 | -42019.63 | -20.87% | 736 | 0 | -736 | -100% | 1157106 | 487916.92 | -669189.08 | -57.83% | 162 | 379.5 | 217.5 | 134.3% | 2019-08-29 01:00
Markham | 2020 | 453305 | 453305 - 8399 KIPLING AVE. UNPLANNED/RELOCATE U/G PRIMARY CONDUCTOR | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Lamb, Tim | 33834.07 | 29869.5 | -3964.57 | -11.72% | 11191.3 | 9689.16 | -1502.14 | -13.42% | 1345.55 | 0 | -1345.55 | -100% | 1005.1 | 411 | -594.1 | -59.11% | 20292.12 | 18082.71 | -2209.41 | -10.89% | 73.6467 | 50 | -23.6467 | -32.11% | 2020-11-24 01:00
Markham | 2021 | 453306 | 453306 - RUTHERFORD RD. PH.3 - BATHURST TO PETER RUPERT | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | Yes | Barry, Kenneth | Ryan Walsh | 4618424.26 | 4315700.96 | -302723.3 | -6.555% | 1447039.97 | 1162388.37 | -284651.6 | -19.67% | 1156451.25 | 1376797.88 | 220346.63 | 19.05% | 329622.26 | 321315 | -8307.26 | -2.52% | 1685310.78 | 1424555.79 | -260754.99 | -15.47% | 12139.8267 | 13149.75 | 1009.9233 | 8.319% | 2021-12-21 01:00
Markham | 2019 | 453325 | (WO 318446) JU 18-135 | 99 | COMPLETE | Converted Project |  |  |  | No | Martin, Shane | Macdonald, Larry | 6746 | 2211.3 | -4534.7 | -67.22% | 2871 | 314.58 | -2556.42 | -89.04% | 710 | 0 | -710 | -100% | 268 | 0 | -268 | -100% | 0 | 1896.72 | 1896.72 |  | 11.59 | 0 | -11.59 | -100% | 2019-10-04 01:00
Markham | 2019 | 453332 | (WO 453332) Joint Use Permit 18-008- Stouffville Road- | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 13518.42 | 5575.52 | -7942.9 | -58.76% | 2313.53 | 721.61 | -1591.92 | -68.81% | 921.61 | 359.53 | -562.08 | -60.99% | 168 | 0 | -168 | -100% | 10115.28 | 4494.38 | -5620.9 | -55.57% | 6.52 | 1 | -5.52 | -84.66% | 2019-09-25 01:00
Markham | 2020 | 453333 | 453333 - PARENT W.O. FOR UNPLANNED/18-042 | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 24421.07 | 18498.25 | -5922.82 | -24.25% | 8710.14 | 8351.05 | -359.09 | -4.123% | 5590.46 | 3555.61 | -2034.85 | -36.4% | 1724.55 | 3573.04 | 1848.49 | 107.2% | 8395.92 | 3018.55 | -5377.37 | -64.05% | 123.52 | 84 | -39.52 | -31.99% | 2020-11-11 01:00
Markham | 2020 | 453360 | 453360 (WO 318496) Relocate Poles (Hwy 50 @ Major Mac) | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 368095.12 | 473932.23 | 105837.11 | 28.75% | 156982.76 | 42083.94 | -114898.82 | -73.19% | 114449.57 | 124812.86 | 10363.29 | 9.055% | 37947.56 | 240 | -37707.56 | -99.37% | 58715.23 | 291946.08 | 233230.85 | 397.2% | 2004.89 | 70.5 | -1934.39 | -96.48% | 2020-06-13 01:00
Markham | 2019 | 453365 | (WO 318501) 520 WORTH BOULEVARD | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Battistella, Alexander | Lamb, Tim | 43153 | 48697.53 | 5544.53 | 12.85% | 8347 | 2151.62 | -6195.38 | -74.22% | 2564 | 0 | -2564 | -100% | 1271 | 0 | -1271 | -100% | 30971 | 35372.07 | 4401.07 | 14.21% | 65 | 33 | -32 | -49.23% | 2019-06-18 01:00
Markham | 2019 | 453375 | (WO318519) UG Cable Replacement. ARROWHEAD DR AND WIGWOSS DR | 99 | COMPLETE | Labour est. under |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 223318 | 191438.72 | -31879.28 | -14.28% | 8636 | 16368.03 | 7732.03 | 89.53% | 108 | 0 | -108 | -100% | 2391 | 0 | -2391 | -100% | 212183 | 175070.69 | -37112.31 | -17.49% | 61 | 86.5 | 25.5 | 41.8% | 2019-06-29 01:00
Markham | 2020 | 453376 | 453376 (WO 318520) 11201 Keele St, Vaughan, ON | 99 | COMPLETE | Converted Project |  |  | Stephens, Barry N. | No | Alectra Utilities | Steve Rumble | 40930.008 | 42848.19 | 1918.182 | 4.686% | 10490.76 | 9682.29 | -808.47 | -7.706% | 19440.75 | 18844.97 | -595.78 | -3.065% | 2633.4 | 3980.83 | 1347.43 | 51.17% | 4305 | 6298.65 | 1993.65 | 46.31% | 154 | 170 | 16 | 10.39% | 2020-04-01 01:00
Markham | 2020 | 453377 | (WO318521) 7700 Bayview Ave | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-28 01:00
Markham | 2019 | 453381 | 453381 (WO 318527) 95 ERIC T SMITH WAY - Flex Office Development | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Martin, Shane | Steve Rumble | 44555.2 | 40182.01 | -4373.19 | -9.815% | 8966.65 | 7923.25 | -1043.4 | -11.64% | 24104.08 | 18596.94 | -5507.14 | -22.85% | 2027.03 | 1160 | -867.03 | -42.77% | 5240.13 | 7191.7 | 1951.57 | 37.24% | 138 | 160 | 22 | 15.94% | 2019-11-28 01:00
Markham | 2019 | 453382 | 453382 (WO 318529) V01 Clark and Yonge (York Hill Phase 4) | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 1446934.74 | 1798733.59 | 351798.85 | 24.31% | 142547.01 | 223769.37 | 81222.36 | 56.98% | 96505.53 | 26838.28 | -69667.25 | -72.19% | 16382.44 | 16373.66 | -8.78 | -0.05359% | 1191499.76 | 1531752.28 | 340252.52 | 28.56% | 1083 | 916.5 | -166.5 | -15.37% | 2019-12-13 01:00
Markham | 2020 | 453387 | 453387 (WO 318536) Nashville Heights - Barons Property | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 925610.7 | 913635.53 | -11975.17 | -1.294% | 60924.07 | 107845.96 | 46921.89 | 77.02% | 3581.19 | 3132.15 | -449.04 | -12.54% | 3325.16 | 4899 | 1573.84 | 47.33% | 857780.28 | 790741 | -67039.28 | -7.815% | 281.92 | 254.25 | -27.67 | -9.815% | 2020-12-07 01:00
Markham | 2020 | 453389 | 453389 (WO 318541) 343,349,355 ELGIN MILLS RD | 99 | COMPLETE | Converted Project |  |  | Penner, Mitchell | No | Alectra Utilities | Steve Rumble | 84558.25 | 85650.31 | 1092.06 | 1.291% | 12219.82 | 14344.05 | 2124.23 | 17.38% | 602.79 | 0 | -602.79 | -100% | 536.64 | 451 | -85.64 | -15.96% | 71199 | 65925 | -5274 | -7.407% | 61.08 | 88.5 | 27.42 | 44.89% | 2020-02-25 01:00
Markham | 2019 | 453394 | (WO318550) 277 Cityview Blvd | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 146245.68 | 140685.16 | -5560.52 | -3.802% | 9003.12 | 6735.45 | -2267.67 | -25.19% | 112297.5 | 110920.42 | -1377.08 | -1.226% | 2541 | 4200 | 1659 | 65.29% | 14521.5 | 13936.73 | -584.77 | -4.027% | 150 | 143.75 | -6.25 | -4.167% | 2019-08-31 01:00
Markham | 2020 | 453405 | (WO318591) 2 Canada's Wonderland Dr | 99 | CANCELLED | N/A |  |  | Stephens, Barry N. | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-04 01:00
Markham | 2019 | 453409 | 453409 (WO 318596) Holiday Inn Hotel. ERIC T SMITH WAY | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Martin, Shane | Steve Rumble | 74600.18 | 69377.42 | -5222.76 | -7.001% | 8966.65 | 9569.73 | 603.08 | 6.726% | 27949.46 | 21804.12 | -6145.34 | -21.99% | 1957.73 | 1770 | -187.73 | -9.589% | 31839.64 | 32425.96 | 586.32 | 1.841% | 134.5 | 163.25 | 28.75 | 21.38% | 2019-10-04 01:00
Markham | 2019 | 453411 | (Wo 318598) Pole Relocation - 19th Avenue & Hwy 48, Markham | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Steve | 28871 | 32493.38 | 3622.38 | 12.55% | 15386 | 13132.35 | -2253.65 | -14.65% | 2220 | 281.62 | -1938.38 | -87.31% | 3845 | 720 | -3125 | -81.27% | 7420 | 18359.41 | 10939.41 | 147.4% | 165 | 129 | -36 | -21.82% | 2019-07-12 01:00
Markham | 2019 | 453413 | (WO 318601) 2019 Pole Replacement Batch 02 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Larry | 114722 | 115067 | 345 | 0.3007% | 56039 | 96942.05 | 40903.05 | 72.99% | 23853 | 15768.12 | -8084.88 | -33.89% | 16455 | 2356.83 | -14098.17 | -85.68% | 18375 | 0 | -18375 | -100% | 752.35 | 47.5 | -704.85 | -93.69% | 2019-02-06 01:00
Markham | 2019 | 453414 | (WO 318602) Pole Replacement 2019 Batch 3 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Morrow, Joe | 152103 | 71783.3 | -80319.7 | -52.81% | 57322 | 3873.24 | -53448.76 | -93.24% | 51677 | 62515.82 | 10838.82 | 20.97% | 16854 | 760.5 | -16093.5 | -95.49% | 26250 | 0 | -26250 | -100% | 769.6 | 1174.5 | 404.9 | 52.61% | 2019-06-28 01:00
Markham | 2020 | 453416 | 453416 (WO 318604) 6220 Highway 7 | 99 | COMPLETE | Converted Project | N/A | N/A | Stephens, Barry N. | No | Alectra Utilities | Steve Rumble | 59857.15 | 54378.88 | -5478.27 | -9.152% | 12182.95 | 8046.22 | -4136.73 | -33.96% | 30731.2 | 31428.86 | 697.66 | 2.27% | 3205.13 | 1745.5 | -1459.63 | -45.54% | 9082.23 | 10969.5 | 1887.27 | 20.78% | 179 | 115 | -64 | -35.75% | 2020-06-14 01:00
Markham | 2019 | 453418 | (WO318610) Build Two Feeder Ties on Hwy 50 between Vaughan and Brampton | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Steve | 80846 | 80615.33 | -230.67 | -0.2853% | 28411 | 3388.97 | -25022.03 | -88.07% | 19139 | 19262.91 | 123.91 | 0.6474% | 7046 | 0 | -7046 | -100% | 26250 | 42362.13 | 16112.13 | 61.38% | 380 | 3 | -377 | -99.21% | 2019-08-08 01:00
Markham | 2019 | 453419 | (WO318611) CAN-AR & Hwy 50 (8905 Hwy 50. Vaughan) | 99 | COMPLETE | Labour est. under |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 132867.45 | 106956.36 | -25911.09 | -19.5% | 9231.36 | 12298.11 | 3066.75 | 33.22% | 78259.8 | 66277.12 | -11982.68 | -15.31% | 5416.05 | 3686 | -1730.05 | -31.94% | 15900 | 9964.03 | -5935.97 | -37.33% | 202 | 235.25 | 33.25 | 16.46% | 2019-07-20 01:00
Markham | 2020 | 453420 | (WO318613) 7615 Keele Street | 99 | CANCELLED | N/A |  |  | Stephens, Barry N. | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-20 01:00
Markham | 2019 | 453421 | 453421 (WO 318614) Cornell Centre Midrise Ph 2. ADAM SELLERS ST. - #58 AT RUSTLE WOODS | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 65636.6518 | 55528.32 | -10108.3319 | -15.4% | 14547.96 | 9026.86 | -5521.1 | -37.95% | 28586.8259 | 25118.57 | -3468.2559 | -12.13% | 3418.8 | 983 | -2435.8 | -71.25% | 14918.8935 | 17572.7 | 2653.8065 | 17.79% | 209 | 143 | -66 | -31.58% | 2019-11-20 01:00
Markham | 2020 | 453423 | 453423 (WO 318616) 2019 Pad TX Repl. - Batch 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Chris Hagan | 345434.7 | 135622.02 | -209812.68 | -60.74% | 88267.66 | 17145.03 | -71122.63 | -80.58% | 173970.77 | 93170.96 | -80799.81 | -46.44% | 11916.27 | 5657.31 | -6258.96 | -52.52% | 71280 | 19648.72 | -51631.28 | -72.43% | 752.53 | 197 | -555.53 | -73.82% | 2020-12-10 01:00
Markham | 2019 | 453424 | 453424 (WO 318617) 2019 Pad TX Repl. - Batch 2 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Cory Ruiter | 101392 | 50184.11 | -51207.89 | -50.5% | 31572 | 7192.79 | -24379.21 | -77.22% | 52573 | 32920.16 | -19652.84 | -37.38% | 12938 | 2309 | -10629 | -82.15% | 4309 | 7762.16 | 3453.16 | 80.14% | 407 | 126 | -281 | -69.04% | 2019-10-30 01:00
Markham | 2019 | 453425 | 453425 (WO 318618) 2019 Pad TX Repl. - Batch 3 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Steve Rumble | 250606.22 | 119767.03 | -130839.19 | -52.21% | 43377.48 | 13240.66 | -30136.82 | -69.48% | 105538.49 | 64137.49 | -41401 | -39.23% | 8886.93 | 1371 | -7515.93 | -84.57% | 92803.32 | 41017.88 | -51785.44 | -55.8% | 349 | 101 | -248 | -71.06% | 2019-12-04 01:00
Markham | 2019 | 453426 | 453426 (WO 318619) 2019 Pad TX Repl. - Batch 4 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Steve Rumble | 157498.05 | 117183 | -40315.05 | -25.6% | 30046.5 | 11161 | -18885.5 | -62.85% | 63609.32 | 53515 | -10094.32 | -15.87% | 5135.59 | 1063 | -4072.59 | -79.3% | 58706.64 | 51444 | -7262.64 | -12.37% | 424.25 | 71.5 | -352.75 | -83.15% | 2019-12-21 01:00
Markham | 2019 | 453427 | 453427 (WO 318621) 2019 Pad TX Repl. - Batch 5 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Steve Rumble | 194796.33 | 53408.28 | -141388.05 | -72.58% | 24855.25 | 12425.26 | -12429.99 | -50.01% | 89116.91 | 38463.02 | -50653.89 | -56.84% | 6185.37 | 2520 | -3665.37 | -59.26% | 74638.8 | 0 | -74638.8 | -100% | 474.35 | 152.5 | -321.85 | -67.85% | 2019-12-17 01:00
Markham | 2019 | 453428 | 453428 (WO 318622) 2019 Padmount Transformer Replacement Batch 6 - Vaughan | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Steve Rumble | 325208.31 | 233031.37 | -92176.94 | -28.34% | 44577.26 | 22523.12 | -22054.14 | -49.47% | 138108.26 | 100720.4 | -37387.86 | -27.07% | 9600.71 | 2997 | -6603.71 | -68.78% | 132922.08 | 106790.85 | -26131.23 | -19.66% | 729.05 | 164.5 | -564.55 | -77.44% | 2019-12-12 01:00
Markham | 2019 | 453429 | (WO318623) 2019 Padmount Transformer Replacement Batch 8 - Vaughan | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Steve Rumble | 95809 | 73870.53 | -21938.47 | -22.9% | 29289 | 27415.8 | -1873.2 | -6.396% | 54611 | 40493.25 | -14117.75 | -25.85% | 7184 | 5961.48 | -1222.52 | -17.02% | 4725 | 0 | -4725 | -100% | 311 | 42 | -269 | -86.5% | 2019-04-17 01:00
Markham | 2019 | 453432 | 453432 (WO 318626) 2019 Padmount Transformer Replacement Batch 10 - Vaughan | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Steve Rumble | 234729.93 | 128008 | -106721.93 | -45.47% | 35461.5 | 19769 | -15692.5 | -44.25% | 92698.24 | 72178 | -20520.24 | -22.14% | 7277.15 | 3430 | -3847.15 | -52.87% | 99293.04 | 32631 | -66662.04 | -67.14% | 552.65 | 205 | -347.65 | -62.91% | 2019-12-15 01:00
Markham | 2019 | 453440 | (WO 318637) MARCO CR AND AIRDRIE DR | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 201520 | 157301.74 | -44218.26 | -21.94% | 7399 | 18448.67 | 11049.67 | 149.3% | 541 | 0 | -541 | -100% | 1849 | 370 | -1479 | -79.99% | 191731 | 136814.17 | -54916.83 | -28.64% | 95 | 141.5 | 46.5 | 48.95% | 2019-09-24 01:00
Markham | 2019 | 453441 | 453441 (WO 318638) Storm Hardening 2019 Keele | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Shortt, Derek B. | 1024259 | 675826.87 | -348432.13 | -34.02% | 446209 | 288182.61 | -158026.39 | -35.42% | 236297 | 160852.52 | -75444.48 | -31.93% | 183175 | 107593 | -75582 | -41.26% | 158578 | 56759.99 | -101818.01 | -64.21% | 4746.98 | 3716.5 | -1030.48 | -21.71% | 2019-12-20 01:00
Markham | 2019 | 453443 | (WO318641) 2019 - Pdmt TX Rep. Batch 11 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 89808.8 | 74255.82 | -15552.98 | -17.32% | 32506 | 348.43 | -32157.57 | -98.93% | 47681.8 | 42158.15 | -5523.65 | -11.58% | 9621 | 5949.77 | -3671.23 | -38.16% | 0 | 0 | 0 |  | 437 | 184.25 | -252.75 | -57.84% | 2019-05-10
Markham | 2019 | 453447 | 453447 (WO 318672) Replace 38TV109 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 25991 | 23932.07 | -2058.93 | -7.922% | 5604 | 5515.96 | -88.04 | -1.571% | 19463 | 17164.11 | -2298.89 | -11.81% | 924 | 1252 | 328 | 35.5% | 0 | 0 | 0 |  | 65 | 75.5 | 10.5 | 16.15% | 2019-10-17 01:00
Markham | 2022 | 453449 | 453449 - ROGERS JOINT USE 18-153 | 99 | COMPLETE | Cont Est Over | Material Over Estimated | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 26208.84 | 22130.56 | -4078.28 | -15.56% | 3767.23 | 5283.45 | 1516.22 | 40.25% | 4397.93 | 2966.2 | -1431.73 | -32.55% | 1143.68 | 1215.5 | 71.82 | 6.28% | 16900 | 12665.41 | -4234.59 | -25.06% | 40.95 | 35.5 | -5.45 | -13.31% | 2022-04-06
Markham | 2019 | 453452 | (Wo 318679) Pole Relocation- BAYVIEW AVENUE, BLOOMINGTON TO VANDORF | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Shortt, Derek B. | 246449 | 122882.35 | -123566.65 | -50.14% | 123279 | 6482.39 | -116796.61 | -94.74% | 35473 | 25579.75 | -9893.25 | -27.89% | 48477 | 972 | -47505 | -97.99% | 39220 | 1570 | -37650 | -96% | 1525 | 888.5 | -636.5 | -41.74% | 2019-05-10
Markham | 2019 | 453455 | 453455 (WO 318683) Pole Relocation - MAJOR MACKENZIE DRIVE | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Steve | 233407.67 | 195616.06 | -37791.61 | -16.19% | 8746.52 | 10588.61 | 1842.09 | 21.06% | 18954.03 | 31251.42 | 12297.39 | 64.88% | 556.8 | 0 | -556.8 | -100% | 205150.32 | 82956.86 | -122193.46 | -59.56% | 39 | 2 | -37 | -94.87% | 2019-11-28 01:00
Markham | 2019 | 453456 | (WO 318684) Replace 44TV030 & 44TV028 | 99 | COMPLETE | Labour est. under |  |  | Tenorlas, Reynaldo | No | Handy, James | Steve Rumble | 44641 | 7714.02 | -36926.98 | -82.72% | 8240 | -11272.87 | -19512.87 | -236.8% | 34553 | 0 | -34553 | -100% | 1848 | 0 | -1848 | -100% | 0 | 12123 | 12123 |  | 110 | 95 | -15 | -13.64% | 2019-07-02 01:00
Markham | 2019 | 453458 | (WO 318686) ASHCROFT CT AND ANDREA LN | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 108986 | 78216.56 | -30769.44 | -28.23% | 5939 | 642.51 | -5296.49 | -89.18% | 0 | 28 | 28 |  | 1187 | 0 | -1187 | -100% | 101860 | 8031.4 | -93828.6 | -92.12% | 76 | 17.5 | -58.5 | -76.97% | 2019-05-24
Markham | 2019 | 453459 | (WO 318687) Cable repl. Emerging. M31. COTTSMORE CR AND HIGHGATE DR | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 168192 | 143601.65 | -24590.35 | -14.62% | 7553 | 3276.96 | -4276.04 | -56.61% | 103 | 272 | 169 | 164.1% | 1398 | 0 | -1398 | -100% | 159138 | 40961.94 | -118176.06 | -74.26% | 101 | 42.5 | -58.5 | -57.92% | 2019-04-24 01:00
Markham | 2020 | 453460 | 453460 (WO 318688) Hydro Relocation,MTO INITIATED | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Morrow, Joe | 51913 | 52378.46 | 465.46 | 0.8966% | 22508 | 12897.91 | -9610.09 | -42.7% | 12935 | 15837.02 | 2902.02 | 22.44% | 6187 | 3312.5 | -2874.5 | -46.46% | 10283 | 20331.03 | 10048.03 | 97.71% | 287.57 | 196.5 | -91.07 | -31.67% | 2020-06-10 01:00
Markham | 2021 | 453461 | 453461 - SRF VAUGHAN SUBDIVSION | 99 | COMPLETE | Cont Est Over | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 96491.39 | 98359.26 | 1867.87 | 1.936% | 19098.71 | 18483.36 | -615.35 | -3.222% | 1815.93 | 2061.29 | 245.36 | 13.51% | 889.35 | 1923.41 | 1034.06 | 116.3% | 74687.4 | 69155 | -5532.4 | -7.407% | 88.44 | 111 | 22.56 | 25.51% | 2021-03-22 01:00
Markham | 2019 | 453462 | 453462 (WO318692) Repl. Switchgear - Batch 3. R15 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Steve Rumble | 56563.67 | 50824.43 | -5739.24 | -10.15% | 16758 | 5013 | -11745 | -70.09% | 35786.67 | 8165.81 | -27620.86 | -77.18% | 4019 | 0 | -4019 | -100% | 0 | 37645.62 | 37645.62 |  | 224 | 19.5 | -204.5 | -91.29% | 2019-07-03 01:00
Markham | 2019 | 453463 | 453463 (WO 318693) Repl. Switchgear - Batch 5 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Steve Rumble | 74713 | 71598.7 | -3114.3 | -4.168% | 6222 | 899.74 | -5322.26 | -85.54% | 61744 | 54787.61 | -6956.39 | -11.27% | 1340 | 7958.19 | 6618.19 | 493.9% | 5407 | 0 | -5407 | -100% | 58 | 114 | 56 | 96.55% | 2019-11-06 01:00
Markham | 2019 | 453464 | 453464 (WO 318694) Repl. Switchgear - Batch 7 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 207741 | 146728.79 | -61012.21 | -29.37% | 19461 | 26402.12 | 6941.12 | 35.67% | 168040 | 106621.17 | -61418.83 | -36.55% | 4019 | 13705.5 | 9686.5 | 241% | 16221 | 0 | -16221 | -100% | 224 | 286.5 | 62.5 | 27.9% | 2019-10-05 01:00
Markham | 2019 | 453465 | (WO318695) SWGR Repl 2019 - Batch 2 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 135441 | 79737.03 | -55703.97 | -41.13% | 28429 | 5628.95 | -22800.05 | -80.2% | 74498 | 64476.51 | -10021.49 | -13.45% | 7531 | 9631.57 | 2100.57 | 27.89% | 24983 | 0 | -24983 | -100% | 356 | 54.5 | -301.5 | -84.69% | 2019-05-01 01:00
Markham | 2019 | 453466 | (WO318696) SWGR Repl 2019 - Batch 4 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Shane Christopher | 157826.69 | 51331.28 | -106495.41 | -67.48% | -41950.31 | 5948.61 | 47898.92 | -114.2% | 175261 | 0 | -175261 | -100% | 7860 | 0 | -7860 | -100% | 16656 | 40681.35 | 24025.35 | 144.2% | 229 | 68.5 | -160.5 | -70.09% | 2019-05-09
Markham | 2019 | 453467 | (WO318697) SWGR Repl 2019 - Batch 6 | 99 | COMPLETE | Engineering by-passed |  |  | Tenorlas, Reynaldo | No | Roy, James | Lamb, Tim | 87410.05 | 11474.37 | -75935.68 | -86.87% | 28950 | 1737.41 | -27212.59 | -94% | 51126.05 | 0 | -51126.05 | -100% | 7334 | 0 | -7334 | -100% | 0 | 9015.7 | 9015.7 |  | 0 | 14.5 | 14.5 |  | 2019-07-26 01:00
Markham | 2019 | 453468 | (WO318698) SWGR Repl 2019 - Batch 8 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Steve Rumble | 299003 | 188733.46 | -110269.54 | -36.88% | 31958 | 12461.01 | -19496.99 | -61.01% | 242419 | 173984.95 | -68434.05 | -28.23% | 7970 | 2287.5 | -5682.5 | -71.3% | 16656 | 0 | -16656 | -100% | 345 | 187 | -158 | -45.8% | 2019-10-10 01:00
Markham | 2019 | 453469 | (WO318699) SW - REPL BATCH 2019 - 9 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Steve Rumble | 136361.88 | 67347.55 | -69014.33 | -50.61% | 20367 | 8288.48 | -12078.52 | -59.3% | 111091.88 | 52561.07 | -58530.81 | -52.69% | 4903 | 6498 | 1595 | 32.53% | 0 | 0 | 0 |  | 272 | 175.5 | -96.5 | -35.48% | 2019-07-06 01:00
Markham | 2019 | 453470 | (WO318700) SW - REPL BATCH 2019 - 10 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Lamb, Tim | 89063.05 | 67911.13 | -21151.92 | -23.75% | 18563 | 4249.06 | -14313.94 | -77.11% | 57829.05 | 62772.07 | 4943.02 | 8.548% | 4343 | 890 | -3453 | -79.51% | 8328 | 0 | -8328 | -100% | 107 | 104.5 | -2.5 | -2.336% | 2019-10-11 01:00
Markham | 2019 | 453471 | (WO 318701) Replace 44TV070 & 44TV047 | 99 | COMPLETE | Labour est. over |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 44641 | 23802 | -20839 | -46.68% | 8240 | 4977 | -3263 | -39.6% | 34553 | 16545 | -18008 | -52.12% | 1848 | 2280 | 432 | 23.38% | 0 | 0 | 0 |  | 110 | 91 | -19 | -17.27% | 2019-07-25 01:00
Markham | 2019 | 453478 | (WO318712) AMBER ST. - #120 | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 111700.34 | 54133.69 | -57566.65 | -51.54% | 19754.7 | 13589.14 | -6165.56 | -31.21% | 43347.17 | 35550.64 | -7796.53 | -17.99% | 5035.8 | 4993.91 | -41.89 | -0.8318% | 39555.48 | 0 | -39555.48 | -100% | 279 | 180.75 | -98.25 | -35.22% | 2019-05-30
Markham | 2021 | 453485 | 453485 (WO 318719) 2019 Cable Injection - (M27) - Kennedy, 16th, McCowan-Hwy 7 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Horlings, Jake | 1102924 | 896395.3 | -206528.7 | -18.73% | 178272 | 72484.36 | -105787.64 | -59.34% | 21787 | 16597.05 | -5189.95 | -23.82% | 75223 | 0 | -75223 | -100% | 827642 | 807313.89 | -20328.11 | -2.456% | 950 | 0 | -950 | -100% | 2021-11-19 10:58
Markham | 2020 | 453486 | 453486 (WO 318720) 2019 Cable Injection - (M37) - Woodbine & 14th | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 838173 | 726143.02 | -112029.98 | -13.37% | 137606 | 58991.35 | -78614.65 | -57.13% | 17310 | 16292.7 | -1017.3 | -5.877% | 57671 | 0 | -57671 | -100% | 625586 | 650858.97 | 25272.97 | 4.04% | 0 | 0 | 0 |  | 2020-12-31 01:00
Markham | 2021 | 453487 | 453487 (WO 318721) 2019 Cable Injection - (M44) - Konrad Cres | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Horlings, Jake | 844830 | 534595.81 | -310234.19 | -36.72% | 149233 | 46367.31 | -102865.69 | -68.93% | 17146 | 464.13 | -16681.87 | -97.29% | 45161 | 0 | -45161 | -100% | 633290 | 487764.37 | -145525.63 | -22.98% | 50 | 38 | -12 | -24% | 2021-11-19 10:55
Markham | 2020 | 453488 | 453488 (WO 318722) 2019 Cable Injection - (V01) - Yonge, Steeles, Bathurst, Centre | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 828153 | 0 | -828153 | -100% | 135669 | 0 | -135669 | -100% | 17310 | 0 | -17310 | -100% | 56835 | 0 | -56835 | -100% | 618339 | 0 | -618339 | -100% | 0 | 0 | 0 |  | 2020-08-14 01:00
Markham | 2020 | 453489 | 453489 (WO 318723) 2019 Cable Injection - (V36) - Steeles & Pinevalley | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 579193 | 84950.81 | -494242.19 | -85.33% | 96794 | 7006.64 | -89787.36 | -92.76% | 20460 | 0 | -20460 | -100% | 28875 | 0 | -28875 | -100% | 433064 | 77944.17 | -355119.83 | -82% | 50 | 17 | -33 | -66% | 2020-08-14 01:00
Markham | 2020 | 453490 | 453490 (WO 318724) 2019 Cable Injection - (V37) - Langstaff & Weston | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 1474888 | 1108537.68 | -366350.32 | -24.84% | 242233 | 158094.05 | -84138.95 | -34.73% | 29674 | 38950.63 | 9276.63 | 31.26% | 101969 | 0 | -101969 | -100% | 1101012 | 911493 | -189519 | -17.21% | 50 | 710.25 | 660.25 | 1320% | 2020-08-14 01:00
Markham | 2020 | 453491 | 453491 (WO 318725) 2019 Cable Injection - (V18) - Major Mackenzie & Keele | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 1093542 | 861217.38 | -232324.62 | -21.25% | 190887 | 79928.88 | -110958.12 | -58.13% | 24495 | 15860.66 | -8634.34 | -35.25% | 58097 | 0 | -58097 | -100% | 820063 | 765427.84 | -54635.16 | -6.662% | 610 | 487.5 | -122.5 | -20.08% | 2020-08-14 01:00
Markham | 2022 | 453493 | (WO 318731) 18-118 York Region JU App | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-15 01:00
Markham | 2019 | 453494 | (WO 318733) 2019 Pole Replacement Batch 04 | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Shortt, Derek B. | 156263 | 169319.54 | 13056.54 | 8.355% | 70536 | 64746.93 | -5789.07 | -8.207% | 45870 | 52195.04 | 6325.04 | 13.79% | 20957 | 29282.1 | 8325.1 | 39.72% | 18900 | 23095.47 | 4195.47 | 22.2% | 947.25 | 1655 | 707.75 | 74.72% | 2019-08-15 01:00
Markham | 2019 | 453495 | (WO 318734) 2019 Pole Replacement Batch 05 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 139489 | 104450.13 | -35038.87 | -25.12% | 70650 | 417.05 | -70232.95 | -99.41% | 23381 | 29889.61 | 6508.61 | 27.84% | 20163 | 2123.51 | -18039.49 | -89.47% | 25295 | 0 | -25295 | -100% | 947.87 | 735 | -212.87 | -22.46% | 2019-06-28 01:00
Markham | 2019 | 453498 | 453498 (WO 318737) Left-Behind Cable Replacement. V37 LANGSTAFF RD AND WESTON AV | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 491085 | 429791.45 | -61293.55 | -12.48% | 17403 | 58348.96 | 40945.96 | 235.3% | 4232 | 1228.67 | -3003.33 | -70.97% | 6135 | 1831 | -4304 | -70.15% | 463315 | 368382.82 | -94932.18 | -20.49% | 224 | 383.5 | 159.5 | 71.21% | 2019-11-28 01:00
Markham | 2019 | 453499 | (WO318738) Left-Behind Cable Replacement. M37 Riviera Dr and Rodick Rd | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 164458 | 130514 | -33944 | -20.64% | 7682 | 10690 | 3008 | 39.16% | 1226 | 1708 | 482 | 39.31% | 1939 | 0 | -1939 | -100% | 153611 | 118116 | -35495 | -23.11% | 74 | 43.5 | -30.5 | -41.22% | 2019-08-02 01:00
Markham | 2019 | 453501 | 453501 (WO 318740) Left-Behind Cable Replacement. M33 WARDEN AV AND HWY 7 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 133958.62 | 117467.15 | -16491.47 | -12.31% | 7866.98 | 11661.32 | 3794.34 | 48.23% | 410.26 | 0 | -410.26 | -100% | 541.78 | 90 | -451.78 | -83.39% | 125139.6 | 105715.83 | -19423.77 | -15.52% | 41 | 44 | 3 | 7.317% | 2019-11-20 01:00
Markham | 2019 | 453502 | 453502 (WO 318742) Left-Behind Cable Replacement, M27 16th and Kennedy | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 396828.39 | 341242 | -55586.39 | -14.01% | 18778.73 | 37257 | 18478.27 | 98.4% | 1844.39 | 851 | -993.39 | -53.86% | 1724.99 | 1354 | -370.99 | -21.51% | 374480.28 | 301780 | -72700.28 | -19.41% | 148 | 191 | 43 | 29.05% | 2019-12-12 01:00
Markham | 2019 | 453503 | (WO 318743) Pole Replacement 2019 Batch 6 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 124999 | 203957.69 | 78958.69 | 63.17% | 59276 | 14392.68 | -44883.32 | -75.72% | 33994 | 0 | -33994 | -100% | 15979 | 0 | -15979 | -100% | 15750 | 117977.6 | 102227.6 | 649.1% | 571.75 | 1040 | 468.25 | 81.9% | 2019-07-11 01:00
Markham | 2019 | 453504 | (WO 318744) Pole Replacement 2019 Batch 7 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 143287 | 95664.24 | -47622.76 | -33.24% | 63089 | 6339.57 | -56749.43 | -89.95% | 51392 | 0 | -51392 | -100% | 17256 | 2040 | -15216 | -88.18% | 11550 | -28134.73 | -39684.73 | -343.6% | 722 | 1089 | 367 | 50.83% | 2019-07-12 01:00
Markham | 2019 | 453508 | (WO318748) KING-VAUGHAN RD. - 3230 | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 73480.77 | 53928.92 | -19551.85 | -26.61% | 21841.12 | 17292.77 | -4548.35 | -20.82% | 39945.38 | 31795.28 | -8150.1 | -20.4% | 5498.96 | 4380.87 | -1118.09 | -20.33% | 3766 | 460 | -3306 | -87.79% | 299 | 169.5 | -129.5 | -43.31% | 2019-04-25 01:00
Markham | 2019 | 453509 | (WO318751) UG Cable Replacement. M44 400-430 COCHRANE DR | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 293147.15 | 292542.9 | -604.25 | -0.2061% | 63341.15 | 4942.72 | -58398.43 | -92.2% | 55717 | 48856.27 | -6860.73 | -12.31% | 5316 | 7328.45 | 2012.45 | 37.86% | 168773 | 10065.63 | -158707.37 | -94.04% | 159 | 142 | -17 | -10.69% | 2019-03-18 01:00
Markham | 2021 | 453511 | 453511 - 18-155 BELL JU APPLICATION | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 23885.46 | 18571.19 | -5314.27 | -22.25% | 7846.21 | 8116.27 | 270.06 | 3.442% | 4092.47 | 3901.61 | -190.86 | -4.664% | 2946.78 | 2330 | -616.78 | -20.93% | 9000 | 4223.31 | -4776.69 | -53.07% | 107.55 | 91.5 | -16.05 | -14.92% | 2021-03-09 01:00
Markham | 2021 | 453512 | 453512 - BOX GROVE RESIDENTIAL E | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 886639.07 | 787866.94 | -98772.13 | -11.14% | 30251.72 | 85779.72 | 55528 | 183.6% | 7064.95 | 4889.19 | -2175.76 | -30.8% | 2433.92 | 3918.24 | 1484.32 | 60.98% | 846888.48 | 682789 | -164099.48 | -19.38% | 214.72 | 235.17 | 20.45 | 9.524% | 2021-01-22 01:00
Markham | 2022 | 453516 | (WO 318762) 18-156 Rogers JU Application | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-26 01:00
Markham | 2019 | 453517 | 453517 (WO 318763) 560 & 510 COPPER CREEK DR | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Dibratto, Susan | Steve Rumble | 113927.3262 | 107973.28 | -5954.0462 | -5.226% | 15973.7851 | 16995.16 | 1021.3749 | 6.394% | 37645.8163 | 27558 | -10087.8163 | -26.8% | 5507.9879 | 2447.5 | -3060.4879 | -55.56% | 54025.1366 | 57971.57 | 3946.4334 | 7.305% | 215 | 212.25 | -2.75 | -1.279% | 2019-10-26 01:00
Markham | 2020 | 453521 | 453521 (WO 318769) 30 ERIC T SMITH WAY, AURORA | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Alectra Utilities | Steve Rumble | 39662.3 | 28579.41 | -11082.89 | -27.94% | 10671.62 | 9542.73 | -1128.89 | -10.58% | 20792.51 | 14514.69 | -6277.82 | -30.19% | 2885.21 | 788.5 | -2096.71 | -72.67% | 5312.96 | 0 | -5312.96 | -100% | 136 | 205.5 | 69.5 | 51.1% | 2020-01-18 01:00
Markham | 2019 | 453524 | (WO318773) Replace SWG 15-L20. 113 VICEROY RD | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Lamb, Tim | 86057 | 23115.97 | -62941.03 | -73.14% | 17994 | 2020.68 | -15973.32 | -88.77% | 52518 | 0 | -52518 | -100% | 12227 | 0 | -12227 | -100% | 3318 | 19317.92 | 15999.92 | 482.2% | 139 | 33.5 | -105.5 | -75.9% | 2019-06-09
Markham | 2019 | 453531 | (WO 318781) YRRTC - H2-West - Phase 4.3 | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Zhang, Jiacheng | Lyle, Sedore | 251315 | 208115.81 | -43199.19 | -17.19% | 15815 | 30712.91 | 14897.91 | 94.2% | 81417 | 3922.05 | -77494.95 | -95.18% | 4201 | 135.16 | -4065.84 | -96.78% | 149882 | 173345.69 | 23463.69 | 15.65% | 212 | 223.5 | 11.5 | 5.425% | 2019-03-08 01:00
Markham | 2020 | 453544 | 453544 (WO 318798) Left-Behind Cable Replacement. V01 7200 YONGE ST | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 280060.19 | 292622.23 | 12562.04 | 4.485% | 27773.19 | 29119.54 | 1346.35 | 4.848% | 3439 | 17542.11 | 14103.11 | 410.1% | 4681 | 2327.36 | -2353.64 | -50.28% | 244167 | 226506.32 | -17660.68 | -7.233% | 140 | 144.5 | 4.5 | 3.214% | 2020-10-21 01:00
Markham | 2020 | 453545 | 453545 (WO 318799) Left-Behind Cable Replacement. V02 DORIAN PL AND FEE AV | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 231161.55 | 191990.2 | -39171.35 | -16.95% | 35506.75 | 25492.07 | -10014.68 | -28.21% | 17792.73 | 18052.03 | 259.3 | 1.457% | 7215.59 | 6648.38 | -567.21 | -7.861% | 170646.48 | 141797.72 | -28848.76 | -16.91% | 553.79 | 173 | -380.79 | -68.76% | 2020-10-21 01:00
Markham | 2019 | 453546 | (WO318800) Left-Behind Cable Segments. V15 GLEN SHIELDS AV | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 350825 | 249482 | -101343 | -28.89% | 7759 | 21011 | 13252 | 170.8% | 1900 | 0 | -1900 | -100% | 1973 | 0 | -1973 | -100% | 339193 | 228471 | -110722 | -32.64% | 99 | 56 | -43 | -43.43% | 2019-10-22 01:00
Markham | 2019 | 453548 | (WO318810) PUCCINI DR & AIDA PL. I&C 47, 47A, 49 RICHMOND HILL. | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Estrada, Michael | Steve Rumble | 82986.01 | 85048.16 | 2062.15 | 2.485% | 9197.31 | 10052.82 | 855.51 | 9.302% | 2595.07 | 1436.86 | -1158.21 | -44.63% | 1796.49 | 620 | -1176.49 | -65.49% | 69397.14 | 63819 | -5578.14 | -8.038% | 0 | 70.5 | 70.5 |  | 2019-11-05 01:00
Markham | 2021 | 453549 | 453549 - UPSIDE TOWNS, GEORGE KIRBY | 99 | COMPLETE | Cont Est Over | N/A | N/A | D'Onofrio, Tony | No | D'Onofrio, Tony | Dave Lindsay | 282796.93 | 318665.36 | 35868.43 | 12.68% | 10616.87 | 15617.94 | 5001.07 | 47.1% | 1861.03 | 1606.45 | -254.58 | -13.68% | 945.03 | 1826 | 880.97 | 93.22% | 269374 | 67.65 | -269306.35 | -99.97% | 96.32 | 102.5 | 6.18 | 6.416% | 2021-03-22 01:00
Markham | 2019 | 453550 | (WO 318815) YRRTC - H2-West - Phase 5.3 | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Zhang, Jiacheng | Macdonald, Steve | 230922 | 304464.08 | 73542.08 | 31.85% | 4019 | 7489.18 | 3470.18 | 86.34% | 87095 | 55144.55 | -31950.45 | -36.68% | 702 | 6234.37 | 5532.37 | 788.1% | 139106 | 235595.98 | 96489.98 | 69.36% | 51 | 142.5 | 91.5 | 179.4% | 2019-05-03 01:00
Markham | 2019 | 453557 | 453557 (WO 318824) Replace Pole P33876 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Morrow, Joe | 58870 | 76248.91 | 17378.91 | 29.52% | 18150 | 22214.5 | 4064.5 | 22.39% | 19520 | 17627.02 | -1892.98 | -9.698% | 5163 | 4326 | -837 | -16.21% | 16037 | 32081.39 | 16044.39 | 100% | 243.5 | 325 | 81.5 | 33.47% | 2019-11-13 01:00
Markham | 2022 | 453561 | (WO 318828) JU HE2018-145 Bell | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-02 01:00
Markham | 2019 | 453565 | (WO 318853) JU HE2018-148 Bell | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Battistella, Alexander | Macdonald, Larry | 8651 | 5178.2 | -3472.8 | -40.14% | 4882 | 2868.27 | -2013.73 | -41.25% | 226 | 89.71 | -136.29 | -60.31% | 1204 | 13.46 | -1190.54 | -98.88% | 2339 | 2206.76 | -132.24 | -5.654% | 56 | 11.75 | -44.25 | -79.02% | 2019-05-09
Markham | 2022 | 453568 | (WO 318858) POLE RELOCATIONS | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Grahovac, John | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-21 01:00
Markham | 2021 | 453570 | 453570 (WO 318860) NEW WESTMINSTER DRIVE. CONDO | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 114284.53 | 84868.22 | -29416.31 | -25.74% | 21892.36 | 17361.29 | -4531.07 | -20.7% | 45609.26 | 38906.66 | -6702.6 | -14.7% | 2459.71 | 2059.28 | -400.43 | -16.28% | 44323.2 | 25623.29 | -18699.91 | -42.19% | 268.35 | 123 | -145.35 | -54.16% | 2021-07-21 01:00
Markham | 2020 | 453571 | 453571 (WO 318861) I & C king's landing Phase II | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 63636.98 | 64386.38 | 749.4 | 1.178% | 11089.28 | 5353.93 | -5735.35 | -51.72% | 265.31 | 0 | -265.31 | -100% | 631.39 | 0 | -631.39 | -100% | 51651 | 54241.92 | 2590.92 | 5.016% | 100 | 6 | -94 | -94% | 2020-11-04 01:00
Markham | 2019 | 453572 | (WO 318863) 2019 Pole Replacement Batch 08 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 126386 | 126565.22 | 179.22 | 0.1418% | 63223 | 62840.82 | -382.18 | -0.6045% | 31047 | 15533.46 | -15513.54 | -49.97% | 17521 | 33175 | 15654 | 89.34% | 14595 | 15015.94 | 420.94 | 2.884% | 773.49 | 1100.5 | 327.01 | 42.28% | 2019-08-08 01:00
Markham | 2019 | 453573 | 453573 (WO 318864) 2019 Pole Replacement Batch 09 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Morrow, Joe | 214297 | 218031.07 | 3734.07 | 1.742% | 73716 | 85728.26 | 12012.26 | 16.3% | 74642 | 68452.77 | -6189.23 | -8.292% | 30959 | 49592 | 18633 | 60.19% | 34980 | 14258.04 | -20721.96 | -59.24% | 952.7 | 1349.5 | 396.8 | 41.65% | 2019-10-29 01:00
Markham | 2019 | 453574 | 453574 (WO 318865) 2019 Pole Replacement Batch 10 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Morrow, Joe | 144733 | 128588.11 | -16144.89 | -11.15% | 51320 | 50880.57 | -439.43 | -0.8563% | 34655 | 43318.04 | 8663.04 | 25% | 21128 | 23218 | 2090 | 9.892% | 37630 | 11171.5 | -26458.5 | -70.31% | 662.87 | 788.75 | 125.88 | 18.99% | 2019-11-19 01:00
Markham | 2020 | 453575 | (WO318866) 2019 Distribution Automation. 370 NORTH RIVERMEDE RD, VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-30 01:00
Markham | 2020 | 453576 | (WO318867) 2019 Distribution Automation. 2 BRADWICK DR, VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-30 01:00
Markham | 2020 | 453577 | (WO318868) 2019 Distribution Automation. 70 TIGI CRT, VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-30 01:00
Markham | 2020 | 453578 | (WO318869) 2019 Distribution Automation. 51 WALTON DR, AURORA | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-30 01:00
Markham | 2020 | 453579 | (WO318870) 2019 Distribution Automation. 33 BIRKSHIRE DR, AURORA | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-30 01:00
Markham | 2019 | 453580 | 453580 (WO 318871) 2019 Distribution Automation. MAJOR MACK DR W/O VELLORE PARK AVE | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 81246 | 97764.14 | 16518.14 | 20.33% | 1728 | 8447.72 | 6719.72 | 388.9% | 52217 | 48820.08 | -3396.92 | -6.505% | 19791 | 0 | -19791 | -100% | 7510 | 40496.34 | 32986.34 | 439.2% | 254.62 | 105.25 | -149.37 | -58.66% | 2019-10-30 01:00
Markham | 2019 | 453581 | 453581 (WO 318872) 2019 Distribution Automation. MAJOR MACK DR W/O JANE ST | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 104365 | 115573.3 | 11208.3 | 10.74% | 26784 | 10762.89 | -16021.11 | -59.82% | 61753 | 45639.77 | -16113.23 | -26.09% | 10528 | 0 | -10528 | -100% | 5300 | 59170.64 | 53870.64 | 1016% | 344.9 | 80 | -264.9 | -76.8% | 2019-12-20 01:00
Markham | 2019 | 453582 | (WO318873) 2019 Distribution Automation. JANE ST N/O MAJOR MACK DR W | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 74864 | 60397.41 | -14466.59 | -19.32% | 14615 | 1583.88 | -13031.12 | -89.16% | 49143 | -1082.09 | -50225.09 | -102.2% | 5276 | 0 | -5276 | -100% | 5830 | 3569.72 | -2260.28 | -38.77% | 187.8 | 150 | -37.8 | -20.13% | 2019-07-12 01:00
Markham | 2019 | 453583 | (WO318875) 2019 Distribution Automation. 8707 JANE ST | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 73906 | 86266.48 | 12360.48 | 16.72% | 1622 | 6474.61 | 4852.61 | 299.2% | 50731 | 55761.96 | 5030.96 | 9.917% | 15776 | 0 | -15776 | -100% | 5777 | 24029.91 | 18252.91 | 316% | 202.79 | 78.5 | -124.29 | -61.29% | 2019-10-04 01:00
Markham | 2019 | 453584 | 453584 (WO 318876) 2019 Distribution Automation. LANGSTAFF RD E/O WESTON RD | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 68906 | 105293.42 | 36387.42 | 52.81% | 12954 | 11686.21 | -1267.79 | -9.787% | 48969 | 65444.49 | 16475.49 | 33.64% | 5075 | 0 | -5075 | -100% | 1908 | 28162.72 | 26254.72 | 1376% | 166.8 | 121.25 | -45.55 | -27.31% | 2019-11-30 01:00
Markham | 2019 | 453585 | 453585 (WO 318877) 2019 Distribution Automation. WESTON RD N/O LANGSTAFF | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 69022 | 113012.19 | 43990.19 | 63.73% | 12954 | 9389.61 | -3564.39 | -27.52% | 49085 | 54675.49 | 5590.49 | 11.39% | 5075 | 0 | -5075 | -100% | 1908 | 48947.09 | 47039.09 | 2465% | 166.8 | 84 | -82.8 | -49.64% | 2019-12-03 01:00
Markham | 2019 | 453586 | (WO318878) 2019 Distribution Automation. 9980 DUFFERIN ST, VAUGHAN | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 73648 | 53507.88 | -20140.12 | -27.35% | 14150 | -1074.46 | -15224.46 | -107.6% | 48593 | 43835.21 | -4757.79 | -9.791% | 5075 | 6277.13 | 1202.13 | 23.69% | 5830 | 4470 | -1360 | -23.33% | 181 | 69.5 | -111.5 | -61.6% | 2019-06-07
Markham | 2019 | 453587 | (WO318880) 2019 Distribution Automation. MAJOR MACK DR W W/O BATHURST ST | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 71713 | 46721.62 | -24991.38 | -34.85% | 14391 | 4680.93 | -9710.07 | -67.47% | 47373 | 21987.44 | -25385.56 | -53.59% | 5179 | 2663.25 | -2515.75 | -48.58% | 4770 | 440 | -4330 | -90.78% | 184.9 | 210 | 25.1 | 13.57% | 2019-05-15
Markham | 2019 | 453588 | 453588 (WO 318881) 2019 Distribution Automation. 6720 HUNTINGTON RD, VAUGHAN | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 74212 | 112756.81 | 38544.81 | 51.94% | 14403 | 9150.36 | -5252.64 | -36.47% | 52201 | 54128.88 | 1927.88 | 3.693% | 5700 | 0 | -5700 | -100% | 1908 | 49477.57 | 47569.57 | 2493% | 185.5 | 103 | -82.5 | -44.47% | 2019-10-30 01:00
Markham | 2020 | 453590 | 453590 (WO 318883) JU HE2018-147 Rogers | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 15944.57 | 12950.06 | -2994.51 | -18.78% | 3622.43 | 3218.64 | -403.79 | -11.15% | 4129.54 | 4458.88 | 329.34 | 7.975% | 942.6 | 0 | -942.6 | -100% | 7250 | 5272.54 | -1977.46 | -27.28% | 72.6 | 18.5 | -54.1 | -74.52% | 2020-09-24 01:00
Markham | 2022 | 453593 | 453593 - RER - MX - RELOC - 19TH AVE - STOUFFVILLE LINE (4) - RAILWAY CROSSINGS | 99 | COMPLETE | Converted Project | N/A | N/A | Khuu, Philander | No | Grahovac, John | Macdonald, Steve | 422900.75 | 426696.12 | 3795.37 | 0.8975% | 33335.55 | 20575.02 | -12760.53 | -38.28% | 188048.2 | 199072.02 | 11023.82 | 5.862% | 1408 | 1856 | 448 | 31.82% | 200109 | 202639.33 | 2530.33 | 1.264% | 128 | 72.5 | -55.5 | -43.36% | 2022-01-29 01:00
Markham | 2020 | 453596 | 453596 (WO 318889) MAJOR MACKENZIE DR E - MARKHAM RD TO NINTH LINE- METROLINX CROSSING #ST780 | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Shane Christopher | 1367668.26 | 1402414.12 | 34745.86 | 2.541% | 16515.32 | 116834.51 | 100319.19 | 607.4% | 64363.2 | 33365.14 | -30998.06 | -48.16% | 0 | 0 | 0 |  | 303724.06 | 1249565.97 | 945841.91 | 311.4% | 57 | 92 | 35 | 61.4% | 2020-11-10 01:00
Markham | 2021 | 453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | 99 | COMPLETE | Under 10% | N/A | N/A | Vande Kuyt, Greg | No | Grahovac, John | Shane Christopher | 3022820.74 | 3140671.69 | 117850.95 | 3.899% | 10141.05 | 210077.22 | 199936.17 | 1972% | 281480.93 | 291461.27 | 9980.34 | 3.546% | 0 | 144 | 144 |  | 2731198.76 | 2635274.72 | -95924.04 | -3.512% | 90 | 151 | 61 | 67.78% | 2021-03-15 01:00
Markham | 2021 | 453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | 99 | COMPLETE | Under 10% | N/A | N/A | Vande Kuyt, Greg | No | Grahovac, John | Shane Christopher | 2003219.96 | 1990123.54 | -13096.42 | -0.6538% | 7756.92 | 161252.81 | 153495.89 | 1979% | 71135.16 | 98333.94 | 27198.78 | 38.24% | 0 | 196 | 196 |  | 1924327.88 | 1726839.29 | -197488.59 | -10.26% | 57 | 156.2 | 99.2 | 174% | 2021-02-23 01:00
Markham | 2022 | 453601 | 453601 - RER - MX - RELOC - ELGIN MILLS RD E - STOUFFVILLE LINE (6) - RAILWAY CROSSINGS | 99 | COMPLETE | Converted Project | N/A | N/A | Khuu, Philander | No | Grahovac, John | Macdonald, Steve | 424215 | 308174.39 | -116040.61 | -27.35% | 18475.3 | 15730.26 | -2745.04 | -14.86% | 223753.7 | 93965.64 | -129788.06 | -58% | 0 | 0 | 0 |  | 181986 | 197399.3 | 15413.3 | 8.469% | 0 | 0 | 0 |  | 2022-01-29 01:00
Markham | 2019 | 453603 | 453603 (WO 318896) ROAD CROSSING RELOCATE. MAJOR MACK DRIVE & BARONS STREET | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Graham, Bruce W. | Steve Rumble | 50517 | 44193.04 | -6323.96 | -12.52% | 9995 | 4676.36 | -5318.64 | -53.21% | 1301 | 1272.9 | -28.1 | -2.16% | 3109 | 0 | -3109 | -100% | 36112 | 34065.97 | -2046.03 | -5.666% | 128 | 82 | -46 | -35.94% | 2019-11-01 01:00
Markham | 2020 | 453605 | (WO 318899) TESTON RD & KEELE ST | 99 | CANCELLED | N/A |  |  | Vande Kuyt, Greg | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-02 01:00
Markham | 2020 | 453608 | 453608 (WO 318902) LANGSTAFF RD & KEELE ST RAILWAY- Metrolinx Electrical | 99 | COMPLETE | Converted Project | N/A | N/A | Vande Kuyt, Greg | No | Alectra Utilities | Shane Christopher | 1893137.89 | 2020043.89 | 126906 | 6.703% | 7756.92 | 155973.43 | 148216.51 | 1911% | 161017.65 | 162030.66 | 1013.01 | 0.6291% | 0 | 161.1 | 161.1 |  | 1724363.32 | 1695995.11 | -28368.21 | -1.645% | 57 | 91.5 | 34.5 | 60.53% | 2020-10-02 01:00
Markham | 2021 | 453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | 99 | COMPLETE | Under 10% | N/A | N/A | Khuu, Philander | No | Grahovac, John | Shane Christopher | 1486374.12 | 1483101.92 | -3272.2 | -0.2201% | 6861.91 | 108325.27 | 101463.36 | 1479% | 31124.61 | 40941.28 | 9816.67 | 31.54% | 0 | 1422.28 | 1422.28 |  | 1448387.6 | 1329031.58 | -119356.02 | -8.241% | 45 | 172.5 | 127.5 | 283.3% | 2021-03-30 01:00
Markham | 2019 | 453610 | (WO 318904) KEELE ST - KIRBY ST TO KING VAUGHAN RD- Metrolinx Electrical | 99 | CANCELLED | N/A |  |  | Vande Kuyt, Greg | No | Grahovac, John | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-05 01:00
Markham | 2019 | 453611 | 453611 (WO 318905) Pole Repl 2019 - Batch 11 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Shortt, Derek B. | 201796 | 92999.43 | -108796.57 | -53.91% | 99240 | 47618.09 | -51621.91 | -52.02% | 41066 | 24738.41 | -16327.59 | -39.76% | 38608 | 12522 | -26086 | -67.57% | 22882 | 8120.93 | -14761.07 | -64.51% | 1044.8 | 667 | -377.8 | -36.16% | 2019-11-05 01:00
Markham | 2019 | 453612 | 453612 (WO 318906) Pole Repl 2019 - Batch 12 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Shortt, Derek B. | 145896 | 171105.28 | 25209.28 | 17.28% | 67619 | 85171.26 | 17552.26 | 25.96% | 38692 | 44144.99 | 5452.99 | 14.09% | 27077 | 32146 | 5069 | 18.72% | 12508 | 9643.03 | -2864.97 | -22.91% | 809.9 | 1160 | 350.1 | 43.23% | 2019-12-04 01:00
Markham | 2019 | 453613 | (WO 318907) Pole Repl 2019 - Batch 13 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 72142 | 23627.57 | -48514.43 | -67.25% | 26665 | 111.22 | -26553.78 | -99.58% | 20717 | 20482.21 | -234.79 | -1.133% | 10476 | 2295.78 | -8180.22 | -78.09% | 14284 | 738.36 | -13545.64 | -94.83% | 343.4 | 425 | 81.6 | 23.76% | 2019-04-12 01:00
Markham | 2019 | 453614 | (WO 318908) REPLACE 15-L18 | 99 | COMPLETE | Labour est. under |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 82820 | 80853.45 | -1966.55 | -2.374% | 17994 | 1396.35 | -16597.65 | -92.24% | 52892 | 50520.17 | -2371.83 | -4.484% | 9458 | 7449.4 | -2008.6 | -21.24% | 2476 | 17454.32 | 14978.32 | 604.9% | 108 | 57.5 | -50.5 | -46.76% | 2019-06-16 01:00
Markham | 2019 | 453615 | (WO 318909) YRRTC-Y2.1-9839 YONGE ST - OH to UG Service Conversion. | 99 | COMPLETE | Converted Project |  |  | Lacombe, Joel | No | Lacombe, Joel | Steve Rumble | 45952 | 19418.45 | -26533.55 | -57.74% | 7901 | 0 | -7901 | -100% | 15582 | 0 | -15582 | -100% | 3410 | 0 | -3410 | -100% | 19059 | 0 | -19059 | -100% | 0 | 0 | 0 |  | 2019-03-01 01:00
Markham | 2020 | 453621 | 453621 - Riverwalk Meadows | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Shane Christopher | 114427.74 | 120991.19 | 6563.45 | 5.736% | 10413.58 | 19568.76 | 9155.18 | 87.92% | 521.48 | 0 | -521.48 | -100% | 361.32 | 835 | 473.68 | 131.1% | 103131.36 | 88642 | -14489.36 | -14.05% | 86.2 | 108 | 21.8 | 25.29% | 2020-07-14 01:00
Markham | 2019 | 453625 | (WO318923) 1443 DENISON AVENUE | 99 | COMPLETE | Converted Project |  |  | Stephens, Barry N. | No | Dibratto, Susan | Steve Rumble | 74130.68 | 47679.81 | -26450.87 | -35.68% | 11671.35 | 1431.89 | -10239.46 | -87.73% | 36279.74 | 28614.32 | -7665.42 | -21.13% | 4128.9 | 0 | -4128.9 | -100% | 18040.65 | 2102.17 | -15938.48 | -88.35% | 172.5 | 133.75 | -38.75 | -22.46% | 2019-10-11 01:00
Markham | 2022 | 453630 | 453630 - RER - MX - RELOC - KENNEDY RD - STOUFFVILLE LINE (16) - RAILWAY CROSSINGS | 99 | COMPLETE | Cont Est Under | N/A | N/A | Khuu, Philander | No | Grahovac, John | Shane Christopher | 153810.09 | 182296.74 | 28486.65 | 18.52% | 7756.92 | 14683.73 | 6926.81 | 89.3% | 8429.85 | 5053.36 | -3376.49 | -40.05% | 0 | 304 | 304 |  | 137623.32 | 152638.75 | 15015.43 | 10.91% | 57 | 87.65 | 30.65 | 53.77% | 2022-03-23 01:00
Markham | 2019 | 453631 | 453631 (WO 318931) HIGHWAY NO. 50 - #7171 AT GIBRALTAR RD. | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 82372.4 | 71827.92 | -10544.48 | -12.8% | 14919.87 | 11954.31 | -2965.56 | -19.88% | 45508.22 | 40984.25 | -4523.97 | -9.941% | 3534.3 | 2455 | -1079.3 | -30.54% | 14245.84 | 11912.38 | -2333.46 | -16.38% | 214 | 188.75 | -25.25 | -11.8% | 2019-12-04 01:00
Markham | 2021 | 453634 | 453634 - CORNELL ROUGE PH9 | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 121109.4 | 110400.86 | -10708.54 | -8.842% | 11177.31 | 16449.78 | 5272.47 | 47.17% | 1619.82 | 1200.62 | -419.2 | -25.88% | 795.03 | 1605 | 809.97 | 101.9% | 107517.24 | 80762 | -26755.24 | -24.88% | 68.32 | 92 | 23.68 | 34.66% | 2021-04-27
Markham | 2020 | 453636 | 453636 (WO 318938) METROLINX CROSSIING #ST773 EUREKA STREET - HWY 7 TO PAVILLION STREET, MARKHAM | 99 | COMPLETE | Converted Project |  |  | Vande Kuyt, Greg | No | Alectra Utilities | Shane Christopher | 297476.26 | 311333.21 | 13856.95 | 4.658% | 7756.92 | 25508.65 | 17751.73 | 228.9% | 24138.7 | 22906.54 | -1232.16 | -5.105% | 0 | 0 | 0 |  | 265580.64 | 259089.57 | -6491.07 | -2.444% | 57 | 42 | -15 | -26.32% | 2020-04-09 01:00
Markham | 2020 | 453637 | 453637 (WO 318939) JU HE2018-149 Rogers PINE VALLEY DR FROM LANGSTAFF RD. TO HWY 7 | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 29450.12 | 44442.04 | 14991.92 | 50.91% | 9220.24 | 4107.56 | -5112.68 | -55.45% | 6612.92 | 7293.95 | 681.03 | 10.3% | 1562 | 0 | -1562 | -100% | 12054.96 | 33040.53 | 20985.57 | 174.1% | 117.73 | 16 | -101.73 | -86.41% | 2020-02-26 01:00
Markham | 2020 | 453640 | 453640 (WO 318944) 57 & 59 Bridlefield Lane | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 89046.39 | 65747.38 | -23299.01 | -26.17% | 8747.24 | 11165.15 | 2417.91 | 27.64% | 649.76 | 1533.13 | 883.37 | 136% | 624.71 | 778.5 | 153.79 | 24.62% | 79024.68 | 51997 | -27027.68 | -34.2% | 103 | 71 | -32 | -31.07% | 2020-07-15 01:00
Markham | 2021 | 453645 | 453645 (WO 318951) 9272 BAYVIEW AVENUE | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 49557.23 | 43446.23 | -6111 | -12.33% | 11942.08 | 9323.2 | -2618.88 | -21.93% | 20430.75 | 16976 | -3454.75 | -16.91% | 1496.32 | 1833.78 | 337.46 | 22.55% | 15688.08 | 13627.23 | -2060.85 | -13.14% | 146.75 | 98.5 | -48.25 | -32.88% | 2021-04-27
Markham | 2019 | 453646 | 453646 (WO 318952) Orlon Cres - Reduce secondary service dips | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 184008.78 | 169106.77 | -14902.01 | -8.099% | 24777.99 | 20528.97 | -4249.02 | -17.15% | 9758.06 | 9657.26 | -100.8 | -1.033% | 2367.01 | 2014 | -353.01 | -14.91% | 147105.72 | 136906.54 | -10199.18 | -6.933% | 170 | 153.5 | -16.5 | -9.706% | 2019-12-12 01:00
Markham | 2019 | 453647 | 453647 (WO 318953) Pole Replacement 2019 - Replace 3 poles at Yonge, Aurora | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Larry | 38642 | 32222.99 | -6419.01 | -16.61% | 19965 | 7803.16 | -12161.84 | -60.92% | 9988 | 5712.91 | -4275.09 | -42.8% | 4972 | 3022 | -1950 | -39.22% | 3717 | 15684.92 | 11967.92 | 322% | 205.25 | 118 | -87.25 | -42.51% | 2019-11-25 01:00
Markham | 2019 | 453648 | (WO 318954) Replace P28996 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Steve | 26107 | 25582.68 | -524.32 | -2.008% | 13282 | 2778.12 | -10503.88 | -79.08% | 5103 | 1350.41 | -3752.59 | -73.54% | 4012 | 0 | -4012 | -100% | 3710 | 21454.15 | 17744.15 | 478.3% | 170 | 0 | -170 | -100% | 2019-08-21 01:00
Markham | 2019 | 453656 | (WO318965) 45 Rodinea Rd | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Paterson, Greg | Steve Rumble | 16203.0222 | 8709.95 | -7493.0722 | -46.24% | 7837.0782 | 219.15 | -7617.9282 | -97.2% | 0 | 0 | 0 |  | 2005.944 | 0 | -2005.944 | -100% | 6360 | 0 | -6360 | -100% | 100 | 91.5 | -8.5 | -8.5% | 2019-04-28 01:00
Markham | 2020 | 453657 | (WO318966) 81 McPherson St | 99 | CANCELLED | N/A |  |  | Stephens, Barry N. | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-17 01:00
Markham | 2020 | 453660 | (Wo 318970) TRCA Pole Relocation | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-03 01:00
Markham | 2019 | 453670 | (WO 318980) Hwy 407 and Woodbine Ave Insulator Replacement | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Larry | 105105.72 | 113389.44 | 8283.72 | 7.881% | 29296.5 | 72339.57 | 43043.07 | 146.9% | 30664.22 | 36526.27 | 5862.05 | 19.12% | 11940 | 4523.6 | -7416.4 | -62.11% | 33205 | 0 | -33205 | -100% | 387.15 | 284.5 | -102.65 | -26.51% | 2019-05-03 01:00
Markham | 2019 | 453675 | (WO 318986) Batch 15 - Replace 16 Poles | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Steve | 113338 | 123144.76 | 9806.76 | 8.653% | 50096 | 10641.68 | -39454.32 | -78.76% | 31062 | 15511.01 | -15550.99 | -50.06% | 20202 | 0 | -20202 | -100% | 11978 | 96992.07 | 85014.07 | 709.8% | 584.27 | 42 | -542.27 | -92.81% | 2019-09-11 01:00
Markham | 2019 | 453676 | (WO318987) 5328 Hwy 7 E | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 47768.6933 | 41022.87 | -6745.8233 | -14.12% | 9688.0767 | 3768.77 | -5919.3067 | -61.1% | 30475 | 30983.37 | 508.37 | 1.668% | 3008.916 | 606 | -2402.916 | -79.86% | 0 | 2772.2 | 2772.2 |  | 130 | 89.24 | -40.76 | -31.35% | 2019-08-14 01:00
Markham | 2019 | 453682 | (WO 318994) JU HE2018-153 Bell | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Battistella, Alexander | Macdonald, Larry | 11133.64 | 11786.46 | 652.82 | 5.863% | 3409.31 | 1643.02 | -1766.29 | -51.81% | 2355.54 | 582.52 | -1773.02 | -75.27% | 400.79 | 0 | -400.79 | -100% | 4968 | 9560.92 | 4592.92 | 92.45% | 29.31 | 2 | -27.31 | -93.18% | 2019-10-10 01:00
Markham | 2019 | 453684 | 453684 (WO 318997) 2019 Steeles and NewWestminster Ph1 | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 511722 | 566853.03 | 55131.03 | 10.77% | 107895 | 124328.65 | 16433.65 | 15.23% | 57217 | 88893.6 | 31676.6 | 55.36% | 41406 | 28507 | -12899 | -31.15% | 305204 | 325123.78 | 19919.78 | 6.527% | 1388.5 | 1327 | -61.5 | -4.429% | 2019-11-28 01:00
Markham | 2019 | 453685 | (WO318998) 2019 Steeles and NewWestminster Ph2 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 248555 | 174376.4 | -74178.6 | -29.84% | 66648 | 9623.95 | -57024.05 | -85.56% | 20992 | 0 | -20992 | -100% | 23603 | 469.77 | -23133.23 | -98.01% | 137312 | 7441.94 | -129870.06 | -94.58% | 856 | 398.5 | -457.5 | -53.45% | 2019-10-22 01:00
Markham | 2019 | 453686 | (WO318999) 2019 Steeles and NewWestminster Ph3 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 224627 | 13607.16 | -211019.84 | -93.94% | 75091 | 6976.52 | -68114.48 | -90.71% | 28452 | 5742.67 | -22709.33 | -79.82% | 27247 | 1007 | -26240 | -96.3% | 93837 | -119.03 | -93956.03 | -100.1% | 965 | 805.5 | -159.5 | -16.53% | 2019-06-11 01:00
Markham | 2020 | 453687 | (WO319000) 60 VIA RENZO DR. - RICHMOND HILL | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-20 01:00
Markham | 2019 | 453689 | (WO 319002) Replace P31121 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Steve | 20230 | 33744.02 | 13514.02 | 66.8% | 7753 | 2432 | -5321 | -68.63% | 4787 | 5273.07 | 486.07 | 10.15% | 2658 | 0 | -2658 | -100% | 5032 | 26038.95 | 21006.95 | 417.5% | 99.5 | 0 | -99.5 | -100% | 2019-09-10 01:00
Markham | 2019 | 453697 | 453697 (WO 319011) Batch 17 - Replace 7 Poles | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Larry | 68890 | 98205.6 | 29315.6 | 42.55% | 28859 | 36850.95 | 7991.95 | 27.69% | 17098 | 43389.28 | 26291.28 | 153.8% | 9550 | 12117.5 | 2567.5 | 26.88% | 13383 | 5847.87 | -7535.13 | -56.3% | 335 | 487.5 | 152.5 | 45.52% | 2019-12-03 01:00
Markham | 2021 | 453698 | 453698 - I & C UNION VILLAGE PHASE 1 | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Dave Lindsay | 126888.01 | 881807.56 | 754919.55 | 594.9% | 63676.48 | 34533.67 | -29142.81 | -45.77% | 22788.48 | 15474.03 | -7314.45 | -32.1% | 7267.05 | 5873.5 | -1393.55 | -19.18% | 33156 | 27200 | -5956 | -17.96% | 362.92 | 271 | -91.92 | -25.33% | 2021-06-30 01:00
Markham | 2020 | 453699 | 453699 (WO 319014) 221 CAMLAREN CRESCENT | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Larry | 65138.54 | 63792.15 | -1346.39 | -2.067% | 16746.67 | 18130 | 1383.33 | 8.26% | 6621.61 | 2862.47 | -3759.14 | -56.77% | 3094.65 | 5264.81 | 2170.16 | 70.13% | 38675.61 | 33622.57 | -5053.04 | -13.07% | 113.31 | 196 | 82.69 | 72.98% | 2020-01-16 01:00
Markham | 2019 | 453700 | 453700 (WO 319015) NORTHERN PINES BLVD. - #1 | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 32701.88 | 27925.04 | -4776.84 | -14.61% | 7953.27 | 7036.76 | -916.51 | -11.52% | 10186 | 9671.8 | -514.2 | -5.048% | 2390.42 | 2025 | -365.42 | -15.29% | 10422.39 | 6186.24 | -4236.15 | -40.64% | 112 | 122.75 | 10.75 | 9.598% | 2019-11-07 01:00
Markham | 2021 | 453701 | 453701 - HIGHWAY NO. 7 - #6800 - HOTEL | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 51856.67 | 55268.38 | 3411.71 | 6.579% | 21396.72 | 15513.48 | -5883.24 | -27.5% | 38185.46 | 27988.43 | -10197.03 | -26.7% | 2657.06 | 3061.38 | 404.32 | 15.22% | 11967.43 | 6689.32 | -5278.11 | -44.1% | 135.3 | 131.5 | -3.8 | -2.809% | 2021-11-11 01:00
Markham | 2019 | 453702 | 453702 (WO 319017) HE2019-001 | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Martin, Shane | Don Rothman | 4562.4 | 1420.92 | -3141.48 | -68.86% | 1918.91 | 1010.37 | -908.54 | -47.35% | 245.77 | 332.55 | 86.78 | 35.31% | 33.6 | 78 | 44.4 | 132.1% | 2364.12 | 0 | -2364.12 | -100% | 2.82 | 8 | 5.18 | 183.7% | 2019-11-28 01:00
Markham | 2019 | 453703 | (WO 319018) Grandview & Younge Anchor Relocation HE2019-022 | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Battistella, Alexander | Macdonald, Larry | 7517 | 3033.93 | -4483.07 | -59.64% | 3311 | 1116.74 | -2194.26 | -66.27% | 611 | 515.19 | -95.81 | -15.68% | 404 | 272 | -132 | -32.67% | 3191 | 1130 | -2061 | -64.59% | 37.5 | 14 | -23.5 | -62.67% | 2019-08-24 01:00
Markham | 2019 | 453710 | 453710 - ROGERS - HE2019-003 | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 6406.98 | 3497.05 | -2909.93 | -45.42% | 2550.72 | 672.41 | -1878.31 | -73.64% | 637.62 | 562.1 | -75.52 | -11.84% | 191.4 | 0 | -191.4 | -100% | 3027.24 | 2262.54 | -764.7 | -25.26% | 7.34 | 2 | -5.34 | -72.75% | 2019-11-08 01:00
Markham | 2019 | 453711 | (WO319027) Soltan-Ahmadi Residence. BALDING BLVD. - #90 | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 26844.89 | 34437.33 | 7592.44 | 28.28% | 7953.27 | 7944.35 | -8.92 | -0.1122% | 6124.65 | 6493.73 | 369.08 | 6.026% | 2390.42 | 360 | -2030.42 | -84.94% | 8626.75 | 18065.86 | 9439.11 | 109.4% | 112 | 127.5 | 15.5 | 13.84% | 2019-10-08 01:00
Markham | 2019 | 453712 | 453712 (WO 319028) 200 Cachet Woods Crt | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 54093.5421 | 54315.38 | 221.8379 | 0.4101% | 9618.6589 | 11759.41 | 2140.7511 | 22.26% | 27427.5 | 24394.34 | -3033.16 | -11.06% | 3242.9428 | 1365 | -1877.9428 | -57.91% | 12720 | 13009.24 | 289.24 | 2.274% | 140 | 142 | 2 | 1.429% | 2019-12-05 01:00
Markham | 2022 | 453728 | 453728 (WO 319045) Ballantry Cornell Phase 8 | 99 | COMPLETE | N/A |  |  | Penner, Mitchell | No | Estrada, Michael | Dave Lindsay | 0 | 211454.96 | 211454.96 |  | 0 | 20462.16 | 20462.16 |  | 0 | 2048.59 | 2048.59 |  | 0 | 816 | 816 |  | 0 | 4900 | 4900 |  | 0 | 120 | 120 |  | 2021-12-30 01:00
Markham | 2022 | 453763 | 453763 (WO 319081) Bell - HE2018-157 | 99 | COMPLETE | Converted Project |  |  |  | No | Martin, Shane | Wong, Henry | 0 | 93.54 | 93.54 |  | 0 | 93.54 | 93.54 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-19 01:00
Markham | 2019 | 453792 | (WO 319111) OH, Tap Removals for Warden Ave Express Feeders, Hwy 7 east of Rodick Rd | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Shortt, Derek B. | 10068 | 16363.95 | 6295.95 | 62.53% | 7393 | 9110.56 | 1717.56 | 23.23% | 0 | 0 | 0 |  | 2675 | 5832 | 3157 | 118% | 0 | 1421.39 | 1421.39 |  | 80 | 126 | 46 | 57.5% | 2019-07-19 01:00
Markham | 2022 | 453796 | 453796 - VIA RENZO DR. #95 - BLDG. DC3 | 99 | ANALYZE |  |  |  | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 328950 | 438387.3 | 109437.3 | 33.27% | 51392.82 | 108438.55 | 57045.73 | 111% | 257262.74 | 301065.49 | 43802.75 | 17.03% | 6294.44 | 3403.5 | -2890.94 | -45.93% | 14000 | 21899.48 | 7899.48 | 56.42% | 330.74 | 931 | 600.26 | 181.5% | 2022-10-07 01:00
Markham | 2020 | 453801 | 453801 - 2020 POLE REPLACEMENT - CN CROSSING - 14TH AVE/ALDEN RD, MARKHAM | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 114170.53 | 149827.54 | 35657.01 | 31.23% | 14099.82 | 11134.77 | -2965.05 | -21.03% | 35131.25 | 40242.82 | 5111.57 | 14.55% | 8747.06 | 0 | -8747.06 | -100% | 56192.4 | 98449.95 | 42257.55 | 75.2% | 768.54 | 15 | -753.54 | -98.05% | 2020-12-24 01:00
Markham | 2021 | 453803 | 453803 (WO 319126) HWY 404 AND 16TH AVE. Pad Tx relocation | 99 | COMPLETE | Under 10% | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Dave Lindsay | 537800.4 | 566748.84 | 28948.44 | 5.383% | 34656.95 | 73671.26 | 39014.31 | 112.6% | 19284.23 | 22345.76 | 3061.53 | 15.88% | 3115.58 | 4991.25 | 1875.67 | 60.2% | 480743.64 | 461728.28 | -19015.36 | -3.955% | 344.06 | 190.5 | -153.56 | -44.63% | 2021-11-11 01:00
Markham | 2019 | 453804 | (WO319127) cable relocation. ROSE BRANCH DRIVE, RICHMOND HILL | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Lamb, Tim | 75393 | 70136.95 | -5256.05 | -6.972% | 12640 | 10569 | -2071 | -16.38% | 0 | 0 | 0 |  | 2140 | 2060 | -80 | -3.738% | 60613 | 57319.16 | -3293.84 | -5.434% | 162 | 92 | -70 | -43.21% | 2019-09-24 01:00
Markham | 2022 | 453815 | (WO319139) WELLINGTON ST E & HWY 404 | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-20 01:00
Markham | 2020 | 453833 | 453833 (WO 319169) 251 Rodinea Rd | 99 | COMPLETE | Converted Project | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Dave Lindsay | 47831.39 | 39915.28 | -7916.11 | -16.55% | 7449.78 | 3930.77 | -3519.01 | -47.24% | 31206.4 | 30356.88 | -849.52 | -2.722% | 2173.11 | 998.98 | -1174.13 | -54.03% | 3180 | 1676.16 | -1503.84 | -47.29% | 105 | 70 | -35 | -33.33% | 2020-10-20 01:00
Markham | 2020 | 453835 | (WO319174) STEELCASE RD WEST - 31 | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Persaud, Ryan | 0 | 1771.44 | 1771.44 |  | 0 | 61.06 | 61.06 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-15 01:00
Markham | 2019 | 453867 | (WO 319207) RA-Service pole relocation | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Barry, Kenneth | Macdonald, Larry | 11292 | 12301.43 | 1009.43 | 8.939% | 5978 | 234.72 | -5743.28 | -96.07% | 2372 | 908.53 | -1463.47 | -61.7% | 1204 | 0 | -1204 | -100% | 1738 | 2340 | 602 | 34.64% | 76 | 87 | 11 | 14.47% | 2019-06-15 01:00
Markham | 2019 | 453873 | (WO319214) Main Street Unionville - #206 | 99 | COMPLETE | Labour est. under |  |  | Cranley, Stephen | No | Yuen, Paul | Steve Rumble | 72951.0184 | 69597.77 | -3353.2484 | -4.597% | 15553.4356 | 22574.71 | 7021.2743 | 45.14% | 26399.0053 | 22016.49 | -4382.5153 | -16.6% | 5115.1572 | 8302.5 | 3187.3428 | 62.31% | 21644.0446 | 11781.66 | -9862.3846 | -45.57% | 214 | 339 | 125 | 58.41% | 2019-07-20 01:00
Markham | 2019 | 453874 | (WO 319215) YRRTC-Y2.1-PERMANENT POLES | 99 | COMPLETE | Engineering by-passed |  |  | Lacombe, Joel | No | Lacombe, Joel | Persaud, Ryan | 0 | 354634 | 354634 |  | 0 | 7077.65 | 7077.65 |  | 0 | 61527.03 | 61527.03 |  | 0 | 0 | 0 |  | 0 | 79423.16 | 79423.16 |  | 0 | 0 | 0 |  | 2019-03-30 01:00
Markham | 2019 | 453878 | 453878 (WO 319220) LESLIE ST WILLIAM LOGAN. guy pole conflict | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Macdonald, Steve | 9431.13 | 17394.61 | 7963.48 | 84.44% | 2273.41 | 6823.59 | 4550.18 | 200.1% | 1934.36 | 1212.84 | -721.52 | -37.3% | 220.8 | 2920 | 2699.2 | 1222% | 5002.56 | 6438.18 | 1435.62 | 28.7% | 10 | 70 | 60 | 600% | 2019-10-30 01:00
Markham | 2022 | 453882 | (WO 319224) HE2019-008 - York Region | 99 | CANCELLED | N/A |  |  |  | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-21 01:00
Markham | 2021 | 453883 | 453883 - NEW SUBDIVISION 4031 16TH AVENUE | 98 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Alarcon, Alejandro | Dave Lindsay | 97672.86 | 102354.3 | 4681.44 | 4.793% | 13046.8 | 18675.16 | 5628.36 | 43.14% | 938.22 | 1229.07 | 290.85 | 31% | 766.84 | 1818.28 | 1051.44 | 137.1% | 82921 | 79469.75 | -3451.25 | -4.162% | 71.44 | 99.25 | 27.81 | 38.93% | 2021-07-21 01:00
Markham | 2021 | 453886 | 453886 - SOUTH 14TH SUBDIVISION - SUBD RES EDS | 99 | COMPLETE | Cont Est Under | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 1018732.97 | 1213470.93 | 194737.96 | 19.12% | 57655.11 | 154560.66 | 96905.55 | 168.1% | 17799.57 | 17084.31 | -715.26 | -4.018% | 7959.29 | 11927.58 | 3968.29 | 49.86% | 935319 | 1022530 | 87211 | 9.324% | 568.88 | 593 | 24.12 | 4.24% | 2021-06-30 01:00
Markham | 2019 | 453887 | 453887 (WO 319231) 241 TRADE VALLEY DRIVE | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Diefenbaker, Trevor A | Steve Rumble | 80091.11 | 92618.2 | 12527.09 | 15.64% | 10505.9 | 16022.24 | 5516.34 | 52.51% | 33809.34 | 69520.34 | 35711 | 105.6% | 751.47 | 1686 | 934.53 | 124.4% | 35024.4 | 3647.04 | -31377.36 | -89.59% | 76.69 | 181.5 | 104.81 | 136.7% | 2019-11-26 01:00
Markham | 2020 | 453888 | 453888 - 190 KENNEDY STREET WEST/INSPECT & CONNECT | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 91956.43 | 85314.44 | -6641.99 | -7.223% | 12618.07 | 7924.25 | -4693.82 | -37.2% | 878.16 | 0 | -878.16 | -100% | 395.64 | 897 | 501.36 | 126.7% | 78064.56 | 419 | -77645.56 | -99.46% | 42.24 | 100 | 57.76 | 136.7% | 2020-04-23
Markham | 2020 | 453889 | 453889 (WO 319234) OH & UG RELOCATION. Phase 1.2 | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 3964469.46 | 3947526.94 | -16942.52 | -0.4274% | 85923.88 | 318594.54 | 232670.66 | 270.8% | 628981.3 | 644240.17 | 15258.87 | 2.426% | 3598 | 0 | -3598 | -100% | 3244391.28 | 2983707.9 | -260683.38 | -8.035% | 524.74 | 411 | -113.74 | -21.68% | 2020-06-30 01:00
Markham | 2019 | 453890 | 453890 (WO 319235) HIGHWAY NO. 7 EAST - #2830 | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Yuen, Paul | Steve Rumble | 34025.4342 | 40944.47 | 6919.0358 | 20.33% | 7953.2682 | 11269.78 | 3316.5118 | 41.7% | 12183.5637 | 9593.04 | -2590.5237 | -21.26% | 2390.4166 | 1897.5 | -492.9166 | -20.62% | 9748.3854 | 16251.91 | 6503.5246 | 66.71% | 112 | 144 | 32 | 28.57% | 2019-11-07 01:00
Markham | 2020 | 453906 | 453906 (WO 319263) HE2018-154 - Rogers DUFFERIN AND CENTRE STREET | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 5288.08 | 6061.73 | 773.65 | 14.63% | 1178.5 | 937.18 | -241.32 | -20.48% | 718.38 | 70.55 | -647.83 | -90.18% | 0 | 0 | 0 |  | 3391.2 | 5054 | 1662.8 | 49.03% | 4.32 | 2.5 | -1.82 | -42.13% | 2020-02-07 01:00
Markham | 2019 | 453912 | 453912 (WO 319269) 3733 Highway 7 | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Paterson, Greg | Steve Rumble | 60096.05 | 39260.23 | -20835.82 | -34.67% | 16356.11 | 5016.6 | -11339.51 | -69.33% | 31432.73 | 30284.09 | -1148.64 | -3.654% | 1702.69 | 1312.5 | -390.19 | -22.92% | 10604.52 | 0 | -10604.52 | -100% | 111 | 57.5 | -53.5 | -48.2% | 2019-12-21 01:00
Markham | 2020 | 453913 | 453913 (WO 319270) POLE RELOCATIONS JOHN STREET, BAYVIEW AVENUE TO RODDICK ROAD | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 94108.43 | 96104.45 | 1996.02 | 2.121% | 58772.78 | 12929.63 | -45843.15 | -78% | 17689.07 | 18612.29 | 923.22 | 5.219% | 9065.98 | 0 | -9065.98 | -100% | 8580.6 | 64562.53 | 55981.93 | 652.4% | 622.25 | 4 | -618.25 | -99.36% | 2020-06-04 01:00
Markham | 2021 | 453915 | 453915 (WO 319272) I&C Dogliola Development | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 209459.1 | 224270.63 | 14811.53 | 7.071% | 11032.19 | 23809.91 | 12777.72 | 115.8% | 1982.27 | 2340.7 | 358.43 | 18.08% | 1574.64 | 3076.13 | 1501.49 | 95.35% | 194870 | 7262 | -187608 | -96.27% | 144.24 | 161 | 16.76 | 11.62% | 2021-01-22 01:00
Markham | 2019 | 453916 | 453916 (WO 319274) 280 Hunters Valley | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Paterson, Greg | Steve Rumble | 82322.05 | 64048.97 | -18273.08 | -22.2% | 13361.31 | 5680.91 | -7680.4 | -57.48% | 33782.8 | 33116.82 | -665.98 | -1.971% | 1298.34 | 528 | -770.34 | -59.33% | 33879.6 | 21506.01 | -12373.59 | -36.52% | 93 | 70 | -23 | -24.73% | 2019-11-26 01:00
Markham | 2021 | 453917 | 453917 - ICI PADMOUNT TX INSTALLATION/2815 14TH AVE | 99 | COMPLETE | Cont Est Under | BOM not accurate | N/A | Dibratto, Susan | No | Paterson, Greg | Dave Lindsay | 191592.61 | 162793.65 | -28798.96 | -15.03% | 31784.09 | 28135.51 | -3648.58 | -11.48% | 116721.75 | 102824.28 | -13897.47 | -11.91% | 4696.55 | 6309.79 | 1613.24 | 34.35% | 38390.22 | 21748.83 | -16641.39 | -43.35% | 215.22 | 224.25 | 9.03 | 4.196% | 2021-06-30 01:00
Markham | 2021 | 453919 | 453919 - PRIMA VISTA PH 4 MUNICIPAL | 98 | COMPLETE | Cont Est Over | N/A | N/A | Penner, Mitchell | No | Estrada, Michael | Dave Lindsay | 62964.16 | 30892.54 | -32071.62 | -50.94% | 12221.5 | 6775.28 | -5446.22 | -44.56% | 1356.49 | 0 | -1356.49 | -100% | 592.85 | 320 | -272.85 | -46.02% | 48793.32 | 0 | -48793.32 | -100% | 64.94 | 20 | -44.94 | -69.2% | 2021-12-08 01:00
Markham | 2020 | 453921 | 453921 - M44 MINI-RUPTER REPLACEMENTS/CHILD WO - M44 2019 CABLE INJ | 99 | COMPLETE | Converted Project |  |  |  | No | Alectra Utilities | Lamb, Tim | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-25 01:00
Markham | 2020 | 453925 | 453925 (WO 319284) 150 VIA RENZO DRIVE | 99 | COMPLETE | Converted Project | N/A | N/A | Stephens, Barry N. | No | Alectra Utilities | Steve Rumble | 77726.5625 | 68890.82 | -8835.7425 | -11.37% | 12003.9586 | 14374.18 | 2370.2214 | 19.75% | 37227.7846 | 38312.91 | 1085.1254 | 2.915% | 4463.2254 | 1913 | -2550.2254 | -57.14% | 17490.053 | 12331.73 | -5158.323 | -29.49% | 184 | 211 | 27 | 14.67% | 2020-06-02 01:00
Markham | 2019 | 453929 | (WO319288) ISLINGTON AVE. - #9230 | 99 | COMPLETE | Labour est. under |  |  | Dibratto, Susan | No | Yuen, Paul | Shane Christopher | 68987.9448 | 54547.56 | -14440.3848 | -20.93% | 15699.2712 | 8153.06 | -7546.2112 | -48.07% | 33581.9262 | 27188.45 | -6393.4762 | -19.04% | 5900.8186 | 3566 | -2334.8186 | -39.57% | 9566.553 | 11487.43 | 1920.877 | 20.08% | 217 | 147.25 | -69.75 | -32.14% | 2019-07-17 00:59
Markham | 2021 | 453933 | 453933 - LESLIE ELGIN - BLOCK 52 SUBDIVISION | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | D'Onofrio, Tony | Dave Lindsay | 278855.17 | 262978.7 | -15876.47 | -5.693% | 32136.86 | 36863.87 | 4727.01 | 14.71% | 1718.35 | 1804.91 | 86.56 | 5.037% | 1518.28 | 1364 | -154.28 | -10.16% | 243481.68 | 222131.45 | -21350.23 | -8.769% | 118.23 | 85.5 | -32.73 | -27.68% | 2021-11-11 01:00
Markham | 2019 | 453937 | 453937 (WO 319298 ) Stouffville to 404 Pole Line Extension | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Morrow, Joe | 153760.07 | 127797.51 | -25962.56 | -16.89% | 54377.64 | 49734.03 | -4643.61 | -8.54% | 34253.53 | 31907.79 | -2345.74 | -6.848% | 10735.51 | 13086.04 | 2350.53 | 21.89% | 54393.39 | 33069.65 | -21323.74 | -39.2% | 624.19 | 586 | -38.19 | -6.118% | 2019-11-30 01:00
Markham | 2020 | 453938 | 453938 (WO 319299) 50 Cityview | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 46545.94 | 35686.31 | -10859.63 | -23.33% | 16370.91 | 11021.9 | -5349.01 | -32.67% | 23116.75 | 22040.09 | -1076.66 | -4.657% | 1756.56 | 2397.5 | 640.94 | 36.49% | 5301.72 | 104.65 | -5197.07 | -98.03% | 178.8 | 102 | -76.8 | -42.95% | 2020-12-10 01:00
Markham | 2020 | 453941 | 453941 (WO 319302) OH and UG, Bathurst St(N. of Rutherford Rd-N. of Lebovic Campus Dr), OH,UG Reloc | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 2188418 | 1620303.74 | -568114.26 | -25.96% | 21620 | 146975.26 | 125355.26 | 579.8% | 374895 | 318438.93 | -56456.07 | -15.06% | 4513 | 0 | -4513 | -100% | 1787390 | 1006136.37 | -781253.63 | -43.71% | 275 | 677 | 402 | 146.2% | 2020-01-15 01:00
Markham | 2020 | 453942 | 453942 - PHASE 2.2-OH&UG RELOC-BATHURST ST(N. OF LEBOVIC CAMPUS DR-N. OF VALLEY VISTA DR) | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 1709963.41 | 1719045.08 | 9081.67 | 0.5311% | 38314.63 | 187050.01 | 148735.38 | 388.2% | 455552.94 | 459625.35 | 4072.41 | 0.8939% | 1988 | 0 | -1988 | -100% | 1214107.84 | 1030233.14 | -183874.7 | -15.14% | 292.04 | 792.5 | 500.46 | 171.4% | 2020-01-15 01:00
Markham | 2020 | 453946 | 453946 (WO 319309) 9700 9th Line | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Ryan Walsh | 131670.9 | 133199.09 | 1528.19 | 1.161% | 50491.68 | 52675.56 | 2183.88 | 4.325% | 30034.72 | 26377.9 | -3656.82 | -12.18% | 7676.98 | 20919.66 | 13242.68 | 172.5% | 43467.52 | 32088.21 | -11379.31 | -26.18% | 462.16 | 575 | 112.84 | 24.42% | 2020-08-10 01:00
Markham | 2020 | 453947 | 453947 (WO 319310) Portage pkway – Jane St | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Shane Christopher | 296860.44 | 252878.72 | -43981.72 | -14.82% | 11583.76 | 25779.4 | 14195.64 | 122.5% | 31290.6 | 0 | -31290.6 | -100% | 831.6 | 704.83 | -126.77 | -15.24% | 253154.48 | 223685.68 | -29468.8 | -11.64% | 54 | 35 | -19 | -35.19% | 2020-10-30 01:00
Markham | 2019 | 453952 | 453952 (WO 319316) HE2019-017 - Bell BLOOMINGTON RD AND BAYVIEW CRT S | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 4058.58 | 3330.15 | -728.43 | -17.95% | 1357.77 | 789.96 | -567.81 | -41.82% | 284.01 | 169.29 | -114.72 | -40.39% | 114.24 | 0 | -114.24 | -100% | 2302.56 | 2370.9 | 68.34 | 2.968% | 8.44 | 4 | -4.44 | -52.61% | 2019-11-08 01:00
Markham | 2020 | 453954 | 453954 (WO 319318) Pole Relocation - Kennedy Road, Bur Oak Ave & Wilfred Murison Ave | 99 | COMPLETE | Converted Project | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Morrow, Joe | 130821 | 110069.54 | -20751.46 | -15.86% | 58633 | 65314.15 | 6681.15 | 11.39% | 35262 | 14000.11 | -21261.89 | -60.3% | 21556 | 21646.78 | 90.78 | 0.4211% | 15370 | 9108.5 | -6261.5 | -40.74% | 679.75 | 725.5 | 45.75 | 6.73% | 2020-12-01 01:00
Markham | 2020 | 453955 | 453955 - HE2019-022 - BELL | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 29351.54 | 20519.51 | -8832.03 | -30.09% | 4916.72 | 5682.94 | 766.22 | 15.58% | 4577.42 | 3328.74 | -1248.68 | -27.28% | 1279.4 | 1070 | -209.4 | -16.37% | 18578 | 10437.83 | -8140.17 | -43.82% | 60 | 50 | -10 | -16.67% | 2020-11-18 01:00
Markham | 2019 | 453959 | 453959 (WO 319325) 196 Citation Dr | 99 | COMPLETE | Converted Project |  |  | Cranley, Stephen | No | Paterson, Greg | Steve Rumble | 55358.6118 | 46736.2 | -8622.4118 | -15.58% | 9463.7388 | 8499.14 | -964.5988 | -10.19% | 33766.3 | 31153.57 | -2612.73 | -7.738% | 3376.6724 | 874.5 | -2502.1724 | -74.1% | 3180 | 2875.05 | -304.95 | -9.59% | 141 | 115.5 | -25.5 | -18.09% | 2019-10-20 01:00
Markham | 2022 | 453961 | (WO 319328) 17-052 - Bell PEELAR RD & JANE ST | 99 | CANCELLED | N/A |  |  |  | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-22 01:00
Markham | 2019 | 453965 | 453965 (WO 319332) HE2019-027 - Rogers MCCOWAN RD & 16TH AVE | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 8021.85 | 4720.32 | -3301.53 | -41.16% | 3536.31 | 1019.85 | -2516.46 | -71.16% | 389.56 | 279.13 | -110.43 | -28.35% | 279.8 | 0 | -279.8 | -100% | 3816.18 | 3421.34 | -394.84 | -10.35% | 26.93 | 5 | -21.93 | -81.43% | 2019-11-22 01:00
Markham | 2022 | 453966 | (WO 319333) BELL COMMUNICATION BONDS LANGSTAFF RD & WOODCROFT LN | 99 | CANCELLED | N/A |  |  |  | No | Martin, Shane | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-03 01:00
Markham | 2019 | 453970 | (WO 319338) V44SL3072 - 5020 Islington Ave | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 87533 | 109635.29 | 22102.29 | 25.25% | 21841 | 9014.23 | -12826.77 | -58.73% | 52871 | 54322.21 | 1451.21 | 2.745% | 8051 | 0 | -8051 | -100% | 4770 | 46298.85 | 41528.85 | 870.6% | 280 | 54 | -226 | -80.71% | 2019-10-03 01:00
Markham | 2019 | 453971 | 453971 (WO 319339) Replace V01SL3013 w/ Recloser | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Steve | 82966 | 105224.99 | 22258.99 | 26.83% | 19174 | 9746.81 | -9427.19 | -49.17% | 52971 | 52099.92 | -871.08 | -1.644% | 6899 | 0 | -6899 | -100% | 3922 | 43378.26 | 39456.26 | 1006% | 246.36 | 106 | -140.36 | -56.97% | 2019-10-30 01:00
Markham | 2020 | 453972 | 453972 (WO 319340) R20SA1001 - 12871 Yonge St | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Macdonald, Steve | 73047.05 | 100298.85 | 27251.8 | 37.31% | 18260.2 | 9319.6 | -8940.6 | -48.96% | 49395.3 | 57817.81 | 8422.51 | 17.05% | 5391.55 | 0 | -5391.55 | -100% | 0 | 33161.44 | 33161.44 |  | 134.4 | 76.5 | -57.9 | -43.08% | 2020-12-21 01:00
Markham | 2020 | 453973 | 453973 (WO 319341) VTS4 Feeder Integration Part 2 - Egress to Kirby Rd | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 592712.48 | 641895.66 | 49183.18 | 8.298% | 26429.5 | 56997.99 | 30568.49 | 115.7% | 19587.3 | 15896.34 | -3690.96 | -18.84% | 4045.36 | 342.34 | -3703.02 | -91.54% | 542650.32 | 558819.94 | 16169.62 | 2.98% | 362.97 | 116.5 | -246.47 | -67.9% | 2020-12-03 01:00
Markham | 2020 | 453974 | 453974 (WO 319342) VTS4 Feeder Integration Part 2 - Kirby Rd - VTS4 to Hwy 27 | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 532345.23 | 987529.02 | 455183.79 | 85.51% | 182393.9 | 241118.66 | 58724.76 | 32.2% | 180834.38 | 213903.88 | 33069.5 | 18.29% | 169116.95 | 115375.67 | -53741.28 | -31.78% | 0 | 411740.55 | 411740.55 |  | 2854.98 | 2757.5 | -97.48 | -3.414% | 2020-09-29 01:00
Markham | 2020 | 453975 | 453975 (WO 319343) VTS4 Feeder Integration Part 2 - Hwy 27 - Nashville to Major Mackenzie Drive | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 258811.53 | 376841.92 | 118030.39 | 45.6% | 56767.2 | 28792.56 | -27974.64 | -49.28% | 70727.75 | 80693.14 | 9965.39 | 14.09% | 131316.58 | 483.31 | -130833.27 | -99.63% | 0 | 238109.35 | 238109.35 |  | 802.37 | 95.5 | -706.87 | -88.1% | 2020-10-31 01:00
Markham | 2020 | 453976 | 453976 (WO 319344) VTS4 Feeder Integration Part 2 - Major Mack Drive - Islington Ave to Weston Rd | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 1021475.77 | 1246740.9 | 225265.13 | 22.05% | 142408.75 | 89279.3 | -53129.45 | -37.31% | 199145.23 | 220367.07 | 21221.84 | 10.66% | 33486.71 | 523.58 | -32963.13 | -98.44% | 646435.08 | 892760.83 | 246325.75 | 38.11% | 2273.16 | 150.5 | -2122.66 | -93.38% | 2020-12-11 01:00
Markham | 2020 | 453985 | 453985 (WO 319354) PERFORMANCE DRIVE - #60 | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 62903.8 | 54870.57 | -8033.23 | -12.77% | 14598.87 | 11748.21 | -2850.66 | -19.53% | 25991.53 | 23111.73 | -2879.8 | -11.08% | 5081.72 | 1405 | -3676.72 | -72.35% | 13999.06 | 15093.35 | 1094.29 | 7.817% | 202 | 167.25 | -34.75 | -17.2% | 2020-08-19 01:00
Markham | 2020 | 453990 | 453990 (WO 319360) 10 AND 20 GATINEAU DR | 99 | COMPLETE | Converted Project |  |  |  | No | Alectra Utilities | Steve Rumble | 179208.95 | 167003.1 | -12205.85 | -6.811% | 14968.48 | 12625.51 | -2342.97 | -15.65% | 2567.75 | 2457.33 | -110.42 | -4.3% | 1092.92 | 1535 | 442.08 | 40.45% | 160579.8 | 0 | -160579.8 | -100% | 193.52 | 142.5 | -51.02 | -26.36% | 2020-02-26 01:00
Markham | 2019 | 453993 | 453993 (WO 319370) NEW HUNTINTGTON RD. - #450 AT HUNTINGTON RD. | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Yuen, Paul | Steve Rumble | 54668.94 | 35927.77 | -18741.17 | -34.28% | 13847.04 | 3943.55 | -9903.49 | -71.52% | 27176.86 | 24552.6 | -2624.26 | -9.656% | 4513.37 | 180 | -4333.37 | -96.01% | 4782.51 | 3980.04 | -802.47 | -16.78% | 195 | 92.5 | -102.5 | -52.56% | 2019-10-30 01:00
Markham | 2020 | 453994 | 453994 - 2430 Teston Rd | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 75806.96 | 75504.92 | -302.04 | -0.3984% | 24779.1 | 25694.14 | 915.04 | 3.693% | 33440.46 | 29663.92 | -3776.54 | -11.29% | 3432.92 | 9671.5 | 6238.58 | 181.7% | 14154.48 | 8723.3 | -5431.18 | -38.37% | 180 | 298 | 118 | 65.56% | 2020-02-20 01:00
Markham | 2020 | 454010 | (WO 319393) Replace P33141 - 295 Steelcase Rd E | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-04 01:00
Markham | 2019 | 454011 | 454011 (WO 319394) Replace P33146 - 395 Steelcase Rd E | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Shortt, Derek B. | 53536 | 15556.99 | -37979.01 | -70.94% | 27914 | 6942.84 | -20971.16 | -75.13% | 2700 | 2702.18 | 2.18 | 0.08074% | 9854 | 1763 | -8091 | -82.11% | 13068 | 4148.97 | -8919.03 | -68.25% | 174 | 78 | -96 | -55.17% | 2019-12-04 01:00
Markham | 2020 | 454012 | (WO 319395) Replace P32953 - 80 Torbay Rd | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-05 01:00
Markham | 2019 | 454013 | 454013 (WO 319396) Replace P33217 - 95 Steelcase Rd E | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Shortt, Derek B. | 124810 | 84489 | -40321 | -32.31% | 68760 | 39505 | -29255 | -42.55% | 19616 | 19823 | 207 | 1.055% | 25711 | 22241 | -3470 | -13.5% | 10723 | 2920 | -7803 | -72.77% | 529 | 506.5 | -22.5 | -4.253% | 2019-11-05 01:00
Markham | 2019 | 454015 | (WO 319399) Pole Replacement 2019 - Replace 2 poles at Old Bloomington Rd., Aurora | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Larry | 23225 | 6974.92 | -16250.08 | -69.97% | 9886 | 417.09 | -9468.91 | -95.78% | 6924 | 5954.2 | -969.8 | -14.01% | 3235 | 603.63 | -2631.37 | -81.34% | 3180 | 0 | -3180 | -100% | 126.75 | 101.5 | -25.25 | -19.92% | 2019-06-24 01:00
Markham | 2022 | 454016 | 454016 - HWY 27 & HWY 7 | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Shane Christopher | 1307128 | 1300763.9 | -6364.1 | -0.4869% | 30987 | 109981.87 | 78994.87 | 254.9% | 72894 | 70518.26 | -2375.74 | -3.259% | 1680 | 2592 | 912 | 54.29% | 1201567 | 1117671.77 | -83895.23 | -6.982% | 160 | 166 | 6 | 3.75% | 2022-01-10 01:00
Markham | 2019 | 454017 | (WO 319401) 10725 Reesor Road | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-05 01:00
Markham | 2019 | 454019 | (WO 319406) HWY 7 & Valleymede Drive | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Steve Rumble | 258115.04 | 538213.19 | 280098.15 | 108.5% | 16172.47 | 44544.57 | 28372.1 | 175.4% | 4908.37 | 1832.03 | -3076.34 | -62.68% | 495.84 | 1156 | 660.16 | 133.1% | 236538.36 | 150539.89 | -85998.47 | -36.36% | 238 | 300 | 62 | 26.05% | 2019-09-05 01:00
Markham | 2020 | 454021 | 454021 (WO 319408) Pole Installation 349 ELGIN MILLS | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 23041.37 | 30339.2 | 7297.83 | 31.67% | 12267.24 | 7378.54 | -4888.7 | -39.85% | 2786.99 | 3387.17 | 600.18 | 21.54% | 882.9 | 0 | -882.9 | -100% | 7104.24 | 19166.24 | 12062 | 169.8% | 109.52 | 8.5 | -101.02 | -92.24% | 2020-08-10 01:00
Markham | 2019 | 454022 | (WO319409) Connect Bell Bond. WESTON RD. S/O COLOSSUS DRIVE | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Cavanaugh, Danny | Don Rothman | 731 | 0 | -731 | -100% | 631 | 0 | -631 | -100% | 0 | 0 | 0 |  | 100 | 0 | -100 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-10 01:00
Markham | 2019 | 454025 | 454025 (WO 319412) 8550 Keele St | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Paterson, Greg | Steve Rumble | 82347.93 | 63606.56 | -18741.37 | -22.76% | 17250.59 | 8331.83 | -8918.76 | -51.7% | 40538.5 | 37137.29 | -3401.21 | -8.39% | 1911.24 | 513 | -1398.24 | -73.16% | 22647.6 | 15995.6 | -6652 | -29.37% | 128 | 73.5 | -54.5 | -42.58% | 2019-11-12 01:00
Markham | 2019 | 454026 | 454026 (WO 319413) M43 Steelcase and Idema - Convert 43T-024 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Handy, James | Cory Ruiter | 105161 | 107495.22 | 2334.22 | 2.22% | 9548 | 7343.85 | -2204.15 | -23.08% | 0 | 12032.43 | 12032.43 |  | 2207 | 0 | -2207 | -100% | 93406 | 88118.94 | -5287.06 | -5.66% | 116 | 6 | -110 | -94.83% | 2019-11-16 01:00
Markham | 2019 | 454066 | (WO 319453) BELL POLE REPLACEMENT 193 KRIEGHOFF AVENUE | 99 | CANCELLED | N/A |  |  |  | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-02 01:00
Markham | 2019 | 454067 | (WO319454) CLARK AVE AND SOUTH PROMENADE | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Alarcon, Alejandro | Lamb, Tim | 44081 | 32959.69 | -11121.31 | -25.23% | 11113 | 9872.52 | -1240.48 | -11.16% | 1301 | 2454.19 | 1153.19 | 88.64% | 3076 | 859 | -2217 | -72.07% | 28591 | 16149.62 | -12441.38 | -43.52% | 142 | 170.5 | 28.5 | 20.07% | 2019-08-02 01:00
Markham | 2021 | 454073 | 454073 (WO 319460) Primont Cornell 2 Detached | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Dave Lindsay | 43087.15 | 37704.35 | -5382.8 | -12.49% | 14403.56 | 11238.97 | -3164.59 | -21.97% | 5.44 | 0 | -5.44 | -100% | 808.75 | 0 | -808.75 | -100% | 27869.4 | 24755 | -3114.4 | -11.17% | 20.25 | 2 | -18.25 | -90.12% | 2021-11-25 01:00
Markham | 2020 | 454078 | 454078 (WO 319466) Pole Relocations JANE STREET & MAJOR MACKENZIE | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Steve Rumble | 86624.6 | 70237.43 | -16387.17 | -18.92% | 37059.08 | 10348.73 | -26710.35 | -72.08% | 18144.1 | 15945.35 | -2198.75 | -12.12% | 4731.92 | 0 | -4731.92 | -100% | 26689.5 | 43943.35 | 17253.85 | 64.65% | 352.08 | 10 | -342.08 | -97.16% | 2020-06-10 01:00
Markham | 2021 | 454080 | (WO 319469) Pole/Grading Issues Extra Cost LESLIE - ELGIN TO 19TH | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-03 01:00
Markham | 2020 | 454081 | 454081 (WO 319470) Road Widening JANE STREET TO HWY 400 | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 219462.36 | 242487.47 | 23025.11 | 10.49% | 74749.52 | 24843.19 | -49906.33 | -66.76% | 54363.39 | 60880.57 | 6517.18 | 11.99% | 13949.17 | 0 | -13949.17 | -100% | 76400.28 | 156763.71 | 80363.43 | 105.2% | 925.455 | 33 | -892.455 | -96.43% | 2020-07-03 01:00
Markham | 2021 | 454086 | (WO319477) 5875 HIGHWAY 7 - VAUGHAN | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Barry, Kenneth | Persaud, Ryan | 0 | 8474.42 | 8474.42 |  | 0 | 8173.03 | 8173.03 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 65.8 | 65.8 |  | 0 | 10.7 | 10.7 |  | 2019-12-21 01:00
Markham | 2019 | 454088 | 454088 (WO 319479) 8251 Keele St | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Paterson, Greg | Steve Rumble | 35160.8 | 26227.22 | -8933.58 | -25.41% | 15412.95 | 13221.46 | -2191.49 | -14.22% | 3200.02 | 2940.71 | -259.31 | -8.103% | 1574.71 | 1131 | -443.71 | -28.18% | 14973.12 | 7905.99 | -7067.13 | -47.2% | 168.98 | 111 | -57.98 | -34.31% | 2019-12-21 01:00
Markham | 2022 | 454089 | 454089 - INTERCHANGE WAY - #250 - MULTIPLE RESIDENTIAL CONDOS | 99 | ANALYZE |  |  |  | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 163871.66 | 134206.83 | -29664.83 | -18.1% | 30364.31 | 46959.58 | 16595.27 | 54.65% | 100293.55 | 57870.42 | -42423.13 | -42.3% | 2765.61 | 1068 | -1697.61 | -61.38% | 35448.19 | 27372.19 | -8076 | -22.78% | 301.42 | 291 | -10.42 | -3.457% | 2022-07-18 01:00
Markham | 2020 | 454090 | 454090 (WO 454090) VICTORIA PARK AVE. #7200 AT TORBAY RD. | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 146438.9888 | 125853.04 | -20585.9488 | -14.06% | 25781.808 | 21939.42 | -3842.388 | -14.9% | 92404.2836 | 85948.44 | -6455.8436 | -6.987% | 9698.7392 | 2971.5 | -6727.2392 | -69.36% | 9189.5428 | 13100.18 | 3910.6372 | 42.56% | 351 | 230.5 | -120.5 | -34.33% | 2020-09-16 01:00
Markham | 2019 | 454093 | 454093 (WO 319485) Replace P32141 BAYVIEW AVE & LAURELEAF, MARKHAM | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Shortt, Derek B. | 81411 | 67112 | -14299 | -17.56% | 29947 | 26683 | -3264 | -10.9% | 20896 | 22254 | 1358 | 6.499% | 10043 | 8002 | -2041 | -20.32% | 20525 | 10173 | -10352 | -50.44% | 200 | 296 | 96 | 48% | 2019-12-18 01:00
Markham | 2020 | 454094 | (WO319486) BARONS STREET & MAJOR MACKENZIE DRIVE | 99 | CANCELLED | N/A |  |  | Penner, Mitchell | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-14 01:00
Markham | 2020 | 454101 | 454101 (WO 319493) 16TH AVENUE - Insulator Repl -2020 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 206395.43 | 228212.33 | 21816.9 | 10.57% | 80084.92 | 83784.67 | 3699.75 | 4.62% | 78229.6 | 74271.69 | -3957.91 | -5.059% | 16986.63 | 29704 | 12717.37 | 74.87% | 31094.28 | 40451.97 | 9357.69 | 30.09% | 1111.75 | 997 | -114.75 | -10.32% | 2020-08-26 01:00
Markham | 2020 | 454102 | 454102 (WO 319494) HUNTINGTON RD - INSULATOR REPL - 2020 Project | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 44829.27 | 51308 | 6478.73 | 14.45% | 14451.21 | 23990 | 9538.79 | 66.01% | 14145.61 | 19007 | 4861.39 | 34.37% | 2710.85 | 5776 | 3065.15 | 113.1% | 13521.6 | 2535 | -10986.6 | -81.25% | 194.44 | 274 | 79.56 | 40.92% | 2020-03-14 01:00
Markham | 2019 | 454105 | (WO319497) 65 Malmo Crt | 99 | COMPLETE | Labour est. under |  |  | Dibratto, Susan | No | Diefenbaker, Trevor A | Steve Rumble | 17401.7433 | 7601.88 | -9799.8633 | -56.32% | 6907.5578 | 987.75 | -5919.8078 | -85.7% | 0 | 0 | 0 |  | 1939.0792 | 0 | -1939.0792 | -100% | 7780.506 | 0 | -7780.506 | -100% | 98 | 118 | 20 | 20.41% | 2019-06-26 01:00
Markham | 2020 | 454106 | 454106 (WO 319498) Hydro Relocation RUTHERFORD RD AND MCGILLIVRAY ROAD, VAUGHAN | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Alectra Utilities | Morrow, Joe | 344136.58 | 255567.1 | -88569.48 | -25.74% | 69060.03 | 78937.12 | 9877.09 | 14.3% | 43322.58 | 31236.12 | -12086.46 | -27.9% | 10623.97 | 26887.67 | 16263.7 | 153.1% | 221130 | 117376.17 | -103753.83 | -46.92% | 1007.32 | 805 | -202.32 | -20.08% | 2020-02-26 01:00
Markham | 2020 | 454110 | 454110 (WO 319503) A02 Steeplechase Ave Cable Replacement ( Incremental Work) | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | Yes | Alectra Utilities | Lamb, Tim | 2110904.21 | 2221843.98 | 110939.77 | 5.256% | 123702.57 | 195343.13 | 71640.56 | 57.91% | 22212.2 | 34461.27 | 12249.07 | 55.15% | 13103.28 | 20.14 | -13083.14 | -99.85% | 1951886.16 | 1992019.44 | 40133.28 | 2.056% | 1753.66 | 309.09 | -1444.57 | -82.37% | 2020-09-28 01:00
Markham | 2020 | 454111 | 454111 (WO 319504) V15 Jardin Dr Cable Replacement ( Incremental Work) | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 1687606.24 | 1788665.77 | 101059.53 | 5.988% | 200744.31 | 158666.66 | -42077.65 | -20.96% | 33818.88 | 57882.46 | 24063.58 | 71.15% | 20270.77 | 0 | -20270.77 | -100% | 1432772.28 | 1572116.65 | 139344.37 | 9.726% | 1445.66 | 220 | -1225.66 | -84.78% | 2020-08-07 01:00
Markham | 2020 | 454119 | 454119 (WO 319512) M41 - Woodbine and Elgin Mills (2020 Cable Injection) | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Lamb, Tim | 113676.99 | 65593.76 | -48083.23 | -42.3% | 4382.04 | 7257.47 | 2875.43 | 65.62% | 2050.95 | 0 | -2050.95 | -100% | 0 | 0 | 0 |  | 107244 | 58336.29 | -48907.71 | -45.6% | 0 | 0 | 0 |  | 2020-12-04 01:00
Markham | 2020 | 454120 | 454120 (WO 319513) M43 - John and Woodbine (2020 Cable Injection) | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Lamb, Tim | 1029638.15 | 1075643.72 | 46005.57 | 4.468% | 4382.04 | 137204.97 | 132822.93 | 3031% | 54850.19 | 0 | -54850.19 | -100% | 0 | 0 | 0 |  | 970405.92 | 938438.75 | -31967.17 | -3.294% | 0 | 562 | 562 |  | 2020-12-04 01:00
Markham | 2020 | 454121 | 454121 (WO 319514) V38 - Rutherford and Weston Rd (2020 Cable Injection) | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Lamb, Tim | 1413868.92 | 809700.12 | -604168.8 | -42.73% | 4382.04 | 64515.99 | 60133.95 | 1372% | 59441.52 | 19350.57 | -40090.95 | -67.45% | 0 | 0 | 0 |  | 1350045.36 | 725833.56 | -624211.8 | -46.24% | 0 | 1 | 1 |  | 2020-12-31 01:00
Markham | 2022 | 454122 | 454122 (WO 319515) V01 - Yonge-Steeles-Bathurst-Centre (2020 Cable Injection) | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 1219621.33 | 913281.59 | -306339.74 | -25.12% | 4382.04 | 76898.75 | 72516.71 | 1655% | 52030.69 | 856.69 | -51174 | -98.35% | 0 | 0 | 0 |  | 1163208.6 | 835526.15 | -327682.45 | -28.17% | 0 | 0 | 0 |  | 2022-01-25 01:00
Markham | 2022 | 454123 | 454123 (WO 319516) V36 - Steeles and Pine Valley (2020 Cable Injection) | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 227528.77 | 229181.79 | 1653.02 | 0.7265% | 4382.04 | 22088.65 | 17706.61 | 404.1% | 26152.57 | 2029.17 | -24123.4 | -92.24% | 0 | 0 | 0 |  | 196994.16 | 205063.97 | 8069.81 | 4.096% | 0 | 0 | 0 |  | 2022-03-22 01:00
Markham | 2020 | 454124 | 454124 (WO 319517) V37 - Langstaff and Wesotn Rd (2020 Cable Injection) | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Lamb, Tim | 1538880.95 | 1344425.82 | -194455.13 | -12.64% | 4382.04 | 108117.47 | 103735.43 | 2367% | 30688.55 | 22476.66 | -8211.89 | -26.76% | 0 | 0 | 0 |  | 1503810.36 | 1213831.69 | -289978.67 | -19.28% | 0 | 0 | 0 |  | 2020-12-04 01:00
Markham | 2022 | 454125 | 454125 (WO 319518) V18 - Major Mackenzie and Keele (2020 Cable Injection) | 99 | COMPLETE | Cont Est Under | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 1112683.66 | 1285428.23 | 172744.57 | 15.53% | 4382.04 | 124671.96 | 120289.92 | 2745% | 48939.34 | 24788.9 | -24150.44 | -49.35% | 0 | 0 | 0 |  | 1059362.28 | 1135967.37 | 76605.09 | 7.231% | 0 | 0 | 0 |  | 2022-04-05
Markham | 2020 | 454126 | 454126 (WO 319519) V43 - Hwy 7 and Pine Valley Dr (2020 Cable Injection) | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Lamb, Tim | 1019464.22 | 868940.29 | -150523.93 | -14.77% | 4382.04 | 70075.47 | 65693.43 | 1499% | 23555.78 | 20953.42 | -2602.36 | -11.05% | 0 | 0 | 0 |  | 991526.4 | 777911.4 | -213615 | -21.54% | 0 | 0.25 | 0.25 |  | 2020-12-04 01:00
Markham | 2020 | 454127 | 454127 - ICI TX UPGRADE/700 CENTRE ST Ex. Walmart Upgrade | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 72010.4 | 75946.87 | 3936.47 | 5.467% | 13757.24 | 19656.44 | 5899.2 | 42.88% | 38637.83 | 38266.92 | -370.91 | -0.96% | 1513.45 | 2727.24 | 1213.79 | 80.2% | 18101.88 | 14074.76 | -4027.12 | -22.25% | 152.3 | 181 | 28.7 | 18.84% | 2020-08-03 01:00
Markham | 2019 | 454128 | (WO454128) 12895 BAYVIEW AVE | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Diefenbaker, Trevor A | Steve Rumble | 39421.04 | 24297.27 | -15123.77 | -38.36% | 14441.02 | 3617.47 | -10823.55 | -74.95% | 23434.18 | 20120.31 | -3313.87 | -14.14% | 1545.84 | 0 | -1545.84 | -100% | 0 | 0 | 0 |  | 31 | 36 | 5 | 16.13% | 2019-09-17 01:00
Markham | 2020 | 454129 | 454129 - 141 NEW HUNTINGTON | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 97149.13 | 81691.57 | -15457.56 | -15.91% | 10277.07 | 12040.09 | 1763.02 | 17.15% | 55669.85 | 51907.81 | -3762.04 | -6.758% | 4563.52 | 1824 | -2739.52 | -60.03% | 16272.48 | 14800.73 | -1471.75 | -9.044% | 177 | 133.75 | -43.25 | -24.44% | 2020-03-06 01:00
Markham | 2020 | 454132 | 454132 - UNPLANNED/JOINT USE HE2019-043 | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Alectra Utilities | Morrow, Joe | 9760.73 | 6813.67 | -2947.06 | -30.19% | 3803.02 | 2012.22 | -1790.8 | -47.09% | 1557.15 | 791.84 | -765.31 | -49.15% | 555.76 | 359.61 | -196.15 | -35.29% | 3844.8 | 3650 | -194.8 | -5.067% | 41.58 | 8 | -33.58 | -80.76% | 2020-06-10 01:00
Markham | 2021 | 454133 | 454133 - JOINT USE HE2019-044 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 21879.81 | 13294.86 | -8584.95 | -39.24% | 5352.89 | 4086.99 | -1265.9 | -23.65% | 2338.12 | 1051.21 | -1286.91 | -55.04% | 688.8 | 778 | 89.2 | 12.95% | 13500 | 7378.66 | -6121.34 | -45.34% | 31.2 | 25.5 | -5.7 | -18.27% | 2021-02-28 01:00
Markham | 2019 | 454134 | (WO 319527) Guy Wire relocation INTERSECTION OF LOCKE AND JANE ST. | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Larry | 7450.26 | 3954.63 | -3495.63 | -46.92% | 6042.23 | 2278.06 | -3764.17 | -62.3% | 630.8 | 333.57 | -297.23 | -47.12% | 202.4 | 558 | 355.6 | 175.7% | 574.83 | 785 | 210.17 | 36.56% | 22.86 | 34 | 11.14 | 48.73% | 2019-09-11 01:00
Markham | 2021 | 454135 | 454135 - I & C UNION VILLAGE PH 1 NORTH | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Dave Lindsay | 86760.05 | 650121.68 | 563361.63 | 649.3% | 43720.39 | 27678.28 | -16042.11 | -36.69% | 9722.37 | 4148.76 | -5573.61 | -57.33% | 3941.29 | 2877.5 | -1063.79 | -26.99% | 29376 | 27200 | -2176 | -7.407% | 323.9 | 155.5 | -168.4 | -51.99% | 2021-07-21 01:00
Markham | 2019 | 454140 | (WO454140) 24 Elva Crt rush cable replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 180494.28 | 125629.13 | -54865.15 | -30.4% | 8213.53 | 13162.47 | 4948.94 | 60.25% | 480.01 | 0 | -480.01 | -100% | 607.24 | 0 | -607.24 | -100% | 171193.5 | 112466.66 | -58726.84 | -34.3% | 37 | 33.5 | -3.5 | -9.459% | 2019-09-24 01:00
Markham | 2019 | 454141 | V37 Ainsley Grove and Airdrie (37-P1 to 37-36) | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 494797.27 | 466980.83 | -27816.44 | -5.622% | 16289.47 | 48974.23 | 32684.76 | 200.6% | 2718.45 | 5224.72 | 2506.27 | 92.19% | 1720.11 | 2274.8 | 554.69 | 32.25% | 474069.24 | 410507.08 | -63562.16 | -13.41% | 134 | 168 | 34 | 25.37% | 2019-10-22 01:00
Markham | 2020 | 454144 | 454144 - 41 KEYES COURT | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 92480.07 | 94949.99 | 2469.92 | 2.671% | 13948.32 | 9583.16 | -4365.16 | -31.3% | 53599.79 | 50916.16 | -2683.63 | -5.007% | 1702.24 | 1640 | -62.24 | -3.656% | 23229.72 | 31622.18 | 8392.46 | 36.13% | 177.99 | 101.5 | -76.49 | -42.97% | 2020-01-28 01:00
Markham | 2020 | 454145 | 454145 - 21 Keyes Court Vaughan | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 105660.602 | 85658.07 | -20002.532 | -18.93% | 15551.1588 | 14109.32 | -1441.8388 | -9.272% | 57094.2786 | 51378.31 | -5715.9686 | -10.01% | 6134.8454 | 1861 | -4273.8454 | -69.67% | 15387.6066 | 15820.41 | 432.8034 | 2.813% | 244 | 149 | -95 | -38.93% | 2020-03-06 01:00
Markham | 2020 | 454148 | 454148 - 615 Bowes Rd, Vaughan | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 162300.68 | 135114.3 | -27186.38 | -16.75% | 18587.31 | 18981.66 | 394.35 | 2.122% | 88389.91 | 95546.11 | 7156.2 | 8.096% | 2465.02 | 4728.09 | 2263.07 | 91.81% | 52858.44 | 15858.44 | -37000 | -70% | 139 | 169 | 30 | 21.58% | 2020-07-17 01:00
Markham | 2020 | 454151 | 454151 (WO 319545) Remington Enterprise Temp | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 94739.66 | 97887.84 | 3148.18 | 3.323% | 13276.46 | 16558.94 | 3282.48 | 24.72% | 53723.18 | 55144.77 | 1421.59 | 2.646% | 1257.34 | 2024 | 766.66 | 60.97% | 26482.68 | 23094.2 | -3388.48 | -12.8% | 92 | 156 | 64 | 69.57% | 2020-02-06 01:00
Markham | 2020 | 454162 | (WO 319558) Joint Use Permit # HE2019-048 RUTHERFORD ROAD - WEST OF HWY 27 | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 6457.55 | 4175.25 | -2282.3 | -35.34% | 2600.62 | 328.16 | -2272.46 | -87.38% | 1711.33 | 1954.56 | 243.23 | 14.21% | 201.6 | 0 | -201.6 | -100% | 1944 | 1892.53 | -51.47 | -2.648% | 14.94 | 7.2 | -7.74 | -51.81% | 2020-01-14 01:00
Markham | 2019 | 454204 | 454204 (WO 454204) Tenth Line Pole Relocation | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Morrow, Joe | 43402.7 | 27837.48 | -15565.22 | -35.86% | 27530.9 | 16619.92 | -10910.98 | -39.63% | 9062.91 | 6769.56 | -2293.35 | -25.3% | 4490.35 | 3568 | -922.35 | -20.54% | 2318.54 | 880 | -1438.54 | -62.05% | 259.14 | 188.5 | -70.64 | -27.26% | 2019-11-19 01:00
Markham | 2021 | 454205 | 454205 - RER - MX - RELOC - KIRBY RD - BARRIE LINE (1907) - RAILWAY CROSSINGS | 99 | COMPLETE | Under 10% | N/A | N/A | Vande Kuyt, Greg | No | Grahovac, John | Macdonald, Steve | 333250.49 | 354264.57 | 21014.08 | 6.306% | 4469.15 | 31695.87 | 27226.72 | 609.2% | 94453.75 | 98238.94 | 3785.19 | 4.007% | 176.03 | 0 | -176.03 | -100% | 234151.56 | 221482.63 | -12668.93 | -5.411% | 5.41 | 10 | 4.59 | 84.84% | 2021-04-29
Markham | 2020 | 454225 | 454225 (WO 319624) MCCACHEN ST & KING ROAD | 99 | COMPLETE | Converted Project | N/A | N/A | Penner, Mitchell | No | Alectra Utilities | Dave Lindsay | 89030.29 | 95669.33 | 6639.04 | 7.457% | 10417.22 | 17899.25 | 7482.03 | 71.82% | 2237.21 | 718.01 | -1519.2 | -67.91% | 817.86 | 1137.79 | 319.93 | 39.12% | 75558 | 75558 | 0 | 0% | 61.92 | 44.5 | -17.42 | -28.13% | 2020-12-16 01:00
Markham | 2019 | 454226 | YRRTC-Y2.2-SEC. SERV. RELOC./YRRTC-Y2.2-UG SEC. SERV. RELOC | 99 | COMPLETE | Converted Project |  |  | Lacombe, Joel | No | Lacombe, Joel | Steve Rumble | 80062.08 | 237238.38 | 157176.3 | 196.3% | 3215.16 | 7946.65 | 4731.49 | 147.2% | 0 | 11361.84 | 11361.84 |  | 330 | 0 | -330 | -100% | 76516.92 | 63175.07 | -13341.85 | -17.44% | 70 | 36.75 | -33.25 | -47.5% | 2019-10-10 01:00
Markham | 2019 | 454229 | (WO319629) 800 Tesma Way | 99 | COMPLETE | Converted Project |  |  | Dibratto, Susan | No | Paterson, Greg | Steve Rumble | 8326.44 | 7547.23 | -779.21 | -9.358% | 7996.44 | 5878.9 | -2117.54 | -26.48% | 0 | 0 | 0 |  | 330 | 436.5 | 106.5 | 32.27% | 0 | 0 | 0 |  | 40 | 38 | -2 | -5% | 2019-10-11 01:00
Markham | 2021 | 454235 | 454235 (WO 319635) Hwy 7 - Dufferin/Langstaff to Bowes/Hwy 7 | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 253294.18 | 559614.3 | 306320.12 | 120.9% | 57562.52 | 38102.27 | -19460.25 | -33.81% | 110521.52 | 122815.43 | 12293.91 | 11.12% | 8625.72 | 0 | -8625.72 | -100% | 76584.42 | 398696.6 | 322112.18 | 420.6% | 815.56 | 2 | -813.56 | -99.75% | 2021-02-05 01:00
Markham | 2019 | 454238 | (WO 319639) V15 Baldwin Dr V15FA1004 to 15-L7 - Rush | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Handy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-07 01:00
Markham | 2019 | 454239 | (WO319641) INTERCHANGE WAY X EXCHANGE AVENUE | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-07 01:00
Markham | 2020 | 454242 | 454242 (WO 319644) Stouffville Rd & Hwy 404 | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 43331.61 | 34706.55 | -8625.06 | -19.9% | 16454.18 | 11283.49 | -5170.69 | -31.42% | 20819.8 | 18612.64 | -2207.16 | -10.6% | 1409.31 | 896.5 | -512.81 | -36.39% | 4648.32 | 3913.92 | -734.4 | -15.8% | 73.85 | 58.5 | -15.35 | -20.79% | 2020-12-07 01:00
Markham | 2020 | 454243 | (WO 319645) Residential Service Adjustment -31 MARK ST. AURORA | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-15 01:00
Markham | 2020 | 454244 | 454244 (WO 319646) 300 Gibraltar Road | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 127510.38 | 119883.11 | -7627.27 | -5.982% | 11723.87 | 18761.63 | 7037.76 | 60.03% | 81780.4 | 76237.7 | -5542.7 | -6.778% | 1056.39 | 1983 | 926.61 | 87.71% | 32949.72 | 22347.62 | -10602.1 | -32.18% | 134.65 | 213.5 | 78.85 | 58.56% | 2020-10-15 01:00
Markham | 2020 | 454249 | 454249 (WO 319651) JU #HE2019-056 - NINTH LINE AND DONALD COUSENS PARKWAY | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 4475.12 | 5403.69 | 928.57 | 20.75% | 2066.64 | 573.82 | -1492.82 | -72.23% | 499.04 | 334.42 | -164.62 | -32.99% | 181.44 | 0 | -181.44 | -100% | 1728 | 4495.45 | 2767.45 | 160.2% | 13.39 | 0 | -13.39 | -100% | 2020-02-27 01:00
Markham | 2020 | 454250 | 454250 (WO 319654) VTS4 - MMD Pine Valley-Weston | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 438263.26 | 584463.08 | 146199.82 | 33.36% | 126529.19 | 42111.61 | -84417.58 | -66.72% | 190501.49 | 191920.54 | 1419.05 | 0.7449% | 121232.58 | 322.21 | -120910.37 | -99.73% | 0 | 349380.82 | 349380.82 |  | 1100.6 | 125 | -975.6 | -88.64% | 2020-12-11 01:00
Markham | 2022 | 454254 | 454254 - ICI NEW CONDOMINIUM CONNECTION/9 CLEGG ROAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Joshi, Namrata | No | Diefenbaker, Trevor A | Dave Lindsay | 82597.03 | 95627.34 | 13030.31 | 15.78% | 24900.29 | 20591.92 | -4308.37 | -17.3% | 55925.7 | 54728.65 | -1197.05 | -2.14% | 3277.04 | 1488 | -1789.04 | -54.59% | 20844 | 18202.43 | -2641.57 | -12.67% | 150.97 | 167 | 16.03 | 10.62% | 2022-10-07 01:00
Markham | 2019 | 454258 | (WO 319663) OH Transfer existing circuits to new Hydro One poles at Yonge & Regatta intersection | 99 | COMPLETE | Converted Project | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Larry | 47127 | 64696.57 | 17569.57 | 37.28% | 22117 | 24246.3 | 2129.3 | 9.627% | 14945 | 17761.59 | 2816.59 | 18.85% | 7415 | 12836 | 5421 | 73.11% | 2650 | 8549.57 | 5899.57 | 222.6% | 110 | 296.5 | 186.5 | 169.5% | 2019-09-11 01:00
Markham | 2019 | 454260 | 454260 - Hughson @ Lunar Pole Relocation | 99 | COMPLETE | Converted Project |  |  | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Larry | 13906.6 | 12234.07 | -1672.53 | -12.03% | 8980.25 | 7566.67 | -1413.58 | -15.74% | 2203.84 | 1669.7 | -534.14 | -24.24% | 1060.39 | 831 | -229.39 | -21.63% | 1662.12 | 1790 | 127.88 | 7.694% | 72.36 | 62 | -10.36 | -14.32% | 2019-10-12 01:00
Markham | 2019 | 454265 | 454265 - Regina Rd. #21 (Vaughan), Hwy. #7 & Martin Grove Rd. | 99 | COMPLETE | Converted Project | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Steve Rumble | 70958.5 | 58874.36 | -12084.14 | -17.03% | 17571.16 | 8840.48 | -8730.68 | -49.69% | 39476.04 | 39663.55 | 187.51 | 0.475% | 2430.9 | 228 | -2202.9 | -90.62% | 11480.4 | 9531.6 | -1948.8 | -16.98% | 114 | 66.5 | -47.5 | -41.67% | 2019-12-04 01:00
Markham | 2019 | 454267 | 454267 - BAYVIEW PUMP STN CABLE REPL/BAYVIEW PUMP STATION CABLES | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Roy, James | Morrow, Joe | 10195.2 | 15930.64 | 5735.44 | 56.26% | 0 | 6490.64 | 6490.64 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10195.2 | 9440 | -755.2 | -7.407% | 0 | 64 | 64 |  | 2019-11-13 01:00
Markham | 2022 | 454268 | 454268 - 175 ENGELHARD DR - PARK SERV/175 ENGELHARD DR - PARK SERV | 99 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Dave Lindsay | 84631.34 | 84094.17 | -537.17 | -0.6347% | 27302.46 | 25847.32 | -1455.14 | -5.33% | 30847.85 | 34878.14 | 4030.29 | 13.07% | 3292.03 | 3526 | 233.97 | 7.107% | 23189 | 19435.48 | -3753.52 | -16.19% | 152.72 | 189 | 36.28 | 23.76% | 2022-10-07 01:00
Markham | 2019 | 454270 | (WO319675) 2019 Padmount Transformer Replacement - Batch 12 | 99 | COMPLETE | Converted Project |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Steve Rumble | 41761.3 | 32266.89 | -9494.41 | -22.73% | 8896.3 | 4315.09 | -4581.21 | -51.5% | 26229 | 16407.64 | -9821.36 | -37.44% | 6636 | 625 | -6011 | -90.58% | 0 | 10919.16 | 10919.16 |  | 209 | 48 | -161 | -77.03% | 2019-10-11 01:00
Markham | 2021 | 454271 | (WO 454271) Yonge St & King Rd Temp O/H Relocation | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | Persaud, Ryan | 0 | 7191.23 | 7191.23 |  | 0 | 7191.23 | 7191.23 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-16 01:00
Markham | 2020 | 631369 | 631369 - MX - RELOC - STEELES AVE - KENNEDY TO MIDLAND | 99 | COMPLETE | Cont Est Under | Labour est. under | BOM not accurate | Vande Kuyt, Greg | No | Alectra Utilities | Shane Christopher | 4125168.39 | 5190266.02 | 1065097.63 | 25.82% | 39241.51 | 421476.64 | 382235.13 | 974.1% | 199325.8 | 495351.25 | 296025.45 | 148.5% | 760 | 5011 | 4251 | 559.3% | 3885841.08 | 4260881.19 | 375040.11 | 9.651% | 450 | 716.99 | 266.99 | 59.33% | 2020-09-15 01:00
Markham | 2019 | 631392 | (WO 631392 ) 2019 POLE REPLACEMENT PROGRAM/ REPLACE P27562 | 99 | COMPLETE | Labour est. over |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Shortt, Derek B. | 64982.28 | 35188.67 | -29793.61 | -45.85% | 28717.61 | 17805.83 | -10911.78 | -38% | 4887.97 | 11788.84 | 6900.87 | 141.2% | 5660.82 | 5594 | -66.82 | -1.18% | 25715.88 | 0 | -25715.88 | -100% | 306.02 | 213 | -93.02 | -30.4% | 2019-09-06 01:00
Markham | 2020 | 631761 | 631761 - VTS4 FEEDER INTEGRATION PART 2 - EGRESS TO KIRBY RD | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 337009.27 | 598483.97 | 261474.7 | 77.59% | 93168.54 | 40655.66 | -52512.88 | -56.36% | 158227.04 | 201071.42 | 42844.38 | 27.08% | 19059.77 | 163.98 | -18895.79 | -99.14% | 66553.92 | 356592.91 | 290038.99 | 435.8% | 801.16 | 33.5 | -767.66 | -95.82% | 2020-12-24 01:00
Markham | 2020 | 631836 | (WO631836) 78 BRADWICK DR UNIT B | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Persaud, Ryan | 0 | 758.37 | 758.37 |  | 0 | 758.37 | 758.37 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-27 01:00
Markham | 2019 | 631916 | 631916 - 2019 PCB TRANSFORMER REPLACEMENT/ REPLACE 26-24 | 99 | COMPLETE | Estimate incorrect |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Lamb, Tim | 24814.14 | 8504.95 | -16309.19 | -65.73% | 9295.6 | 3739.39 | -5556.21 | -59.77% | 9220.54 | 4015.56 | -5204.98 | -56.45% | 810.25 | 750 | -60.25 | -7.436% | 5487.75 | 0 | -5487.75 | -100% | 52 | 33.5 | -18.5 | -35.58% | 2019-11-27 01:00
Markham | 2019 | 631917 | 631917 - 2019 PCB TRANSFORMER REPLACEMENT/ REPLACE 1-186 | 99 | COMPLETE | Estimate incorrect |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Lamb, Tim | 24814.14 | 7815.12 | -16999.02 | -68.51% | 9295.6 | 3224.56 | -6071.04 | -65.31% | 9220.54 | 4015.56 | -5204.98 | -56.45% | 810.25 | 575 | -235.25 | -29.03% | 5487.75 | 0 | -5487.75 | -100% | 52 | 27 | -25 | -48.08% | 2019-12-12 01:00
Markham | 2019 | 631918 | 631918 - 2019 PCB TRANSFORMER REPLACEMENT/ REPLACE M49TP105 | 99 | COMPLETE | Estimate incorrect |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Lamb, Tim | 23345.92 | 9152.31 | -14193.61 | -60.8% | 9295.6 | 4069.86 | -5225.74 | -56.22% | 7752.32 | 4322.45 | -3429.87 | -44.24% | 810.25 | 760 | -50.25 | -6.202% | 5487.75 | 0 | -5487.75 | -100% | 52 | 37.5 | -14.5 | -27.88% | 2019-11-21 01:00
Markham | 2022 | 631939 | 631939 - 9700 9TH LINE MARKHAM | 99 | COMPLETE | BOM not accurate | Cont Est Over | Labour est. over | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 124821.53 | 66991.88 | -57829.65 | -46.33% | 30421.63 | 22303.58 | -8118.05 | -26.69% | 46577.3 | 6862.06 | -39715.24 | -85.27% | 4781.84 | 4061 | -720.84 | -15.07% | 65390.76 | 33765.24 | -31625.52 | -48.36% | 202.47 | 161.5 | -40.97 | -20.24% | 2022-02-11 01:00
Markham | 2019 | 631940 | 631940 - 31 KEYES COURT | 99 | COMPLETE | Weather |  |  | Dibratto, Susan | No | Mann, Drew | Steve Rumble | 61552.77 | 55051.21 | -6501.56 | -10.56% | 12311.89 | 14191.67 | 1879.78 | 15.27% | 25261.06 | 24652.38 | -608.68 | -2.41% | 1158.34 | 1445 | 286.66 | 24.75% | 22821.48 | 14762.16 | -8059.32 | -35.31% | 83 | 149.4 | 66.4 | 80% | 2019-12-18 01:00
Markham | 2020 | 632226 | 632226 (WO 632226) DUFFERIN ST & MAURIER BLVD PROP COM DEV | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 42475.95 | 29903.1 | -12572.85 | -29.6% | 14716.77 | 7321.45 | -7395.32 | -50.25% | 20113.51 | 18469.44 | -1644.07 | -8.174% | 1191.59 | 1917.41 | 725.82 | 60.91% | 6454.08 | 2194.8 | -4259.28 | -65.99% | 159.85 | 53 | -106.85 | -66.84% | 2020-10-29 01:00
Markham | 2022 | 632255 | (WO632255) 144 MARKHAM ROAD, UG CABLE RELOCATION | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | Persaud, Ryan | 0 | 2040.09 | 2040.09 |  | 0 | 2040.09 | 2040.09 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6 | 6 |  | 2020-10-07 01:00
Markham | 2021 | 632279 | (WO632279 ) JOINT USE PERMIT HE2019-063 - BAYVIEW PARK LANE/ SUNSET BEACH ROAD | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Martin, Shane | Persaud, Ryan | 0 | 3857.67 | 3857.67 |  | 0 | 707.67 | 707.67 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3150 | 3150 |  | 0 | 0.5 | 0.5 |  | 2020-01-14 01:00
Markham | 2020 | 632287 | 632287 - JOINT USE PERMIT #HE2019-065 - TESTON ROAD - VAUGHAN | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 20852.35 | 18456.79 | -2395.56 | -11.49% | 7152.66 | 2371.45 | -4781.21 | -66.85% | 6140.01 | 3200.09 | -2939.92 | -47.88% | 1151.5 | 0 | -1151.5 | -100% | 6408.18 | 12885.25 | 6477.07 | 101.1% | 89.87 | 6 | -83.87 | -93.32% | 2020-01-14 01:00
Markham | 2020 | 632377 | 632377 - 130 ST. JOHNS SIDEROAD | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Cranley, Stephen | No | Alectra Utilities | Steve Rumble | 61145.93 | 47843.3 | -13302.63 | -21.76% | 17522.35 | 14305.17 | -3217.18 | -18.36% | 12227.3 | 8482.44 | -3744.86 | -30.63% | 2478.2 | 1221 | -1257.2 | -50.73% | 28918.08 | 23834.69 | -5083.39 | -17.58% | 206.3 | 104.5 | -101.8 | -49.35% | 2020-04-03 01:00
Markham | 2019 | 632410 | (WO632410) 640 APPLEWOOD CRES - DEMOLITION | 99 | COMPLETE | BOM not accurate | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Steve Rumble | 6904.91 | 4109 | -2795.91 | -40.49% | 4842.06 | 3488 | -1354.06 | -27.96% | 1615.68 | 0 | -1615.68 | -100% | 447.17 | 621 | 173.83 | 38.87% | 0 | 0 | 0 |  | 20 | 34.75 | 14.75 | 73.75% | 2019-09-12 01:00
Markham | 2020 | 632468 | 632468 - 110 CITATION DR | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 40377.83 | 33787.43 | -6590.4 | -16.32% | 10523.15 | 10131.67 | -391.48 | -3.72% | 21892.45 | 21364.26 | -528.19 | -2.413% | 914.15 | 2291.5 | 1377.35 | 150.7% | 7048.08 | 0 | -7048.08 | -100% | 107.8 | 136 | 28.2 | 26.16% | 2020-01-09 01:00
Markham | 2020 | 632636 | 632636 - 700 APPLEWOOD CRES - Demolition | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Dibratto, Susan | No | Alectra Utilities | Dave Lindsay | 4722.69 | 1227.1 | -3495.59 | -74.02% | 3067.41 | 1149.1 | -1918.31 | -62.54% | 1615.68 | 0 | -1615.68 | -100% | 39.6 | 78 | 38.4 | 96.97% | 0 | 0 | 0 |  | 5 | 4 | -1 | -20% | 2020-11-04 01:00
Markham | 2022 | 632674 | 632674 - 9560, 9570 KEELE STREET, VAUGHAN, ON | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Alarcon, Alejandro | Dave Lindsay | 47186.38 | 38769.51 | -8416.87 | -17.84% | 30405.03 | 16999.93 | -13405.1 | -44.09% | 8742.43 | 13858.47 | 5116.04 | 58.52% | 4257.84 | 860 | -3397.84 | -79.8% | 3781.08 | 6239.96 | 2458.88 | 65.03% | 185.32 | 97.25 | -88.07 | -47.52% | 2022-07-18 01:00
Markham | 2020 | 632678 | 632678 - PHASE 3-OH&UG RELOC-BATHURST ST(N. OF VALLEY VISTA DR-N.OF MAJOR MACKENZIE DR) | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Steve | 2692160.93 | 2094814.21 | -597346.72 | -22.19% | 19788.61 | 157511.52 | 137722.91 | 696% | 633863.68 | 589537.62 | -44326.06 | -6.993% | 0 | 77.67 | 77.67 |  | 2038508.64 | 1347687.4 | -690821.24 | -33.89% | 11 | 215 | 204 | 1855% | 2020-10-26 01:00
Markham | 2021 | 632698 | (WO632698) 80 DONEY CRESCENT | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Diefenbaker, Trevor A | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-03-06 01:00
Markham | 2020 | 632704 | 632704 - POLE REPLACEMENT SUBDIVISION INCON PROPERTY | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Steve Rumble | 23676.88 | 24674.63 | 997.75 | 4.214% | 14743.83 | 17638.38 | 2894.55 | 19.63% | 3506.01 | 2509.54 | -996.47 | -28.42% | 1562.8 | 1914.5 | 351.7 | 22.5% | 3864.24 | 2612.21 | -1252.03 | -32.4% | 175.49 | 73 | -102.49 | -58.4% | 2020-03-06 01:00
Markham | 2021 | 632723 | 632723 - 98 AUTO VAUGHAN DR (Car Dealership) | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 50946.53 | 39875.07 | -11071.46 | -21.73% | 16115.15 | 9661.19 | -6453.96 | -40.05% | 25302.2 | 23335.57 | -1966.63 | -7.773% | 1101.42 | 1372.25 | 270.83 | 24.59% | 8427.76 | 5506.06 | -2921.7 | -34.67% | 149.46 | 77.25 | -72.21 | -48.31% | 2021-01-13 01:00
Markham | 2021 | 632726 | 632726 - 14 CEDAR AVE | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 63965.91 | 54015.12 | -9950.79 | -15.56% | 21922.38 | 14307.47 | -7614.91 | -34.74% | 27736.02 | 24543.19 | -3192.83 | -11.51% | 2904.33 | 2696.59 | -207.74 | -7.153% | 11403.18 | 12467.87 | 1064.69 | 9.337% | 149.05 | 109.5 | -39.55 | -26.53% | 2021-01-25 01:00
Markham | 2019 | 632732 | 632732 - CONNECT BELL BONDS - COSTA ROAD - VAUGHAN | 99 | COMPLETE | Labour est. under |  |  | O'Gay, Brian | No | Martin, Shane | Don Rothman | 12142.34 | 1642.48 | -10499.86 | -86.47% | 1200.16 | 1486.48 | 286.32 | 23.86% | 0 | 0 | 0 |  | 210 | 156 | -54 | -25.71% | 10732.18 | 0 | -10732.18 | -100% | 7.73 | 16 | 8.27 | 107% | 2019-10-30 01:00
Markham | 2019 | 632767 | 632767 - REPLACE P23179 | 99 | COMPLETE | Labour est. over |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Larry | 18656.66 | 13998.54 | -4658.12 | -24.97% | 12619.14 | 9935.15 | -2683.99 | -21.27% | 2163.12 | 1253.74 | -909.38 | -42.04% | 1174.4 | 2692 | 1517.6 | 129.2% | 2700 | 117.65 | -2582.35 | -95.64% | 154.45 | 109 | -45.45 | -29.43% | 2019-10-23 01:00
Markham | 2021 | 632790 | 632790 - NASHVILLE DEVELOPMENTS (BARONS EAST) - SUBD RES EDS | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 252597.11 | 246365.44 | -6231.67 | -2.467% | 42487.3 | 48145.15 | 5657.85 | 13.32% | 5295.77 | 8199.29 | 2903.52 | 54.83% | 3591.68 | 3704 | 112.32 | 3.127% | 201222.36 | 186317 | -14905.36 | -7.407% | 192.08 | 175 | -17.08 | -8.892% | 2021-11-11 01:00
Markham | 2020 | 632803 | 632803 - POLE RELOCATE - E/O BAYVIEW AND GREE LANE (REFER TO ATTACHMENT TAB) | 99 | COMPLETE | Scope – Const | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 0 | 2193.99 | 2193.99 |  | 0 | 918.99 | 918.99 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1275 | 1275 |  | 0 | 0 | 0 |  | 2020-09-24 01:00
Markham | 2021 | 632805 | 632805 - 63 ERIC T SMITH WAY | 99 | COMPLETE | Under 10% | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Dave Lindsay | 43126.47 | 47397.08 | 4270.61 | 9.903% | 10483.44 | 13983.19 | 3499.75 | 33.38% | 21405.81 | 23406.44 | 2000.63 | 9.346% | 895.14 | 1022.05 | 126.91 | 14.18% | 10342.08 | 8985.4 | -1356.68 | -13.12% | 106.35 | 60 | -46.35 | -43.58% | 2021-03-22 01:00
Markham | 2020 | 632813 | 632813 - JOINT USE PERMIT #HE2019-079 - WESTON ROAD - VAUGHAN | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 7888.89 | 6779.53 | -1109.36 | -14.06% | 3190.49 | 1183.02 | -2007.47 | -62.92% | 1032.48 | 583.27 | -449.21 | -43.51% | 263.92 | 0 | -263.92 | -100% | 3402 | 5013.24 | 1611.24 | 47.36% | 23.95 | 0 | -23.95 | -100% | 2020-02-14 01:00
Markham | 2019 | 632819 | (WO 632819) YRRTC-Y2.2 DUCTBANK RELOCATION - 10579 YONGE STREET | 99 | COMPLETE | Engineering by-passed |  |  | Lacombe, Joel | No | Lacombe, Joel | Persaud, Ryan | 0 | 16299.45 | 16299.45 |  | 0 | 4452.94 | 4452.94 |  | 0 | 0 | 0 |  | 0 | 234 | 234 |  | 0 | 11612.51 | 11612.51 |  | 0 | 58.5 | 58.5 |  | 2019-08-28 01:00
Markham | 2020 | 632839 | 632839 - 45 RODINEA RD | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Dave Lindsay | 83105.26 | 85790.5 | 2685.24 | 3.231% | 20123.7 | 17040.63 | -3083.07 | -15.32% | 45636.67 | 44025.99 | -1610.68 | -3.529% | 2217.33 | 2793.41 | 576.08 | 25.98% | 15127.56 | 21930.47 | 6802.91 | 44.97% | 218.18 | 117.8 | -100.38 | -46.01% | 2020-09-26 01:00
Markham | 2022 | 632846 | (WO632846) 1452 WELLINGTON ST AURORA | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Harris, Geoff L. | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-25 01:00
Markham | 2020 | 632876 | (WO 632876) GUY WIRE RELOCATION - JANE ST & AUTO VAUGHAN DR | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Alectra Utilities | Persaud, Ryan | 0.23 | 0 | -0.23 | -100% | 0.23 | 0 | -0.23 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-21 01:00
Markham | 2020 | 632884 | 632884 - JOINT USE PERMIT #HE2019-086 - LESLIE STREET - RICHMOND HILL | 99 | COMPLETE | Estimate incorrect | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 6352.79 | 7261.41 | 908.62 | 14.3% | 2796.8 | 3220.94 | 424.14 | 15.17% | 0 | 0 | 0 |  | 153.99 | 890.47 | 736.48 | 478.3% | 3402 | 3150 | -252 | -7.407% | 16.01 | 27.5 | 11.49 | 71.77% | 2020-08-21 01:00
Markham | 2021 | 632886 | STEGMANS MILL RD. - #357 TO #375 | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Yuen, Paul | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-02-01 01:00
Markham | 2020 | 632908 | 632908 - POLE REPLACEMENT 2020 BATCH 1 - AURORA - 12 POLES | 99 | COMPLETE | Labour est. under | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 157616.88 | 179669.02 | 22052.14 | 13.99% | 61747.54 | 85909.91 | 24162.37 | 39.13% | 55480.37 | 50831.86 | -4648.51 | -8.379% | 13687.32 | 24810 | 11122.68 | 81.26% | 26701.65 | 18117.25 | -8584.4 | -32.15% | 977.92 | 1022 | 44.08 | 4.508% | 2020-07-14 01:00
Markham | 2020 | 632909 | 632909 - POLE REPLACEMENT 2020 BATCH 3 - MARKHAM - 22 POLES | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 158711.43 | 137411.81 | -21299.62 | -13.42% | 70302.95 | 57088.32 | -13214.63 | -18.8% | 48457.91 | 45282.04 | -3175.87 | -6.554% | 15588.47 | 18774 | 3185.53 | 20.44% | 24362.1 | 16267.45 | -8094.65 | -33.23% | 1098.19 | 681 | -417.19 | -37.99% | 2020-08-14 01:00
Markham | 2020 | 632912 | 632912 - 2020 Pole Replacement Batch 2 - Markham | 99 | COMPLETE | Scope – Const | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 240046.19 | 236552.1 | -3494.09 | -1.456% | 131167.36 | 108182.08 | -22985.28 | -17.52% | 42078.52 | 75734.06 | 33655.54 | 79.98% | 21870.15 | 39723.13 | 17852.98 | 81.63% | 44930.16 | 12912.83 | -32017.33 | -71.26% | 1065.07 | 1318 | 252.93 | 23.75% | 2020-12-16 01:00
Markham | 2022 | 632925 | (WO 632925) FUTURE WORK ST. JOHNS SIDE ROAD BAYVIEW TO 404 | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Barry, Kenneth | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-05 01:00
Markham | 2020 | 633011 | 633011 - 2020 Pole Replacement Batch 4 - Markham | 99 | COMPLETE | Est. Ext. - Act. Internal | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 149517.69 | 115704.61 | -33813.08 | -22.61% | 82263.51 | 60055.45 | -22208.06 | -27% | 31213.57 | 29722.15 | -1491.42 | -4.778% | 8855.93 | 17506 | 8650.07 | 97.68% | 27184.68 | 8421.01 | -18763.67 | -69.02% | 1029.36 | 740 | -289.36 | -28.11% | 2020-03-18 01:00
Markham | 2020 | 633038 | 633038 - 2020 Padmount Transformer Replacement Batch 7 - Vaughan | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Chris Hagan | 156654.95 | 156385.09 | -269.86 | -0.1723% | 48456.05 | 9850.52 | -38605.53 | -79.67% | 88971.72 | 82068.66 | -6903.06 | -7.759% | 8133.42 | 0 | -8133.42 | -100% | 11093.76 | 64465.91 | 53372.15 | 481.1% | 759.8 | 0 | -759.8 | -100% | 2020-12-22 01:00
Markham | 2021 | 633039 | 633039 - 2020 Padmount Transformer Replacement Batch 8 - Vaughan/Markham | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 292423.45 | 222992.96 | -69430.49 | -23.74% | 59521.64 | 31546.05 | -27975.59 | -47% | 182848.23 | 173710.58 | -9137.65 | -4.997% | 9714.5 | 10180.5 | 466 | 4.797% | 40339.08 | 7555.83 | -32783.25 | -81.27% | 814.9 | 307.5 | -507.4 | -62.27% | 2021-03-30 01:00
Markham | 2020 | 633056 | V38 2019 Pre-Work Only For 2020 Injection | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 184554.6 | -467.71 | -185022.31 | -100.3% | 144511.02 | -467.71 | -144978.73 | -100.3% | 23012.17 | 0 | -23012.17 | -100% | 17031.41 | 0 | -17031.41 | -100% | 0 | 0 | 0 |  | 1342 | 0 | -1342 | -100% | 2021-10-01 01:00
Markham | 2020 | 633110 | 633110 - Replace 37TV143 & 37TV115 | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 51402.56 | 0 | -51402.56 | -100% | 15356.48 | 0 | -15356.48 | -100% | 33288.08 | 0 | -33288.08 | -100% | 2758 | 0 | -2758 | -100% | 0 | 0 | 0 |  | 190 | 0 | -190 | -100% | 2020-11-17 01:00
Markham | 2020 | 633111 | 633111 - Replace 37TV133 & 37TV162 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 96472.51 | 69473.3 | -26999.21 | -27.99% | 18264.1 | 13238.74 | -5025.36 | -27.51% | 36555.81 | 21809.37 | -14746.44 | -40.34% | 3365 | 1918.13 | -1446.87 | -43% | 38287.6 | 32507.06 | -5780.54 | -15.1% | 233 | 64 | -169 | -72.53% | 2020-11-17 01:00
Markham | 2020 | 633112 | 633112 - 2020 Switch Replacements - Replace 25TV002 & 21TV010 | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 51391.5 | 28638.35 | -22753.15 | -44.27% | 15356.48 | 9219.51 | -6136.97 | -39.96% | 33277.02 | 17847.37 | -15429.65 | -46.37% | 2758 | 1571.47 | -1186.53 | -43.02% | 0 | 0 | 0 |  | 190 | 55 | -135 | -71.05% | 2020-11-03 01:00
Markham | 2021 | 633125 | 633125 - CEDARTRAIL SUBDIVISION/INSPECT AND CONNECT | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 137391.02 | 132561.29 | -4829.73 | -3.515% | 23388.58 | 26736.79 | 3348.21 | 14.32% | 1395.67 | 1198.89 | -196.78 | -14.1% | 1006.05 | 2122.34 | 1116.29 | 111% | 111600.72 | 99879.4 | -11721.32 | -10.5% | 119.32 | 113.25 | -6.07 | -5.087% | 2021-02-17 01:00
Markham | 2020 | 633126 | 633126 - TRANSFORMER REPLACEMENT 2020 BATCH 9 - VAUGHAN - 11 UNITS | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 307708.34 | 253084.46 | -54623.88 | -17.75% | 37862.61 | 25007.73 | -12854.88 | -33.95% | 215202.29 | 212993.27 | -2209.02 | -1.026% | 4805.64 | 5412.06 | 606.42 | 12.62% | 56810.16 | 9671.4 | -47138.76 | -82.98% | 449.4 | 225.5 | -223.9 | -49.82% | 2020-10-21 01:00
Markham | 2021 | 633127 | 633127 - TRANSFORMER REPLACEMENT 2020 BATCH 10 - VAUGHAN - 30 UNITS | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Tenorlas, Reynaldo | Yes | Murray, Jake R - vacancy | Dave Lindsay | 353619.34 | 236068.83 | -117550.51 | -33.24% | 122787.02 | 48144.14 | -74642.88 | -60.79% | 114322.33 | 151947.25 | 37624.92 | 32.91% | 16476.07 | 15658.86 | -817.21 | -4.96% | 100033.92 | 20318.58 | -79715.34 | -79.69% | 1861.6 | 481.5 | -1380.1 | -74.14% | 2021-12-07 01:00
Markham | 2020 | 633128 | 633128 - TRANSFORMER REPLACEMENT 2020 BATCH 11 - VAUGHAN - 23 UNITS | 99 | COMPLETE | Civil contractor | Labour est. over | BOM not accurate | Tenorlas, Reynaldo | No | Alectra Utilities | Chris Hagan | 395325.49 | 338473.99 | -56851.5 | -14.38% | 72057.45 | 26413.4 | -45644.05 | -63.34% | 233125.95 | 186230.99 | -46894.96 | -20.12% | 11431.05 | 5742.89 | -5688.16 | -49.76% | 85241.74 | 120086.71 | 34844.97 | 40.88% | 1141.4 | 137 | -1004.4 | -88% | 2020-12-22 01:00
Markham | 2021 | 633130 | 633130 - DISTRIBUTION AUTOMATION 2020 - A10SL2026 - AURORA, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Larry | 130788.23 | 140571.45 | 9783.22 | 7.48% | 12270.27 | 12825.36 | 555.09 | 4.524% | 73302.42 | 82505.77 | 9203.35 | 12.56% | 3926.54 | 472.13 | -3454.41 | -87.98% | 41289 | 44768.19 | 3479.19 | 8.426% | 157.2 | 38.5 | -118.7 | -75.51% | 2021-08-09 01:00
Markham | 2021 | 633131 | 633131 - DISTRIBUTION AUTOMATION 2021 - A10SL2035 - AURORA, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 148066.27 | 170901.05 | 22834.78 | 15.42% | 2391.74 | 13769.13 | 11377.39 | 475.7% | 79695.69 | 98528.09 | 18832.4 | 23.63% | 0 | 133.06 | 133.06 |  | 65978.84 | 55731.97 | -10246.87 | -15.53% | 8 | 31.5 | 23.5 | 293.8% | 2021-07-19 01:00
Markham | 2021 | 633132 | 633132 - DISTRIBUTION AUTOMATION 2021 - A06SL2042 - AURORA, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 161834.27 | 159753.67 | -2080.6 | -1.286% | 3940.81 | 14990.31 | 11049.5 | 280.4% | 83049.55 | 89752.79 | 6703.24 | 8.071% | 0 | 0 | 0 |  | 74843.91 | 52262.76 | -22581.15 | -30.17% | 7 | 47 | 40 | 571.4% | 2021-10-01 01:00
Markham | 2021 | 633134 | 633134 - DISTRIBUTION AUTOMATION 2021 - A06SL2024 - AURORA, 1 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 136087.26 | 169052.8 | 32965.54 | 24.22% | 2330.9 | 15068.51 | 12737.61 | 546.5% | 76149.19 | 81526.17 | 5376.98 | 7.061% | 0 | 0 | 0 |  | 57607.17 | 69719.32 | 12112.15 | 21.03% | 0 | 21 | 21 |  | 2021-10-01 01:00
Markham | 2020 | 633135 | 633135 - DISTRIBUTION AUTOMATION 2020 - A06SL2046 - AURORA | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Macdonald, Steve | 118516.02 | 133873.25 | 15357.23 | 12.96% | 22600.22 | 10268.56 | -12331.66 | -54.56% | 75652.75 | 84376.19 | 8723.44 | 11.53% | 4566.6 | 448.79 | -4117.81 | -90.17% | 15696.45 | 38779.71 | 23083.26 | 147.1% | 328.11 | 49.5 | -278.61 | -84.91% | 2020-08-24 01:00
Markham | 2021 | 633136 | (WO 633136) DISTRIBUTION AUTOMATION 2020 - 27S15 - RICHMOND HILL | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Roy, James | Persaud, Ryan | 120170.1 | 16558.39 | -103611.71 | -86.22% | 30794.08 | 4813.97 | -25980.11 | -84.37% | 64356.3 | 0 | -64356.3 | -100% | 6080.3 | 0 | -6080.3 | -100% | 18939.42 | 11744.42 | -7195 | -37.99% | 248.51 | 0 | -248.51 | -100% | 2020-06-29 01:00
Markham | 2020 | 633137 | 633137 - DISTRIBUTION AUTOMATION 2020 - NEW SWITCH - MARKHAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Macdonald, Larry | 67280.61 | 93693.65 | 26413.04 | 39.26% | 17540.77 | 12820.66 | -4720.11 | -26.91% | 47145.64 | 54513.02 | 7367.38 | 15.63% | 2594.2 | 1357.87 | -1236.33 | -47.66% | 0 | 25002.1 | 25002.1 |  | 227.11 | 102 | -125.11 | -55.09% | 2020-06-29 01:00
Markham | 2020 | 633138 | 633138 - DISTRIBUTION AUTOMATION 2020 - V25SL3013 - VAUGHAN | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Macdonald, Steve | 86092.5 | 102625.22 | 16532.72 | 19.2% | 18687.62 | 18710.05 | 22.43 | 0.12% | 52267.96 | 55333.99 | 3066.03 | 5.866% | 3414.6 | 0 | -3414.6 | -100% | 11722.32 | 28581.18 | 16858.86 | 143.8% | 254.45 | 184 | -70.45 | -27.69% | 2020-09-12 01:00
Markham | 2020 | 633139 | 633139 - DISTRIBUTION AUTOMATION 2020 - V25SL3025 - VAUGHAN | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Macdonald, Steve | 79535.23 | 99689.98 | 20154.75 | 25.34% | 16688.85 | 9483.11 | -7205.74 | -43.18% | 50087.74 | 56573.48 | 6485.74 | 12.95% | 2738.4 | 0 | -2738.4 | -100% | 10020.24 | 33633.39 | 23613.15 | 235.7% | 216.75 | 59 | -157.75 | -72.78% | 2020-11-27 01:00
Markham | 2021 | 633140 | (WO 633140) DISTRIBUTION AUTOMATION 2020 - 57SP13 - VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Wong, Henry | 0 | 2773.04 | 2773.04 |  | 0 | 2773.04 | 2773.04 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-10 01:00
Markham | 2021 | 633141 | (WO 633141) DISTRIBUTION AUTOMATION 2020 - 57SP17 - VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Wong, Henry | 0 | 2911.24 | 2911.24 |  | 0 | 2911.24 | 2911.24 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-10 01:00
Markham | 2020 | 633144 | 633144 - 2021 Padmount Transformer Replacement Batch 12 - Vaughan - 11 units | 99 | COMPLETE | Labour est. over | Scope – Eng | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Steve Rumble | 288145.77 | 209074.61 | -79071.16 | -27.44% | 50256.38 | 22388.93 | -27867.45 | -55.45% | 177830.57 | 175033.38 | -2797.19 | -1.573% | 6989.46 | 7465.4 | 475.94 | 6.809% | 62523.36 | 4186.9 | -58336.46 | -93.3% | 647.1 | 203.5 | -443.6 | -68.55% | 2020-09-10 01:00
Markham | 2020 | 633145 | 633145 - DISTRIBUTION AUTOMATION 2020 - 66-L6 - VAUGHAN | 99 | COMPLETE | Inaccurate material return | N/A | N/A | Tenorlas, Reynaldo | yes | Alectra Utilities | Macdonald, Larry | 83413.13 | 64231.03 | -19182.1 | -23% | 20557.38 | 28217.17 | 7659.79 | 37.26% | 49624.55 | 15435.62 | -34188.93 | -68.9% | 4134.9 | 7924.26 | 3789.36 | 91.64% | 9096.3 | 12653.98 | 3557.68 | 39.11% | 289.09 | 301 | 11.91 | 4.12% | 2020-09-24 01:00
Markham | 2019 | 633158 | 633158 - 100 BULLOCK DR | 99 | COMPLETE | Labour est. over | Cont Est Over |  | Dibratto, Susan | No | Mann, Drew | Steve Rumble | 63629.37 | 31961.65 | -31667.72 | -49.77% | 13021.27 | 7011.46 | -6009.81 | -46.15% | 25020.25 | 7972.55 | -17047.7 | -68.14% | 1409.89 | 1894.5 | 484.61 | 34.37% | 24177.96 | 15083.14 | -9094.82 | -37.62% | 80 | 87.99 | 7.99 | 9.987% | 2019-10-24 01:00
Markham | 2020 | 633162 | (WO 633162) Replace 2 poles at Yonge and John St. Markham | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-09 01:00
Markham | 2020 | 633163 | (WO 633163) Replace P30260 at Yonge St and Morgan Ave. Markham | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-09 01:00
Markham | 2019 | 633164 | 633164 - M44 Cochrane 44C-004 to M38FA1006 | 99 | COMPLETE | Cont Est Over |  |  | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 687740.72 | 617867.72 | -69873 | -10.16% | 28570.04 | 63673.78 | 35103.74 | 122.9% | 3785.43 | 4126.88 | 341.45 | 9.02% | 2390.25 | 1543.5 | -846.75 | -35.43% | 652995 | 548523.56 | -104471.44 | -16% | 203.35 | 254 | 50.65 | 24.91% | 2019-11-09 01:00
Markham | 2020 | 633166 | 633166 - 670 APPLEWOOD CRES | 99 | COMPLETE | Cont Est Over | BOM not accurate | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 85268.08 | 70570.95 | -14697.13 | -17.24% | 14151.58 | 12472.9 | -1678.68 | -11.86% | 53768.52 | 47934.15 | -5834.37 | -10.85% | 1420.14 | 1545.5 | 125.36 | 8.827% | 15927.84 | 8618.4 | -7309.44 | -45.89% | 134.15 | 129.8 | -4.35 | -3.243% | 2020-11-04 01:00
Markham | 2021 | 633197 | ALECTRA U/G RELOCATIONS - STEELCASE RD WEST X JOHN ST. | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | Persaud, Ryan | 0 | 6098.58 | 6098.58 |  | 0 | 5892.91 | 5892.91 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 205.67 | 205.67 |  | 0 | 79.5 | 79.5 |  | 2019-10-30 01:00
Markham | 2020 | 633330 | 633330 - SWITCHGEAR REPLACEMENT 2020 - BATCH 1 | 99 | COMPLETE | BOM cost variance | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 235551.64 | 279558.87 | 44007.23 | 18.68% | 24693.81 | 13148.94 | -11544.87 | -46.75% | 188806.8 | 244784.72 | 55977.92 | 29.65% | 2441.47 | 3816.85 | 1375.38 | 56.33% | 19609.56 | 17808.36 | -1801.2 | -9.185% | 268.9 | 128.5 | -140.4 | -52.21% | 2020-06-26 01:00
Markham | 2020 | 633331 | 633331 - SWITCHGEAR REPLACEMENT 2020 - BATCH 2 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 141719.64 | 141376.38 | -343.26 | -0.2422% | 17439.13 | 14193.73 | -3245.4 | -18.61% | 122670.66 | 124909.95 | 2239.29 | 1.825% | 1609.85 | 2272.7 | 662.85 | 41.17% | 0 | 0 | 0 |  | 177 | 108 | -69 | -38.98% | 2020-10-03 01:00
Markham | 2020 | 633332 | 633332 - SWITCHGEAR REPLACEMENT 2020 - BATCH 4 | 99 | COMPLETE | BOM cost variance | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 476514.91 | 415346.82 | -61168.09 | -12.84% | 46301.76 | 39334.61 | -6967.15 | -15.05% | 377679.69 | 325349.17 | -52330.52 | -13.86% | 4938.94 | 8260.85 | 3321.91 | 67.26% | 47594.52 | 42402.19 | -5192.33 | -10.91% | 308.68 | 334 | 25.32 | 8.203% | 2020-12-08 01:00
Markham | 2020 | 633333 | 633333 - SWITCHGEAR REPLACEMENT 2020 - BATCH 5 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 66110.21 | 66758.4 | 648.19 | 0.9805% | 15961.49 | 17573.79 | 1612.3 | 10.1% | 48538.87 | 46106.39 | -2432.48 | -5.011% | 1609.85 | 3078.22 | 1468.37 | 91.21% | 0 | 0 | 0 |  | 100.2 | 165 | 64.8 | 64.67% | 2020-07-14 01:00
Markham | 2020 | 633334 | 633334 - SWITCHGEAR REPLACEMENT 2020 - BATCH 7 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 383896.99 | 381490.52 | -2406.47 | -0.6269% | 51438.3 | 35180.27 | -16258.03 | -31.61% | 306729.99 | 317454.73 | 10724.74 | 3.496% | 6110.5 | 9778.38 | 3667.88 | 60.03% | 19618.2 | 19077.14 | -541.06 | -2.758% | 623 | 316 | -307 | -49.28% | 2020-11-30 01:00
Markham | 2020 | 633337 | 633337 - SWITCHGEAR REPLACEMENT 2020 - BATCH 3 - REPLACE 4 SWGS | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 277402.32 | 262438.19 | -14964.13 | -5.394% | 27313.5 | 16439.35 | -10874.15 | -39.81% | 217787.97 | 240952.14 | 23164.17 | 10.64% | 2955.09 | 5046.7 | 2091.61 | 70.78% | 29345.76 | 0 | -29345.76 | -100% | 171.48 | 167 | -4.48 | -2.613% | 2020-06-25 01:00
Markham | 2020 | 633338 | 633338 - SWITCHGEAR REPLACEMENT 2020 - BATCH 6 - REPLACE 4 SWGS | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 307183.99 | 232568.79 | -74615.2 | -24.29% | 32551.57 | 17391.94 | -15159.63 | -46.57% | 246207.22 | 192205.9 | -54001.32 | -21.93% | 3664.04 | 4270.67 | 606.63 | 16.56% | 24761.16 | 18700.28 | -6060.88 | -24.48% | 366.8 | 133 | -233.8 | -63.74% | 2020-06-25 01:00
Markham | 2020 | 633339 | 633339 - SWITCHGEAR REPLACEMENT 2020 - BATCH 8 - REPLACE 2 SWGS | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 141785.22 | 131094.6 | -10690.62 | -7.54% | 20431.32 | 12548.69 | -7882.63 | -38.58% | 108860.66 | 116186.9 | 7326.24 | 6.73% | 1693.24 | 2359.01 | 665.77 | 39.32% | 10800 | 0 | -10800 | -100% | 111.28 | 117 | 5.72 | 5.14% | 2020-06-30 01:00
Markham | 2020 | 633340 | 633340 - SWITCHGEAR REPLACEMENT 2020 - BATCH 9 - REPLACE 5 SWGS - DEFERRED UNITS | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 184388.12 | 185665.51 | 1277.39 | 0.6928% | 13783.44 | 20303.48 | 6520.04 | 47.3% | 156662.6 | 159645.75 | 2983.15 | 1.904% | 2062.08 | 5716.28 | 3654.2 | 177.2% | 11880 | 0 | -11880 | -100% | 122.26 | 237.5 | 115.24 | 94.26% | 2020-06-25 01:00
Markham | 2020 | 633385 | 633385 - CABLE REPLACEMENT, M15 LARKIN - 15TP124 TO 15TP181 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 223029.72 | 220533.69 | -2496.03 | -1.119% | 11485.27 | 23606.03 | 12120.76 | 105.5% | 410.27 | 0 | -410.27 | -100% | 813.9 | 129.46 | -684.44 | -84.09% | 210320.28 | 196798.2 | -13522.08 | -6.429% | 129 | 65 | -64 | -49.61% | 2020-10-21 01:00
Markham | 2020 | 633386 | 633386 - CABLE REPLACEMENT, V08 DUFFERIN ST - 8-P42 TO V08SP3021 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 233159.83 | 247057.98 | 13898.15 | 5.961% | 68600.51 | 35952.41 | -32648.1 | -47.59% | 3749.28 | 13673.78 | 9924.5 | 264.7% | 1459.28 | 2239.62 | 780.34 | 53.47% | 159350.76 | 195192.17 | 35841.41 | 22.49% | 241.04 | 167 | -74.04 | -30.72% | 2020-12-18 01:00
Markham | 2020 | 633387 | 633387 - CABLE REPLACEMENT, M20 WIGNALL CRES - 20SW012 TO 20SU001-5 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 86502.08 | 86940.67 | 438.59 | 0.507% | 12054.01 | 16557.88 | 4503.87 | 37.36% | 1395.37 | 1137.91 | -257.46 | -18.45% | 1237.02 | 2114.48 | 877.46 | 70.93% | 71815.68 | 67130.4 | -4685.28 | -6.524% | 139.8467 | 96.5 | -43.3467 | -31% | 2020-10-21 01:00
Markham | 2020 | 633388 | 633388 - CABLE REPLACEMENT, M33 CARLTON RD - 33TP002 TO 33TP003 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 106494.3 | 97201.52 | -9292.78 | -8.726% | 9852.73 | 13252.36 | 3399.63 | 34.5% | 410.27 | 0 | -410.27 | -100% | 645.9 | 129.46 | -516.44 | -79.96% | 95585.4 | 83819.7 | -11765.7 | -12.31% | 100 | 46 | -54 | -54% | 2020-10-21 01:00
Markham | 2020 | 633389 | 633389 - CABLE REPLACEMENT, M51 DALMENY RD - SECONDARY CABLE REPLACEMENT | 99 | COMPLETE | Civil contractor | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 205695.16 | 163301.41 | -42393.75 | -20.61% | 13779.13 | 21664.59 | 7885.46 | 57.23% | 1065.96 | 1239.83 | 173.87 | 16.31% | 1348.95 | 1035.66 | -313.29 | -23.22% | 189501.12 | 139361.33 | -50139.79 | -26.46% | 166.05 | 86 | -80.05 | -48.21% | 2020-11-13 01:00
Markham | 2020 | 633392 | 633392 - TRANSFORMER REPLACEMENT 2020 - REPLACE 2 PCB TXS ON M40 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 29686.65 | 28095.83 | -1590.82 | -5.359% | 7733.87 | 6283.73 | -1450.14 | -18.75% | 11044.48 | 10856.29 | -188.19 | -1.704% | 946.38 | 1570.75 | 624.37 | 65.97% | 9961.92 | 9385.06 | -576.86 | -5.791% | 92.2 | 40.5 | -51.7 | -56.07% | 2020-09-07 01:00
Markham | 2021 | 633440 | 633440 - DISTRIBUTION AUTOMATION 2021 - A09SL2015 - AURORA, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 144879.57 | 162892.83 | 18013.26 | 12.43% | 3777.39 | 13863.9 | 10086.51 | 267% | 12856.81 | 89318.24 | 76461.43 | 594.7% | 0 | 0 | 0 |  | 128245.37 | 59710.69 | -68534.68 | -53.44% | 20 | 30 | 10 | 50% | 2021-09-17 01:00
Markham | 2020 | 633441 | 633441 - DISTRIBUTION AUTOMATION 2020 - A07SL2004 - AURORA | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | yes | Alectra Utilities | Macdonald, Steve | 58157.31 | 96058.98 | 37901.67 | 65.17% | 21235.96 | 11369.47 | -9866.49 | -46.46% | 27788.15 | 37952.12 | 10163.97 | 36.58% | 3517.2 | 0 | -3517.2 | -100% | 5616 | 46737.39 | 41121.39 | 732.2% | 287.28 | 52.5 | -234.78 | -81.73% | 2020-12-24 01:00
Markham | 2020 | 633442 | 633442 - DISTRIBUTION AUTOMATION 2020 - A10SL2037 - AURORA | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | yes | Alectra Utilities | Macdonald, Steve | 104020.34 | 120390.62 | 16370.28 | 15.74% | 22928.88 | 9619.48 | -13309.4 | -58.05% | 75378.41 | 69774.32 | -5604.09 | -7.435% | 5713.05 | 0 | -5713.05 | -100% | 0 | 40996.82 | 40996.82 |  | 321.37 | 42 | -279.37 | -86.93% | 2020-09-30 01:00
Markham | 2020 | 633443 | 633443 - DISTRIBUTION AUTOMATION 2020 - V31SL3012 - VAUGHAN | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | yes | Alectra Utilities | Macdonald, Steve | 84230.98 | 91576.65 | 7345.67 | 8.721% | 18248.87 | 7122.06 | -11126.81 | -60.97% | 54277.87 | 60516.38 | 6238.51 | 11.49% | 3304 | 0 | -3304 | -100% | 8400.24 | 23938.21 | 15537.97 | 185% | 286 | 24 | -262 | -91.61% | 2020-12-24 01:00
Markham | 2021 | 633456 | 633456 - HATPIN CONDOMINIUM DEVELOPMENT/ INSPECT & CONNECT | 99 | COMPLETE | Cont Est Over | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 103749.13 | 76353.88 | -27395.25 | -26.41% | 20486.78 | 20297.54 | -189.24 | -0.9237% | 5019.36 | 6152.54 | 1133.18 | 22.58% | 1826.51 | 2344.38 | 517.87 | 28.35% | 76416.48 | 46094.35 | -30322.13 | -39.68% | 99.82 | 108 | 8.18 | 8.195% | 2021-07-21 01:00
Markham | 2020 | 633481 | 633481 - POLE REPLACEMENT 2020 BATCH 11 - AURORA - 15 POLES | 99 | COMPLETE | Labour est. under | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 125166.55 | 158230.27 | 33063.72 | 26.42% | 54111.8 | 64661.08 | 10549.28 | 19.5% | 39094.6 | 42587.16 | 3492.56 | 8.934% | 11078.35 | 30233.43 | 19155.08 | 172.9% | 20881.8 | 20748.6 | -133.2 | -0.6379% | 820.03 | 714 | -106.03 | -12.93% | 2020-10-02 01:00
Markham | 2020 | 633482 | 633482 - POLE REPLACEMENT 2020 BATCH 6 - MARKHAM - 26 POLES | 99 | COMPLETE | Safety | Weather | Material Req incorrectly | Tenorlas, Reynaldo | No | Alectra Utilities | Ryan Walsh | 247047.75 | 436814.51 | 189766.76 | 76.81% | 100562.91 | 191628.65 | 91065.74 | 90.56% | 80750.8 | 83457.44 | 2706.64 | 3.352% | 24424.04 | 57944 | 33519.96 | 137.2% | 41310 | 103784.42 | 62474.42 | 151.2% | 1611.74 | 2171.49 | 559.75 | 34.73% | 2020-09-17 01:00
Markham | 2020 | 633511 | 633511 - JOINT USE PERMIT HE2019-097- WESTON RD. MAJOR MACK TO DAVOS | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 10584.84 | 5942.21 | -4642.63 | -43.86% | 5936.84 | 2077.21 | -3859.63 | -65.01% | 0 | 0 | 0 |  | 760 | 265 | -495 | -65.13% | 3888 | 3600 | -288 | -7.407% | 67.16 | 10 | -57.16 | -85.11% | 2020-10-01 01:00
Markham | 2020 | 633518 | 633518 - POLE REPLACEMENT 2020 - BATCH 7 - VAUGHAN - 17 POLES | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-07 01:00
Markham | 2020 | 633519 | 633519 - SWITCHGEAR REPLACEMENT 2020 - BATCH 10 - 2 DEFERRED UNITS | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 126919.39 | 130294.01 | 3374.62 | 2.659% | 15961.49 | 11276.97 | -4684.52 | -29.35% | 109348.05 | 114023.94 | 4675.89 | 4.276% | 1609.85 | 2114.48 | 504.63 | 31.35% | 0 | 2878.62 | 2878.62 |  | 128.86 | 96.5 | -32.36 | -25.11% | 2020-07-07 01:00
Markham | 2020 | 633546 | 633546 - POLE REPLACEMENT 2020 BATCH 5 - MARKHAM - 14 POLES | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Ryan Walsh | 224484.56 | 178113.33 | -46371.23 | -20.66% | 135567.81 | 68357.39 | -67210.42 | -49.58% | 26628.29 | 45553.89 | 18925.6 | 71.07% | 9693.54 | 32890.91 | 23197.37 | 239.3% | 52594.92 | 30928.01 | -21666.91 | -41.2% | 1446.21 | 777.5 | -668.71 | -46.24% | 2020-07-21 01:00
Markham | 2020 | 633547 | 633547 - POLE REPLACEMENT 2020 BATCH 9 - VAUGHAN - 12 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Ryan Walsh | 160755.2 | 172353.5 | 11598.3 | 7.215% | 77216.73 | 84248.44 | 7031.71 | 9.106% | 30089.45 | 47809.61 | 17720.16 | 58.89% | 5646.06 | 24921 | 19274.94 | 341.4% | 47802.96 | 15374.45 | -32428.51 | -67.84% | 918.38 | 1014 | 95.62 | 10.41% | 2020-07-21 01:00
Markham | 2021 | 633585 | 633585 - GREEN LANE - #1 | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Dibratto, Susan | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-01 01:00
Markham | 2020 | 633607 | 633607 - POLE REPLACEMENT 2020 - BATCH 7 - VAUGHAN | 99 | COMPLETE | Labour est. under | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Larry | 114154 | 138381.75 | 24227.75 | 21.22% | 45597.87 | 65911.28 | 20313.41 | 44.55% | 28441.59 | 34247.53 | 5805.94 | 20.41% | 10038.7 | 24067.64 | 14028.94 | 139.7% | 30075.84 | 14155.3 | -15920.54 | -52.93% | 673.32 | 777.5 | 104.18 | 15.47% | 2020-12-22 01:00
Markham | 2020 | 633608 | 633608 - POLE REPLACEMENT 2020 - BATCH 8 - VAUGHAN | 99 | COMPLETE | Labour est. under | Estimate incorrect | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 166986.64 | 254412.34 | 87425.7 | 52.35% | 60888.37 | 114969.63 | 54081.26 | 88.82% | 58106.55 | 68301.83 | 10195.28 | 17.55% | 47991.72 | 40792.15 | -7199.57 | -15% | 0 | 30348.73 | 30348.73 |  | 941.98 | 1314 | 372.02 | 39.49% | 2020-11-20 01:00
Markham | 2020 | 633609 | 633609 - POLE REPLACEMENT 2020 - BATCH 10 - VAUGHAN | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 292043.75 | 305096.29 | 13052.54 | 4.469% | 70837.01 | 16620.3 | -54216.71 | -76.54% | 155894.08 | 111530.3 | -44363.78 | -28.46% | 65312.66 | 0 | -65312.66 | -100% | 0 | 176945.69 | 176945.69 |  | 1223.2567 | 4 | -1219.2567 | -99.67% | 2020-11-27 01:00
Markham | 2020 | 633610 | 633610 - TRANSFORMER REPLACEMENT 2020 - BATCH 13 - VAUGHAN | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 267170.54 | 178972.81 | -88197.73 | -33.01% | 73122 | 32458.72 | -40663.28 | -55.61% | 129319.92 | 86973.58 | -42346.34 | -32.75% | 10091.42 | 9666.18 | -425.24 | -4.214% | 54637.2 | 49874.33 | -4762.87 | -8.717% | 1125.8 | 336 | -789.8 | -70.15% | 2020-06-25 01:00
Markham | 2020 | 633611 | 633611 - TRANSFORMER REPLACEMENT 2020 - BATCH 14 - VAUGHAN | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Chris Hagan | 360970.61 | 261889.52 | -99081.09 | -27.45% | 90026.68 | 14756.07 | -75270.61 | -83.61% | 227283.91 | 158685.8 | -68598.11 | -30.18% | 7836.42 | 1216.18 | -6620.24 | -84.48% | 35823.6 | 87231.47 | 51407.87 | 143.5% | 1051.15 | 47 | -1004.15 | -95.53% | 2020-12-03 01:00
Markham | 2020 | 633668 | 633668 - 11 HANSON COURT / ICI PADMOUNT TX INSTALLATION | 99 | COMPLETE | Cont Est Over | BOM not accurate | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 40255 | 32122.26 | -8132.74 | -20.2% | 9459.81 | 8991.55 | -468.26 | -4.95% | 8155.51 | 5706.92 | -2448.59 | -30.02% | 926.28 | 720 | -206.28 | -22.27% | 21713.4 | 16703.79 | -5009.61 | -23.07% | 94.25 | 123.5 | 29.25 | 31.03% | 2020-01-08 01:00
Markham | 2019 | 633680 | 633680 - BONDING REQUEST LOCATED ON P54405, WESTON ROAD SOUTH OF HWY 7 | 99 | COMPLETE | Engineering by-passed |  |  | O'Gay, Brian | No | Martin, Shane | Persaud, Ryan | 0 | 711.62 | 711.62 |  | 0 | 614.12 | 614.12 |  | 0 | 0 | 0 |  | 0 | 97.5 | 97.5 |  | 0 | 0 | 0 |  | 0 | 5 | 5 |  | 2019-11-15 01:00
Markham | 2019 | 633681 | BONDING REQUEST LOCATED ON P54172, HWY 7 | 99 | COMPLETE | Engineering by-passed |  |  | O'Gay, Brian | No | Martin, Shane | Don Rothman | 0 | 894.63 | 894.63 |  | 0 | 777.63 | 777.63 |  | 0 | 0 | 0 |  | 0 | 117 | 117 |  | 0 | 0 | 0 |  | 0 | 6 | 6 |  | 2019-11-29 01:00
Markham | 2021 | 633700 | 633700 - PARENT W.O INSPECT/CONNECT/I&C-"NEW SUBDIVISION BLOCK 3- ARNOLD" | 99 | CANCELLED | N/A |  |  | D'Onofrio, Tony | No | Alarcon, Alejandro | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-15 01:00
Markham | 2021 | 633703 | 633703 - POLE RELOCATION BLOCK 3- ARNOLD | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Dave Lindsay | 224485.77 | 232783.02 | 8297.25 | 3.696% | 62628.05 | 57420.52 | -5207.53 | -8.315% | 22292.04 | 19304.87 | -2987.17 | -13.4% | 7843.48 | 9046.5 | 1203.02 | 15.34% | 131722.2 | 147011.13 | 15288.93 | 11.61% | 311.93 | 314 | 2.07 | 0.6636% | 2021-07-15 01:00
Markham | 2020 | 633826 | 633826 - 10 GATINEAU DR - TEMPORARY POWER | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 59102.75 | 48351.59 | -10751.16 | -18.19% | 13845.23 | 7914.94 | -5930.29 | -42.83% | 25401.42 | 26771.65 | 1370.23 | 5.394% | 1374.06 | 745.5 | -628.56 | -45.74% | 18482.04 | 12919.5 | -5562.54 | -30.1% | 153.35 | 56.5 | -96.85 | -63.16% | 2020-03-25 01:00
Markham | 2019 | 633843 | 633843 - POLE REPLACEMENT 2019 - P31527 - EMERGENCY REPLACEMENT | 99 | COMPLETE | Under 10% |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Larry | 19056.73 | 18775.63 | -281.1 | -1.475% | 10465.5 | 11565.84 | 1100.34 | 10.51% | 5390.25 | 3019.79 | -2370.46 | -43.98% | 3200.98 | 3060 | -140.98 | -4.404% | 0 | 1130 | 1130 |  | 145.66 | 121 | -24.66 | -16.93% | 2019-12-12 01:00
Markham | 2020 | 633869 | 633869 - POLE REPLACEMENT 2020 - MARKHAM - REPLACE 1 AND REMOVE 2 POLES | 99 | COMPLETE | BOM not accurate | Labour est. under | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 29044.28 | 67654.55 | 38610.27 | 132.9% | 13580.92 | 26403.08 | 12822.16 | 94.41% | 11568.46 | 22868.11 | 11299.65 | 97.68% | 1842.9 | 10032.26 | 8189.36 | 444.4% | 2052 | 8351.1 | 6299.1 | 307% | 168.69 | 295.5 | 126.81 | 75.17% | 2020-12-21 01:00
Markham | 2020 | 633870 | 633870 - POLE REPLACEMENT 2020 - REPLACE P23368 - AHORN GROVE, MARKHAM | 99 | COMPLETE | Labour est. under | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 16827.45 | 21463.79 | 4636.34 | 27.55% | 11326.69 | 12167.3 | 840.61 | 7.421% | 2787.96 | 2388.49 | -399.47 | -14.33% | 1308.8 | 2612 | 1303.2 | 99.57% | 1404 | 4296 | 2892 | 206% | 131.38 | 127 | -4.38 | -3.334% | 2020-07-21 01:00
Markham | 2020 | 633871 | 633871 - CABLE REPLACEMENT - 269 BAY THORN DR | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-19 01:00
Markham | 2020 | 633885 | 633885 - 919 CLARK AVE / ICI PAD TX INSTALLATION | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 68426.2 | 51226.29 | -17199.91 | -25.14% | 19961.17 | 13135.62 | -6825.55 | -34.19% | 24957.29 | 24403.12 | -554.17 | -2.22% | 1832.14 | 1438.5 | -393.64 | -21.49% | 21675.6 | 12249.05 | -9426.55 | -43.49% | 203.4 | 102.5 | -100.9 | -49.61% | 2020-11-23 01:00
Markham | 2020 | 633943 | (WO 633943) DUCT BANK LOWERING - JANE ST, NORTH OF BASS PRO MILLS DRIVE | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 2 | 2 |  | 2020-02-27 01:00
Markham | 2020 | 633950 | 633950 - POLE RELOCATION - HIGHWAY 50 SOUTH OF TRADE VALLEY DRIVE | 99 | COMPLETE | Labour est. over | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Larry | 34798.98 | 18323.95 | -16475.03 | -47.34% | 18719.07 | 9163.95 | -9555.12 | -51.04% | 6523.09 | 4011.65 | -2511.44 | -38.5% | 3304.7 | 2819.3 | -485.4 | -14.69% | 6252.12 | 2329.05 | -3923.07 | -62.75% | 205.46 | 77 | -128.46 | -62.52% | 2020-02-27 01:00
Markham | 2020 | 633952 | 633952 - ICI NEW COMMERCIAL SERVICE/ 575 COCHRANE DR | 95 | COMPLETE | Estimate incorrect | N/A | N/A | Joshi, Namrata | No | Alectra Utilities | Steve Rumble | 87096.93 | 556290.41 | 469193.48 | 538.7% | 16609.99 | 496067.22 | 479457.23 | 2887% | 40473.44 | 39482.16 | -991.28 | -2.449% | 1374.06 | 1975.67 | 601.61 | 43.78% | 28639.44 | 18765.36 | -9874.08 | -34.48% | 158.35 | 135 | -23.35 | -14.75% | 2020-02-26 01:00
Markham | 2022 | 633955 | 633955 - ICI PADMOUNT TX INSTALLATION/134 FIRST COMMERCE DR | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Paterson, Greg | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-28 01:00
Markham | 2020 | 633975 | (WO 633975) 2020 SUNNIDALE AND ANNE CABLE REPLACEMENT | 99 | CANCELLED | N/A |  |  | Bowman, Todd J | Yes | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-11 01:00
Markham | 2020 | 633979 | 633979 - 196 BRADWICK DR / ICI PADMOUNT TRANSFORMER UPGRADE | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 53753.19 | 53634.75 | -118.44 | -0.2203% | 14085.24 | 11915.24 | -2170 | -15.41% | 23852.97 | 22033.89 | -1819.08 | -7.626% | 1223.1 | 1110 | -113.1 | -9.247% | 14591.88 | 18575.62 | 3983.74 | 27.3% | 147.8 | 119 | -28.8 | -19.49% | 2020-02-11 01:00
Markham | 2020 | 633982 | (WO 633982) 3600 LANGSTAFF RD / ICI DUCTBANK RELOCATION | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-02-22 01:00
Markham | 2020 | 633993 | 633993 - HE2019-103, MAJOR MACK & KEELE AERIAL PERMIT | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 7784.84 | 6714.49 | -1070.35 | -13.75% | 3137.93 | 1180.63 | -1957.3 | -62.38% | 249.71 | 0 | -249.71 | -100% | 217.6 | 0 | -217.6 | -100% | 4179.6 | 5533.86 | 1354.26 | 32.4% | 21.06 | 1.5 | -19.56 | -92.88% | 2020-02-13 01:00
Markham | 2020 | 634040 | (WO 634040) REPLACE 31TP175, 7300 BIRCHMOUNT RD | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-24 01:00
Markham | 2020 | 634047 | 634047 - 115 CIDERMILL AVE. | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 56424.53 | 41063.52 | -15361.01 | -27.22% | 16137.41 | 8017.96 | -8119.45 | -50.31% | 31668.21 | 30728.98 | -939.23 | -2.966% | 1998.51 | 2316.58 | 318.07 | 15.92% | 6620.4 | 0 | -6620.4 | -100% | 165 | 69 | -96 | -58.18% | 2020-10-30 01:00
Markham | 2021 | 634066 | 634066 - POLE RELOCATIONS - 1890 HWY 7 | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Steve | 533866.15 | 521003.67 | -12862.48 | -2.409% | 67506.96 | 68733.41 | 1226.45 | 1.817% | 130429.07 | 132066.75 | 1637.68 | 1.256% | 662.12 | 3809.5 | 3147.38 | 475.3% | 335268 | 316394.01 | -18873.99 | -5.63% | 20.06 | 117 | 96.94 | 483.3% | 2021-12-03 01:00
Markham | 2020 | 634080 | 634080 - POLE REPLACEMENT 2020 - REPLACE P30260 AT YONGE ST AND MORGAN AVE, MARKHAM | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 37097.26 | 13764.47 | -23332.79 | -62.9% | 20842.26 | 6121.53 | -14720.73 | -70.63% | 5341.5 | 5502.94 | 161.44 | 3.022% | 1787.5 | 2140 | 352.5 | 19.72% | 9126 | 0 | -9126 | -100% | 237.74 | 72 | -165.74 | -69.71% | 2020-08-14 01:00
Markham | 2020 | 634081 | 634081 - 2020 POLE REPLACEMENT - REPLACE 2 POLES AT YONGE AND JOHN ST, MARKHAM | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 44003.5 | 29767.09 | -14236.41 | -32.35% | 27090.76 | 13741.05 | -13349.71 | -49.28% | 5835.58 | 4523.31 | -1312.27 | -22.49% | 2413.4 | 4070.73 | 1657.33 | 68.67% | 8663.76 | 7432 | -1231.76 | -14.22% | 313.99 | 150 | -163.99 | -52.23% | 2020-10-14 01:00
Markham | 2022 | 634107 | 634107 - 435 CITYVIEW BLVD / ICI PADMOUNT TX INSTALLATION | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Mann, Drew | Persaud, Ryan | 85305.11 | 0 | -85305.11 | -100% | 13509.83 | 0 | -13509.83 | -100% | 42418.1 | 0 | -42418.1 | -100% | 1191.34 | 0 | -1191.34 | -100% | 28185.84 | 0 | -28185.84 | -100% | 148.65 | 2 | -146.65 | -98.65% | 2021-08-17 01:00
Markham | 2021 | 634124 | 634124 - 189 BULLOCK DR / ICI PADMOUNT TX UPGRADE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 75325.57 | 64544.26 | -10781.31 | -14.31% | 16766.36 | 14114.63 | -2651.73 | -15.82% | 37871.25 | 40328.47 | 2457.22 | 6.488% | 2051.48 | 3742 | 1690.52 | 82.4% | 18636.48 | 6359.16 | -12277.32 | -65.88% | 208.99 | 125 | -83.99 | -40.19% | 2021-08-17 01:00
Markham | 2020 | 634139 | 634139 - POLE REPLACEMENT 2020 - BATCH 17 - AURORA | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 245896.33 | 398020.47 | 152124.14 | 61.87% | 123117.87 | 41164.05 | -81953.82 | -66.57% | 51253.89 | 113724.6 | 62470.71 | 121.9% | 29760.97 | 857.3 | -28903.67 | -97.12% | 41763.6 | 242274.52 | 200510.92 | 480.1% | 2012.67 | 245 | -1767.67 | -87.83% | 2020-12-24 01:00
Markham | 2021 | 634156 | 634156 - TESTON RD. PINE VALLEY TO WESTON - POLE RELOCATION | 99 | COMPLETE | Scope – Cust | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Morrow, Joe | 4462892.98 | 1524432.15 | -2938460.83 | -65.84% | 1285631.45 | 393181.14 | -892450.31 | -69.42% | 1060825.39 | 551492.05 | -509333.34 | -48.01% | 330418.54 | 140849.75 | -189568.79 | -57.37% | 1786017.6 | 438909.21 | -1347108.39 | -75.43% | 8148.7 | 4251.5 | -3897.2 | -47.83% | 2021-08-31 01:00
Markham | 2021 | 634344 | 634344 - STORM HARDENING 2020 - WOODBINE - RIVIERA TO DENISON | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 1001729.31 | 1042939.15 | 41209.84 | 4.114% | -26316.94 | 59534.83 | 85851.77 | -326.2% | 417861 | 371284.13 | -46576.87 | -11.15% | 29252.71 | 0 | -29252.71 | -100% | 580932.54 | 612120.19 | 31187.65 | 5.369% | 111.74 | 126 | 14.26 | 12.76% | 2021-03-27 01:00
Markham | 2019 | 634364 | 634364 - FEEDER RE-CONFIGURATION ON HUNTINGTON RD | 99 | COMPLETE | Labour est. under |  |  | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 28955.31 | 42606.29 | 13650.98 | 47.14% | 18041.03 | 27594.44 | 9553.41 | 52.95% | 2864.74 | 0 | -2864.74 | -100% | 8049.54 | 5745 | -2304.54 | -28.63% | 0 | 9266.85 | 9266.85 |  | 298.85 | 255 | -43.85 | -14.67% | 2019-12-15 01:00
Markham | 2020 | 634378 | 634378 - 2020 CABLE REPLACEMENT/YORK HILL PHASE 4B | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 440108.38 | 91977.67 | -348130.71 | -79.1% | 30021.22 | 14532.21 | -15489.01 | -51.59% | 66432.96 | 68529.93 | 2096.97 | 3.157% | 3114 | 2453.94 | -660.06 | -21.2% | 340540.2 | 6461.59 | -334078.61 | -98.1% | 390 | 160 | -230 | -58.97% | 2020-12-16 01:00
Markham | 2020 | 634389 | 634389 - POLE REPLACEMENT 2020 BATCH 13 - VAUGHAN | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 47864.28 | 40593.77 | -7270.51 | -15.19% | 26934.71 | 19224.89 | -7709.82 | -28.62% | 12403.33 | 9095.92 | -3307.41 | -26.67% | 2853 | 7358.96 | 4505.96 | 157.9% | 5673.24 | 4914 | -759.24 | -13.38% | 350.01 | 217.01 | -133 | -38% | 2020-12-16 01:00
Markham | 2020 | 634390 | 634390 - POLE REPLACEMENT 2020 BATCH 14 - VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 144594.46 | 136861.64 | -7732.82 | -5.348% | 75719.52 | 68761.54 | -6957.98 | -9.189% | 33991.04 | 37079.54 | 3088.5 | 9.086% | 9727.46 | 19070 | 9342.54 | 96.04% | 25156.44 | 11950.56 | -13205.88 | -52.5% | 1023.24 | 832 | -191.24 | -18.69% | 2020-08-26 01:00
Markham | 2020 | 634391 | 634391 - POLE REPLACEMENT 2020 BATCH 15 - VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 72326.6 | 67756.58 | -4570.02 | -6.319% | 42685.55 | 36619.89 | -6065.66 | -14.21% | 16664.95 | 13682.69 | -2982.26 | -17.9% | 5345.9 | 9300 | 3954.1 | 73.97% | 7630.2 | 8154 | 523.8 | 6.865% | 565.56 | 417 | -148.56 | -26.27% | 2020-07-21 01:00
Markham | 2020 | 634392 | 634392 - POLE REPLACEMENT 2020 BATCH 16 - VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 69289.73 | 64898.22 | -4391.51 | -6.338% | 38496.65 | 32500.27 | -5996.38 | -15.58% | 16362.04 | 15642.67 | -719.37 | -4.397% | 5274.8 | 11766.28 | 6491.48 | 123.1% | 9156.24 | 4989 | -4167.24 | -45.51% | 538.27 | 392 | -146.27 | -27.17% | 2020-09-10 01:00
Markham | 2022 | 634467 | 634467 - 24 LANSDOWNE AVE | 98 | ANALYZE |  |  |  | Corriveau, Tom N | No | Silcock, Jordan | Kristine Gordon | 33564.51 | 25622.37 | -7942.14 | -23.66% | 24795.17 | 18363.3 | -6431.87 | -25.94% | 2423.17 | 1410.26 | -1012.91 | -41.8% | 3646.17 | 2657 | -989.17 | -27.13% | 2700 | 3191.81 | 491.81 | 18.22% | 106.22 | 168 | 61.78 | 58.16% | 2022-10-27 01:00
Markham | 2020 | 634469 | 634469 - 13029 BATHURST STREET | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Alectra Utilities | Persaud, Ryan | 1.3 | 0 | -1.3 | -100% | 1.3 | 0 | -1.3 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-18 01:00
Markham | 2020 | 634470 | 634470 - POLE REPLACEMENT 2020 - REPLACE 3 POLES AT HWY 407 AND PINE VALLEY DR, VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 84208.31 | 81618.6 | -2589.71 | -3.075% | 3342.51 | 6206.26 | 2863.75 | 85.68% | 13639.64 | 23504.78 | 9865.14 | 72.33% | 194.88 | 0 | -194.88 | -100% | 67031.28 | 51907.56 | -15123.72 | -22.56% | 13.02 | 0 | -13.02 | -100% | 2020-09-18 01:00
Markham | 2020 | 634471 | 634471 - POLE REPLACEMENT 2020 - REPLACE P46749 AT HWY 407 & ISLINGTON AVE, VAUGHAN | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 57871.99 | 79530.97 | 21658.98 | 37.43% | 27957.57 | 6808.66 | -21148.91 | -75.65% | 13077.1 | 18978.52 | 5901.42 | 45.13% | 3208.8 | 0 | -3208.8 | -100% | 13628.52 | 53743.79 | 40115.27 | 294.3% | 328.79 | 0 | -328.79 | -100% | 2020-09-18 01:00
Markham | 2020 | 634476 | 634476 - 2020 POLE REPLACEMENTS - VAUGHAN - BATCH 18 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Ryan Walsh | 160199.54 | 137656.67 | -22542.87 | -14.07% | 48662.3 | 54782.93 | 6120.63 | 12.58% | 34204.97 | 33155.38 | -1049.59 | -3.069% | 10966.27 | 15836 | 4869.73 | 44.41% | 66366 | 33882.36 | -32483.64 | -48.95% | 737.54 | 571 | -166.54 | -22.58% | 2020-09-14 01:00
Markham | 2020 | 634479 | 634479 - 2020 LEFT-BEHIND CABLE REPLACE/M37 14TH AVE | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 149290.99 | 144883.62 | -4407.37 | -2.952% | 17390.12 | 21438.77 | 4048.65 | 23.28% | 13315.66 | 17722.07 | 4406.41 | 33.09% | 2250.85 | 1680.79 | -570.06 | -25.33% | 116334.36 | 104041.99 | -12292.37 | -10.57% | 242 | 122.5 | -119.5 | -49.38% | 2020-10-21 01:00
Markham | 2020 | 634480 | 634480 - 2020 LEFT-BEHIND CABLE REPLACE/V18 BARRHILL RD | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 720786.36 | 680631.91 | -40154.45 | -5.571% | 18265.7 | 62473.11 | 44207.41 | 242% | 1334.51 | 0 | -1334.51 | -100% | 1661.51 | 717.95 | -943.56 | -56.79% | 699524.64 | 617440.85 | -82083.79 | -11.73% | 235.6 | 57 | -178.6 | -75.81% | 2020-11-03 01:00
Markham | 2020 | 634481 | 634481 - 2020 LEFT-BEHIND CABLE REPLACE/V36 SCHOLES RD | 99 | COMPLETE | Civil contractor | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 196761.53 | 185704.05 | -11057.48 | -5.62% | 12468.18 | 20007.49 | 7539.31 | 60.47% | 1669.89 | 0 | -1669.89 | -100% | 1461.02 | 956.55 | -504.47 | -34.53% | 181162.44 | 164740.01 | -16422.43 | -9.065% | 156.08 | 52 | -104.08 | -66.68% | 2020-11-03 01:00
Markham | 2020 | 634487 | 634487 - 2020 POLE REPLACEMENTS - VAUGHAN - BATCH 19 | 99 | COMPLETE | Material Req incorrectly | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 131114.3 | 100916.19 | -30198.11 | -23.03% | 51424.11 | 48041.09 | -3383.02 | -6.579% | 31791.67 | 32010.5 | 218.83 | 0.6883% | 9450.52 | 10494 | 1043.48 | 11.04% | 38448 | 10370.6 | -28077.4 | -73.03% | 880.77 | 483.5 | -397.27 | -45.1% | 2020-09-18 01:00
Markham | 2020 | 634488 | 634488 - 2020 POLE REPLACEMENT - P43709 | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 211.44 | 211.44 |  | 0 | 211.44 | 211.44 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-01-15 01:00
Markham | 2020 | 634494 | 634494 - 2020 POLE REPLACEMENT -P43706 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 50374.01 | 51871.14 | 1497.13 | 2.972% | 21143.6 | 29540.6 | 8397 | 39.71% | 17129.57 | 13721.6 | -3407.97 | -19.9% | 5443.72 | 8608.94 | 3165.22 | 58.14% | 6657.12 | 0 | -6657.12 | -100% | 427.18 | 304 | -123.18 | -28.84% | 2020-11-23 01:00
Markham | 2022 | 634501 | 634501 - 381 BRADWICK DR / ICI VAULT TX UPGRADE | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Mann, Drew | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-10 01:00
Markham | 2020 | 634522 | 634522 - M43 - John and Woodbine (Mini Rupters) | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Alectra Utilities | Lamb, Tim | 277240.31 | 272472.6 | -4767.71 | -1.72% | 71454.72 | 39648.13 | -31806.59 | -44.51% | 201225.59 | 224891.47 | 23665.88 | 11.76% | 4560 | 7933 | 3373 | 73.97% | 0 | 0 | 0 |  | 720 | 514 | -206 | -28.61% | 2020-06-25 01:00
Markham | 2020 | 634525 | 634525 - 2020 POLE REPLACEMENTS - P41694 | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-24 01:00
Markham | 2020 | 634568 | 634568 - POLE REPLACEMENT 2020 - REPLACE HP AT CREDISTONE RD, VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-17 01:00
Markham | 2020 | 634569 | 634569 - POLE REPLACEMENT 2020 - REPLACE P43255 AT 8000 KEELE ST, VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Handy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-17 01:00
Markham | 2020 | 634571 | 634571 - POLE REPLACEMENT 2020 - REPLACE P52314 AT 7777 KIPLING AVE, VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Handy, James | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-16 01:00
Markham | 2020 | 634572 | 634572 - POLE REPLACEMENT 2020 BATCH 20 - VAUGHAN - REPLACE 12 POLES | 99 | COMPLETE | Labour est. over | Material Req incorrectly | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Larry | 78247.11 | 52871.5 | -25375.61 | -32.43% | 44463.28 | 25254.6 | -19208.68 | -43.2% | 21016.27 | 12524.19 | -8492.08 | -40.41% | 5639.56 | 10588.21 | 4948.65 | 87.75% | 7128 | 4504.5 | -2623.5 | -36.81% | 595.82 | 271 | -324.82 | -54.52% | 2020-12-16 01:00
Markham | 2020 | 634595 | 634595 - 250 INTERCHANGE WAY - TEMPORARY | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 59853.75 | 71459.66 | 11605.91 | 19.39% | 12788.28 | 8486.24 | -4302.04 | -33.64% | 34725.96 | 54889.35 | 20163.39 | 58.06% | 1611.98 | 933 | -678.98 | -42.12% | 10727.53 | 7151.07 | -3576.46 | -33.34% | 159.65 | 80.5 | -79.15 | -49.58% | 2020-03-10 01:00
Markham | 2021 | 634625 | 634625 - HIGHWAY NO. 7 WEST - #2926 (EDGELEY STRATA PARK) | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 180088.47 | 142620.35 | -37468.12 | -20.81% | 21962.35 | 23057.55 | 1095.2 | 4.987% | 42469.74 | 37738.72 | -4731.02 | -11.14% | 2276.31 | 1582.55 | -693.76 | -30.48% | 113380.07 | 80241.53 | -33138.54 | -29.23% | 123.05 | 119.05 | -4 | -3.251% | 2021-09-15 01:00
Markham | 2020 | 634639 | 634639 - Main St. Markham North - #352 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 41252.53 | 25291.29 | -15961.24 | -38.69% | 16604.66 | 8543.88 | -8060.78 | -48.55% | 7468.56 | 6311.43 | -1157.13 | -15.49% | 3043.89 | 1389.51 | -1654.38 | -54.35% | 14135.42 | 9046.47 | -5088.95 | -36% | 215.1 | 51.5 | -163.6 | -76.06% | 2020-12-10 01:00
Markham | 2020 | 634727 | 634727 - ICI DEMOLITION/ 200 ABERDEEN AVE | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 12237.67 | 3219.24 | -9018.43 | -73.69% | 6543.95 | 2835.24 | -3708.71 | -56.67% | 0 | 0 | 0 |  | 392 | 384 | -8 | -2.041% | 5301.72 | 0 | -5301.72 | -100% | 40 | 16 | -24 | -60% | 2020-02-29 01:00
Markham | 2021 | 634740 | 634740 - ICI NEW COMMERCIAL SERVICE / 721 WESTBURNE DR | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 122523.1 | 88669.44 | -33853.66 | -27.63% | 23088.13 | 18304.59 | -4783.54 | -20.72% | 40470.91 | 39383.09 | -1087.82 | -2.688% | 1724.06 | 2321.83 | 597.77 | 34.67% | 57240 | 28659.93 | -28580.07 | -49.93% | 114.78 | 115.5 | 0.72 | 0.6273% | 2021-04-27
Markham | 2021 | 634840 | 634840 - HE2019-120, ROGERS - JANE ST | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 14210.4 | 7789.45 | -6420.95 | -45.18% | 3912.03 | 2146.49 | -1765.54 | -45.13% | 1163.84 | 572.96 | -590.88 | -50.77% | 483.73 | 260 | -223.73 | -46.25% | 8650.8 | 4810 | -3840.8 | -44.4% | 17.89 | 9 | -8.89 | -49.69% | 2021-04-23
Markham | 2022 | 634900 | 634900 - OH AND UG RELOCATION AT SIMMONS ST, VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Morrow, Joe | 555613.31 | 615956.46 | 60343.15 | 10.86% | 168910.05 | 235181.51 | 66271.46 | 39.23% | 129179.07 | 128118.2 | -1060.87 | -0.8212% | 26412.59 | 71164 | 44751.41 | 169.4% | 231111.6 | 181492.75 | -49618.85 | -21.47% | 2395.98 | 2584 | 188.02 | 7.847% | 2022-03-23 01:00
Markham | 2020 | 634943 | 634943 - FAIRTREE BLOCK 151 CONDO BLOCK SEMI DETACHED / INSPECT AND CONNECT WO | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 496942.86 | 488224.81 | -8718.05 | -1.754% | 22294.77 | 50136.67 | 27841.9 | 124.9% | 2209.94 | 0 | -2209.94 | -100% | 1408.03 | 1065.87 | -342.16 | -24.3% | 471030.12 | 432836.8 | -38193.32 | -8.108% | 235.2 | 74.92 | -160.28 | -68.15% | 2020-10-05 01:00
Markham | 2022 | 634946 | 634946 - PALA CONDOMINIUM DEVELOPMENT | 99 | ANALYZE |  |  |  | Penner, Mitchell | No | Swales, Mathew | Dave Lindsay | 262701.09 | 240830 | -21871.09 | -8.325% | 64854.31 | 59964.3 | -4890.01 | -7.54% | 8133.12 | 9009.75 | 876.63 | 10.78% | 5499.14 | 3775 | -1724.14 | -31.35% | 184214.52 | 167211.25 | -17003.27 | -9.23% | 438.06 | 373.75 | -64.31 | -14.68% | 2022-10-07 01:00
Markham | 2019 | 634961 | 634961 - 82 SCIBERRAS - ESA EMERGING PROJECT - REAR LOT CONDUCTOR HEIGHT ADJUSTMENT | 99 | COMPLETE | Labour est. under |  |  | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Larry | 21443.7 | 31427.86 | 9984.16 | 46.56% | 10115.47 | 16446.45 | 6330.98 | 62.59% | 1537.68 | 1874.87 | 337.19 | 21.93% | 1694.6 | 3830 | 2135.4 | 126% | 8095.95 | 9276.54 | 1180.59 | 14.58% | 99.41 | 170 | 70.59 | 71.01% | 2019-12-21 01:00
Markham | 2020 | 634963 | 634963 - POLE REPLACEMENT 2020 BATCH 21 - VAUGHAN - REPLACE 3 POLES | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Larry | 84453.2 | 74877.37 | -9575.83 | -11.34% | 53526.67 | 33408.91 | -20117.76 | -37.58% | 19535.93 | 22881.98 | 3346.05 | 17.13% | 5882.6 | 13901.61 | 8019.01 | 136.3% | 5508 | 4684.87 | -823.13 | -14.94% | 648.01 | 356 | -292.01 | -45.06% | 2020-12-03 01:00
Markham | 2020 | 634964 | 634964 - POLE REPLACEMENT 2020 - REPLACE P46320 AT ISLINGTON AVE & THISTLEWOOD AVE | 99 | COMPLETE | Material Req incorrectly | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Larry | 55765.11 | 65378.01 | 9612.9 | 17.24% | 20129.45 | 21411.37 | 1281.92 | 6.368% | 9384.96 | 13467.22 | 4082.26 | 43.5% | 2220.7 | 7580.47 | 5359.77 | 241.4% | 24030 | 22918.95 | -1111.05 | -4.624% | 203.81 | 184.5 | -19.31 | -9.475% | 2020-12-17 01:00
Markham | 2021 | 635032 | 635032 - OH AND UG RELOCATION AT JANE ST (NORTH OF TESTON RD), VAUGHAN | 98 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Ryan Walsh | 749128.4 | 801141.6 | 52013.2 | 6.943% | 293179.45 | 241734.71 | -51444.74 | -17.55% | 289419.85 | 350830.19 | 61410.34 | 21.22% | 67007.1 | 82012.5 | 15005.4 | 22.39% | 99522 | 126503.63 | 26981.63 | 27.11% | 2630.25 | 2625.5 | -4.75 | -0.1806% | 2021-07-06 01:00
Markham | 2022 | 635051 | 635051 - TRANSFORMER REPLACEMENT 2020 - BATCH 15 - REPLACE 7 TXS | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 62094.37 | 28109.89 | -33984.48 | -54.73% | 16877.41 | 7619.17 | -9258.24 | -54.86% | 41270.73 | 16081.11 | -25189.62 | -61.04% | 3946.23 | 394.71 | -3551.52 | -90% | 0 | 4014.9 | 4014.9 |  | 292.7 | 55 | -237.7 | -81.21% | 2022-10-31 01:00
Markham | 2022 | 635065 | 635065 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.1 | 95 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 1955792.92 | 2038101.4 | 82308.48 | 4.208% | 97756.81 | 228393.57 | 130636.76 | 133.6% | 741242.67 | 745287.68 | 4045.01 | 0.5457% | 160 | 48 | -112 | -70% | 1116633.44 | 1053331.15 | -63302.29 | -5.669% | 58 | 23 | -35 | -60.34% | 2022-09-17 01:00
Markham | 2021 | 635079 | 635079 - CABLE REPLACEMENT, M14 MAJOR BUTTONS AND RICHWOOD - 14TP030 TO 14U030 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Lamb, Tim | 532574.71 | 542307.4 | 9732.69 | 1.827% | 21120.54 | 62159.2 | 41038.66 | 194.3% | 1909.59 | 0 | -1909.59 | -100% | 1835.34 | 3077.76 | 1242.42 | 67.69% | 507709.24 | 477070.44 | -30638.8 | -6.035% | 112.08 | 210 | 97.92 | 87.37% | 2021-02-01 01:00
Markham | 2021 | 635159 | 635159 - MTO- 407 AND YORK DURHAM LINE - POLE REPLACEMENTS - MARKHAM | 99 | COMPLETE | Covid-19 | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Morrow, Joe | 93617.85 | 102802.97 | 9185.12 | 9.811% | 34968.22 | 34490.07 | -478.15 | -1.367% | 25597.05 | 29586.04 | 3988.99 | 15.58% | 5983.58 | 9644.83 | 3661.25 | 61.19% | 27069 | 29082.03 | 2013.03 | 7.437% | 311.69 | 334.5 | 22.81 | 7.318% | 2021-01-07 01:00
Markham | 2022 | 635204 | 635204 - 11110 JANE ST / VAU / NS / 3PH CO-STN | 99 | COMPLETE | Under 10% | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 37697.03 | 34166.79 | -3530.24 | -9.365% | 18654.86 | 22068.97 | 3414.11 | 18.3% | 13718.27 | 4795.99 | -8922.28 | -65.04% | 1098.94 | 3916 | 2817.06 | 256.3% | 4224.96 | 3385.83 | -839.13 | -19.86% | 76.3 | 148 | 71.7 | 93.97% | 2022-02-11 01:00
Markham | 2020 | 635317 | 635317 - 5467 19TH AVE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 44148.28 | 25537.57 | -18610.71 | -42.16% | 12386.75 | 9706.69 | -2680.06 | -21.64% | 14768.44 | 9195.07 | -5573.37 | -37.74% | 3592.09 | 1299 | -2293.09 | -63.84% | 13401 | 5336.81 | -8064.19 | -60.18% | 264.5 | 65 | -199.5 | -75.43% | 2020-11-04 01:00
Markham | 2021 | 635331 | 635331 - ICI NEW CONDOMINIUM/ 8010 KIPLING AVE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 96470.44 | 44792.6 | -51677.84 | -53.57% | 24492.65 | 18797.72 | -5694.93 | -23.25% | 15736.06 | 2760.34 | -12975.72 | -82.46% | 2850.18 | 3607.83 | 757.65 | 26.58% | 58391.55 | 19626.71 | -38764.84 | -66.39% | 153.36 | 140.5 | -12.86 | -8.385% | 2021-10-08 01:00
Markham | 2020 | 635382 | 635382 - JOINT USE HE2019-132 | 99 | COMPLETE | Estimate incorrect | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 40963.25 | 76875.57 | 35912.32 | 87.67% | 17221.36 | 27170.01 | 9948.65 | 57.77% | 8929.09 | 15069.01 | 6139.92 | 68.76% | 2102.28 | 9237.53 | 7135.25 | 339.4% | 12710.52 | 25399.02 | 12688.5 | 99.83% | 291.3 | 274.5 | -16.8 | -5.767% | 2020-08-14 01:00
Markham | 2020 | 635570 | 635570 - 7 EAGLET CRT - KEELE LANDFILL / ICI 1PH PAD TX DEMO | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 7356.02 | 3929.6 | -3426.42 | -46.58% | 6384.21 | 3324.6 | -3059.61 | -47.92% | 0 | 0 | 0 |  | 971.81 | 605 | -366.81 | -37.75% | 0 | 0 | 0 |  | 73.85 | 16.5 | -57.35 | -77.66% | 2020-07-28 01:00
Markham | 2022 | 635587 | 635587 - KING RD, YONGE ST TO BOND CRES | 99 | COMPLETE | Est. Ext. - Act. Internal | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Ryan Walsh | 120072.61 | 109608.17 | -10464.44 | -8.715% | 17391.48 | 54933.22 | 37541.74 | 215.9% | 21734.13 | 28788.37 | 7054.24 | 32.46% | 42 | 14173.5 | 14131.5 | 33646% | 80905 | 11713.08 | -69191.92 | -85.52% | 504 | 609 | 105 | 20.83% | 2022-01-24 01:00
Markham | 2020 | 635618 | 635618 - ICI PADMOUNT TX INSTALLATION/70A ELDERBERRY TRAIL | 99 | COMPLETE | Civil contractor | N/A | N/A | Cranley, Stephen | No | Alectra Utilities | Chris Hagan | 46227.79 | 44757.97 | -1469.82 | -3.18% | 10099.31 | 16728.59 | 6629.28 | 65.64% | 9640.41 | 5484.89 | -4155.52 | -43.11% | 918.03 | 3190.42 | 2272.39 | 247.5% | 25570.04 | 19354.07 | -6215.97 | -24.31% | 197.8167 | 120.6 | -77.2167 | -39.03% | 2020-12-02 01:00
Markham | 2020 | 635655 | 635655 - 2020 CABLE INJECTION/M40 CABLE INJECTION | 99 | COMPLETE | Cont Est Under | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 214326.59 | 240414.1 | 26087.51 | 12.17% | 4303.03 | 21055.93 | 16752.9 | 389.3% | 11689.12 | 11885.32 | 196.2 | 1.678% | 0 | 0 | 0 |  | 198334.44 | 207472.85 | 9138.41 | 4.608% | 0 | 0 | 0 |  | 2020-12-04 01:00
Markham | 2022 | 635657 | 635657 - JOINT USE PERMIT HE2020-003, WESTON ROAD, VAUGHAN | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Steve | 40874.89 | 45766.72 | 4891.83 | 11.97% | 15918.66 | 4791.09 | -11127.57 | -69.9% | 8900.75 | 7233.7 | -1667.05 | -18.73% | 3450.48 | 0 | -3450.48 | -100% | 12605 | 33741.93 | 21136.93 | 167.7% | 119.88 | 0 | -119.88 | -100% | 2022-04-04
Markham | 2021 | 635665 | 635665 - ICI TRANSFORMER UPGRADE/ 500 EGLIN MILLS ROAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 34847.57 | 40781.5 | 5933.93 | 17.03% | 17718.67 | 9764.88 | -7953.79 | -44.89% | 37472.75 | 29364.12 | -8108.63 | -21.64% | 2006.15 | 1652.5 | -353.65 | -17.63% | 0 | 0 | 0 |  | 85.4 | 90.5 | 5.1 | 5.972% | 2021-09-15 01:00
Markham | 2020 | 635680 | 635680 - CABLE REPLACEMENT - 269 BAY THORN DR | 99 | COMPLETE | Civil contractor | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 69747.37 | 54111.45 | -15635.92 | -22.42% | 14045.87 | 8036.89 | -6008.98 | -42.78% | 7091.62 | 9341.16 | 2249.54 | 31.72% | 1723.95 | 872.74 | -851.21 | -49.38% | 46885.93 | 35860.66 | -11025.27 | -23.52% | 205.63 | 51 | -154.63 | -75.2% | 2020-12-21 01:00
Markham | 2020 | 635761 | 635761 - 11408 YONGE STREET - STUB POLE INSTALLATION | 99 | COMPLETE | Scope – Eng | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Ryan Walsh | 15379.58 | 5261.9 | -10117.68 | -65.79% | 7547.58 | 4011.9 | -3535.68 | -46.85% | 3698 | 0 | -3698 | -100% | 1434 | 1250 | -184 | -12.83% | 2700 | 0 | -2700 | -100% | 108 | 50 | -58 | -53.7% | 2020-06-22 01:00
Markham | 2020 | 635799 | 55 GRENCER ROAD | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Alectra Utilities | Wong, Henry | 0 | -2049.84 | -2049.84 |  | 0 | -2049.84 | -2049.84 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-13 01:00
Markham | 2020 | 635805 | 635805 - APPLEWOOD NORTH OF PORTAGE PARKWAY | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Steve Rumble | 168545.26 | 144217.15 | -24328.11 | -14.43% | 10911.76 | 21336.24 | 10424.48 | 95.53% | 0 | 355.83 | 355.83 |  | 680.34 | 1122.69 | 442.35 | 65.02% | 156953.16 | 121402.39 | -35550.77 | -22.65% | 106.02 | 109.9 | 3.88 | 3.66% | 2020-08-13 01:00
Markham | 2020 | 635808 | 635808 - CUSTOMER EMERGING PROJECT FOR HATPIN CONDO DEVELOPMENT - POLE INSTALLATION | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 22102.42 | 18205.91 | -3896.51 | -17.63% | 15380.03 | 5808.91 | -9571.12 | -62.23% | 3143.19 | 3498.89 | 355.7 | 11.32% | 1743.2 | 228.71 | -1514.49 | -86.88% | 1836 | 8669.4 | 6833.4 | 372.2% | 61.4 | 6 | -55.4 | -90.23% | 2020-09-03 01:00
Markham | 2020 | 635882 | 9113 AND 9125 BATHURST/INSPECT AND CONNECT | 99 | CANCELLED | N/A |  |  | D'Onofrio, Tony | No | Alectra Utilities | Wong, Henry | 0 | 5311.6 | 5311.6 |  | 0 | 5311.6 | 5311.6 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 10.5 | 10.5 |  | 2022-10-07 01:00
Markham | 2022 | 635904 | 635904 - GEMTERRA WOODBINE, MARKHAM | 99 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Estrada, Michael | Dave Lindsay | 210274.46 | 205224.23 | -5050.23 | -2.402% | 45589.2 | 42288.44 | -3300.76 | -7.24% | 6491.3 | 6224.32 | -266.98 | -4.113% | 3381.96 | 4315.5 | 933.54 | 27.6% | 154812 | 151394.65 | -3417.35 | -2.207% | 167.8 | 165 | -2.8 | -1.669% | 2022-10-07 01:00
Markham | 2021 | 635906 | 635906 - 1623 WELLINGTON STREET, AURORA | 98 | COMPLETE | Labour est. over | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Larry | 18138.24 | 13606.5 | -4531.74 | -24.98% | 10230.85 | 8078.82 | -2152.03 | -21.03% | 1091.34 | 1176.17 | 84.83 | 7.773% | 649.25 | 0 | -649.25 | -100% | 6166.8 | 4351.51 | -1815.29 | -29.44% | 23.06 | 13.25 | -9.81 | -42.54% | 2021-07-21 01:00
Markham | 2020 | 635933 | 635933 - LESLIE STREET POLE REPLACEMENT (2 POLES) | 99 | COMPLETE | Labour est. under | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 13739.21 | 21867.31 | 8128.1 | 59.16% | 5025.01 | 11973.15 | 6948.14 | 138.3% | 4880.16 | 4853.16 | -27 | -0.5533% | 1049.8 | 2584 | 1534.2 | 146.1% | 2784.24 | 2457 | -327.24 | -11.75% | 67.13 | 156 | 88.87 | 132.4% | 2020-08-26 01:00
Markham | 2022 | 635979 | OH RELOCATION AT STEELES AVE W AND PALM GATE BLVD, VAUGHAN | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Murray, Jake R | Wong, Henry | 0 | 57850.84 | 57850.84 |  | 0 | 5750.84 | 5750.84 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 52100 | 52100 |  | 0 | 0 | 0 |  | 2020-12-16 01:00
Markham | 2022 | 636063 | 636063 - ICI PADMOUNT TX INSTALLATION/LOT 21 ADDISON HALL CIRCLE | 99 | COMPLETE | Under 10% | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Dave Lindsay | 40279.42 | 38109.96 | -2169.46 | -5.386% | 15838.28 | 12669.54 | -3168.74 | -20.01% | 43265.08 | 22223.86 | -21041.22 | -48.63% | 1490.26 | 1646 | 155.74 | 10.45% | 2035.8 | 1570.56 | -465.24 | -22.85% | 89.28 | 87 | -2.28 | -2.554% | 2022-02-11 01:00
Markham | 2022 | 636066 | 636066 - ICI NEW COMMERCIAL CONNECTION/ RUTHERFORD PUMPING STATION | 95 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 151014.19 | 147729.38 | -3284.81 | -2.175% | 49399.1 | 37253.24 | -12145.86 | -24.59% | 40882.05 | 28857.65 | -12024.4 | -29.41% | 6111.04 | 3414 | -2697.04 | -44.13% | 76972 | 78204.49 | 1232.49 | 1.601% | 279.67 | 201.5 | -78.17 | -27.95% | 2022-07-19 01:00
Markham | 2022 | 636102 | 636102 - 8960 JANE ST / VAU / NS/ CO-STN | 98 | ANALYZE |  |  |  | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 46900.2 | 53636.84 | 6736.64 | 14.36% | 18941.19 | 26588.65 | 7647.46 | 40.37% | 13212.11 | 13980.59 | 768.48 | 5.816% | 1304.9 | 1196 | -108.9 | -8.345% | 13442 | 11871.6 | -1570.4 | -11.68% | 90.46 | 176 | 85.54 | 94.56% | 2022-12-08 01:00
Markham | 2022 | 636112 | 636112 - DONNA MAE ESTATES | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Alarcon, Alejandro | Dave Lindsay | 83925.85 | 74785.58 | -9140.27 | -10.89% | 26281.04 | 17984.76 | -8296.28 | -31.57% | 3230.32 | 3025.82 | -204.5 | -6.331% | 1884.49 | 1245 | -639.49 | -33.93% | 52530 | 52530 | 0 | 0% | 96.35 | 62 | -34.35 | -35.65% | 2022-12-08 01:00
Markham | 2020 | 636130 | 636130 - ICI NEW COMMERCIAL / 8745 HIGHWAY 50 | 99 | COMPLETE | Civil contractor | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Dave Lindsay | 108118.58 | 79758.49 | -28360.09 | -26.23% | 21276.55 | 14603.22 | -6673.33 | -31.36% | 54976.47 | 52554.84 | -2421.63 | -4.405% | 2523.56 | 3193.29 | 669.73 | 26.54% | 29342 | 9407.14 | -19934.86 | -67.94% | 143.08 | 127 | -16.08 | -11.24% | 2020-12-21 01:00
Markham | 2022 | 636134 | 636134 - BRENTWOOD SUBDIVISION VAUGHAN / I&C WO | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Sabbah, Amir | Dave Lindsay | 117378.53 | 108199.82 | -9178.71 | -7.82% | 27082.81 | 24477.46 | -2605.35 | -9.62% | 124.17 | 553.36 | 429.19 | 345.6% | 577.55 | 1475 | 897.45 | 155.4% | 89594 | 81694 | -7900 | -8.818% | 45.17 | 58 | 12.83 | 28.4% | 2022-12-08 01:00
Markham | 2021 | 636143 | 636143 - 2021 POLE REPLACEMENTS- MARKHAM - HIGHWAY 7 CROSSING- MTO | 99 | COMPLETE | BOM cost variance | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Macdonald, Larry | 34803.44 | 30893.47 | -3909.97 | -11.23% | 8891.42 | 9417 | 525.58 | 5.911% | 13049.08 | 8091.37 | -4957.71 | -37.99% | 1522.94 | 2346 | 823.06 | 54.04% | 11340 | 11039.1 | -300.9 | -2.653% | 53.89 | 96.5 | 42.61 | 79.07% | 2021-03-17 01:00
Markham | 2020 | 636148 | 636148 - BATHURST ST. - #12955 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 75811.88 | 66532.02 | -9279.86 | -12.24% | 24951.27 | 22234.34 | -2716.93 | -10.89% | 27115.4 | 30287.23 | 3171.83 | 11.7% | 4050.71 | 4525 | 474.29 | 11.71% | 19694.5 | 9485.45 | -10209.05 | -51.84% | 351.46 | 227.5 | -123.96 | -35.27% | 2020-10-14 01:00
Markham | 2020 | 636201 | 636201 - 1100 RODICK RD / ICI PAD TX UPGRADE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 116651.07 | 99727.72 | -16923.35 | -14.51% | 18232.41 | 16440.34 | -1792.07 | -9.829% | 51718.12 | 51416.47 | -301.65 | -0.5833% | 1653.74 | 1846.5 | 192.76 | 11.66% | 45046.8 | 30024.41 | -15022.39 | -33.35% | 216.2 | 143.01 | -73.19 | -33.85% | 2020-08-20 01:00
Markham | 2020 | 636210 | 636210 - JOINT USE PERMIT HE2020-018, CHURCH STREET, RICHMOND HILL | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 5560.75 | 4596.36 | -964.39 | -17.34% | 2730.31 | 1621.68 | -1108.63 | -40.6% | 0 | 0 | 0 |  | 130.44 | 474.68 | 344.24 | 263.9% | 2700 | 2500 | -200 | -7.407% | 12.96 | 9 | -3.96 | -30.56% | 2020-08-17 01:00
Markham | 2022 | 636227 | ICI POLE RELOCATION/130 ST JOHNS SIDEROAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Paterson, Greg | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-15 01:00
Markham | 2022 | 636242 | ICI SERVICE UPGRADE/ 12 BOND CRES | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Diefenbaker, Trevor A | Wong, Henry | 0 | 985.07 | 985.07 |  | 0 | 985.07 | 985.07 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-02 01:00
Markham | 2021 | 636249 | 636249 - TRANSIT CITY (EAST BLOCK) – SUBD CONDO TOWER EDS | 99 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Graham, Bruce W. | Dave Lindsay | 610216.29 | 613590.2 | 3373.91 | 0.5529% | 99774.81 | 123006.14 | 23231.33 | 23.28% | 8472.08 | 23443.25 | 14971.17 | 176.7% | 8346.76 | 10051.5 | 1704.74 | 20.42% | 493622.64 | 455279.34 | -38343.3 | -7.768% | 726.94 | 809 | 82.06 | 11.29% | 2021-09-15 01:00
Markham | 2020 | 636250 | 636250 - 45 FONTHILL - ESA EMERGING PROJECT - REAR LOT CONDUCTOR HEIGHT ADJUSTMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 19403.83 | 19451.12 | 47.29 | 0.2437% | 7879.23 | 8181.95 | 302.72 | 3.842% | 1538.84 | 1453.68 | -85.16 | -5.534% | 1694.6 | 1021.28 | -673.32 | -39.73% | 8291.16 | 8794.21 | 503.05 | 6.067% | 97.91 | 92 | -5.91 | -6.036% | 2020-07-21 01:00
Markham | 2021 | 636271 | 636271 - BERCZY GLEN PHASE 1 - ROMAN PROPERTY / I&C WO | 99 | COMPLETE | Estimate incorrect | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 100623.51 | 932265.8 | 831642.29 | 826.5% | 73554.22 | 48379.37 | -25174.85 | -34.23% | 15514.01 | 17667.54 | 2153.53 | 13.88% | 7775.28 | 2409 | -5366.28 | -69.02% | 3780 | 2795 | -985 | -26.06% | 464.04 | 261.25 | -202.79 | -43.7% | 2021-12-08 01:00
Markham | 2021 | 636273 | 636273 - BERCZY GLEN PHASE 1 - RINAS PROPERTY / I&C WO | 99 | COMPLETE | Estimate incorrect | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 46054.78 | 268307.39 | 222252.61 | 482.6% | 39537.17 | 25542.31 | -13994.86 | -35.4% | 4114.43 | 0 | -4114.43 | -100% | 2403.18 | 736 | -1667.18 | -69.37% | 0 | 0 | 0 |  | 193.74 | 117.5 | -76.24 | -39.35% | 2021-12-08 01:00
Markham | 2020 | 636295 | 636295 - HUNTINGTON AND LANGSTAFF | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Macdonald, Larry | 25111.37 | 13474.65 | -11636.72 | -46.34% | 12125.51 | 8494.08 | -3631.43 | -29.95% | 4128.66 | 2369.75 | -1758.91 | -42.6% | 1804.8 | 1382.32 | -422.48 | -23.41% | 7052.4 | 1228.5 | -5823.9 | -82.58% | 65.87 | 41 | -24.87 | -37.76% | 2020-12-10 01:00
Markham | 2020 | 636304 | 636304 - JOINT USE PERMIT #HE2020-024, HIGHWAY 27, VAUGHAN | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdonald, Larry | 6117.71 | 4439.49 | -1678.22 | -27.43% | 2589.72 | 1183.49 | -1406.23 | -54.3% | 0 | 0 | 0 |  | 125.99 | 106 | -19.99 | -15.87% | 3402 | 3150 | -252 | -7.407% | 11.97 | 4 | -7.97 | -66.58% | 2020-08-14 01:00
Markham | 2021 | 636308 | 636308 - 9111 KEELE ST / ICI PAD TX INSTALLATION | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 63007.13 | 65254.19 | 2247.06 | 3.566% | 15337.1 | 17670.12 | 2333.02 | 15.21% | 25211.53 | 25181.88 | -29.65 | -0.1176% | 1265.34 | 2625.33 | 1359.99 | 107.5% | 21193.16 | 19776.86 | -1416.3 | -6.683% | 158.65 | 145 | -13.65 | -8.604% | 2021-04-27
Markham | 2020 | 636313 | 636313 - ICI PADMOUNT TX INSTALLATION/120 EAGLE ROCK WAY | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 110642.28 | 95711.25 | -14931.03 | -13.49% | 18625.82 | 21817.29 | 3191.47 | 17.13% | 53850.47 | 51417.51 | -2432.96 | -4.518% | 1667.39 | 3869.35 | 2201.96 | 132.1% | 36498.6 | 18607.1 | -17891.5 | -49.02% | 97.79 | 149 | 51.21 | 52.37% | 2020-12-21 01:00
Markham | 2020 | 636314 | 636314 - PARENT W.O. FOR INSPECT/CONNECT/I&C - CP CAPITAL INVESTMENTS | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 329086.91 | 323259.24 | -5827.67 | -1.771% | 37918.86 | 48865.22 | 10946.36 | 28.87% | 1262.93 | 1295.07 | 32.14 | 2.545% | 1881 | 6409.95 | 4528.95 | 240.8% | 288024.12 | 266689 | -21335.12 | -7.407% | 281 | 236.5 | -44.5 | -15.84% | 2020-12-21 01:00
Markham | 2020 | 636408 | 19TH AVENUE, BAYVIEW TO LESLIE - ALECTRA FUNDED | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-06 01:00
Markham | 2022 | 636429 | 636429 - ICI NEW APARTMENT/ 4310 HWY 7 | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 72684 | 68807.52 | -3876.48 | -5.333% | 26508.38 | 14577.67 | -11930.71 | -45.01% | 56731.73 | 46656.23 | -10075.5 | -17.76% | 3153.89 | 1105 | -2048.89 | -64.96% | 8640 | 6468.62 | -2171.38 | -25.13% | 162.54 | 117 | -45.54 | -28.02% | 2022-02-11 01:00
Markham | 2022 | 636449 | 636449 - ICI NEW REC CENTRE CONNECCTION/ 371 CORNELL CENTRE BLVD | 95 | COMPLETE | Under 10% | N/A | N/A | Joshi, Namrata | No | Diefenbaker, Trevor A | Dave Lindsay | 64329.93 | 60198.23 | -4131.7 | -6.423% | 21155.17 | 22852.51 | 1697.34 | 8.023% | 18716.6 | 18873.52 | 156.92 | 0.8384% | 2318.16 | 3563.5 | 1245.34 | 53.72% | 22140 | 14908.7 | -7231.3 | -32.66% | 136.42 | 208.5 | 72.08 | 52.84% | 2022-05-05
Markham | 2020 | 636469 | 1623 WELLINGTON ST, AURORA - NEW 3 PHASE SERVICE | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-05
Markham | 2022 | 636488 | 636488 - DUCHESS OF OXFORD MODERN | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Alarcon, Alejandro | Dave Lindsay | 285796.16 | 283364 | -2432.16 | -0.851% | 57756.46 | 60733 | 2976.54 | 5.154% | 3643.89 | 0 | -3643.89 | -100% | 3462.81 | 1698 | -1764.81 | -50.96% | 220933 | 220933 | 0 | 0% | 246.13 | 213.5 | -32.63 | -13.26% | 2022-05-05
Markham | 2022 | 636498 | 636498 - 4 ADDISON HALL CIRCLE, AURORA - 3 PHASE SERVICE | 99 | ANALYZE |  |  |  | Cranley, Stephen | No | Harris, Geoff L. | Dave Lindsay | 58561.91 | 54288.1 | -4273.81 | -7.298% | 15171.84 | 10816.29 | -4355.55 | -28.71% | 39806.73 | 39299.67 | -507.06 | -1.274% | 1443.86 | 933.5 | -510.36 | -35.35% | 2139.48 | 3238.64 | 1099.16 | 51.38% | 94.15 | 82.5 | -11.65 | -12.37% | 2022-10-07 01:00
Markham | 2022 | 636507 | 636507 - POLE INSTALLATION DONNA MAE SUBDIVISION | 95 | COMPLETE | Labour est. over | Cont Est Over | N/A | Penner, Mitchell | No | Alarcon, Alejandro | Reginald Clarke | 32644.84 | 22267.33 | -10377.51 | -31.79% | 16994.61 | 11093.99 | -5900.62 | -34.72% | 6733.31 | 7098.02 | 364.71 | 5.417% | 1516.92 | 1788 | 271.08 | 17.87% | 7400 | 2287.32 | -5112.68 | -69.09% | 59.58 | 48 | -11.58 | -19.44% | 2022-06-08 01:00
Markham | 2020 | 636529 | 636529 - POPLAR POLE REPLACE AND MAKE READY FOR SUBD | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 15700.1 | 13194.2 | -2505.9 | -15.96% | 9855.55 | 4105.67 | -5749.88 | -58.34% | 2061.65 | 1800.78 | -260.87 | -12.65% | 1460.9 | 341 | -1119.9 | -76.66% | 2322 | 6946.75 | 4624.75 | 199.2% | 115.61 | 21 | -94.61 | -81.84% | 2020-07-08 01:00
Markham | 2020 | 636541 | 636541 - VIA RENZO DR. - #60, PHASE 2 | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 18768.03 | 26411.85 | 7643.82 | 40.73% | 16171.1 | 20955.18 | 4784.08 | 29.58% | 696.97 | 0 | -696.97 | -100% | 1341.06 | 5249.02 | 3907.96 | 291.4% | 558.9 | 207.65 | -351.25 | -62.85% | 148.15 | 164.5 | 16.35 | 11.04% | 2020-11-23 01:00
Markham | 2021 | 636542 | 636542 - 25 STEELE VALLEY RD / ICI 1PH PAD TX INSTALLATION | 99 | COMPLETE | Cont Est Over | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 28817.08 | 32636.37 | 3819.29 | 13.25% | 10850.58 | 13855.5 | 3004.92 | 27.69% | 7242.08 | 7653.32 | 411.24 | 5.678% | 1004.42 | 2628.83 | 1624.41 | 161.7% | 9720 | 8498.72 | -1221.28 | -12.56% | 53.7 | 90 | 36.3 | 67.6% | 2021-07-21 01:00
Markham | 2022 | 636551 | 636551 - 2021 CABLE INJECTION - V37 - LANGSTAFF & WESTON RD, VAUGHAN | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 2209530.91 | 182707.12 | -2026823.79 | -91.73% | 5920.61 | 182707.12 | 176786.51 | 2986% | 29311.1 | 0 | -29311.1 | -100% | 0 | 0 | 0 |  | 2174299.2 | 0 | -2174299.2 | -100% | 0 | 1517.5 | 1517.5 |  | 2022-02-08 01:00
Markham | 2021 | 636552 | 636552 - 2021 CABLE INJECTION - M15 - 16TH AVE & MARKHAM RD, MARKHAM | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 246208.77 | 252974.44 | 6765.67 | 2.748% | 5920.61 | 35482.07 | 29561.46 | 499.3% | 24720.16 | 6524.42 | -18195.74 | -73.61% | 0 | 0 | 0 |  | 215568 | 210967.95 | -4600.05 | -2.134% | 0 | 0 | 0 |  | 2021-12-06 01:00
Markham | 2021 | 636554 | 636554 - 2021 CABLE INJECTION - M14 - HWY 7 & 9TH LINE RD, MARKHAM | 99 | COMPLETE | Cont Est Under | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 262697.21 | 725722.22 | 463025.01 | 176.3% | 5920.61 | 96260.61 | 90340 | 1526% | 23496.6 | 14839.98 | -8656.62 | -36.84% | 0 | 0 | 0 |  | 233280 | 614621.63 | 381341.63 | 163.5% | 0 | 0 | 0 |  | 2021-12-06 01:00
Markham | 2021 | 636555 | 636555 - 2021 CABLE INJECTION - M20 - 14TH AVE & MCCOWAN RD, MARKHAM | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 589042.5 | 577826.8 | -11215.7 | -1.904% | 5920.61 | 78296.3 | 72375.69 | 1222% | 42365.89 | 7921.81 | -34444.08 | -81.3% | 0 | 0 | 0 |  | 540756 | 491608.69 | -49147.31 | -9.089% | 0 | 0 | 0 |  | 2021-12-06 01:00
Markham | 2021 | 636602 | 636602 - STORM HARDENING - HUNTINGTON - RUTHERFORD TO LANGSTAFF - VAUGHAN | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 977426.7 | 364389.42 | -613037.28 | -62.72% | 158892.04 | 35992.89 | -122899.15 | -77.35% | 318633.88 | 87103.07 | -231530.81 | -72.66% | 39002.84 | 0 | -39002.84 | -100% | 460897.94 | 241293.46 | -219604.48 | -47.65% | 0 | 0 | 0 |  | 2021-05-29 01:00
Markham | 2022 | 636603 | 636603 - STORM HARDENING - WESTON - HWY 7 TO LANGSTAFF - VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Wong, Henry | 613454.34 | 0 | -613454.34 | -100% | 172454.86 | 0 | -172454.86 | -100% | 336013.13 | 0 | -336013.13 | -100% | 48286.35 | 0 | -48286.35 | -100% | 56700 | 0 | -56700 | -100% | 1555.88 | 0 | -1555.88 | -100% | 2021-12-03 01:00
Markham | 2021 | 636604 | 636604 - STORM HARDENING - HWY 27 - MAJOR MACKENZIE TO RUTHERFORD - VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Wong, Henry | 728197.05 | -4415.05 | -732612.1 | -100.6% | 209460.27 | -4415.05 | -213875.32 | -102.1% | 338883.91 | 0 | -338883.91 | -100% | 60944.87 | 0 | -60944.87 | -100% | 118908 | 0 | -118908 | -100% | 1893.12 | 0 | -1893.12 | -100% | 2021-12-03 01:00
Markham | 2021 | 636605 | 636605 - STORM HARDENING - HWY 7 - COCHRANE DR TO LESLIE ST - MARKHAM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 214480.89 | 241748.17 | 27267.28 | 12.71% | 38325.86 | 21498.06 | -16827.8 | -43.91% | 83772.71 | 83993.48 | 220.77 | 0.2635% | 9708.32 | 0 | -9708.32 | -100% | 82674 | 136256.63 | 53582.63 | 64.81% | 0 | 0 | 0 |  | 2021-12-03 01:00
Markham | 2021 | 636606 | 636606 - STORM HARDENING - CENTRE ST - HWY 7 TO GREENWOOD TS - MARKHAM | 99 | COMPLETE | Covid-19 | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Ryan Walsh | 121621.12 | 169516.25 | 47895.13 | 39.38% | 38381.72 | 58595.27 | 20213.55 | 52.66% | 48370.4 | 49162.49 | 792.09 | 1.638% | 2839 | 15852 | 13013 | 458.4% | 32030 | 45906.49 | 13876.49 | 43.32% | 551 | 513 | -38 | -6.897% | 2021-05-11
Markham | 2022 | 636633 | 636633 - STORM HARDENING - MAJOR MACKENZIE DR - WESTON RD TO JANE ST - VAUGHAN | 99 | COMPLETE | Cont Est Under | Labour est. under | Est. Int. - Act. External | Tenorlas, Reynaldo | Yes | Roy, James | Reginald Clarke | 298015.76 | 552910.07 | 254894.31 | 85.53% | 60261.29 | 123360.18 | 63098.89 | 104.7% | 163230.47 | 118617.64 | -44612.83 | -27.33% | 14314 | 37425.94 | 23111.94 | 161.5% | 60210 | 273506.31 | 213296.31 | 354.3% | 513.25 | 1046 | 532.75 | 103.8% | 2022-01-25 01:00
Markham | 2021 | 636656 | 636656 - 2021 CABLE INJECTION, M51 - 14TH-BAYVIEW-STEELES-YONGE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 262709.51 | 175924.49 | -86785.02 | -33.03% | 5920.61 | 25576.35 | 19655.74 | 332% | 28206.9 | 0 | -28206.9 | -100% | 0 | 0 | 0 |  | 228582 | 150348.14 | -78233.86 | -34.23% | 0 | 8 | 8 |  | 2021-11-19 01:00
Markham | 2021 | 636663 | 636663 - 2021 UG CABLE REPLACEMENT - V44, WALLACE, FAIRGROUND, PARK, WAKELIN, YELLOW PINE | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 729422.31 | 765153.17 | 35730.86 | 4.899% | 80609.15 | 167566.47 | 86957.32 | 107.9% | 18623.45 | 17786.48 | -836.97 | -4.494% | 12865.31 | 17797.24 | 4931.93 | 38.34% | 617324.4 | 562002.98 | -55321.42 | -8.961% | 624.8467 | 644.5 | 19.6533 | 3.145% | 2021-09-10 01:00
Markham | 2020 | 636664 | 636664 - PARENT W.O. FOR INSPECT/CONNE/I&C CENTERFIELD 2A DEVELOPMENT | 99 | COMPLETE | Estimate incorrect | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 42845.41 | 371990.05 | 329144.64 | 768.2% | 28437.26 | 9059 | -19378.26 | -68.14% | 4905.61 | 0 | -4905.61 | -100% | 1942.54 | 865.93 | -1076.61 | -55.42% | 7560 | 7000 | -560 | -7.407% | 222.04 | 50 | -172.04 | -77.48% | 2020-12-07 01:00
Markham | 2022 | 636704 | 636704 - 73 WOOTEN WAY N / ICI PAD TX INSTALLATION | 98 | ANALYZE |  |  |  | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 64178.32 | 69055.49 | 4877.17 | 7.599% | 20802.33 | 19464.05 | -1338.28 | -6.433% | 18188.71 | 19256.39 | 1067.68 | 5.87% | 2496.48 | 1824.5 | -671.98 | -26.92% | 22690.8 | 28510.55 | 5819.75 | 25.65% | 138.21 | 118.5 | -19.71 | -14.26% | 2022-10-07 01:00
Markham | 2022 | 636706 | 636706 - HUNTINGTON RD. - #7900 INDUSTRIAL/COMMERCIAL | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 63764.18 | 68146.06 | 4381.88 | 6.872% | 27937.56 | 26662.29 | -1275.27 | -4.565% | 35435.86 | 25933.28 | -9502.58 | -26.82% | 3146.54 | 1899 | -1247.54 | -39.65% | 19594.22 | 13651.49 | -5942.73 | -30.33% | 173.26 | 204.5 | 31.24 | 18.03% | 2022-10-07 01:00
Markham | 2020 | 636734 | 636734 - POLE RELOCATION FOR BERCZY GLEN SUBDIVISION | 99 | COMPLETE | Scope – Eng | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 13787.54 | 6980.46 | -6807.08 | -49.37% | 6601.73 | 4762.46 | -1839.27 | -27.86% | 1365.99 | 0 | -1365.99 | -100% | 1061.88 | 268 | -793.88 | -74.76% | 4757.94 | 1950 | -2807.94 | -59.02% | 37.56 | 16 | -21.56 | -57.4% | 2020-09-18 01:00
Markham | 2020 | 636740 | 636740 - POLE REPLACEMENT 2020 - REPLACE P41431 AT YONGE ST & DUNLOP ST | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Larry | 38572.74 | 32146.58 | -6426.16 | -16.66% | 17649.63 | 13011.05 | -4638.58 | -26.28% | 6932.45 | 7701.04 | 768.59 | 11.09% | 2218.66 | 4913.64 | 2694.98 | 121.5% | 11772 | 6520.85 | -5251.15 | -44.61% | 227.72 | 130 | -97.72 | -42.91% | 2020-11-20 01:00
Markham | 2020 | 636747 | POLE REPLACEMENT 2020 - 41 GUARDSMAN RD | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-12 01:00
Markham | 2021 | 636872 | 636872 - AMBER MS F2 FEEDER CONVERSION | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Ryan Walsh | 735554.01 | 749194.89 | 13640.88 | 1.855% | 272410.58 | 265188.75 | -7221.83 | -2.651% | 242424.88 | 250093.35 | 7668.47 | 3.163% | 55455.06 | 73381.07 | 17926.01 | 32.33% | 165263.49 | 157659.32 | -7604.17 | -4.601% | 2965.71 | 2960 | -5.71 | -0.1925% | 2021-05-11
Markham | 2021 | 636895 | 636895 - PRATO ESTATES - AURORA 2B / I&C WO | 99 | COMPLETE | Estimate incorrect | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 19907.53 | 115059.3 | 95151.77 | 478% | 13605.44 | 13970.44 | 365 | 2.683% | 1639.06 | 3663.66 | 2024.6 | 123.5% | 613.03 | 1373 | 759.97 | 124% | 4050 | 3750 | -300 | -7.407% | 59.32 | 83 | 23.68 | 39.92% | 2021-11-11 01:00
Markham | 2021 | 636949 | 636949 - DUCT INSTALLATION 9075 9085 JANE ST | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Shane Christopher | 3167.38 | 2341.5 | -825.88 | -26.07% | 2987.38 | 2053.5 | -933.88 | -31.26% | 0 | 0 | 0 |  | 180 | 288 | 108 | 60% | 0 | 0 | 0 |  | 20 | 18 | -2 | -10% | 2021-06-17 01:00
Markham | 2020 | 636957 | 19TH AV - LESLIE TO WOODBINE/ HWY 404 CROSSING | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-10 01:00
Markham | 2020 | 636960 | HUNTINGTON - TEMPORARY CUSTOMER POLE INSTALLATION | 99 | COMPLETE | BOM not accurate | Labour est. over | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Steve | 11750.86 | 7038.23 | -4712.63 | -40.1% | 5387.23 | 2402.44 | -2984.79 | -55.4% | 5315.03 | 3565.79 | -1749.24 | -32.91% | 1048.6 | 1070 | 21.4 | 2.041% | 0 | 0 | 0 |  | 71.89 | 30 | -41.89 | -58.27% | 2020-06-10 01:00
Markham | 2021 | 636961 | 636961 - HYDRO POLE RELOCATION AT YONGE STREET & TYLER STREET IN AURORA | 99 | COMPLETE | Under 10% | N/A | N/A | Lacombe, Joel | No | Watters, Maxwell | Shane Christopher | 489695.76 | 466688.87 | -23006.89 | -4.698% | 21246.91 | 47394.75 | 26147.84 | 123.1% | 33055.23 | 35292.07 | 2236.84 | 6.767% | 3330.98 | 856 | -2474.98 | -74.3% | 432062.64 | 383146.05 | -48916.59 | -11.32% | 103.02 | 56.5 | -46.52 | -45.16% | 2021-10-25 01:00
Markham | 2022 | 636970 | 636970 - ANGLIN SUBDIVISION / I&C WO | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Sabbah, Amir | Dave Lindsay | 114263.04 | 32713.13 | -81549.91 | -71.37% | 30681.71 | 22143.68 | -8538.03 | -27.83% | 2446.13 | 8108.45 | 5662.32 | 231.5% | 1596.2 | 2341 | 744.8 | 46.66% | 79539 | 0 | -79539 | -100% | 123.64 | 133.5 | 9.86 | 7.975% | 2022-10-07 01:00
Markham | 2021 | 637007 | 637007 - ICI INDUSTRIAL BUILDING/ 27 DIRECTOR COURT | 99 | COMPLETE | BOM cost variance | Labour est. over | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 118111.78 | 120087.48 | 1975.7 | 1.673% | 29672.01 | 21464.48 | -8207.53 | -27.66% | 94805.87 | 76530.8 | -18275.07 | -19.28% | 3502.9 | 3313 | -189.9 | -5.421% | 12481 | 18779.2 | 6298.2 | 50.46% | 179.12 | 167.5 | -11.62 | -6.487% | 2021-11-11 01:00
Markham | 2020 | 637015 | 637015 - UG CABLE REPLACEMENT - A01 TAMARAC TRAIL - A01TP2105 TO A01TP2130 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 109219.23 | 29290.43 | -79928.8 | -73.18% | 9762.31 | 7781.74 | -1980.57 | -20.29% | 2597.7 | 6796.5 | 4198.8 | 161.6% | 754.34 | 420.02 | -334.32 | -44.32% | 96104.88 | 14292.17 | -81812.71 | -85.13% | 55.48 | 38 | -17.48 | -31.51% | 2020-12-08 01:00
Markham | 2020 | 637039 | GUARDSMAN RD. EASTSIDE - #48 | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-05-21
Markham | 2021 | 637056 | 637056 - ICI NEW SERVICE/ 10192 9TH LINE | 99 | COMPLETE | Labour est. under | Cont Est Under | N/A | Joshi, Namrata | No | Diefenbaker, Trevor A | Dave Lindsay | 87145.03 | 71736.03 | -15409 | -17.68% | 26511.95 | 17270.9 | -9241.05 | -34.86% | 32614.27 | 32293.61 | -320.66 | -0.9832% | 4258.81 | 3903.28 | -355.53 | -8.348% | 23760 | 18268.24 | -5491.76 | -23.11% | 184.75 | 148.5 | -36.25 | -19.62% | 2021-10-08 01:00
Markham | 2021 | 637057 | 637057 - ICI NEW COMMERCIAL SERVICE/ 7896 HUNTINGTON RD | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 77482.03 | 58121.63 | -19360.4 | -24.99% | 25022.13 | 12470.96 | -12551.17 | -50.16% | 36973.53 | 36047.7 | -925.83 | -2.504% | 3922.81 | 2918.97 | -1003.84 | -25.59% | 11563.56 | 6684 | -4879.56 | -42.2% | 76.75 | 109 | 32.25 | 42.02% | 2021-05-26 01:00
Markham | 2020 | 637072 | 637072 - 7800 JANE ST / ICI PAD TX DEMO | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 15383.7 | 0 | -15383.7 | -100% | 6300.29 | 0 | -6300.29 | -100% | 0 | 0 | 0 |  | 774.97 | 0 | -774.97 | -100% | 8308.44 | 0 | -8308.44 | -100% | 69.03 | 0 | -69.03 | -100% | 2021-10-13 01:00
Markham | 2020 | 637105 | 637105 - LESLIE ST. AT EAST & WEST WILMOT RD. - N/E CORNER | 99 | COMPLETE | Civil contractor | Labour est. under | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 34813.38 | 41873.99 | 7060.61 | 20.28% | 9507.07 | 12204.7 | 2697.63 | 28.37% | 6500.83 | 7100.2 | 599.37 | 9.22% | 1224.81 | 1434 | 209.19 | 17.08% | 17580.67 | 21135.09 | 3554.42 | 20.22% | 56.78 | 83.5 | 26.72 | 47.06% | 2020-09-15 01:00
Markham | 2020 | 637155 | 637155 - LESLIE ST AT EAST & WEST BEAVER CREEK RD - XXX CORNER / ICI 1PH PAD TX | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 49785.26 | 51984.71 | 2199.45 | 4.418% | 15599.6 | 17712.21 | 2112.61 | 13.54% | 5669.86 | 5475.12 | -194.74 | -3.435% | 1804.92 | 4488.59 | 2683.67 | 148.7% | 26710.88 | 24308.79 | -2402.09 | -8.993% | 89.2 | 123.5 | 34.3 | 38.45% | 2020-12-21 01:00
Markham | 2021 | 637204 | PARENT W.O FOR INSPECT/CONNECT/I&C - NASHVILLE HEIGHTS - MEDIUM DENSITY BLOCK | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 299943.32 | 297123.02 | -2820.3 | -0.9403% | 42154.17 | 39867.85 | -2286.32 | -5.424% | 2012.93 | 1566.35 | -446.58 | -22.19% | 1835.22 | 2890 | 1054.78 | 57.47% | 253941 | 252798.82 | -1142.18 | -0.4498% | 150.54 | 144.25 | -6.29 | -4.178% | 2021-12-07 01:00
Markham | 2022 | 637206 | 637206 - MAPLE PARK HOMES SUBDIVISION | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Swales, Mathew | Dave Lindsay | 145541.8 | 139684.06 | -5857.74 | -4.025% | 34000.86 | 31221.17 | -2779.69 | -8.175% | 5185.26 | 2784.89 | -2400.37 | -46.29% | 3073.68 | 2396 | -677.68 | -22.05% | 103282 | 103282 | 0 | 0% | 167.08 | 119.5 | -47.58 | -28.48% | 2022-10-07 01:00
Markham | 2021 | 637282 | 637282 - JOINT USE HE2020-046- RIVERMEDE RD.- KEELE ST. TO RAYETTE DR. | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 16977.34 | 7507.92 | -9469.42 | -55.78% | 4180.42 | 3202.92 | -977.5 | -23.38% | 884.89 | 0 | -884.89 | -100% | 474.83 | 615 | 140.17 | 29.52% | 11437.2 | 3690 | -7747.2 | -67.74% | 21.18 | 18 | -3.18 | -15.01% | 2021-03-17 01:00
Markham | 2021 | 637321 | 637321 - PENNON RD. - #43 | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 40521.45 | 26674.94 | -13846.51 | -34.17% | 19147.73 | 11381.56 | -7766.17 | -40.56% | 11976.65 | 9865.89 | -2110.76 | -17.62% | 3168.49 | 2014.1 | -1154.39 | -36.43% | 6228.58 | 3413.39 | -2815.19 | -45.2% | 223 | 90 | -133 | -59.64% | 2021-05-26 01:00
Markham | 2021 | 637324 | 637324 - 150 ADDISON HALL CIRCLE/AUR/NS/3 PHASE PAD | 99 | COMPLETE | BOM not accurate | Labour est. over | N/A | Cranley, Stephen | No | Harris, Geoff L. | Dave Lindsay | 67756.8 | 54695.41 | -13061.39 | -19.28% | 15197.73 | 10937.54 | -4260.19 | -28.03% | 45494.77 | 36641.61 | -8853.16 | -19.46% | 1563.86 | 805 | -758.86 | -48.52% | 5500.44 | 6311.26 | 810.82 | 14.74% | 162.25 | 57 | -105.25 | -64.87% | 2021-11-11 01:00
Markham | 2020 | 637354 | 637354 - POLE REPLACEMENT KING AND BOND MINICIPAL SEMIS | 99 | COMPLETE | Labour est. over | Cont Est Over |  | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 43127.24 | 20845.66 | -22281.58 | -51.66% | 15392.8 | 11044.64 | -4348.16 | -28.25% | 6190.48 | 2547.83 | -3642.65 | -58.84% | 2673.12 | 1650 | -1023.12 | -38.27% | 18870.84 | 5603.19 | -13267.65 | -70.31% | 105.04 | 97 | -8.04 | -7.654% | 2020-11-24 01:00
Markham | 2021 | 637455 | 637455 - 5440 16TH AVE / MAR / NS / 3PH PAD TX | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 77027.38 | 69102.45 | -7924.93 | -10.29% | 23928.48 | 22568.74 | -1359.74 | -5.683% | 36441.03 | 31356 | -5085.03 | -13.95% | 3484.03 | 4274.24 | 790.21 | 22.68% | 13173.84 | 10903.47 | -2270.37 | -17.23% | 167.53 | 197 | 29.47 | 17.59% | 2021-11-11 01:00
Markham | 2020 | 637456 | 637456 - ANCHOR RELOCATION ULTRA TOWN INC. | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 10742.04 | 9016.6 | -1725.44 | -16.06% | 5027.66 | 4584.1 | -443.56 | -8.822% | 912.58 | 869.81 | -42.77 | -4.687% | 265.8 | 606 | 340.2 | 128% | 4536 | 2956.69 | -1579.31 | -34.82% | 17.4 | 14 | -3.4 | -19.54% | 2020-12-10 01:00
Markham | 2020 | 637463 | 637463 - ISLINGTON AVE. - 10391 (KLEIMNBURG PUBLIC SCHOOL) | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-15 01:00
Markham | 2022 | 637508 | 637508 - 300 EARL STEWART DR/AURORA/NS/3PH PAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Dave Lindsay | 66901.8 | 82367.49 | 15465.69 | 23.12% | 26719.79 | 20127.14 | -6592.65 | -24.67% | 41708.15 | 33311.64 | -8396.51 | -20.13% | 3813.86 | 3075.28 | -738.58 | -19.37% | 17010 | 25853.43 | 8843.43 | 51.99% | 172.14 | 154 | -18.14 | -10.54% | 2022-02-11 01:00
Markham | 2020 | 637509 | 637509 - UG CABLE REPLACEMENT - V40 GREENBROOKE DR - 40-37 TO 40-22 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 56705.54 | 51198.87 | -5506.67 | -9.711% | 7812.15 | 9011.2 | 1199.05 | 15.35% | 2032.46 | 1595.34 | -437.12 | -21.51% | 485.73 | 339.47 | -146.26 | -30.11% | 46375.2 | 40252.86 | -6122.34 | -13.2% | 36.56 | 26 | -10.56 | -28.88% | 2020-11-02 01:00
Markham | 2021 | 637524 | 637524 - 9560 ISLINGTON AVE / VAU / NS / 3PH PAD TX | 99 | COMPLETE | BOM not accurate | Cont Est Over | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 105494.27 | 96143.92 | -9350.35 | -8.863% | 19953.75 | 19801.77 | -151.98 | -0.7617% | 45895.43 | 36514.58 | -9380.85 | -20.44% | 2595.09 | 3255 | 659.91 | 25.43% | 59400 | 36572.57 | -22827.43 | -38.43% | 131.01 | 134 | 2.99 | 2.282% | 2021-09-15 01:00
Markham | 2022 | 637531 | 637531 - 21 AND 31 PERFORMANCE DR/RHL/NS/3PH PAD | 95 | COMPLETE | Material Under Estimated | Labour est. under | N/A | Joshi, Namrata | No | Diefenbaker, Trevor A | Dave Lindsay | 109448.55 | 136325.39 | 26876.84 | 24.56% | 14973.38 | 19955.53 | 4982.15 | 33.27% | 60899.89 | 79925.31 | 19025.42 | 31.24% | 1175.28 | 1689 | 513.72 | 43.71% | 32400 | 34755.55 | 2355.55 | 7.27% | 81.37 | 158.5 | 77.13 | 94.79% | 2022-12-08 01:00
Markham | 2020 | 637537 | 637537 - PORTAGE PKWY #898 - TEMPORARY RECOVERY | 99 | COMPLETE | Cont Est Under | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 15206.34 | 19620.87 | 4414.53 | 29.03% | 11303.29 | 11879.49 | 576.2 | 5.098% | 2724.58 | 2530.61 | -193.97 | -7.119% | 1178.47 | 2695.6 | 1517.13 | 128.7% | 0 | 2515.17 | 2515.17 |  | 108.15 | 128 | 19.85 | 18.35% | 2020-08-17 01:00
Markham | 2020 | 637554 | 637554 - TX REMOVAL WOODEND PLACE DEVELOPMENT (PHASE) | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Chris Hagan | 25691.42 | 22932.72 | -2758.7 | -10.74% | 9029.66 | 6971.27 | -2058.39 | -22.8% | 460.33 | 0 | -460.33 | -100% | 423.71 | 1487 | 1063.29 | 250.9% | 15777.72 | 14474.45 | -1303.27 | -8.26% | 39.2 | 48 | 8.8 | 22.45% | 2020-10-26 01:00
Markham | 2021 | 637555 | 33 DICKSON HILL ROAD/ MAR/ UP/ 1PH PAD | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Diefenbaker, Trevor A | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-04 01:00
Markham | 2021 | 637556 | 637556 - CREDITSTONE RD. - #777 (EXISTING BUILDING) | 99 | COMPLETE | N/A | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 84033.39 | 76246.26 | -7787.13 | -9.267% | 16571.23 | 11105.97 | -5465.26 | -32.98% | 60719.05 | 58763.22 | -1955.83 | -3.221% | 1909.25 | 2442.79 | 533.54 | 27.95% | 4833.86 | 3934.28 | -899.58 | -18.61% | 182.5 | 108.5 | -74 | -40.55% | 2021-03-04 01:00
Markham | 2021 | 637599 | 637599 - LAWRENCE AVE & PALMER AVE, RICHMOND HILL POLE RELOCATION | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Larry | 23845.35 | 13053.29 | -10792.06 | -45.26% | 13685.71 | 7128.36 | -6557.35 | -47.91% | 2010.3 | 2476.01 | 465.71 | 23.17% | 2857.34 | 1224 | -1633.34 | -57.16% | 5292 | 2224.92 | -3067.08 | -57.96% | 40.1 | 48 | 7.9 | 19.7% | 2021-07-27 01:00
Markham | 2021 | 637600 | 637600 - POLE LINE EXPANSION FOR BERCZY GLEN SUBDIVISION | 99 | COMPLETE | Labour est. over | N/A | N/A | Penner, Mitchell | No | Swales, Mathew | Macdonald, Steve | 92767.21 | 115034.93 | 22267.72 | 24% | 53134.35 | 11620.8 | -41513.55 | -78.13% | 17200.62 | 16230.57 | -970.05 | -5.64% | 11521 | 0 | -11521 | -100% | 10911.24 | 87183.56 | 76272.32 | 699% | 404.66 | 0 | -404.66 | -100% | 2021-09-10 01:00
Markham | 2022 | 637609 | 637609 - 33 COMMERCE VALLEY DR / MAR / UP / CO-STN | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 43437.88 | 46689.12 | 3251.24 | 7.485% | 18623.38 | 21706.06 | 3082.68 | 16.55% | 28300.5 | 19662.61 | -8637.89 | -30.52% | 1514 | 3163 | 1649 | 108.9% | 0 | 2157.45 | 2157.45 |  | 94.03 | 161.5 | 67.47 | 71.75% | 2022-02-11 01:00
Markham | 2022 | 637622 | 637622 - MARKLAND TOWNHOUSE DEVELOPMENT / I&C WO | 99 | ANALYZE |  |  |  | Penner, Mitchell | No | Swales, Mathew | Dave Lindsay | 279602.7 | 273882.77 | -5719.93 | -2.046% | 53783.78 | 52735.97 | -1047.81 | -1.948% | 1765.7 | 1764.8 | -0.9 | -0.05097% | 2335.22 | 1164 | -1171.22 | -50.15% | 221718 | 218218 | -3500 | -1.579% | 198.54 | 142.5 | -56.04 | -28.23% | 2022-07-18 01:00
Markham | 2020 | 637650 | 637650 - 700 APPLEWOOD CRES/ VAU/ SR/ 3PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Steve Rumble | 7877.68 | 2759.84 | -5117.84 | -64.97% | 5814.83 | 2259.84 | -3554.99 | -61.14% | 0 | 0 | 0 |  | 447.17 | 500 | 52.83 | 11.81% | 1615.68 | 0 | -1615.68 | -100% | 33.65 | 15 | -18.65 | -55.42% | 2020-08-25 01:00
Markham | 2022 | 637668 | 637668 - FAIRTREE BLOCK 153 CONDO BLOCK TOWNHOMES / I&C WO | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Swales, Mathew | Dave Lindsay | 562083.63 | 564931.26 | 2847.63 | 0.5066% | 24981.67 | 69997.07 | 45015.4 | 180.2% | 2716.7 | 1936.79 | -779.91 | -28.71% | 2255.22 | 2052 | -203.22 | -9.011% | 532130.04 | 489260.6 | -42869.44 | -8.056% | 186.54 | 193 | 6.46 | 3.463% | 2022-05-05
Markham | 2021 | 637680 | 637680 - CUSTOMER CAPITAL PROJECT FOR MAPLE PARK HOMES SUBDIVISION - POLE UPGRADES | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Macdonald, Larry | 20396.25 | 14986.22 | -5410.03 | -26.52% | 12760.07 | 6954.46 | -5805.61 | -45.5% | 2860.24 | 3352.95 | 492.71 | 17.23% | 1475.94 | 1884 | 408.06 | 27.65% | 3300 | 2794.81 | -505.19 | -15.31% | 62.92 | 48 | -14.92 | -23.71% | 2021-09-16 01:00
Markham | 2020 | 637682 | 230 EDWARD ST, AUR/UP//3PH | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-04 01:00
Markham | 2021 | 637707 | 637707 - JOINT USE HE2020-053 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | O'Gay, Brian | No | Martin, Shane | Don Rothman | 9801.35 | 7215.94 | -2585.41 | -26.38% | 2410.55 | 1423.94 | -986.61 | -40.93% | 0 | 0 | 0 |  | 90 | 122 | 32 | 35.56% | 7300.8 | 5670 | -1630.8 | -22.34% | 4 | 4 | 0 | 0% | 2021-04-21
Markham | 2021 | 637729 | 637729 - JOINT USE PERMIT HE2020-054 | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 22346.6 | 16867.07 | -5479.53 | -24.52% | 4913.63 | 4956.03 | 42.4 | 0.8629% | 1726.35 | 1348.95 | -377.4 | -21.86% | 506.62 | 1148 | 641.38 | 126.6% | 15200 | 9414.09 | -5785.91 | -38.07% | 15.56 | 32 | 16.44 | 105.7% | 2021-10-27 01:00
Markham | 2021 | 637732 | 637732 - 99 GREAT GULF DR / VAU / NS / 3PH PAD | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 57832.7 | 57112.27 | -720.43 | -1.246% | 14300.65 | 14178.29 | -122.36 | -0.8556% | 25491.75 | 24807.98 | -683.77 | -2.682% | 1125.34 | 2460.28 | 1334.94 | 118.6% | 16914.96 | 15665.72 | -1249.24 | -7.385% | 79.19 | 97.5 | 18.31 | 23.12% | 2021-04-27
Markham | 2020 | 637746 | 138,142,148 GREY ALDER AVE - SUBD RES EDS | 99 | CANCELLED | N/A |  |  | D'Onofrio, Tony | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-05-31 01:00
Markham | 2020 | 637805 | 637805 - CUSTOMER CAPTIAL TWO TRANSFOMER & ONE SWITCH REMOVAL FOR BERCZY MARKHAM JOB | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 7863.71 | 4045.67 | -3818.04 | -48.55% | 6862.71 | 3254.54 | -3608.17 | -52.58% | 0 | 0 | 0 |  | 1001 | 791.13 | -209.87 | -20.97% | 0 | 0 | 0 |  | 35.5 | 15 | -20.5 | -57.75% | 2020-09-11 01:00
Markham | 2020 | 637819 | 637819 - UG CABLE RELOCATION - 919 CLARK AVE WEST | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 71354.41 | 67932.72 | -3421.69 | -4.795% | 6456.3 | 11426.8 | 4970.5 | 76.99% | 1638.47 | 0 | -1638.47 | -100% | 456.56 | 647.29 | 190.73 | 41.78% | 62803.08 | 55858.63 | -6944.45 | -11.06% | 37.96 | 53.5 | 15.54 | 40.94% | 2020-10-21 01:00
Markham | 2022 | 637846 | 637846 - 95 & 105 ONEIDA CRES / RHL / 3PH PAD | 99 | COMPLETE | Under 10% | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 82559.03 | 83134.19 | 575.16 | 0.6967% | 11432.63 | 8703.56 | -2729.07 | -23.87% | 70267.85 | 71805.95 | 1538.1 | 2.189% | 858.55 | 709.5 | -149.05 | -17.36% | 0 | 1915.18 | 1915.18 |  | 51.48 | 44 | -7.48 | -14.53% | 2022-02-10 01:00
Markham | 2020 | 637862 | 637862 - 2020 POLE REPLACEMENTS - LONGBRIDGE RD AND BUNKER RD | 99 | COMPLETE | BOM not accurate | Estimate incorrect | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Macdonald, Larry | 78789.36 | 58509.5 | -20279.86 | -25.74% | 31391.9 | 27468.82 | -3923.08 | -12.5% | 17868.42 | 8977.6 | -8890.82 | -49.76% | 6903.04 | 12452.4 | 5549.36 | 80.39% | 22626 | 9610.68 | -13015.32 | -57.52% | 250.23 | 285 | 34.77 | 13.9% | 2020-09-11 01:00
Markham | 2020 | 637869 | 637869 - BOND CRES MAKE READY FOR A SUBD 453133 | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Macdonald, Larry | 13847.08 | 7632.58 | -6214.5 | -44.88% | 6644.03 | 2765.3 | -3878.73 | -58.38% | 6511.65 | 4097.28 | -2414.37 | -37.08% | 691.4 | 770 | 78.6 | 11.37% | 0 | 0 | 0 |  | 24.55 | 21 | -3.55 | -14.46% | 2020-12-04 01:00
Markham | 2021 | 637895 | 637895 - 8025 JANE ST/ VAU/ NS00055586/ CUSTOMER-OWNED STATION | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 120304.23 | 110358.07 | -9946.16 | -8.268% | 41358.32 | 40102.69 | -1255.63 | -3.036% | 42352.99 | 37938.22 | -4414.77 | -10.42% | 8614.44 | 14158 | 5543.56 | 64.35% | 27978.48 | 18159.16 | -9819.32 | -35.1% | 323.21 | 442.5 | 119.29 | 36.91% | 2021-07-21 01:00
Markham | 2021 | 637900 | 637900 - 50 KEYES CRT / VAU / NS / 3PH PAD | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 68817.18 | 67717.51 | -1099.67 | -1.598% | 15570.82 | 14670.95 | -899.87 | -5.779% | 34757.62 | 34774.81 | 17.19 | 0.04946% | 1257.34 | 1834.69 | 577.35 | 45.92% | 17231.4 | 16437.06 | -794.34 | -4.61% | 91.19 | 102.5 | 11.31 | 12.4% | 2021-04-27
Markham | 2021 | 637910 | 637910 - KEYES CRT. - #51 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 99549.8 | 82058.28 | -17491.52 | -17.57% | 23594.84 | 16527.71 | -7067.13 | -29.95% | 50755.26 | 49267.18 | -1488.08 | -2.932% | 2219.62 | 3382.97 | 1163.35 | 52.41% | 22980.08 | 12880.42 | -10099.66 | -43.95% | 138.67 | 171.75 | 33.08 | 23.86% | 2021-03-22 01:00
Markham | 2021 | 637943 | 637943 - YONGE AND SILVER MAPLE/ RHL/ NS/ 3PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 82104.93 | 62718.06 | -19386.87 | -23.61% | 23535.65 | 9470.24 | -14065.41 | -59.76% | 49836.1 | 47287.69 | -2548.41 | -5.114% | 3220.86 | 1618.28 | -1602.58 | -49.76% | 5512.32 | 4341.85 | -1170.47 | -21.23% | 142.15 | 75.75 | -66.4 | -46.71% | 2021-03-22 01:00
Markham | 2021 | 638082 | 638082 - 1SC39 RTU FEED AT LESLIE AND WEST BEAVER CREEK | 99 | COMPLETE | Under 10% |  |  | Tenorlas, Reynaldo | No | Handy, James | Horlings, Jake | 70744.73 | 70082.57 | -662.16 | -0.936% | 8475.16 | 10614.47 | 2139.31 | 25.24% | 895.57 | 0 | -895.57 | -100% | 672.28 | 568 | -104.28 | -15.51% | 60701.72 | 58900.1 | -1801.62 | -2.968% | 45.18 | 28 | -17.18 | -38.03% | 2021-07-07 01:00
Markham | 2022 | 638116 | 638116 - THOMAS COOK AVE. - #2, CARVILLE COMMUNITY CENTRE, LIBRARY AND DISTRICT PARK | 95 | ANALYZE |  |  |  | Joshi, Namrata | No | Yuen, Paul | Dave Lindsay | 90529.99 | 69845.58 | -20684.41 | -22.85% | 27229.47 | 13221.79 | -14007.68 | -51.44% | 57919.39 | 52914.56 | -5004.83 | -8.641% | 3256.33 | 532 | -2724.33 | -83.66% | 2124.8 | 3177.23 | 1052.43 | 49.53% | 147.73 | 78 | -69.73 | -47.2% | 2022-12-08 01:00
Markham | 2021 | 638126 | 638126 - 6675 LANGSTAFF RD / VAU / NS / 3PH PAD | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 136291.3 | 128166.64 | -8124.66 | -5.961% | 16205.91 | 20291.85 | 4085.94 | 25.21% | 82913.61 | 74577.01 | -8336.6 | -10.05% | 1323.34 | 4042.78 | 2719.44 | 205.5% | 35848.44 | 29255 | -6593.44 | -18.39% | 97.19 | 148.5 | 51.31 | 52.79% | 2021-03-21 01:00
Markham | 2020 | 638133 | 638133 - WELLINGTON ST @ BAYVIEW AVE (AURORA) - HYDRO ONE RELOCATIONS | 99 | COMPLETE | Material Req incorrectly | Labour est. under | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Morrow, Joe | 11251.98 | 22187.66 | 10935.68 | 97.19% | 6699.45 | 11516.53 | 4817.08 | 71.9% | 3216.73 | 6678.08 | 3461.35 | 107.6% | 1335.8 | 3993.05 | 2657.25 | 198.9% | 0 | 0 | 0 |  | 47.6 | 106.5 | 58.9 | 123.7% | 2020-10-26 01:00
Markham | 2021 | 638186 | 638186 - TRANSFORMER REPLACEMENT 2021 - BATCH 1 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 277192.09 | 222563.18 | -54628.91 | -19.71% | 57571.38 | 38937.66 | -18633.72 | -32.37% | 120847.41 | 108298.06 | -12549.35 | -10.38% | 11564.38 | 10349.5 | -1214.88 | -10.51% | 87208.92 | 64977.96 | -22230.96 | -25.49% | 408.72 | 364 | -44.72 | -10.94% | 2021-06-30 01:00
Markham | 2021 | 638187 | 638187 - TRANSFORMER REPLACEMENT 2021 - BATCH 2 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 43000.95 | 39210.04 | -3790.91 | -8.816% | 13451.64 | 5482.8 | -7968.84 | -59.24% | 20841.43 | 15938.96 | -4902.47 | -23.52% | 2277.56 | 0 | -2277.56 | -100% | 6430.32 | 17788.28 | 11357.96 | 176.6% | 81.52 | 0 | -81.52 | -100% | 2021-06-05 01:00
Markham | 2021 | 638188 | 638188 - TRANSFORMER REPLACEMENT 2021 - BATCH 3 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 152290.86 | 156719.36 | 4428.5 | 2.908% | 34473.13 | 26872.14 | -7600.99 | -22.05% | 85124.92 | 83229.64 | -1895.28 | -2.226% | 6213.37 | 6779.9 | 566.53 | 9.118% | 26479.44 | 39837.68 | 13358.24 | 50.45% | 208.8 | 160.5 | -48.3 | -23.13% | 2021-12-23 01:00
Markham | 2021 | 638189 | 638189 - TRANSFORMER REPLACEMENT 2021 - BATCH 4 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 127433.78 | 142224.77 | 14790.99 | 11.61% | 32423.75 | 16239.24 | -16184.51 | -49.92% | 55856.04 | 65069.19 | 9213.15 | 16.49% | 6307.79 | 731.85 | -5575.94 | -88.4% | 15919.2 | 60184.49 | 44265.29 | 278.1% | 227.68 | 28.5 | -199.18 | -87.48% | 2021-11-01 01:00
Markham | 2021 | 638190 | 638190 - TRANSFORMER REPLACEMENT 2021 - BATCH 5 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 119682.28 | 119972.58 | 290.3 | 0.2426% | 20804.73 | 19953.06 | -851.67 | -4.094% | 54575.34 | 53979.69 | -595.65 | -1.091% | 2781.61 | 5431.84 | 2650.23 | 95.28% | 41520.6 | 40607.99 | -912.61 | -2.198% | 72.64 | 115 | 42.36 | 58.31% | 2021-10-28 01:00
Markham | 2022 | 638217 | 2440 TESTON RD/VAUGHAN/NS 1PH OH TX | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Paterson, Greg | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-04-16
Markham | 2021 | 638229 | 638229 - TORONTO RV RD. 1PH. TO 3PH CONVERSION | 95 | COMPLETE | Labour est. over | N/A | N/A | Corriveau, Tom N | No | Barry, Kenneth | Ryan Walsh | 154018.12 | 135676.38 | -18341.74 | -11.91% | 84517.09 | 64206.25 | -20310.84 | -24.03% | 33009.41 | 36643.32 | 3633.91 | 11.01% | 20885.62 | 15661.5 | -5224.12 | -25.01% | 15606 | 19165.31 | 3559.31 | 22.81% | 642.82 | 635 | -7.82 | -1.217% | 2021-07-23 01:00
Markham | 2022 | 638240 | 638240 - 2021 CABLE INJECTION - V44 - LANGSTAFF & PINE VALLEY, VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 564812.97 | 515970.16 | -48842.81 | -8.648% | 5920.61 | 69269.47 | 63348.86 | 1070% | 20350.36 | 24081.88 | 3731.52 | 18.34% | 0 | 0 | 0 |  | 538542 | 422618.81 | -115923.19 | -21.53% | 0 | 0 | 0 |  | 2021-12-31 01:00
Markham | 2022 | 638241 | 638241 - 2021 CABLE INJECTION - V34 - KIRBY & JANE, VAUGHAN | 99 | COMPLETE | Cont Est Under | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 111679.08 | 369595.47 | 257916.39 | 230.9% | 5920.61 | 52028.58 | 46107.97 | 778.8% | 4667.23 | 4556.42 | -110.81 | -2.374% | 0 | 0 | 0 |  | 101091.24 | 313010.47 | 211919.23 | 209.6% | 0 | 0 | 0 |  | 2022-01-25 01:00
Markham | 2022 | 638243 | 638243 - 2021 CABLE INJECTION - V62 - KIRBY & HWY 27, VAUGHAN | 99 | COMPLETE | Scope – Eng | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 132448.69 | 3703.62 | -128745.07 | -97.2% | 5920.61 | 3703.62 | -2216.99 | -37.45% | 5028.08 | 0 | -5028.08 | -100% | 0 | 0 | 0 |  | 121500 | 0 | -121500 | -100% | 0 | 0 | 0 |  | 2022-01-25 01:00
Markham | 2021 | 638244 | 638244 - 2021 CABLE INJECTION - M16 - MAJOR MACKENZIE & NINTH LINE, MARKHAM | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 920461.66 | 738689.14 | -181772.52 | -19.75% | 5920.61 | 99228.51 | 93307.9 | 1576% | 55941.05 | 6929.36 | -49011.69 | -87.61% | 0 | 0 | 0 |  | 858600 | 632531.27 | -226068.73 | -26.33% | 0 | 0 | 0 |  | 2021-12-05 01:00
Markham | 2022 | 638246 | 638246 - 2021 CABLE INJECTION - V25 - MAJOR MACKENZIE & KEELE, VAUGHAN | 99 | COMPLETE | Cont Est Under | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 689232.25 | 915571.41 | 226339.16 | 32.84% | 5920.61 | 118177.76 | 112257.15 | 1896% | 32503.64 | 40682.13 | 8178.49 | 25.16% | 0 | 0 | 0 |  | 650808 | 756711.52 | 105903.52 | 16.27% | 0 | 0 | 0 |  | 2022-02-08 01:00
Markham | 2021 | 638254 | 638254 - SWITCHGEAR REPLACEMENT 2021 - BATCH 1 | 99 | COMPLETE | BOM cost variance | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 35651.45 | 48224.43 | 12572.98 | 35.27% | 15157.38 | 10961.94 | -4195.44 | -27.68% | 18560.22 | 28434.25 | 9874.03 | 53.2% | 1933.85 | 1410.63 | -523.22 | -27.06% | 0 | 7417.61 | 7417.61 |  | 111.7 | 58 | -53.7 | -48.08% | 2021-11-18 01:00
Markham | 2021 | 638255 | 638255 - SWITCHGEAR REPLACEMENT 2021 - BATCH 2 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 98835.32 | 111543.65 | 12708.33 | 12.86% | 14583.89 | 46446.17 | 31862.28 | 218.5% | 66563.64 | 12316 | -54247.64 | -81.5% | 1486.71 | 13425.15 | 11938.44 | 803% | 16201.08 | 39356.33 | 23155.25 | 142.9% | 99.74 | 430 | 330.26 | 331.1% | 2021-12-22 01:00
Markham | 2021 | 638256 | 638256 - SWITCHGEAR REPLACEMENT 2021 - BATCH 3 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 593347.67 | 593136.03 | -211.64 | -0.03567% | 55426.01 | 40829.28 | -14596.73 | -26.34% | 513873.19 | 530226.76 | 16353.57 | 3.182% | 8844.23 | 9430.5 | 586.27 | 6.629% | 15204.24 | 12649.49 | -2554.75 | -16.8% | 478.56 | 369 | -109.56 | -22.89% | 2021-06-23 01:00
Markham | 2021 | 638257 | 638257 - SWITCHGEAR REPLACEMENT 2021 - BATCH 4 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 173382.62 | 167559.08 | -5823.54 | -3.359% | 21660.98 | 14623.19 | -7037.79 | -32.49% | 130909.04 | 134625.45 | 3716.41 | 2.839% | 3163.24 | 3416.09 | 252.85 | 7.993% | 17649.36 | 14894.35 | -2755.01 | -15.61% | 164.28 | 82.5 | -81.78 | -49.78% | 2021-07-21 01:00
Markham | 2021 | 638258 | 638258 - SWITCHGEAR REPLACEMENT 2021 - BATCH 5 | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 442894.71 | 244627.49 | -198267.22 | -44.77% | 48868.37 | 10667.42 | -38200.95 | -78.17% | 377615.14 | 219758.29 | -157856.85 | -41.8% | 7953.72 | 3859.63 | -4094.09 | -51.47% | 8457.48 | 10342.15 | 1884.67 | 22.28% | 416.84 | 144.5 | -272.34 | -65.33% | 2021-11-25 01:00
Markham | 2021 | 638259 | 638259 - SWITCHGEAR REPLACEMENT 2021 - BATCH 6 | 99 | COMPLETE | Material reused | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 663591.7 | 509487.01 | -154104.69 | -23.22% | 85452.89 | 52756.93 | -32695.96 | -38.26% | 504626.83 | 402614.05 | -102012.78 | -20.22% | 15611.02 | 11110.01 | -4501.01 | -28.83% | 57900.96 | 43006.02 | -14894.94 | -25.72% | 752.94 | 382 | -370.94 | -49.27% | 2021-12-24 01:00
Markham | 2021 | 638260 | 638260 - SWITCHGEAR REPLACEMENT 2021 - BATCH 7 | 99 | COMPLETE | Material reused | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 415393.2 | 123199.13 | -292194.07 | -70.34% | 49859.36 | 15324.59 | -34534.77 | -69.26% | 324243.53 | 83278.69 | -240964.84 | -74.32% | 8476.67 | 1682.3 | -6794.37 | -80.15% | 32813.64 | 22913.55 | -9900.09 | -30.17% | 424.98 | 71.5 | -353.48 | -83.18% | 2021-12-22 01:00
Markham | 2021 | 638261 | 638261 - M20 SARAH JANE COURT - CABLE FAILURE REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 196022.48 | 189526.11 | -6496.37 | -3.314% | 11323.24 | 24281.57 | 12958.33 | 114.4% | 1601.86 | 0 | -1601.86 | -100% | 1111.98 | 1356 | 244.02 | 21.94% | 181985.4 | 163888.54 | -18096.86 | -9.944% | 72.51 | 77 | 4.49 | 6.192% | 2021-05-21 01:00
Markham | 2022 | 638293 | 638293 - DISTRIBUTION AUTOMATION 2022 - M33SUG001 - MARKHAM | 98 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 174289.9 | 163761.09 | -10528.81 | -6.041% | 34687.2 | 18381.56 | -16305.64 | -47.01% | 101426.98 | 105696.67 | 4269.69 | 4.21% | 3514.72 | 1503.58 | -2011.14 | -57.22% | 34661 | 38179.28 | 3518.28 | 10.15% | 198.94 | 40 | -158.94 | -79.89% | 2022-12-08 01:00
Markham | 2021 | 638294 | 638294 - DISTRIBUTION AUTOMATION 2021 - R12SL3004 - RH, 1 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Larry | 91894.69 | 114429.02 | 22534.33 | 24.52% | 28751.55 | 14400.09 | -14351.46 | -49.92% | 51541.69 | 68618.57 | 17076.88 | 33.13% | 6849.45 | 0 | -6849.45 | -100% | 4752 | 31410.36 | 26658.36 | 561% | 230.92 | 61.5 | -169.42 | -73.37% | 2021-08-13 01:00
Markham | 2021 | 638295 | 638295 - DISTRIBUTION AUTOMATION 2021 - NEW UNIT - VAUGHAN, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Larry | 103033.67 | 113338.78 | 10305.11 | 10% | 30262.82 | 13664.34 | -16598.48 | -54.85% | 51860.61 | 56364.36 | 4503.75 | 8.684% | 7302.24 | 0 | -7302.24 | -100% | 13608 | 43310.08 | 29702.08 | 218.3% | 244.81 | 50 | -194.81 | -79.58% | 2021-08-09 01:00
Markham | 2022 | 638296 | 638296 - 2022 DA - 45SL3002 - VAUGHAN | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Kristine Gordon | 126546.68 | 180618.47 | 54071.79 | 42.73% | 33697.96 | 36195.71 | 2497.75 | 7.412% | 61349.12 | 103817.02 | 42467.9 | 69.22% | 7749.6 | 9803 | 2053.4 | 26.5% | 23750 | 30802.74 | 7052.74 | 29.7% | 259.26 | 352 | 92.74 | 35.77% | 2022-04-13
Markham | 2021 | 638297 | 638297 - DISTRIBUTION AUTOMATION 2021 - TBD - VAUGHAN, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 147083.58 | 155961.8 | 8878.22 | 6.036% | 3478.78 | 15968.12 | 12489.34 | 359% | 70275.56 | 79072.76 | 8797.2 | 12.52% | 0 | 0 | 0 |  | 73329.24 | 60920.92 | -12408.32 | -16.92% | 40 | 36 | -4 | -10% | 2021-07-24 01:00
Markham | 2021 | 638298 | 638298 - DISTRIBUTION AUTOMATION 2021 - NEW - VAUGHAN, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 129432.3 | 134517.97 | 5085.67 | 3.929% | 3478.78 | 16567.83 | 13089.05 | 376.3% | 56479.31 | 59702.31 | 3223 | 5.707% | 0 | 0 | 0 |  | 69474.21 | 58247.83 | -11226.38 | -16.16% | 40 | 49 | 9 | 22.5% | 2021-08-14 01:00
Markham | 2022 | 638299 | 638299 - 2022 DA - R25SL1005 - RICHMOND HILL | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Reginald Clarke | 108592.55 | 89612.03 | -18980.52 | -17.48% | 29387.89 | 12647.2 | -16740.69 | -56.96% | 50566.77 | 57156.2 | 6589.43 | 13.03% | 7037.89 | 3188 | -3849.89 | -54.7% | 21600 | 16620.63 | -4979.37 | -23.05% | 236.83 | 88 | -148.83 | -62.84% | 2022-03-09 01:00
Markham | 2021 | 638300 | 638300 - 2021 DA - V45SL3007 - VAUGHAN, 1 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 87437.51 | 92657.41 | 5219.9 | 5.97% | 26484.4 | 11361.65 | -15122.75 | -57.1% | 48303.9 | 53099.29 | 4795.39 | 9.928% | 6169.21 | 0 | -6169.21 | -100% | 6480 | 28196.47 | 21716.47 | 335.1% | 210.11 | 40 | -170.11 | -80.96% | 2021-09-20 01:00
Markham | 2021 | 638302 | 638302 - 2021 CABLE INJECTION/M22 – MAJOR MACKENZIE – HWY 48 – 16TH – MCCOWAN | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 231608.15 | 124896.24 | -106711.91 | -46.07% | 3947.08 | 17958.5 | 14011.42 | 355% | 9489.19 | 7766.24 | -1722.95 | -18.16% | 0 | 0 | 0 |  | 218171.88 | 99171.5 | -119000.38 | -54.54% | 0 | 0 | 0 |  | 2021-12-05 01:00
Markham | 2021 | 638303 | 638303 - 2021 CABLE INJECTION/M32 – HWY 7 – MAIN – 14TH – WARDEN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 1222804.71 | 1103661.21 | -119143.5 | -9.743% | 3947.08 | 147128.64 | 143181.56 | 3628% | 42230.03 | 7496.94 | -34733.09 | -82.25% | 0 | 0 | 0 |  | 1176627.6 | 949035.63 | -227591.97 | -19.34% | 0 | 0 | 0 |  | 2021-12-05 01:00
Markham | 2021 | 638304 | 638304 - 2021 CABLE INJECTION/V41 – KIRBY – WESTON – TESTON – PINE VALLEY | 99 | COMPLETE | Cont Est Under | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 162409.62 | 225755.24 | 63345.62 | 39% | 3947.08 | 32638.69 | 28691.61 | 726.9% | 6451.46 | 1447.21 | -5004.25 | -77.57% | 0 | 0 | 0 |  | 152011.08 | 191669.34 | 39658.26 | 26.09% | 0 | 0 | 0 |  | 2021-11-19 01:00
Markham | 2022 | 638306 | 638306 - 2021 CABLE INJECTION/V52 – RUTHERFORD – KIPLING – LANGSTAFF – HWY 27 | 99 | COMPLETE | Scope – Eng | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 183714.95 | 459623.28 | 275908.33 | 150.2% | 3947.08 | 52454.69 | 48507.61 | 1229% | 10642.03 | 4487.77 | -6154.26 | -57.83% | 0 | 0 | 0 |  | 169125.84 | 402680.82 | 233554.98 | 138.1% | 0 | 0 | 0 |  | 2022-05-16 01:00
Markham | 2021 | 638308 | 2021 CABLE INJECTION/V18 – MAJOR MACKENZIE – KEELE | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Handy, James | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-10-20 01:00
Markham | 2021 | 638309 | 2021 CABLE INJECTION/V36 – STEELES – PINE VALLEY | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Handy, James | Wong, Henry | 212309.44 | 0 | -212309.44 | -100% | 3727.76 | 0 | -3727.76 | -100% | 17239.16 | 0 | -17239.16 | -100% | 0 | 0 | 0 |  | 191342.52 | 0 | -191342.52 | -100% | 0 | 0 | 0 |  | 2021-10-20 01:00
Markham | 2021 | 638322 | 638322 - UG CABLE REPLACEMENT, V16 BRADWICK DR - 16-L20 TO V16SP3109 (CABLE FAILURE) | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Lamb, Tim | 142460.63 | 117656.17 | -24804.46 | -17.41% | 12349.54 | 14107.09 | 1757.55 | 14.23% | 631.35 | 0 | -631.35 | -100% | 846.34 | 464 | -382.34 | -45.18% | 128633.4 | 103085.08 | -25548.32 | -19.86% | 25 | 29 | 4 | 16% | 2021-04-10 01:00
Markham | 2022 | 638324 | 638324 - 8811 HUNTINGTON RD/ VAU/ NS/ 3PH PAD | 95 | COMPLETE | Estimate incorrect | N/A | N/A | Joshi, Namrata | No | Diefenbaker, Trevor A | Dave Lindsay | 117073.97 | 133444.53 | 16370.56 | 13.98% | 35897.78 | 24461.76 | -11436.02 | -31.86% | 63258.06 | 69708.22 | 6450.16 | 10.2% | 6402.15 | 3100 | -3302.15 | -51.58% | 33865.98 | 36174.55 | 2308.57 | 6.817% | 263.97 | 169 | -94.97 | -35.98% | 2022-10-07 01:00
Markham | 2021 | 638368 | 638368 - 7050 MAJOR MACKENZIE DR / VAU / UP / 3PH PAD | 99 | COMPLETE | Under 10% | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 101154.8 | 96895.63 | -4259.17 | -4.211% | 19361.33 | 18984.17 | -377.16 | -1.948% | 56490.91 | 50721.51 | -5769.4 | -10.21% | 2283.44 | 3222 | 938.56 | 41.1% | 23019.12 | 23967.95 | 948.83 | 4.122% | 128.89 | 135 | 6.11 | 4.74% | 2021-06-03 01:00
Markham | 2021 | 638386 | 638386 - 375 NEW HUNTINGTON/ VAU/ NS/ 3-PH PAD | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 183159.25 | 174013.19 | -9146.06 | -4.994% | 23589.84 | 35081.68 | 11491.84 | 48.72% | 97069.77 | 75833.39 | -21236.38 | -21.88% | 2769.64 | 6745.91 | 3976.27 | 143.6% | 82080 | 56352.21 | -25727.79 | -31.34% | 147.57 | 309 | 161.43 | 109.4% | 2021-05-26 01:00
Markham | 2021 | 638390 | 638390 - SWITCH REPLACEMENT - M52SL3110 | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 62752.06 | 0 | -62752.06 | -100% | 16802.79 | 0 | -16802.79 | -100% | 43221.07 | 0 | -43221.07 | -100% | 2728.2 | 0 | -2728.2 | -100% | 0 | 0 | 0 |  | 119.65 | 0 | -119.65 | -100% | 2021-07-13 01:00
Markham | 2021 | 638391 | 638391 - SWITCH REPLACEMENT - M49SL3108 | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 78076.72 | 0 | -78076.72 | -100% | 21850.75 | 0 | -21850.75 | -100% | 48366.87 | 0 | -48366.87 | -100% | 4079.1 | 0 | -4079.1 | -100% | 3780 | 0 | -3780 | -100% | 165.55 | 0 | -165.55 | -100% | 2021-07-13 01:00
Markham | 2020 | 638392 | SWITCH REPLACEMENT - 37LIS017 | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Alectra Utilities | Wong, Henry | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-13 01:00
Markham | 2021 | 638393 | 638393 - SWITCH REPLACEMENT - M43SL3083 | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 106317.09 | 0 | -106317.09 | -100% | 29832.02 | 0 | -29832.02 | -100% | 62075.47 | 0 | -62075.47 | -100% | 5769.6 | 0 | -5769.6 | -100% | 8640 | 0 | -8640 | -100% | 239.1 | 0 | -239.1 | -100% | 2021-07-13 01:00
Markham | 2021 | 638394 | 638394 - SWITCH REPLACEMENT - V19SL3019 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 67596.1 | 73564.03 | 5967.93 | 8.829% | 18374.28 | 8962.7 | -9411.58 | -51.22% | 43530.42 | 45059.68 | 1529.26 | 3.513% | 2991.4 | 0 | -2991.4 | -100% | 2700 | 19541.65 | 16841.65 | 623.8% | 32 | 32 | 0 | 0% | 2021-07-13 01:00
Markham | 2021 | 638395 | 638395 - SWITCH REPLACEMENT - A03SL2000, A03SL2003 AND A02SL2003 | 99 | COMPLETE | Scope – Const | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 25503.14 | 22462.95 | -3040.19 | -11.92% | 16702.4 | 7001.11 | -9701.29 | -58.08% | 1803.93 | 1310.99 | -492.94 | -27.33% | 2676.81 | 0 | -2676.81 | -100% | 4320 | 14150.85 | 9830.85 | 227.6% | 151.15 | 0 | -151.15 | -100% | 2021-08-09 01:00
Markham | 2021 | 638397 | 638397 - 29 EAST WILMOT ST / RHL / UP / 3PH VAULT | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 69793.19 | 67385.64 | -2407.55 | -3.45% | 28170.55 | 10366.11 | -17804.44 | -63.2% | 61093.86 | 56863.38 | -4230.48 | -6.925% | 2878.78 | 71.5 | -2807.28 | -97.52% | 0 | 84.65 | 84.65 |  | 213.58 | 60 | -153.58 | -71.91% | 2021-11-11 01:00
Markham | 2020 | 638467 | 638467 - UG SECONDARY CABLE REPLACEMENTS, M52 ROMFIELD CIRCUIT | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Alectra Utilities | Lamb, Tim | 587076.39 | 585954.01 | -1122.38 | -0.1912% | 14112.87 | 55304.39 | 41191.52 | 291.9% | 0 | 0 | 0 |  | 840 | 906.2 | 66.2 | 7.881% | 572123.52 | 529743.42 | -42380.1 | -7.408% | 60 | 45 | -15 | -25% | 2020-11-23 01:00
Markham | 2021 | 638561 | 638561 - JOINT USE PERMIT #HE2020-069, YONGE ST. RICHMOND HILL, ONTARIO | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 6218.3 | 5254.48 | -963.82 | -15.5% | 2429.5 | 1799.48 | -630.02 | -25.93% | 265.17 | 0 | -265.17 | -100% | 121.63 | 305 | 183.37 | 150.8% | 3402 | 3150 | -252 | -7.407% | 4.37 | 10 | 5.63 | 128.8% | 2021-04-14
Markham | 2021 | 638572 | 638572 - POLE REPLACEMENT 2021 - BATCH 1 | 99 | COMPLETE | Scope – Eng | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 264718.8 | 240576.64 | -24142.16 | -9.12% | 119014.83 | 80819.48 | -38195.35 | -32.09% | 77417.82 | 72336.26 | -5081.56 | -6.564% | 21906.63 | 34352 | 12445.37 | 56.81% | 46379.52 | 53068.9 | 6689.38 | 14.42% | 1060.43 | 1068 | 7.57 | 0.7139% | 2021-02-02 01:00
Markham | 2021 | 638574 | 638574 - POLE REPLACEMENT 2021 - BATCH 2 - 9 POLES | 99 | COMPLETE | Labour est. under | Covid-19 | N/A | Tenorlas, Reynaldo | No | Handy, James | Ryan Walsh | 199380.77 | 192580.95 | -6799.82 | -3.41% | 84087.04 | 84711.05 | 624.01 | 0.7421% | 59057.45 | 59017.04 | -40.41 | -0.06842% | 23979.92 | 23984 | 4.08 | 0.01701% | 32256.36 | 24868.86 | -7387.5 | -22.9% | 951.62 | 997 | 45.38 | 4.769% | 2021-02-03 01:00
Markham | 2021 | 638575 | 638575 - POLE REPLACEMENT 2021 - BATCH 3 | 99 | COMPLETE | Scope – Const | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 148314.77 | 148134.7 | -180.07 | -0.1214% | 75340.5 | 75830.07 | 489.57 | 0.6498% | 36213.13 | 35696.93 | -516.2 | -1.425% | 29817.58 | 30174 | 356.42 | 1.195% | 6943.56 | 6433.7 | -509.86 | -7.343% | 1017.81 | 1019 | 1.19 | 0.1169% | 2021-02-23 01:00
Markham | 2021 | 638576 | 638576 - POLE REPLACEMENT 2021 - BATCH 4 | 99 | COMPLETE | Scope – Const | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Morrow, Joe | 179661.41 | 183907.39 | 4245.98 | 2.363% | 77330.73 | 78093.9 | 763.17 | 0.9869% | 48825.52 | 50804.84 | 1979.32 | 4.054% | 26585.16 | 27067 | 481.84 | 1.812% | 26920 | 27941.65 | 1021.65 | 3.795% | 1040.5 | 1018 | -22.5 | -2.162% | 2021-03-09 01:00
Markham | 2021 | 638577 | 638577 - POLE REPLACEMENT 2021 - BATCH 5 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Reginald Clarke | 200713.29 | 187901.52 | -12811.77 | -6.383% | 67585.22 | 70199.67 | 2614.45 | 3.868% | 33815.21 | 38974.89 | 5159.68 | 15.26% | 15954.14 | 32076.21 | 16122.07 | 101.1% | 83358.72 | 46650.75 | -36707.97 | -44.04% | 570.32 | 575 | 4.68 | 0.8206% | 2021-11-03 01:00
Markham | 2021 | 638578 | 638578 - POLE REPLACEMENT 2021 - BATCH 6 | 99 | COMPLETE | Scope change - unforeseen | Labour est. under | N/A | Tenorlas, Reynaldo | No | Roy, James | Ryan Walsh | 85160.65 | 91813.56 | 6652.91 | 7.812% | 85310.55 | 43339.49 | -41971.06 | -49.2% | -41920.08 | 12918.11 | 54838.19 | -130.8% | 9640.18 | 14216 | 4575.82 | 47.47% | 32130 | 21339.96 | -10790.04 | -33.58% | 369.44 | 536 | 166.56 | 45.08% | 2021-02-23 01:00
Markham | 2021 | 638579 | 638579 - POLE REPLACEMENT 2021 - BATCH 7 | 99 | COMPLETE | BOM not accurate | Weather | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Ryan Walsh | 75583.04 | 76000.17 | 417.13 | 0.5519% | 33679.97 | 33314.73 | -365.24 | -1.084% | 18466.49 | 18851.59 | 385.1 | 2.085% | 9417.1 | 9482 | 64.9 | 0.6892% | 14019.48 | 14351.85 | 332.37 | 2.371% | 370.9 | 373 | 2.1 | 0.5662% | 2021-01-14 01:00
Markham | 2021 | 638580 | 638580 - POLE REPLACEMENT 2021 - BATCH 8 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Ryan Walsh | 290751.23 | 285515.87 | -5235.36 | -1.801% | 103109.23 | 127764.98 | 24655.75 | 23.91% | 80619.36 | 73155.88 | -7463.48 | -9.258% | 24942.64 | 49586 | 24643.36 | 98.8% | 82080 | 35009.01 | -47070.99 | -57.35% | 1594.15 | 1700.5 | 106.35 | 6.671% | 2021-04-19
Markham | 2022 | 638581 | 638581 - POLE REPLACEMENT 2022 - BATCH 9 | 99 | COMPLETE | Labour est. under | Material Under Estimated | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Morrow, Joe | 297715.67 | 451000.95 | 153285.28 | 51.49% | 94332.65 | 201171.64 | 106838.99 | 113.3% | 82424.54 | 115375.96 | 32951.42 | 39.98% | 26350.48 | 65634.1 | 39283.62 | 149.1% | 94608 | 68819.25 | -25788.75 | -27.26% | 1732.09 | 2185.5 | 453.41 | 26.18% | 2022-12-14 01:00
Markham | 2022 | 638582 | 638582 - POLE REPLACEMENT 2021 - BATCH 10 | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Kristine Gordon | 184810.79 | 295868.55 | 111057.76 | 60.09% | 52866.89 | 75702.12 | 22835.23 | 43.19% | 54673.45 | 69323.07 | 14649.62 | 26.79% | 14675.72 | 19218.19 | 4542.47 | 30.95% | 62594.73 | 131625.17 | 69030.44 | 110.3% | 449.66 | 589 | 139.34 | 30.99% | 2022-12-20 01:00
Markham | 2022 | 638583 | 638583 - POLE REPLACEMENT 2021 - BATCH 11 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Reginald Clarke | 118125.79 | 154234.72 | 36108.93 | 30.57% | 41298.8 | 33237.04 | -8061.76 | -19.52% | 31260.38 | 33352.27 | 2091.89 | 6.692% | 10466.61 | 9079.8 | -1386.81 | -13.25% | 35100 | 78565.61 | 43465.61 | 123.8% | 345.2 | 170 | -175.2 | -50.75% | 2022-01-15 01:00
Markham | 2021 | 638584 | 638584 - 2021 POLE RENEWAL - BATCH 12 - 6 POLES | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 65236.96 | 64774.44 | -462.52 | -0.709% | 26236.78 | 26006.77 | -230.01 | -0.8767% | 21292.29 | 18937.57 | -2354.72 | -11.06% | 7817.69 | 7741.5 | -76.19 | -0.9746% | 9890.2 | 12088.6 | 2198.4 | 22.23% | 271.72 | 274 | 2.28 | 0.8391% | 2021-04-27
Markham | 2021 | 638585 | 638585 - POLE REPLACEMENT 2021 - BATCH 13 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Reginald Clarke | 57480.23 | 45196.25 | -12283.98 | -21.37% | 22314.85 | 18259.23 | -4055.62 | -18.17% | 11018.33 | 11607.09 | 588.76 | 5.343% | 4167.05 | 7379.48 | 3212.43 | 77.09% | 19980 | 7950.45 | -12029.55 | -60.21% | 139.88 | 131.5 | -8.38 | -5.991% | 2021-11-12 01:00
Markham | 2021 | 638586 | 638586 - POLE REPLACEMENT 2021 - BATCH 14 | 99 | COMPLETE | Scope – Const | Labour est. over | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Morrow, Joe | 19445.74 | 16739.06 | -2706.68 | -13.92% | 6706.31 | 6829.68 | 123.37 | 1.84% | 4115.16 | 4289.8 | 174.64 | 4.244% | 2252.27 | 1496 | -756.27 | -33.58% | 6372 | 4123.58 | -2248.42 | -35.29% | 50.51 | 75 | 24.49 | 48.49% | 2021-03-30 01:00
Markham | 2021 | 638587 | 638587 - POLE REPLACEMENT 2021 - BATCH 15 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Larry | 168351.18 | 118754.42 | -49596.76 | -29.46% | 84022.06 | 52295.66 | -31726.4 | -37.76% | 32444.74 | 37605.09 | 5160.35 | 15.91% | 13030.3 | 17120 | 4089.7 | 31.39% | 38854.08 | 11733.67 | -27120.41 | -69.8% | 669.73 | 516.5 | -153.23 | -22.88% | 2021-07-22 01:00
Markham | 2022 | 638589 | 638589 - 2022 POLE RENEWAL - BATCH 1 - 15 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Morrow, Joe | 226973.61 | 220766.64 | -6206.97 | -2.735% | 87349.09 | 88643.13 | 1294.04 | 1.481% | 48222.87 | 45474.69 | -2748.18 | -5.699% | 16341.65 | 23269.81 | 6928.16 | 42.4% | 75060 | 63379.01 | -11680.99 | -15.56% | 840.78 | 904 | 63.22 | 7.519% | 2022-01-23 01:00
Markham | 2022 | 638603 | 638603 - POLE REPLACEMENT 2021 - REPLACE P51710 - RAILWAY CROSSING | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Kristine Gordon | 96562.89 | 90427.25 | -6135.64 | -6.354% | 26481.34 | 31520.3 | 5038.96 | 19.03% | 12602.74 | 12635.47 | 32.73 | 0.2597% | 4839.61 | 11079.53 | 6239.92 | 128.9% | 52639.2 | 35191.95 | -17447.25 | -33.14% | 201.26 | 232.5 | 31.24 | 15.52% | 2022-12-05 01:00
Markham | 2021 | 638604 | 638604 - POLE REPLACEMENT 2021 - REPLACE P37765 - RAILWAY CROSSING | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Ryan Walsh | 33766.76 | 29715.41 | -4051.35 | -12% | 10261.3 | 8759.97 | -1501.33 | -14.63% | 2449.48 | 1545.7 | -903.78 | -36.9% | 1445.34 | 1884 | 438.66 | 30.35% | 19610.64 | 17525.74 | -2084.9 | -10.63% | 49.59 | 59 | 9.41 | 18.98% | 2021-03-16 01:00
Markham | 2022 | 638605 | 638605 - TRANSFORMER REPLACEMENT 2021 - BATCH 6 | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 129038.91 | 142022.78 | 12983.87 | 10.06% | 23003.6 | 17859.46 | -5144.14 | -22.36% | 60820.17 | 72651.03 | 11830.86 | 19.45% | 2415.82 | 890.79 | -1525.03 | -63.13% | 42799.32 | 50621.5 | 7822.18 | 18.28% | 110.35 | 44.5 | -65.85 | -59.67% | 2022-12-02 01:00
Markham | 2021 | 638606 | 638606 - TRANSFORMER REPLACEMENT 2021 - BATCH 7 | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 258378.34 | 236335.86 | -22042.48 | -8.531% | 45566.6 | 43837.46 | -1729.14 | -3.795% | 101079.52 | 109638.1 | 8558.58 | 8.467% | 7532.74 | 11838.69 | 4305.95 | 57.16% | 104199.48 | 71021.61 | -33177.87 | -31.84% | 360.8 | 294 | -66.8 | -18.51% | 2021-12-21 01:00
Markham | 2022 | 638607 | 638607 - TRANSFORMER REPLACEMENT 2021 - BATCH 8 | 99 | COMPLETE | Inaccurate design | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 199487.7 | 132632.39 | -66855.31 | -33.51% | 37829.27 | 25092.69 | -12736.58 | -33.67% | 71460.31 | 62536.45 | -8923.86 | -12.49% | 6079.08 | 5008.89 | -1070.19 | -17.6% | 84119.04 | 39994.36 | -44124.68 | -52.46% | 291.6 | 144.5 | -147.1 | -50.45% | 2022-04-04
Markham | 2021 | 638608 | 638608 - TRANSFORMER REPLACEMENT 2021 - BATCH 9 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Lamb, Tim | 71650.48 | 66600.67 | -5049.81 | -7.048% | 26208.23 | 6837.98 | -19370.25 | -73.91% | 37800.77 | 37135.23 | -665.54 | -1.761% | 4518.12 | 0 | -4518.12 | -100% | 3123.36 | 22627.46 | 19504.1 | 624.5% | 161.04 | 0 | -161.04 | -100% | 2021-05-15
Markham | 2021 | 638609 | 638609 - TRANSFORMER REPLACEMENT 2021 - BATCH 10 | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 325038.2 | 278587.69 | -46450.51 | -14.29% | 53714.7 | 29001.31 | -24713.39 | -46.01% | 120192.96 | 113711.8 | -6481.16 | -5.392% | 8795.18 | 1436.77 | -7358.41 | -83.66% | 142335.36 | 134437.81 | -7897.55 | -5.549% | 403.2 | 33 | -370.2 | -91.82% | 2021-11-05 01:00
Markham | 2021 | 638610 | 638610 - TRANSFORMER REPLACEMENT 2021 - BATCH 11 | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 117681.6 | 105888.48 | -11793.12 | -10.02% | 28248.53 | 23918.6 | -4329.93 | -15.33% | 56166.35 | 55998.86 | -167.49 | -0.2982% | 4248.2 | 6783.07 | 2534.87 | 59.67% | 29018.52 | 19187.95 | -9830.57 | -33.88% | 200 | 169 | -31 | -15.5% | 2021-10-28 01:00
Markham | 2022 | 638622 | 638622 - 7537 WOODBINE AVE / MARKHAM / NS / 3PH PAD TX | 98 | COMPLETE | Estimate incorrect | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 63162.91 | 51402.66 | -11760.25 | -18.62% | 18715.53 | 19101.48 | 385.95 | 2.062% | 52195.54 | 18883.83 | -33311.71 | -63.82% | 2365.44 | 1828 | -537.44 | -22.72% | 12236.4 | 11589.35 | -647.05 | -5.288% | 122.07 | 134 | 11.93 | 9.773% | 2022-07-19 01:00
Markham | 2020 | 638626 | 638626 - 146 OLD KENNEDY RD / MAR / SR / VAULT DEMO | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Alectra Utilities | Chris Hagan | 18367.6 | 12514.26 | -5853.34 | -31.87% | 5946.12 | 4381.07 | -1565.05 | -26.32% | 0 | 0 | 0 |  | 627.88 | 550 | -77.88 | -12.4% | 11793.6 | 7583.19 | -4210.41 | -35.7% | 37.22 | 15 | -22.22 | -59.7% | 2020-11-26 01:00
Markham | 2021 | 638638 | 638638 - 11801 KEELE ST/VAU/NS/1PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 40152.14 | 22505.06 | -17647.08 | -43.95% | 23586.46 | 10271.91 | -13314.55 | -56.45% | 9771.15 | 6528.68 | -3242.47 | -33.18% | 3565.17 | 2182.21 | -1382.96 | -38.79% | 4473.36 | 3522.26 | -951.1 | -21.26% | 163.54 | 89 | -74.54 | -45.58% | 2021-04-27
Markham | 2021 | 638644 | 638644 - CAL-CROWN (THREE) DEVELOPMENT (PHASE 1) – SUBD RES EDS | 99 | COMPLETE | Estimate incorrect | N/A | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Dave Lindsay | 157173.41 | 136655.31 | -20518.1 | -13.05% | 18501.93 | 12830.51 | -5671.42 | -30.65% | 1182.18 | 0 | -1182.18 | -100% | 1100.42 | 2098 | 997.58 | 90.65% | 136388.88 | 0 | -136388.88 | -100% | 103.85 | 87 | -16.85 | -16.23% | 2021-07-21 01:00
Markham | 2021 | 638673 | 638673 - YONGE ST & CATHERINE AVE | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Watters, Maxwell | Shane Christopher | 262267.03 | 265614.42 | 3347.39 | 1.276% | 10883.55 | 27775.37 | 16891.82 | 155.2% | 11802.52 | 14599.34 | 2796.82 | 23.7% | 325.92 | 512 | 186.08 | 57.09% | 239255.04 | 222727.71 | -16527.33 | -6.908% | 10.08 | 35.5 | 25.42 | 252.2% | 2021-10-25 01:00
Markham | 2021 | 638674 | 638674 - POLE REPLACEMENT 2021 - REPLACE P930 & P932 - HWY 7 & HWY 427 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Steve | 182815.12 | 167896.31 | -14918.81 | -8.161% | 101083.21 | 16833.96 | -84249.25 | -83.35% | 37043.89 | 65536.62 | 28492.73 | 76.92% | 7872.98 | 0 | -7872.98 | -100% | 36815.04 | 85525.73 | 48710.69 | 132.3% | 0 | 2 | 2 |  | 2021-10-29 01:00
Markham | 2021 | 638675 | 638675 - POLE REPLACEMENT 2021 - REPLACE P21843 - HWY 407 & MARKHAM RD | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Larry | 47954.35 | 41282.87 | -6671.48 | -13.91% | 15657.76 | 17256.68 | 1598.92 | 10.21% | 4555.24 | 4623.23 | 67.99 | 1.493% | 1756.55 | 4820 | 3063.45 | 174.4% | 25984.8 | 14582.96 | -11401.84 | -43.88% | 161.58 | 176 | 14.42 | 8.924% | 2021-08-09 01:00
Markham | 2022 | 638685 | 638685 - 1360 BLOOMINGTON RD/AUR/NS/3PH PAD | 99 | COMPLETE | Labour est. under | Cont Est Under | N/A | Cranley, Stephen | No | Paterson, Greg | Dave Lindsay | 71718.8 | 84264.99 | 12546.19 | 17.49% | 22274.95 | 31998.43 | 9723.48 | 43.65% | 30644.39 | 22332.46 | -8311.93 | -27.12% | 3653.46 | 7307 | 3653.54 | 100% | 15146 | 22627.1 | 7481.1 | 49.39% | 145.65 | 324 | 178.35 | 122.5% | 2022-05-05
Markham | 2021 | 638771 | 638771 - WOODBINE AND HONDA BLVD/ MAR/ NS/ 3PH PAD | 99 | COMPLETE | BOM not accurate | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 168852.12 | 134859.22 | -33992.9 | -20.13% | 28242.63 | 33966.63 | 5724 | 20.27% | 106882.95 | 59665.6 | -47217.35 | -44.18% | 3384.62 | 1530 | -1854.62 | -54.8% | 35341.92 | 39696.99 | 4355.07 | 12.32% | 176.87 | 273 | 96.13 | 54.35% | 2021-12-08 01:00
Markham | 2022 | 638791 | 638791 - CAL-LESLIE DEVELOPMENT - SUBD RES EDS | 98 | ANALYZE |  |  |  | Penner, Mitchell | No | Estrada, Michael | Dave Lindsay | 138619.52 | 121690.35 | -16929.17 | -12.21% | 20739.31 | 12237.59 | -8501.72 | -40.99% | 947.23 | 0 | -947.23 | -100% | 816.98 | 646 | -170.98 | -20.93% | 116116 | 0 | -116116 | -100% | 84.1 | 70 | -14.1 | -16.77% | 2022-05-05
Markham | 2021 | 638819 | 638819 - TRANSFORMER REPLACEMENT 2021 - BATCH 12 | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 214346.57 | 176284.9 | -38061.67 | -17.76% | 46553.97 | 17486.79 | -29067.18 | -62.44% | 68764.29 | 75232.31 | 6468.02 | 9.406% | 8589.11 | 354.84 | -8234.27 | -95.87% | 90439.2 | 83210.96 | -7228.24 | -7.992% | 408.59 | 16 | -392.59 | -96.08% | 2021-06-23 01:00
Markham | 2022 | 638820 | 638820 - TRANSFORMER REPLACEMENT 2021 - 13 UNITS - BATCH 13 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Dave Lindsay | 200919.14 | 215630.2 | 14711.06 | 7.322% | 47579.04 | 38931.37 | -8647.67 | -18.18% | 70887.22 | 77884.62 | 6997.4 | 9.871% | 9300.16 | 6437.74 | -2862.42 | -30.78% | 73152.72 | 92376.47 | 19223.75 | 26.28% | 304.69 | 210.5 | -94.19 | -30.91% | 2022-06-13 01:00
Markham | 2021 | 638822 | 638822 - ADESSO TOWNS – SUBD RES EDS | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Dave Lindsay | 64315.98 | 62176.53 | -2139.45 | -3.326% | 14367.86 | 12183.09 | -2184.77 | -15.21% | 2230.85 | 2841.82 | 610.97 | 27.39% | 1278.35 | 400 | -878.35 | -68.71% | 46438.92 | 45688 | -750.92 | -1.617% | 62.49 | 27.75 | -34.74 | -55.59% | 2021-12-08 01:00
Markham | 2021 | 638855 | 638855 - FAIRTREE BLOCK 152 CONDO BLOCK SEMI DETACHED (PHASE 1) - SUBD RES EDS | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 517277.06 | 512182.97 | -5094.09 | -0.9848% | 26216.46 | 58166.86 | 31950.4 | 121.9% | 2221.17 | 2042.49 | -178.68 | -8.044% | 1268.03 | 2907 | 1638.97 | 129.3% | 487571.4 | 448002.65 | -39568.75 | -8.115% | 145.32 | 134.5 | -10.82 | -7.446% | 2021-07-21 01:00
Markham | 2021 | 638878 | 638878 - BLOCK 40/47 (3 MODEL HOMES) – SUBD RES EDS | 99 | COMPLETE | Cont Est Over | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Dave Lindsay | 56643.56 | 44539.29 | -12104.27 | -21.37% | 12427.44 | 6461.13 | -5966.31 | -48.01% | 2389.06 | 0 | -2389.06 | -100% | 1871.38 | 480 | -1391.38 | -74.35% | 39955.68 | 3900 | -36055.68 | -90.24% | 96.02 | 35 | -61.02 | -63.55% | 2021-06-23 01:00
Markham | 2021 | 638938 | 638938 - SOUTH 14 SUBDIVISION - POLE RELOCATION | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Estrada, Michael | Macdonald, Larry | 25841.07 | 10124.79 | -15716.28 | -60.82% | 13950.03 | 2584.53 | -11365.5 | -81.47% | 4321.99 | 1611.49 | -2710.5 | -62.71% | 2277.05 | 810.63 | -1466.42 | -64.4% | 5292 | 5118.14 | -173.86 | -3.285% | 85 | 27 | -58 | -68.24% | 2021-07-14 01:00
Markham | 2021 | 638955 | 638955 - 7709 MARKHAM RD / MARKHAM / NS / 3PH PAD | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 64324.65 | 70946.3 | 6621.65 | 10.29% | 22458.02 | 20805.58 | -1652.44 | -7.358% | 27224.53 | 16877.44 | -10347.09 | -38.01% | 2191.26 | 2470 | 278.74 | 12.72% | 34800.84 | 30793.28 | -4007.56 | -11.52% | 149.94 | 150 | 0.06 | 0.04002% | 2021-12-08 01:00
Markham | 2021 | 638965 | 638965 - ESNA PARK DR. - #100 | 99 | COMPLETE | Under 10% |  |  | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 55461.8 | 59957.69 | 4495.89 | 8.106% | 17772.36 | 9759.29 | -8013.07 | -45.09% | 34500.3 | 23662.13 | -10838.17 | -31.41% | 2178.2 | 1308.5 | -869.7 | -39.93% | 23360.94 | 25227.77 | 1866.83 | 7.991% | 115.38 | 72 | -43.38 | -37.6% | 2021-08-17 01:00
Markham | 2021 | 638974 | 638974 - TRANSFORMER RELOCATION - KLEINDOR SUBD | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 104712.35 | 99541.43 | -5170.92 | -4.938% | 18050.7 | 17298.03 | -752.67 | -4.17% | 824.53 | 2624.99 | 1800.46 | 218.4% | 1765.6 | 1774 | 8.4 | 0.4758% | 84071.52 | 77844.41 | -6227.11 | -7.407% | 146.51 | 93 | -53.51 | -36.52% | 2021-09-16 01:00
Markham | 2022 | 638977 | 638977 - FLEURY PARK WASHROOMS/AUR/NS/1PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Cranley, Stephen | No | Paterson, Greg | Dave Lindsay | 24862.48 | 21174.25 | -3688.23 | -14.83% | 15372.15 | 10931.47 | -4440.68 | -28.89% | 7451.7 | 5979.43 | -1472.27 | -19.76% | 1592.43 | 1846 | 253.57 | 15.92% | 2446.2 | 2417.35 | -28.85 | -1.179% | 86 | 61.5 | -24.5 | -28.49% | 2022-05-05
Markham | 2021 | 638987 | 638987 - POLE REBUILD 2021 - HUNTINGTON RD FROM RUTHERFORD RD TO MAJOR MACKENZIE DR | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Steve | 442681.41 | 482952.46 | 40271.05 | 9.097% | 30671.74 | 56660.44 | 25988.7 | 84.73% | 85965.1 | 99030.3 | 13065.2 | 15.2% | 0 | 0 | 0 |  | 326044.57 | 327261.72 | 1217.15 | 0.3733% | 0 | 22.5 | 22.5 |  | 2021-11-26 01:00
Markham | 2020 | 639012 | 4171 HWY 7 / MAR / UP / 3PH PAD TX | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-14 01:00
Markham | 2021 | 639057 | 105 CLEGG ROAD - MARKHAM | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Corriveau, Tom N | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-17 01:00
Markham | 2021 | 639063 | 639063 - 101 BRADWICK DR / VAU / SR / VAULT DEMO | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 21004.63 | 19336.74 | -1667.89 | -7.941% | 6661.66 | 5994.46 | -667.2 | -10.02% | 200 | 0 | -200 | -100% | 990.73 | 1165 | 174.27 | 17.59% | 13152.24 | 12177.28 | -974.96 | -7.413% | 43.24 | 41 | -2.24 | -5.18% | 2021-02-17 01:00
Markham | 2022 | 639069 | 639069 - PHASE 4-UG. FOR DC 3. VIA RENZO DR AND PERFORMANCE DR, RICHMOND HILL | 95 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Dave Lindsay | 1636522.4 | 1627415.35 | -9107.05 | -0.5565% | 167706.62 | 223364.13 | 55657.51 | 33.19% | 973997.56 | 51929.38 | -922068.18 | -94.67% | 8320 | 9519.5 | 1199.5 | 14.42% | 486498.22 | 1342602.34 | 856104.12 | 176% | 870 | 724.5 | -145.5 | -16.72% | 2022-10-07 01:00
Markham | 2021 | 639087 | 639087 - 55M12 FEEDER EXTENSION TO NORTH SIDE OF HWY 7 | 99 | COMPLETE | BOM not accurate | Labour est. under | N/A | Tenorlas, Reynaldo | No | Handy, James | Ryan Walsh | 125002.83 | 140643.85 | 15641.02 | 12.51% | 49801.87 | 69546.22 | 19744.35 | 39.65% | 26425.88 | 25387.07 | -1038.81 | -3.931% | 11226.72 | 22854 | 11627.28 | 103.6% | 37548.36 | 22856.56 | -14691.8 | -39.13% | 783.74 | 848.5 | 64.76 | 8.263% | 2021-02-25 01:00
Markham | 2022 | 639102 | 639102 - TRANSFORMER REPLACEMENT 2021 - REPLACE 15-210 & 15-254 | 99 | COMPLETE | Material reused | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 130395.75 | 107981.96 | -22413.79 | -17.19% | 21785.45 | 20958.53 | -826.92 | -3.796% | 34088.68 | 18882.88 | -15205.8 | -44.61% | 1598.94 | 2423.5 | 824.56 | 51.57% | 72922.68 | 65717.05 | -7205.63 | -9.881% | 8 | 93 | 85 | 1062% | 2022-03-29
Markham | 2021 | 639124 | 639124 - 7537-7541 WOODBINE AVE / MAR / SR / 3PH PAD DEMO | 99 | COMPLETE | Cont Est Over | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 22028.94 | 14904.36 | -7124.58 | -32.34% | 4960.33 | 3730.73 | -1229.6 | -24.79% | 0 | 271.27 | 271.27 |  | 692.57 | 340 | -352.57 | -50.91% | 16376.04 | 10562.36 | -5813.68 | -35.5% | 32.19 | 20 | -12.19 | -37.87% | 2021-04-05 01:00
Markham | 2021 | 639221 | 639221 - REPLACE AND RELOCATE 7T5 - 13433 LESLIE ST | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Horlings, Jake | 43773.41 | 38603.76 | -5169.65 | -11.81% | 9013.2 | 12147.82 | 3134.62 | 34.78% | 5105.35 | 4546.44 | -558.91 | -10.95% | 943.06 | 2509.2 | 1566.14 | 166.1% | 28711.8 | 19400.3 | -9311.5 | -32.43% | 49.27 | 61 | 11.73 | 23.81% | 2021-08-06 01:00
Markham | 2021 | 639349 | 639349 - CONNECTION OF BELL BONDS- HWY 27, VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Don Rothman | 1020.4 | 1006.25 | -14.15 | -1.387% | 930.4 | 884.25 | -46.15 | -4.96% | 0 | 0 | 0 |  | 90 | 122 | 32 | 35.56% | 0 | 0 | 0 |  | 4 | 4 | 0 | 0% | 2021-04-20
Markham | 2022 | 639398 | 639398 - JOINT USE PERMIT #HE2020-079, MAJOR MACKENZIE DR E., MARKHAM | 98 | COMPLETE | Est. Int. - Act. External | Material Over Estimated | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Steve | 47915.4 | 19842.68 | -28072.72 | -58.59% | 16641.49 | 1226.26 | -15415.23 | -92.63% | 10084.74 | 11046.42 | 961.68 | 9.536% | 4519.17 | 0 | -4519.17 | -100% | 16670 | 7570 | -9100 | -54.59% | 121.64 | 0 | -121.64 | -100% | 2022-04-19
Markham | 2020 | 639404 | 639404 - ONEIDA CRESCENT - RICHMOND HILL | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Alectra Utilities | Chris Hagan | 7466.77 | 7611.04 | 144.27 | 1.932% | 986.77 | 1801.91 | 815.14 | 82.61% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6480 | 5809.13 | -670.87 | -10.35% | 0 | 20 | 20 |  | 2020-12-07 01:00
Markham | 2021 | 639432 | 639432 - 5950 14TH AVENUE/MAR/NS/3PH PAD | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 109966.79 | 110943.31 | 976.52 | 0.888% | 21134.11 | 15366.7 | -5767.41 | -27.29% | 86106.96 | 75788.75 | -10318.21 | -11.98% | 2054.44 | 2091 | 36.56 | 1.78% | 23021.28 | 17696.86 | -5324.42 | -23.13% | 128.37 | 130 | 1.63 | 1.27% | 2021-10-27 01:00
Markham | 2021 | 639440 | 639440 - KENNEDY ROAD AND 16TH AVENUE - HYDRO RELOCATION | 98 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Corriveau, Tom N | No | Murray, Jake R | Macdonald, Steve | 598316.69 | 549296.4 | -49020.29 | -8.193% | 178396.11 | 51194.81 | -127201.3 | -71.3% | 132555.44 | 158715.02 | 26159.58 | 19.73% | 43825.14 | 0 | -43825.14 | -100% | 243540 | 339386.57 | 95846.57 | 39.36% | 20 | 31 | 11 | 55% | 2021-12-10 01:00
Markham | 2020 | 639482 | 75 NEWKIRK RD / RHL / NS / 3PH VAULT DOWNGRADE | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Alectra Utilities | East Coordinator | 0 | 602.61 | 602.61 |  | 0 | 602.61 | 602.61 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-30
Markham | 2021 | 639528 | 639528 - 2021 TX RENEWAL, REPLACE AND RELOCATE 15TP197 - 43 MAIN ST N | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 153273.23 | 199582.54 | 46309.31 | 30.21% | 22297.22 | 29821.4 | 7524.18 | 33.74% | 21483.85 | 17341.52 | -4142.33 | -19.28% | 2756.84 | 858.58 | -1898.26 | -68.86% | 106735.32 | 151561.04 | 44825.72 | 42% | 175.94 | 50.5 | -125.44 | -71.3% | 2021-09-25 01:00
Markham | 2021 | 639537 | 639537 - JOINT USE PERMIT #HE2020-084, HWY 7, MARKHAM | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 7322.49 | 4646.33 | -2676.16 | -36.55% | 2453.84 | 1250.33 | -1203.51 | -49.05% | 265.02 | 0 | -265.02 | -100% | 121.63 | 246 | 124.37 | 102.3% | 4482 | 3150 | -1332 | -29.72% | 4.37 | 6 | 1.63 | 37.3% | 2021-04-22
Markham | 2021 | 639566 | 639566 - LESLIE ST. DEFICIENCIES | 98 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Barry, Kenneth | Macdonald, Steve | 66618.23 | 64610.08 | -2008.15 | -3.014% | 13217.88 | 16438.02 | 3220.14 | 24.36% | 8766.97 | 7473.28 | -1293.69 | -14.76% | 0 | 0 | 0 |  | 44633.38 | 40698.78 | -3934.6 | -8.815% | 0 | 0 | 0 |  | 2021-06-12 01:00
Markham | 2022 | 639567 | 639567 - 2022 TX RENEWAL – BATCH 9 – 19 TX | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 342938.09 | 282245.2 | -60692.89 | -17.7% | 69540.34 | 35165.55 | -34374.79 | -49.43% | 166661.07 | 142067.27 | -24593.8 | -14.76% | 9739.68 | 4142.9 | -5596.78 | -57.46% | 96997 | 100869.48 | 3872.48 | 3.992% | 392.96 | 163 | -229.96 | -58.52% | 2022-08-18 01:00
Markham | 2022 | 639568 | 639568 - 2022 TX RENEWAL – BATCH 10 – 5 TX | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 105388.21 | 79111.71 | -26276.5 | -24.93% | 20320.12 | 15187.4 | -5132.72 | -25.26% | 46308.45 | 42558.74 | -3749.71 | -8.097% | 2386.64 | 2375.01 | -11.63 | -0.4873% | 36373 | 18990.56 | -17382.44 | -47.79% | 87.24 | 85.5 | -1.74 | -1.994% | 2022-07-21 01:00
Markham | 2022 | 639678 | 639678 - JOINT USE PERMIT #HE2020-087, 14TH AVE, MARKHAM | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 31533.65 | 26026.62 | -5507.03 | -17.46% | 11373.35 | 9410.66 | -1962.69 | -17.26% | 6547.09 | 6959.76 | 412.67 | 6.303% | 2413.21 | 1958.5 | -454.71 | -18.84% | 11200 | 7697.7 | -3502.3 | -31.27% | 78.7 | 73.5 | -5.2 | -6.607% | 2022-05-18 01:00
Markham | 2022 | 639680 | 639680 - JOINT USE PERMIT #HE2020-088, 14TH AVE., MARKHAM | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Bradley, Alex | Reginald Clarke | 13417.71 | 8753.48 | -4664.23 | -34.76% | 5381.35 | 4800.14 | -581.21 | -10.8% | 1091.49 | 1842.03 | 750.54 | 68.76% | 572.87 | 1105 | 532.13 | 92.89% | 6372 | 1006.31 | -5365.69 | -84.21% | 19.41 | 35 | 15.59 | 80.32% | 2022-04-05
Markham | 2021 | 639693 | 639693 - INSTALL POLE TO MAKE READY ADESSO | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Graham, Bruce W. | Macdonald, Larry | 13062.36 | 7133.48 | -5928.88 | -45.39% | 8481.45 | 4606.32 | -3875.13 | -45.69% | 3217.93 | 1454.16 | -1763.77 | -54.81% | 1362.98 | 1073 | -289.98 | -21.28% | 0 | 0 | 0 |  | 42.09 | 43 | 0.91 | 2.162% | 2021-06-09 01:00
Markham | 2021 | 639722 | 639722 - LESLIE ST. POLE REALIGNMENT | 99 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Barry, Kenneth | Macdonald, Steve | 280584.46 | 234833.72 | -45750.74 | -16.31% | 13217.88 | 26813.05 | 13595.17 | 102.9% | 66857.02 | 46514.91 | -20342.11 | -30.43% | 0 | 0 | 0 |  | 200509.56 | 161505.76 | -39003.8 | -19.45% | 0 | 0 | 0 |  | 2021-07-03 01:00
Markham | 2021 | 639764 | 639764 - JOINT USE PERMIT #HE2020-089, SUNSET BEACH RD, RICHMOND HILL | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 11573.6 | 9454.43 | -2119.17 | -18.31% | 3367.2 | 1635.65 | -1731.55 | -51.42% | 307.76 | 0 | -307.76 | -100% | 198.64 | 132 | -66.64 | -33.55% | 7700 | 7686.78 | -13.22 | -0.1717% | 7.36 | 6 | -1.36 | -18.48% | 2021-11-22 01:00
Markham | 2022 | 639766 | 639766 - JOINT USE PERMIT #HE2021-001- PARKER AVE- MAPLE GROVE AVE TO ELM GROVE AVE | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Steve | 6690.08 | 8028.09 | 1338.01 | 20% | 3033.68 | 0 | -3033.68 | -100% | 307.76 | 0 | -307.76 | -100% | 198.64 | 0 | -198.64 | -100% | 3150 | 8028.09 | 4878.09 | 154.9% | 7.36 | 0 | -7.36 | -100% | 2022-05-09 01:00
Markham | 2021 | 639784 | 639784 - POLE REPLACEMENT 2021 - AURORA PARK POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Morrow, Joe | 48912.66 | 48185 | -727.66 | -1.488% | 19368.22 | 29737.54 | 10369.32 | 53.54% | 12792.99 | 4624.7 | -8168.29 | -63.85% | 4871.45 | 10383 | 5511.55 | 113.1% | 11880 | 3439.76 | -8440.24 | -71.05% | 372.75 | 381 | 8.25 | 2.213% | 2021-03-01 01:00
Markham | 2021 | 639867 | 639867 - 2021 POLE RENEWAL - CN CROSSING - 14TH AVE (LEFTOVER) | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Steve | 48600 | 50685.19 | 2085.19 | 4.291% | 0 | 640.9 | 640.9 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 48600 | 50044.29 | 1444.29 | 2.972% | 0 | 0 | 0 |  | 2021-02-13 01:00
Markham | 2021 | 640069 | 640069 - JOINT USE PERMIT HE2021-002- NASHVILLE ROAD @ KLEIN'S CRES. | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 9542.27 | 8027.19 | -1515.08 | -15.88% | 3237.86 | 2700.71 | -537.15 | -16.59% | 651.09 | 143.04 | -508.05 | -78.03% | 303.32 | 861 | 557.68 | 183.9% | 5350 | 4322.44 | -1027.56 | -19.21% | 12.56 | 24 | 11.44 | 91.08% | 2021-11-03 01:00
Markham | 2021 | 640109 | SUNRISE ACQUISITIONS (HIGHWAY 7) INC. - SUBD RES EDS | 99 | CANCELLED | N/A |  |  | D'Onofrio, Tony | No | Estrada, Michael | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-28
Markham | 2021 | 640137 | 640137 - BUROAK TRANSFORMER RELOCATION | 99 | COMPLETE | Labour est. over | N/A | N/A | Corriveau, Tom N | No | Murray, Jake R | Horlings, Jake | 57568.59 | 43511.25 | -14057.34 | -24.42% | 26757.69 | 13562.59 | -13195.1 | -49.31% | 6937.06 | 4254.99 | -2682.07 | -38.66% | 4485.64 | 1464 | -3021.64 | -67.36% | 19388.2 | 24229.67 | 4841.47 | 24.97% | 177.25 | 56.5 | -120.75 | -68.12% | 2021-07-16 01:00
Markham | 2022 | 640208 | 640208 - 2021 POLE RENEWAL - BATHURST ST - METROLINX CROSSING | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Macdonald, Steve | 338982.68 | 339609.68 | 627 | 0.185% | 26012.15 | 35292.23 | 9280.08 | 35.68% | 65136.3 | 78364.44 | 13228.14 | 20.31% | 0 | 361.17 | 361.17 |  | 247834.23 | 225591.84 | -22242.39 | -8.975% | 0 | 8 | 8 |  | 2022-04-08
Markham | 2021 | 640233 | 640233 - JOINT USE PERMIT HE2021-004 | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 16639.8 | 9179.48 | -7460.32 | -44.83% | 4672.61 | 2947.47 | -1725.14 | -36.92% | 1462.09 | 286.07 | -1176.02 | -80.43% | 505.1 | 861 | 355.9 | 70.46% | 10000 | 5084.94 | -4915.06 | -49.15% | 17.77 | 24 | 6.23 | 35.06% | 2021-10-27 01:00
Markham | 2021 | 640243 | 640243 - 2021 EMERGING UG, V16 BRADWICK DR - 16-L40 TO 16-L38 CABLE REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 134167.79 | 136698.82 | 2531.03 | 1.886% | 12232.4 | 27400.05 | 15167.65 | 124% | 1863.09 | 1341.96 | -521.13 | -27.97% | 979.62 | 2214.56 | 1234.94 | 126.1% | 119092.68 | 105742.25 | -13350.43 | -11.21% | 16 | 77.5 | 61.5 | 384.4% | 2021-08-28 01:00
Markham | 2021 | 640252 | 640252 - HIGHWAY NO. 50 - #8865 - INDUSTRIAL/COMMERCIAL BLDG UPGRADE | 99 | COMPLETE | Under 10% |  |  | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 140175.1 | 143191.28 | 3016.18 | 2.152% | 27401.86 | 23970.54 | -3431.32 | -12.52% | 99091.03 | 88599.34 | -10491.69 | -10.59% | 3254.59 | 2965 | -289.59 | -8.898% | 32777.62 | 27656.4 | -5121.22 | -15.62% | 190.09 | 222.5 | 32.41 | 17.05% | 2021-09-15 01:00
Markham | 2021 | 640269 | 640269 - ANCHOR CONFLICTS - BAYVIEW AVE & VANDORF SDRD | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Larry | 14935.6 | 15142.9 | 207.3 | 1.388% | 6964.96 | 7193.18 | 228.22 | 3.277% | 3168.19 | 2874.9 | -293.29 | -9.257% | 2202.45 | 1345 | -857.45 | -38.93% | 2600 | 3729.82 | 1129.82 | 43.45% | 67.53 | 64 | -3.53 | -5.227% | 2021-04-22
Markham | 2022 | 640281 | 640281 - JOINT USE PERMIT HE2021-008 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Steve | 11798.89 | 8019.74 | -3779.15 | -32.03% | 4519.09 | 1052.25 | -3466.84 | -76.72% | 266.74 | 652.01 | 385.27 | 144.4% | 408.06 | 0 | -408.06 | -100% | 6605 | 6315.48 | -289.52 | -4.383% | 14.37 | 0 | -14.37 | -100% | 2022-05-09 01:00
Markham | 2021 | 640304 | 640304 - 2021 POLE RENEWAL - RELOCATION OF P48765 AT KIPLING AVE & HURRICANE AVE | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 25906.05 | 0 | -25906.05 | -100% | 7287.7 | 0 | -7287.7 | -100% | 1948.5 | 0 | -1948.5 | -100% | 1302.53 | 0 | -1302.53 | -100% | 15367.32 | 0 | -15367.32 | -100% | 49.64 | 0 | -49.64 | -100% | 2022-03-28
Markham | 2022 | 640439 | 640439 - GOULDING AVE PRIVATE ROAD EXTENSION - SUBD COMMERICAL EDS | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Swales, Mathew | Dave Lindsay | 181082.12 | 184838.63 | 3756.51 | 2.074% | 27894.32 | 32198.32 | 4304 | 15.43% | 3061.1 | 2946.11 | -114.99 | -3.756% | 1129.7 | 2116 | 986.3 | 87.31% | 148997 | 145579.65 | -3417.35 | -2.294% | 88.42 | 153.5 | 65.08 | 73.6% | 2022-05-05
Markham | 2022 | 640456 | 640456 - 85 VOGELL RD/RHL / NS/ 3PH PAD | 95 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 95401.05 | 99680.19 | 4279.14 | 4.485% | 23232.84 | 31552.49 | 8319.65 | 35.81% | 49700.89 | 49820.19 | 119.3 | 0.24% | 2467.32 | 1876 | -591.32 | -23.97% | 20000 | 16431.51 | -3568.49 | -17.84% | 132.42 | 271 | 138.58 | 104.7% | 2022-12-08 01:00
Markham | 2022 | 640457 | 11724 DUFFERIN ST / VAU / NS / 1PH PAD TX | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Mann, Drew | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-05-14
Markham | 2022 | 640466 | A05 GOLF LINKS DRIVE, SWITCHGEAR & CABLE REPLACEMENT | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Handy, James | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-04-07
Markham | 2022 | 640467 | 640467 - 2021 EMERGING UG, M46 MARKLAND ST AND HILLMOUNT RD LOOP SPLIT | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Horlings, Jake | 291409.28 | 296301.27 | 4891.99 | 1.679% | 38818.49 | 65076.19 | 26257.7 | 67.64% | 27829.34 | 15393.18 | -12436.16 | -44.69% | 5639.53 | 7589.42 | 1949.89 | 34.58% | 219121.92 | 208242.48 | -10879.44 | -4.965% | 313.31 | 311.5 | -1.81 | -0.5777% | 2022-04-07
Markham | 2021 | 640469 | HIGHLAND GATE - SUBDIVISION RES EDS | 99 | COMPLETE | Converted Project |  |  | D'Onofrio, Tony | No | Perks, Dan | Dave Lindsay | 0 | 24934.97 | 24934.97 |  | 0 | 18133.07 | 18133.07 |  | 0 | 3479.9 | 3479.9 |  | 0 | 3322 | 3322 |  | 0 | 0 | 0 |  | 0 | 187.5 | 187.5 |  | 2021-12-02 01:00
Markham | 2021 | 640515 | 640515 - CONNECTION OF BELL BOND- RUTHERFORD ROAD- P49496 | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | Yes | Martin, Shane | Don Rothman | 748.96 | 630.04 | -118.92 | -15.88% | 703.96 | 591.54 | -112.42 | -15.97% | 0 | 0 | 0 |  | 45 | 38.5 | -6.5 | -14.44% | 0 | 0 | 0 |  | 2 | 2 | 0 | 0% | 2021-04-20
Markham | 2021 | 640518 | 640518 - CONNECTION OF BELL BONDS- VARIOUS LOCATIONS, VAUGHAN | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Don Rothman | 1267.79 | 1075.4 | -192.39 | -15.18% | 1132.79 | 922.9 | -209.89 | -18.53% | 0 | 0 | 0 |  | 135 | 152.5 | 17.5 | 12.96% | 0 | 0 | 0 |  | 6 | 5 | -1 | -16.67% | 2021-04-20
Markham | 2021 | 640520 | 640520 - 2021 LEFT-BEHIND - M37 CABLE REPLACEMENTS, 4 SEGMENTS | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 374447.6 | 342396.94 | -32050.66 | -8.559% | 31314.75 | 63925.89 | 32611.14 | 104.1% | 4818.91 | 4890.38 | 71.47 | 1.483% | 4515.62 | 4479.01 | -36.61 | -0.8107% | 333798.32 | 269101.66 | -64696.66 | -19.38% | 79.69 | 161 | 81.31 | 102% | 2021-10-13 01:00
Markham | 2021 | 640521 | 640521 - 2021 LEFT-BEHIND - M40 CABLE REPLACEMENTS, 2 SEGMENTS | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 222136.59 | 193381.26 | -28755.33 | -12.94% | 17312.3 | 38699.82 | 21387.52 | 123.5% | 1212.09 | 642.32 | -569.77 | -47.01% | 2272.12 | 2757.9 | 485.78 | 21.38% | 201340.08 | 151281.22 | -50058.86 | -24.86% | 109.23 | 96 | -13.23 | -12.11% | 2021-08-31 01:00
Markham | 2021 | 640522 | 640522 - 2021 LB CABLE REPLACEMENT - V18 BARHILL, 3 SEGMENTS | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 362389.94 | 327516.9 | -34873.04 | -9.623% | 20623.93 | 60728.16 | 40104.23 | 194.5% | 2801.23 | 4178.58 | 1377.35 | 49.17% | 2497.26 | 2696.91 | 199.65 | 7.995% | 336467.52 | 259913.25 | -76554.27 | -22.75% | 121.87 | 121 | -0.87 | -0.7139% | 2021-08-25 01:00
Markham | 2021 | 640523 | 640523 - 2021 LEFT-BEHIND - V36 CABLE REPLACEMENT, 36-L20 TO 36-L21 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 216412.55 | 199444.36 | -16968.19 | -7.841% | 14636.9 | 37179.16 | 22542.26 | 154% | 1243.73 | 0 | -1243.73 | -100% | 1031.08 | 1459.74 | 428.66 | 41.57% | 199500.84 | 160805.46 | -38695.38 | -19.4% | 30 | 65 | 35 | 116.7% | 2021-11-06 01:00
Markham | 2021 | 640524 | 640524 - 2021 LEFT-BEHIND - V37 CABLE REPLACEMENTS, 3 SEGMENTS | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 168191.13 | 136064.28 | -32126.85 | -19.1% | 37302.72 | 35577.59 | -1725.13 | -4.625% | 11070.52 | 8270.28 | -2800.24 | -25.29% | 4904.81 | 7027.02 | 2122.21 | 43.27% | 114913.08 | 85189.39 | -29723.69 | -25.87% | 310.17 | 194.5 | -115.67 | -37.29% | 2021-11-12 01:00
Markham | 2021 | 640525 | 640525 - 2021 LEFT-BEHIND - V38 CABLE REPLACEMENT, 38-180 TO 38-181 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 53610.12 | 43450.16 | -10159.96 | -18.95% | 12086.29 | 11479.24 | -607.05 | -5.023% | 847.91 | 0 | -847.91 | -100% | 981.6 | 521.17 | -460.43 | -46.91% | 39694.32 | 31449.75 | -8244.57 | -20.77% | 69.6 | 26 | -43.6 | -62.64% | 2021-08-06 01:00
Markham | 2021 | 640526 | 640526 - 2021 LB CABLE REPLACEMENT - V43 BRUCE ST, 43-69 TO V43FA3037 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 419488.32 | 419288.92 | -199.4 | -0.04753% | 47832.51 | 73927.33 | 26094.82 | 54.55% | 1371.88 | 0 | -1371.88 | -100% | 2112.93 | 4028.34 | 1915.41 | 90.65% | 368171 | 341333.25 | -26837.75 | -7.289% | 100.56 | 108 | 7.44 | 7.399% | 2021-10-26 01:00
Markham | 2021 | 640649 | 640649 - EQUIPMENT REMOVAL FOR SHINING HILL PHASE 2 - SUB CUST CAP | 99 | COMPLETE | Labour est. over | N/A | N/A | D'Onofrio, Tony | No | Swales, Mathew | Dave Lindsay | 11579.89 | 6524.81 | -5055.08 | -43.65% | 9995.83 | 5678.81 | -4317.02 | -43.19% | 0 | 0 | 0 |  | 1584.06 | 846 | -738.06 | -46.59% | 0 | 0 | 0 |  | 41.97 | 30 | -11.97 | -28.52% | 2021-04-27
Markham | 2022 | 640663 | 640663 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.2 | 95 | COMPLETE | Cont Est Over | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Macdonald, Steve | 1556638.48 | 1367165.25 | -189473.23 | -12.17% | 145008.05 | 115241.12 | -29766.93 | -20.53% | 609043.96 | 657520.77 | 48476.81 | 7.959% | 2470 | 1390 | -1080 | -43.72% | 800116.47 | 593013.36 | -207103.11 | -25.88% | 154 | 147 | -7 | -4.545% | 2022-09-17 01:00
Markham | 2022 | 640691 | 640691 - 2022 POLE RENEWAL - FONTHILL BLVD & KREIGHOFF AVE, MARKHAM (2021 CARRYOVER) | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | No | Canale, Alfred | Kristine Gordon | 51996.54 | 54149.81 | 2153.27 | 4.141% | 24254.87 | 23051.16 | -1203.71 | -4.963% | 11400.63 | 12927.68 | 1527.05 | 13.39% | 4461.04 | 5602.63 | 1141.59 | 25.59% | 11880 | 12568.34 | 688.34 | 5.794% | 180.42 | 201 | 20.58 | 11.41% | 2022-11-29 01:00
Markham | 2021 | 640823 | 640823 - JOINT USE PERMIT HE2021-022 | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Larry | 14448.05 | 8355.94 | -6092.11 | -42.17% | 4723.96 | 3428.93 | -1295.03 | -27.41% | 1059.08 | 523.01 | -536.07 | -50.62% | 485.01 | 624 | 138.99 | 28.66% | 8180 | 3780 | -4400 | -53.79% | 19.75 | 24 | 4.25 | 21.52% | 2021-10-12 01:00
Markham | 2021 | 640826 | 640826 - 2021 EMERGING UG, A10 BATSON DR, CABLE FAILURE REPLACEMENTS | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Lamb, Tim | 521712.35 | 478641.7 | -43070.65 | -8.256% | 24523.82 | 79770.4 | 55246.58 | 225.3% | 2406.69 | 782.43 | -1624.26 | -67.49% | 3382.92 | 3850.92 | 468 | 13.83% | 491398.92 | 394237.95 | -97160.97 | -19.77% | 178.82 | 148 | -30.82 | -17.24% | 2021-05-14
Markham | 2021 | 640833 | 640833 - JOINT USE PERMIT HE2021-024 | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 14419.88 | 7985.24 | -6434.64 | -44.62% | 3505.33 | 2998.85 | -506.48 | -14.45% | 1393.17 | 1285.39 | -107.78 | -7.736% | 395.38 | 551 | 155.62 | 39.36% | 9126 | 3150 | -5976 | -65.48% | 14.38 | 21 | 6.62 | 46.04% | 2021-11-05 01:00
Markham | 2022 | 640843 | 640843 - 64/66 GOLF LINKS DR - SWITCHGEAR REMOVAL | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Perks, Dan | Dave Lindsay | 246315.79 | 283393.48 | 37077.69 | 15.05% | 51154.04 | 56950.32 | 5796.28 | 11.33% | 3016.33 | 7954.05 | 4937.72 | 163.7% | 2296.42 | 1278 | -1018.42 | -44.35% | 189849 | 215313.06 | 25464.06 | 13.41% | 254.77 | 162 | -92.77 | -36.41% | 2022-05-05
Markham | 2022 | 640853 | 640853 - LEE AVENUE POLE REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Alarcon, Alejandro | Reginald Clarke | 19313.53 | 20271.02 | 957.49 | 4.958% | 10530.19 | 11300.26 | 770.07 | 7.313% | 3609.88 | 5348.76 | 1738.88 | 48.17% | 1573.46 | 3622 | 2048.54 | 130.2% | 3600 | 0 | -3600 | -100% | 58.6 | 84 | 25.4 | 43.34% | 2022-05-17 01:00
Markham | 2022 | 640872 | 640872 - DICKSON 48 PHASE 2 - STAGE 1 - SUBD RESIDENTIAL EDS | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Swales, Mathew | Dave Lindsay | 17850.04 | 12908.26 | -4941.78 | -27.68% | 12431.26 | 8631.26 | -3800 | -30.57% | 663.48 | 0 | -663.48 | -100% | 855.3 | 377 | -478.3 | -55.92% | 3900 | 3900 | 0 | 0% | 75.13 | 47 | -28.13 | -37.44% | 2022-05-05
Markham | 2021 | 640891 | 640891 - CUSTOMER INITIATED OH RELOCATION - 88 SIMMONS ST, VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Zhang, Jiacheng | Ryan Walsh | 16757.07 | 17196.91 | 439.84 | 2.625% | 7605.86 | 8459.86 | 854 | 11.23% | 1118.29 | 1083.07 | -35.22 | -3.149% | 580.92 | 2256 | 1675.08 | 288.3% | 7452 | 5397.98 | -2054.02 | -27.56% | 36.45 | 71 | 34.55 | 94.79% | 2021-08-03 01:00
Markham | 2021 | 640894 | 640894 - 2021 POLE RENEWAL - GUY WIRE REPLACEMENTS, SAFETY CONCERNS FROM CITY OF MARKHAM | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 10915.22 | 9630.02 | -1285.2 | -11.77% | 5086.33 | 5259.86 | 173.53 | 3.412% | 3443.59 | 3455.16 | 11.57 | 0.336% | 2385.3 | 915 | -1470.3 | -61.64% | 0 | 0 | 0 |  | 38.2 | 30 | -8.2 | -21.47% | 2021-03-19 01:00
Markham | 2022 | 640895 | 640895 - 55 GOULDING AVE, AURORA - 3 PHASE SERVICE | 99 | COMPLETE | Cont Est Over | Material Over Estimated | N/A | Cranley, Stephen | No | Harris, Geoff L. | Dave Lindsay | 76674.19 | 61891.25 | -14782.94 | -19.28% | 21805.74 | 24648.67 | 2842.93 | 13.04% | 40513.21 | 35501.16 | -5012.05 | -12.37% | 1787.24 | 937 | -850.24 | -47.57% | 12568 | 804.42 | -11763.58 | -93.6% | 115.17 | 198 | 82.83 | 71.92% | 2022-07-19 01:00
Markham | 2022 | 640921 | 640921 - JOINT USE PERMIT HE2021-032 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Macdonald, Steve | 12500.52 | 22349.68 | 9849.16 | 78.79% | 3959.12 | 2667.7 | -1291.42 | -32.62% | 423.27 | 670.75 | 247.48 | 58.47% | 266.13 | 0 | -266.13 | -100% | 7852 | 19011.23 | 11159.23 | 142.1% | 8.19 | 0 | -8.19 | -100% | 2022-04-04
Markham | 2022 | 640960 | 640960 - PINE VALLEY DR. - #10150 (BELL SERVICE) | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Joshi, Namrata | No | Yuen, Paul | Dave Lindsay | 51837.29 | 35995.92 | -15841.37 | -30.56% | 21481.96 | 14095.58 | -7386.38 | -34.38% | 14050.67 | 7933.63 | -6117.04 | -43.54% | 2927.86 | 3141 | 213.14 | 7.28% | 13376.8 | 10825.71 | -2551.09 | -19.07% | 102.02 | 125.5 | 23.48 | 23.02% | 2022-10-07 01:00
Markham | 2022 | 640971 | 640971 - HUNT AVENUE SUBDIVISION - SUBD RES EDS | 99 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Swales, Mathew | Dave Lindsay | 202952.82 | 185767.49 | -17185.33 | -8.468% | 48676.05 | 33086.28 | -15589.77 | -32.03% | 5230.73 | 4611.71 | -619.02 | -11.83% | 3444.04 | 2467.5 | -976.54 | -28.35% | 145602 | 145602 | 0 | 0% | 184.9 | 87.5 | -97.4 | -52.68% | 2022-03-17 01:00
Markham | 2021 | 640980 | 640980 - MARKHAM SIDEWALK PROGRAM | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Larry | 13279.88 | 12083.42 | -1196.46 | -9.01% | 7608.71 | 6556.19 | -1052.52 | -13.83% | 2188.71 | 3230.28 | 1041.57 | 47.59% | 1106.46 | 1652 | 545.54 | 49.3% | 2376 | 644.95 | -1731.05 | -72.86% | 53.93 | 55 | 1.07 | 1.984% | 2021-08-09 01:00
Markham | 2022 | 641015 | 641015 - JOINT USE PERMIT HE2021-034 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 14688.77 | 7338.28 | -7350.49 | -50.04% | 5483.92 | 2563.39 | -2920.53 | -53.26% | 688.32 | 724.89 | 36.57 | 5.313% | 766.53 | 0 | -766.53 | -100% | 7750 | 4050 | -3700 | -47.74% | 26.81 | 0 | -26.81 | -100% | 2022-04-27
Markham | 2021 | 641064 | 2851 HWY 7 - HYDRO POLE RELOCATION - VAUGHAN | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Yuen, Paul | East Coordinator | 0 | 1788.18 | 1788.18 |  | 0 | 1788.18 | 1788.18 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0.5 | 0.5 |  | 2021-12-06 01:00
Markham | 2021 | 641130 | 641130 - 135 INDUSTRIAL PARKWAY N/AUR/NS/3PH PAD | 99 | COMPLETE | BOM not accurate | Cont Est Under | N/A | Cranley, Stephen | No | Paterson, Greg | Dave Lindsay | 30191.5 | 69878.58 | 39687.08 | 131.5% | 14198.91 | 21681.34 | 7482.43 | 52.7% | 1493.48 | 21287.77 | 19794.29 | 1325% | 1539.11 | 5594 | 4054.89 | 263.5% | 12960 | 21315.47 | 8355.47 | 64.47% | 82.68 | 199 | 116.32 | 140.7% | 2021-11-11 01:00
Markham | 2022 | 641151 | 641151 - 95 CLEGG RD / MAR / UP / 3PH PAD TX | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 141030.63 | 173511.41 | 32480.78 | 23.03% | 26645.78 | 34227.08 | 7581.3 | 28.45% | 102541.69 | 90057.46 | -12484.23 | -12.17% | 2478.16 | 2890 | 411.84 | 16.62% | 31715 | 46336.87 | 14621.87 | 46.1% | 171.74 | 203 | 31.26 | 18.2% | 2022-03-17 01:00
Markham | 2022 | 641167 | 641167 - 1400 CREDITSTONE RD. | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 107760.65 | 113973.93 | 6213.28 | 5.766% | 16625.17 | 16405.58 | -219.59 | -1.321% | 89049.68 | 92734.98 | 3685.3 | 4.138% | 2085.8 | 2195 | 109.2 | 5.235% | 0 | 2638.37 | 2638.37 |  | 102.08 | 107 | 4.92 | 4.82% | 2022-10-07 01:00
Markham | 2022 | 641197 | 641197 - VOLTAGE CONVERSION - CONVERT CUSTOMERS ON MORGAN MS INTO 27.6KV SUPPLY, MARKHAM | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Morrow, Joe | 1236870.6 | 930506.55 | -306364.05 | -24.77% | 488630.17 | 341433.41 | -147196.76 | -30.12% | 272236.15 | 238296.24 | -33939.91 | -12.47% | 139651.28 | 100500.81 | -39150.47 | -28.03% | 336353 | 250276.09 | -86076.91 | -25.59% | 3748.72 | 3687.5 | -61.22 | -1.633% | 2022-12-29 01:00
Markham | 2021 | 641198 | 641198 - POLE REPLACEMENT 2021 - REPLACE P33475 ON INDUSTRIAL PARKWAY S | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Roy, James | Reginald Clarke | 33143.51 | 31777.92 | -1365.59 | -4.12% | 16408.46 | 12942.32 | -3466.14 | -21.12% | 3805.67 | 2565.41 | -1240.26 | -32.59% | 3529.38 | 4533.66 | 1004.28 | 28.45% | 9400 | 11736.53 | 2336.53 | 24.86% | 107.58 | 68.5 | -39.08 | -36.33% | 2021-11-22 01:00
Markham | 2021 | 641235 | 641235 - STRUT INSTALLATION VILLAGE GATE BROWNSTONES | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Reginald Clarke | 13013.35 | 7024.64 | -5988.71 | -46.02% | 5931.44 | 3629.8 | -2301.64 | -38.8% | 932.18 | 885.8 | -46.38 | -4.975% | 449.73 | 551 | 101.27 | 22.52% | 5700 | 1958.04 | -3741.96 | -65.65% | 19.15 | 21 | 1.85 | 9.661% | 2021-11-22 01:00
Markham | 2022 | 641283 | 5546 MAJOR MACKENZIE DR / MAR / UP / 1PH PAD | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Mann, Drew | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-15 01:00
Markham | 2022 | 641284 | 641284 - 130 ADDISON HALL CIRCLE/AUR/NS/3 PH | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Dave Lindsay | 27354.28 | 41742.66 | 14388.38 | 52.6% | 17742.89 | 12966.88 | -4776.01 | -26.92% | 24802.13 | 24044.99 | -757.14 | -3.053% | 1940.26 | 304 | -1636.26 | -84.33% | 5219 | 4426.79 | -792.21 | -15.18% | 109.28 | 84 | -25.28 | -23.13% | 2022-03-15 01:00
Markham | 2022 | 641289 | 641289 - 17 MILLWOOD PARKWAY DEVELOPMENT – SUBD RES EDS | 99 | ANALYZE |  |  |  | Penner, Mitchell | No | Alarcon, Alejandro | Dave Lindsay | 110563.11 | 98412.03 | -12151.08 | -10.99% | 27842.6 | 17453.03 | -10389.57 | -37.32% | 765.56 | 0 | -765.56 | -100% | 1451.95 | 456 | -995.95 | -68.59% | 80503 | 80503 | 0 | 0% | 90.13 | 65.5 | -24.63 | -27.33% | 2022-12-08 01:00
Markham | 2021 | 641317 | 641317 - 2021 EMERGING OH, RISER TAP CHANGES FOR FEEDER LOAD BALANCING | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 49538.13 | 65832.68 | 16294.55 | 32.89% | 28069.37 | 38105.9 | 10036.53 | 35.76% | 14036.02 | 10017.51 | -4018.51 | -28.63% | 5812.74 | 15584.27 | 9771.53 | 168.1% | 1620 | 2125 | 505 | 31.17% | 327.24 | 338.5 | 11.26 | 3.441% | 2021-07-14 01:00
Markham | 2021 | 641332 | 641332 - JOINT USE PERMIT HE2021-038- 8025 JANE STREET | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 6117.26 | 4631.43 | -1485.83 | -24.29% | 2845.26 | 1283.43 | -1561.83 | -54.89% | 0 | 0 | 0 |  | 122 | 198 | 76 | 62.3% | 3150 | 3150 | 0 | 0% | 6 | 9 | 3 | 50% | 2021-12-09 01:00
Markham | 2022 | 641350 | 641350 - 6685 LANGSTAFF ROAD/VAU/NS/ 3-PH PAD | 99 | COMPLETE | BOM not accurate | Cont Est Over | Labour est. over | Joshi, Namrata | No | Diefenbaker, Trevor A | Dave Lindsay | 142280.58 | 70762.86 | -71517.72 | -50.27% | 23609.25 | 21708.47 | -1900.78 | -8.051% | 109357.89 | 12845.09 | -96512.8 | -88.25% | 2054.44 | 1813 | -241.44 | -11.75% | 29609 | 34396.3 | 4787.3 | 16.17% | 128.37 | 169.5 | 41.13 | 32.04% | 2022-03-17 01:00
Markham | 2021 | 641370 | 641370 - 4134 16TH AVE/MAR/SR/3PH VAULT | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 14229.07 | 11284.16 | -2944.91 | -20.7% | 10981.98 | 8826.16 | -2155.82 | -19.63% | 0 | 0 | 0 |  | 1739.41 | 2458 | 718.59 | 41.31% | 1507.68 | 0 | -1507.68 | -100% | 55.62 | 76 | 20.38 | 36.64% | 2021-07-21 01:00
Markham | 2022 | 641389 | 641389 - 101 MILANI BLVD / VAU / NS / 3PH PAD TX | 99 | COMPLETE | Under 10% | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 234958.08 | 233756.7 | -1201.38 | -0.5113% | 36094.41 | 40791.82 | 4697.41 | 13.01% | 152832.81 | 145680.78 | -7152.03 | -4.68% | 2758.86 | 1348 | -1410.86 | -51.14% | 43272 | 45936.1 | 2664.1 | 6.157% | 200.86 | 266.5 | 65.64 | 32.68% | 2022-05-05
Markham | 2021 | 641407 | 641407 - BLENCATHRA HILL - #18 | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 40012.5 | 39525.34 | -487.16 | -1.218% | 12653.71 | 12272.57 | -381.14 | -3.012% | 10735.71 | 7257.78 | -3477.93 | -32.4% | 1178.08 | 1980 | 801.92 | 68.07% | 16689 | 18014.99 | 1325.99 | 7.945% | 51.71 | 86 | 34.29 | 66.31% | 2021-12-08 01:00
Markham | 2021 | 641460 | 641460 - 5011 TESTON RD/ VAU/ UP/ 1PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Joshi, Namrata | No | Diefenbaker, Trevor A | Reginald Clarke | 12932.42 | 6180.58 | -6751.84 | -52.21% | 11608.12 | 6058.58 | -5549.54 | -47.81% | 10.67 | 0 | -10.67 | -100% | 1313.63 | 122 | -1191.63 | -90.71% | 0 | 0 | 0 |  | 40.57 | 39 | -1.57 | -3.87% | 2021-12-07 01:00
Markham | 2021 | 641474 | 641474 - MURRY DR, EAST OF NISBET DR | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Steve | 57098.36 | 60612.06 | 3513.7 | 6.154% | 10061.36 | 10626.08 | 564.72 | 5.613% | 7969.32 | 10843.03 | 2873.71 | 36.06% | 0 | 0 | 0 |  | 39067.68 | 39142.95 | 75.27 | 0.1927% | 0 | 0 | 0 |  | 2021-12-03 01:00
Markham | 2021 | 641498 | 641498 - BELL BOND CONNECTIONS- PINE VALLEY DR.- MAJOR MACK TO PINE HEIGHTS DR. | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Don Rothman | 1527.2 | 1266.32 | -260.88 | -17.08% | 1347.2 | 1022.32 | -324.88 | -24.12% | 0 | 0 | 0 |  | 180 | 244 | 64 | 35.56% | 0 | 0 | 0 |  | 8 | 10 | 2 | 25% | 2021-07-12 01:00
Markham | 2021 | 641499 | 641499 - BELL BOND CONNECTION- MAJOR MACK WEST OF WESTON ROAD | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Don Rothman | 1267.79 | 670.55 | -597.24 | -47.11% | 1132.79 | 579.05 | -553.74 | -48.88% | 0 | 0 | 0 |  | 135 | 91.5 | -43.5 | -32.22% | 0 | 0 | 0 |  | 6 | 4.5 | -1.5 | -25% | 2021-11-28 01:00
Markham | 2022 | 641575 | 641575 - 2022 TX VAULT RENEWAL, MAIN ST N UNIONVILLE (4 LOCATIONS) | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 493123.05 | 518039.75 | 24916.7 | 5.053% | 127190.95 | 147214.06 | 20023.11 | 15.74% | 54272.74 | 41177.85 | -13094.89 | -24.13% | 9978.11 | 8570.75 | -1407.36 | -14.1% | 301681.25 | 321077.09 | 19395.84 | 6.429% | 312.77 | 494 | 181.23 | 57.94% | 2022-11-04 01:00
Markham | 2021 | 641616 | 641616 - 50 INTERCHANGE WAY / VAU / SR / SEC DEMO | 99 | COMPLETE | BOM not accurate | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 3443.02 | 2640.99 | -802.03 | -23.29% | 2745.11 | 2296.49 | -448.62 | -16.34% | 288 | 0 | -288 | -100% | 409.91 | 344.5 | -65.41 | -15.96% | 0 | 0 | 0 |  | 18.47 | 26.5 | 8.03 | 43.48% | 2021-07-21 01:00
Markham | 2021 | 641620 | 641620 - 2021 POLE RENEWAL - 37 IDLESWIFT DR, VAUGHAN | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Tenorlas, Reynaldo | No | Canale, Alfred | Macdonald, Larry | 11214 | 5514.9 | -5699.1 | -50.82% | 5275.16 | 2964.91 | -2310.25 | -43.79% | 2034.22 | 1308.06 | -726.16 | -35.7% | 880.62 | 1241.93 | 361.31 | 41.03% | 3024 | 0 | -3024 | -100% | 40.19 | 22 | -18.19 | -45.26% | 2021-08-10 01:00
Markham | 2021 | 641646 | 641646 - SPAN GUY TRANSFER ON STEELES AVE W - JU1500079 POLE REMOVAL | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Handy, James | Macdonald, Larry | 14856 | 14681.58 | -174.42 | -1.174% | 5852.7 | 5750.93 | -101.77 | -1.739% | 3258.16 | 2585.49 | -672.67 | -20.65% | 1317.14 | 2993.93 | 1676.79 | 127.3% | 4428 | 3351.23 | -1076.77 | -24.32% | 40.2 | 40 | -0.2 | -0.4975% | 2021-08-19 01:00
Markham | 2021 | 641694 | 641694 - SUNSET SIX – SUBD RES EDS | 99 | COMPLETE | Labour est. over | N/A | N/A | Penner, Mitchell | No | Alarcon, Alejandro | Dave Lindsay | 64314.99 | 56248.53 | -8066.46 | -12.54% | 16486.44 | 12369.8 | -4116.64 | -24.97% | 2260.2 | 1735.73 | -524.47 | -23.2% | 1518.35 | 1093 | -425.35 | -28.01% | 44050 | 41050 | -3000 | -6.81% | 77.49 | 64.5 | -12.99 | -16.76% | 2021-12-02 01:00
Markham | 2021 | 641716 | 641716 - 1 COMMERCE ST / VAU / NS / 3PH PAD TX | 99 | COMPLETE | Under 10% | N/A | N/A | Dibratto, Susan | No | Mann, Drew | Dave Lindsay | 76255.72 | 79846.47 | 3590.75 | 4.709% | 19919.21 | 11870.46 | -8048.75 | -40.41% | 57645.39 | 48978.32 | -8667.07 | -15.04% | 1634.12 | 644.5 | -989.62 | -60.56% | 19407 | 18353.19 | -1053.81 | -5.43% | 120.45 | 63 | -57.45 | -47.7% | 2021-12-02 01:00
Markham | 2021 | 641738 | MARKHAM RD. - #7650 AT HIGHGLEN AVE. (IVY CHARGING STATION) | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Yuen, Paul | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-11 01:00
Markham | 2021 | 641764 | 47 GEORGE STREET HYDRO RELOCATION - NEW TECUMSETH | 99 | CANCELLED | N/A |  |  | Murray, Jake R | No | Corriveau, Tom N | East Coordinator | 0 | 13652.47 | 13652.47 |  | 0 | 5075.06 | 5075.06 |  | 0 | 0 | 0 |  | 0 | 635 | 635 |  | 0 | 7942.41 | 7942.41 |  | 0 | 25 | 25 |  | 2021-08-11 01:00
Markham | 2021 | 641766 | 641766 - MILL STREET & ROUGE STREET, MARKHAM | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Corriveau, Tom N | No | Battistella, Alexander | Macdonald, Larry | 18412.97 | 6775.49 | -11637.48 | -63.2% | 9881.7 | 3597.42 | -6284.28 | -63.6% | 1118.29 | 1083.07 | -35.22 | -3.149% | 1796.98 | 715 | -1081.98 | -60.21% | 5616 | 1380 | -4236 | -75.43% | 54.56 | 25 | -29.56 | -54.18% | 2021-08-11 01:00
Markham | 2022 | 641780 | HUNTINGTON RD, RUTHERFORD RD TO LANGSTAFF RD (SEG 1) | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-04 01:00
Markham | 2022 | 641781 | 641781 - HUNTINGTON RD, MAJOR MACKENZIE DR TO EAST CORNERS BLVD (DEV) | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Corriveau, Tom N | No | Battistella, Alexander | Morrow, Joe | 541529.12 | 618386.73 | 76857.61 | 14.19% | 167624.74 | 258682.79 | 91058.05 | 54.32% | 129618.09 | 125203.22 | -4414.87 | -3.406% | 38539.71 | 83353 | 44813.29 | 116.3% | 205746.58 | 151147.72 | -54598.86 | -26.54% | 3145.02 | 3048 | -97.02 | -3.085% | 2022-10-04 01:00
Markham | 2022 | 641783 | 641783 - 2022 SG REPL - BATCH 1 - AURORA | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 86835.95 | 60960.86 | -25875.09 | -29.8% | 32248.7 | 13819.14 | -18429.56 | -57.15% | 48094.59 | 43699.55 | -4395.04 | -9.138% | 4492.66 | 2299 | -2193.66 | -48.83% | 2000 | 1143.17 | -856.83 | -42.84% | 268.17 | 89 | -179.17 | -66.81% | 2022-11-01 01:00
Markham | 2022 | 641784 | 2022 SG REPL - BATCH 2 - MARKHAM | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Roy, James | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-08 01:00
Markham | 2022 | 641785 | 641785 - 2022 SG REPL - BATCH 3 - RICHMOND HILL | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 93906.56 | 92136.38 | -1770.18 | -1.885% | 18328.55 | 11971.58 | -6356.97 | -34.68% | 67266.81 | 75896.01 | 8629.2 | 12.83% | 2189.2 | 0 | -2189.2 | -100% | 6122 | 4268.79 | -1853.21 | -30.27% | 132.63 | 64 | -68.63 | -51.75% | 2022-12-08 01:00
Markham | 2022 | 641787 | 2022 SG REPL - BATCH 5 - VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Roy, James | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-04 01:00
Markham | 2022 | 641788 | 2022 SG REPL - BATCH 6 - VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Roy, James | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-04 01:00
Markham | 2022 | 641789 | 2022 SG REPL - BATCH 7 - VAUGHAN | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | Yes | Roy, James | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-04 01:00
Markham | 2022 | 641791 | 641791 - 2022 SG REPL - AUTO 31SUG009 - MARKHAM | 99 | COMPLETE | BOM not accurate | Labour est. under | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 171636.03 | 195510.57 | 23874.54 | 13.91% | 17955.19 | 23932.44 | 5977.25 | 33.29% | 98570.58 | 113871.8 | 15301.22 | 15.52% | 1526.26 | 3631 | 2104.74 | 137.9% | 53584 | 54075.33 | 491.33 | 0.9169% | 92.94 | 164 | 71.06 | 76.46% | 2022-11-04 01:00
Markham | 2022 | 641792 | 641792 - 2022 SG REPL - AUTO 43SUG002 - MARKHAM | 99 | COMPLETE | Labour est. under | Cont Est Under | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 180858.26 | 204178.66 | 23320.4 | 12.89% | 18155.27 | 28596.45 | 10441.18 | 57.51% | 105091.73 | 109708.49 | 4616.76 | 4.393% | 1526.26 | 3834.5 | 2308.24 | 151.2% | 56085 | 62039.22 | 5954.22 | 10.62% | 92.94 | 191 | 98.06 | 105.5% | 2022-11-04 01:00
Markham | 2022 | 641793 | 641793 - 2022 SG REPL - AUTO 21SUG007 - MARKHAM | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 164689.11 | 190365.13 | 25676.02 | 15.59% | 17512.47 | 26713.26 | 9200.79 | 52.54% | 97600.38 | 106698.66 | 9098.28 | 9.322% | 1526.26 | 4234.64 | 2708.38 | 177.5% | 48050 | 52718.57 | 4668.57 | 9.716% | 92.94 | 152 | 59.06 | 63.55% | 2022-11-04 01:00
Markham | 2022 | 641794 | 641794 - 2022 SG REPL - AUTO 39SUG001 - MARKHAM | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 250400.47 | 238654.21 | -11746.26 | -4.691% | 44928.64 | 35459.32 | -9469.32 | -21.08% | 109775.47 | 115492.42 | 5716.95 | 5.208% | 6562.36 | 6984 | 421.64 | 6.425% | 89134 | 80718.47 | -8415.53 | -9.441% | 245.77 | 247 | 1.23 | 0.5005% | 2022-07-28 01:00
Markham | 2022 | 641795 | 641795 - 2022 SG REPL - AUTO 9SC32 - RH | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 177493.68 | 187281.98 | 9788.3 | 5.515% | 30143.25 | 30374.94 | 231.69 | 0.7686% | 100789.71 | 104565.14 | 3775.43 | 3.746% | 2864.72 | 3109 | 244.28 | 8.527% | 43696 | 49232.9 | 5536.9 | 12.67% | 148.94 | 221.5 | 72.56 | 48.72% | 2022-09-01 01:00
Markham | 2022 | 641796 | 641796 - 2022 SG REPL - AUTO 17-L80 - VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 168278.5 | 160295.83 | -7982.67 | -4.744% | 27267.37 | 23449.71 | -3817.66 | -14% | 101240.41 | 100289.76 | -950.65 | -0.939% | 2864.72 | 2242.5 | -622.22 | -21.72% | 36906 | 34313.86 | -2592.14 | -7.024% | 148.94 | 152.5 | 3.56 | 2.39% | 2022-09-01 01:00
Markham | 2022 | 641797 | 641797 - 2022 SG REPL - AUTO 43-L17 - VAUGHAN | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Roy, James | Horlings, Jake | 162268.04 | 167027.16 | 4759.12 | 2.933% | 27833.87 | 25501.79 | -2332.08 | -8.379% | 106074.53 | 117912.88 | 11838.35 | 11.16% | 3289.64 | 3441.84 | 152.2 | 4.627% | 25070 | 20170.65 | -4899.35 | -19.54% | 166.34 | 169 | 2.66 | 1.599% | 2022-12-02 01:00
Markham | 2022 | 641801 | 641801 - HUNTINGTON RD & LANGSTAFF RD | 99 | COMPLETE | BOM cost variance | Labour est. under | N/A | Corriveau, Tom N | No | Battistella, Alexander | Morrow, Joe | 93956.54 | 130013.61 | 36057.07 | 38.38% | 34576.63 | 52727.69 | 18151.06 | 52.5% | 24924.15 | 41265.8 | 16341.65 | 65.57% | 6955.76 | 15247.5 | 8291.74 | 119.2% | 27500 | 20772.62 | -6727.38 | -24.46% | 213.28 | 507.5 | 294.22 | 138% | 2022-05-09 01:00
Markham | 2022 | 641802 | 641802 - 8484 & 8470 DUFFERIN ST / VAU / NS / 3PH PAD TX | 99 | COMPLETE | BOM not accurate | Labour est. over | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 78790.41 | 52899.94 | -25890.47 | -32.86% | 22357.35 | 13964.81 | -8392.54 | -37.54% | 39736.89 | 27186.7 | -12550.19 | -31.58% | 3073.17 | 1747 | -1326.17 | -43.15% | 13623 | 10001.43 | -3621.57 | -26.58% | 145.94 | 98 | -47.94 | -32.85% | 2022-02-11 01:00
Markham | 2022 | 641816 | 641816 - WOODBINE AVE. - #10950 & #10952 | 99 | ANALYZE |  |  |  | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 164686.81 | 158857.25 | -5829.56 | -3.54% | 31605.1 | 38615.52 | 7010.42 | 22.18% | 106501.89 | 61247.49 | -45254.4 | -42.49% | 3296.52 | 1110.5 | -2186.02 | -66.31% | 45633.3 | 57883.74 | 12250.44 | 26.85% | 192.4 | 226.5 | 34.1 | 17.72% | 2022-05-05
Markham | 2022 | 641869 | 641869 - 2022 DA - 27MSS-2 - MARKHAM | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Kristine Gordon | 107004.01 | 98900.77 | -8103.24 | -7.573% | 28505.71 | 26625.52 | -1880.19 | -6.596% | 54023.38 | 52717.04 | -1306.34 | -2.418% | 6762.92 | 6916 | 153.08 | 2.264% | 17712 | 12642.21 | -5069.79 | -28.62% | 229.01 | 246 | 16.99 | 7.419% | 2022-06-09 01:00
Markham | 2022 | 641870 | 641870 - 2022 DA - V25SL3088 - VAUGHAN | 99 | COMPLETE | Labour est. over | BOM cost variance | Cont Est Over | Tenorlas, Reynaldo | Yes | Roy, James | Reginald Clarke | 101263.75 | 84882.86 | -16380.89 | -16.18% | 27910.71 | 21025.57 | -6885.14 | -24.67% | 50760.95 | 47271.38 | -3489.57 | -6.875% | 6192.09 | 4762.5 | -1429.59 | -23.09% | 16400 | 11823.41 | -4576.59 | -27.91% | 211.47 | 187 | -24.47 | -11.57% | 2022-03-03 01:00
Markham | 2022 | 641871 | 641871 - 2022 DA - V26SL3004 - VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Reginald Clarke | 123918.39 | 172043.69 | 48125.3 | 38.84% | 36616.3 | 39345.33 | 2729.03 | 7.453% | 60734.47 | 57580.74 | -3153.73 | -5.193% | 8767.62 | 10294.5 | 1526.88 | 17.41% | 17800 | 64823.12 | 47023.12 | 264.2% | 290.43 | 341.5 | 51.07 | 17.58% | 2022-03-15 01:00
Markham | 2022 | 641872 | 641872 - 2022 DA - 09MSS002 - MARKHAM | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Reginald Clarke | 149210.62 | 138762.25 | -10448.37 | -7.002% | 40643.35 | 35255.9 | -5387.45 | -13.26% | 64391.09 | 62177 | -2214.09 | -3.439% | 9576.18 | 11865.5 | 2289.32 | 23.91% | 34600 | 29463.85 | -5136.15 | -14.84% | 314.96 | 306 | -8.96 | -2.845% | 2022-02-17 01:00
Markham | 2022 | 641873 | 76 NOVAN CRES/AUR/UP/1PH PAD | 99 | CANCELLED | N/A |  |  | Cranley, Stephen | No | Paterson, Greg | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-10-14 01:00
Markham | 2022 | 641890 | GARDEN HOMES (MARKHAM) DEVELOPMENT – SUBD RES EDS | 99 | CANCELLED | N/A |  |  | Penner, Mitchell | No | Graham, Bruce W. | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-08-11 01:00
Markham | 2022 | 641915 | 641915 - 2022 POLE REBUILD - OAKBANK RD - 9 POLES | 99 | COMPLETE | Labour est. under | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Morrow, Joe | 112563.75 | 147405.05 | 34841.3 | 30.95% | 39162.62 | 62913.07 | 23750.45 | 60.65% | 16726.93 | 17000.57 | 273.64 | 1.636% | 9432.2 | 19417 | 9984.8 | 105.9% | 47242 | 48074.41 | 832.41 | 1.762% | 689.18 | 751 | 61.82 | 8.97% | 2022-08-11 01:00
Markham | 2022 | 641916 | 641916 - 2022 POLE RENEWAL - YORK & DURHAM LINE - 5 POLES | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Ryan Walsh | 98257.52 | 92806 | -5451.52 | -5.548% | 38834.98 | 45491.17 | 6656.19 | 17.14% | 15131.34 | 16924.47 | 1793.13 | 11.85% | 5624.2 | 10796 | 5171.8 | 91.96% | 38667 | 19594.36 | -19072.64 | -49.33% | 449.55 | 578 | 128.45 | 28.57% | 2022-01-31 01:00
Markham | 2022 | 641917 | 641917 - 2022 TX RENEWAL - BATCH 1 - 15 TX | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 229290.34 | 206293.82 | -22996.52 | -10.03% | 44535.57 | 20410.89 | -24124.68 | -54.17% | 99260.77 | 89142.46 | -10118.31 | -10.19% | 6963 | 1110.82 | -5852.18 | -84.05% | 78531 | 95629.65 | 17098.65 | 21.77% | 324.15 | 35 | -289.15 | -89.2% | 2022-06-22 01:00
Markham | 2022 | 641918 | 641918 - 2022 TX RENEWAL - BATCH 2 - 7 TX | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Dave Lindsay | 75680.4 | 75671.71 | -8.69 | -0.01148% | 20987.17 | 8743.88 | -12243.29 | -58.34% | 51722.83 | 50813.18 | -909.65 | -1.759% | 2970.4 | 970 | -2000.4 | -67.34% | 0 | 15144.65 | 15144.65 |  | 120.86 | 46 | -74.86 | -61.94% | 2022-06-13 01:00
Markham | 2021 | 641926 | 641926 - 40 ALBERT ST - POLE RELOCATION - MARKHAM | 99 | COMPLETE | Labour est. over | N/A | N/A | Murray, Jake R | No | Corriveau, Tom N | Reginald Clarke | 19760.61 | 15615.16 | -4145.45 | -20.98% | 11387.34 | 8422.9 | -2964.44 | -26.03% | 2023.59 | 2226.62 | 203.03 | 10.03% | 2149.68 | 1639.5 | -510.18 | -23.73% | 4200 | 3326.14 | -873.86 | -20.81% | 65.25 | 48 | -17.25 | -26.44% | 2021-11-02 01:00
Markham | 2022 | 641934 | 641934 - 2022 TX RENEWAL - BATCH 3 - 13 TX | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Kahlon, Aneel | Dave Lindsay | 221918.76 | 227754.61 | 5835.85 | 2.63% | 42892.15 | 47938.33 | 5046.18 | 11.76% | 86806.41 | 81922.92 | -4883.49 | -5.626% | 6090.2 | 1144.09 | -4946.11 | -81.21% | 86130 | 96749.27 | 10619.27 | 12.33% | 284.53 | 309.5 | 24.97 | 8.776% | 2022-12-02 01:00
Markham | 2022 | 641936 | 641936 - 2022 TX RENEWAL - BATCH 4 - 17 TX | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Tenorlas, Reynaldo | Yes | Kahlon, Aneel | Dave Lindsay | 317479.81 | 237101.78 | -80378.03 | -25.32% | 65498.41 | 19682.72 | -45815.69 | -69.95% | 120998.47 | 114801.3 | -6197.17 | -5.122% | 9381.93 | 38 | -9343.93 | -99.59% | 121601 | 102579.76 | -19021.24 | -15.64% | 373.77 | 4 | -369.77 | -98.93% | 2022-08-18 01:00
Markham | 2022 | 641942 | 641942 - 2022 DISTRIBUTION AUTOMATION - AURORA - INDUSTRIAL PARKWAY | 98 | COMPLETE | Labour est. over | Cont Est Over | N/A | Bowman, Todd J | Yes | Walters, Geoffrey D | Kristine Gordon | 241744.98 | 216192.05 | -25552.93 | -10.57% | 83130.92 | 64170.36 | -18960.56 | -22.81% | 102850.93 | 106797.07 | 3946.14 | 3.837% | 23263.13 | 21945.13 | -1318 | -5.666% | 32500 | 23279.49 | -9220.51 | -28.37% | 633.18 | 573 | -60.18 | -9.504% | 2022-08-15 01:00
Markham | 2021 | 641946 | 641946 - 135 SPY CRT/MAR/UP/3PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 58224.1 | 49735.18 | -8488.92 | -14.58% | 25851.43 | 17231.3 | -8620.13 | -33.34% | 18227.1 | 18987.64 | 760.54 | 4.173% | 2296.57 | 2011 | -285.57 | -12.43% | 11849 | 11505.24 | -343.76 | -2.901% | 154.88 | 137.5 | -17.38 | -11.22% | 2021-12-08 01:00
Markham | 2021 | 641989 | DUMMY WORK ORDER | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-09-30 01:00
Markham | 2022 | 642140 | 642140 - 2022 POLE REBUILD - PARKWAY AVE - 4 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Morrow, Joe | 64779.49 | 63819.94 | -959.55 | -1.481% | 26973.4 | 27304.1 | 330.7 | 1.226% | 13433.79 | 10844.81 | -2588.98 | -19.27% | 5561.3 | 9695 | 4133.7 | 74.33% | 18811 | 15976.03 | -2834.97 | -15.07% | 299.67 | 310 | 10.33 | 3.447% | 2022-08-11 01:00
Markham | 2022 | 642186 | 7515 MARTIN GROVE RD / VAU / UP / 1PH PAD TX | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Mann, Drew | East Coordinator | 0 | 2654.06 | 2654.06 |  | 0 | 2654.06 | 2654.06 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-05-02
Markham | 2022 | 642198 | 642198 - RUTHERFORD RD. PH.3 - PETER RUPERT INTERSECTION | 95 | COMPLETE | 3rd party plant | N/A | N/A | Corriveau, Tom N | No | Barry, Kenneth | Morrow, Joe | 153995.66 | 398153.5 | 244157.84 | 158.5% | 29080.23 | 152234.35 | 123154.12 | 423.5% | 63232.41 | 108897.69 | 45665.28 | 72.22% | 10095.74 | 41018 | 30922.26 | 306.3% | 51587.28 | 96003.46 | 44416.18 | 86.1% | 264.62 | 1469.5 | 1204.88 | 455.3% | 2021-05-02
Markham | 2022 | 642216 | 642216 - 2022 TX RENEWAL - BATCH 6 - 14 TX | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 219091.27 | 184792.25 | -34299.02 | -15.66% | 44238.39 | 23723.53 | -20514.86 | -46.37% | 73541.28 | 73495.1 | -46.18 | -0.06279% | 6601.6 | 2786.63 | -3814.97 | -57.79% | 94710 | 84786.99 | -9923.01 | -10.48% | 309.34 | 79 | -230.34 | -74.46% | 2022-12-08 01:00
Markham | 2022 | 642217 | 642217 - 2022 TX RENEWAL - BATCH 8 - 4 TX | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 88589.77 | 92006.19 | 3416.42 | 3.856% | 26490.73 | 21466.7 | -5024.03 | -18.97% | 60339.04 | 66703.99 | 6364.95 | 10.55% | 1760 | 3835.5 | 2075.5 | 117.9% | 0 | 0 | 0 |  | 0 | 187.5 | 187.5 |  | 2022-05-17 01:00
Markham | 2022 | 642222 | 642222 - 8440 HWY 27 | 98 | ANALYZE |  |  |  | Corriveau, Tom N | No | Battistella, Alexander | Kristine Gordon | 17775.57 | 19084.09 | 1308.52 | 7.361% | 10787.82 | 8003.72 | -2784.1 | -25.81% | 2706.06 | 2673.51 | -32.55 | -1.203% | 2081.69 | 802 | -1279.69 | -61.47% | 2200 | 7604.86 | 5404.86 | 245.7% | 54.15 | 26 | -28.15 | -51.99% | 2022-12-06 01:00
Markham | 2021 | 642225 | DUFFERIN ST & LANGSTAFF RD - ANCHOR CONFLICT | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-07 01:00
Markham | 2022 | 642318 | 642318 - JOINT USE PERMIT HE2021-088 | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Martin, Shane | Reginald Clarke | 16325.69 | 11772.31 | -4553.38 | -27.89% | 5345.12 | 5134.49 | -210.63 | -3.941% | 3679.81 | 2876.33 | -803.48 | -21.83% | 1000.76 | 1874 | 873.24 | 87.26% | 6300 | 1887.49 | -4412.51 | -70.04% | 26.24 | 55 | 28.76 | 109.6% | 2022-05-03
Markham | 2022 | 642339 | 642339 - 2022 CABLE REPLACEMENT, M31 BIRCHMOUNT AND DENISON ST | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 1052323.82 | 1082160.76 | 29836.94 | 2.835% | 142054.1 | 200439.67 | 58385.57 | 41.1% | 62599.56 | 61573.83 | -1025.73 | -1.639% | 6474.4 | 8520.03 | 2045.63 | 31.6% | 841195.76 | 811627.23 | -29568.53 | -3.515% | 163.79 | 505.5 | 341.71 | 208.6% | 2022-10-06 01:00
Markham | 2022 | 642382 | 642382 - POLE RELOCATION 9113-9125 BATHRUST STREET | 95 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Alarcon, Alejandro | Reginald Clarke | 24617.21 | 22992.31 | -1624.9 | -6.601% | 11698.8 | 12857.41 | 1158.61 | 9.904% | 2794.24 | 2930.58 | 136.34 | 4.879% | 1524.17 | 2802 | 1277.83 | 83.84% | 8600 | 4402.32 | -4197.68 | -48.81% | 66.14 | 84 | 17.86 | 27% | 2022-03-24 01:00
Markham | 2022 | 642412 | 642412 - MAJOR MACKENZIE RELOACTIONS - KEELE TO JANE | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Murray, Jake R | Morrow, Joe | 586598.67 | 628553.15 | 41954.48 | 7.152% | 128278.45 | 153232.08 | 24953.63 | 19.45% | 44164.53 | 64442.9 | 20278.37 | 45.92% | 17813.09 | 23779 | 5965.91 | 33.49% | 396342.6 | 387099.17 | -9243.43 | -2.332% | 1034.51 | 1090 | 55.49 | 5.364% | 2022-08-11 01:00
Markham | 2021 | 642424 | 642424 - POLE REPLACEMENT SUNSET SIX | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | D'Onofrio, Tony | No | Alarcon, Alejandro | Macdonald, Larry | 18245.37 | 14899.16 | -3346.21 | -18.34% | 9180.63 | 7927.01 | -1253.62 | -13.66% | 1856.39 | 1704.33 | -152.06 | -8.191% | 1108.35 | 1575 | 466.65 | 42.1% | 6100 | 3692.82 | -2407.18 | -39.46% | 44.39 | 60.5 | 16.11 | 36.29% | 2021-09-29 01:00
Markham | 2022 | 642446 | 642446 - 2022 POLE REBUILD - KING VAUGHAN RD - 4 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Macdonald, Steve | 105142.99 | 104676.41 | -466.58 | -0.4438% | 6183.25 | 16976.08 | 10792.83 | 174.5% | 16873.82 | 15727.73 | -1146.09 | -6.792% | 0 | 0 | 0 |  | 82085.92 | 71972.6 | -10113.32 | -12.32% | 0 | 4 | 4 |  | 2022-10-08 01:00
Markham | 2022 | 642447 | 642447 - 2022 POLE RENEWAL - P44985 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Morrow, Joe | 61673.88 | 44203.47 | -17470.41 | -28.33% | 28826.54 | 11540.89 | -17285.65 | -59.96% | 7414.15 | 19814.32 | 12400.17 | 167.3% | 7781.19 | 3692.2 | -4088.99 | -52.55% | 17652 | 9156.06 | -8495.94 | -48.13% | 199.64 | 92 | -107.64 | -53.92% | 2022-11-23 01:00
Markham | 2022 | 642448 | 642448 - 2022 POLE RENEWAL - P49523 | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Kristine Gordon | 18364.16 | 21085.31 | 2721.15 | 14.82% | 7967.51 | 9518.29 | 1550.78 | 19.46% | 3340.19 | 5320.2 | 1980.01 | 59.28% | 1346.46 | 3538 | 2191.54 | 162.8% | 5710 | 2708.82 | -3001.18 | -52.56% | 61.11 | 91 | 29.89 | 48.91% | 2022-04-08
Markham | 2022 | 642485 | 642485 - 2022 POLE REPLACEMENT - ROYAL RD, INDUSTRIAL PKWY - 4 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Kahlon, Aneel | Macdonald, Steve | 125125.64 | 125015.3 | -110.34 | -0.08818% | 16752.13 | 20237.43 | 3485.3 | 20.81% | 19031.88 | 22487.34 | 3455.46 | 18.16% | 2256.06 | 213.85 | -2042.21 | -90.52% | 87085.57 | 82076.68 | -5008.89 | -5.752% | 0 | 3 | 3 |  | 2022-12-17 01:00
Markham | 2022 | 642487 | 642487 - 2022 POLE REPLACEMENT - BAYVIEW AVE - 11 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Kahlon, Aneel | Macdonald, Steve | 315529.12 | 327061.24 | 11532.12 | 3.655% | 18383.9 | 30752.84 | 12368.94 | 67.28% | 74704.98 | 98798.75 | 24093.77 | 32.25% | 2326.68 | 0 | -2326.68 | -100% | 220113.56 | 197509.65 | -22603.91 | -10.27% | 0 | 0 | 0 |  | 2022-11-05 01:00
Markham | 2021 | 642490 | 642490 - 27 DIRECTOR COURT/VAU/SR/3PH PAD | 99 | COMPLETE | Labour est. over | N/A | N/A | Dibratto, Susan | No | Diefenbaker, Trevor A | Dave Lindsay | 11113.55 | 2785.11 | -8328.44 | -74.94% | 9661.84 | 2641.11 | -7020.73 | -72.66% | 0 | 0 | 0 |  | 1451.71 | 144 | -1307.71 | -90.08% | 0 | 0 | 0 |  | 33.81 | 9 | -24.81 | -73.38% | 2021-12-02 01:00
Markham | 2022 | 642495 | HUNTINGTON RD, EAST CORNERS BLVD TO NASHVILLE RD (SEG 2) | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-02-02 01:00
Markham | 2022 | 642496 | HUNTINGTON RD, RUTHERFORD RD TO MCGILLIVRAY RD (SEG 3) | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-02-02 01:00
Markham | 2021 | 642526 | 642526 - 2021 EMERGING UG, A11SP2000 CABLE FAULT REPLACEMENT | 99 | COMPLETE | BOM not accurate | Labour est. over | Cont Est Over | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 103757.8 | 76397.57 | -27360.23 | -26.37% | 35022.35 | 26666.62 | -8355.73 | -23.86% | 22622.77 | 11181.15 | -11441.62 | -50.58% | 4769.68 | 5332.04 | 562.36 | 11.79% | 41343 | 33217.76 | -8125.24 | -19.65% | 225.94 | 151.5 | -74.44 | -32.95% | 2021-10-13 01:00
Markham | 2022 | 642576 | 642576 - SECONDARY SERVICE TRANSFER - 2200 STEELES AVE W | 99 | COMPLETE | Cont Est Under | Labour est. under | N/A | Tenorlas, Reynaldo | Yes | Kahlon, Aneel | Dave Lindsay | 36910.03 | 45161.04 | 8251.01 | 22.35% | 13652.81 | 18921.51 | 5268.7 | 38.59% | 755.39 | 264.95 | -490.44 | -64.93% | 1485.83 | 313.5 | -1172.33 | -78.9% | 21016 | 25661.08 | 4645.08 | 22.1% | 51.93 | 111 | 59.07 | 113.7% | 2022-07-18 01:00
Markham | 2022 | 642642 | 642642 - VTS4 PART 3 - YR1 - ADD 2 CCTS TESTON - WESTON TO 400 | 99 | COMPLETE | Cont Est Under | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Morrow, Joe | 502711.09 | 796673.22 | 293962.13 | 58.48% | 171206.57 | 257726.34 | 86519.77 | 50.54% | 196946.63 | 235003.15 | 38056.52 | 19.32% | 49557.89 | 81146.64 | 31588.75 | 63.74% | 85000 | 222797.09 | 137797.09 | 162.1% | 1299.36 | 2488.5 | 1189.14 | 91.52% | 2022-11-21 01:00
Markham | 2022 | 642651 | 642651 - DISTRIBUTION LOOP IMPROVEMENT ON VOGELL RD RICHMOND HILL | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Horlings, Jake | 122184.39 | 123380.49 | 1196.1 | 0.9789% | 21399.8 | 28711.71 | 7311.91 | 34.17% | 7249.15 | 0 | -7249.15 | -100% | 1333.44 | 2847 | 1513.56 | 113.5% | 92202 | 91821.78 | -380.22 | -0.4124% | 97.64 | 149.5 | 51.86 | 53.11% | 2022-07-13 01:00
Markham | 2021 | 642652 | 642652 - 30 INTERCHANGE WAY / VAU / SR / SECONDARY DEMO | 99 | COMPLETE | Labour est. under | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 4462.95 | 5302.68 | 839.73 | 18.82% | 3711.04 | 4537.68 | 826.64 | 22.28% | 96 | 0 | -96 | -100% | 655.91 | 765 | 109.09 | 16.63% | 0 | 0 | 0 |  | 27.47 | 41.5 | 14.03 | 51.07% | 2021-11-11 01:00
Markham | 2022 | 642659 | 642659 - 2 NEWBRIDGE AVE -SECONDARY RELOCATION | 99 | ANALYZE |  |  |  | Corriveau, Tom N | No | Murray, Jake R | Kristine Gordon | 31629.5 | 20940.54 | -10688.96 | -33.79% | 20369.51 | 9502.36 | -10867.15 | -53.35% | 3411.27 | 4838.68 | 1427.41 | 41.84% | 5426.72 | 4456 | -970.72 | -17.89% | 2422 | 2143.5 | -278.5 | -11.5% | 147.8 | 104 | -43.8 | -29.63% | 2022-09-09 01:00
Markham | 2022 | 642684 | 642684 - 2022 POLE RENEWAL - P49859 & P28092 | 99 | COMPLETE | Scope – Const | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Macdonald, Steve | 28649.45 | 14790.9 | -13858.55 | -48.37% | 1030.55 | 2444.07 | 1413.52 | 137.2% | 13646.38 | 1205.33 | -12441.05 | -91.17% | 0 | 0 | 0 |  | 13972.52 | 11141.5 | -2831.02 | -20.26% | 79.86 | 0 | -79.86 | -100% | 2022-11-02 01:00
Markham | 2022 | 642685 | 642685 - VTS4 PART 3 - YR1 - ADD 2 CCTS TESTON - 400 TO JANE | 99 | COMPLETE | Cont Est Under | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Morrow, Joe | 324137.72 | 427965.61 | 103827.89 | 32.03% | 83138.25 | 151528.54 | 68390.29 | 82.26% | 128283.96 | 140715.88 | 12431.92 | 9.691% | 20715.51 | 53116.26 | 32400.75 | 156.4% | 92000 | 82604.93 | -9395.07 | -10.21% | 543.09 | 1535.5 | 992.41 | 182.7% | 2022-12-07 01:00
Markham | 2022 | 642687 | 642687 - WOODEND PLACE RADIAL TX RELOCATION | 99 | COMPLETE | Labour est. over | N/A | N/A | Penner, Mitchell | No | Estrada, Michael | Dave Lindsay | 64869.52 | 53896.21 | -10973.31 | -16.92% | 21451.7 | 10886.19 | -10565.51 | -49.25% | 409.7 | 0 | -409.7 | -100% | 1871.12 | 1873 | 1.88 | 0.1005% | 41137 | 41137.02 | 0.02 | 4.862e-05% | 129.72 | 57 | -72.72 | -56.06% | 2022-03-17 01:00
Markham | 2022 | 642688 | 642688 - VIA BORGHESE TX RELOCATION | 95 | ANALYZE |  |  |  | Penner, Mitchell | No | Estrada, Michael | Dave Lindsay | 63356.09 | 62040.48 | -1315.61 | -2.077% | 19548.68 | 19215.68 | -333 | -1.703% | 381.81 | 0 | -381.81 | -100% | 1512.6 | 912 | -600.6 | -39.71% | 41913 | 41912.8 | -0.2 | -0.0004772% | 110.05 | 123 | 12.95 | 11.77% | 2022-07-19 01:00
Markham | 2022 | 642737 | 642737 - 2022 EMERGING UG, V36 WESTON, STEELES AND PEARCE - V36SP3108 TO 36-L3 | 99 | COMPLETE | Cont Est Over | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 755935.23 | 608794.67 | -147140.56 | -19.46% | 79866.02 | 86919.78 | 7053.76 | 8.832% | 3635.53 | 0 | -3635.53 | -100% | 1768.68 | 2053 | 284.32 | 16.08% | 670665 | 519821.89 | -150843.11 | -22.49% | 80.6 | 112 | 31.4 | 38.96% | 2022-05-07
Markham | 2022 | 642841 | 642841 - 2022 POLE RENEWAL - BATCH 2 - 18 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Morrow, Joe | 297061.7 | 328310.42 | 31248.72 | 10.52% | 87574.1 | 154009.53 | 66435.43 | 75.86% | 64681.03 | 59927.65 | -4753.38 | -7.349% | 22085.53 | 45325.31 | 23239.78 | 105.2% | 122721.04 | 69047.93 | -53673.11 | -43.74% | 1578.02 | 1624.5 | 46.48 | 2.945% | 2022-09-01 01:00
Markham | 2022 | 642842 | 642842 - 2022 POLE RENEWAL - BATCH 3 - 10 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Morrow, Joe | 115173.76 | 114545.09 | -628.67 | -0.5458% | 45086.3 | 57110.94 | 12024.64 | 26.67% | 26551.48 | 28243.89 | 1692.41 | 6.374% | 10535.98 | 17903.5 | 7367.52 | 69.93% | 33000 | 11286.76 | -21713.24 | -65.8% | 656.37 | 683 | 26.63 | 4.057% | 2022-05-02
Markham | 2022 | 642843 | 642843 - 2022 POLE RENEWAL - BATCH 6 - 7 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 144322.26 | 147082.39 | 2760.13 | 1.912% | 41577.45 | 18978.26 | -22599.19 | -54.35% | 38399.36 | 43563.04 | 5163.68 | 13.45% | 9345.45 | 0 | -9345.45 | -100% | 55000 | 84541.09 | 29541.09 | 53.71% | 244.64 | 0 | -244.64 | -100% | 2022-12-17 01:00
Markham | 2022 | 642929 | 642929 - 2022 EMERGING UG, R16 WELDRICK RD E AND CLARISSA DR, CABLE REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 376450.55 | 363270.06 | -13180.49 | -3.501% | 69900.57 | 79602.99 | 9702.42 | 13.88% | 43770.98 | 22092.5 | -21678.48 | -49.53% | 2074 | 3794.5 | 1720.5 | 82.96% | 260705 | 257780.07 | -2924.93 | -1.122% | 38 | 276 | 238 | 626.3% | 2022-06-22 01:00
Markham | 2022 | 642947 | 642947 - 390 KERRYBROOK DRIVE POLE RELOCATION- RICHMONDHILL | 98 | ANALYZE |  |  |  | Corriveau, Tom N | No | Silcock, Jordan | Kristine Gordon | 25761.97 | 20615.15 | -5146.82 | -19.98% | 12793.52 | 12858.02 | 64.5 | 0.5042% | 2113.14 | 2293.63 | 180.49 | 8.541% | 4320.79 | 1920.5 | -2400.29 | -55.55% | 6534.52 | 3543 | -2991.52 | -45.78% | 52.57 | 49 | -3.57 | -6.791% | 2022-09-23 01:00
Markham | 2022 | 642998 | 642998 - 2022 POLE REPLACEMENT - BATCH 9 - 14 POLES | 99 | COMPLETE | Scope – Const | N/A | N/A | Tenorlas, Reynaldo | Yes | Kahlon, Aneel | Macdonald, Steve | 256258.72 | 210318.43 | -45940.29 | -17.93% | 20833.94 | 23127.33 | 2293.39 | 11.01% | 76767.85 | 46814.83 | -29953.02 | -39.02% | 2477.55 | 0 | -2477.55 | -100% | 156179.38 | 140376.27 | -15803.11 | -10.12% | 0 | 0 | 0 |  | 2022-11-23 01:00
Markham | 2022 | 642999 | 642999 - 2022 POLE REPLACEMENT - BATCH 7 - 21 POLES | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | Yes | Kahlon, Aneel | Morrow, Joe | 359051.91 | 309715.9 | -49336.01 | -13.74% | 199106.37 | 131873.98 | -67232.39 | -33.77% | 95618.95 | 108823.34 | 13204.39 | 13.81% | 33526.59 | 37832 | 4305.41 | 12.84% | 30800 | 31186.58 | 386.58 | 1.255% | 1576.11 | 1506.5 | -69.61 | -4.417% | 2022-09-01 01:00
Markham | 2022 | 643002 | 643002 - 87 GOULDING AVE/AUR/NS/3 PHASE PAD | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Cranley, Stephen | No | Harris, Geoff L. | Dave Lindsay | 74059.94 | 64400.95 | -9658.99 | -13.04% | 24856.08 | 21066.91 | -3789.17 | -15.24% | 32943.94 | 28432.59 | -4511.35 | -13.69% | 2142.92 | 3540.5 | 1397.58 | 65.22% | 14117 | 11360.95 | -2756.05 | -19.52% | 143.25 | 187 | 43.75 | 30.54% | 2022-10-07 01:00
Markham | 2022 | 643003 | 140 MARYCROFT AVE / VAU / UP / 3PH PAD TX | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Mann, Drew | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-15 01:00
Markham | 2022 | 643008 | 643008 - 1623 WELLINGTON ST/AUR/NS/3 PHASE PAD | 99 | COMPLETE | Cont Est Over | N/A | N/A | Cranley, Stephen | No | Harris, Geoff L. | Dave Lindsay | 167286.74 | 158505.28 | -8781.46 | -5.249% | 38193.68 | 30906.91 | -7286.77 | -19.08% | 74228.97 | 86306.53 | 12077.56 | 16.27% | 3561.09 | 2045 | -1516.09 | -42.57% | 51303 | 39246.84 | -12056.16 | -23.5% | 203.73 | 170.5 | -33.23 | -16.31% | 2022-10-07 01:00
Markham | 2021 | 643115 | 643115 - KENNEDY RD & BUR OAK AVE | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Corriveau, Tom N | No | Battistella, Alexander | Reginald Clarke | 18544.27 | 8235.16 | -10309.11 | -55.59% | 7646.39 | 3266.18 | -4380.21 | -57.28% | 3924.48 | 2389.16 | -1535.32 | -39.12% | 973.4 | 0 | -973.4 | -100% | 6000 | 2579.82 | -3420.18 | -57% | 29.88 | 21 | -8.88 | -29.72% | 2021-12-23 01:00
Markham | 2022 | 643125 | 643125 - 2022 LB CABLE REPLACEMENTS - M27 WATERBRIDGE LN, MAIN ST UNIONVILLE, ROSEMEAD CL | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 1141112.91 | 1082643.57 | -58469.34 | -5.124% | 188223.48 | 182477.02 | -5746.46 | -3.053% | 13629.38 | 1774.3 | -11855.08 | -86.98% | 6387.05 | 3554.62 | -2832.43 | -44.35% | 932873 | 894837.63 | -38035.37 | -4.077% | 401.67 | 256.5 | -145.17 | -36.14% | 2022-10-29 01:00
Markham | 2022 | 643139 | 643139 - 8550 KEELE ST - POLE RELOCATION | 99 | COMPLETE | Material Over Estimated | N/A | N/A | Corriveau, Tom N | No | Silcock, Jordan | Morrow, Joe | 46293.11 | 39061.88 | -7231.23 | -15.62% | 22164.3 | 21000.24 | -1164.06 | -5.252% | 11040.71 | 7648.61 | -3392.1 | -30.72% | 4693.1 | 4190 | -503.1 | -10.72% | 8395 | 6223.03 | -2171.97 | -25.87% | 137.09 | 147.5 | 10.41 | 7.594% | 2022-06-06 01:00
Markham | 2022 | 643166 | 643166 - 2022 POLE RENEWAL - BATCH 5 - 6 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Macdonald, Steve | 97698.54 | 102806.89 | 5108.35 | 5.229% | 6183.25 | 15414.53 | 9231.28 | 149.3% | 16471.93 | 19534.83 | 3062.9 | 18.59% | 0 | 0 | 0 |  | 75043.36 | 67857.53 | -7185.83 | -9.576% | 330.81 | 2 | -328.81 | -99.4% | 2022-12-17 01:00
Markham | 2022 | 643167 | 643167 - 2022 POLE RENEWAL - BATCH 8 - 4 POLES | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Kristine Gordon | 86665.64 | 79111.07 | -7554.57 | -8.717% | 51496.44 | 30591.37 | -20905.07 | -40.6% | 10032.11 | 22329.11 | 12297 | 122.6% | 15137.09 | 10846.54 | -4290.55 | -28.34% | 10000 | 15344.05 | 5344.05 | 53.44% | 400.13 | 273 | -127.13 | -31.77% | 2022-10-25 01:00
Markham | 2022 | 643168 | 643168 - 2022 POLE RENEWAL - P46443 | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Macdonald, Steve | 39734.82 | 42545.82 | 2811 | 7.074% | 3091.23 | 5641.78 | 2550.55 | 82.51% | 5965.67 | 6586.79 | 621.12 | 10.41% | 0 | 0 | 0 |  | 30677.92 | 30317.25 | -360.67 | -1.176% | 0 | 0 | 0 |  | 2022-10-03 01:00
Markham | 2022 | 643169 | 643169 - 2022 POLE REBUILD - THISTLEWOOD RD - 5 POLES | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Canale, Alfred | Morrow, Joe | 125756.77 | 117711.76 | -8045.01 | -6.397% | 44389.27 | 36874.87 | -7514.4 | -16.93% | 29712.41 | 28078.14 | -1634.27 | -5.5% | 9483.09 | 10792.41 | 1309.32 | 13.81% | 42172 | 41966.34 | -205.66 | -0.4877% | 264.07 | 335 | 70.93 | 26.86% | 2022-12-08 01:00
Markham | 2022 | 643171 | 643171 - 2022 POLE RENEWAL - P44186 | 99 | ANALYZE |  |  |  | Tenorlas, Reynaldo | Yes | Canale, Alfred | Kristine Gordon | 36135.22 | 43513.29 | 7378.07 | 20.42% | 18094.88 | 18910.24 | 815.36 | 4.506% | 8171.82 | 12415.01 | 4243.19 | 51.92% | 3068.52 | 7376.51 | 4307.99 | 140.4% | 6800 | 4811.53 | -1988.47 | -29.24% | 57.5 | 177 | 119.5 | 207.8% | 2022-12-15 01:00
Markham | 2022 | 643178 | 643178 - CHAMPLAIN SHORES – SUBD RES EDS | 92 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Handy, James | Lotto, Jay | 248211.07 | 250612.92 | 2401.85 | 0.9677% | 36713.56 | 38942.92 | 2229.36 | 6.072% | 372.51 | 0 | -372.51 | -100% | 864 | 1409 | 545 | 63.08% | 210261 | 210261 | 0 | 0% | 48 | 74 | 26 | 54.17% | 2022-12-20 01:00
Markham | 2022 | 643202 | 643202 - 2022 CABLE REPLACEMENT, V40 GREENBROOKE | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Tenorlas, Reynaldo | Yes | Handy, James | Horlings, Jake | 705734.58 | 601623.4 | -104111.18 | -14.75% | 109318.52 | 87800.35 | -21518.17 | -19.68% | 2586.45 | 2541.28 | -45.17 | -1.746% | 2997.61 | 1809 | -1188.61 | -39.65% | 590832 | 509472.77 | -81359.23 | -13.77% | 159.49 | 91 | -68.49 | -42.94% | 2022-07-29 01:00
Markham | 2022 | 643216 | 643216 - 2022 STORM HARDENING - WESTON - HWY 7 TO LANGSTAFF - VAUGHAN | 99 | COMPLETE | Under 10% | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Macdonald, Steve | 580017 | 629307.1 | 49290.1 | 8.498% | 45109.46 | 61660.44 | 16550.98 | 36.69% | 169150.18 | 222005.1 | 52854.92 | 31.25% | 0 | 756.71 | 756.71 |  | 365757.36 | 344884.85 | -20872.51 | -5.707% | 1250.83 | 26.5 | -1224.33 | -97.88% | 2022-11-05 01:00
Markham | 2022 | 643217 | 643217 - 2022 STORM HARDENING - HWY 27 - MAJOR MACKENZIE TO RUTHERFORD - VAUGHAN | 99 | COMPLETE | Labour est. under | N/A | N/A | Tenorlas, Reynaldo | Yes | Roy, James | Morrow, Joe | 715735.52 | 891996.55 | 176261.03 | 24.63% | 167794.08 | 269615.35 | 101821.27 | 60.68% | 286253.22 | 308425.95 | 22172.73 | 7.746% | 48388.22 | 84126 | 35737.78 | 73.86% | 213300 | 229829.25 | 16529.25 | 7.749% | 2873.69 | 3170 | 296.31 | 10.31% | 2022-04-29
Markham | 2022 | 643239 | 643239 - 2022 TX RENEWAL - 1-468 - 1 TX | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | Yes | Kahlon, Aneel | Dave Lindsay | 41245.38 | 33218.78 | -8026.6 | -19.46% | 11222.94 | 5149.65 | -6073.29 | -54.11% | 22831.32 | 23572.14 | 740.82 | 3.245% | 1052.12 | 462.37 | -589.75 | -56.05% | 6139 | 4034.62 | -2104.38 | -34.28% | 38.45 | 23 | -15.45 | -40.18% | 2022-11-10 01:00
Markham | 2022 | 643291 | 643291 - 9554 WESTON ROAD HYDRO POLE RELOCATION - VAUGHAN | 99 | ANALYZE |  |  |  | Corriveau, Tom N | No | Silcock, Jordan | Kristine Gordon | 12304.84 | 5758.72 | -6546.12 | -53.2% | 6475.66 | 5316.72 | -1158.94 | -17.9% | 1990.36 | 0 | -1990.36 | -100% | 638.82 | 442 | -196.82 | -30.81% | 3200 | 0 | -3200 | -100% | 16.76 | 14 | -2.76 | -16.47% | 2022-04-06
Markham | 2022 | 643347 | 643347 - HUNTINGTON RD & HWY 7 | 98 | ANALYZE |  |  |  | Corriveau, Tom N | No | Battistella, Alexander | Kristine Gordon | 29037.59 | 23596.26 | -5441.33 | -18.74% | 14381.46 | 12327.49 | -2053.97 | -14.28% | 6492.47 | 6709.95 | 217.48 | 3.35% | 2663.66 | 1850 | -813.66 | -30.55% | 5500 | 2708.82 | -2791.18 | -50.75% | 69.78 | 60 | -9.78 | -14.02% | 2022-10-11 01:00
Markham | 2022 | 643360 | 643360 - 4433, 4455, 4477 MAJOR MACKENZIE DR. W - POLE RELOCATION | 99 | COMPLETE | Under 10% | N/A | N/A | Penner, Mitchell | No | Estrada, Michael | Dave Lindsay | 64994.66 | 59302.56 | -5692.1 | -8.758% | 22749.15 | 17059.46 | -5689.69 | -25.01% | 3405.79 | 4422.92 | 1017.13 | 29.86% | 3339.72 | 5605 | 2265.28 | 67.83% | 35500 | 32215.18 | -3284.82 | -9.253% | 142.56 | 130 | -12.56 | -8.81% | 2022-05-05
Markham | 2022 | 643596 | 35 SILTON RD/ VAU/ UP/ 3PH PAD | 99 | CANCELLED | N/A |  |  | Dibratto, Susan | No | Diefenbaker, Trevor A | East Coordinator | 0 | 4097.3 | 4097.3 |  | 0 | 4097.3 | 4097.3 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 5 | 5 |  | 2022-11-08 01:00
Markham | 2022 | 643672 | 643672 - 41 PERFORMANCE DR. | 99 | ANALYZE |  |  |  | Dibratto, Susan | No | Yuen, Paul | Dave Lindsay | 87952.64 | 63697.39 | -24255.25 | -27.58% | 24595.59 | 20895.02 | -3700.57 | -15.05% | 39721.57 | 28468.62 | -11252.95 | -28.33% | 2444.38 | 948 | -1496.38 | -61.22% | 21191.1 | 13385.75 | -7805.35 | -36.83% | 144.4 | 192.5 | 48.1 | 33.31% | 2022-10-07 01:00
Markham | 2022 | 644022 | HUNTINGTON ROAD, NORTH OF NASHVILLE ROAD - BLOCK 62 W | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Watters, Maxwell | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-08 01:00
Markham | 2022 | 644031 | 644031 - 8361 YONGE ST/MAR/UP/1PH PAD | 95 | COMPLETE | Under 10% | N/A | N/A | Joshi, Namrata | No | Diefenbaker, Trevor A | Dave Lindsay | 56736.69 | 60030.06 | 3293.37 | 5.805% | 32210.27 | 22177.13 | -10033.14 | -31.15% | 12316.28 | 23194.86 | 10878.58 | 88.33% | 4410.14 | 2300.5 | -2109.64 | -47.84% | 7800 | 12357.57 | 4557.57 | 58.43% | 164.11 | 142 | -22.11 | -13.47% | 2022-12-08 01:00
Markham | 2022 | 644113 | 644113 - 73 WOOTTEN WAY / MAR / SR / 1PH PAD TX DEMO | 99 | COMPLETE | Under 10% | N/A | N/A | Joshi, Namrata | No | Mann, Drew | Dave Lindsay | 24328.4 | 25213.28 | 884.88 | 3.637% | 9147.58 | 13124.88 | 3977.3 | 43.48% | 409.7 | 423.29 | 13.59 | 3.317% | 527.12 | 1827.5 | 1300.38 | 246.7% | 14244 | 9837.61 | -4406.39 | -30.94% | 63.72 | 119.5 | 55.78 | 87.54% | 2022-02-11 01:00
Markham | 2022 | 644149 | 644149 - CUSTOMER INITIATED UG RELOCATION-70 CONNIE CRES, VAUGHAN | 95 | ANALYZE |  |  |  | Corriveau, Tom N | No | Zhang, Jiacheng | Dave Lindsay | 39436.07 | 18810.73 | -20625.34 | -52.3% | 34820.07 | 15107.73 | -19712.34 | -56.61% | 0 | 0 | 0 |  | 3116 | 2203 | -913 | -29.3% | 1500 | 1500 | 0 | 0% | 207 | 78 | -129 | -62.32% | 2022-12-08 01:00
Markham | 2022 | 644223 | 644223 - POLE REPLACEMENT AUTUMNHILL DEVELOPMENT | 99 | ANALYZE |  |  |  | Penner, Mitchell | No | Alarcon, Alejandro | Kristine Gordon | 53017.72 | 45809.67 | -7208.05 | -13.6% | 29519.2 | 19121.58 | -10397.62 | -35.22% | 10004.95 | 9020.51 | -984.44 | -9.84% | 3493.57 | 4777.5 | 1283.93 | 36.75% | 10000 | 12890.08 | 2890.08 | 28.9% | 157.39 | 124.5 | -32.89 | -20.9% | 2022-11-21 01:00
Markham | 2022 | 644830 | 8905 BATHURST ST/ RHL/UP/3PH PAD | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Diefenbaker, Trevor A | East Coordinator | 0 | 2931.06 | 2931.06 |  | 0 | 2931.06 | 2931.06 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-20 01:00
Markham | 2022 | 644876 | 644876 - CAPLINK SYSTEM EXPANSION - 6685 LANGSTAFF | 95 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Silcock, Jordan | Morrow, Joe | 214780.49 | 216724.57 | 1944.08 | 0.9051% | 65959.38 | 75034.23 | 9074.85 | 13.76% | 100287.75 | 108288.27 | 8000.52 | 7.978% | 16533.36 | 15345.5 | -1187.86 | -7.185% | 32000 | 18056.57 | -13943.43 | -43.57% | 422.14 | 701.5 | 279.36 | 66.18% | 2022-12-07 01:00
Markham | 2022 | 644275 | ATKINSON AVE. - #300 | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Yuen, Paul | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-01 01:00
Markham | 2022 | 644480 | 644480 - ELGIN MILLS RD. EAST - #1591 | 98 | ANALYZE |  |  |  | Joshi, Namrata | No | Yuen, Paul | Dave Lindsay | 73744.94 | 46864.24 | -26880.7 | -36.45% | 28819.46 | 13771.55 | -15047.91 | -52.21% | 29053.05 | 29751.19 | 698.14 | 2.403% | 3554.03 | 3341.5 | -212.53 | -5.98% | 12318.4 | 0 | -12318.4 | -100% | 150.47 | 107.5 | -42.97 | -28.56% | 2022-12-05 01:00
Markham | 2022 | 644649 | 644649 - 440 HANLAN RD/ VAU/ UP/ 3PH PAD | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Joshi, Namrata | No | Diefenbaker, Trevor A | Dave Lindsay | 159582.05 | 129673.44 | -29908.61 | -18.74% | 30190.14 | 16917.05 | -13273.09 | -43.96% | 104194.38 | 95305.94 | -8888.44 | -8.531% | 3197.53 | 1590 | -1607.53 | -50.27% | 22000 | 15860.45 | -6139.55 | -27.91% | 150.32 | 114 | -36.32 | -24.16% | 2022-10-07 01:00
Markham | 2022 | 644757 | 644757 - CREDITSTONE RD. - #777 | 99 | ANALYZE |  |  |  | Joshi, Namrata | No | Yuen, Paul | Dave Lindsay | 93485.35 | 52233.35 | -41252 | -44.13% | 39771.58 | 24387.87 | -15383.71 | -38.68% | 16821.36 | 7142.87 | -9678.49 | -57.54% | 4370.76 | 2622.5 | -1748.26 | -40% | 32521.65 | 18080.11 | -14441.54 | -44.41% | 66.9 | 197.5 | 130.6 | 195.2% | 2022-10-07 01:00
Markham | 2022 | 646583 | 646583 - 2022 - EMERGING OH - AIDA PL REMOVALS | 99 | COMPLETE | Labour est. over | N/A | N/A | Tenorlas, Reynaldo | No | Kahlon, Aneel | Reginald Clarke | 11683.21 | 0 | -11683.21 | -100% | 10049.03 | 0 | -10049.03 | -100% | 0 | 0 | 0 |  | 1634.18 | 0 | -1634.18 | -100% | 0 | 0 | 0 |  | 60.55 | 0 | -60.55 | -100% | 2022-07-28 01:00
Markham | 2022 | 645209 | 645209 - BERZCY WARDEN SINGLE POLE RELOACTIONS | 99 | COMPLETE | Under 10% | N/A | N/A | Corriveau, Tom N | No | Murray, Jake R | Morrow, Joe | 106907.25 | 98019.07 | -8888.18 | -8.314% | 39896.91 | 48018.53 | 8121.62 | 20.36% | 16611.06 | 14041.49 | -2569.57 | -15.47% | 7479.28 | 15558.5 | 8079.22 | 108% | 42920 | 20400.55 | -22519.45 | -52.47% | 558.43 | 485.5 | -72.93 | -13.06% | 2022-10-04 01:00
Markham | 2022 | 645295 | 19TH AVE. - #3751 | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Yuen, Paul | East Coordinator | 0 | 1255.39 | 1255.39 |  | 0 | 1255.39 | 1255.39 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-22 01:00
Markham | 2022 | 645374 | 645374 - 152 WELLS STREET, AURORA - POLE RELOCATION | 95 | COMPLETE | Labour est. under | N/A | N/A | Corriveau, Tom N | No | Silcock, Jordan | Morrow, Joe | 13393.56 | 18463.48 | 5069.92 | 37.85% | 7174.25 | 12160.29 | 4986.04 | 69.5% | 1593.64 | 1871.19 | 277.55 | 17.42% | 925.67 | 2230 | 1304.33 | 140.9% | 3700 | 2202 | -1498 | -40.49% | 21.91 | 80 | 58.09 | 265.1% | 2022-11-07 01:00
Markham | 2022 | 645426 | RUTHERFORD GRADE SEPARTION POLE RESETTING | 95 | COMPLETE | N/A | N/A | N/A | Corriveau, Tom N | No | Murray, Jake R | Tom Corriveau | 185972.03 | 33156.75 | -152815.28 | -82.17% | 131621.03 | 18905.03 | -112716 | -85.64% | 0 | 266.44 | 266.44 |  | 42350 | 3150 | -39200 | -92.56% | 12001 | 10835.28 | -1165.72 | -9.714% | 1100 | 192.5 | -907.5 | -82.5% | 2022-04-25
Markham | 2022 | 645436 | CONCENTRIC NEUTRALS TO SINGLE POINT - RAIL CROSSINGS - METROLINX | 99 | CANCELLED | N/A |  |  | Vande Kuyt, Greg | No | Washburn, Martin | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-11 01:00
Markham | 2022 | 645466 | GUY WIRES REMOVAL AT 16TH AVENUE AND MARKHAM RD | 95 | COMPLETE | N/A | N/A | N/A | Corriveau, Tom N | No | Murray, Jake R | Tom Corriveau | 653.44 | 977.84 | 324.4 | 49.64% | 493.31 | 596.84 | 103.53 | 20.99% | 0 | 0 | 0 |  | 160.13 | 381 | 220.87 | 137.9% | 0 | 0 | 0 |  | 4.19 | 9 | 4.81 | 114.8% | 2022-05-11 01:00
Markham | 2022 | 645591 | 645591 - 5336 HWY 7 E / MAR / SR / 3PH OH BANK DEMO | 98 | ANALYZE |  |  |  | Joshi, Namrata | No | Mann, Drew | Kristine Gordon | 5057.99 | 5554.4 | 496.41 | 9.814% | 4197.79 | 4437.9 | 240.11 | 5.72% | 0 | 0 | 0 |  | 860.2 | 1116.5 | 256.3 | 29.8% | 0 | 0 | 0 |  | 22.57 | 33 | 10.43 | 46.21% | 2022-06-26 01:00
Markham | 2022 | 645776 | 645776 - 9600 KEELE STREET | 98 | ANALYZE |  |  |  | Joshi, Namrata | No | Yuen, Paul | Kristine Gordon | 6319.53 | 4907.29 | -1412.24 | -22.35% | 5259.68 | 3912.29 | -1347.39 | -25.62% | 0 | 0 | 0 |  | 1059.85 | 995 | -64.85 | -6.119% | 0 | 0 | 0 |  | 27.19 | 25 | -2.19 | -8.054% | 2022-07-28 01:00
Markham | 2022 | 647226 | 647226 - MAJOR MAC & SUSSEX - POLE RELOCATION | 98 | ANALYZE |  |  |  | Corriveau, Tom N | No | Silcock, Jordan | Morrow, Joe | 13254.82 | 15778.02 | 2523.2 | 19.04% | 10339.9 | 12117.89 | 1777.99 | 17.2% | 1232.51 | 0 | -1232.51 | -100% | 1682.41 | 1008 | -674.41 | -40.09% | 0 | 2652.13 | 2652.13 |  | 44.15 | 52.5 | 8.35 | 18.91% | 2022-11-14 01:00
Markham | 2022 | 647758 | MACKENZIE COMMONS - POLE RELOCATION | 99 | CANCELLED | N/A | N/A | N/A | Corriveau, Tom N | No | Silcock, Jordan | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-02 01:00
Markham | 2022 | 648050 | YONGE STREET & BROOKSIDE ROAD | 99 | CANCELLED | N/A |  |  | Corriveau, Tom N | No | Battistella, Alexander | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-29 01:00
Markham | 2022 | 648267 | 2023 CABLE REPLACEMENT - A05 - MURRAY DR - A05SP2004 | 99 | CANCELLED | N/A |  |  | Tenorlas, Reynaldo | No | Kahlon, Aneel | East Coordinator | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-29 01:00
Markham | 2022 | 648299 | 90 RIVIERA DR / MAR / UP / 3PH PAD TX | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Mann, Drew | East Coordinator | 0 | 2057.9 | 2057.9 |  | 0 | 2057.9 | 2057.9 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-29 01:00
Markham | 2022 | 648738 | 10356 HUNTINGTON RD/VAU/NS/3PH PAD | 99 | CANCELLED | N/A |  |  | Joshi, Namrata | No | Diefenbaker, Trevor A | East Coordinator | 0 | 340.18 | 340.18 |  | 0 | 340.18 | 340.18 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-05 00:59
Mississauga | 2022 | 218587 | CHURCHILL MEADOWS TS - TS TO WINSTON CHURCHILL (FEEDER EGRESS) | 99 | CANCELLED | N/A |  |  | Hotham, Matthew | yes | Zaghloul, Sam | Rob Elliot | 2113614.54 | 357047.54 | -1756567 | -83.11% | 462380.82 | 73085.97 | -389294.85 | -84.19% | 956671.78 | 85430.42 | -871241.36 | -91.07% | 340506.96 | 4424 | -336082.96 | -98.7% | 354054.98 | 44207.49 | -309847.49 | -87.51% | 5722.62 | 831.5 | -4891.12 | -85.47% | 2020-04-27
Mississauga | 2020 | 236291 | Galleria Plaza - 3055 Neilco Crt | 99 | CANCELLED | N/A |  |  | Mandic, Goran | no | Alectra Utilities | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-27
Mississauga | 2020 | 251897 | QEW - Hurontario to Mississauga | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | no | Alectra Utilities | Mark Bobanovic | 6124038.78 | 6019747.78 | -104291 | -1.703% | 272662.38 | 602008.82 | 329346.44 | 120.8% | 441135.13 | 584806.66 | 143671.53 | 32.57% | 29679.38 | 2653.5 | -27025.88 | -91.06% | 5380561.89 | 4822821.27 | -557740.62 | -10.37% | 2918.84 | 1928.25 | -990.59 | -33.94% | 2020-04-27
Mississauga | 2019 | 267215 | Malton MS Feeder Egress | 99 | COMPLETE | Labour est. under | Cont Est Over | BOM not accurate | Carter, Gordon | no | Watters, Maxwell | Rob Elliot | 254949.82 | 237775.22 | -17174.6 | -6.736% | 120967.69 | 104250.18 | -16717.51 | -13.82% | 69821.02 | 77344.33 | 7523.31 | 10.78% | 24161.11 | 24929.5 | 768.39 | 3.18% | 40000 | 31251.21 | -8748.79 | -21.87% | 1562.91 | 1361.5 | -201.41 | -12.89% | 2019-05-06
Mississauga | 2019 | 268226 | Creditview - Britannia to Agentia - Brdige Widening - carry over from 2017 | 99 | COMPLETE | Scope change - unforeseen | Vac truck | BOM not accurate | Carter, Gordon | No | Alectra Utilities | Rob Elliot | 692608.14 | 824870.61 | 132262.47 | 19.1% | 222441.28 | 219710.39 | -2730.89 | -1.228% | 363236.94 | 404818.55 | 41581.61 | 11.45% | 39739.57 | 62512 | 22772.43 | 57.3% | 67190.35 | 137829.67 | 70639.32 | 105.1% | 2140 | 3054 | 914 | 42.71% | 2019-02-02 01:00
Mississauga | 2020 | 274888 | 99 Lakeshore Rd. - Waterside Condominium | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Alectra Utilities | Macdougall, Stephen | 0 | 267.32 | 267.32 |  | 0 | 267.32 | 267.32 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Mississauga | 2022 | 282221 | 5388 Mavis Rd - Embee Commercial Development Bldg G | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Huo, Lisa | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Mississauga | 2022 | 282693 | 5328 Mavis Rd - Embee Commercial Development Bldg F | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Huo, Lisa | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Mississauga | 2022 | 283717 | 5378 Mavis Rd - Embee Commercial Development Bldg B | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Huo, Lisa | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 110 | 0 | -110 | -100% | 2019-07-26 01:00
Mississauga | 2022 | 283725 | 5358 Mavis Rd - Embee Commercial Development Bldg D & E - | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Huo, Lisa | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Mississauga | 2019 | 303976 | ORLANDO Spec Bldg A - 6005 Erin Mills Pkwy | 99 | CANCELLED | N/A |  |  |  | no | Cudzilo, Tomasz | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Mississauga | 2022 | 305509 | 2015 OTC (INITIAL) - VIEWMARK HOMES 20416 (EHM) | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Ricci, Leonardo | Weaver, Thomas | 1051354.62 | 5057.51 | -1046297.11 | -99.52% | 40182 | 5057.51 | -35124.49 | -87.41% | 5460.05 | 0 | -5460.05 | -100% | 6699.57 | 0 | -6699.57 | -100% | 999013 | 0 | -999013 | -100% | 388.25 | 6 | -382.25 | -98.45% | 2019-07-26 01:00
Mississauga | 2022 | 317585 | 1344 Fewster Dr. - Inflamax Research Srvice Upgrade | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Huo, Lisa | Macdougall, Stephen | 0 | 2428.76 | 2428.76 |  | 0 | 441.76 | 441.76 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1987 | 1987 |  | 0 | 0 | 0 |  | 2019-02-15 01:00
Mississauga | 2022 | 324638 | 5475 Dixie Rd -OH to UG Conversion | 99 | CANCELLED | N/A |  |  | Sidhu, Paul | no | Ricci, Leonardo | Bourgeois, Craig | 17642.23 | 7132.82 | -10509.41 | -59.57% | 10262.72 | 4760.04 | -5502.68 | -53.62% | 4330 | 106.78 | -4223.22 | -97.53% | 689.51 | 0 | -689.51 | -100% | 2360 | 2266 | -94 | -3.983% | 95.72 | 62.25 | -33.47 | -34.97% | 2019-05-09
Mississauga | 2019 | 325446 | Toyotoshi Dixie Auto Mall - NE cor of Dixie & Hwy 401 | 99 | COMPLETE | BOM not used | Labour est. over | Cont Est Under | Sta. Rita, Leovigildo | no | Macasaet, Ricardo | Macdougall, Stephen | 145872.6 | 66216.65 | -79655.95 | -54.61% | 51551.22 | 35621.34 | -15929.88 | -30.9% | 21331.07 | 16168.64 | -5162.43 | -24.2% | 6379.9 | 4825 | -1554.9 | -24.37% | 2890.41 | 9601.67 | 6711.26 | 232.2% | 468.26 | 508.5 | 40.24 | 8.594% | 2019-05-09
Mississauga | 2019 | 325593 | HOLBURNE/OGDEN OH REBUILD - SE | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A |  | No | Matai, Ihssan (Sam) | Rob Elliot | 772101.68 | 564475.79 | -207625.89 | -26.89% | 261714.74 | 256714.52 | -5000.22 | -1.911% | 262958.52 | 164196.36 | -98762.16 | -37.56% | 94163.13 | 97581 | 3417.87 | 3.63% | 153265.29 | 45983.91 | -107281.38 | -70% | 2883.79 | 3471 | 587.21 | 20.36% | 2019-03-01 01:00
Mississauga | 2020 | 328145 | 1715 Audubon Blvd - 2015 OTC (INITIAL) - AUDUBON HOME | 99 | COMPLETE | Converted Project | N/A | N/A | Penner, Mitchell | No | Alectra Utilities | Paul Tremblay | 160957.19 | 152339.65 | -8617.54 | -5.354% | 29583.1 | 33302.9 | 3719.8 | 12.57% | 406.47 | 449.08 | 42.61 | 10.48% | 3564.34 | 3991.39 | 427.05 | 11.98% | 127403.28 | 113771.28 | -13632 | -10.7% | 215.08 | 243.5 | 28.42 | 13.21% | 2020-09-03 01:00
Mississauga | 2022 | 328161 | 2015 OTC (INITIAL) - 320 DERRY ROAD DEVELOPMENT - EHM COST | 99 | CANCELLED | N/A |  |  | Penner, Mitchell | No | Ricci, Leonardo | XMoinuddin, Saad | 342555.7 | 14243.49 | -328312.21 | -95.84% | 32170.78 | 14243.49 | -17927.29 | -55.73% | 2827.92 | 0 | -2827.92 | -100% | 2194.2 | 0 | -2194.2 | -100% | 305362.8 | 0 | -305362.8 | -100% | 213.5 | 0 | -213.5 | -100% | 2022-05-28 01:00
Mississauga | 2022 | 332849 | 5368 Mavis Rd. - Embee Commercial Development Bldg C | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Huo, Lisa | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-28 01:00
Mississauga | 2022 | 335062 | 36 ELM DRIVE - SOLMAR DEVT - EDGE TOWERS | 95 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Over | Mandic, Goran | no | Garcha, Tirath | Peter Costantini | 104327.96 | 65276.31 | -39051.65 | -37.43% | 50264.69 | 23215.52 | -27049.17 | -53.81% | 39220.71 | 32556.59 | -6664.12 | -16.99% | 4642.56 | 2838 | -1804.56 | -38.87% | 10200 | 6666.2 | -3533.8 | -34.65% | 335.34 | 139 | -196.34 | -58.55% | 2022-05-28 01:00
Mississauga | 2019 | 335071 | The Grand Mirage Phase 3 Bldg C - 349 Rathburn Rd W | 99 | COMPLETE | Labour est. over | Vehicle Under Estimated | N/A |  | no | Macasaet, Ricardo | Macdougall, Stephen | 78689.94 | 68740.64 | -9949.3 | -12.64% | 30996.05 | 24524.89 | -6471.16 | -20.88% | 38596.64 | 39268.75 | 672.11 | 1.741% | 3797.25 | 1476 | -2321.25 | -61.13% | 5300 | 3471 | -1829 | -34.51% | 365.93 | 268.75 | -97.18 | -26.56% | 2019-03-16 01:00
Mississauga | 2019 | 340216 | Glen Erin & Battleford (Phase 1) | 99 | COMPLETE | Engineering by-passed | N/A | N/A | Antonakos, Tony | No | Matai, Ihssan (Sam) | Paul Tremblay | 0 | 20582.5 | 20582.5 |  | 0 | 20582.5 | 20582.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 290.5 | 290.5 |  | 2019-04-02 01:00
Mississauga | 2019 | 341227 | 2018 UG rebuild - Credit Woodlands Crt./ Wiltshire | 99 | COMPLETE | Converted Project | N/A | N/A | Lewis, Kevin | no | Matai, Ihssan (Sam) | Mark Bobanovic | 1385397.29 | 1484845.73 | 99448.44 | 7.178% | 166665.09 | 243247.62 | 76582.53 | 45.95% | 34494.39 | 44226.48 | 9732.09 | 28.21% | 11119.91 | 19574.2 | 8454.29 | 76.03% | 1173117.9 | 1177797.43 | 4679.53 | 0.3989% | 1975.43 | 1709 | -266.43 | -13.49% | 2019-08-03 01:00
Mississauga | 2019 | 344321 | 125 Eglinton Ave W - FS 120 | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | no | Huo, Lisa | Macdougall, Stephen | 48826.26 | 165579.24 | 116752.98 | 239.1% | 0 | 38626.32 | 38626.32 |  | 10092.31 | 21967.86 | 11875.55 | 117.7% | 23873.5 | 5188 | -18685.5 | -78.27% | 10122.04 | 99797.06 | 89675.02 | 885.9% | 474.63 | 404 | -70.63 | -14.88% | 2019-09-04 01:00
Mississauga | 2021 | 344997 | Queen & Britannia Pole Relocation | 99 | CANCELLED | N/A |  |  | Hotham, Matthew | no | Zaghloul, Sam | Paul Murphy | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-25 01:00
Mississauga | 2020 | 345893 | Ninth Line & Argentia Feeder Installation | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | No | Alectra Utilities | Paul Tremblay | 286989.4 | 328638.98 | 41649.58 | 14.51% | 45643.04 | 80900.46 | 35257.42 | 77.25% | 52605.69 | 55754.07 | 3148.38 | 5.985% | 9898.4 | 15556.54 | 5658.14 | 57.16% | 178842.27 | 176427.91 | -2414.36 | -1.35% | 394 | 746 | 352 | 89.34% | 2020-01-25 01:00
Mississauga | 2020 | 346941 | SUMMIT EGLINTON II BLOCK 45 | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Paul Tremblay | 246639.98 | 236189.22 | -10450.76 | -4.237% | 40416.27 | 39295.89 | -1120.38 | -2.772% | 989.52 | 5869.08 | 4879.56 | 493.1% | 1471.67 | 2319.25 | 847.58 | 57.59% | 203762.52 | 188669 | -15093.52 | -7.407% | 287.91 | 164 | -123.91 | -43.04% | 2020-01-24 01:00
Mississauga | 2022 | 352479 | 6740 Meadowvale Town Centre - Meadowvale Town Centre New CIBC | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Jacinto, Gerardo | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-17 01:00
Mississauga | 2020 | 353105 | Reid Temporary Relocation Works - Carry over from 2017 | 99 | COMPLETE | Converted Project |  |  | Hotham, Matthew | no | Alectra Utilities | Rob Elliot | 171908.7 | 76440.49 | -95468.21 | -55.53% | 104606.95 | 44894.16 | -59712.79 | -57.08% | 23386.15 | 17124.79 | -6261.36 | -26.77% | 17513.1 | 12305.18 | -5207.92 | -29.74% | 26402.5 | 2116.36 | -24286.14 | -91.98% | 825 | 463 | -362 | -43.88% | 2020-09-17 01:00
Mississauga | 2022 | 353762 | LT31041 & LT31040 - 2022 SR-QUEENSWAY W & GLENGARRY RD - P08870 & P08872 | 99 | COMPLETE | Material Under Estimated | Vehicle Under Estimated | N/A | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Rob Elliot | 280505.23 | 328122.24 | 47617.01 | 16.98% | 86996.19 | 91526.82 | 4530.63 | 5.208% | 157411.1 | 179612.04 | 22200.94 | 14.1% | 19997.94 | 41646.64 | 21648.7 | 108.3% | 16100 | 15336.74 | -763.26 | -4.741% | 591.68 | 881.5 | 289.82 | 48.98% | 2022-08-22 01:00
Mississauga | 2022 | 354811 | 2379-2385 Camila Road - TEMP | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | No | Bharosi, Mohindra | Macdougall, Stephen | 1094.15 | 0 | -1094.15 | -100% | 1019.18 | 0 | -1019.18 | -100% | 26.22 | 0 | -26.22 | -100% | 48.75 | 0 | -48.75 | -100% | 0 | 0 | 0 |  | 18.31 | 0 | -18.31 | -100% | 2020-01-24 01:00
Mississauga | 2020 | 355944 | Parkside Village Block 9 - 4055 Parkside Village Dr. | 99 | COMPLETE | Engineering by-passed |  |  | Sta. Rita, Leovigildo | no | Alectra Utilities | Paul Tremblay | 133266.38 | 189703.07 | 56436.69 | 42.35% | 37699.53 | 47869.27 | 10169.74 | 26.98% | 85931.72 | 131155.8 | 45224.08 | 52.63% | 3275.13 | 8178 | 4902.87 | 149.7% | 6360 | 500 | -5860 | -92.14% | 453.36 | 64 | -389.36 | -85.88% | 2020-01-24 01:00
Mississauga | 2019 | 358070 | FOLKWAY DR. MF FRO | 99 | COMPLETE | BOM not accurate | Cont Est Over | Labour est. over |  | No | Cudzilo, Tomasz | Paul Tremblay | 794223.56 | 791481.16 | -2742.4 | -0.3453% | 142335.27 | 106060.25 | -36275.02 | -25.49% | 10010.23 | 146871.86 | 136861.63 | 1367% | 4900 | 10290.36 | 5390.36 | 110% | 80000 | 528258.69 | 448258.69 | 560.3% | 1783 | 951 | -832 | -46.66% | 2019-02-16 01:00
Mississauga | 2019 | 359152 | 2145 North Sheridan Way - Marriot Residence Inn | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | no | Huo, Lisa | Macdougall, Stephen | 128461.41 | 129865.67 | 1404.26 | 1.093% | 38096.94 | 31437.29 | -6659.65 | -17.48% | 49697.47 | 49644.25 | -53.22 | -0.1071% | 17768.88 | 3723.5 | -14045.38 | -79.04% | 22898.12 | 45060.63 | 22162.51 | 96.79% | 480.03 | 356 | -124.03 | -25.84% | 2019-09-24 01:00
Mississauga | 2020 | 359161 | 6257 Airport Rd - Element Hotel by Westin | 99 | COMPLETE | Converted Project |  |  | Sidhu, Paul | no | Alectra Utilities | Peter Costantini | 108579.97 | 138341.24 | 29761.27 | 27.41% | 28416.13 | 44801.05 | 16384.92 | 57.66% | 51482.14 | 53447.34 | 1965.2 | 3.817% | 7119 | 5435.5 | -1683.5 | -23.65% | 21562.7 | 34657.35 | 13094.65 | 60.73% | 366.1 | 489 | 122.9 | 33.57% | 2020-02-12 01:00
Mississauga | 2019 | 360621 | 1580 Britannia Rd. E - Addition / Reno | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | no | Huo, Lisa | Macdougall, Stephen | 134562.13 | 133313.12 | -1249.01 | -0.9282% | 34208.11 | 28093.65 | -6114.46 | -17.87% | 34905.32 | 33805.95 | -1099.37 | -3.15% | 4294.78 | 3520 | -774.78 | -18.04% | 61153.92 | 67893.52 | 6739.6 | 11.02% | 288.72 | 122 | -166.72 | -57.74% | 2019-11-20 01:00
Mississauga | 2021 | 360743 | 3618 Hurontario St - Enfield Place II | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Macasaet, Ricardo | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-30 01:00
Mississauga | 2021 | 360751 | 3600-3606 Hurontario St. - Armdale Estate Inc | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | no | Macasaet, Ricardo | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-30 01:00
Mississauga | 2020 | 363573 | Canada Post Gateway Substation - 4567 Dixie Rd. | 99 | COMPLETE | Converted Project |  |  | Sta. Rita, Leovigildo | no | Alectra Utilities | Rob Elliot | 100979.49 | 61633.3 | -39346.19 | -38.96% | 41379.04 | 19891.55 | -21487.49 | -51.93% | 6306.17 | 36807.75 | 30501.58 | 483.7% | 8774.1 | 4934 | -3840.1 | -43.77% | 4520.18 | 0 | -4520.18 | -100% | 418.44 | 219.25 | -199.19 | -47.6% | 2020-01-30 01:00
Mississauga | 2021 | 367232 | 270 DERRY ROAD WEST | 99 | COMPLETE | Cont Est Under | Labour est. over | BOM cost variance | Sta. Rita, Leovigildo | no | Huo, Lisa | Peter Costantini | 150336.18 | 144293.91 | -6042.27 | -4.019% | 61772.4 | 48849.77 | -12922.63 | -20.92% | 64688.79 | 51733.92 | -12954.87 | -20.03% | 5946.99 | 10018.4 | 4071.41 | 68.46% | 17928 | 33691.82 | 15763.82 | 87.93% | 366.95 | 429 | 62.05 | 16.91% | 2021-04-01 01:00
Mississauga | 2020 | 367911 | QEW Improvements from Evans Ave. to Cawthra Rd. - P1 Bridge Section | 99 | CANCELLED | N/A |  |  | Antonakos, Tony | no | Alectra Utilities | Rob Elliot | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-19 01:00
Mississauga | 2020 | 368606 | Church Street Overhead rebuild | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | no | Alectra Utilities | Rob Elliot | 1870560.64 | 1640182.42 | -230378.22 | -12.32% | 498835.43 | 765907.54 | 267072.11 | 53.54% | 507318.12 | 399824.87 | -107493.25 | -21.19% | 128990.49 | 295338.69 | 166348.2 | 129% | 735416.6 | 178528.72 | -556887.88 | -75.72% | 5194.04 | 9642.75 | 4448.71 | 85.65% | 2020-08-19 01:00
Mississauga | 2019 | 369772 | Peel Paramedic Station S3 - 1188 Lakeshore Rd. W | 99 | COMPLETE | Vehicle Under Estimated | N/A | N/A |  | no | Alectra Utilities | Bourgeois, Craig | 14857.89 | 16681.79 | 1823.9 | 12.28% | 8249.33 | 7981.17 | -268.16 | -3.251% | 5555.54 | 5949.52 | 393.98 | 7.092% | 1053.02 | 2078 | 1024.98 | 97.34% | 0 | 673.1 | 673.1 |  | 146.88 | 99 | -47.88 | -32.6% | 2019-01-17 01:00
Mississauga | 2022 | 370239 | 2017 OTC (INITIAL) - MEADOWVALE LANE (EHM COSTS) | 99 | CANCELLED | N/A |  |  | Penner, Mitchell | No | Ricci, Leonardo | Weaver, Thomas | 178514.45 | 8849.56 | -169664.89 | -95.04% | 37754.19 | 8849.56 | -28904.63 | -76.56% | 17913.32 | 0 | -17913.32 | -100% | 2822.94 | 0 | -2822.94 | -100% | 120024 | 0 | -120024 | -100% | 183.41 | 0 | -183.41 | -100% | 2019-02-27 01:00
Mississauga | 2019 | 373579 | 938 East Ave. - Region of Peel Paramedics Station - TEMP SERV. | 99 | COMPLETE | BOM not used | Labour est. under | Cont Est Over |  | no | Bharosi, Mohindra | Bourgeois, Craig | 18513.72 | 14992.85 | -3520.87 | -19.02% | 6591.95 | 7993.77 | 1401.82 | 21.27% | 5568.75 | 1801.08 | -3767.67 | -67.66% | 1053.02 | 1104 | 50.98 | 4.841% | 5300 | 4094 | -1206 | -22.75% | 78.48 | 105 | 26.52 | 33.79% | 2019-02-27 01:00
Mississauga | 2022 | 373771 | McLaughlin Rd Development | 99 | CANCELLED | N/A |  |  | Penner, Mitchell | No | Ricci, Leonardo | Weaver, Thomas | 0 | 4909.06 | 4909.06 |  | 0 | 4635.86 | 4635.86 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 273.2 | 273.2 |  | 0 | 0.5 | 0.5 |  | 2020-01-24 01:00
Mississauga | 2020 | 373940 | Madigan's Lane | 99 | COMPLETE | Converted Project | N/A | N/A | Penner, Mitchell | No | Alectra Utilities | Paul Tremblay | 55866.25 | 154261.2 | 98394.95 | 176.1% | 16096.26 | 48112.51 | 32016.25 | 198.9% | 7732.02 | 28262.77 | 20530.75 | 265.5% | 1759.07 | 8841.65 | 7082.58 | 402.6% | 30278.9 | 69044.27 | 38765.37 | 128% | 194.6 | 131 | -63.6 | -32.68% | 2020-01-24 01:00
Mississauga | 2019 | 374045 | 3105 Argentia Rd. - Tesla Supercharger Meadowvale | 99 | COMPLETE | N/A | N/A | N/A |  | no | Macasaet, Ricardo | Macdougall, Stephen | 229169.66 | 229077.17 | -92.49 | -0.04036% | 11366.05 | 35752.22 | 24386.17 | 214.6% | 53820.07 | 58835.08 | 5015.01 | 9.318% | 29015.86 | 2730 | -26285.86 | -90.59% | 134967.68 | 131557.37 | -3410.31 | -2.527% | 384.98 | 322.5 | -62.48 | -16.23% | 2019-02-16 01:00
Mississauga | 2020 | 374088 | Blanefield Townhomes | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Paul Tremblay | 169019.74 | 144616.17 | -24403.57 | -14.44% | 24002.86 | 36041.45 | 12038.59 | 50.15% | 5958.06 | 3003.99 | -2954.07 | -49.58% | 1788.82 | 5444.79 | 3655.97 | 204.4% | 137270 | 99987.89 | -37282.11 | -27.16% | 248.61 | 272.5 | 23.89 | 9.609% | 2020-05-28
Mississauga | 2020 | 375435 | JOHN STREET SOUTH & LAKE STREET - 2018 O/H REBUILD | 99 | COMPLETE | Under 10% |  |  | Antonakos, Tony | No | Alectra Utilities | Paul Murphy | 285536.6 | 284025.19 | -1511.41 | -0.5293% | 97618.44 | 127366.08 | 29747.64 | 30.47% | 74906.57 | 47900.62 | -27005.95 | -36.05% | 27151.59 | 64708.36 | 37556.77 | 138.3% | 85860 | 44050.13 | -41809.87 | -48.7% | 924.77 | 1480.5 | 555.73 | 60.09% | 2020-03-07 01:00
Mississauga | 2020 | 376032 | City of Mississauga Storm Water Pump - Black Walnut / Cactus Gate | 99 | COMPLETE | Converted Project | N/A | N/A | Sta. Rita, Leovigildo | no | Alectra Utilities | Antonio Mina | 2735.88 | 0 | -2735.88 | -100% | 2360.75 | 0 | -2360.75 | -100% | 29.38 | 0 | -29.38 | -100% | 80.75 | 0 | -80.75 | -100% | 265 | 0 | -265 | -100% | 28.82 | 18.5 | -10.32 | -35.81% | 2020-11-18 01:00
Mississauga | 2019 | 377342 | Courtney Park from Dixie to Shawson | 99 | COMPLETE | Labour est. under | Cont Est Under | BOM not accurate | Carter, Gordon | Yes | Matai, Ihssan (Sam) | Paul Murphy | 582126.17 | 675714.41 | 93588.24 | 16.08% | 231678.82 | 261244.89 | 29566.07 | 12.76% | 216140.56 | 232152.64 | 16012.08 | 7.408% | 74743.01 | 101894 | 27150.99 | 36.33% | 59563.78 | 80422.88 | 20859.1 | 35.02% | 2499.51 | 3622.25 | 1122.74 | 44.92% | 2019-05-07
Mississauga | 2020 | 377764 | 5320 Ninth Line - Churchill Meadows Community Centre | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | no | Alectra Utilities | Peter Costantini | 167016.42 | 161284.59 | -5731.83 | -3.432% | 48640.74 | 37785.08 | -10855.66 | -22.32% | 57778.75 | 55396.71 | -2382.04 | -4.123% | 6965.12 | 4978 | -1987.12 | -28.53% | 53631.81 | 63124.8 | 9492.99 | 17.7% | 516.77 | 413.5 | -103.27 | -19.98% | 2020-08-27 01:00
Mississauga | 2022 | 378249 | 7675 Torbram Rd. - Freedom Mobile TEMP SERV | 98 | CANCELLED | N/A |  |  | Lucic, Marko | no | Cudzilo, Tomasz | Peter Costantini | 23455.61 | 8005.03 | -15450.58 | -65.87% | 11978.23 | 5377.34 | -6600.89 | -55.11% | 4020.28 | 460.69 | -3559.59 | -88.54% | 1097.1 | 654 | -443.1 | -40.39% | 6360 | 1513 | -4847 | -76.21% | 131.25 | 75 | -56.25 | -42.86% | 2021-11-17 01:00
Mississauga | 2021 | 379217 | CARAVELLE SERVICE UPGRADE | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Mandic, Goran | no | Huo, Lisa | Peter Costantini | 146582.95 | 106349.18 | -40233.77 | -27.45% | 53666.11 | 29722.89 | -23943.22 | -44.62% | 54522.74 | 48781.22 | -5741.52 | -10.53% | 5994.1 | 5548.34 | -445.76 | -7.437% | 32400 | 22296.73 | -10103.27 | -31.18% | 400.59 | 210.5 | -190.09 | -47.45% | 2021-11-17 01:00
Mississauga | 2020 | 379989 | Atwater Pole Replacement - Sie | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Alectra Utilities | Antonakos, Tony | 0 | 1617.86 | 1617.86 |  | 0 | 1617.86 | 1617.86 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-17
Mississauga | 2019 | 379997 | DERRY ROAD EXTENSION PH2 | 99 | COMPLETE | Labour est. under | BOM not accurate | Cont Est Over | Carter, Gordon | No | Matai, Ihssan (Sam) | Rob Elliot | 198650.1 | 278571.09 | 79920.99 | 40.23% | 57713.72 | 94545.32 | 36831.6 | 63.82% | 57273.89 | 71780.03 | 14506.14 | 25.33% | 15069.01 | 30380 | 15310.99 | 101.6% | 68593.48 | 81865.74 | 13272.26 | 19.35% | 584.46 | 1301.25 | 716.79 | 122.6% | 2019-05-17
Mississauga | 2019 | 380285 | 2018-NE FIELDGATE & PONYTRAIL TH BLOCK 1/0 CABLE REPLACEMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | Yes | Cudzilo, Tomasz | Paul Tremblay | 215714.56 | 214415.83 | -1298.73 | -0.6021% | 46653.88 | 47690.56 | 1036.68 | 2.222% | 1522.07 | 8053.47 | 6531.4 | 429.1% | 3356.47 | 4661 | 1304.53 | 38.87% | 164182.14 | 154010.8 | -10171.34 | -6.195% | 523.5 | 436 | -87.5 | -16.71% | 2019-11-20 01:00
Mississauga | 2020 | 380322 | SIGSBEE 1/0 CABLE REPLACEMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | Yes | Alectra Utilities | Paul Tremblay | 891979.83 | 909458.67 | 17478.84 | 1.96% | 65389.09 | 155913.12 | 90524.03 | 138.4% | 5763.74 | 7502.33 | 1738.59 | 30.16% | 5323.7 | 12301.27 | 6977.57 | 131.1% | 815503.3 | 733741.95 | -81761.35 | -10.03% | 557.7 | 859 | 301.3 | 54.03% | 2020-03-04 01:00
Mississauga | 2019 | 380533 | Munden/Pear Tree | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | no | Matai, Ihssan (Sam) | Mark Bobanovic | 590957.6 | 951929.25 | 360971.65 | 61.08% | 30644.32 | 108157.95 | 77513.63 | 252.9% | 166747.49 | 231551.37 | 64803.88 | 38.86% | 10954.79 | 4099 | -6855.79 | -62.58% | 382611 | 608120.93 | 225509.93 | 58.94% | 593.01 | 753 | 159.99 | 26.98% | 2019-11-14 01:00
Mississauga | 2019 | 380955 | 309 Lakeshore Road East & Tx R | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Antonakos, Tony | No | Matai, Ihssan (Sam) | Bourgeois, Craig | 0 | 31912.68 | 31912.68 |  | 0 | 20467.51 | 20467.51 |  | 0 | 6455.49 | 6455.49 |  | 0 | 3526 | 3526 |  | 0 | 1463.68 | 1463.68 |  | 0 | 0 | 0 |  | 2019-06-26 01:00
Mississauga | 2022 | 381561 | 6211 Second Line West | 99 | CANCELLED | N/A |  |  | Penner, Mitchell | No | Ricci, Leonardo | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-01 01:00
Mississauga | 2020 | 382619 | Southdown - ROW to Lakeshore | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | no | Alectra Utilities | Rob Elliot | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-01 01:00
Mississauga | 2019 | 382707 | 360 City Centre Dr - Daniels CCW Corp. - The Wesley | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | no | Macasaet, Ricardo | Macdougall, Stephen | 305517.96 | 84113.9 | -221404.06 | -72.47% | 20706.57 | 48530.15 | 27823.58 | 134.4% | 117722.56 | 19816.85 | -97905.71 | -83.17% | 46605.38 | 6644 | -39961.38 | -85.74% | 114296.47 | 8716.25 | -105580.22 | -92.37% | 397.47 | 600.75 | 203.28 | 51.14% | 2019-11-01 01:00
Mississauga | 2019 | 382854 | Adonis Supermarket - 2561 Stanfield Rd | 99 | COMPLETE | Labour est. under | BOM not used | N/A |  | no | Huo, Lisa | Macdougall, Stephen | 121203.39 | 84824.1 | -36379.29 | -30.02% | 49819.08 | 26736.33 | -23082.75 | -46.33% | 48044.41 | 42297.52 | -5746.89 | -11.96% | 9767.66 | 4328 | -5439.66 | -55.69% | 13572.24 | 11462.25 | -2109.99 | -15.55% | 445.5 | 312.25 | -133.25 | -29.91% | 2019-03-16 01:00
Mississauga | 2019 | 383478 | 7355 Goreway Rd - Service Upgrade | 99 | COMPLETE | Converted Project |  |  | Sidhu, Paul | no | Zaghloul, Sam | Macdougall, Stephen | 84464.49 | 71929.41 | -12535.08 | -14.84% | 33346.61 | 30439.98 | -2906.63 | -8.716% | 21784.69 | 10147.04 | -11637.65 | -53.42% | 6852.07 | 7556.5 | 704.43 | 10.28% | 22481.12 | 23785.89 | 1304.77 | 5.804% | 484.76 | 383.5 | -101.26 | -20.89% | 2019-09-17 01:00
Mississauga | 2019 | 383881 | 2018 U/G Rebuild - City Centre Drive Cable Renewal | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | no | Cudzilo, Tomasz | Paul Tremblay | 836311.17 | 894302.35 | 57991.18 | 6.934% | 171968.49 | 238072.15 | 66103.66 | 38.44% | 11865.78 | 10844.81 | -1020.97 | -8.604% | 9961.02 | 34808 | 24846.98 | 249.4% | 638515.88 | 610577.39 | -27938.49 | -4.376% | 1990.51 | 2333.25 | 342.74 | 17.22% | 2019-07-17 01:00
Mississauga | 2019 | 384905 | 4055 Parkside Village Dr. | 99 | COMPLETE | Engineering by-passed | N/A | N/A | Sta. Rita, Leovigildo | No | Macasaet, Ricardo | Paul Tremblay | 0 | 183969 | 183969 |  | 0 | 47308.01 | 47308.01 |  | 0 | 124224.89 | 124224.89 |  | 0 | 9688 | 9688 |  | 0 | 2665 | 2665 |  | 0 | 3 | 3 |  | 2019-10-16 01:00
Mississauga | 2022 | 386151 | 2017 OTC (INITIAL) - M-CITY PHASE 1 (EHM COSTS) | 99 | COMPLETE | Under 10% |  |  | Penner, Mitchell | No | Ricci, Leonardo | Mark Bobanovic | 88498.07 | 83213.17 | -5284.9 | -5.972% | 59096.26 | 69777.83 | 10681.57 | 18.07% | 21972.6 | 6678.74 | -15293.86 | -69.6% | 7429.21 | 6575 | -854.21 | -11.5% | 0 | 181.6 | 181.6 |  | 550.7 | 252.5 | -298.2 | -54.15% | 2022-08-05 01:00
Mississauga | 2019 | 387081 | 360 CITY CENTRE DR. - The Wesley Tower | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Macasaet, Ricardo | Paul Tremblay | 0 | 107450.55 | 107450.55 |  | 0 | 2668.57 | 2668.57 |  | 0 | 104781.98 | 104781.98 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-19 01:00
Mississauga | 2020 | 387516 | MTO Project - 401 West Expansion | 99 | COMPLETE | Converted Project | N/A | N/A | Kafel, Krzysztof | no | Alectra Utilities | Mark Bobanovic | 1005093.26 | 1108824.65 | 103731.39 | 10.32% | 45425.7 | 97069.47 | 51643.77 | 113.7% | 101916.07 | 134619.91 | 32703.84 | 32.09% | 76.2 | 0 | -76.2 | -100% | 772243.2 | 877135.27 | 104892.07 | 13.58% | 110.05 | 40.5 | -69.55 | -63.2% | 2020-04-27
Mississauga | 2019 | 389589 | 2270 Speakman Dr .- Muslim Assoc. Conversion to Alectra TX - | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A |  | no | Zaghloul, Sam | Macdougall, Stephen | 146187.67 | 149630.82 | 3443.15 | 2.355% | 39151.52 | 46297.25 | 7145.73 | 18.25% | 36686.34 | 37257.63 | 571.29 | 1.557% | 6275.19 | 4813 | -1462.19 | -23.3% | 64074.62 | 61262.94 | -2811.68 | -4.388% | 400.24 | 494.5 | 94.26 | 23.55% | 2019-02-23 01:00
Mississauga | 2020 | 389731 | 2475 Hurontario St - 6 Storey Building | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | no | Alectra Utilities | Peter Costantini | 293061.16 | 250696.01 | -42365.15 | -14.46% | 51762.76 | 38647.77 | -13114.99 | -25.34% | 47271.89 | 45670.21 | -1601.68 | -3.388% | 5026.51 | 4990 | -36.51 | -0.7263% | 189000 | 161388.03 | -27611.97 | -14.61% | 342.08 | 245 | -97.08 | -28.38% | 2020-09-11 01:00
Mississauga | 2020 | 390248 | WOODCHUCK LANE OH REBUILD | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Alectra Utilities | Weaver, Thomas | 0 | -54.86 | -54.86 |  | 0 | -54.86 | -54.86 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-26 01:00
Mississauga | 2019 | 390791 | 7070 Derrycrest Dr. - Chartwell Headquarters | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | no | Bharosi, Mohindra | Macdougall, Stephen | 108300.3 | 105768.27 | -2532.03 | -2.338% | 36761.58 | 37700.88 | 939.3 | 2.555% | 45987.48 | 42495.21 | -3492.27 | -7.594% | 8591.24 | 3919 | -4672.24 | -54.38% | 16960 | 21653.18 | 4693.18 | 27.67% | 434.81 | 423 | -11.81 | -2.716% | 2019-11-26 01:00
Mississauga | 2020 | 391005 | 4572 Tomken Rd. - Dezen Tomken Plaza | 99 | COMPLETE | Converted Project |  |  | Sidhu, Paul | no | Alectra Utilities | Macdougall, Stephen | 87315.88 | 136362.53 | 49046.65 | 56.17% | 27751.2 | 32762.18 | 5010.98 | 18.06% | 28136.77 | 28851.78 | 715.01 | 2.541% | 4029.33 | 5323 | 1293.67 | 32.11% | 27398.58 | 69425.57 | 42026.99 | 153.4% | 311.89 | 319.5 | 7.61 | 2.44% | 2020-03-05 01:00
Mississauga | 2019 | 391013 | 4677 Glen Erin Dr. - Mills Square Bldg C | 99 | COMPLETE | Converted Project |  |  | Sidhu, Paul | no | Zaghloul, Sam | Macdougall, Stephen | 13426 | 83248.41 | 69822.41 | 520.1% | 2480.84 | 19713.04 | 17232.2 | 694.6% | 9288.91 | 36143.48 | 26854.57 | 289.1% | 1656.25 | 2218.5 | 562.25 | 33.95% | 0 | 25173.39 | 25173.39 |  | 232.26 | 210 | -22.26 | -9.584% | 2019-11-26 01:00
Mississauga | 2020 | 391021 | 4699 Glen Erin Dr. - Mills Square Bldg D | 99 | COMPLETE | Converted Project | N/A | N/A | Sidhu, Paul | no | Alectra Utilities | Macdougall, Stephen | 251006.52 | 261374.04 | 10367.52 | 4.13% | 44025.09 | 56455.64 | 12430.55 | 28.24% | 128910.66 | 107266.12 | -21644.54 | -16.79% | 7691.54 | 8445.5 | 753.96 | 9.802% | 70379.23 | 89206.78 | 18827.55 | 26.75% | 500.32 | 596 | 95.68 | 19.12% | 2020-01-21 00:59
Mississauga | 2020 | 392884 | 1775 Fifeshire Crt. - Region of Peel Fifeshire Sewage Pumping Station | 99 | COMPLETE | Converted Project |  |  | Sta. Rita, Leovigildo | no | Alectra Utilities | Macdougall, Stephen | 25925.47 | 40558.22 | 14632.75 | 56.44% | 11953.35 | 16636.18 | 4682.83 | 39.18% | 10872.94 | 10619.48 | -253.46 | -2.331% | 1371.18 | 2750 | 1378.82 | 100.6% | 1728 | 10552.56 | 8824.56 | 510.7% | 76.06 | 37 | -39.06 | -51.35% | 2020-05-08
Mississauga | 2019 | 393211 | RATHBURN -ROAD WEST HULRT PLANT RELOCATIONS | 99 | COMPLETE | Cont Est Under | Labour est. over | N/A | Tobin, Michael | no | Garcha, Tirath | Mark Bobanovic | 3958216.9 | 5141206.19 | 1182989.29 | 29.89% | 789577.78 | 651140.66 | -138437.12 | -17.53% | 507241.78 | 456009.33 | -51232.45 | -10.1% | 93246.04 | 72058.5 | -21187.54 | -22.72% | 2568151.3 | 3961926.63 | 1393775.33 | 54.27% | 7515.12 | 6094 | -1421.12 | -18.91% | 2019-04-10 01:00
Mississauga | 2019 | 393511 | Northmount Ave Rebuild | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Bobanovic, Mark | No | Matai, Ihssan (Sam) | Mark Bobanovic | 0 | 43028.96 | 43028.96 |  | 0 | 8983.9 | 8983.9 |  | 0 | 4454.06 | 4454.06 |  | 0 | 0 | 0 |  | 0 | 29591 | 29591 |  | 0 | 0 | 0 |  | 2019-06-26 01:00
Mississauga | 2020 | 393895 | M-CITY TEMPORARY 2MVA SERVICE - 475 WEBB DRIVE - TEMP SERV | 99 | COMPLETE | Converted Project | N/A | N/A | Braletic, Bob | No | Alectra Utilities | Peter Costantini | 141735.8 | 90333.27 | -51402.53 | -36.27% | 64862.26 | 23760.17 | -41102.09 | -63.37% | 51795.67 | 48775.4 | -3020.27 | -5.831% | 13342.77 | 2602.5 | -10740.27 | -80.5% | 11735.1 | 15195.2 | 3460.1 | 29.49% | 385.59 | 291 | -94.59 | -24.53% | 2020-08-03 01:00
Mississauga | 2020 | 394097 | Chinguacousy Road Widening - W | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2023-01-30 01:00
Mississauga | 2020 | 394100 | TORBRAM ROAD WIDENING - QUEEN | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Alectra Utilities | Weaver, Thomas | 0 | -83.46 | -83.46 |  | 0 | -83.46 | -83.46 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2023-01-30 01:00
Mississauga | 2020 | 394126 | STUB POLE TEMPORARY REMOVAL - | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Alectra Utilities | Weaver, Thomas | 0 | -10.54 | -10.54 |  | 0 | -10.54 | -10.54 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2023-01-30 01:00
Mississauga | 2022 | 395209 | Ellisdon sales office temporary 200A 1PH service | 99 | COMPLETE | Labour est. under | N/A | N/A | Sta. Rita, Leovigildo | No | Macasaet, Ricardo | Peter Costantini | 0 | 6266.89 | 6266.89 |  | 0 | 4328.09 | 4328.09 |  | 0 | 533.8 | 533.8 |  | 0 | 932 | 932 |  | 0 | 473 | 473 |  | 0 | 0 | 0 |  | 2023-01-30 01:00
Mississauga | 2019 | 395233 | 190 STATESMAN DRIVE | 99 | COMPLETE | Converted Project |  |  | Sidhu, Paul | no | Zaghloul, Sam | Macdougall, Stephen | 18752.56 | 165168.85 | 146416.29 | 780.8% | 11444.33 | 38930.48 | 27486.15 | 240.2% | 6051.08 | 74398.46 | 68347.38 | 1130% | 1257.15 | 5859 | 4601.85 | 366.1% | 0 | 45903.41 | 45903.41 |  | 461.95 | 424.5 | -37.45 | -8.107% | 2019-10-22 01:00
Mississauga | 2022 | 395399 | 8 Nahani Way - Mississauga Square TEMP SERV | 99 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Sta. Rita, Leovigildo | No | Macasaet, Ricardo | Peter Costantini | 65567.44 | 49110.29 | -16457.15 | -25.1% | 27976.45 | 16479.16 | -11497.29 | -41.1% | 32356.01 | 28658.94 | -3697.07 | -11.43% | 3818.98 | 2604.5 | -1214.48 | -31.8% | 1416 | 1367.69 | -48.31 | -3.412% | 226 | 125.25 | -100.75 | -44.58% | 2020-05-07
Mississauga | 2020 | 395401 | MISSISSAUGA SQUARE 2MVA SERVI | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 81669.79 | 82340.74 | 670.95 | 0.8215% | 31313.87 | 15914.03 | -15399.84 | -49.18% | 42058.43 | 7112.07 | -34946.36 | -83.09% | 2921.25 | 1196 | -1725.25 | -59.06% | 0 | 58118.64 | 58118.64 |  | 342.08 | 141.5 | -200.58 | -58.64% | 2020-05-07
Mississauga | 2019 | 395479 | Mavis Road Widening - Courtney | 99 | COMPLETE | Weather | Labour est. under | BOM not used | Kafel, Krzysztof | No | Truong, Jimmy | Paul Murphy | 320044.66 | 373492.04 | 53447.38 | 16.7% | 149081.15 | 200521.9 | 51440.75 | 34.51% | 88052.79 | 65339.94 | -22712.85 | -25.79% | 23175.56 | 60055 | 36879.44 | 159.1% | 46535.16 | 47575.2 | 1040.04 | 2.235% | 1712.18 | 2517 | 804.82 | 47.01% | 2019-05-22
Mississauga | 2022 | 395487 | 6688 Kitimat Road - Switchgear | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Truong, Jimmy | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-28
Mississauga | 2019 | 395495 | 650 ATWATER - DELLWOOD PARK TOWNHOMES | 99 | COMPLETE | Labour est. over | Cont Est Under | N/A | Mandic, Goran | No | Macasaet, Ricardo | Macdougall, Stephen | 85802.73 | 79750.74 | -6051.99 | -7.053% | 28626.61 | 21436.58 | -7190.03 | -25.12% | 31771.36 | 29428.06 | -2343.3 | -7.376% | 4260.52 | 3101.5 | -1159.02 | -27.2% | 21144.24 | 25784.6 | 4640.36 | 21.95% | 320.14 | 234.5 | -85.64 | -26.75% | 2019-05-28
Mississauga | 2020 | 395583 | 8 Nahani Way, Mississauga U/G | 98 | COMPLETE | Under 10% | N/A | N/A | Kafel, Krzysztof | No | Alectra Utilities | Peter Costantini | 284693.48 | 288345.78 | 3652.3 | 1.283% | 19590.89 | 53199.3 | 33608.41 | 171.6% | 22571.04 | 24056.25 | 1485.21 | 6.58% | 3866.19 | 7414.99 | 3548.8 | 91.79% | 238665.36 | 203675.24 | -34990.12 | -14.66% | 229.51 | 504.75 | 275.24 | 119.9% | 2020-08-24 01:00
Mississauga | 2019 | 395604 | 368 Meadow Wood Lane | 99 | COMPLETE | N/A | N/A | N/A | Kafel, Krzysztof | No | Watters, Maxwell | Mark Bobanovic | 0 | 19281.13 | 19281.13 |  | 0 | 9022.68 | 9022.68 |  | 0 | 1578.9 | 1578.9 |  | 0 | 0 | 0 |  | 0 | 8474.1 | 8474.1 |  | 0 | 118 | 118 |  | 2019-02-08 01:00
Mississauga | 2022 | 395997 | 4100 Ponytrail Dr - Chelsea O | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Jacinto, Gerardo | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-10 01:00
Mississauga | 2022 | 396017 | M-CITY POLELINE RELOCATION - QUARTZ ROAD | 99 | COMPLETE | Labour est. over | Cont Est Under | BOM not accurate | Lacombe, Joel | No | Watters, Maxwell | Mark Bobanovic | 176119.61 | 109639.53 | -66480.08 | -37.75% | 73501.98 | 15949.27 | -57552.71 | -78.3% | 22105.29 | 8187.46 | -13917.83 | -62.96% | 14168.22 | 417 | -13751.22 | -97.06% | 66344.12 | 85085.8 | 18741.68 | 28.25% | 497.37 | 18 | -479.37 | -96.38% | 2022-01-10 01:00
Mississauga | 2022 | 396172 | GO ELEC. - LWL - CONFLICT #LW18 - HAIG BLVD. | 95 | COMPLETE | Scope change - unforeseen | Cont Est Under | BOM not accurate | Khuu, Philander | No | Khuu, Philander | Mark Bobanovic | 2490887.38 | 3579607.91 | 1088720.53 | 43.71% | 185519.87 | 179392.5 | -6127.37 | -3.303% | 219037.78 | 204374.85 | -14662.93 | -6.694% | 41062.67 | 51847.11 | 10784.44 | 26.26% | 2045267.06 | 3143869.96 | 1098602.9 | 53.71% | 1685.72 | 1592.5 | -93.22 | -5.53% | 2022-04-21
Mississauga | 2021 | 396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | 99 | COMPLETE | Scope change - unforeseen | Labour est. under | Vehicle Under Estimated | Tobin, Michael | No | Khuu, Philander | Rob Elliot | 1657293.53 | 2049013.54 | 391720.01 | 23.64% | 192161.24 | 297062.35 | 104901.11 | 54.59% | 214761.49 | 230386.83 | 15625.34 | 7.276% | 40428.34 | 75337.03 | 34908.69 | 86.35% | 1209942.46 | 1446227.33 | 236284.87 | 19.53% | 2697.13 | 1975 | -722.13 | -26.77% | 2021-02-04 01:00
Mississauga | 2022 | 396199 | GO ELEC. - LWL - CONFLICT #LW20 & LW1778 - ALEXANDRA | 99 | CANCELLED | N/A |  |  | Tobin, Michael | No | Khuu, Philander | Weaver, Thomas | 0 | 12588.45 | 12588.45 |  | 0 | 3326.63 | 3326.63 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 9261.82 | 9261.82 |  | 0 | 2.5 | 2.5 |  | 2020-11-05 01:00
Mississauga | 2020 | 396201 | GO ELEC. - LWL - CONFLICT #LW21 - CAWTHRA ROAD | 99 | COMPLETE | Converted Project | N/A | N/A | Tobin, Michael | No | Alectra Utilities | Rob Elliot | 2822879.77 | 3099985.82 | 277106.05 | 9.816% | 253301.39 | 369587.32 | 116285.93 | 45.91% | 375949.92 | 357300.56 | -18649.36 | -4.961% | 55825.92 | 77479.77 | 21653.85 | 38.79% | 2126246.65 | 2295532.68 | 169286.03 | 7.962% | 2254.91 | 1848 | -406.91 | -18.05% | 2020-11-05 01:00
Mississauga | 2020 | 396228 | GO ELEC. - LWL - CONFLICT #LW23 - HURONTARIO ST. | 99 | COMPLETE | Converted Project | N/A | N/A | Tobin, Michael | No | Alectra Utilities | Rob Elliot | 4564622.94 | 4452064.22 | -112558.72 | -2.466% | 1808922.39 | 511867.57 | -1297054.82 | -71.7% | 344957.03 | 384528.43 | 39571.4 | 11.47% | 91442.78 | 71340.68 | -20102.1 | -21.98% | 2319300.74 | 3481116.58 | 1161815.84 | 50.09% | 3386.7 | 2143 | -1243.7 | -36.72% | 2020-07-17 01:00
Mississauga | 2022 | 396236 | GO ELEC. - LWL - CONFLICT #LW24 - STAVEBANK ROAD | 99 | CANCELLED | N/A |  |  | Tobin, Michael | No | Khuu, Philander | Weaver, Thomas | 0 | 11930.6 | 11930.6 |  | 0 | 2998.78 | 2998.78 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 8931.82 | 8931.82 |  | 0 | 8 | 8 |  | 2022-02-28 01:00
Mississauga | 2022 | 396244 | RER MX - LW CONFLICT #LW1654 - MISSISSAUGA ROAD | 99 | COMPLETE | Scope change - unforeseen | Labour est. under | Vehicle Under Estimated | Khuu, Philander | No | Khuu, Philander | Mark Bobanovic | 3822570.43 | 2930970.54 | -891599.89 | -23.32% | 140928.39 | 255994 | 115065.61 | 81.65% | 331130.59 | 282285.07 | -48845.52 | -14.75% | 27720.81 | 90351 | 62630.19 | 225.9% | 3322790.64 | 2302116.77 | -1020673.87 | -30.72% | 1297.56 | 2778.5 | 1480.94 | 114.1% | 2022-02-28 01:00
Mississauga | 2020 | 396439 | RER MX - KT CONFLICT #KT911 - MALTON GO CROSSING: EAST OF MALTON STATION 1 | 99 | COMPLETE | Converted Project |  |  | Tobin, Michael | No | Alectra Utilities | Rob Elliot | 47729.79 | 28946.53 | -18783.26 | -39.35% | 32130.95 | 23869.42 | -8261.53 | -25.71% | 0 | 3048.05 | 3048.05 |  | 7872 | 0 | -7872 | -100% | 2160 | 2000 | -160 | -7.407% | 240 | 247 | 7 | 2.917% | 2020-07-23 01:00
Mississauga | 2021 | 396797 | TX REPLACEMENT TX24275 - 3476 B GLEN ERIN DR | 99 | COMPLETE | Labour est. over | Cont Est Over | Vac truck | Lucic, Marko | No | Matai, Ihssan (Sam) | Gregory Dunfield | 43812.88 | 18595.8 | -25217.08 | -57.56% | 19076.45 | 7682.89 | -11393.56 | -59.73% | 7976.62 | 5493.37 | -2483.25 | -31.13% | 3259.81 | 2597.91 | -661.9 | -20.3% | 13500 | 2821.63 | -10678.37 | -79.1% | 120.17 | 56 | -64.17 | -53.4% | 2021-11-18 01:00
Mississauga | 2019 | 397651 | 6775 MARITZ DRIVE-BLUM | 99 | COMPLETE | Converted Project | N/A | N/A | Sidhu, Paul | No | Zaghloul, Sam | Macdougall, Stephen | 63570.82 | 128286.87 | 64716.05 | 101.8% | 27110.45 | 41599.86 | 14489.41 | 53.45% | 21133.9 | 55305.64 | 34171.74 | 161.7% | 7834.85 | 6264 | -1570.85 | -20.05% | 7491.62 | 25117.37 | 17625.75 | 235.3% | 413.95 | 460 | 46.05 | 11.12% | 2019-12-10 01:00
Mississauga | 2020 | 397669 | MTO QEW Project- Mississauga R | 99 | COMPLETE | Converted Project | N/A | N/A | Kafel, Krzysztof | No | Alectra Utilities | Rob Elliot | 50865.77 | 39561.68 | -11304.09 | -22.22% | 16119.85 | 5292.47 | -10827.38 | -67.17% | 3698.14 | 3505.06 | -193.08 | -5.221% | 2799.3 | 0 | -2799.3 | -100% | 28248.48 | 30764.15 | 2515.67 | 8.906% | 183.45 | 0 | -183.45 | -100% | 2020-04-27
Mississauga | 2020 | 398696 | 3045 Mavis Rd - Bldg C&D | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 49222.14 | 54840.66 | 5618.52 | 11.41% | 17937.4 | 16739.11 | -1198.29 | -6.68% | 22592.35 | 22301.08 | -291.27 | -1.289% | 1272.39 | 3452 | 2179.61 | 171.3% | 7420 | 12348.47 | 4928.47 | 66.42% | 189.07 | 225 | 35.93 | 19% | 2020-01-30 01:00
Mississauga | 2020 | 398733 | Clark Blvd - Road widening | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Alectra Utilities | Weaver, Thomas | 0 | -89.17 | -89.17 |  | 0 | -89.17 | -89.17 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-05 01:00
Mississauga | 2019 | 400119 | 128 Queen St - Pole Relocations | 99 | COMPLETE | Cont Est Over | BOM not accurate | N/A | Carter, Gordon | No | Watters, Maxwell | Rob Elliot | 227704.02 | 206395.65 | -21308.37 | -9.358% | 88677.13 | 87646.9 | -1030.23 | -1.162% | 62716.42 | 51181.68 | -11534.74 | -18.39% | 16325.6 | 24708 | 8382.4 | 51.35% | 59984.87 | 42777.22 | -17207.65 | -28.69% | 766.07 | 1045.75 | 279.68 | 36.51% | 2019-04-05 01:00
Mississauga | 2019 | 400346 | 35 AND 65 WATERGARDEN DRIVE - UG SYSTEM EXPANSION | 98 | COMPLETE | Converted Project |  |  | Kafel, Krzysztof | No | Watters, Maxwell | Paul Tremblay | 524132.41 | 662175.74 | 138043.33 | 26.34% | 41214.82 | 94606.48 | 53391.66 | 129.5% | 9675 | 76833.91 | 67158.91 | 694.1% | 8142.15 | 9991.5 | 1849.35 | 22.71% | 465100.44 | 480707.05 | 15606.61 | 3.356% | 470.17 | 595 | 124.83 | 26.55% | 2019-09-21 01:00
Mississauga | 2019 | 400493 | MALTON GO STATION U/G RELOCATI | 99 | COMPLETE | Cont Est Over | BOM not used | N/A | Carter, Gordon | No | Watters, Maxwell | Rob Elliot | 235140.24 | 168638.55 | -66501.69 | -28.28% | 67735.8 | 68606.04 | 870.24 | 1.285% | 71165.78 | 46437.5 | -24728.28 | -34.75% | 13360.23 | 16423 | 3062.77 | 22.92% | 82878.43 | 37172.01 | -45706.42 | -55.15% | 673.41 | 854.5 | 181.09 | 26.89% | 2019-03-01 01:00
Mississauga | 2019 | 400944 | 3210 Hurontario Street-Cooksville GO Station | 99 | COMPLETE | Cont Est Under | Labour est. over | N/A |  | No | Zaghloul, Sam | Macdougall, Stephen | 226138.68 | 235205.86 | 9067.18 | 4.01% | 71910.11 | 64051.5 | -7858.61 | -10.93% | 128927.31 | 133302.9 | 4375.59 | 3.394% | 10519.56 | 4651 | -5868.56 | -55.79% | 14781.7 | 32881.26 | 18099.56 | 122.4% | 796.1 | 908 | 111.9 | 14.06% | 2019-03-19 01:00
Mississauga | 2020 | 402579 | 2210 & 2230 BROMSGROVE RD -Southdown Towns | 99 | COMPLETE | Converted Project | N/A | N/A | Sta. Rita, Leovigildo | No | Alectra Utilities | Macdougall, Stephen | 109573.04 | 100669.47 | -8903.57 | -8.126% | 9721.8 | 27562.71 | 17840.91 | 183.5% | 33092.79 | 32457.16 | -635.63 | -1.921% | 23074.21 | 3408 | -19666.21 | -85.23% | 43284.24 | 34600.71 | -8683.53 | -20.06% | 320.03 | 296.75 | -23.28 | -7.274% | 2020-05-01
Mississauga | 2020 | 402675 | 1996 LUSHES AVE - TOWNHOMES | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Paul Tremblay | 112684.99 | 116298.86 | 3613.87 | 3.207% | 30533.67 | 22577.95 | -7955.72 | -26.06% | 1091.31 | 11148.32 | 10057.01 | 921.6% | 933.73 | 2397.85 | 1464.12 | 156.8% | 80126.28 | 80174.74 | 48.46 | 0.06048% | 133.56 | 96 | -37.56 | -28.12% | 2020-09-22 01:00
Mississauga | 2022 | 403088 | SG1534 - RATHBURN RD. AND GOLDEN ORCHARD DR. | 99 | CANCELLED | N/A |  |  | Antonakos, Tony | No | Cudzilo, Tomasz | Glenn Guile | 168370.55 | 0 | -168370.55 | -100% | 31871.77 | 0 | -31871.77 | -100% | 19580.03 | 0 | -19580.03 | -100% | 6560.03 | 0 | -6560.03 | -100% | 110358.72 | 0 | -110358.72 | -100% | 570.87 | 103.5 | -467.37 | -81.87% | 2022-02-14 01:00
Mississauga | 2022 | 403141 | 4601 Mississauga Rd | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Ricci, Leonardo | Weaver, Thomas | 0 | 5143.5 | 5143.5 |  | 0 | 5143.5 | 5143.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-02-14 01:00
Mississauga | 2022 | 403627 | 353-417 Rathburn Rd W | 99 | CANCELLED | N/A |  |  | Penner, Mitchell | No | Ricci, Leonardo | Weaver, Thomas | 0 | 11682.99 | 11682.99 |  | 0 | 11682.99 | 11682.99 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6 | 6 |  | 2022-02-14 01:00
Mississauga | 2022 | 403897 | LAIRD/ WCB MAIN FEEDER RELOCATION | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | Yes | Cudzilo, Tomasz | Glenn Guile | 327575.45 | 605833.67 | 278258.22 | 84.94% | 74396.19 | 140441.48 | 66045.29 | 88.78% | 115760.13 | 93380.97 | -22379.16 | -19.33% | 7009.03 | 24348.94 | 17339.91 | 247.4% | 130410.1 | 342181.73 | 211771.63 | 162.4% | 421.69 | 747 | 325.31 | 77.14% | 2022-02-14 01:00
Mississauga | 2020 | 404005 | SOUTHDOWN AND QEW POLE REPLACE | 99 | COMPLETE | Converted Project | N/A | N/A | Bobanovic, Mark | No | Alectra Utilities | Paul Murphy | 120146.77 | 165414.64 | 45267.87 | 37.68% | 31302.32 | 84806.16 | 53503.84 | 170.9% | 26469.16 | 25922.59 | -546.57 | -2.065% | 9375.29 | 32399.66 | 23024.37 | 245.6% | 53000 | 22286.23 | -30713.77 | -57.95% | 348.64 | 876.5 | 527.86 | 151.4% | 2020-02-04 01:00
Mississauga | 2019 | 404620 | 2299 HOGAN DRIVE | 99 | COMPLETE | N/A | N/A | N/A |  | No | Zaghloul, Sam | Macdougall, Stephen | 214986.89 | 216659.92 | 1673.03 | 0.7782% | 35055.08 | 37563.56 | 2508.48 | 7.156% | 53107.67 | 53671.46 | 563.79 | 1.062% | 8244.59 | 4521 | -3723.59 | -45.16% | 118579.55 | 120903.9 | 2324.35 | 1.96% | 367.7 | 360.5 | -7.2 | -1.958% | 2019-03-05 01:00
Mississauga | 2020 | 405121 | MTO PROJECT - 401 WEST & DERRY | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Alectra Utilities | Weaver, Thomas | 0 | -39.2 | -39.2 |  | 0 | -39.2 | -39.2 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-31 01:00
Mississauga | 2020 | 405235 | 6825 MARITZ DRIVE | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 87455.9 | 105900.01 | 18444.11 | 21.09% | 30083.84 | 29220.23 | -863.61 | -2.871% | 43534.82 | 45896.81 | 2361.99 | 5.426% | 6417.24 | 3595.5 | -2821.74 | -43.97% | 7420 | 27187.47 | 19767.47 | 266.4% | 363.28 | 335 | -28.28 | -7.785% | 2020-01-31 01:00
Mississauga | 2019 | 405307 | BURNHAMTHORPE O/H TO U/G CONVE | 99 | CANCELLED | N/A | N/A | N/A |  | No | Watters, Maxwell | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-16 01:00
Mississauga | 2019 | 405331 | 648 HAZELHURST RD - SUPER SUCK | 99 | CANCELLED | N/A |  |  |  | No | Bharosi, Mohindra | Bourgeois, Craig | 53193.72 | 6238.03 | -46955.69 | -88.27% | 7879.89 | 1879.01 | -6000.88 | -76.15% | 17786.81 | 4359.02 | -13427.79 | -75.49% | 1027.02 | 0 | -1027.02 | -100% | 26500 | 0 | -26500 | -100% | 102.24 | 25 | -77.24 | -75.55% | 2019-01-16 01:00
Mississauga | 2019 | 405471 | 630-670 Courtney Valley | 99 | COMPLETE | Scope – Const | BOM not accurate | N/A | Carter, Gordon | No | Central North ICI | Bourgeois, Craig | 72771.33 | 49227.25 | -23544.08 | -32.35% | 29017.87 | 29600.02 | 582.15 | 2.006% | 32145.5 | 6430.07 | -25715.43 | -80% | 7175.83 | 7967 | 791.17 | 11.03% | 4432.13 | 5230.16 | 798.03 | 18.01% | 239.53 | 311.25 | 71.72 | 29.94% | 2019-01-16 01:00
Mississauga | 2020 | 406596 | 3560 ODYSSEY DRIVE "BUILDING H | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 108524.08 | 76788.74 | -31735.34 | -29.24% | 36426.98 | 20717.95 | -15709.03 | -43.12% | 45643 | 43571.12 | -2071.88 | -4.539% | 4497.7 | 3805 | -692.7 | -15.4% | 21956.4 | 8694.67 | -13261.73 | -60.4% | 257.73 | 211 | -46.73 | -18.13% | 2020-05-14
Mississauga | 2020 | 406609 | 3580 ODYSSEY DRIVE "BUILDING G | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 124179.32 | 94032.44 | -30146.88 | -24.28% | 28914.99 | 18853.11 | -10061.88 | -34.8% | 46339.74 | 47441.55 | 1101.81 | 2.378% | 3295.67 | 1204 | -2091.67 | -63.47% | 45628.92 | 26533.78 | -19095.14 | -41.85% | 195.98 | 165 | -30.98 | -15.81% | 2020-02-20 01:00
Mississauga | 2020 | 406617 | 3610 ODYSSEY DRIVE "BUILDING F | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 99576.06 | 71135.05 | -28441.01 | -28.56% | 30998.06 | 18464.42 | -12533.64 | -40.43% | 41893.4 | 33244.2 | -8649.2 | -20.65% | 4018.64 | 1886 | -2132.64 | -53.07% | 22665.96 | 17540.43 | -5125.53 | -22.61% | 214.91 | 127 | -87.91 | -40.91% | 2020-01-21 01:00
Mississauga | 2020 | 406625 | 3630 ODYSSEY DRIVE "BUILDING E | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 102621.43 | 68893.87 | -33727.56 | -32.87% | 31376.1 | 14322.18 | -17053.92 | -54.35% | 44548.77 | 41649.41 | -2899.36 | -6.508% | 4030.6 | 2413 | -1617.6 | -40.13% | 22665.96 | 10509.28 | -12156.68 | -53.63% | 201.85 | 132 | -69.85 | -34.6% | 2020-01-21 01:00
Mississauga | 2019 | 406684 | 2019 - UG REBUILD - COPENHAGEN - SECTION 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | Yes | Cudzilo, Tomasz | Paul Tremblay | 2667208.78 | 2701479.68 | 34270.9 | 1.285% | 305351.47 | 413040.48 | 107689.01 | 35.27% | 0 | 24185.53 | 24185.53 |  | 13300 | 19542.65 | 6242.65 | 46.94% | 2348557.31 | 2244711.02 | -103846.29 | -4.422% | 3519 | 1683.75 | -1835.25 | -52.15% | 2019-11-05 01:00
Mississauga | 2020 | 406941 | 2020 - WEBB M.S. EGRESS | 99 | CANCELLED | N/A | N/A | N/A | Antonakos, Tony | No | Alectra Utilities | Weaver, Thomas | 0 | 3033.13 | 3033.13 |  | 0 | -39.24 | -39.24 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-19 01:00
Mississauga | 2019 | 407695 | 35 & 65 WATERGARDEN DR - PERLA CONDOS BY PINNACLE | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Macasaet, Ricardo | Paul Tremblay | 127852.28 | 86937.97 | -40914.31 | -32% | 11062.3 | 26880.15 | 15817.85 | 143% | 63445.63 | 52361.32 | -11084.31 | -17.47% | 41130.19 | 4581.5 | -36548.69 | -88.86% | 5052.24 | 3115 | -1937.24 | -38.34% | 504.07 | 236.5 | -267.57 | -53.08% | 2019-12-19 01:00
Mississauga | 2020 | 407880 | 2021 44KV YORK-MEADOWPINE LOOP | 99 | CANCELLED | N/A |  |  | Antonakos, Tony | No | Alectra Utilities | Weaver, Thomas | 0 | -39.24 | -39.24 |  | 0 | -39.24 | -39.24 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-22 01:00
Mississauga | 2020 | 408073 | 3320 ELMBANK RD - PARK N FLY 400A SERVICE | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 105477.03 | 110977.03 | 5500 | 5.214% | 68058.46 | 25328.26 | -42730.2 | -62.78% | 32026.63 | 27103.2 | -4923.43 | -15.37% | 5391.94 | 4454 | -937.94 | -17.4% | 0 | 54091.57 | 54091.57 |  | 346.15 | 196 | -150.15 | -43.38% | 2020-01-22 01:00
Mississauga | 2019 | 408292 | 2630 FIFTH LINE WEST - ERINVIEW RETIREMENT RESIDENCE | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Huo, Lisa | Macdougall, Stephen | 157461.61 | 157065.03 | -396.58 | -0.2519% | 45194.24 | 42740.36 | -2453.88 | -5.43% | 50581.7 | 47608.89 | -2972.81 | -5.877% | 9164.19 | 4872 | -4292.19 | -46.84% | 52521.48 | 61843.78 | 9322.3 | 17.75% | 332.45 | 336 | 3.55 | 1.068% | 2019-10-27 01:00
Mississauga | 2022 | 408891 | 270 LAKESHORE RD WEST - SHORES OF PORT CREDIT TEMP SERV | 99 | COMPLETE | Labour est. over | Cont Est Under | Material Over Estimated | Mandic, Goran | No | Macasaet, Ricardo | Peter Costantini | 90654.9 | 59050.55 | -31604.35 | -34.86% | 43353.29 | 16664.02 | -26689.27 | -61.56% | 31205.82 | 24490.14 | -6715.68 | -21.52% | 7919.57 | 1359 | -6560.57 | -82.84% | 8176.22 | 16537.39 | 8361.17 | 102.3% | 366.87 | 164 | -202.87 | -55.3% | 2021-12-23 01:00
Mississauga | 2020 | 408911 | 2023 - WALDEN CIRCLE VOLTAGE C | 99 | CANCELLED | N/A |  |  | Antonakos, Tony | No | Alectra Utilities | Weaver, Thomas | 0 | -33.51 | -33.51 |  | 0 | -33.51 | -33.51 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-23 01:00
Mississauga | 2022 | 408946 | 2300 STANFIELD RD. - 2332574 ONTARIO LIMITED/STANFI | 99 | CANCELLED | N/A |  |  | Sta. Rita, Leovigildo | No | Huo, Lisa | Weaver, Thomas | 0 | 4424.78 | 4424.78 |  | 0 | 4148.13 | 4148.13 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 94 | 94 |  | 0 | 0 | 0 |  | 2021-12-23 01:00
Mississauga | 2020 | 409720 | 2019 - SHAWSON MS EGRESS (FEED | 99 | CANCELLED | N/A |  |  | Antonakos, Tony | No | Alectra Utilities | Paul Tremblay | 0 | 1622.03 | 1622.03 |  | 0 | 1403.39 | 1403.39 |  | 0 | 0 | 0 |  | 0 | 218.64 | 218.64 |  | 0 | 0 | 0 |  | 0 | 16 | 16 |  | 2021-12-23 01:00
Mississauga | 2021 | 409877 | (SG1297) REMOVAL - ROCKWOOD RD. & RATHBURN RD. | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | No | Cudzilo, Tomasz | Mark Bobanovic | 814817.88 | 814823.31 | 5.43 | 0.0006664% | 157949.66 | 197504.18 | 39554.52 | 25.04% | 137719.49 | 114737.09 | -22982.4 | -16.69% | 12802.73 | 24570.61 | 11767.88 | 91.92% | 506346 | 477856.93 | -28489.07 | -5.626% | 650.36 | 823.25 | 172.89 | 26.58% | 2021-12-23 01:00
Mississauga | 2022 | 409922 | 3980 CONFEDERATION PKWY - M-CITY ROGERS PHASE-1 3MVA + | 99 | COMPLETE | Labour est. over | Material Under Estimated | Vehicle Over Estimated- | Mandic, Goran | No | Macasaet, Ricardo | Antonio Mina | 356648.68 | 309628.8 | -47019.88 | -13.18% | 127157.25 | 56705.09 | -70452.16 | -55.41% | 211451.77 | 236511.51 | 25059.74 | 11.85% | 15447.66 | 8195 | -7252.66 | -46.95% | 2592 | 8217.2 | 5625.2 | 217% | 1240.46 | 468.5 | -771.96 | -62.23% | 2022-04-15
Mississauga | 2022 | 409957 | OTC (INITIAL) - M-CITY PHASE 1 (EXPANSION COSTS) | 98 | COMPLETE | Under 10% |  |  | Watters, Maxwell | No | Watters, Maxwell | Mark Bobanovic | 3865773.69 | 3607335.92 | -258437.77 | -6.685% | 327596.45 | 595799.79 | 268203.34 | 81.87% | 789430.64 | 674415.83 | -115014.81 | -14.57% | 46136.61 | 63244.22 | 17107.61 | 37.08% | 2702609.99 | 2270553.57 | -432056.42 | -15.99% | 2026.82 | 3605 | 1578.18 | 77.86% | 2022-05-04
Mississauga | 2019 | 410173 | 5050 SATELLITE DRIVE - SPECTRU | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Bharosi, Mohindra | Macdougall, Stephen | 53761.5724 | 77023.5 | 23261.9276 | 43.27% | 22133.25 | 24946.06 | 2812.81 | 12.71% | 29436.32 | 42841.06 | 13404.74 | 45.54% | 1344.0024 | 3236 | 1891.9976 | 140.8% | 848 | 6000.38 | 5152.38 | 607.6% | 252.48 | 313 | 60.52 | 23.97% | 2019-05-30
Mississauga | 2019 | 410229 | 1201 Fewster Dr. - SOL CUISINE | 99 | COMPLETE | Labour est. under | N/A | N/A | MacDougall, Stephen | No | Huo, Lisa | Macdougall, Stephen | 105432.91 | 128769.8 | 23336.89 | 22.13% | 30447.69 | 40911.97 | 10464.28 | 34.37% | 39430.43 | 38458.85 | -971.58 | -2.464% | 4178.79 | 5024 | 845.21 | 20.23% | 31376 | 43935.98 | 12559.98 | 40.03% | 285.81 | 454.25 | 168.44 | 58.93% | 2019-03-11 01:00
Mississauga | 2022 | 411176 | 1850 RATHBURN ROAD EAST-CHELSEA/LORMEL ON THE GREEN I | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Garcha, Tirath | XMoinuddin, Saad | 0 | 16021.63 | 16021.63 |  | 0 | 15921.43 | 15921.43 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 100.2 | 100.2 |  | 0 | 18 | 18 |  | 2019-01-19 01:00
Mississauga | 2019 | 411619 | 2411 MOTORWAY BLVD - ERIN PARK | 99 | COMPLETE | Labour est. over | BOM not used | N/A |  | no | Alectra Utilities | Macdougall, Stephen | 37292.65 | 27685.48 | -9607.17 | -25.76% | 15489.39 | 8558.8 | -6930.59 | -44.74% | 19416.03 | 18228.68 | -1187.35 | -6.115% | 1539.23 | 898 | -641.23 | -41.66% | 848 | 0 | -848 | -100% | 182.6 | 89 | -93.6 | -51.26% | 2019-01-19 01:00
Mississauga | 2019 | 411993 | 562 Lynd Ave - Pole Relocation | 99 | COMPLETE | Under 10% | N/A | N/A | Lacombe, Joel | No | Truong, Jimmy | Paul Murphy | 9307.6 | 10274.48 | 966.88 | 10.39% | 5406.82 | 6480.48 | 1073.66 | 19.86% | 1620.78 | 886 | -734.78 | -45.33% | 758.98 | 2128 | 1369.02 | 180.4% | 1521.02 | 780 | -741.02 | -48.72% | 50.2 | 54 | 3.8 | 7.57% | 2019-08-17 01:00
Mississauga | 2020 | 412048 | 6020 WINSTON CHURCHILL -DAYCAR | 99 | CANCELLED | N/A |  |  | Braletic, Bob | No | Alectra Utilities | Macdougall, Stephen | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-15 01:00
Mississauga | 2019 | 412110 | SQUARE ONE PARKING LOT BLOCK 4 & 5 | 99 | COMPLETE | N/A |  |  |  | No | Macasaet, Ricardo | Paul Tremblay | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-15 01:00
Mississauga | 2022 | 412195 | 309 RATHBURN RD WEST - LIVING ARTS PARKING LOT 400AM | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Macasaet, Ricardo | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-15 01:00
Mississauga | 2021 | 412945 | U/G DISTRIBUTION AUTOMATION - CITY CENTRE NORTH, 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Houston, Andrew | Yes | Zaghloul, Sam | Antonio Mina | 392177.2 | 453194.4 | 61017.2 | 15.56% | 113614.22 | 153961.49 | 40347.27 | 35.51% | 238229.07 | 262912.39 | 24683.32 | 10.36% | 13333.91 | 35664.17 | 22330.26 | 167.5% | 27000 | 656.35 | -26343.65 | -97.57% | 794.55 | 1538 | 743.45 | 93.57% | 2021-11-15 01:00
Mississauga | 2020 | 413008 | 5809 SHAWSON DRIVE - TEMP SERV | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Bourgeois, Craig | 20006.63 | 7499.63 | -12507 | -62.51% | 14694.4 | 4381.67 | -10312.73 | -70.18% | 3187.52 | 583.38 | -2604.14 | -81.7% | 2124.71 | 827.38 | -1297.33 | -61.06% | 0 | 1707.2 | 1707.2 |  | 133.48 | 85 | -48.48 | -36.32% | 2020-02-25 01:00
Mississauga | 2019 | 413121 | 233 Madill Blvd | 99 | COMPLETE | BOM not used | Labour est. over | N/A | Mandic, Goran | No | Bharosi, Mohindra | Macdougall, Stephen | 99103.98 | 43396.17 | -55707.81 | -56.21% | 32188.84 | 24878.58 | -7310.26 | -22.71% | 61303.32 | 12575.35 | -48727.97 | -79.49% | 4746.86 | 2822 | -1924.86 | -40.55% | 864.96 | 3120.24 | 2255.28 | 260.7% | 296.45 | 203 | -93.45 | -31.52% | 2019-03-05 01:00
Mississauga | 2020 | 413163 | CYNARA RD. AND IRMA RD. - CABLE REPLACEMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | No | Alectra Utilities | Paul Tremblay | 97054.41 | 104577.25 | 7522.84 | 7.751% | 32796.14 | 22889.66 | -9906.48 | -30.21% | 1756.49 | 2077.72 | 321.23 | 18.29% | 1185.54 | 1963.44 | 777.9 | 65.62% | 61316.24 | 77646.43 | 16330.19 | 26.63% | 138.61 | 197 | 58.39 | 42.13% | 2020-03-14 01:00
Mississauga | 2021 | 413585 | 6020 WINSTON CHURCHILL BLVD | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Wickramasinghe, Dinuka | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-24 01:00
Mississauga | 2019 | 413737 | 6965 VANGUARD DR. GAS STATION | 99 | COMPLETE | Converted Project |  |  | MacDougall, Stephen | No | Huo, Lisa | Macdougall, Stephen | 97710.56 | 85181.26 | -12529.3 | -12.82% | 37425.33 | 25022.26 | -12403.07 | -33.14% | 41472.21 | 39303.39 | -2168.82 | -5.23% | 7195.46 | 3482 | -3713.46 | -51.61% | 11617.56 | 17373.61 | 5756.05 | 49.55% | 235.48 | 210 | -25.48 | -10.82% | 2019-12-24 01:00
Mississauga | 2019 | 413809 | 27.6KV FEEDER EXTENSION TRADERS - HURONTARIO-KENNEDY | 99 | CANCELLED | N/A |  |  | Antonakos, Tony | No | Cudzilo, Tomasz | Paul Tremblay | 0 | 603.19 | 603.19 |  | 0 | 603.19 | 603.19 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-06 01:00
Mississauga | 2019 | 413850 | 7675 TORBRAM ROAD - CN MALPORT YARD | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Macasaet, Ricardo | Macdougall, Stephen | 23209.96 | 98560.61 | 75350.65 | 324.6% | 0 | 30754.49 | 30754.49 |  | 0 | 38001.53 | 38001.53 |  | 0 | 3889.5 | 3889.5 |  | 18106 | 25915.09 | 7809.09 | 43.13% | 373.9 | 353 | -20.9 | -5.59% | 2019-07-06 01:00
Mississauga | 2020 | 413876 | 2095&2105 MATHESON BLVD E - HOPEWELL FLEX OFFICE BUILDING | 99 | COMPLETE | Converted Project | N/A | N/A | MacDougall, Stephen | No | Alectra Utilities | Peter Costantini | 349110.39 | 355233.08 | 6122.69 | 1.754% | 79551.76 | 71727.8 | -7823.96 | -9.835% | 128234.58 | 129882.42 | 1647.84 | 1.285% | 8484.05 | 9236.58 | 752.53 | 8.87% | 132840 | 144317.33 | 11477.33 | 8.64% | 604.83 | 586.5 | -18.33 | -3.031% | 2020-10-30 01:00
Mississauga | 2021 | 414107 | Port Credit Village West New Feeder | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | Yes | Tempra, Troylan | Paul Murphy | 1743957.05 | 1367230.79 | -376726.26 | -21.6% | 622061.91 | 322615.36 | -299446.55 | -48.14% | 148074.96 | 136956.89 | -11118.07 | -7.508% | 155488.5 | 130801.47 | -24687.03 | -15.88% | 818331.68 | 776857.07 | -41474.61 | -5.068% | 5927.11 | 2972 | -2955.11 | -49.86% | 2021-01-28 01:00
Mississauga | 2019 | 414115 | U/G FEEDER CABLE REPLACEMENT- AVONWICK AVE WEST OF MAVIS | 99 | COMPLETE | Under 10% |  |  | Lucic, Marko | No | Tempra, Troylan | Paul Tremblay | 199017.26 | 217924.03 | 18906.77 | 9.5% | 56075.83 | 42874.45 | -13201.38 | -23.54% | 33814.06 | 35119.46 | 1305.4 | 3.861% | 11927.37 | 10066 | -1861.37 | -15.61% | 97200 | 129864.12 | 32664.12 | 33.61% | 566.44 | 510 | -56.44 | -9.964% | 2019-04-24 01:00
Mississauga | 2020 | 414140 | 3 QUEEN ST SOUTH, MISSISSAUGA, | 99 | COMPLETE | Engineering by-passed |  |  | Mandic, Goran | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-26 01:00
Mississauga | 2019 | 414191 | 155 OAKES DRIVE TEMPORARY SERVICE | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Mandic, Goran | No | Macasaet, Ricardo | Peter Costantini | 0 | 1845.45 | 1845.45 |  | 0 | 1330.69 | 1330.69 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 514.76 | 514.76 |  | 0 | 10.5 | 10.5 |  | 2019-06-26 01:00
Mississauga | 2021 | 414916 | SILVER SPEAR II APARTMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 136441.54 | 98518.99 | -37922.55 | -27.79% | 72628.56 | 33473.15 | -39155.41 | -53.91% | 43492.11 | 40930.1 | -2562.01 | -5.891% | 6280.87 | 2960 | -3320.87 | -52.87% | 14040 | 21155.74 | 7115.74 | 50.68% | 280.02 | 184 | -96.02 | -34.29% | 2021-11-30 01:00
Mississauga | 2019 | 415126 | POLE REPLACEMENT - BATCH #3 (12 POLES) | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | No | Tempra, Troylan | Rob Elliot | 178125.48 | 257608.78 | 79483.3 | 44.62% | 76267.54 | 120723.91 | 44456.37 | 58.29% | 48227.32 | 59558.86 | 11331.54 | 23.5% | 14629.12 | 38213 | 23583.88 | 161.2% | 39001.5 | 38484.82 | -516.68 | -1.325% | 1670.3867 | 1291 | -379.3867 | -22.71% | 2019-09-13 01:00
Mississauga | 2020 | 415169 | POLE REPLACEMENT - BATCH #7 (4 POLES) | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | No | Alectra Utilities | Rob Elliot | 80865.05 | 67626.97 | -13238.08 | -16.37% | 29005.37 | 35260.44 | 6255.07 | 21.57% | 12717.33 | 9920.77 | -2796.56 | -21.99% | 7822.35 | 12688.3 | 4865.95 | 62.21% | 31320 | 9757.46 | -21562.54 | -68.85% | 265.0333 | 347 | 81.9667 | 30.93% | 2020-02-13 01:00
Mississauga | 2019 | 415177 | POLE LINE REBUILD - BURSLEM RD (7 POLES) | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | No | Matai, Ihssan (Sam) | Rob Elliot | 186461.8 | 162424.83 | -24036.97 | -12.89% | 108314.82 | 93460.75 | -14854.07 | -13.71% | 22118.92 | 36890.27 | 14771.35 | 66.78% | 24275.53 | 22726 | -1549.53 | -6.383% | 31752.53 | 9347.81 | -22404.72 | -70.56% | 870.23 | 747.5 | -122.73 | -14.1% | 2019-12-03 01:00
Mississauga | 2019 | 415185 | 1PH TX REPLACEMENTS - BATCH #5 (10 TX'S) | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Antonakos, Tony | no | Matai, Ihssan (Sam) | Paul Tremblay | 93929 | 57312.07 | -36616.93 | -38.98% | 40915.97 | 17382.44 | -23533.53 | -57.52% | 42575.62 | 36069.63 | -6505.99 | -15.28% | 10437.41 | 3860 | -6577.41 | -63.02% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-26 01:00
Mississauga | 2019 | 415193 | TX10389 AT 4179 SHALEBANK CRT | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Antonakos, Tony | No | Matai, Ihssan (Sam) | Paul Tremblay | 116189.38 | 96611.54 | -19577.84 | -16.85% | 48406.95 | 12503.98 | -35902.97 | -74.17% | 55257.53 | 54620.61 | -636.92 | -1.153% | 12524.9 | 1766 | -10758.9 | -85.9% | 0 | 27720.95 | 27720.95 |  | 480.49 | 139.5 | -340.99 | -70.97% | 2019-10-22 01:00
Mississauga | 2019 | 415329 | POLE REPLACEMENT - BATCH #5 (6 POLES) | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | No | Tempra, Troylan | Paul Murphy | 82334.45 | 104667.75 | 22333.3 | 27.13% | 45385.65 | 59206.06 | 13820.41 | 30.45% | 15112.6 | 12085.18 | -3027.42 | -20.03% | 8803.3 | 17762.5 | 8959.2 | 101.8% | 0 | 15614.01 | 15614.01 |  | 499.9167 | 423 | -76.9167 | -15.39% | 2019-10-05 01:00
Mississauga | 2020 | 415388 | MCVEAN DRIVE WIDENING - CASTLE | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Alectra Utilities | Weaver, Thomas | 18.99 | 0 | -18.99 | -100% | 18.99 | 0 | -18.99 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-26 01:00
Mississauga | 2019 | 415417 | POLE REPLACEMENT - BATCH #4 (17 POLES) | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | No | Tempra, Troylan | Paul Murphy | 225789.19 | 252683.68 | 26894.49 | 11.91% | 123798.42 | 120813.79 | -2984.63 | -2.411% | 32746.31 | 28530.98 | -4215.33 | -12.87% | 27870.57 | 50679.5 | 22808.93 | 81.84% | 41373.89 | 52613.21 | 11239.32 | 27.17% | 1364.8267 | 1497.5 | 132.6733 | 9.721% | 2019-10-26 01:00
Mississauga | 2020 | 415425 | 5320 NINTH LINE - TEMP SERV | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | No | Alectra Utilities | Peter Costantini | 17315.15 | 11425.86 | -5889.29 | -34.01% | 10404.48 | 5196.77 | -5207.71 | -50.05% | 5172.51 | 2457.96 | -2714.55 | -52.48% | 1738.16 | 1160.95 | -577.21 | -33.21% | 0 | 2610.18 | 2610.18 |  | 88.18 | 63.5 | -24.68 | -27.99% | 2020-09-07 01:00
Mississauga | 2019 | 415610 | POLE REPLACEMENT - BATCH #6 (17 POLES) | 99 | COMPLETE | Cont Est Under | Labour est. over | Vehicle Under Estimated | Carter, Gordon | No | Tempra, Troylan | Paul Murphy | 191401.36 | 215072.74 | 23671.38 | 12.37% | 93738.56 | 84875.88 | -8862.68 | -9.455% | 57885.17 | 51098.64 | -6786.53 | -11.72% | 22088.31 | 30870.5 | 8782.19 | 39.76% | 17689.32 | 48227.72 | 30538.4 | 172.6% | 1030.85 | 1019.5 | -11.35 | -1.101% | 2019-02-26 01:00
Mississauga | 2019 | 415628 | 1PH TX REPLACEMENTS - BATCH #7 (10 TX'S) | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Lucic, Marko | No | Tempra, Troylan | Paul Tremblay | 0 | 44350.78 | 44350.78 |  | 0 | 4803.55 | 4803.55 |  | 0 | 35692.97 | 35692.97 |  | 0 | 1989.33 | 1989.33 |  | 0 | 1864.93 | 1864.93 |  | 0 | 0 | 0 |  | 2019-10-22 01:00
Mississauga | 2019 | 415636 | 1PH TX REPLACEMENTS - BATCH #8 (8 TX'S) | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Lucic, Marko | No | Tempra, Troylan | Paul Tremblay | 70137.41 | 44538.23 | -25599.18 | -36.5% | 30303.27 | 10340.67 | -19962.6 | -65.88% | 28182.52 | 27174.06 | -1008.46 | -3.578% | 7733.86 | 2431 | -5302.86 | -68.57% | 0 | 4592.5 | 4592.5 |  | 0 | 0 | 0 |  | 2019-10-22 01:00
Mississauga | 2020 | 415724 | POLE REPLACEMENT - BATCH #10 (11 POLES) | 99 | COMPLETE | Rock | Labour est. over | Vac truck | Antonakos, Tony | No | Alectra Utilities | Rob Elliot | 373775.82 | 342953.48 | -30822.34 | -8.246% | 190267.02 | 131818.49 | -58448.53 | -30.72% | 59596.87 | 99578.73 | 39981.86 | 67.09% | 49931.93 | 73814.22 | 23882.29 | 47.83% | 73980 | 37742.04 | -36237.96 | -48.98% | 1958.99 | 1542 | -416.99 | -21.29% | 2020-12-17 01:00
Mississauga | 2019 | 415767 | POLE REPLACEMENT - BATCH #11 (9 POLES) | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | No | Matai, Ihssan (Sam) | Paul Murphy | 132531.37 | 141466.2 | 8934.83 | 6.742% | 55565.52 | 74195.2 | 18629.68 | 33.53% | 33011.94 | 30193 | -2818.94 | -8.539% | 14469.91 | 28658 | 14188.09 | 98.05% | 29484 | 8420 | -21064 | -71.44% | 551.58 | 801.5 | 249.92 | 45.31% | 2019-11-12 01:00
Mississauga | 2019 | 415880 | POLE REPLACEMENT - BATCH #2 (16 POLES) | 99 | COMPLETE | Converted Project |  |  | Antonakos, Tony | No | Handy, James | Paul Murphy | 148311.84 | 194818.78 | 46506.94 | 31.36% | 43380.23 | 104388.19 | 61007.96 | 140.6% | 25048.18 | 31786.64 | 6738.46 | 26.9% | 10043.43 | 39559.02 | 29515.59 | 293.9% | 67840 | 19084.93 | -48755.07 | -71.87% | 495.9 | 1077.5 | 581.6 | 117.3% | 2019-10-26 01:00
Mississauga | 2019 | 415935 | POLE LINE REBUILD ON SUNNINGDALE | 99 | COMPLETE | Converted Project |  |  | Antonakos, Tony | No | Handy, James | Paul Murphy | 125663.31 | 229311.73 | 103648.42 | 82.48% | 46140.03 | 125131.73 | 78991.7 | 171.2% | 32992.76 | 31629.48 | -1363.28 | -4.132% | 9986.83 | 40514.5 | 30527.67 | 305.7% | 36543.69 | 31985.02 | -4558.67 | -12.47% | 1109 | 1242 | 133 | 11.99% | 2019-10-19 01:00
Mississauga | 2019 | 415978 | POLE REPLACEMENT - BATCH #12 (6 POLES) | 99 | CANCELLED | N/A |  |  | Antonakos, Tony | No | Cudzilo, Tomasz | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-25 01:00
Mississauga | 2022 | 416006 | ELM DRIVE PUBLIC SCHOOL | 99 | COMPLETE | Converted Project | N/A | N/A | Costantini, Peter | No | Huo, Lisa | Peter Costantini | 195749.11 | 197073.6 | 1324.49 | 0.6766% | 87807.25 | 43985.13 | -43822.12 | -49.91% | 37399.41 | 42123.14 | 4723.73 | 12.63% | 8542.45 | 8106 | -436.45 | -5.109% | 62000 | 102859.33 | 40859.33 | 65.9% | 721.03 | 338 | -383.03 | -53.12% | 2022-01-25 01:00
Mississauga | 2021 | 416065 | 21 PARK ST EAST - TANU CONDOS 1200A SERVICE | 99 | COMPLETE | Civil contractor | Vehicle Under Estimated | Covid-19 | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 143231.52 | 219058.98 | 75827.46 | 52.94% | 41037.75 | 42576.49 | 1538.74 | 3.75% | 52730.08 | 50224.95 | -2505.13 | -4.751% | 6471.53 | 10123 | 3651.47 | 56.42% | 65342.16 | 115785.54 | 50443.38 | 77.2% | 218.53 | 284.5 | 65.97 | 30.19% | 2021-03-29 01:00
Mississauga | 2019 | 416073 | 1PH TX REPLACEMENTS - BATCH #1 (9 TX'S) | 99 | COMPLETE | Engineering by-passed |  |  | Antonakos, Tony | No | Cudzilo, Tomasz | Paul Tremblay | 0 | 106299.59 | 106299.59 |  | 0 | 29359.39 | 29359.39 |  | 0 | 41103.18 | 41103.18 |  | 0 | 2422 | 2422 |  | 0 | 33415.02 | 33415.02 |  | 0 | 0 | 0 |  | 2019-10-22 01:00
Mississauga | 2022 | 416137 | 150 PAISLEY BLVD WEST - CANAHAHNS STACKED TOWNHOMES | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Macasaet, Ricardo | Weaver, Thomas | 0 | 2739.21 | 2739.21 |  | 0 | 2739.21 | 2739.21 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-23 01:00
Mississauga | 2019 | 416209 | TX 6773 AT 3530 WISNER RD | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Antonakos, Tony | No | Matai, Ihssan (Sam) | Paul Tremblay | 91614.13 | 49636.66 | -41977.47 | -45.82% | 40915.97 | 3765.54 | -37150.43 | -90.8% | 40260.75 | 28904.37 | -11356.38 | -28.21% | 10437.41 | 0 | -10437.41 | -100% | 0 | 16966.75 | 16966.75 |  | 407.19 | 0 | -407.19 | -100% | 2019-04-23 01:00
Mississauga | 2019 | 416233 | 1PH TX REPLACEMENTS - BATCH #2 (10 TX'S) | 99 | COMPLETE | Engineering by-passed |  |  | Antonakos, Tony | No | Cudzilo, Tomasz | Paul Tremblay | 0 | 50125.22 | 50125.22 |  | 0 | 2928.47 | 2928.47 |  | 0 | 36614.63 | 36614.63 |  | 0 | 0 | 0 |  | 0 | 10582.12 | 10582.12 |  | 0 | 0 | 0 |  | 2019-10-22 01:00
Mississauga | 2020 | 416268 | 170 Pinewood - Pole Reloc | 99 | COMPLETE | Under 10% | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Paul Murphy | 37852.38 | 37015.29 | -837.09 | -2.211% | 21760.67 | 20230.28 | -1530.39 | -7.033% | 4676.29 | 5856.78 | 1180.49 | 25.24% | 4503.42 | 7636 | 3132.58 | 69.56% | 6912 | 3292.23 | -3619.77 | -52.37% | 128.34 | 205 | 76.66 | 59.73% | 2020-03-18 01:00
Mississauga | 2019 | 416321 | 1PH TX REPLACEMENTS - BATCH #3 (11 TX'S) | 99 | COMPLETE | Engineering by-passed |  |  | Antonakos, Tony | No | Cudzilo, Tomasz | Paul Tremblay | 0 | 54209.62 | 54209.62 |  | 0 | 5030.27 | 5030.27 |  | 0 | 20187.35 | 20187.35 |  | 0 | 0 | 0 |  | 0 | 28992 | 28992 |  | 0 | 0 | 0 |  | 2019-10-22 01:00
Mississauga | 2020 | 416356 | 2300 HOGAN DRIVE - KUEHNE + NAGEL TX REPLACEMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 0 | 36726.45 | 36726.45 |  | 0 | 5032.98 | 5032.98 |  | 0 | 30789.47 | 30789.47 |  | 0 | 904 | 904 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-01 01:00
Mississauga | 2020 | 416487 | 1610 KENMUIR | 99 | CANCELLED | N/A |  |  | Kafel, Krzysztof | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-15 01:00
Mississauga | 2022 | 416541 | STARLIGHT RENTAL CONDOMINIUMS | 99 | COMPLETE | Cont Est Under | Labour est. over | N/A | Mustachi, Randy | No | Huo, Lisa | Peter Costantini | 115266.87 | 120567.31 | 5300.44 | 4.598% | 50427.62 | 31558.73 | -18868.89 | -37.42% | 34764.16 | 37337.67 | 2573.51 | 7.403% | 4752.09 | 4889.5 | 137.41 | 2.892% | 25323 | 46781.41 | 21458.41 | 84.74% | 287.13 | 226 | -61.13 | -21.29% | 2022-06-15 01:00
Mississauga | 2021 | 417228 | 182 ROSEMERE ROAD - ROSEMERE PUMPING STATION | 99 | CANCELLED | N/A |  |  | Sidhu, Paul | No | Zaghloul, Sam | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-19 01:00
Mississauga | 2019 | 417261 | 21 COVENTRY RD POLE TRANSFER | 99 | CANCELLED | N/A |  |  |  | No | Truong, Jimmy | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-19 01:00
Mississauga | 2019 | 417463 | 1850 MATHESON BLVD E - CBS CANADA FILM STUDIO | 99 | COMPLETE | Cont Est Under | Labour est. under | N/A | Mandic, Goran | No | Bharosi, Mohindra | Macdougall, Stephen | 65793.59 | 75721.74 | 9928.15 | 15.09% | 16063.59 | 15526.57 | -537.02 | -3.343% | 46451.47 | 55416.49 | 8965.02 | 19.3% | 2430.53 | 1752 | -678.53 | -27.92% | 848 | 3026.68 | 2178.68 | 256.9% | 141.9567 | 168 | 26.0433 | 18.35% | 2019-03-19 01:00
Mississauga | 2019 | 417471 | 7605 BATH ROAD - HOPE AERO SERVICE UPGRADE | 99 | COMPLETE | Labour est. over | Cont Est Under | N/A |  | No | Bharosi, Mohindra | Macdougall, Stephen | 83826.74 | 71368.69 | -12458.05 | -14.86% | 42805.67 | 23504.99 | -19300.68 | -45.09% | 33496.48 | 31334.45 | -2162.03 | -6.454% | 7524.59 | 3734.5 | -3790.09 | -50.37% | 0 | 12794.75 | 12794.75 |  | 447.98 | 248 | -199.98 | -44.64% | 2019-01-15 01:00
Mississauga | 2022 | 417666 | M-CITY ROGERS PHASE-2 3MVA + | 99 | COMPLETE | Labour est. over | Material Under Estimated | Vehicle Over Estimated- | Mandic, Goran | No | Macasaet, Ricardo | Antonio Mina | 358861.25 | 329838.79 | -29022.46 | -8.087% | 129103.66 | 72045 | -57058.66 | -44.2% | 211451.77 | 246122.79 | 34671.02 | 16.4% | 15713.82 | 11671 | -4042.82 | -25.73% | 2592 | 0 | -2592 | -100% | 1057.3 | 707 | -350.3 | -33.13% | 2022-04-15
Mississauga | 2020 | 418183 | RATHBURN RD W CABLE REPLACEMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | Yes | Alectra Utilities | Paul Tremblay | 2834889.75 | 3146031.9 | 311142.15 | 10.98% | 182182.04 | 551053.82 | 368871.78 | 202.5% | 25483.47 | 57585.42 | 32101.95 | 126% | 12491.56 | 46570.92 | 34079.36 | 272.8% | 2614732.68 | 2490664.69 | -124067.99 | -4.745% | 1177 | 2901.5 | 1724.5 | 146.5% | 2020-07-16 01:00
Mississauga | 2019 | 418221 | Ninth Line - Bell Make Ready Project | 99 | COMPLETE | Cont Est Over | BOM not used | Labour est. over | Lacombe, Joel | No | Gonzales, Leonard | Mark Bobanovic | 30106.76 | 18398.44 | -11708.32 | -38.89% | 5229.94 | 673.44 | -4556.5 | -87.12% | 7358.54 | 1804.93 | -5553.61 | -75.47% | 0 | 0 | 0 |  | 17518.28 | 15880.37 | -1637.91 | -9.35% | 46 | 12 | -34 | -73.91% | 2019-01-09 01:00
Mississauga | 2019 | 418255 | 15 SQUARE ONE DRIVE-CITY CENTRE NORTH- CABLE REPLACEMENT | 99 | COMPLETE | N/A | N/A | N/A |  | No | Zaghloul, Sam | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-12 01:00
Mississauga | 2019 | 418538 | 1775 FIFESHIRE COURT -VARCON CONST - TEMP SERV | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Macasaet, Ricardo | Bourgeois, Craig | 28745.04 | 24662.79 | -4082.25 | -14.2% | 6464.78 | 8817.61 | 2352.83 | 36.39% | 3923.23 | 702.45 | -3220.78 | -82.1% | 12929.79 | 885 | -12044.79 | -93.16% | 5427.24 | 14257.73 | 8830.49 | 162.7% | 141.25 | 98.5 | -42.75 | -30.27% | 2019-12-02 00:59
Mississauga | 2020 | 418554 | BURNHAMTHORPE & CENTRAL P - VAN HORNE OUTDOOR BILLBOARD | 99 | COMPLETE | Engineering by-passed |  |  | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-25 01:00
Mississauga | 2019 | 418714 | 2017/18 - FOLKWAY SG1758 BACKU | 99 | COMPLETE | N/A | N/A | N/A |  | No | Cudzilo, Tomasz | Paul Tremblay | 0 | 93987.97 | 93987.97 |  | 0 | 18048.02 | 18048.02 |  | 0 | 16661.66 | 16661.66 |  | 0 | 2363 | 2363 |  | 0 | 56915.29 | 56915.29 |  | 0 | 201 | 201 |  | 2019-01-25 01:00
Mississauga | 2020 | 418781 | 6050 Millcreek Dr. - ORLANDO MILLCREEK BLDG | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 128858.71 | 127112.95 | -1745.76 | -1.355% | 10112.3 | 32120.35 | 22008.05 | 217.6% | 57663.73 | 48816.56 | -8847.17 | -15.34% | 38865.41 | 2809 | -36056.41 | -92.77% | 13295.36 | 43018.04 | 29722.68 | 223.6% | 521.81 | 344.5 | -177.31 | -33.98% | 2020-06-08 01:00
Mississauga | 2019 | 419653 | MALTON GO STATION ROW POLELINE | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | No | Watters, Maxwell | Rob Elliot | 62301.41 | 45406.34 | -16895.07 | -27.12% | 37340.65 | 26672.16 | -10668.49 | -28.57% | 4122.99 | 237.76 | -3885.23 | -94.23% | 7057.77 | 9298 | 2240.23 | 31.74% | 13780 | 9198.42 | -4581.58 | -33.25% | 357.48 | 215.5 | -141.98 | -39.72% | 2019-10-27 01:00
Mississauga | 2020 | 419661 | 1940 CRESTVIEW TOWN HOMES | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Paul Tremblay | 191905.6 | 192633.89 | 728.29 | 0.3795% | 27594.36 | 37983.06 | 10388.7 | 37.65% | 1485.94 | 5753.47 | 4267.53 | 287.2% | 1777.86 | 6015.49 | 4237.63 | 238.4% | 161047.44 | 141813.6 | -19233.84 | -11.94% | 146.27 | 219.5 | 73.23 | 50.06% | 2020-10-05 01:00
Mississauga | 2020 | 419670 | 25 CAPSTON ROAD - PEEL CHILDRE | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 9904.58 | 149586.29 | 139681.71 | 1410% | 7501.58 | 43694.54 | 36192.96 | 482.5% | 0 | 61244.35 | 61244.35 |  | 2403 | 6160.5 | 3757.5 | 156.4% | 0 | 38137.9 | 38137.9 |  | 435.04 | 510.5 | 75.46 | 17.35% | 2020-01-23 01:00
Mississauga | 2019 | 419750 | POLE REPLACEMETS - BATCH #1 (1 POLE) | 99 | COMPLETE | Labour est. over | Cont Est Over | BOM not accurate | Antonakos, Tony | No | Handy, James | Paul Murphy | 17757.09 | 7196.8 | -10560.29 | -59.47% | 10340.15 | 5468.8 | -4871.35 | -47.11% | 1570.18 | 0 | -1570.18 | -100% | 1670.4 | 1728 | 57.6 | 3.448% | 4176.36 | 0 | -4176.36 | -100% | 109.48 | 76.5 | -32.98 | -30.12% | 2019-05-07
Mississauga | 2019 | 419784 | Mississauga Rd - Rogers Make Ready | 99 | COMPLETE | Scope – Const | BOM not used | Labour est. under | Lacombe, Joel | No | Gonzales, Leonard | Mark Bobanovic | 11575.77 | 7520.68 | -4055.09 | -35.03% | 1880.31 | 448.96 | -1431.35 | -76.12% | 1894.48 | 0 | -1894.48 | -100% | 0 | 0 | 0 |  | 7800.98 | 7071.72 | -729.26 | -9.348% | 17 | 8 | -9 | -52.94% | 2019-01-09 01:00
Mississauga | 2021 | 420603 | 848 BURNHAMTHORPE RD WEST - TX UPGRADE | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Bharosi, Mohindra | Peter Costantini | 26624.78 | 5467.57 | -21157.21 | -79.46% | 8221.54 | 2708.57 | -5512.97 | -67.06% | 17702.23 | 0 | -17702.23 | -100% | 701.01 | 0 | -701.01 | -100% | 0 | 2759 | 2759 |  | 92.5533 | 33 | -59.5533 | -64.34% | 2020-01-16 01:00
Mississauga | 2022 | 420638 | 2679 SLOUGH ST. MISSISSAUGA ON | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Central North ICI | Macdougall, Stephen | 0 | 1824.67 | 1824.67 |  | 0 | 1639.97 | 1639.97 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-16 01:00
Mississauga | 2020 | 420646 | 3110 Convair Dr - TEMP SERV | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Rob Elliot | 14937.45 | 11582.35 | -3355.1 | -22.46% | 8647.01 | 5107.54 | -3539.47 | -40.93% | 4164.94 | 4272.72 | 107.78 | 2.588% | 2125.5 | 1104 | -1021.5 | -48.06% | 0 | 1098.09 | 1098.09 |  | 59.46 | 57 | -2.46 | -4.137% | 2020-01-16 01:00
Mississauga | 2019 | 420831 | 5150 DIXIE RD - AFFINIA CANADA | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Macasaet, Ricardo | Macdougall, Stephen | 147257.36 | 94592.77 | -52664.59 | -35.76% | 9908.47 | 36014.55 | 26106.08 | 263.5% | 57242.05 | 37109.26 | -20132.79 | -35.17% | 72669.4 | 5407 | -67262.4 | -92.56% | 300 | 15433.77 | 15133.77 | 5045% | 619.93 | 392.75 | -227.18 | -36.65% | 2019-05-04 01:00
Mississauga | 2021 | 420890 | QEW - PREMIUM WAY PHASE 2 | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-01 01:00
Mississauga | 2019 | 420902 | 1331 MATHESON BLVD E - SERVICE | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Bharosi, Mohindra | Macdougall, Stephen | 17040.71 | 16308.58 | -732.13 | -4.296% | 11957.63 | 11507.07 | -450.56 | -3.768% | 2365.73 | 836.71 | -1529.02 | -64.63% | 1445.35 | 1417 | -28.35 | -1.961% | 1272 | 2547.8 | 1275.8 | 100.3% | 127.98 | 138 | 10.02 | 7.829% | 2019-11-01 01:00
Mississauga | 2019 | 420911 | 1840 Courtney Park Dr. | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Bharosi, Mohindra | Macdougall, Stephen | 67114.42 | 54837.18 | -12277.24 | -18.29% | 19678.55 | 11551.81 | -8126.74 | -41.3% | 42793.98 | 37025.99 | -5767.99 | -13.48% | 2913.89 | 793 | -2120.89 | -72.79% | 1728 | 5466.38 | 3738.38 | 216.3% | 232.72 | 125 | -107.72 | -46.29% | 2019-07-10 01:00
Mississauga | 2019 | 420961 | QEW - PREMIUM WAY FROM DICKSON | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Watters, Maxwell | Mark Bobanovic | 157929.83 | 110860.51 | -47069.32 | -29.8% | 7810.51 | 13452.99 | 5642.48 | 72.24% | 11302 | 24706.79 | 13404.79 | 118.6% | 76.2 | 879 | 802.8 | 1054% | 138741.12 | 71821.73 | -66919.39 | -48.23% | 311.27 | 39 | -272.27 | -87.47% | 2019-10-07 01:00
Mississauga | 2019 | 421008 | EGLINTON AND CREDIT VIEW - VAN HORNE OUTDOOR BILLBOARD | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 45628.94 | 46160.7 | 531.76 | 1.165% | 7323.1 | 8368.83 | 1045.73 | 14.28% | 4866.35 | 3625.46 | -1240.89 | -25.5% | 1219.12 | 1030 | -189.12 | -15.51% | 32220.37 | 33136.41 | 916.04 | 2.843% | 81.64 | 16 | -65.64 | -80.4% | 2019-07-24 01:00
Mississauga | 2020 | 421139 | HOLBURNE SINGLE PHASE OH REBUI | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | No | Alectra Utilities | Paul Murphy | 495015.27 | 598931.55 | 103916.28 | 20.99% | 256229.87 | 265247.65 | 9017.78 | 3.519% | 142147.42 | 123086.34 | -19061.08 | -13.41% | 70240.53 | 160134.27 | 89893.74 | 128% | 26397.45 | 50463.29 | 24065.84 | 91.17% | 2091.87 | 3214 | 1122.13 | 53.64% | 2020-12-22 01:00
Mississauga | 2019 | 421147 | 6500 TOMKEN ROAD - REYNOLDS PRODUCTS 1200AMP SERV | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Mandic, Goran | No | Macasaet, Ricardo | Macdougall, Stephen | 97344.68 | 69521 | -27823.68 | -28.58% | 35642.19 | 22262 | -13380.19 | -37.54% | 46533.02 | 42987 | -3546.02 | -7.62% | 5608.77 | 2670 | -2938.77 | -52.4% | 9560.7 | 1602 | -7958.7 | -83.24% | 413.72 | 261 | -152.72 | -36.91% | 2019-05-28
Mississauga | 2019 | 421420 | 6415 NORTHAM DRIVE - Mitsubishi Canada Aerospace | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Macasaet, Ricardo | Macdougall, Stephen | 1118984.62 | 95277.72 | -1023706.9 | -91.49% | 1011105.63 | 28659.67 | -982445.96 | -97.17% | 54251.29 | 48672.98 | -5578.31 | -10.28% | 38783.66 | 4549 | -34234.66 | -88.27% | 500 | 13047.07 | 12547.07 | 2509% | 449.31 | 318 | -131.31 | -29.22% | 2019-08-20 01:00
Mississauga | 2019 | 421964 | 2555 ROYAL WINDSOR DRIVE, K+S | 99 | COMPLETE | Converted Project |  |  | Sidhu, Paul | No | Zaghloul, Sam | Macdougall, Stephen | 104463.73 | 78027.24 | -26436.49 | -25.31% | 45181.54 | 24679.67 | -20501.87 | -45.38% | 42897.38 | 40660.69 | -2236.69 | -5.214% | 7504.51 | 2903.5 | -4601.01 | -61.31% | 8880.3 | 9783.38 | 903.08 | 10.17% | 467.37 | 224.5 | -242.87 | -51.97% | 2019-10-24 01:00
Mississauga | 2019 | 421999 | PSN MAKE READY -NINTH LINE (DEEPWOODS HEIGHTS TO JANICE DR) | 99 | COMPLETE | N/A | N/A | N/A |  | No | Gonzales, Leonard | Weaver, Thomas | 0 | 18230.94 | 18230.94 |  | 0 | 10837.21 | 10837.21 |  | 0 | 1585.73 | 1585.73 |  | 0 | 3598 | 3598 |  | 0 | 2210 | 2210 |  | 0 | 128 | 128 |  | 2019-02-01 01:00
Mississauga | 2020 | 422351 | 5250 SOLAR DRIVE - WAREHOUSE D | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 194500.33 | 170353.87 | -24146.46 | -12.41% | 55391.89 | 33239.88 | -22152.01 | -39.99% | 82950.19 | 80286.25 | -2663.94 | -3.211% | 9020.73 | 4399.5 | -4621.23 | -51.23% | 42120 | 52428.24 | 10308.24 | 24.47% | 424.87 | 296.5 | -128.37 | -30.21% | 2020-11-20 01:00
Mississauga | 2019 | 422756 | EBONY AVE - HOUSE SERVICES | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Ricci, Leonardo | Paul Tremblay | 31718.33 | 27424.03 | -4294.3 | -13.54% | 7273.83 | 6867.49 | -406.34 | -5.586% | 2489.36 | 1063.1 | -1426.26 | -57.29% | 1223.46 | 1204 | -19.46 | -1.591% | 20731.68 | 812.88 | -19918.8 | -96.08% | 71.62 | 72.5 | 0.88 | 1.229% | 2019-11-20 01:00
Mississauga | 2020 | 422810 | TANU CONDOS - TEMPORARY POLE L | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Mark Bobanovic | 632819.2 | 420441.63 | -212377.57 | -33.56% | 12999.41 | 56704.1 | 43704.69 | 336.2% | 95432.99 | 90384.35 | -5048.64 | -5.29% | 68.4 | 0 | -68.4 | -100% | 524318.4 | 273353.18 | -250965.22 | -47.87% | 55.45 | 39.5 | -15.95 | -28.76% | 2020-01-03 01:00
Mississauga | 2019 | 422836 | ROGERS MAKE READY -MISSISSAUGA RD S/O EGLINTON | 99 | COMPLETE | Labour est. over | Cont Est Over | BOM not accurate | O'Gay, Brian | No | Gonzales, Leonard | Rob Elliot | 57156.14 | 26754.32 | -30401.82 | -53.19% | 35372.33 | 13144 | -22228.33 | -62.84% | 5669.52 | 7536.42 | 1866.9 | 32.93% | 5016.07 | 2622 | -2394.07 | -47.73% | 11098.22 | 3451.9 | -7646.32 | -68.9% | 297.47 | 163.5 | -133.97 | -45.04% | 2019-02-16 01:00
Mississauga | 2019 | 423118 | Falconer Dr & Matlock - Bell Make Ready | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Mark Bobanovic | 3020.14 | 3840.48 | 820.34 | 27.16% | 2855.93 | 1506.24 | -1349.69 | -47.26% | 58.48 | 0 | -58.48 | -100% | 105.73 | 414 | 308.27 | 291.6% | 0 | 0 | 0 |  | 24.68 | 25 | 0.32 | 1.297% | 2019-02-13 01:00
Mississauga | 2019 | 423724 | SG 1549 CREDITVIEW RD. N OF SIR MONTY'S DR. | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | No | Cudzilo, Tomasz | Macdougall, Stephen | 146163.38 | 130726.26 | -15437.12 | -10.56% | 73513.77 | 42816.65 | -30697.12 | -41.76% | 8585.63 | 50719.1 | 42133.47 | 490.7% | 8998.91 | 5499 | -3499.91 | -38.89% | 55065.07 | 31691.51 | -23373.56 | -42.45% | 832.55 | 505 | -327.55 | -39.34% | 2019-08-28 01:00
Mississauga | 2020 | 423986 | 3045 MAVIS ROAD - MIXED USE RE | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 73528.24 | 90898.31 | 17370.07 | 23.62% | 20634.28 | 25645.53 | 5011.25 | 24.29% | 32423.9 | 38132.31 | 5708.41 | 17.61% | 4338.06 | 4070.73 | -267.33 | -6.162% | 16132 | 23049.74 | 6917.74 | 42.88% | 401.12 | 227 | -174.12 | -43.41% | 2020-12-17 01:00
Mississauga | 2020 | 424031 | POLE REPLACEMENT - EGLINTON AV E & 403 | 99 | COMPLETE | Engineering by-passed | N/A | N/A | Antonakos, Tony | No | Alectra Utilities | Weaver, Thomas | 0 | 428786 | 428786 |  | 0 | 184649 | 184649 |  | 0 | 78733 | 78733 |  | 0 | 27775 | 27775 |  | 0 | 137108 | 137108 |  | 0 | 1993.5 | 1993.5 |  | 2020-08-01 01:00
Mississauga | 2020 | 424111 | THE WAY TOWNS-2277 SOUTH MILLW | 99 | COMPLETE | Converted Project | N/A | N/A | Sidhu, Paul | No | Alectra Utilities | Peter Costantini | 116106.68 | 78960.57 | -37146.11 | -31.99% | 60499.72 | 21638.95 | -38860.77 | -64.23% | 41353.4 | 39666.95 | -1686.45 | -4.078% | 5073.56 | 3780.89 | -1292.67 | -25.48% | 9180 | 13873.78 | 4693.78 | 51.13% | 390.8 | 194 | -196.8 | -50.36% | 2020-10-08 01:00
Mississauga | 2019 | 424129 | BELL MAKE READY -DATSUN RD (Y54769) | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Lacombe, Joel | No | Gonzales, Leonard | Mark Bobanovic | 41288.44 | 33454.9 | -7833.54 | -18.97% | 4096.7 | 294.89 | -3801.81 | -92.8% | 5001.34 | 5242.31 | 240.97 | 4.818% | 0 | 0 | 0 |  | 32190.4 | 27917.7 | -4272.7 | -13.27% | 35.7 | 4 | -31.7 | -88.8% | 2019-05-01 01:00
Mississauga | 2019 | 424188 | Winston Churchill Blv Make Ready | 99 | COMPLETE | Estimate incorrect | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Rob Elliot | 7203.08 | 0 | -7203.08 | -100% | 6119.26 | 0 | -6119.26 | -100% | 650.99 | 0 | -650.99 | -100% | 432.83 | 0 | -432.83 | -100% | 0 | 0 | 0 |  | 48.85 | 4 | -44.85 | -91.81% | 2019-02-05 01:00
Mississauga | 2019 | 424874 | POLE RELOCATION - WCH BLVD | 99 | COMPLETE | N/A | N/A | N/A | Truong, Jimmy | No | Truong, Jimmy | Paul Murphy | 8047.16 | 8491.43 | 444.27 | 5.521% | 2652.88 | 4389.43 | 1736.55 | 65.46% | 2218.66 | 1880 | -338.66 | -15.26% | 379.5 | 792 | 412.5 | 108.7% | 2796.12 | 1430 | -1366.12 | -48.86% | 29.99 | 53.5 | 23.51 | 78.39% | 2019-03-30 01:00
Mississauga | 2019 | 424882 | INDIAN RD & MADIGAN'S LANE - Make Ready | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Mark Bobanovic | 58945.25 | 171129.94 | 112184.69 | 190.3% | 15223.52 | 10880.51 | -4343.01 | -28.53% | 31983.91 | 27485.25 | -4498.66 | -14.07% | 3277.37 | 0 | -3277.37 | -100% | 8460.45 | 132643.01 | 124182.56 | 1468% | 51.28 | 4 | -47.28 | -92.2% | 2019-03-01 01:00
Mississauga | 2019 | 425050 | SG1802- 533 MIDDLEBURY DR | 99 | COMPLETE | Labour est. under | BOM not accurate | Cont Est Over | Sidhu, Paul | No | Cudzilo, Tomasz | Glenn Guile | 36573.49 | 51132.17 | 14558.68 | 39.81% | 28715.96 | 18014.18 | -10701.78 | -37.27% | 4016.11 | 7039.65 | 3023.54 | 75.29% | 1681.42 | 2029.5 | 348.08 | 20.7% | 2160 | 24048.84 | 21888.84 | 1013% | 330.11 | 192.5 | -137.61 | -41.69% | 2019-05-15
Mississauga | 2019 | 425164 | SG1650 & SG1237- 2875 THOMAS STREET | 99 | COMPLETE | BOM not accurate | Cont Est Under | Labour est. under | Sidhu, Paul | No | Cudzilo, Tomasz | Glenn Guile | 51585.97 | 154766.66 | 103180.69 | 200% | 29911.76 | 41643.41 | 11731.65 | 39.22% | 17300.52 | 31041.63 | 13741.11 | 79.43% | 2213.69 | 6772 | 4558.31 | 205.9% | 2160 | 75309.62 | 73149.62 | 3387% | 342.66 | 436.5 | 93.84 | 27.39% | 2019-04-26 01:00
Mississauga | 2022 | 425236 | 2019 CABLE INJECTION PROGRAM (PARENT WO) | 99 | CANCELLED | N/A |  |  | Antonakos, Tony | No | Antonakos, Tony -x | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-08-06 15:17
Mississauga | 2019 | 425404 | SG1248- 334 ADMIRAL BLVD | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | No | Cudzilo, Tomasz | Paul Tremblay | 39718.67 | 133045.79 | 93327.12 | 235% | 23810.18 | 63983.42 | 40173.24 | 168.7% | 8373.95 | 12285.87 | 3911.92 | 46.72% | 4294.54 | 3369 | -925.54 | -21.55% | 3240 | 53407.5 | 50167.5 | 1548% | 477.46 | 285.5 | -191.96 | -40.2% | 2019-08-06 15:17
Mississauga | 2020 | 425439 | ORLANDO 6065 MILLCREEK INDUSTR | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 115924.38 | 105954.4 | -9969.98 | -8.6% | 9205.6 | 30382.36 | 21176.76 | 230% | 52135.88 | 39565.73 | -12570.15 | -24.11% | 38054.31 | 4163 | -33891.31 | -89.06% | 0 | 31843.31 | 31843.31 |  | 455.18 | 245 | -210.18 | -46.18% | 2020-05-11
Mississauga | 2020 | 425463 | 1796 MATTAWA AVE | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 35993.34 | 0 | -35993.34 | -100% | 26151 | 0 | -26151 | -100% | 5251.9 | 0 | -5251.9 | -100% | 2302.44 | 0 | -2302.44 | -100% | 2288 | 0 | -2288 | -100% | 240.8 | 69 | -171.8 | -71.35% | 2020-02-04 01:00
Mississauga | 2020 | 425640 | 350 MADILL BLVD - INDUSTRIAL SPEC. BLDG | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 107344.81 | 105538.05 | -1806.76 | -1.683% | 38879.38 | 23429.05 | -15450.33 | -39.74% | 50551.57 | 40116.78 | -10434.79 | -20.64% | 6033.86 | 2996.8 | -3037.06 | -50.33% | 11880 | 38995.42 | 27115.42 | 228.2% | 346.5 | 157 | -189.5 | -54.69% | 2020-02-04 01:00
Mississauga | 2019 | 425703 | GUYING RELOCATIONS - ERIN MILLS PKWY REGION OF PEEL | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Truong, Jimmy | Paul Murphy | 23444.61 | 21264.08 | -2180.53 | -9.301% | 9254.63 | 13240.62 | 3985.99 | 43.07% | 5108.72 | 4306.96 | -801.76 | -15.69% | 1524.02 | 3716.5 | 2192.48 | 143.9% | 7557.24 | 0 | -7557.24 | -100% | 104.04 | 126.5 | 22.46 | 21.59% | 2019-10-11 01:00
Mississauga | 2020 | 425720 | ORLANDO 6135 MILLCREEK INDUSTRIAL BLDG | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 0 | 126070.78 | 126070.78 |  | 0 | 39836.95 | 39836.95 |  | 0 | 54105.95 | 54105.95 |  | 0 | 5659 | 5659 |  | 0 | 26468.88 | 26468.88 |  | 367.23 | 355 | -12.23 | -3.33% | 2020-08-05 01:00
Mississauga | 2020 | 425754 | ROGERS MAKE READY - OLD MALTON VILLAGE - HULL & STUDLEY (MP18-0332) | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Mark Bobanovic | 31206.08 | 11845.72 | -19360.36 | -62.04% | 12744.64 | 0 | -12744.64 | -100% | 1122.29 | 131.05 | -991.24 | -88.32% | 737.73 | 0 | -737.73 | -100% | 16601.42 | 11714.67 | -4886.75 | -29.44% | 108.94 | 0 | -108.94 | -100% | 2020-06-29 01:00
Mississauga | 2019 | 425797 | MALTON GO STATION - RAISE NEUTURAL CONDUCTORS | 99 | COMPLETE | N/A | N/A | N/A |  | No | Watters, Maxwell | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-10 01:00
Mississauga | 2019 | 426044 | 7550 TORBRAM ROAD - TEMPORARY POLE LINE | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Kafel, Krzysztof | No | Truong, Jimmy | Paul Murphy | 44043.42 | 31836.36 | -12207.06 | -27.72% | 24454.13 | 18113.72 | -6340.41 | -25.93% | 9857.36 | 9111.64 | -745.72 | -7.565% | 4787.69 | 4611 | -176.69 | -3.691% | 4944.24 | 0 | -4944.24 | -100% | 257.1 | 202 | -55.1 | -21.43% | 2019-05-14
Mississauga | 2020 | 426159 | MTO CONT. NO. 2019-2014, HWY 4 | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 137926.88 | 75696.69 | -62230.19 | -45.12% | 80252.21 | 32243.65 | -48008.56 | -59.82% | 34931.04 | 31296.04 | -3635 | -10.41% | 19623.51 | 8775 | -10848.51 | -55.28% | 3120.12 | 3382 | 261.88 | 8.393% | 895.28 | 324.5 | -570.78 | -63.75% | 2020-05-07
Mississauga | 2020 | 426255 | 1850 MATHESON BLVD - ADDTIONAL | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 203195.34 | 200343.52 | -2851.82 | -1.403% | 54930.49 | 47721.1 | -7209.39 | -13.12% | 81901.19 | 81162.78 | -738.41 | -0.9016% | 12075.61 | 7822.23 | -4253.38 | -35.22% | 48919.68 | 63288.41 | 14368.73 | 29.37% | 571.55 | 535.5 | -36.05 | -6.307% | 2020-01-07 01:00
Mississauga | 2021 | 426263 | HWY 410 AT DERRY ROAD - HWY CR | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Paul Murphy | 901631.93 | 845129.42 | -56502.51 | -6.267% | 481642.63 | 161439.43 | -320203.2 | -66.48% | 100032.89 | 102385.23 | 2352.34 | 2.352% | 106861.61 | 22673.1 | -84188.51 | -78.78% | 213094.8 | 558611.31 | 345516.51 | 162.1% | 543.34 | 509.75 | -33.59 | -6.182% | 2021-01-18 01:00
Mississauga | 2021 | 426351 | CITY CENTRE NORTH MS - HV2 SWI | 99 | CANCELLED | N/A |  |  | Houston, Andrew | No | Central South | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-05 01:00
Mississauga | 2019 | 426618 | REGION WATERMAIN - BELL PEDEST | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Truong, Jimmy | Macdougall, Stephen | 49187.95 | 54440.69 | 5252.74 | 10.68% | 9402.15 | 8116.47 | -1285.68 | -13.67% | 1441.45 | 825.24 | -616.21 | -42.75% | 1592.52 | 723 | -869.52 | -54.6% | 36751.83 | 44775.98 | 8024.15 | 21.83% | 98.07 | 0 | -98.07 | -100% | 2019-11-05 01:00
Mississauga | 2021 | 426626 | LINCOLN M. ALEXANDER SECONDARY SCHOOL | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Costantini, Peter | No | Huo, Lisa | Peter Costantini | 161903.63 | 123634.57 | -38269.06 | -23.64% | 65819.65 | 30040.34 | -35779.31 | -54.36% | 47763.39 | 47964.82 | 201.43 | 0.4217% | 7280.59 | 5558 | -1722.59 | -23.66% | 41040 | 40071.41 | -968.59 | -2.36% | 380.47 | 278 | -102.47 | -26.93% | 2021-09-27 01:00
Mississauga | 2022 | 426634 | 2022 PR - 9WP - GREENWAY POLE LINE REBUILD | 99 | COMPLETE | Labour est. over | Cont Est Over | Material Under Estimated | Lucic, Marko | Yes | Tempra, Troylan | Mark Bobanovic | 192786.17 | 164657.16 | -28129.01 | -14.59% | 35871.62 | 25101.04 | -10770.58 | -30.03% | 25019.55 | 29480.44 | 4460.89 | 17.83% | 0 | 0 | 0 |  | 131895 | 110075.68 | -21819.32 | -16.54% | 44 | 2 | -42 | -95.45% | 2022-12-22 01:00
Mississauga | 2020 | 426677 | OPP MODERNIZATION PH2 PROJECT | 99 | COMPLETE | Converted Project |  |  | MacDougall, Stephen | No | Alectra Utilities | Macdougall, Stephen | 209806.09 | 195471.37 | -14334.72 | -6.832% | 51276.97 | 36323.08 | -14953.89 | -29.16% | 43500.1 | 40739.94 | -2760.16 | -6.345% | 5301.02 | 2312 | -2989.02 | -56.39% | 109728 | 116096.35 | 6368.35 | 5.804% | 336.36 | 244 | -92.36 | -27.46% | 2020-04-30
Mississauga | 2019 | 426693 | FALCONER DRIVE USED POLE INSTA | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Watters, Maxwell | Mark Bobanovic | 0 | 8245.44 | 8245.44 |  | 0 | 1069.89 | 1069.89 |  | 0 | 679.75 | 679.75 |  | 0 | 0 | 0 |  | 0 | 6449.95 | 6449.95 |  | 0 | 0 | 0 |  | 2019-08-02 01:00
Mississauga | 2019 | 426731 | VAN HORNE OUTDOOR BILLBOARD-CP | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 30163.01 | 24380.9 | -5782.11 | -19.17% | 5999.35 | 4377.74 | -1621.61 | -27.03% | 950.86 | 354.88 | -595.98 | -62.68% | 213.12 | 288 | 74.88 | 35.14% | 22999.68 | 19360.28 | -3639.4 | -15.82% | 15.28 | 19 | 3.72 | 24.35% | 2019-12-15 01:00
Mississauga | 2020 | 426749 | VAN HORNE OUTDOOR BILLBOARD-CP | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 20232.62 | 15003.5 | -5229.12 | -25.84% | 5928.33 | 2812.95 | -3115.38 | -52.55% | 632.82 | 0 | -632.82 | -100% | 751.95 | 78 | -673.95 | -89.63% | 12919.52 | 12112.55 | -806.97 | -6.246% | 31.82 | 8 | -23.82 | -74.86% | 2020-02-12 01:00
Mississauga | 2019 | 426757 | KIPPER AVE OH REBUILD | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | No | Alectra Utilities | Paul Murphy | 144062.2 | 126300.06 | -17762.14 | -12.33% | 76860.57 | 65691.24 | -11169.33 | -14.53% | 24732.91 | 24156.14 | -576.77 | -2.332% | 19680.72 | 28103.21 | 8422.49 | 42.8% | 22788 | 8349.47 | -14438.53 | -63.36% | 716.79 | 765.5 | 48.71 | 6.796% | 2020-01-01 01:00
Mississauga | 2019 | 426802 | NPL CANADA 400A 1PH SERVICE | 99 | COMPLETE | Engineering by-passed |  |  | Mandic, Goran | No | Macasaet, Ricardo | Macdougall, Stephen | 0 | 5910 | 5910 |  | 0 | 4924 | 4924 |  | 0 | 0 | 0 |  | 0 | 452 | 452 |  | 0 | 534 | 534 |  | 0 | 0 | 0 |  | 2019-10-22 01:00
Mississauga | 2020 | 426888 | ROGERS MAKE READY - 2209 STANFIELD RD | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Alectra Utilities | Weaver, Thomas | 0 | 647.28 | 647.28 |  | 0 | 647.28 | 647.28 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-05 01:00
Mississauga | 2019 | 426896 | BELL MAKE READY -2109 PREMIUM WAY | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Mark Bobanovic | 18633.42 | 1971.57 | -16661.85 | -89.42% | 13495.73 | 1294.57 | -12201.16 | -90.41% | 1041.21 | 677 | -364.21 | -34.98% | 2155.38 | 0 | -2155.38 | -100% | 1941.1 | 0 | -1941.1 | -100% | 65.22 | 0 | -65.22 | -100% | 2019-10-05 01:00
Mississauga | 2022 | 426917 | BELL MAKE READY -LAKESHORE RD W & LORNE PARK | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Gonzales, Leonard | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-23 01:00
Mississauga | 2021 | 426984 | 3465 PLATINUM DRIVE - ERIN MILLS MINUK (BUILDING J) | 99 | COMPLETE | Vehicle Under Estimated | Labour est. over | BOM not accurate | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 329610.72 | 252325.19 | -77285.53 | -23.45% | 98427.32 | 43466.21 | -54961.11 | -55.84% | 159471.46 | 138086.76 | -21384.7 | -13.41% | 7991.94 | 10335.24 | 2343.3 | 29.32% | 63720 | 60436.98 | -3283.02 | -5.152% | 552.81 | 433.5 | -119.31 | -21.58% | 2021-03-23 01:00
Mississauga | 2021 | 426992 | 3525 PLATINUM DRIVE - ERIN MILLS MINUK (BUILDING K) | 99 | COMPLETE | Labour est. over | Material Under Estimated | Cont Est Under | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 37108.91 | 27801.62 | -9307.29 | -25.08% | 28908.64 | 12562.7 | -16345.94 | -56.54% | 3896.59 | 8211.12 | 4314.53 | 110.7% | 2143.68 | 1240 | -903.68 | -42.16% | 2160 | 5787.8 | 3627.8 | 168% | 194.88 | 80 | -114.88 | -58.95% | 2021-03-23 01:00
Mississauga | 2021 | 427004 | 3874 EGLINTON AVE W - ERIN MILLS MINUK (BUILDING G) | 99 | COMPLETE | Labour est. over | Material Under Estimated | Cont Est Under | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 52419.98 | 43367.97 | -9052.01 | -17.27% | 34038.12 | 10927.15 | -23110.97 | -67.9% | 13798.34 | 24038.7 | 10240.36 | 74.21% | 2423.52 | 1164 | -1259.52 | -51.97% | 2160 | 7238.12 | 5078.12 | 235.1% | 148.32 | 68 | -80.32 | -54.15% | 2021-03-23 01:00
Mississauga | 2021 | 427012 | 3910 EGLINTON AVE W - ERIN MILLS MINUK (BUILDING D) | 99 | COMPLETE | Cont Est Under | Vehicle Under Estimated | BOM not accurate | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 49449.28 | 75055.86 | 25606.58 | 51.78% | 34649.25 | 32220.53 | -2428.72 | -7.009% | 10166.35 | 24500.71 | 14334.36 | 141% | 2473.68 | 7005.14 | 4531.46 | 183.2% | 2160 | 11329.48 | 9169.48 | 424.5% | 152.88 | 300 | 147.12 | 96.23% | 2021-03-23 01:00
Mississauga | 2019 | 427063 | BLANEFIELD RD POLE REPLACEMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Carter, Gordon | No | Tempra, Troylan | Paul Murphy | 124047.78 | 133926.2 | 9878.42 | 7.963% | 58841.96 | 77810.53 | 18968.57 | 32.24% | 22542.79 | 20179.58 | -2363.21 | -10.48% | 13765.47 | 27117 | 13351.53 | 96.99% | 0 | 8819.09 | 8819.09 |  | 646.83 | 567 | -79.83 | -12.34% | 2019-10-23 01:00
Mississauga | 2019 | 427080 | O/H RELOCATION - 1570 BOTHWELL AVE | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Rob Elliot | 3789.37 | 1430.57 | -2358.8 | -62.25% | 1772.96 | 817.32 | -955.64 | -53.9% | 258.49 | 129.25 | -129.24 | -50% | 365.8 | 484 | 118.2 | 32.31% | 1392.12 | 0 | -1392.12 | -100% | 4.38 | 0 | -4.38 | -100% | 2019-04-24 01:00
Mississauga | 2019 | 427143 | SG 1468-3170 FIFTH LINE | 99 | COMPLETE | Converted Project |  |  | Sidhu, Paul | No | Cudzilo, Tomasz | Glenn Guile | 57676.61 | 40727.4 | -16949.21 | -29.39% | 30901.85 | 14107.26 | -16794.59 | -54.35% | 4919.46 | 6778.93 | 1859.47 | 37.8% | 1791.06 | 1641 | -150.06 | -8.378% | 20064.24 | 18200.21 | -1864.03 | -9.29% | 356.34 | 176 | -180.34 | -50.61% | 2019-05-31
Mississauga | 2020 | 427151 | HEARTLAND CHURCH / 1100 CANADI | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 129753.9 | 106747.74 | -23006.16 | -17.73% | 41892.16 | 26170.62 | -15721.54 | -37.53% | 25831.29 | 27014.48 | 1183.19 | 4.58% | 7457.49 | 3996 | -3461.49 | -46.42% | 54572.96 | 49566.64 | -5006.32 | -9.174% | 326.76 | 222 | -104.76 | -32.06% | 2020-07-15 01:00
Mississauga | 2019 | 427160 | 3480 MORNING STAR DR - WESTWOO | 99 | COMPLETE | Converted Project |  |  | Mandic, Goran | No | Bharosi, Mohindra | Macdougall, Stephen | 30668.5 | 17092.03 | -13576.47 | -44.27% | 20265.28 | 6532.71 | -13732.57 | -67.76% | 6693.9 | 4068.71 | -2625.19 | -39.22% | 2198.7 | 840 | -1358.7 | -61.8% | 1510.62 | 5650.61 | 4139.99 | 274.1% | 240.13 | 80 | -160.13 | -66.68% | 2019-08-19 01:00
Mississauga | 2021 | 427258 | AQUITANE M.S. T60 CONTROLLER U | 99 | COMPLETE | Converted Project |  |  |  | No | Zaghloul, Sam | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-02 01:00
Mississauga | 2019 | 427346 | SG1465 REMOVAL - 3079 FIFTH LINE WEST | 99 | COMPLETE | Converted Project |  |  | Sidhu, Paul | No | Cudzilo, Tomasz | Glenn Guile | 46246.42 | 69224.78 | 22978.36 | 49.69% | 30020.45 | 22826.22 | -7194.23 | -23.96% | 6357.9 | 9178.89 | 2820.99 | 44.37% | 1683.83 | 3483.5 | 1799.67 | 106.9% | 8184.24 | 33736.17 | 25551.93 | 312.2% | 346.38 | 271.5 | -74.88 | -21.62% | 2019-06-05
Mississauga | 2019 | 427557 | Queen St S - Bell Make Ready (Y16415) | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Rob Elliot | 6568.96 | 4606.64 | -1962.32 | -29.87% | 4819.68 | 2312.3 | -2507.38 | -52.02% | 14.21 | 97.34 | 83.13 | 585% | 1180 | 552 | -628 | -53.22% | 555.07 | 1645 | 1089.93 | 196.4% | 16.8 | 16 | -0.8 | -4.762% | 2019-08-23 01:00
Mississauga | 2022 | 427602 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE 1 DIXIE ROAD | 99 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Under Estimated | Watters, Maxwell | No | Watters, Maxwell | Matthew Beach | 3184986.34 | 2808949.12 | -376037.22 | -11.81% | 1330175.03 | 1067035.02 | -263140.01 | -19.78% | 582299.48 | 522332.88 | -59966.6 | -10.3% | 283312.83 | 441442.24 | 158129.41 | 55.81% | 989199 | 775578.88 | -213620.12 | -21.6% | 12792.46 | 11320 | -1472.46 | -11.51% | 2022-11-18 01:00
Mississauga | 2022 | 427611 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE 2 HAIG BOULEVARD | 99 | COMPLETE | Labour est. over |  |  | Watters, Maxwell | No | Watters, Maxwell | Matthew Beach | 1889101.43 | 1613379.17 | -275722.26 | -14.6% | 876065.63 | 609115.09 | -266950.54 | -30.47% | 305739.41 | 318437.05 | 12697.64 | 4.153% | 233213.39 | 229639 | -3574.39 | -1.533% | 474083 | 451892.23 | -22190.77 | -4.681% | 6784.04 | 6531 | -253.04 | -3.73% | 2022-11-18 01:00
Mississauga | 2019 | 427670 | DUNDAS ST W E-O DUNWIN DR - REPLACE LT31135 | 99 | CANCELLED | N/A | N/A | N/A | Carter, Gordon | No | Tempra, Troylan | Paul Murphy | 51333.75 | 0 | -51333.75 | -100% | 20890.34 | 0 | -20890.34 | -100% | 25271.31 | 0 | -25271.31 | -100% | 5172.1 | 0 | -5172.1 | -100% | 0 | 0 | 0 |  | 229.09 | 0 | -229.09 | -100% | 2019-11-24 01:00
Mississauga | 2019 | 427696 | SG LT31039 - SHERIDAN PARK DR W-O HOMELANDS | 99 | CANCELLED | N/A | N/A | N/A | Carter, Gordon | No | Tempra, Troylan | Paul Murphy | 39120.19 | 0 | -39120.19 | -100% | 11023.33 | 0 | -11023.33 | -100% | 25869.56 | 0 | -25869.56 | -100% | 2227.3 | 0 | -2227.3 | -100% | 0 | 0 | 0 |  | 121.79 | 0 | -121.79 | -100% | 2019-11-24 01:00
Mississauga | 2019 | 427733 | 6685 CENTURY AVE - MOVATI ATHL | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Bharosi, Mohindra | Macdougall, Stephen | 66449.29 | 68500.19 | 2050.9 | 3.086% | 26069.17 | 25596.54 | -472.63 | -1.813% | 36218.73 | 37469.79 | 1251.06 | 3.454% | 2865.39 | 2552.5 | -312.89 | -10.92% | 1296 | 2881.36 | 1585.36 | 122.3% | 302.5 | 222.5 | -80 | -26.45% | 2019-11-24 01:00
Mississauga | 2022 | 427741 | POLE REPLACEMETS - PETRIE WAY REBUILD | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | Yes | Matai, Ihssan (Sam) | Paul Murphy | 333711.56 | 348905.07 | 15193.51 | 4.553% | 212376.88 | 172301.42 | -40075.46 | -18.87% | 46362.42 | 45257.87 | -1104.55 | -2.382% | 42071.14 | 101141.33 | 59070.19 | 140.4% | 32901.12 | 30204.45 | -2696.67 | -8.196% | 1656.22 | 1938.5 | 282.28 | 17.04% | 2022-02-11 01:00
Mississauga | 2020 | 427784 | 4655 METCALFE AVE - ERIN SQUAR | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-30 01:00
Mississauga | 2021 | 427792 | 4675 METCALFE AVE - ERIN SQUARE | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 372359.18 | 392750.7 | 20391.52 | 5.476% | 63465.43 | 73519.87 | 10054.44 | 15.84% | 86811.18 | 79775.69 | -7035.49 | -8.104% | 8082.57 | 8082.4 | -0.17 | -0.002103% | 214000 | 231321.74 | 17321.74 | 8.094% | 559.78 | 389.5 | -170.28 | -30.42% | 2021-08-30 01:00
Mississauga | 2021 | 427813 | 401 EXPANSION PROJECT FOR WCC AT CREDITVIEW ROAD & OLD CREDITVIEW ROAD | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-08
Mississauga | 2019 | 427872 | LT41053 - SWITCH REPLACEMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Antonakos, Tony | No | Matai, Ihssan (Sam) | Paul Murphy | 61107.75 | 71518.32 | 10410.57 | 17.04% | 21338.62 | 27728.09 | 6389.47 | 29.94% | 31231.53 | 30381.23 | -850.3 | -2.723% | 5837.6 | 12044 | 6206.4 | 106.3% | 2700 | 1365 | -1335 | -49.44% | 234.5 | 349.25 | 114.75 | 48.93% | 2019-06-08
Mississauga | 2019 | 427987 | TX1964 REPLACEMENT - OVERLOADED/LEAKING | 99 | COMPLETE | BOM not used | Labour est. over | Cont Est Over | Antonakos, Tony | No | Handy, James | Paul Murphy | 73116.39 | 46473.84 | -26642.55 | -36.44% | 21287.54 | 16975.89 | -4311.65 | -20.25% | 45351.58 | 23251.95 | -22099.63 | -48.73% | 4857.27 | 6246 | 1388.73 | 28.59% | 1620 | 0 | -1620 | -100% | 219.35 | 195 | -24.35 | -11.1% | 2019-05-18
Mississauga | 2022 | 428058 | 4100 PONYTRAIL DR - CHELSEA ON | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Jacinto, Gerardo | Weaver, Thomas | 0 | 1485.79 | 1485.79 |  | 0 | 1261.74 | 1261.74 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 224.05 | 224.05 |  | 0 | 6 | 6 |  | 2019-07-30 01:00
Mississauga | 2019 | 428082 | ROGERS MAKE READY - 181 KING ST. E. (MP19-0026 NN | 99 | COMPLETE | Converted Project |  |  | O'Gay, Brian | No | Gonzales, Leonard | Bourgeois, Craig | 10815.83 | 6447.4 | -4368.43 | -40.39% | 6152.3 | 2104.94 | -4047.36 | -65.79% | 427.44 | 0 | -427.44 | -100% | 524.99 | 428 | -96.99 | -18.47% | 3711.1 | 3914.46 | 203.36 | 5.48% | 51.82 | 15.5 | -36.32 | -70.09% | 2019-07-30 01:00
Mississauga | 2022 | 428171 | 80 THOMAS ST TOWNHOMES | 99 | COMPLETE | Labour est. over | Material Under Estimated | Vehicle Under Estimated | Gamboa, Henry | No | Ricci, Leonardo | Mark Bobanovic | 642396.61 | 497191.66 | -145204.95 | -22.6% | 238104.76 | 78779.73 | -159325.03 | -66.91% | 7824.47 | 19258.1 | 11433.63 | 146.1% | 5390.38 | 9866 | 4475.62 | 83.03% | 391077 | 389287.83 | -1789.17 | -0.4575% | 351.72 | 407.5 | 55.78 | 15.86% | 2022-11-22 01:00
Mississauga | 2021 | 428251 | FEEDER REPLACEMENT 45F1 TO 45F | 99 | COMPLETE | Under 10% | Labour est. under | Vehicle Under Estimated | Sidhu, Paul | Yes | Cudzilo, Tomasz | Antonio Mina | 420230.59 | 432585.98 | 12355.39 | 2.94% | 58712.97 | 92907.94 | 34194.97 | 58.24% | 0 | 2485.33 | 2485.33 |  | 1680 | 9900.55 | 8220.55 | 489.3% | 359837.62 | 327292.16 | -32545.46 | -9.044% | 530 | 369.5 | -160.5 | -30.28% | 2021-08-23 01:00
Mississauga | 2020 | 428357 | TROPHY FOODS 3MVA UPGRADE | 99 | COMPLETE | Labour est. over | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 80165.86 | 71556.89 | -8608.97 | -10.74% | 15812.97 | 8312.6 | -7500.37 | -47.43% | 61649.09 | 60022.29 | -1626.8 | -2.639% | 2703.8 | 1620 | -1083.8 | -40.08% | 0 | 1602 | 1602 |  | 96.81 | 89 | -7.81 | -8.067% | 2020-05-23
Mississauga | 2021 | 428373 | CITY CENTRE HV CABLE REPLACEMENTS | 99 | COMPLETE | Converted Project | N/A | N/A | Houston, Andrew | Yes | Zaghloul, Sam | Antonio Mina | 431229.39 | 644285.46 | 213056.07 | 49.41% | 148962.14 | 152360.6 | 3398.46 | 2.281% | 62971.25 | 66060.46 | 3089.21 | 4.906% | 30080 | 23075.42 | -7004.58 | -23.29% | 189216 | 401696.48 | 212480.48 | 112.3% | 780 | 894 | 114 | 14.62% | 2021-12-10 01:00
Mississauga | 2020 | 428390 | Rathburn Rd UG Rebuild - Phase 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | Yes | Alectra Utilities | Paul Tremblay | 761764.5 | 774214.55 | 12450.05 | 1.634% | 39549.39 | 98897.55 | 59348.16 | 150.1% | 4223.26 | 15781.09 | 11557.83 | 273.7% | 2760.85 | 6594.01 | 3833.16 | 138.8% | 715231 | 652941.9 | -62289.1 | -8.709% | 241.2 | 500 | 258.8 | 107.3% | 2020-09-11 01:00
Mississauga | 2022 | 428568 | CAWTHRA RD - ADDITIONAL GUYING AT P04172 | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | No | Matai, Ihssan (Sam) | Gregory Dunfield | 33697.75 | 20390.56 | -13307.19 | -39.49% | 19794.33 | 9556.43 | -10237.9 | -51.72% | 1951.9 | 1522.8 | -429.1 | -21.98% | 3451.52 | 1109.69 | -2341.83 | -67.85% | 8500 | 8201.64 | -298.36 | -3.51% | 162.58 | 26 | -136.58 | -84.01% | 2022-03-14 01:00
Mississauga | 2020 | 428613 | DESIGN HOME GIFT AND PAPER INC | 99 | COMPLETE | Labour est. over | Vac truck | Estimate incorrect | Mandic, Goran | No | Alectra Utilities | Paul Murphy | 89928.8 | 77702.29 | -12226.51 | -13.6% | 44926.67 | 29980.92 | -14945.75 | -33.27% | 34498.19 | 32432.18 | -2066.01 | -5.989% | 7137.74 | 7827 | 689.26 | 9.657% | 3366.2 | 7462.19 | 4095.99 | 121.7% | 320.55 | 271.5 | -49.05 | -15.3% | 2020-02-02 01:00
Mississauga | 2022 | 428710 | LT31137 - 2021 SR-DUNDAS ST W & GLEN ERIN DR - P05560 | 99 | COMPLETE | Material Under Estimated | Vehicle Under Estimated | N/A | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Paul Murphy | 115417.39 | 149685.51 | 34268.12 | 29.69% | 33936.84 | 33695.13 | -241.71 | -0.7122% | 74154.56 | 101147.15 | 26992.59 | 36.4% | 7325.99 | 14843.23 | 7517.24 | 102.6% | 0 | 0 | 0 |  | 242.65 | 278.5 | 35.85 | 14.77% | 2022-08-02 01:00
Mississauga | 2020 | 428744 | STUB POLE RELOCATION FOR JOHN STREET EXPANSION | 99 | COMPLETE | Converted Project |  |  | Tobin, Michael | No | Alectra Utilities | Rob Elliot | 26170.68 | 17487.97 | -8682.71 | -33.18% | 17272.35 | 9180.64 | -8091.71 | -46.85% | 3937.73 | 2482.43 | -1455.3 | -36.96% | 1351.5 | 2363.74 | 1012.24 | 74.9% | 3609.1 | 3461.16 | -147.94 | -4.099% | 62.67 | 128 | 65.33 | 104.2% | 2020-03-13 01:00
Mississauga | 2020 | 428824 | 6685 CENTURY AVE - MOVATI FITNESS TEMP SERV | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Bourgeois, Craig | 13828.74 | 14220.62 | 391.88 | 2.834% | 7291.42 | 7036.17 | -255.25 | -3.501% | 5803.76 | 4926.85 | -876.91 | -15.11% | 733.56 | 833 | 99.44 | 13.56% | 0 | 1424.6 | 1424.6 |  | 83.71 | 88 | 4.29 | 5.125% | 2020-02-04 01:00
Mississauga | 2019 | 428875 | 428875 MGR Group - 1191 Eglinton Ave East | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Macasaet, Ricardo | Macdougall, Stephen | 71009.03 | 75805.57 | 4796.54 | 6.755% | 2703.33 | 21515.29 | 18811.96 | 695.9% | 37690.68 | 35971.9 | -1718.78 | -4.56% | 22017.35 | 3984 | -18033.35 | -81.91% | 3541.92 | 14334.38 | 10792.46 | 304.7% | 240.74 | 205.5 | -35.24 | -14.64% | 2019-09-28 01:00
Mississauga | 2022 | 428921 | 428921 - Orlando Corp Retail Building E | 99 | COMPLETE | Labour est. over | Material Under Estimated | Cont Est Under | Mandic, Goran | No | Macasaet, Ricardo | Peter Costantini | 120806.6 | 120253.82 | -552.78 | -0.4576% | 59556.68 | 43357.21 | -16199.47 | -27.2% | 33578.23 | 42259.69 | 8681.46 | 25.85% | 11280.83 | 14320.22 | 3039.39 | 26.94% | 16390.86 | 20291.2 | 3900.34 | 23.8% | 482.99 | 383.5 | -99.49 | -20.6% | 2022-10-25 01:00
Mississauga | 2020 | 429851 | FEEDER REPLACEMENT - L3359 TO L3321 - FAIRVIEW AND HURONTARIO | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 655889.83 | 720052.35 | 64162.52 | 9.783% | 78982.27 | 102423.04 | 23440.77 | 29.68% | 0 | 8266.96 | 8266.96 |  | 3500 | 9832.93 | 6332.93 | 180.9% | 573407.56 | 599379.42 | 25971.86 | 4.529% | 390 | 397 | 7 | 1.795% | 2020-12-18 01:00
Mississauga | 2020 | 429886 | BEEDIE PROPOSED WAREHOUSE FACILITY | 99 | CANCELLED | N/A |  |  | MacDougall, Stephen | No | Alectra Utilities | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-01-05 01:00
Mississauga | 2021 | 429894 | 2340 & 2370 Meadowvale Blvd - BEEDIE PROPOSED WAREHOUSE FACILITY | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 195770.7 | 180161.21 | -15609.49 | -7.973% | 60603.5 | 42327.09 | -18276.41 | -30.16% | 78288.24 | 76951.22 | -1337.02 | -1.708% | 5038.96 | 7231.13 | 2192.17 | 43.5% | 51840 | 53651.77 | 1811.77 | 3.495% | 432.58 | 338 | -94.58 | -21.86% | 2021-01-05 01:00
Mississauga | 2020 | 429907 | 7481 Torbram Rd | 99 | COMPLETE | Material Req incorrectly | Vac truck | Estimate incorrect | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 33819.66 | 32509.15 | -1310.51 | -3.875% | 14067 | 17579.68 | 3512.68 | 24.97% | 17663.84 | 6413.91 | -11249.93 | -63.69% | 1224.82 | 3972.5 | 2747.68 | 224.3% | 864 | 4543.06 | 3679.06 | 425.8% | 92.5 | 145.5 | 53 | 57.3% | 2020-03-20 01:00
Mississauga | 2020 | 429940 | 270 LAKESHORE ROAD WEST - THE SHORES OF PORT CREDIT RETIREMENT HOMES | 99 | COMPLETE | Converted Project | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 198696.58 | 205431.35 | 6734.77 | 3.389% | 40540.21 | 34985.39 | -5554.82 | -13.7% | 72780.08 | 71461.55 | -1318.53 | -1.812% | 4794.25 | 3891.65 | -902.6 | -18.83% | 80582.04 | 95092.76 | 14510.72 | 18.01% | 293.59 | 208 | -85.59 | -29.15% | 2020-10-15 01:00
Mississauga | 2020 | 430262 | VICTORIA STREET HOLDINGS | 99 | COMPLETE | Converted Project | N/A | N/A | D'Onofrio, Tony | No | Alectra Utilities | Paul Tremblay | 122168.9 | 96920.89 | -25248.01 | -20.67% | 41029.8 | 24709.04 | -16320.76 | -39.78% | 5422.5 | 5286.58 | -135.92 | -2.507% | 3722.72 | 3292.54 | -430.18 | -11.56% | 71993.88 | 63632.73 | -8361.15 | -11.61% | 224.64 | 133 | -91.64 | -40.79% | 2020-06-18 01:00
Mississauga | 2019 | 430334 | Eglinton MUT Relocations | 99 | COMPLETE | Converted Project | N/A | N/A | Lacombe, Joel | No | Gonzales, Leonard | Paul Murphy | 45103.37 | 30268.77 | -14834.6 | -32.89% | 26811.5 | 17101.67 | -9709.83 | -36.22% | 6378.23 | 4675.7 | -1702.53 | -26.69% | 2030.69 | 5634 | 3603.31 | 177.4% | 9882.95 | 2857.4 | -7025.55 | -71.09% | 219.5 | 193 | -26.5 | -12.07% | 2019-12-07 01:00
Mississauga | 2019 | 430406 | Sir Richard Rd - Cable replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | No | Cudzilo, Tomasz | Glenn Guile | 66551.27 | 35399.5 | -31151.77 | -46.81% | 39828.08 | 11811.46 | -28016.62 | -70.34% | 810.53 | 850.31 | 39.78 | 4.908% | 2517.7 | 364 | -2153.7 | -85.54% | 23394.96 | 22373.73 | -1021.23 | -4.365% | 102 | 57.5 | -44.5 | -43.63% | 2019-11-19 01:00
Mississauga | 2020 | 430414 | CABLE REPLACEMENT - TX10375-W TO TX12371-W - FOLKWAY DR. | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | No | Alectra Utilities | Glenn Guile | 135143.96 | 114037.42 | -21106.54 | -15.62% | 28236.26 | 16372.68 | -11863.58 | -42.02% | 2350.6 | 3015.07 | 664.47 | 28.27% | 386.78 | 1219.78 | 833 | 215.4% | 104170.32 | 93429.89 | -10740.43 | -10.31% | 118.16 | 56 | -62.16 | -52.61% | 2020-06-16 01:00
Mississauga | 2020 | 430457 | Phase 3-Rathburn Rd W UG Cable Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Lucic, Marko | Yes | Alectra Utilities | Paul Tremblay | 3650805.45 | 3615968.46 | -34836.99 | -0.9542% | 298071.5 | 474555.72 | 176484.22 | 59.21% | 19381.72 | 32520.66 | 13138.94 | 67.79% | 49415.08 | 40370.49 | -9044.59 | -18.3% | 3254177.51 | 3068521.59 | -185655.92 | -5.705% | 2644.24 | 2384 | -260.24 | -9.842% | 2020-09-11 01:00
Mississauga | 2020 | 430537 | POLE RELOCATION - 588 CURZON AVE | 99 | COMPLETE | Material Req incorrectly | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Rob Elliot | 21127.11 | 18829.16 | -2297.95 | -10.88% | 9368.44 | 8469.1 | -899.34 | -9.6% | 2394.73 | 1498 | -896.73 | -37.45% | 3713.94 | 3688 | -25.94 | -0.6984% | 5650 | 5174.06 | -475.94 | -8.424% | 140.38 | 96 | -44.38 | -31.61% | 2020-03-20 01:00
Mississauga | 2021 | 430625 | SHAWSON M.S. CABLE REPLACEMENT | 99 | COMPLETE | Converted Project | N/A | N/A | Houston, Andrew | No | Zaghloul, Sam | Glenn Guile | 570102.24 | 742170.1 | 172067.86 | 30.18% | 146875.13 | 208343.77 | 61468.64 | 41.85% | 153385.26 | 210292.59 | 56907.33 | 37.1% | 26900.17 | 55101.64 | 28201.47 | 104.8% | 242941.68 | 268432.1 | 25490.42 | 10.49% | 1217.14 | 2124 | 906.86 | 74.51% | 2021-01-22 01:00
Mississauga | 2020 | 631303 | UG CABLE REPLACEMENT - 71F3 | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Beaudrie, Scott | Yes | Alectra Utilities | Paul Tremblay | 1377469.38 | 1228537.5 | -148931.88 | -10.81% | 188395.6 | 170477.56 | -17918.04 | -9.511% | 58441.08 | 34464.37 | -23976.71 | -41.03% | 28329.88 | 23352.02 | -4977.86 | -17.57% | 1102302.82 | 1000093.55 | -102209.27 | -9.272% | 928.56 | 857 | -71.56 | -7.707% | 2020-12-16 01:00
Mississauga | 2020 | 631304 | BOUGH BEECHES UG REBUILD - More info needed | 99 | COMPLETE | Labour est. under | BOM not accurate |  | Beaudrie, Scott | Yes | Alectra Utilities | Paul Tremblay | 972419.3 | 928789.33 | -43629.97 | -4.487% | 87675.33 | 117948.73 | 30273.4 | 34.53% | 6510.54 | 9072.91 | 2562.37 | 39.36% | 8941.43 | 9283.56 | 342.13 | 3.826% | 869292 | 792334.13 | -76957.87 | -8.853% | 731.92 | 411.5 | -320.42 | -43.78% | 2020-10-02 01:00
Mississauga | 2020 | 631305 | 2020 UG REBUILD - FOLKWAY DRIVE | 99 | COMPLETE | Under 10% | Scope change - unforeseen | BOM not accurate | Beaudrie, Scott | Yes | Alectra Utilities | Paul Tremblay | 3285570.1 | 3285484.68 | -85.42 | -0.0026% | 131558.03 | 433200.62 | 301642.59 | 229.3% | 0 | 43692.17 | 43692.17 |  | 4760 | 60819.11 | 56059.11 | 1178% | 3149252.07 | 2747622.78 | -401629.29 | -12.75% | 1120 | 2061.5 | 941.5 | 84.06% | 2020-11-20 01:00
Mississauga | 2021 | 631313 | QUOTE 1100 CANADIAN PLACE - TEMPORARY SERVICE | 99 | COMPLETE | Labour est. over | N/A | N/A | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 23799.81 | 12803.13 | -10996.68 | -46.2% | 14820.77 | 6260.64 | -8560.13 | -57.76% | 3951.3 | 3316.05 | -635.25 | -16.08% | 2667.74 | 1392 | -1275.74 | -47.82% | 2360 | 1834.44 | -525.56 | -22.27% | 80.25 | 73 | -7.25 | -9.034% | 2021-08-02 01:00
Mississauga | 2020 | 631663 | Cogeco Middle Gate Pole Replacement | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | K-Line Construction | 24915.88 | 0 | -24915.88 | -100% | 15533.43 | 0 | -15533.43 | -100% | 7170.64 | 0 | -7170.64 | -100% | 2211.81 | 0 | -2211.81 | -100% | 0 | 0 | 0 |  | 66.55 | 0 | -66.55 | -100% | 2020-07-01 01:00
Mississauga | 2019 | 631920 | MTO HWY401 PATROL YARD 800A UPGRADE | 99 | COMPLETE | Labour est. over | Cont Est Under | N/A | Mandic, Goran | No | Macasaet, Ricardo | Macdougall, Stephen | 50338.09 | 40729.27 | -9608.82 | -19.09% | 17400.7 | 6870.41 | -10530.29 | -60.52% | 29101.78 | 30710.3 | 1608.52 | 5.527% | 2119.49 | 851 | -1268.49 | -59.85% | 1716.12 | 2297.56 | 581.44 | 33.88% | 128.51 | 52 | -76.51 | -59.54% | 2019-10-02 01:00
Mississauga | 2020 | 632210 | Inglewood Drive - Joint Use Permit | 99 | COMPLETE | N/A | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 5749.52 | 3896.34 | -1853.18 | -32.23% | 2369.58 | 2088.52 | -281.06 | -11.86% | 751.19 | 0 | -751.19 | -100% | 268.75 | 307.82 | 39.07 | 14.54% | 2360 | 1500 | -860 | -36.44% | 8.12 | 8 | -0.12 | -1.478% | 2020-09-09 01:00
Mississauga | 2020 | 632259 | UG Rebuld - Shelter Bay Road Area | 99 | COMPLETE | Covid-19 | Cont Est Over | Estimate incorrect | Beaudrie, Scott | Yes | Alectra Utilities | Paul Tremblay | 2075294.17 | 1746745.46 | -328548.71 | -15.83% | 109376.76 | 196137.58 | 86760.82 | 79.32% | 9913.26 | 9442.51 | -470.75 | -4.749% | 9861.71 | 11496.57 | 1634.86 | 16.58% | 1946142.44 | 1529518.8 | -416623.64 | -21.41% | 888.12 | 543.5 | -344.62 | -38.8% | 2020-10-07 01:00
Mississauga | 2020 | 632358 | Parkside Village Phase 3 | 98 | COMPLETE | Labour est. under | Cont Est Over | N/A | Gamboa, Henry | No | Alectra Utilities | Mark Bobanovic | 212424.18 | 206281.1 | -6143.08 | -2.892% | 12886.74 | 21297.1 | 8410.36 | 65.26% | 0 | 0 | 0 |  | 420 | 616 | 196 | 46.67% | 199117.44 | 184368 | -14749.44 | -7.407% | 65 | 46 | -19 | -29.23% | 2020-08-17 01:00
Mississauga | 2021 | 632378 | JOINT USE PERMIT #HM2019-017 - PETER STREET NORTH - MISSISSAUGA | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 7633.38 | 4346.46 | -3286.92 | -43.06% | 2350.19 | 2129.46 | -220.73 | -9.392% | 383.68 | 0 | -383.68 | -100% | 374.85 | 572 | 197.15 | 52.59% | 4524.66 | 1645 | -2879.66 | -63.64% | 11.15 | 21 | 9.85 | 88.34% | 2021-06-07 01:00
Mississauga | 2021 | 632387 | JOINT USE PERMIT #HM2019-028 - OWENWOOD DRIVE - MISSISSAUGA | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 9234.41 | 8520.7 | -713.71 | -7.729% | 2448.17 | 2293.06 | -155.11 | -6.336% | 478.81 | 149.09 | -329.72 | -68.86% | 179.4 | 432 | 252.6 | 140.8% | 6128.03 | 5646.55 | -481.48 | -7.857% | 16 | 14 | -2 | -12.5% | 2021-06-07 01:00
Mississauga | 2020 | 632392 | Britannie Rd and Brookhaven Way - Joint Use Permit | 99 | COMPLETE | No Feedback from Const | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 4127.59 | 8052.65 | 3925.06 | 95.09% | 1607.36 | 2091.16 | 483.8 | 30.1% | 321.75 | 0 | -321.75 | -100% | 155.39 | 615.64 | 460.25 | 296.2% | 2043.09 | 5345.85 | 3302.76 | 161.7% | 8.04 | 13.5 | 5.46 | 67.91% | 2020-09-16 01:00
Mississauga | 2021 | 632716 | JOINT USE PERMIT #HM2019-049 - EGLINTON AVENUE WEST - MISSISSAUGA | 99 | COMPLETE | Under 10% | Cont Est Under | Labour est. over | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 31892.41 | 34579.52 | 2687.11 | 8.426% | 11461.44 | 8935.31 | -2526.13 | -22.04% | 6334.4 | 5506.81 | -827.59 | -13.07% | 1387.18 | 3326 | 1938.82 | 139.8% | 12709.39 | 16811.4 | 4102.01 | 32.28% | 88.08 | 102.5 | 14.42 | 16.37% | 2021-02-12 01:00
Mississauga | 2021 | 632719 | JOINT USE PERMIT #HM2019-073 - MISSISSAUGA ROAD - MISSISSAUGA | 99 | COMPLETE | Vehicle Under Estimated | Labour est. under | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 45229.51 | 38254.58 | -6974.93 | -15.42% | 13097.98 | 8819.3 | -4278.68 | -32.67% | 6845.37 | 2344.66 | -4500.71 | -65.75% | 1632.27 | 4182 | 2549.73 | 156.2% | 23653.89 | 22908.62 | -745.27 | -3.151% | 102.12 | 91.5 | -10.62 | -10.4% | 2021-02-02 01:00
Mississauga | 2019 | 632735 | 1070 Meredith Ave | 99 | COMPLETE | N/A | N/A | N/A | Beaudrie, Scott | No | Pellerin, Patrick | Paul Murphy | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 27.27 | 0 | -27.27 | -100% | 2019-10-05 01:00
Mississauga | 2022 | 632758 | Torbram & Derry Rd E - GO elec | 99 | CANCELLED | N/A |  |  | Tobin, Michael | No | Central South | Dre Danieli | 0 | 23143.83 | 23143.83 |  | 0 | 22944.53 | 22944.53 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 199.3 | 199.3 |  | 0 | 6 | 6 |  | 2021-12-10 01:00
Mississauga | 2020 | 632779 | 600 Arbor Rd - Bell Make Ready | 99 | COMPLETE | Labour est. over | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Macdougall, Stephen | 5156.14 | 5003.05 | -153.09 | -2.969% | 4523.81 | 2814.05 | -1709.76 | -37.79% | 10.46 | 0 | -10.46 | -100% | 619.51 | 544 | -75.51 | -12.19% | 2.36 | 1645 | 1642.64 | 69603% | 26.25 | 24 | -2.25 | -8.571% | 2020-09-21 01:00
Mississauga | 2019 | 632834 | P02687 Replacement - 1082 Meredith Ave | 99 | COMPLETE | N/A | N/A | N/A | Beaudrie, Scott | No | Pellerin, Patrick | Paul Murphy | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 78.27 | 0 | -78.27 | -100% | 2019-10-05 01:00
Mississauga | 2020 | 632842 | 550 Courtneypark Dr W - Switchgear Removal | 99 | COMPLETE | Civil contractor | Cont Est Under | N/A | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 104729.2 | 165242.2 | 60513 | 57.78% | 33184.71 | 31344.96 | -1839.75 | -5.544% | 22654.12 | 26040.73 | 3386.61 | 14.95% | 6915.09 | 6995.76 | 80.67 | 1.167% | 41975.28 | 100860.75 | 58885.47 | 140.3% | 317.6 | 248.5 | -69.1 | -21.76% | 2020-03-11 01:00
Mississauga | 2022 | 632865 | Rathburn Rd W - U/G Cable Repair - 68F4 Part 1 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-25 01:00
Mississauga | 2022 | 632866 | Elora Dr - UG Cable Repair - 68F4 Part 2 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-25 01:00
Mississauga | 2022 | 632869 | Burnhamthorpe Rd W - UG Cable Repair - 68F7 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-25 01:00
Mississauga | 2022 | 632870 | Burhamthorpe Rd W - UG Cable Repair - 83F3 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-25 01:00
Mississauga | 2022 | 632871 | Elora Dr - UG Cable Repairs - 83F5 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-25 01:00
Mississauga | 2020 | 632880 | Pole Relocation - Eglinton and Burgoyne | 99 | COMPLETE | Labour est. over | Vac truck | Estimate incorrect | Lacombe, Joel | No | Alectra Utilities | Macdougall, Stephen | 80792.42 | 67654.78 | -13137.64 | -16.26% | 47198.19 | 27834.49 | -19363.7 | -41.03% | 17845.85 | 18413.6 | 567.75 | 3.181% | 9917.81 | 11539.72 | 1621.91 | 16.35% | 5830.57 | 9866.97 | 4036.4 | 69.23% | 353.63 | 276.5 | -77.13 | -21.81% | 2020-08-21 01:00
Mississauga | 2022 | 632904 | CABLE INJECTION - AREA 46 | 99 | COMPLETE | Scope – Eng |  |  | Beaudrie, Scott | No | Tempra, Troylan | Glenn Guile | 168086.96 | 19908.86 | -148178.1 | -88.16% | 152078.96 | 18044.94 | -134034.02 | -88.13% | 0 | 0 | 0 |  | 16008 | 1863.92 | -14144.08 | -88.36% | 0 | 0 | 0 |  | 1368 | 167 | -1201 | -87.79% | 2022-01-27 01:00
Mississauga | 2022 | 633022 | Derry Rd E and Airport Rd - Go Electr Scope # 2 | 99 | CANCELLED | N/A |  |  | Tobin, Michael | No | Chopra, Rabinder | Dre Danieli | 0 | 56090.33 | 56090.33 |  | 0 | 33077.45 | 33077.45 |  | 0 | 0 | 0 |  | 0 | 5533.6 | 5533.6 |  | 0 | 17430.06 | 17430.06 |  | 0 | 11 | 11 |  | 2019-12-20 01:00
Mississauga | 2022 | 633083 | Argentia Phase 1 - UG Cable Replacement | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-17 01:00
Mississauga | 2022 | 633165 | PCB/AGE Transformer Replacements | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-04 01:00
Mississauga | 2022 | 633181 | Cable Injection - Area 58 & 59 | 99 | COMPLETE | Scope – Eng |  |  | Beaudrie, Scott | No | Tempra, Troylan | Glenn Guile | 273692.74 | 52888.15 | -220804.59 | -80.68% | 248180.74 | 47798.31 | -200382.43 | -80.74% | 0 | 0 | 0 |  | 25512 | 5089.84 | -20422.16 | -80.05% | 0 | 0 | 0 |  | 2232 | 495.5 | -1736.5 | -77.8% | 2022-01-27 14:58
Mississauga | 2020 | 633249 | TRANSFORMER UPGRADE - 345 SUPERIOR BLVD | 99 | COMPLETE | Labour est. under | Cont Est Over | Estimate incorrect | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 60862.76 | 57358.89 | -3503.87 | -5.757% | 10689.28 | 17000.81 | 6311.53 | 59.05% | 43790.45 | 35898.18 | -7892.27 | -18.02% | 1071.59 | 1610 | 538.41 | 50.24% | 5311.44 | 2849.9 | -2461.54 | -46.34% | 75.11 | 176 | 100.89 | 134.3% | 2020-01-16 01:00
Mississauga | 2022 | 633250 | 1075 CLARKSON RD N - PCB TRANSFORMER REPLACEMENT | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-04 01:00
Mississauga | 2022 | 633251 | 7 Elizabeth St N PCB Transformer Replacement | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-04 01:00
Mississauga | 2019 | 633272 | Rathburn Rd - TX replacement | 99 | COMPLETE | Labour est. over |  |  |  | No | Huo, Lisa | Macdougall, Stephen | 27640.39 | 24066.92 | -3573.47 | -12.93% | 9042.03 | 4527.38 | -4514.65 | -49.93% | 17566.64 | 19115.54 | 1548.9 | 8.817% | 1029.56 | 424 | -605.56 | -58.82% | 2.16 | 0 | -2.16 | -100% | 71.8 | 51 | -20.8 | -28.97% | 2019-09-15 01:00
Mississauga | 2019 | 633380 | Mavis Rd - Guy Pole Relocations | 99 | COMPLETE | Labour est. over | Cont Est Over | Estimate incorrect | Lacombe, Joel | No | Watters, Maxwell | Paul Murphy | 23260.85 | 15259.57 | -8001.28 | -34.4% | 10875.08 | 8719.53 | -2155.55 | -19.82% | 4782.57 | 652.14 | -4130.43 | -86.36% | 1663.2 | 2996 | 1332.8 | 80.13% | 5940 | 2891.9 | -3048.1 | -51.31% | 88.55 | 94 | 5.45 | 6.155% | 2019-10-18 01:00
Mississauga | 2021 | 633435 | JOINT USE PERMIT #HM2019-074 - HENSALL STREET - MISSISSAUGA | 99 | COMPLETE | Cont Est Under | Vehicle Under Estimated | Labour est. under | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 35688.35 | 45222.61 | 9534.26 | 26.72% | 18106.38 | 18182.58 | 76.2 | 0.4208% | 6138.32 | 3272.87 | -2865.45 | -46.68% | 2343.52 | 7810 | 5466.48 | 233.3% | 9100.13 | 15957.16 | 6857.03 | 75.35% | 140.28 | 174.5 | 34.22 | 24.39% | 2021-01-29 01:00
Mississauga | 2022 | 633451 | 2075 Sherobee Rd - PCB Transformer Replacement | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-08 01:00
Mississauga | 2020 | 633452 | Erin Square Temporary 600A Service | 99 | COMPLETE | BOM not accurate | Cont Est Under |  | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 50373.43 | 50021.08 | -352.35 | -0.6995% | 28140.19 | 25374.77 | -2765.42 | -9.827% | 11170.3 | 6599.2 | -4571.1 | -40.92% | 4599.29 | 4009.79 | -589.5 | -12.82% | 5963.65 | 14037.32 | 8073.67 | 135.4% | 202.85 | 181 | -21.85 | -10.77% | 2020-06-08 01:00
Mississauga | 2022 | 633458 | 1400 Dixie Rd - PCB Transformer Replacement | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-18 01:00
Mississauga | 2022 | 633469 | Third Party Transfer Project - TX replacement TX641 | 99 | CANCELLED | N/A |  |  | Lucic, Marko | Yes | Beaudrie, Scott | Dre Danieli | 131.01 | 0 | -131.01 | -100% | 0 | 0 | 0 |  | 131.01 | 0 | -131.01 | -100% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-02 01:00
Mississauga | 2020 | 633483 | 2565 Rena Road | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 150048.2 | 122103.8 | -27944.4 | -18.62% | 39501.66 | 20514.3 | -18987.36 | -48.07% | 47589.04 | 41487.17 | -6101.87 | -12.82% | 5341.66 | 3931.2 | -1410.46 | -26.4% | 57615.84 | 56171.13 | -1444.71 | -2.507% | 142.59 | 152.5 | 9.91 | 6.95% | 2020-11-10 01:00
Mississauga | 2021 | 633540 | MISSISSAUGA ROAD SOUTH POLELINE RELOCATION | 98 | COMPLETE | Labour est. over | Cont Est Over |  | Lacombe, Joel | No | Garcha, Tirath | Paul Murphy | 1660318.54 | 1352839.59 | -307478.95 | -18.52% | 477325.72 | 350762.74 | -126562.98 | -26.52% | 181844.73 | 170660.18 | -11184.55 | -6.151% | 102209.01 | 99157.37 | -3051.64 | -2.986% | 898939.08 | 732036.34 | -166902.74 | -18.57% | 3246.58 | 3017.5 | -229.08 | -7.056% | 2021-11-30 01:00
Mississauga | 2020 | 633602 | Elm Dr - Guying Relocation | 99 | CANCELLED | N/A |  |  |  | No | Alectra Utilities | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-22 01:00
Mississauga | 2020 | 633618 | 3 Storey Medical Office | 99 | COMPLETE | Cont Est Under | Labour est. over | N/A | MacDougall, Stephen | No | Alectra Utilities | Peter Costantini | 43701.86 | 56267.41 | 12565.55 | 28.75% | 19382.73 | 15634.91 | -3747.82 | -19.34% | 19610.06 | 17806.04 | -1804.02 | -9.199% | 1901.07 | 4612.5 | 2711.43 | 142.6% | 2808 | 18213.96 | 15405.96 | 548.6% | 132.29 | 144.5 | 12.21 | 9.23% | 2020-08-24 01:00
Mississauga | 2021 | 633629 | Mavis Rd & Terry Fox Way - Joint Use Permit | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Johnson, William | XMoinuddin, Saad | 0 | 3150 | 3150 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3150 | 3150 |  | 0 | 0 | 0 |  | 2020-09-18 01:00
Mississauga | 2020 | 633637 | 425 Lakeshore Blvd - Guying Relocation | 99 | COMPLETE | Material Req incorrectly | Labour est. under | N/A | Lacombe, Joel | No | Alectra Utilities | Paul Murphy | 19357.44 | 16039.04 | -3318.4 | -17.14% | 9053.96 | 9318.41 | 264.45 | 2.921% | 4460.34 | 1510.63 | -2949.71 | -66.13% | 1762.9 | 2995 | 1232.1 | 69.89% | 4080.24 | 2215 | -1865.24 | -45.71% | 63.33 | 91 | 27.67 | 43.69% | 2020-02-13 01:00
Mississauga | 2020 | 633727 | Arbor Rd - Joint Use Permit | 99 | COMPLETE | No Feedback from Const | Labour est. over | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 10887.38 | 5956.77 | -4930.61 | -45.29% | 3943.83 | 1922.21 | -2021.62 | -51.26% | 1005.82 | 268.92 | -736.9 | -73.26% | 424.49 | 615.64 | 191.15 | 45.03% | 5513.24 | 3150 | -2363.24 | -42.86% | 30.04 | 12 | -18.04 | -60.05% | 2020-08-26 01:00
Mississauga | 2020 | 633792 | GREYPAN DIXIE EGLINTON | 99 | COMPLETE | Civil contractor | Scope change - unforeseen | Labour est. over | Mandic, Goran | No | Alectra Utilities | Macdougall, Stephen | 124013.82 | 144465.12 | 20451.3 | 16.49% | 43300.5 | 24104.58 | -19195.92 | -44.33% | 36392.09 | 35949.47 | -442.62 | -1.216% | 4361.23 | 2178.5 | -2182.73 | -50.05% | 39960 | 82232.57 | 42272.57 | 105.8% | 255.14 | 182 | -73.14 | -28.67% | 2020-03-28 01:00
Mississauga | 2020 | 633793 | OH Transformer Replacements - Part 1 | 99 | COMPLETE | Under 10% | BOM not used |  | Beaudrie, Scott | No | Alectra Utilities | Paul Murphy | 126530.83 | 121216.02 | -5314.81 | -4.2% | 33682.08 | 38142.99 | 4460.91 | 13.24% | 73428.76 | 59167.18 | -14261.58 | -19.42% | 5781.75 | 20916.07 | 15134.32 | 261.8% | 13638.24 | 2989.78 | -10648.46 | -78.08% | 225.44 | 413 | 187.56 | 83.2% | 2020-10-27 01:00
Mississauga | 2021 | 633794 | OH TRANSFORMER REPLACEMENTS - PART 2 | 99 | COMPLETE | Under 10% | BOM not used |  | Beaudrie, Scott | No | Pellerin, Patrick | Paul Murphy | 136173.14 | 127481.55 | -8691.59 | -6.383% | 55805.11 | 50763.38 | -5041.73 | -9.035% | 44527.1 | 29518.21 | -15008.89 | -33.71% | 11180.21 | 35675 | 24494.79 | 219.1% | 24660.72 | 11524.96 | -13135.76 | -53.27% | 481.84 | 662 | 180.16 | 37.39% | 2021-02-03 01:00
Mississauga | 2022 | 633795 | OH TRANSFORMER REPLACEMENTS - PART 3 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Pellerin, Patrick | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-07 01:00
Mississauga | 2020 | 633865 | 2020 POLE REPLACEMENT BATCH 2 | 99 | COMPLETE | Estimate incorrect | Labour est. under | Vehicle Under Estimated | Beaudrie, Scott | No | Alectra Utilities | Macdougall, Stephen | 391915.11 | 352447.59 | -39467.52 | -10.07% | 114952.98 | 143029.39 | 28076.41 | 24.42% | 62593.2 | 76511.1 | 13917.9 | 22.24% | 18888.93 | 53822.8 | 34933.87 | 184.9% | 195480 | 79084.3 | -116395.7 | -59.54% | 4201.76 | 1466 | -2735.76 | -65.11% | 2020-12-17 01:00
Mississauga | 2022 | 633867 | 2020 POLE REPLACEMENT BATCH 4 - 12 POLES | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Matai, Ihssan (Sam) | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-21 01:00
Mississauga | 2022 | 633868 | 2020 POLE REPLACEMENT BATCH 5 - 17 POLES | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Matai, Ihssan (Sam) | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-21 01:00
Mississauga | 2021 | 633898 | INDWELL LAKESHORE APARTMENTS | 99 | COMPLETE | Labour est. over | N/A | N/A | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 169766.42 | 142754.9 | -27011.52 | -15.91% | 66369.3 | 35417.19 | -30952.11 | -46.64% | 30416.58 | 31413.5 | 996.92 | 3.278% | 6020.54 | 5402.5 | -618.04 | -10.27% | 66960 | 70521.71 | 3561.71 | 5.319% | 299.3 | 286.5 | -12.8 | -4.277% | 2021-08-03 01:00
Mississauga | 2020 | 633972 | 2020 Tx replacements batch 1 - 11 units | 99 | COMPLETE | Labour est. under | Material Req incorrectly | Civil contractor | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 147870.58 | 203238.45 | 55367.87 | 37.44% | 36294.78 | 60317.64 | 24022.86 | 66.19% | 93805.15 | 111081.34 | 17276.19 | 18.42% | 6970.65 | 14169.88 | 7199.23 | 103.3% | 10800 | 17669.59 | 6869.59 | 63.61% | 308.06 | 697 | 388.94 | 126.3% | 2020-10-28 01:00
Mississauga | 2020 | 633973 | 2020 tx replacements Batch 1 - 9 units | 99 | COMPLETE | Scope – Eng | RFC not approved in time | BOM not accurate | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 207948.94 | 179776.38 | -28172.56 | -13.55% | 42753.7 | 38100.59 | -4653.11 | -10.88% | 160447.13 | 129806.83 | -30640.3 | -19.1% | 4748.11 | 10698.96 | 5950.85 | 125.3% | 0 | 1170 | 1170 |  | 315.87 | 427.5 | 111.63 | 35.34% | 2020-12-31 01:00
Mississauga | 2020 | 633974 | 2020 tx replacements batch 3 - 11 units | 99 | COMPLETE | Labour est. over | Material Req incorrectly | Scope change - unforeseen | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 101188.76 | 78110.55 | -23078.21 | -22.81% | 31990.9 | 15928.01 | -16062.89 | -50.21% | 65266.69 | 48507.56 | -16759.13 | -25.68% | 3931.17 | 6285.9 | 2354.73 | 59.9% | 0 | 7389.08 | 7389.08 |  | 282.77 | 166 | -116.77 | -41.3% | 2020-06-29 01:00
Mississauga | 2021 | 633996 | 2650 MEADOWVALE BLVD - MEADOWVALE LIMITED 3MVA UPGRADE | 99 | COMPLETE | Labour est. over | Cont Est Under | Vehicle Over Estimated- | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 106765.95 | 123151.77 | 16385.82 | 15.35% | 32203.05 | 24940.08 | -7262.97 | -22.55% | 91823.88 | 92530.29 | 706.41 | 0.7693% | 3793.02 | 2844 | -949.02 | -25.02% | 1296 | 2837.4 | 1541.4 | 118.9% | 69 | 236.5 | 167.5 | 242.8% | 2021-09-17 01:00
Mississauga | 2020 | 633999 | QEW - Relocate Fuses @ P06143 on South Sheridan Way | 99 | COMPLETE | Labour est. over | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Rob Elliot | 51133.67 | 45034.8 | -6098.87 | -11.93% | 26027.49 | 17508.58 | -8518.91 | -32.73% | 8076.54 | 8184.6 | 108.06 | 1.338% | 5605.4 | 5746 | 140.6 | 2.508% | 11424.24 | 13595.62 | 2171.38 | 19.01% | 208.74 | 159.5 | -49.24 | -23.59% | 2020-08-13 01:00
Mississauga | 2020 | 634068 | Whites Studio Inc | 99 | COMPLETE | Engineering by-passed | N/A | N/A |  | No | Alectra Utilities | XMoinuddin, Saad | 61205.38 | 7943.3 | -53262.08 | -87.02% | 13943.81 | 5892.27 | -8051.54 | -57.74% | 45752.01 | 1299.03 | -44452.98 | -97.16% | 1293.56 | 752 | -541.56 | -41.87% | 216 | 0 | -216 | -100% | 0 | 59 | 59 |  | 2020-01-29 01:00
Mississauga | 2021 | 634072 | GTAA DIXIE ROAD FEEDER EXTENSION (135M2 - CARDIFF) | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 16613.23 | 16613.23 |  | 0 | 16481.23 | 16481.23 |  | 0 | 0 | 0 |  | 0 | 132 | 132 |  | 0 | 0 | 0 |  | 0 | 12 | 12 |  | 2020-08-14 01:00
Mississauga | 2020 | 634106 | 2020 Tx replacements batch 4 - 15 units | 99 | COMPLETE | Material Req incorrectly | Labour est. under | Vehicle Under Estimated | Beaudrie, Scott | No | Alectra Utilities | Peter Costantini | 149893.18 | 147012.45 | -2880.73 | -1.922% | 40376.74 | 49302.22 | 8925.48 | 22.11% | 101561.39 | 78887.27 | -22674.12 | -22.33% | 5255.05 | 15185.4 | 9930.35 | 189% | 2700 | 3637.56 | 937.56 | 34.72% | 360.05 | 537.5 | 177.45 | 49.28% | 2020-02-03 01:00
Mississauga | 2021 | 634126 | POLE REPLACEMENT - BATCH #1 | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated | Cont Est Over | Beaudrie, Scott | No | Matai, Ihssan (Sam) | Paul Murphy | 213582 | 353269.21 | 139687.21 | 65.4% | 68474.42 | 154016.94 | 85542.52 | 124.9% | 55920.02 | 59047.12 | 3127.1 | 5.592% | 14127.56 | 102613.31 | 88485.75 | 626.3% | 75060 | 37591.84 | -37468.16 | -49.92% | 538.45 | 1614.5 | 1076.05 | 199.8% | 2021-04-09 01:00
Mississauga | 2021 | 634154 | BARBER HOUSE DEVELOPMENT | 99 | COMPLETE | Under 10% | Cont Est Over | Labour est. over | D'Onofrio, Tony | No | Ricci, Leonardo | Antonio Mina | 253369.25 | 228836.43 | -24532.82 | -9.683% | 48930.6 | 40654.87 | -8275.73 | -16.91% | 2727.83 | 3807.69 | 1079.86 | 39.59% | 3404.46 | 2948 | -456.46 | -13.41% | 198306.36 | 180117 | -18189.36 | -9.172% | 229.54 | 150.5 | -79.04 | -34.43% | 2021-10-11 01:00
Mississauga | 2021 | 634204 | FAIR BIRCH DRIVE & BIRCHVIEW DRIVE - OH TO UG RELOCATION | 99 | COMPLETE | Civil contractor | Cont Est Over | Labour est. over | Lacombe, Joel | No | Watters, Maxwell | Paul Tremblay | 511421.85 | 405920.03 | -105501.82 | -20.63% | 97571.86 | 81593.3 | -15978.56 | -16.38% | 55633.07 | 43485.13 | -12147.94 | -21.84% | 18113 | 20175 | 2062 | 11.38% | 340103.92 | 260512.1 | -79591.82 | -23.4% | 556.59 | 588 | 31.41 | 5.643% | 2021-04-22
Mississauga | 2020 | 634363 | 2020 Transformer Replacement Batch 5-10 Units | 99 | COMPLETE | Est. Int. - Act. External | RFC not approved in time | N/A | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 120088.59 | 101831.68 | -18256.91 | -15.2% | 41097.53 | 7099.15 | -33998.38 | -82.73% | 61194.16 | 55983.94 | -5210.22 | -8.514% | 6996.9 | 0 | -6996.9 | -100% | 10800 | 38748.59 | 27948.59 | 258.8% | 372.8 | 11 | -361.8 | -97.05% | 2020-12-17 01:00
Mississauga | 2021 | 634379 | Folkway Rebuild - Phase2 | 99 | COMPLETE | Under 10% | Scope change - unforeseen | BOM not accurate | Beaudrie, Scott | Yes | Cudzilo, Tomasz | Paul Tremblay | 2779472.35 | 3025979.9 | 246507.55 | 8.869% | 106174.74 | 402446.07 | 296271.33 | 279% | 0 | 36877.55 | 36877.55 |  | 3780 | 43169.1 | 39389.1 | 1042% | 2669517.61 | 2543337.18 | -126180.43 | -4.727% | 810 | 1729 | 919 | 113.5% | 2021-03-26 01:00
Mississauga | 2020 | 634421 | PSN Bonds, HM2018-170, HM2019-006, HM2019-111 | 99 | COMPLETE | Material Req incorrectly | Vac truck | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 5615.49 | 6430.33 | 814.84 | 14.51% | 4897.89 | 4422.3 | -475.59 | -9.71% | 0 | 0 | 0 |  | 717.6 | 2008.03 | 1290.43 | 179.8% | 0 | 0 | 0 |  | 37 | 44 | 7 | 18.92% | 2020-09-16 01:00
Mississauga | 2020 | 634427 | 320 Matheson Blvd - 3000KVA Tx Upgrade | 99 | COMPLETE | Material Req incorrectly | Scope change - unforeseen | Civil contractor | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 81646.53 | 109575.54 | 27929.01 | 34.21% | 37749.77 | 32515.89 | -5233.88 | -13.86% | 20182 | 43289.62 | 23107.62 | 114.5% | 7589.28 | 4958.5 | -2630.78 | -34.66% | 16125.48 | 28811.53 | 12686.05 | 78.67% | 366.04 | 356.5 | -9.54 | -2.606% | 2020-08-22 01:00
Mississauga | 2020 | 634509 | OH SW Replacement - LT41206 | 99 | COMPLETE | Vehicle Under Estimated | Covid-19 | N/A | Beaudrie, Scott | No | Alectra Utilities | Paul Murphy | 147624.05 | 152477.4 | 4853.35 | 3.288% | 47210.69 | 44964.49 | -2246.2 | -4.758% | 83520.44 | 83916.21 | 395.77 | 0.4739% | 10868.68 | 21337.52 | 10468.84 | 96.32% | 6024.24 | 2259.18 | -3765.06 | -62.5% | 360.45 | 465.75 | 105.3 | 29.21% | 2020-11-10 01:00
Mississauga | 2020 | 634518 | Switch Replacement (LT41169) | 99 | COMPLETE | BOM not accurate | Labour est. under | Vehicle Under Estimated | Beaudrie, Scott | No | Alectra Utilities | Paul Murphy | 121093.12 | 99145.42 | -21947.7 | -18.12% | 29757.89 | 32426.61 | 2668.72 | 8.968% | 82939.81 | 40926.33 | -42013.48 | -50.66% | 6298.6 | 17992.48 | 11693.88 | 185.7% | 2096.82 | 7800 | 5703.18 | 272% | 242.13 | 324.5 | 82.37 | 34.02% | 2020-08-14 01:00
Mississauga | 2020 | 634519 | Switch Replacement (LT41128) | 99 | COMPLETE | BOM not accurate | Labour est. under | Vehicle Under Estimated | Beaudrie, Scott | No | Alectra Utilities | Paul Murphy | 117763.77 | 70381.36 | -47382.41 | -40.24% | 30777.99 | 23556.96 | -7221.03 | -23.46% | 78338.36 | 34033.25 | -44305.11 | -56.56% | 6550.6 | 12791.15 | 6240.55 | 95.27% | 2096.82 | 0 | -2096.82 | -100% | 251.47 | 236 | -15.47 | -6.152% | 2020-08-14 01:00
Mississauga | 2021 | 634530 | CHURCH STREET - MAIDEN LANE (BORE SHOT) | 99 | COMPLETE | Labour est. under | Cont Est Under | BOM not accurate | Beaudrie, Scott | No | Cudzilo, Tomasz | Rob Elliot | 144229.31 | 161355.89 | 17126.58 | 11.87% | 34604.24 | 50029.33 | 15425.09 | 44.58% | 4890.82 | 8417.62 | 3526.8 | 72.11% | 3696.25 | 13703.95 | 10007.7 | 270.8% | 101038 | 89204.99 | -11833.01 | -11.71% | 136.67 | 282 | 145.33 | 106.3% | 2021-10-28 01:00
Mississauga | 2022 | 634825 | MTO- WINSTON CHURCHILL BLVD AND 401 | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Over | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 65460.42 | 36130.76 | -29329.66 | -44.81% | 28785.81 | 11574.81 | -17211 | -59.79% | 27515.05 | 20142.5 | -7372.55 | -26.79% | 3759.56 | 1901 | -1858.56 | -49.44% | 5400 | 2512.45 | -2887.55 | -53.47% | 198.26 | 92.5 | -105.76 | -53.34% | 2022-05-17 01:00
Mississauga | 2021 | 634872 | POLE RELOCATION - MISSISSAUGA RD. & SEVENOAKS DR. | 99 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Under Estimated | Lacombe, Joel | No | Garcha, Tirath | Paul Murphy | 152661.11 | 87018.99 | -65642.12 | -43% | 94892.31 | 37262.2 | -57630.11 | -60.73% | 13322.38 | 11293.12 | -2029.26 | -15.23% | 9341.19 | 14312 | 4970.81 | 53.21% | 35105.23 | 24151.67 | -10953.56 | -31.2% | 534.82 | 306 | -228.82 | -42.78% | 2021-04-20
Mississauga | 2022 | 634874 | ERIN MILLS NE BLOCK 2 - RESTAURANTS & RENTAL | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-17 01:00
Mississauga | 2022 | 634875 | ERIN MILLS NE BLOCK 3 - CONDOMINIUM | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-12-17 01:00
Mississauga | 2020 | 634933 | QUEENSTON DR OH MINI REBUILD | 99 | COMPLETE | Estimate incorrect | Labour est. over | N/A | Beaudrie, Scott | No | Alectra Utilities | Paul Murphy | 108570.7 | 86084.47 | -22486.23 | -20.71% | 67855 | 46181.72 | -21673.28 | -31.94% | 12323.45 | 8374.62 | -3948.83 | -32.04% | 15972.25 | 23321.1 | 7348.85 | 46.01% | 12420 | 8207.03 | -4212.97 | -33.92% | 549.39 | 493.5 | -55.89 | -10.17% | 2020-06-12 01:00
Mississauga | 2021 | 634962 | 6305 KATESON DR - ORLANDO | 99 | COMPLETE | BOM not accurate | Covid-19 | Cont Est Under | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 151544.56 | 213429.47 | 61884.91 | 40.84% | 43969.05 | 42425.76 | -1543.29 | -3.51% | 63450.87 | 109711.29 | 46260.42 | 72.91% | 5425 | 8870.66 | 3445.66 | 63.51% | 38699.64 | 52421.76 | 13722.12 | 35.46% | 317.84 | 450 | 132.16 | 41.58% | 2021-02-02 01:00
Mississauga | 2021 | 634965 | 50 CAPSTON DRIVE | 99 | COMPLETE | Labour est. over | N/A | N/A | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 151045.11 | 139210.38 | -11834.73 | -7.835% | 43994.48 | 30419.39 | -13575.09 | -30.86% | 61481.85 | 60091.48 | -1390.37 | -2.261% | 5529.94 | 5304.58 | -225.36 | -4.075% | 40038.84 | 43394.93 | 3356.09 | 8.382% | 317.42 | 277.5 | -39.92 | -12.58% | 2021-04-21
Mississauga | 2020 | 634981 | JOINT USE PERMIT HM2019-113 AND HM2019-114 (REMOVALS) - 4000 NASHUA DR - MISS | 99 | COMPLETE | No Feedback from Const | Labour est. under | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 5384.79 | 7498.33 | 2113.54 | 39.25% | 1392.25 | 3732.69 | 2340.44 | 168.1% | 190.64 | 0 | -190.64 | -100% | 179.4 | 615.64 | 436.24 | 243.2% | 3622.5 | 3150 | -472.5 | -13.04% | 12 | 35 | 23 | 191.7% | 2020-09-18 01:00
Mississauga | 2021 | 634983 | WINDJAMMER UG REBUILD | 99 | COMPLETE | Under 10% | Estimate incorrect | N/A | Beaudrie, Scott | Yes | Tempra, Troylan | Paul Tremblay | 4613689.28 | 4704847.78 | 91158.5 | 1.976% | 274494.29 | 610996.78 | 336502.49 | 122.6% | 35625.63 | 51569.09 | 15943.46 | 44.75% | 52029.21 | 60540.68 | 8511.47 | 16.36% | 4251540.15 | 3981591.23 | -269948.92 | -6.349% | 2553.74 | 2114.5 | -439.24 | -17.2% | 2021-03-26 01:00
Mississauga | 2020 | 634996 | 126 CUMBERLAND DRIVE ANCHOR RELOCATION | 99 | COMPLETE | Labour est. over | N/A | N/A | Lacombe, Joel | No | Alectra Utilities | Paul Murphy | 4678.41 | 1501.24 | -3177.17 | -67.91% | 3317.59 | 1113.72 | -2203.87 | -66.43% | 148.52 | 175.52 | 27 | 18.18% | 672.3 | 212 | -460.3 | -68.47% | 540 | 0 | -540 | -100% | 24 | 8 | -16 | -66.67% | 2020-03-14 01:00
Mississauga | 2020 | 635022 | JOINT USE PERMIT HM2019-115 - CAWTHRA RD - MISS | 99 | COMPLETE | Inaccurate design | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 6611.62 | 5597.98 | -1013.64 | -15.33% | 1833.98 | 1832.34 | -1.64 | -0.08942% | 644.26 | 0 | -644.26 | -100% | 221.08 | 615.64 | 394.56 | 178.5% | 3912.3 | 3150 | -762.3 | -19.48% | 13.08 | 12 | -1.08 | -8.257% | 2020-12-10 01:00
Mississauga | 2021 | 635187 | 5086 CREDITVIEW ROAD UNDERGROUND RELOCATIONS | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 3735.29 | 3735.29 |  | 0 | 3199.68 | 3199.68 |  | 0 | 0 | 0 |  | 0 | 535.61 | 535.61 |  | 0 | 0 | 0 |  | 0 | 4 | 4 |  | 2022-02-11 01:00
Mississauga | 2021 | 635205 | 880 AVONHEAD ROAD - NEW SERVICE NS00012665 | 99 | COMPLETE | Material Over Estimated | Cont Est Under | N/A | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 79999.73 | 96726.4 | 16726.67 | 20.91% | 24827.23 | 21419.29 | -3407.94 | -13.73% | 59875.85 | 50804.5 | -9071.35 | -15.15% | 3236.21 | 5305.95 | 2069.74 | 63.96% | 14410.44 | 19196.66 | 4786.22 | 33.21% | 214.43 | 233 | 18.57 | 8.66% | 2021-03-18 01:00
Mississauga | 2020 | 635337 | ALEXANDRIA REBUILD | 99 | COMPLETE | Cont Est Over | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 351791.23 | 266766.81 | -85024.42 | -24.17% | 29735.69 | 22660.49 | -7075.2 | -23.79% | 60884.98 | 62803.98 | 1919 | 3.152% | 34.2 | 483.31 | 449.11 | 1313% | 261136.36 | 180819.03 | -80317.33 | -30.76% | 0 | 23 | 23 |  | 2020-12-17 01:00
Mississauga | 2021 | 635338 | BEXHILL REBUILD | 99 | COMPLETE | Under 10% | Labour est. over | Vehicle Over Estimated- | Beaudrie, Scott | No | Matai, Ihssan (Sam) | Paul Murphy | 386249.82 | 352998.82 | -33251 | -8.609% | 256210.47 | 154997.89 | -101212.58 | -39.5% | 39740.28 | 36617.58 | -3122.7 | -7.858% | 45479.07 | 87719.48 | 42240.41 | 92.88% | 44820 | 73663.87 | 28843.87 | 64.35% | 2128.9 | 1573 | -555.9 | -26.11% | 2021-04-30
Mississauga | 2022 | 635339 | MEADOW WOOD RD REBUILD | 99 | COMPLETE | Estimate incorrect | Vehicle Under Estimated | Labour est. under | Beaudrie, Scott | No | Matai, Ihssan (Sam) | Paul Murphy | 959122.84 | 1250819.07 | 291696.23 | 30.41% | 433257.88 | 520953.81 | 87695.93 | 20.24% | 127256.07 | 145974.25 | 18718.18 | 14.71% | 112408.89 | 283250.16 | 170841.27 | 152% | 286200 | 300483.35 | 14283.35 | 4.991% | 3931.2 | 4712.5 | 781.3 | 19.87% | 2022-01-19 01:00
Mississauga | 2020 | 635340 | ROMETOWN REBUILD PHASE 1 | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Mark Bobanovic | 365962.73 | 462996.3 | 97033.57 | 26.51% | 30531.66 | 46942.42 | 16410.76 | 53.75% | 62657.07 | 78789.55 | 16132.48 | 25.75% | 239.4 | 1308.96 | 1069.56 | 446.8% | 272534.6 | 335805.37 | 63270.77 | 23.22% | 0 | 36 | 36 |  | 2020-11-24 01:00
Mississauga | 2020 | 635341 | VICTORIA & BARRY ST | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Alectra Utilities | Rob Elliot | 310518.69 | 212018.99 | -98499.7 | -31.72% | 215891.52 | 101418.96 | -114472.56 | -53.02% | 26863.07 | 30402.43 | 3539.36 | 13.18% | 35320.9 | 39956.43 | 4635.53 | 13.12% | 32443.2 | 40241.17 | 7797.97 | 24.04% | 1753 | 1108 | -645 | -36.79% | 2020-10-29 01:00
Mississauga | 2020 | 635342 | JOYMAR DR - ANCHOR RELOCATE | 99 | COMPLETE | Estimate incorrect | Flagging | N/A | Beaudrie, Scott | No | Alectra Utilities | Paul Murphy | 12311.39 | 10089.48 | -2221.91 | -18.05% | 6399.29 | 5908.89 | -490.4 | -7.663% | 1221.3 | 2293.38 | 1072.08 | 87.78% | 910.8 | 1887.21 | 976.41 | 107.2% | 3780 | 0 | -3780 | -100% | 33.48 | 40 | 6.52 | 19.47% | 2020-07-23 01:00
Mississauga | 2020 | 635351 | 1180 BRITANNIA ROAD EAST | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Alectra Utilities | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-10 01:00
Mississauga | 2020 | 635352 | CREDITWOODLANDS (NORTH OF QUEENSTON DRIVE) | 99 | COMPLETE | Labour est. over | Covid-19 | BOM not accurate | Beaudrie, Scott | No | Alectra Utilities | Rob Elliot | 111261.17 | 112346.6 | 1085.43 | 0.9756% | 65358.38 | 47029.27 | -18329.11 | -28.04% | 13121.79 | 17762.12 | 4640.33 | 35.36% | 13341 | 22625.63 | 9284.63 | 69.59% | 19440 | 24929.58 | 5489.58 | 28.24% | 523.22 | 502 | -21.22 | -4.056% | 2020-08-10 01:00
Mississauga | 2020 | 635476 | 68F2-ABANDON FEEDER FROM L34077 TO S6365 | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- |  | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 19529.28 | 8930.64 | -10598.64 | -54.27% | 15896.48 | 7477.84 | -8418.64 | -52.96% | 0 | 0 | 0 |  | 3632.8 | 1452.8 | -2180 | -60.01% | 0 | 0 | 0 |  | 120 | 63 | -57 | -47.5% | 2020-09-23 01:00
Mississauga | 2022 | 635493 | 2020 TRANSFORMER REPLACEMENT BATCH 6 - 15 UNITS | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Handy, James | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-23 01:00
Mississauga | 2022 | 635494 | 2020 TRANSFORMER REPLACEMENT BATCH 7 - 9 UNITS | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Handy, James | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-23 01:00
Mississauga | 2022 | 635495 | 2020 TRANSFORMER REPLACEMENT BATCH 8 - 12 UNITS | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Handy, James | XMoinuddin, Saad | 0 | 12.61 | 12.61 |  | 0 | 12.61 | 12.61 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-10-23 01:00
Mississauga | 2021 | 635539 | JOINT USE PERMIT HM2020-001 - CREDITVIEW RD - MISS | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Johnson, William | XMoinuddin, Saad | 0 | 3574.13 | 3574.13 |  | 0 | 424.13 | 424.13 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3150 | 3150 |  | 0 | 0 | 0 |  | 2020-09-21 01:00
Mississauga | 2020 | 635572 | SWGR REPLACEMENT - SG1457 | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 94714.62 | 86436.63 | -8277.99 | -8.74% | 23188.84 | 11113.05 | -12075.79 | -52.08% | 68152.14 | 73430.62 | 5278.48 | 7.745% | 3373.64 | 1892.96 | -1480.68 | -43.89% | 0 | 0 | 0 |  | 183.76 | 101 | -82.76 | -45.04% | 2020-07-30 01:00
Mississauga | 2020 | 635573 | SWGR REPLACEMENT - SG1636 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 185501.83 | 160080.78 | -25421.05 | -13.7% | 42935.37 | 15680.75 | -27254.62 | -63.48% | 135819.18 | 140360.23 | 4541.05 | 3.343% | 6747.28 | 4039.8 | -2707.48 | -40.13% | 0 | 0 | 0 |  | 367.52 | 153 | -214.52 | -58.37% | 2020-03-18 01:00
Mississauga | 2020 | 635574 | SWGR REPLACEMENT - SG1448 | 99 | COMPLETE | Labour est. over | Estimate incorrect |  | Beaudrie, Scott | Yes | Alectra Utilities | Paul Tremblay | 94714.62 | 89256.26 | -5458.36 | -5.763% | 23188.84 | 13246.37 | -9942.47 | -42.88% | 68152.14 | 73131.61 | 4979.47 | 7.306% | 3373.64 | 2878.28 | -495.36 | -14.68% | 0 | 0 | 0 |  | 183.76 | 130 | -53.76 | -29.26% | 2020-07-06 01:00
Mississauga | 2020 | 635575 | SWGR REPLACEMENT - SG1152 | 99 | COMPLETE | BOM not accurate | Labour est. over | Estimate incorrect | Beaudrie, Scott | Yes | Alectra Utilities | Peter Costantini | 131559.72 | 92433.87 | -39125.85 | -29.74% | 29007.3 | 18787.86 | -10219.44 | -35.23% | 98638.72 | 70828.15 | -27810.57 | -28.19% | 3913.7 | 2817.86 | -1095.84 | -28% | 0 | 0 | 0 |  | 238 | 205 | -33 | -13.87% | 2020-11-17 01:00
Mississauga | 2021 | 635647 | 7330 MISSISSAUGA RD - NEW SERVICE | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 81557.18 | 87070.05 | 5512.87 | 6.76% | 34289.71 | 22583.94 | -11705.77 | -34.14% | 53917.59 | 46299.32 | -7618.27 | -14.13% | 7431.88 | 3884 | -3547.88 | -47.74% | 8268 | 14302.79 | 6034.79 | 72.99% | 289.95 | 244.5 | -45.45 | -15.68% | 2021-10-26 01:00
Mississauga | 2021 | 635660 | 1305 CAWTHRA RD - TX UPGRADE | 99 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 130324.65 | 95404.2 | -34920.45 | -26.79% | 52359.62 | 18975.48 | -33384.14 | -63.76% | 65255.83 | 58147.35 | -7108.48 | -10.89% | 10727.88 | 3916 | -6811.88 | -63.5% | 24331.32 | 14365.37 | -9965.95 | -40.96% | 409.95 | 186 | -223.95 | -54.63% | 2021-09-20 01:00
Mississauga | 2021 | 635713 | OLD CREDITVIEW ROAD AND CREDITVIEW ROAD POLE RELOCATIONS - REGION OF PEEL | 99 | COMPLETE | Under 10% | BOM not accurate | Cont Est Under | Lacombe, Joel | No | Watters, Maxwell | Mark Bobanovic | 338890.68 | 328872.29 | -10018.39 | -2.956% | 43193.63 | 48740.44 | 5546.81 | 12.84% | 92533.05 | 66727.97 | -25805.08 | -27.89% | 0 | 0 | 0 |  | 203164 | 213403.88 | 10239.88 | 5.04% | 0 | 74.25 | 74.25 |  | 2021-11-26 01:00
Mississauga | 2021 | 635716 | 3020 LENWORTH DRIVE - MISS - NS - 500KVA | 99 | COMPLETE | Labour est. over | Cont Est Under | N/A | Mandic, Goran | No | Roy, Akash | Peter Costantini | 83099.8 | 103100.98 | 20001.18 | 24.07% | 38312.52 | 28675.96 | -9636.56 | -25.15% | 37480.38 | 35607.21 | -1873.17 | -4.998% | 4888.9 | 5611 | 722.1 | 14.77% | 24768 | 33206.81 | 8438.81 | 34.07% | 319.9 | 256 | -63.9 | -19.97% | 2021-11-11 01:00
Mississauga | 2020 | 635729 | (SG1290) REMOVAL - REXWOOD RD. | 99 | COMPLETE | Labour est. over | BOM not accurate | Estimate incorrect | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 88656.37 | 43908.46 | -44747.91 | -50.47% | 46534 | 10447.48 | -36086.52 | -77.55% | 31833.49 | 10792.21 | -21041.28 | -66.1% | 3496.76 | 1482.29 | -2014.47 | -57.61% | 6792.12 | 21186.48 | 14394.36 | 211.9% | 411.64 | 77.5 | -334.14 | -81.17% | 2020-08-04 01:00
Mississauga | 2020 | 635738 | (SG1690) REMOVAL - DILLINGWOOD DR. | 99 | COMPLETE | Labour est. under | BOM not used |  | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 221559.42 | 234695.28 | 13135.86 | 5.929% | 22870.98 | 41445.85 | 18574.87 | 81.22% | 0 | 4644.75 | 4644.75 |  | 840 | 4238.8 | 3398.8 | 404.6% | 197848.44 | 184215.88 | -13632.56 | -6.89% | 188 | 187 | -1 | -0.5319% | 2020-10-26 01:00
Mississauga | 2020 | 635750 | ENOLA AVE LOW SECONDARY SERVICES (MISSISSAUGA) | 99 | COMPLETE | BOM not used | Estimate incorrect |  | Beaudrie, Scott | No | Alectra Utilities | Macdougall, Stephen | 22141.98 | 17639.61 | -4502.37 | -20.33% | 8314.43 | 6309.42 | -2005.01 | -24.11% | 1660.75 | 0 | -1660.75 | -100% | 2116.8 | 1280.19 | -836.61 | -39.52% | 10050 | 10050 | 0 | 0% | 83.6 | 57 | -26.6 | -31.82% | 2020-08-10 01:00
Mississauga | 2022 | 635762 | CENTRA SOUTH TX REPLACEMENT - BATCH 18 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Paul Tremblay | 24025.07 | 0 | -24025.07 | -100% | 9560.58 | 0 | -9560.58 | -100% | 10626.25 | 0 | -10626.25 | -100% | 2542.24 | 0 | -2542.24 | -100% | 1296 | 0 | -1296 | -100% | 82.32 | 0 | -82.32 | -100% | 2020-08-31 01:00
Mississauga | 2020 | 635763 | CENTRAL SOUTH TX REPLACEMENT - BATCH 19 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 12602.44 | 10800.52 | -1801.92 | -14.3% | 4497.37 | 3005.23 | -1492.14 | -33.18% | 7052.68 | 6874.7 | -177.98 | -2.524% | 1052.39 | 920.59 | -131.8 | -12.52% | 0 | 0 | 0 |  | 33.68 | 24 | -9.68 | -28.74% | 2020-08-31 01:00
Mississauga | 2021 | 635764 | CENTRAL SOUTH TX REPLACEMENT - BATCH 20 | 99 | COMPLETE | Labour est. over | Cont Est Under | Vac truck | Beaudrie, Scott | No | Webb-Murre, Paige | Glenn Guile | 82914.84 | 73904.73 | -9010.11 | -10.87% | 14517.04 | 4804.29 | -9712.75 | -66.91% | 64762.84 | 62784.86 | -1977.98 | -3.054% | 3634.96 | 1081.69 | -2553.27 | -70.24% | 0 | 5233.89 | 5233.89 |  | 127.62 | 38 | -89.62 | -70.22% | 2021-01-15 01:00
Mississauga | 2020 | 635765 | CENTRAL SOUTH TX REPLACEMENT - BATCH 21 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 30321.95 | 11128.6 | -19193.35 | -63.3% | 7548.27 | 2395.67 | -5152.6 | -68.26% | 9868.9 | 8290.54 | -1578.36 | -15.99% | 2104.78 | 379.74 | -1725.04 | -81.96% | 10800 | 0 | -10800 | -100% | 69.36 | 16 | -53.36 | -76.93% | 2020-09-24 01:00
Mississauga | 2021 | 635766 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #6 | 99 | COMPLETE | Labour est. under |  |  | Beaudrie, Scott | No | Karan, Andjelo | Glenn Guile | 74043.18 | 99498.19 | 25455.01 | 34.38% | 24416.18 | 30075.19 | 5659.01 | 23.18% | 37035 | 36187.68 | -847.32 | -2.288% | 7992 | 7760 | -232 | -2.903% | 4600 | 25475.32 | 20875.32 | 453.8% | 243.8 | 340 | 96.2 | 39.46% | 2021-02-10 01:00
Mississauga | 2020 | 635767 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #7 | 99 | COMPLETE | Est. Int. - Act. External | BOM not accurate |  | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 22009.41 | 41979.91 | 19970.5 | 90.74% | 7614.88 | 6029.46 | -1585.42 | -20.82% | 10581.43 | 18392.34 | 7810.91 | 73.82% | 2497.5 | 2360 | -137.5 | -5.506% | 1315.6 | 15198.11 | 13882.51 | 1055% | 74 | 57 | -17 | -22.97% | 2020-12-22 01:00
Mississauga | 2020 | 635768 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #8 | 99 | COMPLETE | Under 10% | Est. Int. - Act. External |  | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 22009.41 | 24641.83 | 2632.42 | 11.96% | 7614.88 | 2361.73 | -5253.15 | -68.99% | 10581.43 | 11048.28 | 466.85 | 4.412% | 2497.5 | 0 | -2497.5 | -100% | 1315.6 | 11231.82 | 9916.22 | 753.7% | 74 | 25 | -49 | -66.22% | 2020-12-03 01:00
Mississauga | 2020 | 635769 | CENTRAL SOUTH TX REPLACEMENT - BATCH 22 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 33158.82 | 26561.47 | -6597.35 | -19.9% | 10708.15 | 5856.33 | -4851.82 | -45.31% | 19868.1 | 19338.64 | -529.46 | -2.665% | 2582.57 | 1366.5 | -1216.07 | -47.09% | 0 | 0 | 0 |  | 89.94 | 56 | -33.94 | -37.74% | 2020-12-19 01:00
Mississauga | 2020 | 635770 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #9 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 23810.73 | 22383.74 | -1426.99 | -5.993% | 7533.88 | 5928.68 | -1605.2 | -21.31% | 13779.35 | 12639.33 | -1140.02 | -8.273% | 2497.5 | 2178.27 | -319.23 | -12.78% | 0 | 1637.46 | 1637.46 |  | 74 | 76 | 2 | 2.703% | 2020-11-25 01:00
Mississauga | 2021 | 635772 | CENTRAL SOUTH TX REPLACEMENT - BATCH 23 | 99 | COMPLETE | Labour est. over | Cont Est Over | Vac truck | Beaudrie, Scott | No | Webb-Murre, Paige | Glenn Guile | 57869.56 | 44998.62 | -12870.94 | -22.24% | 17222.72 | 12905.06 | -4317.66 | -25.07% | 19737.78 | 18082.44 | -1655.34 | -8.387% | 4709.06 | 4111.48 | -597.58 | -12.69% | 16200 | 9899.64 | -6300.36 | -38.89% | 153.52 | 132 | -21.52 | -14.02% | 2021-01-15 01:00
Mississauga | 2020 | 635773 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #10 | 99 | COMPLETE | Under 10% | Est. Int. - Act. External |  | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 22009.41 | 19943.78 | -2065.63 | -9.385% | 7614.88 | 1577.34 | -6037.54 | -79.29% | 10581.43 | 10839.92 | 258.49 | 2.443% | 2497.5 | 0 | -2497.5 | -100% | 1315.6 | 7526.52 | 6210.92 | 472.1% | 74 | 14 | -60 | -81.08% | 2020-11-26 01:00
Mississauga | 2020 | 635774 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #11 | 99 | COMPLETE | Est. Int. - Act. External |  |  | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 46885.73 | 55141.63 | 8255.9 | 17.61% | 13064.65 | 2937.92 | -10126.73 | -77.51% | 26453.58 | 34383.09 | 7929.51 | 29.98% | 4078.5 | 0 | -4078.5 | -100% | 3289 | 17820.62 | 14531.62 | 441.8% | 148 | 21 | -127 | -85.81% | 2020-11-30 01:00
Mississauga | 2020 | 635775 | CENTRAL SOUTH TX REPLACMENT - BATCH 24 | 99 | COMPLETE | Labour est. over | Cont Est Over | Vac truck | Beaudrie, Scott | No | Alectra Utilities | Peter Costantini | 74909.86 | 56236.01 | -18673.85 | -24.93% | 23200.23 | 16495.77 | -6704.46 | -28.9% | 34670.39 | 35452.31 | 781.92 | 2.255% | 6239.24 | 4287.93 | -1951.31 | -31.27% | 10800 | 0 | -10800 | -100% | 205.78 | 184.5 | -21.28 | -10.34% | 2020-11-05 01:00
Mississauga | 2020 | 635776 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #12 | 99 | COMPLETE | Under 10% | Est. Int. - Act. External | BOM not accurate | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 25404.95 | 27854.71 | 2449.76 | 9.643% | 4633.72 | 1946.23 | -2687.49 | -58% | 17957.13 | 13380.62 | -4576.51 | -25.49% | 1498.5 | 0 | -1498.5 | -100% | 1315.6 | 12527.86 | 11212.26 | 852.3% | 74 | 16 | -58 | -78.38% | 2020-12-22 01:00
Mississauga | 2020 | 635777 | CENTRAL SOUTH TX REPLACEMENT - BATCH 25 | 99 | COMPLETE | Est. Int. - Act. External |  |  | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 33033.69 | 15800.16 | -17233.53 | -52.17% | 9760.51 | 2631.67 | -7128.84 | -73.04% | 9868.9 | 4695.46 | -5173.44 | -52.42% | 2604.28 | 0 | -2604.28 | -100% | 10800 | 8473.03 | -2326.97 | -21.55% | 84.16 | 2 | -82.16 | -97.62% | 2020-12-21 01:00
Mississauga | 2020 | 635778 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #13 | 99 | COMPLETE | Labour est. over | Vehicle Not Charged |  | Beaudrie, Scott | No | Alectra Utilities | Peter Costantini | 18491.87 | 26415.16 | 7923.29 | 42.85% | 5348.34 | 8827.73 | 3479.39 | 65.06% | 10581.43 | 12299.75 | 1718.32 | 16.24% | 1246.5 | 3207.68 | 1961.18 | 157.3% | 1315.6 | 2080 | 764.4 | 58.1% | 74 | 110 | 36 | 48.65% | 2020-11-04 01:00
Mississauga | 2020 | 635779 | CENTRAL SOUTH TX REPLACEMENT - BATCH 26 | 99 | COMPLETE | BOM not accurate | Labour est. over | Vac truck | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 47080.29 | 13539.16 | -33541.13 | -71.24% | 15612.9 | 3304.41 | -12308.49 | -78.84% | 21857.83 | 9570.2 | -12287.63 | -56.22% | 4209.56 | 664.55 | -3545.01 | -84.21% | 5400 | 0 | -5400 | -100% | 138.72 | 34 | -104.72 | -75.49% | 2020-09-29 01:00
Mississauga | 2020 | 635780 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #14 | 99 | COMPLETE | Under 10% | Est. Int. - Act. External |  | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 30028.98 | 31252.49 | 1223.51 | 4.074% | 9186.43 | 4525.88 | -4660.55 | -50.73% | 15872.15 | 11701.2 | -4170.95 | -26.28% | 2997 | 1445.61 | -1551.39 | -51.76% | 1973.4 | 13579.8 | 11606.4 | 588.1% | 103.6 | 45.5 | -58.1 | -56.08% | 2020-12-09 01:00
Mississauga | 2020 | 635781 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #15 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 23833.34 | 23491.44 | -341.9 | -1.435% | 6184.84 | 5803.67 | -381.17 | -6.163% | 14011.6 | 9998.24 | -4013.36 | -28.64% | 1663.5 | 1766.38 | 102.88 | 6.185% | 1973.4 | 5923.15 | 3949.75 | 200.1% | 111.1 | 74 | -37.1 | -33.39% | 2020-11-04 01:00
Mississauga | 2020 | 635783 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #16 | 99 | COMPLETE | Est. Int. - Act. External |  |  | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 17561.59 | 22396.11 | 4834.52 | 27.53% | 5348.34 | 1570.34 | -3778 | -70.64% | 9651.15 | 9684.12 | 32.97 | 0.3416% | 1246.5 | 0 | -1246.5 | -100% | 1315.6 | 11141.65 | 9826.05 | 746.9% | 74 | 12 | -62 | -83.78% | 2020-12-23 01:00
Mississauga | 2020 | 635784 | CENTRAL-SOUTH TX REPLACEMENT - BATCH #17 | 99 | COMPLETE | Est. Int. - Act. External | Material Req incorrectly | RFC not approved in time | Beaudrie, Scott | No | Alectra Utilities | K-Line Construction | 41349.9 | 73541.26 | 32191.36 | 77.85% | 8511.93 | 17314.87 | 8802.94 | 103.4% | 27626.77 | 39413.94 | 11787.17 | 42.67% | 2580 | 4770.21 | 2190.21 | 84.89% | 2631.2 | 12042.24 | 9411.04 | 357.7% | 140.7 | 189 | 48.3 | 34.33% | 2020-11-12 01:00
Mississauga | 2020 | 635785 | CENTRAL SOUTH TX REPLACEMENT - BATCH 27 | 99 | COMPLETE | Labour est. over | Cont Est Over | Vac truck | Beaudrie, Scott | No | Alectra Utilities | Peter Costantini | 25524.38 | 16675.9 | -8848.48 | -34.67% | 8150.7 | 5346.56 | -2804.14 | -34.4% | 9868.9 | 8862.34 | -1006.56 | -10.2% | 2104.78 | 1110.46 | -994.32 | -47.24% | 5400 | 1356.54 | -4043.46 | -74.88% | 69.36 | 56 | -13.36 | -19.26% | 2020-08-11 01:00
Mississauga | 2020 | 635786 | CENTRAL SOUTH TX REPLACEMENT - BATCH 28 | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 29673.18 | 15551.65 | -14121.53 | -47.59% | 14805.21 | 7415.73 | -7389.48 | -49.91% | 10986.59 | 5587.04 | -5399.55 | -49.15% | 3881.38 | 2548.88 | -1332.5 | -34.33% | 0 | 0 | 0 |  | 109.55 | 83 | -26.55 | -24.24% | 2020-10-22 01:00
Mississauga | 2021 | 635787 | CENTRAL SOUTH TX REPLACEMENT - BATCH 29 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Glenn Guile | 11041.45 | 7927.63 | -3113.82 | -28.2% | 5471.23 | 2293.37 | -3177.86 | -58.08% | 4252.15 | 4814.08 | 561.93 | 13.22% | 1318.07 | 420 | -898.07 | -68.14% | 0 | 400.18 | 400.18 |  | 47.79 | 15 | -32.79 | -68.61% | 2021-01-07 01:00
Mississauga | 2020 | 635788 | CENTRAL SOUTH TX REPLACEMENT - BATCH 30 | 99 | COMPLETE | Material Req incorrectly | Labour est. over |  | Beaudrie, Scott | No | Alectra Utilities | Peter Costantini | 17001.92 | 4073.31 | -12928.61 | -76.04% | 4497.37 | 2887.97 | -1609.4 | -35.79% | 6052.16 | 1.15 | -6051.01 | -99.98% | 1052.39 | 863.05 | -189.34 | -17.99% | 5400 | 321.14 | -5078.86 | -94.05% | 35.68 | 24 | -11.68 | -32.74% | 2020-09-14 01:00
Mississauga | 2020 | 635789 | CENTRAL SOUTH TX REPLACEMENT - BATCH 31 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Alectra Utilities | Peter Costantini | 45908.81 | 44891.39 | -1017.42 | -2.216% | 12092.73 | 14994.33 | 2901.6 | 23.99% | 25305.64 | 27742.31 | 2436.67 | 9.629% | 3110.44 | 2154.75 | -955.69 | -30.73% | 5400 | 0 | -5400 | -100% | 116.94 | 155 | 38.06 | 32.55% | 2020-08-12 01:00
Mississauga | 2020 | 635790 | CENTRAL SOUTH TX REPLACMENT - BATCH 32 | 99 | COMPLETE | Labour est. over | Vac truck |  | Beaudrie, Scott | No | Alectra Utilities | Peter Costantini | 29909.25 | 16025.81 | -13883.44 | -46.42% | 9916.03 | 3468.28 | -6447.75 | -65.02% | 11988.94 | 11326.24 | -662.7 | -5.528% | 2604.28 | 1231.29 | -1372.99 | -52.72% | 5400 | 0 | -5400 | -100% | 96.96 | 34 | -62.96 | -64.93% | 2020-08-14 01:00
Mississauga | 2020 | 635807 | 2020 REBUILD - TX8829 - TX8830 (RATHBURN AND WILCOX) | 99 | COMPLETE | Under 10% | BOM not accurate |  | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 269842.91 | 281485.99 | 11643.08 | 4.315% | 45763.4 | 51056.62 | 5293.22 | 11.57% | 16058.43 | 27022.54 | 10964.11 | 68.28% | 6371.48 | 12181.98 | 5810.5 | 91.2% | 201649.6 | 191224.85 | -10424.75 | -5.17% | 356.5 | 379 | 22.5 | 6.311% | 2020-09-01 01:00
Mississauga | 2020 | 635809 | BELL BONDS - Y59508 + Y10198 - MISS | 99 | COMPLETE | Labour est. under | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 2296.93 | 2831.97 | 535.04 | 23.29% | 2085.24 | 1923.58 | -161.66 | -7.753% | 0 | 0 | 0 |  | 211.69 | 908.39 | 696.7 | 329.1% | 0 | 0 | 0 |  | 11 | 16 | 5 | 45.45% | 2020-09-16 01:00
Mississauga | 2022 | 635843 | CENTRAL SOUTH TRANSFORMER REPLACEMENT - TX 8325 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | XMoinuddin, Saad | 0 | 16.06 | 16.06 |  | 0 | 16.06 | 16.06 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-03 01:00
Mississauga | 2020 | 635875 | 3060 HURONTARIO ST. | 99 | COMPLETE | Labour est. over | Cont Est Under | Material Req incorrectly | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 78077.56 | 36207.84 | -41869.72 | -53.63% | 53168.13 | 19334.54 | -33833.59 | -63.64% | 12062.93 | 9294.7 | -2768.23 | -22.95% | 5286.5 | 4552.6 | -733.9 | -13.88% | 7560 | 3026 | -4534 | -59.97% | 300.3 | 197 | -103.3 | -34.4% | 2020-12-15 01:00
Mississauga | 2020 | 635913 | (SG1757) REPLACEMENT - 217 STATESMAN DR. | 99 | COMPLETE | Under 10% | Labour est. over | Civil contractor | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 89218.49 | 93615.76 | 4397.27 | 4.929% | 21672.95 | 12938.45 | -8734.5 | -40.3% | 66626.76 | 72030.65 | 5403.89 | 8.111% | 918.78 | 3423.44 | 2504.66 | 272.6% | 0 | 5223.22 | 5223.22 |  | 192.16 | 122.5 | -69.66 | -36.25% | 2020-12-18 01:00
Mississauga | 2020 | 635917 | (SG1280) REPLACEMENT - RATHBURN PARK | 99 | COMPLETE | Labour est. over | BOM not accurate | Estimate incorrect | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 42846.88 | 42613.98 | -232.9 | -0.5436% | 21654.95 | 7754 | -13900.95 | -64.19% | 19949.87 | 29059.56 | 9109.69 | 45.66% | 1242.06 | 2369.8 | 1127.74 | 90.8% | 0 | 3430.62 | 3430.62 |  | 189.82 | 68.5 | -121.32 | -63.91% | 2020-09-25 01:00
Mississauga | 2020 | 635921 | (SG1798) REPLACEMENT - 295 EGLINTON | 99 | COMPLETE | Labour est. over | BOM not accurate | Estimate incorrect | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 87442.33 | 110902.03 | 23459.7 | 26.83% | 19952.63 | 10972.88 | -8979.75 | -45.01% | 66626.92 | 87984.5 | 21357.58 | 32.06% | 862.78 | 2758.89 | 1896.11 | 219.8% | 0 | 9185.76 | 9185.76 |  | 174.16 | 95.5 | -78.66 | -45.17% | 2020-10-02 01:00
Mississauga | 2020 | 635922 | (SG1561) REMOVAL - STRATHAVEN DR. | 99 | COMPLETE | Restoration | Labour est. over |  | Beaudrie, Scott | No | Alectra Utilities | Glenn Guile | 69064.67 | 82602.99 | 13538.32 | 19.6% | 45216.19 | 31655.47 | -13560.72 | -29.99% | 9874.4 | 10950.61 | 1076.21 | 10.9% | 3174.08 | 6511.73 | 3337.65 | 105.2% | 10800 | 33485.18 | 22685.18 | 210% | 372.05 | 247.5 | -124.55 | -33.48% | 2020-10-18 01:00
Mississauga | 2020 | 635923 | (SG1313) REMOVAL - SKYMARK AVE | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Alectra Utilities | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-02 01:00
Mississauga | 2020 | 635924 | (SG1787) REPLACEMENT - CANTAY RD. | 99 | COMPLETE | BOM not accurate | Vehicle Under Estimated | Restoration | Beaudrie, Scott | No | Alectra Utilities | Peter Costantini | 91617.05 | 103376.97 | 11759.92 | 12.84% | 24038.02 | 21569.56 | -2468.46 | -10.27% | 66632.25 | 74448.29 | 7816.04 | 11.73% | 946.78 | 4369.92 | 3423.14 | 361.6% | 0 | 2989.2 | 2989.2 |  | 192.16 | 206 | 13.84 | 7.202% | 2020-12-02 01:00
Mississauga | 2021 | 635925 | (SG1778) REPLACEMENT - WHITE HEART LANE | 99 | COMPLETE | Under 10% | Labour est. over | Civil contractor | Beaudrie, Scott | No | Ferry, Rodnne | Glenn Guile | 91617.05 | 101393.16 | 9776.11 | 10.67% | 24038.02 | 15872.85 | -8165.17 | -33.97% | 66632.25 | 74182.89 | 7550.64 | 11.33% | 946.78 | 3003.43 | 2056.65 | 217.2% | 0 | 8333.99 | 8333.99 |  | 168.16 | 120 | -48.16 | -28.64% | 2021-01-14 01:00
Mississauga | 2022 | 635973 | 5300 BRADCO BLVD - SERVICE UPGRADE | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Pellerin, Patrick | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-16 01:00
Mississauga | 2020 | 636007 | 1798 LANTERN FLY HOLLOW- TX60525 REPLACEMENT - O/H 50KVA 120/240V | 99 | COMPLETE | Labour est. under | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Rob Elliot | 13940.69 | 10186.21 | -3754.48 | -26.93% | 7834.73 | 4449.34 | -3385.39 | -43.21% | 4069.92 | 3757.6 | -312.32 | -7.674% | 1725 | 1979.27 | 254.27 | 14.74% | 311.04 | 0 | -311.04 | -100% | 46.54 | 25.5 | -21.04 | -45.21% | 2020-08-12 01:00
Mississauga | 2020 | 636008 | 3930 NASHUA DR - TX11102 REPLACEMENT - O/H 500KVA 347/600V | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Alectra Utilities | Paul Murphy | 29747.51 | 27734.97 | -2012.54 | -6.765% | 7678.54 | 6560.78 | -1117.76 | -14.56% | 20999.8 | 19698.37 | -1301.43 | -6.197% | 1069.17 | 1475.82 | 406.65 | 38.03% | 0 | 0 | 0 |  | 41 | 43 | 2 | 4.878% | 2020-08-16 01:00
Mississauga | 2020 | 636009 | 7252 WAINBROOK RD - TX6048 REPLACEMENT - O/H 50KVA 120/240V | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Alectra Utilities | Rob Elliot | 12341.2 | 11927.24 | -413.96 | -3.354% | 7792.31 | 6330.2 | -1462.11 | -18.76% | 3369.89 | 3088.44 | -281.45 | -8.352% | 1179 | 2508.6 | 1329.6 | 112.8% | 0 | 0 | 0 |  | 42 | 48 | 6 | 14.29% | 2020-08-20 01:00
Mississauga | 2022 | 636010 | 7140 TRANMERE DR - TX15235 REPLACEMENT - O/H 500KVA 347/600V | 99 | CANCELLED | N/A |  |  | Lucic, Marko | Yes | Ferry, Rodnne | XMoinuddin, Saad | 72569.57 | 0 | -72569.57 | -100% | 19423.97 | 0 | -19423.97 | -100% | 49563.93 | 0 | -49563.93 | -100% | 3581.67 | 0 | -3581.67 | -100% | 0 | 0 | 0 |  | 173.28 | 0 | -173.28 | -100% | 2020-10-01 01:00
Mississauga | 2020 | 636027 | DERRY ROAD & 401 DUCT BANK RELOCATIONS FOR WCC/MTO | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Lacombe, Joel | No | Alectra Utilities | Glenn Guile | 181657.99 | 152910.34 | -28747.65 | -15.83% | 26094.62 | 22404.57 | -3690.05 | -14.14% | 28203.47 | 27975.19 | -228.28 | -0.8094% | 3016.26 | 1912 | -1104.26 | -36.61% | 124343.64 | 100618.58 | -23725.06 | -19.08% | 159.59 | 96.5 | -63.09 | -39.53% | 2020-08-05 01:00
Mississauga | 2020 | 636057 | JOINT USE PERMIT HM2020-003 - GOREWAY DR - MISS | 99 | COMPLETE | No Feedback from Const | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 10105.78 | 7996.16 | -2109.62 | -20.88% | 3387.24 | 3453.77 | 66.53 | 1.964% | 846.5 | 0 | -846.5 | -100% | 358.8 | 1392.39 | 1033.59 | 288.1% | 5513.24 | 3150 | -2363.24 | -42.86% | 0 | 32 | 32 |  | 2020-08-24 01:00
Mississauga | 2020 | 636068 | 2260 MATHESON BLVD EAST | 99 | COMPLETE | Labour est. over | Material Req incorrectly | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 193614.63 | 145241.69 | -48372.94 | -24.98% | 50721.47 | 37829.41 | -12892.06 | -25.42% | 94289.11 | 57457.09 | -36832.02 | -39.06% | 7022.97 | 5357 | -1665.97 | -23.72% | 41581.08 | 44598.19 | 3017.11 | 7.256% | 392 | 383.5 | -8.5 | -2.168% | 2020-10-06 01:00
Mississauga | 2021 | 636069 | 985 HYDRO ROAD - MISS - NS - 3PH - 150KVA | 99 | COMPLETE | Material Over Estimated | Cont Est Over | Labour est. over | Mandic, Goran | No | Roy, Akash | Peter Costantini | 60280.89 | 46900.09 | -13380.8 | -22.2% | 27298.82 | 21200.79 | -6098.03 | -22.34% | 31605.19 | 14003.05 | -17602.14 | -55.69% | 4185.36 | 5939 | 1753.64 | 41.9% | 19541.52 | 4363.28 | -15178.24 | -77.67% | 239.44 | 292 | 52.56 | 21.95% | 2021-08-20 01:00
Mississauga | 2021 | 636072 | 185 ENFIELD PLACE -GWL REALTY ADVISORS | 99 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 131558.94 | 131595.99 | 37.05 | 0.02816% | 40498.6 | 31264.98 | -9233.62 | -22.8% | 42334.59 | 37258.2 | -5076.39 | -11.99% | 4932.23 | 3392 | -1540.23 | -31.23% | 66143.52 | 59371.81 | -6771.71 | -10.24% | 255.1 | 264.5 | 9.4 | 3.685% | 2021-07-28 01:00
Mississauga | 2020 | 636083 | 6688 VANGUARD DR - TX6086 REPLACEMENT - O/H 150KVA 120/208V | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Alectra Utilities | Paul Murphy | 15682.95 | 16077.22 | 394.27 | 2.514% | 4524.21 | 6685.89 | 2161.68 | 47.78% | 10125.57 | 7596.18 | -2529.39 | -24.98% | 1033.17 | 1795.15 | 761.98 | 73.75% | 0 | 0 | 0 |  | 45.52 | 40 | -5.52 | -12.13% | 2020-08-09 01:00
Mississauga | 2020 | 636084 | 522 GARDEN WALK - TX22683 REPLACEMENT - O/H 50KVA 120/240V | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated |  | Beaudrie, Scott | No | Alectra Utilities | Rob Elliot | 10101.36 | 16190.6 | 6089.24 | 60.28% | 4594.44 | 7700.49 | 3106.05 | 67.6% | 4069.92 | 4312.94 | 243.02 | 5.971% | 1149 | 4177.17 | 3028.17 | 263.5% | 288 | 0 | -288 | -100% | 41 | 68 | 27 | 65.85% | 2020-08-24 01:00
Mississauga | 2020 | 636085 | 1700 DERRY ROAD E - TX17101 REPLACEMENT - O/H 15KVA 120/240V | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Alectra Utilities | Rob Elliot | 8800.51 | 8956.48 | 155.97 | 1.772% | 4661.55 | 4901.78 | 240.23 | 5.153% | 2671.96 | 2466.68 | -205.28 | -7.683% | 1179 | 1588.02 | 409.02 | 34.69% | 288 | 0 | -288 | -100% | 47.56 | 40 | -7.56 | -15.9% | 2020-08-26 01:00
Mississauga | 2021 | 636087 | 2250 HOMELANDS- STARLIGHT INVESTMENTS | 99 | COMPLETE | BOM not used | Labour est. over | Restoration | Mandic, Goran | No | Jacinto, Gerardo | XMoinuddin, Saad | 21775.33 | 17314.98 | -4460.35 | -20.48% | 18666.87 | 11421.73 | -7245.14 | -38.81% | 1036.35 | 0 | -1036.35 | -100% | 992.11 | 1638 | 645.89 | 65.1% | 1080 | 4255.25 | 3175.25 | 294% | 123.49 | 101 | -22.49 | -18.21% | 2021-04-30
Mississauga | 2022 | 636105 | REPLACING 3 SPANS OF #6 PRIMARY WITH 1/0 FOR WO415169 ON MELTON COURT | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Matai, Ihssan (Sam) | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-08 01:00
Mississauga | 2020 | 636114 | GUYING RELOCATION - SENECA AVE (P22419) | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A | Lacombe, Joel | No | Alectra Utilities | Paul Murphy | 12965.78 | 3912.1 | -9053.68 | -69.83% | 8941.99 | 3281.31 | -5660.68 | -63.3% | 781.39 | 249.79 | -531.6 | -68.03% | 1406.4 | 381 | -1025.4 | -72.91% | 1836 | 0 | -1836 | -100% | 50.2 | 12 | -38.2 | -76.1% | 2020-08-10 01:00
Mississauga | 2021 | 636169 | 2200 BROMSGROVE RD. - 1200A NEW SERVICE REQUEST | 99 | COMPLETE | Material Under Estimated | Labour est. over | N/A | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 47630.31 | 80549.54 | 32919.23 | 69.11% | 25312.19 | 18008.78 | -7303.41 | -28.85% | 18018.3 | 35058 | 17039.7 | 94.57% | 3898.54 | 3029.5 | -869.04 | -22.29% | 22751.28 | 24453.26 | 1701.98 | 7.481% | 226.67 | 197.5 | -29.17 | -12.87% | 2021-06-21 01:00
Mississauga | 2020 | 636173 | JOINT USE PERMIT HM2020-007 - DERRY RD E - MISS | 99 | COMPLETE | Vehicle Under Estimated | Labour est. under | No Feedback from Const | O'Gay, Brian | No | Alectra Utilities | Paul Murphy | 3684.99 | 6955.37 | 3270.38 | 88.75% | 1780.59 | 3552.02 | 1771.43 | 99.49% | 0 | 315.33 | 315.33 |  | 179.4 | 1588.02 | 1408.62 | 785.2% | 1725 | 1500 | -225 | -13.04% | 14 | 24 | 10 | 71.43% | 2020-06-17 01:00
Mississauga | 2021 | 636202 | 6550 & 6570 GLEN ERIN DRIVE | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 101698.64 | 83826.76 | -17871.88 | -17.57% | 39085.31 | 20124 | -18961.31 | -48.51% | 44051.18 | 41533.88 | -2517.3 | -5.714% | 3748.15 | 3720 | -28.15 | -0.751% | 37164 | 18294.38 | -18869.62 | -50.77% | 169.33 | 232.5 | 63.17 | 37.31% | 2021-10-05 01:00
Mississauga | 2020 | 636211 | DEER RUN CRT UG REBUILD | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Alectra Utilities | Paul Tremblay | 234184.87 | 218338.47 | -15846.4 | -6.767% | 35485.66 | 36896.2 | 1410.54 | 3.975% | 3730.15 | 393.55 | -3336.6 | -89.45% | 3836.06 | 4072.89 | 236.83 | 6.174% | 191133 | 176975.83 | -14157.17 | -7.407% | 242.96 | 184.5 | -58.46 | -24.06% | 2020-09-11 01:00
Mississauga | 2021 | 636224 | 1888 MATTAWA - POLE P16741 | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 22140.05 | 28502.03 | 6361.98 | 28.74% | 699.93 | 2005.81 | 1305.88 | 186.6% | 3806.74 | 8823.76 | 5017.02 | 131.8% | 0 | 0 | 0 |  | 17633.38 | 17672.46 | 39.08 | 0.2216% | 0 | 0 | 0 |  | 2021-05-17 01:00
Mississauga | 2020 | 636288 | JOINT USE PERMIT HM2020-011 - PARK ST EAST - MISS | 99 | COMPLETE | No Feedback from Const | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 5820.3 | 4603.42 | -1216.88 | -20.91% | 2911.24 | 2487.78 | -423.46 | -14.55% | 800.97 | 0 | -800.97 | -100% | 245.09 | 615.64 | 370.55 | 151.2% | 1863 | 1500 | -363 | -19.48% | 14.04 | 16 | 1.96 | 13.96% | 2020-09-28 01:00
Mississauga | 2022 | 636298 | 1293 MEREDITH AVE | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-14 01:00
Mississauga | 2022 | 636413 | CARTTERA MANAGEMENT INC. 2445 SURVEYOR RD. | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Under | Mustachi, Randy | No | Huo, Lisa | Peter Costantini | 161397.6 | 127240.85 | -34156.75 | -21.16% | 56699.28 | 28526.82 | -28172.46 | -49.69% | 54102.83 | 40301.42 | -13801.41 | -25.51% | 5513.49 | 5808.5 | 295.01 | 5.351% | 45082 | 52604.11 | 7522.11 | 16.69% | 321.69 | 279.5 | -42.19 | -13.12% | 2022-06-06 01:00
Mississauga | 2020 | 636436 | GUYING RELOCATIONS - MAVIS RD (P18017, P18018) | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A | Lacombe, Joel | No | Alectra Utilities | Paul Murphy | 34804.03 | 23129.04 | -11674.99 | -33.54% | 22502.31 | 14906.05 | -7596.26 | -33.76% | 2997.67 | 2280.85 | -716.82 | -23.91% | 4499.4 | 2784 | -1715.4 | -38.13% | 4804.65 | 3158.14 | -1646.51 | -34.27% | 160.1 | 121 | -39.1 | -24.42% | 2020-09-09 01:00
Mississauga | 2021 | 636535 | MX - EGLINTON WEST EXTENSION - DRILL POWER SUPPLY - COMMERCE & CITATION | 99 | COMPLETE | Under 10% | Cont Est Under | BOM not accurate | Tobin, Michael | No | Chopra, Rabinder | Antonio Mina | 546635.27 | 589675.66 | 43040.39 | 7.874% | 131237.7 | 121822.14 | -9415.56 | -7.174% | 216882.79 | 189508.5 | -27374.29 | -12.62% | 28133.4 | 11868 | -16265.4 | -57.82% | 170381.38 | 266477.02 | 96095.64 | 56.4% | 640.51 | 714.25 | 73.74 | 11.51% | 2021-10-29 01:00
Mississauga | 2022 | 636649 | UG CABLE REPLACEMENT DARCEL AND BRANDON GATE | 99 | CANCELLED | N/A |  |  | Sidhu, Paul | Yes | Matai, Ihssan (Sam) | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-09 01:00
Mississauga | 2021 | 636650 | UG CABLE REPLACEMENT - SIGSBEE AND BRANDON GATE DRIVE- PHASE 2 | 99 | COMPLETE | Under 10% | Vehicle Under Estimated | BOM not accurate | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Antonio Mina | 2160987.55 | 2180063.49 | 19075.94 | 0.8827% | 111416.49 | 380855.55 | 269439.06 | 241.8% | 16434.64 | 25501.55 | 9066.91 | 55.17% | 16906.02 | 39017.69 | 22111.67 | 130.8% | 2016230.4 | 1734533.94 | -281696.46 | -13.97% | 774.11 | 1268 | 493.89 | 63.8% | 2021-09-09 01:00
Mississauga | 2020 | 636687 | ERIN MILLS PARKWAY ROAD WORK BETWEEN CREDIT VALLEY ROAD AND BRITANNIA ROAD | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A | Lacombe, Joel | No | Alectra Utilities | Macdougall, Stephen | 32698.56 | 17027.09 | -15671.47 | -47.93% | 16652.4 | 9523.2 | -7129.2 | -42.81% | 5148.42 | 5680.89 | 532.47 | 10.34% | 2745.9 | 1823 | -922.9 | -33.61% | 8151.84 | 0 | -8151.84 | -100% | 97.9 | 67.5 | -30.4 | -31.05% | 2020-11-02 01:00
Mississauga | 2021 | 636692 | LENARTHUR DR - LOW SECONDARIES | 99 | COMPLETE | Electrician | Labour est. over | Vehicle Over Estimated- | Lucic, Marko | No | Ferry, Rodnne | Gregory Dunfield | 50947.18 | 39195.83 | -11751.35 | -23.07% | 21217.94 | 17216.86 | -4001.08 | -18.86% | 339.7 | 0 | -339.7 | -100% | 2736 | 978.97 | -1757.03 | -64.22% | 26653.54 | 21000 | -5653.54 | -21.21% | 78 | 26 | -52 | -66.67% | 2021-10-27 01:00
Mississauga | 2020 | 636708 | ANCHOR RELOCATION AT P07954 EGLINTON AVE | 99 | COMPLETE | Estimate incorrect | Labour est. over | Material Req incorrectly | Lacombe, Joel | No | Alectra Utilities | Paul Murphy | 17524.96 | 6058.05 | -11466.91 | -65.43% | 12738 | 3498.56 | -9239.44 | -72.53% | 717.86 | 242.49 | -475.37 | -66.22% | 1909.1 | 962 | -947.1 | -49.61% | 2160 | 1355 | -805 | -37.27% | 105.8 | 29 | -76.8 | -72.59% | 2020-06-22 01:00
Mississauga | 2020 | 636733 | BELL BONDS - Y16415 - MISS | 99 | COMPLETE | Labour est. under | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 1299.47 | 0 | -1299.47 | -100% | 1193.62 | 0 | -1193.62 | -100% | 0 | 0 | 0 |  | 105.85 | 0 | -105.85 | -100% | 0 | 0 | 0 |  | 4 | 0 | -4 | -100% | 2020-09-21 01:00
Mississauga | 2022 | 636743 | 2022 - SIR JOHN HOMESTEAD UG CABLE REPLACEMENT PHASE 1 | 99 | COMPLETE | Labour est. under | Cont Est Under | Vehicle Under Estimated | Lucic, Marko | Yes | Ferry, Rodnne | Antonio Mina | 1165234.8 | 1307442.43 | 142207.63 | 12.2% | 137663.1 | 233301.42 | 95638.32 | 69.47% | 6852.42 | 7134.94 | 282.52 | 4.123% | 3247.28 | 11971.58 | 8724.3 | 268.7% | 1017472 | 1055034.49 | 37562.49 | 3.692% | 415.62 | 450.5 | 34.88 | 8.392% | 2022-11-07 01:00
Mississauga | 2021 | 636765 | 960 BRITANNIA RD E - 3000KVA TRANSFORMER UPGRADE | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 118319.75 | 117526.32 | -793.43 | -0.6706% | 34757.02 | 27085.12 | -7671.9 | -22.07% | 79571.99 | 73805.3 | -5766.69 | -7.247% | 5168.42 | 4088 | -1080.42 | -20.9% | 21172.32 | 12547.9 | -8624.42 | -40.73% | 224.56 | 264.5 | 39.94 | 17.79% | 2021-06-12 01:00
Mississauga | 2021 | 636776 | HULRT METROLINX - OMSF EXPANSION PROJECT - KENNEDY & 407 | 98 | COMPLETE | Cont Est Over | BOM not accurate | N/A | Paesano, Andrew | No | Jolie, Chris | Mark Bobanovic | 7096896.44 | 6133677.68 | -963218.76 | -13.57% | 30662.23 | 187463.8 | 156801.57 | 511.4% | 893075.59 | 946078.26 | 53002.67 | 5.935% | 2228 | 906.2 | -1321.8 | -59.33% | 6170930.62 | 4997870.55 | -1173060.07 | -19.01% | 173 | 316 | 143 | 82.66% | 2021-11-12 01:00
Mississauga | 2021 | 636784 | JOINT USE PERMIT HM2020-015 - SOUTHDOWN - MISS | 98 | COMPLETE | N/A |  |  | O'Gay, Brian | No | Johnson, William | XMoinuddin, Saad | 5088.56 | 4075.39 | -1013.17 | -19.91% | 2266.13 | 1066.58 | -1199.55 | -52.93% | 640.36 | 0 | -640.36 | -100% | 422.07 | 0 | -422.07 | -100% | 1760 | 3008.81 | 1248.81 | 70.96% | 14.3 | 0 | -14.3 | -100% | 2021-11-15 01:00
Mississauga | 2021 | 636785 | JOINT USE PERMIT HM2020-019 - ROYAL WINDSOR, LAKESHORE, SOUTHDOWN - MISS | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 4078.82 | 4475.87 | 397.05 | 9.734% | 1254.89 | 2667.05 | 1412.16 | 112.5% | 641.86 | 0 | -641.86 | -100% | 422.07 | 0 | -422.07 | -100% | 1760 | 1808.82 | 48.82 | 2.774% | 14.3 | 20 | 5.7 | 39.86% | 2021-08-02 01:00
Mississauga | 2020 | 636790 | JOINT USE PERMIT HM2020-027 - CREEKBANK - MISS | 99 | COMPLETE | No Feedback from Const | Labour est. under | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 5192.1 | 5946.07 | 753.97 | 14.52% | 1145.25 | 2180.43 | 1035.18 | 90.39% | 0 | 0 | 0 |  | 134.55 | 615.64 | 481.09 | 357.6% | 3912.3 | 3150 | -762.3 | -19.48% | 6 | 12 | 6 | 100% | 2020-12-10 01:00
Mississauga | 2021 | 636791 | JOINT USE PERMIT HM2020-028 - GOREWAY - MISS | 99 | COMPLETE | Cont Est Under | Civil contractor | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 6417.48 | 11237.97 | 4820.49 | 75.11% | 1926.54 | 2597.49 | 670.95 | 34.83% | 371.64 | 361.63 | -10.01 | -2.693% | 207 | 620 | 413 | 199.5% | 3912.3 | 7658.85 | 3746.55 | 95.76% | 12 | 16 | 4 | 33.33% | 2021-07-14 01:00
Mississauga | 2021 | 636797 | MONTEVIDEO & TREVISO PH-1 CABLE REPLACEMENT | 99 | COMPLETE | Under 10% | Material Req incorrectly | N/A | Lucic, Marko | Yes | Tempra, Troylan | Antonio Mina | 2567572.55 | 2605058.4 | 37485.85 | 1.46% | 116327.54 | 389149.5 | 272821.96 | 234.5% | 9675.85 | 1973.09 | -7702.76 | -79.61% | 14014.88 | 16895.89 | 2881.01 | 20.56% | 2427554.28 | 2197039.92 | -230514.36 | -9.496% | 817.21 | 556 | -261.21 | -31.96% | 2021-09-27 01:00
Mississauga | 2022 | 636873 | UG CABLE REPLACEMENT - MILLCREEK & ERIN MILLS PKWY | 99 | COMPLETE | Labour est. over | Cont Est Over |  | Lucic, Marko | Yes | Tempra, Troylan | Antonio Mina | 1282612.32 | 1190924.58 | -91687.74 | -7.149% | 242844.16 | 212089.54 | -30754.62 | -12.66% | 7957.35 | 8932.93 | 975.58 | 12.26% | 11683.35 | 8056.53 | -3626.82 | -31.04% | 1020127.46 | 961039.18 | -59088.28 | -5.792% | 616.01 | 347.5 | -268.51 | -43.59% | 2022-10-28 01:00
Mississauga | 2021 | 636918 | CABLE REPLACEMENT - DARCEL & BRANDON GATE | 99 | COMPLETE | Under 10% | Vehicle Under Estimated | Material Req incorrectly | Beaudrie, Scott | Yes | Cudzilo, Tomasz | Antonio Mina | 1566404.85 | 1421032.39 | -145372.46 | -9.281% | 176265.53 | 270374.71 | 94109.18 | 53.39% | 0 | 8127.97 | 8127.97 |  | 11978.32 | 21724.19 | 9745.87 | 81.36% | 1378161 | 1120651.02 | -257509.98 | -18.69% | 1270 | 787 | -483 | -38.03% | 2021-07-14 01:00
Mississauga | 2022 | 636983 | AREA 11 - TRUESCOTT AND DOWNSVIEW | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Ferry, Rodnne | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-21 01:00
Mississauga | 2022 | 637020 | CITATION PLACE INVESTIGATION | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Ferry, Rodnne | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-19 01:00
Mississauga | 2022 | 637032 | INSULATORS RENEWAL - BATCH #2 | 99 | COMPLETE | Labour est. over | BOM not accurate | Flagging | Lucic, Marko | No | Matai, Ihssan (Sam) | Gregory Dunfield | 107288.53 | 51535.42 | -55753.11 | -51.97% | 62189.81 | 28737.62 | -33452.19 | -53.79% | 23666.97 | 9887.09 | -13779.88 | -58.22% | 13871.75 | 12910.71 | -961.04 | -6.928% | 7560 | 0 | -7560 | -100% | 429.03 | 247 | -182.03 | -42.43% | 2022-03-17 01:00
Mississauga | 2022 | 637051 | 2531 CAWTHRA RD. 1PH SERVICE | 99 | CANCELLED | N/A |  |  | MacDougall, Stephen | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-08-29 01:00
Mississauga | 2020 | 637090 | OH TRANSFORMERS - CENTRAL SOUTH | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Alectra Utilities | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-06 01:00
Mississauga | 2022 | 637091 | 13 CP - POLE RENEWAL - BURNHAMTHORPE RD | 99 | COMPLETE | Cont Est Under | Labour est. under | Material Under Estimated | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Mark Bobanovic | 431274.32 | 439493.29 | 8218.97 | 1.906% | 37380.9 | 54325.95 | 16945.05 | 45.33% | 92473.43 | 95725.55 | 3252.12 | 3.517% | 0 | 0 | 0 |  | 301419.99 | 289441.79 | -11978.2 | -3.974% | 3493.84 | 19 | -3474.84 | -99.46% | 2022-12-06 01:00
Mississauga | 2020 | 637092 | UG TRANSFORMERS - CENTRAL SOUTH | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Alectra Utilities | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-15 01:00
Mississauga | 2022 | 637100 | POLES - CENTRAL SOUTH | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Billone, Justin | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-09-15 01:00
Mississauga | 2020 | 637156 | 7415 TORBRAM ROAD ANCHOR/DG CONFLICT | 99 | COMPLETE | Vac truck | Labour est. under | N/A | Lacombe, Joel | No | Alectra Utilities | Paul Murphy | 3131.06 | 7038.26 | 3907.2 | 124.8% | 2392.6 | 3783.54 | 1390.94 | 58.14% | 478.66 | 155.72 | -322.94 | -67.47% | 259.8 | 1019 | 759.2 | 292.2% | 0 | 2080 | 2080 |  | 12.6 | 31 | 18.4 | 146% | 2020-08-06 01:00
Mississauga | 2020 | 637174 | QUADREAL DEVELOPMENT - 1600 COURTNEYPARK DR. E. | 99 | COMPLETE | Engineering by-passed | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 101830.77 | 70634.25 | -31196.52 | -30.64% | 43324.75 | 21193.26 | -22131.49 | -51.08% | 49231.7 | 43055.15 | -6176.55 | -12.55% | 3874.32 | 4301.24 | 426.92 | 11.02% | 5400 | 2084.6 | -3315.4 | -61.4% | 249.15 | 196.5 | -52.65 | -21.13% | 2020-11-05 01:00
Mississauga | 2020 | 637240 | CAWTHRA & NEEDHAM POLE REPLACEMENTS FOR ROGERS ATTACHMENTS | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Alectra Utilities | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3 | 3 |  | 2021-08-20 01:00
Mississauga | 2022 | 637258 | 2460 ROYAL WINDSOR DR - MISS - UP - 3PH 1500KVA CUST. OWNEDTX | 99 | COMPLETE | Material Over Estimated | Labour est. over | Cont Est Under | Mandic, Goran | No | Pellerin, Patrick | Gregory Dunfield | 21763.89 | 13631.22 | -8132.67 | -37.37% | 11875.68 | 8885.54 | -2990.14 | -25.18% | 12477.19 | 1700.15 | -10777.04 | -86.37% | 2409.02 | 1376 | -1033.02 | -42.88% | 2 | 1669.53 | 1667.53 | 83376% | 101 | 44 | -57 | -56.44% | 2022-10-14 01:00
Mississauga | 2022 | 637294 | LOCATES AND SURVEYING FOR REGION’S SENIORS HEALTH AND WELLNESS VILLAGE | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Ferry, Rodnne | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-04-22
Mississauga | 2021 | 637322 | CABLE REPLACEMENT - REID DR AND QUEEN ST SOUTH | 99 | COMPLETE | Estimate incorrect | Civil contractor | N/A | Beaudrie, Scott | Yes | Ferry, Rodnne | Glenn Guile | 192926.15 | 399158.78 | 206232.63 | 106.9% | 43183.91 | 355758.77 | 312574.86 | 723.8% | 12981.54 | 17766.6 | 4785.06 | 36.86% | 8173.74 | 9261.38 | 1087.64 | 13.31% | 128586.96 | 16217.53 | -112369.43 | -87.39% | 285.96 | 229.5 | -56.46 | -19.74% | 2021-08-12 01:00
Mississauga | 2021 | 637341 | UG CABLE REPLACEMENT - L6405 TO L6177 - FOLKWAY DR & ERIN MILLS PKWY | 99 | COMPLETE | Under 10% | Scope change - unforeseen | BOM not accurate | Beaudrie, Scott | Yes | Cudzilo, Tomasz | Antonio Mina | 800083.18 | 737535.21 | -62547.97 | -7.818% | 97894.16 | 139968.21 | 42074.05 | 42.98% | 112367.83 | 85183.35 | -27184.48 | -24.19% | 6638.47 | 17938.22 | 11299.75 | 170.2% | 583182.72 | 494290.93 | -88891.79 | -15.24% | 757.72 | 541 | -216.72 | -28.6% | 2021-05-17 01:00
Mississauga | 2020 | 637348 | BAYLIS MEDICAL | 99 | COMPLETE | Cont Est Under | Labour est. over | N/A | MacDougall, Stephen | No | Alectra Utilities | Peter Costantini | 98291.25 | 95321.32 | -2969.93 | -3.022% | 50320.25 | 27663.91 | -22656.34 | -45.02% | 31529.69 | 32894.29 | 1364.6 | 4.328% | 3481.31 | 2947.32 | -533.99 | -15.34% | 12960 | 31815.8 | 18855.8 | 145.5% | 306.05 | 218 | -88.05 | -28.77% | 2020-10-26 01:00
Mississauga | 2021 | 637442 | P15298 POLE RELOCATION - 23 DE JONG DRIVE | 99 | COMPLETE | Labour est. over | Cont Est Over |  | Lacombe, Joel | No | Watters, Maxwell | Macdougall, Stephen | 26920.37 | 20970.04 | -5950.33 | -22.1% | 10407.52 | 7046.34 | -3361.18 | -32.3% | 2368.21 | 1340.12 | -1028.09 | -43.41% | 1400.64 | 3016 | 1615.36 | 115.3% | 12744 | 9567.58 | -3176.42 | -24.92% | 49.93 | 59 | 9.07 | 18.17% | 2021-01-26 01:00
Mississauga | 2021 | 637462 | 69 HIGH ST W - POLE P01935 | 99 | COMPLETE | Est. Int. - Act. External |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 50318.99 | 28805.5 | -21513.49 | -42.75% | 1031.54 | 2125.09 | 1093.55 | 106% | 9543.98 | 7679.42 | -1864.56 | -19.54% | 62.92 | 0 | -62.92 | -100% | 39680.55 | 19000.99 | -20679.56 | -52.12% | 1.66 | 0 | -1.66 | -100% | 2021-05-17 01:00
Mississauga | 2021 | 637507 | 400 AMBASSADOR DR. - MISS - UP - 3PH 1000KVA | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Roy, Akash | Peter Costantini | 80972.21 | 87671.75 | 6699.54 | 8.274% | 39536.61 | 17712.05 | -21824.56 | -55.2% | 42302.48 | 39022.08 | -3280.4 | -7.755% | 4012.12 | 3203 | -809.12 | -20.17% | 17471 | 27734.62 | 10263.62 | 58.75% | 338.45 | 178.5 | -159.95 | -47.26% | 2021-12-02 01:00
Mississauga | 2022 | 637521 | MONTEVIDEO & TREVISO PH2 CABLE REPLACEMENT | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Tempra, Troylan | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-15 01:00
Mississauga | 2022 | 637539 | PLATINUM DR. DEVELOPMENT - 3503 ODYSSEY DR. BLDG H | 99 | COMPLETE | Labour est. over | Cont Est Under | Vehicle Under Estimated | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 103250.16 | 86954.02 | -16296.14 | -15.78% | 47292.25 | 25855.76 | -21436.49 | -45.33% | 37747.37 | 37085 | -662.37 | -1.755% | 4210.54 | 5940 | 1729.46 | 41.07% | 14000 | 18073.26 | 4073.26 | 29.09% | 254.13 | 206 | -48.13 | -18.94% | 2022-02-04 01:00
Mississauga | 2022 | 637540 | PLATINUM DR. DEVELOPMENT - 3460 PLATINUM DR. BLDG B | 99 | COMPLETE | Material Over Estimated | Cont Est Under | Vehicle Under Estimated | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 212060.67 | 214669.36 | 2608.69 | 1.23% | 82812.69 | 62822.21 | -19990.48 | -24.14% | 84366.17 | 82128.85 | -2237.32 | -2.652% | 7881.81 | 13603.5 | 5721.69 | 72.59% | 37000 | 56114.8 | 19114.8 | 51.66% | 394.26 | 524 | 129.74 | 32.91% | 2022-02-08 01:00
Mississauga | 2021 | 637541 | PLATINUM DR. DEVELOPMENT - 3545 ODYSSEY DR. BLDG I | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-18 01:00
Mississauga | 2020 | 637549 | JOINT USE PERMIT HM2020-031 - DERRY W - MISS | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 7743.74 | 7057.54 | -686.2 | -8.861% | 1187.24 | 1634.1 | 446.86 | 37.64% | 95.34 | 0 | -95.34 | -100% | 89.7 | 293.44 | 203.74 | 227.1% | 6371.46 | 5130 | -1241.46 | -19.48% | 6 | 6 | 0 | 0% | 2020-08-19 01:00
Mississauga | 2020 | 637552 | NEW OH BANK TRANSFORMER - 1020 CARDIFF BLVD | 99 | COMPLETE | Converted Project | Engineering by-passed | N/A | Beaudrie, Scott | No | Alectra Utilities | Macdougall, Stephen | 67795.62 | 63623.9 | -4171.72 | -6.153% | 25202.49 | 21808.04 | -3394.45 | -13.47% | 31786.41 | 31434.78 | -351.63 | -1.106% | 3462.72 | 10381.08 | 6918.36 | 199.8% | 7344 | 0 | -7344 | -100% | 159.89 | 197 | 37.11 | 23.21% | 2020-08-12 01:00
Mississauga | 2022 | 637615 | CUSTOMER INITIATED SEC. OH REMOVAL& UG INSTALLATION – 28 ANN ST(WESTPORT CONDO) | 99 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Over Estimated- | Lacombe, Joel | No | Gonzales, Leonard | Paul Murphy | 172324.23 | 111823.01 | -60501.22 | -35.11% | 90801.29 | 55927.57 | -34873.72 | -38.41% | 7796.99 | 7529.87 | -267.12 | -3.426% | 15665.9 | 4839 | -10826.9 | -69.11% | 58060.05 | 43526.57 | -14533.48 | -25.03% | 482.18 | 238 | -244.18 | -50.64% | 2022-01-24 01:00
Mississauga | 2021 | 637643 | 3073 MERRITT AVE - HABITAT FOR HUMANITY | 99 | COMPLETE | Under 10% |  |  | Penner, Mitchell | No | Ricci, Leonardo | Mark Bobanovic | 88838.41 | 86023.74 | -2814.67 | -3.168% | 26506.14 | 26574.86 | 68.72 | 0.2593% | 306.3 | 519.88 | 213.58 | 69.73% | 1117.21 | 2532 | 1414.79 | 126.6% | 60908.76 | 56397 | -4511.76 | -7.407% | 121.7 | 134.5 | 12.8 | 10.52% | 2021-03-19 01:00
Mississauga | 2020 | 637652 | CABLE REPLACEMENT - SIR JOHN'S HOMESTEAD - NBM | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Alectra Utilities | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-08 01:00
Mississauga | 2020 | 637674 | ARGENTIA ROAD AT SG1782 UNDERGROUND CABLE RELOCATIONS | 99 | COMPLETE | Labour est. over | Cont Est Under | N/A | Lacombe, Joel | No | Alectra Utilities | Glenn Guile | 50439.51 | 52145.11 | 1705.6 | 3.381% | 33604.08 | 16904.67 | -16699.41 | -49.69% | 13560.12 | 12839.71 | -720.41 | -5.313% | 3275.31 | 2014.51 | -1260.8 | -38.49% | 0 | 20386.22 | 20386.22 |  | 229.36 | 100.5 | -128.86 | -56.18% | 2020-12-07 01:00
Mississauga | 2020 | 637709 | BARBER HOUSE DEMO | 99 | COMPLETE | Labour est. over | Estimate incorrect | N/A | D'Onofrio, Tony | No | Alectra Utilities | Paul Tremblay | 11929.42 | 4759.48 | -7169.94 | -60.1% | 10980.55 | 4119.48 | -6861.07 | -62.48% | 0 | 0 | 0 |  | 948.87 | 640 | -308.87 | -32.55% | 0 | 0 | 0 |  | 85.23 | 32 | -53.23 | -62.45% | 2020-09-02 01:00
Mississauga | 2021 | 637850 | JOINT USE PERMIT HM2020-032 - DUNDAS WEST - MISS | 99 | COMPLETE | Cont Est Over | N/A | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 10050.86 | 15913.24 | 5862.38 | 58.33% | 3853.97 | 6595.14 | 2741.17 | 71.13% | 314.13 | 1154.64 | 840.51 | 267.6% | 702 | 2647 | 1945 | 277.1% | 5180.76 | 5516.46 | 335.7 | 6.48% | 24 | 69.5 | 45.5 | 189.6% | 2021-06-17 01:00
Mississauga | 2021 | 637851 | JOINT USE PERMIT HM2020-033 - DUNDAS WEST - MISS | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 7239.5 | 9336.32 | 2096.82 | 28.96% | 2067.92 | 3729.94 | 1662.02 | 80.37% | 382.57 | 0 | -382.57 | -100% | 366.41 | 812 | 445.59 | 121.6% | 4422.6 | 4794.38 | 371.78 | 8.406% | 11.15 | 32 | 20.85 | 187% | 2021-06-18 01:00
Mississauga | 2020 | 637858 | JOINT USE PERMIT HM2020-040 - AVONHEAD - MISS | 99 | COMPLETE | Estimate incorrect | No Feedback from Const | N/A | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 6252.75 | 3651.38 | -2601.37 | -41.6% | 1391.64 | 1767.77 | 376.13 | 27.03% | 180.84 | 0 | -180.84 | -100% | 155.61 | 615.64 | 460.03 | 295.6% | 4524.66 | 1267.97 | -3256.69 | -71.98% | 6 | 12 | 6 | 100% | 2020-12-11 01:00
Mississauga | 2021 | 637882 | 6150 KENNEDY RD. SERVICE UPGRADE | 99 | COMPLETE | Material reused | Labour est. over | Cont Est Under | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 84543.66 | 13435.11 | -71108.55 | -84.11% | 23409.23 | 8054.82 | -15354.41 | -65.59% | 58380.35 | 2917.44 | -55462.91 | -95% | 2106.08 | 1286 | -820.08 | -38.94% | 648 | 1176.85 | 528.85 | 81.61% | 139.98 | 54 | -85.98 | -61.42% | 2021-12-18 01:00
Mississauga | 2020 | 637951 | JOB BELONGS TO BRAMPTON - BRAMPTON TERRITORY TO ADDRESS | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Alectra Utilities | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-17 01:00
Mississauga | 2020 | 637965 | JOINT USE PERMIT HM2020-041 - ENTERPRISE - MISS | 99 | COMPLETE | Scope change - unforeseen | Labour est. under | Vehicle Under Estimated | O'Gay, Brian | No | Alectra Utilities | Macdougall, Stephen | 7594 | 7115.32 | -478.68 | -6.303% | 2709.21 | 1428.7 | -1280.51 | -47.27% | 548 | 799.47 | 251.47 | 45.89% | 424.49 | 1737.15 | 1312.66 | 309.2% | 3912.3 | 3150 | -762.3 | -19.48% | 18.04 | 6 | -12.04 | -66.74% | 2020-12-17 01:00
Mississauga | 2022 | 638016 | POLE RELOCATION SHELL GAS STATION AIRPORT ROAD & BRESLER DRIVE | 99 | COMPLETE | Under 10% |  |  | Lacombe, Joel | No | Watters, Maxwell | Paul Murphy | 181738.39 | 178769.72 | -2968.67 | -1.633% | 89350.02 | 86123.27 | -3226.75 | -3.611% | 40631.53 | 28753.06 | -11878.47 | -29.23% | 22268.52 | 46931 | 24662.48 | 110.8% | 29488.32 | 16962.39 | -12525.93 | -42.48% | 544.89 | 1204 | 659.11 | 121% | 2022-12-05 01:00
Mississauga | 2022 | 638035 | 870 BALTIMORE AVE - 1PH PADMOUNT TX REPLACEMENT - TX2542 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Ferry, Rodnne | XMoinuddin, Saad | 0 | -340.22 | -340.22 |  | 0 | -340.22 | -340.22 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-02 01:00
Mississauga | 2022 | 638037 | 1408 SEAVIEW - 1PH PADMOUNT TX REPLACEMENT - TX1920 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Ferry, Rodnne | XMoinuddin, Saad | 0 | -340.22 | -340.22 |  | 0 | -340.22 | -340.22 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-02 01:00
Mississauga | 2022 | 638130 | 1063 DOUGLAS MCCURDY COMMON | 95 | COMPLETE | Cont Est Over | Labour est. over | Material Over Estimated | Mustachi, Randy | No | Gonzales, Leonard | Peter Costantini | 266503.47 | 159104.25 | -107399.22 | -40.3% | 113227.29 | 78028.28 | -35199.01 | -31.09% | 84550.89 | 67726.12 | -16824.77 | -19.9% | 10538.29 | 8082.5 | -2455.79 | -23.3% | 58187 | 5267.35 | -52919.65 | -90.95% | 416.16 | 285.75 | -130.41 | -31.34% | 2022-09-27 01:00
Mississauga | 2021 | 638193 | 1-15 TRANSFORMER REPLACEMENT - TX7823, TX128054, TX60921, TX60139, TX60216 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Ferry, Rodnne | Glenn Guile | 130594.11 | 140725.38 | 10131.27 | 7.758% | 45750.65 | 58057.48 | 12306.83 | 26.9% | 65444.35 | 61562.04 | -3882.31 | -5.932% | 8599.11 | 18929.86 | 10330.75 | 120.1% | 10800 | 2176 | -8624 | -79.85% | 347.91 | 494 | 146.09 | 41.99% | 2021-03-23 01:00
Mississauga | 2022 | 638211 | POLE REPLACEMENTS - HENDERIX CABLES ON DIXIE RD | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | XMoinuddin, Saad | 130131.26 | 0 | -130131.26 | -100% | 83031.22 | 0 | -83031.22 | -100% | 6840.84 | 0 | -6840.84 | -100% | 18259.2 | 0 | -18259.2 | -100% | 22000 | 0 | -22000 | -100% | 651.8 | 0 | -651.8 | -100% | 2022-06-16 01:00
Mississauga | 2022 | 638215 | ODYSSEY DRIVE - PHASE 3 (BUILDING J & K) | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 240707 | 233368.8 | -7338.2 | -3.049% | 95947.07 | 70618.8 | -25328.27 | -26.4% | 109103.93 | 110472.05 | 1368.12 | 1.254% | 9656 | 9502.5 | -153.5 | -1.59% | 26000 | 42775.45 | 16775.45 | 64.52% | 659.61 | 658 | -1.61 | -0.2441% | 2022-06-16 01:00
Mississauga | 2021 | 638216 | ODYSSEY DRIVE - PHASE 3 (BUILDING J) | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-04-16
Mississauga | 2021 | 638242 | 300 STATESMAN DR - MISS - UP - 3PH - 1500KVA | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Roy, Akash | Peter Costantini | 45141.35 | 43892.95 | -1248.4 | -2.766% | 22637.17 | 5577.3 | -17059.87 | -75.36% | 42192.88 | 36766.65 | -5426.23 | -12.86% | 2661.3 | 1076 | -1585.3 | -59.57% | 0 | 473 | 473 |  | 184.81 | 52.5 | -132.31 | -71.59% | 2021-04-24
Mississauga | 2021 | 638325 | (SG1155) REPLACEMENT - 5380 TERRY FOX WAY | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Beaudrie, Scott | No | Cudzilo, Tomasz | Manoj Rao Manjunath | 165539.32 | 188697.37 | 23158.05 | 13.99% | 40715.75 | 15070.2 | -25645.55 | -62.99% | 122876.5 | 131588.05 | 8711.55 | 7.09% | 1947.07 | 747.67 | -1199.4 | -61.6% | 0 | 41291.45 | 41291.45 |  | 332.32 | 44 | -288.32 | -86.76% | 2021-12-31 01:00
Mississauga | 2021 | 638330 | 6707 GOREWAY DR - MISS - UP - 3PH - 2000KVA | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Roy, Akash | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-30 01:00
Mississauga | 2021 | 638334 | GALLOPING CONDUCTORS- INTERPHASE SPACERS | 99 | COMPLETE | Labour est. over | Flagging | BOM not accurate | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | Paul Murphy | 219565.96 | 99317.23 | -120248.73 | -54.77% | 145021.62 | 52249.22 | -92772.4 | -63.97% | 29940.11 | 19612.01 | -10328.1 | -34.5% | 31417 | 26255.48 | -5161.52 | -16.43% | 13187.23 | 1200.52 | -11986.71 | -90.9% | 1281.4 | 401.5 | -879.9 | -68.67% | 2021-09-30 01:00
Mississauga | 2021 | 638336 | (SG1205) REPLACEMENT - 320 NAHANI WAY (EASTGATE PKWY) | 99 | COMPLETE | Material Req incorrectly | Est. Int. - Act. External | RFC not approved in time | Beaudrie, Scott | No | Cudzilo, Tomasz | Manoj Rao Manjunath | 88736.26 | 165848.97 | 77112.71 | 86.9% | 20901.14 | 5369.58 | -15531.56 | -74.31% | 66972.34 | 138271.04 | 71298.7 | 106.5% | 862.78 | 19.01 | -843.77 | -97.8% | 0 | 22189.34 | 22189.34 |  | 162.16 | 4.75 | -157.41 | -97.07% | 2021-11-26 01:00
Mississauga | 2021 | 638337 | (SG1483) REPLACEMENT - WILLOWDALE GDNS & WILLOWDALE CRT | 99 | COMPLETE | Vehicle Under Estimated | N/A | N/A | Beaudrie, Scott | No | Cudzilo, Tomasz | Antonio Mina | 92421.91 | 104393.8 | 11971.89 | 12.95% | 20901.14 | 22904.85 | 2003.71 | 9.587% | 70657.99 | 75501.09 | 4843.1 | 6.854% | 862.78 | 5987.86 | 5125.08 | 594% | 0 | 0 | 0 |  | 162.16 | 206 | 43.84 | 27.04% | 2021-10-22 01:00
Mississauga | 2021 | 638338 | (SG1588) REPLACEMENT - 1060 WHITE CLOVER WAY | 99 | COMPLETE | Est. Int. - Act. External | RFC not approved in time | N/A | Beaudrie, Scott | No | Cudzilo, Tomasz | Manoj Rao Manjunath | 93038.9 | 111693.46 | 18654.56 | 20.05% | 20901.14 | 8604.45 | -12296.69 | -58.83% | 71274.98 | 77750.07 | 6475.09 | 9.085% | 862.78 | 0 | -862.78 | -100% | 0 | 25338.94 | 25338.94 |  | 162.16 | 4 | -158.16 | -97.53% | 2021-12-31 01:00
Mississauga | 2021 | 638339 | (SG1683) REPLACEMENT - 4105 CREDIT POINTE DR. | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Cudzilo, Tomasz | Antonio Mina | 92438.98 | 100503.68 | 8064.7 | 8.724% | 20901.14 | 16802.54 | -4098.6 | -19.61% | 70675.06 | 79452.61 | 8777.55 | 12.42% | 862.78 | 4248.53 | 3385.75 | 392.4% | 0 | 0 | 0 |  | 162.16 | 147 | -15.16 | -9.349% | 2021-07-16 01:00
Mississauga | 2021 | 638363 | 16-30 TRANSFORMER REPLACEMENT - TX20539 TO TX19470 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Ferry, Rodnne | Glenn Guile | 156733.19 | 160908.46 | 4175.27 | 2.664% | 51971.28 | 43456.11 | -8515.17 | -16.38% | 84414.86 | 82099.38 | -2315.48 | -2.743% | 9547.05 | 15153.39 | 5606.34 | 58.72% | 10800 | 20199.58 | 9399.58 | 87.03% | 406.05 | 370 | -36.05 | -8.878% | 2021-12-13 01:00
Mississauga | 2021 | 638406 | 31-45 TRANSFORMER REPLACEMENT - TX13497 TO TX18421 | 99 | COMPLETE | Vehicle Under Estimated | Labour est. under | N/A | Beaudrie, Scott | No | Ferry, Rodnne | Peter Costantini | 140590.72 | 158638.4 | 18047.68 | 12.84% | 35146.61 | 53257.72 | 18111.11 | 51.53% | 88780.88 | 79350.24 | -9430.64 | -10.62% | 5863.23 | 19138.96 | 13275.73 | 226.4% | 10800 | 6891.48 | -3908.52 | -36.19% | 252.63 | 431 | 178.37 | 70.61% | 2021-04-13
Mississauga | 2021 | 638462 | 151 CITY CENTRE DRIVE- TEMPORARY SERVICE-ICI | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Over | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 94649.93 | 49011.4 | -45638.53 | -48.22% | 42021 | 10775.63 | -31245.37 | -74.36% | 61173.17 | 33491.97 | -27681.2 | -45.25% | 6092.7 | 3008 | -3084.7 | -50.63% | 7713.06 | 1735.8 | -5977.26 | -77.5% | 266.58 | 108 | -158.58 | -59.49% | 2021-02-04 01:00
Mississauga | 2021 | 638554 | SWGR REPLACEMENT-SG1571, 205 ANNAGEM BVLD | 99 | COMPLETE | Estimate incorrect | BOM cost variance | Est. Int. - Act. External | Beaudrie, Scott | Yes | Tempra, Troylan | Manoj Rao Manjunath | 102857.51 | 38040.33 | -64817.18 | -63.02% | 23567.96 | 7688.03 | -15879.93 | -67.38% | 75666.26 | 12055.89 | -63610.37 | -84.07% | 3623.29 | 133.06 | -3490.23 | -96.33% | 0 | 18163.35 | 18163.35 |  | 182.17 | 18.5 | -163.67 | -89.84% | 2021-11-26 01:00
Mississauga | 2021 | 638555 | SWGR REPLACEMENT-SG1460, 5750 RIVER GROVE | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | Yes | Tempra, Troylan | Glenn Guile | 102862.37 | 97954.14 | -4908.23 | -4.772% | 23549.87 | 13858.65 | -9691.22 | -41.15% | 75657.81 | 74283.73 | -1374.08 | -1.816% | 3654.69 | 3782.8 | 128.11 | 3.505% | 0 | 6028.96 | 6028.96 |  | 181.93 | 106 | -75.93 | -41.74% | 2021-04-09 01:00
Mississauga | 2021 | 638556 | SWGR REPLACEMENT-SG1503, RIVER GROVE & HIGHBROOK | 99 | COMPLETE | Labour est. over | Civil contractor | N/A | Beaudrie, Scott | Yes | Tempra, Troylan | Glenn Guile | 102862.37 | 91397.09 | -11465.28 | -11.15% | 23549.87 | 12105.27 | -11444.6 | -48.6% | 75657.81 | 71422.06 | -4235.75 | -5.599% | 3654.69 | 3155.5 | -499.19 | -13.66% | 0 | 4714.26 | 4714.26 |  | 181.93 | 83 | -98.93 | -54.38% | 2021-03-30 01:00
Mississauga | 2021 | 638558 | SWGR REPLACEMENT-SG1214, 3111 CONVAIR DR | 99 | COMPLETE | Scope – Cust | Scope change - unforeseen | N/A | Beaudrie, Scott | Yes | Tempra, Troylan | Glenn Guile | 133833.41 | 3194.29 | -130639.12 | -97.61% | 28591.37 | 3133.88 | -25457.49 | -89.04% | 100875.75 | 0 | -100875.75 | -100% | 4366.29 | 60.41 | -4305.88 | -98.62% | 0 | 0 | 0 |  | 230.6 | 4 | -226.6 | -98.27% | 2021-09-27 01:00
Mississauga | 2021 | 638559 | SWGR REPLACEMENT-SG1800, 5482 MIDDLEBURY DR | 99 | COMPLETE | Est. Int. - Act. External | Civil contractor | RFC not approved in time | Beaudrie, Scott | No | Tempra, Troylan | Manoj Rao Manjunath | 50893.73 | 42082.79 | -8810.94 | -17.31% | 20088.94 | 6004.21 | -14084.73 | -70.11% | 27709.42 | 28661.38 | 951.96 | 3.436% | 3095.37 | 0 | -3095.37 | -100% | 0 | 7417.2 | 7417.2 |  | 149.65 | 8 | -141.65 | -94.65% | 2021-12-31 01:00
Mississauga | 2021 | 638646 | 46-60 TRANSFORMER REPLACEMENT - TX8081 TO TX12421 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Ferry, Rodnne | Paul Tremblay | 203357.11 | 197371.71 | -5985.4 | -2.943% | 52912.46 | 66510.43 | 13597.97 | 25.7% | 129235.63 | 95602.9 | -33632.73 | -26.02% | 9147.58 | 22959.78 | 13812.2 | 151% | 12061.44 | 11170.07 | -891.37 | -7.39% | 831.93 | 573 | -258.93 | -31.12% | 2021-04-22
Mississauga | 2021 | 638654 | 61-75 - TRANSFORMER REPLACEMENT - TX12904 TO TX11295 | 99 | COMPLETE | Under 10% | Labour est. over | Civil contractor | Beaudrie, Scott | No | Ferry, Rodnne | Glenn Guile | 123367.53 | 121724.05 | -1643.48 | -1.332% | 45701.84 | 36596.85 | -9104.99 | -19.92% | 59110.49 | 51099.08 | -8011.41 | -13.55% | 7755.2 | 12484.2 | 4729 | 60.98% | 10800 | 21543.92 | 10743.92 | 99.48% | 349.2 | 273 | -76.2 | -21.82% | 2021-03-08 01:00
Mississauga | 2021 | 638656 | 76-90 - TRANSFORMER REPLACEMENT - TX11298 TO TX10708 | 99 | COMPLETE | Under 10% | BOM not accurate | Vehicle Under Estimated | Beaudrie, Scott | No | Ferry, Rodnne | Peter Costantini | 161163.52 | 173866.67 | 12703.15 | 7.882% | 59312.69 | 73465.18 | 14152.49 | 23.86% | 80450.78 | 65619.5 | -14831.28 | -18.44% | 10600.05 | 22968.09 | 12368.04 | 116.7% | 10800 | 11813.9 | 1013.9 | 9.388% | 492 | 678 | 186 | 37.8% | 2021-12-07 01:00
Mississauga | 2021 | 638657 | 91-105 - TRANSFORMER REPLACEMENT - TX10717 TO TX10568 | 99 | COMPLETE | Vehicle Under Estimated | BOM not accurate | Civil contractor | Beaudrie, Scott | No | Ferry, Rodnne | Glenn Guile | 152671.48 | 133744.51 | -18926.97 | -12.4% | 54884.16 | 43668.15 | -11216.01 | -20.44% | 76712.77 | 70245.96 | -6466.81 | -8.43% | 10274.55 | 16566.4 | 6291.85 | 61.24% | 10800 | 3264 | -7536 | -69.78% | 448.5 | 433 | -15.5 | -3.456% | 2021-06-22 01:00
Mississauga | 2021 | 638659 | 106-120 - TRANSFORMER REPLACEMENT - TX5733 TO TX8967 | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Beaudrie, Scott | No | Ferry, Rodnne | Paul Tremblay | 152428.33 | 127481.01 | -24947.32 | -16.37% | 48505.56 | 41109.36 | -7396.2 | -15.25% | 82720.69 | 59314.7 | -23405.99 | -28.3% | 10402.08 | 15717.33 | 5315.25 | 51.1% | 10800 | 11339.62 | 539.62 | 4.996% | 384.6 | 334 | -50.6 | -13.16% | 2021-05-31 01:00
Mississauga | 2021 | 638661 | 121-127 - TRANSFORMER REPLACEMENT - TX8385 TO TX4343 | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated | Cont Est Under | Lucic, Marko | No | Ferry, Rodnne | Peter Costantini | 69355.86 | 101797.5 | 32441.64 | 46.78% | 23808.98 | 44430.9 | 20621.92 | 86.61% | 42367.34 | 31162.97 | -11204.37 | -26.45% | 3179.54 | 14995.86 | 11816.32 | 371.6% | 0 | 11207.77 | 11207.77 |  | 153.3 | 395.5 | 242.2 | 158% | 2021-12-29 01:00
Mississauga | 2022 | 638693 | GALLOPING CONDUCTORS- INTERPHASE SPACERS-BATCH 2 | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Over Estimated | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | Paul Murphy | 193565.66 | 89745.65 | -103820.01 | -53.64% | 131982.06 | 57807.1 | -74174.96 | -56.2% | 26694.26 | 18524.22 | -8170.04 | -30.61% | 27625 | 12606.93 | -15018.07 | -54.36% | 7264.34 | 807.4 | -6456.94 | -88.89% | 1120 | 422.5 | -697.5 | -62.28% | 2022-10-21 01:00
Mississauga | 2021 | 638718 | 6950 KENNEDY RD - MISS - NS - 3PH - 500KVA | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Roy, Akash | Peter Costantini | 82398.86 | 75691.81 | -6707.05 | -8.14% | 32023.12 | 19616.5 | -12406.62 | -38.74% | 36595.94 | 27953.54 | -8642.4 | -23.62% | 3668.24 | 3627 | -41.24 | -1.124% | 32461.56 | 24494.77 | -7966.79 | -24.54% | 280.9 | 222 | -58.9 | -20.97% | 2021-10-11 01:00
Mississauga | 2021 | 638728 | 1517 BALLYCLARE DR-TX RELOCATE | 99 | COMPLETE | Scope – Const | Material reused | N/A | Beaudrie, Scott | No | Tempra, Troylan | Glenn Guile | 53226.43 | 24933.27 | -28293.16 | -53.16% | 18527.7 | 11457.01 | -7070.69 | -38.16% | 5630.53 | 1794.59 | -3835.94 | -68.13% | 2068.2 | 2117.5 | 49.3 | 2.384% | 27000 | 9564.17 | -17435.83 | -64.58% | 120.57 | 77.5 | -43.07 | -35.72% | 2021-04-28
Mississauga | 2020 | 638803 | 3210 HURONTARIO ST- MISS - SR - 3PH SERVICE REMOVAL | 99 | COMPLETE | Engineering by-passed | N/A | N/A | Mandic, Goran | No | Alectra Utilities | Peter Costantini | 10177.44 | 6499.07 | -3678.37 | -36.14% | 8493.48 | 4263.77 | -4229.71 | -49.8% | 0 | 0 | 0 |  | 1677.48 | 2235.3 | 557.82 | 33.25% | 6.48 | 0 | -6.48 | -100% | 69.81 | 52 | -17.81 | -25.51% | 2020-10-30 01:00
Mississauga | 2022 | 638852 | 1150 EGLINTON AVE E - MISS - UP - 1200A UPGRADE | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Hulnitski, Pavel | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-21 01:00
Mississauga | 2021 | 638872 | 2020 ROGERS BONDS 2 - MISS | 99 | COMPLETE | Civil contractor | Estimate incorrect |  | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 2484.93 | 3105.24 | 620.31 | 24.96% | 2240.1 | 493.42 | -1746.68 | -77.97% | 0 | 0 | 0 |  | 244.83 | 32 | -212.83 | -86.93% | 0 | 2579.82 | 2579.82 |  | 8 | 0 | -8 | -100% | 2021-04-23
Mississauga | 2021 | 638880 | OH SWITCH RENEWAL BATCH 1 | 99 | COMPLETE | Under 10% | Labour est. under | Cont Est Over | Beaudrie, Scott | Yes | Tempra, Troylan | Paul Murphy | 97203.56 | 99556.08 | 2352.52 | 2.42% | 53901.74 | 48874.32 | -5027.42 | -9.327% | 18292.64 | 15666.88 | -2625.76 | -14.35% | 12589.18 | 31612.08 | 19022.9 | 151.1% | 12420 | 3402.8 | -9017.2 | -72.6% | 433.32 | 474.5 | 41.18 | 9.503% | 2021-05-14
Mississauga | 2021 | 638881 | OH SWITCH RENEWAL BATCH 2 | 99 | COMPLETE | Under 10% | Labour est. under | Flagging | Beaudrie, Scott | Yes | Tempra, Troylan | Paul Murphy | 125919.4 | 176064.6 | 50145.2 | 39.82% | 58135.34 | 97102.25 | 38966.91 | 67.03% | 21126.93 | 12649.28 | -8477.65 | -40.13% | 15877.13 | 57037.77 | 41160.64 | 259.2% | 30780 | 9275.3 | -21504.7 | -69.87% | 460.75 | 984.5 | 523.75 | 113.7% | 2021-07-06 01:00
Mississauga | 2021 | 638882 | OH SWITCH RENEWAL BATCH 3 | 99 | COMPLETE | Police | Material reused | Vehicle Under Estimated | Beaudrie, Scott | No | Tempra, Troylan | Macdougall, Stephen | 50075.52 | 37177.13 | -12898.39 | -25.76% | 24975.01 | 23419.47 | -1555.54 | -6.228% | 11983.07 | 5021.41 | -6961.66 | -58.1% | 5376 | 8736.25 | 3360.25 | 62.5% | 7741.44 | 0 | -7741.44 | -100% | 192 | 201 | 9 | 4.688% | 2021-04-10 01:00
Mississauga | 2021 | 638883 | OH SWITCH RENEWAL BATCH 4 | 99 | COMPLETE | Labour est. over | Material reused | Police | Beaudrie, Scott | No | Tempra, Troylan | Macdougall, Stephen | 61770.35 | 20041.2 | -41729.15 | -67.56% | 31994.62 | 9210.65 | -22783.97 | -71.21% | 12701.29 | 7071.51 | -5629.78 | -44.32% | 7173 | 3759.04 | -3413.96 | -47.59% | 9901.44 | 0 | -9901.44 | -100% | 256 | 71 | -185 | -72.27% | 2021-01-25 01:00
Mississauga | 2021 | 638884 | OH SWITCH RENEWAL BATCH 5 | 99 | COMPLETE | Material reused | Labour est. over | Vehicle Under Estimated | Beaudrie, Scott | No | Tempra, Troylan | Macdougall, Stephen | 28160.12 | 22379.37 | -5780.75 | -20.53% | 18101.47 | 13171.23 | -4930.24 | -27.24% | 6350.65 | 2393.39 | -3957.26 | -62.31% | 3708 | 6814.75 | 3106.75 | 83.79% | 0 | 0 | 0 |  | 129 | 142 | 13 | 10.08% | 2021-03-11 01:00
Mississauga | 2022 | 638894 | POLE REPLACEMENT (2021) - BATCH #1 | 99 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | Paul Murphy | 201500.26 | 126129.33 | -75370.93 | -37.4% | 111400.94 | 69837.15 | -41563.79 | -37.31% | 33067.04 | 17193.31 | -15873.73 | -48% | 17328.11 | 28598.87 | 11270.76 | 65.04% | 39704.17 | 8940 | -30764.17 | -77.48% | 689.05 | 652 | -37.05 | -5.377% | 2022-04-29
Mississauga | 2021 | 638895 | GALLOPING CONDUCTORS- INTERPHASE SPACERS-BATCH 3 | 99 | COMPLETE | Labour est. over | Flagging | BOM not accurate | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | Rob Elliot | 137000.86 | 40370.12 | -96630.74 | -70.53% | 95246.57 | 22774.19 | -72472.38 | -76.09% | 14174.23 | 8735.46 | -5438.77 | -38.37% | 17507.72 | 7731.94 | -9775.78 | -55.84% | 10072.34 | 1128.53 | -8943.81 | -88.8% | 756.7 | 164 | -592.7 | -78.33% | 2021-08-19 01:00
Mississauga | 2022 | 638896 | GALLOPING CONDUCTORS- INTERPHASE SPACERS - BATCH 4 | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | N/A | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | Matthew Beach | 136686.56 | 108087.48 | -28599.08 | -20.92% | 93111.98 | 67253.52 | -25858.46 | -27.77% | 20060.68 | 18515.57 | -1545.11 | -7.702% | 20813.9 | 18451.98 | -2361.92 | -11.35% | 2700 | 3866.41 | 1166.41 | 43.2% | 645.7 | 625 | -20.7 | -3.206% | 2022-11-24 01:00
Mississauga | 2021 | 638988 | (SG1035) REPLACEMENT - 4314 FOREST FIRE LN., 1 | 99 | COMPLETE | Vehicle Under Estimated | Civil contractor | N/A | Beaudrie, Scott | Yes | Cudzilo, Tomasz | Antonio Mina | 166411.82 | 185826.53 | 19414.71 | 11.67% | 40162.7 | 42360.11 | 2197.41 | 5.471% | 124248.66 | 124515.84 | 267.18 | 0.215% | 2000.46 | 10995.16 | 8994.7 | 449.6% | 0 | 7955.42 | 7955.42 |  | 336.4 | 412.25 | 75.85 | 22.55% | 2021-12-13 01:00
Mississauga | 2021 | 638989 | (SG1036) REPLACEMENT - 4314 FOREST FIRE LN., 1 | 99 | COMPLETE | Under 10% | Civil contractor | N/A | Beaudrie, Scott | Yes | Cudzilo, Tomasz | Antonio Mina | 165738.6 | 181674.78 | 15936.18 | 9.615% | 40715.75 | 40599.06 | -116.69 | -0.2866% | 123075.78 | 122105.93 | -969.85 | -0.788% | 1947.07 | 8208.75 | 6261.68 | 321.6% | 0 | 10761.04 | 10761.04 |  | 332.32 | 364 | 31.68 | 9.533% | 2021-11-19 01:00
Mississauga | 2021 | 639070 | MONTEVIDEO & TREVISO PH2 UG CABLE REPLACEMENT | 99 | COMPLETE | Under 10% |  |  | Lucic, Marko | Yes | Tempra, Troylan | Antonio Mina | 2120242.9 | 1942132.52 | -178110.38 | -8.4% | 157821.62 | 334265.07 | 176443.45 | 111.8% | 9179.27 | 21669.03 | 12489.76 | 136.1% | 20705.13 | 29801.46 | 9096.33 | 43.93% | 1932536.88 | 1555743.79 | -376793.09 | -19.5% | 1124.21 | 989 | -135.21 | -12.03% | 2021-09-27 01:00
Mississauga | 2021 | 639072 | 7300 WEST CREDIT - MISS - NS - 300KVA | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Roy, Akash | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-02-26 01:00
Mississauga | 2021 | 639282 | POLE REPLACEMENT (2021) - BATCH #2 | 99 | COMPLETE | Scope – Const | Labour est. over | Vehicle Under Estimated | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | Rob Elliot | 69817.9 | 60668.11 | -9149.79 | -13.11% | 45178.69 | 28566.76 | -16611.93 | -36.77% | 10974.63 | 10101.47 | -873.16 | -7.956% | 6752.58 | 16441.26 | 9688.68 | 143.5% | 6912 | 5558.62 | -1353.38 | -19.58% | 303.51 | 288 | -15.51 | -5.11% | 2021-08-11 01:00
Mississauga | 2022 | 639316 | RFC#1 FOR "633865" 2020 POLE REPLACEMENT BATCH 2 - 12 POLES | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-04-19
Mississauga | 2022 | 639357 | 190 MATHESON BLVD | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Jacinto, Gerardo | XMoinuddin, Saad | 123397.01 | 4000.38 | -119396.63 | -96.76% | 40137.45 | 2959.78 | -37177.67 | -92.63% | 49804.29 | 0 | -49804.29 | -100% | 4042.27 | 0 | -4042.27 | -100% | 29413 | 1040.6 | -28372.4 | -96.46% | 271.58 | 0 | -271.58 | -100% | 2021-03-11 01:00
Mississauga | 2022 | 639370 | 18 CP - QUEENSWAY W OH REBUILD, (FROM DAMIEN WAY TO PINENEEDLE ROW) | 98 | COMPLETE | Material Under Estimated | Labour est. under | Cont Est Under | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Mark Bobanovic | 626398.62 | 698342.07 | 71943.45 | 11.49% | 38997.06 | 93575.5 | 54578.44 | 140% | 102494.45 | 148665.15 | 46170.7 | 45.05% | 0 | 171.42 | 171.42 |  | 484907.11 | 455930 | -28977.11 | -5.976% | 1912.53 | 18 | -1894.53 | -99.06% | 2022-12-22 01:00
Mississauga | 2021 | 639424 | 2104 LAUGHTON AVE - RELOCATE SERVICE DROP | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Tempra, Troylan | Macdougall, Stephen | 15407.36 | 14194.7 | -1212.66 | -7.871% | 8257.74 | 6330.44 | -1927.3 | -23.34% | 1031.71 | 755.57 | -276.14 | -26.77% | 1365.91 | 1512 | 146.09 | 10.7% | 4752 | 5596.69 | 844.69 | 17.78% | 40.44 | 49 | 8.56 | 21.17% | 2021-02-25 01:00
Mississauga | 2021 | 639443 | SWGR REPLACEMENT - SG1445 LAIRD RD & THE COLLEGEWAY | 99 | COMPLETE | Under 10% | Labour est. over | BOM not accurate | Lucic, Marko | Yes | Tempra, Troylan | Antonio Mina | 157204.94 | 164890.84 | 7685.9 | 4.889% | 42178.09 | 30953.61 | -11224.48 | -26.61% | 107493.69 | 121718.28 | 14224.59 | 13.23% | 7533.16 | 4713.18 | -2819.98 | -37.43% | 0 | 7505.77 | 7505.77 |  | 324.53 | 228.75 | -95.78 | -29.51% | 2021-12-13 01:00
Mississauga | 2021 | 639445 | SWGR REPLACEMENT-SG1504, ACROSS 3067 TACC DR | 99 | COMPLETE | Est. Int. - Act. External | Material Req incorrectly | RFC not approved in time | Beaudrie, Scott | Yes | Tempra, Troylan | Manoj Rao Manjunath | 49229.15 | 35685.58 | -13543.57 | -27.51% | 14895.16 | 3145.12 | -11750.04 | -78.88% | 32520.2 | 28328.76 | -4191.44 | -12.89% | 1813.79 | 0 | -1813.79 | -100% | 0 | 4211.7 | 4211.7 |  | 102.13 | 2 | -100.13 | -98.04% | 2021-12-31 01:00
Mississauga | 2022 | 639473 | MONTEVIDEO & TREVISO UG CABLE REPLACEMENT PH3 | 99 | COMPLETE | Under 10% |  |  | Lucic, Marko | Yes | Tempra, Troylan | Antonio Mina | 1916648.33 | 1863184.77 | -53463.56 | -2.789% | 359234.15 | 318708.08 | -40526.07 | -11.28% | 12983.27 | 17155.55 | 4172.28 | 32.14% | 30766.25 | 16184.11 | -14582.14 | -47.4% | 1513664.66 | 1510982.53 | -2682.13 | -0.1772% | 1088.07 | 696.5 | -391.57 | -35.99% | 2022-10-28 01:00
Mississauga | 2022 | 639551 | 6CP - 2022 POLE RENEWAL - QEW-NORTH SHERIDAN WAY MINI OH REBUILD | 99 | COMPLETE | Labour est. under | Vehicle Under Estimated | Cont Est Under | Beaudrie, Scott | Yes | Tempra, Troylan | Paul Murphy | 287775.65 | 495823.47 | 208047.82 | 72.3% | 107955.98 | 210455.73 | 102499.75 | 94.95% | 53239.48 | 79865.96 | 26626.48 | 50.01% | 27630.19 | 70155.18 | 42524.99 | 153.9% | 98950 | 135346.6 | 36396.6 | 36.78% | 782.68 | 2190.5 | 1407.82 | 179.9% | 2022-11-07 01:00
Mississauga | 2022 | 639554 | 4 POLE - 2021 POLE RENEWAL - BIRCHWOOD & JALNA AREA - 3 | 99 | COMPLETE | Under 10% |  |  | Lucic, Marko | Yes | Tempra, Troylan | Gregory Dunfield | 62722.81 | 61095.96 | -1626.85 | -2.594% | 30727 | 32416.96 | 1689.96 | 5.5% | 6704.2 | 5284.75 | -1419.45 | -21.17% | 6283.61 | 10301.57 | 4017.96 | 63.94% | 19008 | 13092.68 | -5915.32 | -31.12% | 192.14 | 251.5 | 59.36 | 30.89% | 2022-03-17 01:00
Mississauga | 2022 | 639555 | 1500 GULLEDEN - MISS - NS - 3PH - 1500KVA | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Over | Mandic, Goran | No | Roy, Akash | Peter Costantini | 127824.02 | 76795.43 | -51028.59 | -39.92% | 43411.12 | 16257.55 | -27153.57 | -62.55% | 47191.01 | 34495.47 | -12695.54 | -26.9% | 5101.89 | 3667 | -1434.89 | -28.12% | 32120 | 22375.41 | -9744.59 | -30.34% | 370.45 | 169 | -201.45 | -54.38% | 2022-10-03 01:00
Mississauga | 2022 | 639723 | 6933 TOMKEN RD - MISS - NS - 3PH - 1000KVA | 99 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Mandic, Goran | No | Roy, Akash | Peter Costantini | 149234.9 | 90150.69 | -59084.21 | -39.59% | 69912.84 | 25879.66 | -44033.18 | -62.98% | 58763.66 | 45317.43 | -13446.23 | -22.88% | 13867.4 | 5654 | -8213.4 | -59.23% | 6691 | 13299.6 | 6608.6 | 98.77% | 408 | 248 | -160 | -39.22% | 2022-05-09 01:00
Mississauga | 2022 | 639731 | 12 QTY - SPOT POLE REPLACEMENT BATCH 3 - MISSISSAUGA AND KANE | 99 | COMPLETE | Under 10% |  |  | Lucic, Marko | Yes | Ferry, Rodnne | Paul Murphy | 429791.79 | 444955.37 | 15163.58 | 3.528% | 230297.99 | 163098.58 | -67199.41 | -29.18% | 89966.41 | 101869.52 | 11903.11 | 13.23% | 71005.95 | 69578.85 | -1427.1 | -2.01% | 38521.44 | 110408.42 | 71886.98 | 186.6% | 1221.59 | 1276.5 | 54.91 | 4.495% | 2022-10-14 01:00
Mississauga | 2022 | 639732 | 7 QTY - SPOT POLE REPLACEMENT BATCH 4 - MISSISSAUGA AND KANE - 0 | 99 | COMPLETE | Under 10% |  |  | Lucic, Marko | Yes | Ferry, Rodnne | Rob Elliot | 156178.92 | 145284.17 | -10894.75 | -6.976% | 96003.54 | 49425.35 | -46578.19 | -48.52% | 16501.57 | 12317.96 | -4183.61 | -25.35% | 22829.81 | 11897.59 | -10932.22 | -47.89% | 20844 | 71643.27 | 50799.27 | 243.7% | 704.21 | 254.5 | -449.71 | -63.86% | 2022-04-06
Mississauga | 2022 | 639734 | 18 CP - OH REBUILD - OGDEN AVE PHASE 1 | 99 | COMPLETE | Cont Est Under | N/A | N/A | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Mark Bobanovic | 489349.82 | 564943.51 | 75593.69 | 15.45% | 59284.66 | 72086.54 | 12801.88 | 21.59% | 116703.77 | 123785.04 | 7081.27 | 6.068% | 0 | 0 | 0 |  | 313361.39 | 369071.93 | 55710.54 | 17.78% | 1680.43 | 11 | -1669.43 | -99.35% | 2022-09-16 01:00
Mississauga | 2021 | 639736 | OH REBUILD - MEREDITH AVE PH2 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | Yes | Matai, Ihssan (Sam) | Mark Bobanovic | 234054.95 | 248164.47 | 14109.52 | 6.028% | 45019.44 | 39617.79 | -5401.65 | -12% | 43742.18 | 39206.47 | -4535.71 | -10.37% | 1248.04 | 0 | -1248.04 | -100% | 144045.29 | 169340.21 | 25294.92 | 17.56% | 47.46 | 9 | -38.46 | -81.04% | 2021-11-18 01:00
Mississauga | 2022 | 639740 | CITY PARK (DIXIE) INC - 2116 DIXIE RD | 99 | COMPLETE | Labour est. over | Material Under Estimated | Cont Est Over | Gamboa, Henry | No | Ricci, Leonardo | Antonio Mina | 352344.01 | 345927.47 | -6416.54 | -1.821% | 74654.52 | 65667.97 | -8986.55 | -12.04% | 18244.17 | 22929.4 | 4685.23 | 25.68% | 3850.32 | 3805 | -45.32 | -1.177% | 255595 | 251595 | -4000 | -1.565% | 209.26 | 149 | -60.26 | -28.8% | 2022-11-22 01:00
Mississauga | 2021 | 639742 | 920 FOURTH STREET - POLE RELOCATION | 99 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Under Estimated | Lacombe, Joel | No | Watters, Maxwell | Rob Elliot | 94737.62 | 82227.97 | -12509.65 | -13.2% | 56415.62 | 48024.91 | -8390.71 | -14.87% | 9709.36 | 8726.94 | -982.42 | -10.12% | 15328.64 | 19156 | 3827.36 | 24.97% | 13284 | 6320.12 | -6963.88 | -52.42% | 439.82 | 316 | -123.82 | -28.15% | 2021-09-17 01:00
Mississauga | 2021 | 639769 | JOINT USE PERMIT HM2020-059 - SOUTHDOWN - MISS | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 7522.13 | 3721.71 | -3800.42 | -50.52% | 2693.93 | 571.71 | -2122.22 | -78.78% | 0 | 0 | 0 |  | 405.6 | 0 | -405.6 | -100% | 4422.6 | 3150 | -1272.6 | -28.77% | 16 | 0 | -16 | -100% | 2021-04-23
Mississauga | 2021 | 639839 | 6110 CANTAY ROAD L5R 3W5 | 99 | COMPLETE | Under 10% |  |  | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 88362.56 | 85322.36 | -3040.2 | -3.441% | 26567.43 | 12388.41 | -14179.02 | -53.37% | 78694.78 | 70480.75 | -8214.03 | -10.44% | 2750.35 | 2264 | -486.35 | -17.68% | 2700 | 189.2 | -2510.8 | -92.99% | 116.09 | 120.5 | 4.41 | 3.799% | 2021-06-05 01:00
Mississauga | 2022 | 639868 | 2445 LUCKNOW DR - MISS - UP - 3PH - 1000KVA | 95 | ANALYZE |  |  |  | Mandic, Goran | No | Roy, Akash | Peter Costantini | 133833.44 | 113703.23 | -20130.21 | -15.04% | 44293.71 | 23292.53 | -21001.18 | -47.41% | 48307.81 | 45482.94 | -2824.87 | -5.848% | 4983.92 | 4897.5 | -86.42 | -1.734% | 36248 | 40030.26 | 3782.26 | 10.43% | 208.76 | 192.5 | -16.26 | -7.789% | 2022-12-01 01:00
Mississauga | 2021 | 639951 | (SUB-TX) REPLACEMENTS - TYANDAGA CRT | 99 | COMPLETE | Labour est. over | Vehicle Under Estimated | N/A | Beaudrie, Scott | No | Cudzilo, Tomasz | Glenn Guile | 58609.28 | 31686.18 | -26923.1 | -45.94% | 43066.14 | 12791.78 | -30274.36 | -70.3% | 13179.2 | 12905.65 | -273.55 | -2.076% | 2363.94 | 5442.93 | 3078.99 | 130.2% | 0 | 545.82 | 545.82 |  | 357.8 | 118 | -239.8 | -67.02% | 2021-08-09 01:00
Mississauga | 2021 | 639952 | (SUB-TX) REPLACEMENTS - LENEL CRT | 99 | COMPLETE | Civil contractor | Labour est. over | Vehicle Under Estimated | Beaudrie, Scott | No | Cudzilo, Tomasz | Glenn Guile | 67752.32 | 80364.16 | 12611.84 | 18.61% | 45113.67 | 24967.63 | -20146.04 | -44.66% | 19792.74 | 20335.78 | 543.04 | 2.744% | 2845.91 | 7476.9 | 4630.99 | 162.7% | 0 | 27583.85 | 27583.85 |  | 398.7 | 156 | -242.7 | -60.87% | 2021-04-15
Mississauga | 2021 | 640104 | 2021 SWGR RENEWAL-SG1737 AT 385 PRINCE OF WALES | 99 | COMPLETE | Est. Int. - Act. External | RFC not approved in time | N/A | Beaudrie, Scott | Yes | Tempra, Troylan | Manoj Rao Manjunath | 49469.02 | 43718.11 | -5750.91 | -11.63% | 21794.11 | 5139.45 | -16654.66 | -76.42% | 23232.2 | 28328.76 | 5096.56 | 21.94% | 4442.71 | 0 | -4442.71 | -100% | 0 | 10249.9 | 10249.9 |  | 166.92 | 2 | -164.92 | -98.8% | 2021-12-03 01:00
Mississauga | 2021 | 640106 | 2021 SWGR RENEWAL-SG1433 AT 6550 BATTLEFORD RD | 99 | COMPLETE | Under 10% | Est. Int. - Act. External | N/A | Beaudrie, Scott | Yes | Tempra, Troylan | Manoj Rao Manjunath | 44621.84 | 43870.8 | -751.04 | -1.683% | 17805.1 | 5131.48 | -12673.62 | -71.18% | 24006.75 | 28582.62 | 4575.87 | 19.06% | 2809.99 | 0 | -2809.99 | -100% | 0 | 10156.7 | 10156.7 |  | 131.04 | 2 | -129.04 | -98.47% | 2021-11-26 01:00
Mississauga | 2022 | 640111 | 2380 SPEAKMAN DR - 1000KVA TRANSFORMER UPGRADE | 99 | COMPLETE | Material Over Estimated | Cont Est Over | Vehicle Under Estimated | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 113689.69 | 95743.17 | -17946.52 | -15.79% | 44847.05 | 41159.83 | -3687.22 | -8.222% | 42962.88 | 32925.5 | -10037.38 | -23.36% | 6028.76 | 8084 | 2055.24 | 34.09% | 19851 | 13573.84 | -6277.16 | -31.62% | 361.68 | 385 | 23.32 | 6.448% | 2022-03-28
Mississauga | 2021 | 640121 | OLD DERRY ROAD & GOODERHAM ESTATE BOULEVARD U/G RELOCATION | 99 | COMPLETE | Cont Est Over | Civil contractor | N/A | Lacombe, Joel | No | Watters, Maxwell | Glenn Guile | 244115.54 | 181927.85 | -62187.69 | -25.47% | 26915.66 | 24074 | -2841.66 | -10.56% | 124.04 | 0 | -124.04 | -100% | 1819.96 | 1636.5 | -183.46 | -10.08% | 215255.88 | 156062.85 | -59193.03 | -27.5% | 176.42 | 92.5 | -83.92 | -47.57% | 2021-11-08 01:00
Mississauga | 2021 | 640142 | ELETRICAL SERVICE UPGRADE - MARVIN HEIGHTS PS | 99 | COMPLETE | Labour est. over | N/A | N/A | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 93435.55 | 57539.93 | -35895.62 | -38.42% | 60401.34 | 26958.01 | -33443.33 | -55.37% | 25051.04 | 24220.67 | -830.37 | -3.315% | 5983.17 | 4810 | -1173.17 | -19.61% | 2000 | 1551.25 | -448.75 | -22.44% | 350.87 | 220.5 | -130.37 | -37.16% | 2021-08-12 01:00
Mississauga | 2022 | 640144 | MEDICAL OFFICES | 95 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Under | Mustachi, Randy | No | Huo, Lisa | Peter Costantini | 113474.9 | 84798.67 | -28676.23 | -25.27% | 55378.8 | 37900.18 | -17478.62 | -31.56% | 33830.71 | 20424.57 | -13406.14 | -39.63% | 5091.39 | 5213 | 121.61 | 2.389% | 19174 | 21260.92 | 2086.92 | 10.88% | 266.95 | 306 | 39.05 | 14.63% | 2022-09-26 01:00
Mississauga | 2021 | 640211 | INSULATORS RENEWAL - BATCH #1 | 99 | COMPLETE | Labour est. over | Flagging | N/A | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Rob Elliot | 131392.46 | 75678.45 | -55714.01 | -42.4% | 89502.52 | 42971.52 | -46531 | -51.99% | 13531.98 | 10434.64 | -3097.34 | -22.89% | 16477.96 | 22272.29 | 5794.33 | 35.16% | 11880 | 0 | -11880 | -100% | 599.4 | 344 | -255.4 | -42.61% | 2021-08-19 01:00
Mississauga | 2021 | 640231 | GOREWAY & BRANDON GATE PRIMARY 1PH EXTENSION | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | BOM not accurate | Lacombe, Joel | No | Watters, Maxwell | Macdougall, Stephen | 38707.08 | 5305.39 | -33401.69 | -86.29% | 27417.12 | 4223.78 | -23193.34 | -84.59% | 2233.18 | 329.61 | -1903.57 | -85.24% | 6723.98 | 752 | -5971.98 | -88.82% | 2332.8 | 0 | -2332.8 | -100% | 207.53 | 23 | -184.53 | -88.92% | 2021-05-18 01:00
Mississauga | 2022 | 640239 | 3151 LENWORTH DRIVE | 95 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 115201.73 | 81635.65 | -33566.08 | -29.14% | 44201.45 | 19143.79 | -25057.66 | -56.69% | 45311.44 | 37217.67 | -8093.77 | -17.86% | 4892.84 | 3350 | -1542.84 | -31.53% | 20796 | 21924.19 | 1128.19 | 5.425% | 287.88 | 160.5 | -127.38 | -44.25% | 2022-08-19 01:00
Mississauga | 2021 | 640262 | POLE RENEWAL - MINEOLA RD E EAST OF LOCHLIN TRAIL | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Lucic, Marko | Yes | Tempra, Troylan | Rob Elliot | 148902.73 | 105880.23 | -43022.5 | -28.89% | 77334.44 | 50235.98 | -27098.46 | -35.04% | 23995.1 | 16450.59 | -7544.51 | -31.44% | 19493.19 | 32263.14 | 12769.95 | 65.51% | 28080 | 6930.52 | -21149.48 | -75.32% | 641.86 | 486.5 | -155.36 | -24.2% | 2021-10-28 01:00
Mississauga | 2022 | 640325 | POLE RELOCATION - THOMAS ST (P08380) | 99 | COMPLETE | Under 10% |  |  | Lacombe, Joel | No | Gonzales, Leonard | Rob Elliot | 76775.37 | 74421.94 | -2353.43 | -3.065% | 44727.6 | 42600.09 | -2127.51 | -4.757% | 9726.71 | 9572.93 | -153.78 | -1.581% | 9805.06 | 11652 | 1846.94 | 18.84% | 12516 | 10596.92 | -1919.08 | -15.33% | 257.56 | 306 | 48.44 | 18.81% | 2022-05-13 01:00
Mississauga | 2021 | 640335 | 2180 SPEAKMAN DR - 750KVA TEMP | 99 | COMPLETE | Cont Est Under | Labour est. over | BOM not accurate | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 170608.77 | 203648.02 | 33039.25 | 19.37% | 41864.11 | 35638.55 | -6225.56 | -14.87% | 51170.28 | 40590.44 | -10579.84 | -20.68% | 7591.46 | 6418.5 | -1172.96 | -15.45% | 69982.92 | 121000.53 | 51017.61 | 72.9% | 337.78 | 372.5 | 34.72 | 10.28% | 2021-06-16 01:00
Mississauga | 2021 | 640477 | 6900 DIXIE ROAD - POLE RELOCATIONS | 99 | COMPLETE | Under 10% | Labour est. over | Vehicle Under Estimated | Lacombe, Joel | No | Watters, Maxwell | Paul Murphy | 77392.4 | 78320.1 | 927.7 | 1.199% | 41401.04 | 34203.74 | -7197.3 | -17.38% | 14821.63 | 16392.32 | 1570.69 | 10.6% | 10909.73 | 16711 | 5801.27 | 53.18% | 10260 | 11013.04 | 753.04 | 7.34% | 336.28 | 400.5 | 64.22 | 19.1% | 2021-10-29 01:00
Mississauga | 2022 | 640517 | TX12121 - SHEROBEE POWER TX REMOVALS (PCB) | 99 | COMPLETE | Cont Est Over | Labour est. over |  | Lucic, Marko | Yes | Cudzilo, Tomasz | Antonio Mina | 446985.13 | 362906.73 | -84078.4 | -18.81% | 76567.5 | 65649.88 | -10917.62 | -14.26% | 149053.92 | 157852.04 | 8798.12 | 5.903% | 11363.71 | 9200.62 | -2163.09 | -19.04% | 210000 | 130204.19 | -79795.81 | -38% | 489.68 | 395 | -94.68 | -19.34% | 2022-07-26 01:00
Mississauga | 2022 | 640540 | 1293 MEREDITH AVENUE - OH SYSTEM EXPANSION | 95 | COMPLETE | Under 10% |  |  | Watters, Maxwell | No | Watters, Maxwell | Paul Murphy | 228408.44 | 249208.81 | 20800.37 | 9.107% | 114117.66 | 128784.7 | 14667.04 | 12.85% | 37120.28 | 29536.26 | -7584.02 | -20.43% | 24970.5 | 59110 | 34139.5 | 136.7% | 52200 | 31777.85 | -20422.15 | -39.12% | 575.84 | 1458.5 | 882.66 | 153.3% | 2022-11-07 01:00
Mississauga | 2022 | 640565 | 1890 ALSTEP DRIVE | 95 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Under Estimated | Mustachi, Randy | No | Jacinto, Gerardo | Peter Costantini | 207308.57 | 198718.27 | -8590.3 | -4.144% | 87154.24 | 74969.02 | -12185.22 | -13.98% | 93330.91 | 94513.6 | 1182.69 | 1.267% | 15199.42 | 19470 | 4270.58 | 28.1% | 11624 | 9765.65 | -1858.35 | -15.99% | 584.98 | 714.75 | 129.77 | 22.18% | 2022-11-07 01:00
Mississauga | 2021 | 640669 | QEW & CREDIT RIVER - MISSISSAUGA & QEW CROSSING | 99 | COMPLETE | Labour est. over | Cont Est Over |  | Lacombe, Joel | No | Watters, Maxwell | Rob Elliot | 375426.44 | 283339.02 | -92087.42 | -24.53% | 154224.01 | 120424.02 | -33799.99 | -21.92% | 40844.31 | 44300.34 | 3456.03 | 8.461% | 34558.12 | 40407.5 | 5849.38 | 16.93% | 145800 | 78207.16 | -67592.84 | -46.36% | 688.98 | 1202.5 | 513.52 | 74.53% | 2021-08-12 01:00
Mississauga | 2021 | 640675 | (YS101847) REPLACEMENT - 1015 GALESWAY BLVD (P17980) | 99 | COMPLETE | Under 10% | N/A | N/A | Lucic, Marko | Yes | Cudzilo, Tomasz | Gregory Dunfield | 119616.19 | 117118.67 | -2497.52 | -2.088% | 33577.1 | 27786.74 | -5790.36 | -17.24% | 56922.87 | 70599.08 | 13676.21 | 24.03% | 8155.58 | 10098.57 | 1942.99 | 23.82% | 20960.64 | 8634.28 | -12326.36 | -58.81% | 275.27 | 221 | -54.27 | -19.72% | 2021-09-28 01:00
Mississauga | 2021 | 640676 | NEW AUTO SWITCH INSTALLATION (P21046) - 403 / HURONTARIO, 1 | 99 | CANCELLED | N/A |  |  | Lucic, Marko | Yes | Cudzilo, Tomasz | Gregory Dunfield | 201548.83 | 0 | -201548.83 | -100% | 69489.1 | 0 | -69489.1 | -100% | 105869.82 | 0 | -105869.82 | -100% | 16569.27 | 0 | -16569.27 | -100% | 9620.64 | 0 | -9620.64 | -100% | 674.38 | 0 | -674.38 | -100% | 2021-10-26 01:00
Mississauga | 2021 | 640677 | (YS141716) REPLACEMENT - 808 BRITANNIA RD. W. (P17996) | 99 | COMPLETE | Under 10% | N/A | N/A | Lucic, Marko | Yes | Cudzilo, Tomasz | Gregory Dunfield | 109392.23 | 104579.26 | -4812.97 | -4.4% | 38726.18 | 30548.64 | -8177.54 | -21.12% | 55170.4 | 58696.96 | 3526.56 | 6.392% | 8168.93 | 10765.47 | 2596.54 | 31.79% | 7326.72 | 4568.19 | -2758.53 | -37.65% | 244.72 | 269 | 24.28 | 9.922% | 2021-10-26 01:00
Mississauga | 2021 | 640678 | (LT71027) REPLACEMENT - 6553 MISSISSAUGA RD (P19606) | 99 | COMPLETE | Material excess | N/A | N/A | Lucic, Marko | Yes | Cudzilo, Tomasz | Gregory Dunfield | 132636.62 | 195580.81 | 62944.19 | 47.46% | 40184.13 | 57975.2 | 17791.07 | 44.27% | 77754.07 | 110542.43 | 32788.36 | 42.17% | 8650.42 | 18892.63 | 10242.21 | 118.4% | 6048 | 8170.55 | 2122.55 | 35.1% | 340.23 | 525.5 | 185.27 | 54.45% | 2021-11-19 01:00
Mississauga | 2021 | 640679 | (LT31231) REPLACEMENT - 3029 CLAYHILL RD (P6428) | 99 | COMPLETE | Scope change - unforeseen | Road allowance | BOM not accurate | Lucic, Marko | Yes | Cudzilo, Tomasz | Gregory Dunfield | 29232.71 | 165741.39 | 136508.68 | 467% | 22842.65 | 42482.62 | 19639.97 | 85.98% | 3304.06 | 97594.22 | 94290.16 | 2854% | 3086 | 17814.66 | 14728.66 | 477.3% | 0 | 7849.89 | 7849.89 |  | 162 | 357 | 195 | 120.4% | 2021-12-03 01:00
Mississauga | 2022 | 640680 | 2180 SPEAKMAN DR - MISS - NS - 4000A C.O. SERVICE | 95 | COMPLETE | Labour est. under | Cont Est Under | Vehicle Under Estimated | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 108772.13 | 119059.32 | 10287.19 | 9.458% | 21098.41 | 27673.96 | 6575.55 | 31.17% | 80163.18 | 77660.55 | -2502.63 | -3.122% | 1510.54 | 4442 | 2931.46 | 194.1% | 6000 | 9282.81 | 3282.81 | 54.71% | 159.23 | 253 | 93.77 | 58.89% | 2022-10-05 01:00
Mississauga | 2022 | 640684 | BATCH 1 - TRANSFORMER KIOSK REPLACEMENT | 99 | COMPLETE | Labour est. under | Cont Est Over | Vehicle Under Estimated | Lucic, Marko | Yes | Ferry, Rodnne | Glenn Guile | 69995.13 | 89982.33 | 19987.2 | 28.56% | 30139.6 | 45138.66 | 14999.06 | 49.77% | 23085.93 | 27276.56 | 4190.63 | 18.15% | 5969.6 | 12078.59 | 6108.99 | 102.3% | 10800 | 5488.52 | -5311.48 | -49.18% | 207.24 | 266.5 | 59.26 | 28.59% | 2022-12-23 01:00
Mississauga | 2021 | 640721 | 1890 ALSTEP DR - MISS - NS - 3PH - 1500KVA TEMP | 99 | COMPLETE | Labour est. over | Cont Est Under | Vehicle Over Estimated- | Mandic, Goran | No | Roy, Akash | Peter Costantini | 166541.29 | 135057.11 | -31484.18 | -18.9% | 61258.06 | 26336.98 | -34921.08 | -57.01% | 50350.11 | 51050.29 | 700.18 | 1.391% | 6102.12 | 3958 | -2144.12 | -35.14% | 48831 | 53711.84 | 4880.84 | 9.995% | 528.45 | 255.5 | -272.95 | -51.65% | 2021-12-02 01:00
Mississauga | 2022 | 640771 | BRAMALEA ROAD & DERRY ROAD 44KV SYSTEM EXPANSION | 95 | COMPLETE | Under 10% |  |  | Watters, Maxwell | No | Watters, Maxwell | Matthew Beach | 369283.09 | 419062.46 | 49779.37 | 13.48% | 103422.75 | 122016.89 | 18594.14 | 17.98% | 208270.9 | 216712.18 | 8441.28 | 4.053% | 25317.44 | 46836 | 21518.56 | 85% | 32272 | 33497.39 | 1225.39 | 3.797% | 793.9 | 1168.25 | 374.35 | 47.15% | 2022-09-21 01:00
Mississauga | 2021 | 640775 | THE COLLEGEWAY STACKED TOWNHOMES - 3401 RIDGEWAY | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- |  | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 185191.94 | 161213.72 | -23978.22 | -12.95% | 62013.02 | 36865.13 | -25147.89 | -40.55% | 42630.78 | 42034.76 | -596.02 | -1.398% | 5548.14 | 5028 | -520.14 | -9.375% | 75000 | 77285.83 | 2285.83 | 3.048% | 326.73 | 274 | -52.73 | -16.14% | 2021-10-15 01:00
Mississauga | 2022 | 640776 | L7199 TO L7202 GLEN ERIN DR UG CABLE REPLACEMENT | 99 | COMPLETE | Cont Est Over | Labour est. over | Vehicle Over Estimated- | Lucic, Marko | No | Tempra, Troylan | Antonio Mina | 1005601.27 | 865440.51 | -140160.76 | -13.94% | 189076.87 | 154695.11 | -34381.76 | -18.18% | 3713.86 | 5773.67 | 2059.81 | 55.46% | 13444.54 | 10046.98 | -3397.56 | -25.27% | 799366 | 694924.75 | -104441.25 | -13.07% | 524.73 | 349.5 | -175.23 | -33.39% | 2022-12-02 01:00
Mississauga | 2021 | 640782 | JOINT USE PERMIT HM2021-001 - AMERICAN - MISS | 99 | COMPLETE | Labour est. over | BOM not accurate | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 11215.86 | 7790.04 | -3425.82 | -30.54% | 5258.67 | 3528.04 | -1730.63 | -32.91% | 880.43 | 0 | -880.43 | -100% | 994.36 | 1112 | 117.64 | 11.83% | 4082.4 | 3150 | -932.4 | -22.84% | 35.36 | 32 | -3.36 | -9.502% | 2021-05-17 01:00
Mississauga | 2022 | 640790 | FRAM + SLOKKER, 55 PORT ST. E., MISS.- NS00115340 - 3PH PAD | 99 | COMPLETE | Cont Est Over | Material Over Estimated | Labour est. over | Mandic, Goran | No | Garcha, Tirath | Peter Costantini | 137310.86 | 109050.03 | -28260.83 | -20.58% | 40248.57 | 34193.86 | -6054.71 | -15.04% | 47542.31 | 37492.65 | -10049.66 | -21.14% | 4143.88 | 7548 | 3404.12 | 82.15% | 45376.1 | 29815.52 | -15560.58 | -34.29% | 291.35 | 368.75 | 77.4 | 26.57% | 2022-10-19 01:00
Mississauga | 2021 | 640792 | SKYMARK AVE AND SATELLITE - MISS - NS - 25KVA | 99 | COMPLETE | Cont Est Under | Labour est. over | N/A | Mandic, Goran | No | Roy, Akash | Peter Costantini | 44708.4 | 54425.06 | 9716.66 | 21.73% | 20511.67 | 11354.84 | -9156.83 | -44.64% | 4328.73 | 4572.67 | 243.94 | 5.635% | 2163.4 | 2138 | -25.4 | -1.174% | 19704.6 | 36359.55 | 16654.95 | 84.52% | 176.81 | 101 | -75.81 | -42.88% | 2021-09-16 01:00
Mississauga | 2022 | 640793 | 2068 SOUTH SHERIDAN - MISS - NS - 300KVA | 99 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Over Estimated- | Mandic, Goran | No | Roy, Akash | Peter Costantini | 119634.43 | 68684.35 | -50950.08 | -42.59% | 51946.72 | 23531.08 | -28415.64 | -54.7% | 35361.88 | 32165.69 | -3196.19 | -9.039% | 13615.83 | 7829.5 | -5786.33 | -42.5% | 18710 | 5158.08 | -13551.92 | -72.43% | 445.97 | 292.5 | -153.47 | -34.41% | 2022-02-11 01:00
Mississauga | 2022 | 640798 | EXPANSION - 2180 SPEAKMAN DR - MISSISSAUGA - THP | 95 | COMPLETE | Cont Est Over | Labour est. over | Material Over Estimated | Lacombe, Joel | No | Garcha, Tirath | Peter Costantini | 594055.18 | 394569.61 | -199485.57 | -33.58% | 155224.03 | 104833.98 | -50390.05 | -32.46% | 182751.29 | 142769.35 | -39981.94 | -21.88% | 19897.46 | 18281 | -1616.46 | -8.124% | 236182.4 | 128685.28 | -107497.12 | -45.51% | 787.92 | 978 | 190.08 | 24.12% | 2022-10-05 01:00
Mississauga | 2021 | 640800 | BATCH 2 - TRANSFORMER KIOSK REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Lucic, Marko | No | Ferry, Rodnne | Glenn Guile | 70001.16 | 68486.42 | -1514.74 | -2.164% | 30139.6 | 23984.38 | -6155.22 | -20.42% | 23091.96 | 23185.16 | 93.2 | 0.4036% | 5969.6 | 7684.41 | 1714.81 | 28.73% | 10800 | 13632.47 | 2832.47 | 26.23% | 414.49 | 162 | -252.49 | -60.92% | 2021-05-12
Mississauga | 2021 | 640852 | JOINT USE PERMIT HM2021-005 - DERRY E - MISS | 99 | COMPLETE | Under 10% | N/A | N/A | O'Gay, Brian | No | Johnson, William | Macdougall, Stephen | 5459.28 | 4996.54 | -462.74 | -8.476% | 1878.83 | 2842.54 | 963.71 | 51.29% | 380.04 | 0 | -380.04 | -100% | 600.41 | 154 | -446.41 | -74.35% | 2600 | 2000 | -600 | -23.08% | 19.15 | 28 | 8.85 | 46.21% | 2021-07-02 01:00
Mississauga | 2022 | 640854 | ELITE STONE INDUSTRIAL | 99 | COMPLETE | Material Over Estimated | Labour est. over | Cont Est Under | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 111012.32 | 79986.33 | -31025.99 | -27.95% | 46037.22 | 31573.7 | -14463.52 | -31.42% | 36163.56 | 7361.53 | -28802.03 | -79.64% | 3811.54 | 6307.5 | 2495.96 | 65.48% | 25000 | 34743.6 | 9743.6 | 38.97% | 198.63 | 276 | 77.37 | 38.95% | 2022-01-21 01:00
Mississauga | 2022 | 640875 | 1293 MEREDITH AVE - MISS - NS - 3PH - 500KVA | 95 | COMPLETE | Labour est. over | Cont Est Under | N/A | Mandic, Goran | No | Roy, Akash | Peter Costantini | 71325.95 | 64694.66 | -6631.29 | -9.297% | 26312.68 | 17648.89 | -8663.79 | -32.93% | 32751.71 | 30969.54 | -1782.17 | -5.441% | 3436.56 | 4219 | 782.44 | 22.77% | 8825 | 11857.23 | 3032.23 | 34.36% | 224.64 | 195.5 | -29.14 | -12.97% | 2022-11-08 01:00
Mississauga | 2021 | 640878 | 1250 SHAWSON DR - PAVE-AL LIMITED | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Mandic, Goran | No | Jacinto, Gerardo | Macdougall, Stephen | 23110.15 | 12468.52 | -10641.63 | -46.05% | 16635.4 | 9396.94 | -7238.46 | -43.51% | 9032.53 | 1599.19 | -7433.34 | -82.3% | 2442.22 | 1472.39 | -969.83 | -39.71% | 0 | 0 | 0 |  | 70.28 | 52.5 | -17.78 | -25.3% | 2021-05-07
Mississauga | 2022 | 640890 | M-CITY POLE RELOCATION AT FITZROY STREET | 99 | COMPLETE | Under 10% | BOM not accurate |  | Lacombe, Joel | No | Watters, Maxwell | Mark Bobanovic | 123208.54 | 121541.45 | -1667.09 | -1.353% | 17226.64 | 12018.97 | -5207.67 | -30.23% | 15538.78 | 25413.09 | 9874.31 | 63.55% | 1281 | 0 | -1281 | -100% | 89162.12 | 84109.39 | -5052.73 | -5.667% | 63 | 9 | -54 | -85.71% | 2022-01-10 01:00
Mississauga | 2022 | 640938 | CHILD#1 - 4220 LIVING ARTS DRIVE - DANIELS SQUARE ONE INC -INSTALLATION | 99 | COMPLETE | Labour est. over | Material Under Estimated | Vehicle Over Estimated- | Mandic, Goran | No | Jacinto, Gerardo | Peter Costantini | 134805.23 | 118877.83 | -15927.4 | -11.82% | 49840.43 | 29960.97 | -19879.46 | -39.89% | 45960.89 | 50876.39 | 4915.5 | 10.69% | 5581.91 | 4136 | -1445.91 | -25.9% | 33422 | 33904.47 | 482.47 | 1.444% | 361.28 | 283 | -78.28 | -21.67% | 2022-01-24 01:00
Mississauga | 2021 | 640953 | ORLANDO CORPORATION | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Cont Est Over | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 106212.55 | 66076.55 | -40136 | -37.79% | 48489.19 | 16784.02 | -31705.17 | -65.39% | 36179.39 | 33228.37 | -2951.02 | -8.157% | 4543.97 | 2330.5 | -2213.47 | -48.71% | 17000 | 13733.66 | -3266.34 | -19.21% | 227.67 | 96.5 | -131.17 | -57.61% | 2021-12-01 01:00
Mississauga | 2021 | 641065 | CREDITVIEW ROAD & OLD CREDITVIEW ROAD POLE RELOCATIONS - MTO | 99 | COMPLETE | Under 10% | N/A | N/A | Lacombe, Joel | No | Watters, Maxwell | Mark Bobanovic | 303801.01 | 283862.79 | -19938.22 | -6.563% | 16526.33 | 18367.6 | 1841.27 | 11.14% | 125084.83 | 109454.73 | -15630.1 | -12.5% | 1089.65 | 849.5 | -240.15 | -22.04% | 161100.2 | 155190.96 | -5909.24 | -3.668% | 52.69 | 60 | 7.31 | 13.87% | 2021-12-06 01:00
Mississauga | 2021 | 641085 | ANIMAL ABATEMENT - UTM | 99 | COMPLETE | Est. Int. - Act. External | N/A | N/A | Lucic, Marko | No | Ferry, Rodnne | Manoj Rao Manjunath | 53555.9 | 42383.25 | -11172.65 | -20.86% | 39690.84 | 9993.01 | -29697.83 | -74.82% | 3777.06 | 5058.94 | 1281.88 | 33.94% | 10088 | 0 | -10088 | -100% | 0 | 27331.3 | 27331.3 |  | 312 | 2 | -310 | -99.36% | 2021-12-31 01:00
Mississauga | 2021 | 641238 | METROLINX | 99 | COMPLETE | Engineering by-passed | N/A | N/A | Mandic, Goran | No | Huo, Lisa | Gregory Dunfield | 0 | 27115.59 | 27115.59 |  | 0 | 11583.42 | 11583.42 |  | 0 | 7912.46 | 7912.46 |  | 0 | 3456 | 3456 |  | 0 | 4163.71 | 4163.71 |  | 0 | 100 | 100 |  | 2021-12-01 01:00
Mississauga | 2022 | 641240 | PROJECT 151894 _ CABLE REMEDIATION- MAIN FEEDER CABLE (S4802 TO L4835) | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Matai, Ihssan (Sam) | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-30 01:00
Mississauga | 2022 | 641250 | PROJECT_ 151901 _ CABLE REPLACEMENT PROJECT - (AREA16) - HEMUS SQUARE | 99 | CANCELLED | N/A |  |  | Lucic, Marko | No | Matai, Ihssan (Sam) | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-09-07 01:00
Mississauga | 2022 | 641295 | PROJECT_ 151903 _ CABLE REPLACEMENT PROJECT - (AREA25) - SOUTH MILLWAY | 99 | CANCELLED | N/A |  |  | Lucic, Marko | No | Matai, Ihssan (Sam) | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-22 01:00
Mississauga | 2022 | 641314 | 336 WATLINE - MISS - UP - 3PH - 750KVA | 95 | COMPLETE | Cont Est Under | Labour est. over | N/A | Mustachi, Randy | No | Paesano, Chelsea | Peter Costantini | 84808.02 | 101603.71 | 16795.69 | 19.8% | 40309.87 | 28020.45 | -12289.42 | -30.49% | 36989.26 | 37813.47 | 824.21 | 2.228% | 4711.89 | 5177.5 | 465.61 | 9.882% | 2797 | 30592.29 | 27795.29 | 993.8% | 100.45 | 240 | 139.55 | 138.9% | 2022-12-03 01:00
Mississauga | 2022 | 641327 | 2021 MUT CITY OF MISSISSAUGA PROJECT - ALECTRA RELOCATIONS | 99 | COMPLETE | Under 10% | N/A | N/A | Lacombe, Joel | No | Watters, Maxwell | Mark Bobanovic | 404241.76 | 388109.92 | -16131.84 | -3.991% | 14686.55 | 40029.57 | 25343.02 | 172.6% | 29867.18 | 39548.83 | 9681.65 | 32.42% | 0 | 0 | 0 |  | 359688.03 | 308531.52 | -51156.51 | -14.22% | 0 | 4.5 | 4.5 |  | 2022-02-02 01:00
Mississauga | 2021 | 641352 | 7015 KENNEDY RD - MISS - NS - 3PH - 1500KVA | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Cont Est Under | Mandic, Goran | No | Roy, Akash | Peter Costantini | 130738.97 | 103832.07 | -26906.9 | -20.58% | 44756.79 | 20716.11 | -24040.68 | -53.71% | 58240.59 | 55527.79 | -2712.8 | -4.658% | 10144.59 | 6300 | -3844.59 | -37.9% | 17597 | 21288.17 | 3691.17 | 20.98% | 383.85 | 212 | -171.85 | -44.77% | 2021-12-05 01:00
Mississauga | 2021 | 641357 | 2815 EGLINTON AVE W - MISS - NS - 400A | 99 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Under Estimated | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 18721.14 | 30365.11 | 11643.97 | 62.2% | 11580.05 | 10130.74 | -1449.31 | -12.52% | 23262.9 | 18383.02 | -4879.88 | -20.98% | 1220.19 | 1811.5 | 591.31 | 48.46% | 5008 | 39.85 | -4968.15 | -99.2% | 0 | 108.5 | 108.5 |  | 2021-11-25 01:00
Mississauga | 2021 | 641419 | MISSISSAUGA RD & KANE RD MINI REBUILD | 99 | COMPLETE | Cont Est Over | Labour est. over | BOM not accurate | Lucic, Marko | No | Tempra, Troylan | Antonio Mina | 288447.39 | 214848.41 | -73598.98 | -25.52% | 61899.22 | 47132.16 | -14767.06 | -23.86% | 11240.6 | 7765.25 | -3475.35 | -30.92% | 8279.57 | 10907.24 | 2627.67 | 31.74% | 207028 | 148734.77 | -58293.23 | -28.16% | 329.6 | 181 | -148.6 | -45.08% | 2021-11-30 01:00
Mississauga | 2021 | 641425 | STUB POLE RELOCATION - BURNHAMTHORPE RD. W. | 99 | COMPLETE | Labour est. over | BOM not accurate | Vac truck | Lacombe, Joel | No | Garcha, Tirath | Paul Murphy | 30136.8 | 14414.31 | -15722.49 | -52.17% | 16061.39 | 7235.31 | -8826.08 | -54.95% | 4073.75 | 310.78 | -3762.97 | -92.37% | 2890.94 | 3349 | 458.06 | 15.84% | 7110.72 | 3519.22 | -3591.5 | -50.51% | 120.61 | 60 | -60.61 | -50.25% | 2021-06-04 01:00
Mississauga | 2022 | 641486 | PROPOSED EVENT CENTER - 6916 DIXIE RD. | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-03-25 01:00
Mississauga | 2022 | 641496 | 181 LAKESHORE RD W - MISS - NS - 3PH - 1000KVA | 99 | COMPLETE | Labour est. over | Cont Est Under | N/A | Mandic, Goran | No | Roy, Akash | Peter Costantini | 139616.83 | 140850.22 | 1233.39 | 0.8834% | 58059.68 | 33226.65 | -24833.03 | -42.77% | 47597.26 | 49028.43 | 1431.17 | 3.007% | 6999.89 | 7513 | 513.11 | 7.33% | 26960 | 51082.14 | 24122.14 | 89.47% | 512.45 | 346 | -166.45 | -32.48% | 2022-03-25 01:00
Mississauga | 2021 | 641525 | THE FURLAN GROUP SERVICE UPGRADE | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-07-06 01:00
Mississauga | 2022 | 641540 | 2022 OH EMERGING - GALLOPING CONDUCTORS- BATCH # 5 | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- | Material Over Estimated | Lucic, Marko | No | Matai, Ihssan (Sam) | Matthew Beach | 164624.63 | 66785.04 | -97839.59 | -59.43% | 116511.27 | 43436.57 | -73074.7 | -62.72% | 19851.11 | 14668.73 | -5182.38 | -26.11% | 25762.25 | 8006.91 | -17755.34 | -68.92% | 2500 | 672.83 | -1827.17 | -73.09% | 993.95 | 274.5 | -719.45 | -72.38% | 2022-10-21 01:00
Mississauga | 2022 | 641595 | 2020 TRANSFORMER REPLACEMENT BATCH 2 (TX7642RWB/ TX8400RWB) | 99 | COMPLETE | Labour est. under | BOM not accurate | Cont Est Under | Lucic, Marko | Yes | Cudzilo, Tomasz | Antonio Mina | 50535.99 | 68804.35 | 18268.36 | 36.15% | 18407.06 | 29004.01 | 10596.95 | 57.57% | 28779.49 | 32586.25 | 3806.76 | 13.23% | 3349.44 | 4950.64 | 1601.2 | 47.81% | 0 | 2263.45 | 2263.45 |  | 78.2 | 243.5 | 165.3 | 211.4% | 2022-03-01 01:00
Mississauga | 2022 | 641737 | UNDERGROUND REBUILD - BURNHAMTHORPE PHASE 1 | 99 | COMPLETE | Cont Est Over | Labour est. under | Material Over Estimated | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Antonio Mina | 1879494.58 | 1778631.94 | -100862.64 | -5.366% | 162686.26 | 347718 | 185031.74 | 113.7% | 84116.2 | 36060.27 | -48055.93 | -57.13% | 15988.92 | 21254.13 | 5265.21 | 32.93% | 1616703.2 | 1373599.54 | -243103.66 | -15.04% | 1029.7 | 740 | -289.7 | -28.13% | 2022-10-28 01:00
Mississauga | 2022 | 641753 | JOINT USE PERMIT HM - INVESTIGATION FOR BELL | 99 | CANCELLED | N/A |  |  | O'Gay, Brian | No | Johnson, William | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-11 01:00
Mississauga | 2022 | 641832 | LT31135 - 2022 SR-DUNDAS ST W. E-O OF DUNWIN DR - P10331 | 99 | COMPLETE | Vehicle Under Estimated | Material Under Estimated | Labour est. under | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Paul Murphy | 143012.92 | 202808.58 | 59795.66 | 41.81% | 45569.08 | 60236.36 | 14667.28 | 32.19% | 78991.31 | 100726.13 | 21734.82 | 27.52% | 10377.53 | 33865.84 | 23488.31 | 226.3% | 8075 | 7980.25 | -94.75 | -1.173% | 344.79 | 564.5 | 219.71 | 63.72% | 2022-10-07 01:00
Mississauga | 2022 | 641855 | QTY 8 - 2022 TRANSFORMER REPLACEMENT - BATCH 1 | 99 | COMPLETE | Labour est. under | BOM not accurate |  | Beaudrie, Scott | Yes | Ferry, Rodnne | Antonio Mina | 108108.97 | 128896.97 | 20788 | 19.23% | 40819.22 | 49758.1 | 8938.88 | 21.9% | 39444.55 | 44024.45 | 4579.9 | 11.61% | 8553.2 | 12423.68 | 3870.48 | 45.25% | 19292 | 22690.74 | 3398.74 | 17.62% | 270.48 | 374 | 103.52 | 38.27% | 2022-06-14 01:00
Mississauga | 2022 | 641856 | (SG1402) 2022 SG REPLACEMENT - ELMCREEK AND SHORLINE | 99 | COMPLETE | Cont Est Under | Labour est. over | Vehicle Over Estimated- | Lucic, Marko | Yes | Ferry, Rodnne | Glenn Guile | 128196.21 | 98651.08 | -29545.13 | -23.05% | 44663.13 | 32585.33 | -12077.8 | -27.04% | 35642.34 | 38674.07 | 3031.73 | 8.506% | 7890.74 | 4090.85 | -3799.89 | -48.16% | 40000 | 23300.83 | -16699.17 | -41.75% | 221.5 | 256 | 34.5 | 15.58% | 2022-04-01
Mississauga | 2022 | 641865 | LT31097 - 2022 DA - DUNDAS ST & MISS RD - P07936 | 99 | COMPLETE | Labour est. over | Material Under Estimated | N/A | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Paul Murphy | 133287.81 | 130519.06 | -2768.75 | -2.077% | 47692.03 | 32201.74 | -15490.29 | -32.48% | 74166.36 | 84312.12 | 10145.76 | 13.68% | 11429.42 | 13130.2 | 1700.78 | 14.88% | 0 | 875 | 875 |  | 369.56 | 351 | -18.56 | -5.022% | 2022-07-20 01:00
Mississauga | 2022 | 641923 | ROVINELLI HOLDINGS LTD. | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-09-23 01:00
Mississauga | 2022 | 641933 | 6005 ERIN MILLS - MISS - NS - 1200A (EXP. DEM:846KW PER M-REZA) | 95 | ANALYZE |  |  |  | Mustachi, Randy | No | Jacinto, Gerardo | Peter Costantini | 129481.52 | 111061.92 | -18419.6 | -14.23% | 54365.28 | 30552.81 | -23812.47 | -43.8% | 50353.32 | 54093.16 | 3739.84 | 7.427% | 4828.92 | 5742 | 913.08 | 18.91% | 19934 | 20673.95 | 739.95 | 3.712% | 336.51 | 290 | -46.51 | -13.82% | 2023-01-18 01:00
Mississauga | 2022 | 641935 | 6155 ERIN MILLS PARKWAY - MISS - NS - 200A | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Pellerin, Patrick | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-08-18 01:00
Mississauga | 2022 | 642128 | SHELL CANADA LIMITED | 99 | COMPLETE | Labour est. over | Cont Est Under | N/A | Mandic, Goran | No | Huo, Lisa | Peter Costantini | 150118.06 | 133797.51 | -16320.55 | -10.87% | 69594.65 | 48051.67 | -21542.98 | -30.95% | 47733.47 | 47304.56 | -428.91 | -0.8986% | 7789.94 | 10644.5 | 2854.56 | 36.64% | 25000 | 27796.78 | 2796.78 | 11.19% | 491.34 | 484.5 | -6.84 | -1.392% | 2022-04-13
Mississauga | 2021 | 642131 | 6501 GOREWAY DRIVE (GOREWAY ESSO) | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Jacinto, Gerardo | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-08-02 01:00
Mississauga | 2021 | 642148 | BARBERHOUSE POLE RELOCATION | 99 | COMPLETE | Under 10% | N/A | N/A | D'Onofrio, Tony | No | Ricci, Leonardo | Gregory Dunfield | 11708.16 | 11080.79 | -627.37 | -5.358% | 6895.85 | 4704.41 | -2191.44 | -31.78% | 1122.47 | 1155.86 | 33.39 | 2.975% | 1401.84 | 1640 | 238.16 | 16.99% | 2288 | 3580.52 | 1292.52 | 56.49% | 48.57 | 48 | -0.57 | -1.174% | 2021-11-25 01:00
Mississauga | 2022 | 642219 | 1288 SOUTH ALDO DRIVE - POLE RELOCATION | 99 | COMPLETE | Under 10% |  |  | Lacombe, Joel | No | Watters, Maxwell | Gregory Dunfield | 45023.14 | 45827.67 | 804.53 | 1.787% | 24223.7 | 13357.01 | -10866.69 | -44.86% | 1360.23 | 1341.9 | -18.33 | -1.348% | 5439.21 | 3563 | -1876.21 | -34.49% | 14000 | 27565.76 | 13565.76 | 96.9% | 167.79 | 98 | -69.79 | -41.59% | 2022-01-18 01:00
Mississauga | 2022 | 642313 | QTY 12 1PH - 2022 TX REPLACEMENT - BATCH 2 | 99 | COMPLETE | Cont Est Over | Material Under Estimated | Vehicle Under Estimated | Lucic, Marko | Yes | Ferry, Rodnne | Glenn Guile | 158286.97 | 167753.68 | 9466.71 | 5.981% | 53876.26 | 57076.84 | 3200.58 | 5.941% | 68610.91 | 76742.07 | 8131.16 | 11.85% | 11799.8 | 17950.14 | 6150.34 | 52.12% | 24000 | 15984.63 | -8015.37 | -33.4% | 396.72 | 503 | 106.28 | 26.79% | 2022-12-23 01:00
Mississauga | 2022 | 642344 | LT31106 - 2022 SR-DUNDAS ST W & ERIN MILLS - P11533 | 99 | COMPLETE | Labour est. over | Vehicle Under Estimated | Material Under Estimated | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Paul Murphy | 162284.39 | 163517.16 | 1232.77 | 0.7596% | 57517.26 | 46358.5 | -11158.76 | -19.4% | 80344.07 | 88648.1 | 8304.03 | 10.34% | 13523.06 | 23693.68 | 10170.62 | 75.21% | 10900 | 4816.88 | -6083.12 | -55.81% | 867.8433 | 453 | -414.8433 | -47.8% | 2022-09-15 01:00
Mississauga | 2022 | 642394 | 3990 EGLINTON - MISS - NS - 3PH - 500KVA | 99 | COMPLETE | Labour est. over | Material Over Estimated | Vehicle Over Estimated- | Mandic, Goran | No | Pellerin, Patrick | Peter Costantini | 148972.93 | 115936.7 | -33036.23 | -22.18% | 46075.91 | 23980.71 | -22095.2 | -47.95% | 29946.62 | 25641.29 | -4305.33 | -14.38% | 7056.4 | 3601 | -3455.4 | -48.97% | 65894 | 62713.7 | -3180.3 | -4.826% | 272 | 126 | -146 | -53.68% | 2021-12-17 01:00
Mississauga | 2022 | 642404 | 2022 SWGR RENEWAL, SG1041 & SG1194, EXPLORER DR | 99 | ANALYZE |  |  |  | Lucic, Marko | Yes | Cudzilo, Tomasz | Antonio Mina | 340820.29 | 390784.96 | 49964.67 | 14.66% | 76017.44 | 100452.36 | 24434.92 | 32.14% | 223238.53 | 250118.26 | 26879.73 | 12.04% | 7164.32 | 17629.51 | 10465.19 | 146.1% | 34400 | 22584.83 | -11815.17 | -34.35% | 471.92 | 900.5 | 428.58 | 90.82% | 2023-01-06 01:00
Mississauga | 2022 | 642407 | 2022 SWGR RENEWAL, SG1064, 4181 SLADEVIEW CRES | 99 | COMPLETE | Material reused |  |  | Lucic, Marko | Yes | Tempra, Troylan | Antonio Mina | 177257.55 | 81716.75 | -95540.8 | -53.9% | 40635.08 | 33733.49 | -6901.59 | -16.98% | 110504.82 | 11937.64 | -98567.18 | -89.2% | 6117.65 | 5292.45 | -825.2 | -13.49% | 20000 | 30753.17 | 10753.17 | 53.77% | 272.04 | 230.5 | -41.54 | -15.27% | 2022-10-28 01:00
Mississauga | 2022 | 642410 | 2022 SWGR RENEWAL, SG1370, 6807 FOREST PARK DR | 99 | COMPLETE | Cont Est Over | Labour est. over |  | Lucic, Marko | Yes | Tempra, Troylan | Antonio Mina | 177228.93 | 160651.14 | -16577.79 | -9.354% | 40541.93 | 34920.11 | -5621.82 | -13.87% | 111649.73 | 112109.91 | 460.18 | 0.4122% | 5037.27 | 6405.53 | 1368.26 | 27.16% | 20000 | 7215.59 | -12784.41 | -63.92% | 273.42 | 306.5 | 33.08 | 12.1% | 2022-05-27 01:00
Mississauga | 2022 | 642422 | 2775 MATHESON BLVD E - MISS - UP - 2500A | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Pellerin, Patrick | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-29 01:00
Mississauga | 2022 | 642449 | QTY 12 1PH - 2022 TX REPLACEMENT - BATCH #3 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Ferry, Rodnne | Peter Costantini | 175443.71 | 183654.27 | 8210.56 | 4.68% | 67222.11 | 66662.09 | -560.02 | -0.8331% | 65824.8 | 62924.46 | -2900.34 | -4.406% | 16228.8 | 19889.84 | 3661.04 | 22.56% | 26168 | 34177.88 | 8009.88 | 30.61% | 549.72 | 582.5 | 32.78 | 5.963% | 2022-09-28 01:00
Mississauga | 2022 | 642498 | LT31235 - 2022 SR-QUEENSWAY W & STILLMEADOW RD - P13168 | 99 | COMPLETE | Labour est. over | Vehicle Under Estimated | N/A | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Rob Elliot | 125255.05 | 131578.81 | 6323.76 | 5.049% | 41514.07 | 37376.85 | -4137.22 | -9.966% | 74154.56 | 76900.27 | 2745.71 | 3.703% | 9586.42 | 17301.69 | 7715.27 | 80.48% | 0 | 0 | 0 |  | 312.56 | 378.25 | 65.69 | 21.02% | 2022-02-02 01:00
Mississauga | 2022 | 642501 | YL41179 - 2022 SR QUEENSWAY E & EDGEWORTH RD - P11367 | 99 | COMPLETE | Vehicle Under Estimated | Cont Est Over | Material Under Estimated | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Gregory Dunfield | 82369.77 | 98031.2 | 15661.43 | 19.01% | 42670.26 | 48791.2 | 6120.94 | 14.34% | 20584.56 | 24679.54 | 4094.98 | 19.89% | 9114.95 | 21194.06 | 12079.11 | 132.5% | 10000 | 3366.4 | -6633.6 | -66.34% | 297.6 | 369.5 | 71.9 | 24.16% | 2022-12-19 01:00
Mississauga | 2022 | 642536 | YL44352 - 2022 DA - DIXIE RD AND PRIMATE RD - P17025 | 99 | COMPLETE | Under 10% | N/A | N/A | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Gregory Dunfield | 95447.09 | 96771.88 | 1324.79 | 1.388% | 33225.39 | 32267.91 | -957.48 | -2.882% | 51886.71 | 54467.07 | 2580.36 | 4.973% | 7034.99 | 7741.89 | 706.9 | 10.05% | 3300 | 2295.01 | -1004.99 | -30.45% | 233.65 | 232 | -1.65 | -0.7062% | 2022-12-18 01:00
Mississauga | 2022 | 642537 | YL41187 - 2022 DA - DIXIE RD AND TONOLLI RD - USC341 | 99 | COMPLETE | Material excess | Cont Est Over | Vehicle Under Estimated | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Gregory Dunfield | 130786.17 | 161725.48 | 30939.31 | 23.66% | 45969.74 | 49660.33 | 3690.59 | 8.028% | 56225.65 | 92491.11 | 36265.46 | 64.5% | 9890.78 | 14024.5 | 4133.72 | 41.79% | 18700 | 5549.54 | -13150.46 | -70.32% | 321.65 | 462.5 | 140.85 | 43.79% | 2022-04-11
Mississauga | 2022 | 642538 | YS153905 - 2022 DA - BRITANNIA RD AND MAVIS RD - P18118 | 99 | COMPLETE | Under 10% |  |  | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Gregory Dunfield | 94635.1 | 106586.41 | 11951.31 | 12.63% | 33140.75 | 30222.14 | -2918.61 | -8.807% | 51768.79 | 66000.73 | 14231.94 | 27.49% | 6425.56 | 9264.44 | 2838.88 | 44.18% | 3300 | 1099.1 | -2200.9 | -66.69% | 214.8 | 219.75 | 4.95 | 2.304% | 2022-03-14 01:00
Mississauga | 2021 | 642539 | LT71221 - 2021 DA - MISSISSAUGA RD AND MEADOWVALE BLVD - P18998 | 99 | COMPLETE | BOM not accurate | Vehicle Under Estimated | Civil contractor | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Gregory Dunfield | 115415.92 | 158845.77 | 43429.85 | 37.63% | 33936.84 | 37076.55 | 3139.71 | 9.252% | 74153.09 | 100285.41 | 26132.32 | 35.24% | 7325.99 | 15855.14 | 8529.15 | 116.4% | 0 | 5628.67 | 5628.67 |  | 242.65 | 321 | 78.35 | 32.29% | 2021-12-17 01:00
Mississauga | 2022 | 642540 | LT102038 - 2022 DA - HERITAGE RD AND 407 - P21458 | 99 | COMPLETE | Vehicle Under Estimated | Cont Est Over | Material Under Estimated | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Gregory Dunfield | 143297 | 170168.44 | 26871.44 | 18.75% | 42833.21 | 55584.34 | 12751.13 | 29.77% | 79003.4 | 89613.35 | 10609.95 | 13.43% | 9460.39 | 22722.71 | 13262.32 | 140.2% | 12000 | 2248.04 | -9751.96 | -81.27% | 296.32 | 444 | 147.68 | 49.84% | 2022-12-17 01:00
Mississauga | 2022 | 642627 | (SG1456) 2022 SG REPLACEMENT - 4010 SLADVIEW CRESCENT | 99 | COMPLETE | Under 10% |  |  | Lucic, Marko | Yes | Ferry, Rodnne | Antonio Mina | 52498.58 | 52628.35 | 129.77 | 0.2472% | 18864.96 | 17306.22 | -1558.74 | -8.263% | 30834.6 | 33406.11 | 2571.51 | 8.34% | 2799.02 | 1916.02 | -883 | -31.55% | 0 | 0 | 0 |  | 122.1 | 59.5 | -62.6 | -51.27% | 2022-01-13 01:00
Mississauga | 2022 | 642723 | VOICE RADIO COMMUNICATION – MAINGATE MS | 99 | CANCELLED | N/A |  |  | Haid, Philip G. | No | Zaghloul, Sam | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-06-30 01:00
Mississauga | 2022 | 642846 | 6860 REXWOOD ROAD UNIT 1 MISSISSAUGA | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Jacinto, Gerardo | XMoinuddin, Saad | 0 | 534.85 | 534.85 |  | 0 | 534.85 | 534.85 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1.75 | 1.75 |  | 2022-03-25 01:00
Mississauga | 2022 | 642963 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE1.1 DIXIE OUTLET MALL | 99 | COMPLETE | Under 10% |  |  | Lacombe, Joel | No | Watters, Maxwell | Matthew Beach | 1126765.06 | 1025048.15 | -101716.91 | -9.027% | 178963.66 | 156187.28 | -22776.38 | -12.73% | 81811.69 | 83905.25 | 2093.56 | 2.559% | 25370.71 | 28260 | 2889.29 | 11.39% | 840619 | 756695.62 | -83923.38 | -9.984% | 958.97 | 698 | -260.97 | -27.21% | 2022-11-18 01:00
Mississauga | 2022 | 642981 | 1083 EDGELEIGH AVENUE POLE RELOCATION | 99 | COMPLETE | Labour est. over | Civil contractor | N/A | Lacombe, Joel | No | Watters, Maxwell | Gregory Dunfield | 30187.94 | 26233.57 | -3954.37 | -13.1% | 16071.86 | 9407.22 | -6664.64 | -41.47% | 2675.47 | 1638.27 | -1037.2 | -38.77% | 3440.61 | 3593 | 152.39 | 4.429% | 8000 | 11595.08 | 3595.08 | 44.94% | 106.1 | 76 | -30.1 | -28.37% | 2022-02-08 01:00
Mississauga | 2022 | 643018 | POLE RELOCATION - 1115 ALGONQUIN DR | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Gonzales, Leonard | Gregory Dunfield | 25481.34 | 4696.19 | -20785.15 | -81.57% | 15303.44 | 4696.19 | -10607.25 | -69.31% | 1216.57 | 0 | -1216.57 | -100% | 3061.33 | 0 | -3061.33 | -100% | 5900 | 0 | -5900 | -100% | 80.44 | 52 | -28.44 | -35.36% | 2022-09-16 01:00
Mississauga | 2021 | 643020 | 66 QUEEN STREET SOUTH - POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 1600.44 | 1600.44 |  | 0 | 1600.44 | 1600.44 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-09-16 01:00
Mississauga | 2022 | 643088 | TEMP. SERVICE FOR 2020 CAMILLA RD. | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-31 01:00
Mississauga | 2022 | 643123 | 6200 CANTAY ROAD UNIT 1 MISSISSAUIGA L5R 3Y9 | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Under | Mustachi, Randy | No | Jacinto, Gerardo | Peter Costantini | 203361.44 | 171479.46 | -31881.98 | -15.68% | 61782.55 | 35400.21 | -26382.34 | -42.7% | 82093.53 | 71405.93 | -10687.6 | -13.02% | 5715.36 | 5471.5 | -243.86 | -4.267% | 53770 | 59201.82 | 5431.82 | 10.1% | 383.9 | 281 | -102.9 | -26.8% | 2022-08-25 01:00
Mississauga | 2022 | 643163 | ECWE TEMP POWER TBMS | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Paesano, Andrew | No | Chopra, Rabinder | Antonio Mina | 277782.03 | 196386.22 | -81395.81 | -29.3% | 133192.7 | 102622.66 | -30570.04 | -22.95% | 71807.44 | 73434.7 | 1627.26 | 2.266% | 9239.89 | 10647.5 | 1407.61 | 15.23% | 63542 | 9681.36 | -53860.64 | -84.76% | 400 | 591.5 | 191.5 | 47.88% | 2022-04-06
Mississauga | 2021 | 643198 | (SG1493) 2022 SG REPLACEMENT - 2935 ARGENTIA ROAD | 98 | COMPLETE | Scope change - unforeseen |  |  | Lucic, Marko | Yes | Ferry, Rodnne | Antonio Mina | 57371.29 | 4165.68 | -53205.61 | -92.74% | 20202.74 | 4165.68 | -16037.06 | -79.38% | 33806.21 | 0 | -33806.21 | -100% | 3362.34 | 0 | -3362.34 | -100% | 0 | 0 | 0 |  | 134.1 | 0 | -134.1 | -100% | 2021-12-01 01:00
Mississauga | 2022 | 643199 | (SG1536) 2022 SG REPLACEMENT - 3770 A LAIRD DRIVE | 99 | COMPLETE | Labour est. over |  |  | Lucic, Marko | Yes | Ferry, Rodnne | Antonio Mina | 57371.29 | 42042.41 | -15328.88 | -26.72% | 20202.74 | 10038.42 | -10164.32 | -50.31% | 33806.21 | 29963.92 | -3842.29 | -11.37% | 3362.34 | 2040.07 | -1322.27 | -39.33% | 0 | 0 | 0 |  | 134.1 | 78 | -56.1 | -41.83% | 2022-02-03 01:00
Mississauga | 2022 | 643200 | 1 3PH - 2022 TX REPLACEMENT - TX11254 | 99 | COMPLETE | Material reused |  |  | Beaudrie, Scott | Yes | Ferry, Rodnne | Glenn Guile | 52931.26 | 7988.1 | -44943.16 | -84.91% | 17084.59 | 5738.51 | -11346.08 | -66.41% | 13508.55 | 1103.81 | -12404.74 | -91.83% | 2338.12 | 1145.78 | -1192.34 | -51% | 20000 | 0 | -20000 | -100% | 69.45 | 36 | -33.45 | -48.16% | 2022-03-14 01:00
Mississauga | 2022 | 643229 | 2022 SWGR RENEWAL, SG1671 REPLACEMENT, 3329 HUXLEY DR | 99 | COMPLETE | BOM not accurate | Labour est. over |  | Lucic, Marko | Yes | Cudzilo, Tomasz | Antonio Mina | 58916.3 | 53397.69 | -5518.61 | -9.367% | 21441.74 | 18612.95 | -2828.79 | -13.19% | 35277.51 | 30338.79 | -4938.72 | -14% | 2197.05 | 2987.37 | 790.32 | 35.97% | 0 | 1458.58 | 1458.58 |  | 130.11 | 119 | -11.11 | -8.539% | 2022-03-04 01:00
Mississauga | 2022 | 643305 | 7174 DERRYCREST DR - MISS - NS - 3PH - 2000KVA | 99 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Mandic, Goran | No | Roy, Akash | Peter Costantini | 116507.99 | 93014.42 | -23493.57 | -20.16% | 33071.28 | 14644.84 | -18426.44 | -55.72% | 62975.82 | 61742.3 | -1233.52 | -1.959% | 3645.89 | 3003 | -642.89 | -17.63% | 16815 | 13624.28 | -3190.72 | -18.98% | 258.45 | 138.5 | -119.95 | -46.41% | 2022-09-13 01:00
Mississauga | 2021 | 643470 | HULRT TPSS#15 - SQUARE ONE DR - MISS - 3PH - PRIMARY | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Chopra, Rabinder | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-03 01:00
Mississauga | 2022 | 643494 | 2775 MATHESON BLVD E | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Jacinto, Gerardo | XMoinuddin, Saad | 0 | 1800.67 | 1800.67 |  | 0 | 1800.67 | 1800.67 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-03 01:00
Mississauga | 2022 | 643559 | 1589 GLENHILL CRESCENT - OH TO UG CONVERSION POLE TO POLE | 99 | COMPLETE | Under 10% |  |  | Lacombe, Joel | No | Watters, Maxwell | Rob Elliot | 68814.17 | 72559.69 | 3745.52 | 5.443% | 41627.28 | 35239.51 | -6387.77 | -15.35% | 9108.24 | 8483.9 | -624.34 | -6.855% | 11578.65 | 15584 | 4005.35 | 34.59% | 6500 | 13252.28 | 6752.28 | 103.9% | 303.66 | 341.5 | 37.84 | 12.46% | 2022-09-09 01:00
Mississauga | 2021 | 643563 | QEW CREDIT RIVER IMPROVEMENT PROJECT - POLE RELOCATION NEAR MISSISSAUGA RD | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-04-22
Mississauga | 2022 | 643675 | 2022 SWGR RENEWAL, SG1581 REMOVAL, 3675 THOMAS ST. | 99 | COMPLETE | Cont Est Over |  |  | Lucic, Marko | Yes | Cudzilo, Tomasz | Antonio Mina | 61592.61 | 57726.56 | -3866.05 | -6.277% | 28501.3 | 31344.84 | 2843.54 | 9.977% | 6624.85 | 4897.84 | -1727.01 | -26.07% | 2066.46 | 5074.8 | 3008.34 | 145.6% | 24400 | 16409.08 | -7990.92 | -32.75% | 160.74 | 252.5 | 91.76 | 57.09% | 2022-05-02
Mississauga | 2022 | 643711 | 2022 SWGR RENEWAL, SG1482, MARVIN HEIGHTS PARK AT REDSTONE RD | 99 | COMPLETE | Cont Est Over | Labour est. over | N/A | Lucic, Marko | Yes | Tempra, Troylan | Glenn Guile | 185631.87 | 165531.78 | -20100.09 | -10.83% | 40432.5 | 30954.07 | -9478.43 | -23.44% | 120195.1 | 122083.74 | 1888.64 | 1.571% | 5004.27 | 5483.04 | 478.77 | 9.567% | 20000 | 7010.93 | -12989.07 | -64.95% | 272.42 | 229 | -43.42 | -15.94% | 2022-05-27 01:00
Mississauga | 2022 | 643822 | (SG1734 AND SG1372) 2022 SG REPLACEMENT - 6755 AND 6135 LISGAR DRIVE | 99 | COMPLETE | Labour est. over | Vehicle Over Estimated- |  | Lucic, Marko | Yes | Ferry, Rodnne | Glenn Guile | 120086.44 | 92142.25 | -27944.19 | -23.27% | 45511.86 | 24668.84 | -20843.02 | -45.8% | 64902.54 | 62000.19 | -2902.35 | -4.472% | 9672.04 | 4372.22 | -5299.82 | -54.8% | 0 | 1101 | 1101 |  | 370.2 | 215 | -155.2 | -41.92% | 2022-02-16 01:00
Mississauga | 2022 | 644014 | 300 STATESMAN DRIVE | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Bojanic, Dusan | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-05 01:00
Mississauga | 2022 | 644115 | RER MX - LW CONFLICT #LW21 - CAWTHRA ROAD - REMOVALS | 98 | COMPLETE | Labour est. under | Vehicle Under Estimated |  | Tobin, Michael | No | Khuu, Philander | Rob Elliot | 16821.64 | 30353.14 | 13531.5 | 80.44% | 5325.64 | 14565.94 | 9240.3 | 173.5% | 0 | 734.7 | 734.7 |  | 1488 | 4542 | 3054 | 205.2% | 10008 | 10510.5 | 502.5 | 5.021% | 48 | 205 | 157 | 327.1% | 2022-08-04 01:00
Mississauga | 2022 | 644128 | TX8769 VAULT RENEWAL - 3233 BRANDON GATE DR | 99 | CANCELLED | N/A |  |  | Lucic, Marko | Yes | Cudzilo, Tomasz | XMoinuddin, Saad | 0 | -446.21 | -446.21 |  | 0 | -446.21 | -446.21 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-08 01:00
Mississauga | 2022 | 644152 | 290 DERRY RD W PACINI RESTAURANT | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Central South | XMoinuddin, Saad | 0 | 2849.41 | 2849.41 |  | 0 | 2823.41 | 2823.41 |  | 0 | 0 | 0 |  | 0 | 26 | 26 |  | 0 | 0 | 0 |  | 0 | 1 | 1 |  | 2022-11-21 01:00
Mississauga | 2022 | 644169 | MEADOWVALE ROTARY PARK | 99 | COMPLETE | Labour est. under | N/A | N/A | Mandic, Goran | No | Macasaet, Ricardo | XMoinuddin, Saad | 0 | 2697.27 | 2697.27 |  | 0 | 2697.27 | 2697.27 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-21 01:00
Mississauga | 2022 | 644782 | ANCHOR RELOCATION AT P06498 - NOVAR RD. | 99 | COMPLETE | Labour est. over | Cont Est Over | Vehicle Under Estimated | Lacombe, Joel | No | Garcha, Tirath | Paul Murphy | 8430.76 | 4716.22 | -3714.54 | -44.06% | 4850.54 | 2215.61 | -2634.93 | -54.32% | 731.05 | 206.11 | -524.94 | -71.81% | 849.17 | 1744 | 894.83 | 105.4% | 2000 | 550.5 | -1449.5 | -72.47% | 31.16 | 24 | -7.16 | -22.98% | 2022-03-17 01:00
Mississauga | 2022 | 644804 | PREMIUM WAY TEMPORARY STUB POLE INSTALLATIONS | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Lacombe, Joel | No | Watters, Maxwell | Paul Murphy | 26363.63 | 18231.14 | -8132.49 | -30.85% | 13735.63 | 9058.79 | -4676.84 | -34.05% | 3742.48 | 4208.35 | 465.87 | 12.45% | 2885.52 | 3464 | 578.48 | 20.05% | 6000 | 1500 | -4500 | -75% | 75.62 | 88 | 12.38 | 16.37% | 2022-06-30 01:00
Mississauga | 2022 | 644840 | 2022 EM OH, P12296 ADDITIONAL GUYING - CAWTHRA RD | 99 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Lucic, Marko | No | Matai, Ihssan (Sam) | Gregory Dunfield | 46065.61 | 17752.16 | -28313.45 | -61.46% | 26577.33 | 11774.46 | -14802.87 | -55.7% | 6301.67 | 1251.99 | -5049.68 | -80.13% | 4686.61 | 2959.17 | -1727.44 | -36.86% | 8500 | 1766.54 | -6733.46 | -79.22% | 168.31 | 64 | -104.31 | -61.97% | 2022-06-20 01:00
Mississauga | 2022 | 644930 | 6501 GOREWAY DRIVE (GOREWAY ESSO) | 95 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Mustachi, Randy | No | Jacinto, Gerardo | Peter Costantini | 102962.39 | 59546.61 | -43415.78 | -42.17% | 49244.93 | 23013.18 | -26231.75 | -53.27% | 30590.02 | 23092.36 | -7497.66 | -24.51% | 9103.44 | 5427 | -3676.44 | -40.39% | 14024 | 8014.07 | -6009.93 | -42.85% | 320.25 | 242 | -78.25 | -24.43% | 2022-12-13 01:00
Mississauga | 2022 | 644962 | HURONTARIO (LCBO) - MISS - NS00212505 - 3PH | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Paesano, Chelsea | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-15 01:00
Mississauga | 2022 | 644964 | 86 DUNDAS STREET EAST DEVELOPMENT - POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-15 01:00
Mississauga | 2022 | 644997 | 2022 EM UG, 1 FAIRVIEW RD. EAST - DUCTBANK RELOCATION | 99 | COMPLETE | Estimate incorrect | Cont Est Under |  | Lucic, Marko | No | Cudzilo, Tomasz | Antonio Mina | 36780.23 | 226564.59 | 189784.36 | 516% | 26461.14 | 61713.07 | 35251.93 | 133.2% | 8342.09 | 5981.41 | -2360.68 | -28.3% | 1977 | 3266.34 | 1289.34 | 65.22% | 0 | 155603.77 | 155603.77 |  | 153.8 | 201.5 | 47.7 | 31.01% | 2022-07-15 01:00
Mississauga | 2022 | 644230 | P06387 - BURNHAMTHORPE RD W & GRAND PARK DR - P06387 - LT31057 REMOVAL | 99 | COMPLETE | Estimate incorrect | Cont Est Under |  | Lucic, Marko | No | Matai, Ihssan (Sam) | Gregory Dunfield | 106883.95 | 167664.47 | 60780.52 | 56.87% | 50424.7 | 51379.43 | 954.73 | 1.893% | 34481.95 | 38917.65 | 4435.7 | 12.86% | 10477.3 | 15753.88 | 5276.58 | 50.36% | 11500 | 61613.51 | 50113.51 | 435.8% | 354.84 | 424.5 | 69.66 | 19.63% | 2022-04-04
Mississauga | 2022 | 644236 | U/G DISTRIBUTION AUTOMATION - GROSSBEAK MS | 99 | COMPLETE | Under 10% |  |  | Houston, Andrew | Yes | Zaghloul, Sam | Antonio Mina | 579686.89 | 668043.42 | 88356.53 | 15.24% | 113038.83 | 157703.97 | 44665.14 | 39.51% | 270529.21 | 310712.21 | 40183 | 14.85% | 13214.75 | 24534.97 | 11320.22 | 85.66% | 182904.1 | 175092.27 | -7811.83 | -4.271% | 796.55 | 1362 | 565.45 | 70.99% | 2022-07-14 01:00
Mississauga | 2022 | 644249 | 2475 MEADOWPINE BLVD. - MISS - NS00193451 - 3PH - 2000KVA | 99 | CANCELLED | N/A |  |  | Mandic, Goran | No | Garcha, Tirath | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-18 01:00
Mississauga | 2022 | 644551 | LT71089 - 2022 DA - ERIN MILLS PKWY & BRITTANNIA RD W - P20409 | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Lucic, Marko | Yes | Matai, Ihssan (Sam) | Gregory Dunfield | 157533.45 | 139178.9 | -18354.55 | -11.65% | 52622.77 | 39075.28 | -13547.49 | -25.74% | 81225.11 | 80687.19 | -537.92 | -0.6623% | 12735.57 | 13300.49 | 564.92 | 4.436% | 10950 | 6115.94 | -4834.06 | -44.15% | 328.31 | 329 | 0.69 | 0.2102% | 2022-12-13 01:00
Mississauga | 2022 | 646670 | 855 BRITANNIA ROAD EAST / MISS / NS | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Yoon, Irene | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-03 01:00
Mississauga | 2022 | 646892 | 1106 WESTMOUNT AVE MISSISSAUGA - POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-14 01:00
Mississauga | 2022 | 646923 | 5835 AIRPORT ROAD SUNCOR ENERGY - POLE RELOCATIONS | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 3279.86 | 3279.86 |  | 0 | 3279.86 | 3279.86 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-04 01:00
Mississauga | 2022 | 645232 | 2140 GORDON DRIVE - 100KVA -600A 1-PHASE UPGRADE | 99 | COMPLETE | Labour est. over | Material Over Estimated | Cont Est Under | Mustachi, Randy | No | Hulnitski, Pavel | Peter Costantini | 70068.31 | 56524.26 | -13544.05 | -19.33% | 33763.33 | 19959.06 | -13804.27 | -40.89% | 14790.79 | 10927.8 | -3862.99 | -26.12% | 6308.19 | 6890 | 581.81 | 9.223% | 15206 | 18747.4 | 3541.4 | 23.29% | 259.98 | 220 | -39.98 | -15.38% | 2022-07-19 01:00
Mississauga | 2022 | 645301 | 6767 PACIFIC CIR | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Yoon, Irene | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-22 01:00
Mississauga | 2022 | 645302 | 5105 HURONTARIO | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Yoon, Irene | XMoinuddin, Saad | 0 | 347.8 | 347.8 |  | 0 | 37.26 | 37.26 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 310.54 | 310.54 |  | 0 | 0 | 0 |  | 2022-12-22 01:00
Mississauga | 2022 | 645334 | BRITANNIA ROAD WEST ANCHOR RELOCATIONS - REGION OF PEEL | 99 | COMPLETE | Under 10% |  |  | Lacombe, Joel | No | Watters, Maxwell | Gregory Dunfield | 17051.08 | 18461.31 | 1410.23 | 8.271% | 12316.15 | 7937.39 | -4378.76 | -35.55% | 2623.29 | 1458.56 | -1164.73 | -44.4% | 2111.64 | 2132 | 20.36 | 0.9642% | 0 | 6933.36 | 6933.36 |  | 0 | 60 | 60 |  | 2022-07-16 01:00
Mississauga | 2022 | 645585 | 6301 SILVER DART DR | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Yoon, Irene | XMoinuddin, Saad | 0 | 417.37 | 417.37 |  | 0 | 44.72 | 44.72 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 372.65 | 372.65 |  | 0 | 0 | 0 |  | 2022-08-22 01:00
Mississauga | 2022 | 645592 | 175 WATLINE AVE | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Yoon, Irene | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-08-25 01:00
Mississauga | 2022 | 645731 | BRIGHTWATER DEVELOPMENT - PINE AVE SOUTH SECONDARY RELOCATIONS | 98 | COMPLETE | Cont Est Over | BOM not accurate |  | Lacombe, Joel | No | Watters, Maxwell | Gregory Dunfield | 71752.84 | 54641.95 | -17110.89 | -23.85% | 21746.77 | 18445.37 | -3301.4 | -15.18% | 8391.66 | 5766.67 | -2624.99 | -31.28% | 3316.41 | 3134 | -182.41 | -5.5% | 38298 | 27295.91 | -11002.09 | -28.73% | 96.31 | 138 | 41.69 | 43.29% | 2022-12-13 01:00
Mississauga | 2022 | 647193 | 129 HIGH STREET WEST - PADMOUNT TX RELOCATION | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-21 01:00
Mississauga | 2022 | 647201 | WATERGARDEN DRIVE SWITCHGEAR 2457 RELOCATION | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-21 01:00
Mississauga | 2022 | 647667 | 1644 GLENBURNIE ROAD - POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Lacombe, Joel | No | Watters, Maxwell | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-09-06 01:00
Mississauga | 2022 | 647729 | 971 MATHESON BLVD E- MISS - UP - 3PH - UP00250505 | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Yoon, Irene | XMoinuddin, Saad | 0 | 255.06 | 255.06 |  | 0 | 27.33 | 27.33 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 227.73 | 227.73 |  | 0 | 0 | 0 |  | 2022-10-24 01:00
Mississauga | 2022 | 647735 | 3650 DIXIE RD - MISS - UP - 3PH - UP00268034 | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Yoon, Irene | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-10-24 01:00
Mississauga | 2022 | 647748 | P18440 POLE RELOCATION - 1400 AIMCO BLVD | 99 | COMPLETE | Labour est. over | BOM not accurate | Vehicle Not Charged | Lacombe, Joel | No | Watters, Maxwell | Gregory Dunfield | 12618.86 | 5589.74 | -7029.12 | -55.7% | 6263.46 | 1773.4 | -4490.06 | -71.69% | 2454.88 | 128.76 | -2326.12 | -94.75% | 1400.52 | 0 | -1400.52 | -100% | 2500 | 3687.58 | 1187.58 | 47.5% | 36.65 | 0 | -36.65 | -100% | 2022-10-24 01:00
Mississauga | 2022 | 647793 | 3520 LAIRD RD. UNIT 1 - MISS - UP - 3PH - UP00271173 | 95 | COMPLETE | Labour est. over | Cont Est Over | Material Over Estimated | Mustachi, Randy | No | Yoon, Irene | Peter Costantini | 309821.26 | 244977.85 | -64843.41 | -20.93% | 96749.56 | 41447.66 | -55301.9 | -57.16% | 157087.41 | 133663.54 | -23423.87 | -14.91% | 10984.29 | 6934 | -4050.29 | -36.87% | 45000 | 62932.65 | 17932.65 | 39.85% | 711.57 | 378 | -333.57 | -46.88% | 2022-12-02 01:00
Mississauga | 2022 | 647796 | KENAIDAN CONTRACTING LTD. | 99 | CANCELLED | N/A |  |  | Mustachi, Randy | No | Huo, Lisa | XMoinuddin, Saad | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-29 01:00
Mississauga | 2022 | 648947 | 2023 TX RENEWAL, BATCH 2 - PRIORITIZED LIST (TX10316) | 99 | CANCELLED | N/A |  |  | Lucic, Marko | No | Cudzilo, Tomasz | Persaud, Ryan | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-04-05 00:59
St. Catharines | 2019 | 13101 | December Ice Storm Damage St. Catharines | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jakubowski, Mark | Stinson, Jim | 0 | 0 | 0 |  | 18513.72 | 0 | -18513.72 | -100% | 10730.4 | 0 | -10730.4 | -100% | 1076.8 | 0 | -1076.8 | -100% | 104326.56 | 0 | -104326.56 | -100% | 1050 | 0 | -1050 | -100% | 2019-01-04 01:00
St. Catharines | 2019 | 14439 | Glenridge Pedestals - 2018 | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Frank Giancola | 13092.47 | 1309.32 | -11783.15 | -90% | 6997.92 | 1309.32 | -5688.6 | -81.29% | 3172.61 | 0 | -3172.61 | -100% | 521.94 | 0 | -521.94 | -100% | 2400 | 0 | -2400 | -100% | 105 | 20.5 | -84.5 | -80.48% | 2019-05-04 01:00
St. Catharines | 2019 | 14444 | St Catharines Locate Requests | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
St. Catharines | 2019 | 15487 | 75 Oliver Lane STC | 99 | CANCELLED | N/A | N/A | N/A |  | No | Montgomery, Michael | Weaver, Thomas | 0 | 882.84 | 882.84 |  | 0 | 882.84 | 882.84 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 14 | 14 |  | 2019-05-07
St. Catharines | 2019 | 15551 | 8-12-14-16 Brookdale Ave | 99 | COMPLETE | Cont Est Over | N/A | N/A |  | No | Rolfe, Eric | Carr, Brad | 22406.6 | 27720.6 | 5314 | 23.72% | 4407.08 | 3656.35 | -750.73 | -17.03% | 1062.19 | 0 | -1062.19 | -100% | 681.76 | 0 | -681.76 | -100% | 16255.57 | 22772.37 | 6516.8 | 40.09% | 60 | 54.75 | -5.25 | -8.75% | 2019-01-23 01:00
St. Catharines | 2019 | 15874 | 1132 Lakeshore Rd W, St Catharines | 99 | COMPLETE | N/A | N/A | N/A |  | No | Paesano, Andrew | Hewitson, Trevor | 1766.74 | 312.08 | -1454.66 | -82.34% | 1094.47 | 291.56 | -802.91 | -73.36% | 451.89 | 0 | -451.89 | -100% | 220.38 | 0 | -220.38 | -100% | 0 | 0 | 0 |  | 16 | 4 | -12 | -75% | 2019-01-17 01:00
St. Catharines | 2019 | 15916 | 2018-Pole Residuals-St. Catherines | 99 | COMPLETE | Labour est. under | BOM not accurate | Cont Est Over |  | No | Rolfe, Eric | Dan Despres | 89180.89 | 80951.52 | -8229.37 | -9.228% | 34799.03 | 48955.92 | 14156.89 | 40.68% | 17963.22 | 11538.87 | -6424.35 | -35.76% | 25918.64 | 13612 | -12306.64 | -47.48% | 10500 | 6453.75 | -4046.25 | -38.54% | 468 | 734.75 | 266.75 | 57% | 2019-01-22 01:00
St. Catharines | 2019 | 15964 | Jacobson UG Services | 99 | COMPLETE | Scope change - unforeseen | Cont Est Under | N/A |  | No | Webb-Murre, Paige | Hewitson, Trevor | 11330.04 | 25348.48 | 14018.44 | 123.7% | 994.87 | 2128.48 | 1133.61 | 113.9% | 531.09 | 0 | -531.09 | -100% | 73.58 | 0 | -73.58 | -100% | 9730.5 | 23220 | 13489.5 | 138.6% | 14.2 | 29 | 14.8 | 104.2% | 2019-01-09 01:00
St. Catharines | 2019 | 16039 | 29 Powerglen Rd, St.Catharines | 99 | COMPLETE | Vac truck | Labour est. over | N/A |  | No | Laus, Tomislav | Frank Giancola | 15686.39 | 13871.36 | -1815.03 | -11.57% | 7179.09 | 5538.7 | -1640.39 | -22.85% | 1873.9 | 1913.62 | 39.72 | 2.12% | 1649.4 | 346.98 | -1302.42 | -78.96% | 4984 | 4124 | -860 | -17.26% | 99 | 78.5 | -20.5 | -20.71% | 2019-03-15 01:00
St. Catharines | 2019 | 16332 | 124 St. David's Rd, St. Catharines | 99 | COMPLETE | N/A | N/A | N/A |  | No | Patel, Ketan | Hewitson, Trevor | 13772.76 | 15893.84 | 2121.08 | 15.4% | 2444.64 | 2460.81 | 16.17 | 0.6614% | 1771.52 | 3373.07 | 1601.55 | 90.41% | 56.6 | 7.62 | -48.98 | -86.54% | 9500 | 9500 | 0 | 0% | 28 | 31 | 3 | 10.71% | 2019-01-08 01:00
St. Catharines | 2019 | 16407 | 27 Ridgewood Rd | 99 | COMPLETE | N/A | N/A | N/A |  | No | Dragojevic, Igor | Frank Giancola | 16666.27 | 15323.31 | -1342.96 | -8.058% | 7931.37 | 7363.86 | -567.51 | -7.155% | 1500.8 | 1275.39 | -225.41 | -15.02% | 1849.1 | 337.84 | -1511.26 | -81.73% | 5385 | 4660 | -725 | -13.46% | 119 | 113.5 | -5.5 | -4.622% | 2019-02-14 01:00
St. Catharines | 2019 | 16413 | 2595 Fifth St. | 99 | COMPLETE | Labour est. over | N/A | N/A |  | No | Dragojevic, Igor | Frank Giancola | 11297.18 | 10962.16 | -335.02 | -2.966% | 3161.58 | 2579.99 | -581.59 | -18.4% | 3063.55 | 2911.24 | -152.31 | -4.972% | 625.8 | 103.96 | -521.84 | -83.39% | 4446.25 | 4446.25 | 0 | 0% | 53 | 41.75 | -11.25 | -21.23% | 2019-03-19 01:00
St. Catharines | 2019 | 16428 | 5A Hazel St, St. Catharines | 99 | COMPLETE | N/A | N/A | N/A |  | No | Patel, Ketan | Carr, Brad | 8104.18 | 7524.78 | -579.4 | -7.149% | 1222.32 | 1163.78 | -58.54 | -4.789% | 528.56 | 0 | -528.56 | -100% | 28.3 | 5.08 | -23.22 | -82.05% | 6325 | 6325 | 0 | 0% | 16 | 16 | 0 | 0% | 2019-01-15 01:00
St. Catharines | 2019 | 16450 | 140 Glendale Ave, St. Kitts | 99 | COMPLETE | N/A | N/A | N/A |  | No | Patel, Ketan | Carr, Brad | 3854.43 | 3661.56 | -192.87 | -5.004% | 1222.32 | 1315.56 | 93.24 | 7.628% | 293.81 | 0 | -293.81 | -100% | 28.3 | 5.08 | -23.22 | -82.05% | 2310 | 2310 | 0 | 0% | 16 | 16 | 0 | 0% | 2019-01-16 01:00
St. Catharines | 2019 | 16536 | Cogeco Make Ready - Broadway Ave | 99 | COMPLETE | Labour est. under | N/A | N/A |  | No | Celic, Dusan | Dan Despres | 3887.15 | 5225.39 | 1338.24 | 34.43% | 1930.1 | 0 | -1930.1 | -100% | 204.94 | 0 | -204.94 | -100% | 341.2 | 0 | -341.2 | -100% | 1410.91 | 0 | -1410.91 | -100% | 26 | 42.25 | 16.25 | 62.5% | 2019-04-10 01:00
St. Catharines | 2020 | 451012 | 433 Pelham Road | 99 | CANCELLED | N/A | N/A | N/A | Kafel, Krzysztof | No | Alectra Utilities | Jakubowski, Mark | 0 | 6453.22 | 6453.22 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-01-14 01:00
St. Catharines | 2019 | 451087 | 6 & 10 Dalhousie Ave, St. Kitts | 99 | COMPLETE | Labour est. under | Cont Est Over | N/A | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 95614.15 | 106716.13 | 11101.98 | 11.61% | 22406.56 | 204.6 | -22201.96 | -99.09% | 28414.61 | 0 | -28414.61 | -100% | 944.86 | 0 | -944.86 | -100% | 36415 | 2557.5 | -33857.5 | -92.98% | 330 | 484.25 | 154.25 | 46.74% | 2019-02-14 01:00
St. Catharines | 2019 | 451105 | K-Bar Unit Replace - Westland St | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Frank Giancola | 25408.56 | 24925.76 | -482.8 | -1.9% | 13823.62 | 10819.03 | -3004.59 | -21.74% | 5717.2 | 7663 | 1945.8 | 34.03% | 182.28 | 2905 | 2722.72 | 1494% | 4800 | 0 | -4800 | -100% | 209 | 192.25 | -16.75 | -8.014% | 2019-11-09 01:00
St. Catharines | 2021 | 451107 | 2021 EMERGING OH - 2 ANCHOR RELOCATION | 99 | COMPLETE | Converted Project |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Dan Despres | 5091.44 | 3744.36 | -1347.08 | -26.46% | 1727.95 | 1692.84 | -35.11 | -2.032% | 632.8 | 580.11 | -52.69 | -8.326% | 354.69 | 1228.46 | 873.77 | 246.3% | 2376 | 0 | -2376 | -100% | 12.57 | 15 | 2.43 | 19.33% | 2021-06-29 01:00
St. Catharines | 2022 | 451114 | Bromley Gardens - Subdivision | 99 | CANCELLED | N/A |  |  | Velickovski, Goran | No | Vandekuyt, Greg | Destefano, Nick | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-15 01:00
St. Catharines | 2022 | 451134 | 84 James St, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 18522.35 | 8905.69 | -9616.66 | -51.92% | 10112.76 | 308.42 | -9804.34 | -96.95% | 3849.21 | 0 | -3849.21 | -100% | 294.92 | 0 | -294.92 | -100% | 4250 | 0 | -4250 | -100% | 145.25 | 78 | -67.25 | -46.3% | 2022-02-04 01:00
St. Catharines | 2019 | 451202 | Skyway Bridge Reconstrution | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jolie, Chris | Dan Despres | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
St. Catharines | 2022 | 451223 | Vault Repairs - St. Catharines | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Paesano, Andrew | Frank Giancola | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
St. Catharines | 2019 | 451256 | 2017 St Cath LBDS Replacement | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
St. Catharines | 2021 | 451264 | Lakeshore Rd Road Widening | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Dan Despres | 1540630.54 | 1431927.87 | -108702.67 | -7.056% | 618529.97 | 429889.22 | -188640.75 | -30.5% | 342211.7 | 419613.16 | 77401.46 | 22.62% | 129968.33 | 116732.61 | -13235.72 | -10.18% | 449920.54 | 412050.09 | -37870.45 | -8.417% | 4991 | 4918.75 | -72.25 | -1.448% | 2021-08-13 01:00
St. Catharines | 2019 | 451268 | St Anthony School - Bollards | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
St. Catharines | 2019 | 451270 | Trenergy Boiler Large Load Move | 99 | COMPLETE | Converted Project | N/A | N/A | O'Gay, Brian | No | Johnson, William | Weaver, Thomas | 0 | 16076.96 | 16076.96 |  | 0 | 3073.36 | 3073.36 |  | 0 | 0 | 0 |  | 0 | 375 | 375 |  | 0 | 0 | 0 |  | 0 | 31 | 31 |  | 2019-05-29
St. Catharines | 2022 | 451279 | 281/283 St Paul St | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Dragojevic, Igor | Brad Carr | 50238.2 | 49397.06 | -841.14 | -1.674% | 10783.93 | 130.18 | -10653.75 | -98.79% | 5070.79 | 8848.18 | 3777.39 | 74.49% | 2056 | 0 | -2056 | -100% | 32327.48 | 0 | -32327.48 | -100% | 162.5 | 161 | -1.5 | -0.9231% | 2022-11-01 01:00
St. Catharines | 2021 | 451283 | Thomas Switching Station | 99 | COMPLETE | Converted Project | Covid-19 |  | Beaudrie, Scott | Yes | Billone, Justin | Tony Ierace | 439692.41 | 566476.37 | 126783.96 | 28.83% | 175814.65 | 111303.07 | -64511.58 | -36.69% | 134023.17 | 253259.93 | 119236.76 | 88.97% | 76607.12 | 24723.75 | -51883.37 | -67.73% | 53247.47 | 16011.6 | -37235.87 | -69.93% | 2572 | 2760.25 | 188.25 | 7.319% | 2021-06-17 01:00
St. Catharines | 2022 | 451285 | Welland SS 13kV Removal | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Tony Ierace | 239280.53 | 0 | -239280.53 | -100% | 55343.08 | 0 | -55343.08 | -100% | 121831.65 | 0 | -121831.65 | -100% | 6180.8 | 0 | -6180.8 | -100% | 55925 | 0 | -55925 | -100% | 605.5 | 159.5 | -446 | -73.66% | 2020-01-09 01:00
St. Catharines | 2020 | 451289 | Taylor SS- Cable Removals | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Andrew Mehlenbacher | 96063.31 | 156477.98 | 60414.67 | 62.89% | 35465.61 | 24363.18 | -11102.43 | -31.3% | 55620.9 | 98892.02 | 43271.12 | 77.8% | 4976.8 | 4301.02 | -675.78 | -13.58% | 0 | 2640 | 2640 |  | 628.5 | 639.2 | 10.7 | 1.702% | 2020-01-09 01:00
St. Catharines | 2020 | 451292 | 175-177 Russell Ave | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Frank Giancola | 111390.33 | 122395.64 | 11005.31 | 9.88% | 13969.12 | 18925.32 | 4956.2 | 35.48% | 5315.21 | 5665.6 | 350.39 | 6.592% | 1934 | 2028.9 | 94.9 | 4.907% | 90172 | 91612 | 1440 | 1.597% | 190 | 189.25 | -0.75 | -0.3947% | 2020-06-29 01:00
St. Catharines | 2020 | 451293 | 350 Scott Street | 99 | COMPLETE | FTE OTP | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 50730.75 | 67836.88 | 17106.13 | 33.72% | 11100.81 | 23488.17 | 12387.36 | 111.6% | 22579.32 | 26091.59 | 3512.27 | 15.56% | 6404.62 | 6034.89 | -369.73 | -5.773% | 10646 | 9092.51 | -1553.49 | -14.59% | 200 | 200 | 0 | 0% | 2020-10-26 01:00
St. Catharines | 2022 | 451295 | Killarney Circle Duct & Pad Rebuild | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Paesano, Andrew | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-31 01:00
St. Catharines | 2019 | 451304 | Pole Replacement - 34 Bayview Dr | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Dan Despres | 21225.97 | 29641.04 | 8415.07 | 39.65% | 5740.74 | 7627.5 | 1886.76 | 32.87% | 2022.03 | 3204.6 | 1182.57 | 58.48% | 1573.2 | 3461 | 1887.8 | 120% | 11890 | 0 | -11890 | -100% | 73.2 | 71 | -2.2 | -3.005% | 2019-10-31 01:00
St. Catharines | 2021 | 451305 | PETRIE ST. AND SMITH ST. | 99 | COMPLETE | Under 10% | Vehicle Under Estimated |  | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 91688.26 | 103895.24 | 12206.98 | 13.31% | 51380.43 | 48450.73 | -2929.7 | -5.702% | 15955.44 | 20888.12 | 4932.68 | 30.92% | 14810.59 | 21302.83 | 6492.24 | 43.84% | 9541.8 | 9581.68 | 39.88 | 0.418% | 460 | 476 | 16 | 3.478% | 2021-11-05 01:00
St. Catharines | 2021 | 451324 | 518 Linwell Rd, St Catharines | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-09
St. Catharines | 2019 | 451325 | 275 Ontario St, St. Catharines | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Paesano, Andrew | Weaver, Thomas | 0 | 99440.32 | 99440.32 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-09
St. Catharines | 2022 | 451328 | 179 Louth St, st catharines | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-29 01:00
St. Catharines | 2022 | 451341 | 525 Welland Ave, st catharines | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-03 01:00
St. Catharines | 2019 | 451354 | 212 Lakeport Rd, st catharines | 99 | COMPLETE | Under 10% | N/A | N/A | Gamboa, Henry | No | Paesano, Andrew | Frank Giancola | 60433 | 57467.93 | -2965.07 | -4.906% | 24741.36 | 6 | -24735.36 | -99.98% | 23862.84 | 0 | -23862.84 | -100% | 6328.8 | 0 | -6328.8 | -100% | 5500 | 75.1 | -5424.9 | -98.63% | 346.5 | 311.25 | -35.25 | -10.17% | 2019-02-13 01:00
St. Catharines | 2019 | 451356 | 2017 SCH LBDS Replacement Carryover | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Jolie, Chris | Jakubowski, Mark | 0 | 94280.2 | 94280.2 |  | 0 | 21336.42 | 21336.42 |  | 0 | 41360.41 | 41360.41 |  | 0 | 1091.77 | 1091.77 |  | 0 | 19679.06 | 19679.06 |  | 145 | 311.25 | 166.25 | 114.7% | 2019-05-08
St. Catharines | 2019 | 451360 | St Paul Upgrade - Louth to First | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jolie, Chris | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
St. Catharines | 2019 | 451363 | October Dr URD (St. Catharines) | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | Yes | Karan, Andjelo | Carr, Brad | 1066044.1 | 1351742.66 | 285698.56 | 26.8% | 36236.84 | 25606.18 | -10630.66 | -29.34% | 109363.98 | 122955.8 | 13591.82 | 12.43% | 3158.28 | 0 | -3158.28 | -100% | 917285 | 315721.78 | -601563.22 | -65.58% | 564 | 458.75 | -105.25 | -18.66% | 2019-06-22 01:00
St. Catharines | 2020 | 451364 | 77 Yates, st catharines | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 201192.83 | 106120.69 | -95072.14 | -47.25% | 25391.46 | 24185.55 | -1205.91 | -4.749% | 64111.58 | 56556.71 | -7554.87 | -11.78% | 4951.4 | 9923.58 | 4972.18 | 100.4% | 106738.39 | 0 | -106738.39 | -100% | 289.5 | 459.75 | 170.25 | 58.81% | 2020-09-15 01:00
St. Catharines | 2019 | 451367 | 433 Linwell Rd. | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 38233.93 | 50473.02 | 12239.09 | 32.01% | 12750.71 | 146.5 | -12604.21 | -98.85% | 10900.48 | 13163.64 | 2263.16 | 20.76% | 641.99 | 0 | -641.99 | -100% | 13940.75 | 1749.66 | -12191.09 | -87.45% | 203 | 220.5 | 17.5 | 8.621% | 2019-06-20 01:00
St. Catharines | 2019 | 451381 | 315 Glendale Ave | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Dragojevic, Igor | Weaver, Thomas | 0 | 45366.34 | 45366.34 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-16
St. Catharines | 2019 | 451386 | Haig/Carlton Duct structure | 99 | CANCELLED | N/A | N/A | N/A |  | No | Jolie, Chris | Dan Despres | 162958.58 | 9065.15 | -153893.43 | -94.44% | 18479.99 | 3033.45 | -15446.54 | -83.59% | 31708.79 | 0 | -31708.79 | -100% | 3754.8 | 0 | -3754.8 | -100% | 109015 | 2998.25 | -106016.75 | -97.25% | 267 | 45.5 | -221.5 | -82.96% | 2019-05-29
St. Catharines | 2019 | 451393 | 697 Niagara St, st catharines | 99 | CANCELLED | N/A | N/A | N/A |  | No | Morris, Mark | Weaver, Thomas | 0 | 904.28 | 904.28 |  | 0 | 452.14 | 452.14 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 6 | 6 |  | 2019-05-02 01:00
St. Catharines | 2022 | 451409 | 155 Ontario St, st catharines | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-21 01:00
St. Catharines | 2019 | 451433 | Cable Replacement on MacTurnbull Dr | 99 | COMPLETE | Commodity Price | Labour est. under | BOM not accurate |  | No | Rolfe, Eric | Frank Giancola | 222137 | 155870.16 | -66266.84 | -29.83% | 83117.04 | 320 | -82797.04 | -99.62% | 64594.56 | 112964.55 | 48369.99 | 74.88% | 10590.4 | 2799.2 | -7791.2 | -73.57% | 63835 | 4000 | -59835 | -93.73% | 1492 | 1413.25 | -78.75 | -5.278% | 2019-03-16 01:00
St. Catharines | 2022 | 451435 | 41 MOFFATT STREET - DEVELOPMENT | 99 | CANCELLED | N/A |  |  | Velickovski, Goran | No | Paesano, Andrew | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-19 01:00
St. Catharines | 2019 | 451444 | Marshall Lane Development | 98 | COMPLETE | Converted Project |  |  | Velickovski, Goran | No | Morris, Mark | Frank Giancola | 25253.31 | 159256.69 | 134003.38 | 530.6% | 24231.31 | 12081.22 | -12150.09 | -50.14% | 0 | 614.03 | 614.03 |  | 1022 | 2464 | 1442 | 141.1% | 0 | 0 | 0 |  | 338 | 198.75 | -139.25 | -41.2% | 2019-11-19 01:00
St. Catharines | 2019 | 451452 | Butler Cresent - URD | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Billone, Justin | Carr, Brad | 731210.72 | 1050914.79 | 319704.07 | 43.72% | 30886.5 | 22989.49 | -7897.01 | -25.57% | 109585.7 | 116254.5 | 6668.8 | 6.085% | 2445.12 | 114 | -2331.12 | -95.34% | 588010.4 | 274730.88 | -313279.52 | -53.28% | 477 | 508 | 31 | 6.499% | 2019-06-22 01:00
St. Catharines | 2019 | 451466 | 300 Fourth Ave. St Catharines | 99 | COMPLETE | Material reused | N/A | N/A | McAlpine, Robert | No | Paesano, Andrew | Frank Giancola | 50121.3 | 48135.99 | -1985.31 | -3.961% | 9527.22 | 0 | -9527.22 | -100% | 37963.48 | 0 | -37963.48 | -100% | 2630.6 | 0 | -2630.6 | -100% | 0 | 0 | 0 |  | 139 | 119.5 | -19.5 | -14.03% | 2019-01-30 01:00
St. Catharines | 2020 | 451471 | Hallcrest Ave Rebuild-St.Catharines | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-01 01:00
St. Catharines | 2019 | 451472 | 1160 Lakeshore Rd W, St Catharines | 99 | COMPLETE | N/A | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-01 01:00
St. Catharines | 2019 | 451476 | Moffat Street Reconstruction | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Johnson, William | Dan Despres | 644160.28 | 709733.04 | 65572.76 | 10.18% | 249392.94 | 595.8 | -248797.14 | -99.76% | 157427.44 | 220394.89 | 62967.45 | 40% | 59700.4 | 312 | -59388.4 | -99.48% | 177639.5 | 0 | -177639.5 | -100% | 4191 | 4341.05 | 150.05 | 3.58% | 2019-11-01 01:00
St. Catharines | 2022 | 451501 | 131 Rockwood Ave URD - SCH | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Paesano, Andrew | Jakubowski, Mark | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-28 01:00
St. Catharines | 2020 | 451502 | Geneva St. and Wellend Ave. | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Hotham, Matthew | 0 | 1185.45 | 1185.45 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-02-28 01:00
St. Catharines | 2022 | 451527 | 2B Arlington Ave, St Catharines | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Dragojevic, Igor | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-11 01:00
St. Catharines | 2019 | 451562 | Hilda Street- Pole Replacement- | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 61346.69 | 82447.49 | 21100.8 | 34.4% | 28316.2 | 37913.49 | 9597.29 | 33.89% | 19338.49 | 24391.72 | 5053.23 | 26.13% | 5692 | 11370 | 5678 | 99.75% | 8000 | 3268.75 | -4731.25 | -59.14% | 310 | 492 | 182 | 58.71% | 2019-12-14 01:00
St. Catharines | 2019 | 451574 | New Fourth Ave Road Subdivision | 99 | COMPLETE | Converted Project |  |  | Velickovski, Goran | No | Morris, Mark | Carr, Brad | 5791.73 | 4010.61 | -1781.12 | -30.75% | 5395.53 | 1068.31 | -4327.22 | -80.2% | 0 | 0 | 0 |  | 396.2 | 180 | -216.2 | -54.57% | 0 | 0 | 0 |  | 75 | 53.5 | -21.5 | -28.67% | 2019-09-05 01:00
St. Catharines | 2020 | 451575 | Village on the Twelve Subdivision | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Frank Giancola | 13487.51 | 77201.09 | 63713.58 | 472.4% | 12077.51 | 6591.12 | -5486.39 | -45.43% | 0 | 101.67 | 101.67 |  | 1410 | 493.5 | -916.5 | -65% | 0 | 197.05 | 197.05 |  | 136 | 53 | -83 | -61.03% | 2020-06-15 01:00
St. Catharines | 2021 | 451588 | Glen Morris Dr PMH Unit Drain | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-10-12 01:00
St. Catharines | 2022 | 451592 | 473-475 Carlton Street Development | 99 | CANCELLED | N/A |  |  | Velickovski, Goran | No | Paesano, Andrew | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-08
St. Catharines | 2021 | 451593 | Martindale Road Duct Work | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-08
St. Catharines | 2020 | 451601 | Yates St , St Catharines | 98 | COMPLETE | 3rd party plant |  |  | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 8692.81 | 144053.41 | 135360.6 | 1557% | 7213.21 | 11888.53 | 4675.32 | 64.82% | 0 | 0 | 0 |  | 1479.6 | 0 | -1479.6 | -100% | 0 | 128029.89 | 128029.89 |  | 99 | 51.75 | -47.25 | -47.73% | 2020-12-08 01:00
St. Catharines | 2019 | 451602 | Burgoyne Bridge Additional Costs | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Karan, Andjelo | Weaver, Thomas | 0 | 48357.63 | 48357.63 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 48357.63 | 48357.63 |  | 0 | 0 | 0 |  | 2019-05-08
St. Catharines | 2020 | 451603 | 155 Ontario (temp) - St Catharines | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 18095.63 | 0 | -18095.63 | -100% | 7822.33 | 0 | -7822.33 | -100% | 7764.65 | 0 | -7764.65 | -100% | 1808.65 | 0 | -1808.65 | -100% | 700 | 0 | -700 | -100% | 117.5 | 20.25 | -97.25 | -82.77% | 2020-02-26 01:00
St. Catharines | 2021 | 451607 | 201 St Paul St,St Catharines | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Morris, Mark | Weaver, Thomas | 0 | 634.8 | 634.8 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-16 01:00
St. Catharines | 2019 | 451614 | 2019 Ridley Heights Area Rebuild | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 292635.81 | 214351.57 | -78284.24 | -26.75% | 125026.08 | 5567.74 | -119458.34 | -95.55% | 128154.8 | 47766.46 | -80388.34 | -62.73% | 18890.38 | 1635.01 | -17255.37 | -91.34% | 20564.55 | 3999 | -16565.55 | -80.55% | 1772 | 1948.95 | 176.95 | 9.986% | 2019-11-07 01:00
St. Catharines | 2019 | 451654 | Jacobson Ave. Rearlot Rebuild | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Dan Despres | 491483.9 | 352511.92 | -138971.98 | -28.28% | 258362.01 | 60707.68 | -197654.33 | -76.5% | 102071.49 | 129172.98 | 27101.49 | 26.55% | 54850.4 | 19524 | -35326.4 | -64.4% | 76200 | 973.75 | -75226.25 | -98.72% | 3600 | 2296.75 | -1303.25 | -36.2% | 2019-11-16 01:00
St. Catharines | 2022 | 451656 | 2022 POLE REPLACEMENT-BATCH 2 (12-WP) | 99 | COMPLETE | Under 10% | Vac truck |  | Beaudrie, Scott | Yes | Rolfe, Eric | Frank Giancola | 160352.58 | 150547.84 | -9804.74 | -6.114% | 78744.94 | 72477.73 | -6267.21 | -7.959% | 39873.94 | 41455.04 | 1581.1 | 3.965% | 22483.7 | 24278.5 | 1794.8 | 7.983% | 19250 | 11347.03 | -7902.97 | -41.05% | 689.9 | 747 | 57.1 | 8.277% | 2022-06-20 01:00
St. Catharines | 2019 | 451665 | Pen Centre (sch) | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 107355.97 | 97062.64 | -10293.33 | -9.588% | 33501.01 | 18576.82 | -14924.19 | -44.55% | 67625.09 | 59545.6 | -8079.49 | -11.95% | 4829.87 | 8863.5 | 4033.63 | 83.51% | 1400 | 563.75 | -836.25 | -59.73% | 396.25 | 361.5 | -34.75 | -8.77% | 2019-12-10 01:00
St. Catharines | 2020 | 451671 | 464 Welland Ave, St Catharines | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 55535.1 | 58328.07 | 2792.97 | 5.029% | 20809.53 | 17312.6 | -3496.93 | -16.8% | 23888.99 | 29743.4 | 5854.41 | 24.51% | 3990.46 | 4110 | 119.54 | 2.996% | 6846.12 | 5050 | -1796.12 | -26.24% | 156 | 131.5 | -24.5 | -15.71% | 2020-08-21 01:00
St. Catharines | 2019 | 451676 | 405 Merritt St, St Catharines | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 44664.04 | 47245.37 | 2581.33 | 5.779% | 16409.06 | 8984.24 | -7424.82 | -45.25% | 21895.18 | 21707.56 | -187.62 | -0.8569% | 2484.8 | 3344 | 859.2 | 34.58% | 3875 | 2075 | -1800 | -46.45% | 224.7 | 238.5 | 13.8 | 6.142% | 2019-07-12 01:00
St. Catharines | 2019 | 451678 | Bell Make Ready - S.Service Rd -SCH - work not require now | 99 | COMPLETE | N/A | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 6901.38 | 6901.38 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-01-09 01:00
St. Catharines | 2019 | 451685 | 1643 Third Ave Louth - Raw Perform | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Lustrinelli, Mark | Frank Giancola | 77248.34 | 168353.02 | 91104.68 | 117.9% | 13600 | 16892.75 | 3292.75 | 24.21% | 4865.8 | 34195.64 | 29329.84 | 602.8% | 31611.12 | 2893.5 | -28717.62 | -90.85% | 27171.42 | 18479.82 | -8691.6 | -31.99% | 377 | 297 | -80 | -21.22% | 2019-08-24 01:00
St. Catharines | 2019 | 451687 | 1629 Third Ave. | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Lustrinelli, Mark | Frank Giancola | 34575.53 | 29191.76 | -5383.77 | -15.57% | 13431.39 | 897.99 | -12533.4 | -93.31% | 13689.27 | 13339.76 | -349.51 | -2.553% | 2529.87 | 0 | -2529.87 | -100% | 4925 | 0 | -4925 | -100% | 187.5 | 124 | -63.5 | -33.87% | 2019-08-03 01:00
St. Catharines | 2020 | 451698 | 229 Read Rd, St. Catharines | 95 | COMPLETE | Converted Project |  |  | Frigotto, Rodrigo | No | Alectra Utilities | Frank Giancola | 55619.68 | 46931.9 | -8687.78 | -15.62% | 18784.46 | 12614.21 | -6170.25 | -32.85% | 26964.18 | 21487.72 | -5476.46 | -20.31% | 2432 | 6112.57 | 3680.57 | 151.3% | 7439.04 | 4215.9 | -3223.14 | -43.33% | 138 | 148.5 | 10.5 | 7.609% | 2020-06-30 01:00
St. Catharines | 2019 | 451705 | 79 Simpson Rd, St. Catharines | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Laus, Tomislav | Carr, Brad | 5683.07 | 4822.25 | -860.82 | -15.15% | 1183.72 | 325.2 | -858.52 | -72.53% | 321.15 | 0 | -321.15 | -100% | 113.2 | 0 | -113.2 | -100% | 4065 | 4065 | 0 | 0% | 20.5 | 17.5 | -3 | -14.63% | 2019-10-30 01:00
St. Catharines | 2022 | 451707 | 155 Ontario St, St. Catharines - temp | 95 | COMPLETE | Labour est. under | Metering under |  | Paesano, Andrew | No | Laus, Tomislav | Frank Giancola | 69589.71 | 75843.64 | 6253.93 | 8.987% | 12456.16 | 20257.44 | 7801.28 | 62.63% | 44563.41 | 44103.29 | -460.12 | -1.033% | 1014.14 | 6982.91 | 5968.77 | 588.6% | 11556 | 4500 | -7056 | -61.06% | 72 | 215 | 143 | 198.6% | 2022-05-27 01:00
St. Catharines | 2019 | 451731 | 425 Glendale Ave | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Lustrinelli, Mark | Frank Giancola | 2649.22 | 2729.76 | 80.54 | 3.04% | 2364.62 | 0 | -2364.62 | -100% | 0 | 0 | 0 |  | 284.6 | 0 | -284.6 | -100% | 0 | 0 | 0 |  | 31.5 | 24.25 | -7.25 | -23.02% | 2019-07-26 01:00
St. Catharines | 2021 | 451735 | 285 Geneva St, St Catharines | 99 | CANCELLED | N/A |  |  | McAlpine, Robert | No | Morris, Mark | Weaver, Thomas | 0 | 289.62 | 289.62 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-15 01:00
St. Catharines | 2019 | 451741 | 1242 Fourth Ave, St. Catharines | 99 | COMPLETE | Labour est. under | BOM not accurate | N/A | Kappheim, Adam | No | Bennett, Aaron | Frank Giancola | 47632.41 | 57872.94 | 10240.53 | 21.5% | 9649.05 | 13225.66 | 3576.61 | 37.07% | 24504.76 | 25194.59 | 689.83 | 2.815% | 1638.6 | 670.27 | -968.33 | -59.09% | 11840 | 11840 | 0 | 0% | 133 | 190.5 | 57.5 | 43.23% | 2019-03-30 01:00
St. Catharines | 2019 | 451756 | 16 Preston Dr, St. Catharines | 99 | CANCELLED | N/A | N/A | N/A |  | No | Bennett, Aaron | Weaver, Thomas | 0 | 419 | 419 |  | 0 | 209.5 | 209.5 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-06-07
St. Catharines | 2022 | 451758 | 32 Towering Heights Blvd - temp | 98 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 64680.22 | 64656.16 | -24.06 | -0.0372% | 22543.86 | 440.95 | -22102.91 | -98.04% | 37274.36 | 39287.45 | 2013.09 | 5.401% | 2762 | 0 | -2762 | -100% | 2100 | 200 | -1900 | -90.48% | 312.5 | 300.75 | -11.75 | -3.76% | 2022-11-18 01:00
St. Catharines | 2022 | 451759 | 32 Towering Heights Blvd - pads | 95 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 98433.79 | 99735.87 | 1302.08 | 1.323% | 13769.82 | 23314.32 | 9544.5 | 69.31% | 70333.25 | 70029.01 | -304.24 | -0.4326% | 1089.92 | 4784.25 | 3694.33 | 339% | 13240.8 | 169.55 | -13071.25 | -98.72% | 90 | 207.75 | 117.75 | 130.8% | 2022-11-17 01:00
St. Catharines | 2022 | 451760 | Estimates for COS | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-06 01:00
St. Catharines | 2019 | 451763 | The Enclave Townhomes Sub | 98 | COMPLETE | Converted Project |  |  | Velickovski, Goran | No | Morris, Mark | Frank Giancola | 9278.37 | 150754.86 | 141476.49 | 1525% | 7841.55 | 3063.43 | -4778.12 | -60.93% | 186.82 | 527.5 | 340.68 | 182.4% | 1250 | 639.77 | -610.23 | -48.82% | 0 | 0 | 0 |  | 107 | 99.5 | -7.5 | -7.009% | 2019-09-06 01:00
St. Catharines | 2019 | 451774 | 149 Read Rd | 99 | COMPLETE | N/A | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-05-01
St. Catharines | 2021 | 451775 | 3 Rivercrest Dr, St Catharines | 99 | CANCELLED | N/A |  |  | Gamboa, Henry | No | Morris, Mark | Frank Giancola | 2968.22 | 0 | -2968.22 | -100% | 1970.47 | 0 | -1970.47 | -100% | 486.75 | 0 | -486.75 | -100% | 511 | 0 | -511 | -100% | 0 | 0 | 0 |  | 27 | 21.5 | -5.5 | -20.37% | 2020-05-01
St. Catharines | 2020 | 451778 | 105 Vansickle Rd, St.Catharines | 95 | COMPLETE | Converted Project |  |  | Frigotto, Rodrigo | No | Alectra Utilities | Frank Giancola | 79619.45 | 68199.51 | -11419.94 | -14.34% | 17587.89 | 7367.63 | -10220.26 | -58.11% | 46892.96 | 35722.5 | -11170.46 | -23.82% | 2988.6 | 647.89 | -2340.71 | -78.32% | 12150 | 10650 | -1500 | -12.35% | 249 | 233.25 | -15.75 | -6.325% | 2020-05-01
St. Catharines | 2021 | 451783 | Elllis Ave Condo | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Frank Giancola | 216637.5 | 217062.5 | 425 | 0.1962% | 16589.73 | 15164.53 | -1425.2 | -8.591% | 3638.73 | 2301.19 | -1337.54 | -36.76% | 1325.4 | 2726.5 | 1401.1 | 105.7% | 195083.64 | 96.76 | -194986.88 | -99.95% | 67 | 123.5 | 56.5 | 84.33% | 2021-03-22 01:00
St. Catharines | 2019 | 451796 | 57 Lakeport, (St.Cath) | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Frank Giancola | 21091.22 | 8974.68 | -12116.54 | -57.45% | 15306.15 | 0 | -15306.15 | -100% | 1325.87 | 1455.95 | 130.08 | 9.811% | 2959.2 | 0 | -2959.2 | -100% | 1500 | 0 | -1500 | -100% | 211 | 69.25 | -141.75 | -67.18% | 2019-04-24 01:00
St. Catharines | 2019 | 451799 | 7/9 Abby Ave | 99 | COMPLETE | Scope – Eng | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Frank Giancola | 12190.77 | 16462.15 | 4271.38 | 35.04% | 4546.14 | 4586.62 | 40.48 | 0.8904% | 369.84 | 414.85 | 45.01 | 12.17% | 591.84 | 84.76 | -507.08 | -85.68% | 6682.95 | 10922.45 | 4239.5 | 63.44% | 62 | 56.5 | -5.5 | -8.871% | 2019-05-31
St. Catharines | 2020 | 451800 | Port Dalhousie Marina | 99 | CANCELLED | N/A | N/A | N/A | Kappheim, Adam | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-24 01:00
St. Catharines | 2022 | 451807 | Burbank Dr | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Oosterlinck, David | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-11-14 01:00
St. Catharines | 2019 | 451853 | 23 Clayburn Ave | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 29394.95 | 25859.52 | -3535.43 | -12.03% | 10464.2 | 2893.71 | -7570.49 | -72.35% | 7178.35 | 6837.85 | -340.5 | -4.743% | 2467.4 | 112 | -2355.4 | -95.46% | 9285 | 7285 | -2000 | -21.54% | 164.5 | 127.75 | -36.75 | -22.34% | 2019-09-24 01:00
St. Catharines | 2019 | 451854 | 2018 NRBN Permit Review | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Weaver, Thomas | 0 | 2021.28 | 2021.28 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 3 | 3 |  | 2019-03-14 01:00
St. Catharines | 2021 | 451858 | BROMLEY GARDENS - SUBD RES EDS | 99 | COMPLETE | Labour est. over | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Frank Giancola | 34909.07 | 165040.38 | 130131.31 | 372.8% | 26412.18 | 17222.29 | -9189.89 | -34.79% | 4855.18 | 4596.83 | -258.35 | -5.321% | 3641.71 | 6192 | 2550.29 | 70.03% | 0 | 877.5 | 877.5 |  | 248 | 186.5 | -61.5 | -24.8% | 2021-09-03 01:00
St. Catharines | 2019 | 451861 | 2018 Automated Switches - Part 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Billone, Justin | Dan Despres | 100506.6 | 108745.36 | 8238.76 | 8.197% | 24179.56 | 956.61 | -23222.95 | -96.04% | 72176.88 | 75447.61 | 3270.73 | 4.532% | 4150.16 | 0 | -4150.16 | -100% | 0 | 0 | 0 |  | 324.5 | 362.5 | 38 | 11.71% | 2019-06-15 01:00
St. Catharines | 2019 | 451862 | 2018 Pole Residual PH2 St. Cather | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Frank Giancola | 98450.85 | 56505.97 | -41944.88 | -42.6% | 52059.72 | 18530.89 | -33528.83 | -64.4% | 18769.08 | 9860.07 | -8909.01 | -47.47% | 8990.8 | 5057.63 | -3933.17 | -43.75% | 18631.25 | 0 | -18631.25 | -100% | 721 | 533.5 | -187.5 | -26.01% | 2019-11-26 01:00
St. Catharines | 2022 | 451872 | 40 Lighthouse Rd, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-17 01:00
St. Catharines | 2021 | 451874 | 139 Oakdale Ave, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-17 01:00
St. Catharines | 2021 | 451876 | 20 Gale Cres, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-19 01:00
St. Catharines | 2022 | 451877 | 57 Carlisle Dedicated Feeder | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Johnson, William | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-19 01:00
St. Catharines | 2019 | 451879 | 118 Glenridge Ave, St. Catharines | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 61328.85 | 63093.38 | 1764.53 | 2.877% | 26256.29 | 849.53 | -25406.76 | -96.76% | 23588.56 | 23722.05 | 133.49 | 0.5659% | 4924 | 114 | -4810 | -97.68% | 6560 | 0 | -6560 | -100% | 374 | 379 | 5 | 1.337% | 2019-07-05 01:00
St. Catharines | 2020 | 451915 | The Orchard - Formerly Simpson Rd Condos | 99 | COMPLETE | Converted Project |  |  | Gamboa, Henry | No | Alectra Utilities | Frank Giancola | 197842.39 | 162188.53 | -35653.86 | -18.02% | 24628.86 | 10819.92 | -13808.94 | -56.07% | 2448.65 | 1956.61 | -492.04 | -20.09% | 2968.52 | 2411.51 | -557.01 | -18.76% | 167796.36 | 0 | -167796.36 | -100% | 150.5 | 86 | -64.5 | -42.86% | 2020-08-13 01:00
St. Catharines | 2021 | 451917 | 103 Pelham Rd.-West Park Care Home | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Frank Giancola | 48796.63 | 13431.06 | -35365.57 | -72.48% | 19193.46 | 0 | -19193.46 | -100% | 10091.71 | 8120.38 | -1971.33 | -19.53% | 3698.2 | 0 | -3698.2 | -100% | 15813.26 | 0 | -15813.26 | -100% | 266 | 73.75 | -192.25 | -72.27% | 2021-02-19 01:00
St. Catharines | 2019 | 451918 | Collier St and Beard Pl. | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 136347.74 | 163079.94 | 26732.2 | 19.61% | 58096.84 | 348.43 | -57748.41 | -99.4% | 22300.62 | 31302.01 | 9001.39 | 40.36% | 11950 | 0 | -11950 | -100% | 44000.28 | 0 | -44000.28 | -100% | 815 | 909.4 | 94.4 | 11.58% | 2019-06-05
St. Catharines | 2022 | 451921 | Bunting M75 Reliability - Part 2 | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-28
St. Catharines | 2019 | 451923 | 15 Yale Cres, St. Catharines | 99 | COMPLETE | Under 10% | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 68360.67 | 68904.51 | 543.84 | 0.7955% | 17730.33 | 0 | -17730.33 | -100% | 43424.84 | 0 | -43424.84 | -100% | 2680.5 | 0 | -2680.5 | -100% | 4525 | 0 | -4525 | -100% | 248 | 230.5 | -17.5 | -7.056% | 2019-05-31
St. Catharines | 2019 | 451925 | 387/389 Ontario St - Down to Strut | 99 | CANCELLED | N/A | N/A | N/A |  | No | Johnson, William | Weaver, Thomas | 0 | 759.17 | 759.17 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-05-29
St. Catharines | 2019 | 451926 | Henley Dr. Rear Yard Rebuild | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 103912.64 | 108547.39 | 4634.75 | 4.46% | 58827.27 | 680.89 | -58146.38 | -98.84% | 21725.87 | 29813.15 | 8087.28 | 37.22% | 11384 | 0 | -11384 | -100% | 11975.5 | 922.5 | -11053 | -92.3% | 817 | 584.75 | -232.25 | -28.43% | 2019-06-21 01:00
St. Catharines | 2021 | 451938 | ELLIS AVE 3PH EXPANSION | 99 | COMPLETE | BOM – truck stock | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Brad Carr | 287379.01 | 263691.62 | -23687.39 | -8.243% | 22571.21 | 47574.79 | 25003.58 | 110.8% | 19846.51 | 11685.55 | -8160.96 | -41.12% | 336 | 1039 | 703 | 209.2% | 244625.29 | 200900.12 | -43725.17 | -17.87% | 28.48 | 55.5 | 27.02 | 94.87% | 2021-03-04 01:00
St. Catharines | 2020 | 451941 | 27 Lombardy Ave, St. Catharines | 98 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 92610.21 | 66548.43 | -26061.78 | -28.14% | 50704.41 | 30999.46 | -19704.95 | -38.86% | 20809.05 | 16680.47 | -4128.58 | -19.84% | 10674.75 | 8125 | -2549.75 | -23.89% | 10422 | 8404.13 | -2017.87 | -19.36% | 393 | 270 | -123 | -31.3% | 2020-08-19 01:00
St. Catharines | 2019 | 451942 | 37 Bayview Ave, St. Catharines | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Patel, Ketan | Carr, Brad | 2705.1 | 7299.65 | 4594.55 | 169.8% | 2346.86 | 965.11 | -1381.75 | -58.88% | 358.24 | 0 | -358.24 | -100% | 0 | 76 | 76 |  | 0 | 5232.5 | 5232.5 |  | 0 | 3 | 3 |  | 2019-10-10 01:00
St. Catharines | 2021 | 451943 | 5 Oblate St, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2023-01-03 01:00
St. Catharines | 2019 | 451949 | 1 Abbott St, St. Catharines | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 28401.13 | 27264.95 | -1136.18 | -4% | 11867.44 | 0 | -11867.44 | -100% | 10264.26 | 9808.27 | -455.99 | -4.443% | 2154.43 | 0 | -2154.43 | -100% | 4115 | 0 | -4115 | -100% | 164.75 | 146.25 | -18.5 | -11.23% | 2019-07-26 01:00
St. Catharines | 2019 | 451950 | 12 Colton Ave, St. Catharines | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Carr, Brad | 1094.89 | 1096.26 | 1.37 | 0.1251% | 1066.59 | 0 | -1066.59 | -100% | 0 | 0 | 0 |  | 28.3 | 0 | -28.3 | -100% | 0 | 0 | 0 |  | 14 | 13 | -1 | -7.143% | 2019-05-01 01:00
St. Catharines | 2020 | 451957 | Towering Heights Expansion | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Frank Giancola | 255128.91 | 221035.48 | -34093.43 | -13.36% | 59605.26 | 59380.72 | -224.54 | -0.3767% | 25816.54 | 20652.37 | -5164.17 | -20% | 12131.12 | 9097 | -3034.12 | -25.01% | 157575.99 | 130558.26 | -27017.73 | -17.15% | 436 | 497 | 61 | 13.99% | 2020-11-20 01:00
St. Catharines | 2022 | 451958 | King UG Sec Conversion, St Cath | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Johnson, William | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-04-20
St. Catharines | 2022 | 451962 | MH52 Adjustment | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Johnson, William | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-12-13 01:00
St. Catharines | 2020 | 451965 | 2018 Pole Residual Phase 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 147913.58 | 163678.99 | 15765.41 | 10.66% | 74597.64 | 80779 | 6181.36 | 8.286% | 40859.54 | 42573.92 | 1714.38 | 4.196% | 14456.4 | 19792.5 | 5336.1 | 36.91% | 18000 | 14729.51 | -3270.49 | -18.17% | 891 | 993 | 102 | 11.45% | 2020-02-12 01:00
St. Catharines | 2020 | 451967 | Jacobson Ave - UG Portion | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 1898503.62 | 1920569.82 | 22066.2 | 1.162% | 52300.66 | 177579.67 | 125279.01 | 239.5% | 76144.42 | 71826.74 | -4317.68 | -5.67% | 5096 | 4921.18 | -174.82 | -3.431% | 1764962.54 | 1664803.89 | -100158.65 | -5.675% | 455 | 279.5 | -175.5 | -38.57% | 2020-05-27
St. Catharines | 2019 | 451968 | Cedarbrook Landing | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Frank Giancola | 30317.54 | 217406.33 | 187088.79 | 617.1% | 19269.15 | 19974.54 | 705.39 | 3.661% | 6975.99 | 7141.32 | 165.33 | 2.37% | 3072.4 | 6416 | 3343.6 | 108.8% | 1000 | 1686.5 | 686.5 | 68.65% | 264 | 351.25 | 87.25 | 33.05% | 2019-09-09 01:00
St. Catharines | 2021 | 451969 | Burgoyne Bridge Manhole Adjustment | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Weaver, Thomas | 0 | 21815 | 21815 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-23 01:00
St. Catharines | 2020 | 451973 | 176 Pelham Rd Pole Move | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Frank Giancola | 12040.47 | 11148.24 | -892.23 | -7.41% | 7703.38 | 6977.65 | -725.73 | -9.421% | 1448.72 | 2536.34 | 1087.62 | 75.07% | 1496.25 | 159 | -1337.25 | -89.37% | 1392.12 | 450 | -942.12 | -67.68% | 58 | 84 | 26 | 44.83% | 2020-01-18 01:00
St. Catharines | 2019 | 451978 | SCH 2019 Pole Resduals - Part 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Frank Giancola | 35400.09 | 28949.71 | -6450.38 | -18.22% | 19394.51 | 3860.66 | -15533.85 | -80.09% | 7920.58 | 8533.43 | 612.85 | 7.737% | 717 | 976 | 259 | 36.12% | 7368 | 0 | -7368 | -100% | 254 | 205 | -49 | -19.29% | 2019-09-10 01:00
St. Catharines | 2021 | 451994 | Glenridge Estates | 99 | COMPLETE | Labour est. over | BOM not accurate |  | Gamboa, Henry | No | Morris, Mark | Frank Giancola | 41893.9 | 32849.31 | -9044.59 | -21.59% | 28119.85 | 5177.17 | -22942.68 | -81.59% | 10555.45 | 5411.09 | -5144.36 | -48.74% | 3218.6 | 342 | -2876.6 | -89.37% | 0 | 87.5 | 87.5 |  | 209 | 59 | -150 | -71.77% | 2021-10-04 01:00
St. Catharines | 2019 | 451998 | Ridgewood and Highland Expansion | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Oosterlinck, David | Dan Despres | 54177.31 | 49504.11 | -4673.2 | -8.626% | 28309.9 | 1080.06 | -27229.84 | -96.18% | 5349.2 | 12879.29 | 7530.09 | 140.8% | 4800 | 0 | -4800 | -100% | 15718.21 | 0 | -15718.21 | -100% | 388 | 415.75 | 27.75 | 7.152% | 2019-07-04 01:00
St. Catharines | 2019 | 451999 | 459 Welland Ave. Leaking Pad Mount | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Frank Giancola | 24922.44 | 16210.62 | -8711.82 | -34.96% | 12360.09 | 2448.46 | -9911.63 | -80.19% | 8963.1 | 9618.79 | 655.69 | 7.315% | 1820.8 | 0 | -1820.8 | -100% | 1778.45 | 0 | -1778.45 | -100% | 171 | 78 | -93 | -54.39% | 2019-07-19 01:00
St. Catharines | 2019 | 452002 | 16 Lombardy Ave | 99 | COMPLETE | Vac truck | N/A | N/A | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 24999.32 | 20680.1 | -4319.22 | -17.28% | 13453.74 | 11264.39 | -2189.35 | -16.27% | 6070.68 | 5762.86 | -307.82 | -5.071% | 2474.9 | 745.78 | -1729.12 | -69.87% | 3000 | 0 | -3000 | -100% | 191 | 174 | -17 | -8.901% | 2019-05-18
St. Catharines | 2020 | 452003 | 12 Silverdale Dr | 99 | CANCELLED | N/A | N/A | N/A | Paesano, Andrew | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-07-25 01:00
St. Catharines | 2019 | 452005 | 1 Dunn St | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 8295.54 | 7474.33 | -821.21 | -9.899% | 4268.65 | 0 | -4268.65 | -100% | 3372.79 | 3780.66 | 407.87 | 12.09% | 654.1 | 0 | -654.1 | -100% | 0 | 0 | 0 |  | 65 | 29 | -36 | -55.38% | 2019-07-25 01:00
St. Catharines | 2019 | 452006 | 304 Read Rd | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 4009.54 | 1220.83 | -2788.71 | -69.55% | 0 | 0 | 0 |  | 654.1 | 0 | -654.1 | -100% | 0 | 0 | 0 |  | 3355.44 | 0 | -3355.44 | -100% | 54.5 | 20.5 | -34 | -62.39% | 2019-07-10 01:00
St. Catharines | 2019 | 452007 | 40 Louth St | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 20175.79 | 19196.3 | -979.49 | -4.855% | 10183.21 | 6210.77 | -3972.44 | -39.01% | 1556.23 | 1084.27 | -471.96 | -30.33% | 1995.23 | 3614 | 1618.77 | 81.13% | 6441.12 | 7052.64 | 611.52 | 9.494% | 81 | 72 | -9 | -11.11% | 2019-10-19 01:00
St. Catharines | 2020 | 452013 | St. Catharines 2019 Pole Removals | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Brian Robinson | 0 | 266778.57 | 266778.57 |  | 0 | 66125.86 | 66125.86 |  | 0 | 1045.7 | 1045.7 |  | 0 | 16618 | 16618 |  | 0 | 28127.62 | 28127.62 |  | 0 | 2345.25 | 2345.25 |  | 2020-02-04 01:00
St. Catharines | 2019 | 452014 | SCH 2019 Pole Residuals Phase 1 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Dan Despres | 42489.92 | 48330.35 | 5840.43 | 13.75% | 23925.75 | 22394.06 | -1531.69 | -6.402% | 8825.07 | 7624 | -1201.07 | -13.61% | 4239.1 | 5583 | 1343.9 | 31.7% | 5500 | 6250 | 750 | 13.64% | 314 | 396 | 82 | 26.11% | 2019-09-05 01:00
St. Catharines | 2020 | 452015 | SCH 2019 Pole Residuals Phase 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 95156.09 | 128445.44 | 33289.35 | 34.98% | 48224.68 | 61542.93 | 13318.25 | 27.62% | 27110.41 | 28528.04 | 1417.63 | 5.229% | 8821 | 18473 | 9652 | 109.4% | 11000 | 16893.28 | 5893.28 | 53.58% | 548 | 708 | 160 | 29.2% | 2020-02-11 01:00
St. Catharines | 2019 | 452017 | NRBN Make Ready - Ridley Rd | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Dan Despres | 2341.61 | 2568.84 | 227.23 | 9.704% | 913.81 | 0 | -913.81 | -100% | 262.41 | 0 | -262.41 | -100% | 420.1 | 0 | -420.1 | -100% | 745.29 | 0 | -745.29 | -100% | 12 | 6 | -6 | -50% | 2019-02-01 01:00
St. Catharines | 2019 | 452020 | Bell Make Ready - Secord St | 99 | COMPLETE | BOM not used | Labour est. over | N/A | Jakubowski, Mark | No | Celic, Dusan | Dan Despres | 4806.38 | 6893.18 | 2086.8 | 43.42% | 1923.03 | 0 | -1923.03 | -100% | 237.45 | 0 | -237.45 | -100% | 335.54 | 0 | -335.54 | -100% | 2310.36 | 0 | -2310.36 | -100% | 26 | 13 | -13 | -50% | 2019-05-17
St. Catharines | 2022 | 452040 | BROCK U. ION METER INSTALL (2019) | 99 | COMPLETE | N/A |  |  | Beaudrie, Scott | No | Karan, Andjelo | Weaver, Thomas | 0 | 15945.96 | 15945.96 |  | 0 | 0 | 0 |  | 0 | 873.77 | 873.77 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-12-21 01:00
St. Catharines | 2021 | 452047 | 111 Fourth Ave, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-09-19 01:00
St. Catharines | 2019 | 452051 | 9 West Hampton Rd. | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 25957.51 | 26748.38 | 790.87 | 3.047% | 5250 | 10610.82 | 5360.82 | 102.1% | 2503.2 | 5020.86 | 2517.66 | 100.6% | 3336.93 | 4428.5 | 1091.57 | 32.71% | 14867.38 | 5291.71 | -9575.67 | -64.41% | 207 | 179 | -28 | -13.53% | 2019-09-19 01:00
St. Catharines | 2019 | 452052 | 27 Scott St W, St Cath | 99 | COMPLETE | Converted Project | N/A | N/A | Kappheim, Adam | No | Oosterlinck, David | Dan Despres | 4089.34 | 3481.83 | -607.51 | -14.86% | 3664.59 | 0 | -3664.59 | -100% | 0 | 0 | 0 |  | 84.95 | 0 | -84.95 | -100% | 0 | 0 | 0 |  | 39 | 40 | 1 | 2.564% | 2019-06-05
St. Catharines | 2020 | 452053 | SCH 2019 Pole Residuals Phase 3 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 138041.39 | 141780.33 | 3738.94 | 2.709% | 61247.03 | 9555.1 | -51691.93 | -84.4% | 31759.06 | 35111.14 | 3352.08 | 10.55% | 12007.72 | 190 | -11817.72 | -98.42% | 33027.58 | 95924.85 | 62897.27 | 190.4% | 502.5 | 14 | -488.5 | -97.21% | 2020-02-25 01:00
St. Catharines | 2020 | 452054 | SCH 2019 Pole Residuals Phase 4 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 60447.86 | 72857.83 | 12409.97 | 20.53% | 34897.35 | 4799.95 | -30097.4 | -86.25% | 11534.61 | 13375.52 | 1840.91 | 15.96% | 6515.9 | 0 | -6515.9 | -100% | 7500 | 53459.83 | 45959.83 | 612.8% | 287 | 0 | -287 | -100% | 2020-01-30 01:00
St. Catharines | 2020 | 452055 | SCH 2019 Pole Residuals Phase 5 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 132949.93 | 125865.1 | -7084.83 | -5.329% | 53669.01 | 54462.53 | 793.52 | 1.479% | 56536.92 | 36081.94 | -20454.98 | -36.18% | 10244 | 21181.45 | 10937.45 | 106.8% | 12500 | 12890.11 | 390.11 | 3.121% | 1147 | 619.5 | -527.5 | -45.99% | 2020-08-17 01:00
St. Catharines | 2020 | 452056 | SCH 2019 Pole Residuals Phase 6 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 135770.89 | 119865.64 | -15905.25 | -11.71% | 70843.76 | 55252.78 | -15590.98 | -22.01% | 37711.34 | 23995.79 | -13715.55 | -36.37% | 13715.79 | 22638.57 | 8922.78 | 65.05% | 13500 | 16951.64 | 3451.64 | 25.57% | 1300 | 579 | -721 | -55.46% | 2020-09-28 01:00
St. Catharines | 2019 | 452057 | SCH 2019 Pole Residuals Phase 7 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Dan Despres | 96776.06 | 116346.84 | 19570.78 | 20.22% | 51778.1 | 60270.83 | 8492.73 | 16.4% | 20753.96 | 22319.06 | 1565.1 | 7.541% | 10244 | 19319 | 9075 | 88.59% | 14000 | 12191 | -1809 | -12.92% | 723 | 757.5 | 34.5 | 4.772% | 2019-12-14 01:00
St. Catharines | 2019 | 452060 | Rogers Make Ready - Hwy 6 | 99 | COMPLETE | BOM – truck stock | Labour est. over | N/A | Jakubowski, Mark | No | Celic, Dusan | XPopiel, Joseph | 7878.18 | 4134.08 | -3744.1 | -47.52% | 5043.69 | 0 | -5043.69 | -100% | 783.09 | 0 | -783.09 | -100% | 1223.3 | 0 | -1223.3 | -100% | 828.1 | 0 | -828.1 | -100% | 62 | 10 | -52 | -83.87% | 2019-04-16 01:00
St. Catharines | 2020 | 452065 | LBDS-Switch Replacement-St. Cath. | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 114837.88 | 156059.12 | 41221.24 | 35.9% | 8500 | 74217.38 | 65717.38 | 773.1% | 12066.4 | 43772.52 | 31706.12 | 262.8% | 36633.39 | 21470.76 | -15162.63 | -41.39% | 57638.09 | 3880.5 | -53757.59 | -93.27% | 802 | 935.5 | 133.5 | 16.65% | 2020-02-08 01:00
St. Catharines | 2019 | 452066 | 10 Head St, St. Catharines | 99 | COMPLETE | Labour est. over | BOM – truck stock | N/A | Jakubowski, Mark | No | Patel, Ketan | Carr, Brad | 7268.15 | 6152.67 | -1115.48 | -15.35% | 1789.71 | 1151.67 | -638.04 | -35.65% | 485.14 | 0 | -485.14 | -100% | 28.3 | 5.08 | -23.22 | -82.05% | 4965 | 4965 | 0 | 0% | 23 | 17.5 | -5.5 | -23.91% | 2019-04-26 01:00
St. Catharines | 2021 | 452067 | 425 Lakeshore Rd, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-03-22 01:00
St. Catharines | 2020 | 452078 | 1926 Seventh St Louth, St. Catharines | 98 | COMPLETE | Converted Project | Labour est. under |  | Jakubowski, Mark | No | Alectra Utilities | Frank Giancola | 96436.19 | 143589.04 | 47152.85 | 48.9% | 45208.15 | 40547.83 | -4660.32 | -10.31% | 37344.91 | 84697.82 | 47352.91 | 126.8% | 9384.39 | 11474 | 2089.61 | 22.27% | 4498.74 | 3388.73 | -1110.01 | -24.67% | 237 | 389 | 152 | 64.14% | 2020-10-27 01:00
St. Catharines | 2021 | 452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | 99 | COMPLETE | Labour est. under |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 2020150.47 | 2311987.74 | 291837.27 | 14.45% | 73342.54 | 304909.68 | 231567.14 | 315.7% | 419743.6 | 605209.94 | 185466.34 | 44.19% | 10623.25 | 21530.14 | 10906.89 | 102.7% | 1516441.08 | 1358327.94 | -158113.14 | -10.43% | 698.9667 | 956.9667 | 258 | 36.91% | 2021-08-26 01:00
St. Catharines | 2019 | 452092 | 25 Chetwood St, St. Catharines | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Carr, Brad | 3894.44 | 3502.02 | -392.42 | -10.08% | 1079.86 | 946.02 | -133.84 | -12.39% | 266.28 | 0 | -266.28 | -100% | 28.3 | 5.08 | -23.22 | -82.05% | 2520 | 2520 | 0 | 0% | 14 | 13 | -1 | -7.143% | 2019-04-27 01:00
St. Catharines | 2019 | 452105 | Glendale UG Road Crossingx | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Frank Giancola | 63240 | 89280 | 26040 | 41.18% | 4743.77 | 17524 | 12780.23 | 269.4% | 9804.03 | 18668 | 8863.97 | 90.41% | 852.2 | 2032 | 1179.8 | 138.4% | 47840 | 50583 | 2743 | 5.734% | 66 | 173 | 107 | 162.1% | 2019-10-19 01:00
St. Catharines | 2019 | 452106 | 690 Lake St - TX Replacement | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Webb-Murre, Paige | Dan Despres | 84448.55 | 75439.03 | -9009.52 | -10.67% | 24133.45 | 20627.35 | -3506.1 | -14.53% | 2446.6 | 23830.11 | 21383.51 | 874% | 43562.27 | 4576 | -38986.27 | -89.5% | 14306.23 | 24955.75 | 10649.52 | 74.44% | 198 | 401.5 | 203.5 | 102.8% | 2019-07-24 01:00
St. Catharines | 2019 | 452111 | U/G Pedestal Replacement PHASE 2 | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Frank Giancola | 31317.94 | 31465.29 | 147.35 | 0.4705% | 16600.59 | 11580.39 | -5020.2 | -30.24% | 6214.15 | 5507.58 | -706.57 | -11.37% | 2503.2 | 6814 | 4310.8 | 172.2% | 6000 | 4509.5 | -1490.5 | -24.84% | 230 | 213 | -17 | -7.391% | 2019-10-19 01:00
St. Catharines | 2022 | 452112 | 133 Hannover Dr, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-07-09 01:00
St. Catharines | 2020 | 452114 | 173 Rykert St | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Frank Giancola | 67568.69 | 55360.64 | -12208.05 | -18.07% | 18756.24 | 8277.32 | -10478.92 | -55.87% | 5177.05 | 3586.67 | -1590.38 | -30.72% | 2437.72 | 1686.55 | -751.17 | -30.81% | 41197.68 | 1237.5 | -39960.18 | -97% | 114 | 81.5 | -32.5 | -28.51% | 2020-10-01 01:00
St. Catharines | 2019 | 452118 | Bell Make Ready - Decew Rd | 99 | COMPLETE | Converted Project | N/A | N/A | Jakubowski, Mark | No | Celic, Dusan | Hewitson, Trevor | 6792.82 | 3585.05 | -3207.77 | -47.22% | 1912.34 | 114.51 | -1797.83 | -94.01% | 0 | 0 | 0 |  | 198.24 | 0 | -198.24 | -100% | 4682.24 | 1159.34 | -3522.9 | -75.24% | 8 | 0 | -8 | -100% | 2019-11-01 01:00
St. Catharines | 2019 | 452125 | 22 Townline RD. West | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 26375.57 | 36238.41 | 9862.84 | 37.39% | 16854.65 | 0 | -16854.65 | -100% | 4561.72 | 4772.79 | 211.07 | 4.627% | 2959.2 | 0 | -2959.2 | -100% | 2000 | 0 | -2000 | -100% | 234 | 388.5 | 154.5 | 66.03% | 2019-05-07
St. Catharines | 2019 | 452127 | 1520 Fifth St, St. Catharines | 99 | COMPLETE | Converted Project | N/A | N/A |  | No | Patel, Ketan | Carr, Brad | 5292.99 | 5218.74 | -74.25 | -1.403% | 1382.83 | 414.67 | -968.16 | -70.01% | 373.16 | 645.33 | 272.17 | 72.94% | 0 | 38 | 38 |  | 3537 | 3275 | -262 | -7.407% | 0 | 2 | 2 |  | 2019-10-29 01:00
St. Catharines | 2020 | 452128 | 9 Main St, St. Catharines | 98 | COMPLETE | Converted Project |  |  | Jakubowski, Mark | No | Alectra Utilities | Frank Giancola | 16160.3 | 9154.84 | -7005.46 | -43.35% | 13536.45 | 6797.48 | -6738.97 | -49.78% | 299.97 | 114.76 | -185.21 | -61.74% | 2323.88 | 507.5 | -1816.38 | -78.16% | 0 | 0 | 0 |  | 84 | 29 | -55 | -65.48% | 2020-08-27 01:00
St. Catharines | 2022 | 452139 | U/G PEDESTAL REPLACEMENT 2022 (15 PEDS) | 99 | COMPLETE | Vac truck | Vehicle Not Charged |  | Beaudrie, Scott | No | Rolfe, Eric | Frank Giancola | 104035.35 | 75006.12 | -29029.23 | -27.9% | 50913.76 | 42676.83 | -8236.93 | -16.18% | 20600.54 | 19993.31 | -607.23 | -2.948% | 6121.05 | 0 | -6121.05 | -100% | 26400 | 9477.74 | -16922.26 | -64.1% | 431.28 | 416 | -15.28 | -3.543% | 2022-05-24 01:00
St. Catharines | 2022 | 452143 | VINE SS - DECOMMISSIONING | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-13 01:00
St. Catharines | 2022 | 452144 | GRANTHAM SS - DECOMMISSIONING | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-08-13 01:00
St. Catharines | 2022 | 452147 | 17 East St. (SCH) | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Morris, Mark | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-02-01 01:00
St. Catharines | 2019 | 452149 | 0 St David's Rd | 99 | COMPLETE | Converted Project |  |  | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 12294.4 | 7237.24 | -5057.16 | -41.13% | 10299.34 | 3896.12 | -6403.22 | -62.17% | 0 | 0 | 0 |  | 1995.06 | 3144 | 1148.94 | 57.59% | 0 | 0 | 0 |  | 78 | 32 | -46 | -58.97% | 2019-09-26 01:00
St. Catharines | 2019 | 452150 | 206 Bunting Rd | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 3978.1 | 1123.18 | -2854.92 | -71.77% | 0 | 0 | 0 |  | 654.1 | 0 | -654.1 | -100% | 0 | 0 | 0 |  | 3324 | 0 | -3324 | -100% | 46.5 | 16.5 | -30 | -64.52% | 2019-07-26 01:00
St. Catharines | 2019 | 452162 | 2513 Fifth St. St. Catharines | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Lustrinelli, Mark | Frank Giancola | 25315.99 | 24935.73 | -380.26 | -1.502% | 0 | 7443.46 | 7443.46 |  | 1820.8 | 12256.39 | 10435.59 | 573.1% | 11682.17 | 2599 | -9083.17 | -77.75% | 11813.02 | 0 | -11813.02 | -100% | 164 | 145 | -19 | -11.59% | 2019-09-04 01:00
St. Catharines | 2020 | 452166 | Westchester & 406, St. Catharines | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-04 01:00
St. Catharines | 2020 | 452167 | 427 Geneva St. (SCH) | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Frank Giancola | 91710.37 | 85857.73 | -5852.64 | -6.382% | 26163.9 | 20058.71 | -6105.19 | -23.33% | 6903.95 | 8317.9 | 1413.95 | 20.48% | 4016.12 | 5704.77 | 1688.65 | 42.05% | 54626.4 | 36.5 | -54589.9 | -99.93% | 142.5 | 196.5 | 54 | 37.89% | 2020-12-04 01:00
St. Catharines | 2020 | 452168 | St. Davids Rd Pole Relocations | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-26 01:00
St. Catharines | 2022 | 452169 | Lakeport Rd , St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-26 01:00
St. Catharines | 2022 | 452170 | Main St, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-26 01:00
St. Catharines | 2022 | 452172 | 43 Scott St W, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-06-26 01:00
St. Catharines | 2020 | 452173 | 125 Rykert St. (SCH) | 99 | COMPLETE | Converted Project | N/A | N/A | Gamboa, Henry | No | Alectra Utilities | Frank Giancola | 107611.3 | 126503.26 | 18891.96 | 17.56% | 32141.12 | 36368.67 | 4227.55 | 13.15% | 15989.82 | 12106.19 | -3883.63 | -24.29% | 5138.27 | 14965.32 | 9827.05 | 191.3% | 54342.09 | 8600.66 | -45741.43 | -84.17% | 234 | 393.5 | 159.5 | 68.16% | 2020-06-26 01:00
St. Catharines | 2021 | 452174 | 128 Grantham Ave | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | No | Karan, Andjelo | Dan Despres | 50240.38 | 28460.32 | -21780.06 | -43.35% | 22364.44 | 9672.11 | -12692.33 | -56.75% | 9309.35 | 8364.41 | -944.94 | -10.15% | 4252.53 | 2418 | -1834.53 | -43.14% | 14314.06 | 7488.36 | -6825.7 | -47.69% | 178 | 102 | -76 | -42.7% | 2021-01-15 01:00
St. Catharines | 2020 | 452175 | 340 Welland Ave | 99 | COMPLETE | Cont Est Over | Electrician | Labour est. over | Beaudrie, Scott | No | Alectra Utilities | Frank Giancola | 99083.89 | 84776.5 | -14307.39 | -14.44% | 39498.09 | 31550.35 | -7947.74 | -20.12% | 26404.38 | 39407.83 | 13003.45 | 49.25% | 9332.86 | 10123.6 | 790.74 | 8.473% | 23848.56 | 2512 | -21336.56 | -89.47% | 320 | 267.5 | -52.5 | -16.41% | 2020-11-03 01:00
St. Catharines | 2022 | 452176 | 2 CUSHMAN RD. | 99 | COMPLETE | N/A |  |  | Beaudrie, Scott | No | Rolfe, Eric | Weaver, Thomas | 155460.16 | 25204.7 | -130255.46 | -83.79% | 92035.07 | 19012.8 | -73022.27 | -79.34% | 17152.5 | 3533.75 | -13618.75 | -79.4% | 21331.59 | 957.99 | -20373.6 | -95.51% | 24941 | 0 | -24941 | -100% | 770.65 | 132 | -638.65 | -82.87% | 2022-12-21 01:00
St. Catharines | 2019 | 452177 | 43 Scott Street-Pole Residual | 99 | COMPLETE | Converted Project | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 52889.03 | 62618.1 | 9729.07 | 18.4% | 38105.84 | 31628.35 | -6477.49 | -17% | 7992.51 | 10895.26 | 2902.75 | 36.32% | 6790.68 | 11078 | 4287.32 | 63.14% | 0 | 8622.25 | 8622.25 |  | 268 | 375.5 | 107.5 | 40.11% | 2019-10-17 01:00
St. Catharines | 2019 | 452179 | 57 Lakeport Rd | 99 | COMPLETE | Converted Project | N/A | N/A | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 20374.28 | 19431.94 | -942.34 | -4.625% | 8282.04 | 5867.91 | -2414.13 | -29.15% | 9374.72 | 10131.07 | 756.35 | 8.068% | 1325.4 | 3088 | 1762.6 | 133% | 1392.12 | 0 | -1392.12 | -100% | 55 | 54.5 | -0.5 | -0.9091% | 2019-09-24 01:00
St. Catharines | 2022 | 452182 | Hastings St, St. Catharines | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-05-05
St. Catharines | 2020 | 631686 | MOFFATT ST, ST. CATHARINES | 99 | COMPLETE | Safety |  |  | Jakubowski, Mark | No | Alectra Utilities | Dan Despres | 76003.14 | 83557.92 | 7554.78 | 9.94% | 41087.7 | 50041.94 | 8954.24 | 21.79% | 6109.58 | 17088.18 | 10978.6 | 179.7% | 16227.86 | 11063.5 | -5164.36 | -31.82% | 12578 | 5364.3 | -7213.7 | -57.35% | 568 | 510.5 | -57.5 | -10.12% | 2020-09-04 01:00
St. Catharines | 2021 | 631935 | 2021 - EMERGING UG - 2 POLES & CABLE REPLACEMENT | 99 | COMPLETE | Cont Est Over |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Brad Carr | 60128.5 | 49041.7 | -11086.8 | -18.44% | 3183.7 | 9534.13 | 6350.43 | 199.5% | 6933.81 | 5957.71 | -976.1 | -14.08% | 192 | 139.4 | -52.6 | -27.4% | 49818.99 | 33410.46 | -16408.53 | -32.94% | 12 | 3 | -9 | -75% | 2021-06-21 01:00
St. Catharines | 2020 | 633175 | HYDRO POLE RELOCATION - GENEVA ST & GUY RD | 99 | COMPLETE | Cont Est Over |  |  | Jakubowski, Mark | No | Alectra Utilities | Frank Giancola | 5217.46 | 2256.09 | -2961.37 | -56.76% | 3173.72 | 1905.4 | -1268.32 | -39.96% | 195.62 | 132.69 | -62.93 | -32.17% | 456 | 218 | -238 | -52.19% | 1392.12 | 0 | -1392.12 | -100% | 16 | 8 | -8 | -50% | 2020-06-17 01:00
St. Catharines | 2019 | 633210 | 224 - 228 GLENDALE AVE | 99 | COMPLETE | Cont Est Over | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 93157.83 | 70861.81 | -22296.02 | -23.93% | 22553.5 | 20124.68 | -2428.82 | -10.77% | 10500.97 | 11966.36 | 1465.39 | 13.95% | 3956.32 | 9072 | 5115.68 | 129.3% | 56147.04 | 29698.77 | -26448.27 | -47.11% | 167 | 173 | 6 | 3.593% | 2019-09-12 01:00
St. Catharines | 2020 | 633222 | 2020 SWITCH REPLACEMENT PROGRAM - ST. CATHARINES | 99 | COMPLETE | Scope change - unforeseen | Labour est. over | Vac truck | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 211562.02 | 32824.78 | -178737.24 | -84.48% | 73671.94 | 20504.38 | -53167.56 | -72.17% | 126715.88 | 638.91 | -126076.97 | -99.5% | 11174.2 | 7180.59 | -3993.61 | -35.74% | 0 | 4500.9 | 4500.9 |  | 666 | 208 | -458 | -68.77% | 2020-12-04 01:00
St. Catharines | 2022 | 633232 | BUM81 FEEDER EXTENSION PART 2 - NORTH OF CARLTON (ST. CATH) | 95 | ANALYZE |  |  |  | Beaudrie, Scott | Yes | Karan, Andjelo | Brad Carr | 2950963.79 | 2867327.61 | -83636.18 | -2.834% | 184184.53 | 294101.25 | 109916.72 | 59.68% | 653921.03 | 845389.8 | 191468.77 | 29.28% | 794 | 2331.03 | 1537.03 | 193.6% | 2112064.23 | 1725282.78 | -386781.45 | -18.31% | 272 | 207 | -65 | -23.9% | 2022-10-28 01:00
St. Catharines | 2021 | 633234 | 57 STRATHCONA DR - POLE REPLACEMENT | 99 | COMPLETE | Engineering by-passed |  |  | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 451.43 | 13799.72 | 13348.29 | 2957% | 451.43 | 1578.13 | 1126.7 | 249.6% | 0 | 1220.16 | 1220.16 |  | 0 | 0 | 0 |  | 0 | 11001.43 | 11001.43 |  | 0 | 4 | 4 |  | 2021-09-13 01:00
St. Catharines | 2020 | 633235 | POLE REPLACEMENT 2020- PH1 POLES - FLamingo Ave | 99 | COMPLETE | Labour est. over | Vac truck | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 117469.69 | 89083.11 | -28386.58 | -24.17% | 73286.73 | 44669.59 | -28617.14 | -39.05% | 18737.08 | 27399.29 | 8662.21 | 46.23% | 17093.16 | 15317.73 | -1775.43 | -10.39% | 8352.72 | 1696.5 | -6656.22 | -79.69% | 624 | 392 | -232 | -37.18% | 2020-07-20 01:00
St. Catharines | 2020 | 633236 | POLE REPLACEMENT 2020 - PH2 POLES - Silverdale Dr | 99 | COMPLETE | Labour est. over | Vac truck | BOM not accurate | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 150096.89 | 85078.49 | -65018.4 | -43.32% | 88786.53 | 45968.83 | -42817.7 | -48.23% | 25150.24 | 18191.06 | -6959.18 | -27.67% | 21472.12 | 16862.6 | -4609.52 | -21.47% | 14688 | 4056 | -10632 | -72.39% | 826 | 432 | -394 | -47.7% | 2020-07-20 01:00
St. Catharines | 2020 | 633237 | POLE REPLACEMENT 2020- PH3 POLES - Decew Pole Line | 99 | COMPLETE | Electrician | Vac truck | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 192677.96 | 123779.54 | -68898.42 | -35.76% | 85975.59 | 74977.13 | -10998.46 | -12.79% | 30020.59 | 27769.98 | -2250.61 | -7.497% | 19729.06 | 16699.42 | -3029.64 | -15.36% | 56952.72 | 4333.01 | -52619.71 | -92.39% | 729 | 776 | 47 | 6.447% | 2020-09-18 01:00
St. Catharines | 2020 | 633238 | U/G PEDESTAL REPLACEMENT 2020 - PH1 | 99 | COMPLETE | Labour est. over | Vac truck | N/A | Beaudrie, Scott | No | Alectra Utilities | Frank Giancola | 134736.46 | 92334.65 | -42401.81 | -31.47% | 89013.13 | 32581.16 | -56431.97 | -63.4% | 26702.43 | 31203.42 | 4500.99 | 16.86% | 8580 | 11894.3 | 3314.3 | 38.63% | 10440.9 | 16655.77 | 6214.87 | 59.52% | 804 | 369 | -435 | -54.1% | 2020-11-05 01:00
St. Catharines | 2021 | 633239 | U/G PEDESTAL REPLACEMENT 2020 - PH2 | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | Yes | Rolfe, Eric | Frank Giancola | 151483.38 | 137627.33 | -13856.05 | -9.147% | 99883.2 | 64931.58 | -34951.62 | -34.99% | 31061.28 | 41667.4 | 10606.12 | 34.15% | 10098 | 1169.75 | -8928.25 | -88.42% | 10440.9 | 29858.6 | 19417.7 | 186% | 926 | 761 | -165 | -17.82% | 2021-02-11 01:00
St. Catharines | 2021 | 633240 | U/G PEDESTAL REPLACEMENT 2020 - PH3 | 99 | COMPLETE | Vac truck | N/A | N/A | Beaudrie, Scott | Yes | Rolfe, Eric | Frank Giancola | 84626.42 | 118955.97 | 34329.55 | 40.57% | 51990.62 | 51759.92 | -230.7 | -0.4437% | 19100.55 | 23193.19 | 4092.64 | 21.43% | 4834.5 | 0 | -4834.5 | -100% | 8700.75 | 44002.86 | 35302.11 | 405.7% | 458 | 566.5 | 108.5 | 23.69% | 2021-05-05
St. Catharines | 2019 | 633504 | 350 SCOTT STREET | 99 | COMPLETE | Labour est. over |  |  | Paesano, Andrew | No | Bharosi, Mohindra | Frank Giancola | 33830.92 | 0 | -33830.92 | -100% | 19442.47 | 0 | -19442.47 | -100% | 8167.68 | 0 | -8167.68 | -100% | 2748.57 | 0 | -2748.57 | -100% | 3472.2 | 0 | -3472.2 | -100% | 158 | 0 | -158 | -100% | 2019-12-11 01:00
St. Catharines | 2020 | 633563 | 439 VINE ST - POLE & SERVICE RELOCATION | 99 | COMPLETE | Labour est. over | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Dan Despres | 20663.11 | 13791.73 | -6871.38 | -33.25% | 10053.98 | 5871.91 | -4182.07 | -41.6% | 5924.63 | 5522.32 | -402.31 | -6.79% | 1984.5 | 1310 | -674.5 | -33.99% | 2700 | 1087.5 | -1612.5 | -59.72% | 78 | 50 | -28 | -35.9% | 2020-06-05 01:00
St. Catharines | 2020 | 633675 | 64 CURRIE ST | 99 | CANCELLED | N/A | N/A | N/A | Jakubowski, Mark | No | Alectra Utilities | Dre Danieli | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2019-11-15 01:00
St. Catharines | 2020 | 633809 | 189 RIVERVIEW BLVD - ARIAL TRESPASS | 99 | COMPLETE | FTE OTP | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Carr, Brad | 26891.13 | 31812.11 | 4920.98 | 18.3% | 1898.17 | 5209.27 | 3311.1 | 174.4% | 0 | 4068.36 | 4068.36 |  | 242.6 | 654.48 | 411.88 | 169.8% | 24750.36 | 21880 | -2870.36 | -11.6% | 9 | 21 | 12 | 133.3% | 2020-05-27
St. Catharines | 2021 | 634043 | JOINT USE PERMIT HW2019-121 - COURT AND CENTRE, ST CATH | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Hewitson, Trevor | 7005.08 | 2369.58 | -4635.5 | -66.17% | 2097.85 | 821.86 | -1275.99 | -60.82% | 449.32 | 0 | -449.32 | -100% | 183.36 | 149.41 | -33.95 | -18.52% | 4274.55 | 1398.31 | -2876.24 | -67.29% | 6 | 18 | 12 | 200% | 2021-03-24 01:00
St. Catharines | 2020 | 634058 | JOINT USE PERMIT HW2019-104 - SEAPARK DR, ST CATH | 99 | COMPLETE | Scope change - unforeseen | Scope change - unforeseen | BOM not accurate | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 5247.4 | 4974.28 | -273.12 | -5.205% | 1129.22 | 1964.67 | 835.45 | 73.98% | 178.28 | 382.75 | 204.47 | 114.7% | 89.7 | 729.72 | 640.02 | 713.5% | 3850.2 | 1897.14 | -1953.06 | -50.73% | 6 | 24 | 18 | 300% | 2020-08-21 01:00
St. Catharines | 2020 | 634171 | BELL BONDS - Y06557, ST CATH | 99 | COMPLETE | Labour est. over | Scope change - unforeseen | Labour est. under | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 5561.47 | 1702.94 | -3858.53 | -69.38% | 4926.39 | 1521.7 | -3404.69 | -69.11% | 0 | 0 | 0 |  | 635.08 | 181.24 | -453.84 | -71.46% | 0 | 0 | 0 |  | 28 | 16 | -12 | -42.86% | 2020-06-01 01:00
St. Catharines | 2020 | 634497 | ST. CATHARINES PCB TX REPLACEMENT 2020 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 25051.32 | 23459.36 | -1591.96 | -6.355% | 16109.1 | 9374.43 | -6734.67 | -41.81% | 5420.67 | 5590.45 | 169.78 | 3.132% | 3173.52 | 4660.48 | 1486.96 | 46.86% | 348.03 | 3834 | 3485.97 | 1002% | 117 | 107 | -10 | -8.547% | 2020-03-05 01:00
St. Catharines | 2019 | 634719 | TOWERING HEIGHTS - EMERGENCY CABLE REPAIRS/REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 58994.63 | 55439.54 | -3555.09 | -6.026% | 30361.12 | 30616.59 | 255.47 | 0.8414% | 10026.98 | 7482.95 | -2544.03 | -25.37% | 4600.01 | 5790 | 1189.99 | 25.87% | 14006.52 | 11550 | -2456.52 | -17.54% | 220 | 302.5 | 82.5 | 37.5% | 2019-12-20 01:00
St. Catharines | 2020 | 634906 | ROAD RECONSTRUCTION - ST.DAVIDS RD | 99 | COMPLETE | Civil contractor | Labour est. under | N/A | Jakubowski, Mark | No | Alectra Utilities | Carr, Brad | 563046 | 604052.41 | 41006.41 | 7.283% | 16036.62 | 52478.21 | 36441.59 | 227.2% | 76631.21 | 129048.12 | 52416.91 | 68.4% | 1078 | 1053 | -25 | -2.319% | 469300.17 | 420937.64 | -48362.53 | -10.31% | 64 | 74 | 10 | 15.62% | 2020-09-10 01:00
St. Catharines | 2022 | 635016 | CABLE INJECT - LAKESHORE/STANLEY/PARNELL | 99 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 75066.64 | 76883.35 | 1816.71 | 2.42% | 4440.46 | 9450.48 | 5010.02 | 112.8% | 1506.18 | 3264.06 | 1757.88 | 116.7% | 0 | 69.7 | 69.7 |  | 69120 | 64099.11 | -5020.89 | -7.264% | 0 | 2.5 | 2.5 |  | 2022-05-31 01:00
St. Catharines | 2022 | 635017 | CABLE INJECT - MILLWARD/JEANETTE/TREVOR | 99 | COMPLETE | Cont Est Under |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 54925.46 | 79573.37 | 24647.91 | 44.88% | 4440.46 | 14690.19 | 10249.73 | 230.8% | 805 | 1842.45 | 1037.45 | 128.9% | 0 | 383.35 | 383.35 |  | 49680 | 62657.38 | 12977.38 | 26.12% | 1 | 35.25 | 34.25 | 3425% | 2022-02-24 01:00
St. Catharines | 2020 | 635068 | 350 SCOTT ST PHASE 2 | 99 | COMPLETE | Labour est. under | Electrician | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 86868.63 | 96860.27 | 9991.64 | 11.5% | 26221.39 | 40859.84 | 14638.45 | 55.83% | 32548.88 | 32838.29 | 289.41 | 0.8892% | 6951.96 | 11990.67 | 5038.71 | 72.48% | 21146.4 | 11171.47 | -9974.93 | -47.17% | 248 | 368.5 | 120.5 | 48.59% | 2020-10-26 01:00
St. Catharines | 2021 | 635181 | VSM82 - AUTOMATION - 2 | 99 | COMPLETE | BOM not accurate | Labour est. under | N/A | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 324838.43 | 345721.32 | 20882.89 | 6.429% | 8908.89 | 35969.68 | 27060.79 | 303.8% | 56126.54 | 96898.61 | 40772.07 | 72.64% | 728 | 953.6 | 225.6 | 30.99% | 259075 | 211899.43 | -47175.57 | -18.21% | 52 | 173.5 | 121.5 | 233.7% | 2021-03-04 01:00
St. Catharines | 2020 | 635414 | SCH 2020 Bell Transfers | 99 | COMPLETE | FTE OTP | BOM not accurate | N/A | Beaudrie, Scott | No | Alectra Utilities | Frank Giancola | 28502.99 | 12812.81 | -15690.18 | -55.05% | 10442.48 | 7240.76 | -3201.72 | -30.66% | 15423.69 | 5097.37 | -10326.32 | -66.95% | 2636.82 | 474.68 | -2162.14 | -82% | 0 | 0 | 0 |  | 92 | 68 | -24 | -26.09% | 2020-02-24 01:00
St. Catharines | 2021 | 635627 | POLE RESIDUAL 2021 PH1 - 11 | 99 | COMPLETE | Labour est. under | Vac truck | N/A | Beaudrie, Scott | Yes | Rolfe, Eric | Dan Despres | 157373.91 | 156595.29 | -778.62 | -0.4948% | 88710.45 | 72298.36 | -16412.09 | -18.5% | 37309.26 | 45915.07 | 8605.81 | 23.07% | 20338.2 | 19724.5 | -613.7 | -3.017% | 11016 | 18657.36 | 7641.36 | 69.37% | 752 | 805 | 53 | 7.048% | 2021-02-08 01:00
St. Catharines | 2020 | 635634 | TRENERGY INC. - OVERSIZE LOAD MOVE, ST. CATHARINES | 99 | COMPLETE | Labour est. over |  |  | Jakubowski, Mark | No | Alectra Utilities | Dan Despres | 40230.35 | 29366.47 | -10863.88 | -27% | 29814.7 | 24669.29 | -5145.41 | -17.26% | 1609.69 | 2000.58 | 390.89 | 24.28% | 4793.96 | 2588 | -2205.96 | -46.02% | 4012 | 0 | -4012 | -100% | 144 | 232 | 88 | 61.11% | 2020-05-24
St. Catharines | 2020 | 635714 | PEN CENTER - P10248 TX REPLACEMENT | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Brian Robinson | 27854.78 | 21617.8 | -6236.98 | -22.39% | 7307.73 | 2317.66 | -4990.07 | -68.28% | 19028.57 | 19300.14 | 271.57 | 1.427% | 1518.48 | 0 | -1518.48 | -100% | 0 | 0 | 0 |  | 70 | 26 | -44 | -62.86% | 2020-02-10 01:00
St. Catharines | 2020 | 635757 | SC1474 - HEYWOOD GS | 99 | COMPLETE | Scope change - unforeseen | N/A | N/A | Beaudrie, Scott | Yes | Alectra Utilities | Frank Giancola | 127551.86 | 175554.49 | 48002.63 | 37.63% | 23070.13 | 52558.84 | 29488.71 | 127.8% | 92505.97 | 109801.09 | 17295.12 | 18.7% | 3416.76 | 10796.06 | 7379.3 | 216% | 8559 | 2398.5 | -6160.5 | -71.98% | 142 | 495.5 | 353.5 | 248.9% | 2020-11-05 01:00
St. Catharines | 2020 | 635817 | BELL BONDS - X79674 AND Y41957 - ST CATH | 99 | COMPLETE | Labour est. over | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 2428.84 | 774.88 | -1653.96 | -68.1% | 2217.15 | 774.88 | -1442.27 | -65.05% | 0 | 0 | 0 |  | 211.69 | 0 | -211.69 | -100% | 0 | 0 | 0 |  | 11 | 4 | -7 | -63.64% | 2020-06-10 01:00
St. Catharines | 2021 | 635951 | POLE RESIDUAL 2021 PH 2 - BARTON ST - 8 | 99 | COMPLETE | BOM not accurate | N/A | N/A | Beaudrie, Scott | Yes | Rolfe, Eric | Dan Despres | 118802.33 | 90287.86 | -28514.47 | -24% | 74221.07 | 44663.83 | -29557.24 | -39.82% | 20531.63 | 25996.28 | 5464.65 | 26.62% | 16705.63 | 11819 | -4886.63 | -29.25% | 7344 | 7808.75 | 464.75 | 6.328% | 623 | 575 | -48 | -7.705% | 2021-03-12 01:00
St. Catharines | 2020 | 636018 | ALTMAR COURT - CABLE REPLACEMENT | 99 | COMPLETE | Labour est. over | Cont Est Over | N/A | Beaudrie, Scott | No | Alectra Utilities | Frank Giancola | 73878.23 | 58293.16 | -15585.07 | -21.1% | 22520.54 | 12149.13 | -10371.41 | -46.05% | 3678.81 | 38915.44 | 35236.63 | 957.8% | 5149.56 | 628.59 | -4520.97 | -87.79% | 42529.32 | 6600 | -35929.32 | -84.48% | 172.49 | 81 | -91.49 | -53.04% | 2020-10-01 01:00
St. Catharines | 2020 | 636021 | 376 READ RD | 98 | COMPLETE | Cont Est Over | Labour est. over |  | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 61084.8 | 46202.08 | -14882.72 | -24.36% | 20383.24 | 13941.9 | -6441.34 | -31.6% | 24424 | 24124.45 | -299.55 | -1.226% | 3461.2 | 3583 | 121.8 | 3.519% | 12816.36 | 4552.73 | -8263.63 | -64.48% | 156 | 104 | -52 | -33.33% | 2020-08-07 01:00
St. Catharines | 2021 | 636048 | POLE RESIDUAL 2021 PHASE 3 - 14 | 99 | COMPLETE | Labour est. under | N/A | N/A | Beaudrie, Scott | Yes | Rolfe, Eric | Frank Giancola | 175584.88 | 190536.29 | 14951.41 | 8.515% | 101885.06 | 104317.11 | 2432.05 | 2.387% | 27600.62 | 33268.24 | 5667.62 | 20.53% | 24024 | 31997 | 7973 | 33.19% | 22075.2 | 20953.94 | -1121.26 | -5.079% | 850 | 1158.5 | 308.5 | 36.29% | 2021-04-14
St. Catharines | 2021 | 636055 | 57 LAKEPORT RD PERM | 95 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Dragojevic, Igor | Frank Giancola | 133059.03 | 126850.22 | -6208.81 | -4.666% | 46139.83 | 45197.58 | -942.25 | -2.042% | 52245.82 | 57846.32 | 5600.5 | 10.72% | 8728.42 | 13053.19 | 4324.77 | 49.55% | 25944.96 | 10753.13 | -15191.83 | -58.55% | 327.01 | 413.2 | 86.19 | 26.36% | 2021-11-16 01:00
St. Catharines | 2021 | 636243 | 101 HANNOVER DR | 99 | CANCELLED |  |  |  | Paesano, Andrew | No | Laus, Tomislav | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-11-02 01:00
St. Catharines | 2021 | 636338 | 57 CARLISLE ST, ST.CATHARINES - PHASE 1 | 95 | COMPLETE | BOM not accurate |  |  | Frigotto, Rodrigo | No | Laus, Tomislav | Frank Giancola | 87887.75 | 62898.89 | -24988.86 | -28.43% | 27258.57 | 32016.87 | 4758.3 | 17.46% | 7418.28 | 8499.57 | 1081.29 | 14.58% | 2010.9 | 1698 | -312.9 | -15.56% | 51200 | 20684.45 | -30515.55 | -59.6% | 156.65 | 268.75 | 112.1 | 71.56% | 2021-08-30 01:00
St. Catharines | 2020 | 636440 | 514 QUEENSTON ST - LEAKING TX. REPLACEMENT | 99 | COMPLETE | Vac truck | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 48821.59 | 35723.65 | -13097.94 | -26.83% | 25553.53 | 20397.58 | -5155.95 | -20.18% | 11130.12 | 9800.03 | -1330.09 | -11.95% | 5933.34 | 1659.94 | -4273.4 | -72.02% | 6204.6 | 3866.1 | -2338.5 | -37.69% | 214.87 | 177.5 | -37.37 | -17.39% | 2020-11-19 01:00
St. Catharines | 2021 | 636549 | 179 LOUTH ST, ST.CATHARINES | 95 | COMPLETE | Labour est. over |  |  | Paesano, Andrew | No | Laus, Tomislav | Frank Giancola | 94217.28 | 65723.87 | -28493.41 | -30.24% | 35605.7 | 12883.79 | -22721.91 | -63.82% | 36179.46 | 37084.46 | 905 | 2.501% | 6766.72 | 4226.12 | -2540.6 | -37.55% | 15665.4 | 11529.5 | -4135.9 | -26.4% | 279.23 | 117 | -162.23 | -58.1% | 2021-04-08 01:00
St. Catharines | 2021 | 636624 | ELMA ST - 2021 CABLE REPLACEMENT | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Dan Despres | 932034.5 | 962765.1 | 30730.6 | 3.297% | 172940.4 | 259512.07 | 86571.67 | 50.06% | 74790.6 | 74544.2 | -246.4 | -0.3295% | 31715.39 | 70042.07 | 38326.68 | 120.8% | 652588.11 | 558666.76 | -93921.35 | -14.39% | 760 | 2052.5 | 1292.5 | 170.1% | 2021-11-08 01:00
St. Catharines | 2021 | 636625 | WEIDEN CABLE REPLACEMENT | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Dan Despres | 269116.17 | 307927.71 | 38811.54 | 14.42% | 87400.89 | 100815.66 | 13414.77 | 15.35% | 74776.65 | 83064.91 | 8288.26 | 11.08% | 20071.63 | 37936.55 | 17864.92 | 89.01% | 86867 | 86110.59 | -756.41 | -0.8708% | 644 | 995.5 | 351.5 | 54.58% | 2021-11-16 01:00
St. Catharines | 2022 | 636628 | 76 BUNTING RD, ST. CATHARINES - GUY-WIRE & ANCHOR RELOCATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-01-25 01:00
St. Catharines | 2021 | 636730 | 133 HANNOVER DR, ST.CATHARINES | 99 | CANCELLED | N/A |  |  | Paesano, Andrew | No | Laus, Tomislav | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-04 01:00
St. Catharines | 2022 | 636783 | BULA DRIVE EMERGENCY REPLACEMENTS | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Karan, Andjelo | Brad Carr | 196081.6 | 188357.86 | -7723.74 | -3.939% | 28646.62 | 31132.81 | 2486.19 | 8.679% | 20064.98 | 28815.08 | 8750.1 | 43.61% | 0 | 0 | 0 |  | 147370 | 128409.97 | -18960.03 | -12.87% | 28 | 0 | -28 | -100% | 2022-05-20 01:00
St. Catharines | 2021 | 636842 | 75 NIAGARA ST / SCH / NS00035622 / 3PH PAD | 99 | COMPLETE | Under 10% |  |  | Paesano, Andrew | No | Laus, Tomislav | Frank Giancola | 49643.95 | 52968.1 | 3324.15 | 6.696% | 17053.02 | 21404.68 | 4351.66 | 25.52% | 30291.25 | 27622.42 | -2668.83 | -8.811% | 2299.68 | 3941 | 1641.32 | 71.37% | 0 | 0 | 0 |  | 115.16 | 179 | 63.84 | 55.44% | 2021-09-07 01:00
St. Catharines | 2022 | 636982 | 403 ONTARIO ST, ST.CATHARINES - NIAGARA REGION LINHAVEN LODGE | 95 | COMPLETE | Labour est. under | BOM not accurate | Vac truck | Paesano, Andrew | No | Laus, Tomislav | Frank Giancola | 77627.19 | 218891.86 | 141264.67 | 182% | 25479.63 | 56355.95 | 30876.32 | 121.2% | 72635.84 | 101058.44 | 28422.6 | 39.13% | 4055.68 | 18981 | 14925.32 | 368% | 20156.04 | 26789.35 | 6633.31 | 32.91% | 180.21 | 550 | 369.79 | 205.2% | 2022-12-08 01:00
St. Catharines | 2022 | 637024 | INSULATORS - WEST - ST.CATHARINES | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Weaver, Thomas | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-19 01:00
St. Catharines | 2021 | 637029 | AUTO SW - ITD - ST CATHARINES, 5 | 99 | COMPLETE | Estimate incorrect | BOM not accurate |  | Beaudrie, Scott | No | Billone, Justin | Dan Despres | 322189.92 | 323143.38 | 953.46 | 0.2959% | 70082.55 | 74769.82 | 4687.27 | 6.688% | 236189 | 212894.91 | -23294.09 | -9.862% | 15918.37 | 30135.7 | 14217.33 | 89.31% | 0 | 5342.95 | 5342.95 |  | 781.63 | 836.75 | 55.12 | 7.052% | 2021-11-19 01:00
St. Catharines | 2022 | 637119 | ALECTRA WEST - CAPACITOR BANK | 99 | CANCELLED | N/A |  |  | Beaudrie, Scott | No | Billone, Justin | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-23 01:00
St. Catharines | 2022 | 637154 | POLE RELOCATION - 11 SHELLEY AVE, ST. CATHARINES | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2020-12-21 01:00
St. Catharines | 2022 | 637277 | OVERHEAD POLE LINE RELOCATION - 149 HARTZEL RD | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-03-17 01:00
St. Catharines | 2021 | 637306 | 286 BUNTING - PMH3 REMOVAL | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Dan Despres | 145618.45 | 141710.92 | -3907.53 | -2.683% | 41255.64 | 40178.88 | -1076.76 | -2.61% | 23594.77 | 23388.64 | -206.13 | -0.8736% | 9123 | 10980.45 | 1857.45 | 20.36% | 71645.04 | 67162.95 | -4482.09 | -6.256% | 354.8 | 386 | 31.2 | 8.794% | 2021-04-22
St. Catharines | 2020 | 637347 | JOINT USE PERMIT HW2020-078 - BUNTING AND DIEPPE - ST CATH | 99 | COMPLETE | BOM – truck stock | N/A | N/A | O'Gay, Brian | No | Alectra Utilities | Hewitson, Trevor | 9333.16 | 5323.25 | -4009.91 | -42.96% | 2324.7 | 2069.68 | -255.02 | -10.97% | 2764.55 | 0 | -2764.55 | -100% | 331.61 | 103.57 | -228.04 | -68.77% | 3912.3 | 3150 | -762.3 | -19.48% | 15 | 8 | -7 | -46.67% | 2020-08-27 01:00
St. Catharines | 2020 | 637489 | 250 BUNTING ROAD - TX AND CABLE REPLACEMENT | 99 | COMPLETE | Cont Est Under | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Frank Giancola | 113728.86 | 115940.01 | 2211.15 | 1.944% | 48192.15 | 38305.34 | -9886.81 | -20.52% | 41119.19 | 43899.2 | 2780.01 | 6.761% | 10418.56 | 14793.43 | 4374.87 | 41.99% | 13998.96 | 18942.04 | 4943.08 | 35.31% | 440 | 386 | -54 | -12.27% | 2020-07-27 01:00
St. Catharines | 2021 | 637561 | EXPANSION WORK FOR 75 NIAGARA ST | 98 | COMPLETE | Under 10% |  |  | Jakubowski, Mark | No | Patel, Ketan | Brad Carr | 189969.77 | 194352.5 | 4382.73 | 2.307% | 26538.3 | 47331.71 | 20793.41 | 78.35% | 85 | -89.33 | -174.33 | -205.1% | 2697.26 | 1993 | -704.26 | -26.11% | 160649.21 | 144899.92 | -15749.29 | -9.804% | 16 | 83.5 | 67.5 | 421.9% | 2021-06-21 01:00
St. Catharines | 2020 | 637590 | 80 GRANTHAM TX REPLACEMENT | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 61921.16 | 62887.07 | 965.91 | 1.56% | 20844.02 | 18075.01 | -2769.01 | -13.28% | 22448.07 | 19798.8 | -2649.27 | -11.8% | 4311.51 | 5967.29 | 1655.78 | 38.4% | 14317.56 | 19045.97 | 4728.41 | 33.03% | 173.17 | 171.5 | -1.67 | -0.9644% | 2020-12-07 01:00
St. Catharines | 2020 | 637591 | 16 KEEFER ROAD - TX REPLACEMENT | 99 | COMPLETE | Labour est. over | BOM cost variance | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 69143.08 | 46153.54 | -22989.54 | -33.25% | 25160.1 | 11083.35 | -14076.75 | -55.95% | 21598.52 | 17439.77 | -4158.75 | -19.25% | 4770.47 | 1730.42 | -3040.05 | -63.73% | 17613.99 | 15900 | -1713.99 | -9.731% | 193.19 | 87 | -106.19 | -54.97% | 2020-11-30 01:00
St. Catharines | 2021 | 637596 | 36 MCDONALD- 6 REAR YARD SERVICE RELOCATE | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Rolfe, Eric | Frank Giancola | 90043.73 | 93616.72 | 3572.99 | 3.968% | 28342.84 | 26957.65 | -1385.19 | -4.887% | 14247.49 | 15304.28 | 1056.79 | 7.417% | 5333.4 | 4949 | -384.4 | -7.207% | 42120 | 46405.79 | 4285.79 | 10.18% | 227.8 | 198 | -29.8 | -13.08% | 2021-04-19
St. Catharines | 2020 | 637602 | 44 ROCHELLE DR AND 12 VILLAGE GATE PEDESTAL RELOCATE | 99 | COMPLETE | Vac truck | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 39878.5 | 23910.4 | -15968.1 | -40.04% | 14888.88 | 11911.08 | -2977.8 | -20% | 2949.61 | 4105.99 | 1156.38 | 39.2% | 2778.75 | 4617.33 | 1838.58 | 66.17% | 19261.26 | 3276 | -15985.26 | -82.99% | 120.25 | 123.5 | 3.25 | 2.703% | 2020-10-19 01:00
St. Catharines | 2020 | 637603 | 21 KEEFER ROAD - TX REPLACEMENT | 99 | COMPLETE | Labour est. over | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 73299.21 | 59452.66 | -13846.55 | -18.89% | 25574.68 | 14697.2 | -10877.48 | -42.53% | 21811.87 | 23133.29 | 1321.42 | 6.058% | 4826.47 | 2507.17 | -2319.3 | -48.05% | 21086.19 | 19115 | -1971.19 | -9.348% | 197.19 | 143.5 | -53.69 | -27.23% | 2020-11-30 01:00
St. Catharines | 2020 | 637604 | HUNTINGTON ROAD - CABLE REPLACEMENT P9295-P9297 | 99 | COMPLETE | Under 10% | N/A | N/A | Beaudrie, Scott | No | Alectra Utilities | Dan Despres | 26575.61 | 26490.6 | -85.01 | -0.3199% | 5499.11 | 7489.21 | 1990.1 | 36.19% | 2139.58 | 371.94 | -1767.64 | -82.62% | 420.32 | 1484.45 | 1064.13 | 253.2% | 18516.6 | 17145 | -1371.6 | -7.407% | 37.12 | 60.5 | 23.38 | 62.98% | 2020-12-08 01:00
St. Catharines | 2022 | 637617 | DOWNING ST - CITY OF ST. CATHARINES | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-18 01:00
St. Catharines | 2020 | 637703 | 1250 LAKESHORE RD W / SCH / NS00042061 / 1PH PAD | 99 | COMPLETE | Labour est. over | BOM – truck stock | Cont Est Over | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 57884.1 | 37999.94 | -19884.16 | -34.35% | 21611.43 | 9574.72 | -12036.71 | -55.7% | 12111.73 | 7908.1 | -4203.63 | -34.71% | 4594.58 | 3689.55 | -905.03 | -19.7% | 19566.36 | 16827.57 | -2738.79 | -14% | 178.08 | 82 | -96.08 | -53.95% | 2020-12-04 01:00
St. Catharines | 2020 | 638009 | 70 NIAGARA ST / SCH / UP00055820 / 3PH PAD REPLACEMENT | 99 | COMPLETE | Labour est. over | Vac truck | N/A | Paesano, Andrew | No | Alectra Utilities | Frank Giancola | 48425.95 | 30702.31 | -17723.64 | -36.6% | 12261.6 | 4151.28 | -8110.32 | -66.14% | 26938.87 | 25124.12 | -1814.75 | -6.737% | 2605.08 | 1426.91 | -1178.17 | -45.23% | 6620.4 | 0 | -6620.4 | -100% | 93.99 | 38 | -55.99 | -59.57% | 2020-10-09 01:00
St. Catharines | 2021 | 638102 | 19 COLLIER ST / SCH / UP00055822 / 3PH PAD INSTALL | 95 | COMPLETE | Labour est. over |  |  | Paesano, Andrew | No | Laus, Tomislav | Frank Giancola | 32122 | 31203.19 | -918.81 | -2.86% | 20977.17 | 7243.8 | -13733.37 | -65.47% | 23003.31 | 17237.39 | -5765.92 | -25.07% | 3201.52 | 2072 | -1129.52 | -35.28% | 7290 | 4650 | -2640 | -36.21% | 148.23 | 78 | -70.23 | -47.38% | 2021-04-09 01:00
St. Catharines | 2022 | 638264 | ST CATH AUTO SWITCHES - BRANCH PLANT 830 | 99 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | Billone, Justin | Weaver, Thomas | 0 | 195360.42 | 195360.42 |  | 0 | 31345.65 | 31345.65 |  | 0 | 153882.58 | 153882.58 |  | 0 | 6057.19 | 6057.19 |  | 0 | 4075 | 4075 |  | 0 | 353 | 353 |  | 2022-12-21 01:00
St. Catharines | 2021 | 638420 | TX RENEWAL PROGRAM 2021 - PHASE 4 - 224 GLENRIDGE AVE - 1 | 99 | COMPLETE | Labour est. under | Safety | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Frank Giancola | 42179.03 | 69709.7 | 27530.67 | 65.27% | 12798.55 | 27232.78 | 14434.23 | 112.8% | 19998.43 | 24780.78 | 4782.35 | 23.91% | 2254.05 | 9051.64 | 6797.59 | 301.6% | 7128 | 8644.5 | 1516.5 | 21.28% | 96 | 311 | 215 | 224% | 2021-05-17 01:00
St. Catharines | 2021 | 638518 | 2021 EMERGING UG - CABLE FAULT WILLCHER DR - 3 TX | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Webb-Murre, Paige | Dan Despres | 89853.76 | 98387.1 | 8533.34 | 9.497% | 24442.59 | 32673.72 | 8231.13 | 33.68% | 20505.68 | 17091.71 | -3413.97 | -16.65% | 2731.49 | 9571.67 | 6840.18 | 250.4% | 42174 | 39050 | -3124 | -7.407% | 204 | 306 | 102 | 50% | 2021-08-20 01:00
St. Catharines | 2021 | 638524 | AUTO SWITCH INSTALLS - VANSICKLE TS FEEDER, 4 | 99 | COMPLETE | Scope – Const |  |  | Beaudrie, Scott | Yes | Billone, Justin | Dan Despres | 276812.34 | 342646.34 | 65834 | 23.78% | 81067.02 | 68854.2 | -12212.82 | -15.07% | 177697.32 | 246689.19 | 68991.87 | 38.83% | 18048 | 21747.95 | 3699.95 | 20.5% | 0 | 5355 | 5355 |  | 688 | 745 | 57 | 8.285% | 2021-06-29 01:00
St. Catharines | 2021 | 638550 | TX RENEWAL PROGRAM 2021 - PHASE 8 - SCH NORTH 1 - 6 | 99 | COMPLETE | Covid-19 | Vac truck | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Frank Giancola | 98875.07 | 92063.15 | -6811.92 | -6.889% | 39806.4 | 36365.73 | -3440.67 | -8.644% | 37996.15 | 33671.08 | -4325.07 | -11.38% | 9192.52 | 14886.34 | 5693.82 | 61.94% | 11880 | 7140 | -4740 | -39.9% | 326.44 | 434 | 107.56 | 32.95% | 2021-03-11 01:00
St. Catharines | 2021 | 638551 | TX RENEWAL PROGRAM 2021 - PHASE 9 - SCH NORTH 2 - 9 | 99 | COMPLETE | Labour est. under | Vac truck | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Frank Giancola | 169351.74 | 166592.61 | -2759.13 | -1.629% | 70752.07 | 71328 | 575.93 | 0.814% | 60082.99 | 54643.95 | -5439.04 | -9.053% | 17132.68 | 28964.41 | 11831.73 | 69.06% | 21384 | 11656.25 | -9727.75 | -45.49% | 608 | 927 | 319 | 52.47% | 2021-05-12
St. Catharines | 2022 | 638552 | TX RENEWAL PROGRAM 2021 - PHASE 10 - SCH SOUTH 1 - 7 | 99 | COMPLETE | Vac truck | Labour est. over |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Dan Despres | 143878.94 | 94553.67 | -49325.27 | -34.28% | 59117.11 | 34085.66 | -25031.45 | -42.34% | 46852.47 | 40068.8 | -6783.67 | -14.48% | 14149.36 | 15999.33 | 1849.97 | 13.07% | 23760 | 4399.88 | -19360.12 | -81.48% | 500 | 394 | -106 | -21.2% | 2022-04-11
St. Catharines | 2022 | 638636 | 2021 TX RENEWAL - 75 VENTURA - 5 | 99 | COMPLETE | Commodity Price | Labour est. under |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Frank Giancola | 43747.85 | 63348.02 | 19600.17 | 44.8% | 13475.96 | 19708.89 | 6232.93 | 46.25% | 26775.39 | 35612 | 8836.61 | 33% | 3496.5 | 8027.13 | 4530.63 | 129.6% | 0 | 0 | 0 |  | 96 | 272 | 176 | 183.3% | 2022-05-27 01:00
St. Catharines | 2021 | 638637 | VANSICKLE ROAD - TX REPLACEMENT - 4 | 99 | COMPLETE | Covid-19 |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Dan Despres | 24858.07 | 33916.66 | 9058.59 | 36.44% | 6350.9 | 8677.35 | 2326.45 | 36.63% | 17847.17 | 19153.18 | 1306.01 | 7.318% | 660 | 5726.13 | 5066.13 | 767.6% | 0 | 360 | 360 |  | 60 | 84 | 24 | 40% | 2021-08-13 01:00
St. Catharines | 2021 | 638645 | AUTO SWITCH INSTALLS - GLENDALE TS FEEDERS, 6 | 99 | COMPLETE | Cont Est Over | Labour est. under |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 479841.03 | 444418.39 | -35422.64 | -7.382% | 17762.38 | 42127.22 | 24364.84 | 137.2% | 320808.67 | 342346.41 | 21537.74 | 6.714% | 1284 | 4142.39 | 2858.39 | 222.6% | 139985.98 | 55802.37 | -84183.61 | -60.14% | 126 | 314 | 188 | 149.2% | 2021-09-23 01:00
St. Catharines | 2021 | 638658 | COSTCO ST.CATHARINES - 3 NORTH SERVICE RD | 95 | COMPLETE | BOM not accurate | Covid-19 |  | Kappheim, Adam | No | Oosterlinck, David | Frank Giancola | 167745.65 | 265615.94 | 97870.29 | 58.34% | 45307.31 | 67250.53 | 21943.22 | 48.43% | 87359.09 | 156481.17 | 69122.08 | 79.12% | 7958 | 24997.72 | 17039.72 | 214.1% | 27121.25 | 16886.52 | -10234.73 | -37.74% | 741.3 | 785 | 43.7 | 5.895% | 2021-07-02 01:00
St. Catharines | 2022 | 638667 | 10 NASH ST, ST. CATHARINES - ANCHOR RELOCATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-11-11 01:00
St. Catharines | 2022 | 638770 | POWERVIEW AVE. POLE LINE REPLACEMENT - 13 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Rolfe, Eric | Dan Despres | 163862.56 | 153619.88 | -10242.68 | -6.251% | 85123.18 | 74465.14 | -10658.04 | -12.52% | 40247.49 | 36829.54 | -3417.95 | -8.492% | 24235.89 | 23888 | -347.89 | -1.435% | 14256 | 18437.2 | 4181.2 | 29.33% | 760 | 751 | -9 | -1.184% | 2022-03-18 01:00
St. Catharines | 2022 | 638903 | CABLE INJECT - JACOBSON/CHESTNUT/WOODCREST | 99 | COMPLETE | N/A |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 125255.5 | 209930.21 | 84674.71 | 67.6% | 4440.46 | 30474.6 | 26034.14 | 586.3% | 2015.04 | 3078.99 | 1063.95 | 52.8% | 0 | 627.3 | 627.3 |  | 118800 | 175749.32 | 56949.32 | 47.94% | 0 | 23 | 23 |  | 2022-05-31 01:00
St. Catharines | 2022 | 638930 | 2021 POLE RENEWAL - ROSEMOUNT - 7 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Dan Despres | 106822.37 | 106859.56 | 37.19 | 0.03481% | 50986.27 | 59447.06 | 8460.79 | 16.59% | 24711.62 | 24481.87 | -229.75 | -0.9297% | 14492.48 | 19280 | 4787.52 | 33.03% | 16632 | 3650.63 | -12981.37 | -78.05% | 448 | 724 | 276 | 61.61% | 2022-02-28 01:00
St. Catharines | 2022 | 638951 | CARLTON M10 RELIABILITY CONCERNS | 99 | COMPLETE | Labour est. under | Flagging |  | Beaudrie, Scott | Yes | Karan, Andjelo | Dan Despres | 120730.43 | 144157.61 | 23427.18 | 19.4% | 60519.13 | 79585.33 | 19066.2 | 31.5% | 40495.25 | 39068.18 | -1427.07 | -3.524% | 19716.05 | 21664.1 | 1948.05 | 9.881% | 0 | 3840 | 3840 |  | 586.26 | 806 | 219.74 | 37.48% | 2022-02-14 01:00
St. Catharines | 2021 | 638969 | MAUNAL SWITCH RENEWAL - ST. CATHARINES 2021, 1 | 99 | COMPLETE | BOM not accurate | N/A | N/A | Beaudrie, Scott | Yes | Webb-Murre, Paige | Dan Despres | 21509.35 | 24997.08 | 3487.73 | 16.21% | 10981.94 | 8798.16 | -2183.78 | -19.89% | 3896.4 | 9658.42 | 5762.02 | 147.9% | 2308.2 | 2738 | 429.8 | 18.62% | 4322.81 | 3802.5 | -520.31 | -12.04% | 82.05 | 118 | 35.95 | 43.81% | 2021-04-05 01:00
St. Catharines | 2022 | 639129 | 7 KIRK ST, ST. CATHARINES - POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-06-08 01:00
St. Catharines | 2021 | 639155 | JOINT USE PERMIT HW2020-144 - BUNTING AND LAKESHORE - STC | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 8407.92 | 5894.04 | -2513.88 | -29.9% | 952.98 | 1000.75 | 47.77 | 5.013% | 444.33 | 0 | -444.33 | -100% | 132.41 | 0 | -132.41 | -100% | 6878.2 | 4893.29 | -1984.91 | -28.86% | 3.15 | 0 | -3.15 | -100% | 2021-06-08 01:00
St. Catharines | 2022 | 639348 | 50 HERRICK AVE / SCH / NS00073409 / 3PH PAD INSTALL - Temp | 95 | COMPLETE | Labour est. under | Scope – Eng |  | Frigotto, Rodrigo | No | Laus, Tomislav | Frank Giancola | 85801.62 | 95095.32 | 9293.7 | 10.83% | 21939.41 | 18621.34 | -3318.07 | -15.12% | 44761.23 | 54328.73 | 9567.5 | 21.37% | 3200.98 | 6150 | 2949.02 | 92.13% | 15900 | 15995.25 | 95.25 | 0.5991% | 133.72 | 183 | 49.28 | 36.85% | 2022-11-17 01:00
St. Catharines | 2021 | 639456 | 63 VINE ST / SCH / NS00077208 / 3PH PAD INSTALL | 95 | COMPLETE | Cont Est Over |  |  | Paesano, Andrew | No | Laus, Tomislav | Frank Giancola | 42706.46 | 23769.96 | -18936.5 | -44.34% | 14254.13 | 9425.57 | -4828.56 | -33.87% | 19436.81 | 8140.39 | -11296.42 | -58.12% | 1725.52 | 1704 | -21.52 | -1.247% | 7290 | 4500 | -2790 | -38.27% | 96.23 | 96 | -0.23 | -0.239% | 2021-07-08 01:00
St. Catharines | 2021 | 639718 | JOINT USE PERMIT HW2020-153 - LAKESHORE - ST CATH | 99 | COMPLETE | Cont Est Over |  |  | O'Gay, Brian | No | Johnson, William | Brad Carr | 12494.72 | 9997.03 | -2497.69 | -19.99% | 520.89 | 1182.91 | 662.02 | 127.1% | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 11973.83 | 8814.12 | -3159.71 | -26.39% | 0 | 0 | 0 |  | 2021-06-08 01:00
St. Catharines | 2021 | 639720 | HEYWOOD GS - NEW FEEDER CABLE & POLE | 99 | COMPLETE | Engineering by-passed | N/A | N/A | Beaudrie, Scott | No | Billone, Justin | Frank Giancola | 20398.83 | 81859.06 | 61460.23 | 301.3% | 0 | 39417.9 | 39417.9 |  | 20398.83 | 32255.1 | 11856.27 | 58.12% | 0 | 8723.56 | 8723.56 |  | 0 | 1462.5 | 1462.5 |  | 0 | 563 | 563 |  | 2021-01-12 01:00
St. Catharines | 2022 | 639774 | 23 MICHIGAN AVE - SUBD RES EDS | 98 | COMPLETE | Under 10% |  |  | Velickovski, Goran | No | Morris, Mark | Frank Giancola | 36382.87 | 118602.5 | 82219.63 | 226% | 24609.78 | 23011.88 | -1597.9 | -6.493% | 3511.57 | 5623.47 | 2111.9 | 60.14% | 3861.52 | 7399 | 3537.48 | 91.61% | 4400 | 1731.95 | -2668.05 | -60.64% | 132 | 229 | 97 | 73.48% | 2022-10-28 01:00
St. Catharines | 2022 | 639873 | MILLBANK STREET - SERVICE RELOCATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-08-09 01:00
St. Catharines | 2021 | 640153 | AUTO SWITCH INSTALLS - CARLTON TS FEEDERS, 6 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 393397.26 | 423475.18 | 30077.92 | 7.646% | 14943.16 | 42880.41 | 27937.25 | 187% | 263757.02 | 277999.14 | 14242.12 | 5.4% | 1008 | 3903.19 | 2895.19 | 287.2% | 113689.08 | 98692.44 | -14996.64 | -13.19% | 96 | 244.25 | 148.25 | 154.4% | 2021-11-26 01:00
St. Catharines | 2021 | 640201 | AUTO SWITCH INSTALLS - BUNTING & CARLTON TS FEEDERS, 3 | 99 | COMPLETE | Labour est. under |  |  | Beaudrie, Scott | Yes | Billone, Justin | Frank Giancola | 185288.15 | 251869.1 | 66580.95 | 35.93% | 41948.24 | 75352.58 | 33404.34 | 79.63% | 132842.97 | 139643.69 | 6800.72 | 5.119% | 10496.94 | 36872.83 | 26375.89 | 251.3% | 0 | 0 | 0 |  | 405.06 | 762.75 | 357.69 | 88.31% | 2021-07-23 01:00
St. Catharines | 2021 | 640278 | GRAPEVIEW COMMON - SUBD RES EDS | 99 | COMPLETE | Under 10% | N/A | N/A | Gamboa, Henry | No | Morris, Mark | Frank Giancola | 195879.46 | 185080.52 | -10798.94 | -5.513% | 37585.75 | 34316.6 | -3269.15 | -8.698% | 7973.43 | 10723.92 | 2750.49 | 34.5% | 5841.12 | 7483 | 1641.88 | 28.11% | 144479.16 | 132557 | -11922.16 | -8.252% | 213.57 | 243.5 | 29.93 | 14.01% | 2021-10-01 01:00
St. Catharines | 2022 | 640308 | GENEVA ST & CARLTON ST POLE RELOCATION | 99 | COMPLETE | Cont Est Over | Vac truck |  | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 108528.69 | 85727.48 | -22801.21 | -21.01% | 48508.08 | 49754.9 | 1246.82 | 2.57% | 23446.56 | 17267.51 | -6179.05 | -26.35% | 9234.93 | 10440 | 1205.07 | 13.05% | 27339.12 | 8265.07 | -19074.05 | -69.77% | 295.89 | 291.5 | -4.39 | -1.484% | 2022-03-28
St. Catharines | 2021 | 640513 | YALE CRES - OVERHEAD PRIMARY RELOCATION | 99 | COMPLETE | Labour est. over |  |  | Jakubowski, Mark | No | Patel, Ketan | Dan Despres | 121835.32 | 77226.8 | -44608.52 | -36.61% | 81981.69 | 57973.89 | -24007.8 | -29.28% | 6444.74 | 5886.41 | -558.33 | -8.663% | 19752.89 | 12237 | -7515.89 | -38.05% | 13656 | 1129.5 | -12526.5 | -91.73% | 608.04 | 374 | -234.04 | -38.49% | 2021-11-25 01:00
St. Catharines | 2021 | 640633 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 2, 5 | 99 | COMPLETE | Cont Est Over | BOM – truck stock |  | Beaudrie, Scott | No | Billone, Justin | Brad Carr | 451355.72 | 384075.34 | -67280.38 | -14.91% | 31853.5 | 40234.87 | 8381.37 | 26.31% | 297984.46 | 253967.1 | -44017.36 | -14.77% | 3840 | 2857.7 | -982.3 | -25.58% | 117677.76 | 87015.67 | -30662.09 | -26.06% | 240 | 243.75 | 3.75 | 1.562% | 2021-11-26 01:00
St. Catharines | 2021 | 640634 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 3, 6 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Brad Carr | 495386.95 | 468131.8 | -27255.15 | -5.502% | 39041.22 | 45361.95 | 6320.73 | 16.19% | 281517.93 | 283073.15 | 1555.22 | 0.5524% | 4736 | 4112.29 | -623.71 | -13.17% | 170091.8 | 135584.41 | -34507.39 | -20.29% | 296 | 240.25 | -55.75 | -18.83% | 2021-11-26 01:00
St. Catharines | 2022 | 640729 | 318 ONTARIO ST. PMH REPLACEMENT PH1 | 95 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Rolfe, Eric | Frank Giancola | 186195.6 | 198131.56 | 11935.96 | 6.41% | 58439.65 | 73739.37 | 15299.72 | 26.18% | 31731.08 | 31655.14 | -75.94 | -0.2393% | 3167.91 | 351.85 | -2816.06 | -88.89% | 92856.96 | 92385.2 | -471.76 | -0.5081% | 188.21 | 166.5 | -21.71 | -11.53% | 2022-10-20 01:00
St. Catharines | 2022 | 640813 | 2021 EMERGING UG - RIVERVIEW BLVD REAR LOT CONVERSION | 99 | COMPLETE | Cont Est Over | Material Req incorrectly |  | Beaudrie, Scott | No | Webb-Murre, Paige | Brad Carr | 585116.28 | 666690.01 | 81573.73 | 13.94% | 26701.98 | 103454.14 | 76752.16 | 287.4% | 33816.15 | 53014.2 | 19198.05 | 56.77% | 2951.2 | 0 | -2951.2 | -100% | 521646.95 | 510221.67 | -11425.28 | -2.19% | 60 | 5 | -55 | -91.67% | 2022-07-14 01:00
St. Catharines | 2021 | 640858 | 456 WELLAND AVE - POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-21 01:00
St. Catharines | 2022 | 640859 | 15 NORTHWOOD DR, ST. CATHARINES - BELL POLE RELOCATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2021-09-21 01:00
St. Catharines | 2022 | 640869 | 1387 FOURTH AVE - 600A 347/600V UPGRADE | 95 | COMPLETE | Under 10% |  |  | Kappheim, Adam | No | Oosterlinck, David | Frank Giancola | 77010.64 | 79078.37 | 2067.73 | 2.685% | 29890.83 | 26471.81 | -3419.02 | -11.44% | 29120.46 | 31722.99 | 2602.53 | 8.937% | 5663.35 | 8901 | 3237.65 | 57.17% | 12336 | 11982.57 | -353.43 | -2.865% | 195.53 | 241 | 45.47 | 23.25% | 2022-04-22
St. Catharines | 2022 | 640905 | 2021 POLE RENEWAL MINI REBUILD-BOGART AND MELODY ST. - 12 POLES | 95 | COMPLETE | Labour est. under | Material Req incorrectly |  | Beaudrie, Scott | Yes | Rolfe, Eric | Dan Despres | 202543.39 | 284594.54 | 82051.15 | 40.51% | 95474.48 | 160687.39 | 65212.91 | 68.3% | 59275.36 | 53679.99 | -5595.37 | -9.44% | 25193.55 | 45540.14 | 20346.59 | 80.76% | 22600 | 24687.02 | 2087.02 | 9.235% | 828.86 | 1415 | 586.14 | 70.72% | 2022-11-18 01:00
St. Catharines | 2021 | 640945 | 192 GLENDALE AVE - SUBD RES EDS | 98 | COMPLETE | Labour est. over | Cont Est Under |  | Gamboa, Henry | No | Morris, Mark | Frank Giancola | 40829.95 | 82867.6 | 42037.65 | 103% | 34347.73 | 13488.06 | -20859.67 | -60.73% | 3171.54 | 3685.32 | 513.78 | 16.2% | 2960.68 | 2580 | -380.68 | -12.86% | 350 | 2110.22 | 1760.22 | 502.9% | 140.32 | 123.5 | -16.82 | -11.99% | 2021-11-24 01:00
St. Catharines | 2022 | 641063 | 284 GLENDALE AVE - 400A 347/600V UPGRADE | 95 | COMPLETE | Estimate incorrect | Labour est. over |  | Frigotto, Rodrigo | No | Oosterlinck, David | Frank Giancola | 64208.86 | 39196.05 | -25012.81 | -38.96% | 23898.66 | 13809.86 | -10088.8 | -42.21% | 27932.48 | 22508.62 | -5423.86 | -19.42% | 4567.72 | 2530 | -2037.72 | -44.61% | 7810 | 347.57 | -7462.43 | -95.55% | 142.93 | 95 | -47.93 | -33.53% | 2022-07-28 01:00
St. Catharines | 2021 | 641242 | 196 GLENDALE AVE. - AERIAL TRESPASS RELOCATION | 99 | COMPLETE | Covid-19 |  |  | Beaudrie, Scott | No | Rolfe, Eric | Frank Giancola | 32604.7 | 42405.01 | 9800.31 | 30.06% | 10662.51 | 14842.51 | 4180 | 39.2% | 6110.54 | 5805.65 | -304.89 | -4.99% | 2496.89 | 8402.01 | 5905.12 | 236.5% | 13334.76 | 13354.84 | 20.08 | 0.1506% | 80 | 124 | 44 | 55% | 2021-06-30 01:00
St. Catharines | 2022 | 641252 | 2022 POLE RENEWAL - LINWELL - 6 POLES | 99 | COMPLETE | Labour est. over | Vac truck |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Frank Giancola | 163279.49 | 84885.2 | -78394.29 | -48.01% | 82598.26 | 31965.71 | -50632.55 | -61.3% | 39692.34 | 31394.73 | -8297.61 | -20.9% | 23388.89 | 11952 | -11436.89 | -48.9% | 17600 | 9572.76 | -8027.24 | -45.61% | 729.45 | 400 | -329.45 | -45.16% | 2022-09-07 01:00
St. Catharines | 2021 | 641276 | GLENDALE TS - POLE RELOCATION - CHILD WO FOR 636003 | 99 | COMPLETE | N/A | N/A | N/A | Braletic, Bob | No | Lustrinelli, Mark | Frank Giancola | 0 | 40666.34 | 40666.34 |  | 0 | 31014.61 | 31014.61 |  | 0 | 1337.16 | 1337.16 |  | 0 | 4871 | 4871 |  | 0 | 3443.57 | 3443.57 |  | 0 | 340 | 340 |  | 2021-04-16
St. Catharines | 2022 | 641364 | SHAMROCK COMMON - SUBD RES EDS | 95 | ANALYZE |  |  |  | Velickovski, Goran | No | Morris, Mark | Frank Giancola | 32785.52 | 19771.16 | -13014.36 | -39.7% | 20511.73 | 12374.93 | -8136.8 | -39.67% | 5330.65 | 2914.54 | -2416.11 | -45.32% | 2543.14 | 2876 | 332.86 | 13.09% | 4400 | 49.65 | -4350.35 | -98.87% | 94.96 | 107.75 | 12.79 | 13.47% | 2023-01-26 01:00
St. Catharines | 2022 | 641415 | AUTO SWITCH - SCOTT & HAIG - 1 | 98 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 271100.63 | 312923.18 | 41822.55 | 15.43% | 14044.69 | 45112.44 | 31067.75 | 221.2% | 86865.9 | 99406.29 | 12540.39 | 14.44% | 1280 | 1888.11 | 608.11 | 47.51% | 168910.04 | 166516.34 | -2393.7 | -1.417% | 80 | 98 | 18 | 22.5% | 2022-08-22 01:00
St. Catharines | 2021 | 641569 | AUTO SW - ONTARIO ST (SOUTH OF LINWELL), 1 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Brad Carr | 72099.11 | 75945.66 | 3846.55 | 5.335% | 7422.41 | 11505.09 | 4082.68 | 55% | 43692.06 | 46425.94 | 2733.88 | 6.257% | 672 | 1115.2 | 443.2 | 65.95% | 20312.64 | 16899.43 | -3413.21 | -16.8% | 42 | 60 | 18 | 42.86% | 2021-11-26 01:00
St. Catharines | 2022 | 641688 | 2021 POLE RENEWAL MINI REBUILD - NORTHGLEN AND CUMBERLAND RD- 10 POLES | 95 | COMPLETE | Labour est. under | Vac truck |  | Beaudrie, Scott | Yes | Rolfe, Eric | Dan Despres | 136861.21 | 178091.93 | 41230.72 | 30.13% | 72165.5 | 105176.78 | 33011.28 | 45.74% | 35846.2 | 37893.31 | 2047.11 | 5.711% | 19749.51 | 28231.68 | 8482.17 | 42.95% | 9100 | 6790.16 | -2309.84 | -25.38% | 621.92 | 1082 | 460.08 | 73.98% | 2022-11-16 01:00
St. Catharines | 2022 | 641689 | 2021 POLE RENEWAL MINI REBUILD- DURHAM DR AND WILDWOOD RD - 14 POLES | 99 | COMPLETE | Under 10% | Material Req incorrectly |  | Beaudrie, Scott | Yes | Rolfe, Eric | Dan Despres | 160172.92 | 168007.57 | 7834.65 | 4.891% | 90871.06 | 89425.67 | -1445.39 | -1.591% | 33062.72 | 48781.34 | 15718.62 | 47.54% | 25239.14 | 22219 | -3020.14 | -11.97% | 11000 | 7581.56 | -3418.44 | -31.08% | 792.67 | 1025 | 232.33 | 29.31% | 2022-07-11 01:00
St. Catharines | 2022 | 641698 | 35 TOWERING HEIGHTS BLVD - TRANSFORMER RELOCATION | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | Yes | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2022-07-11 01:00
St. Catharines | 2022 | 641725 | 456 WELLAND AVE - NEW 400A 347/600V SERVICE | 95 | COMPLETE | Labour est. over |  |  | Frigotto, Rodrigo | No | Oosterlinck, David | Frank Giancola | 71663.04 | 62328.89 | -9334.15 | -13.03% | 30738.95 | 20660.32 | -10078.63 | -32.79% | 24880.81 | 27728.57 | 2847.76 | 11.45% | 6093.28 | 6190 | 96.72 | 1.587% | 9950 | 7750 | -2200 | -22.11% | 204.84 | 184 | -20.84 | -10.17% | 2022-01-27 01:00
St. Catharines | 2021 | 641978 | FAIRVIEW PARK - GENEVA STREET, ANCHOR RELOCATION | 99 | COMPLETE | Labour est. over |  |  | Jakubowski, Mark | No | Patel, Ketan | Frank Giancola | 9986.17 | 5962.94 | -4023.23 | -40.29% | 6813.01 | 3830.32 | -2982.69 | -43.78% | 753.79 | 1284.62 | 530.83 | 70.42% | 1319.37 | 848 | -471.37 | -35.73% | 1100 | 0 | -1100 | -100% | 39.98 | 32 | -7.98 | -19.96% | 2021-12-03 01:00
St. Catharines | 2022 | 641998 | 2022 POLE RENEWAL - BATCH 1 (8- WP) | 99 | COMPLETE | Estimate incorrect | Vac truck |  | Beaudrie, Scott | Yes | Rolfe, Eric | Frank Giancola | 69180.44 | 78333.87 | 9153.43 | 13.23% | 29188.64 | 45231.28 | 16042.64 | 54.96% | 17239.43 | 16884.59 | -354.84 | -2.058% | 7352.37 | 11654 | 4301.63 | 58.51% | 15400 | 4564 | -10836 | -70.36% | 230.51 | 371 | 140.49 | 60.95% | 2022-04-04
St. Catharines | 2022 | 642009 | PROMENADE BLVD OH LINE REPLACE (ST. CATHARINES) | 99 | COMPLETE | Labour est. over | Vac truck |  | Beaudrie, Scott | No | Karan, Andjelo | Dan Despres | 46916.11 | 28611.31 | -18304.8 | -39.02% | 24054.85 | 12808.78 | -11246.07 | -46.75% | 14198.54 | 11138.53 | -3060.01 | -21.55% | 6462.72 | 4664 | -1798.72 | -27.83% | 2200 | 0 | -2200 | -100% | 195.84 | 114 | -81.84 | -41.79% | 2022-06-28 01:00
St. Catharines | 2022 | 642174 | WILD LIFE MITIGATION (ST. CATHARINES) | 99 | COMPLETE | Estimate incorrect | Scope – Const |  | Beaudrie, Scott | No | Karan, Andjelo | Dan Despres | 83457.76 | 109250.48 | 25792.72 | 30.91% | 57059.15 | 47413.11 | -9646.04 | -16.91% | 9960.99 | 27788.82 | 17827.83 | 179% | 16437.62 | 16880 | 442.38 | 2.691% | 0 | 17168.55 | 17168.55 |  | 508.38 | 542.5 | 34.12 | 6.712% | 2022-07-28 01:00
St. Catharines | 2022 | 642302 | 2022 - TX RENEWAL - SCH BATCH 1 - 4TX'S | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Webb-Murre, Paige | Frank Giancola | 103445.31 | 69102.24 | -34343.07 | -33.2% | 56242.2 | 24736.85 | -31505.35 | -56.02% | 22675.34 | 25550.49 | 2875.15 | 12.68% | 15727.77 | 10375.15 | -5352.62 | -34.03% | 8800 | 8439.75 | -360.25 | -4.094% | 484.34 | 240 | -244.34 | -50.45% | 2022-09-23 01:00
St. Catharines | 2021 | 642444 | EMERGING 2021 - INSULATOR CHANGES. CHURCH ST. | 99 | COMPLETE | Labour est. under |  |  | Beaudrie, Scott | No | Rolfe, Eric | Brad Carr | 42557.6 | 50612.95 | 8055.35 | 18.93% | 6929.44 | 12665.63 | 5736.19 | 82.78% | 13232.46 | 15132.92 | 1900.46 | 14.36% | 0 | 418.2 | 418.2 |  | 22395.7 | 22396.2 | 0.5 | 0.002233% | 14 | 28 | 14 | 100% | 2021-12-10 01:00
St. Catharines | 2022 | 642494 | BELL BONDS - Y32921 & C00322 - ST CATH | 95 | ANALYZE |  |  |  | O'Gay, Brian | No | Johnson, William | K-Line Construction | 3223.17 | 867.8 | -2355.37 | -73.08% | 2840.85 | 867.8 | -1973.05 | -69.45% | 0 | 0 | 0 |  | 382.32 | 0 | -382.32 | -100% | 0 | 0 | 0 |  | 12 | 0 | -12 | -100% | 2022-05-13 01:00
St. Catharines | 2022 | 642512 | OH AUTO SWITCHES (DA) 2022 - PART 4 - 4 | 99 | COMPLETE | Under 10% | Estimate incorrect |  | Beaudrie, Scott | Yes | Billone, Justin | Dan Despres | 283407.15 | 268438.05 | -14969.1 | -5.282% | 88225.07 | 61567.94 | -26657.13 | -30.21% | 173222.08 | 189245.73 | 16023.65 | 9.25% | 21960 | 16661 | -5299 | -24.13% | 0 | 963.38 | 963.38 |  | 760 | 729.5 | -30.5 | -4.013% | 2022-06-28 01:00
St. Catharines | 2022 | 642513 | OH AUTO SWITCHES (DA) 2022 - PART 5 - 7 | 99 | COMPLETE | BOM not accurate |  |  | Beaudrie, Scott | Yes | Billone, Justin | Dan Despres | 428082.12 | 643328.11 | 215245.99 | 50.28% | 155572.61 | 119775.74 | -35796.87 | -23.01% | 226956.67 | 479301.73 | 252345.06 | 111.2% | 40552.84 | 36285.39 | -4267.45 | -10.52% | 5000 | 7965.25 | 2965.25 | 59.3% | 1207.18 | 1191.25 | -15.93 | -1.32% | 2022-12-16 01:00
St. Catharines | 2022 | 642520 | UG AUTO SWITCHES (DA) 2022 - CARLISLE - 1 | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Billone, Justin | Dan Despres | 147566.89 | 152676.77 | 5109.88 | 3.463% | 18318.08 | 17304.76 | -1013.32 | -5.532% | 125944.89 | 134624.32 | 8679.43 | 6.891% | 3303.92 | 747.69 | -2556.23 | -77.37% | 0 | 0 | 0 |  | 111.08 | 119.5 | 8.42 | 7.58% | 2022-07-10 01:00
St. Catharines | 2022 | 642525 | 2021 - OH EMERGING - 2 WYCHWOOD ROAD | 99 | COMPLETE | Labour est. under | Estimate incorrect |  | Beaudrie, Scott | No | Webb-Murre, Paige | Dan Despres | 88049.63 | 78629.63 | -9420 | -10.7% | 32413.73 | 25217.37 | -7196.36 | -22.2% | 9555.81 | 9812.22 | 256.41 | 2.683% | 7588.09 | 7377.25 | -210.84 | -2.779% | 38492 | 36222.79 | -2269.21 | -5.895% | 245.02 | 206.5 | -38.52 | -15.72% | 2022-02-16 01:00
St. Catharines | 2022 | 642568 | 2022 EMERGING UG - RIVERVIEW REAR LOT CONVERSION | 99 | COMPLETE | Under 10% | Material Req incorrectly |  | Beaudrie, Scott | No | Webb-Murre, Paige | Brad Carr | 926197.58 | 906053.34 | -20144.24 | -2.175% | 78815.39 | 98649.51 | 19834.12 | 25.17% | 52384.92 | 0 | -52384.92 | -100% | 1533.16 | 0 | -1533.16 | -100% | 793464.11 | 807403.83 | 13939.72 | 1.757% | 148.46 | 8 | -140.46 | -94.61% | 2022-07-14 01:00
St. Catharines | 2022 | 643155 | 300B FOURTH AVE / SCH / NS00102866 / 1000KVA 3PH COMMERCIAL SERVICE | 95 | ANALYZE |  |  |  | Frigotto, Rodrigo | No | Laus, Tomislav | Frank Giancola | 64788.95 | 49160.97 | -15627.98 | -24.12% | 9012.63 | 9795.2 | 782.57 | 8.683% | 55156.92 | 36141.77 | -19015.15 | -34.47% | 619.4 | 3224 | 2604.6 | 420.5% | 0 | 0 | 0 |  | 48.9 | 83 | 34.1 | 69.73% | 2022-12-02 01:00
St. Catharines | 2022 | 643174 | OVERSIZE LOAD MOVE - ST. CATHARINES HOSPITAL | 99 | CANCELLED | N/A |  |  | Jakubowski, Mark | No | Patel, Ketan | Calvin Arsenault | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2023-01-13 01:00
St. Catharines | 2022 | 643176 | NV25 & NV35 - NEW MH ROOF | 95 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Brad Carr | 291089.79 | 293903.29 | 2813.5 | 0.9665% | 50052.21 | 46908 | -3144.21 | -6.282% | 6879.32 | 7042.55 | 163.23 | 2.373% | 1368 | 1380.84 | 12.84 | 0.9386% | 232790.26 | 238571.9 | 5781.64 | 2.484% | 72 | 48 | -24 | -33.33% | 2023-01-13 01:00
St. Catharines | 2022 | 643240 | 119 CUSHMAN RD | 95 | COMPLETE | BOM not accurate | Labour est. over | Metering under | Frigotto, Rodrigo | No | Bennett, Aaron | Frank Giancola | 89753.49 | 85310.31 | -4443.18 | -4.95% | 38939.22 | 27403.94 | -11535.28 | -29.62% | 28451.48 | 37073.24 | 8621.76 | 30.3% | 9641.79 | 8600 | -1041.79 | -10.8% | 12721 | 12233.13 | -487.87 | -3.835% | 313.16 | 277 | -36.16 | -11.55% | 2022-05-17 01:00
St. Catharines | 2022 | 643308 | FIFTY RD & SONOMA LANE - POLE CONFLICT - SUBD CAP PROJ | 95 | COMPLETE | Vehicle Under Estimated |  |  | Gamboa, Henry | No | Morris, Mark | Macdougall, Stephen | 12125.76 | 14773.1 | 2647.34 | 21.83% | 6878.16 | 7824.42 | 946.26 | 13.76% | 1621.07 | 2252.41 | 631.34 | 38.95% | 821.53 | 2704 | 1882.47 | 229.1% | 2805 | 1992.27 | -812.73 | -28.97% | 25.12 | 68 | 42.88 | 170.7% | 2022-01-13 01:00
St. Catharines | 2022 | 643385 | NV 21 - NEW ROOF + OTHER NV LIDS & ASSOCIATED WORK - 2 | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 207835.91 | 239115.56 | 31279.65 | 15.05% | 42215.62 | 31920.68 | -10294.94 | -24.39% | 3476 | 6879.32 | 3403.32 | 97.91% | 1728 | 832 | -896 | -51.85% | 160416.29 | 177668.56 | 17252.27 | 10.75% | 108 | 32 | -76 | -70.37% | 2022-04-21
St. Catharines | 2022 | 643650 | 2022 - BULA DRIVE URD | 95 | COMPLETE | Under 10% | BOM cost variance |  | Beaudrie, Scott | No | Karan, Andjelo | Brad Carr | 569953.91 | 625463.59 | 55509.68 | 9.739% | 63828.41 | 81519.55 | 17691.14 | 27.72% | 51060.05 | 70224.45 | 19164.4 | 37.53% | 0 | 0 | 0 |  | 455065.45 | 473719.59 | 18654.14 | 4.099% | 67 | 8 | -59 | -88.06% | 2022-12-01 01:00
St. Catharines | 2022 | 644020 | 281 MARTINGDALE RD | 95 | COMPLETE | Labour est. over | Est. Ext. - Act. Internal |  | Frigotto, Rodrigo | No | Bennett, Aaron | Frank Giancola | 62793.45 | 42089.84 | -20703.61 | -32.97% | 25744.1 | 17312.06 | -8432.04 | -32.75% | 18891.02 | 22256.74 | 3365.72 | 17.82% | 4676.33 | 273 | -4403.33 | -94.16% | 13482 | 2248.04 | -11233.96 | -83.33% | 202.33 | 106.5 | -95.83 | -47.36% | 2022-12-05 01:00
St. Catharines | 2022 | 644050 | 2022 POLE RENEWAL MINI REBUILD-AQUADALE DR. | 95 | COMPLETE | Labour est. under | Vac truck |  | Beaudrie, Scott | No | Rolfe, Eric | Dan Despres | 160832.59 | 210527.49 | 49694.9 | 30.9% | 73852.02 | 124342.85 | 50490.83 | 68.37% | 48886.24 | 47806.83 | -1079.41 | -2.208% | 21586.33 | 13372.67 | -8213.66 | -38.05% | 16508 | 25005.14 | 8497.14 | 51.47% | 577.3 | 1113.5 | 536.2 | 92.88% | 2022-12-01 01:00
St. Catharines | 2022 | 644340 | 2022- SWITCH GEAR REMOVAL- SC1044 | 95 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | Yes | Billone, Justin | Brad Carr | 224344.48 | 210597.16 | -13747.32 | -6.128% | 34437.99 | 32826.58 | -1611.41 | -4.679% | 43280.49 | 45400.17 | 2119.68 | 4.898% | 608 | 747.69 | 139.69 | 22.98% | 146018 | 131622.72 | -14395.28 | -9.859% | 32 | 33.5 | 1.5 | 4.688% | 2022-12-01 01:00
St. Catharines | 2022 | 645697 | 390 ONTARIO ST | 95 | COMPLETE | Labour est. over | Metering over | Estimate incorrect | Mandic, Goran | No | Bennett, Aaron | Frank Giancola | 73171.29 | 58839.15 | -14332.14 | -19.59% | 30777.83 | 14056.19 | -16721.64 | -54.33% | 23776.56 | 25186.71 | 1410.15 | 5.931% | 6105.9 | 3420 | -2685.9 | -43.99% | 12511 | 16176.25 | 3665.25 | 29.3% | 190.07 | 98 | -92.07 | -48.44% | 2022-10-31 01:00
St. Catharines | 2022 | 647313 | 2022 EMERGING- 19 NORTHWOOD DRIVE | 99 | COMPLETE | Under 10% |  |  | Beaudrie, Scott | No | Billone, Justin | Frank Giancola | 12791.72 | 13180.74 | 389.02 | 3.041% | 6269.03 | 5902.94 | -366.09 | -5.84% | 5290.74 | 5274.95 | -15.79 | -0.2984% | 1231.95 | 2002.85 | 770.9 | 62.58% | 0 | 0 | 0 |  | 32 | 40 | 8 | 25% | 2022-11-18 01:00
St. Catharines | 2022 | 647557 | 15 GALE CRES POLE RELOCATION - ST. CATHARINES | 99 | COMPLETE | Labour est. over |  |  | Beaudrie, Scott | No | Karan, Andjelo | Dan Despres | 15062.61 | 7577.7 | -7484.91 | -49.69% | 8589.33 | 3703.48 | -4885.85 | -56.88% | 1699.02 | 1396.97 | -302.05 | -17.78% | 2574.26 | 0 | -2574.26 | -100% | 2200 | 2477.25 | 277.25 | 12.6% | 66.86 | 48 | -18.86 | -28.21% | 2022-09-14 01:00
St. Catharines | 2022 | 647711 | CUSTOMER INTITIATED POLE HEIGHT INCREASE - LAKESHORE RD - ST. CATHARINES | 99 | COMPLETE | Labour est. over | Vac truck | Flagging | Jakubowski, Mark | No | Celic, Dusan | Frank Giancola | 48357.56 | 13743.03 | -34614.53 | -71.58% | 27696.12 | 4300.8 | -23395.32 | -84.47% | 6972.04 | 5846.66 | -1125.38 | -16.14% | 6188.4 | 3248 | -2940.4 | -47.51% | 7501 | 347.57 | -7153.43 | -95.37% | 162 | 0 | -162 | -100% | 2022-09-06 01:00
[18 empty] | 158363.53 | 92504.309
[18 empty] | 158363.53 | 146742.46 |  | 53251.11
[18 empty] | 316727.06 | 239246.769 |  | 15052.58
68303.69

## RFC Report - Feb 7
Project ID | Project Name | CITY | Department | RFC Status | RFC Amount | Original Budget | Current Budget | Current Actual Cost | Responsible | RFC # | Reason | Create Date | Last Updated Date | Alectra Status
451132 | Residual Poles - East Downtown 2016 | Hamilton | PLNC | Approved | 43.12 | 51665.84 | 60999.92 | 99090.27 | 09-03-2017 | 999 | Burdens | 2017-03-09 | 2019-09-30 20:05 | 99
451132 | Residual Poles - East Downtown 2016 | Hamilton | PLNC | Approved | 9290.96 | 51665.84 | 60999.92 | 99090.27 | 17-07-2017 | 001 | new poles | 2017-07-17 01:00 | 2019-09-30 20:05 | 99
451135 | Waste Water Treatment Plant | Hamilton | CSCP | Not Approved | 58932.15 | 504058.03 | 500103.92 | 936804.26 | 08-06-2022 | 002 | Labour Overages | 2022-04-12 09:00 | 2022-06-08 13:31 | 98
451135 | Waste Water Treatment Plant | Hamilton | CSCP | Approved | -3954.11 | 504058.03 | 500103.92 | 936804.26 | 25-04-2019 | 001 | Efficiencies | 2019-04-10 01:00 | 2019-07-03 00:49 | 98
451115 | 2021 TX RENEWAL - KICKER TX OH - 1 | Hamilton | PLNC | Approved | -30038.5 | 73093.95 | 43055.45 | 44792.59 | 16-11-2021 | 001 | Reduction RFC | 2021-08-24 12:03 | 2021-11-16 20:25 | 99
451283 | Thomas Switching Station | St. Catharines | PLNC | Approved | 27709.35 | 291574.7 | 439692.41 | 566476.37 | 10-02-2021 | 101 | Delays and Unforseen Scope | 2019-06-13 01:00 | 2021-02-10 19:56 | 99
451283 | Thomas Switching Station | St. Catharines | PLNC | Approved | 614.11 | 291574.7 | 439692.41 | 566476.37 | 27-09-2019 | 102 | OC Hours | 2019-07-03 01:00 | 2019-11-07 21:28 | 99
451283 | Thomas Switching Station | St. Catharines | PLNC | Approved | 126856.78 | 291574.7 | 439692.41 | 566476.37 | 21-06-2021 | 003 | Labour Overages | 2021-06-21 09:18 | 2021-09-28 15:50 | 99
451283 | Thomas Switching Station | St. Catharines | PLNC | Approved |  | 291574.7 | 439692.41 | 566476.37 | 04-05-2021 | 103 |  | 2021-04-28 09:28 | 2021-09-28 15:50 | 99
451283 | Thomas Switching Station | St. Catharines | PLNC | Approved | -7062.53 | 291574.7 | 439692.41 | 566476.37 | 02-04-2019 | 001 | Efficiencies | 2019-03-18 01:00 | 2019-07-03 00:50 | 99
451279 | 281/283 St Paul St | St. Catharines | ICIL | Approved | 1591.08 | 41287.71 | 50238.2 | 49397.06 | 26-07-2017 | 001 | Add OC hours due to more admin | 2017-07-25 01:00 | 2019-07-03 00:50 | 99
451279 | 281/283 St Paul St | St. Catharines | ICIL | Approved | 5825.2 | 41287.71 | 50238.2 | 49397.06 | 02-08-2017 | 002 | Duct to be concrete in case | 2017-08-02 01:00 | 2019-07-03 00:50 | 99
451279 | 281/283 St Paul St | St. Catharines | ICIL | Approved | 881.28 | 41287.71 | 50238.2 | 49397.06 | 02-10-2017 | 003 | OC extra | 2017-10-02 01:00 | 2019-07-03 00:50 | 99
451279 | 281/283 St Paul St | St. Catharines | ICIL | Approved | 652.93 | 41287.71 | 50238.2 | 49397.06 | 30-01-2018 | 004 | OC Hours, Tech Hours - Customer delays | 2018-01-30 | 2019-07-03 00:50 | 99
451294 | ROAD AUTHORITY - MOUNTAINBROW RD AND WATERDOWN RD WIDENING | Hamilton | CSCP | Approved | -4447.06 | 291048.1 | 307077.65 | 301192.79 | 15-11-2021 | 002 | Anchor Removal | 2021-11-15 09:21 | 2021-11-15 14:34 | 99
451294 | ROAD AUTHORITY - MOUNTAINBROW RD AND WATERDOWN RD WIDENING | Hamilton | CSCP | Approved | 8791.48 | 291048.1 | 307077.65 | 301192.79 | 12-04-2022 | 004 | Sleeve out temp switches | 2022-04-05 13:31 | 2022-04-20 11:51 | 99
451294 | ROAD AUTHORITY - MOUNTAINBROW RD AND WATERDOWN RD WIDENING | Hamilton | CSCP | Approved | 5922.69 | 291048.1 | 307077.65 | 301192.79 | 02-02-2022 | 003 | Rock | 2022-01-20 12:00 | 2022-02-02 20:41 | 99
451294 | ROAD AUTHORITY - MOUNTAINBROW RD AND WATERDOWN RD WIDENING | Hamilton | CSCP | Approved | 5762.44 | 291048.1 | 307077.65 | 301192.79 | 05-11-2021 | 001 | Scope Change | 2021-11-02 11:34 | 2021-10-05 18:51 | 99
450226 | DENISION AVE & HAGGERT AVE | Brampton | SUBD | Not Approved | 0 | 87247.39 | 87247.39 | 88096.71 | Pending with OC | 001 | Extra Inspection hours | 2021-01-05 15:52 | 2021-06-22 19:39 | 99
451600 | Mountain URD - Phase 2 - (South) | Hamilton | PLNC | Approved | -18912.25 | 532011.16 | 516979.71 | 671204.05 | 16-11-2020 | 001 | Efficiencies | 2019-12-23 01:00 | 2020-11-24 15:56 | 99
451600 | Mountain URD - Phase 2 - (South) | Hamilton | PLNC | Approved | 0 | 532011.16 | 516979.71 | 671204.05 | 06-09-2019 | 101 | Drawing Revision | 2019-09-06 01:00 | 2019-09-09 21:52 | 99
451600 | Mountain URD - Phase 2 - (South) | Hamilton | PLNC | Approved | 3880.8 | 532011.16 | 516979.71 | 671204.05 | 11-19-2020 | 102 | Labour Overages | 2020-10-08 11:48 | 2020-11-20 13:34 | 99
451392 | Celtic Dr. - 8kV Conversion | Hamilton | PLNC | Approved | 105064.44 | 1412581.59 | 1550275.51 | 1573258.45 | 28-05-2021 | 002 | Productivity Loss, Civil Overruns | 2021-04-23 08:41 | 2021-09-15 20:59 | 99
451392 | Celtic Dr. - 8kV Conversion | Hamilton | PLNC | Approved | 32629.48 | 1412581.59 | 1550275.51 | 1573258.45 | 28-01-2021 | 001 | Digging Conditions | 2020-12-11 09:14 | 2021-01-29 02:26 | 99
451264 | Lakeshore Rd Road Widening | St. Catharines | CSCP | Approved | 18403.7 | 1518711.84 | 1540630.54 | 1431927.87 | 24-08-2021 | 003 | Repair Damaged Drain Pipe | 2021-08-09 14:41 | 2021-09-28 15:48 | 99
451264 | Lakeshore Rd Road Widening | St. Catharines | CSCP | Approved | 3515 | 1518711.84 | 1540630.54 | 1431927.87 | 03-02-2022 | 001 | Re-route duct | 2022-01-26 11:00 | 2022-02-03 17:04 | 99
451469 | Elgin TS Rebuild Phase 2 | Hamilton | STND | Approved | 0 | 1327490.81 | 1327490.81 | 1548300.4 | 05-05-2021 | 001 | Labour Overages | 2021-04-28 09:47 | 2021-09-21 21:06 | 99
409957 | OTC (INITIAL) - M-CITY PHASE 1 (EXPANSION COSTS) | Mississauga | CSCP | Approved | 465337.07 | 3400436.62 | 3865773.69 | 3607334.68 | 22-10-2021 | 101 | Premium costs to work outside of regular hours | 2021-09-22 10:43 | 2021-11-02 00:32 | 98
450756 | MAYFIELD RD CHING.TO HURONTAR0 | Brampton | CSCP | Approved | 0 | 2704310.56 | 2704310.56 | 2073237.45 | 20-09-2022 | 101 | Related to coordination efforts with HONI for pole installations/conductor transfers and isolation of SNEL F5 Feeder. | 2022-09-14 15:45 | 2022-09-20 19:50 | 84
451647 | Celtic Dr - 8 kV Conv. - Phase 2 | Hamilton | PLNC | Approved | 33864.2 | 1461920.31 | 1632511.31 | 1831021.15 | 16-11-2020 | 001 | Scope Change | 2020-10-30 12:46 | 2021-03-19 15:31 | 99
451647 | Celtic Dr - 8 kV Conv. - Phase 2 | Hamilton | PLNC | Approved | 46871.41 | 1461920.31 | 1632511.31 | 1831021.15 | 30-06-2021 | 002 | Scope Change | 2020-11-20 09:48 | 2021-09-28 15:43 | 99
451647 | Celtic Dr - 8 kV Conv. - Phase 2 | Hamilton | PLNC | Approved | 66125.39 | 1461920.31 | 1632511.31 | 1831021.15 | 30-06-2021 | 003 | Scope Changes | 2020-12-02 17:16 | 2021-09-28 15:43 | 99
451647 | Celtic Dr - 8 kV Conv. - Phase 2 | Hamilton | PLNC | Approved | 23730 | 1461920.31 | 1632511.31 | 1831021.15 | 30-06-2021 | 004 | Loss of Production | 2021-03-19 01:00 | 2021-09-28 15:43 | 99
392403 | EXPANSION - OXFORD - BLOCK 8 - PH1 | Mississauga | CSCP | Approved | 114102.34 | 1335969.25 | 1529869.24 | 747652.3 | 07-11-2022 | 102 | RFC required for removal of shale in trench along Square One Dr and at the corner of Confederation and Square One Dr. | 2022-08-03 10:16 | 2022-11-07 21:06 | 84
392403 | EXPANSION - OXFORD - BLOCK 8 - PH1 | Mississauga | CSCP | Approved | 79797.65 | 1335969.25 | 1529869.24 | 747652.3 | 07-11-2022 | 101 | RFC required for pricing change of cable and manhole (2021 pricing to 2022 pricing): | 2022-08-03 10:17 | 2022-11-07 21:06 | 84
396017 | M-CITY POLELINE RELOCATION - QUARTZ ROAD | Mississauga | CSCP | Approved | 40367.96 | 135751.65 | 176119.61 | 109639.53 | 14-02-2022 | 101 | Delays, design and scope changes | 2022-01-20 12:59 | 2022-02-18 14:58 | 99
451759 | 32 Towering Heights Blvd - pads | St. Catharines | ICIL | Approved | 1145.04 | 97288.75 | 98433.79 | 99735.87 | 29-10-2020 | 001 | Design Hours | 2020-10-29 11:32 | 2020-10-29 15:47 | 92
451643 | Mountain URD - Phase 2 - (North) | Hamilton | PLNC | Approved | 59847.3 | 963851.09 | 1087289.31 | 1479882.47 | 23-09-2021 | 001 | Design Changes | 2019-11-01 01:00 | 2021-09-23 17:03 | 99
451643 | Mountain URD - Phase 2 - (North) | Hamilton | PLNC | Approved | 9430.35 | 963851.09 | 1087289.31 | 1479882.47 | 24-03-2021 | 002 | Scope Change regarding Duct | 2021-01-28 12:18 | 2021-04-13 12:42 | 99
451643 | Mountain URD - Phase 2 - (North) | Hamilton | PLNC | Approved | 40179.32 | 963851.09 | 1087289.31 | 1479882.47 | 16-11-2021 | 003 | Labour Overages | 2021-04-13 12:00 | 2021-11-16 20:43 | 99
451643 | Mountain URD - Phase 2 - (North) | Hamilton | PLNC | Approved | 13981.25 | 963851.09 | 1087289.31 | 1479882.47 | 16-11-2021 | 004 | Scope Change foundation and duct | 2021-07-19 10:38 | 2021-11-16 17:43 | 99
451643 | Mountain URD - Phase 2 - (North) | Hamilton | PLNC | Approved | 0 | 963851.09 | 1087289.31 | 1479882.47 | 01-11-2019 | 101 | Drawing Revision | 2019-11-01 01:00 | 2019-11-01 21:47 | 99
451628 | 1212 MAIN ST - MAPLE AVE UPGRADE | Hamilton | CSCP | Approved | 23822.81 | 971160.47 | 999618.35 | 834947.45 | 25-11-2020 | 002 | Crane | 2020-06-09 13:06 | 2020-11-25 20:08 | 99
451628 | 1212 MAIN ST - MAPLE AVE UPGRADE | Hamilton | CSCP | Approved | 4635.07 | 971160.47 | 999618.35 | 834947.45 | 25-11-2020 | 001 | Scope Change | 2020-04-30 13:14 | 2020-11-25 20:08 | 99
451758 | 32 Towering Heights Blvd - temp | St. Catharines | ICIL | Approved | -7761.61 | 72441.83 | 64680.22 | 64656.16 | 24-04-2019 | 001 | Engineering Revision | 2019-04-24 01:00 | 2019-07-03 00:54 | 98
636863 | 636863 - 700 MAPLEVIEW DRIVE - BLOCK 8/INSPECT AND CONNECT | Barrie | SUBD | Approved | 0 | 265373.3 | 265373.3 | 260860.73 | 09-09-2021 | 001 | Tx relocation and additional house meters added on developer's side | 2021-09-09 14:26 | 2021-09-27 20:09 | 98
636863 | 636863 - 700 MAPLEVIEW DRIVE - BLOCK 8/INSPECT AND CONNECT | Barrie | SUBD | Approved | 0 | 265373.3 | 265373.3 | 260860.73 | 02-09-2022 | 003 | Primary cable routing changed to match existing duct structure configuration | 2022-09-02 11:37 | 2022-09-02 16:04 | 98
451615 | Hamilton 2018 Pole Residuals - 3 | Hamilton | PLNC | Approved | 10822.59 | 88861.67 | 103102.77 | 96089.26 | 19-07-2019 | 001 | Additional location at Bonadventure | 2019-07-19 01:00 | 2021-02-10 03:46 | 99
451615 | Hamilton 2018 Pole Residuals - 3 | Hamilton | PLNC | Approved | 3418.51 | 88861.67 | 103102.77 | 96089.26 | 02-10-2019 | 002 | External costs at Bonadventure | 2019-10-02 01:00 | 2021-02-10 03:46 | 99
451938 | ELLIS AVE 3PH EXPANSION | St. Catharines | CSCP | Approved | 5657.77 | 267160.44 | 287379.01 | 263691.62 | 11-05-2021 | 002 | Landscaping Overruns | 2021-04-16 11:25 | 2021-09-27 15:47 | 99
451938 | ELLIS AVE 3PH EXPANSION | St. Catharines | CSCP | Approved | 14560.8 | 267160.44 | 287379.01 | 263691.62 | 17-03-2021 | 001 | Snow Removal, Frost | 2021-03-10 14:54 | 2021-03-17 15:38 | 99
451573 | WALNUT/JACKSON FEEDER EXPANSION | Hamilton | CSCP | Approved | 18108.25 | 657393.61 | 659790.45 | 690508.9 | 16-04-2021 | 001 | Scope Change | 2021-04-12 12:56 | 2021-09-27 18:20 | 98
451573 | WALNUT/JACKSON FEEDER EXPANSION | Hamilton | CSCP | Approved | -15711.41 | 657393.61 | 659790.45 | 690508.9 | 22-07-2021 | 002 | Efficiencies | 2021-07-14 09:29 | 2021-09-27 18:21 | 98
414107 | Port Credit Village West New Feeder | Mississauga | PLNC | Approved | -41137.97 | 1683966.5 | 1743957.05 | 1367230.79 | 06-10-2020 | 003 | Adjusted OH scope of work based on new estimates | 2020-08-10 08:01 | 2021-03-17 15:41 | 99
414107 | Port Credit Village West New Feeder | Mississauga | PLNC | Approved | 113548.53 | 1683966.5 | 1743957.05 | 1367230.79 | 04-01-2021 | 002 | Exploratory work, extension of Queen St drilling, connection pits | 2020-07-09 01:00 | 2021-01-04 20:36 | 99
414107 | Port Credit Village West New Feeder | Mississauga | PLNC | Approved | -12420.01 | 1683966.5 | 1743957.05 | 1367230.79 | 11-03-2020 | 001 | Revised drawings and pricing from Transpower | 2020-03-11 01:00 | 2020-09-22 19:28 | 99
451927 | Skinner Rd - pad re-location | Hamilton | CSCP | Not Approved | -49502.49 | 118712.87 | 118712.87 | 62747.8 | Pending With Construction | 001 | The RFC was not received by closure. | 2021-05-06 10:47 | 2021-10-15 17:21 | 99
451539 | 52 Ottawa St N, Hamilton - Temp | Hamilton | ICIL | Approved | 38547.73 | 80400.97 | 118948.7 | 113919.95 | 26-04-2021 | 001 | Hours Adjustment | 2021-04-19 09:10 | 2021-09-27 15:32 | 92
334035 | 2016 OTC (INITIAL) - ELM DRIVE CONDOMINIUMS (EHM COSTS) | Mississauga | CSCP | Approved | 114300.05 | 1635113.84 | 1749413.89 | 1690401.45 | 10-06-2022 | 101 | The extra cost associated with frost due to working in the winter months | 2022-05-06 11:15 | 2022-06-14 15:26 | 84
453114 | 453114 (WO 317980) M48/R05 19th Av - Leslie to Woodbine - New 27.6kV Pole Line | Markham | PLNC | Approved | 219895.09 | 1237828.5 | 1488597.52 | 1527118.06 | 02-12-2020 | 002 | Extra time required due to design changes | 2020-12-02 01:00 | 2021-02-03 15:40 | 99
453114 | 453114 (WO 317980) M48/R05 19th Av - Leslie to Woodbine - New 27.6kV Pole Line | Markham | PLNC | Approved | 30873.93 | 1237828.5 | 1488597.52 | 1527118.06 | 19-10-2020 | 001 | Inventory pole change, pole relocation, Transpower cost, TRCA application fee | 2020-10-19 13:06 | 2021-02-03 15:40 | 99
451907 | 15 Queen St S, Hamilton | Hamilton | ICIL | Approved | 703.92 | 96753.69 | 97457.61 | 142636.96 | 29-06-2020 | 001 | OC Hours | 2020-06-24 11:46 | 2020-06-29 20:22 | 98
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 3840.27 | 1739814.7 | 2020150.47 | 2311987.74 | 14-01-2021 | 004 | Pole Delivery | 2020-03-11 01:00 | 2021-06-22 20:34 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 0 | 1739814.7 | 2020150.47 | 2311987.74 | 20-02-2020 | 003 | Scheduled Date Change | 2020-02-20 01:00 | 2021-06-22 20:34 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 0 | 1739814.7 | 2020150.47 | 2311987.74 | 11-02-2020 | 002 | Scheduled Date Change | 2020-02-11 01:00 | 2021-06-22 20:34 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 0 | 1739814.7 | 2020150.47 | 2311987.74 | 13-01-2020 | 001 | Scheduled date change | 2020-01-13 01:00 | 2021-06-22 20:34 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 9282.62 | 1739814.7 | 2020150.47 | 2311987.74 | 12-08-2021 | 008 | Scope Change - Concrete Removal | 2021-07-05 14:37 | 2021-09-28 15:10 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 23364 | 1739814.7 | 2020150.47 | 2311987.74 | 06-05-2021 | 005 | Additional Vac Truck | 2021-05-05 11:01 | 2021-09-28 15:00 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 35738.07 | 1739814.7 | 2020150.47 | 2311987.74 | 22-09-2021 | 007 | Scope Change | 2021-06-10 11:24 | 2021-09-28 15:01 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 20300.81 | 1739814.7 | 2020150.47 | 2311987.74 | 10-08-2021 | 010 | Design and P&C hours missing | 2021-07-13 10:19 | 2021-09-28 15:15 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 166800 | 1739814.7 | 2020150.47 | 2311987.74 | 22-09-2021 | 009 | Additional Labour and Materials | 2021-07-19 14:08 | 2021-09-28 15:14 | 99
452089 | BUM81 FEEDER EXTENSION PART 1 - SOUTH OF CARLTON (ST. CATH), 3 | St. Catharines | PLNC | Approved | 21010 | 1739814.7 | 2020150.47 | 2311987.74 | 22-09-2021 | 006 | Scope Change | 2021-05-31 12:41 | 2021-09-28 15:00 | 99
453598 | 453598 (WO 318891) - NINTH LINE - 19TH AVENUE TO ELGIN MILLS ROAD E | Markham | TRNS | Approved | 0 | 391311 | 391311 | 558191.05 | 26-08-2022 | RFC101 | Change in pole class, no cost affected | 2022-08-23 11:01 | 2022-08-29 04:36 | 84
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 8050 | 1497296.02 | 1657293.53 | 2049013.54 | 10-12-2020 | 004 | Replacement of residential wooden fence | 2020-12-10 01:00 | 2020-12-18 06:00 | 99
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 6371 | 1497296.02 | 1657293.53 | 2049013.54 | 11-02-2021 | 013 | Compaction Testing plus 5% MSA and 10% Transpower burden. | 2021-02-08 01:00 | 2021-02-12 05:49 | 99
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 943 | 1497296.02 | 1657293.53 | 2049013.54 | 11-02-2021 | 014 | CN locates plus 5% MSA and 10% Transpower burden | 2021-02-08 01:00 | 2021-02-12 15:43 | 99
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 7234.94 | 1497296.02 | 1657293.53 | 2049013.54 | 11-02-2021 | 010 | CN locates plus 5% MSA and 10% Transpower burden. | 2021-01-19 01:00 | 2021-02-12 05:49 | 99
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 11368.44 | 1497296.02 | 1657293.53 | 2049013.54 | 15-01-2021 | 006 | Earth Boring cost to complete utility verification | 2021-01-06 01:00 | 2021-01-20 08:46 | 99
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 7042.49 | 1497296.02 | 1657293.53 | 2049013.54 | 15-01-2021 | 007 | Earth Boring cost to remove residential fence | 2021-01-05 01:00 | 2021-01-20 08:46 | 99
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 45712.5 | 1497296.02 | 1657293.53 | 2049013.54 | 18-01-2021 | 002 | Earth Boring change cementitious to cellular grout due to duct breakdown | 2020-07-23 01:00 | 2021-01-20 08:46 | 99
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 40233.45 | 1497296.02 | 1657293.53 | 2049013.54 | 18-01-2021 | 005 | Earth Boring cost to fill pits with Gr4anular B | 2021-01-06 01:00 | 2021-01-20 08:46 | 99
396181 | GO ELEC. - LWL - CONFLICT #LW1548 & LW2222 - OGDEN | Mississauga | TRNS | Approved | 33041.69 | 1497296.02 | 1657293.53 | 2049013.54 | 18-01-2021 | 008 | Earth Boring cost to remove vac spoils. | 2021-01-18 01:00 | 2021-02-03 15:43 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 20987 | 2453670.74 | 3022820.74 | 3140671.69 | 29-12-2020 | 003 | Compaction testing | 2020-12-29 15:13 | 2021-01-26 21:35 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 11230 | 2453670.74 | 3022820.74 | 3140671.69 | 25-05-2021 | 016 | Transpower additional traffic control | 2021-05-25 16:07 | 2021-05-26 04:37 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 20656 | 2453670.74 | 3022820.74 | 3140671.69 | 29-12-2020 | 005 | Transpower additional traffic control, waterfilled attenuators as requested by Metrolinx | 2020-12-29 15:14 | 2021-01-26 21:35 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 81011 | 2453670.74 | 3022820.74 | 3140671.69 | 05-01-2021 | 001 | Equipment and labour costs to break out of foreign concrete encountered in trench | 2021-01-05 13:59 | 2021-01-26 21:35 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 46685 | 2453670.74 | 3022820.74 | 3140671.69 | 04-01-2021 | 002 | Traffic control attenuators | 2021-01-04 17:01 | 2021-01-26 21:35 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 222911 | 2453670.74 | 3022820.74 | 3140671.69 | 26-01-2021 | 006 | Transpower additional hard surface restoration as requested by York Region | 2021-01-26 16:34 | 2021-01-27 08:46 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 2931 | 2453670.74 | 3022820.74 | 3140671.69 | 19-03-2021 | 009 | K-Line work to remove all OH conductors on overtime | 2021-03-19 14:50 | 2021-03-19 21:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 11537 | 2453670.74 | 3022820.74 | 3140671.69 | 19-03-2021 | 010 | Transpower yearly price increase | 2021-03-19 14:51 | 2021-03-19 21:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 11834 | 2453670.74 | 3022820.74 | 3140671.69 | 19-03-2021 | 011 | Transpower yearly price increase | 2021-03-19 14:51 | 2021-03-19 21:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 2649 | 2453670.74 | 3022820.74 | 3140671.69 | 19-03-2021 | 012 | K-Line switching that had to be done on off peak time due to heavy loading | 2021-03-19 14:52 | 2021-03-19 21:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 2313 | 2453670.74 | 3022820.74 | 3140671.69 | 19-03-2021 | 013 | Transpower cost for tree trimming | 2021-03-19 14:52 | 2021-03-19 21:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 3950 | 2453670.74 | 3022820.74 | 3140671.69 | 19-03-2021 | 014 | K-Line replaced conductors from #2 to 1/0 | 2021-03-19 14:53 | 2021-03-19 21:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 2732 | 2453670.74 | 3022820.74 | 3140671.69 | 19-03-2021 | 015 | K-Line OH removals done on overtime | 2021-03-19 14:54 | 2021-03-19 21:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 38067 | 2453670.74 | 3022820.74 | 3140671.69 | 19-03-2021 | 007 | Lump sum yearly pricing increase for K-Line | 2021-03-19 14:55 | 2021-03-19 21:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 51217 | 2453670.74 | 3022820.74 | 3140671.69 | 22-03-2021 | 008 | K-Line yearly pricing increase | 2021-03-22 16:29 | 2021-03-22 20:45 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 11736 | 2453670.74 | 3022820.74 | 3140671.69 | 22-07-2021 | 018 | Transpower supply and install additional PVC and FRE ducts due to design change | 2021-07-22 14:55 | 2021-07-23 04:36 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 10703 | 2453670.74 | 3022820.74 | 3140671.69 | 25-05-2021 | 017 | Transpower additional admin fees | 2021-05-25 16:07 | 2021-05-26 04:37 | 99
453597 | 453597 (WO 318890) HWY7 BALDWIN AVE TO CENTRE ST- Metrolinx Electrical | Markham | TRNS | Approved | 16001 | 2453670.74 | 3022820.74 | 3140671.69 | 29-12-2020 | 004 | Transpower additional work to remove abandoned storm sewer that was in conflict with trench | 2020-12-29 15:14 | 2021-01-26 21:35 | 99
634503 | ST. PETERS HOSPITAL UPGRADE - CUMBERLAND AVE | Hamilton | CSCP | Approved | 9120.43 | 736547.02 | 759207.45 | 722719.01 | 11-06-2021 | 002 | Scope Change - Conduit | 2021-05-31 12:26 | 2021-09-27 17:18 | 99
634503 | ST. PETERS HOSPITAL UPGRADE - CUMBERLAND AVE | Hamilton | CSCP | Approved | 13540 | 736547.02 | 759207.45 | 722719.01 | 26-03-2021 | 001 | Scope Change | 2021-03-26 13:54 | 2021-03-29 20:46 | 99
452008 | 690 Rennie St | Hamilton | ICIL | Approved | 6650.95 | 54032.43 | 60683.38 | 72232.38 | 08-07-2021 | 001 | Customer Requested Design Change | 2021-07-08 11:26 | 2021-07-10 06:34 | 98
452001 | 50 Secord Dr | Hamilton | ICIL | Approved | -9169.29 | 98400.46 | 89231.17 | 97992.88 | 12-05-2020 | 001 | Efficiencies | 2020-05-12 15:26 | 2020-12-29 16:01 | 92
452122 | CENTRAL CONVERSION - MARKLAND ST | Hamilton | PLNC | Approved | 17104.97 | 1318964.01 | 1352318.74 | 1408639.48 | 28-01-2021 | 001 | Scope Change - Poles Added | 2021-01-07 10:46 | 2021-01-29 02:54 | 99
452122 | CENTRAL CONVERSION - MARKLAND ST | Hamilton | PLNC | Approved | 4946.76 | 1318964.01 | 1352318.74 | 1408639.48 | 06-05-2021 | 003 | Scope Change - Scada delays | 2021-05-05 10:30 | 2021-09-28 15:21 | 99
452122 | CENTRAL CONVERSION - MARKLAND ST | Hamilton | PLNC | Approved | 3545 | 1318964.01 | 1352318.74 | 1408639.48 | 16-11-2021 | 004 | Scope Change | 2021-10-06 10:39 | 2021-11-16 17:35 | 99
452122 | CENTRAL CONVERSION - MARKLAND ST | Hamilton | PLNC | Approved | 7758 | 1318964.01 | 1352318.74 | 1408639.48 | 27-04-2021 | 002 | Scope Change | 2021-03-22 14:13 | 2021-09-28 15:20 | 99
396172 | GO ELEC. - LWL - CONFLICT #LW18 - HAIG BLVD. | Mississauga | TRNS | Approved | 677262.05 | 1571119.1 | 2490887.38 | 3576161.47 | 14-09-2022 | 101 | Extra costs associated with working OT and through the winter to get the project completed, as requested by Metrolinx and Alectra | 2022-05-27 14:52 | 2022-09-16 20:48 | 95
396172 | GO ELEC. - LWL - CONFLICT #LW18 - HAIG BLVD. | Mississauga | TRNS | Not Approved | 0 | 1571119.1 | 2490887.38 | 3576161.47 | 26-01-2022 | 000 | RFC cancelled, scope and costs to be incorporated into the other RFCs on this work order. Original value of RFC was $14,775.00 | 2022-01-20 15:52 | 2022-06-09 15:12 | 95
396172 | GO ELEC. - LWL - CONFLICT #LW18 - HAIG BLVD. | Mississauga | TRNS | Approved | 242506.23 | 1571119.1 | 2490887.38 | 3576161.47 | 25-08-2022 | 102 | Extra costs associated with working OT and through the winter to get the project completed, as requested by Metrolinx and Alectra | 2022-05-27 16:44 | 2022-09-08 19:44 | 95
403897 | LAIRD/ WCB MAIN FEEDER RELOCATION | Mississauga | PLNC | Approved | 15035.86 | 312539.59 | 327575.45 | 605833.67 | 08-03-2022 | 001 | Mechanical exploration to expose existing poly pipe in the vicinity of SG1442 | 2022-01-20 17:03 | 2022-03-15 21:17 | 95
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 42423 | 966566.2 | 1486374.12 | 1483101.92 | 13-11-2020 | 004 | Earth Boring change from cementitious to cellular grout | 2020-11-13 14:50 | 2020-11-14 08:47 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 4725 | 966566.2 | 1486374.12 | 1483101.92 | 20-09-2021 | 021 | Earth Boring cost to remobilize as project was delayed due to revised elevation relating to watermain | 2021-09-20 12:24 | 2021-09-21 04:35 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 156975 | 966566.2 | 1486374.12 | 1483101.92 | 16-11-2020 | 003 | Earth boring charge for additional depth required due to watermain obstruction not located on original design | 2020-11-17 12:00 | 2020-11-18 08:48 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 6089.92 | 966566.2 | 1486374.12 | 1483101.92 | 12-05-2020 | 002 | Additional cable work for design changes to move tx | 2020-05-12 14:54 | 2020-05-13 14:47 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 4506 | 966566.2 | 1486374.12 | 1483101.92 | 09-02-2021 | 006 | Earth Boring cost for utility verification | 2021-02-09 09:42 | 2021-02-10 08:46 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 2209 | 966566.2 | 1486374.12 | 1483101.92 | 16-03-2021 | 008 | Lump sum yearly pricing increase for K-Line | 2021-03-16 16:24 | 2021-03-17 06:45 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 5048 | 966566.2 | 1486374.12 | 1483101.92 | 16-03-2021 | 009 | Transpower yearly increase based on 2% civil items on WBS | 2021-03-16 16:25 | 2021-03-17 06:45 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 54073 | 966566.2 | 1486374.12 | 1483101.92 | 16-03-2021 | 005 | Earth boring cost for additional traffic control | 2021-03-16 16:27 | 2021-03-17 06:45 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 37485 | 966566.2 | 1486374.12 | 1483101.92 | 16-03-2021 | 007 | Lump sum yearly pricing increase for Earth Boring | 2021-03-16 16:29 | 2021-03-17 06:45 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 29131 | 966566.2 | 1486374.12 | 1483101.92 | 16-03-2021 | 010 | Earth Boring cost for additional traffic control | 2021-03-16 16:30 | 2021-03-17 06:45 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 7427 | 966566.2 | 1486374.12 | 1483101.92 | 16-03-2021 | 011 | K-Line pole support | 2021-03-16 16:30 | 2021-03-17 06:45 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 54270 | 966566.2 | 1486374.12 | 1483101.92 | 05-10-2021 | 020 | Earth Boring costs associated with delay in removing shoring system | 2021-10-05 16:26 | 2021-10-06 04:35 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 37692 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 019 | Transpower overnight premium to complete civil - due to traffic control requirements | 2021-08-17 17:06 | 2021-08-18 04:36 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 16979 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 023 | Transpower additional admin, consulation, engineering feeds due to field changes throughout duration of the project | 2021-08-17 14:21 | 2021-08-17 18:34 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 1134 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 014 | Transpower cost for compaction testing | 2021-08-17 14:18 | 2021-08-17 18:34 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 27180 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 012 | Transpower cost for additional traffic control (overnights) | 2021-08-17 14:17 | 2021-08-17 18:34 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 6756 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 018 | EXP additional monitoring due to project delays | 2021-08-17 14:20 | 2021-08-17 18:34 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 1155 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 022 | Transpower cost for additional layout as requested due to revised elevation | 2021-08-17 14:21 | 2021-08-17 18:34 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 2802 | 966566.2 | 1486374.12 | 1483101.92 | 21-05-2021 | 013 | K-Line overtime for OH conductor removal | 2021-05-21 14:22 | 2021-05-22 06:35 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 1050 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 015 | Transpower cost for CN locates | 2021-08-17 14:19 | 2021-08-17 18:34 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 16482 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 016 | Transpower cost for PNR locates | 2021-08-17 14:19 | 2021-08-17 18:34 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 4216 | 966566.2 | 1486374.12 | 1483101.92 | 17-08-2021 | 017 | Transpower ost for fencing | 2021-08-17 14:20 | 2021-08-17 18:34 | 99
453609 | 453609 (WO 318903) TESTON RD & KEELE ST TO RODINEA RD- Metrolinx Electrical | Markham | TRNS | Approved | 0 | 966566.2 | 1486374.12 | 1483101.92 | 07-04-2020 | 001 | Changes to duct bank and tx locations | 2020-04-07 01:00 | 2020-04-14 22:00 | 99
428251 | FEEDER REPLACEMENT 45F1 TO 45F | Mississauga | PLNC | Approved | 24027.82 | 396202.77 | 420230.59 | 432585.98 | 11-05-2021 | 101 | Extra charge for the exploratory work to find a trench off set on site | 2021-04-28 15:35 | 2021-07-13 20:08 | 99
451812 | 354 King St.W - Temp | Hamilton | ICIL | Approved | 1407.84 | 45486.1 | 46893.94 | 56390.46 | 29-06-2020 | 001 | OC Hours | 2020-06-24 11:47 | 2020-06-29 20:26 | 99
631939 | 631939 - 9700 9TH LINE MARKHAM | Markham | ICIL | Approved | 0 | 124821.53 | 124821.53 | 66991.88 | 22-10-2021 | 001 | Rerouted the design to be a road crossing since contractor ran into constructability issues | 2021-10-22 11:06 | 2022-07-06 16:11 | 99
450280 | CUMBERLAND DR/BRISCO ST - 2019 Pole Batch #20 | Brampton | PLNC | Approved | 0 | 665148.01 | 665148.01 | 534030.36 | 09-09-2020 | 001 | Pole class change | 2020-09-09 13:05 | 2020-12-21 16:44 | 99
636041 | CAL-GORE DEVELOPMENT INC. - SUBD RES EDS | Brampton | SUBD | Not Approved | 0 | 204570.53 | 204570.53 | 144135.82 | 16-11-2021 | 001 | Additional hours | 2021-08-11 12:01 | 2021-11-16 18:07 | 99
634204 | FAIR BIRCH DRIVE & BIRCHVIEW DRIVE - OH TO UG RELOCATION | Mississauga | CSCP | Approved | 78845.44 | 432576.41 | 511421.85 | 405920.03 | 02-07-2021 | 001 | Changed to concrete encased duct structure. Additional time required to install concrete encased structure plus dig extra depth to | 2021-04-20 09:54 | 2021-07-02 20:50 | 99
636043 | CHEDOKE HEIGHTS - PHASE 1 - SUBD RES EDS | Hamilton | SUBD | Approved | -42437.59 | 299234.01 | 256796.42 | 686697.17 | 10-08-2021 | 001 | Efficiencies | 2021-07-22 09:33 | 2021-09-27 18:07 | 99
636055 | 57 LAKEPORT RD PERM | St. Catharines | ICIL | Approved | 2658 | 127782.03 | 133059.03 | 131256.41 | 27-04-2021 | 001 | Concrete conflict | 2021-04-23 08:22 | 2021-09-28 14:38 | 92
636055 | 57 LAKEPORT RD PERM | St. Catharines | ICIL | Approved | 2250 | 127782.03 | 133059.03 | 131256.41 | 27-04-2021 | 003 | Concrete shroud | 2021-04-23 08:22 | 2021-09-28 14:41 | 92
636055 | 57 LAKEPORT RD PERM | St. Catharines | ICIL | Approved | 369 | 127782.03 | 133059.03 | 131256.41 | 27-04-2021 | 002 | Unidentified UG conflict | 2021-04-23 08:22 | 2021-09-28 14:41 | 92
632760 | CABLE INJECTION INVESTIGATION | Hamilton | PLNC | Approved | 677.44 | 379952 | 390385.43 | 262048 | 11-11-2020 | 004 | Waiting for Control | 2020-03-11 01:00 | 2020-11-11 16:27 | 99
632760 | CABLE INJECTION INVESTIGATION | Hamilton | PLNC | Approved | 9755.99 | 379952 | 390385.43 | 262048 | 11-11-2020 | 003 | Numerous difficulties | 2020-03-02 01:00 | 2020-11-11 16:27 | 99
635932 | RYMAL RD WIDENING - CITY OF HAMILTON - PHASE 2 | Hamilton | CSCP | Approved | 40948.19 | 925685.1 | 972707.84 | 885834.81 | 16-02-2021 | 001 | Scope Change | 2021-02-08 18:17 | 2021-02-16 16:31 | 99
635932 | RYMAL RD WIDENING - CITY OF HAMILTON - PHASE 2 | Hamilton | CSCP | Pending | -269678.04 | 925685.1 | 972707.84 | 885834.81 | Pending With Design | 003 | Change from Ext to Int (Contractor) | 2022-03-25 14:27 | 2022-04-11 17:03 | 99
635932 | RYMAL RD WIDENING - CITY OF HAMILTON - PHASE 2 | Hamilton | CSCP | Approved | 6074.55 | 925685.1 | 972707.84 | 885834.81 | 02-02-2022 | 002 | Lashed Secondary Install | 2022-01-20 14:00 | 2022-02-02 20:23 | 99
635932 | RYMAL RD WIDENING - CITY OF HAMILTON - PHASE 2 | Hamilton | CSCP | Pending | 0 | 925685.1 | 972707.84 | 885834.81 | Pending With Design | 103 | Change from Ext to Int | 2022-02-14 09:00 | 2022-03-25 18:27 | 99
452140 | CENTRAL - ST JAMES PL- 16664 (2020) | Hamilton | PLNC | Approved | -91554.18 | 1076793.8 | 1000752.3 | 1058346.96 | 16-11-2021 | 002 | Efficiencies | 2021-11-09 10:28 | 2021-11-17 14:26 | 99
452140 | CENTRAL - ST JAMES PL- 16664 (2020) | Hamilton | PLNC | Approved | 15512.68 | 1076793.8 | 1000752.3 | 1058346.96 | 05-07-2021 | 001 | Scope Change | 2021-06-29 15:23 | 2021-07-06 02:19 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 6225 | 1556424.96 | 2003219.96 | 1990123.54 | 02-12-2020 | 003 | Transpower standby costs for delay due to culvert obstruction | 2020-12-02 15:29 | 2021-02-26 15:59 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 10177 | 1556424.96 | 2003219.96 | 1990123.54 | 22-03-2021 | 015 | K-Line additonal work due to design change | 2021-03-22 16:13 | 2021-03-22 21:45 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 2542 | 1556424.96 | 2003219.96 | 1990123.54 | 02-12-2020 | 004 | Police duty | 2020-12-02 15:30 | 2021-02-26 15:59 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 16640 | 1556424.96 | 2003219.96 | 1990123.54 | 02-12-2020 | 005 | Compaction testing | 2020-12-02 15:31 | 2021-02-26 15:59 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 8269 | 1556424.96 | 2003219.96 | 1990123.54 | 02-12-2020 | 006 | Transpower investigation and repair of sink hole | 2020-12-02 15:32 | 2021-02-26 15:59 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 237458 | 1556424.96 | 2003219.96 | 1990123.54 | 02-12-2020 | 008 | Additional road restoration as requested by the Region | 2020-12-02 15:33 | 2021-02-26 15:59 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 0 | 1556424.96 | 2003219.96 | 1990123.54 | 23-04-2020 | 001 | Design changes | 2020-04-22 | 2020-09-22 19:31 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 9040 | 1556424.96 | 2003219.96 | 1990123.54 | 09-02-2021 | 010 | K-Line pole support | 2021-02-09 11:03 | 2021-02-10 08:46 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 3475 | 1556424.96 | 2003219.96 | 1990123.54 | 09-02-2021 | 011 | K-Line overtime removals | 2021-02-09 11:04 | 2021-02-10 08:46 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 44356 | 1556424.96 | 2003219.96 | 1990123.54 | 04-12-2020 | 009 | Additional road restoration | 2020-12-04 12:30 | 2021-02-26 15:59 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 4233 | 1556424.96 | 2003219.96 | 1990123.54 | 19-03-2021 | 007 | K-Line float Nodwell | 2021-03-19 12:38 | 2021-03-19 20:45 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 3242 | 1556424.96 | 2003219.96 | 1990123.54 | 19-03-2021 | 012 | Lump sum yearly pricing increase for K-Line | 2021-03-19 12:39 | 2021-03-19 20:45 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 17914 | 1556424.96 | 2003219.96 | 1990123.54 | 19-03-2021 | 013 | Transpower yearly price increase | 2021-03-19 12:40 | 2021-03-19 20:45 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 1807 | 1556424.96 | 2003219.96 | 1990123.54 | 19-03-2021 | 014 | Transpower additional admin fees | 2021-03-19 12:40 | 2021-03-19 20:45 | 99
453599 | 453599 (WO 318892) MAJOR MACKENZIE DR W-KEELE ST TO MCNAUGHTON RD E- Metrolinx Electrical | Markham | TRNS | Approved | 81417 | 1556424.96 | 2003219.96 | 1990123.54 | 02-12-2020 | 002 | Additional traffic control barricades | 2020-12-02 15:27 | 2021-02-26 15:59 | 99
636602 | 636602 - STORM HARDENING - HUNTINGTON - RUTHERFORD TO LANGSTAFF - VAUGHAN | Markham | PLNC | Approved | 320142.62 | 657284.08 | 977426.7 | 364389.42 | 20-05-2021 | 001 | Removing internal construction labour costs, adding external K-Line costs | 2021-05-03 14:49 | 2021-06-16 20:35 | 99
427602 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE 1 DIXIE ROAD | Mississauga | CSCP | Approved | 7926.54 | 3397365.54 | 3184986.34 | 2808949.12 | 09-02-2021 | 001 | P01429 requires replacement | 2021-02-02 01:00 | 2021-02-11 08:46 | 98
427602 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE 1 DIXIE ROAD | Mississauga | CSCP | Approved | 16101.6 | 3397365.54 | 3184986.34 | 2808949.12 | 19-04-2021 | 002 | Temporary by pass line to keep the MTO light alive | 2021-03-17 17:00 | 2021-08-25 14:20 | 98
427602 | QEW IMPROVEMENTS FROM EVANS AVE TO CAWTHRA RD - PHASE 1 DIXIE ROAD | Mississauga | CSCP | Approved | -236407.34 | 3397365.54 | 3184986.34 | 2808949.12 | 23-09-2021 | 003 | Reduction of working hours and labour | 2021-09-20 18:41 | 2022-03-22 02:28 | 98
636606 | 636606 - STORM HARDENING - CENTRE ST - HWY 7 TO GREENWOOD TS - MARKHAM | Markham | PLNC | Approved | 41350.42 | 80270.7 | 121621.12 | 169516.25 | 19-03-2021 | 001 | Additional OT hours for switching and costs for budget overages | 2021-03-16 11:21 | 2021-04-15 18:09 | 99
637171 | 1478 QUEEN ST. E.- 27.6KV SUPPLY TO ELECTRIC BUS CHARGING STATION | Brampton | ICIL | Approved | 17500 | 89507.93 | 107007.93 | 99534.89 | 08-02-2021 | 001 | Extra Lines hours | 2021-02-03 13:44 | 2022-07-06 16:12 | 92
637170 | COMMUTER DR. - 27.6KV SUPPLY TO ELECTRIC BUS STATION | Brampton | ICIL | Approved | 6217.41 | 165328.03 | 171545.44 | 206173.92 | 03-03-2021 | 001 | Scope Change due to conflicting utilities | 2021-02-12 14:27 | 2021-03-30 15:01 | 92
634156 | 634156 - TESTON RD. PINE VALLEY TO WESTON - POLE RELOCATION | Markham | CSCP | Approved | 4159.55 | 4520823.93 | 4462892.98 | 1524432.15 | 16-06-2021 | 004 | Relocation, modified framing standards, modified schematic, drawing changes. | 2021-06-14 09:07 | 2021-09-28 14:53 | 99
634156 | 634156 - TESTON RD. PINE VALLEY TO WESTON - POLE RELOCATION | Markham | CSCP | Approved | 2500 | 4520823.93 | 4462892.98 | 1524432.15 | 31-05-2021 | 003 | Removal of tx, and relocations | 2021-05-28 16:07 | 2021-09-28 14:53 | 99
634156 | 634156 - TESTON RD. PINE VALLEY TO WESTON - POLE RELOCATION | Markham | CSCP | Approved | 395.55 | 4520823.93 | 4462892.98 | 1524432.15 | 06-05-2021 | 001 | Additional float move was required | 2021-05-05 15:30 | 2021-05-07 04:07 | 99
634156 | 634156 - TESTON RD. PINE VALLEY TO WESTON - POLE RELOCATION | Markham | CSCP | Approved | -64986.05 | 4520823.93 | 4462892.98 | 1524432.15 | 20-05-2021 | 002 | Material removed as scope changed and not required. Drawing changes. | 2021-05-20 15:30 | 2021-09-28 16:04 | 99
634379 | Folkway Rebuild - Phase2 | Mississauga | PLNC | Approved | 41811.41 | 2731756.26 | 2779472.35 | 3025979.9 | 15-11-2021 | 103 | This RFC is for the extra Charge for the hard surface restoration that was estimated vs what was actually completed. Vaughan Pavin | 2021-08-24 18:43 | 2021-11-16 15:43 | 99
634379 | Folkway Rebuild - Phase2 | Mississauga | PLNC | Approved | 5904.68 | 2731756.26 | 2779472.35 | 3025979.9 | 11-01-2021 | 101 | To complete the temporary restoration of the asphalt driveway aprons | 2020-12-11 01:00 | 2021-08-24 16:03 | 99
454016 | 454016 - HWY 27 & HWY 7 | Markham | CSCP | Approved | 0 | 1307128 | 1307128 | 1300763.9 | 01-09-2021 | 001 | Shift poles north, one circuit avoid culvert and second circuit bore shot underneath culvert. No material or labor charges | 2021-09-01 15:06 | 2021-09-01 19:34 | 99
646221 | Guelph West Reinforcement, Phase 3 - Edinburgh Road North | Guelph | PLNC | Not Approved | 3000 | 648023.9 | 648023.9 | 592902.74 | 31-05-2022 | 001 | TP Scope Change | 2021-03-08 16:06 | 2022-09-27 16:20 | 92
637894 | 637894 - 6 DAVID EYER ROAD/ RHL/ NS/ 3PH PAD | Markham | ICIL | Approved | 0 | 100291.79 | 100291.79 | 6923.42 | 17-06-2022 | 002 | Primary feeders were changed. Drawings updated. | 2022-06-17 16:13 | 2022-07-06 16:11 | 82
637894 | 637894 - 6 DAVID EYER ROAD/ RHL/ NS/ 3PH PAD | Markham | ICIL | Approved | 0 | 100291.79 | 100291.79 | 6923.42 | 18-03-2022 | 001 | IFC stamp has been added to the drawings. | 2022-03-18 15:00 | 2022-07-06 16:11 | 82
633938 | CHEGWIN STREET POLE RELOCATION - 3 | Hamilton | PLNC | Approved | 985 | 36642.2 | 37627.2 | 26634.22 | 04-01-2021 | 001 | Design change - Electrician costs | 2021-01-04 01:00 | 2021-02-10 03:46 | 99
635835 | ROAD AUTHORITY - PARKIDE DR ROAD WIDENING - WATERDOWN | Hamilton | CSCP | Approved | 9477.3 | 2222139.53 | 2271588.88 | 2234118.46 | 12-04-2022 | 002 | Performance: March 28 and March 29- Jack hammered pole hole and hydrovac; March 30 - Removed guard rail for crane outriggers and r | 2022-04-11 09:24 | 2022-04-13 12:55 | 99
635835 | ROAD AUTHORITY - PARKIDE DR ROAD WIDENING - WATERDOWN | Hamilton | CSCP | Approved | 5199.44 | 2222139.53 | 2271588.88 | 2234118.46 | 29-03-2022 | 001 | Unforseen Scope Changes | 2022-03-28 09:08 | 2022-03-30 12:54 | 99
635835 | ROAD AUTHORITY - PARKIDE DR ROAD WIDENING - WATERDOWN | Hamilton | CSCP | Approved | 8712.61 | 2222139.53 | 2271588.88 | 2234118.46 | 15-08-2022 | 103 | Delays | 2022-08-11 10:15 | 2022-08-17 12:37 | 99
635835 | ROAD AUTHORITY - PARKIDE DR ROAD WIDENING - WATERDOWN | Hamilton | CSCP | Not Approved | 132324.85 | 2222139.53 | 2271588.88 | 2234118.46 | 20-09-2022 | 105 | Delays | 2022-08-16 09:03 | 2022-09-20 19:54 | 99
635835 | ROAD AUTHORITY - PARKIDE DR ROAD WIDENING - WATERDOWN | Hamilton | CSCP | Approved | 26060 | 2222139.53 | 2271588.88 | 2234118.46 | 07-10-2022 | 104 | Additional vac truck charges | 2022-08-15 14:23 | 2022-10-17 18:45 | 99
633130 | 633130 - DISTRIBUTION AUTOMATION 2020 - A10SL2026 - AURORA, 1 | Markham | PLNC | Approved | 30000 | 100788.23 | 130788.23 | 140571.45 | 10-05-2021 | 001 | K-Line to complete work | 2021-05-10 14:32 | 2021-09-27 16:24 | 99
633131 | 633131 - DISTRIBUTION AUTOMATION 2021 - A10SL2035 - AURORA, 1 | Markham | PLNC | Approved | 31308.57 | 116757.7 | 148066.27 | 170901.05 | 16-06-2021 | 001 | Contracted out to K-Line | 2021-06-16 14:49 | 2021-09-27 16:33 | 99
633132 | 633132 - DISTRIBUTION AUTOMATION 2021 - A06SL2042 - AURORA, 1 | Markham | PLNC | Approved | 17224.82 | 144609.45 | 161834.27 | 159753.67 | 16-06-2021 | 001 | Contracted out to K-Line | 2021-06-16 15:51 | 2021-09-27 16:41 | 99
632805 | 632805 - 63 ERIC T SMITH WAY | Markham | ICIL | Approved | 0 | 43126.47 | 43126.47 | 47397.08 | 26-03-2020 | 001 | Unforeseen customer change of transformer | 2020-03-26 01:00 | 2020-09-22 19:34 | 99
636663 | 636663 - 2021 UG CABLE REPLACEMENT - V44, WALLACE, FAIRGROUND, PARK, WAKELIN, YELLOW PINE | Markham | PLNC | Approved | -93456 | 822878.31 | 729422.31 | 765153.17 | 14-10-2021 | 001 | Existing duct strucutre reused which reduced civil costs | 2021-10-14 14:15 | 2021-10-14 18:34 | 99
632723 | 632723 - 98 AUTO VAUGHAN DR (Car Dealership) | Markham | ICIL | Approved | 358 | 50588.53 | 50946.53 | 39875.07 | 08-12-2020 | 001 | RFC for additional cable meters pulled in by Somerville | 2020-11-24 15:24 | 2020-12-21 16:48 | 99
634983 | WINDJAMMER UG REBUILD | Mississauga | PLNC | Approved | 20157.38 | 4455400.97 | 4613689.28 | 4704847.78 | 24-02-2021 | 101 | To complete the temporary restoration of the asphalt driveway aprons | 2020-12-11 01:00 | 2021-04-28 20:26 | 99
634983 | WINDJAMMER UG REBUILD | Mississauga | PLNC | Approved | 23820.49 | 4455400.97 | 4613689.28 | 4704847.78 | 28-05-2021 | 104 | Extra splice pit added, work around a S/G and we had to move a transformer from a fence to the boulevard | 2021-04-28 15:42 | 2021-07-14 17:06 | 99
634983 | WINDJAMMER UG REBUILD | Mississauga | PLNC | Approved | 21027.24 | 4455400.97 | 4613689.28 | 4704847.78 | 21-05-2021 | 103 | Extra charge associated with the overtime work that took place over the weekend (Saturyda) | 2021-05-20 11:49 | 2021-05-24 05:08 | 99
634983 | WINDJAMMER UG REBUILD | Mississauga | PLNC | Approved | 93283.2 | 4455400.97 | 4613689.28 | 4704847.78 | 15-11-2021 | 105 | This RFC is for the extra Charge for the hard surface restoration that was estimated vs what was actually completed. Vaughan Pavin | 2021-08-24 12:03 | 2021-11-17 18:47 | 99
634983 | WINDJAMMER UG REBUILD | Mississauga | PLNC | Approved | 0 | 4455400.97 | 4613689.28 | 4704847.78 | 22-09-2020 | 001 | Revised drawings - no impact to cost or scope | 2020-09-22 16:46 | 2021-04-30 04:08 | 99
636872 | 636872 - AMBER MS F2 FEEDER CONVERSION | Markham | PLNC | Approved | 52011.37 | 591910.82 | 735554.01 | 749194.89 | 24-03-2021 | 001 | Padmount relocation, new duct required, conversion of 13.8kV to 27.6kV | 2021-03-17 15:18 | 2021-05-05 20:34 | 99
636872 | 636872 - AMBER MS F2 FEEDER CONVERSION | Markham | PLNC | Approved | 63927.1 | 591910.82 | 735554.01 | 749194.89 | 19-04-2021 | 002 | Removal of unused conductors and switches | 2021-04-19 15:50 | 2021-05-05 20:34 | 99
636872 | 636872 - AMBER MS F2 FEEDER CONVERSION | Markham | PLNC | Approved | 27704.72 | 591910.82 | 735554.01 | 749194.89 | 05-05-2021 | 003 | Exploratory work, found cable direct buried, added installation of ductbank | 2021-04-29 16:09 | 2021-05-05 20:34 | 99
636873 | UG CABLE REPLACEMENT - MILLCREEK & ERIN MILLS PKWY | Mississauga | PLNC | Approved | 8131.46 | 1274480.86 | 1282612.32 | 1185252.74 | 18-07-2022 | 101 | Civil scope expanded. | 2022-06-29 14:57 | 2022-07-19 04:38 | 95
633562 | REBUILD: W 34TH & W 33RD STREET, N OF LESLIE AVE (HAMILTON) - 16 | Hamilton | PLNC | Approved | 11382.21 | 347796.56 | 341580.3 | 320776.97 | 10-08-2021 | 002 | Labour Hours Missing | 2021-07-20 16:11 | 2021-09-27 20:50 | 99
633562 | REBUILD: W 34TH & W 33RD STREET, N OF LESLIE AVE (HAMILTON) - 16 | Hamilton | PLNC | Approved | -17598.47 | 347796.56 | 341580.3 | 320776.97 | 10-08-2021 | 001 | Efficiencies | 2021-07-14 09:35 | 2021-09-27 20:51 | 99
633375 | C1-6 - 1465 MAYFIELD RD - 27.6KV U/G RADIAL 750KVA | Brampton | ICIL | Approved | 1305 | 82825.88 | 84130.88 | 62418.22 | 22-07-2021 | 001 | Civil depth change | 2021-07-20 14:35 | 2021-09-27 16:45 | 95
635642 | 134 KENNEDY RD. S. - SERVICE UPGRADE | Brampton | ICIL | Approved | 8750 | 186047.85 | 194797.85 | 139047.9 | 02-03-2021 | 001 | Easement Issues - Add hours | 2021-02-03 13:41 | 2021-03-19 17:05 | 95
636894 | 9280 AND 9300 GOREWAY DR - 27.6KV TO 1500 KVA TX | Brampton | ICIL | Approved | 7500 | 110264.1 | 117764.1 | 99176.21 | 08-02-2021 | 001 | Extra Lines hours | 2021-02-03 13:42 | 2021-03-19 15:41 | 92
636898 | ATTMAR DR AND THE GORE RD - FEEDER EXTENSION | Brampton | CSCP | Approved | 25733 | 200612.13 | 226345.13 | 234073.63 | 02-03-2021 | 001 | Add Scope | 2021-02-01 12:48 | 2021-03-02 17:35 | 92
637029 | AUTO SW - ITD - ST CATHARINES, 5 | St. Catharines | PLNC | Approved | 115004.97 | 437158.89 | 552163.86 | 323143.38 | 02-02-2022 | 001 | Scope Change - Reclosure removed | 2022-01-20 14:00 | 2022-02-02 20:52 | 99
638016 | POLE RELOCATION SHELL GAS STATION AIRPORT ROAD & BRESLER DRIVE | Mississauga | CSCP | Pending | 0 | 181738.39 | 181738.39 | 178769.72 | Pending with Design | 001 | There's one pole left to remove. We're waiting for the city to coordinate Guild Electric and Peel police for cut over to new pole. | 2022-12-01 16:02 | 2022-12-04 21:04 | 99
637917 | POLE 41797 - REPLACE FUSES ON POLE | Hamilton | PLNC | Approved | 3125.47 | 27120.74 | 30246.21 | 14664.29 | 20-12-2022 | 001 | Scope Change | 2022-12-20 15:23 | 2022-12-20 20:34 | 92
632681 | 200 Largerfeld Dr and Creditview Rd - Block 7 | Brampton | ICIL | Approved | -20729.31 | 87911.14 | 67181.83 | 66679.83 | 01-04-2020 | 001 | scope reduction - no civil work required | 2020-03-30 01:00 | 2020-04-01 20:33 | 92
635659 | 160 SALVATION RD | Brampton | ICIL | Approved | 8750 | 63849.37 | 72599.37 | 60193.49 | 18-02-2021 | 001 | Addtional Lines Hours | 2021-02-02 14:43 | 2022-07-06 16:12 | 92
637046 | 45 WEST DR - 27.6KV SUPPLY TO 1500 KVA TX | Brampton | ICIL | Approved | 0 | 156206.57 | 156206.57 | 169999.99 | 12-05-2021 | 001 | Extra hours | 2021-05-12 13:10 | 2021-09-27 20:11 | 92
635032 | 635032 - OH AND UG RELOCATION AT JANE ST (NORTH OF TESTON RD), VAUGHAN | Markham | CSCP | Approved | 5000 | 744128.4 | 749128.4 | 801141.6 | 08-07-2021 | 001 | Install 2 step down transformers to replace existing switches due to voltage conversion | 2021-07-08 13:25 | 2021-09-27 17:38 | 98
637091 | 13 CP - POLE RENEWAL - BURNHAMTHORPE RD | Mississauga | PLNC | Pending | 17027.35 | 414246.97 | 414246.97 | 462285.29 | Pending with Design | 101 | Control room delays, extra hydrovac for each pole installed to accommodate ground rod | 2022-11-25 02:27 | 2022-11-29 07:34 | 92
638082 | 638082 - 1SC39 RTU FEED AT LESLIE AND WEST BEAVER CREEK | Markham | PLNC | Approved | -11776 | 82520.73 | 70744.73 | 70082.57 | 21-04-2021 | 001 | Existing spare ducts across both Leslie St and West Beaver Creek that can be utilized | 2021-04-21 13:37 | 2021-04-22 05:34 | 99
635713 | OLD CREDITVIEW ROAD AND CREDITVIEW ROAD POLE RELOCATIONS - REGION OF PEEL | Mississauga | CSCP | Approved | 8462 | 308483.68 | 338890.68 | 328872.29 | 02-11-2021 | 102 | Performance: Oct 18, 2021 - Downtime hours due to delay in control room. | 2021-11-02 15:32 | 2021-11-04 13:32 | 99
635713 | OLD CREDITVIEW ROAD AND CREDITVIEW ROAD POLE RELOCATIONS - REGION OF PEEL | Mississauga | CSCP | Approved | 21945 | 308483.68 | 338890.68 | 328872.29 | 12-10-2021 | 101 | Flagging required to be added to estimate. (approx. 133 hours at $150/hour rate + 10% markup) | 2021-10-07 15:00 | 2021-11-02 20:04 | 99
635065 | 635065 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.1 | Markham | CSCP | Approved | 12623.95 | 1870186.88 | 1955792.92 | 2043451.52 | 25-04-2022 | 102 | Additional labour and clean up | 2022-04-14 13:26 | 2022-04-26 18:05 | 92
635065 | 635065 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.1 | Markham | CSCP | Approved | 8266.33 | 1870186.88 | 1955792.92 | 2043451.52 | 22-06-2022 | 104 | Additional labour for 2 transformers | 2022-06-20 15:54 | 2022-06-22 20:04 | 92
635065 | 635065 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.1 | Markham | CSCP | Approved | 57788.51 | 1870186.88 | 1955792.92 | 2043451.52 | 15-12-2021 | 101 | Adding labour due to out of scope work | 2021-12-14 14:32 | 2022-04-26 17:27 | 92
635065 | 635065 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.1 | Markham | CSCP | Approved | 6927.25 | 1870186.88 | 1955792.92 | 2043451.52 | 27-04-2022 | 103 | Additional labour with vac and glass insulators | 2022-04-26 13:31 | 2022-04-27 17:34 | 92
635079 | 635079 - CABLE REPLACEMENT, M14 MAJOR BUTTONS AND RICHWOOD - 14TP030 TO 14U030 | Markham | PLNC | Approved | -43715 | 576289.71 | 532574.71 | 542307.4 | 18-03-2021 | 001 | Transpower credit for reusing existing ducts, reusing existing road crossing, not replacing sidewalk bays and cheaper restoration | 2021-03-18 14:19 | 2021-03-19 04:46 | 99
633440 | 633440 - DISTRIBUTION AUTOMATION 2021 - A09SL2015 - AURORA, 1 | Markham | PLNC | Approved | 23760.6 | 121118.97 | 144879.57 | 162892.83 | 16-06-2021 | 001 | Contracted out to K-Line | 2021-06-16 16:32 | 2021-09-27 16:49 | 99
635174 | HAMILTON HEALTH SCIENCES - ST. PETER'S HOSPITAL. | Hamilton | ICIL | Pending | 15328.13 | 117013.54 | 117013.54 | 90094.71 | Pending With Design | 001 | Fuse Size Changes | 2022-12-13 14:00 | 2023-01-10 16:23 | 84
633134 | 633134 - DISTRIBUTION AUTOMATION 2021 - A06SL2024 - AURORA, 1 | Markham | PLNC | Approved | 27598.72 | 108488.54 | 136087.26 | 169052.8 | 16-06-2021 | 001 | Contracted out to K-Line | 2021-06-16 16:11 | 2021-09-27 16:42 | 99
637117 | SISTER VARGA | Hamilton | ICIL | Approved | 16945.1 | 57085.12 | 74030.22 | 50362.73 | 21-06-2021 | D001 | Materials Correction | 2021-06-21 15:54 | 2021-06-22 06:39 | 92
633540 | MISSISSAUGA ROAD SOUTH POLELINE RELOCATION | Mississauga | CSCP | Approved | 14314.19 | 1646004.35 | 1660318.54 | 1351475.17 | 23-11-2021 | 001 | Weekend work required to remove pole - line during high demand of work | 2021-11-22 12:00 | 2021-12-08 18:04 | 98
635715 | MH2163 SEWERING | Hamilton | CSCP | Approved | -39847.1 | 106297.41 | 66450.31 | 56242.99 | 02-02-2022 | 001 | Efficiencies | 2022-01-20 10:00 | 2022-02-09 14:23 | 99
635840 | ROAD AUTHORITY - GRINDSTONE BRIDGE OVERHEAD WIRE RELOCATION | Hamilton | CSCP | Approved | 9060.85 | 337176.4 | 321701.44 | 305659.74 | 09-03-2022 | 001 | Vac truck, small scope change | 2022-03-09 15:02 | 2022-03-09 20:34 | 99
635840 | ROAD AUTHORITY - GRINDSTONE BRIDGE OVERHEAD WIRE RELOCATION | Hamilton | CSCP | Approved | -24535.81 | 337176.4 | 321701.44 | 305659.74 | 25-04-2022 | 002 | Reduction RFC | 2022-04-20 08:15 | 2022-04-25 13:27 | 99
637148 | HERITAGE ROAD DEVELOPMENT ENTRANCE POLE RELOCATION | Brampton | CSCP | Approved | 21370.34 | 70979.47 | 92349.81 | 92654.83 | 14-04-2021 | 001 | Additional hours and missing T/F costs | 2021-03-29 16:11 | 2021-09-27 20:13 | 98
635749 | HAMILTON KICKER TX REPLACEMENT - TX 7675 AND 8050 - 2 | Hamilton | PLNC | Approved | 3845 | 27435.53 | 35125.53 | 48392.54 | 20-01-2022 | 002 | Unforeseen Scope | 2022-01-20 10:49 | 2022-01-20 16:06 | 99
635749 | HAMILTON KICKER TX REPLACEMENT - TX 7675 AND 8050 - 2 | Hamilton | PLNC | Approved | 3845 | 27435.53 | 35125.53 | 48392.54 | 20-01-2022 | 001 | Unforeseen Scope | 2022-01-20 10:49 | 2022-01-20 16:06 | 99
635756 | HAMILTON KICKER TX REPLACEMENT - TX 13000 - 1 | Hamilton | PLNC | Approved | 4937.01 | 3574.01 | 8511.02 | 9587.03 | 08-06-2021 | 001 | Scope Change | 2021-06-08 14:10 | 2021-09-27 18:02 | 99
634827 | HAMILTON 2020 POLE RESIDUALS PHASE 6 - 8 | Hamilton | PLNC | Approved | 45614.81 | 116206.58 | 161821.39 | 155133.87 | 02-06-2021 | 001 | Rock and Hours Overage | 2021-04-22 16:00 | 2021-09-27 17:34 | 99
637561 | EXPANSION WORK FOR 75 NIAGARA ST | St. Catharines | CSCP | Approved | 8464.25 | 175615.23 | 189969.77 | 194489.14 | 15-06-2021 | 004 | Sidewalk, concrete road base | 2021-06-15 13:40 | 2021-06-16 05:12 | 98
637561 | EXPANSION WORK FOR 75 NIAGARA ST | St. Catharines | CSCP | Approved | 3021.63 | 175615.23 | 189969.77 | 194489.14 | 09-06-2021 | 003 | Water Conflicts - Repairs | 2021-06-09 09:43 | 2021-06-11 05:11 | 98
637561 | EXPANSION WORK FOR 75 NIAGARA ST | St. Catharines | CSCP | Approved | 1639.06 | 175615.23 | 189969.77 | 194489.14 | 09-06-2021 | 002 | Water Conflicts | 2021-06-09 09:43 | 2021-06-11 05:11 | 98
637561 | EXPANSION WORK FOR 75 NIAGARA ST | St. Catharines | CSCP | Approved | 1229.6 | 175615.23 | 189969.77 | 194489.14 | 09-06-2021 | 001 | Bell Conflicts | 2021-06-09 09:43 | 2021-06-11 05:11 | 98
635338 | BEXHILL REBUILD | Mississauga | PLNC | Not Approved | 5460 | 386249.82 | 386249.82 | 352998.82 | 16-12-2020 | 001 | Breakout and removal of concrete at 8 pole locations - included in the WBS. RFC rejected | 2020-12-16 15:53 | 2020-12-22 09:06 | 99
635339 | MEADOW WOOD RD REBUILD | Mississauga | PLNC | Approved | 6640.29 | 1135276.07 | 959122.84 | 1250819.07 | 19-08-2021 | 002 | Replacement of an additional transformer | 2021-08-19 11:07 | 2022-03-22 03:27 | 99
635339 | MEADOW WOOD RD REBUILD | Mississauga | PLNC | Approved | -182793.52 | 1135276.07 | 959122.84 | 1250819.07 | 23-07-2021 | 001 | Removal of 1300 hours from original estimate | 2021-07-22 10:45 | 2021-09-28 14:47 | 99
634900 | 634900 - OH AND UG RELOCATION AT SIMMONS ST, VAUGHAN | Markham | CSCP | Approved | -75017.07 | 630630.38 | 555613.31 | 615956.46 | 10-01-2022 | 001 | Originally external moved to internal | 2022-01-10 15:13 | 2022-01-10 20:34 | 98
639734 | 18 CP - OH REBUILD - OGDEN AVE PHASE 1 | Mississauga | PLNC | Approved | 20547.47 | 468802.35 | 489349.82 | 563791.11 | 13-09-2022 | 101 | For the following reasons: defective switch, shale, bedrock, hydrovac, extra work | 2022-08-30 11:46 | 2022-09-13 21:35 | 95
639736 | OH REBUILD - MEREDITH AVE PH2 | Mississauga | PLNC | Approved | 6944.08 | 214312.66 | 234054.95 | 248164.47 | 09-11-2021 | 101 | Three power interruption were scheduled, but Control Room was unable to issue a permit in a timely manner | 2021-11-08 21:54 | 2021-11-19 15:33 | 99
639736 | OH REBUILD - MEREDITH AVE PH2 | Mississauga | PLNC | Approved | 9388.21 | 214312.66 | 234054.95 | 248164.47 | 19-01-2022 | 103 | extra hydrovac scope, hydrovac pole down to 7 feet deep & jackhammered 6 feet. Nov 16 - Pole support for extra depth set. 6' of sh | 2021-12-08 12:23 | 2022-01-24 23:37 | 99
639736 | OH REBUILD - MEREDITH AVE PH2 | Mississauga | PLNC | Approved | 3410 | 214312.66 | 234054.95 | 248164.47 | 07-12-2021 | 102 | Additional hydrovac due to ground conditions on poles P01, P05, P14, P15, P16, P18 and P19. (PO 405790 OS) | 2021-12-02 14:00 | 2021-12-14 14:10 | 99
639011 | EMERGING OH INSULATOR REPLACMENT 2022 - LAKE M2 | Hamilton | PLNC | Approved | 18752.83 | 66470.62 | 85223.45 | 111624.75 | 11-01-2023 | 001 | Operating delayes & OT to accomodate customers | 2022-12-06 08:50 | 2023-01-12 19:16 | 92
638606 | 638606 - TRANSFORMER REPLACEMENT 2021 - BATCH 7 | Markham | PLNC | Approved | -15056 | 273434.34 | 258378.34 | 236335.86 | 02-12-2021 | 001 | Removal of 2 TX units as they currently have no backup supply available to allow for replacement | 2021-12-02 15:34 | 2022-07-06 16:19 | 99
640494 | 2021 DA- AIRPORT RD S OF WILLIAMS PKWY, 1 | Brampton | PLNC | Approved | 16113.6 | 103160.37 | 119273.97 | 69880.26 | 21-06-2021 | 001 | Internal to contractor | 2021-06-21 16:57 | 2021-09-27 21:12 | 99
638586 | 638586 - POLE REPLACEMENT 2021 - BATCH 14 | Markham | PLNC | Approved | -18160 | 35765.74 | 17605.74 | 16739.06 | 11-05-2021 | 001 | Pole removed from batch, labour overestimated, tree trimming not required | 2021-05-11 15:36 | 2021-09-27 20:44 | 99
638585 | 638585 - POLE REPLACEMENT 2021 - BATCH 13 | Markham | PLNC | Approved | 3266.2 | 54214.03 | 57480.23 | 45196.25 | 20-05-2021 | 001 | Additional OT hours for weekend installation | 2021-05-17 15:23 | 2021-09-10 15:16 | 99
638584 | 638584 - 2021 POLE RENEWAL - BATCH 12 - 6 POLES | Markham | PLNC | Approved | -16000 | 81236.96 | 65236.96 | 64774.44 | 29-06-2021 | 001 | Labour overestimated and not as much hydro vaccing required | 2021-06-28 10:09 | 2021-09-27 20:44 | 99
638580 | 638580 - POLE REPLACEMENT 2021 - BATCH 8 | Markham | PLNC | Approved | -17598.71 | 308349.94 | 290751.23 | 285515.87 | 16-03-2021 | 001 | Remove 1 pole, anchor, transformer as they're unnecessary | 2021-03-15 14:39 | 2021-09-27 20:42 | 99
639751 | 1 JARVIS - LINE RELOCATION | Hamilton | CSCP | Approved | -8603.1 | 176098.58 | 167495.48 | 153500.22 | 22-07-2021 | 001 | Efficiencies | 2021-07-14 09:36 | 2021-09-27 21:09 | 99
638968 | AUTOMATE SWITCH RENEWAL - HAMILTON 2021, 4 | Hamilton | PLNC | Approved | 30946.7 | 319462.49 | 363415.38 | 379462.21 | 16-06-2021 | 002 | P&C Hours | 2021-06-16 10:29 | 2021-09-27 20:54 | 99
638968 | AUTOMATE SWITCH RENEWAL - HAMILTON 2021, 4 | Hamilton | PLNC | Approved | 13907.9 | 319462.49 | 363415.38 | 379462.21 | 05-05-2021 | 001 | Rock and Scope | 2021-04-28 08:34 | 2021-09-27 20:53 | 99
638968 | AUTOMATE SWITCH RENEWAL - HAMILTON 2021, 4 | Hamilton | PLNC | Approved | -901.71 | 319462.49 | 363415.38 | 379462.21 | 05-08-2021 | 003 | Efficiencies | 2021-07-14 09:34 | 2021-09-27 20:55 | 99
638987 | 638987 - POLE REBUILD 2021 - HUNTINGTON RD FROM RUTHERFORD RD TO MAJOR MACKENZIE DR | Markham | PLNC | Approved | 65035.57 | 377645.84 | 442681.41 | 482952.46 | 29-12-2021 | C001 | Outage cancellation and logistic issues | 2021-12-08 16:58 | 2021-12-30 06:07 | 99
639551 | 6CP - 2022 POLE RENEWAL - QEW-NORTH SHERIDAN WAY MINI OH REBUILD | Mississauga | PLNC | Pending | 0 | 287775.65 | 287775.65 | 495823.47 | Pending with Design | 001 | YL31051 was proposed for transfer, an old switch with no parts available for transfer to new pole. New switch had to be installed. | 2022-10-06 17:49 | 2022-10-07 05:05 | 98
638673 | 638673 - YONGE ST & CATHERINE AVE | Markham | CSCP | Approved | 12333 | 249934.03 | 262267.03 | 265614.42 | 25-11-2021 | 001 | Addiitonal mob and de-mob costs due to sheduling issues with Transpower | 2021-12-01 12:54 | 2022-07-06 16:13 | 99
638951 | CARLTON M10 RELIABILITY CONCERNS | St. Catharines | PLNC | Approved | 8128.28 | 112602.15 | 120730.43 | 144157.61 | 10-02-2021 | 001 | Labour Overage | 2022-02-09 14:28 | 2022-02-11 16:25 | 99
634021 | 634021 - ICI NEW COMMERCIAL SERVICE/ 1 PINE VALLEY DR | Markham | ICIL | Approved | 0 | 71214.73 | 71214.73 | 63834.16 | 04-11-2020 | RFC001 | Updated drawings with a new pole number | 2020-11-06 11:33 | 2020-12-21 17:06 | 84
638658 | COSTCO ST.CATHARINES - 3 NORTH SERVICE RD | St. Catharines | ICIL | Not Approved | 0 | 161567.76 | 167745.65 | 265615.94 | 26-10-2021 | 002 | Labour Overages - Scope Changes | 2021-06-08 09:59 | 2021-10-27 19:20 | 92
638658 | COSTCO ST.CATHARINES - 3 NORTH SERVICE RD | St. Catharines | ICIL | Approved | 6177.89 | 161567.76 | 167745.65 | 265615.94 | 22-01-2021 | 001 | Civil Scope increase | 2021-01-22 15:26 | 2021-01-26 02:46 | 92
639849 | 7850 HERITAGE RD/BRA/UP00103588/4.5 MVA C.O. TX'S | Brampton | ICIL | Approved | 0 | 50902.39 | 50902.39 | 43945.37 | 21-05-2021 | 001 | Revised Drawing | 2021-05-21 15:07 | 2021-09-27 21:11 | 95
640520 | 640520 - 2021 LEFT-BEHIND - M37 CABLE REPLACEMENTS, 4 SEGMENTS | Markham | PLNC | Approved | 33419 | 341028.6 | 374447.6 | 342396.94 | 26-07-2021 | 001 | Additional 5 days of Transpower work due to change in method of excavation from direction drill to open-cut for approx 40m | 2021-07-26 11:59 | 2021-07-26 16:05 | 99
640201 | AUTO SWITCH INSTALLS - BUNTING & CARLTON TS FEEDERS, 3 | St. Catharines | PLNC | Approved | 1657.5 | 183630.65 | 185288.15 | 251869.1 | 22-09-2021 | 001 | Material Addition | 2021-09-22 15:08 | 2021-09-22 19:34 | 98
638967 | MAUNAL SWITCH RENEWAL - HAMILTON 2021 - 2 | Hamilton | PLNC | Approved | -25287.4 | 73767.12 | 48479.72 | 53497.16 | 27-08-2021 | 001 | Scope Change | 2021-07-15 14:45 | 2021-09-27 20:57 | 99
640663 | 640663 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.2 | Markham | CSCP | Approved | 8674 | 1529061.01 | 1556638.48 | 1360618.68 | 14-06-2022 | 101 | Temporarily relocated streetlight bus to OH to clear pole hole conflicts | 2022-06-09 09:45 | 2022-06-14 14:04 | 92
640663 | 640663 - CUSTOMER INITIATED EXPANSION-RICHMOND HILL, LESLIE ST, PHASE 3.2 | Markham | CSCP | Approved | 18903.47 | 1529061.01 | 1556638.48 | 1360618.68 | 10-08-2022 | 102 | Extra work required to carry wire, and relocate transformer | 2022-08-17 12:54 | 2022-08-18 05:05 | 92
638668 | MOHAWK & UPPER JAMES SWITCH, 1 | Hamilton | PLNC | Approved | -10615.17 | 787631.9 | 777016.73 | 649019.37 | 29-12-2021 | 001 | Reduction | 2021-12-29 10:21 | 2021-12-30 06:07 | 99
632889 | WATERDOWN BAY - PHASE 3 (POND 5) | Hamilton | SUBD | Not Approved | 0 | 1163726.02 | 1163726.02 | 1169088.25 | Pending With Design | 001 | Labour Overages | 2021-06-10 10:56 | 2021-09-28 14:55 | 99
639714 | 90 GLOVER RD EXPANSION | Hamilton | CSCP | Approved | 30910.61 | 589643.33 | 620553.94 | 561999.48 | 02-02-2022 | 001 | Scope Change | 2022-01-20 16:00 | 2022-02-03 14:07 | 95
640634 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 3, 6 | St. Catharines | PLNC | Approved | 4703.52 | 477031.43 | 495386.95 | 468131.8 | 12-11-2021 | 002 | Scope Change | 2021-11-04 15:17 | 2021-11-16 15:03 | 99
640634 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 3, 6 | St. Catharines | PLNC | Approved | 10337 | 477031.43 | 495386.95 | 468131.8 | 23-09-2021 | 001 | Control delays, changes to design | 2021-09-23 12:22 | 2021-11-04 19:09 | 99
640634 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 3, 6 | St. Catharines | PLNC | Approved | 3315 | 477031.43 | 495386.95 | 468131.8 | 22-09-2021 | 101 | Materials Addition | 2021-09-22 15:56 | 2021-11-04 19:09 | 99
635159 | 635159 - MTO- 407 AND YORK DURHAM LINE - POLE REPLACEMENTS - MARKHAM | Markham | PLNC | Approved | 18000 | 75617.85 | 93617.85 | 102802.97 | 27-04-2021 | 001 | Difficulty securing peronnel between vacation and restrictions due to covid. Restrictions also extended timeline | 2021-04-27 11:48 | 2021-09-27 17:40 | 99
638579 | 638579 - POLE REPLACEMENT 2021 - BATCH 7 | Markham | PLNC | Approved | 16000 | 59583.04 | 75583.04 | 76000.17 | 11-05-2021 | 001 | Material missed in estimate. Inclement weather and re-scheduling increased labour cost | 2021-05-11 15:29 | 2021-09-27 20:41 | 99
638578 | 638578 - POLE REPLACEMENT 2021 - BATCH 6 | Markham | PLNC | Approved | 44000 | 142038.99 | 85160.65 | 91813.56 | 11-05-2021 | 002 | OT not alloted in estimate, vault room switches and tx required to be replaced (UG resources required) | 2021-05-11 15:23 | 2021-09-27 20:40 | 99
638578 | 638578 - POLE REPLACEMENT 2021 - BATCH 6 | Markham | PLNC | Approved | -100878.34 | 142038.99 | 85160.65 | 91813.56 | 27-01-2021 | 001 | 6 of 8 poles in good condition - doesn't require change - taken out of batch | 2021-01-27 15:36 | 2021-09-27 20:40 | 99
633234 | 57 STRATHCONA DR - POLE REPLACEMENT | St. Catharines | PLNC | Approved | 451.43 |  | 451.43 | 13799.72 | 16-11-2021 | 001 | Travel Time | 2021-09-20 01:00 | 2021-11-16 19:45 | 99
636776 | HULRT METROLINX - OMSF EXPANSION PROJECT - KENNEDY & 407 | Mississauga | TRNS | Approved | 85418.98 | 7011477.46 | 7096896.44 | 6133677.68 | 13-12-2021 | 101 | Contractor additional costs | 2021-12-13 12:37 | 2021-12-13 18:04 | 98
639069 | 639069 - PHASE 4-UG. FOR DC 3. VIA RENZO DR AND PERFORMANCE DR, RICHMOND HILL | Markham | CSCP | Approved | 36694.22 | 1599828.18 | 1636522.4 | 1627415.35 | 23/11/2022 | 001 | Extra cost associated with poles not installed on Leslie, extra time to restore interlock, remob costs | 2022-11-29 11:46 | 2022-11-29 17:04 | 95
638365 | 2021 TX RENEWAL-GRID G3-10 TX | Brampton | PLNC | Approved | -10000 | 182943.46 | 172943.46 | 169941.6 | 28-09-2021 | 001 | Internal to External | 2021-08-11 09:26 | 2021-09-28 20:19 | 99
636797 | MONTEVIDEO & TREVISO PH-1 CABLE REPLACEMENT | Mississauga | PLNC | Approved | 573.3 | 2535761.75 | 2567572.55 | 2605058.4 | 27-10-2021 | 102 | The cost for security watch at 2700 Aquitaine for the power outage $546.00 plus 5% mark up= $573.30 | 2021-08-31 16:39 | 2021-11-02 00:26 | 99
636797 | MONTEVIDEO & TREVISO PH-1 CABLE REPLACEMENT | Mississauga | PLNC | Approved | 31237.5 | 2535761.75 | 2567572.55 | 2605058.4 | 03-08-2021 | 101 | Guild Electric held the traffic pole at the corner of Montevideo and Battleford so TP could install trench | 2021-06-29 16:49 | 2021-08-03 22:51 | 99
639022 | BALDWIN CARRY-OVER WORK 2021 | Hamilton | PLNC | Approved | 22260.17 | 505748.73 | 554071.86 | 609366.87 | 22-12-2021 | 003 | Generator | 2021-11-30 12:27 | 2021-12-22 16:49 | 99
639022 | BALDWIN CARRY-OVER WORK 2021 | Hamilton | PLNC | Approved | 5782.14 | 505748.73 | 554071.86 | 609366.87 | 20-01-2022 | 005 | Scope Change | 2022-01-20 13:11 | 2022-01-20 19:21 | 99
639022 | BALDWIN CARRY-OVER WORK 2021 | Hamilton | PLNC | Approved | 5051.76 | 505748.73 | 554071.86 | 609366.87 | 22-12-2021 | 002 | Scope Change | 2021-11-25 14:15 | 2021-12-22 16:49 | 99
639022 | BALDWIN CARRY-OVER WORK 2021 | Hamilton | PLNC | Approved | 5967.5 | 505748.73 | 554071.86 | 609366.87 | 12-11-2021 | 001 | Tree Trimming | 2021-11-02 15:35 | 2021-11-16 14:56 | 99
639022 | BALDWIN CARRY-OVER WORK 2021 | Hamilton | PLNC | Approved | 9261.56 | 505748.73 | 554071.86 | 609366.87 | 22-12-2021 | 004 | Temp Tx during Outage | 2021-12-06 15:00 | 2021-12-22 16:49 | 99
636624 | ELMA ST - 2021 CABLE REPLACEMENT | St. Catharines | PLNC | Approved | -50261.85 | 906775.12 | 932034.5 | 962765.1 | 16-11-2021 | 001 | Reduction RFC | 2021-08-24 11:51 | 2021-11-16 20:33 | 99
636624 | ELMA ST - 2021 CABLE REPLACEMENT | St. Catharines | PLNC | Approved | 75521.23 | 906775.12 | 932034.5 | 962765.1 | 03-02-2022 | 002 | Labour Hours | 2022-01-20 10:00 | 2022-02-09 13:47 | 99
636626 | BERKLEY CABLE REPLACEMENT 2022 | St. Catharines | PLNC | Approved | 20271.62 | 1075687.09 | 1210731.5 | 1324393.97 | 18-02-2022 | 001 | BOM Revision - Foundations | 2022-02-18 08:00 | 2022-07-05 19:36 | 92
636626 | BERKLEY CABLE REPLACEMENT 2022 | St. Catharines | PLNC | Approved | 11351.64 | 1075687.09 | 1210731.5 | 1324393.97 | 18-02-2022 | 002 | BOM Revision - Inlines Added | 2022-02-18 08:00 | 2022-07-05 19:36 | 92
636626 | BERKLEY CABLE REPLACEMENT 2022 | St. Catharines | PLNC | Approved | 20904.04 | 1075687.09 | 1210731.5 | 1324393.97 | 04-04-2022 | 101 | Watermain Issues | 2022-03-25 10:00 | 2022-05-06 15:07 | 92
636626 | BERKLEY CABLE REPLACEMENT 2022 | St. Catharines | PLNC | Approved | 7910.46 | 1075687.09 | 1210731.5 | 1324393.97 | 12-08-2022 | 104 | Generator | 2022-08-03 09:00 | 2022-08-12 19:23 | 92
636626 | BERKLEY CABLE REPLACEMENT 2022 | St. Catharines | PLNC | Approved | 43837.86 | 1075687.09 | 1210731.5 | 1324393.97 | 05-07-2022 | 103 | Extra Drilling Reqd | 2022-05-18 11:00 | 2022-07-05 19:35 | 92
636626 | BERKLEY CABLE REPLACEMENT 2022 | St. Catharines | PLNC | Approved | 30768.79 | 1075687.09 | 1210731.5 | 1324393.97 | 17-05-2022 | 102 | Additional Vac Truck | 2022-05-05 11:00 | 2022-06-08 18:07 | 92
638395 | 638395 - SWITCH REPLACEMENT - A03SL2000, A03SL2003 AND A02SL2003 | Markham | PLNC | Approved | -19089.76 | 44592.9 | 25503.14 | 22462.95 | 12-05-2021 | 001 | Unnecessary to replace switch, reduction in Lines labour hours, equipment and material | 2021-05-12 15:47 | 2021-09-27 20:27 | 99
637218 | POLE LINE ENCROACHMENT- #8406 CREDITVIEW RD - | Brampton | PLNC | Approved | 22000 | 193000.65 | 115000.65 | 126963.23 | 05-05-2021 | 001 | Design Change and new shedule | 2021-05-05 11:54 | 2021-09-27 20:15 | 99
637218 | POLE LINE ENCROACHMENT- #8406 CREDITVIEW RD - | Brampton | PLNC | Approved | -100000 | 193000.65 | 115000.65 | 126963.23 | 01-10-2021 | 002 | Revised Scope | 2021-08-11 14:33 | 2021-10-01 19:52 | 99
636625 | WEIDEN CABLE REPLACEMENT | St. Catharines | PLNC | Approved | 10033.11 | 238779.31 | 269116.17 | 307927.71 | 31-05-2021 | 001 | Scope Changes - New Dwgs | 2021-05-31 10:30 | 2021-11-29 17:44 | 99
636625 | WEIDEN CABLE REPLACEMENT | St. Catharines | PLNC | Approved | -5245 | 238779.31 | 269116.17 | 307927.71 | 23-08-2021 | 003 | Generator run time reduction | 2021-08-23 14:07 | 2021-09-27 20:06 | 99
636625 | WEIDEN CABLE REPLACEMENT | St. Catharines | PLNC | Approved | 20263.47 | 238779.31 | 269116.17 | 307927.71 | 29-10-2021 | 004 | Labour Overages | 2021-10-05 14:28 | 2021-11-01 12:42 | 99
636625 | WEIDEN CABLE REPLACEMENT | St. Catharines | PLNC | Approved | 5285.28 | 238779.31 | 269116.17 | 307927.71 | 03-08-2021 | 002 | Scope Change | 2021-08-03 15:50 | 2021-09-27 20:06 | 99
450714 | 1713 STEELES AVE E - PERMANENT SERVICE | Brampton | ICIL | Approved | 10242 | 77432.98 | 87674.98 | 93067.86 | 19-08-2021 | 001 | Additional Lines hours | 2021-05-06 07:42 | 2021-10-21 13:38 | 99
642226 | 2022-44KV D/A SWITCH INSTALLATION(44-325) - ITD2022-19 | Brampton | PLNC | Approved | -28969.76 | 191232.83 | 162263.07 | 147925 | 14-06-2022 | 001 | Project estimated internally but now contracted out to A&W for completion. Design to quantify change in costs based on A&W est. | 2022-05-19 11:06 | 2022-06-29 12:51 | 98
638324 | 638324 - 8811 HUNTINGTON RD/ VAU/ NS/ 3PH PAD | Markham | ICIL | Approved | 11795.1 | 105278.87 | 117073.97 | 133444.53 | 24-05-2022 | 001 | To cover the recover of the cable and re-installation | 2022-05-27 10:31 | 2022-07-06 16:13 | 95
639525 | 2021 EMERGING OH - EAST 16TH - BELL POLES | Hamilton | PLNC | Approved | 11039.81 | 75421.37 | 86461.18 | 26084.92 | 05-05-2021 | 001 | Rock Anchor & Snow Removal | 2021-03-10 14:56 | 2021-05-05 14:14 | 99
640772 | 2021 - MH 39A - MANHOLE ROOF REPLACEMENT | Hamilton | PLNC | Approved | -49820.29 | 208382.92 | 158562.63 | 191440.49 | 30-12-2021 | 001 | Reduction RFC | 2021-12-29 10:01 | 2021-12-30 15:16 | 99
638427 | 432 HIGHLAND RD -HIGHLAND PACKERS/HAM/UP00056773/3PHPAD | Hamilton | ICIL | Approved | 5739.3 | 144667.02 | 150406.32 | 141617.13 | 06-05-2021 | 001 | Design Change | 2021-05-06 12:22 | 2021-05-11 16:34 | 99
640280 | 5 HAMILTON ST N / HAM / NS | Hamilton | ICIL | Pending | 0 | 119045.71 | 119045.71 | 182936.28 | Pending With Design | 001 | Missing OH hours | 2022-10-27 09:56 | 2022-10-27 14:04 | 84
638297 | 638297 - DISTRIBUTION AUTOMATION 2021 - TBD - VAUGHAN, 1 | Markham | PLNC | Approved | -17940.99 | 165024.57 | 147083.58 | 155961.8 | 16-06-2021 | 001 | Contracted out to K-Line | 2021-06-16 17:02 | 2021-09-27 20:21 | 99
638424 | 237 ARVIN AVE - TK PLASTICS LTD/HAM/UP00070769 /3PHPAD | Hamilton | ICIL | Approved | 38252.58 | 102458.78 | 140711.36 | 128710.29 | 05-08-2021 | 001 | Customer requested Tx Change | 2021-07-26 09:16 | 2021-09-27 20:28 | 99
634365 | WATERDOWN 3RD FEEDER - Deep Dive | Hamilton | PLNC | Not Approved | 10295 | 2170455.76 | 2328847.76 | 2119956.7 | 11-11-2020 | 002 | Scope Change | 2020-11-11 10:30 | 2021-04-27 15:04 | 99
634365 | WATERDOWN 3RD FEEDER - Deep Dive | Hamilton | PLNC | Approved | 29271 | 2170455.76 | 2328847.76 | 2119956.7 | 22-03-2021 | 006 | Scope Change | 2021-02-05 09:53 | 2021-04-27 15:04 | 99
634365 | WATERDOWN 3RD FEEDER - Deep Dive | Hamilton | PLNC | Approved | 10295 | 2170455.76 | 2328847.76 | 2119956.7 | 28-01-2021 | 003 | Scope Change | 2020-11-11 14:31 | 2021-04-27 15:04 | 99
634365 | WATERDOWN 3RD FEEDER - Deep Dive | Hamilton | PLNC | Approved | 66741 | 2170455.76 | 2328847.76 | 2119956.7 | 17-01-2021 | 004 | OT | 2020-12-21 09:14 | 2021-04-27 15:04 | 99
634365 | WATERDOWN 3RD FEEDER - Deep Dive | Hamilton | PLNC | Approved | 7381 | 2170455.76 | 2328847.76 | 2119956.7 | 25-02-2021 | 007 | Scope Change | 2021-02-09 13:29 | 2021-04-27 15:04 | 99
634365 | WATERDOWN 3RD FEEDER - Deep Dive | Hamilton | PLNC | Approved | 36410 | 2170455.76 | 2328847.76 | 2119956.7 | 28-01-2021 | 005 | Scope Change | 2021-01-19 15:02 | 2021-04-27 15:04 | 99
634365 | WATERDOWN 3RD FEEDER - Deep Dive | Hamilton | PLNC | Approved | 8294 | 2170455.76 | 2328847.76 | 2119956.7 | 10-11-2020 | 001 | Additional Subcontractor Costs | 2020-10-16 12:37 | 2021-04-27 15:04 | 99
638323 | ABERDEEN #4 O/H -BAY TO MTN ACCESS | Hamilton | PLNC | Approved | -312057.7 | 963748.7 | 658514 | 774592.06 | 28-07-2021 | 003 | Efficiencies | 2021-06-08 14:01 | 2021-09-27 20:24 | 99
638323 | ABERDEEN #4 O/H -BAY TO MTN ACCESS | Hamilton | PLNC | Approved | 6823 | 963748.7 | 658514 | 774592.06 | 22-03-2021 | 001 | K-Line to Assist | 2021-02-23 11:33 | 2021-03-23 13:53 | 99
638587 | 638587 - POLE REPLACEMENT 2021 - BATCH 15 | Markham | PLNC | Approved | 0 | 168351.18 | 168351.18 | 118754.42 | 17-05-2021 | 001 | Change of nomenclature on 2 poles | 2021-05-14 10:42 | 2021-09-27 20:45 | 99
640497 | ROXBOROUGH PARK PHASE 2 - SUBD EDS | Hamilton | SUBD | Approved | 0 | 2010170.31 | 2010170.31 | 1162378.27 | 15-09-2022 | 001 | Drawing Revision | 2022-09-13 09:34 | 2022-09-15 16:42 | 84
638569 | 2021 MINI-POLE REBUILDS - REBUILD 12 CLUSTER ID 14 - 5 | Brampton | PLNC | Approved | 0 | 282853.45 | 282853.45 | 324535.06 | 27-10-2021 | 101 | Revised start/finishdate | 2021-09-07 15:48 | 2021-11-16 17:52 | 99
639656 | 56 DUNDAS ST E PRIVATE LINE BURIAL | Hamilton | CSCP | Approved | -1407.95 | 69651.97 | 68244.02 | 65545.36 | 06-05-2021 | 001 | Efficiencies | 2021-05-06 11:31 | 2021-09-27 21:03 | 99
639581 | UPPER JAMES & LINC PMH SWITCH, 1 | Hamilton | PLNC | Approved | -9368.85 | 613926.09 | 604557.24 | 605600.73 | 29-12-2021 | 001 | Reduction RFC | 2021-12-29 10:51 | 2021-12-30 06:07 | 99
639748 | 2021 4KV CONV PH3E - (ETOBICOKE DR) | Brampton | PLNC | Approved | 0 | 156969.74 | 156969.74 | 148783.51 | 08-08-2021 | 001 | revised completion date | 2021-08-05 08:51 | 2021-09-27 21:05 | 99
638189 | 638189 - TRANSFORMER REPLACEMENT 2021 - BATCH 4 | Markham | PLNC | Approved | 16927 | 110506.78 | 127433.78 | 142224.77 | 29-01-2021 | 001 | Added 2 extra padmounted transformers in the batch. 40 additional labour hours added | 2021-01-29 11:51 | 2021-01-30 08:45 | 99
639007 | INSULATOR RENEWAL - HAMILTON 2021 - PHASE 1 | Hamilton | PLNC | Approved | 18678.98 | 145084.69 | 163763.67 | 149176.6 | 15-09-2021 | 001 | Labour Overage | 2021-08-27 14:00 | 2021-09-27 21:01 | 99
638553 | TX RENEWAL PROGRAM 2021 - PHASE 11 - SCH SOUTH 2 - 7 | St. Catharines | PLNC | Approved | -24511.12 | 173328.44 | 148817.32 | 120557.44 | 22-11-2022 | 001 | Reduction in scope, remove 1 Tx due to customer | 2022-10-24 14:00 | 2022-11-29 15:47 | 92
638645 | AUTO SWITCH INSTALLS - GLENDALE TS FEEDERS, 6 | St. Catharines | PLNC | Approved | 1000.98 | 469958.33 | 479841.03 | 444418.39 | 03-09-2021 | 002 | Budget Overruns | 2021-08-30 09:27 | 2021-09-27 20:48 | 99
638645 | AUTO SWITCH INSTALLS - GLENDALE TS FEEDERS, 6 | St. Catharines | PLNC | Approved | 8881.72 | 469958.33 | 479841.03 | 444418.39 | 10-08-2021 | 001 | Insulator Changes due to Safety | 2021-07-14 09:59 | 2021-09-27 20:47 | 99
638298 | 638298 - DISTRIBUTION AUTOMATION 2021 - NEW - VAUGHAN, 1 | Markham | PLNC | Approved | 12999.62 | 116432.68 | 129432.3 | 134517.97 | 16-06-2021 | 001 | Contracted out to K-Line | 2021-06-16 17:23 | 2021-09-27 20:22 | 99
638568 | 2021 MINI-POLE REBUILDS - REBUILD 9 CLUSTER ID 78 - 5 | Brampton | PLNC | Approved | 0 | 215705.52 | 215705.52 | 207753.11 | 27-10-2021 | 101 | Revised start/finish date | 2021-09-07 15:47 | 2021-10-27 22:00 | 99
638572 | 638572 - POLE REPLACEMENT 2021 - BATCH 1 | Markham | PLNC | Approved | 0 | 344010.8 | 264718.8 | 240576.64 | 31-12-2020 | 001 | Minor changes to drawing based on GIS comments | 2020-12-30 01:00 | 2021-03-19 15:48 | 99
638572 | 638572 - POLE REPLACEMENT 2021 - BATCH 1 | Markham | PLNC | Approved | -34730.64 | 344010.8 | 264718.8 | 240576.64 | 11-05-2021 | 003 | Removal of labour for 6 concrete poles removed | 2021-05-05 17:21 | 2021-09-27 20:37 | 99
638572 | 638572 - POLE REPLACEMENT 2021 - BATCH 1 | Markham | PLNC | Approved | -44561.36 | 344010.8 | 264718.8 | 240576.64 | 27-01-2021 | 002 | Removal of 6 concrete poles - not Alectra owned | 2021-01-27 01:00 | 2021-01-27 21:45 | 99
638259 | 638259 - SWITCHGEAR REPLACEMENT 2021 - BATCH 6 | Markham | PLNC | Approved | -79356.79 | 742948.49 | 663591.7 | 509487.01 | 02-12-2020 | 001 | Removal of one switchgear as it was replaced in 2020 | 2020-12-02 10:40 | 2020-12-21 17:11 | 99
639086 | DOWN GUYS WIRES AND ANCHORS RELOCATION - HUMBERWEST PKWY | Brampton | CSCP | Not Approved | 0 | 13148.11 | 13148.11 | 28719.92 | Pending with Design | 001 | Locates redo | 2022-01-20 09:50 | 2022-03-15 21:32 | 92
638674 | 638674 - POLE REPLACEMENT 2021 - REPLACE P930 & P932 - HWY 7 & HWY 427 | Markham | PLNC | Approved | 64014.73 | 118800.39 | 182815.12 | 167896.31 | 08-08-2021 | 001 | Work to be executed by K-Line rather than the internal Lines crew as per PDG | 2021-08-04 13:08 | 2021-09-27 20:59 | 99
640496 | 2021-44KV D/A SWITCH REPLACEMENT(44-137) - ITD2021-43, 1 | Brampton | PLNC | Approved | 23268.62 | 161966.28 | 185234.9 | 227022.27 | 21-06-2021 | 001 | Internal to contractor | 2021-06-21 16:56 | 2021-09-27 21:12 | 99
637710 | V1061 RELOCATON | Hamilton | CSCP | Approved | 5762.44 | 179380.7 | 182201.3 | 177247.81 | 16-04-2021 | 001 | Project Delays | 2021-04-12 11:10 | 2021-09-27 20:19 | 99
637710 | V1061 RELOCATON | Hamilton | CSCP | Approved | -2941.84 | 179380.7 | 182201.3 | 177247.81 | 11-05-2021 | 002 | Efficiencies | 2021-05-06 14:02 | 2021-09-27 20:20 | 99
640633 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 2, 5 | St. Catharines | PLNC | Approved | 0 | 437738.72 | 451355.72 | 384075.34 | 17-09-2021 | 002 | Drawing Change | 2021-09-17 15:34 | 2021-09-21 05:11 | 99
640633 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 2, 5 | St. Catharines | PLNC | Approved | 10302 | 437738.72 | 451355.72 | 384075.34 | 16-11-2021 | 101 | Extras | 2021-10-20 08:57 | 2021-11-16 17:30 | 99
640633 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 2, 5 | St. Catharines | PLNC | Approved | 3315 | 437738.72 | 451355.72 | 384075.34 | 22-09-2021 | 001 | Material Changes | 2021-09-22 15:34 | 2021-09-22 20:04 | 99
640633 | AUTO SWITCH INSTALLS - CARLTON TS - PHASE 2, 5 | St. Catharines | PLNC | Approved | 0 | 437738.72 | 451355.72 | 384075.34 | 17-09-2021 | 003 | Drawing Change | 2021-09-17 15:35 | 2021-09-21 05:11 | 99
631935 | 2021 - EMERGING UG - 2 POLES & CABLE REPLACEMENT | St. Catharines | PLNC | Approved | -22022.61 | 82151.11 | 60128.5 | 49041.7 | 05-08-2021 | 001 | Efficiencies | 2021-07-22 09:58 | 2021-09-27 16:04 | 99
640269 | 640269 - ANCHOR CONFLICTS - BAYVIEW AVE & VANDORF SDRD | Markham | CSCP | Approved | -7100 | 22035.6 | 14935.6 | 15142.9 | 28-05-2021 | 001 | Hydro vac estimate higher due to remote location, not required. labour estimate over | 2021-05-18 12:19 | 2021-06-16 20:37 | 99
639566 | 639566 - LESLIE ST. DEFICIENCIES | Markham | CSCP | Approved | 10732.18 | 55886.05 | 66618.23 | 64610.08 | 24-06-2021 | 001 | Additional anchor rod extensions and grounding repairs | 2021-06-24 14:28 | 2021-11-16 06:08 | 95
638577 | 638577 - POLE REPLACEMENT 2021 - BATCH 5 | Markham | PLNC | Approved | -15679.71 | 216393 | 200713.29 | 187901.52 | 18-02-2021 | 001 | Remove P42606 from batch - in good condition | 2021-02-18 17:27 | 2021-03-19 15:44 | 99
638952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 1) | Hamilton | PLNC | Approved | 28710.31 | 1764106.06 | 1973542.16 | 2241077.84 | 19-01-2021 | 003 | Scope Change, Conflicts | 2021-11-04 14:51 | 2022-01-19 19:06 | 98
638952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 1) | Hamilton | PLNC | Approved | 0 | 1764106.06 | 1973542.16 | 2241077.84 | 02-12-2021 | 101 | Drawing Revision | 2021-12-02 09:00 | 2021-12-07 06:06 | 98
638952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 1) | Hamilton | PLNC | Approved | 63611.1 | 1764106.06 | 1973542.16 | 2241077.84 | 20-01-2022 | 001 | Scope Change | 2022-01-20 09:00 | 2022-01-24 13:33 | 98
638952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 1) | Hamilton | PLNC | Approved | 33087.6 | 1764106.06 | 1973542.16 | 2241077.84 | 22-12-2021 | 004 | OT | 2021-11-04 14:52 | 2021-12-29 13:42 | 98
638952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 1) | Hamilton | PLNC | Approved | 56662.67 | 1764106.06 | 1973542.16 | 2241077.84 | 19-01-2021 | 005 | Duct Conflicts | 2021-11-22 14:23 | 2022-01-19 19:06 | 98
638952 | STONECHURCH & UPPER PARADISE CABLE REPLACEMENTS (PART 1) | Hamilton | PLNC | Approved | 27364.42 | 1764106.06 | 1973542.16 | 2241077.84 | 22-12-2021 | 002 | Scope Change, Utility Conflicts | 2021-10-21 14:00 | 2022-01-20 13:53 | 98
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 1495 | 980351.14 | 1554201.75 | 1738111.65 | 04-12-2020 | 008 | On site Geotechnical engineer for boulder obstruction removal | 2020-12-04 12:38 | 2020-12-21 17:00 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 4060 | 980351.14 | 1554201.75 | 1738111.65 | 21-05-2021 | 019 | Transpower yearly increase based on 2% civil items on WBS | 2021-05-21 11:37 | 2021-05-21 16:04 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 59063 | 980351.14 | 1554201.75 | 1738111.65 | 28-10-2020 | 005 | Boulder obstruction investigation | 2020-10-28 13:52 | 2020-12-21 17:00 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 5175 | 980351.14 | 1554201.75 | 1738111.65 | 09-02-2021 | 016 | Earth boring cost to remobilize | 2021-02-09 11:25 | 2021-02-10 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 34615 | 980351.14 | 1554201.75 | 1738111.65 | 04-12-2020 | 009 | Earth Boring change from cementitious to cellular grout | 2020-12-04 12:39 | 2020-12-21 17:00 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 3470.94 | 980351.14 | 1554201.75 | 1738111.65 | 22-06-2020 | 002 | Truck relocation and material delay due to covid | 2020-06-22 10:41 | 2020-09-22 19:38 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 35075 | 980351.14 | 1554201.75 | 1738111.65 | 28-10-2020 | 006 | Fabrication of custom shoring for pit to expose boulder obstruction | 2020-10-28 13:54 | 2020-12-21 17:00 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 7820.48 | 980351.14 | 1554201.75 | 1738111.65 | 22-06-2020 | 001 | 3 1/0 splices added as cable not long enough | 2020-06-22 13:37 | 2020-09-22 19:38 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 10273 | 980351.14 | 1554201.75 | 1738111.65 | 03-02-2021 | 011 | K Line overtime | 2021-02-03 16:19 | 2021-02-04 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 8731 | 980351.14 | 1554201.75 | 1738111.65 | 03-02-2021 | 012 | K Line standby costs | 2021-02-03 16:19 | 2021-02-04 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 4886 | 980351.14 | 1554201.75 | 1738111.65 | 03-02-2021 | 013 | K Line yearly increase | 2021-02-03 16:20 | 2021-02-04 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 21014 | 980351.14 | 1554201.75 | 1738111.65 | 03-02-2021 | 014 | Earth boring shoring system | 2021-02-03 16:21 | 2021-02-04 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 13738 | 980351.14 | 1554201.75 | 1738111.65 | 03-02-2021 | 010 | K Line pole support | 2021-02-03 16:18 | 2021-02-04 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 19550 | 980351.14 | 1554201.75 | 1738111.65 | 09-02-2021 | 017 | Earth boring yearly increase | 2021-02-09 11:25 | 2021-02-10 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 3277 | 980351.14 | 1554201.75 | 1738111.65 | 09-02-2021 | 018 | Transpower cost for compaction testing | 2021-02-09 11:26 | 2021-02-10 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 14100.73 | 980351.14 | 1554201.75 | 1738111.65 | 15-10-2020 | 003 | Earth boring required for access pad | 2020-09-25 01:00 | 2020-12-21 17:00 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 23732.46 | 980351.14 | 1554201.75 | 1738111.65 | 15-10-2020 | 004 | Vac trucks required to confirm location of utilities | 2020-09-25 01:00 | 2020-12-21 17:00 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 23705 | 980351.14 | 1554201.75 | 1738111.65 | 09-02-2021 | 015 | Earth boring granular installation | 2021-02-09 11:21 | 2021-02-10 08:46 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 18187 | 980351.14 | 1554201.75 | 1738111.65 | 24-06-2021 | 023 | Transpower additional work to investigate and excavate boulder obstruction | 2021-06-24 14:11 | 2021-06-25 04:38 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 101204 | 980351.14 | 1554201.75 | 1738111.65 | 01-06-2021 | 021 | Additional monitoring during project delay period from July 2020 - Nov 2020 | 2021-06-01 14:28 | 2021-06-02 04:37 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 17579 | 980351.14 | 1554201.75 | 1738111.65 | 21-05-2021 | 025 | Transpower additional admin, consultation and engineering fees due to field changes throughout project | 2021-05-21 11:40 | 2021-05-21 16:04 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 13659 | 980351.14 | 1554201.75 | 1738111.65 | 21-05-2021 | 020 | Transpower additional cost for daylighting and work around Bell structure | 2021-05-21 11:38 | 2021-05-21 16:04 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 24969 | 980351.14 | 1554201.75 | 1738111.65 | 21-05-2021 | 022 | Transpower supply and install additional PVC and FRE ducts due to design change | 2021-05-21 11:39 | 2021-05-21 16:04 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 5000 | 980351.14 | 1554201.75 | 1738111.65 | 21-05-2021 | 024 | Transpower lump sum payment for standby crew due to project delay | 2021-05-21 11:39 | 2021-05-21 16:04 | 99
452753 | 452753 - RER - MX - RELOC - STEELES AVE W - BARRIE LINE (21) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 99471 | 980351.14 | 1554201.75 | 1738111.65 | 28-10-2020 | 007 | Standby costs while boulder got approved (4.5 months) | 2020-10-28 01:00 | 2021-02-03 15:44 | 99
635601 | REBUILD: W 31ST, BTWN ANGELA AVE & LESLIE AVE (HAMILTON) - 9 | Hamilton | PLNC | Approved | 30016.88 | 87517.09 | 117533.97 | 150356.25 | 06-07-2021 | 001 | Materials Re-Added | 2021-07-06 10:51 | 2021-07-06 15:04 | 99
635602 | REBUILD: LESLIE & W 32ND, N OF BENDAMERE (HAMILTON) -18 | Hamilton | PLNC | Approved | 11461.17 | 124584.75 | 136045.92 | 228320.81 | 05-05-2021 | 001 | Scope Increase | 2021-04-13 08:25 | 2021-09-27 17:47 | 99
635603 | REBUILD: W 31ST, N OF BENDAMERE (HAMILTON) - 7 | Hamilton | PLNC | Approved | 41410.58 | 86017.09 | 127427.67 | 150279.73 | 16-06-2021 | 001 | Materials Correction | 2021-06-16 11:17 | 2021-09-27 17:59 | 99
635604 | REBUILD: W 33RD, N OF SANATORIUM (HAMILTON) - 7 | Hamilton | PLNC | Approved | 21173 | 111642.54 | 132815.54 | 153475.93 | 05-07-2021 | 001 | Materials Re-Added to JDE | 2021-07-05 22:25 | 2021-07-06 05:10 | 92
635605 | REBUILD: W 31ST, N OF SANATORIUM (HAMILTON) - 6 | Hamilton | PLNC | Approved | 34268.94 | 121064.6 | 155333.54 | 188794.06 | 06-07-2021 | 001 | Materials Re-Added | 2021-07-06 10:45 | 2021-07-07 05:09 | 99
635607 | REBUILD: ELMWOOD & W 25TH (HAMILTON) - 2 | Hamilton | PLNC | Approved | 2436.93 | 17703.42 | 20140.35 | 21173.22 | 16-06-2021 | 001 | Materials Adjustment | 2021-06-16 11:00 | 2021-09-27 18:00 | 99
635608 | REBUILD: DENLOW & GARTH (HAMILTON) - 3 | Hamilton | PLNC | Approved | 12287.18 | 40688.2 | 52975.38 | 67249.29 | 05-07-2021 | 001 | Materials Re-Added to JDE | 2021-07-05 22:50 | 2021-07-06 05:09 | 99
635609 | REBUILD: AUCHMAR & GARTH (HAMILTON) - 3 | Hamilton | PLNC | Not Approved | 12286.11 | 80157.63 | 80157.63 | 64364.55 | 02-06-2021 | 001 | Materials Corrected - Project Re-Released to K-Line | 2021-06-02 11:14 | 2021-09-27 18:01 | 99
638575 | 638575 - POLE REPLACEMENT 2021 - BATCH 3 | Markham | PLNC | Approved | -48000 | 196314.77 | 148314.77 | 148134.7 | 06-05-2021 | 001 | Labour mixed with another pole batch (638576) in same vicinity, some poles removed, covid increase truck costs | 2021-04-27 15:48 | 2021-05-07 04:12 | 99
633227 | KENILWORTH TS - STATION UPGRADE | Hamilton | STND | Approved | 227868.29 | 1059640.5 | 1287508.79 | 1324793.21 | 11-02-2022 | 001 | Hours Overage | 2022-01-20 10:00 | 2022-02-15 19:39 | 99
640208 | 640208 - 2021 POLE RENEWAL - BATHURST ST - METROLINX CROSSING | Markham | PLNC | Approved | 14473.23 | 324509.45 | 338982.68 | 339609.68 | 12-04-2022 | 001 | Additional time and labour ue to delay in Metrolinx permit | 2022-04-12 16:01 | 2022-04-14 05:34 | 99
639433 | MAPLE AVE / KENILWORTH TERM POLE | Hamilton | CSCP | Approved | -2441.17 | 150655.12 | 148213.95 | 133212.08 | 25-01-2022 | 001 | Reduction RFC | 2022-01-20 10:00 | 2022-01-28 15:22 | 98
640467 | 640467 - 2021 EMERGING UG, M46 MARKLAND ST AND HILLMOUNT RD LOOP SPLIT | Markham | PLNC | Approved | 34065 | 257344.28 | 291409.28 | 296301.27 | 19-01-2022 | 001 | Winter premiums | 2022-01-19 14:57 | 2022-01-25 22:05 | 99
633530 | 4KV CONV PH3C - APARTMENTS | Brampton | PLNC | Approved | 25715.09 | 695427.87 | 885776.78 | 881604.5 | 10-12-2021 | 103 | Extra customer premise | 2021-12-09 15:12 | 2021-12-21 15:41 | 99
633530 | 4KV CONV PH3C - APARTMENTS | Brampton | PLNC | Approved | 164633.82 | 695427.87 | 885776.78 | 881604.5 | 12-10-2021 | 102 | Scope Change - customer civil work | 2021-09-17 14:38 | 2021-10-26 21:18 | 99
633530 | 4KV CONV PH3C - APARTMENTS | Brampton | PLNC | Approved | 0 | 695427.87 | 885776.78 | 881604.5 | 08-08-2021 | 001 | Revised completion date | 2021-08-05 08:50 | 2021-09-21 20:26 | 99
634344 | 634344 - STORM HARDENING 2020 - WOODBINE - RIVIERA TO DENISON | Markham | PLNC | Approved | 31360 | 630883.05 | 1001729.31 | 1042939.15 | 05-01-2021 | 001 | Cost for additional materials ordered that were missed in the ordering process | 2021-01-05 15:14 | 2021-02-26 16:10 | 99
634344 | 634344 - STORM HARDENING 2020 - WOODBINE - RIVIERA TO DENISON | Markham | PLNC | Approved | 336898.51 | 630883.05 | 1001729.31 | 1042939.15 | 23-05-2021 | 003 | Contracted out to K-Line because of covid | 2021-03-23 18:17 | 2021-06-16 20:37 | 99
634344 | 634344 - STORM HARDENING 2020 - WOODBINE - RIVIERA TO DENISON | Markham | PLNC | Approved | 2587.75 | 630883.05 | 1001729.31 | 1042939.15 | 15-01-2021 | 002 | Additional cost to get proper pole height | 2021-01-15 16:57 | 2021-02-26 16:10 | 99
638970 | 2021 EMERGING OH - EAST 25TH ST - BELL POLES | Hamilton | PLNC | Approved | -11797.99 | 127384.36 | 115586.37 | 122667.69 | 22-09-2021 | 001 | Reduction RFC | 2021-08-24 14:22 | 2021-09-27 21:00 | 99
640629 | AUTO SWITCH INSTALLS - DUNDAS TS - PHASE 2, 3 | Hamilton | PLNC | Approved | 0 | 203380.77 | 219274.41 | 241656.74 | 19-10-2021 | 002 | Drawing Revision | 2021-10-19 11:01 | 2021-10-19 15:04 | 99
640629 | AUTO SWITCH INSTALLS - DUNDAS TS - PHASE 2, 3 | Hamilton | PLNC | Approved | 2762.5 | 203380.77 | 219274.41 | 241656.74 | 22-09-2021 | 001 | Material Addition | 2021-09-22 15:21 | 2021-09-22 19:34 | 99
640629 | AUTO SWITCH INSTALLS - DUNDAS TS - PHASE 2, 3 | Hamilton | PLNC | Approved | 13131.14 | 203380.77 | 219274.41 | 241656.74 | 26-11-2021 | 003 | K-Line mis-estimated | 2021-11-16 14:01 | 2021-11-29 13:55 | 99
639473 | MONTEVIDEO & TREVISO UG CABLE REPLACEMENT PH3 | Mississauga | PLNC | Approved | 8533.66 | 1908114.67 | 1916648.33 | 1863184.77 | 22-07-2022 | 101 | Trench Line changes | 2022-06-30 14:36 | 2022-07-28 18:26 | 95
632772 | 4KV CONVERSION - PHASE 8 | Brampton | PLNC | Approved | -26394.29 | 1969325.83 | 1942931.54 | 1974478.16 | 09-19-2022 | 101 | Reduction in scope of work affecting labour/equipment costs related to Pole #42 | 2022-04-07 13:29 | 2022-10-04 14:24 | 98
632799 | 4KV CONVERSION PH7-BRAMPTON - 2021 | Brampton | PLNC | Approved | 32500.95 | 1032245.96 | 1129992.47 | 1143521.75 | 27-10-2021 | 101 | TP estimate missing scope | 2021-09-22 16:13 | 2021-10-27 21:46 | 99
632799 | 4KV CONVERSION PH7-BRAMPTON - 2021 | Brampton | PLNC | Approved | 20000 | 1032245.96 | 1129992.47 | 1143521.75 | 27-07-2021 | 001 | Additional Lines hours | 2021-06-01 14:55 | 2021-09-22 20:14 | 99
632799 | 4KV CONVERSION PH7-BRAMPTON - 2021 | Brampton | PLNC | Approved | 45245.56 | 1032245.96 | 1129992.47 | 1143521.75 | 28-09-2021 | 102 | Hard Surface Restoration | 2021-08-31 10:18 | 2021-09-29 13:28 | 99
639087 | 639087 - 55M12 FEEDER EXTENSION TO NORTH SIDE OF HWY 7 | Markham | PLNC | Approved | 2505.99 | 122496.84 | 125002.83 | 140643.85 | 03-02-2021 | 001 | Additional OH transformer | 2021-02-03 14:56 | 2021-02-04 08:46 | 99
638426 | 2 MEDICORUM PLACE - VICANO CONSTRUCTION LTD/HAM/NS00046555/3PHPAD | Hamilton | ICIL | Approved | 8767.88 | 77972.43 | 86740.31 | 74671.79 | 19-08-2021 | 001 | Labour overages | 2021-07-28 10:47 | 2021-09-27 20:29 | 99
637453 | INGLEWOOD & UNDERCLIFFE CONVERSION | Hamilton | PLNC | Approved | 1200 | 675718.5 | 641525.11 | 559012.29 | 22-10-2021 | 001 | Scope Change | 2021-10-22 10:49 | 2021-10-22 15:04 | 99
637453 | INGLEWOOD & UNDERCLIFFE CONVERSION | Hamilton | PLNC | Approved | -35393.39 | 675718.5 | 641525.11 | 559012.29 | 30-12-2021 | 002 | Reduction RFC | 2021-12-29 10:32 | 2021-12-30 15:23 | 99
453630 | 453630 - RER - MX - RELOC - KENNEDY RD - STOUFFVILLE LINE (16) - RAILWAY CROSSINGS | Markham | TRNS | Approved | 0 | 153810.09 | 153810.09 | 182296.74 | 03-11-2021 | 001 | RFC completed for drawing revision 2 | 2021-11-03 16:19 | 2021-11-09 22:24 | 99
638576 | 638576 - POLE REPLACEMENT 2021 - BATCH 4 | Markham | PLNC | Approved | 26000 | 153661.41 | 179661.41 | 183907.39 | 05-06-2021 | 001 | Labour mixed with another pole batch (638575) in same vicinity, some poles removed, covid increase truck costs | 2021-05-27 16:54 | 2021-07-13 19:33 | 99
638574 | 638574 - POLE REPLACEMENT 2021 - BATCH 2 - 9 POLES | Markham | PLNC | Approved | 54000 | 145380.77 | 199380.77 | 192580.95 | 11-05-2021 | 001 | Esimate under estimated (required more labour for 80' pole and extra material | 2021-05-11 15:14 | 2021-09-27 20:38 | 99
636308 | 636308 - 9111 KEELE ST / ICI PAD TX INSTALLATION | Markham | ICIL | Approved | 2075 | 60932.13 | 63007.13 | 65254.19 | 22-01-2021 | 001 | Temporary sidewalks installed by Somerville | 2021-01-22 12:38 | 2021-01-23 08:45 | 99
636431 | 2020 SWITCHGEAR RENEWAL-SITE# 484(FORMERLY 98)-SANDALWOOD PKWY AND ROSEDALE | Brampton | PLNC | Approved | -3000 | 165125.08 | 162125.08 | 222622.31 | 09-08-2021 | 001 | Internal to External | 2021-07-27 12:09 | 2021-09-27 20:00 | 99
636432 | 2020 SWITCHGEAR RENEWAL - SITE# 480 (FORMERLY 149)- PETER ROBINSON EAST OF DIXIE | Brampton | PLNC | Approved | -3000 | 165125.08 | 162125.08 | 172738.43 | 09-08-2021 | 001 | Internal to External | 2021-07-27 12:56 | 2021-09-27 20:01 | 99
636433 | 2020 SWITCHGEAR RENEWAL-SITE# 478 (FORMERLY 181)-GURU NANAK ST W OF DIXIE | Brampton | PLNC | Approved | -3000 | 165125.08 | 162125.08 | 199778.73 | 09-08-2021 | 001 | Internal to external | 2021-07-27 12:57 | 2021-09-27 20:02 | 99
639370 | 18 CP - QUEENSWAY W OH REBUILD, (FROM DAMIEN WAY TO PINENEEDLE ROW) | Mississauga | PLNC | Pending | 70319.98 | 527284.47 | 527284.47 | 699403.74 | Pending with Lines | 101 | Additional costs for scope change, new pole holes to be excavated, additional pole, additional machinery | 2022-12-08 17:31 | 2022-12-08 22:34 | 92
450748 | 10300 HEART LAKE RD.N. | Brampton | ICIL | Approved | 887.51 | 121255.39 | 122142.9 | 115982.54 | 03-03-2021 | 001 | Additional cable length required | 2021-03-03 08:50 | 2021-03-12 19:22 | 98
450918 | HERITAGE RD, S OF EMBLETON | Brampton | PLNC | Approved | 105643.84 | 412957.07 | 549100.91 | 597433 | 10-05-2021 | 002 | Addtional hours and costs | 2021-03-29 09:16 | 2021-09-21 18:33 | 99
450918 | HERITAGE RD, S OF EMBLETON | Brampton | PLNC | Approved | 30500 | 412957.07 | 549100.91 | 597433 | 07-09-2020 | 001 | External extra | 2020-06-15 15:25 | 2020-09-22 19:39 | 99
635534 | JOINT USE PERMIT HW2020-002 - CROCKETT, E24, QUEENSDALE E - HAM | Hamilton | CVJU | Not Approved | 0 | 20856.28 | 20856.28 | 54238.85 | 07-07-2021 | 001 | Original Estimate had no hours | 2021-04-22 15:56 | 2021-09-27 17:44 | 99
640153 | AUTO SWITCH INSTALLS - CARLTON TS FEEDERS, 6 | St. Catharines | PLNC | Approved | 3315 | 384232.26 | 393397.26 | 423475.18 | 22-09-2021 | 002 | Materials Addition | 2021-09-22 15:02 | 2021-10-26 12:29 | 99
640153 | AUTO SWITCH INSTALLS - CARLTON TS FEEDERS, 6 | St. Catharines | PLNC | Approved | 5850 | 384232.26 | 393397.26 | 423475.18 | 07-10-2021 | 001 | Scope Added | 2021-10-04 16:00 | 2021-10-07 17:13 | 99
450528 | 209 QUEEN ST E | Brampton | ICIL | Approved | 0 | 478353.35 | 478353.35 | 541980.43 | 11-05-2020 | 001 | Drawing Rev | 2020-05-11 11:49 | 2020-09-22 19:41 | 92
641032 | SC752 AREA - NEW AB TRANSFORMERS | Hamilton | PLNC | Approved | 12440 | 75559.9 | 87999.9 | 79554.53 | 28-01-2022 | 001 | Open Trench | 2022-01-28 16:00 | 2022-02-02 15:25 | 99
640834 | 380 MCNEILLY RD/HAM/NS/NS00106348/3PHPAD | Hamilton | ICIL | Approved | 0 | 243989.2 | 243989.2 | 209993.18 | 14-04-2022 | 001 | Drawing Revision | 2022-04-14 11:24 | 2022-04-14 15:34 | 92
641016 | FINANCIAL/BRAM/ NS0011106/ 1000 KVA AND 2000 KVA PAD TX | Brampton | ICIL | Approved | 23103.13 | 258844.51 | 281947.64 | 23060.31 | 29-07-2022 | 001 | Scope Change, additional civil required | 2022-07-20 08:48 | 2022-08-08 14:10 | 82
641065 | CREDITVIEW ROAD & OLD CREDITVIEW ROAD POLE RELOCATIONS - MTO | Mississauga | CSCP | Approved | 14355 | 279503.21 | 303801.01 | 283862.79 | 10-12-2021 | 101 | Flagging required to be added to estimate. (approx. 87 hours at $150/hour rate + 10% markup) When K-Line estimated project road | 2021-10-07 14:00 | 2021-11-02 19:04 | 99
641065 | CREDITVIEW ROAD & OLD CREDITVIEW ROAD POLE RELOCATIONS - MTO | Mississauga | CSCP | Approved | 9942.8 | 279503.21 | 303801.01 | 283862.79 | 10-12-2021 | 102 | Site changes resulting in extra work | 2021-12-09 09:15 | 2022-01-06 19:32 | 99
640813 | 2021 EMERGING UG - RIVERVIEW BLVD REAR LOT CONVERSION | St. Catharines | PLNC | Approved | 25025.15 | 554671.03 | 585116.28 | 666690.01 | 15-03-2022 | 101 | Trenching | 2022-02-25 14:01 | 2022-06-01 18:54 | 99
640813 | 2021 EMERGING UG - RIVERVIEW BLVD REAR LOT CONVERSION | St. Catharines | PLNC | Approved | 5420.1 | 554671.03 | 585116.28 | 666690.01 | 01-06-2022 | 007 | Design Hours | 2022-06-01 14:55 | 2022-06-01 19:04 | 99
640812 | 2021 CABLE REPLACEMENT - CLAPPSION TIE POINT - 1300M'S | Hamilton | PLNC | Approved | 20607.7 | 448754.27 | 644487.57 | 664538.66 | 08-12-2021 | 002 | Change to Switch | 2021-12-08 09:00 | 2021-12-10 14:34 | 92
640812 | 2021 CABLE REPLACEMENT - CLAPPSION TIE POINT - 1300M'S | Hamilton | PLNC | Approved | 132232.75 | 448754.27 | 644487.57 | 664538.66 | 03-02-2022 | 001 | Rock, Unforeseen Scope Change | 2022-01-20 15:00 | 2022-02-03 21:32 | 92
640812 | 2021 CABLE REPLACEMENT - CLAPPSION TIE POINT - 1300M'S | Hamilton | PLNC | Approved | 42892.85 | 448754.27 | 644487.57 | 664538.66 | 22-07-2022 | 003 | Scope Change | 2022-07-06 11:49 | 2022-07-22 18:44 | 92
640890 | M-CITY POLE RELOCATION AT FITZROY STREET | Mississauga | CSCP | Approved | 30612.12 | 92596.42 | 123208.54 | 121541.45 | 30-12-2021 | 101 | Delays and Scope Changes | 2021-12-24 12:53 | 2021-12-30 15:07 | 99
640894 | 640894 - 2021 POLE RENEWAL - GUY WIRE REPLACEMENTS, SAFETY CONCERNS FROM CITY OF MARKHAM | Markham | PLNC | Approved | -7800 | 18715.22 | 10915.22 | 9630.02 | 09-07-2021 | 001 | Labour overestimated | 2021-07-07 10:40 | 2021-07-22 05:11 | 99
641138 | JOINT USE PERMIT HW2021-044 - BEACH - HAM | Hamilton | CVJU | Pending | 0 | 7843.61 | 7843.61 | 7561.33 | Pending With Desiign | 0 | Generator and exploir | 2022-07-06 10:56 | 2022-07-07 05:06 | 99
641159 | V63 & V64 VAULT LID REPLACEMENT | Hamilton | PLNC | Approved | 6761.92 | 23001.93 | 29763.85 | 36620.47 | 28-03-2022 | 001 | Custom Lid | 2022-03-28 11:14 | 2022-03-28 15:34 | 99
641121 | 2022 POLE REPLACEMENTS - EAST 43RD ST - 22 POLES | Hamilton | PLNC | Approved | 19908.38 | 289290.61 | 309198.99 | 319611.9 | 28-10-2022 | 101 | Added scope | 2022-10-28 12:39 | 2022-11-02 12:53 | 92
642487 | 642487 - 2022 POLE REPLACEMENT - BAYVIEW AVE - 11 POLES | Markham | PLNC | Approved | -21701.16 | 337230.28 | 315529.12 | 327061.24 | 07-12-2022 | 101 | Crane not required, bucket truck able to be used instead | 2022-12-07 14:32 | 2022-12-08 06:34 | 99
642485 | 642485 - 2022 POLE REPLACEMENT - ROYAL RD, INDUSTRIAL PKWY - 4 POLES | Markham | PLNC | Approved | 4982.85 | 120142.79 | 125125.64 | 125015.3 | 20-12-2022 | 101 | Changed out insulators | 2022-12-19 11:31 | 2022-12-20 19:04 | 98
643066 | 200 KENNEDY RD S/ BRAM/ NS00172256/ 2000 KVA PAD | Brampton | ICIL | Pending | 11029.32 | 361038.09 | 361038.09 | 388671.6 | Pending with Design | 101 | Additional scope of work added | 2022-12-14 08:51 | 2022-12-14 14:04 | 84
642119 | 2022 DA- SW 44-436 AIRPORT/NEVETS | Brampton | PLNC | Approved | 8504.32 | 123646.88 | 132151.2 | 112357.01 | 14-06-2022 | 001 | Project estimated internally but now contracted out to A&W for completion. Design to quantify change in costs based on A&W est. | 2022-05-19 12:01 | 2022-06-22 16:31 | 98
641360 | 641360 - 2022 CABLE REPLACEMENT - A05 - MURRAY DR - GOLF LINKS, AURORA - PHASE 1 | Markham | PLNC | Approved | 0 | 998999.83 | 1014880.68 | 1116469.26 | 05-04-2022 | 001 | Design drawings updated | 2022-04-05 09:29 | 2022-07-06 16:14 | 92
641360 | 641360 - 2022 CABLE REPLACEMENT - A05 - MURRAY DR - GOLF LINKS, AURORA - PHASE 1 | Markham | PLNC | Approved | 15880.85 | 998999.83 | 1014880.68 | 1116469.26 | 13-05-2022 | 002 | Lines requested 90 OT hours | 2022-05-13 15:09 | 2022-07-06 16:14 | 92
641415 | AUTO SWITCH - SCOTT & HAIG - 1 | St. Catharines | PLNC | Approved | 51010.3 | 214581.87 | 271100.63 | 312923.18 | 26-05-2022 | 001 | Plugged ducts | 2022-04-11 14:00 | 2022-05-26 19:29 | 98
641415 | AUTO SWITCH - SCOTT & HAIG - 1 | St. Catharines | PLNC | Approved | 5508.46 | 214581.87 | 271100.63 | 312923.18 | 06-06-2022 | 003 | Change to design | 2022-06-06 09:00 | 2022-06-08 14:04 | 98
642033 | WINONA RD POLE RELOCATIONS (SOUTH OF BASELINE ROAD) HAMILTON | Hamilton | PLNC | Approved | 5278.84 | 146831.72 | 152110.56 | 129194.98 | 22-12-2021 | 001 | Control Room | 2021-12-06 12:00 | 2021-12-22 16:27 | 99
643216 | 643216 - 2022 STORM HARDENING - WESTON - HWY 7 TO LANGSTAFF - VAUGHAN | Markham | PLNC | Approved | 50743.02 | 529273.98 | 580017 | 625943.77 | 07-12-2022 | 101 | Extra work required Sep 6, 12, 15. Oct 3-6, 13, Nov 1 | 2022-11-09 12:45 | 2022-12-08 06:35 | 98
428171 | 80 THOMAS ST TOWNHOMES | Mississauga | SUBD | Approved | 140000 | 502396.61 | 642396.61 | 497191.66 | 28-09-2022 | 101 | ver the course of the project, 25 additional days required to accommodate developers building program and site staging requirement | 2022-06-07 10:33 | 2022-10-26 03:53 | 99
642998 | 642998 - 2022 POLE REPLACEMENT - BATCH 9 - 14 POLES | Markham | PLNC | Approved | -81231.5 | 337490.22 | 256258.72 | 210318.43 | 07-12-2022 | 101 | 5 poles removed from scope | 2022-12-07 14:44 | 2022-12-08 06:35 | 99
641379 | 55 1/2 ROCKCLIFFE ROAD - UG SERVICE TO BE RELOCATED | Hamilton | PLNC | Approved | 180.6 | 28147.05 | 28327.65 | 30407.32 | 25-05-2021 | 001 | Civil alignment change | 2021-05-25 16:57 | 2021-09-27 21:13 | 99
641474 | 641474 - MURRY DR, EAST OF NISBET DR | Markham | CSCP | Approved | 17861.68 | 39236.68 | 57098.36 | 60612.06 | 13-12-2021 | RFC001C | Estimate based on preliminary drawings, IFC had 2 additional poles. RFC to add this cost | 2021-12-13 17:55 | 2021-12-14 06:07 | 99
642684 | 642684 - 2022 POLE RENEWAL - P49859 & P28092 | Markham | PLNC | Approved | -20290.52 | 48939.97 | 28649.45 | 14790.9 | 20-01-2023 | 101 | Removed one pole from scope due to easement | 2022-12-07 11:05 | 2023-01-21 06:38 | 98
642505 | OH AUTO SWITCHES (DA) 2022 - PART 3 - 4 | Hamilton | PLNC | Approved | 12006.12 | 347362.04 | 365294.42 | 360213.16 | 04-04-2022 | 001 | Missed UG Hours | 2022-04-04 15:17 | 2022-04-04 19:34 | 92
642505 | OH AUTO SWITCHES (DA) 2022 - PART 3 - 4 | Hamilton | PLNC | Approved | 5926.26 | 347362.04 | 365294.42 | 360213.16 | 12-05-2022 | 002 | Scope to Fairway | 2022-05-12 12:54 | 2022-06-07 18:31 | 92
642568 | 2022 EMERGING UG - RIVERVIEW REAR LOT CONVERSION | St. Catharines | PLNC | Approved | 25692.11 | 900505.47 | 926197.58 | 906053.34 | 10-05-2022 | 101 | Pad location change, daylighting | 2022-04-25 08:00 | 2022-05-11 13:53 | 99
641327 | 2021 MUT CITY OF MISSISSAUGA PROJECT - ALECTRA RELOCATIONS | Mississauga | CSCP | Approved | 4249.84 | 334191.37 | 404241.76 | 388109.92 | 14-02-2022 | 102 | Overtime work on Sunday January 30, 2022 due to customer outage impacts. | 2022-01-28 15:12 | 2022-03-01 21:36 | 99
641327 | 2021 MUT CITY OF MISSISSAUGA PROJECT - ALECTRA RELOCATIONS | Mississauga | CSCP | Approved | 12076.53 | 334191.37 | 404241.76 | 388109.92 | 23-02-2022 | 103 | Extra ducts, fittings, backfilling at open cut sections, removal of span guys, and more. | 2022-02-22 11:42 | 2022-03-01 21:36 | 99
641327 | 2021 MUT CITY OF MISSISSAUGA PROJECT - ALECTRA RELOCATIONS | Mississauga | CSCP | Approved | 53724.02 | 334191.37 | 404241.76 | 388109.92 | 21-03-2022 | 101 | Added scope, rock breaking and lost productivity as per the cost breakdown. | 2022-01-28 12:50 | 2022-04-01 12:53 | 99
642404 | 2022 SWGR RENEWAL, SG1041 & SG1194, EXPLORER DR | Mississauga | PLNC | Approved | 0 | 340820.29 | 340820.29 | 374548.48 | 17-02-2022 | 001 | CHANGE TO SUIT COMMENTS FROM AM & OPS REGARDING PLACING THE EXISTING 1PH RADIAL TX ON LOOP FEED | 2022-02-17 18:10 | 2022-03-07 23:34 | 92
641781 | 641781 - HUNTINGTON RD, MAJOR MACKENZIE DR TO EAST CORNERS BLVD (DEV) | Markham | CSCP | Approved | 0 | 531282.54 | 541529.12 | 617101.5 | 03-05-2022 | 001 | Pole relocation in design due to original being on private prroperty | 2022-05-03 10:44 | 2022-05-11 05:05 | 98
641781 | 641781 - HUNTINGTON RD, MAJOR MACKENZIE DR TO EAST CORNERS BLVD (DEV) | Markham | CSCP | Approved | 10246.58 | 531282.54 | 541529.12 | 617101.5 | 06-10-2022 | 101 | 2 days of Transpower crew | 2022-09-30 14:28 | 2022-10-07 05:04 | 98
642354 | 2022 DA SW20-1184 - INTERMODAL DR E/O DEVON RD | Brampton | PLNC | Approved | -9209.81 | 142058.75 | 132848.94 | 176132.26 | 15-06-2022 | 001 | Project estimated internally but now contracted out to A&W for completion. Design to quantify change in costs based on A&W est. | 2022-05-19 12:01 | 2022-06-15 19:39 | 98
641834 | 20 EAST AVENUE SOUTH / HAM / NS / 3PH PAD | Hamilton | ICIL | Approved | 2498.55 | 51508.46 | 54007.01 | 51465.37 | 14-07-2022 | 001 | Remove abandoned structure | 2022-07-14 15:19 | 2022-08-08 13:27 | 92
641927 | 2022 SWITCHGEAR RENEWAL - SITE# 555 - McLaughlin Rd & Steeles Ave. W | Brampton | PLNC | Approved | 11553.23 | 213686.13 | 225239.36 | 234709.07 | 28-11-2022 | 001 | Civil work added | 2022-11-28 13:22 | 2022-12-08 22:38 | 98
642832 | HYDRO VAULT LID REPLACEMENT-V77-CHAMPLAIN AVE | Hamilton | CSCP | Approved | 7605.19 | 14784.9 | 22390.09 | 22496.17 | 28-03-2022 | 001 | Custom Lid | 2022-03-28 11:19 | 2022-03-28 15:34 | 99
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 88479.84 | 3122362 | 3122362 | 2863238.16 | Pending With Design | 109 | Extra OH work | 2023-01-03 17:00 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 35058.25 | 3122362 | 3122362 | 2863238.16 | Pending With Design | 101 | Equipment Damage | 2023-01-03 14:42 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 4897.37 | 3122362 | 3122362 | 2863238.16 | Pending with Design | 104 | Kline - scope change - new d/h guys | 2023-01-03 14:44 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 10892.73 | 3122362 | 3122362 | 2863238.16 | Pedning with Design | 107 | Extra site weekend monitor | 2023-01-03 14:49 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 28336 | 3122362 | 3122362 | 2863238.16 | Pending With Design | 105 | Extra Traffic control | 2023-01-03 14:46 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 28336 | 3122362 | 3122362 | 2863238.16 | Pending With Design | 111 | Additional Traffic Control fic ontrol | 2023-01-03 16:52 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 61670.02 | 3122362 | 3122362 | 2863238.16 | Pending With Design | 112 | EB Delays due to site issues | 2023-01-03 16:54 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 13020.79 | 3122362 | 3122362 | 2863238.16 | Pending With Desiign | 103 | Kline Scope Change | 2023-01-03 14:39 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 105452 | 3122362 | 3122362 | 2863238.16 | Pending With Design | 110 | Shift Shalf approved by Aecom | 2023-01-03 16:51 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 4311.38 | 3122362 | 3122362 | 2863238.16 | Pending With Design | 102 | Kline - R2 change | 2023-01-03 16:49 | 2023-01-03 22:04 | 92
452764 | 452764 - RER - MX - RELOC - KING VAUGHAN RD - BARRIE LINE (1911,1912) - RAILWAY CROSSINGS | Markham | TRNS | Pending | 88426.55 | 3122362 | 3122362 | 2863238.16 | Pending With Design | 106 | Extras OSMOS monitoring | 2023-01-03 14:48 | 2023-01-03 22:04 | 92
642451 | 2022 POLE RENEWAL GRID H4 - 17 POLES (HALE RD) | Brampton | PLNC | Not Approved | 0 | 522588.4 | 522588.4 | 659419.07 | Pending with Design | 0 | Project contracted out to K-Line | 2022-08-08 15:57 | 2022-12-04 18:10 | 98
642451 | 2022 POLE RENEWAL GRID H4 - 17 POLES (HALE RD) | Brampton | PLNC | Pending | 37614.2 | 522588.4 | 522588.4 | 659419.07 | Pending with Design | 101 | Working hours changed to night hours in an effort to minimize in impact on the local businesses during Scheduled Outage | 2022-12-02 13:07 | 2022-12-12 21:06 | 98
642451 | 2022 POLE RENEWAL GRID H4 - 17 POLES (HALE RD) | Brampton | PLNC | Pending | 15760 | 522588.4 | 522588.4 | 659419.07 | Pending with Design | 102 | Electrician cost for work during the outage & extra backfill costs | 2022-12-16 15:10 | 2022-12-19 06:04 | 98
642518 | UG AUTO SWITCHES (DA) 2022 - CLAPPISON - 1 | Hamilton | PLNC | Approved | 35016.76 | 404232.82 | 447750.27 | 501441.55 | 11-07-2022 | 001 | Redesign | 2022-07-11 13:05 | 2022-07-11 17:34 | 92
642518 | UG AUTO SWITCHES (DA) 2022 - CLAPPISON - 1 | Hamilton | PLNC | Approved | 8500.69 | 404232.82 | 447750.27 | 501441.55 | 13-12-2022 | 101 | Additional Duct | 2022-12-16 14:14 | 2022-12-16 19:34 | 92
642518 | UG AUTO SWITCHES (DA) 2022 - CLAPPISON - 1 | Hamilton | PLNC | Approved | 0 | 404232.82 | 447750.27 | 501441.55 | 11-07-2022 | 002 | Revised Drawings | 2022-07-11 13:05 | 2022-07-11 17:34 | 92
642348 | 2022-44KV LIS SWITCH INSTALLATION(44-434) | Brampton | PLNC | Approved | -25171.82 | 180786.23 | 155614.41 | 114573.89 | 14-06-2022 | 001 | Project estimated internally but now contracted out to A&W for completion. Design to quantify change in costs based on A&W est. | 2022-05-19 11:09 | 2022-06-22 17:51 | 98
641805 | CUST RELOC - NOVAR ROAD & DUNDAS STREET OH TO UG | Mississauga | CSCP | Approved | 9581.71 | 708814.68 | 718396.39 | 599538.32 | 28-11-2022 | 101 | Increased labour scope | 2022-11-25 12:31 | 2022-11-28 18:04 | 84
643385 | NV 21 - NEW ROOF + OTHER NV LIDS & ASSOCIATED WORK - 2 | St. Catharines | PLNC | Approved | 6109.51 | 329543.62 | 207835.91 | 239115.56 | 25-04-2022 | 102 | Grind lid to flush | 2022-04-25 09:25 | 2022-04-26 13:38 | 99
643385 | NV 21 - NEW ROOF + OTHER NV LIDS & ASSOCIATED WORK - 2 | St. Catharines | PLNC | Approved | 10537.31 | 329543.62 | 207835.91 | 239115.56 | 04-04-2022 | 001 | Field Changes | 2022-03-29 13:17 | 2022-04-04 18:16 | 99
643385 | NV 21 - NEW ROOF + OTHER NV LIDS & ASSOCIATED WORK - 2 | St. Catharines | PLNC | Approved | -138354.53 | 329543.62 | 207835.91 | 239115.56 | 20-12-2022 | 101 | Reduction RFC | 2022-08-31 09:00 | 2022-12-21 14:10 | 99
642444 | EMERGING 2021 - INSULATOR CHANGES. CHURCH ST. | St. Catharines | PLNC | Approved | -26179.3 | 68736.9 | 42557.6 | 50612.95 | 30-12-2021 | 001 | Reduction RFC | 2021-12-29 10:00 | 2022-01-04 14:36 | 99
643473 | HAMILTON SOUTH MOUNTAIN FEEDERS PART 3 | Hamilton | PLNC | Approved | 8866.87 | 226227.74 | 252241.61 | 230819.96 | 12-08-2022 | 101 | Multiple Small Field Changes | 2022-08-08 12:37 | 2022-08-15 18:16 | 92
643473 | HAMILTON SOUTH MOUNTAIN FEEDERS PART 3 | Hamilton | PLNC | Approved | 0 | 226227.74 | 252241.61 | 230819.96 | 27-04-2022 | 001 | Drawing Revision | 2022-04-27 10:39 | 2022-04-27 15:04 | 92
643473 | HAMILTON SOUTH MOUNTAIN FEEDERS PART 3 | Hamilton | PLNC | Approved | 17147 | 226227.74 | 252241.61 | 230819.96 | 18-10-2022 | 102 | Sidewalk Excavation | 2022-09-26 14:10 | 2022-10-18 16:28 | 92
642339 | 642339 - 2022 CABLE REPLACEMENT, M31 BIRCHMOUNT AND DENISON ST | Markham | PLNC | Approved | 13956.84 | 790053.68 | 1052323.82 | 1088467.92 | 31-05-2022 | 001 | Increased cost of cable | 2022-07-26 12:30 | 2022-07-26 16:34 | 99
642339 | 642339 - 2022 CABLE REPLACEMENT, M31 BIRCHMOUNT AND DENISON ST | Markham | PLNC | Approved | 248313.3 | 790053.68 | 1052323.82 | 1088467.92 | 26-07-2022 | 002 | Open trench / over dig required rather than directional drill. | 2022-07-26 11:54 | 2022-07-26 16:31 | 99
646077 | P-166 COLLEGE AVE W/GUE/NS | Guelph | ICIL | Approved | 7634.39 | 83859.01 | 91493.4 | 10583.31 | 23-11-2022 | 001 | Scope Change due to JU | 2022-11-24 08:33 | 2022-11-24 14:04 | 82
642454 | 2022 MINI-POLE REBUILD - GLIDDEN RD - 28 Poles | Brampton | PLNC | Pending | 41722.61 | 685007.21 | 685007.21 | 804907.45 | Pending with Design | 101 | Cost: $41,722.61 to be added on the project cost. (PO 422585 OS) The overtime cost was missed and not included in the submitted es | 2022-11-14 02:48 | 2022-12-12 21:06 | 98
642454 | 2022 MINI-POLE REBUILD - GLIDDEN RD - 28 Poles | Brampton | PLNC | Not Approved | 0 | 685007.21 | 685007.21 | 804907.45 | Pending with Design | 0 | Project contracted out to K-Line | 2022-07-13 15:58 | 2022-11-29 07:48 | 98
641575 | 641575 - 2022 TX VAULT RENEWAL, MAIN ST N UNIONVILLE (4 LOCATIONS) | Markham | PLNC | Approved | 36102.25 | 457020.8 | 493123.05 | 517243.43 | 02-09-2022 | 001 | Hapamp to subcontract and manage Toromont for temp power generation | 2022-09-02 11:33 | 2022-10-11 16:29 | 95
642326 | 2022 DA SW20-1485 - HWY 407 HONI ROW E/O HURONTARIO ST | Brampton | PLNC | Approved | -21550.73 | 117893.04 | 96342.31 | 108852.15 | 14-06-2022 | 001 | Project estimated internally but now contracted out to A&W for completion. Design to quantify change in costs based on A&W est. | 2022-05-19 11:11 | 2022-06-22 16:56 | 98
642342 | 2022 DA- SW 20-1239 | Brampton | PLNC | Approved | 26578.99 | 104294.85 | 130873.84 | 151297.76 | 14-06-2022 | 001 | Project estimated internally but now contracted out to A&W for completion. Design to quantify change in costs based on A&W est. | 2022-05-19 12:00 | 2022-06-22 17:44 | 98
642061 | OH AUTO SWITCHES (DA) 2022 - PART 2 - 4 | Hamilton | PLNC | Approved | 0 | 406574.77 | 406574.77 | 391909.04 | 25-08-2022 | 001 | Drawing change only | 2022-08-25 14:50 | 2022-08-25 19:04 | 92
642060 | OH AUTO SWITCHES (DA) 2022 - PART 1 - 6 | Hamilton | PLNC | Not Approved | 0 | 439669.2 | 439669.2 | 500067.35 | Pending With Construction | 001 | Hours Overages | 2022-04-05 11:00 | 2022-07-05 20:37 | 99
452832 | 452832 - RER - MX - RELOC - GIVEN RD & BRIDGE ST - BARRIE LINE (1924) - RAILWAY CROSSINGS | Barrie | TRNS | Approved | 8900.54 | 201660.72 | 210561.26 | 220527.7 | 30-03-2022 | 001 | Additional cost due to extensive time applying for Metrolinx permitting | 2022-03-29 14:18 | 2022-03-31 03:35 | 99
645101 | 41 REID AVE / HAM / NS00280013 / RELOCATE 3PH PAD | Hamilton | ICIL | Approved | -5351.36 | 41968.62 | 36617.26 | 18057.97 | 28-09-2022 | 001 | Scope Change - Rev Dwg | 2022-09-28 11:00 | 2022-10-11 16:29 | 92
644788 | 2022 EMERGING PROJECT - STORM DRAIN REPLACEMENT 136M52FEEDER CABLE RELOCATION | Brampton | PLNC | Pending | 44066.75 | 316330.97 | 316330.97 | 328360.83 | Pending with Design | 101 | RFC required for 24hr paid duty as requested by Peel Region for ROP approval. | 2022-11-04 16:40 | 2022-11-17 22:23 | 98
644788 | 2022 EMERGING PROJECT - STORM DRAIN REPLACEMENT 136M52FEEDER CABLE RELOCATION | Brampton | PLNC | Pending | 40005 | 316330.97 | 316330.97 | 328360.83 | Pending with Lines | 102 | RFC required for sewer pipe bypass and pipe connections that were not part of original scope/ estimate. | 2022-11-17 17:21 | 2022-11-17 22:34 | 98
644788 | 2022 EMERGING PROJECT - STORM DRAIN REPLACEMENT 136M52FEEDER CABLE RELOCATION | Brampton | PLNC | Pending | 3905.67 | 316330.97 | 316330.97 | 328360.83 | Pending with Design | 103 | RFC required due to sewer being 4ft deep, was supposed to be 10ft deep. Had to change to smaller excavator | 2022-11-25 02:32 | 2023-01-17 15:15 | 98
644523 | 644523 - 6885 LANGSTAFF RD/VAU/NS/CUST OWNED | Markham | ICIL | Approved | 0 | 390995.16 | 390995.16 | 22379.68 | 27-09-2022 | 001 | Drawing updated to match correct grid location | 2022-09-27 14:35 | 2022-09-27 19:04 | 82
646085 | YORKSHIRE ST N (LONDON RD W TO NORTHUMBERLAND ST) & LIVERPOOL ST | Guelph | PLNC | Pending | 0 | 380907.1 | 380907.1 | 340734.73 | Pending With Design | 001 | Scope Change | 2022-12-12 11:04 | 2023-01-10 16:34 | 84
644551 | LT71089 - 2022 DA - ERIN MILLS PKWY & BRITTANNIA RD W - P20409 | Mississauga | PLNC | Approved | 11598.47 | 145934.98 | 157533.45 | 139178.9 | 31-05-2022 | 001 | Install 140m of new 3/0 triplex secondary bus, Install two down guys and two 12" anchors | 2022-05-31 10:39 | 2022-06-01 15:04 | 98
452834 | 452834 - RER - MX - RELOC - DISSETTE ST - BARRIE LINE (66) - RAILWAY CROSSINGS | Barrie | TRNS | Approved | 7871.4 | 159927.31 | 167798.71 | 189299.84 | 30-03-2022 | 001 | Additional cost due to extensive time applying for Metrolinx permitting | 2022-03-29 14:27 | 2022-03-31 03:35 | 99
645116 | 42 - 54 WATERSHOR DR, SERVICE REMOVAL/RELOCATION FOR SUBDIVISION | Hamilton | CSCP | Pending | 0 | 117114.43 | 117114.43 | 25780.93 | Pending with Fairway | 101 | Additional duct at road crossing | 2022-11-14 09:03 | 2022-11-14 17:34 | 84
643837 | 643837 - ROAD AUTHORITY RELOCATION-HWY 400 AND LITTLE AVENUE | Barrie | CSCP | Approved | 27197.03 | 819314.71 | 846511.74 | 656791.69 | 04-01-2023 | 001 | Added padmount transformer to scope | 2023-01-04 17:39 | 2023-01-06 06:36 | 84
646166 | P - PARK AVE - REAR LOT CONVERSION PROJECT | Guelph | PLNC | Pending | 0 | 940835.39 | 940835.39 | 886992.98 | Pending With Design | 001 | Scope reduction - JU Trench | 2022-09-27 12:10 | 2022-11-09 15:08 | 92
646882 | 2022 - S&C FACEPLATE UPGRADES - DA 44-427 | Brampton | PLNC | Approved | 23434.36 | 71564.06 | 94998.42 | 72785.08 | 22/12/2022 | 101 | Shortage on PO to bill WE Dec 10 & Dec 17 | 2022-12-22 15:58 | 2022-12-22 21:04 | 98
646372 | 178 NEBO RD - GIANEL HOLDINGS INC../HAM/NS00240837/3PHPAD | Hamilton | ICIL | Approved | 317.31 | 67974.13 | 68291.44 | 5473.23 | 21-12-2022 | 001 | Drawing Change - | 2022-12-21 11:38 | 2022-12-21 17:04 | 82
645128 | 2022 EMERGING OVERHEAD - 16 & 22 CANNON ST EAST - AERIAL TRESPASSING | Hamilton | PLNC | Approved | 212088.9 | 318178.92 | 562808.82 | 546356.85 | 21-12-2022 | 102 | Work completed after hours | 2022-12-02 10:00 | 2022-12-21 19:33 | 84
645128 | 2022 EMERGING OVERHEAD - 16 & 22 CANNON ST EAST - AERIAL TRESPASSING | Hamilton | PLNC | Approved | 32541 | 318178.92 | 562808.82 | 546356.85 | 19-12-2022 | 101 | After hours | 2022-11-07 08:46 | 2022-12-19 20:17 | 84
644236 | U/G DISTRIBUTION AUTOMATION - GROSSBEAK MS | Mississauga | PLNC | Pending | 119872.74 | 459814.15 | 459814.15 | 668043.42 | Pending with Design | 101 | RFC for additional work as required by Alectra | 2022-08-24 23:09 | 2022-10-19 02:13 | 95
644478 | EMERGING - 2022 BEACH CABLE RELOCATION | Hamilton | PLNC | Approved | 300000 | 97715.01 | 397715.01 | 427340.91 | 26-10-2022 | 001 | Generator | 2022-10-26 11:00 | 2022-10-26 17:42 | 92
648177 | SC760 - NEW SWITCH GEAR | Hamilton | PLNC | Approved | 0 | 161855.06 | 161855.06 | 1904.13 | 12-01-2023 | 001 | Drawing Revision | 2023-01-12 14:51 | 2023-01-12 20:04 | 82
644997 | 2022 EM UG, 1 FAIRVIEW RD. EAST - DUCTBANK RELOCATION | Mississauga | PLNC | Pending | 59450.41 | 36780.23 | 36780.23 | 172904.05 | Pending with Design | 101 | Additional civil work | 2022-11-15 15:16 | 2022-11-17 20:34 | 95
647155 | CENTRAL VOLTAGE CONVERSION FUSING | Hamilton | PLNC | Approved | 13255.21 | 36028.68 | 57231.61 | 60434.85 | 19-12-2022 | 102 | OT Hours | 2022-11-21 12:08 | 2022-12-19 20:21 | 92
647155 | CENTRAL VOLTAGE CONVERSION FUSING | Hamilton | PLNC | Approved | 7947.72 | 36028.68 | 57231.61 | 60434.85 | 19-12-2022 | 101 | OT hours | 2022-11-21 09:59 | 2022-12-19 20:21 | 92

## Template Proposed
Project Close Out | [7 empty] | Input
[5 empty] | Date: |  | 2023-08-01 | Manual entry
Project Details
Work Order Number
Project Name | [7 empty] | Manual entry
Design Tech | [7 empty] | Manual entry
Lines Supervisor | [7 empty] | Manual entry
Cost Breakdown
Project Estimate | 40735.33 | [6 empty] | Formula - Once entries have been completed verify correct
Actual Cost | 0 | [6 empty] | Formula - Once entries have been completed verify correct
Difference | -40735.33 | [6 empty] | Formula
% Difference | -100% | [6 empty] | Formula
[8 empty] | Input | Input
| Planned Cost |  | Actual Cost |  | Difference |  | % Difference | Planned Cost | Actual Cost
Total Material $'s to Analyze | 6822.77 |  | 0 |  | -6822.77 |  | -1
Material | 6822.77 |  |  |  | -6822.77 |  | -100% | JDE Estimate - Cost Summary | Hubble WO Analysis
Material - Burden |  |  |  |  | 0 |  |  | JDE Estimate - Cost Summary | Hubble WO Analysis
Mat DIRM | 6778.33 |  |  |  | -6778.33 |  | -100% | JDE Estimate - Cost Summary | Hubble WO Analysis
Total LBr $'s to Analyze | 23423 |  |  |  | -23423
Personnel |  |  |  |  | 0 |  |  | JDE Estimate - Cost Summary including NU | Hubble WO Analysis
Personnel - Burden | 23423 |  |  |  | -23423 |  | -100% | JDE Estimate - Cost Summary including NU | Hubble WO Analysis
Travel time | 1652.71 |  |  |  | -1652.71 |  | -100% | JDE Estimate - Cost Summary | Hubble WO Analysis
Total Tools $'s to Analyze | 6483.52 |  |  |  | -6483.52
Tools/Facilities | 6483.52 |  |  |  | -6483.52 |  | -100% | JDE Estimate - Cost Summary | Hubble WO Analysis
Total Ext Contract $'s to Analyze | 575 |  |  |  | -575 |  | -100%
External Contractor - SC | 232 |  |  |  | -232 |  | -100% | JDE Estimate - Cost Summary | Hubble WO Analysis
External Contr Burden - SC | 343 |  |  |  | -343 |  | -100% | JDE Estimate - Cost Summary | Hubble WO Analysis
Expenses - OTHER |  |  |  |  | 0 |  |  | JDE Estimate - Cost Summary | Hubble WO Analysis
ICI Serv Credit - OTHER | -5000 |  |  |  | 5000 |  | -100% | JDE Estimate - Cost Summary | Hubble WO Analysis
Additional unmapped charges |  |  |  |  | 0 |  |  |  | Hubble WO Analysis
RFC - Total Material | [7 empty] | P6
RFC - Total Personnel | [7 empty] | P6
RFC - Total Tools | [7 empty] | P6
RFC - Total External Contr | [7 empty] | P6
| Planned Hours | Actual Hours | Difference | % Difference | Input
Total Labour Hrs | 0 | 0 | 0 | 0% | Formula
Reg Hrs | 0 | 0 | 0 | 0% | Formula - Once entries have been completed verify correct
OT Hrs | 0 | 0 | 0 | 0% | Formula - Once entries have been completed verify correct
[5 empty] | Input | Input
[5 empty] | Plan | Actual
Task 1 Hrs |  |  | 0 | 0% | JDE Estimate - Cost Summary - NU | JDE WO - WO Cost
Task 1 OT Hrs |  |  | 0 | 0% | JDE Estimate - Cost Summary - NU | JDE WO - WO Cost
Des Hrs (incl 115) |  |  | 0 | 0% | JDE Estimate - Cost Summary | JDE WO - WO Cost
Des OT (incl 115) |  |  | 0 | 0% | JDE Estimate - Cost Summary | JDE WO - WO Cost
Insp Hrs |  |  | 0 | 0% | JDE Estimate - Cost Summary | JDE WO - WO Cost
Insp OT Hrs |  |  | 0 | 0% | JDE Estimate - Cost Summary | JDE WO - WO Cost
Lines Hrs (incl 100) |  |  | 0 | 0% | JDE Estimate - Cost Summary | JDE WO - WO Cost | Note: Total should equal total of all Lines tasks minus Metering
Lines OT Hrs (incl 100) |  |  | 0 | 0% | JDE Estimate - Cost Summary | JDE WO - WO Cost | Note: Total should equal total of all Lines tasks minus Metering
P&C Hrs |  |  | 0 | 0% | JDE Estimate - Cost Summary | JDE WO - WO Cost
P&C OT Hrs |  |  | 0 | 0% | JDE Estimate - Cost Summary | JDE WO - WO Cost
Metering Hrs (Task 800) |  |  | 0 | 0% | JDE Estimate - Cost Summary | Hubble - WO Task Detail | Note: If there are actual Metering Hrs, subtract the same number from Task 130
Metering Hrs OT (Task 800) |  |  | 0 | 0% | JDE Estimate - Cost Summary | Hubble - WO Task Detail | Note: If there are actual Metering Hrs, subtract the same number from Task 130
Lessons Learned/Mitigating Actions
People | Process |  |  |  | System